## 1.Awarded contracts_On&off-farm
EMERGENCY FOOD SECURITY PROJECT (EFSP)
Component 2: Provision of Water and Resilience Services
Additional financing (AF-2)
List of ongoing contract under Restoration of on-farm and off-farm Irrigation activity
Sno | Package / Contract name | Name of the sub-project | Location |  |  |  | Contract signed date | Contract end date | Contract number | Contract Cost (USD) | Cosntrution company | Physical progress % |  | Actual completion date | Remarks
|  |  | Region | Province | District | Village | [5 empty] | Sub-projects | Packages
Activity 2.2.a: Restoration of on-farm and off-farm Irrigation schemes
1 | Package #1-AF2 IS: Rehabilitation of Joy Bazar irrigation scheme located in Obe district of Herat province. | Joy Bazar Canal irrigation Scheme | West/Herat | Herat | Obeh | Center | 2025-09-16 | 2026-09-15 | 050/2025 | 222241.38 | Afghan Aakam Construction and Road Company C. JV with D-Amini Mashwani Construction Road Juroni and Construction Materials Production Company (AACRC&JV DAMCC) | 100% | 100% | May, 2026 | Completed in May 2026
2 | Package # 2-AF2 IS: Rehabilitation of irrigation schemes of 1.Ali Mansoor Canal in Karukh district, 2.Joy Sork and 3.Sar Kari canals in Farsi districts of Herat province. | Ali Mansoor Canal Irrigation Scheme |  | Herat | Karukh | Dahan-e-Ghar Villages | 2026-07-22 | 2027-07-21 | 046/2026 | 119404.6108 | Arman Millad Construction Company (AMCC) | 45% | 33% |  | on track and will be completed by July 2027
3 |  | Joy Sork Irrigation Schemes |  | Herat | Farsi | Peyazak and Joy Markaz villages |  |  |  | 127771.6492 |  | 5%
4 |  | Sar Kari Irrigation Schemes |  | Herat | Farsi | Peyazak and Joy Markaz villages | [5 empty] | 49%
5 | Package #6-AF2 IS: Rehabilitation of Kushtal Canal, Checknawar canal, and Patikhirrki canal irrigation schemes, located in Lalpora ,Spinghar and Khogyani districts of Nangarhar province. | Kushtal canal irrigation Scheme | East/Jalalabad | Nangarhar | Lalpora | Checknawar | 2025-10-25 | 2026-10-24 | 054/2025 | 57919.7698 | Shirali Khan Barakatzai Construction Company (SBCC) | 95% | 91.67% |  | on track and will be completed by Oct. 2026
6 |  | Checknawar canal irrigation scheme |  | Nangarhar | Spinghar | Kushtal |  |  |  | 221002.9727 |  | 90%
7 |  | Patikhirki canal irrigation Scheme |  | Nangarhar | Khogyani | Patikhirrki |  |  |  | 96234.3975 |  | 90%
8 | Package #8-AF2 IS: Rehabilitation of Khas Kunar Lower canal and Bahrabad canal irrigation schemes, located in Khas Kunar district of Kunar and Behsood district of Nangarhar provinces. | Khas Kunar Lower Canal irrigation Scheme |  | Kunar | Khas Kunar | Khas Kunar 36 tiny villages | 2026-08-20 | 2027-08-19 | 055/2026 | 428653.6033 | Awrish builder construction company (ABCC) | 1% | 1.5% |  | on track and will be completed by August 2027
9 |  | Bahrabad Canal irrigation Scheme |  | Nangarhar | Behsood | Bahrabad |  |  |  | 155202.1667 |  | 2%
10 | Package #10-AF2 IS: Rehabilitation of 1.Baraki canal, 2. Darbal canal, 3. Nawikhar canal and 4. Mangali canal irrigation schemes, located in Sayed Abad, Chak and Jaghato districts of Wardak province. | Baraki Canal irrigation Scheme | Central/Kabul | Wardak | Sayed Abad | Patan khil, Barat khil, Shadi khil, Sado khil and Laram | 2025-11-18 | 2026-11-17 | 057/2025 | 112870.515 | Zahid Saeed Engineering and Construction Company (ZSCC) | 100% | 30% | Sep, 2026 | partly on track, one package will need NCE and works will be completed by May/June 2027
11 |  | Darbal canal irrigation Scheme |  | Wardak | Chak | Darbal |  |  |  | 102415.9033 |  | 0%
12 |  | Nawikhar canal irrigation scheme |  | Wardak | Jaghato | Nawikhar |  |  |  | 77263.89 |  | 20%
13 |  | Mangali Canal irrigation Scheme |  | Wardak | Jaghato | Mamal khil, Mushangai, Adena and Mangali |  |  |  | 16116.335 |  | 0%
14 | Package #11-AF2 IS: Rehabilitation of Musahi Sufla canal irrigation schemes, located in Musahi districts of Kabul province. | Musahi Sufla Canal irrigation Scheme |  | Kabul | Musahi | Musahi Sufla | 2025-10-27 | 2026-10-26 | 056/2025 | 196473.81 | Seddiq Amini Construction and Logistic Services (SACC) | 98% | 98% |  | on track and will be completed in Oct. 2026
15 | Package #14-AF2 IS: Rehabilitation of Zard Sang and Topchi Cluster Canal Irrigation scheme, located in Center district of Bamyan province. | Sar Qul Topchi canal irrigation schemes | Central Highlan/ Bamyan | Bamyan | Center | Topchi | 2026-01-24 | 2027-01-23 | 002/2026 | 165609.6662 | Nomae Shahr Construction Company (NSCC) | 85% | 77.5% |  | on track and will be completed in 2026
16 |  | Zard Sang canal irrigation schemes |  |  |  | Zard Sang |  |  |  | 143050.8289 |  | 70% |  |  | on track and will be completed in 2027
17 | Package #16-AF2 IS: Rehabilitation of Pato (Paye Raqul, Sangchal Takhomak and Kadalak) Cluster canal irrigation scheme in Pato district of Daykundi province | Pato Irrigation Canal Cluster of (Paye Raqul, Sangchal Takhomak and Kadalak) |  | Daykundi | Pato | Paye Raqul, Sangchal Takhomak and Kadalak | 2026-01-21 | 2027-01-20 | 007/2026 | 232647.5 | Estehkam Baba Construction Company JV Tamadon Bamik Construction Company (EBCC) | 100% | 100% | July. 2026 | Completed in July 2026.
18 | Package #19-AF2 IS: Rehabilitation of Khwaja Angor canal and Qalai Wazir canal irrigation schemes located in Kharwar and Pol-i-Alam districts of Logar province. | Khwaja Angor Irrigation Scheme (OFWM Project) | Southeast/Gardez | Logar | Kharwar | Khwaja Angor | 2025-12-31 | 2026-12-30 | 074/2026 | 143249.7671 | Unique Wahaj Construction Company (UWCC) | 98% | 99% |  | on track and will be completed in 2026
19 |  | Qalai Wazir Irrigation Scheme (OFWM Project) |  |  | Pol-i-Alam | Qalai Wazir |  |  |  | 239337.2036 |  | 100% |  | Sep, 2026
20 | Package #20-AF2 IS: Rehabilitation of Welgai irrigation system, located in Matoon district of Khost province. | Welgai (Off-Farm & On-Farm Project) |  | Khost | Matoon | Shamal Piran | 2025-10-12 | 11-Oc-26 | 053/2025 | 229783.31 | Mahmood Raqi Nawin Construction & Road Building Company (MRCC) | 100% | 100% | June, 2026 | Completed in June 2026.
21 | Package # 21-AF2 IS: Rehabilitation of Markazi Ziruk and Mulakh canal irrigation schemes, located in Ziruk and Yousaf Khil districts of Pakteka province. | Markazi Ziruk Irrigation Scheme (Off & On-Farm Project) |  | Pakteka | Ziruk | Markazi Ziruk | 2026-06-06 | 2027-06-05 | 038/2026 | 94650.1056 | Farhad Matoonyar Construction Company (FMCC) | 20% | 25% |  | on track and will be completed by June 2027
22 |  | Mulakh Irrigation Scheme (On- Farm Project) |  |  | Yousaf Khil | Mest |  |  |  | 239482.1395 |  | 30%
23 | Package #25-AF2 IS: Rehabilitation of Urdo Kas canal and Sarkay Lazhey canal irrigation schemes, located in Sha Wali Kot and Boldak districts of Kandahar province. | Urdo Kas Irrigation Scheme | South/Kandahar | Kandahar | Sha Wali Kot | Urdo Kas | 2026-02-09 | 2026-12-08 | 012/2026 | 90157.4475 | Wasif Construction Company | 15% | 12.5% |  | Needs NCE and work will be completed by June 2027
24 |  | Sarkay Lazhey Canal Irrigation Scheme |  | Kandahar | Boldak | Sarkay Lazhey |  |  |  | 235424.7881 |  | 10%
25 | Package #26-AF2 IS: Rehabilitation of Sarwan Qala canal irrigation schemes, located in Sangin district of Kandahar province. | Sarwan Qala Canal Irrigation Scheme |  | Helmand | Sangin | Sarwan Qala | 2026-03-03 | 2027-03-02 | 019/2026 | 351552.71 | New Safi Zada Construction & Road Building Company JV with Elyas Aryoubi Constructin Road building and Logistic Company (NSZ&EACC) | 0% | 0% |  | package / contract cancelled
26 | Package # 28 – AF2 IS: Rehabilitation of Irrigation Schemes of 1. Abil Aroq (Qanjogha), 2. Shaitan Aroq Cluster Canals in Khwaja Ghar District and 3. Kalta Aroq, 4. Pacha Khail, and 5. Sayed Miran (Khar Kar) Cluster Canals in Eshkamish District of Takhar Province | Abil Aroq (Qanjugh) and Shaitan Aroq Cluster Canal Irrigation Schemes | Northeast/Kunduz | Takhar | Khwaja Ghar | Qanjogha | 2025-12-22 | 2026-12-21 | 067/2025 | 159788.8 | SHAMAL KARDAN ROAD CONSTRUCTION AND LOGISTIC SERVICES COMPANY LTD (SKRCC) | 0% | 40% |  | off track and close follow up to ensure completion by June 2027 after potential NCE
27 |  | Khar Kar (Kalta Aroq, Pacha Khail and Sayed Miran) Cluster Canal Irrigation Schemes |  | Takhar | Eshkamish | Kat Qurugh |  |  |  | 89881.2 |  | 80% |  |  | on track and will be completed by Dec. 2026
28 | Package #31-AF2 IS: Rehabilitation of 1. Shahidan &Dasht-e Lajam Canal schems in Tala wa barfak district, 2.Sardar Ha canal scheme in Deh Salah district, and 3. Kambilan cluster canal schemes in Fring districts of Baghlan province. | Shahidan & Dasht-e Lajam Canals |  | Baghlan | Tala wa barfak | Shahidan & Dast-e-Lajam | 2026-01-29 | 2026-11-28 | 009/2026 | 190128.7685 | Afghan Eithad construction and Road Building company (AECC) | 100% | 96.67% | July. 2025 | on track and will be completed by Nov. 2026
29 |  | Sardara Canal Irrigation scheme |  | Baghlan | Deh Salah | Sardara |  |  |  | 167265.5365 |  | 90%
30 |  | Juybar-e-Maidan (Payendakhail), Nahr-e-Salih, Khambilan, Dara-e-Bazar Irrigation Schemes |  | Baghlan | Fring | Juybar-e-Maidan (Payendakhail), Salih, Khambilan, Dara-e-Bazar |  |  |  | 120795.678 |  | 100% |  | August, 2026
31 | Package #32-AF2 IS: Rehabilitation of Abdul Baqi canal and Mulla Oma canal irrigation schemes, located in Chemtal districts of Balkh province. | Abdul Baqi Canal Irrigation scheme | North/Mazar | Balkh | Chemtal | Sari Asiab | 2025-12-31 | 2026-11-29 | 075/2025 | 141012.0085 | Trust Grow Construction and Engineering Company (TGCC) | 100% | 100% | July, 2026 | Completed in July 2026.
32 |  | Mulla Omar Canal Irrigation scheme |  | Balkh | Chemtal | Sarkar |  |  |  | 159013.5415 |  | 100% |  | July, 2026
33 | Package #33-AF2 IS: Rehabilitation of Chela Mazar canal and Kushkak canal irrigation schemes, located in Dara-e- Suf-e-Bala and Dara-e-Suf-e-Payeen districts of Samangan province. | Chela Mazar Canal Irrigation scheme |  | Samangan | Dara-e- Suf-e-Payeen | Chela Mazar | 2026-01-15 | 2026-12-14 | 003/2026 | 143685.362 | AFGHAN LUCKY CONSTRUCTION COMPANY (ALCC) | 25% | 46% |  | one scheme will be completed by Dec. 2026 and other scheme to be completed by June 2027 after NCE
34 |  | Kushkak Canal Irrigation scheme |  | Samangan | Dara-e- Suf-e-Bala | Kushkak |  |  |  | 140859.9445 |  | 67%
35 | Package # 35-AF2 IS: Rehabilitation of Bahr-e Ameq canal irrigation scheme, located in Sozma Qala districts of Sar-e-Pul province. | Bahr-e Ameq Canal Irrigation scheme |  | Sar-e- Pul | Sozma Qala | Bahr-e Ameq | 2026-02-17 | 2027-01-16 | 016/2026 | 249484.29 | Sakht shamal construction and road building company (SSCC) | 60% | 60% |  | on track and will be completed by Jan. 2027
35 |  | Total |  |  |  |  | 18 |  |  | 5660431.5992

## 2.Remain contracts_On&off-farm
EMERGENCY FOOD SECURITY PROJECT (EFSP)
| Component 2: Provision of Water and Resilience Services | [8 empty] | 7.8
WBK/AF-2
List of contracts yet to be awarded
Sno | Package / Contract name | Name of the sub-project | Location |  |  |  | Current Status | Expected contract signed date | Expected contract end date | Estimated Cost (USD) | Remarks
|  |  | Region | Province | District | Village
1 | Package #3-AF2 IS: Rehabilitation of Yazdi irrigation scheme, located in Center Districts of Farah province. | Yazdeh Canal irrigation Scheme | West/Herat | Farah | Center | Yazdi | Under WRI review (design review) | 2026-12-15 | 2027-09-14 | 180000 | Two months slack period Mar-Apr during the flood. Seven months construction period. Explore split into 2 lots if needed |  |  | 7.5
2 | Package #38-AF2 IS: Rehabilitation of Todanak Payen irrigation scheme, located in Farahrud Districts of Farah province. | Todanak Payen Canal irrigation Scheme |  | Farah | Farahrud | Todanak Payen villages |  |  |  | 170000
3 | Package #4-AF2 IS: Rehabilitation of Joi Gang irrigation scheme in Bala Murghab districts of Badghis provinec. | Joi Ganj Canal irrigation Scheme |  | Badghis | Bala Murghab | Joi Ganj and Ludeenha | PR to be raised | 2026-12-31 | 2027-10-27 | 248511.19 | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals |  | 9.9404 | 5
4 | Package #39-AF2 IS: Rehabilitation of Ludeenha and Joi Kar irrigation schemes in Bala Murghab districts of Badghis provinec. | Ludeenha and Joi Kar canal irrigation Scheme |  | Badghis | Bala Murghab | Joi Kar | PR to be raised | 2026-12-30 | 2027-08-27 | 195488.81 | Three months slack period Jan-Mar during winter. Five months construction period required for two canals |  | 7.8196
5 | Package #5-AF2 IS: Rehabilitation of Korakha irrigation scheme, located in Dawlatyar District of Ghor province. | Korakha Irrigation Scheme |  | Ghor | Dawlatyar | Sumak | PR to be raised | 2026-12-25 | 2027-08-12 | 101250 | Three months slack period Jan-Mar during winter. Five months construction period required for two canals
6 | Package #40-AF2 IS: Rehabilitation of Loka Mazar irrigation schemes, located in Dawlatyar District of Ghor province. | Loka Mazar Irrigation Scheme |  | Ghor | Dawlatyar | Lokamazar | PR to be raised | 2026-12-31 | 2027-08-28 | 141250 | Three months slack period Jan-Mar during winter. Five months construction period required for two canals |  |  | 12.125
7 | Package #37-AF2 IS: Rehabilitation of Oshtorkhan/Ahangaran irrigation scheme, located in Firozkoh district of Ghor province. | Oshtorkhan/Ahangaran irrigation Schemes |  | Ghor | Firozkoh | Oshtorkhan, Ahangaran and Madrasa | Under design | 2026-12-30 | 2027-08-17 | 128000 | Three months slack period Jan-Mar during winter. Five months construction period required for two canals
8 | Package #41-AF2 IS: Rehabilitation of Madrasa irrigation schemes, located in Firozkoh district of Ghor province. | Mardras irrigation Schemes |  | Ghor | Firozkoh | Oshtorkhan, Ahangaran and Madrasa | Under design | 2026-12-20 | 2027-08-17 | 85000 | Three months slack period Jan-Mar during winter Five months construction period required for three canals. To explore 2 lots for 2 contracts and simultaneous work
9 | Package #7-AF2 IS: Rehabilitation of Kham Canal and Shandi Toot canal irrigation schemes, located in Dehbala and Sherzad districts of Nangarhar provinces. | Kham canal irrigation Scheme | East/Jalalabad | Nangarhar | Dehbala | Kham Kali and 6 tiny villages | TE completed | 2026-10-30 | 2027-05-28 | 270698.1019 | Seven months construction period required for two canals | August | 9 months
10 |  | Shandi Toot Canal irrigation Scheme |  | Nangarhar | Sherzad | Markikhil/Shandi Toot and 14 tiny villages
11 | Package #9-AF2 IS: Rehabilitation of Akchori canal irrigation scheme, located in Waigal districts of Nuristan provinces. | Akchori Canal irrigation Scheme |  | Nuristan | Waigal | Akchori two main and 9 tiny villages | ITB launched | 2026-11-27 | 2027-09-26 | 101175 | Five months slack period Dec-Apr during winter Five months construction period required for the canals | December | 8 months
12 | Package #12-AF2 IS: Rehabilitation of Tapa-e-Ahmad Big canal and Shahre Beland canal irrigation schemes, located in Nijrab and Paryan districts of Kapisa and Panjsher provinces. | Tapa e- Ahmad Big Canal | Central/Kabul | Kapisa | Nijrab | Tapa e Ahmad Big, Shahre Naw | Under TE | 2026-11-01 | 2027-07-29 | 191270 | Four months slack period Dec-Mar during winter. Five months construction period required for two canals | July | 6 months
13 |  | Shahre Beland Canal irrigation Scheme |  | Panjshir | Paryan | Shahre Beland
14 | Package #13-AF2 IS: Rehabilitation of Kamar China canal, Khenkot canal, and Zargara irrigation schemes, located in Sarobi, Chahar Asiab and Paghman districts of Kabul province. | Kamar China Canal irrigation Scheme |  | Kabul | Sarobi | Warkhralah | Under TE | 2026-11-10 | 2027-07-08 | 290000 | Three months slack period Jan-Mar during winter. Five months construction period required for three canals | August | 9 months
15 |  | Khenkot irrigation Scheme |  |  | Chahar Asiab | Shah Toot
16 |  | Zargara canal irrigation Scheme |  |  | Paghman | Qla-e- Hakeem, Somochak and Ala Bala
17 | Package #15-AF2 IS: Rehabilitation of Pitab joy and Sorkh Kawak Cluster Canal Irrigation scheme, located in Waras districts of Bamyan province. | Pitab Joy Cluster canal irrigation schemce | Central Highlan/ Bamyan | Bamyan | Waras | Pitab and 6 tiny villages | Retendered (ReITB) | 2026-12-15 | 2027-09-21 | 335855.1692 | Three months slack period Jan-Mar during winter. Eight months construction period required for two canals. Explore possibility of BAFO and split to 2 contracts based on the outcome of the reITB | July | 11 months
18 |  | Sorkh Kawak Cluster canal irrigation schemce |  |  |  | SorKh kawak and 6 tiny villages | [7 empty] | Rebid
19 | Package #17-AF2 IS: Rehabilitation of Hezhdi- Nilli, Cluster Canal irrigation schemes, located in Nilli district of Daykundi province. | Hezhdi- Nilli Charsapan Cluster Canal irrigation schemes |  | Daykundi | Nilli | Hezhdi |  | 2026-12-15 | 2027-09-11 | 94951
20 | Package #42-AF2 IS: Rehabilitation of Zard Nai Charsapan Cluster Canal irrigation schemes, located in Sharrisatan district of Daykundi province. | Zard Nai Charsapan Cluster Canal irrigation schemes |  | Daykundi | Shahristan | Zardnai Payeen, Zardnai Bala, | Under LTO review | 2026-12-15 | 2027-10-21 | 257667 | 2.5 months slack period Mid Jan-Mar during winter. Eight months construction period required for the cluster canals in two districts. Explore possibility of 2 lots for PR and contract award
21 | Package #18-AF2 IS: Rehabilitation of Drang canal irrigation schemes, located in Zurmat district of Paktya province. | Drang canal irrigation Scheme (On-FWM Project) |  | Paktya | Zurmat | Drang | ITB launched | 2026-11-30 | 2027-10-29 | 393953 | Three months slack period Jan-Mar during winter. Nine months construction period required for the cluster canals in two districts | January | 12 months |  | 2026-10-28
22 | Package # 22-AF2 IS: Rehabilitation of Gero canal irrigation scheme, located in Center and Qarabagh districts of Ghazni province. | Gero Irrigation Scheme (Off & On-Farm Project) Gero&Qarabagh |  | Ghazni | Center | Gero | Under LTO review | 2026-12-28 | 2027-10-24 | 290000 | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals in two districts
23 | Package #23-AF2 IS: Rehabilitation of Patab canal irrigation schemes, located in Khas Urozgan of Urozgan province. | Patab Irrigation Schem |  | Urozgan | Khas Urozgan | Patab | Retendered (ReITB) | 2026-12-15 | 2027-09-11 | 290442.55 | The submitted work plan to be revised | July | 12 months
24 | Package #24-AF2 IS: Rehabilitation of Shajoy canal irrigation scheme, located in Dayee Chopan districts of Zabul province. | Shajoy Canal Irrigation Scheme |  | Zabul | Dayee Chopan | - | Under design | 2026-12-20 | 2027-09-16 | 155000 | Three months slack period Jan-Mar during winter. Six months construction period required for two canals in two districts. Explore splitting into two lots and if one lot ready then raise PR.
25 | Package #43-AF2 IS: Rehabilitation of Sar Nary canal irrigation scheme, located in Arghandab districts of Zabul province. | Sar Nary Canals Irrigation Scheme |  | Zabul | Arghandab | - | Under design | 2026-12-20 | 2027-09-16 | 160000
26 | Package # 27-AF2 IS: Rehabilitation of Firozi canal irrigation scheme, located in Delaram districts of Nimroz province. | Firozi Canal Irrigation Schem |  | Nimruz | Delaram | - | Under WRI review (design review) | 2026-12-25 | 2027-09-21 | 195000 | Nine months construction period required for the canal
27 | Package #29-AF2 IS: Rehabilitation of Dagh Aruq canal irrigation scheme, located in Chahar Dara district of Kunduz province. | Dagh Aruq Canal Irrigation Scheme |  | Kunduz | Chahar Dara | Dagh Aruq | PR to be raised | 2026-11-25 | 2027-09-21 | 200000 | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals. Split into 2 lots and make 2 PRs
28 | Package #44-AF2 IS: Rehabilitation of Boghoz Qum canal irrigation schemes, located in Chahar Dara district of Kunduz province. | Boghoz Qum Irrigation scheme |  | Kunduz | Chahar Dara | Boghoz Qum | PR to be raised |  |  | 200000
29 | Package # 30-AF2 IS: Rehabilitation of Teshkhan canal canals irrigation scheme, located in Ishkashim districts of Badakhshan province. | Teshkhan Canal Irrigation Scheme |  | Badakhshan | Ishkashim | Teshkhan | PR to be raised | 2027-01-12 | 2027-10-09 | 126516.451 | Three months slack period Jan-Mar during winter. Six months construction period required for two canals
30 | Package # 45-AF2 IS: Rehabilitation of Khushpak Markazi canals irrigation scheme, located in Ishkashim districts of Badakhshan province. | Khushpak Markazi Canal Irrigation Scheme |  | Badakhshan | Ishkashim | Osas | PR to be raised | 2027-01-13 | 2027-08-11 | 85774.9653 | Three months slack period Jan-Mar during winter. Six months construction period required for two canals
31 | Package #34-AF2 IS: Rehabilitation of Hashtman canal and Qashqasai canal irrigation schemes, located in Qaisar district of Faryab province. | Hashtman Canal Irrigation scheme |  | Faryab | Qaisar | Chechakto Majnon and Payan Guzar | ITB launched | 2026-12-30 | 2027-10-06 | 397007.8629 | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals | December | 11 months
32 |  | Qashqasai Canal Irrigation scheme |  | Faryab | Qaisar | Yaka Bagh, Kham badal, Pacha Khor, and Borghan Erak. | [8 empty] | 2026-11-27
33 | Package # 36-AF2 IS: Rehabilitation of Joy Shahr canal irrigation scheme, located in Aqcha district of Jawzjan province. | Joy Shahr Canal Irrigation scheme |  | Jawzjan | Aqcha | Joy Shahr in Jiza | Under LTO review | 2026-12-17 | 2027-06-05 | 55950 | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals. Explore split into 2 lots
34 | Package # 46-AF2 IS: Rehabilitation of Joy Shahr canal and Khanum Arabia canal irrigation schemes, located in Aqcha and Faizabad districts of Jawzjan province. | Hidar Abad Canal Irrigation scheme |  | Jawzjan | Faizabad | Haidar Abad and Naw Abad | Under LTO review | 2026-12-18 | 2027-10-14 | 276650 | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals. Explore split into 2 lots
34 |  | Total | [6 empty] | 28
Formulas:
Expected contract end date = [Expected contract signed date]+300

## 3.WSM awarded contracts
EMERGENCY FOOD SECURITY PROJECT (EFSP)
Component 2: Provision of Water and Resilience Services
WBK/AF-2
List of ongoing contract under Watershed Management activity (Construction of Check Dams)
S N0 | Package / Contract name | Name of the sub-project | Location |  |  |  | Contract signed date | Contract end date | Contract Cost (USD) | Contract number | Cosntrution company | Physical progress % |  | Overall progress at the region (%) | Remarks
|  |  | Region | Province | District | Village | [5 empty] | Sub-projects | Packages
Activity 2.1.a: Watershed Management interventions (construction of check dams, including improvement of upper catchment of Karezes)
1 | Package #2 -AF2 WSM: Construction of 1. Dareh Shah Toot-1, 2. Dareh ShahToot-2, and 3. Jar Sono check dams in Obe District of Herat Province | Dareh Shah Toot Check dam-1 | West/Herat | Herat | Obe | Gonabad, Qala Yar Mohammad Khan, Zori ha, Dasht Servan | 2026-02-09 | 2026-12-08 | 194033 | 014/2026 | Shams Afghan Vision Construction and Logistic Services (SAVCC) | 95% | 75% | 69% | Expected to complete by the end of the contract NTE.
2 |  | Dareh Shah Toot Check dam-2 |  | Herat | Obe | [6 empty] | 75%
3 |  | Jar Sunu Check dam-3 |  | Herat | Obe | [6 empty] | 55%
4 | Package #3 -AF2 WSM: Construction of Koklam three Check Dams (# 1, # 2 and # 3 ) in Kushk-e-Kohna District of Herat Province | Jar Koklam, Dara Koklam Bala Check Dam # 1 |  | Herat | Koshk-e-Kohna | Koklam village (Jar Koklam, Dara Koklam Bala, Baland Bazar, Jar Ahmad and Pastaliq Bazar) | 2026-01-21 | 2026-11-20 | 71140.923 | 006/2026 | Afghan Aakam Construction and Road Company. JV with D- Amini Mashwani Construction Company (AACC) | 89% | 63% |  | Expected to complete by the end of the contract NTE.
5 |  | Baland Bazar, Jar Ahmad Check Dam # 2 |  | Herat | Koshk-e-Kohna |  |  |  | 68058.5955 |  |  | 70%
6 |  | Pastaliq Bazar Check Dam # 3 |  | Herat | Koshk-e-Kohna |  |  |  | 74256.6815 |  |  | 30%
7 | Package #5-AF2 WSM/Part-2: Construction of 4 Check dams of 1.Farman Khil and 2.Kharoti in Qarghaee district of Laghman province; 3. Lokhy Solozi and 4. Lala Kali in Chaparhar districts of Nangarhar province. | 1. Farman khill Check dam | East/Jalalabad | Laghman | Qarghaee | Farmankhil | 2026-05-30 | 2026-10-29 | 29781.8831 | 040/2026 | Khaliqi Building & Road Construction Company (KBRCC) | 50% | 44.5% | 72.25% | A check dam, a pond and a social structure. Contract extension needs to be sought.
8 |  | 2. Kharoti Check dam |  | Laghman | Qarghaee | Kharoti |  |  | 24682.6541 |  |  | 68%
9 |  | 3. Lokhy Solozi Check dam |  | Nangarhar | Chaparhar | Lokhy Solozi |  |  | 38189.6098 |  |  | 60%
10 |  | 4. Lala Kali/Ranju Ghar Check dam |  | Nangarhar | Chaparhar | Lala Kali/Ranjo ghar |  |  | 17344.5136 |  |  | 0%
11 | Package #6-AF2 WSM: Construction of Jarobi Tangi, Chaghari and Adore check dams, located in Shirzad, Rodat, and Khogyani, districts of Nangarhar province. | 1. Markikhil/Jarobi Tangi Check dam |  | Nangarhar | Sherzad | Jarobi Tangi | 2025-12-23 | 2026-07-22 | 51209.988 | 065/2026 | Naeemi Safi Construction & Construction Material Company (NSCC) | 100% | 100% |  | Completed on July, 2026
12 |  | 2. Chaghari Check dams |  | Nangarhar | Rodat | Chaghari |  |  | 27989.4314 |  |  | 100%
13 |  | 3. Adore check dam |  | Nangarhar | Khogyani | Adore |  |  | 50713.552 |  |  | 100%
3 | Package #7-AF2 WSM: Construction of 3 Check dams of 1.Dargrak, 2. Migano, and 3.Lachagali the Sawkai, Khas Kunar and Narang districts of Kunar province. | Lachagali Boulder Check Dam and Water Pond | East/Jalalabad | Kunar | Narang | Lachagali/ Jaroobi | 2026-10-11 | 2027-03-10 | 99590 | 064/2026 | Green Bentley construction Company (GBCC) | 0% | 0%
4 |  | Dargarak Check Dam |  | Kunar | Sawkai | Daar Garak | [5 empty] | 0% |  | 0% | Awarded on 11 oct.2026
5 |  | Miagan Check Dam |  | Kunar | Khas Kunar | Miagan Kali | [5 empty] | 0%
14 | Package #8-AF2 WSM: Construction of 1.Ghazgai Check dam in Khake Jabar districts, 2.Toop Dara Check dam and 3.Toot Dara Check dam in Center/ 13th City district Kabul province. | 1.Toop Dara Check dam | Central/Kabul | Kabul | Center | 13th district | 2026-01-20 | 2026-08-19 | 65749 | 005/2026 | ALTIN CONSTRUCTION AND ROAD BUILDING COMPANY (ACC) | 100% | 100% | 77.08% | Completed on July, 2026
15 |  | 2.Toot Dara Check dam |  | Kabul | Center | 13th district | [5 empty] | 100%
16 |  | 3.Ghazgi Check dam |  | Kabul | Khake Jabar | Ghazgai | [5 empty] | 100%
17 | Package #9-AF2 WSM: Construction of 1.Aka Khil Check dam and 2. Sra Qala Check dam in Sayed district, 3.Khar Check dam and 4.Mardala Check dam, located in Jaghatu districts of Wardak province. | 1.Aka Khil Check dams |  | Maidan Wardak | Sayed Abad | Aka Khil | 2026-03-10 | 2026-10-08 | 68618.92 | 021/2026 | Sayed Abad Construction Company (SACC) | 100% | 100% |  | Completed on August, 2026
18 |  | 2.Sra Qala Check dams |  | Maidan Wardak | Sayed Abad | Sra Qala | [5 empty] | 100%
19 |  | 3.Khar Check dams |  | Maidan Wardak | Jaghatu | Khar | [5 empty] | 100%
20 |  | 4.Mardala Check dams |  | Maidan Wardak | Jaghatu | Mardala | [5 empty] | 100%
21 | Package #10-AF2 WSM: Construction of Loy Shenkai Check dams # 1 and # 2 in Tagab district, and Shahr-e-Naw Check dam # 3 located in Nijrab districts of Kapisa province. | 1. Loy Shenkai Check dams-1 |  | Kapisa | Tagab | Loy Shenkai-1 | 2026-03-09 | 2026-09-08 | 44028.02 | 020/2026 | Kapisa Kohna Dah Construction Company (KKCC) | 100% | 100% |  | Completed on August 2026
22 |  | 2. Loy Shenkai Check dams-2 |  | Kapisa | Tagab | Loy Shenkai-2 | [5 empty] | 100%
23 |  | 3. Shahr-e-Naw Check dam |  | Kapisa | Nijrab | Shahr-e-Naw | [5 empty] | 100%
24 | Package #11-AF2 WSM: Construction of 3 Check dams 1.Wolangak in Shikh Ali, 2.Sanzalai, and 3.Sharkai Olia in Koh-e-Safi district of Parwan province. | Wolangak Check dams |  | Parwan | Shikh Ali | Wolangak | 2026-06-24 | 2026-11-23 | 77145 | 043/2026 | Hemat Ghorzang Construction & Logistic Service Company (HGCC) | 0% | 8.333%
25 |  | Sanzalai and Sharki Olia |  | Parwan | Koh-e-Safi | Sanzalai | [5 empty] | 20%
26 |  | Sharkai Olia Check dam |  | Parwan | Koh-e-Safi | Sharki Olia | [5 empty] | 5%
27 | Package #13-AF2 WSM: Construction of 4 Check Dams in 4 district sites of 1.Kata Khana in Yakawlang , 2. Nawora in Panjab, 3.Nahorak in Waras, and 4.Bayani in Sayghan districts of Bamyan province | 1.Kata Khana Check dam | Central Highlan/ Bamyan | Bamyan | Yakawalang | Kata Khana, Check dam | 2026-07-22 | 2027-02-21 | 66705.5053 | 051/2026 | Estehkam Baba Construction and Road Construction Company (EBCC) | 35% | 47.5% | 73.75%
28 |  | 2.Nawora Check dam |  | Bamyan | Panjab | Nawora |  |  | 52796.7609 |  |  | 45%
29 |  | 3.Nahorak Check dam |  | Bamyan | Waras | Nahorak |  |  | 54600.6533 |  |  | 60%
30 |  | 4.Bayani Check dam |  | Bamyan | Sayghan | Bayani |  |  | 35843.0675 |  |  | 50%
31 | Package #14-AF2 WSM: Construction of 1.Shahristan Check dama in Shahristan district, 2.Miramor Check dam in Miramor district, and 3.Khidir Check dams in Khidir districts of Daykundi province. | 1. Shahristan Check dam |  | Daykundi | Shahristan | Dar Band, Dasht-e Safid, Madar, Lorange | 2026-04-01 | 2026-10-30 | 52946.0537 | 025/2026 | Da Maidan Zawahnono Construction Company (DMZCC) | 100% | 100% |  | Completed on Sep, 2026
32 |  | 2. Miramor Check dam |  | Daykundi | Miramor | Folad, Deh Ghulam, |  |  | 48360.8649 |  |  | 100%
33 |  | 3. Khidir Check dam |  | Daykundi | Khidir | Dahan-e Degshoyak, Dahan-e Mardakmoda |  |  | 40132.4999 |  |  | 100%
8 | Package #15-AF2 WSM: Construction of 3 Check dams of 1. Sangmom, 2. Shilan Korga, and 3.Khulbar in Nili, Ashtarlay, and Sang Takhta districts of Daykundi province. | Sangmom Check dam | Central Highlan/ Bamyan | Daykundi | Nili | Sangmom | 2026-10-08 | 2027-03-07 | 179455 | 065/2026 | Bahartamadun Construction Company (BCC)
9 |  | Shilan Korga Check dam |  | Daykundi | Ashtarlay | Korga-e Shelan, Naiak-e Shelan
10 |  | Khulbarg Check dam |  | Daykundi | Sang Takht wa Bandar | Shamshir Sang, Dughur Ulya & Sufla
34 | Package #16-AF2 WSM: Construction of Panami Check dams, located in Mohammad Agha district of Logar province. | Panami Check dam | Southeast/Gardez | Logar | M.Agha | Ab Bazak (Panami) | 2026-04-18 | 2026-11-17 | 109583.21 | 030/2026 | Sayed Shirazi Construction and Road Building Company (SCRC) | 64% | 64% | 50%
35 | Package #18-AF2 WSM: Construction of Muqarab Check dams, located in Gelan districts of Ghazni province. | Muqarab Check dam |  | Ghazni | Gelan | Muqarab | 2026-07-23 | 2027-01-22 | 79567.97 | 047/2026 | Hemat safi construction company (HSCC) | 36% | 36%
36 | Package #21-AF2 WSM: Construction of 4 Check Dams 1.Choghazey and 2.Sardarkey in Arghistan, 3. Loy Laher in Spin Boldak and 4.Ab Samad Aka in Takhta Pull districts of Kandahar province. | Choghazey Check Dam | South/Kandahar | Kandahar | Arghistan | Ab Samad Aka | 2026-04-28 | 2026-09-27 | 12021.057 | 031/2026 | Bakhter Pairoz Construction Company (BPCC) | 100% | 50% | 25%
37 |  | Sardarkey Check Dam |  | Kandahar | Arghistan | Loy Laher |  |  | 34095.1634 |  |  | 95%
38 |  | Loy Laher Check Dam |  | Kandahar | Spin Boldak | Sardarkey |  |  | 30196.0813 |  |  | 15%
39 |  | Ab Samad Aka Check Dam |  | Kandahar | Takhta Pul | Choghazey |  |  | 38337.0651 |  |  | 10%
40 | Package #23-AF2 WSM: Construction of 1,Payazak, 2.Sharak, 3.Khairtot, and 4. Mula Hanifiya Check Dams, located in Shawalikot district of Kandahar province. | Payazak Check Dam |  | Kandahar | Shawalikot | Payazak | 2026-08-27 | 2026-02-26 | 28065.1049 | 057/2026 | Afghan Laser Engineering and Construction Company (ALCC) | 0% | 0%
41 |  | Sharak Check Dam |  | Kandahar | Shawalikot | Sharak |  |  | 34142.2598 |  |  | 0%
42 |  | Khairtot Check Dam |  | Kandahar | Shawalikot | Khairtot |  |  | 34668.6216 |  |  | 0%
43 |  | Mula Hanifiya Check Dam |  | Kandahar | Shawalikot | Mula Hanifiya |  |  | 27314.9796 |  |  | 0%
44 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | 1. Yawol Ha Check Dam-1 | Northeast/Kunduz | Badakhshan | Teshkan | Yawol Ha-1 | 2026-04-09 | 2026-11-08 | 28489.9035 | 027/2026 | Faiz Qurbani Construction Company (FQCC) | 10% | 35% | 36.17%
45 |  | 2. Yawol Ha Check Dam-2 |  | Badakhshan | Teshkan | Yawol Ha-2 |  |  | 29242.9574 |  |  | 0%
46 |  | 3.Sewak Dara Kelaki Check Dam |  | Badakhshan | Darayim | Sewak Dara |  |  | 59018.9924 |  |  | 100%
47 |  | 4. Golaki Check Dam |  | Badakhshan | Darayim | Golaki |  |  | 62408.8816 |  |  | 100%
48 |  | 5. Khanaqa Check Dam |  | Badakhshan | Arghanj Khwah | Khanaqa |  |  | 29058.4896 |  |  | 0%
49 |  | 6. Sum Darra Check Dam |  | Badakhshan | Arghanj Khwah | Sum Dara |  |  | 31519.8959 |  |  | 0%
50 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | 1.Sholish Darra Check Dam |  | Takhar | Namak Ab | Sholish Darra | 2026-05-21 | 2026-11-20 | 29465.2654 | 037/2026 | Shafiqullah Wahidi Construction Company (SWCC) | 0% | 36%
51 |  | 2.Gaji Darra Check Dam |  | Takhar | Hazar Sumoch | Gaji Darra |  |  | 28776.591 |  |  | 0%
52 |  | 3.Silaba Check Dam |  | Takhar | Khwaja Ghar | Charagh Sai-e, Silaba |  |  | 17455.3916 |  |  | 100%
53 |  | 4.Shoor Toghai Check Dam |  | Takhar | Khwaja Bahawuddin | Shoor Toghai and Koratam |  |  | 93678.8973 |  |  | 80%
54 |  | 5.Khalyazi Check Dam |  | Takhar | Yangi Qala | Khalyazi |  |  | 30229.5684 |  |  | 0%
55 | Package #28-AF2 WSM: Construction of 2 Check dams of 1. Chatqa Sai in Dahna-e-Ghori and 2.Tahiryan in Baghlan Markazi districts of Baghlan province. | Chatqa Sai Check Dam |  | Baghlan | Dahna-e-Ghori | Chatqa Sai | 2026-08-08 | 2026-12-07 | 62969 | 054/2026 | Arman Sharq Construction Company ASCC) | 70% | 37.5%
56 |  | Tahiryan Check Dam |  | Baghlan | Baghlan Markazi | Tahiryan |  |  | 36531 |  |  | 5%
57 | Package # 29-AF2 WSM: Construction 1. Alburs and 2. Marmul Check dams, located in Marmul and Alburs districts of Balkh province | Alburz Check dam | North/Mazar | Balkh | Alburz | Barga Turkmaniya, Tagab-e-Emam Sahib Fatima Khail, Khedr Khail | 2026-05-12 | 11-Oc-26 | 54628.2566 | 034/2026 | Omar Mortaza Construction & Road Building JV Karwan Seraji Construction and Road Building Company (OMCC&KSCC) | 100% | 99% | 58.94% | Completed on Sep, 2026
58 |  | Marmul Check dam |  | Balkh | Marmul | Pusht-e-Baghcha and Charmaghz Say |  |  | 45083.7434 |  |  | 98%
59 | Package #30-AF2 WSM: Construction of 5 Check Damas of A. Majar site # 1 and site # 2; B.Elyasgar site # 3, site 4 and site # 5, located in Aljahad district of Sar-e-Pul province. | Majar Check dam |  | Sar-e-Pul | Aljahad | Mullah Baba, Bahauden, Katlo Soy, Majar Ulia, Majar Aji | 2026-07-23 | 2026-11-22 | 22485.1393 | 050/2026 | Waheed Wahaj Construction Company (WWCC) | 6% | 12% |  | The contract has recently been awarded. Mobilization is being carried out by the contractor.
60 |  | Elyasgar Check dam |  | Sar-e-Pul | Aljahad | Ayob, Jar Abdara, Mula Salam, Haji Talib, Hajib Pirak |  |  | 48085.9662 |  |  | 6%
61 | Package # 31-AF2 WSM: Construction of 1. Khaibar and 2. Chelgazi Check dams, located in Khaibar and Chelgazi districts of Faryab province. | Khaibar Check dam |  | Faryab | Khaibar | Mesh mast and Pasha Khan Abdal | 2026-05-07 | 2026-09-06 | 44507.7603 | 033/2026 | Malik Hajdar Construction and Road Company (MHCC) | 100% | 100% |  | Completed on Aug, 2026
62 |  | Chelgazi Check dam |  | Faryab | Chelgazi | Hazar qala and Aq Mazar |  |  | 36101.0341 |  |  | 100% |  |  | Completed on Aug, 2026
63 | Package #32-AF2 WSM: Construction of Tai Khunak 4 Check dams of A. Khoja Momin site # 1 and site # 2, B. Sari Shor site # 3 and site #4, located in Aybak district of Samangan province. | Taikhunak (Khoja Momen) Check dams site # 1 and #2 |  | Samangan | Aybak | Shorabak, Khoja Momen. | 2026-07-22 | 2026-11-21 | 61755.9843 | 045/2026 | Mudeser Bigmurad Construction Company (MBCC) | 30% | 24.75% |  | The contract has recently been awarded; Mobilzation has started.
64 |  | Taikhunak (Sari Shor) 2 Check dams site # 3 and # 4 |  | Samangan | Aybak | Sar-i-Shor, Ozon Say |  |  | 53185.5008 |  |  | 19.49%
64 | [6 empty] | 23 |  | 2866041.9091 |  |  |  |  | 57.77%

## 4.WSM remaining contracts
EMERGENCY FOOD SECURITY PROJECT (EFSP)
Component 2: Provision of Water and Resilience Services
WBK/AF-2
List of contract yet to be awarded Construction of Check Dams)
S N0 | Package / Contract name | Name of the sub-project | Location |  |  |  | Current status | Expected contract award date | Expected contract end date | Estimated Cost (USD) | Remarks
|  |  | Region | Province | District | Village
1 | Package #1-AF2 WSM: Construction of Dara Garmak Check dam, located in Qadis districts of Badghis province | Dara Garmak Check dam | West/Herat | Badghis | Qadis | Langar | PR to be raised | 2026-12-05 | 2027-09-01 | 131000 | Construction of the check dam will be completed in six months. Additional three months have been kept as slack period during Jan-March.
2 | Package #4-AF2 WSM: Construction of .Qalai Gerd check dam in Firozkoh dustrict of Ghor province. | Qalai Gerd Check dam |  | Ghor | Firozkoh | Qalai Gerd | PR to be raised | 2026-12-10 | 2027-10-06 | 219000 | Construction of the check dam will be completed in seven months. Additional three months have been kept as slack period during Jan-March.
3 | Package #12-AF2 WSM: Construction of 4 Check dams 1. Qoli Ghafoor, 2. Dara-e-Qala-e-Qazi in PD#13 Kabul city, 3.Gul Mohammad and 4.Qala-e-Shah Mahmood in Deh Sabz district of Kabul province. | Qoli Ghafoor, Dara-e-Qala-e-Qazi Check dams | Central/Kabul | Kabul | PD#13 Kabul | Qoli Ghafoor, Dara-e-Qala-e-Qazi | PR to be raised | 2026-12-15 | 2027-09-11 | 197430 | Construction of the check dam will be completed in seven months. Additional three months have been kept as slack period during Jan-March.
4 |  | Gul Mohammad, Qalai e Shah mohammad Check dams |  | Kabul | Deh Sabz | Gul Mohammad, Qalai e Shah mohammad
5 | Package #17-AF2 WSM: Construction of Ghoriza Check dams, located in Sayed Karam districts of Paktya province. | Ghawreza Check dam | Southeast/Gardez | Paktya | Sayed Karam | Bara Ghoriza | PR to be raised | 2026-11-20 | 2027-06-28 | 86330 | Construction of the check dam will be completed in four months. 20-Dec to March end as the slack period.
6 | Package #19-AF2 WSM: Construction of two Check dams 1. Wazgarai and 2. Chenargai in Zazai Maidan districts of Khost province. | Wozgarai and Chenargai Check dams |  | Khost | Zazai Maidan | 3.Wozgarai, Majbor Abad and Chenargai | ITB launched | 2026-11-30 | 2027-06-28 | 85715.76 | Construction of the check dam will be completed in four months. Jan to March end as the slack period. | September | 5 months
7 | Package #20-AF2 WSM: Construction of Sapari Check dams, located in Sarubi districts of Paktika province. | Sapari Check dam |  | Paktika | Sarubi | Abas Khil | PR to be raised | 2026-11-25 | 2027-07-03 | 84683 | Construction of the check dam will be completed in four months. Jan to March end as the slack period.
8 | Package #22-AF2 WSM: Construction of 5 Check dams 1.Kocni Karez , 2.By Khosh , 3. Ghul Khani, 4. Chy Dara in Ghorak district , and 5. Khanjak Mastan Aka in Nesh district of Kandahar province. | Kocni Karez Check Dam | South/Kandahar | Kandahar | Ghorak | Kocni Karez Village | Under Design | 2026-11-30 | 2027-05-29 | 135000 | Technical clearance is expected to receive at end October. PR raised and ITB launched by the first week of November and award of contract by the end of November. Construction period for six months
9 |  | By Khosh Dara Check Dam |  | Kandahar | Ghorak | By Khosh Village
10 |  | Ghul Khani Dara Check Dam |  | Kandahar | Ghorak | Ghul Khani Village
11 |  | Chy Dara Check Dam |  | Kandahar | Ghorak | Chy dar Village
12 |  | Khanjak Check Dam |  | Kandahar | Nesh | Khanjak Mastan Aka
13 | Package #24-AF2 WSM: Construction of 5 Check dams 1. Kashata Tangi, 2. Forodi, 3. Valary in Nawzad district, 4.Band Khawanin, and 5.Tykhoghi in Washer district of Helmand province. | Kashata Tangi Check Dam |  | Helmand | Nawzad | Kashata Tangi Village | Under Design | 2026-12-03 | 2027-06-01 | 125000 | Technical clearance is expected to receive at first week of November. PR raised and ITB launched by the second week of November and award of contract by the first week of December. Construction period for six months
14 |  | Forodi Check Dam |  | Helmand | Nawzad | Zoroji Village
15 |  | Valary Check Dam |  | Helmand | Nawzad | Valary village
16 |  | Band Khawanin check dam |  | Helmand | Washer | Shaposhta Village
17 |  | Tykhoghi Check Dam |  | Helmand | Washer | Koshki Spid Villag
18 | Package #25-AF2 WSM: Construction of Qali Gaz, Ghobana, and Nawi Kach Check dams, located in Mizana district of Zabul province. | Qali Gaz Check Dam |  | Zabul | Mizana | Qali Gaz Village | PR to be raised | 2026-11-25 | 2027-06-23 | 97679 | Construction period seven months including slack period.
19 |  | Ghobana Check Dam |  | Zabul | Mizana | Takhom Village
20 |  | Nawi Kach Check Dam |  | Zabul | Mizana | Landi Nawa Village
21 | Package #34-AF2 WSM: Construction of two Check dams, 1.Tawqus Sangaw and 2. Khalkoma in Kalbad and Ali Abad district of Kunduz province. | Tawqus Sangaw Check Dam | South/Kandahar | Kunduz | Kalbad | Tawqus Sangaw | ITB launched | 2026-10-31 | 2027-04-29 | 66984.5785 | Construction period six months including slack period (Dec-Jan). | Sep | 4 months
22 |  | Khalkoma Check Dam |  | Kunduz | Ali Abad | Khalkoma
23 | Package #33-AF2 WSM: Construction of 2 Check dams of Ala Taba-1 and Ala Taba-2 in Ablurz district of Balkh province. | Ala Taba-1 | North/Mazar | Balkh | Alburz | Chashma Gudar and Ala Tawa | PR to be raised | 2026-11-25 | 2027-05-24 | 55029 | Construction period six months including slack period (Dec-Jan).
24 |  | Ala Taba-2 |  | Balkh | Alburz | Sang Toda and Charso
24 |  | Total | [5 empty] | 11
Formulas:
Expected contract end date = [Expected contract award date]+270

## 5. Drip Irrigation systems
EMERGENCY FOOD SECURITY PROJECT (EFSP)
Component 2: Provision of Water and Resilience Services
OSRO/AFG/150/WBK IDA and OSRO/AFG/151/WBK ARTF
Yeal-1 Civil Works Procurement Plan (PP) for 2025
S N0 of the sub-project | Package / Contract name | No of Packages | WBK AF-2 Project Code | Sub-project Code No | Name of the sub-project | Location |  |  |  | Beneiciary/Farmer Name | Contact number | Estimated cost (USD) package wise | Estimated cost (USD)-Sub-project wise | Current status | Expected Contract award date | Expected Contract end date | Rmarks
[6 empty] | Region | Province | District | Village
Activity 2.1.b: Demonstration of high efficiency irrigation plot (drip irrigation)
West/Herat Region
1 | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 1.A | OSRO/AFG/150/WBK ARTF | HRT-BDS-A29 | Jakana Drip Irrigation schemes | West/Herat Region | Badghis | Moqur | Jakana | Sobhan | 7955947008 | 51600 | 7977.58 | Retendered (Re-ITB) | 2026-12-05 | 2027-05-30 | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. | ITB
2 |  |  |  | HRT-BDS -A30 | Baghak Drip Irrigation schemes |  | Badghis | Qala-e-Naw | Baghak | Edi Mohammad | 797795556 |  | 8943.67
3 |  |  |  | HRT-BDS- A31 | Kharistan Drip Irrigation schemes |  | Badghis | Moqur | Kharistan | Saifuddin | 792590111 |  | 9550.69
4 |  |  |  | HRT-GWR-A32 | Ahangaran Drip Irrigation schemes |  | Ghor | Firozkoh | Ahangaran | Haji Yaqoub | 778224593 |  | 5783.61
5 |  |  |  | HRT-GWR-A33 | Hamaye Khan Drip Irrigation schemes |  | Ghor | Dawlatyar | Hamaye khan | Haji Abdul Qaiyom | 798804829 |  | 6737.72
6 |  |  |  | HRT-HRT-A34 | Shadeh Olia Drip Irrigation Scheme |  | Herat | Zinda Jan | Shadeh Olia | Abdul Ghafour | 786500777 |  | 6110.88
7 |  |  |  | HRT-HRT-A35 | Shadeh Sofla Drip Irrigation Scheme |  | Herat | Zinda Jan | Shadeh Sofla | Ahmad Zia | 791308888 |  | 6495.85
8 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 1.B |  | HRT/HRT/A1/22 | Doormishi Drip Irrigation Scheme |  | Herat | Kushk e Rabat Sangi | Dormishi | Abdul Qayum | 789892603 | 57500 | 6771.3963 | Retendered (Re-ITB) | 2026-12-15 | 2027-04-29 | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. | ITB
9 |  |  |  | HRT/HRT/A1/23 | Khodrawan Drip Irrigation schemes |  | Herat | Kushk e Rabat Sangi | Khodrawan | Sadullah | 799878922 |  | 8259.9726
10 |  |  |  | HRT/HRT/A1/24 | Karez Naw Drip Irrigation schemes |  | Herat | Kushk e Rabat Sangi | Karez Naw | Ghulam Mahboob | 782308470 |  | 8066.2912
11 |  |  |  | HRT/HRT/A1/25 | Koklam Olia Drip Irrigation schemes |  | Herat | Kushk e Kohna | Koklam Olia | Fazl Ahmad | 774584144 |  | 9545.1912
12 |  |  |  | HRT/HRT/A1/26 | Koklam Sofla Drip Irrigation schemes |  | Herat | Kushk e Kohna | Koklam Sofla | Nesar Ahmad, Koklam | 771729725 |  | 7974.3058
13 |  |  |  | HRT/HRT/A1/27 | Joi Sultani Drip Irrigation schemes |  | Herat | Kushk e Kohna | Joy sultany | Habiburahman | 779154238 |  | 6417.2209
14 |  |  |  | HRT/HRT/A1/28 | Kushk Kohna Drip Irrigation schemes |  | Herat | Kushk e Kohna | Kushk Kohna | Mohammad Ibrahim | 776124090 |  | 10465.622
14 | Subtotal | [10 empty] | 109100 | 109100
East/Jalalabad Region
1 | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 2.A and B | OSRO/AFG/150/WBK ARTF | A: JLBD-NGR- DI – 01, 010 & 02 | 1. Abdul Qadir Drip Irrigation Scheme | East/Jalalabad | Laghman | Alishing | Darwesh Abad | Abdul Qadeer | 772091873 | 58290 | 13115.38 | Retendered (Re-ITB) | 2026-12-24 | 2027-05-23 | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- | ITB
2 |  |  |  |  | 2. Abdul Raqib drip Irrigation Scheme |  | Nangarhar | Pacheragam | Landi Khil | Abdur Raqeeb | 797947879
3 |  |  |  |  | 3. Nazar Khan Drip Irrigation Scheme |  | Nangarhar | Batikot | Heabat Khil | Nazar Khan | 729299520
4 |  |  |  | B: JLBD-NGR- DI – 03, 04, 05, 09, 06, 07, 08,11 & 12 | 4.Khas Kunar Drip Irrigation Scheme |  | Kunar | Khas Kunar | Chanchan | M. Nabi | 772230298 |  | 6935.5
6 |  |  |  |  | 5.Asmar Drip Irrigation Scheme |  | Kunar | Asmar | Baylaye | Malik Rostam | 777765237 |  | 4921.9
5 |  |  |  |  | 6.Manogai Drip Irrigation Scheme |  | Kunar | Manogai | Dabarzai | M. Afzal | 776488142 |  | 5530.7
7 |  |  |  |  | 7.Kunar University Drip irrigation Scheme |  | Kunar | Asadabad | Kunar University | Kunar University | 785940586 |  | 4255.5
8 |  |  |  |  | 8.Parun Drip irrigation Site |  | Nuristan | Parun | Ishtivi | Ehsanullah | 708542920 |  | 5725.3
9 |  |  |  |  | 9.Mateeullah Drip irrigation Site |  | Nuristan | Parun | Pronz | Mateeullah | 708425064 |  | 5216.26
10 |  |  |  |  | 10.Habibullah Drip irrigation Site |  | Nuristan | Barg-e-Matal | Barg-e-Matal Sharqi | Habibullah | 702353159 |  | 4194.9
11 |  |  |  |  | 11.Surkhrood Drip irrigation Site |  | Nangarhar | Sorkhrud | Fatih Abad | Ehsanullah | 731616020 |  | 4831.74
12 |  |  |  |  | 12.Khewa Drip irrigation Site |  | Nangarhar | Khewa | Sarjal | Ramin | 730773730 |  | 3562.46
12 | Subtotal | [10 empty] | 58290 | 58289.64
Central/Kabul Region
1 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 3 | OSRO/AFG/150/WBK ARTF | KBL-PRN-AF2-DI-(01, 02, 03) | Dahan Rabat Drip irrigation schemes | Central/Kabul | Parwan | Shikh Ali | Dahan Rabat | Abdullah | 765663708 | 17000 | 4250 | Retendered (Re-ITB) | 2026-12-15 | 2027-06-28 | Slack period from mid December to March 2026. Four months construction period.'- | ITB
2 |  |  |  |  | Lolenj Drip irrigation schemes |  | Parwan | Surkh Parsa | Lolenj | Ghulam Haider Shah | 776438295 |  | 8500
3 |  |  |  |  | Qala-e- Nasro Drip irrigation schemes |  | Parwan | Bagram | Qala-e- Nasro | Mohammad Waseem | 779942735 |  | 4250
4 |  |  |  | KBL-KBL-AF2-DI-(01, 02, 03, 04) | Goga Manda Drip irrigation schemes |  | Kabul | Sarobi | Goga manda | Hayatullah | 779843106 | 25500 | 4250 | Retendered (Re-ITB) | 2026-12-20 | 2027-06-30 | Slack period from mid December to March 2026. Four months construction period.''-
5 |  |  |  |  | Qafas Qala Drip irrigation schemes |  | Kabul | Khak-e-Jabar | Qafas Qala | Jalal | 776522552 |  | 8500
6 |  |  |  |  | Arghande Bala Drip irrigation schemes |  | Kabul | Paghman | Arghande bala | Mohammad Yousaf | 788802323 |  | 8500
7 |  |  |  |  | Zar Shakh Drip irrigation schemes |  | Kabul | Paghman | Zar Shakh | Khairullah Zia | 700170300 |  | 4250
8 |  |  |  | KBL-WRK-AF2-DI-(01, 02, 03, 04) | Khar Drip irrigation schemes |  | Wardak | Jaghatu | Khar | Mohammad Akbar | 707688539 | 25500 | 8500 | Retendered (Re-ITB) | 2026-12-25 | 2027-07-05 | Slack period from mid December to March 2026. Four months construction period.''-
9 |  |  |  |  | Madad Drip irrigation schemes |  | Wardak | Chack | Madad | Mohammad Qasim | 779977195 |  | 4250
10 |  |  |  |  | Dasht-e- Top Drip irrigation schemes |  | Wardak | Saydabad | Wardak university | Wardak University | 786278827 |  | 4250
11 |  |  |  |  | Durani Drip irrigation schemes |  | Wardak | Nirkh | Durani | Fazel Rahman | 785517326 |  | 8500
12 |  |  |  | KBL-KPS-AF2-DI-(01, 02, 03) | Alberoni University Drip irrigation schemes |  | Kapisa | Hesa-e- Awal Kohistan | Alberoni university | Alberoni University | 774332007 | 17000 | 4250 | Retendered (Re-ITB) | 2026-12-20 | 2027-06-30 | Slack period from mid December to March 2026. Four months construction period.'''-
13 |  |  |  |  | Nizam Khil Drip irrigation schemes |  | Kapisa | Tagab | Nizam khil | Najeebullah | 744751925 |  | 4250
14 |  |  |  |  | Reg-e-Rawan Drip irrigation schemes |  | Kapisa | Mahmood Raqi | Reg-e-Rawan | Reg-e-Rawa park | 728080465 |  | 8500
14 | Subtotal | [10 empty] | 85000 | 85000
Central Highland/Bamyan Region
1 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 4 | OSRO/AFG/150/WBK ARTF | BMN-DI-01 | Deraw drip Irrigation Systen | Central Highland/Bamayn | Daykundi | Miramor | Deraw | Mohammad Arif | 767855526 | 12872.54 | 6011.99 | Retentered (Re-ITB) | 2026-12-20 | 2027-06-28 | Slack period up to end March. Four months construction period starting from April 2026. | ITB
2 |  |  |  | BMN-D1-02 | Sarawood Drip Irrigation System |  | Daykundi | Miramor | Sarawood | Sayed Hassan | 765656907 |  | 3559.69
3 |  |  |  | BMN-D1-03 | Bagh Drip Irrigation System |  | Daykundi | Miramor | Bagh | Ghulam | 777181610 |  | 3300.86
4 |  |  |  | BMN-D1-04 | Ghaf Drip Irrigation |  | Daykundi | Shahristan | Ghaf | Mohammad Ibrahim | 776762200 | 11245.06 | 5880.43
5 |  |  |  | BMN-D1-05 | Khawja Chast )Drip irrigation Sysytem |  | Daykundi | Shahristan | Khwaja Chasht | Mohammad Hashim | 770887737 |  | 5364.63
6 |  |  |  | BMN-D1-06 | Safid Derakht 01 Drip Irrigtion System |  | Daykundi | Nilli | Safid Derakht, | Sayed Mohammad | 773703862 | 26271.23 | 5459.95
7 |  |  |  | BMN-D1-07 | Safid Derakht 02 Drip Irrigtion System |  | Daykundi |  | Safid Derakht, | Ghulam Hussain | 775655216 |  | 3764.17
8 |  |  |  | BMN-D1-08 | Sorkh Nawor Drip Irrigation |  | Daykundi |  | Sorkh Nawor | Reza | 776278014 |  | 5564.4
9 |  |  |  | BMN-D1-09 | Gorg Kosht Drip Irrigation system |  | Daykundi |  | Gorg Koshta | Ahmad | 772928540 |  | 3484.2
10 |  |  |  | BMN-D1-10 | Hejdi Drip irrigatio System |  | Daykundi |  | Hijdi | Mohammad Ali | 770700885 |  | 4425.06
11 |  |  |  | BMN-D1-11 | Khawalak Drip irrigatio SYSTEM |  | Daykundi |  | Khawalak | Ali Dost | 771218803 |  | 3573.45
12 |  |  |  | BMN-D1-12 | Peshang Drip Irrigation system |  | Bamyan | Sayghan | Peshang | Abdul Rahman | 767464384 | 3856.11 | 3856.11
12 | Subtotal | [10 empty] | 54244.94 | 54244.94
Southeast/Gardez Region
1 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 5 | OSRO/AFG/151/WBK ARTF | GDZ-D1-10 | Hassan Khil-A Drip Irrigation Scheme | Gardez | Paktya | Ahmad Aba | Machalghu | Hasan Khil | 775594515 | 21250 |  | Retendered (Re-ITB) | 2026-12-25 | 2027-07-03 | Slack period up to end March. Four months construction period starting from April 2026. | ITB
2 |  |  |  | GDZ-D1-11 | Hassan Khil- B Drip Irrigation Scheme |  | Paktya | Ahmad Aba | Machalghu | Zabihullah | 778010025
3 |  |  |  | GDZ-D1-12 | Ghafoor khil Drip irrigation Scheme |  | Paktya | Center | Gafoor khil | Salam Jan | 773200524
4 |  |  |  | GDZ-D1-13 | Paktia University Drip irrigation Scheme |  | Paktya | Gardez_center | Beland Mazal | Mohammad Rasool Gharani | 777303089
5 |  |  |  | GDZ-D1-04 | Nughi Drip Irrigation Scheme |  | Ghazni | Center | Nughi | Hakim Khan | 796816848 | 17000
6 |  |  |  | GDZ-D1-05 | Deyak Drip Irrigation Scheme |  | Ghazni | Deyak | Ramaki | Naser Khan | 797499580
7 |  |  |  | GDZ-D1-06 | Basana Drip irrigation Scheme |  | Ghazni | Andar | Basana | Mohammad Naim | 793541496
8 |  |  |  | GDZ-D1-07 | Nawe Patana Drip Irrigation Scheme |  | Pakteka | Sharana | Patana | Ghazi Khan | 773003296 | 12750
9 |  |  |  | GDZ-D1-08 | Sultani Drip Irrigation Scheme |  | Pakteka | Sarhawza | Sultani | Akhtar Mohammad | 744243215
10 |  |  |  | GDZ-D1-09 | Gir Drip irrigation Scheme |  | Pakteka | Sharana | Gari | Fazal Din | 776280676
11 |  |  |  | GDZ-D1-01 | Milma Kot Bagh Drip Irrigation Schem |  | Khost | Matoon | Milma Kot Bagh | Saifullah | 766949790 | 21250
12 |  |  |  | GDZ-D1-02 | Sahra Bagh Drip Irrigation Scheme |  | Khost | Matoon | Sahra bagh | Gafoor Jan | 770813301
13 |  |  |  | GDZ-D1-03 | Agriculture Research Drip Irrigation scheme |  | Khost | Matoon | Agriculture Feseach Farm | Hazrat Wali | 778804065
14 |  |  |  | GDZ-D1-14 | Logar University Drip Irrigation Scheme |  | Logar | Pole Alam | Logar University | Islam Gul | 764716588 | 12750
15 |  |  |  | GDZ-D1-15 | Dabar Allu Drip Irrigation Scheme |  | Logar | Charkh | Dabar Allu | Mohammad Akbar | 767216335
15 | Subtotal | 5 |  |  | Sub total | [6 empty] | 85000
South/Kandahar Region
1 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. |  | OSRO/AFG/150/WBK ARTF |  | Mohmad Drip irrigation schemes | South/Kandahar | Kandahar | Daman | Mohmand |  |  | 25500 | 4250 | Design under WRI review | 2027-01-25 | 2027-06-24 | Five months for the construction. | WRI
2 |  |  |  |  | Garmaw Kali Drip irrigation schemes |  | Kandahar | Panjwai | Garmaw Kali |  |  |  | 8500
3 |  |  |  |  | Serdagh Kali Drip irrigation schemes |  | Kandahar | Naish | Serdagh Kali |  |  |  | 4250
4 |  |  |  |  | Garmaw Kali Drip irrigation schemes |  | Kandahar | Shah Wali Kot | Garmaw kali |  |  |  | 8500
5 |  |  |  |  | Rud Kali Drip irrigation schemes |  | Zabul | Tarnak- Jaldak | Rud Kali |  |  | 21250 | 8500
6 |  |  |  |  | Omarzai Drip irrigation schemes |  | Zabul | Seyure | Omerzai |  |  |  | 4250
7 |  |  |  |  | Bahu Kalai Drip irrigation schemes |  | Zabul | Seyure | Bahu Kali |  |  |  | 8500
8 |  |  |  |  | Kona Kala Drip irrigation schemes |  | Urozgan | Terinkot | Kona Kala |  |  | 17000 | 4250
9 |  |  |  |  | Khair Abad Drip irrigation schemes |  | Urozgan | Terinkot | Khair Abad |  |  |  | 8500
10 |  |  |  |  | Badam Kalai Drip irrigation schemes |  | Helmand | Nawzad | Badam Kali |  |  |  | 4250
11 |  |  |  |  | Loy Razi Drip irrigation schemes |  | Nemroz | Khashrod | Loy Razi |  |  | 12750 | 4250
12 |  |  |  |  | Firozi Drip irrigation schemes |  | Nemroz | Delaram | Firozi Village |  |  |  | 8500
12 | Subtotal | 4 |  |  | Sub total | [6 empty] | 76500 | 76500
Northeast/Kunduz Region
1 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 9 | OSRO/AFG/151/WBK ARTF | KDZ-DI-01 | Khoja Bolak Drip Irrigation Scheme | Northeast/Kunduz | Kunudz | Khan Abad | Khoja Bolak | Mohammad Qasim | 0794833452, 0774092600 | 25500 | 8500 | Design under WRI review | 2027-01-25 | 2027-08-03 | Construction period five months starting from March 2027.
2 |  |  |  | KDZ-DI-02 | Shamba Bazar Drip Irrgiatation Scheme |  | Kunduz | Dashte Archi | Shamba Bazar | Shamsurahman | 0744605625, 0798546814 |  | 4250 |  |  |  |  | WRI
3 |  |  |  | KDZ-DI-03 | Haji Atta Khan Drip Irrgiatation Scheme |  | Kunduz | Chahar Dara | Haji Atta Khan Masjid | Haji Hamayoon Salimi | 0708752022, 0777310520 |  | 8500
4 |  |  |  | KDZ-DI-04 | Masjid Dr. Shafiq Mamakhail Drip Irrigation Scheme |  | Kunduz | Chahar Dara | Mamakhail | Ziaurrahman Mohammadi | 700701193 |  | 4250
5 |  |  |  | KDZ-DI-05 | Tilajat Drip Irrigation Scheme |  | Takhar | Rustaq | Tilajat Baloch | Fida Mohammad | 0700601104, 0789943601 | 12750 | 8500
6 |  |  |  | KDZ-DI-06 | Chaqul Drip Irrigation Scheme |  | Takhar | Baharak | Chaqul | Nasratullah | 795468372 |  | 4250
7 |  |  |  | KDZ-DI-07 | Sara-e-Gharbi Drip Irrigation Scheme |  | Badakhshan | Kishem | Sara-e-Gharbi | Haji Jamal | 778106352 | 8500 | 8500
8 |  |  |  | KDZ-DI-08 | Khoja Alwan Drip Irrigation Scheme |  | Baghlan | Dand Ghori | Khoja Alwan | Haji Amir Gul | 0708152952, 0773665565 | 12750 | 8500
9 |  |  |  | KDZ-DI-09 | Qatar Fateh Drip Irrigation Scheme |  | Baghlan | Dahna-e-Ghori | Qatar Fateh | Haji Nazar Gul | 703279863 |  | 4250
9 | Subtotal | 5 |  |  | Sub total | [6 empty] | 59500 | 59500
North/Mazar Region
1 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 10 | North/Mazar |  | Uch Tepa drip irrigation | North/Mazar | Balkh | Dehdadi | Uch Tepa |  |  | 34000 | 8500 | Design under WRI review | 2026-01-20 | 2026-07-29 | Construction period five months starting from March 2027. | WRI
2 |  |  |  |  | Balkh university drip irrigation |  | Balkh | Mazar-e-Sharif | Center |  |  |  | 4250
3 |  |  |  |  | Balkh Agriculture and Livestock drip irrigation 3 |  | Balkh | Mazar-e-Sharif | Center |  |  |  | 8500
4 |  |  |  |  | Dehdadi drip irrigation |  | Balkh | Dehdadi | Sher Abad Olya |  |  |  | 4250
5 |  |  |  |  | Charkent drip irrigation |  | Balkh | Charkent | Modafean Payen |  |  |  | 8500
6 |  |  |  |  | Maimana drip irrigation |  | Faryab | Khwaja Sabz Posh | Tepa Qishlaq |  |  | 4250 | 4250
7 |  |  |  |  | Hassan Tabin drip irrigation |  | Jawzjan | Sheberghan | Hassan Tabin |  |  | 8500 | 8500
8 |  |  |  |  | Imam Jaffar drip irrigation |  | Sari Pul | Sayed Abad | Imam Jaffar |  |  | 17000 | 4250
9 |  |  |  |  | Had Bakhshy drip irrigation |  | Sari Pul | Sayed Abad | Had Bakhshy |  |  |  | 8500
10 |  |  |  |  | Nawabad Imam drip irrigation |  | Sari Pul | Center | Nawabad Imam Kalan |  |  |  | 4250
11 |  |  |  |  | Hazrat-e-Sultan drip irrigation |  | Samangan | Hazrat-e-Sultan | Asiabad |  |  | 12750 | 8500
12 |  |  |  |  | Aybak drip irrigation |  | Samangan | Aybak | Joy Zindan |  |  |  | 4250
12 | Subtotal | 6 |  |  | Sub total | [6 empty] | 76500 | 76500
100 | Grand total | [10 empty] | 604134.94 | 519134.58
Formulas:
Expected Contract end date = [Expected Contract award date]+176

## 6. Supply and delivery of LLL
EMERGENCY FOOD SECURITY PROJECT (EFSP)
Component 2: Provision of Water and Resilience Services
OSRO/AFG/150/WBK IDA and OSRO/AFG/151/WBK ARTF
A. Procurement and distribution plan of 50 LLL units under EFSP-AF2
S# | Region | Number of LLL allotted units | Expected date of PO award | Expected date of supply | Expected date of distribution | Remarks
1 | Kabul | 5 | 2026-10-30 | 2026-12-30 | 2027-01-31 | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed.
2 | Jalalabad | 5
3 | Herat | 9
4 | Kandahar | 5
5 | Kunduz | 9
6 | Mazar | 9
7 | Bamiyan | 1
8 | Gardiz | 7
| Total | 50
B. Detailed List of 50 planned LLLs under EFSP -AF2
S.No | Name of Rehabilitated Irrigation Scheme (IS) | Region | Province | District | LLL Allocated # | Expected date of PO award | Expected date of supply | Expected date of distribution | Remarks
1 | Kamary Canal | Kabul | Kabul | Qarabagh | 1 | 2026-10-30 | 2026-12-30 | 2027-01-31 | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries.
2 | Zema Canal | Kabul | Kabul | Kalakan | 1
3 | Qala-e-Ahmad Big Canal | Kabul | Kapisa | Nijrab | 1
4 | Mandaliat -e-Tanor canal | Kabul | Midan Wardak | Hesa Awal Behsood | 1
5 | Eshq Abad canal | Kabul | Parwan | Jabul Saraj | 1
6 | Khas kunar irrigation scheme | Jalalabad | Kunar | Khas kunar | 1
7 | Badiabad irrigation scheme | Jalalabad | Laghman | Alingar | 1
8 | Cheknawar irrigation scheme | Jalalabad | Nangarhar | Lalpoora | 1
9 | Patikharkay irrigation scheme | Jalalabad | Nangarhar | Khogiani | 1
10 | Pachajoy irrigation scheme | Jalalabad | Laghman | Mehtherlam | 1
11 | Abdul Baqi irrigation scheme | Mazar | Balklh | Chimtal | 1
12 | Mulla Omar irrigation scheme | Mazar | Balklh | Chimtal | 1
13 | Kushkak irrigation scheme | Mazar | Samangan | Dara-e-Suf-e-Bala | 1
14 | Chela Mazar irrigation scheme | Mazar | Samangan | Dara-e-Suf-e-Payeen | 1
15 | Bahr-e-Ameq irrigation scheme | Mazar | Sar-E-Pul | Sozma Qala | 1
16 | Hashtman Canal Irrigation scheme | Mazar | Faryab | Qaisar | 1
17 | Qashqasai Canal Irrigation scheme | Mazar | Faryab | Qaisar | 1
18 | Joy Shahr Canal Irrigation scheme | Mazar | Jawzjan | Aqcha | 1
19 | Khanum Arabia Canal Irrigation scheme | Mazar | Jawzjan | Faizabad | 1
20 | Abi Aruq and Shaitan Aruq Irrigation Schemes | Kundoz | Takhar | Khwaja Ghar | 1
21 | Khar Kar and Sayed Miran IS | Kundoz | Takhar | Eshkamish | 1
22 | Shahidan, Dasht-e Lajam IS | Kundoz | Baghlan | Tala Wa Barfak | 1
23 | Khambilan, Nahr-e-Saleh and Dara-e-Bazar IS | Kundoz | Baghlan | Firing | 1
24 | Sardar Ha IS | Kundoz | Baghlan | Deh Sala | 1
25 | Dagh Aruq Irrigation Scheme | Kundoz | Kunduz | Char Dara | 1
26 | Boghos Qum Irrigation Scheme | Kundoz | Kunduz | Char Dara | 1
27 | Teshkhan Irrigation Scheme | Kundoz | Badakhshan | Ishkashim | 1
28 | Khuspak-e-Markazi | Kundoz | Badakhshan | Ishkashim | 1
29 | Urdokas irrigation scheme | Kandahar | Kandahar | Shawalikot | 1
30 | Sarkay Lazhey irrigation scheme | Kandahar | Kandahar | Spin Boldak | 1
31 | Patab irrigation scheme | Kandahar | Urozgan | Khas Urozgan | 1
32 | Nahri Siraj irrigation scheme | Kandahar | Helamand | Nahri Siraj | 1
33 | Shawarooz irrigation scheme | Kandahar | Zabul | Khak e Afghan | 1
34 | Zard Sang Irrigation Scheme | Bamiyan | Bamyan | Bamiyan | 1
35 | Qala-E-Wazir Irrigation Scheme | Gardiz | Logar | Qala-E-Wazir | 1
36 | Khwaja Angor Irrigation Scheme | Gardiz | Logar | Kharwar | 1
37 | Welgai Irrigation Scheme | Gardiz | Khost | Matoon | 1
38 | Mulakh Irrigation Scheme | Gardiz | Paktika | Yousif Khail | 1
39 | Noghi Irrigation Scheme | Gardiz | Ghazni | Ghazni | 1
40 | Shir Abad Irrigation Scheme | Gardiz | Ghazni | Qarabagh | 1
41 | Drang Irrigation Scheme | Gardiz | Paktya | Zurmat | 1
42 | Shaflan Irrigation Canal | Herat | Herat | Pashton Zarghon | 1
43 | Joi Bazar irrigation scheme | Herat | Herat | Obe | 1
44 | Yar Mohammad Khan Irrigation Scheme | Herat | Herat | Obe | 1
45 | Ali Mansoor Irrigation Scheme | Herat | Herat | Karukh | 1
46 | Sang Bast Irrigation Scheme | Herat | Herat | Zinda Jan | 1
47 | Naw Deh Irrigation Canal | Herat | Farah | Farah | 1
48 | Joi Ganj Irrigation Scheme | Herat | Badghis | Balamorghab | 1
49 | Joi Kar Irrigation Scheme | Herat | Badghis | Balamorghab | 1
50 | Joi Baratha Ulya IS | Herat | Ghor | Dawlatyar | 1
Note: The beneficiary selection is underway and will be finalized prior to distribution by December 2026.

## 7. Agroforestry Saplings-seeds
EMERGENCY FOOD SECURITY PROJECT (EFSP)
Component 2: Provision of Water and Resilience Services
OSRO/AFG/150/WBK IDA and OSRO/AFG/151/WBK ARTF
Procurement and distribution of Agroforestry Saplings and Seeds 2026/27
S# | Region | Number of saplings | Qty of Seeds (kg) | Expected date of award for the contracts | Expected date of completion for the contracts | Remarks
1 | Central/Kabul | 20000 | 850 | 4/30/2026 saplings and 11/30/2026 seeds | 2027-04-01 | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026
2 | East/Jalalabad | 48000 | 850
3 | West/Herat | 15000 | 940
4 | South/Kandahar | 20000 | 850
5 | North-east/Kunduz | 25000 | 850
6 | North/Mazar | 15000 | 1250
7 | Central highland/Bamyan | 20000 | 870
8 | South-east/Gardez | 52000 | 610
| Total | 215000 | 7070
S# | Region | Province | District | Number of Saplings | Qty of seeds(kg) | Expected Date of award for the contracts | Expected Date of Completion for the Contract | Remarks
1 | Northeast/Kunduz | Takhar | Bangi | 8500 | 234 | 4/30/2026 saplings and 11/30/2026 seeds | 2027-04-01 | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026
2 | Northeast/Kunduz | Baghlan | Banu | 8316 | 121
3 | Northeast/Kunduz | Badakhshan | Wardoj | 8184 | 495
4 | West/Herat | Ghor | Allahyar | 5000 | 363
5 | West/Herat | Ghor | Shahrak | 10000 | 487
6 | West/Herat | Herat | Koshk-e-kohna | 0 | 40
7 | West/Herat | Herat | Rabat Sangi | 0 | 30
8 | West/Herat | Badghis | Sang Atish | 0 | 20
9 | Southern/Kandahar | Helmand | Nawzad | 10032 | 462
10 | Southern/Kandahar | Oruzgan | Tarinkot | 9968 | 388
11 | Central Highland/Bamyan | Daikundi | Khedir | 6000 | 477
12 | Central Highland/Bamyan | Daikundi | Sharistan | 7000 | 195.5
13 | Central Highland/Bamyan | Daikundi | Meramour | 7000 | 197.5
14 | Southeastern/Gardez | Logar | Azra | 15000 | 242
15 | Southeastern/Gardez | Paktia | Zazi Aryoub | 9919 | 132
16 | Southeastern/Gardez | Paktia | Zurmat | 8581 | 66
17 | Southeastern/Gardez | Paktika | Surobi | 3500 | 44
18 | Southeastern/Gardez | Khost | Qalander | 7920 | 44
19 | Southeastern/Gardez | Khost | Musa Khil | 7080 | 82
20 | Central /Kabul | Kabul | Surubi | 10000 | 250
21 | Central /Kabul | Panjsher | Unaba | 4000 | 250
22 | Central /Kabul | Panjsher | Khinj | 3000 | 150
23 | Central /Kabul | Panjsher | Paryan | 3000 | 200
24 | Eastern | Nangarhar | Pachiragam | 11792 | 442
25 | Eastern | Laghman | Alishing | 12056 | 174
26 | Eastern | Nuristan | Kamdish | 24152 | 234
27 | Northern/Mazar | Jawzgan | Sheberghan | 3250 | 0
28 | Northern/Mazar | Faryab | Khoja Sabz Posh | 3250 | 154
29 | Northern/Mazar | Faryab | Almar | 0 | 154
30 | Northern/Mazar | Balkh | Dehdadi | 2400 | 21
31 | Northern/Mazar | Balkh | Nahre Shahi | 0 | 246
32 | Northern/Mazar | Balkh | Marmul | 0 | 41
33 | Northern/Mazar | Balkh | Charkent | 0 | 31
34 | Northern/Mazar | Balkh | Kishendeh | 0 | 46
35 | Northern/Mazar | Sari Pul | Center | 4800 | 259
36 | Northern/Mazar | Sari Pul | Kohistanat | 0 | 30
37 | Northern/Mazar | Sari Pul | Balkhab | 0 | 30
38 | Northern/Mazar | Samangan | Hazrat-e-Sultan | 1300 | 65
39 | Northern/Mazar | Samangan | Aybak | 0 | 173
| Total |  |  | 215000 | 7070