## 00_How_to_Use
Construction Works Scheme Tracker
Emergency Food Security Project (EFSP) · Component 2: Water and Resilience Services · WBK/AF-2 · How to use and how to add or remove columns and domains
What this workbook does
Purpose | Track every construction scheme from design through handover. Each scheme is one row. Each pipeline step has its own date. Excel then calculates how many days it took to move from one step to the next, how long the scheme has sat in the current step, and the total days from the first date to the last.
Sheets | 01_Scheme_Tracker is the working register (one row per sub-project). 02_Dashboard summarises counts and average durations. 03_Package_Summary rolls every contract package to one row (Package #8 and #10 sit here as single packages). 10_By_Contractor lists each company once, with how many unique contracts it holds (Zahid Saeed / ZSCC is one awarded contract covering four canals). 11_Package_Status counts unique packages in each pipeline step and shows how each status is shared across Watershed Management, Irrigation Scheme, Drip Irrigation, LLL, and Agroforestry. 04_Date_Rules explains how each date is used and how schedule health is coloured. 05_Example_Filled shows two worked examples so you can see the day-count formulas. 06_Status_Pipeline is the ordered list of steps. 07_Domains holds dropdown lists (major intervention, sub-type, donor, project, region, Awarded / Not awarded). 08_Geography holds province and district lists. 09_Lookups maps region/province names to those lists.
Daily use
Add a scheme | Go to 01_Scheme_Tracker and type in the next empty row. Choose Major intervention first (Watershed Management, Irrigation Scheme, Drip Irrigation, Agroforestry saplings / seeds, or Laser Land Leveler), then Intervention sub-type (protection wall, irrigation canal, check dam, and so on). Dropdowns are also attached for Project, Region, Province, District, Donor, Awarded / Not awarded, and Reported Status. | 01_Scheme_Tracker
Packages that cover several sites | One Package / Contract Name can cover several canals or check dams in different districts. Keep one row per sub-project (location) so province, district, village, and progress stay honest. Give every row of that contract the same Package ID and the same Package / Contract Name. Sub-project in package shows 1 of 4, 2 of 4, … Example: Package #8-AF2 IS (Khas Kunar Lower canal + Bahrabad canal) is two rows, one Package ID. Package #10-AF2 IS (Baraki, Darbal, Nawikhar, Mangali) is four rows, one Package ID. On the tracker, extra rows of the same package are grouped — use the outline +/- at the left margin to collapse them. 03_Package_Summary lists each package once. | 01_Scheme_Tracker / 03_Package_Summary
Find contracts awarded to one company | The contractor name is repeated on every sub-project of that contract. Filtering Contractor Name on 01_Scheme_Tracker for 'Zahid Saeed Engineering and Construction Company (ZSCC)' shows four rows — those are four canals on the same Package #10 contract (057/2025), not four contracts. To see unique contracts: open 10_By_Contractor and filter the company (ZSCC = 1 awarded contract, 4 sub-projects), or open 03_Package_Summary and filter Contractor Name. Count Package IDs / Contract Numbers, not the number of tracker rows. | 10_By_Contractor / 03_Package_Summary
How many packages are in each status | 02_Dashboard counts sub-projects. That overstates a step when one contract has many sites (50 LLL units and 39 agroforestry rows are each one package still Under Awarding). Open 11_Package_Status for unique-package counts: Under Design, Under Review of WRI, Under LTO Review, PR to be Raised, ITB Launched, Retendered, Technical Evaluation, Under Awarding, Awarded, Under Construction, Completed. A package takes the least-advanced status of its unfinished sites. It is Completed only when every sub-project is completed. Filter Package status on 03_Package_Summary to list them. | 11_Package_Status
Enter status dates | When a scheme reaches a step, type that day's date in the matching 'Date:' column (for example Date: Under Design, Date: ITB Launched). Use a real date, not text. Current Status then switches automatically to the latest dated step. If no dates are entered yet, Current Status falls back to Reported Status. | Section 4 of the tracker
Awarded date and contract duration | Type the contract-signature (or notice of award) date in the Date: Awarded column in section 4. The Awarded Date field in section 2 copies it automatically. Contract Duration (months) is the period in the contract. Planned End Date is calculated with EDATE(Awarded Date, duration). Physical Works Progress % is 0–100. Contractor Name and Contract Number are free text. | Sections 2 and 4 of the tracker
Reading the day counts | Each 'Days … → …' column is the number of days from the previous filled date to this step's date. If a step is skipped, the count still uses the last previous date that was filled. 'Days in current status' is TODAY minus the latest status date (this number changes every day). 'Total days first → last step' is last filled date minus first filled date. 'Days over target this step' is days in current status minus the target days set on 06_Status_Pipeline (blank if there is no target). | Sections 3 and 5
Schedule health colours | Schedule health is calculated from planned dates and TODAY() — it changes every calendar day. GREEN — On track, or completed. AMBER — At risk / close to off track: the planned award or contract end is within 30 days. RED — Behind: today is after the expected award date (Not awarded) or after the contract end date (Awarded), or physical progress is more than 15 percentage points behind the share of the contract period that has already elapsed. 'Days vs planned date' is days remaining (positive) or days overdue (negative). Full rules, including which date each condition uses, are on 04_Date_Rules. | 04_Date_Rules
What a status date means | Type the calendar day the scheme reached that step (the day the step started or was achieved), not a forecast. Leave later steps blank until they happen. Current Status is the latest dated step. If no dates are entered yet, Current Status uses Reported Status. Awarded Date copies Date: Awarded. Planned End Date uses the contract end if you typed one, otherwise EDATE(Awarded Date, duration months). Not awarded rows are judged against Expected award date (and, if that is blank, the expected end). Awarded rows are judged against the planned / contract end and against physical progress over elapsed time. | 04_Date_Rules
Add or remove domains (dropdown values)
Add an intervention type, donor, project, or region | Open 07_Domains. Type the new value in the first empty cell at the bottom of that column. Do not leave a blank row in the middle of the list. The dropdowns expand automatically (named ranges use COUNTA). You do not need to re-run the generator for this. | 07_Domains
Remove a domain value | Delete the cell on 07_Domains (or 08_Geography). Existing scheme rows that already use that value keep showing it; new rows will no longer offer it in the dropdown. | 07_Domains / 08_Geography
Add a province | 1) On 08_Geography, under the correct region code column in the province block, type the province name. 2) Add a new district column for that province in the district block (copy an adjacent column). 3) On 09_Lookups, add a row: Province name ¦ Dist_<Province> named range. 4) Define the named range Dist_<Province> (Formulas → Name Manager) pointing at the district cells. The reliable alternative is to add the province in tracker_config.py GEOGRAPHY and run generate_tracker.py. | 08_Geography + 09_Lookups
Add a district | On 08_Geography find the province column in the district block and type the district in the next empty cell. The Dist_ named range grows automatically. No other change is required. | 08_Geography
Add or remove status steps (the tracking pipeline)
Add a step at the end (no script) | Open 06_Status_Pipeline. Spare slots are already reserved at the bottom. Type the new status name, a short name, a description, and optional target days in the first spare row. The matching Date column header on 01_Scheme_Tracker updates itself. Start entering dates in that column. Duration headers also pick up the new name. | 06_Status_Pipeline spare slots
Add a step in the middle, or remove a step | Changing order affects rows that already have dates, because dates sit in fixed columns. Preferred method: edit STATUS_PIPELINE in tracker_config.py (add, remove, or reorder dicts) and run python3 generate_tracker.py. That rebuilds date columns, duration formulas, dropdowns, and the dashboard. Copy any dates you already typed into a backup first — regenerating replaces the workbook file. | tracker_config.py
Hide a column you do not need | On 01_Scheme_Tracker, select the column → right-click → Hide. Do not delete formula columns (sections 3 and 5) or the tracker will break. Hidden columns can be unhidden later. | 01_Scheme_Tracker
Add an extra data column (GPS, engineer, photo link, …) | Insert a column inside section 1 (identity) or section 2 (contract), not inside the date or duration blocks. Give it a header in row 3. Filters will include it after you re-apply AutoFilter if needed. To make it permanent in future rebuilds, append a tuple to IDENTITY_COLUMNS or CONTRACT_COLUMNS in tracker_config.py. | 01_Scheme_Tracker / tracker_config.py
Rules that keep the numbers honest
Dates must move forward | A later step should not have an earlier date than a previous step. Negative day-counts mean the dates need checking.
One row = one sub-project; one Package ID = one contract | If a package has three check dams or four canals, use three or four rows. Do not merge those rows — AutoFilter and sort would break. Repeat the Package / Contract Name and Package ID on every row. Cost may be per sub-project (as in the master file) or only on the first row. | 03_Package_Summary
Grey cells are formulas | Do not type over Current Status, Planned End Date, day-count columns, or helper columns. White cells are inputs.
DEMO rows | 05_Example_Filled is for learning. Do not copy those dates into official reports. | 05_Example_Filled
Status pipeline (default)
Step | Status | What it means | Target days
1 | Under Design | Detailed design, surveys, and drawings are being prepared. | 30
2 | Under Review of WRI | Water Resources / WRI is reviewing the design package. | 14
3 | Under LTO Review | Legal / LTO clearance of the package. | 10
4 | PR to be Raised | Purchase request / procurement request still to be raised. | 10
5 | ITB Launched | Invitation to Bid has been issued. | 21
6 | Retendered (Re-ITB) | Previous bid failed or was cancelled; invitation re-issued. | 21
7 | Under Technical Evaluation | Bids are under technical evaluation. | 14
8 | Under Awarding | Award recommendation, negotiations, and approval. | 14
9 | Awarded | Contract signed / notice of award issued. | —
10 | Under Construction | Contractor is mobilised and physical works are ongoing. | 150
11 | Completed / Handover | Works completed and handed over. | —

## 01_Scheme_Tracker
Construction Works Scheme Tracker · live register — type dates in section 4
1. Scheme identity | [15 empty] | 2. Contract and physical progress | [11 empty] | 3. Live status and schedule health (calculated) | [5 empty] | 4. Status dates — enter the date each step was reached | [13 empty] | 5. Days between steps (calculated)
SN | Package ID | Package / Contract Name | Sub-project in package | Scheme ID | Sub-project / scheme name | Major intervention | Intervention sub-type | Project Name | Region | Province | District | Village | Donor | Awarded / Not awarded | Source sheet | Contractor Name | Contract Number | Contract Cost (USD) | Awarded Date | Expected award date | Contract Duration (months) | Contract / expected end date | Planned End Date | Actual completion date | Physical Works Progress % | Reported Status | Remarks | Current Status (auto) | Days in current status | Total days first → last step | Days over target this step | Schedule health | Days vs planned date | IF('06_Status_Pipeline'!B3="","(spare slot 1)","Date: "&'06_Status_Pipeline'!B3) | IF('06_Status_Pipeline'!B4="","(spare slot 2)","Date: "&'06_Status_Pipeline'!B4) | IF('06_Status_Pipeline'!B5="","(spare slot 3)","Date: "&'06_Status_Pipeline'!B5) | IF('06_Status_Pipeline'!B6="","(spare slot 4)","Date: "&'06_Status_Pipeline'!B6) | IF('06_Status_Pipeline'!B7="","(spare slot 5)","Date: "&'06_Status_Pipeline'!B7) | IF('06_Status_Pipeline'!B8="","(spare slot 6)","Date: "&'06_Status_Pipeline'!B8) | IF('06_Status_Pipeline'!B9="","(spare slot 7)","Date: "&'06_Status_Pipeline'!B9) | IF('06_Status_Pipeline'!B10="","(spare slot 8)","Date: "&'06_Status_Pipeline'!B10) | IF('06_Status_Pipeline'!B11="","(spare slot 9)","Date: "&'06_Status_Pipeline'!B11) | IF('06_Status_Pipeline'!B12="","(spare slot 10)","Date: "&'06_Status_Pipeline'!B12) | IF('06_Status_Pipeline'!B13="","(spare slot 11)","Date: "&'06_Status_Pipeline'!B13) | IF('06_Status_Pipeline'!B14="","(spare slot 12)","Date: "&'06_Status_Pipeline'!B14) | IF('06_Status_Pipeline'!B15="","(spare slot 13)","Date: "&'06_Status_Pipeline'!B15) | IF('06_Status_Pipeline'!B16="","(spare slot 14)","Date: "&'06_Status_Pipeline'!B16) | IF(AND('06_Status_Pipeline'!B3="",'06_Status_Pipeline'!B4=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B3="","(prev)",'06_Status_Pipeline'!B3)&" → "&IF('06_Status_Pipeline'!B4="","(next)",'06_Status_Pipeline'!B4)) | IF(AND('06_Status_Pipeline'!B4="",'06_Status_Pipeline'!B5=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B4="","(prev)",'06_Status_Pipeline'!B4)&" → "&IF('06_Status_Pipeline'!B5="","(next)",'06_Status_Pipeline'!B5)) | IF(AND('06_Status_Pipeline'!B5="",'06_Status_Pipeline'!B6=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B5="","(prev)",'06_Status_Pipeline'!B5)&" → "&IF('06_Status_Pipeline'!B6="","(next)",'06_Status_Pipeline'!B6)) | IF(AND('06_Status_Pipeline'!B6="",'06_Status_Pipeline'!B7=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B6="","(prev)",'06_Status_Pipeline'!B6)&" → "&IF('06_Status_Pipeline'!B7="","(next)",'06_Status_Pipeline'!B7)) | IF(AND('06_Status_Pipeline'!B7="",'06_Status_Pipeline'!B8=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B7="","(prev)",'06_Status_Pipeline'!B7)&" → "&IF('06_Status_Pipeline'!B8="","(next)",'06_Status_Pipeline'!B8)) | IF(AND('06_Status_Pipeline'!B8="",'06_Status_Pipeline'!B9=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B8="","(prev)",'06_Status_Pipeline'!B8)&" → "&IF('06_Status_Pipeline'!B9="","(next)",'06_Status_Pipeline'!B9)) | IF(AND('06_Status_Pipeline'!B9="",'06_Status_Pipeline'!B10=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B9="","(prev)",'06_Status_Pipeline'!B9)&" → "&IF('06_Status_Pipeline'!B10="","(next)",'06_Status_Pipeline'!B10)) | IF(AND('06_Status_Pipeline'!B10="",'06_Status_Pipeline'!B11=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B10="","(prev)",'06_Status_Pipeline'!B10)&" → "&IF('06_Status_Pipeline'!B11="","(next)",'06_Status_Pipeline'!B11)) | IF(AND('06_Status_Pipeline'!B11="",'06_Status_Pipeline'!B12=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B11="","(prev)",'06_Status_Pipeline'!B11)&" → "&IF('06_Status_Pipeline'!B12="","(next)",'06_Status_Pipeline'!B12)) | IF(AND('06_Status_Pipeline'!B12="",'06_Status_Pipeline'!B13=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B12="","(prev)",'06_Status_Pipeline'!B12)&" → "&IF('06_Status_Pipeline'!B13="","(next)",'06_Status_Pipeline'!B13)) | IF(AND('06_Status_Pipeline'!B13="",'06_Status_Pipeline'!B14=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B13="","(prev)",'06_Status_Pipeline'!B13)&" → "&IF('06_Status_Pipeline'!B14="","(next)",'06_Status_Pipeline'!B14)) | IF(AND('06_Status_Pipeline'!B14="",'06_Status_Pipeline'!B15=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B14="","(prev)",'06_Status_Pipeline'!B14)&" → "&IF('06_Status_Pipeline'!B15="","(next)",'06_Status_Pipeline'!B15)) | IF(AND('06_Status_Pipeline'!B15="",'06_Status_Pipeline'!B16=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B15="","(prev)",'06_Status_Pipeline'!B15)&" → "&IF('06_Status_Pipeline'!B16="","(next)",'06_Status_Pipeline'!B16)) | _ProvinceList | _DistrictList
IF(F4="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 1 of 39 | AF2-AGF-N-001 | Agroforestry — Badakhshan / Wardoj | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Wardoj | Saplings: 8184; Seeds kg: 495 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ4="","",AQ4) | 2026-04-30 | 12 | 2027-04-01 | IF(W4<>"",W4,IF(OR(T4="",V4=""),"",EDATE(T4,V4))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F4="","",IF(COUNT(AI4:AV4)=0,IF(AA4="","Not started",AA4),SUBSTITUTE(LOOKUP(2,1/(AI4:AV4<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F4="",COUNT(AI4:AV4)=0),"",TODAY()-LOOKUP(2,1/(AI4:AV4<>""),AI4:AV4)) | IF(OR(F4="",COUNT(AI4:AV4)<2),"",LOOKUP(2,1/(AI4:AV4<>""),AI4:AV4)-MIN(AI4:AV4)) | IF(OR(AD4="",AC4="Not started",AC4=""),"",IFERROR(AD4-IF(VLOOKUP(AC4,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC4,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F4="","",IF(OR(AA4="Cancelled",AC4="Cancelled"),"Cancelled",IF(OR(AC4="Completed / Handover",Y4<>"",Z4>=100),"Completed — on track",IF(O4="Not awarded",IF(U4="",IF(X4="","No planned date",IF(TODAY()>X4,"Behind — past planned date",IF(X4-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U4,"Behind — award date passed",IF(U4-TODAY()<=30,"At risk — close to off track","On track"))),IF(X4="","No planned date",IF(AND(TODAY()>X4,OR(Z4="",Z4<100)),"Behind — past end date",IF(AND(T4<>"",X4<>"",Z4<>"",(Z4<100),((TODAY()-T4)/MAX(X4-T4,1)*100)-Z4>15),"Behind — progress lag",IF(AND(X4-TODAY()<=30,X4-TODAY()>=0,OR(Z4="",Z4<90)),"At risk — close to off track","On track")))))))) | IF(OR(F4="",AC4="Completed / Handover",AC4="Cancelled"),"",IF(O4="Not awarded",IF(U4<>"",U4-TODAY(),IF(X4="","",X4-TODAY())),IF(X4="","",X4-TODAY()))) | [14 empty] | IF(OR(F4="",AJ4=""),"",IF(COUNT(AI4:AI4)=0,"",AJ4-LOOKUP(2,1/(AI4:AI4<>""),AI4:AI4))) | IF(OR(F4="",AK4=""),"",IF(COUNT(AI4:AJ4)=0,"",AK4-LOOKUP(2,1/(AI4:AJ4<>""),AI4:AJ4))) | IF(OR(F4="",AL4=""),"",IF(COUNT(AI4:AK4)=0,"",AL4-LOOKUP(2,1/(AI4:AK4<>""),AI4:AK4))) | IF(OR(F4="",AM4=""),"",IF(COUNT(AI4:AL4)=0,"",AM4-LOOKUP(2,1/(AI4:AL4<>""),AI4:AL4))) | IF(OR(F4="",AN4=""),"",IF(COUNT(AI4:AM4)=0,"",AN4-LOOKUP(2,1/(AI4:AM4<>""),AI4:AM4))) | IF(OR(F4="",AO4=""),"",IF(COUNT(AI4:AN4)=0,"",AO4-LOOKUP(2,1/(AI4:AN4<>""),AI4:AN4))) | IF(OR(F4="",AP4=""),"",IF(COUNT(AI4:AO4)=0,"",AP4-LOOKUP(2,1/(AI4:AO4<>""),AI4:AO4))) | IF(OR(F4="",AQ4=""),"",IF(COUNT(AI4:AP4)=0,"",AQ4-LOOKUP(2,1/(AI4:AP4<>""),AI4:AP4))) | IF(OR(F4="",AR4=""),"",IF(COUNT(AI4:AQ4)=0,"",AR4-LOOKUP(2,1/(AI4:AQ4<>""),AI4:AQ4))) | IF(OR(F4="",AS4=""),"",IF(COUNT(AI4:AR4)=0,"",AS4-LOOKUP(2,1/(AI4:AR4<>""),AI4:AR4))) | IF(OR(F4="",AT4=""),"",IF(COUNT(AI4:AS4)=0,"",AT4-LOOKUP(2,1/(AI4:AS4<>""),AI4:AS4))) | IF(OR(F4="",AU4=""),"",IF(COUNT(AI4:AT4)=0,"",AU4-LOOKUP(2,1/(AI4:AT4<>""),AI4:AT4))) | IF(OR(F4="",AV4=""),"",IF(COUNT(AI4:AU4)=0,"",AV4-LOOKUP(2,1/(AI4:AU4<>""),AI4:AU4))) | IF(J4="","All_Provinces",IFERROR(VLOOKUP(J4,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K4="","All_Districts",IFERROR(VLOOKUP(K4,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F5="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 2 of 39 | AF2-AGF-N-002 | Agroforestry — Badghis / Sang Atish | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Sang Atish | Saplings: 0; Seeds kg: 20 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ5="","",AQ5) | 2026-04-30 | 12 | 2027-04-01 | IF(W5<>"",W5,IF(OR(T5="",V5=""),"",EDATE(T5,V5))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F5="","",IF(COUNT(AI5:AV5)=0,IF(AA5="","Not started",AA5),SUBSTITUTE(LOOKUP(2,1/(AI5:AV5<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F5="",COUNT(AI5:AV5)=0),"",TODAY()-LOOKUP(2,1/(AI5:AV5<>""),AI5:AV5)) | IF(OR(F5="",COUNT(AI5:AV5)<2),"",LOOKUP(2,1/(AI5:AV5<>""),AI5:AV5)-MIN(AI5:AV5)) | IF(OR(AD5="",AC5="Not started",AC5=""),"",IFERROR(AD5-IF(VLOOKUP(AC5,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC5,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F5="","",IF(OR(AA5="Cancelled",AC5="Cancelled"),"Cancelled",IF(OR(AC5="Completed / Handover",Y5<>"",Z5>=100),"Completed — on track",IF(O5="Not awarded",IF(U5="",IF(X5="","No planned date",IF(TODAY()>X5,"Behind — past planned date",IF(X5-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U5,"Behind — award date passed",IF(U5-TODAY()<=30,"At risk — close to off track","On track"))),IF(X5="","No planned date",IF(AND(TODAY()>X5,OR(Z5="",Z5<100)),"Behind — past end date",IF(AND(T5<>"",X5<>"",Z5<>"",(Z5<100),((TODAY()-T5)/MAX(X5-T5,1)*100)-Z5>15),"Behind — progress lag",IF(AND(X5-TODAY()<=30,X5-TODAY()>=0,OR(Z5="",Z5<90)),"At risk — close to off track","On track")))))))) | IF(OR(F5="",AC5="Completed / Handover",AC5="Cancelled"),"",IF(O5="Not awarded",IF(U5<>"",U5-TODAY(),IF(X5="","",X5-TODAY())),IF(X5="","",X5-TODAY()))) | [14 empty] | IF(OR(F5="",AJ5=""),"",IF(COUNT(AI5:AI5)=0,"",AJ5-LOOKUP(2,1/(AI5:AI5<>""),AI5:AI5))) | IF(OR(F5="",AK5=""),"",IF(COUNT(AI5:AJ5)=0,"",AK5-LOOKUP(2,1/(AI5:AJ5<>""),AI5:AJ5))) | IF(OR(F5="",AL5=""),"",IF(COUNT(AI5:AK5)=0,"",AL5-LOOKUP(2,1/(AI5:AK5<>""),AI5:AK5))) | IF(OR(F5="",AM5=""),"",IF(COUNT(AI5:AL5)=0,"",AM5-LOOKUP(2,1/(AI5:AL5<>""),AI5:AL5))) | IF(OR(F5="",AN5=""),"",IF(COUNT(AI5:AM5)=0,"",AN5-LOOKUP(2,1/(AI5:AM5<>""),AI5:AM5))) | IF(OR(F5="",AO5=""),"",IF(COUNT(AI5:AN5)=0,"",AO5-LOOKUP(2,1/(AI5:AN5<>""),AI5:AN5))) | IF(OR(F5="",AP5=""),"",IF(COUNT(AI5:AO5)=0,"",AP5-LOOKUP(2,1/(AI5:AO5<>""),AI5:AO5))) | IF(OR(F5="",AQ5=""),"",IF(COUNT(AI5:AP5)=0,"",AQ5-LOOKUP(2,1/(AI5:AP5<>""),AI5:AP5))) | IF(OR(F5="",AR5=""),"",IF(COUNT(AI5:AQ5)=0,"",AR5-LOOKUP(2,1/(AI5:AQ5<>""),AI5:AQ5))) | IF(OR(F5="",AS5=""),"",IF(COUNT(AI5:AR5)=0,"",AS5-LOOKUP(2,1/(AI5:AR5<>""),AI5:AR5))) | IF(OR(F5="",AT5=""),"",IF(COUNT(AI5:AS5)=0,"",AT5-LOOKUP(2,1/(AI5:AS5<>""),AI5:AS5))) | IF(OR(F5="",AU5=""),"",IF(COUNT(AI5:AT5)=0,"",AU5-LOOKUP(2,1/(AI5:AT5<>""),AI5:AT5))) | IF(OR(F5="",AV5=""),"",IF(COUNT(AI5:AU5)=0,"",AV5-LOOKUP(2,1/(AI5:AU5<>""),AI5:AU5))) | IF(J5="","All_Provinces",IFERROR(VLOOKUP(J5,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K5="","All_Districts",IFERROR(VLOOKUP(K5,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F6="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 3 of 39 | AF2-AGF-N-003 | Agroforestry — Baghlan / Banu | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Banu | Saplings: 8316; Seeds kg: 121 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ6="","",AQ6) | 2026-04-30 | 12 | 2027-04-01 | IF(W6<>"",W6,IF(OR(T6="",V6=""),"",EDATE(T6,V6))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F6="","",IF(COUNT(AI6:AV6)=0,IF(AA6="","Not started",AA6),SUBSTITUTE(LOOKUP(2,1/(AI6:AV6<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F6="",COUNT(AI6:AV6)=0),"",TODAY()-LOOKUP(2,1/(AI6:AV6<>""),AI6:AV6)) | IF(OR(F6="",COUNT(AI6:AV6)<2),"",LOOKUP(2,1/(AI6:AV6<>""),AI6:AV6)-MIN(AI6:AV6)) | IF(OR(AD6="",AC6="Not started",AC6=""),"",IFERROR(AD6-IF(VLOOKUP(AC6,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC6,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F6="","",IF(OR(AA6="Cancelled",AC6="Cancelled"),"Cancelled",IF(OR(AC6="Completed / Handover",Y6<>"",Z6>=100),"Completed — on track",IF(O6="Not awarded",IF(U6="",IF(X6="","No planned date",IF(TODAY()>X6,"Behind — past planned date",IF(X6-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U6,"Behind — award date passed",IF(U6-TODAY()<=30,"At risk — close to off track","On track"))),IF(X6="","No planned date",IF(AND(TODAY()>X6,OR(Z6="",Z6<100)),"Behind — past end date",IF(AND(T6<>"",X6<>"",Z6<>"",(Z6<100),((TODAY()-T6)/MAX(X6-T6,1)*100)-Z6>15),"Behind — progress lag",IF(AND(X6-TODAY()<=30,X6-TODAY()>=0,OR(Z6="",Z6<90)),"At risk — close to off track","On track")))))))) | IF(OR(F6="",AC6="Completed / Handover",AC6="Cancelled"),"",IF(O6="Not awarded",IF(U6<>"",U6-TODAY(),IF(X6="","",X6-TODAY())),IF(X6="","",X6-TODAY()))) | [14 empty] | IF(OR(F6="",AJ6=""),"",IF(COUNT(AI6:AI6)=0,"",AJ6-LOOKUP(2,1/(AI6:AI6<>""),AI6:AI6))) | IF(OR(F6="",AK6=""),"",IF(COUNT(AI6:AJ6)=0,"",AK6-LOOKUP(2,1/(AI6:AJ6<>""),AI6:AJ6))) | IF(OR(F6="",AL6=""),"",IF(COUNT(AI6:AK6)=0,"",AL6-LOOKUP(2,1/(AI6:AK6<>""),AI6:AK6))) | IF(OR(F6="",AM6=""),"",IF(COUNT(AI6:AL6)=0,"",AM6-LOOKUP(2,1/(AI6:AL6<>""),AI6:AL6))) | IF(OR(F6="",AN6=""),"",IF(COUNT(AI6:AM6)=0,"",AN6-LOOKUP(2,1/(AI6:AM6<>""),AI6:AM6))) | IF(OR(F6="",AO6=""),"",IF(COUNT(AI6:AN6)=0,"",AO6-LOOKUP(2,1/(AI6:AN6<>""),AI6:AN6))) | IF(OR(F6="",AP6=""),"",IF(COUNT(AI6:AO6)=0,"",AP6-LOOKUP(2,1/(AI6:AO6<>""),AI6:AO6))) | IF(OR(F6="",AQ6=""),"",IF(COUNT(AI6:AP6)=0,"",AQ6-LOOKUP(2,1/(AI6:AP6<>""),AI6:AP6))) | IF(OR(F6="",AR6=""),"",IF(COUNT(AI6:AQ6)=0,"",AR6-LOOKUP(2,1/(AI6:AQ6<>""),AI6:AQ6))) | IF(OR(F6="",AS6=""),"",IF(COUNT(AI6:AR6)=0,"",AS6-LOOKUP(2,1/(AI6:AR6<>""),AI6:AR6))) | IF(OR(F6="",AT6=""),"",IF(COUNT(AI6:AS6)=0,"",AT6-LOOKUP(2,1/(AI6:AS6<>""),AI6:AS6))) | IF(OR(F6="",AU6=""),"",IF(COUNT(AI6:AT6)=0,"",AU6-LOOKUP(2,1/(AI6:AT6<>""),AI6:AT6))) | IF(OR(F6="",AV6=""),"",IF(COUNT(AI6:AU6)=0,"",AV6-LOOKUP(2,1/(AI6:AU6<>""),AI6:AU6))) | IF(J6="","All_Provinces",IFERROR(VLOOKUP(J6,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K6="","All_Districts",IFERROR(VLOOKUP(K6,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F7="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 4 of 39 | AF2-AGF-N-004 | Agroforestry — Balkh / Charkent | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Charkent | Saplings: 0; Seeds kg: 31 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ7="","",AQ7) | 2026-04-30 | 12 | 2027-04-01 | IF(W7<>"",W7,IF(OR(T7="",V7=""),"",EDATE(T7,V7))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F7="","",IF(COUNT(AI7:AV7)=0,IF(AA7="","Not started",AA7),SUBSTITUTE(LOOKUP(2,1/(AI7:AV7<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F7="",COUNT(AI7:AV7)=0),"",TODAY()-LOOKUP(2,1/(AI7:AV7<>""),AI7:AV7)) | IF(OR(F7="",COUNT(AI7:AV7)<2),"",LOOKUP(2,1/(AI7:AV7<>""),AI7:AV7)-MIN(AI7:AV7)) | IF(OR(AD7="",AC7="Not started",AC7=""),"",IFERROR(AD7-IF(VLOOKUP(AC7,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC7,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F7="","",IF(OR(AA7="Cancelled",AC7="Cancelled"),"Cancelled",IF(OR(AC7="Completed / Handover",Y7<>"",Z7>=100),"Completed — on track",IF(O7="Not awarded",IF(U7="",IF(X7="","No planned date",IF(TODAY()>X7,"Behind — past planned date",IF(X7-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U7,"Behind — award date passed",IF(U7-TODAY()<=30,"At risk — close to off track","On track"))),IF(X7="","No planned date",IF(AND(TODAY()>X7,OR(Z7="",Z7<100)),"Behind — past end date",IF(AND(T7<>"",X7<>"",Z7<>"",(Z7<100),((TODAY()-T7)/MAX(X7-T7,1)*100)-Z7>15),"Behind — progress lag",IF(AND(X7-TODAY()<=30,X7-TODAY()>=0,OR(Z7="",Z7<90)),"At risk — close to off track","On track")))))))) | IF(OR(F7="",AC7="Completed / Handover",AC7="Cancelled"),"",IF(O7="Not awarded",IF(U7<>"",U7-TODAY(),IF(X7="","",X7-TODAY())),IF(X7="","",X7-TODAY()))) | [14 empty] | IF(OR(F7="",AJ7=""),"",IF(COUNT(AI7:AI7)=0,"",AJ7-LOOKUP(2,1/(AI7:AI7<>""),AI7:AI7))) | IF(OR(F7="",AK7=""),"",IF(COUNT(AI7:AJ7)=0,"",AK7-LOOKUP(2,1/(AI7:AJ7<>""),AI7:AJ7))) | IF(OR(F7="",AL7=""),"",IF(COUNT(AI7:AK7)=0,"",AL7-LOOKUP(2,1/(AI7:AK7<>""),AI7:AK7))) | IF(OR(F7="",AM7=""),"",IF(COUNT(AI7:AL7)=0,"",AM7-LOOKUP(2,1/(AI7:AL7<>""),AI7:AL7))) | IF(OR(F7="",AN7=""),"",IF(COUNT(AI7:AM7)=0,"",AN7-LOOKUP(2,1/(AI7:AM7<>""),AI7:AM7))) | IF(OR(F7="",AO7=""),"",IF(COUNT(AI7:AN7)=0,"",AO7-LOOKUP(2,1/(AI7:AN7<>""),AI7:AN7))) | IF(OR(F7="",AP7=""),"",IF(COUNT(AI7:AO7)=0,"",AP7-LOOKUP(2,1/(AI7:AO7<>""),AI7:AO7))) | IF(OR(F7="",AQ7=""),"",IF(COUNT(AI7:AP7)=0,"",AQ7-LOOKUP(2,1/(AI7:AP7<>""),AI7:AP7))) | IF(OR(F7="",AR7=""),"",IF(COUNT(AI7:AQ7)=0,"",AR7-LOOKUP(2,1/(AI7:AQ7<>""),AI7:AQ7))) | IF(OR(F7="",AS7=""),"",IF(COUNT(AI7:AR7)=0,"",AS7-LOOKUP(2,1/(AI7:AR7<>""),AI7:AR7))) | IF(OR(F7="",AT7=""),"",IF(COUNT(AI7:AS7)=0,"",AT7-LOOKUP(2,1/(AI7:AS7<>""),AI7:AS7))) | IF(OR(F7="",AU7=""),"",IF(COUNT(AI7:AT7)=0,"",AU7-LOOKUP(2,1/(AI7:AT7<>""),AI7:AT7))) | IF(OR(F7="",AV7=""),"",IF(COUNT(AI7:AU7)=0,"",AV7-LOOKUP(2,1/(AI7:AU7<>""),AI7:AU7))) | IF(J7="","All_Provinces",IFERROR(VLOOKUP(J7,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K7="","All_Districts",IFERROR(VLOOKUP(K7,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F8="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 5 of 39 | AF2-AGF-N-005 | Agroforestry — Balkh / Dehdadi | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Dehdadi | Saplings: 2400; Seeds kg: 21 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ8="","",AQ8) | 2026-04-30 | 12 | 2027-04-01 | IF(W8<>"",W8,IF(OR(T8="",V8=""),"",EDATE(T8,V8))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F8="","",IF(COUNT(AI8:AV8)=0,IF(AA8="","Not started",AA8),SUBSTITUTE(LOOKUP(2,1/(AI8:AV8<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F8="",COUNT(AI8:AV8)=0),"",TODAY()-LOOKUP(2,1/(AI8:AV8<>""),AI8:AV8)) | IF(OR(F8="",COUNT(AI8:AV8)<2),"",LOOKUP(2,1/(AI8:AV8<>""),AI8:AV8)-MIN(AI8:AV8)) | IF(OR(AD8="",AC8="Not started",AC8=""),"",IFERROR(AD8-IF(VLOOKUP(AC8,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC8,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F8="","",IF(OR(AA8="Cancelled",AC8="Cancelled"),"Cancelled",IF(OR(AC8="Completed / Handover",Y8<>"",Z8>=100),"Completed — on track",IF(O8="Not awarded",IF(U8="",IF(X8="","No planned date",IF(TODAY()>X8,"Behind — past planned date",IF(X8-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U8,"Behind — award date passed",IF(U8-TODAY()<=30,"At risk — close to off track","On track"))),IF(X8="","No planned date",IF(AND(TODAY()>X8,OR(Z8="",Z8<100)),"Behind — past end date",IF(AND(T8<>"",X8<>"",Z8<>"",(Z8<100),((TODAY()-T8)/MAX(X8-T8,1)*100)-Z8>15),"Behind — progress lag",IF(AND(X8-TODAY()<=30,X8-TODAY()>=0,OR(Z8="",Z8<90)),"At risk — close to off track","On track")))))))) | IF(OR(F8="",AC8="Completed / Handover",AC8="Cancelled"),"",IF(O8="Not awarded",IF(U8<>"",U8-TODAY(),IF(X8="","",X8-TODAY())),IF(X8="","",X8-TODAY()))) | [14 empty] | IF(OR(F8="",AJ8=""),"",IF(COUNT(AI8:AI8)=0,"",AJ8-LOOKUP(2,1/(AI8:AI8<>""),AI8:AI8))) | IF(OR(F8="",AK8=""),"",IF(COUNT(AI8:AJ8)=0,"",AK8-LOOKUP(2,1/(AI8:AJ8<>""),AI8:AJ8))) | IF(OR(F8="",AL8=""),"",IF(COUNT(AI8:AK8)=0,"",AL8-LOOKUP(2,1/(AI8:AK8<>""),AI8:AK8))) | IF(OR(F8="",AM8=""),"",IF(COUNT(AI8:AL8)=0,"",AM8-LOOKUP(2,1/(AI8:AL8<>""),AI8:AL8))) | IF(OR(F8="",AN8=""),"",IF(COUNT(AI8:AM8)=0,"",AN8-LOOKUP(2,1/(AI8:AM8<>""),AI8:AM8))) | IF(OR(F8="",AO8=""),"",IF(COUNT(AI8:AN8)=0,"",AO8-LOOKUP(2,1/(AI8:AN8<>""),AI8:AN8))) | IF(OR(F8="",AP8=""),"",IF(COUNT(AI8:AO8)=0,"",AP8-LOOKUP(2,1/(AI8:AO8<>""),AI8:AO8))) | IF(OR(F8="",AQ8=""),"",IF(COUNT(AI8:AP8)=0,"",AQ8-LOOKUP(2,1/(AI8:AP8<>""),AI8:AP8))) | IF(OR(F8="",AR8=""),"",IF(COUNT(AI8:AQ8)=0,"",AR8-LOOKUP(2,1/(AI8:AQ8<>""),AI8:AQ8))) | IF(OR(F8="",AS8=""),"",IF(COUNT(AI8:AR8)=0,"",AS8-LOOKUP(2,1/(AI8:AR8<>""),AI8:AR8))) | IF(OR(F8="",AT8=""),"",IF(COUNT(AI8:AS8)=0,"",AT8-LOOKUP(2,1/(AI8:AS8<>""),AI8:AS8))) | IF(OR(F8="",AU8=""),"",IF(COUNT(AI8:AT8)=0,"",AU8-LOOKUP(2,1/(AI8:AT8<>""),AI8:AT8))) | IF(OR(F8="",AV8=""),"",IF(COUNT(AI8:AU8)=0,"",AV8-LOOKUP(2,1/(AI8:AU8<>""),AI8:AU8))) | IF(J8="","All_Provinces",IFERROR(VLOOKUP(J8,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K8="","All_Districts",IFERROR(VLOOKUP(K8,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F9="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 6 of 39 | AF2-AGF-N-006 | Agroforestry — Balkh / Kishendeh | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Kishendeh | Saplings: 0; Seeds kg: 46 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ9="","",AQ9) | 2026-04-30 | 12 | 2027-04-01 | IF(W9<>"",W9,IF(OR(T9="",V9=""),"",EDATE(T9,V9))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F9="","",IF(COUNT(AI9:AV9)=0,IF(AA9="","Not started",AA9),SUBSTITUTE(LOOKUP(2,1/(AI9:AV9<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F9="",COUNT(AI9:AV9)=0),"",TODAY()-LOOKUP(2,1/(AI9:AV9<>""),AI9:AV9)) | IF(OR(F9="",COUNT(AI9:AV9)<2),"",LOOKUP(2,1/(AI9:AV9<>""),AI9:AV9)-MIN(AI9:AV9)) | IF(OR(AD9="",AC9="Not started",AC9=""),"",IFERROR(AD9-IF(VLOOKUP(AC9,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC9,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F9="","",IF(OR(AA9="Cancelled",AC9="Cancelled"),"Cancelled",IF(OR(AC9="Completed / Handover",Y9<>"",Z9>=100),"Completed — on track",IF(O9="Not awarded",IF(U9="",IF(X9="","No planned date",IF(TODAY()>X9,"Behind — past planned date",IF(X9-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U9,"Behind — award date passed",IF(U9-TODAY()<=30,"At risk — close to off track","On track"))),IF(X9="","No planned date",IF(AND(TODAY()>X9,OR(Z9="",Z9<100)),"Behind — past end date",IF(AND(T9<>"",X9<>"",Z9<>"",(Z9<100),((TODAY()-T9)/MAX(X9-T9,1)*100)-Z9>15),"Behind — progress lag",IF(AND(X9-TODAY()<=30,X9-TODAY()>=0,OR(Z9="",Z9<90)),"At risk — close to off track","On track")))))))) | IF(OR(F9="",AC9="Completed / Handover",AC9="Cancelled"),"",IF(O9="Not awarded",IF(U9<>"",U9-TODAY(),IF(X9="","",X9-TODAY())),IF(X9="","",X9-TODAY()))) | [14 empty] | IF(OR(F9="",AJ9=""),"",IF(COUNT(AI9:AI9)=0,"",AJ9-LOOKUP(2,1/(AI9:AI9<>""),AI9:AI9))) | IF(OR(F9="",AK9=""),"",IF(COUNT(AI9:AJ9)=0,"",AK9-LOOKUP(2,1/(AI9:AJ9<>""),AI9:AJ9))) | IF(OR(F9="",AL9=""),"",IF(COUNT(AI9:AK9)=0,"",AL9-LOOKUP(2,1/(AI9:AK9<>""),AI9:AK9))) | IF(OR(F9="",AM9=""),"",IF(COUNT(AI9:AL9)=0,"",AM9-LOOKUP(2,1/(AI9:AL9<>""),AI9:AL9))) | IF(OR(F9="",AN9=""),"",IF(COUNT(AI9:AM9)=0,"",AN9-LOOKUP(2,1/(AI9:AM9<>""),AI9:AM9))) | IF(OR(F9="",AO9=""),"",IF(COUNT(AI9:AN9)=0,"",AO9-LOOKUP(2,1/(AI9:AN9<>""),AI9:AN9))) | IF(OR(F9="",AP9=""),"",IF(COUNT(AI9:AO9)=0,"",AP9-LOOKUP(2,1/(AI9:AO9<>""),AI9:AO9))) | IF(OR(F9="",AQ9=""),"",IF(COUNT(AI9:AP9)=0,"",AQ9-LOOKUP(2,1/(AI9:AP9<>""),AI9:AP9))) | IF(OR(F9="",AR9=""),"",IF(COUNT(AI9:AQ9)=0,"",AR9-LOOKUP(2,1/(AI9:AQ9<>""),AI9:AQ9))) | IF(OR(F9="",AS9=""),"",IF(COUNT(AI9:AR9)=0,"",AS9-LOOKUP(2,1/(AI9:AR9<>""),AI9:AR9))) | IF(OR(F9="",AT9=""),"",IF(COUNT(AI9:AS9)=0,"",AT9-LOOKUP(2,1/(AI9:AS9<>""),AI9:AS9))) | IF(OR(F9="",AU9=""),"",IF(COUNT(AI9:AT9)=0,"",AU9-LOOKUP(2,1/(AI9:AT9<>""),AI9:AT9))) | IF(OR(F9="",AV9=""),"",IF(COUNT(AI9:AU9)=0,"",AV9-LOOKUP(2,1/(AI9:AU9<>""),AI9:AU9))) | IF(J9="","All_Provinces",IFERROR(VLOOKUP(J9,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K9="","All_Districts",IFERROR(VLOOKUP(K9,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F10="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 7 of 39 | AF2-AGF-N-007 | Agroforestry — Balkh / Marmul | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Marmul | Saplings: 0; Seeds kg: 41 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ10="","",AQ10) | 2026-04-30 | 12 | 2027-04-01 | IF(W10<>"",W10,IF(OR(T10="",V10=""),"",EDATE(T10,V10))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F10="","",IF(COUNT(AI10:AV10)=0,IF(AA10="","Not started",AA10),SUBSTITUTE(LOOKUP(2,1/(AI10:AV10<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F10="",COUNT(AI10:AV10)=0),"",TODAY()-LOOKUP(2,1/(AI10:AV10<>""),AI10:AV10)) | IF(OR(F10="",COUNT(AI10:AV10)<2),"",LOOKUP(2,1/(AI10:AV10<>""),AI10:AV10)-MIN(AI10:AV10)) | IF(OR(AD10="",AC10="Not started",AC10=""),"",IFERROR(AD10-IF(VLOOKUP(AC10,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC10,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F10="","",IF(OR(AA10="Cancelled",AC10="Cancelled"),"Cancelled",IF(OR(AC10="Completed / Handover",Y10<>"",Z10>=100),"Completed — on track",IF(O10="Not awarded",IF(U10="",IF(X10="","No planned date",IF(TODAY()>X10,"Behind — past planned date",IF(X10-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U10,"Behind — award date passed",IF(U10-TODAY()<=30,"At risk — close to off track","On track"))),IF(X10="","No planned date",IF(AND(TODAY()>X10,OR(Z10="",Z10<100)),"Behind — past end date",IF(AND(T10<>"",X10<>"",Z10<>"",(Z10<100),((TODAY()-T10)/MAX(X10-T10,1)*100)-Z10>15),"Behind — progress lag",IF(AND(X10-TODAY()<=30,X10-TODAY()>=0,OR(Z10="",Z10<90)),"At risk — close to off track","On track")))))))) | IF(OR(F10="",AC10="Completed / Handover",AC10="Cancelled"),"",IF(O10="Not awarded",IF(U10<>"",U10-TODAY(),IF(X10="","",X10-TODAY())),IF(X10="","",X10-TODAY()))) | [14 empty] | IF(OR(F10="",AJ10=""),"",IF(COUNT(AI10:AI10)=0,"",AJ10-LOOKUP(2,1/(AI10:AI10<>""),AI10:AI10))) | IF(OR(F10="",AK10=""),"",IF(COUNT(AI10:AJ10)=0,"",AK10-LOOKUP(2,1/(AI10:AJ10<>""),AI10:AJ10))) | IF(OR(F10="",AL10=""),"",IF(COUNT(AI10:AK10)=0,"",AL10-LOOKUP(2,1/(AI10:AK10<>""),AI10:AK10))) | IF(OR(F10="",AM10=""),"",IF(COUNT(AI10:AL10)=0,"",AM10-LOOKUP(2,1/(AI10:AL10<>""),AI10:AL10))) | IF(OR(F10="",AN10=""),"",IF(COUNT(AI10:AM10)=0,"",AN10-LOOKUP(2,1/(AI10:AM10<>""),AI10:AM10))) | IF(OR(F10="",AO10=""),"",IF(COUNT(AI10:AN10)=0,"",AO10-LOOKUP(2,1/(AI10:AN10<>""),AI10:AN10))) | IF(OR(F10="",AP10=""),"",IF(COUNT(AI10:AO10)=0,"",AP10-LOOKUP(2,1/(AI10:AO10<>""),AI10:AO10))) | IF(OR(F10="",AQ10=""),"",IF(COUNT(AI10:AP10)=0,"",AQ10-LOOKUP(2,1/(AI10:AP10<>""),AI10:AP10))) | IF(OR(F10="",AR10=""),"",IF(COUNT(AI10:AQ10)=0,"",AR10-LOOKUP(2,1/(AI10:AQ10<>""),AI10:AQ10))) | IF(OR(F10="",AS10=""),"",IF(COUNT(AI10:AR10)=0,"",AS10-LOOKUP(2,1/(AI10:AR10<>""),AI10:AR10))) | IF(OR(F10="",AT10=""),"",IF(COUNT(AI10:AS10)=0,"",AT10-LOOKUP(2,1/(AI10:AS10<>""),AI10:AS10))) | IF(OR(F10="",AU10=""),"",IF(COUNT(AI10:AT10)=0,"",AU10-LOOKUP(2,1/(AI10:AT10<>""),AI10:AT10))) | IF(OR(F10="",AV10=""),"",IF(COUNT(AI10:AU10)=0,"",AV10-LOOKUP(2,1/(AI10:AU10<>""),AI10:AU10))) | IF(J10="","All_Provinces",IFERROR(VLOOKUP(J10,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K10="","All_Districts",IFERROR(VLOOKUP(K10,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F11="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 8 of 39 | AF2-AGF-N-008 | Agroforestry — Balkh / Nahre Shahi | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Nahre Shahi | Saplings: 0; Seeds kg: 246 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ11="","",AQ11) | 2026-04-30 | 12 | 2027-04-01 | IF(W11<>"",W11,IF(OR(T11="",V11=""),"",EDATE(T11,V11))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F11="","",IF(COUNT(AI11:AV11)=0,IF(AA11="","Not started",AA11),SUBSTITUTE(LOOKUP(2,1/(AI11:AV11<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F11="",COUNT(AI11:AV11)=0),"",TODAY()-LOOKUP(2,1/(AI11:AV11<>""),AI11:AV11)) | IF(OR(F11="",COUNT(AI11:AV11)<2),"",LOOKUP(2,1/(AI11:AV11<>""),AI11:AV11)-MIN(AI11:AV11)) | IF(OR(AD11="",AC11="Not started",AC11=""),"",IFERROR(AD11-IF(VLOOKUP(AC11,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC11,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F11="","",IF(OR(AA11="Cancelled",AC11="Cancelled"),"Cancelled",IF(OR(AC11="Completed / Handover",Y11<>"",Z11>=100),"Completed — on track",IF(O11="Not awarded",IF(U11="",IF(X11="","No planned date",IF(TODAY()>X11,"Behind — past planned date",IF(X11-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U11,"Behind — award date passed",IF(U11-TODAY()<=30,"At risk — close to off track","On track"))),IF(X11="","No planned date",IF(AND(TODAY()>X11,OR(Z11="",Z11<100)),"Behind — past end date",IF(AND(T11<>"",X11<>"",Z11<>"",(Z11<100),((TODAY()-T11)/MAX(X11-T11,1)*100)-Z11>15),"Behind — progress lag",IF(AND(X11-TODAY()<=30,X11-TODAY()>=0,OR(Z11="",Z11<90)),"At risk — close to off track","On track")))))))) | IF(OR(F11="",AC11="Completed / Handover",AC11="Cancelled"),"",IF(O11="Not awarded",IF(U11<>"",U11-TODAY(),IF(X11="","",X11-TODAY())),IF(X11="","",X11-TODAY()))) | [14 empty] | IF(OR(F11="",AJ11=""),"",IF(COUNT(AI11:AI11)=0,"",AJ11-LOOKUP(2,1/(AI11:AI11<>""),AI11:AI11))) | IF(OR(F11="",AK11=""),"",IF(COUNT(AI11:AJ11)=0,"",AK11-LOOKUP(2,1/(AI11:AJ11<>""),AI11:AJ11))) | IF(OR(F11="",AL11=""),"",IF(COUNT(AI11:AK11)=0,"",AL11-LOOKUP(2,1/(AI11:AK11<>""),AI11:AK11))) | IF(OR(F11="",AM11=""),"",IF(COUNT(AI11:AL11)=0,"",AM11-LOOKUP(2,1/(AI11:AL11<>""),AI11:AL11))) | IF(OR(F11="",AN11=""),"",IF(COUNT(AI11:AM11)=0,"",AN11-LOOKUP(2,1/(AI11:AM11<>""),AI11:AM11))) | IF(OR(F11="",AO11=""),"",IF(COUNT(AI11:AN11)=0,"",AO11-LOOKUP(2,1/(AI11:AN11<>""),AI11:AN11))) | IF(OR(F11="",AP11=""),"",IF(COUNT(AI11:AO11)=0,"",AP11-LOOKUP(2,1/(AI11:AO11<>""),AI11:AO11))) | IF(OR(F11="",AQ11=""),"",IF(COUNT(AI11:AP11)=0,"",AQ11-LOOKUP(2,1/(AI11:AP11<>""),AI11:AP11))) | IF(OR(F11="",AR11=""),"",IF(COUNT(AI11:AQ11)=0,"",AR11-LOOKUP(2,1/(AI11:AQ11<>""),AI11:AQ11))) | IF(OR(F11="",AS11=""),"",IF(COUNT(AI11:AR11)=0,"",AS11-LOOKUP(2,1/(AI11:AR11<>""),AI11:AR11))) | IF(OR(F11="",AT11=""),"",IF(COUNT(AI11:AS11)=0,"",AT11-LOOKUP(2,1/(AI11:AS11<>""),AI11:AS11))) | IF(OR(F11="",AU11=""),"",IF(COUNT(AI11:AT11)=0,"",AU11-LOOKUP(2,1/(AI11:AT11<>""),AI11:AT11))) | IF(OR(F11="",AV11=""),"",IF(COUNT(AI11:AU11)=0,"",AV11-LOOKUP(2,1/(AI11:AU11<>""),AI11:AU11))) | IF(J11="","All_Provinces",IFERROR(VLOOKUP(J11,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K11="","All_Districts",IFERROR(VLOOKUP(K11,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F12="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 9 of 39 | AF2-AGF-N-009 | Agroforestry — Daikundi / Khedir | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daikundi | Khedir | Saplings: 6000; Seeds kg: 477 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ12="","",AQ12) | 2026-04-30 | 12 | 2027-04-01 | IF(W12<>"",W12,IF(OR(T12="",V12=""),"",EDATE(T12,V12))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F12="","",IF(COUNT(AI12:AV12)=0,IF(AA12="","Not started",AA12),SUBSTITUTE(LOOKUP(2,1/(AI12:AV12<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F12="",COUNT(AI12:AV12)=0),"",TODAY()-LOOKUP(2,1/(AI12:AV12<>""),AI12:AV12)) | IF(OR(F12="",COUNT(AI12:AV12)<2),"",LOOKUP(2,1/(AI12:AV12<>""),AI12:AV12)-MIN(AI12:AV12)) | IF(OR(AD12="",AC12="Not started",AC12=""),"",IFERROR(AD12-IF(VLOOKUP(AC12,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC12,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F12="","",IF(OR(AA12="Cancelled",AC12="Cancelled"),"Cancelled",IF(OR(AC12="Completed / Handover",Y12<>"",Z12>=100),"Completed — on track",IF(O12="Not awarded",IF(U12="",IF(X12="","No planned date",IF(TODAY()>X12,"Behind — past planned date",IF(X12-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U12,"Behind — award date passed",IF(U12-TODAY()<=30,"At risk — close to off track","On track"))),IF(X12="","No planned date",IF(AND(TODAY()>X12,OR(Z12="",Z12<100)),"Behind — past end date",IF(AND(T12<>"",X12<>"",Z12<>"",(Z12<100),((TODAY()-T12)/MAX(X12-T12,1)*100)-Z12>15),"Behind — progress lag",IF(AND(X12-TODAY()<=30,X12-TODAY()>=0,OR(Z12="",Z12<90)),"At risk — close to off track","On track")))))))) | IF(OR(F12="",AC12="Completed / Handover",AC12="Cancelled"),"",IF(O12="Not awarded",IF(U12<>"",U12-TODAY(),IF(X12="","",X12-TODAY())),IF(X12="","",X12-TODAY()))) | [14 empty] | IF(OR(F12="",AJ12=""),"",IF(COUNT(AI12:AI12)=0,"",AJ12-LOOKUP(2,1/(AI12:AI12<>""),AI12:AI12))) | IF(OR(F12="",AK12=""),"",IF(COUNT(AI12:AJ12)=0,"",AK12-LOOKUP(2,1/(AI12:AJ12<>""),AI12:AJ12))) | IF(OR(F12="",AL12=""),"",IF(COUNT(AI12:AK12)=0,"",AL12-LOOKUP(2,1/(AI12:AK12<>""),AI12:AK12))) | IF(OR(F12="",AM12=""),"",IF(COUNT(AI12:AL12)=0,"",AM12-LOOKUP(2,1/(AI12:AL12<>""),AI12:AL12))) | IF(OR(F12="",AN12=""),"",IF(COUNT(AI12:AM12)=0,"",AN12-LOOKUP(2,1/(AI12:AM12<>""),AI12:AM12))) | IF(OR(F12="",AO12=""),"",IF(COUNT(AI12:AN12)=0,"",AO12-LOOKUP(2,1/(AI12:AN12<>""),AI12:AN12))) | IF(OR(F12="",AP12=""),"",IF(COUNT(AI12:AO12)=0,"",AP12-LOOKUP(2,1/(AI12:AO12<>""),AI12:AO12))) | IF(OR(F12="",AQ12=""),"",IF(COUNT(AI12:AP12)=0,"",AQ12-LOOKUP(2,1/(AI12:AP12<>""),AI12:AP12))) | IF(OR(F12="",AR12=""),"",IF(COUNT(AI12:AQ12)=0,"",AR12-LOOKUP(2,1/(AI12:AQ12<>""),AI12:AQ12))) | IF(OR(F12="",AS12=""),"",IF(COUNT(AI12:AR12)=0,"",AS12-LOOKUP(2,1/(AI12:AR12<>""),AI12:AR12))) | IF(OR(F12="",AT12=""),"",IF(COUNT(AI12:AS12)=0,"",AT12-LOOKUP(2,1/(AI12:AS12<>""),AI12:AS12))) | IF(OR(F12="",AU12=""),"",IF(COUNT(AI12:AT12)=0,"",AU12-LOOKUP(2,1/(AI12:AT12<>""),AI12:AT12))) | IF(OR(F12="",AV12=""),"",IF(COUNT(AI12:AU12)=0,"",AV12-LOOKUP(2,1/(AI12:AU12<>""),AI12:AU12))) | IF(J12="","All_Provinces",IFERROR(VLOOKUP(J12,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K12="","All_Districts",IFERROR(VLOOKUP(K12,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F13="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 10 of 39 | AF2-AGF-N-010 | Agroforestry — Daikundi / Meramour | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daikundi | Meramour | Saplings: 7000; Seeds kg: 197.5 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ13="","",AQ13) | 2026-04-30 | 12 | 2027-04-01 | IF(W13<>"",W13,IF(OR(T13="",V13=""),"",EDATE(T13,V13))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F13="","",IF(COUNT(AI13:AV13)=0,IF(AA13="","Not started",AA13),SUBSTITUTE(LOOKUP(2,1/(AI13:AV13<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F13="",COUNT(AI13:AV13)=0),"",TODAY()-LOOKUP(2,1/(AI13:AV13<>""),AI13:AV13)) | IF(OR(F13="",COUNT(AI13:AV13)<2),"",LOOKUP(2,1/(AI13:AV13<>""),AI13:AV13)-MIN(AI13:AV13)) | IF(OR(AD13="",AC13="Not started",AC13=""),"",IFERROR(AD13-IF(VLOOKUP(AC13,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC13,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F13="","",IF(OR(AA13="Cancelled",AC13="Cancelled"),"Cancelled",IF(OR(AC13="Completed / Handover",Y13<>"",Z13>=100),"Completed — on track",IF(O13="Not awarded",IF(U13="",IF(X13="","No planned date",IF(TODAY()>X13,"Behind — past planned date",IF(X13-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U13,"Behind — award date passed",IF(U13-TODAY()<=30,"At risk — close to off track","On track"))),IF(X13="","No planned date",IF(AND(TODAY()>X13,OR(Z13="",Z13<100)),"Behind — past end date",IF(AND(T13<>"",X13<>"",Z13<>"",(Z13<100),((TODAY()-T13)/MAX(X13-T13,1)*100)-Z13>15),"Behind — progress lag",IF(AND(X13-TODAY()<=30,X13-TODAY()>=0,OR(Z13="",Z13<90)),"At risk — close to off track","On track")))))))) | IF(OR(F13="",AC13="Completed / Handover",AC13="Cancelled"),"",IF(O13="Not awarded",IF(U13<>"",U13-TODAY(),IF(X13="","",X13-TODAY())),IF(X13="","",X13-TODAY()))) | [14 empty] | IF(OR(F13="",AJ13=""),"",IF(COUNT(AI13:AI13)=0,"",AJ13-LOOKUP(2,1/(AI13:AI13<>""),AI13:AI13))) | IF(OR(F13="",AK13=""),"",IF(COUNT(AI13:AJ13)=0,"",AK13-LOOKUP(2,1/(AI13:AJ13<>""),AI13:AJ13))) | IF(OR(F13="",AL13=""),"",IF(COUNT(AI13:AK13)=0,"",AL13-LOOKUP(2,1/(AI13:AK13<>""),AI13:AK13))) | IF(OR(F13="",AM13=""),"",IF(COUNT(AI13:AL13)=0,"",AM13-LOOKUP(2,1/(AI13:AL13<>""),AI13:AL13))) | IF(OR(F13="",AN13=""),"",IF(COUNT(AI13:AM13)=0,"",AN13-LOOKUP(2,1/(AI13:AM13<>""),AI13:AM13))) | IF(OR(F13="",AO13=""),"",IF(COUNT(AI13:AN13)=0,"",AO13-LOOKUP(2,1/(AI13:AN13<>""),AI13:AN13))) | IF(OR(F13="",AP13=""),"",IF(COUNT(AI13:AO13)=0,"",AP13-LOOKUP(2,1/(AI13:AO13<>""),AI13:AO13))) | IF(OR(F13="",AQ13=""),"",IF(COUNT(AI13:AP13)=0,"",AQ13-LOOKUP(2,1/(AI13:AP13<>""),AI13:AP13))) | IF(OR(F13="",AR13=""),"",IF(COUNT(AI13:AQ13)=0,"",AR13-LOOKUP(2,1/(AI13:AQ13<>""),AI13:AQ13))) | IF(OR(F13="",AS13=""),"",IF(COUNT(AI13:AR13)=0,"",AS13-LOOKUP(2,1/(AI13:AR13<>""),AI13:AR13))) | IF(OR(F13="",AT13=""),"",IF(COUNT(AI13:AS13)=0,"",AT13-LOOKUP(2,1/(AI13:AS13<>""),AI13:AS13))) | IF(OR(F13="",AU13=""),"",IF(COUNT(AI13:AT13)=0,"",AU13-LOOKUP(2,1/(AI13:AT13<>""),AI13:AT13))) | IF(OR(F13="",AV13=""),"",IF(COUNT(AI13:AU13)=0,"",AV13-LOOKUP(2,1/(AI13:AU13<>""),AI13:AU13))) | IF(J13="","All_Provinces",IFERROR(VLOOKUP(J13,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K13="","All_Districts",IFERROR(VLOOKUP(K13,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F14="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 11 of 39 | AF2-AGF-N-011 | Agroforestry — Daikundi / Sharistan | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daikundi | Sharistan | Saplings: 7000; Seeds kg: 195.5 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ14="","",AQ14) | 2026-04-30 | 12 | 2027-04-01 | IF(W14<>"",W14,IF(OR(T14="",V14=""),"",EDATE(T14,V14))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F14="","",IF(COUNT(AI14:AV14)=0,IF(AA14="","Not started",AA14),SUBSTITUTE(LOOKUP(2,1/(AI14:AV14<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F14="",COUNT(AI14:AV14)=0),"",TODAY()-LOOKUP(2,1/(AI14:AV14<>""),AI14:AV14)) | IF(OR(F14="",COUNT(AI14:AV14)<2),"",LOOKUP(2,1/(AI14:AV14<>""),AI14:AV14)-MIN(AI14:AV14)) | IF(OR(AD14="",AC14="Not started",AC14=""),"",IFERROR(AD14-IF(VLOOKUP(AC14,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC14,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F14="","",IF(OR(AA14="Cancelled",AC14="Cancelled"),"Cancelled",IF(OR(AC14="Completed / Handover",Y14<>"",Z14>=100),"Completed — on track",IF(O14="Not awarded",IF(U14="",IF(X14="","No planned date",IF(TODAY()>X14,"Behind — past planned date",IF(X14-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U14,"Behind — award date passed",IF(U14-TODAY()<=30,"At risk — close to off track","On track"))),IF(X14="","No planned date",IF(AND(TODAY()>X14,OR(Z14="",Z14<100)),"Behind — past end date",IF(AND(T14<>"",X14<>"",Z14<>"",(Z14<100),((TODAY()-T14)/MAX(X14-T14,1)*100)-Z14>15),"Behind — progress lag",IF(AND(X14-TODAY()<=30,X14-TODAY()>=0,OR(Z14="",Z14<90)),"At risk — close to off track","On track")))))))) | IF(OR(F14="",AC14="Completed / Handover",AC14="Cancelled"),"",IF(O14="Not awarded",IF(U14<>"",U14-TODAY(),IF(X14="","",X14-TODAY())),IF(X14="","",X14-TODAY()))) | [14 empty] | IF(OR(F14="",AJ14=""),"",IF(COUNT(AI14:AI14)=0,"",AJ14-LOOKUP(2,1/(AI14:AI14<>""),AI14:AI14))) | IF(OR(F14="",AK14=""),"",IF(COUNT(AI14:AJ14)=0,"",AK14-LOOKUP(2,1/(AI14:AJ14<>""),AI14:AJ14))) | IF(OR(F14="",AL14=""),"",IF(COUNT(AI14:AK14)=0,"",AL14-LOOKUP(2,1/(AI14:AK14<>""),AI14:AK14))) | IF(OR(F14="",AM14=""),"",IF(COUNT(AI14:AL14)=0,"",AM14-LOOKUP(2,1/(AI14:AL14<>""),AI14:AL14))) | IF(OR(F14="",AN14=""),"",IF(COUNT(AI14:AM14)=0,"",AN14-LOOKUP(2,1/(AI14:AM14<>""),AI14:AM14))) | IF(OR(F14="",AO14=""),"",IF(COUNT(AI14:AN14)=0,"",AO14-LOOKUP(2,1/(AI14:AN14<>""),AI14:AN14))) | IF(OR(F14="",AP14=""),"",IF(COUNT(AI14:AO14)=0,"",AP14-LOOKUP(2,1/(AI14:AO14<>""),AI14:AO14))) | IF(OR(F14="",AQ14=""),"",IF(COUNT(AI14:AP14)=0,"",AQ14-LOOKUP(2,1/(AI14:AP14<>""),AI14:AP14))) | IF(OR(F14="",AR14=""),"",IF(COUNT(AI14:AQ14)=0,"",AR14-LOOKUP(2,1/(AI14:AQ14<>""),AI14:AQ14))) | IF(OR(F14="",AS14=""),"",IF(COUNT(AI14:AR14)=0,"",AS14-LOOKUP(2,1/(AI14:AR14<>""),AI14:AR14))) | IF(OR(F14="",AT14=""),"",IF(COUNT(AI14:AS14)=0,"",AT14-LOOKUP(2,1/(AI14:AS14<>""),AI14:AS14))) | IF(OR(F14="",AU14=""),"",IF(COUNT(AI14:AT14)=0,"",AU14-LOOKUP(2,1/(AI14:AT14<>""),AI14:AT14))) | IF(OR(F14="",AV14=""),"",IF(COUNT(AI14:AU14)=0,"",AV14-LOOKUP(2,1/(AI14:AU14<>""),AI14:AU14))) | IF(J14="","All_Provinces",IFERROR(VLOOKUP(J14,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K14="","All_Districts",IFERROR(VLOOKUP(K14,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F15="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 12 of 39 | AF2-AGF-N-012 | Agroforestry — Faryab / Almar | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Faryab | Almar | Saplings: 0; Seeds kg: 154 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ15="","",AQ15) | 2026-04-30 | 12 | 2027-04-01 | IF(W15<>"",W15,IF(OR(T15="",V15=""),"",EDATE(T15,V15))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F15="","",IF(COUNT(AI15:AV15)=0,IF(AA15="","Not started",AA15),SUBSTITUTE(LOOKUP(2,1/(AI15:AV15<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F15="",COUNT(AI15:AV15)=0),"",TODAY()-LOOKUP(2,1/(AI15:AV15<>""),AI15:AV15)) | IF(OR(F15="",COUNT(AI15:AV15)<2),"",LOOKUP(2,1/(AI15:AV15<>""),AI15:AV15)-MIN(AI15:AV15)) | IF(OR(AD15="",AC15="Not started",AC15=""),"",IFERROR(AD15-IF(VLOOKUP(AC15,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC15,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F15="","",IF(OR(AA15="Cancelled",AC15="Cancelled"),"Cancelled",IF(OR(AC15="Completed / Handover",Y15<>"",Z15>=100),"Completed — on track",IF(O15="Not awarded",IF(U15="",IF(X15="","No planned date",IF(TODAY()>X15,"Behind — past planned date",IF(X15-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U15,"Behind — award date passed",IF(U15-TODAY()<=30,"At risk — close to off track","On track"))),IF(X15="","No planned date",IF(AND(TODAY()>X15,OR(Z15="",Z15<100)),"Behind — past end date",IF(AND(T15<>"",X15<>"",Z15<>"",(Z15<100),((TODAY()-T15)/MAX(X15-T15,1)*100)-Z15>15),"Behind — progress lag",IF(AND(X15-TODAY()<=30,X15-TODAY()>=0,OR(Z15="",Z15<90)),"At risk — close to off track","On track")))))))) | IF(OR(F15="",AC15="Completed / Handover",AC15="Cancelled"),"",IF(O15="Not awarded",IF(U15<>"",U15-TODAY(),IF(X15="","",X15-TODAY())),IF(X15="","",X15-TODAY()))) | [14 empty] | IF(OR(F15="",AJ15=""),"",IF(COUNT(AI15:AI15)=0,"",AJ15-LOOKUP(2,1/(AI15:AI15<>""),AI15:AI15))) | IF(OR(F15="",AK15=""),"",IF(COUNT(AI15:AJ15)=0,"",AK15-LOOKUP(2,1/(AI15:AJ15<>""),AI15:AJ15))) | IF(OR(F15="",AL15=""),"",IF(COUNT(AI15:AK15)=0,"",AL15-LOOKUP(2,1/(AI15:AK15<>""),AI15:AK15))) | IF(OR(F15="",AM15=""),"",IF(COUNT(AI15:AL15)=0,"",AM15-LOOKUP(2,1/(AI15:AL15<>""),AI15:AL15))) | IF(OR(F15="",AN15=""),"",IF(COUNT(AI15:AM15)=0,"",AN15-LOOKUP(2,1/(AI15:AM15<>""),AI15:AM15))) | IF(OR(F15="",AO15=""),"",IF(COUNT(AI15:AN15)=0,"",AO15-LOOKUP(2,1/(AI15:AN15<>""),AI15:AN15))) | IF(OR(F15="",AP15=""),"",IF(COUNT(AI15:AO15)=0,"",AP15-LOOKUP(2,1/(AI15:AO15<>""),AI15:AO15))) | IF(OR(F15="",AQ15=""),"",IF(COUNT(AI15:AP15)=0,"",AQ15-LOOKUP(2,1/(AI15:AP15<>""),AI15:AP15))) | IF(OR(F15="",AR15=""),"",IF(COUNT(AI15:AQ15)=0,"",AR15-LOOKUP(2,1/(AI15:AQ15<>""),AI15:AQ15))) | IF(OR(F15="",AS15=""),"",IF(COUNT(AI15:AR15)=0,"",AS15-LOOKUP(2,1/(AI15:AR15<>""),AI15:AR15))) | IF(OR(F15="",AT15=""),"",IF(COUNT(AI15:AS15)=0,"",AT15-LOOKUP(2,1/(AI15:AS15<>""),AI15:AS15))) | IF(OR(F15="",AU15=""),"",IF(COUNT(AI15:AT15)=0,"",AU15-LOOKUP(2,1/(AI15:AT15<>""),AI15:AT15))) | IF(OR(F15="",AV15=""),"",IF(COUNT(AI15:AU15)=0,"",AV15-LOOKUP(2,1/(AI15:AU15<>""),AI15:AU15))) | IF(J15="","All_Provinces",IFERROR(VLOOKUP(J15,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K15="","All_Districts",IFERROR(VLOOKUP(K15,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F16="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 13 of 39 | AF2-AGF-N-013 | Agroforestry — Faryab / Khoja Sabz Posh | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Faryab | Khoja Sabz Posh | Saplings: 3250; Seeds kg: 154 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ16="","",AQ16) | 2026-04-30 | 12 | 2027-04-01 | IF(W16<>"",W16,IF(OR(T16="",V16=""),"",EDATE(T16,V16))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F16="","",IF(COUNT(AI16:AV16)=0,IF(AA16="","Not started",AA16),SUBSTITUTE(LOOKUP(2,1/(AI16:AV16<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F16="",COUNT(AI16:AV16)=0),"",TODAY()-LOOKUP(2,1/(AI16:AV16<>""),AI16:AV16)) | IF(OR(F16="",COUNT(AI16:AV16)<2),"",LOOKUP(2,1/(AI16:AV16<>""),AI16:AV16)-MIN(AI16:AV16)) | IF(OR(AD16="",AC16="Not started",AC16=""),"",IFERROR(AD16-IF(VLOOKUP(AC16,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC16,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F16="","",IF(OR(AA16="Cancelled",AC16="Cancelled"),"Cancelled",IF(OR(AC16="Completed / Handover",Y16<>"",Z16>=100),"Completed — on track",IF(O16="Not awarded",IF(U16="",IF(X16="","No planned date",IF(TODAY()>X16,"Behind — past planned date",IF(X16-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U16,"Behind — award date passed",IF(U16-TODAY()<=30,"At risk — close to off track","On track"))),IF(X16="","No planned date",IF(AND(TODAY()>X16,OR(Z16="",Z16<100)),"Behind — past end date",IF(AND(T16<>"",X16<>"",Z16<>"",(Z16<100),((TODAY()-T16)/MAX(X16-T16,1)*100)-Z16>15),"Behind — progress lag",IF(AND(X16-TODAY()<=30,X16-TODAY()>=0,OR(Z16="",Z16<90)),"At risk — close to off track","On track")))))))) | IF(OR(F16="",AC16="Completed / Handover",AC16="Cancelled"),"",IF(O16="Not awarded",IF(U16<>"",U16-TODAY(),IF(X16="","",X16-TODAY())),IF(X16="","",X16-TODAY()))) | [14 empty] | IF(OR(F16="",AJ16=""),"",IF(COUNT(AI16:AI16)=0,"",AJ16-LOOKUP(2,1/(AI16:AI16<>""),AI16:AI16))) | IF(OR(F16="",AK16=""),"",IF(COUNT(AI16:AJ16)=0,"",AK16-LOOKUP(2,1/(AI16:AJ16<>""),AI16:AJ16))) | IF(OR(F16="",AL16=""),"",IF(COUNT(AI16:AK16)=0,"",AL16-LOOKUP(2,1/(AI16:AK16<>""),AI16:AK16))) | IF(OR(F16="",AM16=""),"",IF(COUNT(AI16:AL16)=0,"",AM16-LOOKUP(2,1/(AI16:AL16<>""),AI16:AL16))) | IF(OR(F16="",AN16=""),"",IF(COUNT(AI16:AM16)=0,"",AN16-LOOKUP(2,1/(AI16:AM16<>""),AI16:AM16))) | IF(OR(F16="",AO16=""),"",IF(COUNT(AI16:AN16)=0,"",AO16-LOOKUP(2,1/(AI16:AN16<>""),AI16:AN16))) | IF(OR(F16="",AP16=""),"",IF(COUNT(AI16:AO16)=0,"",AP16-LOOKUP(2,1/(AI16:AO16<>""),AI16:AO16))) | IF(OR(F16="",AQ16=""),"",IF(COUNT(AI16:AP16)=0,"",AQ16-LOOKUP(2,1/(AI16:AP16<>""),AI16:AP16))) | IF(OR(F16="",AR16=""),"",IF(COUNT(AI16:AQ16)=0,"",AR16-LOOKUP(2,1/(AI16:AQ16<>""),AI16:AQ16))) | IF(OR(F16="",AS16=""),"",IF(COUNT(AI16:AR16)=0,"",AS16-LOOKUP(2,1/(AI16:AR16<>""),AI16:AR16))) | IF(OR(F16="",AT16=""),"",IF(COUNT(AI16:AS16)=0,"",AT16-LOOKUP(2,1/(AI16:AS16<>""),AI16:AS16))) | IF(OR(F16="",AU16=""),"",IF(COUNT(AI16:AT16)=0,"",AU16-LOOKUP(2,1/(AI16:AT16<>""),AI16:AT16))) | IF(OR(F16="",AV16=""),"",IF(COUNT(AI16:AU16)=0,"",AV16-LOOKUP(2,1/(AI16:AU16<>""),AI16:AU16))) | IF(J16="","All_Provinces",IFERROR(VLOOKUP(J16,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K16="","All_Districts",IFERROR(VLOOKUP(K16,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F17="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 14 of 39 | AF2-AGF-N-014 | Agroforestry — Ghor / Allahyar | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Allahyar | Saplings: 5000; Seeds kg: 363 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ17="","",AQ17) | 2026-04-30 | 12 | 2027-04-01 | IF(W17<>"",W17,IF(OR(T17="",V17=""),"",EDATE(T17,V17))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F17="","",IF(COUNT(AI17:AV17)=0,IF(AA17="","Not started",AA17),SUBSTITUTE(LOOKUP(2,1/(AI17:AV17<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F17="",COUNT(AI17:AV17)=0),"",TODAY()-LOOKUP(2,1/(AI17:AV17<>""),AI17:AV17)) | IF(OR(F17="",COUNT(AI17:AV17)<2),"",LOOKUP(2,1/(AI17:AV17<>""),AI17:AV17)-MIN(AI17:AV17)) | IF(OR(AD17="",AC17="Not started",AC17=""),"",IFERROR(AD17-IF(VLOOKUP(AC17,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC17,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F17="","",IF(OR(AA17="Cancelled",AC17="Cancelled"),"Cancelled",IF(OR(AC17="Completed / Handover",Y17<>"",Z17>=100),"Completed — on track",IF(O17="Not awarded",IF(U17="",IF(X17="","No planned date",IF(TODAY()>X17,"Behind — past planned date",IF(X17-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U17,"Behind — award date passed",IF(U17-TODAY()<=30,"At risk — close to off track","On track"))),IF(X17="","No planned date",IF(AND(TODAY()>X17,OR(Z17="",Z17<100)),"Behind — past end date",IF(AND(T17<>"",X17<>"",Z17<>"",(Z17<100),((TODAY()-T17)/MAX(X17-T17,1)*100)-Z17>15),"Behind — progress lag",IF(AND(X17-TODAY()<=30,X17-TODAY()>=0,OR(Z17="",Z17<90)),"At risk — close to off track","On track")))))))) | IF(OR(F17="",AC17="Completed / Handover",AC17="Cancelled"),"",IF(O17="Not awarded",IF(U17<>"",U17-TODAY(),IF(X17="","",X17-TODAY())),IF(X17="","",X17-TODAY()))) | [14 empty] | IF(OR(F17="",AJ17=""),"",IF(COUNT(AI17:AI17)=0,"",AJ17-LOOKUP(2,1/(AI17:AI17<>""),AI17:AI17))) | IF(OR(F17="",AK17=""),"",IF(COUNT(AI17:AJ17)=0,"",AK17-LOOKUP(2,1/(AI17:AJ17<>""),AI17:AJ17))) | IF(OR(F17="",AL17=""),"",IF(COUNT(AI17:AK17)=0,"",AL17-LOOKUP(2,1/(AI17:AK17<>""),AI17:AK17))) | IF(OR(F17="",AM17=""),"",IF(COUNT(AI17:AL17)=0,"",AM17-LOOKUP(2,1/(AI17:AL17<>""),AI17:AL17))) | IF(OR(F17="",AN17=""),"",IF(COUNT(AI17:AM17)=0,"",AN17-LOOKUP(2,1/(AI17:AM17<>""),AI17:AM17))) | IF(OR(F17="",AO17=""),"",IF(COUNT(AI17:AN17)=0,"",AO17-LOOKUP(2,1/(AI17:AN17<>""),AI17:AN17))) | IF(OR(F17="",AP17=""),"",IF(COUNT(AI17:AO17)=0,"",AP17-LOOKUP(2,1/(AI17:AO17<>""),AI17:AO17))) | IF(OR(F17="",AQ17=""),"",IF(COUNT(AI17:AP17)=0,"",AQ17-LOOKUP(2,1/(AI17:AP17<>""),AI17:AP17))) | IF(OR(F17="",AR17=""),"",IF(COUNT(AI17:AQ17)=0,"",AR17-LOOKUP(2,1/(AI17:AQ17<>""),AI17:AQ17))) | IF(OR(F17="",AS17=""),"",IF(COUNT(AI17:AR17)=0,"",AS17-LOOKUP(2,1/(AI17:AR17<>""),AI17:AR17))) | IF(OR(F17="",AT17=""),"",IF(COUNT(AI17:AS17)=0,"",AT17-LOOKUP(2,1/(AI17:AS17<>""),AI17:AS17))) | IF(OR(F17="",AU17=""),"",IF(COUNT(AI17:AT17)=0,"",AU17-LOOKUP(2,1/(AI17:AT17<>""),AI17:AT17))) | IF(OR(F17="",AV17=""),"",IF(COUNT(AI17:AU17)=0,"",AV17-LOOKUP(2,1/(AI17:AU17<>""),AI17:AU17))) | IF(J17="","All_Provinces",IFERROR(VLOOKUP(J17,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K17="","All_Districts",IFERROR(VLOOKUP(K17,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F18="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 15 of 39 | AF2-AGF-N-015 | Agroforestry — Ghor / Shahrak | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Shahrak | Saplings: 10000; Seeds kg: 487 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ18="","",AQ18) | 2026-04-30 | 12 | 2027-04-01 | IF(W18<>"",W18,IF(OR(T18="",V18=""),"",EDATE(T18,V18))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F18="","",IF(COUNT(AI18:AV18)=0,IF(AA18="","Not started",AA18),SUBSTITUTE(LOOKUP(2,1/(AI18:AV18<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F18="",COUNT(AI18:AV18)=0),"",TODAY()-LOOKUP(2,1/(AI18:AV18<>""),AI18:AV18)) | IF(OR(F18="",COUNT(AI18:AV18)<2),"",LOOKUP(2,1/(AI18:AV18<>""),AI18:AV18)-MIN(AI18:AV18)) | IF(OR(AD18="",AC18="Not started",AC18=""),"",IFERROR(AD18-IF(VLOOKUP(AC18,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC18,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F18="","",IF(OR(AA18="Cancelled",AC18="Cancelled"),"Cancelled",IF(OR(AC18="Completed / Handover",Y18<>"",Z18>=100),"Completed — on track",IF(O18="Not awarded",IF(U18="",IF(X18="","No planned date",IF(TODAY()>X18,"Behind — past planned date",IF(X18-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U18,"Behind — award date passed",IF(U18-TODAY()<=30,"At risk — close to off track","On track"))),IF(X18="","No planned date",IF(AND(TODAY()>X18,OR(Z18="",Z18<100)),"Behind — past end date",IF(AND(T18<>"",X18<>"",Z18<>"",(Z18<100),((TODAY()-T18)/MAX(X18-T18,1)*100)-Z18>15),"Behind — progress lag",IF(AND(X18-TODAY()<=30,X18-TODAY()>=0,OR(Z18="",Z18<90)),"At risk — close to off track","On track")))))))) | IF(OR(F18="",AC18="Completed / Handover",AC18="Cancelled"),"",IF(O18="Not awarded",IF(U18<>"",U18-TODAY(),IF(X18="","",X18-TODAY())),IF(X18="","",X18-TODAY()))) | [14 empty] | IF(OR(F18="",AJ18=""),"",IF(COUNT(AI18:AI18)=0,"",AJ18-LOOKUP(2,1/(AI18:AI18<>""),AI18:AI18))) | IF(OR(F18="",AK18=""),"",IF(COUNT(AI18:AJ18)=0,"",AK18-LOOKUP(2,1/(AI18:AJ18<>""),AI18:AJ18))) | IF(OR(F18="",AL18=""),"",IF(COUNT(AI18:AK18)=0,"",AL18-LOOKUP(2,1/(AI18:AK18<>""),AI18:AK18))) | IF(OR(F18="",AM18=""),"",IF(COUNT(AI18:AL18)=0,"",AM18-LOOKUP(2,1/(AI18:AL18<>""),AI18:AL18))) | IF(OR(F18="",AN18=""),"",IF(COUNT(AI18:AM18)=0,"",AN18-LOOKUP(2,1/(AI18:AM18<>""),AI18:AM18))) | IF(OR(F18="",AO18=""),"",IF(COUNT(AI18:AN18)=0,"",AO18-LOOKUP(2,1/(AI18:AN18<>""),AI18:AN18))) | IF(OR(F18="",AP18=""),"",IF(COUNT(AI18:AO18)=0,"",AP18-LOOKUP(2,1/(AI18:AO18<>""),AI18:AO18))) | IF(OR(F18="",AQ18=""),"",IF(COUNT(AI18:AP18)=0,"",AQ18-LOOKUP(2,1/(AI18:AP18<>""),AI18:AP18))) | IF(OR(F18="",AR18=""),"",IF(COUNT(AI18:AQ18)=0,"",AR18-LOOKUP(2,1/(AI18:AQ18<>""),AI18:AQ18))) | IF(OR(F18="",AS18=""),"",IF(COUNT(AI18:AR18)=0,"",AS18-LOOKUP(2,1/(AI18:AR18<>""),AI18:AR18))) | IF(OR(F18="",AT18=""),"",IF(COUNT(AI18:AS18)=0,"",AT18-LOOKUP(2,1/(AI18:AS18<>""),AI18:AS18))) | IF(OR(F18="",AU18=""),"",IF(COUNT(AI18:AT18)=0,"",AU18-LOOKUP(2,1/(AI18:AT18<>""),AI18:AT18))) | IF(OR(F18="",AV18=""),"",IF(COUNT(AI18:AU18)=0,"",AV18-LOOKUP(2,1/(AI18:AU18<>""),AI18:AU18))) | IF(J18="","All_Provinces",IFERROR(VLOOKUP(J18,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K18="","All_Districts",IFERROR(VLOOKUP(K18,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F19="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 16 of 39 | AF2-AGF-N-016 | Agroforestry — Helmand / Nawzad | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Nawzad | Saplings: 10032; Seeds kg: 462 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ19="","",AQ19) | 2026-04-30 | 12 | 2027-04-01 | IF(W19<>"",W19,IF(OR(T19="",V19=""),"",EDATE(T19,V19))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F19="","",IF(COUNT(AI19:AV19)=0,IF(AA19="","Not started",AA19),SUBSTITUTE(LOOKUP(2,1/(AI19:AV19<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F19="",COUNT(AI19:AV19)=0),"",TODAY()-LOOKUP(2,1/(AI19:AV19<>""),AI19:AV19)) | IF(OR(F19="",COUNT(AI19:AV19)<2),"",LOOKUP(2,1/(AI19:AV19<>""),AI19:AV19)-MIN(AI19:AV19)) | IF(OR(AD19="",AC19="Not started",AC19=""),"",IFERROR(AD19-IF(VLOOKUP(AC19,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC19,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F19="","",IF(OR(AA19="Cancelled",AC19="Cancelled"),"Cancelled",IF(OR(AC19="Completed / Handover",Y19<>"",Z19>=100),"Completed — on track",IF(O19="Not awarded",IF(U19="",IF(X19="","No planned date",IF(TODAY()>X19,"Behind — past planned date",IF(X19-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U19,"Behind — award date passed",IF(U19-TODAY()<=30,"At risk — close to off track","On track"))),IF(X19="","No planned date",IF(AND(TODAY()>X19,OR(Z19="",Z19<100)),"Behind — past end date",IF(AND(T19<>"",X19<>"",Z19<>"",(Z19<100),((TODAY()-T19)/MAX(X19-T19,1)*100)-Z19>15),"Behind — progress lag",IF(AND(X19-TODAY()<=30,X19-TODAY()>=0,OR(Z19="",Z19<90)),"At risk — close to off track","On track")))))))) | IF(OR(F19="",AC19="Completed / Handover",AC19="Cancelled"),"",IF(O19="Not awarded",IF(U19<>"",U19-TODAY(),IF(X19="","",X19-TODAY())),IF(X19="","",X19-TODAY()))) | [14 empty] | IF(OR(F19="",AJ19=""),"",IF(COUNT(AI19:AI19)=0,"",AJ19-LOOKUP(2,1/(AI19:AI19<>""),AI19:AI19))) | IF(OR(F19="",AK19=""),"",IF(COUNT(AI19:AJ19)=0,"",AK19-LOOKUP(2,1/(AI19:AJ19<>""),AI19:AJ19))) | IF(OR(F19="",AL19=""),"",IF(COUNT(AI19:AK19)=0,"",AL19-LOOKUP(2,1/(AI19:AK19<>""),AI19:AK19))) | IF(OR(F19="",AM19=""),"",IF(COUNT(AI19:AL19)=0,"",AM19-LOOKUP(2,1/(AI19:AL19<>""),AI19:AL19))) | IF(OR(F19="",AN19=""),"",IF(COUNT(AI19:AM19)=0,"",AN19-LOOKUP(2,1/(AI19:AM19<>""),AI19:AM19))) | IF(OR(F19="",AO19=""),"",IF(COUNT(AI19:AN19)=0,"",AO19-LOOKUP(2,1/(AI19:AN19<>""),AI19:AN19))) | IF(OR(F19="",AP19=""),"",IF(COUNT(AI19:AO19)=0,"",AP19-LOOKUP(2,1/(AI19:AO19<>""),AI19:AO19))) | IF(OR(F19="",AQ19=""),"",IF(COUNT(AI19:AP19)=0,"",AQ19-LOOKUP(2,1/(AI19:AP19<>""),AI19:AP19))) | IF(OR(F19="",AR19=""),"",IF(COUNT(AI19:AQ19)=0,"",AR19-LOOKUP(2,1/(AI19:AQ19<>""),AI19:AQ19))) | IF(OR(F19="",AS19=""),"",IF(COUNT(AI19:AR19)=0,"",AS19-LOOKUP(2,1/(AI19:AR19<>""),AI19:AR19))) | IF(OR(F19="",AT19=""),"",IF(COUNT(AI19:AS19)=0,"",AT19-LOOKUP(2,1/(AI19:AS19<>""),AI19:AS19))) | IF(OR(F19="",AU19=""),"",IF(COUNT(AI19:AT19)=0,"",AU19-LOOKUP(2,1/(AI19:AT19<>""),AI19:AT19))) | IF(OR(F19="",AV19=""),"",IF(COUNT(AI19:AU19)=0,"",AV19-LOOKUP(2,1/(AI19:AU19<>""),AI19:AU19))) | IF(J19="","All_Provinces",IFERROR(VLOOKUP(J19,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K19="","All_Districts",IFERROR(VLOOKUP(K19,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F20="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 17 of 39 | AF2-AGF-N-017 | Agroforestry — Herat / Koshk-e-kohna | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Koshk-e-kohna | Saplings: 0; Seeds kg: 40 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ20="","",AQ20) | 2026-04-30 | 12 | 2027-04-01 | IF(W20<>"",W20,IF(OR(T20="",V20=""),"",EDATE(T20,V20))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F20="","",IF(COUNT(AI20:AV20)=0,IF(AA20="","Not started",AA20),SUBSTITUTE(LOOKUP(2,1/(AI20:AV20<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F20="",COUNT(AI20:AV20)=0),"",TODAY()-LOOKUP(2,1/(AI20:AV20<>""),AI20:AV20)) | IF(OR(F20="",COUNT(AI20:AV20)<2),"",LOOKUP(2,1/(AI20:AV20<>""),AI20:AV20)-MIN(AI20:AV20)) | IF(OR(AD20="",AC20="Not started",AC20=""),"",IFERROR(AD20-IF(VLOOKUP(AC20,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC20,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F20="","",IF(OR(AA20="Cancelled",AC20="Cancelled"),"Cancelled",IF(OR(AC20="Completed / Handover",Y20<>"",Z20>=100),"Completed — on track",IF(O20="Not awarded",IF(U20="",IF(X20="","No planned date",IF(TODAY()>X20,"Behind — past planned date",IF(X20-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U20,"Behind — award date passed",IF(U20-TODAY()<=30,"At risk — close to off track","On track"))),IF(X20="","No planned date",IF(AND(TODAY()>X20,OR(Z20="",Z20<100)),"Behind — past end date",IF(AND(T20<>"",X20<>"",Z20<>"",(Z20<100),((TODAY()-T20)/MAX(X20-T20,1)*100)-Z20>15),"Behind — progress lag",IF(AND(X20-TODAY()<=30,X20-TODAY()>=0,OR(Z20="",Z20<90)),"At risk — close to off track","On track")))))))) | IF(OR(F20="",AC20="Completed / Handover",AC20="Cancelled"),"",IF(O20="Not awarded",IF(U20<>"",U20-TODAY(),IF(X20="","",X20-TODAY())),IF(X20="","",X20-TODAY()))) | [14 empty] | IF(OR(F20="",AJ20=""),"",IF(COUNT(AI20:AI20)=0,"",AJ20-LOOKUP(2,1/(AI20:AI20<>""),AI20:AI20))) | IF(OR(F20="",AK20=""),"",IF(COUNT(AI20:AJ20)=0,"",AK20-LOOKUP(2,1/(AI20:AJ20<>""),AI20:AJ20))) | IF(OR(F20="",AL20=""),"",IF(COUNT(AI20:AK20)=0,"",AL20-LOOKUP(2,1/(AI20:AK20<>""),AI20:AK20))) | IF(OR(F20="",AM20=""),"",IF(COUNT(AI20:AL20)=0,"",AM20-LOOKUP(2,1/(AI20:AL20<>""),AI20:AL20))) | IF(OR(F20="",AN20=""),"",IF(COUNT(AI20:AM20)=0,"",AN20-LOOKUP(2,1/(AI20:AM20<>""),AI20:AM20))) | IF(OR(F20="",AO20=""),"",IF(COUNT(AI20:AN20)=0,"",AO20-LOOKUP(2,1/(AI20:AN20<>""),AI20:AN20))) | IF(OR(F20="",AP20=""),"",IF(COUNT(AI20:AO20)=0,"",AP20-LOOKUP(2,1/(AI20:AO20<>""),AI20:AO20))) | IF(OR(F20="",AQ20=""),"",IF(COUNT(AI20:AP20)=0,"",AQ20-LOOKUP(2,1/(AI20:AP20<>""),AI20:AP20))) | IF(OR(F20="",AR20=""),"",IF(COUNT(AI20:AQ20)=0,"",AR20-LOOKUP(2,1/(AI20:AQ20<>""),AI20:AQ20))) | IF(OR(F20="",AS20=""),"",IF(COUNT(AI20:AR20)=0,"",AS20-LOOKUP(2,1/(AI20:AR20<>""),AI20:AR20))) | IF(OR(F20="",AT20=""),"",IF(COUNT(AI20:AS20)=0,"",AT20-LOOKUP(2,1/(AI20:AS20<>""),AI20:AS20))) | IF(OR(F20="",AU20=""),"",IF(COUNT(AI20:AT20)=0,"",AU20-LOOKUP(2,1/(AI20:AT20<>""),AI20:AT20))) | IF(OR(F20="",AV20=""),"",IF(COUNT(AI20:AU20)=0,"",AV20-LOOKUP(2,1/(AI20:AU20<>""),AI20:AU20))) | IF(J20="","All_Provinces",IFERROR(VLOOKUP(J20,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K20="","All_Districts",IFERROR(VLOOKUP(K20,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F21="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 18 of 39 | AF2-AGF-N-018 | Agroforestry — Herat / Rabat Sangi | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Rabat Sangi | Saplings: 0; Seeds kg: 30 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ21="","",AQ21) | 2026-04-30 | 12 | 2027-04-01 | IF(W21<>"",W21,IF(OR(T21="",V21=""),"",EDATE(T21,V21))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F21="","",IF(COUNT(AI21:AV21)=0,IF(AA21="","Not started",AA21),SUBSTITUTE(LOOKUP(2,1/(AI21:AV21<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F21="",COUNT(AI21:AV21)=0),"",TODAY()-LOOKUP(2,1/(AI21:AV21<>""),AI21:AV21)) | IF(OR(F21="",COUNT(AI21:AV21)<2),"",LOOKUP(2,1/(AI21:AV21<>""),AI21:AV21)-MIN(AI21:AV21)) | IF(OR(AD21="",AC21="Not started",AC21=""),"",IFERROR(AD21-IF(VLOOKUP(AC21,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC21,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F21="","",IF(OR(AA21="Cancelled",AC21="Cancelled"),"Cancelled",IF(OR(AC21="Completed / Handover",Y21<>"",Z21>=100),"Completed — on track",IF(O21="Not awarded",IF(U21="",IF(X21="","No planned date",IF(TODAY()>X21,"Behind — past planned date",IF(X21-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U21,"Behind — award date passed",IF(U21-TODAY()<=30,"At risk — close to off track","On track"))),IF(X21="","No planned date",IF(AND(TODAY()>X21,OR(Z21="",Z21<100)),"Behind — past end date",IF(AND(T21<>"",X21<>"",Z21<>"",(Z21<100),((TODAY()-T21)/MAX(X21-T21,1)*100)-Z21>15),"Behind — progress lag",IF(AND(X21-TODAY()<=30,X21-TODAY()>=0,OR(Z21="",Z21<90)),"At risk — close to off track","On track")))))))) | IF(OR(F21="",AC21="Completed / Handover",AC21="Cancelled"),"",IF(O21="Not awarded",IF(U21<>"",U21-TODAY(),IF(X21="","",X21-TODAY())),IF(X21="","",X21-TODAY()))) | [14 empty] | IF(OR(F21="",AJ21=""),"",IF(COUNT(AI21:AI21)=0,"",AJ21-LOOKUP(2,1/(AI21:AI21<>""),AI21:AI21))) | IF(OR(F21="",AK21=""),"",IF(COUNT(AI21:AJ21)=0,"",AK21-LOOKUP(2,1/(AI21:AJ21<>""),AI21:AJ21))) | IF(OR(F21="",AL21=""),"",IF(COUNT(AI21:AK21)=0,"",AL21-LOOKUP(2,1/(AI21:AK21<>""),AI21:AK21))) | IF(OR(F21="",AM21=""),"",IF(COUNT(AI21:AL21)=0,"",AM21-LOOKUP(2,1/(AI21:AL21<>""),AI21:AL21))) | IF(OR(F21="",AN21=""),"",IF(COUNT(AI21:AM21)=0,"",AN21-LOOKUP(2,1/(AI21:AM21<>""),AI21:AM21))) | IF(OR(F21="",AO21=""),"",IF(COUNT(AI21:AN21)=0,"",AO21-LOOKUP(2,1/(AI21:AN21<>""),AI21:AN21))) | IF(OR(F21="",AP21=""),"",IF(COUNT(AI21:AO21)=0,"",AP21-LOOKUP(2,1/(AI21:AO21<>""),AI21:AO21))) | IF(OR(F21="",AQ21=""),"",IF(COUNT(AI21:AP21)=0,"",AQ21-LOOKUP(2,1/(AI21:AP21<>""),AI21:AP21))) | IF(OR(F21="",AR21=""),"",IF(COUNT(AI21:AQ21)=0,"",AR21-LOOKUP(2,1/(AI21:AQ21<>""),AI21:AQ21))) | IF(OR(F21="",AS21=""),"",IF(COUNT(AI21:AR21)=0,"",AS21-LOOKUP(2,1/(AI21:AR21<>""),AI21:AR21))) | IF(OR(F21="",AT21=""),"",IF(COUNT(AI21:AS21)=0,"",AT21-LOOKUP(2,1/(AI21:AS21<>""),AI21:AS21))) | IF(OR(F21="",AU21=""),"",IF(COUNT(AI21:AT21)=0,"",AU21-LOOKUP(2,1/(AI21:AT21<>""),AI21:AT21))) | IF(OR(F21="",AV21=""),"",IF(COUNT(AI21:AU21)=0,"",AV21-LOOKUP(2,1/(AI21:AU21<>""),AI21:AU21))) | IF(J21="","All_Provinces",IFERROR(VLOOKUP(J21,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K21="","All_Districts",IFERROR(VLOOKUP(K21,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F22="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 19 of 39 | AF2-AGF-N-019 | Agroforestry — Jawzgan / Sheberghan | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Jawzgan | Sheberghan | Saplings: 3250; Seeds kg: 0 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ22="","",AQ22) | 2026-04-30 | 12 | 2027-04-01 | IF(W22<>"",W22,IF(OR(T22="",V22=""),"",EDATE(T22,V22))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F22="","",IF(COUNT(AI22:AV22)=0,IF(AA22="","Not started",AA22),SUBSTITUTE(LOOKUP(2,1/(AI22:AV22<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F22="",COUNT(AI22:AV22)=0),"",TODAY()-LOOKUP(2,1/(AI22:AV22<>""),AI22:AV22)) | IF(OR(F22="",COUNT(AI22:AV22)<2),"",LOOKUP(2,1/(AI22:AV22<>""),AI22:AV22)-MIN(AI22:AV22)) | IF(OR(AD22="",AC22="Not started",AC22=""),"",IFERROR(AD22-IF(VLOOKUP(AC22,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC22,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F22="","",IF(OR(AA22="Cancelled",AC22="Cancelled"),"Cancelled",IF(OR(AC22="Completed / Handover",Y22<>"",Z22>=100),"Completed — on track",IF(O22="Not awarded",IF(U22="",IF(X22="","No planned date",IF(TODAY()>X22,"Behind — past planned date",IF(X22-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U22,"Behind — award date passed",IF(U22-TODAY()<=30,"At risk — close to off track","On track"))),IF(X22="","No planned date",IF(AND(TODAY()>X22,OR(Z22="",Z22<100)),"Behind — past end date",IF(AND(T22<>"",X22<>"",Z22<>"",(Z22<100),((TODAY()-T22)/MAX(X22-T22,1)*100)-Z22>15),"Behind — progress lag",IF(AND(X22-TODAY()<=30,X22-TODAY()>=0,OR(Z22="",Z22<90)),"At risk — close to off track","On track")))))))) | IF(OR(F22="",AC22="Completed / Handover",AC22="Cancelled"),"",IF(O22="Not awarded",IF(U22<>"",U22-TODAY(),IF(X22="","",X22-TODAY())),IF(X22="","",X22-TODAY()))) | [14 empty] | IF(OR(F22="",AJ22=""),"",IF(COUNT(AI22:AI22)=0,"",AJ22-LOOKUP(2,1/(AI22:AI22<>""),AI22:AI22))) | IF(OR(F22="",AK22=""),"",IF(COUNT(AI22:AJ22)=0,"",AK22-LOOKUP(2,1/(AI22:AJ22<>""),AI22:AJ22))) | IF(OR(F22="",AL22=""),"",IF(COUNT(AI22:AK22)=0,"",AL22-LOOKUP(2,1/(AI22:AK22<>""),AI22:AK22))) | IF(OR(F22="",AM22=""),"",IF(COUNT(AI22:AL22)=0,"",AM22-LOOKUP(2,1/(AI22:AL22<>""),AI22:AL22))) | IF(OR(F22="",AN22=""),"",IF(COUNT(AI22:AM22)=0,"",AN22-LOOKUP(2,1/(AI22:AM22<>""),AI22:AM22))) | IF(OR(F22="",AO22=""),"",IF(COUNT(AI22:AN22)=0,"",AO22-LOOKUP(2,1/(AI22:AN22<>""),AI22:AN22))) | IF(OR(F22="",AP22=""),"",IF(COUNT(AI22:AO22)=0,"",AP22-LOOKUP(2,1/(AI22:AO22<>""),AI22:AO22))) | IF(OR(F22="",AQ22=""),"",IF(COUNT(AI22:AP22)=0,"",AQ22-LOOKUP(2,1/(AI22:AP22<>""),AI22:AP22))) | IF(OR(F22="",AR22=""),"",IF(COUNT(AI22:AQ22)=0,"",AR22-LOOKUP(2,1/(AI22:AQ22<>""),AI22:AQ22))) | IF(OR(F22="",AS22=""),"",IF(COUNT(AI22:AR22)=0,"",AS22-LOOKUP(2,1/(AI22:AR22<>""),AI22:AR22))) | IF(OR(F22="",AT22=""),"",IF(COUNT(AI22:AS22)=0,"",AT22-LOOKUP(2,1/(AI22:AS22<>""),AI22:AS22))) | IF(OR(F22="",AU22=""),"",IF(COUNT(AI22:AT22)=0,"",AU22-LOOKUP(2,1/(AI22:AT22<>""),AI22:AT22))) | IF(OR(F22="",AV22=""),"",IF(COUNT(AI22:AU22)=0,"",AV22-LOOKUP(2,1/(AI22:AU22<>""),AI22:AU22))) | IF(J22="","All_Provinces",IFERROR(VLOOKUP(J22,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K22="","All_Districts",IFERROR(VLOOKUP(K22,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F23="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 20 of 39 | AF2-AGF-N-020 | Agroforestry — Kabul / Surubi | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Surubi | Saplings: 10000; Seeds kg: 250 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ23="","",AQ23) | 2026-04-30 | 12 | 2027-04-01 | IF(W23<>"",W23,IF(OR(T23="",V23=""),"",EDATE(T23,V23))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F23="","",IF(COUNT(AI23:AV23)=0,IF(AA23="","Not started",AA23),SUBSTITUTE(LOOKUP(2,1/(AI23:AV23<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F23="",COUNT(AI23:AV23)=0),"",TODAY()-LOOKUP(2,1/(AI23:AV23<>""),AI23:AV23)) | IF(OR(F23="",COUNT(AI23:AV23)<2),"",LOOKUP(2,1/(AI23:AV23<>""),AI23:AV23)-MIN(AI23:AV23)) | IF(OR(AD23="",AC23="Not started",AC23=""),"",IFERROR(AD23-IF(VLOOKUP(AC23,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC23,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F23="","",IF(OR(AA23="Cancelled",AC23="Cancelled"),"Cancelled",IF(OR(AC23="Completed / Handover",Y23<>"",Z23>=100),"Completed — on track",IF(O23="Not awarded",IF(U23="",IF(X23="","No planned date",IF(TODAY()>X23,"Behind — past planned date",IF(X23-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U23,"Behind — award date passed",IF(U23-TODAY()<=30,"At risk — close to off track","On track"))),IF(X23="","No planned date",IF(AND(TODAY()>X23,OR(Z23="",Z23<100)),"Behind — past end date",IF(AND(T23<>"",X23<>"",Z23<>"",(Z23<100),((TODAY()-T23)/MAX(X23-T23,1)*100)-Z23>15),"Behind — progress lag",IF(AND(X23-TODAY()<=30,X23-TODAY()>=0,OR(Z23="",Z23<90)),"At risk — close to off track","On track")))))))) | IF(OR(F23="",AC23="Completed / Handover",AC23="Cancelled"),"",IF(O23="Not awarded",IF(U23<>"",U23-TODAY(),IF(X23="","",X23-TODAY())),IF(X23="","",X23-TODAY()))) | [14 empty] | IF(OR(F23="",AJ23=""),"",IF(COUNT(AI23:AI23)=0,"",AJ23-LOOKUP(2,1/(AI23:AI23<>""),AI23:AI23))) | IF(OR(F23="",AK23=""),"",IF(COUNT(AI23:AJ23)=0,"",AK23-LOOKUP(2,1/(AI23:AJ23<>""),AI23:AJ23))) | IF(OR(F23="",AL23=""),"",IF(COUNT(AI23:AK23)=0,"",AL23-LOOKUP(2,1/(AI23:AK23<>""),AI23:AK23))) | IF(OR(F23="",AM23=""),"",IF(COUNT(AI23:AL23)=0,"",AM23-LOOKUP(2,1/(AI23:AL23<>""),AI23:AL23))) | IF(OR(F23="",AN23=""),"",IF(COUNT(AI23:AM23)=0,"",AN23-LOOKUP(2,1/(AI23:AM23<>""),AI23:AM23))) | IF(OR(F23="",AO23=""),"",IF(COUNT(AI23:AN23)=0,"",AO23-LOOKUP(2,1/(AI23:AN23<>""),AI23:AN23))) | IF(OR(F23="",AP23=""),"",IF(COUNT(AI23:AO23)=0,"",AP23-LOOKUP(2,1/(AI23:AO23<>""),AI23:AO23))) | IF(OR(F23="",AQ23=""),"",IF(COUNT(AI23:AP23)=0,"",AQ23-LOOKUP(2,1/(AI23:AP23<>""),AI23:AP23))) | IF(OR(F23="",AR23=""),"",IF(COUNT(AI23:AQ23)=0,"",AR23-LOOKUP(2,1/(AI23:AQ23<>""),AI23:AQ23))) | IF(OR(F23="",AS23=""),"",IF(COUNT(AI23:AR23)=0,"",AS23-LOOKUP(2,1/(AI23:AR23<>""),AI23:AR23))) | IF(OR(F23="",AT23=""),"",IF(COUNT(AI23:AS23)=0,"",AT23-LOOKUP(2,1/(AI23:AS23<>""),AI23:AS23))) | IF(OR(F23="",AU23=""),"",IF(COUNT(AI23:AT23)=0,"",AU23-LOOKUP(2,1/(AI23:AT23<>""),AI23:AT23))) | IF(OR(F23="",AV23=""),"",IF(COUNT(AI23:AU23)=0,"",AV23-LOOKUP(2,1/(AI23:AU23<>""),AI23:AU23))) | IF(J23="","All_Provinces",IFERROR(VLOOKUP(J23,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K23="","All_Districts",IFERROR(VLOOKUP(K23,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F24="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 21 of 39 | AF2-AGF-N-021 | Agroforestry — Khost / Musa Khil | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Musa Khil | Saplings: 7080; Seeds kg: 82 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ24="","",AQ24) | 2026-04-30 | 12 | 2027-04-01 | IF(W24<>"",W24,IF(OR(T24="",V24=""),"",EDATE(T24,V24))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F24="","",IF(COUNT(AI24:AV24)=0,IF(AA24="","Not started",AA24),SUBSTITUTE(LOOKUP(2,1/(AI24:AV24<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F24="",COUNT(AI24:AV24)=0),"",TODAY()-LOOKUP(2,1/(AI24:AV24<>""),AI24:AV24)) | IF(OR(F24="",COUNT(AI24:AV24)<2),"",LOOKUP(2,1/(AI24:AV24<>""),AI24:AV24)-MIN(AI24:AV24)) | IF(OR(AD24="",AC24="Not started",AC24=""),"",IFERROR(AD24-IF(VLOOKUP(AC24,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC24,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F24="","",IF(OR(AA24="Cancelled",AC24="Cancelled"),"Cancelled",IF(OR(AC24="Completed / Handover",Y24<>"",Z24>=100),"Completed — on track",IF(O24="Not awarded",IF(U24="",IF(X24="","No planned date",IF(TODAY()>X24,"Behind — past planned date",IF(X24-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U24,"Behind — award date passed",IF(U24-TODAY()<=30,"At risk — close to off track","On track"))),IF(X24="","No planned date",IF(AND(TODAY()>X24,OR(Z24="",Z24<100)),"Behind — past end date",IF(AND(T24<>"",X24<>"",Z24<>"",(Z24<100),((TODAY()-T24)/MAX(X24-T24,1)*100)-Z24>15),"Behind — progress lag",IF(AND(X24-TODAY()<=30,X24-TODAY()>=0,OR(Z24="",Z24<90)),"At risk — close to off track","On track")))))))) | IF(OR(F24="",AC24="Completed / Handover",AC24="Cancelled"),"",IF(O24="Not awarded",IF(U24<>"",U24-TODAY(),IF(X24="","",X24-TODAY())),IF(X24="","",X24-TODAY()))) | [14 empty] | IF(OR(F24="",AJ24=""),"",IF(COUNT(AI24:AI24)=0,"",AJ24-LOOKUP(2,1/(AI24:AI24<>""),AI24:AI24))) | IF(OR(F24="",AK24=""),"",IF(COUNT(AI24:AJ24)=0,"",AK24-LOOKUP(2,1/(AI24:AJ24<>""),AI24:AJ24))) | IF(OR(F24="",AL24=""),"",IF(COUNT(AI24:AK24)=0,"",AL24-LOOKUP(2,1/(AI24:AK24<>""),AI24:AK24))) | IF(OR(F24="",AM24=""),"",IF(COUNT(AI24:AL24)=0,"",AM24-LOOKUP(2,1/(AI24:AL24<>""),AI24:AL24))) | IF(OR(F24="",AN24=""),"",IF(COUNT(AI24:AM24)=0,"",AN24-LOOKUP(2,1/(AI24:AM24<>""),AI24:AM24))) | IF(OR(F24="",AO24=""),"",IF(COUNT(AI24:AN24)=0,"",AO24-LOOKUP(2,1/(AI24:AN24<>""),AI24:AN24))) | IF(OR(F24="",AP24=""),"",IF(COUNT(AI24:AO24)=0,"",AP24-LOOKUP(2,1/(AI24:AO24<>""),AI24:AO24))) | IF(OR(F24="",AQ24=""),"",IF(COUNT(AI24:AP24)=0,"",AQ24-LOOKUP(2,1/(AI24:AP24<>""),AI24:AP24))) | IF(OR(F24="",AR24=""),"",IF(COUNT(AI24:AQ24)=0,"",AR24-LOOKUP(2,1/(AI24:AQ24<>""),AI24:AQ24))) | IF(OR(F24="",AS24=""),"",IF(COUNT(AI24:AR24)=0,"",AS24-LOOKUP(2,1/(AI24:AR24<>""),AI24:AR24))) | IF(OR(F24="",AT24=""),"",IF(COUNT(AI24:AS24)=0,"",AT24-LOOKUP(2,1/(AI24:AS24<>""),AI24:AS24))) | IF(OR(F24="",AU24=""),"",IF(COUNT(AI24:AT24)=0,"",AU24-LOOKUP(2,1/(AI24:AT24<>""),AI24:AT24))) | IF(OR(F24="",AV24=""),"",IF(COUNT(AI24:AU24)=0,"",AV24-LOOKUP(2,1/(AI24:AU24<>""),AI24:AU24))) | IF(J24="","All_Provinces",IFERROR(VLOOKUP(J24,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K24="","All_Districts",IFERROR(VLOOKUP(K24,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F25="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 22 of 39 | AF2-AGF-N-022 | Agroforestry — Khost / Qalander | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Qalander | Saplings: 7920; Seeds kg: 44 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ25="","",AQ25) | 2026-04-30 | 12 | 2027-04-01 | IF(W25<>"",W25,IF(OR(T25="",V25=""),"",EDATE(T25,V25))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F25="","",IF(COUNT(AI25:AV25)=0,IF(AA25="","Not started",AA25),SUBSTITUTE(LOOKUP(2,1/(AI25:AV25<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F25="",COUNT(AI25:AV25)=0),"",TODAY()-LOOKUP(2,1/(AI25:AV25<>""),AI25:AV25)) | IF(OR(F25="",COUNT(AI25:AV25)<2),"",LOOKUP(2,1/(AI25:AV25<>""),AI25:AV25)-MIN(AI25:AV25)) | IF(OR(AD25="",AC25="Not started",AC25=""),"",IFERROR(AD25-IF(VLOOKUP(AC25,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC25,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F25="","",IF(OR(AA25="Cancelled",AC25="Cancelled"),"Cancelled",IF(OR(AC25="Completed / Handover",Y25<>"",Z25>=100),"Completed — on track",IF(O25="Not awarded",IF(U25="",IF(X25="","No planned date",IF(TODAY()>X25,"Behind — past planned date",IF(X25-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U25,"Behind — award date passed",IF(U25-TODAY()<=30,"At risk — close to off track","On track"))),IF(X25="","No planned date",IF(AND(TODAY()>X25,OR(Z25="",Z25<100)),"Behind — past end date",IF(AND(T25<>"",X25<>"",Z25<>"",(Z25<100),((TODAY()-T25)/MAX(X25-T25,1)*100)-Z25>15),"Behind — progress lag",IF(AND(X25-TODAY()<=30,X25-TODAY()>=0,OR(Z25="",Z25<90)),"At risk — close to off track","On track")))))))) | IF(OR(F25="",AC25="Completed / Handover",AC25="Cancelled"),"",IF(O25="Not awarded",IF(U25<>"",U25-TODAY(),IF(X25="","",X25-TODAY())),IF(X25="","",X25-TODAY()))) | [14 empty] | IF(OR(F25="",AJ25=""),"",IF(COUNT(AI25:AI25)=0,"",AJ25-LOOKUP(2,1/(AI25:AI25<>""),AI25:AI25))) | IF(OR(F25="",AK25=""),"",IF(COUNT(AI25:AJ25)=0,"",AK25-LOOKUP(2,1/(AI25:AJ25<>""),AI25:AJ25))) | IF(OR(F25="",AL25=""),"",IF(COUNT(AI25:AK25)=0,"",AL25-LOOKUP(2,1/(AI25:AK25<>""),AI25:AK25))) | IF(OR(F25="",AM25=""),"",IF(COUNT(AI25:AL25)=0,"",AM25-LOOKUP(2,1/(AI25:AL25<>""),AI25:AL25))) | IF(OR(F25="",AN25=""),"",IF(COUNT(AI25:AM25)=0,"",AN25-LOOKUP(2,1/(AI25:AM25<>""),AI25:AM25))) | IF(OR(F25="",AO25=""),"",IF(COUNT(AI25:AN25)=0,"",AO25-LOOKUP(2,1/(AI25:AN25<>""),AI25:AN25))) | IF(OR(F25="",AP25=""),"",IF(COUNT(AI25:AO25)=0,"",AP25-LOOKUP(2,1/(AI25:AO25<>""),AI25:AO25))) | IF(OR(F25="",AQ25=""),"",IF(COUNT(AI25:AP25)=0,"",AQ25-LOOKUP(2,1/(AI25:AP25<>""),AI25:AP25))) | IF(OR(F25="",AR25=""),"",IF(COUNT(AI25:AQ25)=0,"",AR25-LOOKUP(2,1/(AI25:AQ25<>""),AI25:AQ25))) | IF(OR(F25="",AS25=""),"",IF(COUNT(AI25:AR25)=0,"",AS25-LOOKUP(2,1/(AI25:AR25<>""),AI25:AR25))) | IF(OR(F25="",AT25=""),"",IF(COUNT(AI25:AS25)=0,"",AT25-LOOKUP(2,1/(AI25:AS25<>""),AI25:AS25))) | IF(OR(F25="",AU25=""),"",IF(COUNT(AI25:AT25)=0,"",AU25-LOOKUP(2,1/(AI25:AT25<>""),AI25:AT25))) | IF(OR(F25="",AV25=""),"",IF(COUNT(AI25:AU25)=0,"",AV25-LOOKUP(2,1/(AI25:AU25<>""),AI25:AU25))) | IF(J25="","All_Provinces",IFERROR(VLOOKUP(J25,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K25="","All_Districts",IFERROR(VLOOKUP(K25,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F26="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 23 of 39 | AF2-AGF-N-023 | Agroforestry — Laghman / Alishing | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Laghman | Alishing | Saplings: 12056; Seeds kg: 174 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ26="","",AQ26) | 2026-04-30 | 12 | 2027-04-01 | IF(W26<>"",W26,IF(OR(T26="",V26=""),"",EDATE(T26,V26))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F26="","",IF(COUNT(AI26:AV26)=0,IF(AA26="","Not started",AA26),SUBSTITUTE(LOOKUP(2,1/(AI26:AV26<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F26="",COUNT(AI26:AV26)=0),"",TODAY()-LOOKUP(2,1/(AI26:AV26<>""),AI26:AV26)) | IF(OR(F26="",COUNT(AI26:AV26)<2),"",LOOKUP(2,1/(AI26:AV26<>""),AI26:AV26)-MIN(AI26:AV26)) | IF(OR(AD26="",AC26="Not started",AC26=""),"",IFERROR(AD26-IF(VLOOKUP(AC26,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC26,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F26="","",IF(OR(AA26="Cancelled",AC26="Cancelled"),"Cancelled",IF(OR(AC26="Completed / Handover",Y26<>"",Z26>=100),"Completed — on track",IF(O26="Not awarded",IF(U26="",IF(X26="","No planned date",IF(TODAY()>X26,"Behind — past planned date",IF(X26-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U26,"Behind — award date passed",IF(U26-TODAY()<=30,"At risk — close to off track","On track"))),IF(X26="","No planned date",IF(AND(TODAY()>X26,OR(Z26="",Z26<100)),"Behind — past end date",IF(AND(T26<>"",X26<>"",Z26<>"",(Z26<100),((TODAY()-T26)/MAX(X26-T26,1)*100)-Z26>15),"Behind — progress lag",IF(AND(X26-TODAY()<=30,X26-TODAY()>=0,OR(Z26="",Z26<90)),"At risk — close to off track","On track")))))))) | IF(OR(F26="",AC26="Completed / Handover",AC26="Cancelled"),"",IF(O26="Not awarded",IF(U26<>"",U26-TODAY(),IF(X26="","",X26-TODAY())),IF(X26="","",X26-TODAY()))) | [14 empty] | IF(OR(F26="",AJ26=""),"",IF(COUNT(AI26:AI26)=0,"",AJ26-LOOKUP(2,1/(AI26:AI26<>""),AI26:AI26))) | IF(OR(F26="",AK26=""),"",IF(COUNT(AI26:AJ26)=0,"",AK26-LOOKUP(2,1/(AI26:AJ26<>""),AI26:AJ26))) | IF(OR(F26="",AL26=""),"",IF(COUNT(AI26:AK26)=0,"",AL26-LOOKUP(2,1/(AI26:AK26<>""),AI26:AK26))) | IF(OR(F26="",AM26=""),"",IF(COUNT(AI26:AL26)=0,"",AM26-LOOKUP(2,1/(AI26:AL26<>""),AI26:AL26))) | IF(OR(F26="",AN26=""),"",IF(COUNT(AI26:AM26)=0,"",AN26-LOOKUP(2,1/(AI26:AM26<>""),AI26:AM26))) | IF(OR(F26="",AO26=""),"",IF(COUNT(AI26:AN26)=0,"",AO26-LOOKUP(2,1/(AI26:AN26<>""),AI26:AN26))) | IF(OR(F26="",AP26=""),"",IF(COUNT(AI26:AO26)=0,"",AP26-LOOKUP(2,1/(AI26:AO26<>""),AI26:AO26))) | IF(OR(F26="",AQ26=""),"",IF(COUNT(AI26:AP26)=0,"",AQ26-LOOKUP(2,1/(AI26:AP26<>""),AI26:AP26))) | IF(OR(F26="",AR26=""),"",IF(COUNT(AI26:AQ26)=0,"",AR26-LOOKUP(2,1/(AI26:AQ26<>""),AI26:AQ26))) | IF(OR(F26="",AS26=""),"",IF(COUNT(AI26:AR26)=0,"",AS26-LOOKUP(2,1/(AI26:AR26<>""),AI26:AR26))) | IF(OR(F26="",AT26=""),"",IF(COUNT(AI26:AS26)=0,"",AT26-LOOKUP(2,1/(AI26:AS26<>""),AI26:AS26))) | IF(OR(F26="",AU26=""),"",IF(COUNT(AI26:AT26)=0,"",AU26-LOOKUP(2,1/(AI26:AT26<>""),AI26:AT26))) | IF(OR(F26="",AV26=""),"",IF(COUNT(AI26:AU26)=0,"",AV26-LOOKUP(2,1/(AI26:AU26<>""),AI26:AU26))) | IF(J26="","All_Provinces",IFERROR(VLOOKUP(J26,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K26="","All_Districts",IFERROR(VLOOKUP(K26,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F27="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 24 of 39 | AF2-AGF-N-024 | Agroforestry — Logar / Azra | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Logar | Azra | Saplings: 15000; Seeds kg: 242 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ27="","",AQ27) | 2026-04-30 | 12 | 2027-04-01 | IF(W27<>"",W27,IF(OR(T27="",V27=""),"",EDATE(T27,V27))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F27="","",IF(COUNT(AI27:AV27)=0,IF(AA27="","Not started",AA27),SUBSTITUTE(LOOKUP(2,1/(AI27:AV27<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F27="",COUNT(AI27:AV27)=0),"",TODAY()-LOOKUP(2,1/(AI27:AV27<>""),AI27:AV27)) | IF(OR(F27="",COUNT(AI27:AV27)<2),"",LOOKUP(2,1/(AI27:AV27<>""),AI27:AV27)-MIN(AI27:AV27)) | IF(OR(AD27="",AC27="Not started",AC27=""),"",IFERROR(AD27-IF(VLOOKUP(AC27,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC27,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F27="","",IF(OR(AA27="Cancelled",AC27="Cancelled"),"Cancelled",IF(OR(AC27="Completed / Handover",Y27<>"",Z27>=100),"Completed — on track",IF(O27="Not awarded",IF(U27="",IF(X27="","No planned date",IF(TODAY()>X27,"Behind — past planned date",IF(X27-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U27,"Behind — award date passed",IF(U27-TODAY()<=30,"At risk — close to off track","On track"))),IF(X27="","No planned date",IF(AND(TODAY()>X27,OR(Z27="",Z27<100)),"Behind — past end date",IF(AND(T27<>"",X27<>"",Z27<>"",(Z27<100),((TODAY()-T27)/MAX(X27-T27,1)*100)-Z27>15),"Behind — progress lag",IF(AND(X27-TODAY()<=30,X27-TODAY()>=0,OR(Z27="",Z27<90)),"At risk — close to off track","On track")))))))) | IF(OR(F27="",AC27="Completed / Handover",AC27="Cancelled"),"",IF(O27="Not awarded",IF(U27<>"",U27-TODAY(),IF(X27="","",X27-TODAY())),IF(X27="","",X27-TODAY()))) | [14 empty] | IF(OR(F27="",AJ27=""),"",IF(COUNT(AI27:AI27)=0,"",AJ27-LOOKUP(2,1/(AI27:AI27<>""),AI27:AI27))) | IF(OR(F27="",AK27=""),"",IF(COUNT(AI27:AJ27)=0,"",AK27-LOOKUP(2,1/(AI27:AJ27<>""),AI27:AJ27))) | IF(OR(F27="",AL27=""),"",IF(COUNT(AI27:AK27)=0,"",AL27-LOOKUP(2,1/(AI27:AK27<>""),AI27:AK27))) | IF(OR(F27="",AM27=""),"",IF(COUNT(AI27:AL27)=0,"",AM27-LOOKUP(2,1/(AI27:AL27<>""),AI27:AL27))) | IF(OR(F27="",AN27=""),"",IF(COUNT(AI27:AM27)=0,"",AN27-LOOKUP(2,1/(AI27:AM27<>""),AI27:AM27))) | IF(OR(F27="",AO27=""),"",IF(COUNT(AI27:AN27)=0,"",AO27-LOOKUP(2,1/(AI27:AN27<>""),AI27:AN27))) | IF(OR(F27="",AP27=""),"",IF(COUNT(AI27:AO27)=0,"",AP27-LOOKUP(2,1/(AI27:AO27<>""),AI27:AO27))) | IF(OR(F27="",AQ27=""),"",IF(COUNT(AI27:AP27)=0,"",AQ27-LOOKUP(2,1/(AI27:AP27<>""),AI27:AP27))) | IF(OR(F27="",AR27=""),"",IF(COUNT(AI27:AQ27)=0,"",AR27-LOOKUP(2,1/(AI27:AQ27<>""),AI27:AQ27))) | IF(OR(F27="",AS27=""),"",IF(COUNT(AI27:AR27)=0,"",AS27-LOOKUP(2,1/(AI27:AR27<>""),AI27:AR27))) | IF(OR(F27="",AT27=""),"",IF(COUNT(AI27:AS27)=0,"",AT27-LOOKUP(2,1/(AI27:AS27<>""),AI27:AS27))) | IF(OR(F27="",AU27=""),"",IF(COUNT(AI27:AT27)=0,"",AU27-LOOKUP(2,1/(AI27:AT27<>""),AI27:AT27))) | IF(OR(F27="",AV27=""),"",IF(COUNT(AI27:AU27)=0,"",AV27-LOOKUP(2,1/(AI27:AU27<>""),AI27:AU27))) | IF(J27="","All_Provinces",IFERROR(VLOOKUP(J27,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K27="","All_Districts",IFERROR(VLOOKUP(K27,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F28="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 25 of 39 | AF2-AGF-N-025 | Agroforestry — Nangarhar / Pachiragam | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Pachiragam | Saplings: 11792; Seeds kg: 442 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ28="","",AQ28) | 2026-04-30 | 12 | 2027-04-01 | IF(W28<>"",W28,IF(OR(T28="",V28=""),"",EDATE(T28,V28))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F28="","",IF(COUNT(AI28:AV28)=0,IF(AA28="","Not started",AA28),SUBSTITUTE(LOOKUP(2,1/(AI28:AV28<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F28="",COUNT(AI28:AV28)=0),"",TODAY()-LOOKUP(2,1/(AI28:AV28<>""),AI28:AV28)) | IF(OR(F28="",COUNT(AI28:AV28)<2),"",LOOKUP(2,1/(AI28:AV28<>""),AI28:AV28)-MIN(AI28:AV28)) | IF(OR(AD28="",AC28="Not started",AC28=""),"",IFERROR(AD28-IF(VLOOKUP(AC28,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC28,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F28="","",IF(OR(AA28="Cancelled",AC28="Cancelled"),"Cancelled",IF(OR(AC28="Completed / Handover",Y28<>"",Z28>=100),"Completed — on track",IF(O28="Not awarded",IF(U28="",IF(X28="","No planned date",IF(TODAY()>X28,"Behind — past planned date",IF(X28-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U28,"Behind — award date passed",IF(U28-TODAY()<=30,"At risk — close to off track","On track"))),IF(X28="","No planned date",IF(AND(TODAY()>X28,OR(Z28="",Z28<100)),"Behind — past end date",IF(AND(T28<>"",X28<>"",Z28<>"",(Z28<100),((TODAY()-T28)/MAX(X28-T28,1)*100)-Z28>15),"Behind — progress lag",IF(AND(X28-TODAY()<=30,X28-TODAY()>=0,OR(Z28="",Z28<90)),"At risk — close to off track","On track")))))))) | IF(OR(F28="",AC28="Completed / Handover",AC28="Cancelled"),"",IF(O28="Not awarded",IF(U28<>"",U28-TODAY(),IF(X28="","",X28-TODAY())),IF(X28="","",X28-TODAY()))) | [14 empty] | IF(OR(F28="",AJ28=""),"",IF(COUNT(AI28:AI28)=0,"",AJ28-LOOKUP(2,1/(AI28:AI28<>""),AI28:AI28))) | IF(OR(F28="",AK28=""),"",IF(COUNT(AI28:AJ28)=0,"",AK28-LOOKUP(2,1/(AI28:AJ28<>""),AI28:AJ28))) | IF(OR(F28="",AL28=""),"",IF(COUNT(AI28:AK28)=0,"",AL28-LOOKUP(2,1/(AI28:AK28<>""),AI28:AK28))) | IF(OR(F28="",AM28=""),"",IF(COUNT(AI28:AL28)=0,"",AM28-LOOKUP(2,1/(AI28:AL28<>""),AI28:AL28))) | IF(OR(F28="",AN28=""),"",IF(COUNT(AI28:AM28)=0,"",AN28-LOOKUP(2,1/(AI28:AM28<>""),AI28:AM28))) | IF(OR(F28="",AO28=""),"",IF(COUNT(AI28:AN28)=0,"",AO28-LOOKUP(2,1/(AI28:AN28<>""),AI28:AN28))) | IF(OR(F28="",AP28=""),"",IF(COUNT(AI28:AO28)=0,"",AP28-LOOKUP(2,1/(AI28:AO28<>""),AI28:AO28))) | IF(OR(F28="",AQ28=""),"",IF(COUNT(AI28:AP28)=0,"",AQ28-LOOKUP(2,1/(AI28:AP28<>""),AI28:AP28))) | IF(OR(F28="",AR28=""),"",IF(COUNT(AI28:AQ28)=0,"",AR28-LOOKUP(2,1/(AI28:AQ28<>""),AI28:AQ28))) | IF(OR(F28="",AS28=""),"",IF(COUNT(AI28:AR28)=0,"",AS28-LOOKUP(2,1/(AI28:AR28<>""),AI28:AR28))) | IF(OR(F28="",AT28=""),"",IF(COUNT(AI28:AS28)=0,"",AT28-LOOKUP(2,1/(AI28:AS28<>""),AI28:AS28))) | IF(OR(F28="",AU28=""),"",IF(COUNT(AI28:AT28)=0,"",AU28-LOOKUP(2,1/(AI28:AT28<>""),AI28:AT28))) | IF(OR(F28="",AV28=""),"",IF(COUNT(AI28:AU28)=0,"",AV28-LOOKUP(2,1/(AI28:AU28<>""),AI28:AU28))) | IF(J28="","All_Provinces",IFERROR(VLOOKUP(J28,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K28="","All_Districts",IFERROR(VLOOKUP(K28,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F29="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 26 of 39 | AF2-AGF-N-026 | Agroforestry — Nuristan / Kamdish | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nuristan | Kamdish | Saplings: 24152; Seeds kg: 234 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ29="","",AQ29) | 2026-04-30 | 12 | 2027-04-01 | IF(W29<>"",W29,IF(OR(T29="",V29=""),"",EDATE(T29,V29))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F29="","",IF(COUNT(AI29:AV29)=0,IF(AA29="","Not started",AA29),SUBSTITUTE(LOOKUP(2,1/(AI29:AV29<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F29="",COUNT(AI29:AV29)=0),"",TODAY()-LOOKUP(2,1/(AI29:AV29<>""),AI29:AV29)) | IF(OR(F29="",COUNT(AI29:AV29)<2),"",LOOKUP(2,1/(AI29:AV29<>""),AI29:AV29)-MIN(AI29:AV29)) | IF(OR(AD29="",AC29="Not started",AC29=""),"",IFERROR(AD29-IF(VLOOKUP(AC29,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC29,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F29="","",IF(OR(AA29="Cancelled",AC29="Cancelled"),"Cancelled",IF(OR(AC29="Completed / Handover",Y29<>"",Z29>=100),"Completed — on track",IF(O29="Not awarded",IF(U29="",IF(X29="","No planned date",IF(TODAY()>X29,"Behind — past planned date",IF(X29-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U29,"Behind — award date passed",IF(U29-TODAY()<=30,"At risk — close to off track","On track"))),IF(X29="","No planned date",IF(AND(TODAY()>X29,OR(Z29="",Z29<100)),"Behind — past end date",IF(AND(T29<>"",X29<>"",Z29<>"",(Z29<100),((TODAY()-T29)/MAX(X29-T29,1)*100)-Z29>15),"Behind — progress lag",IF(AND(X29-TODAY()<=30,X29-TODAY()>=0,OR(Z29="",Z29<90)),"At risk — close to off track","On track")))))))) | IF(OR(F29="",AC29="Completed / Handover",AC29="Cancelled"),"",IF(O29="Not awarded",IF(U29<>"",U29-TODAY(),IF(X29="","",X29-TODAY())),IF(X29="","",X29-TODAY()))) | [14 empty] | IF(OR(F29="",AJ29=""),"",IF(COUNT(AI29:AI29)=0,"",AJ29-LOOKUP(2,1/(AI29:AI29<>""),AI29:AI29))) | IF(OR(F29="",AK29=""),"",IF(COUNT(AI29:AJ29)=0,"",AK29-LOOKUP(2,1/(AI29:AJ29<>""),AI29:AJ29))) | IF(OR(F29="",AL29=""),"",IF(COUNT(AI29:AK29)=0,"",AL29-LOOKUP(2,1/(AI29:AK29<>""),AI29:AK29))) | IF(OR(F29="",AM29=""),"",IF(COUNT(AI29:AL29)=0,"",AM29-LOOKUP(2,1/(AI29:AL29<>""),AI29:AL29))) | IF(OR(F29="",AN29=""),"",IF(COUNT(AI29:AM29)=0,"",AN29-LOOKUP(2,1/(AI29:AM29<>""),AI29:AM29))) | IF(OR(F29="",AO29=""),"",IF(COUNT(AI29:AN29)=0,"",AO29-LOOKUP(2,1/(AI29:AN29<>""),AI29:AN29))) | IF(OR(F29="",AP29=""),"",IF(COUNT(AI29:AO29)=0,"",AP29-LOOKUP(2,1/(AI29:AO29<>""),AI29:AO29))) | IF(OR(F29="",AQ29=""),"",IF(COUNT(AI29:AP29)=0,"",AQ29-LOOKUP(2,1/(AI29:AP29<>""),AI29:AP29))) | IF(OR(F29="",AR29=""),"",IF(COUNT(AI29:AQ29)=0,"",AR29-LOOKUP(2,1/(AI29:AQ29<>""),AI29:AQ29))) | IF(OR(F29="",AS29=""),"",IF(COUNT(AI29:AR29)=0,"",AS29-LOOKUP(2,1/(AI29:AR29<>""),AI29:AR29))) | IF(OR(F29="",AT29=""),"",IF(COUNT(AI29:AS29)=0,"",AT29-LOOKUP(2,1/(AI29:AS29<>""),AI29:AS29))) | IF(OR(F29="",AU29=""),"",IF(COUNT(AI29:AT29)=0,"",AU29-LOOKUP(2,1/(AI29:AT29<>""),AI29:AT29))) | IF(OR(F29="",AV29=""),"",IF(COUNT(AI29:AU29)=0,"",AV29-LOOKUP(2,1/(AI29:AU29<>""),AI29:AU29))) | IF(J29="","All_Provinces",IFERROR(VLOOKUP(J29,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K29="","All_Districts",IFERROR(VLOOKUP(K29,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F30="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 27 of 39 | AF2-AGF-N-027 | Agroforestry — Oruzgan / Tarinkot | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Oruzgan | Tarinkot | Saplings: 9968; Seeds kg: 388 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ30="","",AQ30) | 2026-04-30 | 12 | 2027-04-01 | IF(W30<>"",W30,IF(OR(T30="",V30=""),"",EDATE(T30,V30))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F30="","",IF(COUNT(AI30:AV30)=0,IF(AA30="","Not started",AA30),SUBSTITUTE(LOOKUP(2,1/(AI30:AV30<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F30="",COUNT(AI30:AV30)=0),"",TODAY()-LOOKUP(2,1/(AI30:AV30<>""),AI30:AV30)) | IF(OR(F30="",COUNT(AI30:AV30)<2),"",LOOKUP(2,1/(AI30:AV30<>""),AI30:AV30)-MIN(AI30:AV30)) | IF(OR(AD30="",AC30="Not started",AC30=""),"",IFERROR(AD30-IF(VLOOKUP(AC30,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC30,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F30="","",IF(OR(AA30="Cancelled",AC30="Cancelled"),"Cancelled",IF(OR(AC30="Completed / Handover",Y30<>"",Z30>=100),"Completed — on track",IF(O30="Not awarded",IF(U30="",IF(X30="","No planned date",IF(TODAY()>X30,"Behind — past planned date",IF(X30-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U30,"Behind — award date passed",IF(U30-TODAY()<=30,"At risk — close to off track","On track"))),IF(X30="","No planned date",IF(AND(TODAY()>X30,OR(Z30="",Z30<100)),"Behind — past end date",IF(AND(T30<>"",X30<>"",Z30<>"",(Z30<100),((TODAY()-T30)/MAX(X30-T30,1)*100)-Z30>15),"Behind — progress lag",IF(AND(X30-TODAY()<=30,X30-TODAY()>=0,OR(Z30="",Z30<90)),"At risk — close to off track","On track")))))))) | IF(OR(F30="",AC30="Completed / Handover",AC30="Cancelled"),"",IF(O30="Not awarded",IF(U30<>"",U30-TODAY(),IF(X30="","",X30-TODAY())),IF(X30="","",X30-TODAY()))) | [14 empty] | IF(OR(F30="",AJ30=""),"",IF(COUNT(AI30:AI30)=0,"",AJ30-LOOKUP(2,1/(AI30:AI30<>""),AI30:AI30))) | IF(OR(F30="",AK30=""),"",IF(COUNT(AI30:AJ30)=0,"",AK30-LOOKUP(2,1/(AI30:AJ30<>""),AI30:AJ30))) | IF(OR(F30="",AL30=""),"",IF(COUNT(AI30:AK30)=0,"",AL30-LOOKUP(2,1/(AI30:AK30<>""),AI30:AK30))) | IF(OR(F30="",AM30=""),"",IF(COUNT(AI30:AL30)=0,"",AM30-LOOKUP(2,1/(AI30:AL30<>""),AI30:AL30))) | IF(OR(F30="",AN30=""),"",IF(COUNT(AI30:AM30)=0,"",AN30-LOOKUP(2,1/(AI30:AM30<>""),AI30:AM30))) | IF(OR(F30="",AO30=""),"",IF(COUNT(AI30:AN30)=0,"",AO30-LOOKUP(2,1/(AI30:AN30<>""),AI30:AN30))) | IF(OR(F30="",AP30=""),"",IF(COUNT(AI30:AO30)=0,"",AP30-LOOKUP(2,1/(AI30:AO30<>""),AI30:AO30))) | IF(OR(F30="",AQ30=""),"",IF(COUNT(AI30:AP30)=0,"",AQ30-LOOKUP(2,1/(AI30:AP30<>""),AI30:AP30))) | IF(OR(F30="",AR30=""),"",IF(COUNT(AI30:AQ30)=0,"",AR30-LOOKUP(2,1/(AI30:AQ30<>""),AI30:AQ30))) | IF(OR(F30="",AS30=""),"",IF(COUNT(AI30:AR30)=0,"",AS30-LOOKUP(2,1/(AI30:AR30<>""),AI30:AR30))) | IF(OR(F30="",AT30=""),"",IF(COUNT(AI30:AS30)=0,"",AT30-LOOKUP(2,1/(AI30:AS30<>""),AI30:AS30))) | IF(OR(F30="",AU30=""),"",IF(COUNT(AI30:AT30)=0,"",AU30-LOOKUP(2,1/(AI30:AT30<>""),AI30:AT30))) | IF(OR(F30="",AV30=""),"",IF(COUNT(AI30:AU30)=0,"",AV30-LOOKUP(2,1/(AI30:AU30<>""),AI30:AU30))) | IF(J30="","All_Provinces",IFERROR(VLOOKUP(J30,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K30="","All_Districts",IFERROR(VLOOKUP(K30,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F31="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 28 of 39 | AF2-AGF-N-028 | Agroforestry — Paktia / Zazi Aryoub | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktia | Zazi Aryoub | Saplings: 9919; Seeds kg: 132 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ31="","",AQ31) | 2026-04-30 | 12 | 2027-04-01 | IF(W31<>"",W31,IF(OR(T31="",V31=""),"",EDATE(T31,V31))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F31="","",IF(COUNT(AI31:AV31)=0,IF(AA31="","Not started",AA31),SUBSTITUTE(LOOKUP(2,1/(AI31:AV31<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F31="",COUNT(AI31:AV31)=0),"",TODAY()-LOOKUP(2,1/(AI31:AV31<>""),AI31:AV31)) | IF(OR(F31="",COUNT(AI31:AV31)<2),"",LOOKUP(2,1/(AI31:AV31<>""),AI31:AV31)-MIN(AI31:AV31)) | IF(OR(AD31="",AC31="Not started",AC31=""),"",IFERROR(AD31-IF(VLOOKUP(AC31,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC31,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F31="","",IF(OR(AA31="Cancelled",AC31="Cancelled"),"Cancelled",IF(OR(AC31="Completed / Handover",Y31<>"",Z31>=100),"Completed — on track",IF(O31="Not awarded",IF(U31="",IF(X31="","No planned date",IF(TODAY()>X31,"Behind — past planned date",IF(X31-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U31,"Behind — award date passed",IF(U31-TODAY()<=30,"At risk — close to off track","On track"))),IF(X31="","No planned date",IF(AND(TODAY()>X31,OR(Z31="",Z31<100)),"Behind — past end date",IF(AND(T31<>"",X31<>"",Z31<>"",(Z31<100),((TODAY()-T31)/MAX(X31-T31,1)*100)-Z31>15),"Behind — progress lag",IF(AND(X31-TODAY()<=30,X31-TODAY()>=0,OR(Z31="",Z31<90)),"At risk — close to off track","On track")))))))) | IF(OR(F31="",AC31="Completed / Handover",AC31="Cancelled"),"",IF(O31="Not awarded",IF(U31<>"",U31-TODAY(),IF(X31="","",X31-TODAY())),IF(X31="","",X31-TODAY()))) | [14 empty] | IF(OR(F31="",AJ31=""),"",IF(COUNT(AI31:AI31)=0,"",AJ31-LOOKUP(2,1/(AI31:AI31<>""),AI31:AI31))) | IF(OR(F31="",AK31=""),"",IF(COUNT(AI31:AJ31)=0,"",AK31-LOOKUP(2,1/(AI31:AJ31<>""),AI31:AJ31))) | IF(OR(F31="",AL31=""),"",IF(COUNT(AI31:AK31)=0,"",AL31-LOOKUP(2,1/(AI31:AK31<>""),AI31:AK31))) | IF(OR(F31="",AM31=""),"",IF(COUNT(AI31:AL31)=0,"",AM31-LOOKUP(2,1/(AI31:AL31<>""),AI31:AL31))) | IF(OR(F31="",AN31=""),"",IF(COUNT(AI31:AM31)=0,"",AN31-LOOKUP(2,1/(AI31:AM31<>""),AI31:AM31))) | IF(OR(F31="",AO31=""),"",IF(COUNT(AI31:AN31)=0,"",AO31-LOOKUP(2,1/(AI31:AN31<>""),AI31:AN31))) | IF(OR(F31="",AP31=""),"",IF(COUNT(AI31:AO31)=0,"",AP31-LOOKUP(2,1/(AI31:AO31<>""),AI31:AO31))) | IF(OR(F31="",AQ31=""),"",IF(COUNT(AI31:AP31)=0,"",AQ31-LOOKUP(2,1/(AI31:AP31<>""),AI31:AP31))) | IF(OR(F31="",AR31=""),"",IF(COUNT(AI31:AQ31)=0,"",AR31-LOOKUP(2,1/(AI31:AQ31<>""),AI31:AQ31))) | IF(OR(F31="",AS31=""),"",IF(COUNT(AI31:AR31)=0,"",AS31-LOOKUP(2,1/(AI31:AR31<>""),AI31:AR31))) | IF(OR(F31="",AT31=""),"",IF(COUNT(AI31:AS31)=0,"",AT31-LOOKUP(2,1/(AI31:AS31<>""),AI31:AS31))) | IF(OR(F31="",AU31=""),"",IF(COUNT(AI31:AT31)=0,"",AU31-LOOKUP(2,1/(AI31:AT31<>""),AI31:AT31))) | IF(OR(F31="",AV31=""),"",IF(COUNT(AI31:AU31)=0,"",AV31-LOOKUP(2,1/(AI31:AU31<>""),AI31:AU31))) | IF(J31="","All_Provinces",IFERROR(VLOOKUP(J31,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K31="","All_Districts",IFERROR(VLOOKUP(K31,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F32="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 29 of 39 | AF2-AGF-N-029 | Agroforestry — Paktia / Zurmat | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktia | Zurmat | Saplings: 8581; Seeds kg: 66 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ32="","",AQ32) | 2026-04-30 | 12 | 2027-04-01 | IF(W32<>"",W32,IF(OR(T32="",V32=""),"",EDATE(T32,V32))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F32="","",IF(COUNT(AI32:AV32)=0,IF(AA32="","Not started",AA32),SUBSTITUTE(LOOKUP(2,1/(AI32:AV32<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F32="",COUNT(AI32:AV32)=0),"",TODAY()-LOOKUP(2,1/(AI32:AV32<>""),AI32:AV32)) | IF(OR(F32="",COUNT(AI32:AV32)<2),"",LOOKUP(2,1/(AI32:AV32<>""),AI32:AV32)-MIN(AI32:AV32)) | IF(OR(AD32="",AC32="Not started",AC32=""),"",IFERROR(AD32-IF(VLOOKUP(AC32,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC32,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F32="","",IF(OR(AA32="Cancelled",AC32="Cancelled"),"Cancelled",IF(OR(AC32="Completed / Handover",Y32<>"",Z32>=100),"Completed — on track",IF(O32="Not awarded",IF(U32="",IF(X32="","No planned date",IF(TODAY()>X32,"Behind — past planned date",IF(X32-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U32,"Behind — award date passed",IF(U32-TODAY()<=30,"At risk — close to off track","On track"))),IF(X32="","No planned date",IF(AND(TODAY()>X32,OR(Z32="",Z32<100)),"Behind — past end date",IF(AND(T32<>"",X32<>"",Z32<>"",(Z32<100),((TODAY()-T32)/MAX(X32-T32,1)*100)-Z32>15),"Behind — progress lag",IF(AND(X32-TODAY()<=30,X32-TODAY()>=0,OR(Z32="",Z32<90)),"At risk — close to off track","On track")))))))) | IF(OR(F32="",AC32="Completed / Handover",AC32="Cancelled"),"",IF(O32="Not awarded",IF(U32<>"",U32-TODAY(),IF(X32="","",X32-TODAY())),IF(X32="","",X32-TODAY()))) | [14 empty] | IF(OR(F32="",AJ32=""),"",IF(COUNT(AI32:AI32)=0,"",AJ32-LOOKUP(2,1/(AI32:AI32<>""),AI32:AI32))) | IF(OR(F32="",AK32=""),"",IF(COUNT(AI32:AJ32)=0,"",AK32-LOOKUP(2,1/(AI32:AJ32<>""),AI32:AJ32))) | IF(OR(F32="",AL32=""),"",IF(COUNT(AI32:AK32)=0,"",AL32-LOOKUP(2,1/(AI32:AK32<>""),AI32:AK32))) | IF(OR(F32="",AM32=""),"",IF(COUNT(AI32:AL32)=0,"",AM32-LOOKUP(2,1/(AI32:AL32<>""),AI32:AL32))) | IF(OR(F32="",AN32=""),"",IF(COUNT(AI32:AM32)=0,"",AN32-LOOKUP(2,1/(AI32:AM32<>""),AI32:AM32))) | IF(OR(F32="",AO32=""),"",IF(COUNT(AI32:AN32)=0,"",AO32-LOOKUP(2,1/(AI32:AN32<>""),AI32:AN32))) | IF(OR(F32="",AP32=""),"",IF(COUNT(AI32:AO32)=0,"",AP32-LOOKUP(2,1/(AI32:AO32<>""),AI32:AO32))) | IF(OR(F32="",AQ32=""),"",IF(COUNT(AI32:AP32)=0,"",AQ32-LOOKUP(2,1/(AI32:AP32<>""),AI32:AP32))) | IF(OR(F32="",AR32=""),"",IF(COUNT(AI32:AQ32)=0,"",AR32-LOOKUP(2,1/(AI32:AQ32<>""),AI32:AQ32))) | IF(OR(F32="",AS32=""),"",IF(COUNT(AI32:AR32)=0,"",AS32-LOOKUP(2,1/(AI32:AR32<>""),AI32:AR32))) | IF(OR(F32="",AT32=""),"",IF(COUNT(AI32:AS32)=0,"",AT32-LOOKUP(2,1/(AI32:AS32<>""),AI32:AS32))) | IF(OR(F32="",AU32=""),"",IF(COUNT(AI32:AT32)=0,"",AU32-LOOKUP(2,1/(AI32:AT32<>""),AI32:AT32))) | IF(OR(F32="",AV32=""),"",IF(COUNT(AI32:AU32)=0,"",AV32-LOOKUP(2,1/(AI32:AU32<>""),AI32:AU32))) | IF(J32="","All_Provinces",IFERROR(VLOOKUP(J32,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K32="","All_Districts",IFERROR(VLOOKUP(K32,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F33="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 30 of 39 | AF2-AGF-N-030 | Agroforestry — Paktika / Surobi | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktika | Surobi | Saplings: 3500; Seeds kg: 44 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ33="","",AQ33) | 2026-04-30 | 12 | 2027-04-01 | IF(W33<>"",W33,IF(OR(T33="",V33=""),"",EDATE(T33,V33))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F33="","",IF(COUNT(AI33:AV33)=0,IF(AA33="","Not started",AA33),SUBSTITUTE(LOOKUP(2,1/(AI33:AV33<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F33="",COUNT(AI33:AV33)=0),"",TODAY()-LOOKUP(2,1/(AI33:AV33<>""),AI33:AV33)) | IF(OR(F33="",COUNT(AI33:AV33)<2),"",LOOKUP(2,1/(AI33:AV33<>""),AI33:AV33)-MIN(AI33:AV33)) | IF(OR(AD33="",AC33="Not started",AC33=""),"",IFERROR(AD33-IF(VLOOKUP(AC33,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC33,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F33="","",IF(OR(AA33="Cancelled",AC33="Cancelled"),"Cancelled",IF(OR(AC33="Completed / Handover",Y33<>"",Z33>=100),"Completed — on track",IF(O33="Not awarded",IF(U33="",IF(X33="","No planned date",IF(TODAY()>X33,"Behind — past planned date",IF(X33-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U33,"Behind — award date passed",IF(U33-TODAY()<=30,"At risk — close to off track","On track"))),IF(X33="","No planned date",IF(AND(TODAY()>X33,OR(Z33="",Z33<100)),"Behind — past end date",IF(AND(T33<>"",X33<>"",Z33<>"",(Z33<100),((TODAY()-T33)/MAX(X33-T33,1)*100)-Z33>15),"Behind — progress lag",IF(AND(X33-TODAY()<=30,X33-TODAY()>=0,OR(Z33="",Z33<90)),"At risk — close to off track","On track")))))))) | IF(OR(F33="",AC33="Completed / Handover",AC33="Cancelled"),"",IF(O33="Not awarded",IF(U33<>"",U33-TODAY(),IF(X33="","",X33-TODAY())),IF(X33="","",X33-TODAY()))) | [14 empty] | IF(OR(F33="",AJ33=""),"",IF(COUNT(AI33:AI33)=0,"",AJ33-LOOKUP(2,1/(AI33:AI33<>""),AI33:AI33))) | IF(OR(F33="",AK33=""),"",IF(COUNT(AI33:AJ33)=0,"",AK33-LOOKUP(2,1/(AI33:AJ33<>""),AI33:AJ33))) | IF(OR(F33="",AL33=""),"",IF(COUNT(AI33:AK33)=0,"",AL33-LOOKUP(2,1/(AI33:AK33<>""),AI33:AK33))) | IF(OR(F33="",AM33=""),"",IF(COUNT(AI33:AL33)=0,"",AM33-LOOKUP(2,1/(AI33:AL33<>""),AI33:AL33))) | IF(OR(F33="",AN33=""),"",IF(COUNT(AI33:AM33)=0,"",AN33-LOOKUP(2,1/(AI33:AM33<>""),AI33:AM33))) | IF(OR(F33="",AO33=""),"",IF(COUNT(AI33:AN33)=0,"",AO33-LOOKUP(2,1/(AI33:AN33<>""),AI33:AN33))) | IF(OR(F33="",AP33=""),"",IF(COUNT(AI33:AO33)=0,"",AP33-LOOKUP(2,1/(AI33:AO33<>""),AI33:AO33))) | IF(OR(F33="",AQ33=""),"",IF(COUNT(AI33:AP33)=0,"",AQ33-LOOKUP(2,1/(AI33:AP33<>""),AI33:AP33))) | IF(OR(F33="",AR33=""),"",IF(COUNT(AI33:AQ33)=0,"",AR33-LOOKUP(2,1/(AI33:AQ33<>""),AI33:AQ33))) | IF(OR(F33="",AS33=""),"",IF(COUNT(AI33:AR33)=0,"",AS33-LOOKUP(2,1/(AI33:AR33<>""),AI33:AR33))) | IF(OR(F33="",AT33=""),"",IF(COUNT(AI33:AS33)=0,"",AT33-LOOKUP(2,1/(AI33:AS33<>""),AI33:AS33))) | IF(OR(F33="",AU33=""),"",IF(COUNT(AI33:AT33)=0,"",AU33-LOOKUP(2,1/(AI33:AT33<>""),AI33:AT33))) | IF(OR(F33="",AV33=""),"",IF(COUNT(AI33:AU33)=0,"",AV33-LOOKUP(2,1/(AI33:AU33<>""),AI33:AU33))) | IF(J33="","All_Provinces",IFERROR(VLOOKUP(J33,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K33="","All_Districts",IFERROR(VLOOKUP(K33,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F34="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 31 of 39 | AF2-AGF-N-031 | Agroforestry — Panjsher / Khinj | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Panjsher | Khinj | Saplings: 3000; Seeds kg: 150 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ34="","",AQ34) | 2026-04-30 | 12 | 2027-04-01 | IF(W34<>"",W34,IF(OR(T34="",V34=""),"",EDATE(T34,V34))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F34="","",IF(COUNT(AI34:AV34)=0,IF(AA34="","Not started",AA34),SUBSTITUTE(LOOKUP(2,1/(AI34:AV34<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F34="",COUNT(AI34:AV34)=0),"",TODAY()-LOOKUP(2,1/(AI34:AV34<>""),AI34:AV34)) | IF(OR(F34="",COUNT(AI34:AV34)<2),"",LOOKUP(2,1/(AI34:AV34<>""),AI34:AV34)-MIN(AI34:AV34)) | IF(OR(AD34="",AC34="Not started",AC34=""),"",IFERROR(AD34-IF(VLOOKUP(AC34,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC34,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F34="","",IF(OR(AA34="Cancelled",AC34="Cancelled"),"Cancelled",IF(OR(AC34="Completed / Handover",Y34<>"",Z34>=100),"Completed — on track",IF(O34="Not awarded",IF(U34="",IF(X34="","No planned date",IF(TODAY()>X34,"Behind — past planned date",IF(X34-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U34,"Behind — award date passed",IF(U34-TODAY()<=30,"At risk — close to off track","On track"))),IF(X34="","No planned date",IF(AND(TODAY()>X34,OR(Z34="",Z34<100)),"Behind — past end date",IF(AND(T34<>"",X34<>"",Z34<>"",(Z34<100),((TODAY()-T34)/MAX(X34-T34,1)*100)-Z34>15),"Behind — progress lag",IF(AND(X34-TODAY()<=30,X34-TODAY()>=0,OR(Z34="",Z34<90)),"At risk — close to off track","On track")))))))) | IF(OR(F34="",AC34="Completed / Handover",AC34="Cancelled"),"",IF(O34="Not awarded",IF(U34<>"",U34-TODAY(),IF(X34="","",X34-TODAY())),IF(X34="","",X34-TODAY()))) | [14 empty] | IF(OR(F34="",AJ34=""),"",IF(COUNT(AI34:AI34)=0,"",AJ34-LOOKUP(2,1/(AI34:AI34<>""),AI34:AI34))) | IF(OR(F34="",AK34=""),"",IF(COUNT(AI34:AJ34)=0,"",AK34-LOOKUP(2,1/(AI34:AJ34<>""),AI34:AJ34))) | IF(OR(F34="",AL34=""),"",IF(COUNT(AI34:AK34)=0,"",AL34-LOOKUP(2,1/(AI34:AK34<>""),AI34:AK34))) | IF(OR(F34="",AM34=""),"",IF(COUNT(AI34:AL34)=0,"",AM34-LOOKUP(2,1/(AI34:AL34<>""),AI34:AL34))) | IF(OR(F34="",AN34=""),"",IF(COUNT(AI34:AM34)=0,"",AN34-LOOKUP(2,1/(AI34:AM34<>""),AI34:AM34))) | IF(OR(F34="",AO34=""),"",IF(COUNT(AI34:AN34)=0,"",AO34-LOOKUP(2,1/(AI34:AN34<>""),AI34:AN34))) | IF(OR(F34="",AP34=""),"",IF(COUNT(AI34:AO34)=0,"",AP34-LOOKUP(2,1/(AI34:AO34<>""),AI34:AO34))) | IF(OR(F34="",AQ34=""),"",IF(COUNT(AI34:AP34)=0,"",AQ34-LOOKUP(2,1/(AI34:AP34<>""),AI34:AP34))) | IF(OR(F34="",AR34=""),"",IF(COUNT(AI34:AQ34)=0,"",AR34-LOOKUP(2,1/(AI34:AQ34<>""),AI34:AQ34))) | IF(OR(F34="",AS34=""),"",IF(COUNT(AI34:AR34)=0,"",AS34-LOOKUP(2,1/(AI34:AR34<>""),AI34:AR34))) | IF(OR(F34="",AT34=""),"",IF(COUNT(AI34:AS34)=0,"",AT34-LOOKUP(2,1/(AI34:AS34<>""),AI34:AS34))) | IF(OR(F34="",AU34=""),"",IF(COUNT(AI34:AT34)=0,"",AU34-LOOKUP(2,1/(AI34:AT34<>""),AI34:AT34))) | IF(OR(F34="",AV34=""),"",IF(COUNT(AI34:AU34)=0,"",AV34-LOOKUP(2,1/(AI34:AU34<>""),AI34:AU34))) | IF(J34="","All_Provinces",IFERROR(VLOOKUP(J34,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K34="","All_Districts",IFERROR(VLOOKUP(K34,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F35="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 32 of 39 | AF2-AGF-N-032 | Agroforestry — Panjsher / Paryan | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Panjsher | Paryan | Saplings: 3000; Seeds kg: 200 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ35="","",AQ35) | 2026-04-30 | 12 | 2027-04-01 | IF(W35<>"",W35,IF(OR(T35="",V35=""),"",EDATE(T35,V35))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F35="","",IF(COUNT(AI35:AV35)=0,IF(AA35="","Not started",AA35),SUBSTITUTE(LOOKUP(2,1/(AI35:AV35<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F35="",COUNT(AI35:AV35)=0),"",TODAY()-LOOKUP(2,1/(AI35:AV35<>""),AI35:AV35)) | IF(OR(F35="",COUNT(AI35:AV35)<2),"",LOOKUP(2,1/(AI35:AV35<>""),AI35:AV35)-MIN(AI35:AV35)) | IF(OR(AD35="",AC35="Not started",AC35=""),"",IFERROR(AD35-IF(VLOOKUP(AC35,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC35,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F35="","",IF(OR(AA35="Cancelled",AC35="Cancelled"),"Cancelled",IF(OR(AC35="Completed / Handover",Y35<>"",Z35>=100),"Completed — on track",IF(O35="Not awarded",IF(U35="",IF(X35="","No planned date",IF(TODAY()>X35,"Behind — past planned date",IF(X35-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U35,"Behind — award date passed",IF(U35-TODAY()<=30,"At risk — close to off track","On track"))),IF(X35="","No planned date",IF(AND(TODAY()>X35,OR(Z35="",Z35<100)),"Behind — past end date",IF(AND(T35<>"",X35<>"",Z35<>"",(Z35<100),((TODAY()-T35)/MAX(X35-T35,1)*100)-Z35>15),"Behind — progress lag",IF(AND(X35-TODAY()<=30,X35-TODAY()>=0,OR(Z35="",Z35<90)),"At risk — close to off track","On track")))))))) | IF(OR(F35="",AC35="Completed / Handover",AC35="Cancelled"),"",IF(O35="Not awarded",IF(U35<>"",U35-TODAY(),IF(X35="","",X35-TODAY())),IF(X35="","",X35-TODAY()))) | [14 empty] | IF(OR(F35="",AJ35=""),"",IF(COUNT(AI35:AI35)=0,"",AJ35-LOOKUP(2,1/(AI35:AI35<>""),AI35:AI35))) | IF(OR(F35="",AK35=""),"",IF(COUNT(AI35:AJ35)=0,"",AK35-LOOKUP(2,1/(AI35:AJ35<>""),AI35:AJ35))) | IF(OR(F35="",AL35=""),"",IF(COUNT(AI35:AK35)=0,"",AL35-LOOKUP(2,1/(AI35:AK35<>""),AI35:AK35))) | IF(OR(F35="",AM35=""),"",IF(COUNT(AI35:AL35)=0,"",AM35-LOOKUP(2,1/(AI35:AL35<>""),AI35:AL35))) | IF(OR(F35="",AN35=""),"",IF(COUNT(AI35:AM35)=0,"",AN35-LOOKUP(2,1/(AI35:AM35<>""),AI35:AM35))) | IF(OR(F35="",AO35=""),"",IF(COUNT(AI35:AN35)=0,"",AO35-LOOKUP(2,1/(AI35:AN35<>""),AI35:AN35))) | IF(OR(F35="",AP35=""),"",IF(COUNT(AI35:AO35)=0,"",AP35-LOOKUP(2,1/(AI35:AO35<>""),AI35:AO35))) | IF(OR(F35="",AQ35=""),"",IF(COUNT(AI35:AP35)=0,"",AQ35-LOOKUP(2,1/(AI35:AP35<>""),AI35:AP35))) | IF(OR(F35="",AR35=""),"",IF(COUNT(AI35:AQ35)=0,"",AR35-LOOKUP(2,1/(AI35:AQ35<>""),AI35:AQ35))) | IF(OR(F35="",AS35=""),"",IF(COUNT(AI35:AR35)=0,"",AS35-LOOKUP(2,1/(AI35:AR35<>""),AI35:AR35))) | IF(OR(F35="",AT35=""),"",IF(COUNT(AI35:AS35)=0,"",AT35-LOOKUP(2,1/(AI35:AS35<>""),AI35:AS35))) | IF(OR(F35="",AU35=""),"",IF(COUNT(AI35:AT35)=0,"",AU35-LOOKUP(2,1/(AI35:AT35<>""),AI35:AT35))) | IF(OR(F35="",AV35=""),"",IF(COUNT(AI35:AU35)=0,"",AV35-LOOKUP(2,1/(AI35:AU35<>""),AI35:AU35))) | IF(J35="","All_Provinces",IFERROR(VLOOKUP(J35,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K35="","All_Districts",IFERROR(VLOOKUP(K35,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F36="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 33 of 39 | AF2-AGF-N-033 | Agroforestry — Panjsher / Unaba | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Panjsher | Unaba | Saplings: 4000; Seeds kg: 250 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ36="","",AQ36) | 2026-04-30 | 12 | 2027-04-01 | IF(W36<>"",W36,IF(OR(T36="",V36=""),"",EDATE(T36,V36))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F36="","",IF(COUNT(AI36:AV36)=0,IF(AA36="","Not started",AA36),SUBSTITUTE(LOOKUP(2,1/(AI36:AV36<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F36="",COUNT(AI36:AV36)=0),"",TODAY()-LOOKUP(2,1/(AI36:AV36<>""),AI36:AV36)) | IF(OR(F36="",COUNT(AI36:AV36)<2),"",LOOKUP(2,1/(AI36:AV36<>""),AI36:AV36)-MIN(AI36:AV36)) | IF(OR(AD36="",AC36="Not started",AC36=""),"",IFERROR(AD36-IF(VLOOKUP(AC36,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC36,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F36="","",IF(OR(AA36="Cancelled",AC36="Cancelled"),"Cancelled",IF(OR(AC36="Completed / Handover",Y36<>"",Z36>=100),"Completed — on track",IF(O36="Not awarded",IF(U36="",IF(X36="","No planned date",IF(TODAY()>X36,"Behind — past planned date",IF(X36-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U36,"Behind — award date passed",IF(U36-TODAY()<=30,"At risk — close to off track","On track"))),IF(X36="","No planned date",IF(AND(TODAY()>X36,OR(Z36="",Z36<100)),"Behind — past end date",IF(AND(T36<>"",X36<>"",Z36<>"",(Z36<100),((TODAY()-T36)/MAX(X36-T36,1)*100)-Z36>15),"Behind — progress lag",IF(AND(X36-TODAY()<=30,X36-TODAY()>=0,OR(Z36="",Z36<90)),"At risk — close to off track","On track")))))))) | IF(OR(F36="",AC36="Completed / Handover",AC36="Cancelled"),"",IF(O36="Not awarded",IF(U36<>"",U36-TODAY(),IF(X36="","",X36-TODAY())),IF(X36="","",X36-TODAY()))) | [14 empty] | IF(OR(F36="",AJ36=""),"",IF(COUNT(AI36:AI36)=0,"",AJ36-LOOKUP(2,1/(AI36:AI36<>""),AI36:AI36))) | IF(OR(F36="",AK36=""),"",IF(COUNT(AI36:AJ36)=0,"",AK36-LOOKUP(2,1/(AI36:AJ36<>""),AI36:AJ36))) | IF(OR(F36="",AL36=""),"",IF(COUNT(AI36:AK36)=0,"",AL36-LOOKUP(2,1/(AI36:AK36<>""),AI36:AK36))) | IF(OR(F36="",AM36=""),"",IF(COUNT(AI36:AL36)=0,"",AM36-LOOKUP(2,1/(AI36:AL36<>""),AI36:AL36))) | IF(OR(F36="",AN36=""),"",IF(COUNT(AI36:AM36)=0,"",AN36-LOOKUP(2,1/(AI36:AM36<>""),AI36:AM36))) | IF(OR(F36="",AO36=""),"",IF(COUNT(AI36:AN36)=0,"",AO36-LOOKUP(2,1/(AI36:AN36<>""),AI36:AN36))) | IF(OR(F36="",AP36=""),"",IF(COUNT(AI36:AO36)=0,"",AP36-LOOKUP(2,1/(AI36:AO36<>""),AI36:AO36))) | IF(OR(F36="",AQ36=""),"",IF(COUNT(AI36:AP36)=0,"",AQ36-LOOKUP(2,1/(AI36:AP36<>""),AI36:AP36))) | IF(OR(F36="",AR36=""),"",IF(COUNT(AI36:AQ36)=0,"",AR36-LOOKUP(2,1/(AI36:AQ36<>""),AI36:AQ36))) | IF(OR(F36="",AS36=""),"",IF(COUNT(AI36:AR36)=0,"",AS36-LOOKUP(2,1/(AI36:AR36<>""),AI36:AR36))) | IF(OR(F36="",AT36=""),"",IF(COUNT(AI36:AS36)=0,"",AT36-LOOKUP(2,1/(AI36:AS36<>""),AI36:AS36))) | IF(OR(F36="",AU36=""),"",IF(COUNT(AI36:AT36)=0,"",AU36-LOOKUP(2,1/(AI36:AT36<>""),AI36:AT36))) | IF(OR(F36="",AV36=""),"",IF(COUNT(AI36:AU36)=0,"",AV36-LOOKUP(2,1/(AI36:AU36<>""),AI36:AU36))) | IF(J36="","All_Provinces",IFERROR(VLOOKUP(J36,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K36="","All_Districts",IFERROR(VLOOKUP(K36,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F37="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 34 of 39 | AF2-AGF-N-034 | Agroforestry — Samangan / Aybak | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Aybak | Saplings: 0; Seeds kg: 173 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ37="","",AQ37) | 2026-04-30 | 12 | 2027-04-01 | IF(W37<>"",W37,IF(OR(T37="",V37=""),"",EDATE(T37,V37))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F37="","",IF(COUNT(AI37:AV37)=0,IF(AA37="","Not started",AA37),SUBSTITUTE(LOOKUP(2,1/(AI37:AV37<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F37="",COUNT(AI37:AV37)=0),"",TODAY()-LOOKUP(2,1/(AI37:AV37<>""),AI37:AV37)) | IF(OR(F37="",COUNT(AI37:AV37)<2),"",LOOKUP(2,1/(AI37:AV37<>""),AI37:AV37)-MIN(AI37:AV37)) | IF(OR(AD37="",AC37="Not started",AC37=""),"",IFERROR(AD37-IF(VLOOKUP(AC37,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC37,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F37="","",IF(OR(AA37="Cancelled",AC37="Cancelled"),"Cancelled",IF(OR(AC37="Completed / Handover",Y37<>"",Z37>=100),"Completed — on track",IF(O37="Not awarded",IF(U37="",IF(X37="","No planned date",IF(TODAY()>X37,"Behind — past planned date",IF(X37-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U37,"Behind — award date passed",IF(U37-TODAY()<=30,"At risk — close to off track","On track"))),IF(X37="","No planned date",IF(AND(TODAY()>X37,OR(Z37="",Z37<100)),"Behind — past end date",IF(AND(T37<>"",X37<>"",Z37<>"",(Z37<100),((TODAY()-T37)/MAX(X37-T37,1)*100)-Z37>15),"Behind — progress lag",IF(AND(X37-TODAY()<=30,X37-TODAY()>=0,OR(Z37="",Z37<90)),"At risk — close to off track","On track")))))))) | IF(OR(F37="",AC37="Completed / Handover",AC37="Cancelled"),"",IF(O37="Not awarded",IF(U37<>"",U37-TODAY(),IF(X37="","",X37-TODAY())),IF(X37="","",X37-TODAY()))) | [14 empty] | IF(OR(F37="",AJ37=""),"",IF(COUNT(AI37:AI37)=0,"",AJ37-LOOKUP(2,1/(AI37:AI37<>""),AI37:AI37))) | IF(OR(F37="",AK37=""),"",IF(COUNT(AI37:AJ37)=0,"",AK37-LOOKUP(2,1/(AI37:AJ37<>""),AI37:AJ37))) | IF(OR(F37="",AL37=""),"",IF(COUNT(AI37:AK37)=0,"",AL37-LOOKUP(2,1/(AI37:AK37<>""),AI37:AK37))) | IF(OR(F37="",AM37=""),"",IF(COUNT(AI37:AL37)=0,"",AM37-LOOKUP(2,1/(AI37:AL37<>""),AI37:AL37))) | IF(OR(F37="",AN37=""),"",IF(COUNT(AI37:AM37)=0,"",AN37-LOOKUP(2,1/(AI37:AM37<>""),AI37:AM37))) | IF(OR(F37="",AO37=""),"",IF(COUNT(AI37:AN37)=0,"",AO37-LOOKUP(2,1/(AI37:AN37<>""),AI37:AN37))) | IF(OR(F37="",AP37=""),"",IF(COUNT(AI37:AO37)=0,"",AP37-LOOKUP(2,1/(AI37:AO37<>""),AI37:AO37))) | IF(OR(F37="",AQ37=""),"",IF(COUNT(AI37:AP37)=0,"",AQ37-LOOKUP(2,1/(AI37:AP37<>""),AI37:AP37))) | IF(OR(F37="",AR37=""),"",IF(COUNT(AI37:AQ37)=0,"",AR37-LOOKUP(2,1/(AI37:AQ37<>""),AI37:AQ37))) | IF(OR(F37="",AS37=""),"",IF(COUNT(AI37:AR37)=0,"",AS37-LOOKUP(2,1/(AI37:AR37<>""),AI37:AR37))) | IF(OR(F37="",AT37=""),"",IF(COUNT(AI37:AS37)=0,"",AT37-LOOKUP(2,1/(AI37:AS37<>""),AI37:AS37))) | IF(OR(F37="",AU37=""),"",IF(COUNT(AI37:AT37)=0,"",AU37-LOOKUP(2,1/(AI37:AT37<>""),AI37:AT37))) | IF(OR(F37="",AV37=""),"",IF(COUNT(AI37:AU37)=0,"",AV37-LOOKUP(2,1/(AI37:AU37<>""),AI37:AU37))) | IF(J37="","All_Provinces",IFERROR(VLOOKUP(J37,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K37="","All_Districts",IFERROR(VLOOKUP(K37,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F38="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 35 of 39 | AF2-AGF-N-035 | Agroforestry — Samangan / Hazrat-e-Sultan | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Hazrat-e-Sultan | Saplings: 1300; Seeds kg: 65 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ38="","",AQ38) | 2026-04-30 | 12 | 2027-04-01 | IF(W38<>"",W38,IF(OR(T38="",V38=""),"",EDATE(T38,V38))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F38="","",IF(COUNT(AI38:AV38)=0,IF(AA38="","Not started",AA38),SUBSTITUTE(LOOKUP(2,1/(AI38:AV38<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F38="",COUNT(AI38:AV38)=0),"",TODAY()-LOOKUP(2,1/(AI38:AV38<>""),AI38:AV38)) | IF(OR(F38="",COUNT(AI38:AV38)<2),"",LOOKUP(2,1/(AI38:AV38<>""),AI38:AV38)-MIN(AI38:AV38)) | IF(OR(AD38="",AC38="Not started",AC38=""),"",IFERROR(AD38-IF(VLOOKUP(AC38,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC38,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F38="","",IF(OR(AA38="Cancelled",AC38="Cancelled"),"Cancelled",IF(OR(AC38="Completed / Handover",Y38<>"",Z38>=100),"Completed — on track",IF(O38="Not awarded",IF(U38="",IF(X38="","No planned date",IF(TODAY()>X38,"Behind — past planned date",IF(X38-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U38,"Behind — award date passed",IF(U38-TODAY()<=30,"At risk — close to off track","On track"))),IF(X38="","No planned date",IF(AND(TODAY()>X38,OR(Z38="",Z38<100)),"Behind — past end date",IF(AND(T38<>"",X38<>"",Z38<>"",(Z38<100),((TODAY()-T38)/MAX(X38-T38,1)*100)-Z38>15),"Behind — progress lag",IF(AND(X38-TODAY()<=30,X38-TODAY()>=0,OR(Z38="",Z38<90)),"At risk — close to off track","On track")))))))) | IF(OR(F38="",AC38="Completed / Handover",AC38="Cancelled"),"",IF(O38="Not awarded",IF(U38<>"",U38-TODAY(),IF(X38="","",X38-TODAY())),IF(X38="","",X38-TODAY()))) | [14 empty] | IF(OR(F38="",AJ38=""),"",IF(COUNT(AI38:AI38)=0,"",AJ38-LOOKUP(2,1/(AI38:AI38<>""),AI38:AI38))) | IF(OR(F38="",AK38=""),"",IF(COUNT(AI38:AJ38)=0,"",AK38-LOOKUP(2,1/(AI38:AJ38<>""),AI38:AJ38))) | IF(OR(F38="",AL38=""),"",IF(COUNT(AI38:AK38)=0,"",AL38-LOOKUP(2,1/(AI38:AK38<>""),AI38:AK38))) | IF(OR(F38="",AM38=""),"",IF(COUNT(AI38:AL38)=0,"",AM38-LOOKUP(2,1/(AI38:AL38<>""),AI38:AL38))) | IF(OR(F38="",AN38=""),"",IF(COUNT(AI38:AM38)=0,"",AN38-LOOKUP(2,1/(AI38:AM38<>""),AI38:AM38))) | IF(OR(F38="",AO38=""),"",IF(COUNT(AI38:AN38)=0,"",AO38-LOOKUP(2,1/(AI38:AN38<>""),AI38:AN38))) | IF(OR(F38="",AP38=""),"",IF(COUNT(AI38:AO38)=0,"",AP38-LOOKUP(2,1/(AI38:AO38<>""),AI38:AO38))) | IF(OR(F38="",AQ38=""),"",IF(COUNT(AI38:AP38)=0,"",AQ38-LOOKUP(2,1/(AI38:AP38<>""),AI38:AP38))) | IF(OR(F38="",AR38=""),"",IF(COUNT(AI38:AQ38)=0,"",AR38-LOOKUP(2,1/(AI38:AQ38<>""),AI38:AQ38))) | IF(OR(F38="",AS38=""),"",IF(COUNT(AI38:AR38)=0,"",AS38-LOOKUP(2,1/(AI38:AR38<>""),AI38:AR38))) | IF(OR(F38="",AT38=""),"",IF(COUNT(AI38:AS38)=0,"",AT38-LOOKUP(2,1/(AI38:AS38<>""),AI38:AS38))) | IF(OR(F38="",AU38=""),"",IF(COUNT(AI38:AT38)=0,"",AU38-LOOKUP(2,1/(AI38:AT38<>""),AI38:AT38))) | IF(OR(F38="",AV38=""),"",IF(COUNT(AI38:AU38)=0,"",AV38-LOOKUP(2,1/(AI38:AU38<>""),AI38:AU38))) | IF(J38="","All_Provinces",IFERROR(VLOOKUP(J38,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K38="","All_Districts",IFERROR(VLOOKUP(K38,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F39="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 36 of 39 | AF2-AGF-N-036 | Agroforestry — Sari Pul / Balkhab | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sari Pul | Balkhab | Saplings: 0; Seeds kg: 30 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ39="","",AQ39) | 2026-04-30 | 12 | 2027-04-01 | IF(W39<>"",W39,IF(OR(T39="",V39=""),"",EDATE(T39,V39))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F39="","",IF(COUNT(AI39:AV39)=0,IF(AA39="","Not started",AA39),SUBSTITUTE(LOOKUP(2,1/(AI39:AV39<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F39="",COUNT(AI39:AV39)=0),"",TODAY()-LOOKUP(2,1/(AI39:AV39<>""),AI39:AV39)) | IF(OR(F39="",COUNT(AI39:AV39)<2),"",LOOKUP(2,1/(AI39:AV39<>""),AI39:AV39)-MIN(AI39:AV39)) | IF(OR(AD39="",AC39="Not started",AC39=""),"",IFERROR(AD39-IF(VLOOKUP(AC39,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC39,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F39="","",IF(OR(AA39="Cancelled",AC39="Cancelled"),"Cancelled",IF(OR(AC39="Completed / Handover",Y39<>"",Z39>=100),"Completed — on track",IF(O39="Not awarded",IF(U39="",IF(X39="","No planned date",IF(TODAY()>X39,"Behind — past planned date",IF(X39-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U39,"Behind — award date passed",IF(U39-TODAY()<=30,"At risk — close to off track","On track"))),IF(X39="","No planned date",IF(AND(TODAY()>X39,OR(Z39="",Z39<100)),"Behind — past end date",IF(AND(T39<>"",X39<>"",Z39<>"",(Z39<100),((TODAY()-T39)/MAX(X39-T39,1)*100)-Z39>15),"Behind — progress lag",IF(AND(X39-TODAY()<=30,X39-TODAY()>=0,OR(Z39="",Z39<90)),"At risk — close to off track","On track")))))))) | IF(OR(F39="",AC39="Completed / Handover",AC39="Cancelled"),"",IF(O39="Not awarded",IF(U39<>"",U39-TODAY(),IF(X39="","",X39-TODAY())),IF(X39="","",X39-TODAY()))) | [14 empty] | IF(OR(F39="",AJ39=""),"",IF(COUNT(AI39:AI39)=0,"",AJ39-LOOKUP(2,1/(AI39:AI39<>""),AI39:AI39))) | IF(OR(F39="",AK39=""),"",IF(COUNT(AI39:AJ39)=0,"",AK39-LOOKUP(2,1/(AI39:AJ39<>""),AI39:AJ39))) | IF(OR(F39="",AL39=""),"",IF(COUNT(AI39:AK39)=0,"",AL39-LOOKUP(2,1/(AI39:AK39<>""),AI39:AK39))) | IF(OR(F39="",AM39=""),"",IF(COUNT(AI39:AL39)=0,"",AM39-LOOKUP(2,1/(AI39:AL39<>""),AI39:AL39))) | IF(OR(F39="",AN39=""),"",IF(COUNT(AI39:AM39)=0,"",AN39-LOOKUP(2,1/(AI39:AM39<>""),AI39:AM39))) | IF(OR(F39="",AO39=""),"",IF(COUNT(AI39:AN39)=0,"",AO39-LOOKUP(2,1/(AI39:AN39<>""),AI39:AN39))) | IF(OR(F39="",AP39=""),"",IF(COUNT(AI39:AO39)=0,"",AP39-LOOKUP(2,1/(AI39:AO39<>""),AI39:AO39))) | IF(OR(F39="",AQ39=""),"",IF(COUNT(AI39:AP39)=0,"",AQ39-LOOKUP(2,1/(AI39:AP39<>""),AI39:AP39))) | IF(OR(F39="",AR39=""),"",IF(COUNT(AI39:AQ39)=0,"",AR39-LOOKUP(2,1/(AI39:AQ39<>""),AI39:AQ39))) | IF(OR(F39="",AS39=""),"",IF(COUNT(AI39:AR39)=0,"",AS39-LOOKUP(2,1/(AI39:AR39<>""),AI39:AR39))) | IF(OR(F39="",AT39=""),"",IF(COUNT(AI39:AS39)=0,"",AT39-LOOKUP(2,1/(AI39:AS39<>""),AI39:AS39))) | IF(OR(F39="",AU39=""),"",IF(COUNT(AI39:AT39)=0,"",AU39-LOOKUP(2,1/(AI39:AT39<>""),AI39:AT39))) | IF(OR(F39="",AV39=""),"",IF(COUNT(AI39:AU39)=0,"",AV39-LOOKUP(2,1/(AI39:AU39<>""),AI39:AU39))) | IF(J39="","All_Provinces",IFERROR(VLOOKUP(J39,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K39="","All_Districts",IFERROR(VLOOKUP(K39,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F40="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 37 of 39 | AF2-AGF-N-037 | Agroforestry — Sari Pul / Center | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sari Pul | Center | Saplings: 4800; Seeds kg: 259 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ40="","",AQ40) | 2026-04-30 | 12 | 2027-04-01 | IF(W40<>"",W40,IF(OR(T40="",V40=""),"",EDATE(T40,V40))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F40="","",IF(COUNT(AI40:AV40)=0,IF(AA40="","Not started",AA40),SUBSTITUTE(LOOKUP(2,1/(AI40:AV40<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F40="",COUNT(AI40:AV40)=0),"",TODAY()-LOOKUP(2,1/(AI40:AV40<>""),AI40:AV40)) | IF(OR(F40="",COUNT(AI40:AV40)<2),"",LOOKUP(2,1/(AI40:AV40<>""),AI40:AV40)-MIN(AI40:AV40)) | IF(OR(AD40="",AC40="Not started",AC40=""),"",IFERROR(AD40-IF(VLOOKUP(AC40,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC40,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F40="","",IF(OR(AA40="Cancelled",AC40="Cancelled"),"Cancelled",IF(OR(AC40="Completed / Handover",Y40<>"",Z40>=100),"Completed — on track",IF(O40="Not awarded",IF(U40="",IF(X40="","No planned date",IF(TODAY()>X40,"Behind — past planned date",IF(X40-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U40,"Behind — award date passed",IF(U40-TODAY()<=30,"At risk — close to off track","On track"))),IF(X40="","No planned date",IF(AND(TODAY()>X40,OR(Z40="",Z40<100)),"Behind — past end date",IF(AND(T40<>"",X40<>"",Z40<>"",(Z40<100),((TODAY()-T40)/MAX(X40-T40,1)*100)-Z40>15),"Behind — progress lag",IF(AND(X40-TODAY()<=30,X40-TODAY()>=0,OR(Z40="",Z40<90)),"At risk — close to off track","On track")))))))) | IF(OR(F40="",AC40="Completed / Handover",AC40="Cancelled"),"",IF(O40="Not awarded",IF(U40<>"",U40-TODAY(),IF(X40="","",X40-TODAY())),IF(X40="","",X40-TODAY()))) | [14 empty] | IF(OR(F40="",AJ40=""),"",IF(COUNT(AI40:AI40)=0,"",AJ40-LOOKUP(2,1/(AI40:AI40<>""),AI40:AI40))) | IF(OR(F40="",AK40=""),"",IF(COUNT(AI40:AJ40)=0,"",AK40-LOOKUP(2,1/(AI40:AJ40<>""),AI40:AJ40))) | IF(OR(F40="",AL40=""),"",IF(COUNT(AI40:AK40)=0,"",AL40-LOOKUP(2,1/(AI40:AK40<>""),AI40:AK40))) | IF(OR(F40="",AM40=""),"",IF(COUNT(AI40:AL40)=0,"",AM40-LOOKUP(2,1/(AI40:AL40<>""),AI40:AL40))) | IF(OR(F40="",AN40=""),"",IF(COUNT(AI40:AM40)=0,"",AN40-LOOKUP(2,1/(AI40:AM40<>""),AI40:AM40))) | IF(OR(F40="",AO40=""),"",IF(COUNT(AI40:AN40)=0,"",AO40-LOOKUP(2,1/(AI40:AN40<>""),AI40:AN40))) | IF(OR(F40="",AP40=""),"",IF(COUNT(AI40:AO40)=0,"",AP40-LOOKUP(2,1/(AI40:AO40<>""),AI40:AO40))) | IF(OR(F40="",AQ40=""),"",IF(COUNT(AI40:AP40)=0,"",AQ40-LOOKUP(2,1/(AI40:AP40<>""),AI40:AP40))) | IF(OR(F40="",AR40=""),"",IF(COUNT(AI40:AQ40)=0,"",AR40-LOOKUP(2,1/(AI40:AQ40<>""),AI40:AQ40))) | IF(OR(F40="",AS40=""),"",IF(COUNT(AI40:AR40)=0,"",AS40-LOOKUP(2,1/(AI40:AR40<>""),AI40:AR40))) | IF(OR(F40="",AT40=""),"",IF(COUNT(AI40:AS40)=0,"",AT40-LOOKUP(2,1/(AI40:AS40<>""),AI40:AS40))) | IF(OR(F40="",AU40=""),"",IF(COUNT(AI40:AT40)=0,"",AU40-LOOKUP(2,1/(AI40:AT40<>""),AI40:AT40))) | IF(OR(F40="",AV40=""),"",IF(COUNT(AI40:AU40)=0,"",AV40-LOOKUP(2,1/(AI40:AU40<>""),AI40:AU40))) | IF(J40="","All_Provinces",IFERROR(VLOOKUP(J40,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K40="","All_Districts",IFERROR(VLOOKUP(K40,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F41="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 38 of 39 | AF2-AGF-N-038 | Agroforestry — Sari Pul / Kohistanat | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sari Pul | Kohistanat | Saplings: 0; Seeds kg: 30 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ41="","",AQ41) | 2026-04-30 | 12 | 2027-04-01 | IF(W41<>"",W41,IF(OR(T41="",V41=""),"",EDATE(T41,V41))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F41="","",IF(COUNT(AI41:AV41)=0,IF(AA41="","Not started",AA41),SUBSTITUTE(LOOKUP(2,1/(AI41:AV41<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F41="",COUNT(AI41:AV41)=0),"",TODAY()-LOOKUP(2,1/(AI41:AV41<>""),AI41:AV41)) | IF(OR(F41="",COUNT(AI41:AV41)<2),"",LOOKUP(2,1/(AI41:AV41<>""),AI41:AV41)-MIN(AI41:AV41)) | IF(OR(AD41="",AC41="Not started",AC41=""),"",IFERROR(AD41-IF(VLOOKUP(AC41,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC41,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F41="","",IF(OR(AA41="Cancelled",AC41="Cancelled"),"Cancelled",IF(OR(AC41="Completed / Handover",Y41<>"",Z41>=100),"Completed — on track",IF(O41="Not awarded",IF(U41="",IF(X41="","No planned date",IF(TODAY()>X41,"Behind — past planned date",IF(X41-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U41,"Behind — award date passed",IF(U41-TODAY()<=30,"At risk — close to off track","On track"))),IF(X41="","No planned date",IF(AND(TODAY()>X41,OR(Z41="",Z41<100)),"Behind — past end date",IF(AND(T41<>"",X41<>"",Z41<>"",(Z41<100),((TODAY()-T41)/MAX(X41-T41,1)*100)-Z41>15),"Behind — progress lag",IF(AND(X41-TODAY()<=30,X41-TODAY()>=0,OR(Z41="",Z41<90)),"At risk — close to off track","On track")))))))) | IF(OR(F41="",AC41="Completed / Handover",AC41="Cancelled"),"",IF(O41="Not awarded",IF(U41<>"",U41-TODAY(),IF(X41="","",X41-TODAY())),IF(X41="","",X41-TODAY()))) | [14 empty] | IF(OR(F41="",AJ41=""),"",IF(COUNT(AI41:AI41)=0,"",AJ41-LOOKUP(2,1/(AI41:AI41<>""),AI41:AI41))) | IF(OR(F41="",AK41=""),"",IF(COUNT(AI41:AJ41)=0,"",AK41-LOOKUP(2,1/(AI41:AJ41<>""),AI41:AJ41))) | IF(OR(F41="",AL41=""),"",IF(COUNT(AI41:AK41)=0,"",AL41-LOOKUP(2,1/(AI41:AK41<>""),AI41:AK41))) | IF(OR(F41="",AM41=""),"",IF(COUNT(AI41:AL41)=0,"",AM41-LOOKUP(2,1/(AI41:AL41<>""),AI41:AL41))) | IF(OR(F41="",AN41=""),"",IF(COUNT(AI41:AM41)=0,"",AN41-LOOKUP(2,1/(AI41:AM41<>""),AI41:AM41))) | IF(OR(F41="",AO41=""),"",IF(COUNT(AI41:AN41)=0,"",AO41-LOOKUP(2,1/(AI41:AN41<>""),AI41:AN41))) | IF(OR(F41="",AP41=""),"",IF(COUNT(AI41:AO41)=0,"",AP41-LOOKUP(2,1/(AI41:AO41<>""),AI41:AO41))) | IF(OR(F41="",AQ41=""),"",IF(COUNT(AI41:AP41)=0,"",AQ41-LOOKUP(2,1/(AI41:AP41<>""),AI41:AP41))) | IF(OR(F41="",AR41=""),"",IF(COUNT(AI41:AQ41)=0,"",AR41-LOOKUP(2,1/(AI41:AQ41<>""),AI41:AQ41))) | IF(OR(F41="",AS41=""),"",IF(COUNT(AI41:AR41)=0,"",AS41-LOOKUP(2,1/(AI41:AR41<>""),AI41:AR41))) | IF(OR(F41="",AT41=""),"",IF(COUNT(AI41:AS41)=0,"",AT41-LOOKUP(2,1/(AI41:AS41<>""),AI41:AS41))) | IF(OR(F41="",AU41=""),"",IF(COUNT(AI41:AT41)=0,"",AU41-LOOKUP(2,1/(AI41:AT41<>""),AI41:AT41))) | IF(OR(F41="",AV41=""),"",IF(COUNT(AI41:AU41)=0,"",AV41-LOOKUP(2,1/(AI41:AU41<>""),AI41:AU41))) | IF(J41="","All_Provinces",IFERROR(VLOOKUP(J41,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K41="","All_Districts",IFERROR(VLOOKUP(K41,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F42="","",ROW()-3) | AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | 39 of 39 | AF2-AGF-N-039 | Agroforestry — Takhar / Bangi | Agroforestry saplings / seeds | Saplings and seeds | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Bangi | Saplings: 8500; Seeds kg: 234 | World Bank (WBK/AF-2) | Not awarded | 7. Agroforestry Saplings-seeds |  |  |  | IF(AQ42="","",AQ42) | 2026-04-30 | 12 | 2027-04-01 | IF(W42<>"",W42,IF(OR(T42="",V42=""),"",EDATE(T42,V42))) |  |  | Under Awarding | The saplings PO has already been issued and PO for seeds is expected to be issued in November 2026 | IF(F42="","",IF(COUNT(AI42:AV42)=0,IF(AA42="","Not started",AA42),SUBSTITUTE(LOOKUP(2,1/(AI42:AV42<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F42="",COUNT(AI42:AV42)=0),"",TODAY()-LOOKUP(2,1/(AI42:AV42<>""),AI42:AV42)) | IF(OR(F42="",COUNT(AI42:AV42)<2),"",LOOKUP(2,1/(AI42:AV42<>""),AI42:AV42)-MIN(AI42:AV42)) | IF(OR(AD42="",AC42="Not started",AC42=""),"",IFERROR(AD42-IF(VLOOKUP(AC42,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC42,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F42="","",IF(OR(AA42="Cancelled",AC42="Cancelled"),"Cancelled",IF(OR(AC42="Completed / Handover",Y42<>"",Z42>=100),"Completed — on track",IF(O42="Not awarded",IF(U42="",IF(X42="","No planned date",IF(TODAY()>X42,"Behind — past planned date",IF(X42-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U42,"Behind — award date passed",IF(U42-TODAY()<=30,"At risk — close to off track","On track"))),IF(X42="","No planned date",IF(AND(TODAY()>X42,OR(Z42="",Z42<100)),"Behind — past end date",IF(AND(T42<>"",X42<>"",Z42<>"",(Z42<100),((TODAY()-T42)/MAX(X42-T42,1)*100)-Z42>15),"Behind — progress lag",IF(AND(X42-TODAY()<=30,X42-TODAY()>=0,OR(Z42="",Z42<90)),"At risk — close to off track","On track")))))))) | IF(OR(F42="",AC42="Completed / Handover",AC42="Cancelled"),"",IF(O42="Not awarded",IF(U42<>"",U42-TODAY(),IF(X42="","",X42-TODAY())),IF(X42="","",X42-TODAY()))) | [14 empty] | IF(OR(F42="",AJ42=""),"",IF(COUNT(AI42:AI42)=0,"",AJ42-LOOKUP(2,1/(AI42:AI42<>""),AI42:AI42))) | IF(OR(F42="",AK42=""),"",IF(COUNT(AI42:AJ42)=0,"",AK42-LOOKUP(2,1/(AI42:AJ42<>""),AI42:AJ42))) | IF(OR(F42="",AL42=""),"",IF(COUNT(AI42:AK42)=0,"",AL42-LOOKUP(2,1/(AI42:AK42<>""),AI42:AK42))) | IF(OR(F42="",AM42=""),"",IF(COUNT(AI42:AL42)=0,"",AM42-LOOKUP(2,1/(AI42:AL42<>""),AI42:AL42))) | IF(OR(F42="",AN42=""),"",IF(COUNT(AI42:AM42)=0,"",AN42-LOOKUP(2,1/(AI42:AM42<>""),AI42:AM42))) | IF(OR(F42="",AO42=""),"",IF(COUNT(AI42:AN42)=0,"",AO42-LOOKUP(2,1/(AI42:AN42<>""),AI42:AN42))) | IF(OR(F42="",AP42=""),"",IF(COUNT(AI42:AO42)=0,"",AP42-LOOKUP(2,1/(AI42:AO42<>""),AI42:AO42))) | IF(OR(F42="",AQ42=""),"",IF(COUNT(AI42:AP42)=0,"",AQ42-LOOKUP(2,1/(AI42:AP42<>""),AI42:AP42))) | IF(OR(F42="",AR42=""),"",IF(COUNT(AI42:AQ42)=0,"",AR42-LOOKUP(2,1/(AI42:AQ42<>""),AI42:AQ42))) | IF(OR(F42="",AS42=""),"",IF(COUNT(AI42:AR42)=0,"",AS42-LOOKUP(2,1/(AI42:AR42<>""),AI42:AR42))) | IF(OR(F42="",AT42=""),"",IF(COUNT(AI42:AS42)=0,"",AT42-LOOKUP(2,1/(AI42:AS42<>""),AI42:AS42))) | IF(OR(F42="",AU42=""),"",IF(COUNT(AI42:AT42)=0,"",AU42-LOOKUP(2,1/(AI42:AT42<>""),AI42:AT42))) | IF(OR(F42="",AV42=""),"",IF(COUNT(AI42:AU42)=0,"",AV42-LOOKUP(2,1/(AI42:AU42<>""),AI42:AU42))) | IF(J42="","All_Provinces",IFERROR(VLOOKUP(J42,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K42="","All_Districts",IFERROR(VLOOKUP(K42,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F43="","",ROW()-3) | AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 1 of 7 | AF2-DIS-N-001 | Doormishi Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Kushk e Rabat Sangi | Dormishi | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Abdul Qayum |  | 6771.4 | IF(AQ43="","",AQ43) | 2026-12-15 | 4.4 | 2027-04-29 | IF(W43<>"",W43,IF(OR(T43="",V43=""),"",EDATE(T43,V43))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Abdul Qayum | IF(F43="","",IF(COUNT(AI43:AV43)=0,IF(AA43="","Not started",AA43),SUBSTITUTE(LOOKUP(2,1/(AI43:AV43<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F43="",COUNT(AI43:AV43)=0),"",TODAY()-LOOKUP(2,1/(AI43:AV43<>""),AI43:AV43)) | IF(OR(F43="",COUNT(AI43:AV43)<2),"",LOOKUP(2,1/(AI43:AV43<>""),AI43:AV43)-MIN(AI43:AV43)) | IF(OR(AD43="",AC43="Not started",AC43=""),"",IFERROR(AD43-IF(VLOOKUP(AC43,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC43,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F43="","",IF(OR(AA43="Cancelled",AC43="Cancelled"),"Cancelled",IF(OR(AC43="Completed / Handover",Y43<>"",Z43>=100),"Completed — on track",IF(O43="Not awarded",IF(U43="",IF(X43="","No planned date",IF(TODAY()>X43,"Behind — past planned date",IF(X43-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U43,"Behind — award date passed",IF(U43-TODAY()<=30,"At risk — close to off track","On track"))),IF(X43="","No planned date",IF(AND(TODAY()>X43,OR(Z43="",Z43<100)),"Behind — past end date",IF(AND(T43<>"",X43<>"",Z43<>"",(Z43<100),((TODAY()-T43)/MAX(X43-T43,1)*100)-Z43>15),"Behind — progress lag",IF(AND(X43-TODAY()<=30,X43-TODAY()>=0,OR(Z43="",Z43<90)),"At risk — close to off track","On track")))))))) | IF(OR(F43="",AC43="Completed / Handover",AC43="Cancelled"),"",IF(O43="Not awarded",IF(U43<>"",U43-TODAY(),IF(X43="","",X43-TODAY())),IF(X43="","",X43-TODAY()))) | [14 empty] | IF(OR(F43="",AJ43=""),"",IF(COUNT(AI43:AI43)=0,"",AJ43-LOOKUP(2,1/(AI43:AI43<>""),AI43:AI43))) | IF(OR(F43="",AK43=""),"",IF(COUNT(AI43:AJ43)=0,"",AK43-LOOKUP(2,1/(AI43:AJ43<>""),AI43:AJ43))) | IF(OR(F43="",AL43=""),"",IF(COUNT(AI43:AK43)=0,"",AL43-LOOKUP(2,1/(AI43:AK43<>""),AI43:AK43))) | IF(OR(F43="",AM43=""),"",IF(COUNT(AI43:AL43)=0,"",AM43-LOOKUP(2,1/(AI43:AL43<>""),AI43:AL43))) | IF(OR(F43="",AN43=""),"",IF(COUNT(AI43:AM43)=0,"",AN43-LOOKUP(2,1/(AI43:AM43<>""),AI43:AM43))) | IF(OR(F43="",AO43=""),"",IF(COUNT(AI43:AN43)=0,"",AO43-LOOKUP(2,1/(AI43:AN43<>""),AI43:AN43))) | IF(OR(F43="",AP43=""),"",IF(COUNT(AI43:AO43)=0,"",AP43-LOOKUP(2,1/(AI43:AO43<>""),AI43:AO43))) | IF(OR(F43="",AQ43=""),"",IF(COUNT(AI43:AP43)=0,"",AQ43-LOOKUP(2,1/(AI43:AP43<>""),AI43:AP43))) | IF(OR(F43="",AR43=""),"",IF(COUNT(AI43:AQ43)=0,"",AR43-LOOKUP(2,1/(AI43:AQ43<>""),AI43:AQ43))) | IF(OR(F43="",AS43=""),"",IF(COUNT(AI43:AR43)=0,"",AS43-LOOKUP(2,1/(AI43:AR43<>""),AI43:AR43))) | IF(OR(F43="",AT43=""),"",IF(COUNT(AI43:AS43)=0,"",AT43-LOOKUP(2,1/(AI43:AS43<>""),AI43:AS43))) | IF(OR(F43="",AU43=""),"",IF(COUNT(AI43:AT43)=0,"",AU43-LOOKUP(2,1/(AI43:AT43<>""),AI43:AT43))) | IF(OR(F43="",AV43=""),"",IF(COUNT(AI43:AU43)=0,"",AV43-LOOKUP(2,1/(AI43:AU43<>""),AI43:AU43))) | IF(J43="","All_Provinces",IFERROR(VLOOKUP(J43,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K43="","All_Districts",IFERROR(VLOOKUP(K43,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F44="","",ROW()-3) | AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 2 of 7 | AF2-DIS-N-002 | Joi Sultani Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Kushk e Kohna | Joy sultany | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Habiburahman |  | 6417.22 | IF(AQ44="","",AQ44) | 2026-12-15 | 4.4 | 2027-04-29 | IF(W44<>"",W44,IF(OR(T44="",V44=""),"",EDATE(T44,V44))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Habiburahman | IF(F44="","",IF(COUNT(AI44:AV44)=0,IF(AA44="","Not started",AA44),SUBSTITUTE(LOOKUP(2,1/(AI44:AV44<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F44="",COUNT(AI44:AV44)=0),"",TODAY()-LOOKUP(2,1/(AI44:AV44<>""),AI44:AV44)) | IF(OR(F44="",COUNT(AI44:AV44)<2),"",LOOKUP(2,1/(AI44:AV44<>""),AI44:AV44)-MIN(AI44:AV44)) | IF(OR(AD44="",AC44="Not started",AC44=""),"",IFERROR(AD44-IF(VLOOKUP(AC44,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC44,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F44="","",IF(OR(AA44="Cancelled",AC44="Cancelled"),"Cancelled",IF(OR(AC44="Completed / Handover",Y44<>"",Z44>=100),"Completed — on track",IF(O44="Not awarded",IF(U44="",IF(X44="","No planned date",IF(TODAY()>X44,"Behind — past planned date",IF(X44-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U44,"Behind — award date passed",IF(U44-TODAY()<=30,"At risk — close to off track","On track"))),IF(X44="","No planned date",IF(AND(TODAY()>X44,OR(Z44="",Z44<100)),"Behind — past end date",IF(AND(T44<>"",X44<>"",Z44<>"",(Z44<100),((TODAY()-T44)/MAX(X44-T44,1)*100)-Z44>15),"Behind — progress lag",IF(AND(X44-TODAY()<=30,X44-TODAY()>=0,OR(Z44="",Z44<90)),"At risk — close to off track","On track")))))))) | IF(OR(F44="",AC44="Completed / Handover",AC44="Cancelled"),"",IF(O44="Not awarded",IF(U44<>"",U44-TODAY(),IF(X44="","",X44-TODAY())),IF(X44="","",X44-TODAY()))) | [14 empty] | IF(OR(F44="",AJ44=""),"",IF(COUNT(AI44:AI44)=0,"",AJ44-LOOKUP(2,1/(AI44:AI44<>""),AI44:AI44))) | IF(OR(F44="",AK44=""),"",IF(COUNT(AI44:AJ44)=0,"",AK44-LOOKUP(2,1/(AI44:AJ44<>""),AI44:AJ44))) | IF(OR(F44="",AL44=""),"",IF(COUNT(AI44:AK44)=0,"",AL44-LOOKUP(2,1/(AI44:AK44<>""),AI44:AK44))) | IF(OR(F44="",AM44=""),"",IF(COUNT(AI44:AL44)=0,"",AM44-LOOKUP(2,1/(AI44:AL44<>""),AI44:AL44))) | IF(OR(F44="",AN44=""),"",IF(COUNT(AI44:AM44)=0,"",AN44-LOOKUP(2,1/(AI44:AM44<>""),AI44:AM44))) | IF(OR(F44="",AO44=""),"",IF(COUNT(AI44:AN44)=0,"",AO44-LOOKUP(2,1/(AI44:AN44<>""),AI44:AN44))) | IF(OR(F44="",AP44=""),"",IF(COUNT(AI44:AO44)=0,"",AP44-LOOKUP(2,1/(AI44:AO44<>""),AI44:AO44))) | IF(OR(F44="",AQ44=""),"",IF(COUNT(AI44:AP44)=0,"",AQ44-LOOKUP(2,1/(AI44:AP44<>""),AI44:AP44))) | IF(OR(F44="",AR44=""),"",IF(COUNT(AI44:AQ44)=0,"",AR44-LOOKUP(2,1/(AI44:AQ44<>""),AI44:AQ44))) | IF(OR(F44="",AS44=""),"",IF(COUNT(AI44:AR44)=0,"",AS44-LOOKUP(2,1/(AI44:AR44<>""),AI44:AR44))) | IF(OR(F44="",AT44=""),"",IF(COUNT(AI44:AS44)=0,"",AT44-LOOKUP(2,1/(AI44:AS44<>""),AI44:AS44))) | IF(OR(F44="",AU44=""),"",IF(COUNT(AI44:AT44)=0,"",AU44-LOOKUP(2,1/(AI44:AT44<>""),AI44:AT44))) | IF(OR(F44="",AV44=""),"",IF(COUNT(AI44:AU44)=0,"",AV44-LOOKUP(2,1/(AI44:AU44<>""),AI44:AU44))) | IF(J44="","All_Provinces",IFERROR(VLOOKUP(J44,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K44="","All_Districts",IFERROR(VLOOKUP(K44,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F45="","",ROW()-3) | AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 3 of 7 | AF2-DIS-N-003 | Karez Naw Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Kushk e Rabat Sangi | Karez Naw | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ghulam Mahboob |  | 8066.29 | IF(AQ45="","",AQ45) | 2026-12-15 | 4.4 | 2027-04-29 | IF(W45<>"",W45,IF(OR(T45="",V45=""),"",EDATE(T45,V45))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Ghulam Mahboob | IF(F45="","",IF(COUNT(AI45:AV45)=0,IF(AA45="","Not started",AA45),SUBSTITUTE(LOOKUP(2,1/(AI45:AV45<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F45="",COUNT(AI45:AV45)=0),"",TODAY()-LOOKUP(2,1/(AI45:AV45<>""),AI45:AV45)) | IF(OR(F45="",COUNT(AI45:AV45)<2),"",LOOKUP(2,1/(AI45:AV45<>""),AI45:AV45)-MIN(AI45:AV45)) | IF(OR(AD45="",AC45="Not started",AC45=""),"",IFERROR(AD45-IF(VLOOKUP(AC45,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC45,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F45="","",IF(OR(AA45="Cancelled",AC45="Cancelled"),"Cancelled",IF(OR(AC45="Completed / Handover",Y45<>"",Z45>=100),"Completed — on track",IF(O45="Not awarded",IF(U45="",IF(X45="","No planned date",IF(TODAY()>X45,"Behind — past planned date",IF(X45-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U45,"Behind — award date passed",IF(U45-TODAY()<=30,"At risk — close to off track","On track"))),IF(X45="","No planned date",IF(AND(TODAY()>X45,OR(Z45="",Z45<100)),"Behind — past end date",IF(AND(T45<>"",X45<>"",Z45<>"",(Z45<100),((TODAY()-T45)/MAX(X45-T45,1)*100)-Z45>15),"Behind — progress lag",IF(AND(X45-TODAY()<=30,X45-TODAY()>=0,OR(Z45="",Z45<90)),"At risk — close to off track","On track")))))))) | IF(OR(F45="",AC45="Completed / Handover",AC45="Cancelled"),"",IF(O45="Not awarded",IF(U45<>"",U45-TODAY(),IF(X45="","",X45-TODAY())),IF(X45="","",X45-TODAY()))) | [14 empty] | IF(OR(F45="",AJ45=""),"",IF(COUNT(AI45:AI45)=0,"",AJ45-LOOKUP(2,1/(AI45:AI45<>""),AI45:AI45))) | IF(OR(F45="",AK45=""),"",IF(COUNT(AI45:AJ45)=0,"",AK45-LOOKUP(2,1/(AI45:AJ45<>""),AI45:AJ45))) | IF(OR(F45="",AL45=""),"",IF(COUNT(AI45:AK45)=0,"",AL45-LOOKUP(2,1/(AI45:AK45<>""),AI45:AK45))) | IF(OR(F45="",AM45=""),"",IF(COUNT(AI45:AL45)=0,"",AM45-LOOKUP(2,1/(AI45:AL45<>""),AI45:AL45))) | IF(OR(F45="",AN45=""),"",IF(COUNT(AI45:AM45)=0,"",AN45-LOOKUP(2,1/(AI45:AM45<>""),AI45:AM45))) | IF(OR(F45="",AO45=""),"",IF(COUNT(AI45:AN45)=0,"",AO45-LOOKUP(2,1/(AI45:AN45<>""),AI45:AN45))) | IF(OR(F45="",AP45=""),"",IF(COUNT(AI45:AO45)=0,"",AP45-LOOKUP(2,1/(AI45:AO45<>""),AI45:AO45))) | IF(OR(F45="",AQ45=""),"",IF(COUNT(AI45:AP45)=0,"",AQ45-LOOKUP(2,1/(AI45:AP45<>""),AI45:AP45))) | IF(OR(F45="",AR45=""),"",IF(COUNT(AI45:AQ45)=0,"",AR45-LOOKUP(2,1/(AI45:AQ45<>""),AI45:AQ45))) | IF(OR(F45="",AS45=""),"",IF(COUNT(AI45:AR45)=0,"",AS45-LOOKUP(2,1/(AI45:AR45<>""),AI45:AR45))) | IF(OR(F45="",AT45=""),"",IF(COUNT(AI45:AS45)=0,"",AT45-LOOKUP(2,1/(AI45:AS45<>""),AI45:AS45))) | IF(OR(F45="",AU45=""),"",IF(COUNT(AI45:AT45)=0,"",AU45-LOOKUP(2,1/(AI45:AT45<>""),AI45:AT45))) | IF(OR(F45="",AV45=""),"",IF(COUNT(AI45:AU45)=0,"",AV45-LOOKUP(2,1/(AI45:AU45<>""),AI45:AU45))) | IF(J45="","All_Provinces",IFERROR(VLOOKUP(J45,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K45="","All_Districts",IFERROR(VLOOKUP(K45,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F46="","",ROW()-3) | AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 4 of 7 | AF2-DIS-N-004 | Khodrawan Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Kushk e Rabat Sangi | Khodrawan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Sadullah |  | 8259.97 | IF(AQ46="","",AQ46) | 2026-12-15 | 4.4 | 2027-04-29 | IF(W46<>"",W46,IF(OR(T46="",V46=""),"",EDATE(T46,V46))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Sadullah | IF(F46="","",IF(COUNT(AI46:AV46)=0,IF(AA46="","Not started",AA46),SUBSTITUTE(LOOKUP(2,1/(AI46:AV46<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F46="",COUNT(AI46:AV46)=0),"",TODAY()-LOOKUP(2,1/(AI46:AV46<>""),AI46:AV46)) | IF(OR(F46="",COUNT(AI46:AV46)<2),"",LOOKUP(2,1/(AI46:AV46<>""),AI46:AV46)-MIN(AI46:AV46)) | IF(OR(AD46="",AC46="Not started",AC46=""),"",IFERROR(AD46-IF(VLOOKUP(AC46,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC46,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F46="","",IF(OR(AA46="Cancelled",AC46="Cancelled"),"Cancelled",IF(OR(AC46="Completed / Handover",Y46<>"",Z46>=100),"Completed — on track",IF(O46="Not awarded",IF(U46="",IF(X46="","No planned date",IF(TODAY()>X46,"Behind — past planned date",IF(X46-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U46,"Behind — award date passed",IF(U46-TODAY()<=30,"At risk — close to off track","On track"))),IF(X46="","No planned date",IF(AND(TODAY()>X46,OR(Z46="",Z46<100)),"Behind — past end date",IF(AND(T46<>"",X46<>"",Z46<>"",(Z46<100),((TODAY()-T46)/MAX(X46-T46,1)*100)-Z46>15),"Behind — progress lag",IF(AND(X46-TODAY()<=30,X46-TODAY()>=0,OR(Z46="",Z46<90)),"At risk — close to off track","On track")))))))) | IF(OR(F46="",AC46="Completed / Handover",AC46="Cancelled"),"",IF(O46="Not awarded",IF(U46<>"",U46-TODAY(),IF(X46="","",X46-TODAY())),IF(X46="","",X46-TODAY()))) | [14 empty] | IF(OR(F46="",AJ46=""),"",IF(COUNT(AI46:AI46)=0,"",AJ46-LOOKUP(2,1/(AI46:AI46<>""),AI46:AI46))) | IF(OR(F46="",AK46=""),"",IF(COUNT(AI46:AJ46)=0,"",AK46-LOOKUP(2,1/(AI46:AJ46<>""),AI46:AJ46))) | IF(OR(F46="",AL46=""),"",IF(COUNT(AI46:AK46)=0,"",AL46-LOOKUP(2,1/(AI46:AK46<>""),AI46:AK46))) | IF(OR(F46="",AM46=""),"",IF(COUNT(AI46:AL46)=0,"",AM46-LOOKUP(2,1/(AI46:AL46<>""),AI46:AL46))) | IF(OR(F46="",AN46=""),"",IF(COUNT(AI46:AM46)=0,"",AN46-LOOKUP(2,1/(AI46:AM46<>""),AI46:AM46))) | IF(OR(F46="",AO46=""),"",IF(COUNT(AI46:AN46)=0,"",AO46-LOOKUP(2,1/(AI46:AN46<>""),AI46:AN46))) | IF(OR(F46="",AP46=""),"",IF(COUNT(AI46:AO46)=0,"",AP46-LOOKUP(2,1/(AI46:AO46<>""),AI46:AO46))) | IF(OR(F46="",AQ46=""),"",IF(COUNT(AI46:AP46)=0,"",AQ46-LOOKUP(2,1/(AI46:AP46<>""),AI46:AP46))) | IF(OR(F46="",AR46=""),"",IF(COUNT(AI46:AQ46)=0,"",AR46-LOOKUP(2,1/(AI46:AQ46<>""),AI46:AQ46))) | IF(OR(F46="",AS46=""),"",IF(COUNT(AI46:AR46)=0,"",AS46-LOOKUP(2,1/(AI46:AR46<>""),AI46:AR46))) | IF(OR(F46="",AT46=""),"",IF(COUNT(AI46:AS46)=0,"",AT46-LOOKUP(2,1/(AI46:AS46<>""),AI46:AS46))) | IF(OR(F46="",AU46=""),"",IF(COUNT(AI46:AT46)=0,"",AU46-LOOKUP(2,1/(AI46:AT46<>""),AI46:AT46))) | IF(OR(F46="",AV46=""),"",IF(COUNT(AI46:AU46)=0,"",AV46-LOOKUP(2,1/(AI46:AU46<>""),AI46:AU46))) | IF(J46="","All_Provinces",IFERROR(VLOOKUP(J46,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K46="","All_Districts",IFERROR(VLOOKUP(K46,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F47="","",ROW()-3) | AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 5 of 7 | AF2-DIS-N-005 | Koklam Olia Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Kushk e Kohna | Koklam Olia | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Fazl Ahmad |  | 9545.19 | IF(AQ47="","",AQ47) | 2026-12-15 | 4.4 | 2027-04-29 | IF(W47<>"",W47,IF(OR(T47="",V47=""),"",EDATE(T47,V47))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Fazl Ahmad | IF(F47="","",IF(COUNT(AI47:AV47)=0,IF(AA47="","Not started",AA47),SUBSTITUTE(LOOKUP(2,1/(AI47:AV47<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F47="",COUNT(AI47:AV47)=0),"",TODAY()-LOOKUP(2,1/(AI47:AV47<>""),AI47:AV47)) | IF(OR(F47="",COUNT(AI47:AV47)<2),"",LOOKUP(2,1/(AI47:AV47<>""),AI47:AV47)-MIN(AI47:AV47)) | IF(OR(AD47="",AC47="Not started",AC47=""),"",IFERROR(AD47-IF(VLOOKUP(AC47,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC47,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F47="","",IF(OR(AA47="Cancelled",AC47="Cancelled"),"Cancelled",IF(OR(AC47="Completed / Handover",Y47<>"",Z47>=100),"Completed — on track",IF(O47="Not awarded",IF(U47="",IF(X47="","No planned date",IF(TODAY()>X47,"Behind — past planned date",IF(X47-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U47,"Behind — award date passed",IF(U47-TODAY()<=30,"At risk — close to off track","On track"))),IF(X47="","No planned date",IF(AND(TODAY()>X47,OR(Z47="",Z47<100)),"Behind — past end date",IF(AND(T47<>"",X47<>"",Z47<>"",(Z47<100),((TODAY()-T47)/MAX(X47-T47,1)*100)-Z47>15),"Behind — progress lag",IF(AND(X47-TODAY()<=30,X47-TODAY()>=0,OR(Z47="",Z47<90)),"At risk — close to off track","On track")))))))) | IF(OR(F47="",AC47="Completed / Handover",AC47="Cancelled"),"",IF(O47="Not awarded",IF(U47<>"",U47-TODAY(),IF(X47="","",X47-TODAY())),IF(X47="","",X47-TODAY()))) | [14 empty] | IF(OR(F47="",AJ47=""),"",IF(COUNT(AI47:AI47)=0,"",AJ47-LOOKUP(2,1/(AI47:AI47<>""),AI47:AI47))) | IF(OR(F47="",AK47=""),"",IF(COUNT(AI47:AJ47)=0,"",AK47-LOOKUP(2,1/(AI47:AJ47<>""),AI47:AJ47))) | IF(OR(F47="",AL47=""),"",IF(COUNT(AI47:AK47)=0,"",AL47-LOOKUP(2,1/(AI47:AK47<>""),AI47:AK47))) | IF(OR(F47="",AM47=""),"",IF(COUNT(AI47:AL47)=0,"",AM47-LOOKUP(2,1/(AI47:AL47<>""),AI47:AL47))) | IF(OR(F47="",AN47=""),"",IF(COUNT(AI47:AM47)=0,"",AN47-LOOKUP(2,1/(AI47:AM47<>""),AI47:AM47))) | IF(OR(F47="",AO47=""),"",IF(COUNT(AI47:AN47)=0,"",AO47-LOOKUP(2,1/(AI47:AN47<>""),AI47:AN47))) | IF(OR(F47="",AP47=""),"",IF(COUNT(AI47:AO47)=0,"",AP47-LOOKUP(2,1/(AI47:AO47<>""),AI47:AO47))) | IF(OR(F47="",AQ47=""),"",IF(COUNT(AI47:AP47)=0,"",AQ47-LOOKUP(2,1/(AI47:AP47<>""),AI47:AP47))) | IF(OR(F47="",AR47=""),"",IF(COUNT(AI47:AQ47)=0,"",AR47-LOOKUP(2,1/(AI47:AQ47<>""),AI47:AQ47))) | IF(OR(F47="",AS47=""),"",IF(COUNT(AI47:AR47)=0,"",AS47-LOOKUP(2,1/(AI47:AR47<>""),AI47:AR47))) | IF(OR(F47="",AT47=""),"",IF(COUNT(AI47:AS47)=0,"",AT47-LOOKUP(2,1/(AI47:AS47<>""),AI47:AS47))) | IF(OR(F47="",AU47=""),"",IF(COUNT(AI47:AT47)=0,"",AU47-LOOKUP(2,1/(AI47:AT47<>""),AI47:AT47))) | IF(OR(F47="",AV47=""),"",IF(COUNT(AI47:AU47)=0,"",AV47-LOOKUP(2,1/(AI47:AU47<>""),AI47:AU47))) | IF(J47="","All_Provinces",IFERROR(VLOOKUP(J47,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K47="","All_Districts",IFERROR(VLOOKUP(K47,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F48="","",ROW()-3) | AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 6 of 7 | AF2-DIS-N-006 | Koklam Sofla Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Kushk e Kohna | Koklam Sofla | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Nesar Ahmad, Koklam |  | 7974.31 | IF(AQ48="","",AQ48) | 2026-12-15 | 4.4 | 2027-04-29 | IF(W48<>"",W48,IF(OR(T48="",V48=""),"",EDATE(T48,V48))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Nesar Ahmad, Koklam | IF(F48="","",IF(COUNT(AI48:AV48)=0,IF(AA48="","Not started",AA48),SUBSTITUTE(LOOKUP(2,1/(AI48:AV48<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F48="",COUNT(AI48:AV48)=0),"",TODAY()-LOOKUP(2,1/(AI48:AV48<>""),AI48:AV48)) | IF(OR(F48="",COUNT(AI48:AV48)<2),"",LOOKUP(2,1/(AI48:AV48<>""),AI48:AV48)-MIN(AI48:AV48)) | IF(OR(AD48="",AC48="Not started",AC48=""),"",IFERROR(AD48-IF(VLOOKUP(AC48,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC48,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F48="","",IF(OR(AA48="Cancelled",AC48="Cancelled"),"Cancelled",IF(OR(AC48="Completed / Handover",Y48<>"",Z48>=100),"Completed — on track",IF(O48="Not awarded",IF(U48="",IF(X48="","No planned date",IF(TODAY()>X48,"Behind — past planned date",IF(X48-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U48,"Behind — award date passed",IF(U48-TODAY()<=30,"At risk — close to off track","On track"))),IF(X48="","No planned date",IF(AND(TODAY()>X48,OR(Z48="",Z48<100)),"Behind — past end date",IF(AND(T48<>"",X48<>"",Z48<>"",(Z48<100),((TODAY()-T48)/MAX(X48-T48,1)*100)-Z48>15),"Behind — progress lag",IF(AND(X48-TODAY()<=30,X48-TODAY()>=0,OR(Z48="",Z48<90)),"At risk — close to off track","On track")))))))) | IF(OR(F48="",AC48="Completed / Handover",AC48="Cancelled"),"",IF(O48="Not awarded",IF(U48<>"",U48-TODAY(),IF(X48="","",X48-TODAY())),IF(X48="","",X48-TODAY()))) | [14 empty] | IF(OR(F48="",AJ48=""),"",IF(COUNT(AI48:AI48)=0,"",AJ48-LOOKUP(2,1/(AI48:AI48<>""),AI48:AI48))) | IF(OR(F48="",AK48=""),"",IF(COUNT(AI48:AJ48)=0,"",AK48-LOOKUP(2,1/(AI48:AJ48<>""),AI48:AJ48))) | IF(OR(F48="",AL48=""),"",IF(COUNT(AI48:AK48)=0,"",AL48-LOOKUP(2,1/(AI48:AK48<>""),AI48:AK48))) | IF(OR(F48="",AM48=""),"",IF(COUNT(AI48:AL48)=0,"",AM48-LOOKUP(2,1/(AI48:AL48<>""),AI48:AL48))) | IF(OR(F48="",AN48=""),"",IF(COUNT(AI48:AM48)=0,"",AN48-LOOKUP(2,1/(AI48:AM48<>""),AI48:AM48))) | IF(OR(F48="",AO48=""),"",IF(COUNT(AI48:AN48)=0,"",AO48-LOOKUP(2,1/(AI48:AN48<>""),AI48:AN48))) | IF(OR(F48="",AP48=""),"",IF(COUNT(AI48:AO48)=0,"",AP48-LOOKUP(2,1/(AI48:AO48<>""),AI48:AO48))) | IF(OR(F48="",AQ48=""),"",IF(COUNT(AI48:AP48)=0,"",AQ48-LOOKUP(2,1/(AI48:AP48<>""),AI48:AP48))) | IF(OR(F48="",AR48=""),"",IF(COUNT(AI48:AQ48)=0,"",AR48-LOOKUP(2,1/(AI48:AQ48<>""),AI48:AQ48))) | IF(OR(F48="",AS48=""),"",IF(COUNT(AI48:AR48)=0,"",AS48-LOOKUP(2,1/(AI48:AR48<>""),AI48:AR48))) | IF(OR(F48="",AT48=""),"",IF(COUNT(AI48:AS48)=0,"",AT48-LOOKUP(2,1/(AI48:AS48<>""),AI48:AS48))) | IF(OR(F48="",AU48=""),"",IF(COUNT(AI48:AT48)=0,"",AU48-LOOKUP(2,1/(AI48:AT48<>""),AI48:AT48))) | IF(OR(F48="",AV48=""),"",IF(COUNT(AI48:AU48)=0,"",AV48-LOOKUP(2,1/(AI48:AU48<>""),AI48:AU48))) | IF(J48="","All_Provinces",IFERROR(VLOOKUP(J48,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K48="","All_Districts",IFERROR(VLOOKUP(K48,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F49="","",ROW()-3) | AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | 7 of 7 | AF2-DIS-N-007 | Kushk Kohna Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Kushk e Kohna | Kushk Kohna | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Ibrahim |  | 10465.62 | IF(AQ49="","",AQ49) | 2026-12-15 | 4.4 | 2027-04-29 | IF(W49<>"",W49,IF(OR(T49="",V49=""),"",EDATE(T49,V49))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Mohammad Ibrahim | IF(F49="","",IF(COUNT(AI49:AV49)=0,IF(AA49="","Not started",AA49),SUBSTITUTE(LOOKUP(2,1/(AI49:AV49<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F49="",COUNT(AI49:AV49)=0),"",TODAY()-LOOKUP(2,1/(AI49:AV49<>""),AI49:AV49)) | IF(OR(F49="",COUNT(AI49:AV49)<2),"",LOOKUP(2,1/(AI49:AV49<>""),AI49:AV49)-MIN(AI49:AV49)) | IF(OR(AD49="",AC49="Not started",AC49=""),"",IFERROR(AD49-IF(VLOOKUP(AC49,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC49,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F49="","",IF(OR(AA49="Cancelled",AC49="Cancelled"),"Cancelled",IF(OR(AC49="Completed / Handover",Y49<>"",Z49>=100),"Completed — on track",IF(O49="Not awarded",IF(U49="",IF(X49="","No planned date",IF(TODAY()>X49,"Behind — past planned date",IF(X49-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U49,"Behind — award date passed",IF(U49-TODAY()<=30,"At risk — close to off track","On track"))),IF(X49="","No planned date",IF(AND(TODAY()>X49,OR(Z49="",Z49<100)),"Behind — past end date",IF(AND(T49<>"",X49<>"",Z49<>"",(Z49<100),((TODAY()-T49)/MAX(X49-T49,1)*100)-Z49>15),"Behind — progress lag",IF(AND(X49-TODAY()<=30,X49-TODAY()>=0,OR(Z49="",Z49<90)),"At risk — close to off track","On track")))))))) | IF(OR(F49="",AC49="Completed / Handover",AC49="Cancelled"),"",IF(O49="Not awarded",IF(U49<>"",U49-TODAY(),IF(X49="","",X49-TODAY())),IF(X49="","",X49-TODAY()))) | [14 empty] | IF(OR(F49="",AJ49=""),"",IF(COUNT(AI49:AI49)=0,"",AJ49-LOOKUP(2,1/(AI49:AI49<>""),AI49:AI49))) | IF(OR(F49="",AK49=""),"",IF(COUNT(AI49:AJ49)=0,"",AK49-LOOKUP(2,1/(AI49:AJ49<>""),AI49:AJ49))) | IF(OR(F49="",AL49=""),"",IF(COUNT(AI49:AK49)=0,"",AL49-LOOKUP(2,1/(AI49:AK49<>""),AI49:AK49))) | IF(OR(F49="",AM49=""),"",IF(COUNT(AI49:AL49)=0,"",AM49-LOOKUP(2,1/(AI49:AL49<>""),AI49:AL49))) | IF(OR(F49="",AN49=""),"",IF(COUNT(AI49:AM49)=0,"",AN49-LOOKUP(2,1/(AI49:AM49<>""),AI49:AM49))) | IF(OR(F49="",AO49=""),"",IF(COUNT(AI49:AN49)=0,"",AO49-LOOKUP(2,1/(AI49:AN49<>""),AI49:AN49))) | IF(OR(F49="",AP49=""),"",IF(COUNT(AI49:AO49)=0,"",AP49-LOOKUP(2,1/(AI49:AO49<>""),AI49:AO49))) | IF(OR(F49="",AQ49=""),"",IF(COUNT(AI49:AP49)=0,"",AQ49-LOOKUP(2,1/(AI49:AP49<>""),AI49:AP49))) | IF(OR(F49="",AR49=""),"",IF(COUNT(AI49:AQ49)=0,"",AR49-LOOKUP(2,1/(AI49:AQ49<>""),AI49:AQ49))) | IF(OR(F49="",AS49=""),"",IF(COUNT(AI49:AR49)=0,"",AS49-LOOKUP(2,1/(AI49:AR49<>""),AI49:AR49))) | IF(OR(F49="",AT49=""),"",IF(COUNT(AI49:AS49)=0,"",AT49-LOOKUP(2,1/(AI49:AS49<>""),AI49:AS49))) | IF(OR(F49="",AU49=""),"",IF(COUNT(AI49:AT49)=0,"",AU49-LOOKUP(2,1/(AI49:AT49<>""),AI49:AT49))) | IF(OR(F49="",AV49=""),"",IF(COUNT(AI49:AU49)=0,"",AV49-LOOKUP(2,1/(AI49:AU49<>""),AI49:AU49))) | IF(J49="","All_Provinces",IFERROR(VLOOKUP(J49,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K49="","All_Districts",IFERROR(VLOOKUP(K49,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F50="","",ROW()-3) | AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 1 of 7 | AF2-DIS-N-008 | Ahangaran Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Firozkoh | Ahangaran | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Haji Yaqoub |  | 5783.61 | IF(AQ50="","",AQ50) | 2026-12-05 | 5.8 | 2027-05-30 | IF(W50<>"",W50,IF(OR(T50="",V50=""),"",EDATE(T50,V50))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Haji Yaqoub | IF(F50="","",IF(COUNT(AI50:AV50)=0,IF(AA50="","Not started",AA50),SUBSTITUTE(LOOKUP(2,1/(AI50:AV50<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F50="",COUNT(AI50:AV50)=0),"",TODAY()-LOOKUP(2,1/(AI50:AV50<>""),AI50:AV50)) | IF(OR(F50="",COUNT(AI50:AV50)<2),"",LOOKUP(2,1/(AI50:AV50<>""),AI50:AV50)-MIN(AI50:AV50)) | IF(OR(AD50="",AC50="Not started",AC50=""),"",IFERROR(AD50-IF(VLOOKUP(AC50,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC50,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F50="","",IF(OR(AA50="Cancelled",AC50="Cancelled"),"Cancelled",IF(OR(AC50="Completed / Handover",Y50<>"",Z50>=100),"Completed — on track",IF(O50="Not awarded",IF(U50="",IF(X50="","No planned date",IF(TODAY()>X50,"Behind — past planned date",IF(X50-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U50,"Behind — award date passed",IF(U50-TODAY()<=30,"At risk — close to off track","On track"))),IF(X50="","No planned date",IF(AND(TODAY()>X50,OR(Z50="",Z50<100)),"Behind — past end date",IF(AND(T50<>"",X50<>"",Z50<>"",(Z50<100),((TODAY()-T50)/MAX(X50-T50,1)*100)-Z50>15),"Behind — progress lag",IF(AND(X50-TODAY()<=30,X50-TODAY()>=0,OR(Z50="",Z50<90)),"At risk — close to off track","On track")))))))) | IF(OR(F50="",AC50="Completed / Handover",AC50="Cancelled"),"",IF(O50="Not awarded",IF(U50<>"",U50-TODAY(),IF(X50="","",X50-TODAY())),IF(X50="","",X50-TODAY()))) | [14 empty] | IF(OR(F50="",AJ50=""),"",IF(COUNT(AI50:AI50)=0,"",AJ50-LOOKUP(2,1/(AI50:AI50<>""),AI50:AI50))) | IF(OR(F50="",AK50=""),"",IF(COUNT(AI50:AJ50)=0,"",AK50-LOOKUP(2,1/(AI50:AJ50<>""),AI50:AJ50))) | IF(OR(F50="",AL50=""),"",IF(COUNT(AI50:AK50)=0,"",AL50-LOOKUP(2,1/(AI50:AK50<>""),AI50:AK50))) | IF(OR(F50="",AM50=""),"",IF(COUNT(AI50:AL50)=0,"",AM50-LOOKUP(2,1/(AI50:AL50<>""),AI50:AL50))) | IF(OR(F50="",AN50=""),"",IF(COUNT(AI50:AM50)=0,"",AN50-LOOKUP(2,1/(AI50:AM50<>""),AI50:AM50))) | IF(OR(F50="",AO50=""),"",IF(COUNT(AI50:AN50)=0,"",AO50-LOOKUP(2,1/(AI50:AN50<>""),AI50:AN50))) | IF(OR(F50="",AP50=""),"",IF(COUNT(AI50:AO50)=0,"",AP50-LOOKUP(2,1/(AI50:AO50<>""),AI50:AO50))) | IF(OR(F50="",AQ50=""),"",IF(COUNT(AI50:AP50)=0,"",AQ50-LOOKUP(2,1/(AI50:AP50<>""),AI50:AP50))) | IF(OR(F50="",AR50=""),"",IF(COUNT(AI50:AQ50)=0,"",AR50-LOOKUP(2,1/(AI50:AQ50<>""),AI50:AQ50))) | IF(OR(F50="",AS50=""),"",IF(COUNT(AI50:AR50)=0,"",AS50-LOOKUP(2,1/(AI50:AR50<>""),AI50:AR50))) | IF(OR(F50="",AT50=""),"",IF(COUNT(AI50:AS50)=0,"",AT50-LOOKUP(2,1/(AI50:AS50<>""),AI50:AS50))) | IF(OR(F50="",AU50=""),"",IF(COUNT(AI50:AT50)=0,"",AU50-LOOKUP(2,1/(AI50:AT50<>""),AI50:AT50))) | IF(OR(F50="",AV50=""),"",IF(COUNT(AI50:AU50)=0,"",AV50-LOOKUP(2,1/(AI50:AU50<>""),AI50:AU50))) | IF(J50="","All_Provinces",IFERROR(VLOOKUP(J50,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K50="","All_Districts",IFERROR(VLOOKUP(K50,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F51="","",ROW()-3) | AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 2 of 7 | AF2-DIS-N-009 | Baghak Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Qala-e-Naw | Baghak | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Edi Mohammad |  | 8943.67 | IF(AQ51="","",AQ51) | 2026-12-05 | 5.8 | 2027-05-30 | IF(W51<>"",W51,IF(OR(T51="",V51=""),"",EDATE(T51,V51))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Edi Mohammad | IF(F51="","",IF(COUNT(AI51:AV51)=0,IF(AA51="","Not started",AA51),SUBSTITUTE(LOOKUP(2,1/(AI51:AV51<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F51="",COUNT(AI51:AV51)=0),"",TODAY()-LOOKUP(2,1/(AI51:AV51<>""),AI51:AV51)) | IF(OR(F51="",COUNT(AI51:AV51)<2),"",LOOKUP(2,1/(AI51:AV51<>""),AI51:AV51)-MIN(AI51:AV51)) | IF(OR(AD51="",AC51="Not started",AC51=""),"",IFERROR(AD51-IF(VLOOKUP(AC51,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC51,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F51="","",IF(OR(AA51="Cancelled",AC51="Cancelled"),"Cancelled",IF(OR(AC51="Completed / Handover",Y51<>"",Z51>=100),"Completed — on track",IF(O51="Not awarded",IF(U51="",IF(X51="","No planned date",IF(TODAY()>X51,"Behind — past planned date",IF(X51-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U51,"Behind — award date passed",IF(U51-TODAY()<=30,"At risk — close to off track","On track"))),IF(X51="","No planned date",IF(AND(TODAY()>X51,OR(Z51="",Z51<100)),"Behind — past end date",IF(AND(T51<>"",X51<>"",Z51<>"",(Z51<100),((TODAY()-T51)/MAX(X51-T51,1)*100)-Z51>15),"Behind — progress lag",IF(AND(X51-TODAY()<=30,X51-TODAY()>=0,OR(Z51="",Z51<90)),"At risk — close to off track","On track")))))))) | IF(OR(F51="",AC51="Completed / Handover",AC51="Cancelled"),"",IF(O51="Not awarded",IF(U51<>"",U51-TODAY(),IF(X51="","",X51-TODAY())),IF(X51="","",X51-TODAY()))) | [14 empty] | IF(OR(F51="",AJ51=""),"",IF(COUNT(AI51:AI51)=0,"",AJ51-LOOKUP(2,1/(AI51:AI51<>""),AI51:AI51))) | IF(OR(F51="",AK51=""),"",IF(COUNT(AI51:AJ51)=0,"",AK51-LOOKUP(2,1/(AI51:AJ51<>""),AI51:AJ51))) | IF(OR(F51="",AL51=""),"",IF(COUNT(AI51:AK51)=0,"",AL51-LOOKUP(2,1/(AI51:AK51<>""),AI51:AK51))) | IF(OR(F51="",AM51=""),"",IF(COUNT(AI51:AL51)=0,"",AM51-LOOKUP(2,1/(AI51:AL51<>""),AI51:AL51))) | IF(OR(F51="",AN51=""),"",IF(COUNT(AI51:AM51)=0,"",AN51-LOOKUP(2,1/(AI51:AM51<>""),AI51:AM51))) | IF(OR(F51="",AO51=""),"",IF(COUNT(AI51:AN51)=0,"",AO51-LOOKUP(2,1/(AI51:AN51<>""),AI51:AN51))) | IF(OR(F51="",AP51=""),"",IF(COUNT(AI51:AO51)=0,"",AP51-LOOKUP(2,1/(AI51:AO51<>""),AI51:AO51))) | IF(OR(F51="",AQ51=""),"",IF(COUNT(AI51:AP51)=0,"",AQ51-LOOKUP(2,1/(AI51:AP51<>""),AI51:AP51))) | IF(OR(F51="",AR51=""),"",IF(COUNT(AI51:AQ51)=0,"",AR51-LOOKUP(2,1/(AI51:AQ51<>""),AI51:AQ51))) | IF(OR(F51="",AS51=""),"",IF(COUNT(AI51:AR51)=0,"",AS51-LOOKUP(2,1/(AI51:AR51<>""),AI51:AR51))) | IF(OR(F51="",AT51=""),"",IF(COUNT(AI51:AS51)=0,"",AT51-LOOKUP(2,1/(AI51:AS51<>""),AI51:AS51))) | IF(OR(F51="",AU51=""),"",IF(COUNT(AI51:AT51)=0,"",AU51-LOOKUP(2,1/(AI51:AT51<>""),AI51:AT51))) | IF(OR(F51="",AV51=""),"",IF(COUNT(AI51:AU51)=0,"",AV51-LOOKUP(2,1/(AI51:AU51<>""),AI51:AU51))) | IF(J51="","All_Provinces",IFERROR(VLOOKUP(J51,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K51="","All_Districts",IFERROR(VLOOKUP(K51,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F52="","",ROW()-3) | AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 3 of 7 | AF2-DIS-N-010 | Hamaye Khan Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Dawlatyar | Hamaye khan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Haji Abdul Qaiyom |  | 6737.72 | IF(AQ52="","",AQ52) | 2026-12-05 | 5.8 | 2027-05-30 | IF(W52<>"",W52,IF(OR(T52="",V52=""),"",EDATE(T52,V52))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Haji Abdul Qaiyom | IF(F52="","",IF(COUNT(AI52:AV52)=0,IF(AA52="","Not started",AA52),SUBSTITUTE(LOOKUP(2,1/(AI52:AV52<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F52="",COUNT(AI52:AV52)=0),"",TODAY()-LOOKUP(2,1/(AI52:AV52<>""),AI52:AV52)) | IF(OR(F52="",COUNT(AI52:AV52)<2),"",LOOKUP(2,1/(AI52:AV52<>""),AI52:AV52)-MIN(AI52:AV52)) | IF(OR(AD52="",AC52="Not started",AC52=""),"",IFERROR(AD52-IF(VLOOKUP(AC52,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC52,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F52="","",IF(OR(AA52="Cancelled",AC52="Cancelled"),"Cancelled",IF(OR(AC52="Completed / Handover",Y52<>"",Z52>=100),"Completed — on track",IF(O52="Not awarded",IF(U52="",IF(X52="","No planned date",IF(TODAY()>X52,"Behind — past planned date",IF(X52-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U52,"Behind — award date passed",IF(U52-TODAY()<=30,"At risk — close to off track","On track"))),IF(X52="","No planned date",IF(AND(TODAY()>X52,OR(Z52="",Z52<100)),"Behind — past end date",IF(AND(T52<>"",X52<>"",Z52<>"",(Z52<100),((TODAY()-T52)/MAX(X52-T52,1)*100)-Z52>15),"Behind — progress lag",IF(AND(X52-TODAY()<=30,X52-TODAY()>=0,OR(Z52="",Z52<90)),"At risk — close to off track","On track")))))))) | IF(OR(F52="",AC52="Completed / Handover",AC52="Cancelled"),"",IF(O52="Not awarded",IF(U52<>"",U52-TODAY(),IF(X52="","",X52-TODAY())),IF(X52="","",X52-TODAY()))) | [14 empty] | IF(OR(F52="",AJ52=""),"",IF(COUNT(AI52:AI52)=0,"",AJ52-LOOKUP(2,1/(AI52:AI52<>""),AI52:AI52))) | IF(OR(F52="",AK52=""),"",IF(COUNT(AI52:AJ52)=0,"",AK52-LOOKUP(2,1/(AI52:AJ52<>""),AI52:AJ52))) | IF(OR(F52="",AL52=""),"",IF(COUNT(AI52:AK52)=0,"",AL52-LOOKUP(2,1/(AI52:AK52<>""),AI52:AK52))) | IF(OR(F52="",AM52=""),"",IF(COUNT(AI52:AL52)=0,"",AM52-LOOKUP(2,1/(AI52:AL52<>""),AI52:AL52))) | IF(OR(F52="",AN52=""),"",IF(COUNT(AI52:AM52)=0,"",AN52-LOOKUP(2,1/(AI52:AM52<>""),AI52:AM52))) | IF(OR(F52="",AO52=""),"",IF(COUNT(AI52:AN52)=0,"",AO52-LOOKUP(2,1/(AI52:AN52<>""),AI52:AN52))) | IF(OR(F52="",AP52=""),"",IF(COUNT(AI52:AO52)=0,"",AP52-LOOKUP(2,1/(AI52:AO52<>""),AI52:AO52))) | IF(OR(F52="",AQ52=""),"",IF(COUNT(AI52:AP52)=0,"",AQ52-LOOKUP(2,1/(AI52:AP52<>""),AI52:AP52))) | IF(OR(F52="",AR52=""),"",IF(COUNT(AI52:AQ52)=0,"",AR52-LOOKUP(2,1/(AI52:AQ52<>""),AI52:AQ52))) | IF(OR(F52="",AS52=""),"",IF(COUNT(AI52:AR52)=0,"",AS52-LOOKUP(2,1/(AI52:AR52<>""),AI52:AR52))) | IF(OR(F52="",AT52=""),"",IF(COUNT(AI52:AS52)=0,"",AT52-LOOKUP(2,1/(AI52:AS52<>""),AI52:AS52))) | IF(OR(F52="",AU52=""),"",IF(COUNT(AI52:AT52)=0,"",AU52-LOOKUP(2,1/(AI52:AT52<>""),AI52:AT52))) | IF(OR(F52="",AV52=""),"",IF(COUNT(AI52:AU52)=0,"",AV52-LOOKUP(2,1/(AI52:AU52<>""),AI52:AU52))) | IF(J52="","All_Provinces",IFERROR(VLOOKUP(J52,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K52="","All_Districts",IFERROR(VLOOKUP(K52,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F53="","",ROW()-3) | AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 4 of 7 | AF2-DIS-N-011 | Jakana Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Moqur | Jakana | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Sobhan |  | 7977.58 | IF(AQ53="","",AQ53) | 2026-12-05 | 5.8 | 2027-05-30 | IF(W53<>"",W53,IF(OR(T53="",V53=""),"",EDATE(T53,V53))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Sobhan | IF(F53="","",IF(COUNT(AI53:AV53)=0,IF(AA53="","Not started",AA53),SUBSTITUTE(LOOKUP(2,1/(AI53:AV53<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F53="",COUNT(AI53:AV53)=0),"",TODAY()-LOOKUP(2,1/(AI53:AV53<>""),AI53:AV53)) | IF(OR(F53="",COUNT(AI53:AV53)<2),"",LOOKUP(2,1/(AI53:AV53<>""),AI53:AV53)-MIN(AI53:AV53)) | IF(OR(AD53="",AC53="Not started",AC53=""),"",IFERROR(AD53-IF(VLOOKUP(AC53,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC53,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F53="","",IF(OR(AA53="Cancelled",AC53="Cancelled"),"Cancelled",IF(OR(AC53="Completed / Handover",Y53<>"",Z53>=100),"Completed — on track",IF(O53="Not awarded",IF(U53="",IF(X53="","No planned date",IF(TODAY()>X53,"Behind — past planned date",IF(X53-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U53,"Behind — award date passed",IF(U53-TODAY()<=30,"At risk — close to off track","On track"))),IF(X53="","No planned date",IF(AND(TODAY()>X53,OR(Z53="",Z53<100)),"Behind — past end date",IF(AND(T53<>"",X53<>"",Z53<>"",(Z53<100),((TODAY()-T53)/MAX(X53-T53,1)*100)-Z53>15),"Behind — progress lag",IF(AND(X53-TODAY()<=30,X53-TODAY()>=0,OR(Z53="",Z53<90)),"At risk — close to off track","On track")))))))) | IF(OR(F53="",AC53="Completed / Handover",AC53="Cancelled"),"",IF(O53="Not awarded",IF(U53<>"",U53-TODAY(),IF(X53="","",X53-TODAY())),IF(X53="","",X53-TODAY()))) | [14 empty] | IF(OR(F53="",AJ53=""),"",IF(COUNT(AI53:AI53)=0,"",AJ53-LOOKUP(2,1/(AI53:AI53<>""),AI53:AI53))) | IF(OR(F53="",AK53=""),"",IF(COUNT(AI53:AJ53)=0,"",AK53-LOOKUP(2,1/(AI53:AJ53<>""),AI53:AJ53))) | IF(OR(F53="",AL53=""),"",IF(COUNT(AI53:AK53)=0,"",AL53-LOOKUP(2,1/(AI53:AK53<>""),AI53:AK53))) | IF(OR(F53="",AM53=""),"",IF(COUNT(AI53:AL53)=0,"",AM53-LOOKUP(2,1/(AI53:AL53<>""),AI53:AL53))) | IF(OR(F53="",AN53=""),"",IF(COUNT(AI53:AM53)=0,"",AN53-LOOKUP(2,1/(AI53:AM53<>""),AI53:AM53))) | IF(OR(F53="",AO53=""),"",IF(COUNT(AI53:AN53)=0,"",AO53-LOOKUP(2,1/(AI53:AN53<>""),AI53:AN53))) | IF(OR(F53="",AP53=""),"",IF(COUNT(AI53:AO53)=0,"",AP53-LOOKUP(2,1/(AI53:AO53<>""),AI53:AO53))) | IF(OR(F53="",AQ53=""),"",IF(COUNT(AI53:AP53)=0,"",AQ53-LOOKUP(2,1/(AI53:AP53<>""),AI53:AP53))) | IF(OR(F53="",AR53=""),"",IF(COUNT(AI53:AQ53)=0,"",AR53-LOOKUP(2,1/(AI53:AQ53<>""),AI53:AQ53))) | IF(OR(F53="",AS53=""),"",IF(COUNT(AI53:AR53)=0,"",AS53-LOOKUP(2,1/(AI53:AR53<>""),AI53:AR53))) | IF(OR(F53="",AT53=""),"",IF(COUNT(AI53:AS53)=0,"",AT53-LOOKUP(2,1/(AI53:AS53<>""),AI53:AS53))) | IF(OR(F53="",AU53=""),"",IF(COUNT(AI53:AT53)=0,"",AU53-LOOKUP(2,1/(AI53:AT53<>""),AI53:AT53))) | IF(OR(F53="",AV53=""),"",IF(COUNT(AI53:AU53)=0,"",AV53-LOOKUP(2,1/(AI53:AU53<>""),AI53:AU53))) | IF(J53="","All_Provinces",IFERROR(VLOOKUP(J53,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K53="","All_Districts",IFERROR(VLOOKUP(K53,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F54="","",ROW()-3) | AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 5 of 7 | AF2-DIS-N-012 | Kharistan Drip Irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Moqur | Kharistan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Saifuddin |  | 9550.69 | IF(AQ54="","",AQ54) | 2026-12-05 | 5.8 | 2027-05-30 | IF(W54<>"",W54,IF(OR(T54="",V54=""),"",EDATE(T54,V54))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Saifuddin | IF(F54="","",IF(COUNT(AI54:AV54)=0,IF(AA54="","Not started",AA54),SUBSTITUTE(LOOKUP(2,1/(AI54:AV54<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F54="",COUNT(AI54:AV54)=0),"",TODAY()-LOOKUP(2,1/(AI54:AV54<>""),AI54:AV54)) | IF(OR(F54="",COUNT(AI54:AV54)<2),"",LOOKUP(2,1/(AI54:AV54<>""),AI54:AV54)-MIN(AI54:AV54)) | IF(OR(AD54="",AC54="Not started",AC54=""),"",IFERROR(AD54-IF(VLOOKUP(AC54,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC54,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F54="","",IF(OR(AA54="Cancelled",AC54="Cancelled"),"Cancelled",IF(OR(AC54="Completed / Handover",Y54<>"",Z54>=100),"Completed — on track",IF(O54="Not awarded",IF(U54="",IF(X54="","No planned date",IF(TODAY()>X54,"Behind — past planned date",IF(X54-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U54,"Behind — award date passed",IF(U54-TODAY()<=30,"At risk — close to off track","On track"))),IF(X54="","No planned date",IF(AND(TODAY()>X54,OR(Z54="",Z54<100)),"Behind — past end date",IF(AND(T54<>"",X54<>"",Z54<>"",(Z54<100),((TODAY()-T54)/MAX(X54-T54,1)*100)-Z54>15),"Behind — progress lag",IF(AND(X54-TODAY()<=30,X54-TODAY()>=0,OR(Z54="",Z54<90)),"At risk — close to off track","On track")))))))) | IF(OR(F54="",AC54="Completed / Handover",AC54="Cancelled"),"",IF(O54="Not awarded",IF(U54<>"",U54-TODAY(),IF(X54="","",X54-TODAY())),IF(X54="","",X54-TODAY()))) | [14 empty] | IF(OR(F54="",AJ54=""),"",IF(COUNT(AI54:AI54)=0,"",AJ54-LOOKUP(2,1/(AI54:AI54<>""),AI54:AI54))) | IF(OR(F54="",AK54=""),"",IF(COUNT(AI54:AJ54)=0,"",AK54-LOOKUP(2,1/(AI54:AJ54<>""),AI54:AJ54))) | IF(OR(F54="",AL54=""),"",IF(COUNT(AI54:AK54)=0,"",AL54-LOOKUP(2,1/(AI54:AK54<>""),AI54:AK54))) | IF(OR(F54="",AM54=""),"",IF(COUNT(AI54:AL54)=0,"",AM54-LOOKUP(2,1/(AI54:AL54<>""),AI54:AL54))) | IF(OR(F54="",AN54=""),"",IF(COUNT(AI54:AM54)=0,"",AN54-LOOKUP(2,1/(AI54:AM54<>""),AI54:AM54))) | IF(OR(F54="",AO54=""),"",IF(COUNT(AI54:AN54)=0,"",AO54-LOOKUP(2,1/(AI54:AN54<>""),AI54:AN54))) | IF(OR(F54="",AP54=""),"",IF(COUNT(AI54:AO54)=0,"",AP54-LOOKUP(2,1/(AI54:AO54<>""),AI54:AO54))) | IF(OR(F54="",AQ54=""),"",IF(COUNT(AI54:AP54)=0,"",AQ54-LOOKUP(2,1/(AI54:AP54<>""),AI54:AP54))) | IF(OR(F54="",AR54=""),"",IF(COUNT(AI54:AQ54)=0,"",AR54-LOOKUP(2,1/(AI54:AQ54<>""),AI54:AQ54))) | IF(OR(F54="",AS54=""),"",IF(COUNT(AI54:AR54)=0,"",AS54-LOOKUP(2,1/(AI54:AR54<>""),AI54:AR54))) | IF(OR(F54="",AT54=""),"",IF(COUNT(AI54:AS54)=0,"",AT54-LOOKUP(2,1/(AI54:AS54<>""),AI54:AS54))) | IF(OR(F54="",AU54=""),"",IF(COUNT(AI54:AT54)=0,"",AU54-LOOKUP(2,1/(AI54:AT54<>""),AI54:AT54))) | IF(OR(F54="",AV54=""),"",IF(COUNT(AI54:AU54)=0,"",AV54-LOOKUP(2,1/(AI54:AU54<>""),AI54:AU54))) | IF(J54="","All_Provinces",IFERROR(VLOOKUP(J54,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K54="","All_Districts",IFERROR(VLOOKUP(K54,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F55="","",ROW()-3) | AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 6 of 7 | AF2-DIS-N-013 | Shadeh Olia Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Zinda Jan | Shadeh Olia | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Abdul Ghafour |  | 6110.88 | IF(AQ55="","",AQ55) | 2026-12-05 | 5.8 | 2027-05-30 | IF(W55<>"",W55,IF(OR(T55="",V55=""),"",EDATE(T55,V55))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Abdul Ghafour | IF(F55="","",IF(COUNT(AI55:AV55)=0,IF(AA55="","Not started",AA55),SUBSTITUTE(LOOKUP(2,1/(AI55:AV55<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F55="",COUNT(AI55:AV55)=0),"",TODAY()-LOOKUP(2,1/(AI55:AV55<>""),AI55:AV55)) | IF(OR(F55="",COUNT(AI55:AV55)<2),"",LOOKUP(2,1/(AI55:AV55<>""),AI55:AV55)-MIN(AI55:AV55)) | IF(OR(AD55="",AC55="Not started",AC55=""),"",IFERROR(AD55-IF(VLOOKUP(AC55,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC55,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F55="","",IF(OR(AA55="Cancelled",AC55="Cancelled"),"Cancelled",IF(OR(AC55="Completed / Handover",Y55<>"",Z55>=100),"Completed — on track",IF(O55="Not awarded",IF(U55="",IF(X55="","No planned date",IF(TODAY()>X55,"Behind — past planned date",IF(X55-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U55,"Behind — award date passed",IF(U55-TODAY()<=30,"At risk — close to off track","On track"))),IF(X55="","No planned date",IF(AND(TODAY()>X55,OR(Z55="",Z55<100)),"Behind — past end date",IF(AND(T55<>"",X55<>"",Z55<>"",(Z55<100),((TODAY()-T55)/MAX(X55-T55,1)*100)-Z55>15),"Behind — progress lag",IF(AND(X55-TODAY()<=30,X55-TODAY()>=0,OR(Z55="",Z55<90)),"At risk — close to off track","On track")))))))) | IF(OR(F55="",AC55="Completed / Handover",AC55="Cancelled"),"",IF(O55="Not awarded",IF(U55<>"",U55-TODAY(),IF(X55="","",X55-TODAY())),IF(X55="","",X55-TODAY()))) | [14 empty] | IF(OR(F55="",AJ55=""),"",IF(COUNT(AI55:AI55)=0,"",AJ55-LOOKUP(2,1/(AI55:AI55<>""),AI55:AI55))) | IF(OR(F55="",AK55=""),"",IF(COUNT(AI55:AJ55)=0,"",AK55-LOOKUP(2,1/(AI55:AJ55<>""),AI55:AJ55))) | IF(OR(F55="",AL55=""),"",IF(COUNT(AI55:AK55)=0,"",AL55-LOOKUP(2,1/(AI55:AK55<>""),AI55:AK55))) | IF(OR(F55="",AM55=""),"",IF(COUNT(AI55:AL55)=0,"",AM55-LOOKUP(2,1/(AI55:AL55<>""),AI55:AL55))) | IF(OR(F55="",AN55=""),"",IF(COUNT(AI55:AM55)=0,"",AN55-LOOKUP(2,1/(AI55:AM55<>""),AI55:AM55))) | IF(OR(F55="",AO55=""),"",IF(COUNT(AI55:AN55)=0,"",AO55-LOOKUP(2,1/(AI55:AN55<>""),AI55:AN55))) | IF(OR(F55="",AP55=""),"",IF(COUNT(AI55:AO55)=0,"",AP55-LOOKUP(2,1/(AI55:AO55<>""),AI55:AO55))) | IF(OR(F55="",AQ55=""),"",IF(COUNT(AI55:AP55)=0,"",AQ55-LOOKUP(2,1/(AI55:AP55<>""),AI55:AP55))) | IF(OR(F55="",AR55=""),"",IF(COUNT(AI55:AQ55)=0,"",AR55-LOOKUP(2,1/(AI55:AQ55<>""),AI55:AQ55))) | IF(OR(F55="",AS55=""),"",IF(COUNT(AI55:AR55)=0,"",AS55-LOOKUP(2,1/(AI55:AR55<>""),AI55:AR55))) | IF(OR(F55="",AT55=""),"",IF(COUNT(AI55:AS55)=0,"",AT55-LOOKUP(2,1/(AI55:AS55<>""),AI55:AS55))) | IF(OR(F55="",AU55=""),"",IF(COUNT(AI55:AT55)=0,"",AU55-LOOKUP(2,1/(AI55:AT55<>""),AI55:AT55))) | IF(OR(F55="",AV55=""),"",IF(COUNT(AI55:AU55)=0,"",AV55-LOOKUP(2,1/(AI55:AU55<>""),AI55:AU55))) | IF(J55="","All_Provinces",IFERROR(VLOOKUP(J55,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K55="","All_Districts",IFERROR(VLOOKUP(K55,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F56="","",ROW()-3) | AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | 7 of 7 | AF2-DIS-N-014 | Shadeh Sofla Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Zinda Jan | Shadeh Sofla | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ahmad Zia |  | 6495.85 | IF(AQ56="","",AQ56) | 2026-12-05 | 5.8 | 2027-05-30 | IF(W56<>"",W56,IF(OR(T56="",V56=""),"",EDATE(T56,V56))) |  |  | Retendered (Re-ITB) | Work starting from March 2026. A total of 90 days for completion Slack period until end February 2026. ¦ Farmer: Ahmad Zia | IF(F56="","",IF(COUNT(AI56:AV56)=0,IF(AA56="","Not started",AA56),SUBSTITUTE(LOOKUP(2,1/(AI56:AV56<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F56="",COUNT(AI56:AV56)=0),"",TODAY()-LOOKUP(2,1/(AI56:AV56<>""),AI56:AV56)) | IF(OR(F56="",COUNT(AI56:AV56)<2),"",LOOKUP(2,1/(AI56:AV56<>""),AI56:AV56)-MIN(AI56:AV56)) | IF(OR(AD56="",AC56="Not started",AC56=""),"",IFERROR(AD56-IF(VLOOKUP(AC56,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC56,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F56="","",IF(OR(AA56="Cancelled",AC56="Cancelled"),"Cancelled",IF(OR(AC56="Completed / Handover",Y56<>"",Z56>=100),"Completed — on track",IF(O56="Not awarded",IF(U56="",IF(X56="","No planned date",IF(TODAY()>X56,"Behind — past planned date",IF(X56-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U56,"Behind — award date passed",IF(U56-TODAY()<=30,"At risk — close to off track","On track"))),IF(X56="","No planned date",IF(AND(TODAY()>X56,OR(Z56="",Z56<100)),"Behind — past end date",IF(AND(T56<>"",X56<>"",Z56<>"",(Z56<100),((TODAY()-T56)/MAX(X56-T56,1)*100)-Z56>15),"Behind — progress lag",IF(AND(X56-TODAY()<=30,X56-TODAY()>=0,OR(Z56="",Z56<90)),"At risk — close to off track","On track")))))))) | IF(OR(F56="",AC56="Completed / Handover",AC56="Cancelled"),"",IF(O56="Not awarded",IF(U56<>"",U56-TODAY(),IF(X56="","",X56-TODAY())),IF(X56="","",X56-TODAY()))) | [14 empty] | IF(OR(F56="",AJ56=""),"",IF(COUNT(AI56:AI56)=0,"",AJ56-LOOKUP(2,1/(AI56:AI56<>""),AI56:AI56))) | IF(OR(F56="",AK56=""),"",IF(COUNT(AI56:AJ56)=0,"",AK56-LOOKUP(2,1/(AI56:AJ56<>""),AI56:AJ56))) | IF(OR(F56="",AL56=""),"",IF(COUNT(AI56:AK56)=0,"",AL56-LOOKUP(2,1/(AI56:AK56<>""),AI56:AK56))) | IF(OR(F56="",AM56=""),"",IF(COUNT(AI56:AL56)=0,"",AM56-LOOKUP(2,1/(AI56:AL56<>""),AI56:AL56))) | IF(OR(F56="",AN56=""),"",IF(COUNT(AI56:AM56)=0,"",AN56-LOOKUP(2,1/(AI56:AM56<>""),AI56:AM56))) | IF(OR(F56="",AO56=""),"",IF(COUNT(AI56:AN56)=0,"",AO56-LOOKUP(2,1/(AI56:AN56<>""),AI56:AN56))) | IF(OR(F56="",AP56=""),"",IF(COUNT(AI56:AO56)=0,"",AP56-LOOKUP(2,1/(AI56:AO56<>""),AI56:AO56))) | IF(OR(F56="",AQ56=""),"",IF(COUNT(AI56:AP56)=0,"",AQ56-LOOKUP(2,1/(AI56:AP56<>""),AI56:AP56))) | IF(OR(F56="",AR56=""),"",IF(COUNT(AI56:AQ56)=0,"",AR56-LOOKUP(2,1/(AI56:AQ56<>""),AI56:AQ56))) | IF(OR(F56="",AS56=""),"",IF(COUNT(AI56:AR56)=0,"",AS56-LOOKUP(2,1/(AI56:AR56<>""),AI56:AR56))) | IF(OR(F56="",AT56=""),"",IF(COUNT(AI56:AS56)=0,"",AT56-LOOKUP(2,1/(AI56:AS56<>""),AI56:AS56))) | IF(OR(F56="",AU56=""),"",IF(COUNT(AI56:AT56)=0,"",AU56-LOOKUP(2,1/(AI56:AT56<>""),AI56:AT56))) | IF(OR(F56="",AV56=""),"",IF(COUNT(AI56:AU56)=0,"",AV56-LOOKUP(2,1/(AI56:AU56<>""),AI56:AU56))) | IF(J56="","All_Provinces",IFERROR(VLOOKUP(J56,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K56="","All_Districts",IFERROR(VLOOKUP(K56,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F57="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 1 of 12 | AF2-DIS-N-015 | 1. Abdul Qadir Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Laghman | Alishing | Darwesh Abad | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Abdul Qadeer |  | 13115.38 | IF(AQ57="","",AQ57) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W57<>"",W57,IF(OR(T57="",V57=""),"",EDATE(T57,V57))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Abdul Qadeer | IF(F57="","",IF(COUNT(AI57:AV57)=0,IF(AA57="","Not started",AA57),SUBSTITUTE(LOOKUP(2,1/(AI57:AV57<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F57="",COUNT(AI57:AV57)=0),"",TODAY()-LOOKUP(2,1/(AI57:AV57<>""),AI57:AV57)) | IF(OR(F57="",COUNT(AI57:AV57)<2),"",LOOKUP(2,1/(AI57:AV57<>""),AI57:AV57)-MIN(AI57:AV57)) | IF(OR(AD57="",AC57="Not started",AC57=""),"",IFERROR(AD57-IF(VLOOKUP(AC57,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC57,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F57="","",IF(OR(AA57="Cancelled",AC57="Cancelled"),"Cancelled",IF(OR(AC57="Completed / Handover",Y57<>"",Z57>=100),"Completed — on track",IF(O57="Not awarded",IF(U57="",IF(X57="","No planned date",IF(TODAY()>X57,"Behind — past planned date",IF(X57-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U57,"Behind — award date passed",IF(U57-TODAY()<=30,"At risk — close to off track","On track"))),IF(X57="","No planned date",IF(AND(TODAY()>X57,OR(Z57="",Z57<100)),"Behind — past end date",IF(AND(T57<>"",X57<>"",Z57<>"",(Z57<100),((TODAY()-T57)/MAX(X57-T57,1)*100)-Z57>15),"Behind — progress lag",IF(AND(X57-TODAY()<=30,X57-TODAY()>=0,OR(Z57="",Z57<90)),"At risk — close to off track","On track")))))))) | IF(OR(F57="",AC57="Completed / Handover",AC57="Cancelled"),"",IF(O57="Not awarded",IF(U57<>"",U57-TODAY(),IF(X57="","",X57-TODAY())),IF(X57="","",X57-TODAY()))) | [14 empty] | IF(OR(F57="",AJ57=""),"",IF(COUNT(AI57:AI57)=0,"",AJ57-LOOKUP(2,1/(AI57:AI57<>""),AI57:AI57))) | IF(OR(F57="",AK57=""),"",IF(COUNT(AI57:AJ57)=0,"",AK57-LOOKUP(2,1/(AI57:AJ57<>""),AI57:AJ57))) | IF(OR(F57="",AL57=""),"",IF(COUNT(AI57:AK57)=0,"",AL57-LOOKUP(2,1/(AI57:AK57<>""),AI57:AK57))) | IF(OR(F57="",AM57=""),"",IF(COUNT(AI57:AL57)=0,"",AM57-LOOKUP(2,1/(AI57:AL57<>""),AI57:AL57))) | IF(OR(F57="",AN57=""),"",IF(COUNT(AI57:AM57)=0,"",AN57-LOOKUP(2,1/(AI57:AM57<>""),AI57:AM57))) | IF(OR(F57="",AO57=""),"",IF(COUNT(AI57:AN57)=0,"",AO57-LOOKUP(2,1/(AI57:AN57<>""),AI57:AN57))) | IF(OR(F57="",AP57=""),"",IF(COUNT(AI57:AO57)=0,"",AP57-LOOKUP(2,1/(AI57:AO57<>""),AI57:AO57))) | IF(OR(F57="",AQ57=""),"",IF(COUNT(AI57:AP57)=0,"",AQ57-LOOKUP(2,1/(AI57:AP57<>""),AI57:AP57))) | IF(OR(F57="",AR57=""),"",IF(COUNT(AI57:AQ57)=0,"",AR57-LOOKUP(2,1/(AI57:AQ57<>""),AI57:AQ57))) | IF(OR(F57="",AS57=""),"",IF(COUNT(AI57:AR57)=0,"",AS57-LOOKUP(2,1/(AI57:AR57<>""),AI57:AR57))) | IF(OR(F57="",AT57=""),"",IF(COUNT(AI57:AS57)=0,"",AT57-LOOKUP(2,1/(AI57:AS57<>""),AI57:AS57))) | IF(OR(F57="",AU57=""),"",IF(COUNT(AI57:AT57)=0,"",AU57-LOOKUP(2,1/(AI57:AT57<>""),AI57:AT57))) | IF(OR(F57="",AV57=""),"",IF(COUNT(AI57:AU57)=0,"",AV57-LOOKUP(2,1/(AI57:AU57<>""),AI57:AU57))) | IF(J57="","All_Provinces",IFERROR(VLOOKUP(J57,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K57="","All_Districts",IFERROR(VLOOKUP(K57,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F58="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 2 of 12 | AF2-DIS-N-016 | 10.Habibullah Drip irrigation Site | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nuristan | Barg-e-Matal | Barg-e-Matal Sharqi | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Habibullah |  | 4194.9 | IF(AQ58="","",AQ58) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W58<>"",W58,IF(OR(T58="",V58=""),"",EDATE(T58,V58))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Habibullah | IF(F58="","",IF(COUNT(AI58:AV58)=0,IF(AA58="","Not started",AA58),SUBSTITUTE(LOOKUP(2,1/(AI58:AV58<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F58="",COUNT(AI58:AV58)=0),"",TODAY()-LOOKUP(2,1/(AI58:AV58<>""),AI58:AV58)) | IF(OR(F58="",COUNT(AI58:AV58)<2),"",LOOKUP(2,1/(AI58:AV58<>""),AI58:AV58)-MIN(AI58:AV58)) | IF(OR(AD58="",AC58="Not started",AC58=""),"",IFERROR(AD58-IF(VLOOKUP(AC58,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC58,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F58="","",IF(OR(AA58="Cancelled",AC58="Cancelled"),"Cancelled",IF(OR(AC58="Completed / Handover",Y58<>"",Z58>=100),"Completed — on track",IF(O58="Not awarded",IF(U58="",IF(X58="","No planned date",IF(TODAY()>X58,"Behind — past planned date",IF(X58-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U58,"Behind — award date passed",IF(U58-TODAY()<=30,"At risk — close to off track","On track"))),IF(X58="","No planned date",IF(AND(TODAY()>X58,OR(Z58="",Z58<100)),"Behind — past end date",IF(AND(T58<>"",X58<>"",Z58<>"",(Z58<100),((TODAY()-T58)/MAX(X58-T58,1)*100)-Z58>15),"Behind — progress lag",IF(AND(X58-TODAY()<=30,X58-TODAY()>=0,OR(Z58="",Z58<90)),"At risk — close to off track","On track")))))))) | IF(OR(F58="",AC58="Completed / Handover",AC58="Cancelled"),"",IF(O58="Not awarded",IF(U58<>"",U58-TODAY(),IF(X58="","",X58-TODAY())),IF(X58="","",X58-TODAY()))) | [14 empty] | IF(OR(F58="",AJ58=""),"",IF(COUNT(AI58:AI58)=0,"",AJ58-LOOKUP(2,1/(AI58:AI58<>""),AI58:AI58))) | IF(OR(F58="",AK58=""),"",IF(COUNT(AI58:AJ58)=0,"",AK58-LOOKUP(2,1/(AI58:AJ58<>""),AI58:AJ58))) | IF(OR(F58="",AL58=""),"",IF(COUNT(AI58:AK58)=0,"",AL58-LOOKUP(2,1/(AI58:AK58<>""),AI58:AK58))) | IF(OR(F58="",AM58=""),"",IF(COUNT(AI58:AL58)=0,"",AM58-LOOKUP(2,1/(AI58:AL58<>""),AI58:AL58))) | IF(OR(F58="",AN58=""),"",IF(COUNT(AI58:AM58)=0,"",AN58-LOOKUP(2,1/(AI58:AM58<>""),AI58:AM58))) | IF(OR(F58="",AO58=""),"",IF(COUNT(AI58:AN58)=0,"",AO58-LOOKUP(2,1/(AI58:AN58<>""),AI58:AN58))) | IF(OR(F58="",AP58=""),"",IF(COUNT(AI58:AO58)=0,"",AP58-LOOKUP(2,1/(AI58:AO58<>""),AI58:AO58))) | IF(OR(F58="",AQ58=""),"",IF(COUNT(AI58:AP58)=0,"",AQ58-LOOKUP(2,1/(AI58:AP58<>""),AI58:AP58))) | IF(OR(F58="",AR58=""),"",IF(COUNT(AI58:AQ58)=0,"",AR58-LOOKUP(2,1/(AI58:AQ58<>""),AI58:AQ58))) | IF(OR(F58="",AS58=""),"",IF(COUNT(AI58:AR58)=0,"",AS58-LOOKUP(2,1/(AI58:AR58<>""),AI58:AR58))) | IF(OR(F58="",AT58=""),"",IF(COUNT(AI58:AS58)=0,"",AT58-LOOKUP(2,1/(AI58:AS58<>""),AI58:AS58))) | IF(OR(F58="",AU58=""),"",IF(COUNT(AI58:AT58)=0,"",AU58-LOOKUP(2,1/(AI58:AT58<>""),AI58:AT58))) | IF(OR(F58="",AV58=""),"",IF(COUNT(AI58:AU58)=0,"",AV58-LOOKUP(2,1/(AI58:AU58<>""),AI58:AU58))) | IF(J58="","All_Provinces",IFERROR(VLOOKUP(J58,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K58="","All_Districts",IFERROR(VLOOKUP(K58,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F59="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 3 of 12 | AF2-DIS-N-017 | 11.Surkhrood Drip irrigation Site | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Sorkhrud | Fatih Abad | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ehsanullah |  | 4831.74 | IF(AQ59="","",AQ59) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W59<>"",W59,IF(OR(T59="",V59=""),"",EDATE(T59,V59))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Ehsanullah | IF(F59="","",IF(COUNT(AI59:AV59)=0,IF(AA59="","Not started",AA59),SUBSTITUTE(LOOKUP(2,1/(AI59:AV59<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F59="",COUNT(AI59:AV59)=0),"",TODAY()-LOOKUP(2,1/(AI59:AV59<>""),AI59:AV59)) | IF(OR(F59="",COUNT(AI59:AV59)<2),"",LOOKUP(2,1/(AI59:AV59<>""),AI59:AV59)-MIN(AI59:AV59)) | IF(OR(AD59="",AC59="Not started",AC59=""),"",IFERROR(AD59-IF(VLOOKUP(AC59,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC59,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F59="","",IF(OR(AA59="Cancelled",AC59="Cancelled"),"Cancelled",IF(OR(AC59="Completed / Handover",Y59<>"",Z59>=100),"Completed — on track",IF(O59="Not awarded",IF(U59="",IF(X59="","No planned date",IF(TODAY()>X59,"Behind — past planned date",IF(X59-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U59,"Behind — award date passed",IF(U59-TODAY()<=30,"At risk — close to off track","On track"))),IF(X59="","No planned date",IF(AND(TODAY()>X59,OR(Z59="",Z59<100)),"Behind — past end date",IF(AND(T59<>"",X59<>"",Z59<>"",(Z59<100),((TODAY()-T59)/MAX(X59-T59,1)*100)-Z59>15),"Behind — progress lag",IF(AND(X59-TODAY()<=30,X59-TODAY()>=0,OR(Z59="",Z59<90)),"At risk — close to off track","On track")))))))) | IF(OR(F59="",AC59="Completed / Handover",AC59="Cancelled"),"",IF(O59="Not awarded",IF(U59<>"",U59-TODAY(),IF(X59="","",X59-TODAY())),IF(X59="","",X59-TODAY()))) | [14 empty] | IF(OR(F59="",AJ59=""),"",IF(COUNT(AI59:AI59)=0,"",AJ59-LOOKUP(2,1/(AI59:AI59<>""),AI59:AI59))) | IF(OR(F59="",AK59=""),"",IF(COUNT(AI59:AJ59)=0,"",AK59-LOOKUP(2,1/(AI59:AJ59<>""),AI59:AJ59))) | IF(OR(F59="",AL59=""),"",IF(COUNT(AI59:AK59)=0,"",AL59-LOOKUP(2,1/(AI59:AK59<>""),AI59:AK59))) | IF(OR(F59="",AM59=""),"",IF(COUNT(AI59:AL59)=0,"",AM59-LOOKUP(2,1/(AI59:AL59<>""),AI59:AL59))) | IF(OR(F59="",AN59=""),"",IF(COUNT(AI59:AM59)=0,"",AN59-LOOKUP(2,1/(AI59:AM59<>""),AI59:AM59))) | IF(OR(F59="",AO59=""),"",IF(COUNT(AI59:AN59)=0,"",AO59-LOOKUP(2,1/(AI59:AN59<>""),AI59:AN59))) | IF(OR(F59="",AP59=""),"",IF(COUNT(AI59:AO59)=0,"",AP59-LOOKUP(2,1/(AI59:AO59<>""),AI59:AO59))) | IF(OR(F59="",AQ59=""),"",IF(COUNT(AI59:AP59)=0,"",AQ59-LOOKUP(2,1/(AI59:AP59<>""),AI59:AP59))) | IF(OR(F59="",AR59=""),"",IF(COUNT(AI59:AQ59)=0,"",AR59-LOOKUP(2,1/(AI59:AQ59<>""),AI59:AQ59))) | IF(OR(F59="",AS59=""),"",IF(COUNT(AI59:AR59)=0,"",AS59-LOOKUP(2,1/(AI59:AR59<>""),AI59:AR59))) | IF(OR(F59="",AT59=""),"",IF(COUNT(AI59:AS59)=0,"",AT59-LOOKUP(2,1/(AI59:AS59<>""),AI59:AS59))) | IF(OR(F59="",AU59=""),"",IF(COUNT(AI59:AT59)=0,"",AU59-LOOKUP(2,1/(AI59:AT59<>""),AI59:AT59))) | IF(OR(F59="",AV59=""),"",IF(COUNT(AI59:AU59)=0,"",AV59-LOOKUP(2,1/(AI59:AU59<>""),AI59:AU59))) | IF(J59="","All_Provinces",IFERROR(VLOOKUP(J59,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K59="","All_Districts",IFERROR(VLOOKUP(K59,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F60="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 4 of 12 | AF2-DIS-N-018 | 12.Khewa Drip irrigation Site | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Khewa | Sarjal | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ramin |  | 3562.46 | IF(AQ60="","",AQ60) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W60<>"",W60,IF(OR(T60="",V60=""),"",EDATE(T60,V60))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Ramin | IF(F60="","",IF(COUNT(AI60:AV60)=0,IF(AA60="","Not started",AA60),SUBSTITUTE(LOOKUP(2,1/(AI60:AV60<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F60="",COUNT(AI60:AV60)=0),"",TODAY()-LOOKUP(2,1/(AI60:AV60<>""),AI60:AV60)) | IF(OR(F60="",COUNT(AI60:AV60)<2),"",LOOKUP(2,1/(AI60:AV60<>""),AI60:AV60)-MIN(AI60:AV60)) | IF(OR(AD60="",AC60="Not started",AC60=""),"",IFERROR(AD60-IF(VLOOKUP(AC60,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC60,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F60="","",IF(OR(AA60="Cancelled",AC60="Cancelled"),"Cancelled",IF(OR(AC60="Completed / Handover",Y60<>"",Z60>=100),"Completed — on track",IF(O60="Not awarded",IF(U60="",IF(X60="","No planned date",IF(TODAY()>X60,"Behind — past planned date",IF(X60-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U60,"Behind — award date passed",IF(U60-TODAY()<=30,"At risk — close to off track","On track"))),IF(X60="","No planned date",IF(AND(TODAY()>X60,OR(Z60="",Z60<100)),"Behind — past end date",IF(AND(T60<>"",X60<>"",Z60<>"",(Z60<100),((TODAY()-T60)/MAX(X60-T60,1)*100)-Z60>15),"Behind — progress lag",IF(AND(X60-TODAY()<=30,X60-TODAY()>=0,OR(Z60="",Z60<90)),"At risk — close to off track","On track")))))))) | IF(OR(F60="",AC60="Completed / Handover",AC60="Cancelled"),"",IF(O60="Not awarded",IF(U60<>"",U60-TODAY(),IF(X60="","",X60-TODAY())),IF(X60="","",X60-TODAY()))) | [14 empty] | IF(OR(F60="",AJ60=""),"",IF(COUNT(AI60:AI60)=0,"",AJ60-LOOKUP(2,1/(AI60:AI60<>""),AI60:AI60))) | IF(OR(F60="",AK60=""),"",IF(COUNT(AI60:AJ60)=0,"",AK60-LOOKUP(2,1/(AI60:AJ60<>""),AI60:AJ60))) | IF(OR(F60="",AL60=""),"",IF(COUNT(AI60:AK60)=0,"",AL60-LOOKUP(2,1/(AI60:AK60<>""),AI60:AK60))) | IF(OR(F60="",AM60=""),"",IF(COUNT(AI60:AL60)=0,"",AM60-LOOKUP(2,1/(AI60:AL60<>""),AI60:AL60))) | IF(OR(F60="",AN60=""),"",IF(COUNT(AI60:AM60)=0,"",AN60-LOOKUP(2,1/(AI60:AM60<>""),AI60:AM60))) | IF(OR(F60="",AO60=""),"",IF(COUNT(AI60:AN60)=0,"",AO60-LOOKUP(2,1/(AI60:AN60<>""),AI60:AN60))) | IF(OR(F60="",AP60=""),"",IF(COUNT(AI60:AO60)=0,"",AP60-LOOKUP(2,1/(AI60:AO60<>""),AI60:AO60))) | IF(OR(F60="",AQ60=""),"",IF(COUNT(AI60:AP60)=0,"",AQ60-LOOKUP(2,1/(AI60:AP60<>""),AI60:AP60))) | IF(OR(F60="",AR60=""),"",IF(COUNT(AI60:AQ60)=0,"",AR60-LOOKUP(2,1/(AI60:AQ60<>""),AI60:AQ60))) | IF(OR(F60="",AS60=""),"",IF(COUNT(AI60:AR60)=0,"",AS60-LOOKUP(2,1/(AI60:AR60<>""),AI60:AR60))) | IF(OR(F60="",AT60=""),"",IF(COUNT(AI60:AS60)=0,"",AT60-LOOKUP(2,1/(AI60:AS60<>""),AI60:AS60))) | IF(OR(F60="",AU60=""),"",IF(COUNT(AI60:AT60)=0,"",AU60-LOOKUP(2,1/(AI60:AT60<>""),AI60:AT60))) | IF(OR(F60="",AV60=""),"",IF(COUNT(AI60:AU60)=0,"",AV60-LOOKUP(2,1/(AI60:AU60<>""),AI60:AU60))) | IF(J60="","All_Provinces",IFERROR(VLOOKUP(J60,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K60="","All_Districts",IFERROR(VLOOKUP(K60,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F61="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 5 of 12 | AF2-DIS-N-019 | 2. Abdul Raqib drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Pacheragam | Landi Khil | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Abdur Raqeeb |  |  | IF(AQ61="","",AQ61) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W61<>"",W61,IF(OR(T61="",V61=""),"",EDATE(T61,V61))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Abdur Raqeeb | IF(F61="","",IF(COUNT(AI61:AV61)=0,IF(AA61="","Not started",AA61),SUBSTITUTE(LOOKUP(2,1/(AI61:AV61<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F61="",COUNT(AI61:AV61)=0),"",TODAY()-LOOKUP(2,1/(AI61:AV61<>""),AI61:AV61)) | IF(OR(F61="",COUNT(AI61:AV61)<2),"",LOOKUP(2,1/(AI61:AV61<>""),AI61:AV61)-MIN(AI61:AV61)) | IF(OR(AD61="",AC61="Not started",AC61=""),"",IFERROR(AD61-IF(VLOOKUP(AC61,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC61,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F61="","",IF(OR(AA61="Cancelled",AC61="Cancelled"),"Cancelled",IF(OR(AC61="Completed / Handover",Y61<>"",Z61>=100),"Completed — on track",IF(O61="Not awarded",IF(U61="",IF(X61="","No planned date",IF(TODAY()>X61,"Behind — past planned date",IF(X61-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U61,"Behind — award date passed",IF(U61-TODAY()<=30,"At risk — close to off track","On track"))),IF(X61="","No planned date",IF(AND(TODAY()>X61,OR(Z61="",Z61<100)),"Behind — past end date",IF(AND(T61<>"",X61<>"",Z61<>"",(Z61<100),((TODAY()-T61)/MAX(X61-T61,1)*100)-Z61>15),"Behind — progress lag",IF(AND(X61-TODAY()<=30,X61-TODAY()>=0,OR(Z61="",Z61<90)),"At risk — close to off track","On track")))))))) | IF(OR(F61="",AC61="Completed / Handover",AC61="Cancelled"),"",IF(O61="Not awarded",IF(U61<>"",U61-TODAY(),IF(X61="","",X61-TODAY())),IF(X61="","",X61-TODAY()))) | [14 empty] | IF(OR(F61="",AJ61=""),"",IF(COUNT(AI61:AI61)=0,"",AJ61-LOOKUP(2,1/(AI61:AI61<>""),AI61:AI61))) | IF(OR(F61="",AK61=""),"",IF(COUNT(AI61:AJ61)=0,"",AK61-LOOKUP(2,1/(AI61:AJ61<>""),AI61:AJ61))) | IF(OR(F61="",AL61=""),"",IF(COUNT(AI61:AK61)=0,"",AL61-LOOKUP(2,1/(AI61:AK61<>""),AI61:AK61))) | IF(OR(F61="",AM61=""),"",IF(COUNT(AI61:AL61)=0,"",AM61-LOOKUP(2,1/(AI61:AL61<>""),AI61:AL61))) | IF(OR(F61="",AN61=""),"",IF(COUNT(AI61:AM61)=0,"",AN61-LOOKUP(2,1/(AI61:AM61<>""),AI61:AM61))) | IF(OR(F61="",AO61=""),"",IF(COUNT(AI61:AN61)=0,"",AO61-LOOKUP(2,1/(AI61:AN61<>""),AI61:AN61))) | IF(OR(F61="",AP61=""),"",IF(COUNT(AI61:AO61)=0,"",AP61-LOOKUP(2,1/(AI61:AO61<>""),AI61:AO61))) | IF(OR(F61="",AQ61=""),"",IF(COUNT(AI61:AP61)=0,"",AQ61-LOOKUP(2,1/(AI61:AP61<>""),AI61:AP61))) | IF(OR(F61="",AR61=""),"",IF(COUNT(AI61:AQ61)=0,"",AR61-LOOKUP(2,1/(AI61:AQ61<>""),AI61:AQ61))) | IF(OR(F61="",AS61=""),"",IF(COUNT(AI61:AR61)=0,"",AS61-LOOKUP(2,1/(AI61:AR61<>""),AI61:AR61))) | IF(OR(F61="",AT61=""),"",IF(COUNT(AI61:AS61)=0,"",AT61-LOOKUP(2,1/(AI61:AS61<>""),AI61:AS61))) | IF(OR(F61="",AU61=""),"",IF(COUNT(AI61:AT61)=0,"",AU61-LOOKUP(2,1/(AI61:AT61<>""),AI61:AT61))) | IF(OR(F61="",AV61=""),"",IF(COUNT(AI61:AU61)=0,"",AV61-LOOKUP(2,1/(AI61:AU61<>""),AI61:AU61))) | IF(J61="","All_Provinces",IFERROR(VLOOKUP(J61,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K61="","All_Districts",IFERROR(VLOOKUP(K61,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F62="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 6 of 12 | AF2-DIS-N-020 | 3. Nazar Khan Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Batikot | Heabat Khil | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Nazar Khan |  |  | IF(AQ62="","",AQ62) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W62<>"",W62,IF(OR(T62="",V62=""),"",EDATE(T62,V62))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Nazar Khan | IF(F62="","",IF(COUNT(AI62:AV62)=0,IF(AA62="","Not started",AA62),SUBSTITUTE(LOOKUP(2,1/(AI62:AV62<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F62="",COUNT(AI62:AV62)=0),"",TODAY()-LOOKUP(2,1/(AI62:AV62<>""),AI62:AV62)) | IF(OR(F62="",COUNT(AI62:AV62)<2),"",LOOKUP(2,1/(AI62:AV62<>""),AI62:AV62)-MIN(AI62:AV62)) | IF(OR(AD62="",AC62="Not started",AC62=""),"",IFERROR(AD62-IF(VLOOKUP(AC62,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC62,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F62="","",IF(OR(AA62="Cancelled",AC62="Cancelled"),"Cancelled",IF(OR(AC62="Completed / Handover",Y62<>"",Z62>=100),"Completed — on track",IF(O62="Not awarded",IF(U62="",IF(X62="","No planned date",IF(TODAY()>X62,"Behind — past planned date",IF(X62-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U62,"Behind — award date passed",IF(U62-TODAY()<=30,"At risk — close to off track","On track"))),IF(X62="","No planned date",IF(AND(TODAY()>X62,OR(Z62="",Z62<100)),"Behind — past end date",IF(AND(T62<>"",X62<>"",Z62<>"",(Z62<100),((TODAY()-T62)/MAX(X62-T62,1)*100)-Z62>15),"Behind — progress lag",IF(AND(X62-TODAY()<=30,X62-TODAY()>=0,OR(Z62="",Z62<90)),"At risk — close to off track","On track")))))))) | IF(OR(F62="",AC62="Completed / Handover",AC62="Cancelled"),"",IF(O62="Not awarded",IF(U62<>"",U62-TODAY(),IF(X62="","",X62-TODAY())),IF(X62="","",X62-TODAY()))) | [14 empty] | IF(OR(F62="",AJ62=""),"",IF(COUNT(AI62:AI62)=0,"",AJ62-LOOKUP(2,1/(AI62:AI62<>""),AI62:AI62))) | IF(OR(F62="",AK62=""),"",IF(COUNT(AI62:AJ62)=0,"",AK62-LOOKUP(2,1/(AI62:AJ62<>""),AI62:AJ62))) | IF(OR(F62="",AL62=""),"",IF(COUNT(AI62:AK62)=0,"",AL62-LOOKUP(2,1/(AI62:AK62<>""),AI62:AK62))) | IF(OR(F62="",AM62=""),"",IF(COUNT(AI62:AL62)=0,"",AM62-LOOKUP(2,1/(AI62:AL62<>""),AI62:AL62))) | IF(OR(F62="",AN62=""),"",IF(COUNT(AI62:AM62)=0,"",AN62-LOOKUP(2,1/(AI62:AM62<>""),AI62:AM62))) | IF(OR(F62="",AO62=""),"",IF(COUNT(AI62:AN62)=0,"",AO62-LOOKUP(2,1/(AI62:AN62<>""),AI62:AN62))) | IF(OR(F62="",AP62=""),"",IF(COUNT(AI62:AO62)=0,"",AP62-LOOKUP(2,1/(AI62:AO62<>""),AI62:AO62))) | IF(OR(F62="",AQ62=""),"",IF(COUNT(AI62:AP62)=0,"",AQ62-LOOKUP(2,1/(AI62:AP62<>""),AI62:AP62))) | IF(OR(F62="",AR62=""),"",IF(COUNT(AI62:AQ62)=0,"",AR62-LOOKUP(2,1/(AI62:AQ62<>""),AI62:AQ62))) | IF(OR(F62="",AS62=""),"",IF(COUNT(AI62:AR62)=0,"",AS62-LOOKUP(2,1/(AI62:AR62<>""),AI62:AR62))) | IF(OR(F62="",AT62=""),"",IF(COUNT(AI62:AS62)=0,"",AT62-LOOKUP(2,1/(AI62:AS62<>""),AI62:AS62))) | IF(OR(F62="",AU62=""),"",IF(COUNT(AI62:AT62)=0,"",AU62-LOOKUP(2,1/(AI62:AT62<>""),AI62:AT62))) | IF(OR(F62="",AV62=""),"",IF(COUNT(AI62:AU62)=0,"",AV62-LOOKUP(2,1/(AI62:AU62<>""),AI62:AU62))) | IF(J62="","All_Provinces",IFERROR(VLOOKUP(J62,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K62="","All_Districts",IFERROR(VLOOKUP(K62,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F63="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 7 of 12 | AF2-DIS-N-021 | 4.Khas Kunar Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Khas Kunar | Chanchan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | M. Nabi |  | 6935.5 | IF(AQ63="","",AQ63) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W63<>"",W63,IF(OR(T63="",V63=""),"",EDATE(T63,V63))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: M. Nabi | IF(F63="","",IF(COUNT(AI63:AV63)=0,IF(AA63="","Not started",AA63),SUBSTITUTE(LOOKUP(2,1/(AI63:AV63<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F63="",COUNT(AI63:AV63)=0),"",TODAY()-LOOKUP(2,1/(AI63:AV63<>""),AI63:AV63)) | IF(OR(F63="",COUNT(AI63:AV63)<2),"",LOOKUP(2,1/(AI63:AV63<>""),AI63:AV63)-MIN(AI63:AV63)) | IF(OR(AD63="",AC63="Not started",AC63=""),"",IFERROR(AD63-IF(VLOOKUP(AC63,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC63,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F63="","",IF(OR(AA63="Cancelled",AC63="Cancelled"),"Cancelled",IF(OR(AC63="Completed / Handover",Y63<>"",Z63>=100),"Completed — on track",IF(O63="Not awarded",IF(U63="",IF(X63="","No planned date",IF(TODAY()>X63,"Behind — past planned date",IF(X63-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U63,"Behind — award date passed",IF(U63-TODAY()<=30,"At risk — close to off track","On track"))),IF(X63="","No planned date",IF(AND(TODAY()>X63,OR(Z63="",Z63<100)),"Behind — past end date",IF(AND(T63<>"",X63<>"",Z63<>"",(Z63<100),((TODAY()-T63)/MAX(X63-T63,1)*100)-Z63>15),"Behind — progress lag",IF(AND(X63-TODAY()<=30,X63-TODAY()>=0,OR(Z63="",Z63<90)),"At risk — close to off track","On track")))))))) | IF(OR(F63="",AC63="Completed / Handover",AC63="Cancelled"),"",IF(O63="Not awarded",IF(U63<>"",U63-TODAY(),IF(X63="","",X63-TODAY())),IF(X63="","",X63-TODAY()))) | [14 empty] | IF(OR(F63="",AJ63=""),"",IF(COUNT(AI63:AI63)=0,"",AJ63-LOOKUP(2,1/(AI63:AI63<>""),AI63:AI63))) | IF(OR(F63="",AK63=""),"",IF(COUNT(AI63:AJ63)=0,"",AK63-LOOKUP(2,1/(AI63:AJ63<>""),AI63:AJ63))) | IF(OR(F63="",AL63=""),"",IF(COUNT(AI63:AK63)=0,"",AL63-LOOKUP(2,1/(AI63:AK63<>""),AI63:AK63))) | IF(OR(F63="",AM63=""),"",IF(COUNT(AI63:AL63)=0,"",AM63-LOOKUP(2,1/(AI63:AL63<>""),AI63:AL63))) | IF(OR(F63="",AN63=""),"",IF(COUNT(AI63:AM63)=0,"",AN63-LOOKUP(2,1/(AI63:AM63<>""),AI63:AM63))) | IF(OR(F63="",AO63=""),"",IF(COUNT(AI63:AN63)=0,"",AO63-LOOKUP(2,1/(AI63:AN63<>""),AI63:AN63))) | IF(OR(F63="",AP63=""),"",IF(COUNT(AI63:AO63)=0,"",AP63-LOOKUP(2,1/(AI63:AO63<>""),AI63:AO63))) | IF(OR(F63="",AQ63=""),"",IF(COUNT(AI63:AP63)=0,"",AQ63-LOOKUP(2,1/(AI63:AP63<>""),AI63:AP63))) | IF(OR(F63="",AR63=""),"",IF(COUNT(AI63:AQ63)=0,"",AR63-LOOKUP(2,1/(AI63:AQ63<>""),AI63:AQ63))) | IF(OR(F63="",AS63=""),"",IF(COUNT(AI63:AR63)=0,"",AS63-LOOKUP(2,1/(AI63:AR63<>""),AI63:AR63))) | IF(OR(F63="",AT63=""),"",IF(COUNT(AI63:AS63)=0,"",AT63-LOOKUP(2,1/(AI63:AS63<>""),AI63:AS63))) | IF(OR(F63="",AU63=""),"",IF(COUNT(AI63:AT63)=0,"",AU63-LOOKUP(2,1/(AI63:AT63<>""),AI63:AT63))) | IF(OR(F63="",AV63=""),"",IF(COUNT(AI63:AU63)=0,"",AV63-LOOKUP(2,1/(AI63:AU63<>""),AI63:AU63))) | IF(J63="","All_Provinces",IFERROR(VLOOKUP(J63,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K63="","All_Districts",IFERROR(VLOOKUP(K63,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F64="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 8 of 12 | AF2-DIS-N-022 | 5.Asmar Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Asmar | Baylaye | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Malik Rostam |  | 4921.9 | IF(AQ64="","",AQ64) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W64<>"",W64,IF(OR(T64="",V64=""),"",EDATE(T64,V64))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Malik Rostam | IF(F64="","",IF(COUNT(AI64:AV64)=0,IF(AA64="","Not started",AA64),SUBSTITUTE(LOOKUP(2,1/(AI64:AV64<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F64="",COUNT(AI64:AV64)=0),"",TODAY()-LOOKUP(2,1/(AI64:AV64<>""),AI64:AV64)) | IF(OR(F64="",COUNT(AI64:AV64)<2),"",LOOKUP(2,1/(AI64:AV64<>""),AI64:AV64)-MIN(AI64:AV64)) | IF(OR(AD64="",AC64="Not started",AC64=""),"",IFERROR(AD64-IF(VLOOKUP(AC64,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC64,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F64="","",IF(OR(AA64="Cancelled",AC64="Cancelled"),"Cancelled",IF(OR(AC64="Completed / Handover",Y64<>"",Z64>=100),"Completed — on track",IF(O64="Not awarded",IF(U64="",IF(X64="","No planned date",IF(TODAY()>X64,"Behind — past planned date",IF(X64-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U64,"Behind — award date passed",IF(U64-TODAY()<=30,"At risk — close to off track","On track"))),IF(X64="","No planned date",IF(AND(TODAY()>X64,OR(Z64="",Z64<100)),"Behind — past end date",IF(AND(T64<>"",X64<>"",Z64<>"",(Z64<100),((TODAY()-T64)/MAX(X64-T64,1)*100)-Z64>15),"Behind — progress lag",IF(AND(X64-TODAY()<=30,X64-TODAY()>=0,OR(Z64="",Z64<90)),"At risk — close to off track","On track")))))))) | IF(OR(F64="",AC64="Completed / Handover",AC64="Cancelled"),"",IF(O64="Not awarded",IF(U64<>"",U64-TODAY(),IF(X64="","",X64-TODAY())),IF(X64="","",X64-TODAY()))) | [14 empty] | IF(OR(F64="",AJ64=""),"",IF(COUNT(AI64:AI64)=0,"",AJ64-LOOKUP(2,1/(AI64:AI64<>""),AI64:AI64))) | IF(OR(F64="",AK64=""),"",IF(COUNT(AI64:AJ64)=0,"",AK64-LOOKUP(2,1/(AI64:AJ64<>""),AI64:AJ64))) | IF(OR(F64="",AL64=""),"",IF(COUNT(AI64:AK64)=0,"",AL64-LOOKUP(2,1/(AI64:AK64<>""),AI64:AK64))) | IF(OR(F64="",AM64=""),"",IF(COUNT(AI64:AL64)=0,"",AM64-LOOKUP(2,1/(AI64:AL64<>""),AI64:AL64))) | IF(OR(F64="",AN64=""),"",IF(COUNT(AI64:AM64)=0,"",AN64-LOOKUP(2,1/(AI64:AM64<>""),AI64:AM64))) | IF(OR(F64="",AO64=""),"",IF(COUNT(AI64:AN64)=0,"",AO64-LOOKUP(2,1/(AI64:AN64<>""),AI64:AN64))) | IF(OR(F64="",AP64=""),"",IF(COUNT(AI64:AO64)=0,"",AP64-LOOKUP(2,1/(AI64:AO64<>""),AI64:AO64))) | IF(OR(F64="",AQ64=""),"",IF(COUNT(AI64:AP64)=0,"",AQ64-LOOKUP(2,1/(AI64:AP64<>""),AI64:AP64))) | IF(OR(F64="",AR64=""),"",IF(COUNT(AI64:AQ64)=0,"",AR64-LOOKUP(2,1/(AI64:AQ64<>""),AI64:AQ64))) | IF(OR(F64="",AS64=""),"",IF(COUNT(AI64:AR64)=0,"",AS64-LOOKUP(2,1/(AI64:AR64<>""),AI64:AR64))) | IF(OR(F64="",AT64=""),"",IF(COUNT(AI64:AS64)=0,"",AT64-LOOKUP(2,1/(AI64:AS64<>""),AI64:AS64))) | IF(OR(F64="",AU64=""),"",IF(COUNT(AI64:AT64)=0,"",AU64-LOOKUP(2,1/(AI64:AT64<>""),AI64:AT64))) | IF(OR(F64="",AV64=""),"",IF(COUNT(AI64:AU64)=0,"",AV64-LOOKUP(2,1/(AI64:AU64<>""),AI64:AU64))) | IF(J64="","All_Provinces",IFERROR(VLOOKUP(J64,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K64="","All_Districts",IFERROR(VLOOKUP(K64,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F65="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 9 of 12 | AF2-DIS-N-023 | 6.Manogai Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Manogai | Dabarzai | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | M. Afzal |  | 5530.7 | IF(AQ65="","",AQ65) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W65<>"",W65,IF(OR(T65="",V65=""),"",EDATE(T65,V65))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: M. Afzal | IF(F65="","",IF(COUNT(AI65:AV65)=0,IF(AA65="","Not started",AA65),SUBSTITUTE(LOOKUP(2,1/(AI65:AV65<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F65="",COUNT(AI65:AV65)=0),"",TODAY()-LOOKUP(2,1/(AI65:AV65<>""),AI65:AV65)) | IF(OR(F65="",COUNT(AI65:AV65)<2),"",LOOKUP(2,1/(AI65:AV65<>""),AI65:AV65)-MIN(AI65:AV65)) | IF(OR(AD65="",AC65="Not started",AC65=""),"",IFERROR(AD65-IF(VLOOKUP(AC65,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC65,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F65="","",IF(OR(AA65="Cancelled",AC65="Cancelled"),"Cancelled",IF(OR(AC65="Completed / Handover",Y65<>"",Z65>=100),"Completed — on track",IF(O65="Not awarded",IF(U65="",IF(X65="","No planned date",IF(TODAY()>X65,"Behind — past planned date",IF(X65-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U65,"Behind — award date passed",IF(U65-TODAY()<=30,"At risk — close to off track","On track"))),IF(X65="","No planned date",IF(AND(TODAY()>X65,OR(Z65="",Z65<100)),"Behind — past end date",IF(AND(T65<>"",X65<>"",Z65<>"",(Z65<100),((TODAY()-T65)/MAX(X65-T65,1)*100)-Z65>15),"Behind — progress lag",IF(AND(X65-TODAY()<=30,X65-TODAY()>=0,OR(Z65="",Z65<90)),"At risk — close to off track","On track")))))))) | IF(OR(F65="",AC65="Completed / Handover",AC65="Cancelled"),"",IF(O65="Not awarded",IF(U65<>"",U65-TODAY(),IF(X65="","",X65-TODAY())),IF(X65="","",X65-TODAY()))) | [14 empty] | IF(OR(F65="",AJ65=""),"",IF(COUNT(AI65:AI65)=0,"",AJ65-LOOKUP(2,1/(AI65:AI65<>""),AI65:AI65))) | IF(OR(F65="",AK65=""),"",IF(COUNT(AI65:AJ65)=0,"",AK65-LOOKUP(2,1/(AI65:AJ65<>""),AI65:AJ65))) | IF(OR(F65="",AL65=""),"",IF(COUNT(AI65:AK65)=0,"",AL65-LOOKUP(2,1/(AI65:AK65<>""),AI65:AK65))) | IF(OR(F65="",AM65=""),"",IF(COUNT(AI65:AL65)=0,"",AM65-LOOKUP(2,1/(AI65:AL65<>""),AI65:AL65))) | IF(OR(F65="",AN65=""),"",IF(COUNT(AI65:AM65)=0,"",AN65-LOOKUP(2,1/(AI65:AM65<>""),AI65:AM65))) | IF(OR(F65="",AO65=""),"",IF(COUNT(AI65:AN65)=0,"",AO65-LOOKUP(2,1/(AI65:AN65<>""),AI65:AN65))) | IF(OR(F65="",AP65=""),"",IF(COUNT(AI65:AO65)=0,"",AP65-LOOKUP(2,1/(AI65:AO65<>""),AI65:AO65))) | IF(OR(F65="",AQ65=""),"",IF(COUNT(AI65:AP65)=0,"",AQ65-LOOKUP(2,1/(AI65:AP65<>""),AI65:AP65))) | IF(OR(F65="",AR65=""),"",IF(COUNT(AI65:AQ65)=0,"",AR65-LOOKUP(2,1/(AI65:AQ65<>""),AI65:AQ65))) | IF(OR(F65="",AS65=""),"",IF(COUNT(AI65:AR65)=0,"",AS65-LOOKUP(2,1/(AI65:AR65<>""),AI65:AR65))) | IF(OR(F65="",AT65=""),"",IF(COUNT(AI65:AS65)=0,"",AT65-LOOKUP(2,1/(AI65:AS65<>""),AI65:AS65))) | IF(OR(F65="",AU65=""),"",IF(COUNT(AI65:AT65)=0,"",AU65-LOOKUP(2,1/(AI65:AT65<>""),AI65:AT65))) | IF(OR(F65="",AV65=""),"",IF(COUNT(AI65:AU65)=0,"",AV65-LOOKUP(2,1/(AI65:AU65<>""),AI65:AU65))) | IF(J65="","All_Provinces",IFERROR(VLOOKUP(J65,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K65="","All_Districts",IFERROR(VLOOKUP(K65,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F66="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 10 of 12 | AF2-DIS-N-024 | 7.Kunar University Drip irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Asadabad | Kunar University | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Kunar University |  | 4255.5 | IF(AQ66="","",AQ66) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W66<>"",W66,IF(OR(T66="",V66=""),"",EDATE(T66,V66))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Kunar University | IF(F66="","",IF(COUNT(AI66:AV66)=0,IF(AA66="","Not started",AA66),SUBSTITUTE(LOOKUP(2,1/(AI66:AV66<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F66="",COUNT(AI66:AV66)=0),"",TODAY()-LOOKUP(2,1/(AI66:AV66<>""),AI66:AV66)) | IF(OR(F66="",COUNT(AI66:AV66)<2),"",LOOKUP(2,1/(AI66:AV66<>""),AI66:AV66)-MIN(AI66:AV66)) | IF(OR(AD66="",AC66="Not started",AC66=""),"",IFERROR(AD66-IF(VLOOKUP(AC66,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC66,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F66="","",IF(OR(AA66="Cancelled",AC66="Cancelled"),"Cancelled",IF(OR(AC66="Completed / Handover",Y66<>"",Z66>=100),"Completed — on track",IF(O66="Not awarded",IF(U66="",IF(X66="","No planned date",IF(TODAY()>X66,"Behind — past planned date",IF(X66-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U66,"Behind — award date passed",IF(U66-TODAY()<=30,"At risk — close to off track","On track"))),IF(X66="","No planned date",IF(AND(TODAY()>X66,OR(Z66="",Z66<100)),"Behind — past end date",IF(AND(T66<>"",X66<>"",Z66<>"",(Z66<100),((TODAY()-T66)/MAX(X66-T66,1)*100)-Z66>15),"Behind — progress lag",IF(AND(X66-TODAY()<=30,X66-TODAY()>=0,OR(Z66="",Z66<90)),"At risk — close to off track","On track")))))))) | IF(OR(F66="",AC66="Completed / Handover",AC66="Cancelled"),"",IF(O66="Not awarded",IF(U66<>"",U66-TODAY(),IF(X66="","",X66-TODAY())),IF(X66="","",X66-TODAY()))) | [14 empty] | IF(OR(F66="",AJ66=""),"",IF(COUNT(AI66:AI66)=0,"",AJ66-LOOKUP(2,1/(AI66:AI66<>""),AI66:AI66))) | IF(OR(F66="",AK66=""),"",IF(COUNT(AI66:AJ66)=0,"",AK66-LOOKUP(2,1/(AI66:AJ66<>""),AI66:AJ66))) | IF(OR(F66="",AL66=""),"",IF(COUNT(AI66:AK66)=0,"",AL66-LOOKUP(2,1/(AI66:AK66<>""),AI66:AK66))) | IF(OR(F66="",AM66=""),"",IF(COUNT(AI66:AL66)=0,"",AM66-LOOKUP(2,1/(AI66:AL66<>""),AI66:AL66))) | IF(OR(F66="",AN66=""),"",IF(COUNT(AI66:AM66)=0,"",AN66-LOOKUP(2,1/(AI66:AM66<>""),AI66:AM66))) | IF(OR(F66="",AO66=""),"",IF(COUNT(AI66:AN66)=0,"",AO66-LOOKUP(2,1/(AI66:AN66<>""),AI66:AN66))) | IF(OR(F66="",AP66=""),"",IF(COUNT(AI66:AO66)=0,"",AP66-LOOKUP(2,1/(AI66:AO66<>""),AI66:AO66))) | IF(OR(F66="",AQ66=""),"",IF(COUNT(AI66:AP66)=0,"",AQ66-LOOKUP(2,1/(AI66:AP66<>""),AI66:AP66))) | IF(OR(F66="",AR66=""),"",IF(COUNT(AI66:AQ66)=0,"",AR66-LOOKUP(2,1/(AI66:AQ66<>""),AI66:AQ66))) | IF(OR(F66="",AS66=""),"",IF(COUNT(AI66:AR66)=0,"",AS66-LOOKUP(2,1/(AI66:AR66<>""),AI66:AR66))) | IF(OR(F66="",AT66=""),"",IF(COUNT(AI66:AS66)=0,"",AT66-LOOKUP(2,1/(AI66:AS66<>""),AI66:AS66))) | IF(OR(F66="",AU66=""),"",IF(COUNT(AI66:AT66)=0,"",AU66-LOOKUP(2,1/(AI66:AT66<>""),AI66:AT66))) | IF(OR(F66="",AV66=""),"",IF(COUNT(AI66:AU66)=0,"",AV66-LOOKUP(2,1/(AI66:AU66<>""),AI66:AU66))) | IF(J66="","All_Provinces",IFERROR(VLOOKUP(J66,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K66="","All_Districts",IFERROR(VLOOKUP(K66,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F67="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 11 of 12 | AF2-DIS-N-025 | 8.Parun Drip irrigation Site | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nuristan | Parun | Ishtivi | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ehsanullah |  | 5725.3 | IF(AQ67="","",AQ67) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W67<>"",W67,IF(OR(T67="",V67=""),"",EDATE(T67,V67))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Ehsanullah | IF(F67="","",IF(COUNT(AI67:AV67)=0,IF(AA67="","Not started",AA67),SUBSTITUTE(LOOKUP(2,1/(AI67:AV67<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F67="",COUNT(AI67:AV67)=0),"",TODAY()-LOOKUP(2,1/(AI67:AV67<>""),AI67:AV67)) | IF(OR(F67="",COUNT(AI67:AV67)<2),"",LOOKUP(2,1/(AI67:AV67<>""),AI67:AV67)-MIN(AI67:AV67)) | IF(OR(AD67="",AC67="Not started",AC67=""),"",IFERROR(AD67-IF(VLOOKUP(AC67,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC67,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F67="","",IF(OR(AA67="Cancelled",AC67="Cancelled"),"Cancelled",IF(OR(AC67="Completed / Handover",Y67<>"",Z67>=100),"Completed — on track",IF(O67="Not awarded",IF(U67="",IF(X67="","No planned date",IF(TODAY()>X67,"Behind — past planned date",IF(X67-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U67,"Behind — award date passed",IF(U67-TODAY()<=30,"At risk — close to off track","On track"))),IF(X67="","No planned date",IF(AND(TODAY()>X67,OR(Z67="",Z67<100)),"Behind — past end date",IF(AND(T67<>"",X67<>"",Z67<>"",(Z67<100),((TODAY()-T67)/MAX(X67-T67,1)*100)-Z67>15),"Behind — progress lag",IF(AND(X67-TODAY()<=30,X67-TODAY()>=0,OR(Z67="",Z67<90)),"At risk — close to off track","On track")))))))) | IF(OR(F67="",AC67="Completed / Handover",AC67="Cancelled"),"",IF(O67="Not awarded",IF(U67<>"",U67-TODAY(),IF(X67="","",X67-TODAY())),IF(X67="","",X67-TODAY()))) | [14 empty] | IF(OR(F67="",AJ67=""),"",IF(COUNT(AI67:AI67)=0,"",AJ67-LOOKUP(2,1/(AI67:AI67<>""),AI67:AI67))) | IF(OR(F67="",AK67=""),"",IF(COUNT(AI67:AJ67)=0,"",AK67-LOOKUP(2,1/(AI67:AJ67<>""),AI67:AJ67))) | IF(OR(F67="",AL67=""),"",IF(COUNT(AI67:AK67)=0,"",AL67-LOOKUP(2,1/(AI67:AK67<>""),AI67:AK67))) | IF(OR(F67="",AM67=""),"",IF(COUNT(AI67:AL67)=0,"",AM67-LOOKUP(2,1/(AI67:AL67<>""),AI67:AL67))) | IF(OR(F67="",AN67=""),"",IF(COUNT(AI67:AM67)=0,"",AN67-LOOKUP(2,1/(AI67:AM67<>""),AI67:AM67))) | IF(OR(F67="",AO67=""),"",IF(COUNT(AI67:AN67)=0,"",AO67-LOOKUP(2,1/(AI67:AN67<>""),AI67:AN67))) | IF(OR(F67="",AP67=""),"",IF(COUNT(AI67:AO67)=0,"",AP67-LOOKUP(2,1/(AI67:AO67<>""),AI67:AO67))) | IF(OR(F67="",AQ67=""),"",IF(COUNT(AI67:AP67)=0,"",AQ67-LOOKUP(2,1/(AI67:AP67<>""),AI67:AP67))) | IF(OR(F67="",AR67=""),"",IF(COUNT(AI67:AQ67)=0,"",AR67-LOOKUP(2,1/(AI67:AQ67<>""),AI67:AQ67))) | IF(OR(F67="",AS67=""),"",IF(COUNT(AI67:AR67)=0,"",AS67-LOOKUP(2,1/(AI67:AR67<>""),AI67:AR67))) | IF(OR(F67="",AT67=""),"",IF(COUNT(AI67:AS67)=0,"",AT67-LOOKUP(2,1/(AI67:AS67<>""),AI67:AS67))) | IF(OR(F67="",AU67=""),"",IF(COUNT(AI67:AT67)=0,"",AU67-LOOKUP(2,1/(AI67:AT67<>""),AI67:AT67))) | IF(OR(F67="",AV67=""),"",IF(COUNT(AI67:AU67)=0,"",AV67-LOOKUP(2,1/(AI67:AU67<>""),AI67:AU67))) | IF(J67="","All_Provinces",IFERROR(VLOOKUP(J67,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K67="","All_Districts",IFERROR(VLOOKUP(K67,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F68="","",ROW()-3) | AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | 12 of 12 | AF2-DIS-N-026 | 9.Mateeullah Drip irrigation Site | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nuristan | Parun | Pronz | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mateeullah |  | 5216.26 | IF(AQ68="","",AQ68) | 2026-12-24 | 4.9 | 2027-05-23 | IF(W68<>"",W68,IF(OR(T68="",V68=""),"",EDATE(T68,V68))) |  |  | Retendered (Re-ITB) | Five month construction period. No slack period considered for Laghman and Nagrahar and two months slack period for Kunar and Nuristan. '- ¦ Farmer: Mateeullah | IF(F68="","",IF(COUNT(AI68:AV68)=0,IF(AA68="","Not started",AA68),SUBSTITUTE(LOOKUP(2,1/(AI68:AV68<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F68="",COUNT(AI68:AV68)=0),"",TODAY()-LOOKUP(2,1/(AI68:AV68<>""),AI68:AV68)) | IF(OR(F68="",COUNT(AI68:AV68)<2),"",LOOKUP(2,1/(AI68:AV68<>""),AI68:AV68)-MIN(AI68:AV68)) | IF(OR(AD68="",AC68="Not started",AC68=""),"",IFERROR(AD68-IF(VLOOKUP(AC68,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC68,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F68="","",IF(OR(AA68="Cancelled",AC68="Cancelled"),"Cancelled",IF(OR(AC68="Completed / Handover",Y68<>"",Z68>=100),"Completed — on track",IF(O68="Not awarded",IF(U68="",IF(X68="","No planned date",IF(TODAY()>X68,"Behind — past planned date",IF(X68-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U68,"Behind — award date passed",IF(U68-TODAY()<=30,"At risk — close to off track","On track"))),IF(X68="","No planned date",IF(AND(TODAY()>X68,OR(Z68="",Z68<100)),"Behind — past end date",IF(AND(T68<>"",X68<>"",Z68<>"",(Z68<100),((TODAY()-T68)/MAX(X68-T68,1)*100)-Z68>15),"Behind — progress lag",IF(AND(X68-TODAY()<=30,X68-TODAY()>=0,OR(Z68="",Z68<90)),"At risk — close to off track","On track")))))))) | IF(OR(F68="",AC68="Completed / Handover",AC68="Cancelled"),"",IF(O68="Not awarded",IF(U68<>"",U68-TODAY(),IF(X68="","",X68-TODAY())),IF(X68="","",X68-TODAY()))) | [14 empty] | IF(OR(F68="",AJ68=""),"",IF(COUNT(AI68:AI68)=0,"",AJ68-LOOKUP(2,1/(AI68:AI68<>""),AI68:AI68))) | IF(OR(F68="",AK68=""),"",IF(COUNT(AI68:AJ68)=0,"",AK68-LOOKUP(2,1/(AI68:AJ68<>""),AI68:AJ68))) | IF(OR(F68="",AL68=""),"",IF(COUNT(AI68:AK68)=0,"",AL68-LOOKUP(2,1/(AI68:AK68<>""),AI68:AK68))) | IF(OR(F68="",AM68=""),"",IF(COUNT(AI68:AL68)=0,"",AM68-LOOKUP(2,1/(AI68:AL68<>""),AI68:AL68))) | IF(OR(F68="",AN68=""),"",IF(COUNT(AI68:AM68)=0,"",AN68-LOOKUP(2,1/(AI68:AM68<>""),AI68:AM68))) | IF(OR(F68="",AO68=""),"",IF(COUNT(AI68:AN68)=0,"",AO68-LOOKUP(2,1/(AI68:AN68<>""),AI68:AN68))) | IF(OR(F68="",AP68=""),"",IF(COUNT(AI68:AO68)=0,"",AP68-LOOKUP(2,1/(AI68:AO68<>""),AI68:AO68))) | IF(OR(F68="",AQ68=""),"",IF(COUNT(AI68:AP68)=0,"",AQ68-LOOKUP(2,1/(AI68:AP68<>""),AI68:AP68))) | IF(OR(F68="",AR68=""),"",IF(COUNT(AI68:AQ68)=0,"",AR68-LOOKUP(2,1/(AI68:AQ68<>""),AI68:AQ68))) | IF(OR(F68="",AS68=""),"",IF(COUNT(AI68:AR68)=0,"",AS68-LOOKUP(2,1/(AI68:AR68<>""),AI68:AR68))) | IF(OR(F68="",AT68=""),"",IF(COUNT(AI68:AS68)=0,"",AT68-LOOKUP(2,1/(AI68:AS68<>""),AI68:AS68))) | IF(OR(F68="",AU68=""),"",IF(COUNT(AI68:AT68)=0,"",AU68-LOOKUP(2,1/(AI68:AT68<>""),AI68:AT68))) | IF(OR(F68="",AV68=""),"",IF(COUNT(AI68:AU68)=0,"",AV68-LOOKUP(2,1/(AI68:AU68<>""),AI68:AU68))) | IF(J68="","All_Provinces",IFERROR(VLOOKUP(J68,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K68="","All_Districts",IFERROR(VLOOKUP(K68,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F69="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 1 of 14 | AF2-DIS-N-027 | Alberoni University Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Hesa-e- Awal Kohistan | Alberoni university | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Alberoni University |  | 4250 | IF(AQ69="","",AQ69) | 2026-12-20 | 6.3 | 2027-06-30 | IF(W69<>"",W69,IF(OR(T69="",V69=""),"",EDATE(T69,V69))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.'''- ¦ Farmer: Alberoni University | IF(F69="","",IF(COUNT(AI69:AV69)=0,IF(AA69="","Not started",AA69),SUBSTITUTE(LOOKUP(2,1/(AI69:AV69<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F69="",COUNT(AI69:AV69)=0),"",TODAY()-LOOKUP(2,1/(AI69:AV69<>""),AI69:AV69)) | IF(OR(F69="",COUNT(AI69:AV69)<2),"",LOOKUP(2,1/(AI69:AV69<>""),AI69:AV69)-MIN(AI69:AV69)) | IF(OR(AD69="",AC69="Not started",AC69=""),"",IFERROR(AD69-IF(VLOOKUP(AC69,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC69,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F69="","",IF(OR(AA69="Cancelled",AC69="Cancelled"),"Cancelled",IF(OR(AC69="Completed / Handover",Y69<>"",Z69>=100),"Completed — on track",IF(O69="Not awarded",IF(U69="",IF(X69="","No planned date",IF(TODAY()>X69,"Behind — past planned date",IF(X69-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U69,"Behind — award date passed",IF(U69-TODAY()<=30,"At risk — close to off track","On track"))),IF(X69="","No planned date",IF(AND(TODAY()>X69,OR(Z69="",Z69<100)),"Behind — past end date",IF(AND(T69<>"",X69<>"",Z69<>"",(Z69<100),((TODAY()-T69)/MAX(X69-T69,1)*100)-Z69>15),"Behind — progress lag",IF(AND(X69-TODAY()<=30,X69-TODAY()>=0,OR(Z69="",Z69<90)),"At risk — close to off track","On track")))))))) | IF(OR(F69="",AC69="Completed / Handover",AC69="Cancelled"),"",IF(O69="Not awarded",IF(U69<>"",U69-TODAY(),IF(X69="","",X69-TODAY())),IF(X69="","",X69-TODAY()))) | [14 empty] | IF(OR(F69="",AJ69=""),"",IF(COUNT(AI69:AI69)=0,"",AJ69-LOOKUP(2,1/(AI69:AI69<>""),AI69:AI69))) | IF(OR(F69="",AK69=""),"",IF(COUNT(AI69:AJ69)=0,"",AK69-LOOKUP(2,1/(AI69:AJ69<>""),AI69:AJ69))) | IF(OR(F69="",AL69=""),"",IF(COUNT(AI69:AK69)=0,"",AL69-LOOKUP(2,1/(AI69:AK69<>""),AI69:AK69))) | IF(OR(F69="",AM69=""),"",IF(COUNT(AI69:AL69)=0,"",AM69-LOOKUP(2,1/(AI69:AL69<>""),AI69:AL69))) | IF(OR(F69="",AN69=""),"",IF(COUNT(AI69:AM69)=0,"",AN69-LOOKUP(2,1/(AI69:AM69<>""),AI69:AM69))) | IF(OR(F69="",AO69=""),"",IF(COUNT(AI69:AN69)=0,"",AO69-LOOKUP(2,1/(AI69:AN69<>""),AI69:AN69))) | IF(OR(F69="",AP69=""),"",IF(COUNT(AI69:AO69)=0,"",AP69-LOOKUP(2,1/(AI69:AO69<>""),AI69:AO69))) | IF(OR(F69="",AQ69=""),"",IF(COUNT(AI69:AP69)=0,"",AQ69-LOOKUP(2,1/(AI69:AP69<>""),AI69:AP69))) | IF(OR(F69="",AR69=""),"",IF(COUNT(AI69:AQ69)=0,"",AR69-LOOKUP(2,1/(AI69:AQ69<>""),AI69:AQ69))) | IF(OR(F69="",AS69=""),"",IF(COUNT(AI69:AR69)=0,"",AS69-LOOKUP(2,1/(AI69:AR69<>""),AI69:AR69))) | IF(OR(F69="",AT69=""),"",IF(COUNT(AI69:AS69)=0,"",AT69-LOOKUP(2,1/(AI69:AS69<>""),AI69:AS69))) | IF(OR(F69="",AU69=""),"",IF(COUNT(AI69:AT69)=0,"",AU69-LOOKUP(2,1/(AI69:AT69<>""),AI69:AT69))) | IF(OR(F69="",AV69=""),"",IF(COUNT(AI69:AU69)=0,"",AV69-LOOKUP(2,1/(AI69:AU69<>""),AI69:AU69))) | IF(J69="","All_Provinces",IFERROR(VLOOKUP(J69,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K69="","All_Districts",IFERROR(VLOOKUP(K69,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F70="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 2 of 14 | AF2-DIS-N-028 | Arghande Bala Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Paghman | Arghande bala | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Yousaf |  | 8500 | IF(AQ70="","",AQ70) | 2026-12-20 | 6.3 | 2027-06-30 | IF(W70<>"",W70,IF(OR(T70="",V70=""),"",EDATE(T70,V70))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Mohammad Yousaf | IF(F70="","",IF(COUNT(AI70:AV70)=0,IF(AA70="","Not started",AA70),SUBSTITUTE(LOOKUP(2,1/(AI70:AV70<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F70="",COUNT(AI70:AV70)=0),"",TODAY()-LOOKUP(2,1/(AI70:AV70<>""),AI70:AV70)) | IF(OR(F70="",COUNT(AI70:AV70)<2),"",LOOKUP(2,1/(AI70:AV70<>""),AI70:AV70)-MIN(AI70:AV70)) | IF(OR(AD70="",AC70="Not started",AC70=""),"",IFERROR(AD70-IF(VLOOKUP(AC70,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC70,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F70="","",IF(OR(AA70="Cancelled",AC70="Cancelled"),"Cancelled",IF(OR(AC70="Completed / Handover",Y70<>"",Z70>=100),"Completed — on track",IF(O70="Not awarded",IF(U70="",IF(X70="","No planned date",IF(TODAY()>X70,"Behind — past planned date",IF(X70-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U70,"Behind — award date passed",IF(U70-TODAY()<=30,"At risk — close to off track","On track"))),IF(X70="","No planned date",IF(AND(TODAY()>X70,OR(Z70="",Z70<100)),"Behind — past end date",IF(AND(T70<>"",X70<>"",Z70<>"",(Z70<100),((TODAY()-T70)/MAX(X70-T70,1)*100)-Z70>15),"Behind — progress lag",IF(AND(X70-TODAY()<=30,X70-TODAY()>=0,OR(Z70="",Z70<90)),"At risk — close to off track","On track")))))))) | IF(OR(F70="",AC70="Completed / Handover",AC70="Cancelled"),"",IF(O70="Not awarded",IF(U70<>"",U70-TODAY(),IF(X70="","",X70-TODAY())),IF(X70="","",X70-TODAY()))) | [14 empty] | IF(OR(F70="",AJ70=""),"",IF(COUNT(AI70:AI70)=0,"",AJ70-LOOKUP(2,1/(AI70:AI70<>""),AI70:AI70))) | IF(OR(F70="",AK70=""),"",IF(COUNT(AI70:AJ70)=0,"",AK70-LOOKUP(2,1/(AI70:AJ70<>""),AI70:AJ70))) | IF(OR(F70="",AL70=""),"",IF(COUNT(AI70:AK70)=0,"",AL70-LOOKUP(2,1/(AI70:AK70<>""),AI70:AK70))) | IF(OR(F70="",AM70=""),"",IF(COUNT(AI70:AL70)=0,"",AM70-LOOKUP(2,1/(AI70:AL70<>""),AI70:AL70))) | IF(OR(F70="",AN70=""),"",IF(COUNT(AI70:AM70)=0,"",AN70-LOOKUP(2,1/(AI70:AM70<>""),AI70:AM70))) | IF(OR(F70="",AO70=""),"",IF(COUNT(AI70:AN70)=0,"",AO70-LOOKUP(2,1/(AI70:AN70<>""),AI70:AN70))) | IF(OR(F70="",AP70=""),"",IF(COUNT(AI70:AO70)=0,"",AP70-LOOKUP(2,1/(AI70:AO70<>""),AI70:AO70))) | IF(OR(F70="",AQ70=""),"",IF(COUNT(AI70:AP70)=0,"",AQ70-LOOKUP(2,1/(AI70:AP70<>""),AI70:AP70))) | IF(OR(F70="",AR70=""),"",IF(COUNT(AI70:AQ70)=0,"",AR70-LOOKUP(2,1/(AI70:AQ70<>""),AI70:AQ70))) | IF(OR(F70="",AS70=""),"",IF(COUNT(AI70:AR70)=0,"",AS70-LOOKUP(2,1/(AI70:AR70<>""),AI70:AR70))) | IF(OR(F70="",AT70=""),"",IF(COUNT(AI70:AS70)=0,"",AT70-LOOKUP(2,1/(AI70:AS70<>""),AI70:AS70))) | IF(OR(F70="",AU70=""),"",IF(COUNT(AI70:AT70)=0,"",AU70-LOOKUP(2,1/(AI70:AT70<>""),AI70:AT70))) | IF(OR(F70="",AV70=""),"",IF(COUNT(AI70:AU70)=0,"",AV70-LOOKUP(2,1/(AI70:AU70<>""),AI70:AU70))) | IF(J70="","All_Provinces",IFERROR(VLOOKUP(J70,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K70="","All_Districts",IFERROR(VLOOKUP(K70,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F71="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 3 of 14 | AF2-DIS-N-029 | Dahan Rabat Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Parwan | Shikh Ali | Dahan Rabat | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Abdullah |  | 4250 | IF(AQ71="","",AQ71) | 2026-12-15 | 6.4 | 2027-06-28 | IF(W71<>"",W71,IF(OR(T71="",V71=""),"",EDATE(T71,V71))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.'- ¦ Farmer: Abdullah | IF(F71="","",IF(COUNT(AI71:AV71)=0,IF(AA71="","Not started",AA71),SUBSTITUTE(LOOKUP(2,1/(AI71:AV71<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F71="",COUNT(AI71:AV71)=0),"",TODAY()-LOOKUP(2,1/(AI71:AV71<>""),AI71:AV71)) | IF(OR(F71="",COUNT(AI71:AV71)<2),"",LOOKUP(2,1/(AI71:AV71<>""),AI71:AV71)-MIN(AI71:AV71)) | IF(OR(AD71="",AC71="Not started",AC71=""),"",IFERROR(AD71-IF(VLOOKUP(AC71,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC71,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F71="","",IF(OR(AA71="Cancelled",AC71="Cancelled"),"Cancelled",IF(OR(AC71="Completed / Handover",Y71<>"",Z71>=100),"Completed — on track",IF(O71="Not awarded",IF(U71="",IF(X71="","No planned date",IF(TODAY()>X71,"Behind — past planned date",IF(X71-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U71,"Behind — award date passed",IF(U71-TODAY()<=30,"At risk — close to off track","On track"))),IF(X71="","No planned date",IF(AND(TODAY()>X71,OR(Z71="",Z71<100)),"Behind — past end date",IF(AND(T71<>"",X71<>"",Z71<>"",(Z71<100),((TODAY()-T71)/MAX(X71-T71,1)*100)-Z71>15),"Behind — progress lag",IF(AND(X71-TODAY()<=30,X71-TODAY()>=0,OR(Z71="",Z71<90)),"At risk — close to off track","On track")))))))) | IF(OR(F71="",AC71="Completed / Handover",AC71="Cancelled"),"",IF(O71="Not awarded",IF(U71<>"",U71-TODAY(),IF(X71="","",X71-TODAY())),IF(X71="","",X71-TODAY()))) | [14 empty] | IF(OR(F71="",AJ71=""),"",IF(COUNT(AI71:AI71)=0,"",AJ71-LOOKUP(2,1/(AI71:AI71<>""),AI71:AI71))) | IF(OR(F71="",AK71=""),"",IF(COUNT(AI71:AJ71)=0,"",AK71-LOOKUP(2,1/(AI71:AJ71<>""),AI71:AJ71))) | IF(OR(F71="",AL71=""),"",IF(COUNT(AI71:AK71)=0,"",AL71-LOOKUP(2,1/(AI71:AK71<>""),AI71:AK71))) | IF(OR(F71="",AM71=""),"",IF(COUNT(AI71:AL71)=0,"",AM71-LOOKUP(2,1/(AI71:AL71<>""),AI71:AL71))) | IF(OR(F71="",AN71=""),"",IF(COUNT(AI71:AM71)=0,"",AN71-LOOKUP(2,1/(AI71:AM71<>""),AI71:AM71))) | IF(OR(F71="",AO71=""),"",IF(COUNT(AI71:AN71)=0,"",AO71-LOOKUP(2,1/(AI71:AN71<>""),AI71:AN71))) | IF(OR(F71="",AP71=""),"",IF(COUNT(AI71:AO71)=0,"",AP71-LOOKUP(2,1/(AI71:AO71<>""),AI71:AO71))) | IF(OR(F71="",AQ71=""),"",IF(COUNT(AI71:AP71)=0,"",AQ71-LOOKUP(2,1/(AI71:AP71<>""),AI71:AP71))) | IF(OR(F71="",AR71=""),"",IF(COUNT(AI71:AQ71)=0,"",AR71-LOOKUP(2,1/(AI71:AQ71<>""),AI71:AQ71))) | IF(OR(F71="",AS71=""),"",IF(COUNT(AI71:AR71)=0,"",AS71-LOOKUP(2,1/(AI71:AR71<>""),AI71:AR71))) | IF(OR(F71="",AT71=""),"",IF(COUNT(AI71:AS71)=0,"",AT71-LOOKUP(2,1/(AI71:AS71<>""),AI71:AS71))) | IF(OR(F71="",AU71=""),"",IF(COUNT(AI71:AT71)=0,"",AU71-LOOKUP(2,1/(AI71:AT71<>""),AI71:AT71))) | IF(OR(F71="",AV71=""),"",IF(COUNT(AI71:AU71)=0,"",AV71-LOOKUP(2,1/(AI71:AU71<>""),AI71:AU71))) | IF(J71="","All_Provinces",IFERROR(VLOOKUP(J71,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K71="","All_Districts",IFERROR(VLOOKUP(K71,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F72="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 4 of 14 | AF2-DIS-N-030 | Dasht-e- Top Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Saydabad | Wardak university | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Wardak University |  | 4250 | IF(AQ72="","",AQ72) | 2026-12-25 | 6.3 | 2027-07-05 | IF(W72<>"",W72,IF(OR(T72="",V72=""),"",EDATE(T72,V72))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Wardak University | IF(F72="","",IF(COUNT(AI72:AV72)=0,IF(AA72="","Not started",AA72),SUBSTITUTE(LOOKUP(2,1/(AI72:AV72<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F72="",COUNT(AI72:AV72)=0),"",TODAY()-LOOKUP(2,1/(AI72:AV72<>""),AI72:AV72)) | IF(OR(F72="",COUNT(AI72:AV72)<2),"",LOOKUP(2,1/(AI72:AV72<>""),AI72:AV72)-MIN(AI72:AV72)) | IF(OR(AD72="",AC72="Not started",AC72=""),"",IFERROR(AD72-IF(VLOOKUP(AC72,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC72,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F72="","",IF(OR(AA72="Cancelled",AC72="Cancelled"),"Cancelled",IF(OR(AC72="Completed / Handover",Y72<>"",Z72>=100),"Completed — on track",IF(O72="Not awarded",IF(U72="",IF(X72="","No planned date",IF(TODAY()>X72,"Behind — past planned date",IF(X72-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U72,"Behind — award date passed",IF(U72-TODAY()<=30,"At risk — close to off track","On track"))),IF(X72="","No planned date",IF(AND(TODAY()>X72,OR(Z72="",Z72<100)),"Behind — past end date",IF(AND(T72<>"",X72<>"",Z72<>"",(Z72<100),((TODAY()-T72)/MAX(X72-T72,1)*100)-Z72>15),"Behind — progress lag",IF(AND(X72-TODAY()<=30,X72-TODAY()>=0,OR(Z72="",Z72<90)),"At risk — close to off track","On track")))))))) | IF(OR(F72="",AC72="Completed / Handover",AC72="Cancelled"),"",IF(O72="Not awarded",IF(U72<>"",U72-TODAY(),IF(X72="","",X72-TODAY())),IF(X72="","",X72-TODAY()))) | [14 empty] | IF(OR(F72="",AJ72=""),"",IF(COUNT(AI72:AI72)=0,"",AJ72-LOOKUP(2,1/(AI72:AI72<>""),AI72:AI72))) | IF(OR(F72="",AK72=""),"",IF(COUNT(AI72:AJ72)=0,"",AK72-LOOKUP(2,1/(AI72:AJ72<>""),AI72:AJ72))) | IF(OR(F72="",AL72=""),"",IF(COUNT(AI72:AK72)=0,"",AL72-LOOKUP(2,1/(AI72:AK72<>""),AI72:AK72))) | IF(OR(F72="",AM72=""),"",IF(COUNT(AI72:AL72)=0,"",AM72-LOOKUP(2,1/(AI72:AL72<>""),AI72:AL72))) | IF(OR(F72="",AN72=""),"",IF(COUNT(AI72:AM72)=0,"",AN72-LOOKUP(2,1/(AI72:AM72<>""),AI72:AM72))) | IF(OR(F72="",AO72=""),"",IF(COUNT(AI72:AN72)=0,"",AO72-LOOKUP(2,1/(AI72:AN72<>""),AI72:AN72))) | IF(OR(F72="",AP72=""),"",IF(COUNT(AI72:AO72)=0,"",AP72-LOOKUP(2,1/(AI72:AO72<>""),AI72:AO72))) | IF(OR(F72="",AQ72=""),"",IF(COUNT(AI72:AP72)=0,"",AQ72-LOOKUP(2,1/(AI72:AP72<>""),AI72:AP72))) | IF(OR(F72="",AR72=""),"",IF(COUNT(AI72:AQ72)=0,"",AR72-LOOKUP(2,1/(AI72:AQ72<>""),AI72:AQ72))) | IF(OR(F72="",AS72=""),"",IF(COUNT(AI72:AR72)=0,"",AS72-LOOKUP(2,1/(AI72:AR72<>""),AI72:AR72))) | IF(OR(F72="",AT72=""),"",IF(COUNT(AI72:AS72)=0,"",AT72-LOOKUP(2,1/(AI72:AS72<>""),AI72:AS72))) | IF(OR(F72="",AU72=""),"",IF(COUNT(AI72:AT72)=0,"",AU72-LOOKUP(2,1/(AI72:AT72<>""),AI72:AT72))) | IF(OR(F72="",AV72=""),"",IF(COUNT(AI72:AU72)=0,"",AV72-LOOKUP(2,1/(AI72:AU72<>""),AI72:AU72))) | IF(J72="","All_Provinces",IFERROR(VLOOKUP(J72,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K72="","All_Districts",IFERROR(VLOOKUP(K72,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F73="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 5 of 14 | AF2-DIS-N-031 | Durani Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Nirkh | Durani | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Fazel Rahman |  | 8500 | IF(AQ73="","",AQ73) | 2026-12-25 | 6.3 | 2027-07-05 | IF(W73<>"",W73,IF(OR(T73="",V73=""),"",EDATE(T73,V73))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Fazel Rahman | IF(F73="","",IF(COUNT(AI73:AV73)=0,IF(AA73="","Not started",AA73),SUBSTITUTE(LOOKUP(2,1/(AI73:AV73<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F73="",COUNT(AI73:AV73)=0),"",TODAY()-LOOKUP(2,1/(AI73:AV73<>""),AI73:AV73)) | IF(OR(F73="",COUNT(AI73:AV73)<2),"",LOOKUP(2,1/(AI73:AV73<>""),AI73:AV73)-MIN(AI73:AV73)) | IF(OR(AD73="",AC73="Not started",AC73=""),"",IFERROR(AD73-IF(VLOOKUP(AC73,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC73,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F73="","",IF(OR(AA73="Cancelled",AC73="Cancelled"),"Cancelled",IF(OR(AC73="Completed / Handover",Y73<>"",Z73>=100),"Completed — on track",IF(O73="Not awarded",IF(U73="",IF(X73="","No planned date",IF(TODAY()>X73,"Behind — past planned date",IF(X73-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U73,"Behind — award date passed",IF(U73-TODAY()<=30,"At risk — close to off track","On track"))),IF(X73="","No planned date",IF(AND(TODAY()>X73,OR(Z73="",Z73<100)),"Behind — past end date",IF(AND(T73<>"",X73<>"",Z73<>"",(Z73<100),((TODAY()-T73)/MAX(X73-T73,1)*100)-Z73>15),"Behind — progress lag",IF(AND(X73-TODAY()<=30,X73-TODAY()>=0,OR(Z73="",Z73<90)),"At risk — close to off track","On track")))))))) | IF(OR(F73="",AC73="Completed / Handover",AC73="Cancelled"),"",IF(O73="Not awarded",IF(U73<>"",U73-TODAY(),IF(X73="","",X73-TODAY())),IF(X73="","",X73-TODAY()))) | [14 empty] | IF(OR(F73="",AJ73=""),"",IF(COUNT(AI73:AI73)=0,"",AJ73-LOOKUP(2,1/(AI73:AI73<>""),AI73:AI73))) | IF(OR(F73="",AK73=""),"",IF(COUNT(AI73:AJ73)=0,"",AK73-LOOKUP(2,1/(AI73:AJ73<>""),AI73:AJ73))) | IF(OR(F73="",AL73=""),"",IF(COUNT(AI73:AK73)=0,"",AL73-LOOKUP(2,1/(AI73:AK73<>""),AI73:AK73))) | IF(OR(F73="",AM73=""),"",IF(COUNT(AI73:AL73)=0,"",AM73-LOOKUP(2,1/(AI73:AL73<>""),AI73:AL73))) | IF(OR(F73="",AN73=""),"",IF(COUNT(AI73:AM73)=0,"",AN73-LOOKUP(2,1/(AI73:AM73<>""),AI73:AM73))) | IF(OR(F73="",AO73=""),"",IF(COUNT(AI73:AN73)=0,"",AO73-LOOKUP(2,1/(AI73:AN73<>""),AI73:AN73))) | IF(OR(F73="",AP73=""),"",IF(COUNT(AI73:AO73)=0,"",AP73-LOOKUP(2,1/(AI73:AO73<>""),AI73:AO73))) | IF(OR(F73="",AQ73=""),"",IF(COUNT(AI73:AP73)=0,"",AQ73-LOOKUP(2,1/(AI73:AP73<>""),AI73:AP73))) | IF(OR(F73="",AR73=""),"",IF(COUNT(AI73:AQ73)=0,"",AR73-LOOKUP(2,1/(AI73:AQ73<>""),AI73:AQ73))) | IF(OR(F73="",AS73=""),"",IF(COUNT(AI73:AR73)=0,"",AS73-LOOKUP(2,1/(AI73:AR73<>""),AI73:AR73))) | IF(OR(F73="",AT73=""),"",IF(COUNT(AI73:AS73)=0,"",AT73-LOOKUP(2,1/(AI73:AS73<>""),AI73:AS73))) | IF(OR(F73="",AU73=""),"",IF(COUNT(AI73:AT73)=0,"",AU73-LOOKUP(2,1/(AI73:AT73<>""),AI73:AT73))) | IF(OR(F73="",AV73=""),"",IF(COUNT(AI73:AU73)=0,"",AV73-LOOKUP(2,1/(AI73:AU73<>""),AI73:AU73))) | IF(J73="","All_Provinces",IFERROR(VLOOKUP(J73,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K73="","All_Districts",IFERROR(VLOOKUP(K73,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F74="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 6 of 14 | AF2-DIS-N-032 | Goga Manda Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Sarobi | Goga manda | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Hayatullah |  | 4250 | IF(AQ74="","",AQ74) | 2026-12-20 | 6.3 | 2027-06-30 | IF(W74<>"",W74,IF(OR(T74="",V74=""),"",EDATE(T74,V74))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Hayatullah | IF(F74="","",IF(COUNT(AI74:AV74)=0,IF(AA74="","Not started",AA74),SUBSTITUTE(LOOKUP(2,1/(AI74:AV74<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F74="",COUNT(AI74:AV74)=0),"",TODAY()-LOOKUP(2,1/(AI74:AV74<>""),AI74:AV74)) | IF(OR(F74="",COUNT(AI74:AV74)<2),"",LOOKUP(2,1/(AI74:AV74<>""),AI74:AV74)-MIN(AI74:AV74)) | IF(OR(AD74="",AC74="Not started",AC74=""),"",IFERROR(AD74-IF(VLOOKUP(AC74,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC74,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F74="","",IF(OR(AA74="Cancelled",AC74="Cancelled"),"Cancelled",IF(OR(AC74="Completed / Handover",Y74<>"",Z74>=100),"Completed — on track",IF(O74="Not awarded",IF(U74="",IF(X74="","No planned date",IF(TODAY()>X74,"Behind — past planned date",IF(X74-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U74,"Behind — award date passed",IF(U74-TODAY()<=30,"At risk — close to off track","On track"))),IF(X74="","No planned date",IF(AND(TODAY()>X74,OR(Z74="",Z74<100)),"Behind — past end date",IF(AND(T74<>"",X74<>"",Z74<>"",(Z74<100),((TODAY()-T74)/MAX(X74-T74,1)*100)-Z74>15),"Behind — progress lag",IF(AND(X74-TODAY()<=30,X74-TODAY()>=0,OR(Z74="",Z74<90)),"At risk — close to off track","On track")))))))) | IF(OR(F74="",AC74="Completed / Handover",AC74="Cancelled"),"",IF(O74="Not awarded",IF(U74<>"",U74-TODAY(),IF(X74="","",X74-TODAY())),IF(X74="","",X74-TODAY()))) | [14 empty] | IF(OR(F74="",AJ74=""),"",IF(COUNT(AI74:AI74)=0,"",AJ74-LOOKUP(2,1/(AI74:AI74<>""),AI74:AI74))) | IF(OR(F74="",AK74=""),"",IF(COUNT(AI74:AJ74)=0,"",AK74-LOOKUP(2,1/(AI74:AJ74<>""),AI74:AJ74))) | IF(OR(F74="",AL74=""),"",IF(COUNT(AI74:AK74)=0,"",AL74-LOOKUP(2,1/(AI74:AK74<>""),AI74:AK74))) | IF(OR(F74="",AM74=""),"",IF(COUNT(AI74:AL74)=0,"",AM74-LOOKUP(2,1/(AI74:AL74<>""),AI74:AL74))) | IF(OR(F74="",AN74=""),"",IF(COUNT(AI74:AM74)=0,"",AN74-LOOKUP(2,1/(AI74:AM74<>""),AI74:AM74))) | IF(OR(F74="",AO74=""),"",IF(COUNT(AI74:AN74)=0,"",AO74-LOOKUP(2,1/(AI74:AN74<>""),AI74:AN74))) | IF(OR(F74="",AP74=""),"",IF(COUNT(AI74:AO74)=0,"",AP74-LOOKUP(2,1/(AI74:AO74<>""),AI74:AO74))) | IF(OR(F74="",AQ74=""),"",IF(COUNT(AI74:AP74)=0,"",AQ74-LOOKUP(2,1/(AI74:AP74<>""),AI74:AP74))) | IF(OR(F74="",AR74=""),"",IF(COUNT(AI74:AQ74)=0,"",AR74-LOOKUP(2,1/(AI74:AQ74<>""),AI74:AQ74))) | IF(OR(F74="",AS74=""),"",IF(COUNT(AI74:AR74)=0,"",AS74-LOOKUP(2,1/(AI74:AR74<>""),AI74:AR74))) | IF(OR(F74="",AT74=""),"",IF(COUNT(AI74:AS74)=0,"",AT74-LOOKUP(2,1/(AI74:AS74<>""),AI74:AS74))) | IF(OR(F74="",AU74=""),"",IF(COUNT(AI74:AT74)=0,"",AU74-LOOKUP(2,1/(AI74:AT74<>""),AI74:AT74))) | IF(OR(F74="",AV74=""),"",IF(COUNT(AI74:AU74)=0,"",AV74-LOOKUP(2,1/(AI74:AU74<>""),AI74:AU74))) | IF(J74="","All_Provinces",IFERROR(VLOOKUP(J74,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K74="","All_Districts",IFERROR(VLOOKUP(K74,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F75="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 7 of 14 | AF2-DIS-N-033 | Khar Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Jaghatu | Khar | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Akbar |  | 8500 | IF(AQ75="","",AQ75) | 2026-12-25 | 6.3 | 2027-07-05 | IF(W75<>"",W75,IF(OR(T75="",V75=""),"",EDATE(T75,V75))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Mohammad Akbar | IF(F75="","",IF(COUNT(AI75:AV75)=0,IF(AA75="","Not started",AA75),SUBSTITUTE(LOOKUP(2,1/(AI75:AV75<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F75="",COUNT(AI75:AV75)=0),"",TODAY()-LOOKUP(2,1/(AI75:AV75<>""),AI75:AV75)) | IF(OR(F75="",COUNT(AI75:AV75)<2),"",LOOKUP(2,1/(AI75:AV75<>""),AI75:AV75)-MIN(AI75:AV75)) | IF(OR(AD75="",AC75="Not started",AC75=""),"",IFERROR(AD75-IF(VLOOKUP(AC75,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC75,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F75="","",IF(OR(AA75="Cancelled",AC75="Cancelled"),"Cancelled",IF(OR(AC75="Completed / Handover",Y75<>"",Z75>=100),"Completed — on track",IF(O75="Not awarded",IF(U75="",IF(X75="","No planned date",IF(TODAY()>X75,"Behind — past planned date",IF(X75-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U75,"Behind — award date passed",IF(U75-TODAY()<=30,"At risk — close to off track","On track"))),IF(X75="","No planned date",IF(AND(TODAY()>X75,OR(Z75="",Z75<100)),"Behind — past end date",IF(AND(T75<>"",X75<>"",Z75<>"",(Z75<100),((TODAY()-T75)/MAX(X75-T75,1)*100)-Z75>15),"Behind — progress lag",IF(AND(X75-TODAY()<=30,X75-TODAY()>=0,OR(Z75="",Z75<90)),"At risk — close to off track","On track")))))))) | IF(OR(F75="",AC75="Completed / Handover",AC75="Cancelled"),"",IF(O75="Not awarded",IF(U75<>"",U75-TODAY(),IF(X75="","",X75-TODAY())),IF(X75="","",X75-TODAY()))) | [14 empty] | IF(OR(F75="",AJ75=""),"",IF(COUNT(AI75:AI75)=0,"",AJ75-LOOKUP(2,1/(AI75:AI75<>""),AI75:AI75))) | IF(OR(F75="",AK75=""),"",IF(COUNT(AI75:AJ75)=0,"",AK75-LOOKUP(2,1/(AI75:AJ75<>""),AI75:AJ75))) | IF(OR(F75="",AL75=""),"",IF(COUNT(AI75:AK75)=0,"",AL75-LOOKUP(2,1/(AI75:AK75<>""),AI75:AK75))) | IF(OR(F75="",AM75=""),"",IF(COUNT(AI75:AL75)=0,"",AM75-LOOKUP(2,1/(AI75:AL75<>""),AI75:AL75))) | IF(OR(F75="",AN75=""),"",IF(COUNT(AI75:AM75)=0,"",AN75-LOOKUP(2,1/(AI75:AM75<>""),AI75:AM75))) | IF(OR(F75="",AO75=""),"",IF(COUNT(AI75:AN75)=0,"",AO75-LOOKUP(2,1/(AI75:AN75<>""),AI75:AN75))) | IF(OR(F75="",AP75=""),"",IF(COUNT(AI75:AO75)=0,"",AP75-LOOKUP(2,1/(AI75:AO75<>""),AI75:AO75))) | IF(OR(F75="",AQ75=""),"",IF(COUNT(AI75:AP75)=0,"",AQ75-LOOKUP(2,1/(AI75:AP75<>""),AI75:AP75))) | IF(OR(F75="",AR75=""),"",IF(COUNT(AI75:AQ75)=0,"",AR75-LOOKUP(2,1/(AI75:AQ75<>""),AI75:AQ75))) | IF(OR(F75="",AS75=""),"",IF(COUNT(AI75:AR75)=0,"",AS75-LOOKUP(2,1/(AI75:AR75<>""),AI75:AR75))) | IF(OR(F75="",AT75=""),"",IF(COUNT(AI75:AS75)=0,"",AT75-LOOKUP(2,1/(AI75:AS75<>""),AI75:AS75))) | IF(OR(F75="",AU75=""),"",IF(COUNT(AI75:AT75)=0,"",AU75-LOOKUP(2,1/(AI75:AT75<>""),AI75:AT75))) | IF(OR(F75="",AV75=""),"",IF(COUNT(AI75:AU75)=0,"",AV75-LOOKUP(2,1/(AI75:AU75<>""),AI75:AU75))) | IF(J75="","All_Provinces",IFERROR(VLOOKUP(J75,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K75="","All_Districts",IFERROR(VLOOKUP(K75,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F76="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 8 of 14 | AF2-DIS-N-034 | Lolenj Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Parwan | Surkh Parsa | Lolenj | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ghulam Haider Shah |  | 8500 | IF(AQ76="","",AQ76) | 2026-12-15 | 6.4 | 2027-06-28 | IF(W76<>"",W76,IF(OR(T76="",V76=""),"",EDATE(T76,V76))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.'- ¦ Farmer: Ghulam Haider Shah | IF(F76="","",IF(COUNT(AI76:AV76)=0,IF(AA76="","Not started",AA76),SUBSTITUTE(LOOKUP(2,1/(AI76:AV76<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F76="",COUNT(AI76:AV76)=0),"",TODAY()-LOOKUP(2,1/(AI76:AV76<>""),AI76:AV76)) | IF(OR(F76="",COUNT(AI76:AV76)<2),"",LOOKUP(2,1/(AI76:AV76<>""),AI76:AV76)-MIN(AI76:AV76)) | IF(OR(AD76="",AC76="Not started",AC76=""),"",IFERROR(AD76-IF(VLOOKUP(AC76,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC76,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F76="","",IF(OR(AA76="Cancelled",AC76="Cancelled"),"Cancelled",IF(OR(AC76="Completed / Handover",Y76<>"",Z76>=100),"Completed — on track",IF(O76="Not awarded",IF(U76="",IF(X76="","No planned date",IF(TODAY()>X76,"Behind — past planned date",IF(X76-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U76,"Behind — award date passed",IF(U76-TODAY()<=30,"At risk — close to off track","On track"))),IF(X76="","No planned date",IF(AND(TODAY()>X76,OR(Z76="",Z76<100)),"Behind — past end date",IF(AND(T76<>"",X76<>"",Z76<>"",(Z76<100),((TODAY()-T76)/MAX(X76-T76,1)*100)-Z76>15),"Behind — progress lag",IF(AND(X76-TODAY()<=30,X76-TODAY()>=0,OR(Z76="",Z76<90)),"At risk — close to off track","On track")))))))) | IF(OR(F76="",AC76="Completed / Handover",AC76="Cancelled"),"",IF(O76="Not awarded",IF(U76<>"",U76-TODAY(),IF(X76="","",X76-TODAY())),IF(X76="","",X76-TODAY()))) | [14 empty] | IF(OR(F76="",AJ76=""),"",IF(COUNT(AI76:AI76)=0,"",AJ76-LOOKUP(2,1/(AI76:AI76<>""),AI76:AI76))) | IF(OR(F76="",AK76=""),"",IF(COUNT(AI76:AJ76)=0,"",AK76-LOOKUP(2,1/(AI76:AJ76<>""),AI76:AJ76))) | IF(OR(F76="",AL76=""),"",IF(COUNT(AI76:AK76)=0,"",AL76-LOOKUP(2,1/(AI76:AK76<>""),AI76:AK76))) | IF(OR(F76="",AM76=""),"",IF(COUNT(AI76:AL76)=0,"",AM76-LOOKUP(2,1/(AI76:AL76<>""),AI76:AL76))) | IF(OR(F76="",AN76=""),"",IF(COUNT(AI76:AM76)=0,"",AN76-LOOKUP(2,1/(AI76:AM76<>""),AI76:AM76))) | IF(OR(F76="",AO76=""),"",IF(COUNT(AI76:AN76)=0,"",AO76-LOOKUP(2,1/(AI76:AN76<>""),AI76:AN76))) | IF(OR(F76="",AP76=""),"",IF(COUNT(AI76:AO76)=0,"",AP76-LOOKUP(2,1/(AI76:AO76<>""),AI76:AO76))) | IF(OR(F76="",AQ76=""),"",IF(COUNT(AI76:AP76)=0,"",AQ76-LOOKUP(2,1/(AI76:AP76<>""),AI76:AP76))) | IF(OR(F76="",AR76=""),"",IF(COUNT(AI76:AQ76)=0,"",AR76-LOOKUP(2,1/(AI76:AQ76<>""),AI76:AQ76))) | IF(OR(F76="",AS76=""),"",IF(COUNT(AI76:AR76)=0,"",AS76-LOOKUP(2,1/(AI76:AR76<>""),AI76:AR76))) | IF(OR(F76="",AT76=""),"",IF(COUNT(AI76:AS76)=0,"",AT76-LOOKUP(2,1/(AI76:AS76<>""),AI76:AS76))) | IF(OR(F76="",AU76=""),"",IF(COUNT(AI76:AT76)=0,"",AU76-LOOKUP(2,1/(AI76:AT76<>""),AI76:AT76))) | IF(OR(F76="",AV76=""),"",IF(COUNT(AI76:AU76)=0,"",AV76-LOOKUP(2,1/(AI76:AU76<>""),AI76:AU76))) | IF(J76="","All_Provinces",IFERROR(VLOOKUP(J76,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K76="","All_Districts",IFERROR(VLOOKUP(K76,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F77="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 9 of 14 | AF2-DIS-N-035 | Madad Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Chack | Madad | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Qasim |  | 4250 | IF(AQ77="","",AQ77) | 2026-12-25 | 6.3 | 2027-07-05 | IF(W77<>"",W77,IF(OR(T77="",V77=""),"",EDATE(T77,V77))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Mohammad Qasim | IF(F77="","",IF(COUNT(AI77:AV77)=0,IF(AA77="","Not started",AA77),SUBSTITUTE(LOOKUP(2,1/(AI77:AV77<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F77="",COUNT(AI77:AV77)=0),"",TODAY()-LOOKUP(2,1/(AI77:AV77<>""),AI77:AV77)) | IF(OR(F77="",COUNT(AI77:AV77)<2),"",LOOKUP(2,1/(AI77:AV77<>""),AI77:AV77)-MIN(AI77:AV77)) | IF(OR(AD77="",AC77="Not started",AC77=""),"",IFERROR(AD77-IF(VLOOKUP(AC77,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC77,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F77="","",IF(OR(AA77="Cancelled",AC77="Cancelled"),"Cancelled",IF(OR(AC77="Completed / Handover",Y77<>"",Z77>=100),"Completed — on track",IF(O77="Not awarded",IF(U77="",IF(X77="","No planned date",IF(TODAY()>X77,"Behind — past planned date",IF(X77-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U77,"Behind — award date passed",IF(U77-TODAY()<=30,"At risk — close to off track","On track"))),IF(X77="","No planned date",IF(AND(TODAY()>X77,OR(Z77="",Z77<100)),"Behind — past end date",IF(AND(T77<>"",X77<>"",Z77<>"",(Z77<100),((TODAY()-T77)/MAX(X77-T77,1)*100)-Z77>15),"Behind — progress lag",IF(AND(X77-TODAY()<=30,X77-TODAY()>=0,OR(Z77="",Z77<90)),"At risk — close to off track","On track")))))))) | IF(OR(F77="",AC77="Completed / Handover",AC77="Cancelled"),"",IF(O77="Not awarded",IF(U77<>"",U77-TODAY(),IF(X77="","",X77-TODAY())),IF(X77="","",X77-TODAY()))) | [14 empty] | IF(OR(F77="",AJ77=""),"",IF(COUNT(AI77:AI77)=0,"",AJ77-LOOKUP(2,1/(AI77:AI77<>""),AI77:AI77))) | IF(OR(F77="",AK77=""),"",IF(COUNT(AI77:AJ77)=0,"",AK77-LOOKUP(2,1/(AI77:AJ77<>""),AI77:AJ77))) | IF(OR(F77="",AL77=""),"",IF(COUNT(AI77:AK77)=0,"",AL77-LOOKUP(2,1/(AI77:AK77<>""),AI77:AK77))) | IF(OR(F77="",AM77=""),"",IF(COUNT(AI77:AL77)=0,"",AM77-LOOKUP(2,1/(AI77:AL77<>""),AI77:AL77))) | IF(OR(F77="",AN77=""),"",IF(COUNT(AI77:AM77)=0,"",AN77-LOOKUP(2,1/(AI77:AM77<>""),AI77:AM77))) | IF(OR(F77="",AO77=""),"",IF(COUNT(AI77:AN77)=0,"",AO77-LOOKUP(2,1/(AI77:AN77<>""),AI77:AN77))) | IF(OR(F77="",AP77=""),"",IF(COUNT(AI77:AO77)=0,"",AP77-LOOKUP(2,1/(AI77:AO77<>""),AI77:AO77))) | IF(OR(F77="",AQ77=""),"",IF(COUNT(AI77:AP77)=0,"",AQ77-LOOKUP(2,1/(AI77:AP77<>""),AI77:AP77))) | IF(OR(F77="",AR77=""),"",IF(COUNT(AI77:AQ77)=0,"",AR77-LOOKUP(2,1/(AI77:AQ77<>""),AI77:AQ77))) | IF(OR(F77="",AS77=""),"",IF(COUNT(AI77:AR77)=0,"",AS77-LOOKUP(2,1/(AI77:AR77<>""),AI77:AR77))) | IF(OR(F77="",AT77=""),"",IF(COUNT(AI77:AS77)=0,"",AT77-LOOKUP(2,1/(AI77:AS77<>""),AI77:AS77))) | IF(OR(F77="",AU77=""),"",IF(COUNT(AI77:AT77)=0,"",AU77-LOOKUP(2,1/(AI77:AT77<>""),AI77:AT77))) | IF(OR(F77="",AV77=""),"",IF(COUNT(AI77:AU77)=0,"",AV77-LOOKUP(2,1/(AI77:AU77<>""),AI77:AU77))) | IF(J77="","All_Provinces",IFERROR(VLOOKUP(J77,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K77="","All_Districts",IFERROR(VLOOKUP(K77,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F78="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 10 of 14 | AF2-DIS-N-036 | Nizam Khil Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Tagab | Nizam khil | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Najeebullah |  | 4250 | IF(AQ78="","",AQ78) | 2026-12-20 | 6.3 | 2027-06-30 | IF(W78<>"",W78,IF(OR(T78="",V78=""),"",EDATE(T78,V78))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.'''- ¦ Farmer: Najeebullah | IF(F78="","",IF(COUNT(AI78:AV78)=0,IF(AA78="","Not started",AA78),SUBSTITUTE(LOOKUP(2,1/(AI78:AV78<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F78="",COUNT(AI78:AV78)=0),"",TODAY()-LOOKUP(2,1/(AI78:AV78<>""),AI78:AV78)) | IF(OR(F78="",COUNT(AI78:AV78)<2),"",LOOKUP(2,1/(AI78:AV78<>""),AI78:AV78)-MIN(AI78:AV78)) | IF(OR(AD78="",AC78="Not started",AC78=""),"",IFERROR(AD78-IF(VLOOKUP(AC78,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC78,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F78="","",IF(OR(AA78="Cancelled",AC78="Cancelled"),"Cancelled",IF(OR(AC78="Completed / Handover",Y78<>"",Z78>=100),"Completed — on track",IF(O78="Not awarded",IF(U78="",IF(X78="","No planned date",IF(TODAY()>X78,"Behind — past planned date",IF(X78-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U78,"Behind — award date passed",IF(U78-TODAY()<=30,"At risk — close to off track","On track"))),IF(X78="","No planned date",IF(AND(TODAY()>X78,OR(Z78="",Z78<100)),"Behind — past end date",IF(AND(T78<>"",X78<>"",Z78<>"",(Z78<100),((TODAY()-T78)/MAX(X78-T78,1)*100)-Z78>15),"Behind — progress lag",IF(AND(X78-TODAY()<=30,X78-TODAY()>=0,OR(Z78="",Z78<90)),"At risk — close to off track","On track")))))))) | IF(OR(F78="",AC78="Completed / Handover",AC78="Cancelled"),"",IF(O78="Not awarded",IF(U78<>"",U78-TODAY(),IF(X78="","",X78-TODAY())),IF(X78="","",X78-TODAY()))) | [14 empty] | IF(OR(F78="",AJ78=""),"",IF(COUNT(AI78:AI78)=0,"",AJ78-LOOKUP(2,1/(AI78:AI78<>""),AI78:AI78))) | IF(OR(F78="",AK78=""),"",IF(COUNT(AI78:AJ78)=0,"",AK78-LOOKUP(2,1/(AI78:AJ78<>""),AI78:AJ78))) | IF(OR(F78="",AL78=""),"",IF(COUNT(AI78:AK78)=0,"",AL78-LOOKUP(2,1/(AI78:AK78<>""),AI78:AK78))) | IF(OR(F78="",AM78=""),"",IF(COUNT(AI78:AL78)=0,"",AM78-LOOKUP(2,1/(AI78:AL78<>""),AI78:AL78))) | IF(OR(F78="",AN78=""),"",IF(COUNT(AI78:AM78)=0,"",AN78-LOOKUP(2,1/(AI78:AM78<>""),AI78:AM78))) | IF(OR(F78="",AO78=""),"",IF(COUNT(AI78:AN78)=0,"",AO78-LOOKUP(2,1/(AI78:AN78<>""),AI78:AN78))) | IF(OR(F78="",AP78=""),"",IF(COUNT(AI78:AO78)=0,"",AP78-LOOKUP(2,1/(AI78:AO78<>""),AI78:AO78))) | IF(OR(F78="",AQ78=""),"",IF(COUNT(AI78:AP78)=0,"",AQ78-LOOKUP(2,1/(AI78:AP78<>""),AI78:AP78))) | IF(OR(F78="",AR78=""),"",IF(COUNT(AI78:AQ78)=0,"",AR78-LOOKUP(2,1/(AI78:AQ78<>""),AI78:AQ78))) | IF(OR(F78="",AS78=""),"",IF(COUNT(AI78:AR78)=0,"",AS78-LOOKUP(2,1/(AI78:AR78<>""),AI78:AR78))) | IF(OR(F78="",AT78=""),"",IF(COUNT(AI78:AS78)=0,"",AT78-LOOKUP(2,1/(AI78:AS78<>""),AI78:AS78))) | IF(OR(F78="",AU78=""),"",IF(COUNT(AI78:AT78)=0,"",AU78-LOOKUP(2,1/(AI78:AT78<>""),AI78:AT78))) | IF(OR(F78="",AV78=""),"",IF(COUNT(AI78:AU78)=0,"",AV78-LOOKUP(2,1/(AI78:AU78<>""),AI78:AU78))) | IF(J78="","All_Provinces",IFERROR(VLOOKUP(J78,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K78="","All_Districts",IFERROR(VLOOKUP(K78,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F79="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 11 of 14 | AF2-DIS-N-037 | Qafas Qala Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Khak-e-Jabar | Qafas Qala | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Jalal |  | 8500 | IF(AQ79="","",AQ79) | 2026-12-20 | 6.3 | 2027-06-30 | IF(W79<>"",W79,IF(OR(T79="",V79=""),"",EDATE(T79,V79))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Jalal | IF(F79="","",IF(COUNT(AI79:AV79)=0,IF(AA79="","Not started",AA79),SUBSTITUTE(LOOKUP(2,1/(AI79:AV79<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F79="",COUNT(AI79:AV79)=0),"",TODAY()-LOOKUP(2,1/(AI79:AV79<>""),AI79:AV79)) | IF(OR(F79="",COUNT(AI79:AV79)<2),"",LOOKUP(2,1/(AI79:AV79<>""),AI79:AV79)-MIN(AI79:AV79)) | IF(OR(AD79="",AC79="Not started",AC79=""),"",IFERROR(AD79-IF(VLOOKUP(AC79,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC79,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F79="","",IF(OR(AA79="Cancelled",AC79="Cancelled"),"Cancelled",IF(OR(AC79="Completed / Handover",Y79<>"",Z79>=100),"Completed — on track",IF(O79="Not awarded",IF(U79="",IF(X79="","No planned date",IF(TODAY()>X79,"Behind — past planned date",IF(X79-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U79,"Behind — award date passed",IF(U79-TODAY()<=30,"At risk — close to off track","On track"))),IF(X79="","No planned date",IF(AND(TODAY()>X79,OR(Z79="",Z79<100)),"Behind — past end date",IF(AND(T79<>"",X79<>"",Z79<>"",(Z79<100),((TODAY()-T79)/MAX(X79-T79,1)*100)-Z79>15),"Behind — progress lag",IF(AND(X79-TODAY()<=30,X79-TODAY()>=0,OR(Z79="",Z79<90)),"At risk — close to off track","On track")))))))) | IF(OR(F79="",AC79="Completed / Handover",AC79="Cancelled"),"",IF(O79="Not awarded",IF(U79<>"",U79-TODAY(),IF(X79="","",X79-TODAY())),IF(X79="","",X79-TODAY()))) | [14 empty] | IF(OR(F79="",AJ79=""),"",IF(COUNT(AI79:AI79)=0,"",AJ79-LOOKUP(2,1/(AI79:AI79<>""),AI79:AI79))) | IF(OR(F79="",AK79=""),"",IF(COUNT(AI79:AJ79)=0,"",AK79-LOOKUP(2,1/(AI79:AJ79<>""),AI79:AJ79))) | IF(OR(F79="",AL79=""),"",IF(COUNT(AI79:AK79)=0,"",AL79-LOOKUP(2,1/(AI79:AK79<>""),AI79:AK79))) | IF(OR(F79="",AM79=""),"",IF(COUNT(AI79:AL79)=0,"",AM79-LOOKUP(2,1/(AI79:AL79<>""),AI79:AL79))) | IF(OR(F79="",AN79=""),"",IF(COUNT(AI79:AM79)=0,"",AN79-LOOKUP(2,1/(AI79:AM79<>""),AI79:AM79))) | IF(OR(F79="",AO79=""),"",IF(COUNT(AI79:AN79)=0,"",AO79-LOOKUP(2,1/(AI79:AN79<>""),AI79:AN79))) | IF(OR(F79="",AP79=""),"",IF(COUNT(AI79:AO79)=0,"",AP79-LOOKUP(2,1/(AI79:AO79<>""),AI79:AO79))) | IF(OR(F79="",AQ79=""),"",IF(COUNT(AI79:AP79)=0,"",AQ79-LOOKUP(2,1/(AI79:AP79<>""),AI79:AP79))) | IF(OR(F79="",AR79=""),"",IF(COUNT(AI79:AQ79)=0,"",AR79-LOOKUP(2,1/(AI79:AQ79<>""),AI79:AQ79))) | IF(OR(F79="",AS79=""),"",IF(COUNT(AI79:AR79)=0,"",AS79-LOOKUP(2,1/(AI79:AR79<>""),AI79:AR79))) | IF(OR(F79="",AT79=""),"",IF(COUNT(AI79:AS79)=0,"",AT79-LOOKUP(2,1/(AI79:AS79<>""),AI79:AS79))) | IF(OR(F79="",AU79=""),"",IF(COUNT(AI79:AT79)=0,"",AU79-LOOKUP(2,1/(AI79:AT79<>""),AI79:AT79))) | IF(OR(F79="",AV79=""),"",IF(COUNT(AI79:AU79)=0,"",AV79-LOOKUP(2,1/(AI79:AU79<>""),AI79:AU79))) | IF(J79="","All_Provinces",IFERROR(VLOOKUP(J79,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K79="","All_Districts",IFERROR(VLOOKUP(K79,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F80="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 12 of 14 | AF2-DIS-N-038 | Qala-e- Nasro Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Parwan | Bagram | Qala-e- Nasro | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Waseem |  | 4250 | IF(AQ80="","",AQ80) | 2026-12-15 | 6.4 | 2027-06-28 | IF(W80<>"",W80,IF(OR(T80="",V80=""),"",EDATE(T80,V80))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.'- ¦ Farmer: Mohammad Waseem | IF(F80="","",IF(COUNT(AI80:AV80)=0,IF(AA80="","Not started",AA80),SUBSTITUTE(LOOKUP(2,1/(AI80:AV80<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F80="",COUNT(AI80:AV80)=0),"",TODAY()-LOOKUP(2,1/(AI80:AV80<>""),AI80:AV80)) | IF(OR(F80="",COUNT(AI80:AV80)<2),"",LOOKUP(2,1/(AI80:AV80<>""),AI80:AV80)-MIN(AI80:AV80)) | IF(OR(AD80="",AC80="Not started",AC80=""),"",IFERROR(AD80-IF(VLOOKUP(AC80,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC80,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F80="","",IF(OR(AA80="Cancelled",AC80="Cancelled"),"Cancelled",IF(OR(AC80="Completed / Handover",Y80<>"",Z80>=100),"Completed — on track",IF(O80="Not awarded",IF(U80="",IF(X80="","No planned date",IF(TODAY()>X80,"Behind — past planned date",IF(X80-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U80,"Behind — award date passed",IF(U80-TODAY()<=30,"At risk — close to off track","On track"))),IF(X80="","No planned date",IF(AND(TODAY()>X80,OR(Z80="",Z80<100)),"Behind — past end date",IF(AND(T80<>"",X80<>"",Z80<>"",(Z80<100),((TODAY()-T80)/MAX(X80-T80,1)*100)-Z80>15),"Behind — progress lag",IF(AND(X80-TODAY()<=30,X80-TODAY()>=0,OR(Z80="",Z80<90)),"At risk — close to off track","On track")))))))) | IF(OR(F80="",AC80="Completed / Handover",AC80="Cancelled"),"",IF(O80="Not awarded",IF(U80<>"",U80-TODAY(),IF(X80="","",X80-TODAY())),IF(X80="","",X80-TODAY()))) | [14 empty] | IF(OR(F80="",AJ80=""),"",IF(COUNT(AI80:AI80)=0,"",AJ80-LOOKUP(2,1/(AI80:AI80<>""),AI80:AI80))) | IF(OR(F80="",AK80=""),"",IF(COUNT(AI80:AJ80)=0,"",AK80-LOOKUP(2,1/(AI80:AJ80<>""),AI80:AJ80))) | IF(OR(F80="",AL80=""),"",IF(COUNT(AI80:AK80)=0,"",AL80-LOOKUP(2,1/(AI80:AK80<>""),AI80:AK80))) | IF(OR(F80="",AM80=""),"",IF(COUNT(AI80:AL80)=0,"",AM80-LOOKUP(2,1/(AI80:AL80<>""),AI80:AL80))) | IF(OR(F80="",AN80=""),"",IF(COUNT(AI80:AM80)=0,"",AN80-LOOKUP(2,1/(AI80:AM80<>""),AI80:AM80))) | IF(OR(F80="",AO80=""),"",IF(COUNT(AI80:AN80)=0,"",AO80-LOOKUP(2,1/(AI80:AN80<>""),AI80:AN80))) | IF(OR(F80="",AP80=""),"",IF(COUNT(AI80:AO80)=0,"",AP80-LOOKUP(2,1/(AI80:AO80<>""),AI80:AO80))) | IF(OR(F80="",AQ80=""),"",IF(COUNT(AI80:AP80)=0,"",AQ80-LOOKUP(2,1/(AI80:AP80<>""),AI80:AP80))) | IF(OR(F80="",AR80=""),"",IF(COUNT(AI80:AQ80)=0,"",AR80-LOOKUP(2,1/(AI80:AQ80<>""),AI80:AQ80))) | IF(OR(F80="",AS80=""),"",IF(COUNT(AI80:AR80)=0,"",AS80-LOOKUP(2,1/(AI80:AR80<>""),AI80:AR80))) | IF(OR(F80="",AT80=""),"",IF(COUNT(AI80:AS80)=0,"",AT80-LOOKUP(2,1/(AI80:AS80<>""),AI80:AS80))) | IF(OR(F80="",AU80=""),"",IF(COUNT(AI80:AT80)=0,"",AU80-LOOKUP(2,1/(AI80:AT80<>""),AI80:AT80))) | IF(OR(F80="",AV80=""),"",IF(COUNT(AI80:AU80)=0,"",AV80-LOOKUP(2,1/(AI80:AU80<>""),AI80:AU80))) | IF(J80="","All_Provinces",IFERROR(VLOOKUP(J80,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K80="","All_Districts",IFERROR(VLOOKUP(K80,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F81="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 13 of 14 | AF2-DIS-N-039 | Reg-e-Rawan Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Mahmood Raqi | Reg-e-Rawan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Reg-e-Rawa park |  | 8500 | IF(AQ81="","",AQ81) | 2026-12-20 | 6.3 | 2027-06-30 | IF(W81<>"",W81,IF(OR(T81="",V81=""),"",EDATE(T81,V81))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.'''- ¦ Farmer: Reg-e-Rawa park | IF(F81="","",IF(COUNT(AI81:AV81)=0,IF(AA81="","Not started",AA81),SUBSTITUTE(LOOKUP(2,1/(AI81:AV81<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F81="",COUNT(AI81:AV81)=0),"",TODAY()-LOOKUP(2,1/(AI81:AV81<>""),AI81:AV81)) | IF(OR(F81="",COUNT(AI81:AV81)<2),"",LOOKUP(2,1/(AI81:AV81<>""),AI81:AV81)-MIN(AI81:AV81)) | IF(OR(AD81="",AC81="Not started",AC81=""),"",IFERROR(AD81-IF(VLOOKUP(AC81,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC81,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F81="","",IF(OR(AA81="Cancelled",AC81="Cancelled"),"Cancelled",IF(OR(AC81="Completed / Handover",Y81<>"",Z81>=100),"Completed — on track",IF(O81="Not awarded",IF(U81="",IF(X81="","No planned date",IF(TODAY()>X81,"Behind — past planned date",IF(X81-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U81,"Behind — award date passed",IF(U81-TODAY()<=30,"At risk — close to off track","On track"))),IF(X81="","No planned date",IF(AND(TODAY()>X81,OR(Z81="",Z81<100)),"Behind — past end date",IF(AND(T81<>"",X81<>"",Z81<>"",(Z81<100),((TODAY()-T81)/MAX(X81-T81,1)*100)-Z81>15),"Behind — progress lag",IF(AND(X81-TODAY()<=30,X81-TODAY()>=0,OR(Z81="",Z81<90)),"At risk — close to off track","On track")))))))) | IF(OR(F81="",AC81="Completed / Handover",AC81="Cancelled"),"",IF(O81="Not awarded",IF(U81<>"",U81-TODAY(),IF(X81="","",X81-TODAY())),IF(X81="","",X81-TODAY()))) | [14 empty] | IF(OR(F81="",AJ81=""),"",IF(COUNT(AI81:AI81)=0,"",AJ81-LOOKUP(2,1/(AI81:AI81<>""),AI81:AI81))) | IF(OR(F81="",AK81=""),"",IF(COUNT(AI81:AJ81)=0,"",AK81-LOOKUP(2,1/(AI81:AJ81<>""),AI81:AJ81))) | IF(OR(F81="",AL81=""),"",IF(COUNT(AI81:AK81)=0,"",AL81-LOOKUP(2,1/(AI81:AK81<>""),AI81:AK81))) | IF(OR(F81="",AM81=""),"",IF(COUNT(AI81:AL81)=0,"",AM81-LOOKUP(2,1/(AI81:AL81<>""),AI81:AL81))) | IF(OR(F81="",AN81=""),"",IF(COUNT(AI81:AM81)=0,"",AN81-LOOKUP(2,1/(AI81:AM81<>""),AI81:AM81))) | IF(OR(F81="",AO81=""),"",IF(COUNT(AI81:AN81)=0,"",AO81-LOOKUP(2,1/(AI81:AN81<>""),AI81:AN81))) | IF(OR(F81="",AP81=""),"",IF(COUNT(AI81:AO81)=0,"",AP81-LOOKUP(2,1/(AI81:AO81<>""),AI81:AO81))) | IF(OR(F81="",AQ81=""),"",IF(COUNT(AI81:AP81)=0,"",AQ81-LOOKUP(2,1/(AI81:AP81<>""),AI81:AP81))) | IF(OR(F81="",AR81=""),"",IF(COUNT(AI81:AQ81)=0,"",AR81-LOOKUP(2,1/(AI81:AQ81<>""),AI81:AQ81))) | IF(OR(F81="",AS81=""),"",IF(COUNT(AI81:AR81)=0,"",AS81-LOOKUP(2,1/(AI81:AR81<>""),AI81:AR81))) | IF(OR(F81="",AT81=""),"",IF(COUNT(AI81:AS81)=0,"",AT81-LOOKUP(2,1/(AI81:AS81<>""),AI81:AS81))) | IF(OR(F81="",AU81=""),"",IF(COUNT(AI81:AT81)=0,"",AU81-LOOKUP(2,1/(AI81:AT81<>""),AI81:AT81))) | IF(OR(F81="",AV81=""),"",IF(COUNT(AI81:AU81)=0,"",AV81-LOOKUP(2,1/(AI81:AU81<>""),AI81:AU81))) | IF(J81="","All_Provinces",IFERROR(VLOOKUP(J81,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K81="","All_Districts",IFERROR(VLOOKUP(K81,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F82="","",ROW()-3) | AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | 14 of 14 | AF2-DIS-N-040 | Zar Shakh Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Paghman | Zar Shakh | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Khairullah Zia |  | 4250 | IF(AQ82="","",AQ82) | 2026-12-20 | 6.3 | 2027-06-30 | IF(W82<>"",W82,IF(OR(T82="",V82=""),"",EDATE(T82,V82))) |  |  | Retendered (Re-ITB) | Slack period from mid December to March 2026. Four months construction period.''- ¦ Farmer: Khairullah Zia | IF(F82="","",IF(COUNT(AI82:AV82)=0,IF(AA82="","Not started",AA82),SUBSTITUTE(LOOKUP(2,1/(AI82:AV82<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F82="",COUNT(AI82:AV82)=0),"",TODAY()-LOOKUP(2,1/(AI82:AV82<>""),AI82:AV82)) | IF(OR(F82="",COUNT(AI82:AV82)<2),"",LOOKUP(2,1/(AI82:AV82<>""),AI82:AV82)-MIN(AI82:AV82)) | IF(OR(AD82="",AC82="Not started",AC82=""),"",IFERROR(AD82-IF(VLOOKUP(AC82,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC82,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F82="","",IF(OR(AA82="Cancelled",AC82="Cancelled"),"Cancelled",IF(OR(AC82="Completed / Handover",Y82<>"",Z82>=100),"Completed — on track",IF(O82="Not awarded",IF(U82="",IF(X82="","No planned date",IF(TODAY()>X82,"Behind — past planned date",IF(X82-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U82,"Behind — award date passed",IF(U82-TODAY()<=30,"At risk — close to off track","On track"))),IF(X82="","No planned date",IF(AND(TODAY()>X82,OR(Z82="",Z82<100)),"Behind — past end date",IF(AND(T82<>"",X82<>"",Z82<>"",(Z82<100),((TODAY()-T82)/MAX(X82-T82,1)*100)-Z82>15),"Behind — progress lag",IF(AND(X82-TODAY()<=30,X82-TODAY()>=0,OR(Z82="",Z82<90)),"At risk — close to off track","On track")))))))) | IF(OR(F82="",AC82="Completed / Handover",AC82="Cancelled"),"",IF(O82="Not awarded",IF(U82<>"",U82-TODAY(),IF(X82="","",X82-TODAY())),IF(X82="","",X82-TODAY()))) | [14 empty] | IF(OR(F82="",AJ82=""),"",IF(COUNT(AI82:AI82)=0,"",AJ82-LOOKUP(2,1/(AI82:AI82<>""),AI82:AI82))) | IF(OR(F82="",AK82=""),"",IF(COUNT(AI82:AJ82)=0,"",AK82-LOOKUP(2,1/(AI82:AJ82<>""),AI82:AJ82))) | IF(OR(F82="",AL82=""),"",IF(COUNT(AI82:AK82)=0,"",AL82-LOOKUP(2,1/(AI82:AK82<>""),AI82:AK82))) | IF(OR(F82="",AM82=""),"",IF(COUNT(AI82:AL82)=0,"",AM82-LOOKUP(2,1/(AI82:AL82<>""),AI82:AL82))) | IF(OR(F82="",AN82=""),"",IF(COUNT(AI82:AM82)=0,"",AN82-LOOKUP(2,1/(AI82:AM82<>""),AI82:AM82))) | IF(OR(F82="",AO82=""),"",IF(COUNT(AI82:AN82)=0,"",AO82-LOOKUP(2,1/(AI82:AN82<>""),AI82:AN82))) | IF(OR(F82="",AP82=""),"",IF(COUNT(AI82:AO82)=0,"",AP82-LOOKUP(2,1/(AI82:AO82<>""),AI82:AO82))) | IF(OR(F82="",AQ82=""),"",IF(COUNT(AI82:AP82)=0,"",AQ82-LOOKUP(2,1/(AI82:AP82<>""),AI82:AP82))) | IF(OR(F82="",AR82=""),"",IF(COUNT(AI82:AQ82)=0,"",AR82-LOOKUP(2,1/(AI82:AQ82<>""),AI82:AQ82))) | IF(OR(F82="",AS82=""),"",IF(COUNT(AI82:AR82)=0,"",AS82-LOOKUP(2,1/(AI82:AR82<>""),AI82:AR82))) | IF(OR(F82="",AT82=""),"",IF(COUNT(AI82:AS82)=0,"",AT82-LOOKUP(2,1/(AI82:AS82<>""),AI82:AS82))) | IF(OR(F82="",AU82=""),"",IF(COUNT(AI82:AT82)=0,"",AU82-LOOKUP(2,1/(AI82:AT82<>""),AI82:AT82))) | IF(OR(F82="",AV82=""),"",IF(COUNT(AI82:AU82)=0,"",AV82-LOOKUP(2,1/(AI82:AU82<>""),AI82:AU82))) | IF(J82="","All_Provinces",IFERROR(VLOOKUP(J82,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K82="","All_Districts",IFERROR(VLOOKUP(K82,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F83="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 1 of 12 | AF2-DIS-N-041 | Bagh Drip Irrigation System | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Miramor | Bagh | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ghulam |  | 3300.86 | IF(AQ83="","",AQ83) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W83<>"",W83,IF(OR(T83="",V83=""),"",EDATE(T83,V83))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Ghulam | IF(F83="","",IF(COUNT(AI83:AV83)=0,IF(AA83="","Not started",AA83),SUBSTITUTE(LOOKUP(2,1/(AI83:AV83<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F83="",COUNT(AI83:AV83)=0),"",TODAY()-LOOKUP(2,1/(AI83:AV83<>""),AI83:AV83)) | IF(OR(F83="",COUNT(AI83:AV83)<2),"",LOOKUP(2,1/(AI83:AV83<>""),AI83:AV83)-MIN(AI83:AV83)) | IF(OR(AD83="",AC83="Not started",AC83=""),"",IFERROR(AD83-IF(VLOOKUP(AC83,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC83,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F83="","",IF(OR(AA83="Cancelled",AC83="Cancelled"),"Cancelled",IF(OR(AC83="Completed / Handover",Y83<>"",Z83>=100),"Completed — on track",IF(O83="Not awarded",IF(U83="",IF(X83="","No planned date",IF(TODAY()>X83,"Behind — past planned date",IF(X83-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U83,"Behind — award date passed",IF(U83-TODAY()<=30,"At risk — close to off track","On track"))),IF(X83="","No planned date",IF(AND(TODAY()>X83,OR(Z83="",Z83<100)),"Behind — past end date",IF(AND(T83<>"",X83<>"",Z83<>"",(Z83<100),((TODAY()-T83)/MAX(X83-T83,1)*100)-Z83>15),"Behind — progress lag",IF(AND(X83-TODAY()<=30,X83-TODAY()>=0,OR(Z83="",Z83<90)),"At risk — close to off track","On track")))))))) | IF(OR(F83="",AC83="Completed / Handover",AC83="Cancelled"),"",IF(O83="Not awarded",IF(U83<>"",U83-TODAY(),IF(X83="","",X83-TODAY())),IF(X83="","",X83-TODAY()))) | [14 empty] | IF(OR(F83="",AJ83=""),"",IF(COUNT(AI83:AI83)=0,"",AJ83-LOOKUP(2,1/(AI83:AI83<>""),AI83:AI83))) | IF(OR(F83="",AK83=""),"",IF(COUNT(AI83:AJ83)=0,"",AK83-LOOKUP(2,1/(AI83:AJ83<>""),AI83:AJ83))) | IF(OR(F83="",AL83=""),"",IF(COUNT(AI83:AK83)=0,"",AL83-LOOKUP(2,1/(AI83:AK83<>""),AI83:AK83))) | IF(OR(F83="",AM83=""),"",IF(COUNT(AI83:AL83)=0,"",AM83-LOOKUP(2,1/(AI83:AL83<>""),AI83:AL83))) | IF(OR(F83="",AN83=""),"",IF(COUNT(AI83:AM83)=0,"",AN83-LOOKUP(2,1/(AI83:AM83<>""),AI83:AM83))) | IF(OR(F83="",AO83=""),"",IF(COUNT(AI83:AN83)=0,"",AO83-LOOKUP(2,1/(AI83:AN83<>""),AI83:AN83))) | IF(OR(F83="",AP83=""),"",IF(COUNT(AI83:AO83)=0,"",AP83-LOOKUP(2,1/(AI83:AO83<>""),AI83:AO83))) | IF(OR(F83="",AQ83=""),"",IF(COUNT(AI83:AP83)=0,"",AQ83-LOOKUP(2,1/(AI83:AP83<>""),AI83:AP83))) | IF(OR(F83="",AR83=""),"",IF(COUNT(AI83:AQ83)=0,"",AR83-LOOKUP(2,1/(AI83:AQ83<>""),AI83:AQ83))) | IF(OR(F83="",AS83=""),"",IF(COUNT(AI83:AR83)=0,"",AS83-LOOKUP(2,1/(AI83:AR83<>""),AI83:AR83))) | IF(OR(F83="",AT83=""),"",IF(COUNT(AI83:AS83)=0,"",AT83-LOOKUP(2,1/(AI83:AS83<>""),AI83:AS83))) | IF(OR(F83="",AU83=""),"",IF(COUNT(AI83:AT83)=0,"",AU83-LOOKUP(2,1/(AI83:AT83<>""),AI83:AT83))) | IF(OR(F83="",AV83=""),"",IF(COUNT(AI83:AU83)=0,"",AV83-LOOKUP(2,1/(AI83:AU83<>""),AI83:AU83))) | IF(J83="","All_Provinces",IFERROR(VLOOKUP(J83,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K83="","All_Districts",IFERROR(VLOOKUP(K83,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F84="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 2 of 12 | AF2-DIS-N-042 | Deraw drip Irrigation Systen | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Miramor | Deraw | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Arif |  | 6011.99 | IF(AQ84="","",AQ84) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W84<>"",W84,IF(OR(T84="",V84=""),"",EDATE(T84,V84))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Mohammad Arif | IF(F84="","",IF(COUNT(AI84:AV84)=0,IF(AA84="","Not started",AA84),SUBSTITUTE(LOOKUP(2,1/(AI84:AV84<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F84="",COUNT(AI84:AV84)=0),"",TODAY()-LOOKUP(2,1/(AI84:AV84<>""),AI84:AV84)) | IF(OR(F84="",COUNT(AI84:AV84)<2),"",LOOKUP(2,1/(AI84:AV84<>""),AI84:AV84)-MIN(AI84:AV84)) | IF(OR(AD84="",AC84="Not started",AC84=""),"",IFERROR(AD84-IF(VLOOKUP(AC84,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC84,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F84="","",IF(OR(AA84="Cancelled",AC84="Cancelled"),"Cancelled",IF(OR(AC84="Completed / Handover",Y84<>"",Z84>=100),"Completed — on track",IF(O84="Not awarded",IF(U84="",IF(X84="","No planned date",IF(TODAY()>X84,"Behind — past planned date",IF(X84-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U84,"Behind — award date passed",IF(U84-TODAY()<=30,"At risk — close to off track","On track"))),IF(X84="","No planned date",IF(AND(TODAY()>X84,OR(Z84="",Z84<100)),"Behind — past end date",IF(AND(T84<>"",X84<>"",Z84<>"",(Z84<100),((TODAY()-T84)/MAX(X84-T84,1)*100)-Z84>15),"Behind — progress lag",IF(AND(X84-TODAY()<=30,X84-TODAY()>=0,OR(Z84="",Z84<90)),"At risk — close to off track","On track")))))))) | IF(OR(F84="",AC84="Completed / Handover",AC84="Cancelled"),"",IF(O84="Not awarded",IF(U84<>"",U84-TODAY(),IF(X84="","",X84-TODAY())),IF(X84="","",X84-TODAY()))) | [14 empty] | IF(OR(F84="",AJ84=""),"",IF(COUNT(AI84:AI84)=0,"",AJ84-LOOKUP(2,1/(AI84:AI84<>""),AI84:AI84))) | IF(OR(F84="",AK84=""),"",IF(COUNT(AI84:AJ84)=0,"",AK84-LOOKUP(2,1/(AI84:AJ84<>""),AI84:AJ84))) | IF(OR(F84="",AL84=""),"",IF(COUNT(AI84:AK84)=0,"",AL84-LOOKUP(2,1/(AI84:AK84<>""),AI84:AK84))) | IF(OR(F84="",AM84=""),"",IF(COUNT(AI84:AL84)=0,"",AM84-LOOKUP(2,1/(AI84:AL84<>""),AI84:AL84))) | IF(OR(F84="",AN84=""),"",IF(COUNT(AI84:AM84)=0,"",AN84-LOOKUP(2,1/(AI84:AM84<>""),AI84:AM84))) | IF(OR(F84="",AO84=""),"",IF(COUNT(AI84:AN84)=0,"",AO84-LOOKUP(2,1/(AI84:AN84<>""),AI84:AN84))) | IF(OR(F84="",AP84=""),"",IF(COUNT(AI84:AO84)=0,"",AP84-LOOKUP(2,1/(AI84:AO84<>""),AI84:AO84))) | IF(OR(F84="",AQ84=""),"",IF(COUNT(AI84:AP84)=0,"",AQ84-LOOKUP(2,1/(AI84:AP84<>""),AI84:AP84))) | IF(OR(F84="",AR84=""),"",IF(COUNT(AI84:AQ84)=0,"",AR84-LOOKUP(2,1/(AI84:AQ84<>""),AI84:AQ84))) | IF(OR(F84="",AS84=""),"",IF(COUNT(AI84:AR84)=0,"",AS84-LOOKUP(2,1/(AI84:AR84<>""),AI84:AR84))) | IF(OR(F84="",AT84=""),"",IF(COUNT(AI84:AS84)=0,"",AT84-LOOKUP(2,1/(AI84:AS84<>""),AI84:AS84))) | IF(OR(F84="",AU84=""),"",IF(COUNT(AI84:AT84)=0,"",AU84-LOOKUP(2,1/(AI84:AT84<>""),AI84:AT84))) | IF(OR(F84="",AV84=""),"",IF(COUNT(AI84:AU84)=0,"",AV84-LOOKUP(2,1/(AI84:AU84<>""),AI84:AU84))) | IF(J84="","All_Provinces",IFERROR(VLOOKUP(J84,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K84="","All_Districts",IFERROR(VLOOKUP(K84,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F85="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 3 of 12 | AF2-DIS-N-043 | Ghaf Drip Irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Shahristan | Ghaf | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Ibrahim |  | 5880.43 | IF(AQ85="","",AQ85) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W85<>"",W85,IF(OR(T85="",V85=""),"",EDATE(T85,V85))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Mohammad Ibrahim | IF(F85="","",IF(COUNT(AI85:AV85)=0,IF(AA85="","Not started",AA85),SUBSTITUTE(LOOKUP(2,1/(AI85:AV85<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F85="",COUNT(AI85:AV85)=0),"",TODAY()-LOOKUP(2,1/(AI85:AV85<>""),AI85:AV85)) | IF(OR(F85="",COUNT(AI85:AV85)<2),"",LOOKUP(2,1/(AI85:AV85<>""),AI85:AV85)-MIN(AI85:AV85)) | IF(OR(AD85="",AC85="Not started",AC85=""),"",IFERROR(AD85-IF(VLOOKUP(AC85,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC85,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F85="","",IF(OR(AA85="Cancelled",AC85="Cancelled"),"Cancelled",IF(OR(AC85="Completed / Handover",Y85<>"",Z85>=100),"Completed — on track",IF(O85="Not awarded",IF(U85="",IF(X85="","No planned date",IF(TODAY()>X85,"Behind — past planned date",IF(X85-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U85,"Behind — award date passed",IF(U85-TODAY()<=30,"At risk — close to off track","On track"))),IF(X85="","No planned date",IF(AND(TODAY()>X85,OR(Z85="",Z85<100)),"Behind — past end date",IF(AND(T85<>"",X85<>"",Z85<>"",(Z85<100),((TODAY()-T85)/MAX(X85-T85,1)*100)-Z85>15),"Behind — progress lag",IF(AND(X85-TODAY()<=30,X85-TODAY()>=0,OR(Z85="",Z85<90)),"At risk — close to off track","On track")))))))) | IF(OR(F85="",AC85="Completed / Handover",AC85="Cancelled"),"",IF(O85="Not awarded",IF(U85<>"",U85-TODAY(),IF(X85="","",X85-TODAY())),IF(X85="","",X85-TODAY()))) | [14 empty] | IF(OR(F85="",AJ85=""),"",IF(COUNT(AI85:AI85)=0,"",AJ85-LOOKUP(2,1/(AI85:AI85<>""),AI85:AI85))) | IF(OR(F85="",AK85=""),"",IF(COUNT(AI85:AJ85)=0,"",AK85-LOOKUP(2,1/(AI85:AJ85<>""),AI85:AJ85))) | IF(OR(F85="",AL85=""),"",IF(COUNT(AI85:AK85)=0,"",AL85-LOOKUP(2,1/(AI85:AK85<>""),AI85:AK85))) | IF(OR(F85="",AM85=""),"",IF(COUNT(AI85:AL85)=0,"",AM85-LOOKUP(2,1/(AI85:AL85<>""),AI85:AL85))) | IF(OR(F85="",AN85=""),"",IF(COUNT(AI85:AM85)=0,"",AN85-LOOKUP(2,1/(AI85:AM85<>""),AI85:AM85))) | IF(OR(F85="",AO85=""),"",IF(COUNT(AI85:AN85)=0,"",AO85-LOOKUP(2,1/(AI85:AN85<>""),AI85:AN85))) | IF(OR(F85="",AP85=""),"",IF(COUNT(AI85:AO85)=0,"",AP85-LOOKUP(2,1/(AI85:AO85<>""),AI85:AO85))) | IF(OR(F85="",AQ85=""),"",IF(COUNT(AI85:AP85)=0,"",AQ85-LOOKUP(2,1/(AI85:AP85<>""),AI85:AP85))) | IF(OR(F85="",AR85=""),"",IF(COUNT(AI85:AQ85)=0,"",AR85-LOOKUP(2,1/(AI85:AQ85<>""),AI85:AQ85))) | IF(OR(F85="",AS85=""),"",IF(COUNT(AI85:AR85)=0,"",AS85-LOOKUP(2,1/(AI85:AR85<>""),AI85:AR85))) | IF(OR(F85="",AT85=""),"",IF(COUNT(AI85:AS85)=0,"",AT85-LOOKUP(2,1/(AI85:AS85<>""),AI85:AS85))) | IF(OR(F85="",AU85=""),"",IF(COUNT(AI85:AT85)=0,"",AU85-LOOKUP(2,1/(AI85:AT85<>""),AI85:AT85))) | IF(OR(F85="",AV85=""),"",IF(COUNT(AI85:AU85)=0,"",AV85-LOOKUP(2,1/(AI85:AU85<>""),AI85:AU85))) | IF(J85="","All_Provinces",IFERROR(VLOOKUP(J85,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K85="","All_Districts",IFERROR(VLOOKUP(K85,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F86="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 4 of 12 | AF2-DIS-N-044 | Gorg Kosht Drip Irrigation system | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi |  | Gorg Koshta | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ahmad |  | 3484.2 | IF(AQ86="","",AQ86) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W86<>"",W86,IF(OR(T86="",V86=""),"",EDATE(T86,V86))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Ahmad | IF(F86="","",IF(COUNT(AI86:AV86)=0,IF(AA86="","Not started",AA86),SUBSTITUTE(LOOKUP(2,1/(AI86:AV86<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F86="",COUNT(AI86:AV86)=0),"",TODAY()-LOOKUP(2,1/(AI86:AV86<>""),AI86:AV86)) | IF(OR(F86="",COUNT(AI86:AV86)<2),"",LOOKUP(2,1/(AI86:AV86<>""),AI86:AV86)-MIN(AI86:AV86)) | IF(OR(AD86="",AC86="Not started",AC86=""),"",IFERROR(AD86-IF(VLOOKUP(AC86,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC86,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F86="","",IF(OR(AA86="Cancelled",AC86="Cancelled"),"Cancelled",IF(OR(AC86="Completed / Handover",Y86<>"",Z86>=100),"Completed — on track",IF(O86="Not awarded",IF(U86="",IF(X86="","No planned date",IF(TODAY()>X86,"Behind — past planned date",IF(X86-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U86,"Behind — award date passed",IF(U86-TODAY()<=30,"At risk — close to off track","On track"))),IF(X86="","No planned date",IF(AND(TODAY()>X86,OR(Z86="",Z86<100)),"Behind — past end date",IF(AND(T86<>"",X86<>"",Z86<>"",(Z86<100),((TODAY()-T86)/MAX(X86-T86,1)*100)-Z86>15),"Behind — progress lag",IF(AND(X86-TODAY()<=30,X86-TODAY()>=0,OR(Z86="",Z86<90)),"At risk — close to off track","On track")))))))) | IF(OR(F86="",AC86="Completed / Handover",AC86="Cancelled"),"",IF(O86="Not awarded",IF(U86<>"",U86-TODAY(),IF(X86="","",X86-TODAY())),IF(X86="","",X86-TODAY()))) | [14 empty] | IF(OR(F86="",AJ86=""),"",IF(COUNT(AI86:AI86)=0,"",AJ86-LOOKUP(2,1/(AI86:AI86<>""),AI86:AI86))) | IF(OR(F86="",AK86=""),"",IF(COUNT(AI86:AJ86)=0,"",AK86-LOOKUP(2,1/(AI86:AJ86<>""),AI86:AJ86))) | IF(OR(F86="",AL86=""),"",IF(COUNT(AI86:AK86)=0,"",AL86-LOOKUP(2,1/(AI86:AK86<>""),AI86:AK86))) | IF(OR(F86="",AM86=""),"",IF(COUNT(AI86:AL86)=0,"",AM86-LOOKUP(2,1/(AI86:AL86<>""),AI86:AL86))) | IF(OR(F86="",AN86=""),"",IF(COUNT(AI86:AM86)=0,"",AN86-LOOKUP(2,1/(AI86:AM86<>""),AI86:AM86))) | IF(OR(F86="",AO86=""),"",IF(COUNT(AI86:AN86)=0,"",AO86-LOOKUP(2,1/(AI86:AN86<>""),AI86:AN86))) | IF(OR(F86="",AP86=""),"",IF(COUNT(AI86:AO86)=0,"",AP86-LOOKUP(2,1/(AI86:AO86<>""),AI86:AO86))) | IF(OR(F86="",AQ86=""),"",IF(COUNT(AI86:AP86)=0,"",AQ86-LOOKUP(2,1/(AI86:AP86<>""),AI86:AP86))) | IF(OR(F86="",AR86=""),"",IF(COUNT(AI86:AQ86)=0,"",AR86-LOOKUP(2,1/(AI86:AQ86<>""),AI86:AQ86))) | IF(OR(F86="",AS86=""),"",IF(COUNT(AI86:AR86)=0,"",AS86-LOOKUP(2,1/(AI86:AR86<>""),AI86:AR86))) | IF(OR(F86="",AT86=""),"",IF(COUNT(AI86:AS86)=0,"",AT86-LOOKUP(2,1/(AI86:AS86<>""),AI86:AS86))) | IF(OR(F86="",AU86=""),"",IF(COUNT(AI86:AT86)=0,"",AU86-LOOKUP(2,1/(AI86:AT86<>""),AI86:AT86))) | IF(OR(F86="",AV86=""),"",IF(COUNT(AI86:AU86)=0,"",AV86-LOOKUP(2,1/(AI86:AU86<>""),AI86:AU86))) | IF(J86="","All_Provinces",IFERROR(VLOOKUP(J86,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K86="","All_Districts",IFERROR(VLOOKUP(K86,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F87="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 5 of 12 | AF2-DIS-N-045 | Hejdi Drip irrigatio System | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi |  | Hijdi | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Ali |  | 4425.06 | IF(AQ87="","",AQ87) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W87<>"",W87,IF(OR(T87="",V87=""),"",EDATE(T87,V87))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Mohammad Ali | IF(F87="","",IF(COUNT(AI87:AV87)=0,IF(AA87="","Not started",AA87),SUBSTITUTE(LOOKUP(2,1/(AI87:AV87<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F87="",COUNT(AI87:AV87)=0),"",TODAY()-LOOKUP(2,1/(AI87:AV87<>""),AI87:AV87)) | IF(OR(F87="",COUNT(AI87:AV87)<2),"",LOOKUP(2,1/(AI87:AV87<>""),AI87:AV87)-MIN(AI87:AV87)) | IF(OR(AD87="",AC87="Not started",AC87=""),"",IFERROR(AD87-IF(VLOOKUP(AC87,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC87,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F87="","",IF(OR(AA87="Cancelled",AC87="Cancelled"),"Cancelled",IF(OR(AC87="Completed / Handover",Y87<>"",Z87>=100),"Completed — on track",IF(O87="Not awarded",IF(U87="",IF(X87="","No planned date",IF(TODAY()>X87,"Behind — past planned date",IF(X87-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U87,"Behind — award date passed",IF(U87-TODAY()<=30,"At risk — close to off track","On track"))),IF(X87="","No planned date",IF(AND(TODAY()>X87,OR(Z87="",Z87<100)),"Behind — past end date",IF(AND(T87<>"",X87<>"",Z87<>"",(Z87<100),((TODAY()-T87)/MAX(X87-T87,1)*100)-Z87>15),"Behind — progress lag",IF(AND(X87-TODAY()<=30,X87-TODAY()>=0,OR(Z87="",Z87<90)),"At risk — close to off track","On track")))))))) | IF(OR(F87="",AC87="Completed / Handover",AC87="Cancelled"),"",IF(O87="Not awarded",IF(U87<>"",U87-TODAY(),IF(X87="","",X87-TODAY())),IF(X87="","",X87-TODAY()))) | [14 empty] | IF(OR(F87="",AJ87=""),"",IF(COUNT(AI87:AI87)=0,"",AJ87-LOOKUP(2,1/(AI87:AI87<>""),AI87:AI87))) | IF(OR(F87="",AK87=""),"",IF(COUNT(AI87:AJ87)=0,"",AK87-LOOKUP(2,1/(AI87:AJ87<>""),AI87:AJ87))) | IF(OR(F87="",AL87=""),"",IF(COUNT(AI87:AK87)=0,"",AL87-LOOKUP(2,1/(AI87:AK87<>""),AI87:AK87))) | IF(OR(F87="",AM87=""),"",IF(COUNT(AI87:AL87)=0,"",AM87-LOOKUP(2,1/(AI87:AL87<>""),AI87:AL87))) | IF(OR(F87="",AN87=""),"",IF(COUNT(AI87:AM87)=0,"",AN87-LOOKUP(2,1/(AI87:AM87<>""),AI87:AM87))) | IF(OR(F87="",AO87=""),"",IF(COUNT(AI87:AN87)=0,"",AO87-LOOKUP(2,1/(AI87:AN87<>""),AI87:AN87))) | IF(OR(F87="",AP87=""),"",IF(COUNT(AI87:AO87)=0,"",AP87-LOOKUP(2,1/(AI87:AO87<>""),AI87:AO87))) | IF(OR(F87="",AQ87=""),"",IF(COUNT(AI87:AP87)=0,"",AQ87-LOOKUP(2,1/(AI87:AP87<>""),AI87:AP87))) | IF(OR(F87="",AR87=""),"",IF(COUNT(AI87:AQ87)=0,"",AR87-LOOKUP(2,1/(AI87:AQ87<>""),AI87:AQ87))) | IF(OR(F87="",AS87=""),"",IF(COUNT(AI87:AR87)=0,"",AS87-LOOKUP(2,1/(AI87:AR87<>""),AI87:AR87))) | IF(OR(F87="",AT87=""),"",IF(COUNT(AI87:AS87)=0,"",AT87-LOOKUP(2,1/(AI87:AS87<>""),AI87:AS87))) | IF(OR(F87="",AU87=""),"",IF(COUNT(AI87:AT87)=0,"",AU87-LOOKUP(2,1/(AI87:AT87<>""),AI87:AT87))) | IF(OR(F87="",AV87=""),"",IF(COUNT(AI87:AU87)=0,"",AV87-LOOKUP(2,1/(AI87:AU87<>""),AI87:AU87))) | IF(J87="","All_Provinces",IFERROR(VLOOKUP(J87,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K87="","All_Districts",IFERROR(VLOOKUP(K87,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F88="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 6 of 12 | AF2-DIS-N-046 | Khawalak Drip irrigatio SYSTEM | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi |  | Khawalak | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ali Dost |  | 3573.45 | IF(AQ88="","",AQ88) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W88<>"",W88,IF(OR(T88="",V88=""),"",EDATE(T88,V88))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Ali Dost | IF(F88="","",IF(COUNT(AI88:AV88)=0,IF(AA88="","Not started",AA88),SUBSTITUTE(LOOKUP(2,1/(AI88:AV88<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F88="",COUNT(AI88:AV88)=0),"",TODAY()-LOOKUP(2,1/(AI88:AV88<>""),AI88:AV88)) | IF(OR(F88="",COUNT(AI88:AV88)<2),"",LOOKUP(2,1/(AI88:AV88<>""),AI88:AV88)-MIN(AI88:AV88)) | IF(OR(AD88="",AC88="Not started",AC88=""),"",IFERROR(AD88-IF(VLOOKUP(AC88,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC88,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F88="","",IF(OR(AA88="Cancelled",AC88="Cancelled"),"Cancelled",IF(OR(AC88="Completed / Handover",Y88<>"",Z88>=100),"Completed — on track",IF(O88="Not awarded",IF(U88="",IF(X88="","No planned date",IF(TODAY()>X88,"Behind — past planned date",IF(X88-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U88,"Behind — award date passed",IF(U88-TODAY()<=30,"At risk — close to off track","On track"))),IF(X88="","No planned date",IF(AND(TODAY()>X88,OR(Z88="",Z88<100)),"Behind — past end date",IF(AND(T88<>"",X88<>"",Z88<>"",(Z88<100),((TODAY()-T88)/MAX(X88-T88,1)*100)-Z88>15),"Behind — progress lag",IF(AND(X88-TODAY()<=30,X88-TODAY()>=0,OR(Z88="",Z88<90)),"At risk — close to off track","On track")))))))) | IF(OR(F88="",AC88="Completed / Handover",AC88="Cancelled"),"",IF(O88="Not awarded",IF(U88<>"",U88-TODAY(),IF(X88="","",X88-TODAY())),IF(X88="","",X88-TODAY()))) | [14 empty] | IF(OR(F88="",AJ88=""),"",IF(COUNT(AI88:AI88)=0,"",AJ88-LOOKUP(2,1/(AI88:AI88<>""),AI88:AI88))) | IF(OR(F88="",AK88=""),"",IF(COUNT(AI88:AJ88)=0,"",AK88-LOOKUP(2,1/(AI88:AJ88<>""),AI88:AJ88))) | IF(OR(F88="",AL88=""),"",IF(COUNT(AI88:AK88)=0,"",AL88-LOOKUP(2,1/(AI88:AK88<>""),AI88:AK88))) | IF(OR(F88="",AM88=""),"",IF(COUNT(AI88:AL88)=0,"",AM88-LOOKUP(2,1/(AI88:AL88<>""),AI88:AL88))) | IF(OR(F88="",AN88=""),"",IF(COUNT(AI88:AM88)=0,"",AN88-LOOKUP(2,1/(AI88:AM88<>""),AI88:AM88))) | IF(OR(F88="",AO88=""),"",IF(COUNT(AI88:AN88)=0,"",AO88-LOOKUP(2,1/(AI88:AN88<>""),AI88:AN88))) | IF(OR(F88="",AP88=""),"",IF(COUNT(AI88:AO88)=0,"",AP88-LOOKUP(2,1/(AI88:AO88<>""),AI88:AO88))) | IF(OR(F88="",AQ88=""),"",IF(COUNT(AI88:AP88)=0,"",AQ88-LOOKUP(2,1/(AI88:AP88<>""),AI88:AP88))) | IF(OR(F88="",AR88=""),"",IF(COUNT(AI88:AQ88)=0,"",AR88-LOOKUP(2,1/(AI88:AQ88<>""),AI88:AQ88))) | IF(OR(F88="",AS88=""),"",IF(COUNT(AI88:AR88)=0,"",AS88-LOOKUP(2,1/(AI88:AR88<>""),AI88:AR88))) | IF(OR(F88="",AT88=""),"",IF(COUNT(AI88:AS88)=0,"",AT88-LOOKUP(2,1/(AI88:AS88<>""),AI88:AS88))) | IF(OR(F88="",AU88=""),"",IF(COUNT(AI88:AT88)=0,"",AU88-LOOKUP(2,1/(AI88:AT88<>""),AI88:AT88))) | IF(OR(F88="",AV88=""),"",IF(COUNT(AI88:AU88)=0,"",AV88-LOOKUP(2,1/(AI88:AU88<>""),AI88:AU88))) | IF(J88="","All_Provinces",IFERROR(VLOOKUP(J88,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K88="","All_Districts",IFERROR(VLOOKUP(K88,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F89="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 7 of 12 | AF2-DIS-N-047 | Khawja Chast )Drip irrigation Sysytem | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Shahristan | Khwaja Chasht | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Hashim |  | 5364.63 | IF(AQ89="","",AQ89) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W89<>"",W89,IF(OR(T89="",V89=""),"",EDATE(T89,V89))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Mohammad Hashim | IF(F89="","",IF(COUNT(AI89:AV89)=0,IF(AA89="","Not started",AA89),SUBSTITUTE(LOOKUP(2,1/(AI89:AV89<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F89="",COUNT(AI89:AV89)=0),"",TODAY()-LOOKUP(2,1/(AI89:AV89<>""),AI89:AV89)) | IF(OR(F89="",COUNT(AI89:AV89)<2),"",LOOKUP(2,1/(AI89:AV89<>""),AI89:AV89)-MIN(AI89:AV89)) | IF(OR(AD89="",AC89="Not started",AC89=""),"",IFERROR(AD89-IF(VLOOKUP(AC89,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC89,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F89="","",IF(OR(AA89="Cancelled",AC89="Cancelled"),"Cancelled",IF(OR(AC89="Completed / Handover",Y89<>"",Z89>=100),"Completed — on track",IF(O89="Not awarded",IF(U89="",IF(X89="","No planned date",IF(TODAY()>X89,"Behind — past planned date",IF(X89-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U89,"Behind — award date passed",IF(U89-TODAY()<=30,"At risk — close to off track","On track"))),IF(X89="","No planned date",IF(AND(TODAY()>X89,OR(Z89="",Z89<100)),"Behind — past end date",IF(AND(T89<>"",X89<>"",Z89<>"",(Z89<100),((TODAY()-T89)/MAX(X89-T89,1)*100)-Z89>15),"Behind — progress lag",IF(AND(X89-TODAY()<=30,X89-TODAY()>=0,OR(Z89="",Z89<90)),"At risk — close to off track","On track")))))))) | IF(OR(F89="",AC89="Completed / Handover",AC89="Cancelled"),"",IF(O89="Not awarded",IF(U89<>"",U89-TODAY(),IF(X89="","",X89-TODAY())),IF(X89="","",X89-TODAY()))) | [14 empty] | IF(OR(F89="",AJ89=""),"",IF(COUNT(AI89:AI89)=0,"",AJ89-LOOKUP(2,1/(AI89:AI89<>""),AI89:AI89))) | IF(OR(F89="",AK89=""),"",IF(COUNT(AI89:AJ89)=0,"",AK89-LOOKUP(2,1/(AI89:AJ89<>""),AI89:AJ89))) | IF(OR(F89="",AL89=""),"",IF(COUNT(AI89:AK89)=0,"",AL89-LOOKUP(2,1/(AI89:AK89<>""),AI89:AK89))) | IF(OR(F89="",AM89=""),"",IF(COUNT(AI89:AL89)=0,"",AM89-LOOKUP(2,1/(AI89:AL89<>""),AI89:AL89))) | IF(OR(F89="",AN89=""),"",IF(COUNT(AI89:AM89)=0,"",AN89-LOOKUP(2,1/(AI89:AM89<>""),AI89:AM89))) | IF(OR(F89="",AO89=""),"",IF(COUNT(AI89:AN89)=0,"",AO89-LOOKUP(2,1/(AI89:AN89<>""),AI89:AN89))) | IF(OR(F89="",AP89=""),"",IF(COUNT(AI89:AO89)=0,"",AP89-LOOKUP(2,1/(AI89:AO89<>""),AI89:AO89))) | IF(OR(F89="",AQ89=""),"",IF(COUNT(AI89:AP89)=0,"",AQ89-LOOKUP(2,1/(AI89:AP89<>""),AI89:AP89))) | IF(OR(F89="",AR89=""),"",IF(COUNT(AI89:AQ89)=0,"",AR89-LOOKUP(2,1/(AI89:AQ89<>""),AI89:AQ89))) | IF(OR(F89="",AS89=""),"",IF(COUNT(AI89:AR89)=0,"",AS89-LOOKUP(2,1/(AI89:AR89<>""),AI89:AR89))) | IF(OR(F89="",AT89=""),"",IF(COUNT(AI89:AS89)=0,"",AT89-LOOKUP(2,1/(AI89:AS89<>""),AI89:AS89))) | IF(OR(F89="",AU89=""),"",IF(COUNT(AI89:AT89)=0,"",AU89-LOOKUP(2,1/(AI89:AT89<>""),AI89:AT89))) | IF(OR(F89="",AV89=""),"",IF(COUNT(AI89:AU89)=0,"",AV89-LOOKUP(2,1/(AI89:AU89<>""),AI89:AU89))) | IF(J89="","All_Provinces",IFERROR(VLOOKUP(J89,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K89="","All_Districts",IFERROR(VLOOKUP(K89,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F90="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 8 of 12 | AF2-DIS-N-048 | Peshang Drip Irrigation system | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Sayghan | Peshang | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Abdul Rahman |  | 3856.11 | IF(AQ90="","",AQ90) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W90<>"",W90,IF(OR(T90="",V90=""),"",EDATE(T90,V90))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Abdul Rahman | IF(F90="","",IF(COUNT(AI90:AV90)=0,IF(AA90="","Not started",AA90),SUBSTITUTE(LOOKUP(2,1/(AI90:AV90<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F90="",COUNT(AI90:AV90)=0),"",TODAY()-LOOKUP(2,1/(AI90:AV90<>""),AI90:AV90)) | IF(OR(F90="",COUNT(AI90:AV90)<2),"",LOOKUP(2,1/(AI90:AV90<>""),AI90:AV90)-MIN(AI90:AV90)) | IF(OR(AD90="",AC90="Not started",AC90=""),"",IFERROR(AD90-IF(VLOOKUP(AC90,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC90,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F90="","",IF(OR(AA90="Cancelled",AC90="Cancelled"),"Cancelled",IF(OR(AC90="Completed / Handover",Y90<>"",Z90>=100),"Completed — on track",IF(O90="Not awarded",IF(U90="",IF(X90="","No planned date",IF(TODAY()>X90,"Behind — past planned date",IF(X90-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U90,"Behind — award date passed",IF(U90-TODAY()<=30,"At risk — close to off track","On track"))),IF(X90="","No planned date",IF(AND(TODAY()>X90,OR(Z90="",Z90<100)),"Behind — past end date",IF(AND(T90<>"",X90<>"",Z90<>"",(Z90<100),((TODAY()-T90)/MAX(X90-T90,1)*100)-Z90>15),"Behind — progress lag",IF(AND(X90-TODAY()<=30,X90-TODAY()>=0,OR(Z90="",Z90<90)),"At risk — close to off track","On track")))))))) | IF(OR(F90="",AC90="Completed / Handover",AC90="Cancelled"),"",IF(O90="Not awarded",IF(U90<>"",U90-TODAY(),IF(X90="","",X90-TODAY())),IF(X90="","",X90-TODAY()))) | [14 empty] | IF(OR(F90="",AJ90=""),"",IF(COUNT(AI90:AI90)=0,"",AJ90-LOOKUP(2,1/(AI90:AI90<>""),AI90:AI90))) | IF(OR(F90="",AK90=""),"",IF(COUNT(AI90:AJ90)=0,"",AK90-LOOKUP(2,1/(AI90:AJ90<>""),AI90:AJ90))) | IF(OR(F90="",AL90=""),"",IF(COUNT(AI90:AK90)=0,"",AL90-LOOKUP(2,1/(AI90:AK90<>""),AI90:AK90))) | IF(OR(F90="",AM90=""),"",IF(COUNT(AI90:AL90)=0,"",AM90-LOOKUP(2,1/(AI90:AL90<>""),AI90:AL90))) | IF(OR(F90="",AN90=""),"",IF(COUNT(AI90:AM90)=0,"",AN90-LOOKUP(2,1/(AI90:AM90<>""),AI90:AM90))) | IF(OR(F90="",AO90=""),"",IF(COUNT(AI90:AN90)=0,"",AO90-LOOKUP(2,1/(AI90:AN90<>""),AI90:AN90))) | IF(OR(F90="",AP90=""),"",IF(COUNT(AI90:AO90)=0,"",AP90-LOOKUP(2,1/(AI90:AO90<>""),AI90:AO90))) | IF(OR(F90="",AQ90=""),"",IF(COUNT(AI90:AP90)=0,"",AQ90-LOOKUP(2,1/(AI90:AP90<>""),AI90:AP90))) | IF(OR(F90="",AR90=""),"",IF(COUNT(AI90:AQ90)=0,"",AR90-LOOKUP(2,1/(AI90:AQ90<>""),AI90:AQ90))) | IF(OR(F90="",AS90=""),"",IF(COUNT(AI90:AR90)=0,"",AS90-LOOKUP(2,1/(AI90:AR90<>""),AI90:AR90))) | IF(OR(F90="",AT90=""),"",IF(COUNT(AI90:AS90)=0,"",AT90-LOOKUP(2,1/(AI90:AS90<>""),AI90:AS90))) | IF(OR(F90="",AU90=""),"",IF(COUNT(AI90:AT90)=0,"",AU90-LOOKUP(2,1/(AI90:AT90<>""),AI90:AT90))) | IF(OR(F90="",AV90=""),"",IF(COUNT(AI90:AU90)=0,"",AV90-LOOKUP(2,1/(AI90:AU90<>""),AI90:AU90))) | IF(J90="","All_Provinces",IFERROR(VLOOKUP(J90,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K90="","All_Districts",IFERROR(VLOOKUP(K90,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F91="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 9 of 12 | AF2-DIS-N-049 | Safid Derakht 01 Drip Irrigtion System | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Nilli | Safid Derakht, | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Sayed Mohammad |  | 5459.95 | IF(AQ91="","",AQ91) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W91<>"",W91,IF(OR(T91="",V91=""),"",EDATE(T91,V91))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Sayed Mohammad | IF(F91="","",IF(COUNT(AI91:AV91)=0,IF(AA91="","Not started",AA91),SUBSTITUTE(LOOKUP(2,1/(AI91:AV91<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F91="",COUNT(AI91:AV91)=0),"",TODAY()-LOOKUP(2,1/(AI91:AV91<>""),AI91:AV91)) | IF(OR(F91="",COUNT(AI91:AV91)<2),"",LOOKUP(2,1/(AI91:AV91<>""),AI91:AV91)-MIN(AI91:AV91)) | IF(OR(AD91="",AC91="Not started",AC91=""),"",IFERROR(AD91-IF(VLOOKUP(AC91,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC91,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F91="","",IF(OR(AA91="Cancelled",AC91="Cancelled"),"Cancelled",IF(OR(AC91="Completed / Handover",Y91<>"",Z91>=100),"Completed — on track",IF(O91="Not awarded",IF(U91="",IF(X91="","No planned date",IF(TODAY()>X91,"Behind — past planned date",IF(X91-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U91,"Behind — award date passed",IF(U91-TODAY()<=30,"At risk — close to off track","On track"))),IF(X91="","No planned date",IF(AND(TODAY()>X91,OR(Z91="",Z91<100)),"Behind — past end date",IF(AND(T91<>"",X91<>"",Z91<>"",(Z91<100),((TODAY()-T91)/MAX(X91-T91,1)*100)-Z91>15),"Behind — progress lag",IF(AND(X91-TODAY()<=30,X91-TODAY()>=0,OR(Z91="",Z91<90)),"At risk — close to off track","On track")))))))) | IF(OR(F91="",AC91="Completed / Handover",AC91="Cancelled"),"",IF(O91="Not awarded",IF(U91<>"",U91-TODAY(),IF(X91="","",X91-TODAY())),IF(X91="","",X91-TODAY()))) | [14 empty] | IF(OR(F91="",AJ91=""),"",IF(COUNT(AI91:AI91)=0,"",AJ91-LOOKUP(2,1/(AI91:AI91<>""),AI91:AI91))) | IF(OR(F91="",AK91=""),"",IF(COUNT(AI91:AJ91)=0,"",AK91-LOOKUP(2,1/(AI91:AJ91<>""),AI91:AJ91))) | IF(OR(F91="",AL91=""),"",IF(COUNT(AI91:AK91)=0,"",AL91-LOOKUP(2,1/(AI91:AK91<>""),AI91:AK91))) | IF(OR(F91="",AM91=""),"",IF(COUNT(AI91:AL91)=0,"",AM91-LOOKUP(2,1/(AI91:AL91<>""),AI91:AL91))) | IF(OR(F91="",AN91=""),"",IF(COUNT(AI91:AM91)=0,"",AN91-LOOKUP(2,1/(AI91:AM91<>""),AI91:AM91))) | IF(OR(F91="",AO91=""),"",IF(COUNT(AI91:AN91)=0,"",AO91-LOOKUP(2,1/(AI91:AN91<>""),AI91:AN91))) | IF(OR(F91="",AP91=""),"",IF(COUNT(AI91:AO91)=0,"",AP91-LOOKUP(2,1/(AI91:AO91<>""),AI91:AO91))) | IF(OR(F91="",AQ91=""),"",IF(COUNT(AI91:AP91)=0,"",AQ91-LOOKUP(2,1/(AI91:AP91<>""),AI91:AP91))) | IF(OR(F91="",AR91=""),"",IF(COUNT(AI91:AQ91)=0,"",AR91-LOOKUP(2,1/(AI91:AQ91<>""),AI91:AQ91))) | IF(OR(F91="",AS91=""),"",IF(COUNT(AI91:AR91)=0,"",AS91-LOOKUP(2,1/(AI91:AR91<>""),AI91:AR91))) | IF(OR(F91="",AT91=""),"",IF(COUNT(AI91:AS91)=0,"",AT91-LOOKUP(2,1/(AI91:AS91<>""),AI91:AS91))) | IF(OR(F91="",AU91=""),"",IF(COUNT(AI91:AT91)=0,"",AU91-LOOKUP(2,1/(AI91:AT91<>""),AI91:AT91))) | IF(OR(F91="",AV91=""),"",IF(COUNT(AI91:AU91)=0,"",AV91-LOOKUP(2,1/(AI91:AU91<>""),AI91:AU91))) | IF(J91="","All_Provinces",IFERROR(VLOOKUP(J91,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K91="","All_Districts",IFERROR(VLOOKUP(K91,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F92="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 10 of 12 | AF2-DIS-N-050 | Safid Derakht 02 Drip Irrigtion System | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi |  | Safid Derakht, | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ghulam Hussain |  | 3764.17 | IF(AQ92="","",AQ92) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W92<>"",W92,IF(OR(T92="",V92=""),"",EDATE(T92,V92))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Ghulam Hussain | IF(F92="","",IF(COUNT(AI92:AV92)=0,IF(AA92="","Not started",AA92),SUBSTITUTE(LOOKUP(2,1/(AI92:AV92<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F92="",COUNT(AI92:AV92)=0),"",TODAY()-LOOKUP(2,1/(AI92:AV92<>""),AI92:AV92)) | IF(OR(F92="",COUNT(AI92:AV92)<2),"",LOOKUP(2,1/(AI92:AV92<>""),AI92:AV92)-MIN(AI92:AV92)) | IF(OR(AD92="",AC92="Not started",AC92=""),"",IFERROR(AD92-IF(VLOOKUP(AC92,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC92,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F92="","",IF(OR(AA92="Cancelled",AC92="Cancelled"),"Cancelled",IF(OR(AC92="Completed / Handover",Y92<>"",Z92>=100),"Completed — on track",IF(O92="Not awarded",IF(U92="",IF(X92="","No planned date",IF(TODAY()>X92,"Behind — past planned date",IF(X92-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U92,"Behind — award date passed",IF(U92-TODAY()<=30,"At risk — close to off track","On track"))),IF(X92="","No planned date",IF(AND(TODAY()>X92,OR(Z92="",Z92<100)),"Behind — past end date",IF(AND(T92<>"",X92<>"",Z92<>"",(Z92<100),((TODAY()-T92)/MAX(X92-T92,1)*100)-Z92>15),"Behind — progress lag",IF(AND(X92-TODAY()<=30,X92-TODAY()>=0,OR(Z92="",Z92<90)),"At risk — close to off track","On track")))))))) | IF(OR(F92="",AC92="Completed / Handover",AC92="Cancelled"),"",IF(O92="Not awarded",IF(U92<>"",U92-TODAY(),IF(X92="","",X92-TODAY())),IF(X92="","",X92-TODAY()))) | [14 empty] | IF(OR(F92="",AJ92=""),"",IF(COUNT(AI92:AI92)=0,"",AJ92-LOOKUP(2,1/(AI92:AI92<>""),AI92:AI92))) | IF(OR(F92="",AK92=""),"",IF(COUNT(AI92:AJ92)=0,"",AK92-LOOKUP(2,1/(AI92:AJ92<>""),AI92:AJ92))) | IF(OR(F92="",AL92=""),"",IF(COUNT(AI92:AK92)=0,"",AL92-LOOKUP(2,1/(AI92:AK92<>""),AI92:AK92))) | IF(OR(F92="",AM92=""),"",IF(COUNT(AI92:AL92)=0,"",AM92-LOOKUP(2,1/(AI92:AL92<>""),AI92:AL92))) | IF(OR(F92="",AN92=""),"",IF(COUNT(AI92:AM92)=0,"",AN92-LOOKUP(2,1/(AI92:AM92<>""),AI92:AM92))) | IF(OR(F92="",AO92=""),"",IF(COUNT(AI92:AN92)=0,"",AO92-LOOKUP(2,1/(AI92:AN92<>""),AI92:AN92))) | IF(OR(F92="",AP92=""),"",IF(COUNT(AI92:AO92)=0,"",AP92-LOOKUP(2,1/(AI92:AO92<>""),AI92:AO92))) | IF(OR(F92="",AQ92=""),"",IF(COUNT(AI92:AP92)=0,"",AQ92-LOOKUP(2,1/(AI92:AP92<>""),AI92:AP92))) | IF(OR(F92="",AR92=""),"",IF(COUNT(AI92:AQ92)=0,"",AR92-LOOKUP(2,1/(AI92:AQ92<>""),AI92:AQ92))) | IF(OR(F92="",AS92=""),"",IF(COUNT(AI92:AR92)=0,"",AS92-LOOKUP(2,1/(AI92:AR92<>""),AI92:AR92))) | IF(OR(F92="",AT92=""),"",IF(COUNT(AI92:AS92)=0,"",AT92-LOOKUP(2,1/(AI92:AS92<>""),AI92:AS92))) | IF(OR(F92="",AU92=""),"",IF(COUNT(AI92:AT92)=0,"",AU92-LOOKUP(2,1/(AI92:AT92<>""),AI92:AT92))) | IF(OR(F92="",AV92=""),"",IF(COUNT(AI92:AU92)=0,"",AV92-LOOKUP(2,1/(AI92:AU92<>""),AI92:AU92))) | IF(J92="","All_Provinces",IFERROR(VLOOKUP(J92,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K92="","All_Districts",IFERROR(VLOOKUP(K92,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F93="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 11 of 12 | AF2-DIS-N-051 | Sarawood Drip Irrigation System | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Miramor | Sarawood | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Sayed Hassan |  | 3559.69 | IF(AQ93="","",AQ93) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W93<>"",W93,IF(OR(T93="",V93=""),"",EDATE(T93,V93))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Sayed Hassan | IF(F93="","",IF(COUNT(AI93:AV93)=0,IF(AA93="","Not started",AA93),SUBSTITUTE(LOOKUP(2,1/(AI93:AV93<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F93="",COUNT(AI93:AV93)=0),"",TODAY()-LOOKUP(2,1/(AI93:AV93<>""),AI93:AV93)) | IF(OR(F93="",COUNT(AI93:AV93)<2),"",LOOKUP(2,1/(AI93:AV93<>""),AI93:AV93)-MIN(AI93:AV93)) | IF(OR(AD93="",AC93="Not started",AC93=""),"",IFERROR(AD93-IF(VLOOKUP(AC93,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC93,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F93="","",IF(OR(AA93="Cancelled",AC93="Cancelled"),"Cancelled",IF(OR(AC93="Completed / Handover",Y93<>"",Z93>=100),"Completed — on track",IF(O93="Not awarded",IF(U93="",IF(X93="","No planned date",IF(TODAY()>X93,"Behind — past planned date",IF(X93-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U93,"Behind — award date passed",IF(U93-TODAY()<=30,"At risk — close to off track","On track"))),IF(X93="","No planned date",IF(AND(TODAY()>X93,OR(Z93="",Z93<100)),"Behind — past end date",IF(AND(T93<>"",X93<>"",Z93<>"",(Z93<100),((TODAY()-T93)/MAX(X93-T93,1)*100)-Z93>15),"Behind — progress lag",IF(AND(X93-TODAY()<=30,X93-TODAY()>=0,OR(Z93="",Z93<90)),"At risk — close to off track","On track")))))))) | IF(OR(F93="",AC93="Completed / Handover",AC93="Cancelled"),"",IF(O93="Not awarded",IF(U93<>"",U93-TODAY(),IF(X93="","",X93-TODAY())),IF(X93="","",X93-TODAY()))) | [14 empty] | IF(OR(F93="",AJ93=""),"",IF(COUNT(AI93:AI93)=0,"",AJ93-LOOKUP(2,1/(AI93:AI93<>""),AI93:AI93))) | IF(OR(F93="",AK93=""),"",IF(COUNT(AI93:AJ93)=0,"",AK93-LOOKUP(2,1/(AI93:AJ93<>""),AI93:AJ93))) | IF(OR(F93="",AL93=""),"",IF(COUNT(AI93:AK93)=0,"",AL93-LOOKUP(2,1/(AI93:AK93<>""),AI93:AK93))) | IF(OR(F93="",AM93=""),"",IF(COUNT(AI93:AL93)=0,"",AM93-LOOKUP(2,1/(AI93:AL93<>""),AI93:AL93))) | IF(OR(F93="",AN93=""),"",IF(COUNT(AI93:AM93)=0,"",AN93-LOOKUP(2,1/(AI93:AM93<>""),AI93:AM93))) | IF(OR(F93="",AO93=""),"",IF(COUNT(AI93:AN93)=0,"",AO93-LOOKUP(2,1/(AI93:AN93<>""),AI93:AN93))) | IF(OR(F93="",AP93=""),"",IF(COUNT(AI93:AO93)=0,"",AP93-LOOKUP(2,1/(AI93:AO93<>""),AI93:AO93))) | IF(OR(F93="",AQ93=""),"",IF(COUNT(AI93:AP93)=0,"",AQ93-LOOKUP(2,1/(AI93:AP93<>""),AI93:AP93))) | IF(OR(F93="",AR93=""),"",IF(COUNT(AI93:AQ93)=0,"",AR93-LOOKUP(2,1/(AI93:AQ93<>""),AI93:AQ93))) | IF(OR(F93="",AS93=""),"",IF(COUNT(AI93:AR93)=0,"",AS93-LOOKUP(2,1/(AI93:AR93<>""),AI93:AR93))) | IF(OR(F93="",AT93=""),"",IF(COUNT(AI93:AS93)=0,"",AT93-LOOKUP(2,1/(AI93:AS93<>""),AI93:AS93))) | IF(OR(F93="",AU93=""),"",IF(COUNT(AI93:AT93)=0,"",AU93-LOOKUP(2,1/(AI93:AT93<>""),AI93:AT93))) | IF(OR(F93="",AV93=""),"",IF(COUNT(AI93:AU93)=0,"",AV93-LOOKUP(2,1/(AI93:AU93<>""),AI93:AU93))) | IF(J93="","All_Provinces",IFERROR(VLOOKUP(J93,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K93="","All_Districts",IFERROR(VLOOKUP(K93,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F94="","",ROW()-3) | AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | 12 of 12 | AF2-DIS-N-052 | Sorkh Nawor Drip Irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi |  | Sorkh Nawor | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Reza |  | 5564.4 | IF(AQ94="","",AQ94) | 2026-12-20 | 6.2 | 2027-06-28 | IF(W94<>"",W94,IF(OR(T94="",V94=""),"",EDATE(T94,V94))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Reza | IF(F94="","",IF(COUNT(AI94:AV94)=0,IF(AA94="","Not started",AA94),SUBSTITUTE(LOOKUP(2,1/(AI94:AV94<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F94="",COUNT(AI94:AV94)=0),"",TODAY()-LOOKUP(2,1/(AI94:AV94<>""),AI94:AV94)) | IF(OR(F94="",COUNT(AI94:AV94)<2),"",LOOKUP(2,1/(AI94:AV94<>""),AI94:AV94)-MIN(AI94:AV94)) | IF(OR(AD94="",AC94="Not started",AC94=""),"",IFERROR(AD94-IF(VLOOKUP(AC94,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC94,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F94="","",IF(OR(AA94="Cancelled",AC94="Cancelled"),"Cancelled",IF(OR(AC94="Completed / Handover",Y94<>"",Z94>=100),"Completed — on track",IF(O94="Not awarded",IF(U94="",IF(X94="","No planned date",IF(TODAY()>X94,"Behind — past planned date",IF(X94-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U94,"Behind — award date passed",IF(U94-TODAY()<=30,"At risk — close to off track","On track"))),IF(X94="","No planned date",IF(AND(TODAY()>X94,OR(Z94="",Z94<100)),"Behind — past end date",IF(AND(T94<>"",X94<>"",Z94<>"",(Z94<100),((TODAY()-T94)/MAX(X94-T94,1)*100)-Z94>15),"Behind — progress lag",IF(AND(X94-TODAY()<=30,X94-TODAY()>=0,OR(Z94="",Z94<90)),"At risk — close to off track","On track")))))))) | IF(OR(F94="",AC94="Completed / Handover",AC94="Cancelled"),"",IF(O94="Not awarded",IF(U94<>"",U94-TODAY(),IF(X94="","",X94-TODAY())),IF(X94="","",X94-TODAY()))) | [14 empty] | IF(OR(F94="",AJ94=""),"",IF(COUNT(AI94:AI94)=0,"",AJ94-LOOKUP(2,1/(AI94:AI94<>""),AI94:AI94))) | IF(OR(F94="",AK94=""),"",IF(COUNT(AI94:AJ94)=0,"",AK94-LOOKUP(2,1/(AI94:AJ94<>""),AI94:AJ94))) | IF(OR(F94="",AL94=""),"",IF(COUNT(AI94:AK94)=0,"",AL94-LOOKUP(2,1/(AI94:AK94<>""),AI94:AK94))) | IF(OR(F94="",AM94=""),"",IF(COUNT(AI94:AL94)=0,"",AM94-LOOKUP(2,1/(AI94:AL94<>""),AI94:AL94))) | IF(OR(F94="",AN94=""),"",IF(COUNT(AI94:AM94)=0,"",AN94-LOOKUP(2,1/(AI94:AM94<>""),AI94:AM94))) | IF(OR(F94="",AO94=""),"",IF(COUNT(AI94:AN94)=0,"",AO94-LOOKUP(2,1/(AI94:AN94<>""),AI94:AN94))) | IF(OR(F94="",AP94=""),"",IF(COUNT(AI94:AO94)=0,"",AP94-LOOKUP(2,1/(AI94:AO94<>""),AI94:AO94))) | IF(OR(F94="",AQ94=""),"",IF(COUNT(AI94:AP94)=0,"",AQ94-LOOKUP(2,1/(AI94:AP94<>""),AI94:AP94))) | IF(OR(F94="",AR94=""),"",IF(COUNT(AI94:AQ94)=0,"",AR94-LOOKUP(2,1/(AI94:AQ94<>""),AI94:AQ94))) | IF(OR(F94="",AS94=""),"",IF(COUNT(AI94:AR94)=0,"",AS94-LOOKUP(2,1/(AI94:AR94<>""),AI94:AR94))) | IF(OR(F94="",AT94=""),"",IF(COUNT(AI94:AS94)=0,"",AT94-LOOKUP(2,1/(AI94:AS94<>""),AI94:AS94))) | IF(OR(F94="",AU94=""),"",IF(COUNT(AI94:AT94)=0,"",AU94-LOOKUP(2,1/(AI94:AT94<>""),AI94:AT94))) | IF(OR(F94="",AV94=""),"",IF(COUNT(AI94:AU94)=0,"",AV94-LOOKUP(2,1/(AI94:AU94<>""),AI94:AU94))) | IF(J94="","All_Provinces",IFERROR(VLOOKUP(J94,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K94="","All_Districts",IFERROR(VLOOKUP(K94,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F95="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 1 of 15 | AF2-DIS-N-053 | Agriculture Research Drip Irrigation scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Matoon | Agriculture Feseach Farm | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Hazrat Wali |  |  | IF(AQ95="","",AQ95) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W95<>"",W95,IF(OR(T95="",V95=""),"",EDATE(T95,V95))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Hazrat Wali | IF(F95="","",IF(COUNT(AI95:AV95)=0,IF(AA95="","Not started",AA95),SUBSTITUTE(LOOKUP(2,1/(AI95:AV95<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F95="",COUNT(AI95:AV95)=0),"",TODAY()-LOOKUP(2,1/(AI95:AV95<>""),AI95:AV95)) | IF(OR(F95="",COUNT(AI95:AV95)<2),"",LOOKUP(2,1/(AI95:AV95<>""),AI95:AV95)-MIN(AI95:AV95)) | IF(OR(AD95="",AC95="Not started",AC95=""),"",IFERROR(AD95-IF(VLOOKUP(AC95,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC95,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F95="","",IF(OR(AA95="Cancelled",AC95="Cancelled"),"Cancelled",IF(OR(AC95="Completed / Handover",Y95<>"",Z95>=100),"Completed — on track",IF(O95="Not awarded",IF(U95="",IF(X95="","No planned date",IF(TODAY()>X95,"Behind — past planned date",IF(X95-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U95,"Behind — award date passed",IF(U95-TODAY()<=30,"At risk — close to off track","On track"))),IF(X95="","No planned date",IF(AND(TODAY()>X95,OR(Z95="",Z95<100)),"Behind — past end date",IF(AND(T95<>"",X95<>"",Z95<>"",(Z95<100),((TODAY()-T95)/MAX(X95-T95,1)*100)-Z95>15),"Behind — progress lag",IF(AND(X95-TODAY()<=30,X95-TODAY()>=0,OR(Z95="",Z95<90)),"At risk — close to off track","On track")))))))) | IF(OR(F95="",AC95="Completed / Handover",AC95="Cancelled"),"",IF(O95="Not awarded",IF(U95<>"",U95-TODAY(),IF(X95="","",X95-TODAY())),IF(X95="","",X95-TODAY()))) | [14 empty] | IF(OR(F95="",AJ95=""),"",IF(COUNT(AI95:AI95)=0,"",AJ95-LOOKUP(2,1/(AI95:AI95<>""),AI95:AI95))) | IF(OR(F95="",AK95=""),"",IF(COUNT(AI95:AJ95)=0,"",AK95-LOOKUP(2,1/(AI95:AJ95<>""),AI95:AJ95))) | IF(OR(F95="",AL95=""),"",IF(COUNT(AI95:AK95)=0,"",AL95-LOOKUP(2,1/(AI95:AK95<>""),AI95:AK95))) | IF(OR(F95="",AM95=""),"",IF(COUNT(AI95:AL95)=0,"",AM95-LOOKUP(2,1/(AI95:AL95<>""),AI95:AL95))) | IF(OR(F95="",AN95=""),"",IF(COUNT(AI95:AM95)=0,"",AN95-LOOKUP(2,1/(AI95:AM95<>""),AI95:AM95))) | IF(OR(F95="",AO95=""),"",IF(COUNT(AI95:AN95)=0,"",AO95-LOOKUP(2,1/(AI95:AN95<>""),AI95:AN95))) | IF(OR(F95="",AP95=""),"",IF(COUNT(AI95:AO95)=0,"",AP95-LOOKUP(2,1/(AI95:AO95<>""),AI95:AO95))) | IF(OR(F95="",AQ95=""),"",IF(COUNT(AI95:AP95)=0,"",AQ95-LOOKUP(2,1/(AI95:AP95<>""),AI95:AP95))) | IF(OR(F95="",AR95=""),"",IF(COUNT(AI95:AQ95)=0,"",AR95-LOOKUP(2,1/(AI95:AQ95<>""),AI95:AQ95))) | IF(OR(F95="",AS95=""),"",IF(COUNT(AI95:AR95)=0,"",AS95-LOOKUP(2,1/(AI95:AR95<>""),AI95:AR95))) | IF(OR(F95="",AT95=""),"",IF(COUNT(AI95:AS95)=0,"",AT95-LOOKUP(2,1/(AI95:AS95<>""),AI95:AS95))) | IF(OR(F95="",AU95=""),"",IF(COUNT(AI95:AT95)=0,"",AU95-LOOKUP(2,1/(AI95:AT95<>""),AI95:AT95))) | IF(OR(F95="",AV95=""),"",IF(COUNT(AI95:AU95)=0,"",AV95-LOOKUP(2,1/(AI95:AU95<>""),AI95:AU95))) | IF(J95="","All_Provinces",IFERROR(VLOOKUP(J95,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K95="","All_Districts",IFERROR(VLOOKUP(K95,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F96="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 2 of 15 | AF2-DIS-N-054 | Basana Drip irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Ghazni | Andar | Basana | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Naim |  |  | IF(AQ96="","",AQ96) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W96<>"",W96,IF(OR(T96="",V96=""),"",EDATE(T96,V96))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Mohammad Naim | IF(F96="","",IF(COUNT(AI96:AV96)=0,IF(AA96="","Not started",AA96),SUBSTITUTE(LOOKUP(2,1/(AI96:AV96<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F96="",COUNT(AI96:AV96)=0),"",TODAY()-LOOKUP(2,1/(AI96:AV96<>""),AI96:AV96)) | IF(OR(F96="",COUNT(AI96:AV96)<2),"",LOOKUP(2,1/(AI96:AV96<>""),AI96:AV96)-MIN(AI96:AV96)) | IF(OR(AD96="",AC96="Not started",AC96=""),"",IFERROR(AD96-IF(VLOOKUP(AC96,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC96,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F96="","",IF(OR(AA96="Cancelled",AC96="Cancelled"),"Cancelled",IF(OR(AC96="Completed / Handover",Y96<>"",Z96>=100),"Completed — on track",IF(O96="Not awarded",IF(U96="",IF(X96="","No planned date",IF(TODAY()>X96,"Behind — past planned date",IF(X96-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U96,"Behind — award date passed",IF(U96-TODAY()<=30,"At risk — close to off track","On track"))),IF(X96="","No planned date",IF(AND(TODAY()>X96,OR(Z96="",Z96<100)),"Behind — past end date",IF(AND(T96<>"",X96<>"",Z96<>"",(Z96<100),((TODAY()-T96)/MAX(X96-T96,1)*100)-Z96>15),"Behind — progress lag",IF(AND(X96-TODAY()<=30,X96-TODAY()>=0,OR(Z96="",Z96<90)),"At risk — close to off track","On track")))))))) | IF(OR(F96="",AC96="Completed / Handover",AC96="Cancelled"),"",IF(O96="Not awarded",IF(U96<>"",U96-TODAY(),IF(X96="","",X96-TODAY())),IF(X96="","",X96-TODAY()))) | [14 empty] | IF(OR(F96="",AJ96=""),"",IF(COUNT(AI96:AI96)=0,"",AJ96-LOOKUP(2,1/(AI96:AI96<>""),AI96:AI96))) | IF(OR(F96="",AK96=""),"",IF(COUNT(AI96:AJ96)=0,"",AK96-LOOKUP(2,1/(AI96:AJ96<>""),AI96:AJ96))) | IF(OR(F96="",AL96=""),"",IF(COUNT(AI96:AK96)=0,"",AL96-LOOKUP(2,1/(AI96:AK96<>""),AI96:AK96))) | IF(OR(F96="",AM96=""),"",IF(COUNT(AI96:AL96)=0,"",AM96-LOOKUP(2,1/(AI96:AL96<>""),AI96:AL96))) | IF(OR(F96="",AN96=""),"",IF(COUNT(AI96:AM96)=0,"",AN96-LOOKUP(2,1/(AI96:AM96<>""),AI96:AM96))) | IF(OR(F96="",AO96=""),"",IF(COUNT(AI96:AN96)=0,"",AO96-LOOKUP(2,1/(AI96:AN96<>""),AI96:AN96))) | IF(OR(F96="",AP96=""),"",IF(COUNT(AI96:AO96)=0,"",AP96-LOOKUP(2,1/(AI96:AO96<>""),AI96:AO96))) | IF(OR(F96="",AQ96=""),"",IF(COUNT(AI96:AP96)=0,"",AQ96-LOOKUP(2,1/(AI96:AP96<>""),AI96:AP96))) | IF(OR(F96="",AR96=""),"",IF(COUNT(AI96:AQ96)=0,"",AR96-LOOKUP(2,1/(AI96:AQ96<>""),AI96:AQ96))) | IF(OR(F96="",AS96=""),"",IF(COUNT(AI96:AR96)=0,"",AS96-LOOKUP(2,1/(AI96:AR96<>""),AI96:AR96))) | IF(OR(F96="",AT96=""),"",IF(COUNT(AI96:AS96)=0,"",AT96-LOOKUP(2,1/(AI96:AS96<>""),AI96:AS96))) | IF(OR(F96="",AU96=""),"",IF(COUNT(AI96:AT96)=0,"",AU96-LOOKUP(2,1/(AI96:AT96<>""),AI96:AT96))) | IF(OR(F96="",AV96=""),"",IF(COUNT(AI96:AU96)=0,"",AV96-LOOKUP(2,1/(AI96:AU96<>""),AI96:AU96))) | IF(J96="","All_Provinces",IFERROR(VLOOKUP(J96,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K96="","All_Districts",IFERROR(VLOOKUP(K96,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F97="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 3 of 15 | AF2-DIS-N-055 | Dabar Allu Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Logar | Charkh | Dabar Allu | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Akbar |  |  | IF(AQ97="","",AQ97) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W97<>"",W97,IF(OR(T97="",V97=""),"",EDATE(T97,V97))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Mohammad Akbar | IF(F97="","",IF(COUNT(AI97:AV97)=0,IF(AA97="","Not started",AA97),SUBSTITUTE(LOOKUP(2,1/(AI97:AV97<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F97="",COUNT(AI97:AV97)=0),"",TODAY()-LOOKUP(2,1/(AI97:AV97<>""),AI97:AV97)) | IF(OR(F97="",COUNT(AI97:AV97)<2),"",LOOKUP(2,1/(AI97:AV97<>""),AI97:AV97)-MIN(AI97:AV97)) | IF(OR(AD97="",AC97="Not started",AC97=""),"",IFERROR(AD97-IF(VLOOKUP(AC97,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC97,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F97="","",IF(OR(AA97="Cancelled",AC97="Cancelled"),"Cancelled",IF(OR(AC97="Completed / Handover",Y97<>"",Z97>=100),"Completed — on track",IF(O97="Not awarded",IF(U97="",IF(X97="","No planned date",IF(TODAY()>X97,"Behind — past planned date",IF(X97-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U97,"Behind — award date passed",IF(U97-TODAY()<=30,"At risk — close to off track","On track"))),IF(X97="","No planned date",IF(AND(TODAY()>X97,OR(Z97="",Z97<100)),"Behind — past end date",IF(AND(T97<>"",X97<>"",Z97<>"",(Z97<100),((TODAY()-T97)/MAX(X97-T97,1)*100)-Z97>15),"Behind — progress lag",IF(AND(X97-TODAY()<=30,X97-TODAY()>=0,OR(Z97="",Z97<90)),"At risk — close to off track","On track")))))))) | IF(OR(F97="",AC97="Completed / Handover",AC97="Cancelled"),"",IF(O97="Not awarded",IF(U97<>"",U97-TODAY(),IF(X97="","",X97-TODAY())),IF(X97="","",X97-TODAY()))) | [14 empty] | IF(OR(F97="",AJ97=""),"",IF(COUNT(AI97:AI97)=0,"",AJ97-LOOKUP(2,1/(AI97:AI97<>""),AI97:AI97))) | IF(OR(F97="",AK97=""),"",IF(COUNT(AI97:AJ97)=0,"",AK97-LOOKUP(2,1/(AI97:AJ97<>""),AI97:AJ97))) | IF(OR(F97="",AL97=""),"",IF(COUNT(AI97:AK97)=0,"",AL97-LOOKUP(2,1/(AI97:AK97<>""),AI97:AK97))) | IF(OR(F97="",AM97=""),"",IF(COUNT(AI97:AL97)=0,"",AM97-LOOKUP(2,1/(AI97:AL97<>""),AI97:AL97))) | IF(OR(F97="",AN97=""),"",IF(COUNT(AI97:AM97)=0,"",AN97-LOOKUP(2,1/(AI97:AM97<>""),AI97:AM97))) | IF(OR(F97="",AO97=""),"",IF(COUNT(AI97:AN97)=0,"",AO97-LOOKUP(2,1/(AI97:AN97<>""),AI97:AN97))) | IF(OR(F97="",AP97=""),"",IF(COUNT(AI97:AO97)=0,"",AP97-LOOKUP(2,1/(AI97:AO97<>""),AI97:AO97))) | IF(OR(F97="",AQ97=""),"",IF(COUNT(AI97:AP97)=0,"",AQ97-LOOKUP(2,1/(AI97:AP97<>""),AI97:AP97))) | IF(OR(F97="",AR97=""),"",IF(COUNT(AI97:AQ97)=0,"",AR97-LOOKUP(2,1/(AI97:AQ97<>""),AI97:AQ97))) | IF(OR(F97="",AS97=""),"",IF(COUNT(AI97:AR97)=0,"",AS97-LOOKUP(2,1/(AI97:AR97<>""),AI97:AR97))) | IF(OR(F97="",AT97=""),"",IF(COUNT(AI97:AS97)=0,"",AT97-LOOKUP(2,1/(AI97:AS97<>""),AI97:AS97))) | IF(OR(F97="",AU97=""),"",IF(COUNT(AI97:AT97)=0,"",AU97-LOOKUP(2,1/(AI97:AT97<>""),AI97:AT97))) | IF(OR(F97="",AV97=""),"",IF(COUNT(AI97:AU97)=0,"",AV97-LOOKUP(2,1/(AI97:AU97<>""),AI97:AU97))) | IF(J97="","All_Provinces",IFERROR(VLOOKUP(J97,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K97="","All_Districts",IFERROR(VLOOKUP(K97,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F98="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 4 of 15 | AF2-DIS-N-056 | Deyak Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Ghazni | Deyak | Ramaki | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Naser Khan |  |  | IF(AQ98="","",AQ98) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W98<>"",W98,IF(OR(T98="",V98=""),"",EDATE(T98,V98))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Naser Khan | IF(F98="","",IF(COUNT(AI98:AV98)=0,IF(AA98="","Not started",AA98),SUBSTITUTE(LOOKUP(2,1/(AI98:AV98<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F98="",COUNT(AI98:AV98)=0),"",TODAY()-LOOKUP(2,1/(AI98:AV98<>""),AI98:AV98)) | IF(OR(F98="",COUNT(AI98:AV98)<2),"",LOOKUP(2,1/(AI98:AV98<>""),AI98:AV98)-MIN(AI98:AV98)) | IF(OR(AD98="",AC98="Not started",AC98=""),"",IFERROR(AD98-IF(VLOOKUP(AC98,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC98,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F98="","",IF(OR(AA98="Cancelled",AC98="Cancelled"),"Cancelled",IF(OR(AC98="Completed / Handover",Y98<>"",Z98>=100),"Completed — on track",IF(O98="Not awarded",IF(U98="",IF(X98="","No planned date",IF(TODAY()>X98,"Behind — past planned date",IF(X98-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U98,"Behind — award date passed",IF(U98-TODAY()<=30,"At risk — close to off track","On track"))),IF(X98="","No planned date",IF(AND(TODAY()>X98,OR(Z98="",Z98<100)),"Behind — past end date",IF(AND(T98<>"",X98<>"",Z98<>"",(Z98<100),((TODAY()-T98)/MAX(X98-T98,1)*100)-Z98>15),"Behind — progress lag",IF(AND(X98-TODAY()<=30,X98-TODAY()>=0,OR(Z98="",Z98<90)),"At risk — close to off track","On track")))))))) | IF(OR(F98="",AC98="Completed / Handover",AC98="Cancelled"),"",IF(O98="Not awarded",IF(U98<>"",U98-TODAY(),IF(X98="","",X98-TODAY())),IF(X98="","",X98-TODAY()))) | [14 empty] | IF(OR(F98="",AJ98=""),"",IF(COUNT(AI98:AI98)=0,"",AJ98-LOOKUP(2,1/(AI98:AI98<>""),AI98:AI98))) | IF(OR(F98="",AK98=""),"",IF(COUNT(AI98:AJ98)=0,"",AK98-LOOKUP(2,1/(AI98:AJ98<>""),AI98:AJ98))) | IF(OR(F98="",AL98=""),"",IF(COUNT(AI98:AK98)=0,"",AL98-LOOKUP(2,1/(AI98:AK98<>""),AI98:AK98))) | IF(OR(F98="",AM98=""),"",IF(COUNT(AI98:AL98)=0,"",AM98-LOOKUP(2,1/(AI98:AL98<>""),AI98:AL98))) | IF(OR(F98="",AN98=""),"",IF(COUNT(AI98:AM98)=0,"",AN98-LOOKUP(2,1/(AI98:AM98<>""),AI98:AM98))) | IF(OR(F98="",AO98=""),"",IF(COUNT(AI98:AN98)=0,"",AO98-LOOKUP(2,1/(AI98:AN98<>""),AI98:AN98))) | IF(OR(F98="",AP98=""),"",IF(COUNT(AI98:AO98)=0,"",AP98-LOOKUP(2,1/(AI98:AO98<>""),AI98:AO98))) | IF(OR(F98="",AQ98=""),"",IF(COUNT(AI98:AP98)=0,"",AQ98-LOOKUP(2,1/(AI98:AP98<>""),AI98:AP98))) | IF(OR(F98="",AR98=""),"",IF(COUNT(AI98:AQ98)=0,"",AR98-LOOKUP(2,1/(AI98:AQ98<>""),AI98:AQ98))) | IF(OR(F98="",AS98=""),"",IF(COUNT(AI98:AR98)=0,"",AS98-LOOKUP(2,1/(AI98:AR98<>""),AI98:AR98))) | IF(OR(F98="",AT98=""),"",IF(COUNT(AI98:AS98)=0,"",AT98-LOOKUP(2,1/(AI98:AS98<>""),AI98:AS98))) | IF(OR(F98="",AU98=""),"",IF(COUNT(AI98:AT98)=0,"",AU98-LOOKUP(2,1/(AI98:AT98<>""),AI98:AT98))) | IF(OR(F98="",AV98=""),"",IF(COUNT(AI98:AU98)=0,"",AV98-LOOKUP(2,1/(AI98:AU98<>""),AI98:AU98))) | IF(J98="","All_Provinces",IFERROR(VLOOKUP(J98,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K98="","All_Districts",IFERROR(VLOOKUP(K98,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F99="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 5 of 15 | AF2-DIS-N-057 | Ghafoor khil Drip irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktya | Center | Gafoor khil | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Salam Jan |  |  | IF(AQ99="","",AQ99) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W99<>"",W99,IF(OR(T99="",V99=""),"",EDATE(T99,V99))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Salam Jan | IF(F99="","",IF(COUNT(AI99:AV99)=0,IF(AA99="","Not started",AA99),SUBSTITUTE(LOOKUP(2,1/(AI99:AV99<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F99="",COUNT(AI99:AV99)=0),"",TODAY()-LOOKUP(2,1/(AI99:AV99<>""),AI99:AV99)) | IF(OR(F99="",COUNT(AI99:AV99)<2),"",LOOKUP(2,1/(AI99:AV99<>""),AI99:AV99)-MIN(AI99:AV99)) | IF(OR(AD99="",AC99="Not started",AC99=""),"",IFERROR(AD99-IF(VLOOKUP(AC99,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC99,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F99="","",IF(OR(AA99="Cancelled",AC99="Cancelled"),"Cancelled",IF(OR(AC99="Completed / Handover",Y99<>"",Z99>=100),"Completed — on track",IF(O99="Not awarded",IF(U99="",IF(X99="","No planned date",IF(TODAY()>X99,"Behind — past planned date",IF(X99-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U99,"Behind — award date passed",IF(U99-TODAY()<=30,"At risk — close to off track","On track"))),IF(X99="","No planned date",IF(AND(TODAY()>X99,OR(Z99="",Z99<100)),"Behind — past end date",IF(AND(T99<>"",X99<>"",Z99<>"",(Z99<100),((TODAY()-T99)/MAX(X99-T99,1)*100)-Z99>15),"Behind — progress lag",IF(AND(X99-TODAY()<=30,X99-TODAY()>=0,OR(Z99="",Z99<90)),"At risk — close to off track","On track")))))))) | IF(OR(F99="",AC99="Completed / Handover",AC99="Cancelled"),"",IF(O99="Not awarded",IF(U99<>"",U99-TODAY(),IF(X99="","",X99-TODAY())),IF(X99="","",X99-TODAY()))) | [14 empty] | IF(OR(F99="",AJ99=""),"",IF(COUNT(AI99:AI99)=0,"",AJ99-LOOKUP(2,1/(AI99:AI99<>""),AI99:AI99))) | IF(OR(F99="",AK99=""),"",IF(COUNT(AI99:AJ99)=0,"",AK99-LOOKUP(2,1/(AI99:AJ99<>""),AI99:AJ99))) | IF(OR(F99="",AL99=""),"",IF(COUNT(AI99:AK99)=0,"",AL99-LOOKUP(2,1/(AI99:AK99<>""),AI99:AK99))) | IF(OR(F99="",AM99=""),"",IF(COUNT(AI99:AL99)=0,"",AM99-LOOKUP(2,1/(AI99:AL99<>""),AI99:AL99))) | IF(OR(F99="",AN99=""),"",IF(COUNT(AI99:AM99)=0,"",AN99-LOOKUP(2,1/(AI99:AM99<>""),AI99:AM99))) | IF(OR(F99="",AO99=""),"",IF(COUNT(AI99:AN99)=0,"",AO99-LOOKUP(2,1/(AI99:AN99<>""),AI99:AN99))) | IF(OR(F99="",AP99=""),"",IF(COUNT(AI99:AO99)=0,"",AP99-LOOKUP(2,1/(AI99:AO99<>""),AI99:AO99))) | IF(OR(F99="",AQ99=""),"",IF(COUNT(AI99:AP99)=0,"",AQ99-LOOKUP(2,1/(AI99:AP99<>""),AI99:AP99))) | IF(OR(F99="",AR99=""),"",IF(COUNT(AI99:AQ99)=0,"",AR99-LOOKUP(2,1/(AI99:AQ99<>""),AI99:AQ99))) | IF(OR(F99="",AS99=""),"",IF(COUNT(AI99:AR99)=0,"",AS99-LOOKUP(2,1/(AI99:AR99<>""),AI99:AR99))) | IF(OR(F99="",AT99=""),"",IF(COUNT(AI99:AS99)=0,"",AT99-LOOKUP(2,1/(AI99:AS99<>""),AI99:AS99))) | IF(OR(F99="",AU99=""),"",IF(COUNT(AI99:AT99)=0,"",AU99-LOOKUP(2,1/(AI99:AT99<>""),AI99:AT99))) | IF(OR(F99="",AV99=""),"",IF(COUNT(AI99:AU99)=0,"",AV99-LOOKUP(2,1/(AI99:AU99<>""),AI99:AU99))) | IF(J99="","All_Provinces",IFERROR(VLOOKUP(J99,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K99="","All_Districts",IFERROR(VLOOKUP(K99,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F100="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 6 of 15 | AF2-DIS-N-058 | Gir Drip irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Pakteka | Sharana | Gari | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Fazal Din |  |  | IF(AQ100="","",AQ100) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W100<>"",W100,IF(OR(T100="",V100=""),"",EDATE(T100,V100))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Fazal Din | IF(F100="","",IF(COUNT(AI100:AV100)=0,IF(AA100="","Not started",AA100),SUBSTITUTE(LOOKUP(2,1/(AI100:AV100<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F100="",COUNT(AI100:AV100)=0),"",TODAY()-LOOKUP(2,1/(AI100:AV100<>""),AI100:AV100)) | IF(OR(F100="",COUNT(AI100:AV100)<2),"",LOOKUP(2,1/(AI100:AV100<>""),AI100:AV100)-MIN(AI100:AV100)) | IF(OR(AD100="",AC100="Not started",AC100=""),"",IFERROR(AD100-IF(VLOOKUP(AC100,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC100,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F100="","",IF(OR(AA100="Cancelled",AC100="Cancelled"),"Cancelled",IF(OR(AC100="Completed / Handover",Y100<>"",Z100>=100),"Completed — on track",IF(O100="Not awarded",IF(U100="",IF(X100="","No planned date",IF(TODAY()>X100,"Behind — past planned date",IF(X100-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U100,"Behind — award date passed",IF(U100-TODAY()<=30,"At risk — close to off track","On track"))),IF(X100="","No planned date",IF(AND(TODAY()>X100,OR(Z100="",Z100<100)),"Behind — past end date",IF(AND(T100<>"",X100<>"",Z100<>"",(Z100<100),((TODAY()-T100)/MAX(X100-T100,1)*100)-Z100>15),"Behind — progress lag",IF(AND(X100-TODAY()<=30,X100-TODAY()>=0,OR(Z100="",Z100<90)),"At risk — close to off track","On track")))))))) | IF(OR(F100="",AC100="Completed / Handover",AC100="Cancelled"),"",IF(O100="Not awarded",IF(U100<>"",U100-TODAY(),IF(X100="","",X100-TODAY())),IF(X100="","",X100-TODAY()))) | [14 empty] | IF(OR(F100="",AJ100=""),"",IF(COUNT(AI100:AI100)=0,"",AJ100-LOOKUP(2,1/(AI100:AI100<>""),AI100:AI100))) | IF(OR(F100="",AK100=""),"",IF(COUNT(AI100:AJ100)=0,"",AK100-LOOKUP(2,1/(AI100:AJ100<>""),AI100:AJ100))) | IF(OR(F100="",AL100=""),"",IF(COUNT(AI100:AK100)=0,"",AL100-LOOKUP(2,1/(AI100:AK100<>""),AI100:AK100))) | IF(OR(F100="",AM100=""),"",IF(COUNT(AI100:AL100)=0,"",AM100-LOOKUP(2,1/(AI100:AL100<>""),AI100:AL100))) | IF(OR(F100="",AN100=""),"",IF(COUNT(AI100:AM100)=0,"",AN100-LOOKUP(2,1/(AI100:AM100<>""),AI100:AM100))) | IF(OR(F100="",AO100=""),"",IF(COUNT(AI100:AN100)=0,"",AO100-LOOKUP(2,1/(AI100:AN100<>""),AI100:AN100))) | IF(OR(F100="",AP100=""),"",IF(COUNT(AI100:AO100)=0,"",AP100-LOOKUP(2,1/(AI100:AO100<>""),AI100:AO100))) | IF(OR(F100="",AQ100=""),"",IF(COUNT(AI100:AP100)=0,"",AQ100-LOOKUP(2,1/(AI100:AP100<>""),AI100:AP100))) | IF(OR(F100="",AR100=""),"",IF(COUNT(AI100:AQ100)=0,"",AR100-LOOKUP(2,1/(AI100:AQ100<>""),AI100:AQ100))) | IF(OR(F100="",AS100=""),"",IF(COUNT(AI100:AR100)=0,"",AS100-LOOKUP(2,1/(AI100:AR100<>""),AI100:AR100))) | IF(OR(F100="",AT100=""),"",IF(COUNT(AI100:AS100)=0,"",AT100-LOOKUP(2,1/(AI100:AS100<>""),AI100:AS100))) | IF(OR(F100="",AU100=""),"",IF(COUNT(AI100:AT100)=0,"",AU100-LOOKUP(2,1/(AI100:AT100<>""),AI100:AT100))) | IF(OR(F100="",AV100=""),"",IF(COUNT(AI100:AU100)=0,"",AV100-LOOKUP(2,1/(AI100:AU100<>""),AI100:AU100))) | IF(J100="","All_Provinces",IFERROR(VLOOKUP(J100,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K100="","All_Districts",IFERROR(VLOOKUP(K100,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F101="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 7 of 15 | AF2-DIS-N-059 | Hassan Khil- B Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktya | Ahmad Aba | Machalghu | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Zabihullah |  |  | IF(AQ101="","",AQ101) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W101<>"",W101,IF(OR(T101="",V101=""),"",EDATE(T101,V101))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Zabihullah | IF(F101="","",IF(COUNT(AI101:AV101)=0,IF(AA101="","Not started",AA101),SUBSTITUTE(LOOKUP(2,1/(AI101:AV101<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F101="",COUNT(AI101:AV101)=0),"",TODAY()-LOOKUP(2,1/(AI101:AV101<>""),AI101:AV101)) | IF(OR(F101="",COUNT(AI101:AV101)<2),"",LOOKUP(2,1/(AI101:AV101<>""),AI101:AV101)-MIN(AI101:AV101)) | IF(OR(AD101="",AC101="Not started",AC101=""),"",IFERROR(AD101-IF(VLOOKUP(AC101,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC101,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F101="","",IF(OR(AA101="Cancelled",AC101="Cancelled"),"Cancelled",IF(OR(AC101="Completed / Handover",Y101<>"",Z101>=100),"Completed — on track",IF(O101="Not awarded",IF(U101="",IF(X101="","No planned date",IF(TODAY()>X101,"Behind — past planned date",IF(X101-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U101,"Behind — award date passed",IF(U101-TODAY()<=30,"At risk — close to off track","On track"))),IF(X101="","No planned date",IF(AND(TODAY()>X101,OR(Z101="",Z101<100)),"Behind — past end date",IF(AND(T101<>"",X101<>"",Z101<>"",(Z101<100),((TODAY()-T101)/MAX(X101-T101,1)*100)-Z101>15),"Behind — progress lag",IF(AND(X101-TODAY()<=30,X101-TODAY()>=0,OR(Z101="",Z101<90)),"At risk — close to off track","On track")))))))) | IF(OR(F101="",AC101="Completed / Handover",AC101="Cancelled"),"",IF(O101="Not awarded",IF(U101<>"",U101-TODAY(),IF(X101="","",X101-TODAY())),IF(X101="","",X101-TODAY()))) | [14 empty] | IF(OR(F101="",AJ101=""),"",IF(COUNT(AI101:AI101)=0,"",AJ101-LOOKUP(2,1/(AI101:AI101<>""),AI101:AI101))) | IF(OR(F101="",AK101=""),"",IF(COUNT(AI101:AJ101)=0,"",AK101-LOOKUP(2,1/(AI101:AJ101<>""),AI101:AJ101))) | IF(OR(F101="",AL101=""),"",IF(COUNT(AI101:AK101)=0,"",AL101-LOOKUP(2,1/(AI101:AK101<>""),AI101:AK101))) | IF(OR(F101="",AM101=""),"",IF(COUNT(AI101:AL101)=0,"",AM101-LOOKUP(2,1/(AI101:AL101<>""),AI101:AL101))) | IF(OR(F101="",AN101=""),"",IF(COUNT(AI101:AM101)=0,"",AN101-LOOKUP(2,1/(AI101:AM101<>""),AI101:AM101))) | IF(OR(F101="",AO101=""),"",IF(COUNT(AI101:AN101)=0,"",AO101-LOOKUP(2,1/(AI101:AN101<>""),AI101:AN101))) | IF(OR(F101="",AP101=""),"",IF(COUNT(AI101:AO101)=0,"",AP101-LOOKUP(2,1/(AI101:AO101<>""),AI101:AO101))) | IF(OR(F101="",AQ101=""),"",IF(COUNT(AI101:AP101)=0,"",AQ101-LOOKUP(2,1/(AI101:AP101<>""),AI101:AP101))) | IF(OR(F101="",AR101=""),"",IF(COUNT(AI101:AQ101)=0,"",AR101-LOOKUP(2,1/(AI101:AQ101<>""),AI101:AQ101))) | IF(OR(F101="",AS101=""),"",IF(COUNT(AI101:AR101)=0,"",AS101-LOOKUP(2,1/(AI101:AR101<>""),AI101:AR101))) | IF(OR(F101="",AT101=""),"",IF(COUNT(AI101:AS101)=0,"",AT101-LOOKUP(2,1/(AI101:AS101<>""),AI101:AS101))) | IF(OR(F101="",AU101=""),"",IF(COUNT(AI101:AT101)=0,"",AU101-LOOKUP(2,1/(AI101:AT101<>""),AI101:AT101))) | IF(OR(F101="",AV101=""),"",IF(COUNT(AI101:AU101)=0,"",AV101-LOOKUP(2,1/(AI101:AU101<>""),AI101:AU101))) | IF(J101="","All_Provinces",IFERROR(VLOOKUP(J101,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K101="","All_Districts",IFERROR(VLOOKUP(K101,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F102="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 8 of 15 | AF2-DIS-N-060 | Hassan Khil-A Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktya | Ahmad Aba | Machalghu | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Hasan Khil |  |  | IF(AQ102="","",AQ102) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W102<>"",W102,IF(OR(T102="",V102=""),"",EDATE(T102,V102))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Hasan Khil | IF(F102="","",IF(COUNT(AI102:AV102)=0,IF(AA102="","Not started",AA102),SUBSTITUTE(LOOKUP(2,1/(AI102:AV102<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F102="",COUNT(AI102:AV102)=0),"",TODAY()-LOOKUP(2,1/(AI102:AV102<>""),AI102:AV102)) | IF(OR(F102="",COUNT(AI102:AV102)<2),"",LOOKUP(2,1/(AI102:AV102<>""),AI102:AV102)-MIN(AI102:AV102)) | IF(OR(AD102="",AC102="Not started",AC102=""),"",IFERROR(AD102-IF(VLOOKUP(AC102,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC102,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F102="","",IF(OR(AA102="Cancelled",AC102="Cancelled"),"Cancelled",IF(OR(AC102="Completed / Handover",Y102<>"",Z102>=100),"Completed — on track",IF(O102="Not awarded",IF(U102="",IF(X102="","No planned date",IF(TODAY()>X102,"Behind — past planned date",IF(X102-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U102,"Behind — award date passed",IF(U102-TODAY()<=30,"At risk — close to off track","On track"))),IF(X102="","No planned date",IF(AND(TODAY()>X102,OR(Z102="",Z102<100)),"Behind — past end date",IF(AND(T102<>"",X102<>"",Z102<>"",(Z102<100),((TODAY()-T102)/MAX(X102-T102,1)*100)-Z102>15),"Behind — progress lag",IF(AND(X102-TODAY()<=30,X102-TODAY()>=0,OR(Z102="",Z102<90)),"At risk — close to off track","On track")))))))) | IF(OR(F102="",AC102="Completed / Handover",AC102="Cancelled"),"",IF(O102="Not awarded",IF(U102<>"",U102-TODAY(),IF(X102="","",X102-TODAY())),IF(X102="","",X102-TODAY()))) | [14 empty] | IF(OR(F102="",AJ102=""),"",IF(COUNT(AI102:AI102)=0,"",AJ102-LOOKUP(2,1/(AI102:AI102<>""),AI102:AI102))) | IF(OR(F102="",AK102=""),"",IF(COUNT(AI102:AJ102)=0,"",AK102-LOOKUP(2,1/(AI102:AJ102<>""),AI102:AJ102))) | IF(OR(F102="",AL102=""),"",IF(COUNT(AI102:AK102)=0,"",AL102-LOOKUP(2,1/(AI102:AK102<>""),AI102:AK102))) | IF(OR(F102="",AM102=""),"",IF(COUNT(AI102:AL102)=0,"",AM102-LOOKUP(2,1/(AI102:AL102<>""),AI102:AL102))) | IF(OR(F102="",AN102=""),"",IF(COUNT(AI102:AM102)=0,"",AN102-LOOKUP(2,1/(AI102:AM102<>""),AI102:AM102))) | IF(OR(F102="",AO102=""),"",IF(COUNT(AI102:AN102)=0,"",AO102-LOOKUP(2,1/(AI102:AN102<>""),AI102:AN102))) | IF(OR(F102="",AP102=""),"",IF(COUNT(AI102:AO102)=0,"",AP102-LOOKUP(2,1/(AI102:AO102<>""),AI102:AO102))) | IF(OR(F102="",AQ102=""),"",IF(COUNT(AI102:AP102)=0,"",AQ102-LOOKUP(2,1/(AI102:AP102<>""),AI102:AP102))) | IF(OR(F102="",AR102=""),"",IF(COUNT(AI102:AQ102)=0,"",AR102-LOOKUP(2,1/(AI102:AQ102<>""),AI102:AQ102))) | IF(OR(F102="",AS102=""),"",IF(COUNT(AI102:AR102)=0,"",AS102-LOOKUP(2,1/(AI102:AR102<>""),AI102:AR102))) | IF(OR(F102="",AT102=""),"",IF(COUNT(AI102:AS102)=0,"",AT102-LOOKUP(2,1/(AI102:AS102<>""),AI102:AS102))) | IF(OR(F102="",AU102=""),"",IF(COUNT(AI102:AT102)=0,"",AU102-LOOKUP(2,1/(AI102:AT102<>""),AI102:AT102))) | IF(OR(F102="",AV102=""),"",IF(COUNT(AI102:AU102)=0,"",AV102-LOOKUP(2,1/(AI102:AU102<>""),AI102:AU102))) | IF(J102="","All_Provinces",IFERROR(VLOOKUP(J102,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K102="","All_Districts",IFERROR(VLOOKUP(K102,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F103="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 9 of 15 | AF2-DIS-N-061 | Logar University Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Logar | Pole Alam | Logar University | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Islam Gul |  |  | IF(AQ103="","",AQ103) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W103<>"",W103,IF(OR(T103="",V103=""),"",EDATE(T103,V103))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Islam Gul | IF(F103="","",IF(COUNT(AI103:AV103)=0,IF(AA103="","Not started",AA103),SUBSTITUTE(LOOKUP(2,1/(AI103:AV103<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F103="",COUNT(AI103:AV103)=0),"",TODAY()-LOOKUP(2,1/(AI103:AV103<>""),AI103:AV103)) | IF(OR(F103="",COUNT(AI103:AV103)<2),"",LOOKUP(2,1/(AI103:AV103<>""),AI103:AV103)-MIN(AI103:AV103)) | IF(OR(AD103="",AC103="Not started",AC103=""),"",IFERROR(AD103-IF(VLOOKUP(AC103,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC103,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F103="","",IF(OR(AA103="Cancelled",AC103="Cancelled"),"Cancelled",IF(OR(AC103="Completed / Handover",Y103<>"",Z103>=100),"Completed — on track",IF(O103="Not awarded",IF(U103="",IF(X103="","No planned date",IF(TODAY()>X103,"Behind — past planned date",IF(X103-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U103,"Behind — award date passed",IF(U103-TODAY()<=30,"At risk — close to off track","On track"))),IF(X103="","No planned date",IF(AND(TODAY()>X103,OR(Z103="",Z103<100)),"Behind — past end date",IF(AND(T103<>"",X103<>"",Z103<>"",(Z103<100),((TODAY()-T103)/MAX(X103-T103,1)*100)-Z103>15),"Behind — progress lag",IF(AND(X103-TODAY()<=30,X103-TODAY()>=0,OR(Z103="",Z103<90)),"At risk — close to off track","On track")))))))) | IF(OR(F103="",AC103="Completed / Handover",AC103="Cancelled"),"",IF(O103="Not awarded",IF(U103<>"",U103-TODAY(),IF(X103="","",X103-TODAY())),IF(X103="","",X103-TODAY()))) | [14 empty] | IF(OR(F103="",AJ103=""),"",IF(COUNT(AI103:AI103)=0,"",AJ103-LOOKUP(2,1/(AI103:AI103<>""),AI103:AI103))) | IF(OR(F103="",AK103=""),"",IF(COUNT(AI103:AJ103)=0,"",AK103-LOOKUP(2,1/(AI103:AJ103<>""),AI103:AJ103))) | IF(OR(F103="",AL103=""),"",IF(COUNT(AI103:AK103)=0,"",AL103-LOOKUP(2,1/(AI103:AK103<>""),AI103:AK103))) | IF(OR(F103="",AM103=""),"",IF(COUNT(AI103:AL103)=0,"",AM103-LOOKUP(2,1/(AI103:AL103<>""),AI103:AL103))) | IF(OR(F103="",AN103=""),"",IF(COUNT(AI103:AM103)=0,"",AN103-LOOKUP(2,1/(AI103:AM103<>""),AI103:AM103))) | IF(OR(F103="",AO103=""),"",IF(COUNT(AI103:AN103)=0,"",AO103-LOOKUP(2,1/(AI103:AN103<>""),AI103:AN103))) | IF(OR(F103="",AP103=""),"",IF(COUNT(AI103:AO103)=0,"",AP103-LOOKUP(2,1/(AI103:AO103<>""),AI103:AO103))) | IF(OR(F103="",AQ103=""),"",IF(COUNT(AI103:AP103)=0,"",AQ103-LOOKUP(2,1/(AI103:AP103<>""),AI103:AP103))) | IF(OR(F103="",AR103=""),"",IF(COUNT(AI103:AQ103)=0,"",AR103-LOOKUP(2,1/(AI103:AQ103<>""),AI103:AQ103))) | IF(OR(F103="",AS103=""),"",IF(COUNT(AI103:AR103)=0,"",AS103-LOOKUP(2,1/(AI103:AR103<>""),AI103:AR103))) | IF(OR(F103="",AT103=""),"",IF(COUNT(AI103:AS103)=0,"",AT103-LOOKUP(2,1/(AI103:AS103<>""),AI103:AS103))) | IF(OR(F103="",AU103=""),"",IF(COUNT(AI103:AT103)=0,"",AU103-LOOKUP(2,1/(AI103:AT103<>""),AI103:AT103))) | IF(OR(F103="",AV103=""),"",IF(COUNT(AI103:AU103)=0,"",AV103-LOOKUP(2,1/(AI103:AU103<>""),AI103:AU103))) | IF(J103="","All_Provinces",IFERROR(VLOOKUP(J103,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K103="","All_Districts",IFERROR(VLOOKUP(K103,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F104="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 10 of 15 | AF2-DIS-N-062 | Milma Kot Bagh Drip Irrigation Schem | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Matoon | Milma Kot Bagh | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Saifullah |  |  | IF(AQ104="","",AQ104) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W104<>"",W104,IF(OR(T104="",V104=""),"",EDATE(T104,V104))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Saifullah | IF(F104="","",IF(COUNT(AI104:AV104)=0,IF(AA104="","Not started",AA104),SUBSTITUTE(LOOKUP(2,1/(AI104:AV104<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F104="",COUNT(AI104:AV104)=0),"",TODAY()-LOOKUP(2,1/(AI104:AV104<>""),AI104:AV104)) | IF(OR(F104="",COUNT(AI104:AV104)<2),"",LOOKUP(2,1/(AI104:AV104<>""),AI104:AV104)-MIN(AI104:AV104)) | IF(OR(AD104="",AC104="Not started",AC104=""),"",IFERROR(AD104-IF(VLOOKUP(AC104,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC104,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F104="","",IF(OR(AA104="Cancelled",AC104="Cancelled"),"Cancelled",IF(OR(AC104="Completed / Handover",Y104<>"",Z104>=100),"Completed — on track",IF(O104="Not awarded",IF(U104="",IF(X104="","No planned date",IF(TODAY()>X104,"Behind — past planned date",IF(X104-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U104,"Behind — award date passed",IF(U104-TODAY()<=30,"At risk — close to off track","On track"))),IF(X104="","No planned date",IF(AND(TODAY()>X104,OR(Z104="",Z104<100)),"Behind — past end date",IF(AND(T104<>"",X104<>"",Z104<>"",(Z104<100),((TODAY()-T104)/MAX(X104-T104,1)*100)-Z104>15),"Behind — progress lag",IF(AND(X104-TODAY()<=30,X104-TODAY()>=0,OR(Z104="",Z104<90)),"At risk — close to off track","On track")))))))) | IF(OR(F104="",AC104="Completed / Handover",AC104="Cancelled"),"",IF(O104="Not awarded",IF(U104<>"",U104-TODAY(),IF(X104="","",X104-TODAY())),IF(X104="","",X104-TODAY()))) | [14 empty] | IF(OR(F104="",AJ104=""),"",IF(COUNT(AI104:AI104)=0,"",AJ104-LOOKUP(2,1/(AI104:AI104<>""),AI104:AI104))) | IF(OR(F104="",AK104=""),"",IF(COUNT(AI104:AJ104)=0,"",AK104-LOOKUP(2,1/(AI104:AJ104<>""),AI104:AJ104))) | IF(OR(F104="",AL104=""),"",IF(COUNT(AI104:AK104)=0,"",AL104-LOOKUP(2,1/(AI104:AK104<>""),AI104:AK104))) | IF(OR(F104="",AM104=""),"",IF(COUNT(AI104:AL104)=0,"",AM104-LOOKUP(2,1/(AI104:AL104<>""),AI104:AL104))) | IF(OR(F104="",AN104=""),"",IF(COUNT(AI104:AM104)=0,"",AN104-LOOKUP(2,1/(AI104:AM104<>""),AI104:AM104))) | IF(OR(F104="",AO104=""),"",IF(COUNT(AI104:AN104)=0,"",AO104-LOOKUP(2,1/(AI104:AN104<>""),AI104:AN104))) | IF(OR(F104="",AP104=""),"",IF(COUNT(AI104:AO104)=0,"",AP104-LOOKUP(2,1/(AI104:AO104<>""),AI104:AO104))) | IF(OR(F104="",AQ104=""),"",IF(COUNT(AI104:AP104)=0,"",AQ104-LOOKUP(2,1/(AI104:AP104<>""),AI104:AP104))) | IF(OR(F104="",AR104=""),"",IF(COUNT(AI104:AQ104)=0,"",AR104-LOOKUP(2,1/(AI104:AQ104<>""),AI104:AQ104))) | IF(OR(F104="",AS104=""),"",IF(COUNT(AI104:AR104)=0,"",AS104-LOOKUP(2,1/(AI104:AR104<>""),AI104:AR104))) | IF(OR(F104="",AT104=""),"",IF(COUNT(AI104:AS104)=0,"",AT104-LOOKUP(2,1/(AI104:AS104<>""),AI104:AS104))) | IF(OR(F104="",AU104=""),"",IF(COUNT(AI104:AT104)=0,"",AU104-LOOKUP(2,1/(AI104:AT104<>""),AI104:AT104))) | IF(OR(F104="",AV104=""),"",IF(COUNT(AI104:AU104)=0,"",AV104-LOOKUP(2,1/(AI104:AU104<>""),AI104:AU104))) | IF(J104="","All_Provinces",IFERROR(VLOOKUP(J104,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K104="","All_Districts",IFERROR(VLOOKUP(K104,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F105="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 11 of 15 | AF2-DIS-N-063 | Nawe Patana Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Pakteka | Sharana | Patana | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ghazi Khan |  |  | IF(AQ105="","",AQ105) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W105<>"",W105,IF(OR(T105="",V105=""),"",EDATE(T105,V105))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Ghazi Khan | IF(F105="","",IF(COUNT(AI105:AV105)=0,IF(AA105="","Not started",AA105),SUBSTITUTE(LOOKUP(2,1/(AI105:AV105<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F105="",COUNT(AI105:AV105)=0),"",TODAY()-LOOKUP(2,1/(AI105:AV105<>""),AI105:AV105)) | IF(OR(F105="",COUNT(AI105:AV105)<2),"",LOOKUP(2,1/(AI105:AV105<>""),AI105:AV105)-MIN(AI105:AV105)) | IF(OR(AD105="",AC105="Not started",AC105=""),"",IFERROR(AD105-IF(VLOOKUP(AC105,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC105,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F105="","",IF(OR(AA105="Cancelled",AC105="Cancelled"),"Cancelled",IF(OR(AC105="Completed / Handover",Y105<>"",Z105>=100),"Completed — on track",IF(O105="Not awarded",IF(U105="",IF(X105="","No planned date",IF(TODAY()>X105,"Behind — past planned date",IF(X105-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U105,"Behind — award date passed",IF(U105-TODAY()<=30,"At risk — close to off track","On track"))),IF(X105="","No planned date",IF(AND(TODAY()>X105,OR(Z105="",Z105<100)),"Behind — past end date",IF(AND(T105<>"",X105<>"",Z105<>"",(Z105<100),((TODAY()-T105)/MAX(X105-T105,1)*100)-Z105>15),"Behind — progress lag",IF(AND(X105-TODAY()<=30,X105-TODAY()>=0,OR(Z105="",Z105<90)),"At risk — close to off track","On track")))))))) | IF(OR(F105="",AC105="Completed / Handover",AC105="Cancelled"),"",IF(O105="Not awarded",IF(U105<>"",U105-TODAY(),IF(X105="","",X105-TODAY())),IF(X105="","",X105-TODAY()))) | [14 empty] | IF(OR(F105="",AJ105=""),"",IF(COUNT(AI105:AI105)=0,"",AJ105-LOOKUP(2,1/(AI105:AI105<>""),AI105:AI105))) | IF(OR(F105="",AK105=""),"",IF(COUNT(AI105:AJ105)=0,"",AK105-LOOKUP(2,1/(AI105:AJ105<>""),AI105:AJ105))) | IF(OR(F105="",AL105=""),"",IF(COUNT(AI105:AK105)=0,"",AL105-LOOKUP(2,1/(AI105:AK105<>""),AI105:AK105))) | IF(OR(F105="",AM105=""),"",IF(COUNT(AI105:AL105)=0,"",AM105-LOOKUP(2,1/(AI105:AL105<>""),AI105:AL105))) | IF(OR(F105="",AN105=""),"",IF(COUNT(AI105:AM105)=0,"",AN105-LOOKUP(2,1/(AI105:AM105<>""),AI105:AM105))) | IF(OR(F105="",AO105=""),"",IF(COUNT(AI105:AN105)=0,"",AO105-LOOKUP(2,1/(AI105:AN105<>""),AI105:AN105))) | IF(OR(F105="",AP105=""),"",IF(COUNT(AI105:AO105)=0,"",AP105-LOOKUP(2,1/(AI105:AO105<>""),AI105:AO105))) | IF(OR(F105="",AQ105=""),"",IF(COUNT(AI105:AP105)=0,"",AQ105-LOOKUP(2,1/(AI105:AP105<>""),AI105:AP105))) | IF(OR(F105="",AR105=""),"",IF(COUNT(AI105:AQ105)=0,"",AR105-LOOKUP(2,1/(AI105:AQ105<>""),AI105:AQ105))) | IF(OR(F105="",AS105=""),"",IF(COUNT(AI105:AR105)=0,"",AS105-LOOKUP(2,1/(AI105:AR105<>""),AI105:AR105))) | IF(OR(F105="",AT105=""),"",IF(COUNT(AI105:AS105)=0,"",AT105-LOOKUP(2,1/(AI105:AS105<>""),AI105:AS105))) | IF(OR(F105="",AU105=""),"",IF(COUNT(AI105:AT105)=0,"",AU105-LOOKUP(2,1/(AI105:AT105<>""),AI105:AT105))) | IF(OR(F105="",AV105=""),"",IF(COUNT(AI105:AU105)=0,"",AV105-LOOKUP(2,1/(AI105:AU105<>""),AI105:AU105))) | IF(J105="","All_Provinces",IFERROR(VLOOKUP(J105,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K105="","All_Districts",IFERROR(VLOOKUP(K105,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F106="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 12 of 15 | AF2-DIS-N-064 | Nughi Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Ghazni | Center | Nughi | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Hakim Khan |  |  | IF(AQ106="","",AQ106) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W106<>"",W106,IF(OR(T106="",V106=""),"",EDATE(T106,V106))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Hakim Khan | IF(F106="","",IF(COUNT(AI106:AV106)=0,IF(AA106="","Not started",AA106),SUBSTITUTE(LOOKUP(2,1/(AI106:AV106<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F106="",COUNT(AI106:AV106)=0),"",TODAY()-LOOKUP(2,1/(AI106:AV106<>""),AI106:AV106)) | IF(OR(F106="",COUNT(AI106:AV106)<2),"",LOOKUP(2,1/(AI106:AV106<>""),AI106:AV106)-MIN(AI106:AV106)) | IF(OR(AD106="",AC106="Not started",AC106=""),"",IFERROR(AD106-IF(VLOOKUP(AC106,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC106,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F106="","",IF(OR(AA106="Cancelled",AC106="Cancelled"),"Cancelled",IF(OR(AC106="Completed / Handover",Y106<>"",Z106>=100),"Completed — on track",IF(O106="Not awarded",IF(U106="",IF(X106="","No planned date",IF(TODAY()>X106,"Behind — past planned date",IF(X106-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U106,"Behind — award date passed",IF(U106-TODAY()<=30,"At risk — close to off track","On track"))),IF(X106="","No planned date",IF(AND(TODAY()>X106,OR(Z106="",Z106<100)),"Behind — past end date",IF(AND(T106<>"",X106<>"",Z106<>"",(Z106<100),((TODAY()-T106)/MAX(X106-T106,1)*100)-Z106>15),"Behind — progress lag",IF(AND(X106-TODAY()<=30,X106-TODAY()>=0,OR(Z106="",Z106<90)),"At risk — close to off track","On track")))))))) | IF(OR(F106="",AC106="Completed / Handover",AC106="Cancelled"),"",IF(O106="Not awarded",IF(U106<>"",U106-TODAY(),IF(X106="","",X106-TODAY())),IF(X106="","",X106-TODAY()))) | [14 empty] | IF(OR(F106="",AJ106=""),"",IF(COUNT(AI106:AI106)=0,"",AJ106-LOOKUP(2,1/(AI106:AI106<>""),AI106:AI106))) | IF(OR(F106="",AK106=""),"",IF(COUNT(AI106:AJ106)=0,"",AK106-LOOKUP(2,1/(AI106:AJ106<>""),AI106:AJ106))) | IF(OR(F106="",AL106=""),"",IF(COUNT(AI106:AK106)=0,"",AL106-LOOKUP(2,1/(AI106:AK106<>""),AI106:AK106))) | IF(OR(F106="",AM106=""),"",IF(COUNT(AI106:AL106)=0,"",AM106-LOOKUP(2,1/(AI106:AL106<>""),AI106:AL106))) | IF(OR(F106="",AN106=""),"",IF(COUNT(AI106:AM106)=0,"",AN106-LOOKUP(2,1/(AI106:AM106<>""),AI106:AM106))) | IF(OR(F106="",AO106=""),"",IF(COUNT(AI106:AN106)=0,"",AO106-LOOKUP(2,1/(AI106:AN106<>""),AI106:AN106))) | IF(OR(F106="",AP106=""),"",IF(COUNT(AI106:AO106)=0,"",AP106-LOOKUP(2,1/(AI106:AO106<>""),AI106:AO106))) | IF(OR(F106="",AQ106=""),"",IF(COUNT(AI106:AP106)=0,"",AQ106-LOOKUP(2,1/(AI106:AP106<>""),AI106:AP106))) | IF(OR(F106="",AR106=""),"",IF(COUNT(AI106:AQ106)=0,"",AR106-LOOKUP(2,1/(AI106:AQ106<>""),AI106:AQ106))) | IF(OR(F106="",AS106=""),"",IF(COUNT(AI106:AR106)=0,"",AS106-LOOKUP(2,1/(AI106:AR106<>""),AI106:AR106))) | IF(OR(F106="",AT106=""),"",IF(COUNT(AI106:AS106)=0,"",AT106-LOOKUP(2,1/(AI106:AS106<>""),AI106:AS106))) | IF(OR(F106="",AU106=""),"",IF(COUNT(AI106:AT106)=0,"",AU106-LOOKUP(2,1/(AI106:AT106<>""),AI106:AT106))) | IF(OR(F106="",AV106=""),"",IF(COUNT(AI106:AU106)=0,"",AV106-LOOKUP(2,1/(AI106:AU106<>""),AI106:AU106))) | IF(J106="","All_Provinces",IFERROR(VLOOKUP(J106,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K106="","All_Districts",IFERROR(VLOOKUP(K106,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F107="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 13 of 15 | AF2-DIS-N-065 | Paktia University Drip irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktya | Gardez_center | Beland Mazal | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Rasool Gharani |  |  | IF(AQ107="","",AQ107) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W107<>"",W107,IF(OR(T107="",V107=""),"",EDATE(T107,V107))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Mohammad Rasool Gharani | IF(F107="","",IF(COUNT(AI107:AV107)=0,IF(AA107="","Not started",AA107),SUBSTITUTE(LOOKUP(2,1/(AI107:AV107<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F107="",COUNT(AI107:AV107)=0),"",TODAY()-LOOKUP(2,1/(AI107:AV107<>""),AI107:AV107)) | IF(OR(F107="",COUNT(AI107:AV107)<2),"",LOOKUP(2,1/(AI107:AV107<>""),AI107:AV107)-MIN(AI107:AV107)) | IF(OR(AD107="",AC107="Not started",AC107=""),"",IFERROR(AD107-IF(VLOOKUP(AC107,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC107,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F107="","",IF(OR(AA107="Cancelled",AC107="Cancelled"),"Cancelled",IF(OR(AC107="Completed / Handover",Y107<>"",Z107>=100),"Completed — on track",IF(O107="Not awarded",IF(U107="",IF(X107="","No planned date",IF(TODAY()>X107,"Behind — past planned date",IF(X107-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U107,"Behind — award date passed",IF(U107-TODAY()<=30,"At risk — close to off track","On track"))),IF(X107="","No planned date",IF(AND(TODAY()>X107,OR(Z107="",Z107<100)),"Behind — past end date",IF(AND(T107<>"",X107<>"",Z107<>"",(Z107<100),((TODAY()-T107)/MAX(X107-T107,1)*100)-Z107>15),"Behind — progress lag",IF(AND(X107-TODAY()<=30,X107-TODAY()>=0,OR(Z107="",Z107<90)),"At risk — close to off track","On track")))))))) | IF(OR(F107="",AC107="Completed / Handover",AC107="Cancelled"),"",IF(O107="Not awarded",IF(U107<>"",U107-TODAY(),IF(X107="","",X107-TODAY())),IF(X107="","",X107-TODAY()))) | [14 empty] | IF(OR(F107="",AJ107=""),"",IF(COUNT(AI107:AI107)=0,"",AJ107-LOOKUP(2,1/(AI107:AI107<>""),AI107:AI107))) | IF(OR(F107="",AK107=""),"",IF(COUNT(AI107:AJ107)=0,"",AK107-LOOKUP(2,1/(AI107:AJ107<>""),AI107:AJ107))) | IF(OR(F107="",AL107=""),"",IF(COUNT(AI107:AK107)=0,"",AL107-LOOKUP(2,1/(AI107:AK107<>""),AI107:AK107))) | IF(OR(F107="",AM107=""),"",IF(COUNT(AI107:AL107)=0,"",AM107-LOOKUP(2,1/(AI107:AL107<>""),AI107:AL107))) | IF(OR(F107="",AN107=""),"",IF(COUNT(AI107:AM107)=0,"",AN107-LOOKUP(2,1/(AI107:AM107<>""),AI107:AM107))) | IF(OR(F107="",AO107=""),"",IF(COUNT(AI107:AN107)=0,"",AO107-LOOKUP(2,1/(AI107:AN107<>""),AI107:AN107))) | IF(OR(F107="",AP107=""),"",IF(COUNT(AI107:AO107)=0,"",AP107-LOOKUP(2,1/(AI107:AO107<>""),AI107:AO107))) | IF(OR(F107="",AQ107=""),"",IF(COUNT(AI107:AP107)=0,"",AQ107-LOOKUP(2,1/(AI107:AP107<>""),AI107:AP107))) | IF(OR(F107="",AR107=""),"",IF(COUNT(AI107:AQ107)=0,"",AR107-LOOKUP(2,1/(AI107:AQ107<>""),AI107:AQ107))) | IF(OR(F107="",AS107=""),"",IF(COUNT(AI107:AR107)=0,"",AS107-LOOKUP(2,1/(AI107:AR107<>""),AI107:AR107))) | IF(OR(F107="",AT107=""),"",IF(COUNT(AI107:AS107)=0,"",AT107-LOOKUP(2,1/(AI107:AS107<>""),AI107:AS107))) | IF(OR(F107="",AU107=""),"",IF(COUNT(AI107:AT107)=0,"",AU107-LOOKUP(2,1/(AI107:AT107<>""),AI107:AT107))) | IF(OR(F107="",AV107=""),"",IF(COUNT(AI107:AU107)=0,"",AV107-LOOKUP(2,1/(AI107:AU107<>""),AI107:AU107))) | IF(J107="","All_Provinces",IFERROR(VLOOKUP(J107,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K107="","All_Districts",IFERROR(VLOOKUP(K107,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F108="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 14 of 15 | AF2-DIS-N-066 | Sahra Bagh Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Matoon | Sahra bagh | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Gafoor Jan |  |  | IF(AQ108="","",AQ108) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W108<>"",W108,IF(OR(T108="",V108=""),"",EDATE(T108,V108))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Gafoor Jan | IF(F108="","",IF(COUNT(AI108:AV108)=0,IF(AA108="","Not started",AA108),SUBSTITUTE(LOOKUP(2,1/(AI108:AV108<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F108="",COUNT(AI108:AV108)=0),"",TODAY()-LOOKUP(2,1/(AI108:AV108<>""),AI108:AV108)) | IF(OR(F108="",COUNT(AI108:AV108)<2),"",LOOKUP(2,1/(AI108:AV108<>""),AI108:AV108)-MIN(AI108:AV108)) | IF(OR(AD108="",AC108="Not started",AC108=""),"",IFERROR(AD108-IF(VLOOKUP(AC108,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC108,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F108="","",IF(OR(AA108="Cancelled",AC108="Cancelled"),"Cancelled",IF(OR(AC108="Completed / Handover",Y108<>"",Z108>=100),"Completed — on track",IF(O108="Not awarded",IF(U108="",IF(X108="","No planned date",IF(TODAY()>X108,"Behind — past planned date",IF(X108-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U108,"Behind — award date passed",IF(U108-TODAY()<=30,"At risk — close to off track","On track"))),IF(X108="","No planned date",IF(AND(TODAY()>X108,OR(Z108="",Z108<100)),"Behind — past end date",IF(AND(T108<>"",X108<>"",Z108<>"",(Z108<100),((TODAY()-T108)/MAX(X108-T108,1)*100)-Z108>15),"Behind — progress lag",IF(AND(X108-TODAY()<=30,X108-TODAY()>=0,OR(Z108="",Z108<90)),"At risk — close to off track","On track")))))))) | IF(OR(F108="",AC108="Completed / Handover",AC108="Cancelled"),"",IF(O108="Not awarded",IF(U108<>"",U108-TODAY(),IF(X108="","",X108-TODAY())),IF(X108="","",X108-TODAY()))) | [14 empty] | IF(OR(F108="",AJ108=""),"",IF(COUNT(AI108:AI108)=0,"",AJ108-LOOKUP(2,1/(AI108:AI108<>""),AI108:AI108))) | IF(OR(F108="",AK108=""),"",IF(COUNT(AI108:AJ108)=0,"",AK108-LOOKUP(2,1/(AI108:AJ108<>""),AI108:AJ108))) | IF(OR(F108="",AL108=""),"",IF(COUNT(AI108:AK108)=0,"",AL108-LOOKUP(2,1/(AI108:AK108<>""),AI108:AK108))) | IF(OR(F108="",AM108=""),"",IF(COUNT(AI108:AL108)=0,"",AM108-LOOKUP(2,1/(AI108:AL108<>""),AI108:AL108))) | IF(OR(F108="",AN108=""),"",IF(COUNT(AI108:AM108)=0,"",AN108-LOOKUP(2,1/(AI108:AM108<>""),AI108:AM108))) | IF(OR(F108="",AO108=""),"",IF(COUNT(AI108:AN108)=0,"",AO108-LOOKUP(2,1/(AI108:AN108<>""),AI108:AN108))) | IF(OR(F108="",AP108=""),"",IF(COUNT(AI108:AO108)=0,"",AP108-LOOKUP(2,1/(AI108:AO108<>""),AI108:AO108))) | IF(OR(F108="",AQ108=""),"",IF(COUNT(AI108:AP108)=0,"",AQ108-LOOKUP(2,1/(AI108:AP108<>""),AI108:AP108))) | IF(OR(F108="",AR108=""),"",IF(COUNT(AI108:AQ108)=0,"",AR108-LOOKUP(2,1/(AI108:AQ108<>""),AI108:AQ108))) | IF(OR(F108="",AS108=""),"",IF(COUNT(AI108:AR108)=0,"",AS108-LOOKUP(2,1/(AI108:AR108<>""),AI108:AR108))) | IF(OR(F108="",AT108=""),"",IF(COUNT(AI108:AS108)=0,"",AT108-LOOKUP(2,1/(AI108:AS108<>""),AI108:AS108))) | IF(OR(F108="",AU108=""),"",IF(COUNT(AI108:AT108)=0,"",AU108-LOOKUP(2,1/(AI108:AT108<>""),AI108:AT108))) | IF(OR(F108="",AV108=""),"",IF(COUNT(AI108:AU108)=0,"",AV108-LOOKUP(2,1/(AI108:AU108<>""),AI108:AU108))) | IF(J108="","All_Provinces",IFERROR(VLOOKUP(J108,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K108="","All_Districts",IFERROR(VLOOKUP(K108,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F109="","",ROW()-3) | AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | 15 of 15 | AF2-DIS-N-067 | Sultani Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Pakteka | Sarhawza | Sultani | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Akhtar Mohammad |  |  | IF(AQ109="","",AQ109) | 2026-12-25 | 6.2 | 2027-07-03 | IF(W109<>"",W109,IF(OR(T109="",V109=""),"",EDATE(T109,V109))) |  |  | Retendered (Re-ITB) | Slack period up to end March. Four months construction period starting from April 2026. ¦ Farmer: Akhtar Mohammad | IF(F109="","",IF(COUNT(AI109:AV109)=0,IF(AA109="","Not started",AA109),SUBSTITUTE(LOOKUP(2,1/(AI109:AV109<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F109="",COUNT(AI109:AV109)=0),"",TODAY()-LOOKUP(2,1/(AI109:AV109<>""),AI109:AV109)) | IF(OR(F109="",COUNT(AI109:AV109)<2),"",LOOKUP(2,1/(AI109:AV109<>""),AI109:AV109)-MIN(AI109:AV109)) | IF(OR(AD109="",AC109="Not started",AC109=""),"",IFERROR(AD109-IF(VLOOKUP(AC109,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC109,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F109="","",IF(OR(AA109="Cancelled",AC109="Cancelled"),"Cancelled",IF(OR(AC109="Completed / Handover",Y109<>"",Z109>=100),"Completed — on track",IF(O109="Not awarded",IF(U109="",IF(X109="","No planned date",IF(TODAY()>X109,"Behind — past planned date",IF(X109-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U109,"Behind — award date passed",IF(U109-TODAY()<=30,"At risk — close to off track","On track"))),IF(X109="","No planned date",IF(AND(TODAY()>X109,OR(Z109="",Z109<100)),"Behind — past end date",IF(AND(T109<>"",X109<>"",Z109<>"",(Z109<100),((TODAY()-T109)/MAX(X109-T109,1)*100)-Z109>15),"Behind — progress lag",IF(AND(X109-TODAY()<=30,X109-TODAY()>=0,OR(Z109="",Z109<90)),"At risk — close to off track","On track")))))))) | IF(OR(F109="",AC109="Completed / Handover",AC109="Cancelled"),"",IF(O109="Not awarded",IF(U109<>"",U109-TODAY(),IF(X109="","",X109-TODAY())),IF(X109="","",X109-TODAY()))) | [14 empty] | IF(OR(F109="",AJ109=""),"",IF(COUNT(AI109:AI109)=0,"",AJ109-LOOKUP(2,1/(AI109:AI109<>""),AI109:AI109))) | IF(OR(F109="",AK109=""),"",IF(COUNT(AI109:AJ109)=0,"",AK109-LOOKUP(2,1/(AI109:AJ109<>""),AI109:AJ109))) | IF(OR(F109="",AL109=""),"",IF(COUNT(AI109:AK109)=0,"",AL109-LOOKUP(2,1/(AI109:AK109<>""),AI109:AK109))) | IF(OR(F109="",AM109=""),"",IF(COUNT(AI109:AL109)=0,"",AM109-LOOKUP(2,1/(AI109:AL109<>""),AI109:AL109))) | IF(OR(F109="",AN109=""),"",IF(COUNT(AI109:AM109)=0,"",AN109-LOOKUP(2,1/(AI109:AM109<>""),AI109:AM109))) | IF(OR(F109="",AO109=""),"",IF(COUNT(AI109:AN109)=0,"",AO109-LOOKUP(2,1/(AI109:AN109<>""),AI109:AN109))) | IF(OR(F109="",AP109=""),"",IF(COUNT(AI109:AO109)=0,"",AP109-LOOKUP(2,1/(AI109:AO109<>""),AI109:AO109))) | IF(OR(F109="",AQ109=""),"",IF(COUNT(AI109:AP109)=0,"",AQ109-LOOKUP(2,1/(AI109:AP109<>""),AI109:AP109))) | IF(OR(F109="",AR109=""),"",IF(COUNT(AI109:AQ109)=0,"",AR109-LOOKUP(2,1/(AI109:AQ109<>""),AI109:AQ109))) | IF(OR(F109="",AS109=""),"",IF(COUNT(AI109:AR109)=0,"",AS109-LOOKUP(2,1/(AI109:AR109<>""),AI109:AR109))) | IF(OR(F109="",AT109=""),"",IF(COUNT(AI109:AS109)=0,"",AT109-LOOKUP(2,1/(AI109:AS109<>""),AI109:AS109))) | IF(OR(F109="",AU109=""),"",IF(COUNT(AI109:AT109)=0,"",AU109-LOOKUP(2,1/(AI109:AT109<>""),AI109:AT109))) | IF(OR(F109="",AV109=""),"",IF(COUNT(AI109:AU109)=0,"",AV109-LOOKUP(2,1/(AI109:AU109<>""),AI109:AU109))) | IF(J109="","All_Provinces",IFERROR(VLOOKUP(J109,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K109="","All_Districts",IFERROR(VLOOKUP(K109,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F110="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 1 of 12 | AF2-DIS-N-068 | Badam Kalai Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Nawzad | Badam Kali | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ110="","",AQ110) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W110<>"",W110,IF(OR(T110="",V110=""),"",EDATE(T110,V110))) |  |  | Under Review of WRI | Five months for the construction. | IF(F110="","",IF(COUNT(AI110:AV110)=0,IF(AA110="","Not started",AA110),SUBSTITUTE(LOOKUP(2,1/(AI110:AV110<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F110="",COUNT(AI110:AV110)=0),"",TODAY()-LOOKUP(2,1/(AI110:AV110<>""),AI110:AV110)) | IF(OR(F110="",COUNT(AI110:AV110)<2),"",LOOKUP(2,1/(AI110:AV110<>""),AI110:AV110)-MIN(AI110:AV110)) | IF(OR(AD110="",AC110="Not started",AC110=""),"",IFERROR(AD110-IF(VLOOKUP(AC110,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC110,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F110="","",IF(OR(AA110="Cancelled",AC110="Cancelled"),"Cancelled",IF(OR(AC110="Completed / Handover",Y110<>"",Z110>=100),"Completed — on track",IF(O110="Not awarded",IF(U110="",IF(X110="","No planned date",IF(TODAY()>X110,"Behind — past planned date",IF(X110-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U110,"Behind — award date passed",IF(U110-TODAY()<=30,"At risk — close to off track","On track"))),IF(X110="","No planned date",IF(AND(TODAY()>X110,OR(Z110="",Z110<100)),"Behind — past end date",IF(AND(T110<>"",X110<>"",Z110<>"",(Z110<100),((TODAY()-T110)/MAX(X110-T110,1)*100)-Z110>15),"Behind — progress lag",IF(AND(X110-TODAY()<=30,X110-TODAY()>=0,OR(Z110="",Z110<90)),"At risk — close to off track","On track")))))))) | IF(OR(F110="",AC110="Completed / Handover",AC110="Cancelled"),"",IF(O110="Not awarded",IF(U110<>"",U110-TODAY(),IF(X110="","",X110-TODAY())),IF(X110="","",X110-TODAY()))) | [14 empty] | IF(OR(F110="",AJ110=""),"",IF(COUNT(AI110:AI110)=0,"",AJ110-LOOKUP(2,1/(AI110:AI110<>""),AI110:AI110))) | IF(OR(F110="",AK110=""),"",IF(COUNT(AI110:AJ110)=0,"",AK110-LOOKUP(2,1/(AI110:AJ110<>""),AI110:AJ110))) | IF(OR(F110="",AL110=""),"",IF(COUNT(AI110:AK110)=0,"",AL110-LOOKUP(2,1/(AI110:AK110<>""),AI110:AK110))) | IF(OR(F110="",AM110=""),"",IF(COUNT(AI110:AL110)=0,"",AM110-LOOKUP(2,1/(AI110:AL110<>""),AI110:AL110))) | IF(OR(F110="",AN110=""),"",IF(COUNT(AI110:AM110)=0,"",AN110-LOOKUP(2,1/(AI110:AM110<>""),AI110:AM110))) | IF(OR(F110="",AO110=""),"",IF(COUNT(AI110:AN110)=0,"",AO110-LOOKUP(2,1/(AI110:AN110<>""),AI110:AN110))) | IF(OR(F110="",AP110=""),"",IF(COUNT(AI110:AO110)=0,"",AP110-LOOKUP(2,1/(AI110:AO110<>""),AI110:AO110))) | IF(OR(F110="",AQ110=""),"",IF(COUNT(AI110:AP110)=0,"",AQ110-LOOKUP(2,1/(AI110:AP110<>""),AI110:AP110))) | IF(OR(F110="",AR110=""),"",IF(COUNT(AI110:AQ110)=0,"",AR110-LOOKUP(2,1/(AI110:AQ110<>""),AI110:AQ110))) | IF(OR(F110="",AS110=""),"",IF(COUNT(AI110:AR110)=0,"",AS110-LOOKUP(2,1/(AI110:AR110<>""),AI110:AR110))) | IF(OR(F110="",AT110=""),"",IF(COUNT(AI110:AS110)=0,"",AT110-LOOKUP(2,1/(AI110:AS110<>""),AI110:AS110))) | IF(OR(F110="",AU110=""),"",IF(COUNT(AI110:AT110)=0,"",AU110-LOOKUP(2,1/(AI110:AT110<>""),AI110:AT110))) | IF(OR(F110="",AV110=""),"",IF(COUNT(AI110:AU110)=0,"",AV110-LOOKUP(2,1/(AI110:AU110<>""),AI110:AU110))) | IF(J110="","All_Provinces",IFERROR(VLOOKUP(J110,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K110="","All_Districts",IFERROR(VLOOKUP(K110,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F111="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 2 of 12 | AF2-DIS-N-069 | Bahu Kalai Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Zabul | Seyure | Bahu Kali | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ111="","",AQ111) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W111<>"",W111,IF(OR(T111="",V111=""),"",EDATE(T111,V111))) |  |  | Under Review of WRI | Five months for the construction. | IF(F111="","",IF(COUNT(AI111:AV111)=0,IF(AA111="","Not started",AA111),SUBSTITUTE(LOOKUP(2,1/(AI111:AV111<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F111="",COUNT(AI111:AV111)=0),"",TODAY()-LOOKUP(2,1/(AI111:AV111<>""),AI111:AV111)) | IF(OR(F111="",COUNT(AI111:AV111)<2),"",LOOKUP(2,1/(AI111:AV111<>""),AI111:AV111)-MIN(AI111:AV111)) | IF(OR(AD111="",AC111="Not started",AC111=""),"",IFERROR(AD111-IF(VLOOKUP(AC111,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC111,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F111="","",IF(OR(AA111="Cancelled",AC111="Cancelled"),"Cancelled",IF(OR(AC111="Completed / Handover",Y111<>"",Z111>=100),"Completed — on track",IF(O111="Not awarded",IF(U111="",IF(X111="","No planned date",IF(TODAY()>X111,"Behind — past planned date",IF(X111-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U111,"Behind — award date passed",IF(U111-TODAY()<=30,"At risk — close to off track","On track"))),IF(X111="","No planned date",IF(AND(TODAY()>X111,OR(Z111="",Z111<100)),"Behind — past end date",IF(AND(T111<>"",X111<>"",Z111<>"",(Z111<100),((TODAY()-T111)/MAX(X111-T111,1)*100)-Z111>15),"Behind — progress lag",IF(AND(X111-TODAY()<=30,X111-TODAY()>=0,OR(Z111="",Z111<90)),"At risk — close to off track","On track")))))))) | IF(OR(F111="",AC111="Completed / Handover",AC111="Cancelled"),"",IF(O111="Not awarded",IF(U111<>"",U111-TODAY(),IF(X111="","",X111-TODAY())),IF(X111="","",X111-TODAY()))) | [14 empty] | IF(OR(F111="",AJ111=""),"",IF(COUNT(AI111:AI111)=0,"",AJ111-LOOKUP(2,1/(AI111:AI111<>""),AI111:AI111))) | IF(OR(F111="",AK111=""),"",IF(COUNT(AI111:AJ111)=0,"",AK111-LOOKUP(2,1/(AI111:AJ111<>""),AI111:AJ111))) | IF(OR(F111="",AL111=""),"",IF(COUNT(AI111:AK111)=0,"",AL111-LOOKUP(2,1/(AI111:AK111<>""),AI111:AK111))) | IF(OR(F111="",AM111=""),"",IF(COUNT(AI111:AL111)=0,"",AM111-LOOKUP(2,1/(AI111:AL111<>""),AI111:AL111))) | IF(OR(F111="",AN111=""),"",IF(COUNT(AI111:AM111)=0,"",AN111-LOOKUP(2,1/(AI111:AM111<>""),AI111:AM111))) | IF(OR(F111="",AO111=""),"",IF(COUNT(AI111:AN111)=0,"",AO111-LOOKUP(2,1/(AI111:AN111<>""),AI111:AN111))) | IF(OR(F111="",AP111=""),"",IF(COUNT(AI111:AO111)=0,"",AP111-LOOKUP(2,1/(AI111:AO111<>""),AI111:AO111))) | IF(OR(F111="",AQ111=""),"",IF(COUNT(AI111:AP111)=0,"",AQ111-LOOKUP(2,1/(AI111:AP111<>""),AI111:AP111))) | IF(OR(F111="",AR111=""),"",IF(COUNT(AI111:AQ111)=0,"",AR111-LOOKUP(2,1/(AI111:AQ111<>""),AI111:AQ111))) | IF(OR(F111="",AS111=""),"",IF(COUNT(AI111:AR111)=0,"",AS111-LOOKUP(2,1/(AI111:AR111<>""),AI111:AR111))) | IF(OR(F111="",AT111=""),"",IF(COUNT(AI111:AS111)=0,"",AT111-LOOKUP(2,1/(AI111:AS111<>""),AI111:AS111))) | IF(OR(F111="",AU111=""),"",IF(COUNT(AI111:AT111)=0,"",AU111-LOOKUP(2,1/(AI111:AT111<>""),AI111:AT111))) | IF(OR(F111="",AV111=""),"",IF(COUNT(AI111:AU111)=0,"",AV111-LOOKUP(2,1/(AI111:AU111<>""),AI111:AU111))) | IF(J111="","All_Provinces",IFERROR(VLOOKUP(J111,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K111="","All_Districts",IFERROR(VLOOKUP(K111,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F112="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 3 of 12 | AF2-DIS-N-070 | Firozi Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Nemroz | Delaram | Firozi Village | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ112="","",AQ112) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W112<>"",W112,IF(OR(T112="",V112=""),"",EDATE(T112,V112))) |  |  | Under Review of WRI | Five months for the construction. | IF(F112="","",IF(COUNT(AI112:AV112)=0,IF(AA112="","Not started",AA112),SUBSTITUTE(LOOKUP(2,1/(AI112:AV112<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F112="",COUNT(AI112:AV112)=0),"",TODAY()-LOOKUP(2,1/(AI112:AV112<>""),AI112:AV112)) | IF(OR(F112="",COUNT(AI112:AV112)<2),"",LOOKUP(2,1/(AI112:AV112<>""),AI112:AV112)-MIN(AI112:AV112)) | IF(OR(AD112="",AC112="Not started",AC112=""),"",IFERROR(AD112-IF(VLOOKUP(AC112,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC112,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F112="","",IF(OR(AA112="Cancelled",AC112="Cancelled"),"Cancelled",IF(OR(AC112="Completed / Handover",Y112<>"",Z112>=100),"Completed — on track",IF(O112="Not awarded",IF(U112="",IF(X112="","No planned date",IF(TODAY()>X112,"Behind — past planned date",IF(X112-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U112,"Behind — award date passed",IF(U112-TODAY()<=30,"At risk — close to off track","On track"))),IF(X112="","No planned date",IF(AND(TODAY()>X112,OR(Z112="",Z112<100)),"Behind — past end date",IF(AND(T112<>"",X112<>"",Z112<>"",(Z112<100),((TODAY()-T112)/MAX(X112-T112,1)*100)-Z112>15),"Behind — progress lag",IF(AND(X112-TODAY()<=30,X112-TODAY()>=0,OR(Z112="",Z112<90)),"At risk — close to off track","On track")))))))) | IF(OR(F112="",AC112="Completed / Handover",AC112="Cancelled"),"",IF(O112="Not awarded",IF(U112<>"",U112-TODAY(),IF(X112="","",X112-TODAY())),IF(X112="","",X112-TODAY()))) | [14 empty] | IF(OR(F112="",AJ112=""),"",IF(COUNT(AI112:AI112)=0,"",AJ112-LOOKUP(2,1/(AI112:AI112<>""),AI112:AI112))) | IF(OR(F112="",AK112=""),"",IF(COUNT(AI112:AJ112)=0,"",AK112-LOOKUP(2,1/(AI112:AJ112<>""),AI112:AJ112))) | IF(OR(F112="",AL112=""),"",IF(COUNT(AI112:AK112)=0,"",AL112-LOOKUP(2,1/(AI112:AK112<>""),AI112:AK112))) | IF(OR(F112="",AM112=""),"",IF(COUNT(AI112:AL112)=0,"",AM112-LOOKUP(2,1/(AI112:AL112<>""),AI112:AL112))) | IF(OR(F112="",AN112=""),"",IF(COUNT(AI112:AM112)=0,"",AN112-LOOKUP(2,1/(AI112:AM112<>""),AI112:AM112))) | IF(OR(F112="",AO112=""),"",IF(COUNT(AI112:AN112)=0,"",AO112-LOOKUP(2,1/(AI112:AN112<>""),AI112:AN112))) | IF(OR(F112="",AP112=""),"",IF(COUNT(AI112:AO112)=0,"",AP112-LOOKUP(2,1/(AI112:AO112<>""),AI112:AO112))) | IF(OR(F112="",AQ112=""),"",IF(COUNT(AI112:AP112)=0,"",AQ112-LOOKUP(2,1/(AI112:AP112<>""),AI112:AP112))) | IF(OR(F112="",AR112=""),"",IF(COUNT(AI112:AQ112)=0,"",AR112-LOOKUP(2,1/(AI112:AQ112<>""),AI112:AQ112))) | IF(OR(F112="",AS112=""),"",IF(COUNT(AI112:AR112)=0,"",AS112-LOOKUP(2,1/(AI112:AR112<>""),AI112:AR112))) | IF(OR(F112="",AT112=""),"",IF(COUNT(AI112:AS112)=0,"",AT112-LOOKUP(2,1/(AI112:AS112<>""),AI112:AS112))) | IF(OR(F112="",AU112=""),"",IF(COUNT(AI112:AT112)=0,"",AU112-LOOKUP(2,1/(AI112:AT112<>""),AI112:AT112))) | IF(OR(F112="",AV112=""),"",IF(COUNT(AI112:AU112)=0,"",AV112-LOOKUP(2,1/(AI112:AU112<>""),AI112:AU112))) | IF(J112="","All_Provinces",IFERROR(VLOOKUP(J112,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K112="","All_Districts",IFERROR(VLOOKUP(K112,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F113="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 4 of 12 | AF2-DIS-N-071 | Garmaw Kali Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Panjwai | Garmaw Kali | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ113="","",AQ113) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W113<>"",W113,IF(OR(T113="",V113=""),"",EDATE(T113,V113))) |  |  | Under Review of WRI | Five months for the construction. | IF(F113="","",IF(COUNT(AI113:AV113)=0,IF(AA113="","Not started",AA113),SUBSTITUTE(LOOKUP(2,1/(AI113:AV113<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F113="",COUNT(AI113:AV113)=0),"",TODAY()-LOOKUP(2,1/(AI113:AV113<>""),AI113:AV113)) | IF(OR(F113="",COUNT(AI113:AV113)<2),"",LOOKUP(2,1/(AI113:AV113<>""),AI113:AV113)-MIN(AI113:AV113)) | IF(OR(AD113="",AC113="Not started",AC113=""),"",IFERROR(AD113-IF(VLOOKUP(AC113,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC113,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F113="","",IF(OR(AA113="Cancelled",AC113="Cancelled"),"Cancelled",IF(OR(AC113="Completed / Handover",Y113<>"",Z113>=100),"Completed — on track",IF(O113="Not awarded",IF(U113="",IF(X113="","No planned date",IF(TODAY()>X113,"Behind — past planned date",IF(X113-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U113,"Behind — award date passed",IF(U113-TODAY()<=30,"At risk — close to off track","On track"))),IF(X113="","No planned date",IF(AND(TODAY()>X113,OR(Z113="",Z113<100)),"Behind — past end date",IF(AND(T113<>"",X113<>"",Z113<>"",(Z113<100),((TODAY()-T113)/MAX(X113-T113,1)*100)-Z113>15),"Behind — progress lag",IF(AND(X113-TODAY()<=30,X113-TODAY()>=0,OR(Z113="",Z113<90)),"At risk — close to off track","On track")))))))) | IF(OR(F113="",AC113="Completed / Handover",AC113="Cancelled"),"",IF(O113="Not awarded",IF(U113<>"",U113-TODAY(),IF(X113="","",X113-TODAY())),IF(X113="","",X113-TODAY()))) | [14 empty] | IF(OR(F113="",AJ113=""),"",IF(COUNT(AI113:AI113)=0,"",AJ113-LOOKUP(2,1/(AI113:AI113<>""),AI113:AI113))) | IF(OR(F113="",AK113=""),"",IF(COUNT(AI113:AJ113)=0,"",AK113-LOOKUP(2,1/(AI113:AJ113<>""),AI113:AJ113))) | IF(OR(F113="",AL113=""),"",IF(COUNT(AI113:AK113)=0,"",AL113-LOOKUP(2,1/(AI113:AK113<>""),AI113:AK113))) | IF(OR(F113="",AM113=""),"",IF(COUNT(AI113:AL113)=0,"",AM113-LOOKUP(2,1/(AI113:AL113<>""),AI113:AL113))) | IF(OR(F113="",AN113=""),"",IF(COUNT(AI113:AM113)=0,"",AN113-LOOKUP(2,1/(AI113:AM113<>""),AI113:AM113))) | IF(OR(F113="",AO113=""),"",IF(COUNT(AI113:AN113)=0,"",AO113-LOOKUP(2,1/(AI113:AN113<>""),AI113:AN113))) | IF(OR(F113="",AP113=""),"",IF(COUNT(AI113:AO113)=0,"",AP113-LOOKUP(2,1/(AI113:AO113<>""),AI113:AO113))) | IF(OR(F113="",AQ113=""),"",IF(COUNT(AI113:AP113)=0,"",AQ113-LOOKUP(2,1/(AI113:AP113<>""),AI113:AP113))) | IF(OR(F113="",AR113=""),"",IF(COUNT(AI113:AQ113)=0,"",AR113-LOOKUP(2,1/(AI113:AQ113<>""),AI113:AQ113))) | IF(OR(F113="",AS113=""),"",IF(COUNT(AI113:AR113)=0,"",AS113-LOOKUP(2,1/(AI113:AR113<>""),AI113:AR113))) | IF(OR(F113="",AT113=""),"",IF(COUNT(AI113:AS113)=0,"",AT113-LOOKUP(2,1/(AI113:AS113<>""),AI113:AS113))) | IF(OR(F113="",AU113=""),"",IF(COUNT(AI113:AT113)=0,"",AU113-LOOKUP(2,1/(AI113:AT113<>""),AI113:AT113))) | IF(OR(F113="",AV113=""),"",IF(COUNT(AI113:AU113)=0,"",AV113-LOOKUP(2,1/(AI113:AU113<>""),AI113:AU113))) | IF(J113="","All_Provinces",IFERROR(VLOOKUP(J113,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K113="","All_Districts",IFERROR(VLOOKUP(K113,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F114="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 5 of 12 | AF2-DIS-N-072 | Garmaw Kali Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Shah Wali Kot | Garmaw kali | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ114="","",AQ114) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W114<>"",W114,IF(OR(T114="",V114=""),"",EDATE(T114,V114))) |  |  | Under Review of WRI | Five months for the construction. | IF(F114="","",IF(COUNT(AI114:AV114)=0,IF(AA114="","Not started",AA114),SUBSTITUTE(LOOKUP(2,1/(AI114:AV114<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F114="",COUNT(AI114:AV114)=0),"",TODAY()-LOOKUP(2,1/(AI114:AV114<>""),AI114:AV114)) | IF(OR(F114="",COUNT(AI114:AV114)<2),"",LOOKUP(2,1/(AI114:AV114<>""),AI114:AV114)-MIN(AI114:AV114)) | IF(OR(AD114="",AC114="Not started",AC114=""),"",IFERROR(AD114-IF(VLOOKUP(AC114,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC114,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F114="","",IF(OR(AA114="Cancelled",AC114="Cancelled"),"Cancelled",IF(OR(AC114="Completed / Handover",Y114<>"",Z114>=100),"Completed — on track",IF(O114="Not awarded",IF(U114="",IF(X114="","No planned date",IF(TODAY()>X114,"Behind — past planned date",IF(X114-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U114,"Behind — award date passed",IF(U114-TODAY()<=30,"At risk — close to off track","On track"))),IF(X114="","No planned date",IF(AND(TODAY()>X114,OR(Z114="",Z114<100)),"Behind — past end date",IF(AND(T114<>"",X114<>"",Z114<>"",(Z114<100),((TODAY()-T114)/MAX(X114-T114,1)*100)-Z114>15),"Behind — progress lag",IF(AND(X114-TODAY()<=30,X114-TODAY()>=0,OR(Z114="",Z114<90)),"At risk — close to off track","On track")))))))) | IF(OR(F114="",AC114="Completed / Handover",AC114="Cancelled"),"",IF(O114="Not awarded",IF(U114<>"",U114-TODAY(),IF(X114="","",X114-TODAY())),IF(X114="","",X114-TODAY()))) | [14 empty] | IF(OR(F114="",AJ114=""),"",IF(COUNT(AI114:AI114)=0,"",AJ114-LOOKUP(2,1/(AI114:AI114<>""),AI114:AI114))) | IF(OR(F114="",AK114=""),"",IF(COUNT(AI114:AJ114)=0,"",AK114-LOOKUP(2,1/(AI114:AJ114<>""),AI114:AJ114))) | IF(OR(F114="",AL114=""),"",IF(COUNT(AI114:AK114)=0,"",AL114-LOOKUP(2,1/(AI114:AK114<>""),AI114:AK114))) | IF(OR(F114="",AM114=""),"",IF(COUNT(AI114:AL114)=0,"",AM114-LOOKUP(2,1/(AI114:AL114<>""),AI114:AL114))) | IF(OR(F114="",AN114=""),"",IF(COUNT(AI114:AM114)=0,"",AN114-LOOKUP(2,1/(AI114:AM114<>""),AI114:AM114))) | IF(OR(F114="",AO114=""),"",IF(COUNT(AI114:AN114)=0,"",AO114-LOOKUP(2,1/(AI114:AN114<>""),AI114:AN114))) | IF(OR(F114="",AP114=""),"",IF(COUNT(AI114:AO114)=0,"",AP114-LOOKUP(2,1/(AI114:AO114<>""),AI114:AO114))) | IF(OR(F114="",AQ114=""),"",IF(COUNT(AI114:AP114)=0,"",AQ114-LOOKUP(2,1/(AI114:AP114<>""),AI114:AP114))) | IF(OR(F114="",AR114=""),"",IF(COUNT(AI114:AQ114)=0,"",AR114-LOOKUP(2,1/(AI114:AQ114<>""),AI114:AQ114))) | IF(OR(F114="",AS114=""),"",IF(COUNT(AI114:AR114)=0,"",AS114-LOOKUP(2,1/(AI114:AR114<>""),AI114:AR114))) | IF(OR(F114="",AT114=""),"",IF(COUNT(AI114:AS114)=0,"",AT114-LOOKUP(2,1/(AI114:AS114<>""),AI114:AS114))) | IF(OR(F114="",AU114=""),"",IF(COUNT(AI114:AT114)=0,"",AU114-LOOKUP(2,1/(AI114:AT114<>""),AI114:AT114))) | IF(OR(F114="",AV114=""),"",IF(COUNT(AI114:AU114)=0,"",AV114-LOOKUP(2,1/(AI114:AU114<>""),AI114:AU114))) | IF(J114="","All_Provinces",IFERROR(VLOOKUP(J114,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K114="","All_Districts",IFERROR(VLOOKUP(K114,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F115="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 6 of 12 | AF2-DIS-N-073 | Khair Abad Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Urozgan | Terinkot | Khair Abad | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ115="","",AQ115) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W115<>"",W115,IF(OR(T115="",V115=""),"",EDATE(T115,V115))) |  |  | Under Review of WRI | Five months for the construction. | IF(F115="","",IF(COUNT(AI115:AV115)=0,IF(AA115="","Not started",AA115),SUBSTITUTE(LOOKUP(2,1/(AI115:AV115<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F115="",COUNT(AI115:AV115)=0),"",TODAY()-LOOKUP(2,1/(AI115:AV115<>""),AI115:AV115)) | IF(OR(F115="",COUNT(AI115:AV115)<2),"",LOOKUP(2,1/(AI115:AV115<>""),AI115:AV115)-MIN(AI115:AV115)) | IF(OR(AD115="",AC115="Not started",AC115=""),"",IFERROR(AD115-IF(VLOOKUP(AC115,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC115,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F115="","",IF(OR(AA115="Cancelled",AC115="Cancelled"),"Cancelled",IF(OR(AC115="Completed / Handover",Y115<>"",Z115>=100),"Completed — on track",IF(O115="Not awarded",IF(U115="",IF(X115="","No planned date",IF(TODAY()>X115,"Behind — past planned date",IF(X115-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U115,"Behind — award date passed",IF(U115-TODAY()<=30,"At risk — close to off track","On track"))),IF(X115="","No planned date",IF(AND(TODAY()>X115,OR(Z115="",Z115<100)),"Behind — past end date",IF(AND(T115<>"",X115<>"",Z115<>"",(Z115<100),((TODAY()-T115)/MAX(X115-T115,1)*100)-Z115>15),"Behind — progress lag",IF(AND(X115-TODAY()<=30,X115-TODAY()>=0,OR(Z115="",Z115<90)),"At risk — close to off track","On track")))))))) | IF(OR(F115="",AC115="Completed / Handover",AC115="Cancelled"),"",IF(O115="Not awarded",IF(U115<>"",U115-TODAY(),IF(X115="","",X115-TODAY())),IF(X115="","",X115-TODAY()))) | [14 empty] | IF(OR(F115="",AJ115=""),"",IF(COUNT(AI115:AI115)=0,"",AJ115-LOOKUP(2,1/(AI115:AI115<>""),AI115:AI115))) | IF(OR(F115="",AK115=""),"",IF(COUNT(AI115:AJ115)=0,"",AK115-LOOKUP(2,1/(AI115:AJ115<>""),AI115:AJ115))) | IF(OR(F115="",AL115=""),"",IF(COUNT(AI115:AK115)=0,"",AL115-LOOKUP(2,1/(AI115:AK115<>""),AI115:AK115))) | IF(OR(F115="",AM115=""),"",IF(COUNT(AI115:AL115)=0,"",AM115-LOOKUP(2,1/(AI115:AL115<>""),AI115:AL115))) | IF(OR(F115="",AN115=""),"",IF(COUNT(AI115:AM115)=0,"",AN115-LOOKUP(2,1/(AI115:AM115<>""),AI115:AM115))) | IF(OR(F115="",AO115=""),"",IF(COUNT(AI115:AN115)=0,"",AO115-LOOKUP(2,1/(AI115:AN115<>""),AI115:AN115))) | IF(OR(F115="",AP115=""),"",IF(COUNT(AI115:AO115)=0,"",AP115-LOOKUP(2,1/(AI115:AO115<>""),AI115:AO115))) | IF(OR(F115="",AQ115=""),"",IF(COUNT(AI115:AP115)=0,"",AQ115-LOOKUP(2,1/(AI115:AP115<>""),AI115:AP115))) | IF(OR(F115="",AR115=""),"",IF(COUNT(AI115:AQ115)=0,"",AR115-LOOKUP(2,1/(AI115:AQ115<>""),AI115:AQ115))) | IF(OR(F115="",AS115=""),"",IF(COUNT(AI115:AR115)=0,"",AS115-LOOKUP(2,1/(AI115:AR115<>""),AI115:AR115))) | IF(OR(F115="",AT115=""),"",IF(COUNT(AI115:AS115)=0,"",AT115-LOOKUP(2,1/(AI115:AS115<>""),AI115:AS115))) | IF(OR(F115="",AU115=""),"",IF(COUNT(AI115:AT115)=0,"",AU115-LOOKUP(2,1/(AI115:AT115<>""),AI115:AT115))) | IF(OR(F115="",AV115=""),"",IF(COUNT(AI115:AU115)=0,"",AV115-LOOKUP(2,1/(AI115:AU115<>""),AI115:AU115))) | IF(J115="","All_Provinces",IFERROR(VLOOKUP(J115,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K115="","All_Districts",IFERROR(VLOOKUP(K115,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F116="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 7 of 12 | AF2-DIS-N-074 | Kona Kala Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Urozgan | Terinkot | Kona Kala | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ116="","",AQ116) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W116<>"",W116,IF(OR(T116="",V116=""),"",EDATE(T116,V116))) |  |  | Under Review of WRI | Five months for the construction. | IF(F116="","",IF(COUNT(AI116:AV116)=0,IF(AA116="","Not started",AA116),SUBSTITUTE(LOOKUP(2,1/(AI116:AV116<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F116="",COUNT(AI116:AV116)=0),"",TODAY()-LOOKUP(2,1/(AI116:AV116<>""),AI116:AV116)) | IF(OR(F116="",COUNT(AI116:AV116)<2),"",LOOKUP(2,1/(AI116:AV116<>""),AI116:AV116)-MIN(AI116:AV116)) | IF(OR(AD116="",AC116="Not started",AC116=""),"",IFERROR(AD116-IF(VLOOKUP(AC116,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC116,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F116="","",IF(OR(AA116="Cancelled",AC116="Cancelled"),"Cancelled",IF(OR(AC116="Completed / Handover",Y116<>"",Z116>=100),"Completed — on track",IF(O116="Not awarded",IF(U116="",IF(X116="","No planned date",IF(TODAY()>X116,"Behind — past planned date",IF(X116-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U116,"Behind — award date passed",IF(U116-TODAY()<=30,"At risk — close to off track","On track"))),IF(X116="","No planned date",IF(AND(TODAY()>X116,OR(Z116="",Z116<100)),"Behind — past end date",IF(AND(T116<>"",X116<>"",Z116<>"",(Z116<100),((TODAY()-T116)/MAX(X116-T116,1)*100)-Z116>15),"Behind — progress lag",IF(AND(X116-TODAY()<=30,X116-TODAY()>=0,OR(Z116="",Z116<90)),"At risk — close to off track","On track")))))))) | IF(OR(F116="",AC116="Completed / Handover",AC116="Cancelled"),"",IF(O116="Not awarded",IF(U116<>"",U116-TODAY(),IF(X116="","",X116-TODAY())),IF(X116="","",X116-TODAY()))) | [14 empty] | IF(OR(F116="",AJ116=""),"",IF(COUNT(AI116:AI116)=0,"",AJ116-LOOKUP(2,1/(AI116:AI116<>""),AI116:AI116))) | IF(OR(F116="",AK116=""),"",IF(COUNT(AI116:AJ116)=0,"",AK116-LOOKUP(2,1/(AI116:AJ116<>""),AI116:AJ116))) | IF(OR(F116="",AL116=""),"",IF(COUNT(AI116:AK116)=0,"",AL116-LOOKUP(2,1/(AI116:AK116<>""),AI116:AK116))) | IF(OR(F116="",AM116=""),"",IF(COUNT(AI116:AL116)=0,"",AM116-LOOKUP(2,1/(AI116:AL116<>""),AI116:AL116))) | IF(OR(F116="",AN116=""),"",IF(COUNT(AI116:AM116)=0,"",AN116-LOOKUP(2,1/(AI116:AM116<>""),AI116:AM116))) | IF(OR(F116="",AO116=""),"",IF(COUNT(AI116:AN116)=0,"",AO116-LOOKUP(2,1/(AI116:AN116<>""),AI116:AN116))) | IF(OR(F116="",AP116=""),"",IF(COUNT(AI116:AO116)=0,"",AP116-LOOKUP(2,1/(AI116:AO116<>""),AI116:AO116))) | IF(OR(F116="",AQ116=""),"",IF(COUNT(AI116:AP116)=0,"",AQ116-LOOKUP(2,1/(AI116:AP116<>""),AI116:AP116))) | IF(OR(F116="",AR116=""),"",IF(COUNT(AI116:AQ116)=0,"",AR116-LOOKUP(2,1/(AI116:AQ116<>""),AI116:AQ116))) | IF(OR(F116="",AS116=""),"",IF(COUNT(AI116:AR116)=0,"",AS116-LOOKUP(2,1/(AI116:AR116<>""),AI116:AR116))) | IF(OR(F116="",AT116=""),"",IF(COUNT(AI116:AS116)=0,"",AT116-LOOKUP(2,1/(AI116:AS116<>""),AI116:AS116))) | IF(OR(F116="",AU116=""),"",IF(COUNT(AI116:AT116)=0,"",AU116-LOOKUP(2,1/(AI116:AT116<>""),AI116:AT116))) | IF(OR(F116="",AV116=""),"",IF(COUNT(AI116:AU116)=0,"",AV116-LOOKUP(2,1/(AI116:AU116<>""),AI116:AU116))) | IF(J116="","All_Provinces",IFERROR(VLOOKUP(J116,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K116="","All_Districts",IFERROR(VLOOKUP(K116,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F117="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 8 of 12 | AF2-DIS-N-075 | Loy Razi Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Nemroz | Khashrod | Loy Razi | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ117="","",AQ117) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W117<>"",W117,IF(OR(T117="",V117=""),"",EDATE(T117,V117))) |  |  | Under Review of WRI | Five months for the construction. | IF(F117="","",IF(COUNT(AI117:AV117)=0,IF(AA117="","Not started",AA117),SUBSTITUTE(LOOKUP(2,1/(AI117:AV117<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F117="",COUNT(AI117:AV117)=0),"",TODAY()-LOOKUP(2,1/(AI117:AV117<>""),AI117:AV117)) | IF(OR(F117="",COUNT(AI117:AV117)<2),"",LOOKUP(2,1/(AI117:AV117<>""),AI117:AV117)-MIN(AI117:AV117)) | IF(OR(AD117="",AC117="Not started",AC117=""),"",IFERROR(AD117-IF(VLOOKUP(AC117,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC117,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F117="","",IF(OR(AA117="Cancelled",AC117="Cancelled"),"Cancelled",IF(OR(AC117="Completed / Handover",Y117<>"",Z117>=100),"Completed — on track",IF(O117="Not awarded",IF(U117="",IF(X117="","No planned date",IF(TODAY()>X117,"Behind — past planned date",IF(X117-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U117,"Behind — award date passed",IF(U117-TODAY()<=30,"At risk — close to off track","On track"))),IF(X117="","No planned date",IF(AND(TODAY()>X117,OR(Z117="",Z117<100)),"Behind — past end date",IF(AND(T117<>"",X117<>"",Z117<>"",(Z117<100),((TODAY()-T117)/MAX(X117-T117,1)*100)-Z117>15),"Behind — progress lag",IF(AND(X117-TODAY()<=30,X117-TODAY()>=0,OR(Z117="",Z117<90)),"At risk — close to off track","On track")))))))) | IF(OR(F117="",AC117="Completed / Handover",AC117="Cancelled"),"",IF(O117="Not awarded",IF(U117<>"",U117-TODAY(),IF(X117="","",X117-TODAY())),IF(X117="","",X117-TODAY()))) | [14 empty] | IF(OR(F117="",AJ117=""),"",IF(COUNT(AI117:AI117)=0,"",AJ117-LOOKUP(2,1/(AI117:AI117<>""),AI117:AI117))) | IF(OR(F117="",AK117=""),"",IF(COUNT(AI117:AJ117)=0,"",AK117-LOOKUP(2,1/(AI117:AJ117<>""),AI117:AJ117))) | IF(OR(F117="",AL117=""),"",IF(COUNT(AI117:AK117)=0,"",AL117-LOOKUP(2,1/(AI117:AK117<>""),AI117:AK117))) | IF(OR(F117="",AM117=""),"",IF(COUNT(AI117:AL117)=0,"",AM117-LOOKUP(2,1/(AI117:AL117<>""),AI117:AL117))) | IF(OR(F117="",AN117=""),"",IF(COUNT(AI117:AM117)=0,"",AN117-LOOKUP(2,1/(AI117:AM117<>""),AI117:AM117))) | IF(OR(F117="",AO117=""),"",IF(COUNT(AI117:AN117)=0,"",AO117-LOOKUP(2,1/(AI117:AN117<>""),AI117:AN117))) | IF(OR(F117="",AP117=""),"",IF(COUNT(AI117:AO117)=0,"",AP117-LOOKUP(2,1/(AI117:AO117<>""),AI117:AO117))) | IF(OR(F117="",AQ117=""),"",IF(COUNT(AI117:AP117)=0,"",AQ117-LOOKUP(2,1/(AI117:AP117<>""),AI117:AP117))) | IF(OR(F117="",AR117=""),"",IF(COUNT(AI117:AQ117)=0,"",AR117-LOOKUP(2,1/(AI117:AQ117<>""),AI117:AQ117))) | IF(OR(F117="",AS117=""),"",IF(COUNT(AI117:AR117)=0,"",AS117-LOOKUP(2,1/(AI117:AR117<>""),AI117:AR117))) | IF(OR(F117="",AT117=""),"",IF(COUNT(AI117:AS117)=0,"",AT117-LOOKUP(2,1/(AI117:AS117<>""),AI117:AS117))) | IF(OR(F117="",AU117=""),"",IF(COUNT(AI117:AT117)=0,"",AU117-LOOKUP(2,1/(AI117:AT117<>""),AI117:AT117))) | IF(OR(F117="",AV117=""),"",IF(COUNT(AI117:AU117)=0,"",AV117-LOOKUP(2,1/(AI117:AU117<>""),AI117:AU117))) | IF(J117="","All_Provinces",IFERROR(VLOOKUP(J117,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K117="","All_Districts",IFERROR(VLOOKUP(K117,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F118="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 9 of 12 | AF2-DIS-N-076 | Mohmad Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Daman | Mohmand | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ118="","",AQ118) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W118<>"",W118,IF(OR(T118="",V118=""),"",EDATE(T118,V118))) |  |  | Under Review of WRI | Five months for the construction. | IF(F118="","",IF(COUNT(AI118:AV118)=0,IF(AA118="","Not started",AA118),SUBSTITUTE(LOOKUP(2,1/(AI118:AV118<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F118="",COUNT(AI118:AV118)=0),"",TODAY()-LOOKUP(2,1/(AI118:AV118<>""),AI118:AV118)) | IF(OR(F118="",COUNT(AI118:AV118)<2),"",LOOKUP(2,1/(AI118:AV118<>""),AI118:AV118)-MIN(AI118:AV118)) | IF(OR(AD118="",AC118="Not started",AC118=""),"",IFERROR(AD118-IF(VLOOKUP(AC118,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC118,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F118="","",IF(OR(AA118="Cancelled",AC118="Cancelled"),"Cancelled",IF(OR(AC118="Completed / Handover",Y118<>"",Z118>=100),"Completed — on track",IF(O118="Not awarded",IF(U118="",IF(X118="","No planned date",IF(TODAY()>X118,"Behind — past planned date",IF(X118-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U118,"Behind — award date passed",IF(U118-TODAY()<=30,"At risk — close to off track","On track"))),IF(X118="","No planned date",IF(AND(TODAY()>X118,OR(Z118="",Z118<100)),"Behind — past end date",IF(AND(T118<>"",X118<>"",Z118<>"",(Z118<100),((TODAY()-T118)/MAX(X118-T118,1)*100)-Z118>15),"Behind — progress lag",IF(AND(X118-TODAY()<=30,X118-TODAY()>=0,OR(Z118="",Z118<90)),"At risk — close to off track","On track")))))))) | IF(OR(F118="",AC118="Completed / Handover",AC118="Cancelled"),"",IF(O118="Not awarded",IF(U118<>"",U118-TODAY(),IF(X118="","",X118-TODAY())),IF(X118="","",X118-TODAY()))) | [14 empty] | IF(OR(F118="",AJ118=""),"",IF(COUNT(AI118:AI118)=0,"",AJ118-LOOKUP(2,1/(AI118:AI118<>""),AI118:AI118))) | IF(OR(F118="",AK118=""),"",IF(COUNT(AI118:AJ118)=0,"",AK118-LOOKUP(2,1/(AI118:AJ118<>""),AI118:AJ118))) | IF(OR(F118="",AL118=""),"",IF(COUNT(AI118:AK118)=0,"",AL118-LOOKUP(2,1/(AI118:AK118<>""),AI118:AK118))) | IF(OR(F118="",AM118=""),"",IF(COUNT(AI118:AL118)=0,"",AM118-LOOKUP(2,1/(AI118:AL118<>""),AI118:AL118))) | IF(OR(F118="",AN118=""),"",IF(COUNT(AI118:AM118)=0,"",AN118-LOOKUP(2,1/(AI118:AM118<>""),AI118:AM118))) | IF(OR(F118="",AO118=""),"",IF(COUNT(AI118:AN118)=0,"",AO118-LOOKUP(2,1/(AI118:AN118<>""),AI118:AN118))) | IF(OR(F118="",AP118=""),"",IF(COUNT(AI118:AO118)=0,"",AP118-LOOKUP(2,1/(AI118:AO118<>""),AI118:AO118))) | IF(OR(F118="",AQ118=""),"",IF(COUNT(AI118:AP118)=0,"",AQ118-LOOKUP(2,1/(AI118:AP118<>""),AI118:AP118))) | IF(OR(F118="",AR118=""),"",IF(COUNT(AI118:AQ118)=0,"",AR118-LOOKUP(2,1/(AI118:AQ118<>""),AI118:AQ118))) | IF(OR(F118="",AS118=""),"",IF(COUNT(AI118:AR118)=0,"",AS118-LOOKUP(2,1/(AI118:AR118<>""),AI118:AR118))) | IF(OR(F118="",AT118=""),"",IF(COUNT(AI118:AS118)=0,"",AT118-LOOKUP(2,1/(AI118:AS118<>""),AI118:AS118))) | IF(OR(F118="",AU118=""),"",IF(COUNT(AI118:AT118)=0,"",AU118-LOOKUP(2,1/(AI118:AT118<>""),AI118:AT118))) | IF(OR(F118="",AV118=""),"",IF(COUNT(AI118:AU118)=0,"",AV118-LOOKUP(2,1/(AI118:AU118<>""),AI118:AU118))) | IF(J118="","All_Provinces",IFERROR(VLOOKUP(J118,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K118="","All_Districts",IFERROR(VLOOKUP(K118,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F119="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 10 of 12 | AF2-DIS-N-077 | Omarzai Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Zabul | Seyure | Omerzai | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ119="","",AQ119) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W119<>"",W119,IF(OR(T119="",V119=""),"",EDATE(T119,V119))) |  |  | Under Review of WRI | Five months for the construction. | IF(F119="","",IF(COUNT(AI119:AV119)=0,IF(AA119="","Not started",AA119),SUBSTITUTE(LOOKUP(2,1/(AI119:AV119<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F119="",COUNT(AI119:AV119)=0),"",TODAY()-LOOKUP(2,1/(AI119:AV119<>""),AI119:AV119)) | IF(OR(F119="",COUNT(AI119:AV119)<2),"",LOOKUP(2,1/(AI119:AV119<>""),AI119:AV119)-MIN(AI119:AV119)) | IF(OR(AD119="",AC119="Not started",AC119=""),"",IFERROR(AD119-IF(VLOOKUP(AC119,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC119,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F119="","",IF(OR(AA119="Cancelled",AC119="Cancelled"),"Cancelled",IF(OR(AC119="Completed / Handover",Y119<>"",Z119>=100),"Completed — on track",IF(O119="Not awarded",IF(U119="",IF(X119="","No planned date",IF(TODAY()>X119,"Behind — past planned date",IF(X119-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U119,"Behind — award date passed",IF(U119-TODAY()<=30,"At risk — close to off track","On track"))),IF(X119="","No planned date",IF(AND(TODAY()>X119,OR(Z119="",Z119<100)),"Behind — past end date",IF(AND(T119<>"",X119<>"",Z119<>"",(Z119<100),((TODAY()-T119)/MAX(X119-T119,1)*100)-Z119>15),"Behind — progress lag",IF(AND(X119-TODAY()<=30,X119-TODAY()>=0,OR(Z119="",Z119<90)),"At risk — close to off track","On track")))))))) | IF(OR(F119="",AC119="Completed / Handover",AC119="Cancelled"),"",IF(O119="Not awarded",IF(U119<>"",U119-TODAY(),IF(X119="","",X119-TODAY())),IF(X119="","",X119-TODAY()))) | [14 empty] | IF(OR(F119="",AJ119=""),"",IF(COUNT(AI119:AI119)=0,"",AJ119-LOOKUP(2,1/(AI119:AI119<>""),AI119:AI119))) | IF(OR(F119="",AK119=""),"",IF(COUNT(AI119:AJ119)=0,"",AK119-LOOKUP(2,1/(AI119:AJ119<>""),AI119:AJ119))) | IF(OR(F119="",AL119=""),"",IF(COUNT(AI119:AK119)=0,"",AL119-LOOKUP(2,1/(AI119:AK119<>""),AI119:AK119))) | IF(OR(F119="",AM119=""),"",IF(COUNT(AI119:AL119)=0,"",AM119-LOOKUP(2,1/(AI119:AL119<>""),AI119:AL119))) | IF(OR(F119="",AN119=""),"",IF(COUNT(AI119:AM119)=0,"",AN119-LOOKUP(2,1/(AI119:AM119<>""),AI119:AM119))) | IF(OR(F119="",AO119=""),"",IF(COUNT(AI119:AN119)=0,"",AO119-LOOKUP(2,1/(AI119:AN119<>""),AI119:AN119))) | IF(OR(F119="",AP119=""),"",IF(COUNT(AI119:AO119)=0,"",AP119-LOOKUP(2,1/(AI119:AO119<>""),AI119:AO119))) | IF(OR(F119="",AQ119=""),"",IF(COUNT(AI119:AP119)=0,"",AQ119-LOOKUP(2,1/(AI119:AP119<>""),AI119:AP119))) | IF(OR(F119="",AR119=""),"",IF(COUNT(AI119:AQ119)=0,"",AR119-LOOKUP(2,1/(AI119:AQ119<>""),AI119:AQ119))) | IF(OR(F119="",AS119=""),"",IF(COUNT(AI119:AR119)=0,"",AS119-LOOKUP(2,1/(AI119:AR119<>""),AI119:AR119))) | IF(OR(F119="",AT119=""),"",IF(COUNT(AI119:AS119)=0,"",AT119-LOOKUP(2,1/(AI119:AS119<>""),AI119:AS119))) | IF(OR(F119="",AU119=""),"",IF(COUNT(AI119:AT119)=0,"",AU119-LOOKUP(2,1/(AI119:AT119<>""),AI119:AT119))) | IF(OR(F119="",AV119=""),"",IF(COUNT(AI119:AU119)=0,"",AV119-LOOKUP(2,1/(AI119:AU119<>""),AI119:AU119))) | IF(J119="","All_Provinces",IFERROR(VLOOKUP(J119,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K119="","All_Districts",IFERROR(VLOOKUP(K119,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F120="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 11 of 12 | AF2-DIS-N-078 | Rud Kali Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Zabul | Tarnak- Jaldak | Rud Kali | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ120="","",AQ120) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W120<>"",W120,IF(OR(T120="",V120=""),"",EDATE(T120,V120))) |  |  | Under Review of WRI | Five months for the construction. | IF(F120="","",IF(COUNT(AI120:AV120)=0,IF(AA120="","Not started",AA120),SUBSTITUTE(LOOKUP(2,1/(AI120:AV120<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F120="",COUNT(AI120:AV120)=0),"",TODAY()-LOOKUP(2,1/(AI120:AV120<>""),AI120:AV120)) | IF(OR(F120="",COUNT(AI120:AV120)<2),"",LOOKUP(2,1/(AI120:AV120<>""),AI120:AV120)-MIN(AI120:AV120)) | IF(OR(AD120="",AC120="Not started",AC120=""),"",IFERROR(AD120-IF(VLOOKUP(AC120,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC120,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F120="","",IF(OR(AA120="Cancelled",AC120="Cancelled"),"Cancelled",IF(OR(AC120="Completed / Handover",Y120<>"",Z120>=100),"Completed — on track",IF(O120="Not awarded",IF(U120="",IF(X120="","No planned date",IF(TODAY()>X120,"Behind — past planned date",IF(X120-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U120,"Behind — award date passed",IF(U120-TODAY()<=30,"At risk — close to off track","On track"))),IF(X120="","No planned date",IF(AND(TODAY()>X120,OR(Z120="",Z120<100)),"Behind — past end date",IF(AND(T120<>"",X120<>"",Z120<>"",(Z120<100),((TODAY()-T120)/MAX(X120-T120,1)*100)-Z120>15),"Behind — progress lag",IF(AND(X120-TODAY()<=30,X120-TODAY()>=0,OR(Z120="",Z120<90)),"At risk — close to off track","On track")))))))) | IF(OR(F120="",AC120="Completed / Handover",AC120="Cancelled"),"",IF(O120="Not awarded",IF(U120<>"",U120-TODAY(),IF(X120="","",X120-TODAY())),IF(X120="","",X120-TODAY()))) | [14 empty] | IF(OR(F120="",AJ120=""),"",IF(COUNT(AI120:AI120)=0,"",AJ120-LOOKUP(2,1/(AI120:AI120<>""),AI120:AI120))) | IF(OR(F120="",AK120=""),"",IF(COUNT(AI120:AJ120)=0,"",AK120-LOOKUP(2,1/(AI120:AJ120<>""),AI120:AJ120))) | IF(OR(F120="",AL120=""),"",IF(COUNT(AI120:AK120)=0,"",AL120-LOOKUP(2,1/(AI120:AK120<>""),AI120:AK120))) | IF(OR(F120="",AM120=""),"",IF(COUNT(AI120:AL120)=0,"",AM120-LOOKUP(2,1/(AI120:AL120<>""),AI120:AL120))) | IF(OR(F120="",AN120=""),"",IF(COUNT(AI120:AM120)=0,"",AN120-LOOKUP(2,1/(AI120:AM120<>""),AI120:AM120))) | IF(OR(F120="",AO120=""),"",IF(COUNT(AI120:AN120)=0,"",AO120-LOOKUP(2,1/(AI120:AN120<>""),AI120:AN120))) | IF(OR(F120="",AP120=""),"",IF(COUNT(AI120:AO120)=0,"",AP120-LOOKUP(2,1/(AI120:AO120<>""),AI120:AO120))) | IF(OR(F120="",AQ120=""),"",IF(COUNT(AI120:AP120)=0,"",AQ120-LOOKUP(2,1/(AI120:AP120<>""),AI120:AP120))) | IF(OR(F120="",AR120=""),"",IF(COUNT(AI120:AQ120)=0,"",AR120-LOOKUP(2,1/(AI120:AQ120<>""),AI120:AQ120))) | IF(OR(F120="",AS120=""),"",IF(COUNT(AI120:AR120)=0,"",AS120-LOOKUP(2,1/(AI120:AR120<>""),AI120:AR120))) | IF(OR(F120="",AT120=""),"",IF(COUNT(AI120:AS120)=0,"",AT120-LOOKUP(2,1/(AI120:AS120<>""),AI120:AS120))) | IF(OR(F120="",AU120=""),"",IF(COUNT(AI120:AT120)=0,"",AU120-LOOKUP(2,1/(AI120:AT120<>""),AI120:AT120))) | IF(OR(F120="",AV120=""),"",IF(COUNT(AI120:AU120)=0,"",AV120-LOOKUP(2,1/(AI120:AU120<>""),AI120:AU120))) | IF(J120="","All_Provinces",IFERROR(VLOOKUP(J120,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K120="","All_Districts",IFERROR(VLOOKUP(K120,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F121="","",ROW()-3) | AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | 12 of 12 | AF2-DIS-N-079 | Serdagh Kali Drip irrigation schemes | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Naish | Serdagh Kali | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ121="","",AQ121) | 2027-01-25 | 4.9 | 2027-06-24 | IF(W121<>"",W121,IF(OR(T121="",V121=""),"",EDATE(T121,V121))) |  |  | Under Review of WRI | Five months for the construction. | IF(F121="","",IF(COUNT(AI121:AV121)=0,IF(AA121="","Not started",AA121),SUBSTITUTE(LOOKUP(2,1/(AI121:AV121<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F121="",COUNT(AI121:AV121)=0),"",TODAY()-LOOKUP(2,1/(AI121:AV121<>""),AI121:AV121)) | IF(OR(F121="",COUNT(AI121:AV121)<2),"",LOOKUP(2,1/(AI121:AV121<>""),AI121:AV121)-MIN(AI121:AV121)) | IF(OR(AD121="",AC121="Not started",AC121=""),"",IFERROR(AD121-IF(VLOOKUP(AC121,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC121,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F121="","",IF(OR(AA121="Cancelled",AC121="Cancelled"),"Cancelled",IF(OR(AC121="Completed / Handover",Y121<>"",Z121>=100),"Completed — on track",IF(O121="Not awarded",IF(U121="",IF(X121="","No planned date",IF(TODAY()>X121,"Behind — past planned date",IF(X121-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U121,"Behind — award date passed",IF(U121-TODAY()<=30,"At risk — close to off track","On track"))),IF(X121="","No planned date",IF(AND(TODAY()>X121,OR(Z121="",Z121<100)),"Behind — past end date",IF(AND(T121<>"",X121<>"",Z121<>"",(Z121<100),((TODAY()-T121)/MAX(X121-T121,1)*100)-Z121>15),"Behind — progress lag",IF(AND(X121-TODAY()<=30,X121-TODAY()>=0,OR(Z121="",Z121<90)),"At risk — close to off track","On track")))))))) | IF(OR(F121="",AC121="Completed / Handover",AC121="Cancelled"),"",IF(O121="Not awarded",IF(U121<>"",U121-TODAY(),IF(X121="","",X121-TODAY())),IF(X121="","",X121-TODAY()))) | [14 empty] | IF(OR(F121="",AJ121=""),"",IF(COUNT(AI121:AI121)=0,"",AJ121-LOOKUP(2,1/(AI121:AI121<>""),AI121:AI121))) | IF(OR(F121="",AK121=""),"",IF(COUNT(AI121:AJ121)=0,"",AK121-LOOKUP(2,1/(AI121:AJ121<>""),AI121:AJ121))) | IF(OR(F121="",AL121=""),"",IF(COUNT(AI121:AK121)=0,"",AL121-LOOKUP(2,1/(AI121:AK121<>""),AI121:AK121))) | IF(OR(F121="",AM121=""),"",IF(COUNT(AI121:AL121)=0,"",AM121-LOOKUP(2,1/(AI121:AL121<>""),AI121:AL121))) | IF(OR(F121="",AN121=""),"",IF(COUNT(AI121:AM121)=0,"",AN121-LOOKUP(2,1/(AI121:AM121<>""),AI121:AM121))) | IF(OR(F121="",AO121=""),"",IF(COUNT(AI121:AN121)=0,"",AO121-LOOKUP(2,1/(AI121:AN121<>""),AI121:AN121))) | IF(OR(F121="",AP121=""),"",IF(COUNT(AI121:AO121)=0,"",AP121-LOOKUP(2,1/(AI121:AO121<>""),AI121:AO121))) | IF(OR(F121="",AQ121=""),"",IF(COUNT(AI121:AP121)=0,"",AQ121-LOOKUP(2,1/(AI121:AP121<>""),AI121:AP121))) | IF(OR(F121="",AR121=""),"",IF(COUNT(AI121:AQ121)=0,"",AR121-LOOKUP(2,1/(AI121:AQ121<>""),AI121:AQ121))) | IF(OR(F121="",AS121=""),"",IF(COUNT(AI121:AR121)=0,"",AS121-LOOKUP(2,1/(AI121:AR121<>""),AI121:AR121))) | IF(OR(F121="",AT121=""),"",IF(COUNT(AI121:AS121)=0,"",AT121-LOOKUP(2,1/(AI121:AS121<>""),AI121:AS121))) | IF(OR(F121="",AU121=""),"",IF(COUNT(AI121:AT121)=0,"",AU121-LOOKUP(2,1/(AI121:AT121<>""),AI121:AT121))) | IF(OR(F121="",AV121=""),"",IF(COUNT(AI121:AU121)=0,"",AV121-LOOKUP(2,1/(AI121:AU121<>""),AI121:AU121))) | IF(J121="","All_Provinces",IFERROR(VLOOKUP(J121,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K121="","All_Districts",IFERROR(VLOOKUP(K121,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F122="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 1 of 9 | AF2-DIS-N-080 | Chaqul Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Baharak | Chaqul | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Nasratullah |  | 4250 | IF(AQ122="","",AQ122) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W122<>"",W122,IF(OR(T122="",V122=""),"",EDATE(T122,V122))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Nasratullah | IF(F122="","",IF(COUNT(AI122:AV122)=0,IF(AA122="","Not started",AA122),SUBSTITUTE(LOOKUP(2,1/(AI122:AV122<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F122="",COUNT(AI122:AV122)=0),"",TODAY()-LOOKUP(2,1/(AI122:AV122<>""),AI122:AV122)) | IF(OR(F122="",COUNT(AI122:AV122)<2),"",LOOKUP(2,1/(AI122:AV122<>""),AI122:AV122)-MIN(AI122:AV122)) | IF(OR(AD122="",AC122="Not started",AC122=""),"",IFERROR(AD122-IF(VLOOKUP(AC122,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC122,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F122="","",IF(OR(AA122="Cancelled",AC122="Cancelled"),"Cancelled",IF(OR(AC122="Completed / Handover",Y122<>"",Z122>=100),"Completed — on track",IF(O122="Not awarded",IF(U122="",IF(X122="","No planned date",IF(TODAY()>X122,"Behind — past planned date",IF(X122-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U122,"Behind — award date passed",IF(U122-TODAY()<=30,"At risk — close to off track","On track"))),IF(X122="","No planned date",IF(AND(TODAY()>X122,OR(Z122="",Z122<100)),"Behind — past end date",IF(AND(T122<>"",X122<>"",Z122<>"",(Z122<100),((TODAY()-T122)/MAX(X122-T122,1)*100)-Z122>15),"Behind — progress lag",IF(AND(X122-TODAY()<=30,X122-TODAY()>=0,OR(Z122="",Z122<90)),"At risk — close to off track","On track")))))))) | IF(OR(F122="",AC122="Completed / Handover",AC122="Cancelled"),"",IF(O122="Not awarded",IF(U122<>"",U122-TODAY(),IF(X122="","",X122-TODAY())),IF(X122="","",X122-TODAY()))) | [14 empty] | IF(OR(F122="",AJ122=""),"",IF(COUNT(AI122:AI122)=0,"",AJ122-LOOKUP(2,1/(AI122:AI122<>""),AI122:AI122))) | IF(OR(F122="",AK122=""),"",IF(COUNT(AI122:AJ122)=0,"",AK122-LOOKUP(2,1/(AI122:AJ122<>""),AI122:AJ122))) | IF(OR(F122="",AL122=""),"",IF(COUNT(AI122:AK122)=0,"",AL122-LOOKUP(2,1/(AI122:AK122<>""),AI122:AK122))) | IF(OR(F122="",AM122=""),"",IF(COUNT(AI122:AL122)=0,"",AM122-LOOKUP(2,1/(AI122:AL122<>""),AI122:AL122))) | IF(OR(F122="",AN122=""),"",IF(COUNT(AI122:AM122)=0,"",AN122-LOOKUP(2,1/(AI122:AM122<>""),AI122:AM122))) | IF(OR(F122="",AO122=""),"",IF(COUNT(AI122:AN122)=0,"",AO122-LOOKUP(2,1/(AI122:AN122<>""),AI122:AN122))) | IF(OR(F122="",AP122=""),"",IF(COUNT(AI122:AO122)=0,"",AP122-LOOKUP(2,1/(AI122:AO122<>""),AI122:AO122))) | IF(OR(F122="",AQ122=""),"",IF(COUNT(AI122:AP122)=0,"",AQ122-LOOKUP(2,1/(AI122:AP122<>""),AI122:AP122))) | IF(OR(F122="",AR122=""),"",IF(COUNT(AI122:AQ122)=0,"",AR122-LOOKUP(2,1/(AI122:AQ122<>""),AI122:AQ122))) | IF(OR(F122="",AS122=""),"",IF(COUNT(AI122:AR122)=0,"",AS122-LOOKUP(2,1/(AI122:AR122<>""),AI122:AR122))) | IF(OR(F122="",AT122=""),"",IF(COUNT(AI122:AS122)=0,"",AT122-LOOKUP(2,1/(AI122:AS122<>""),AI122:AS122))) | IF(OR(F122="",AU122=""),"",IF(COUNT(AI122:AT122)=0,"",AU122-LOOKUP(2,1/(AI122:AT122<>""),AI122:AT122))) | IF(OR(F122="",AV122=""),"",IF(COUNT(AI122:AU122)=0,"",AV122-LOOKUP(2,1/(AI122:AU122<>""),AI122:AU122))) | IF(J122="","All_Provinces",IFERROR(VLOOKUP(J122,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K122="","All_Districts",IFERROR(VLOOKUP(K122,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F123="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 2 of 9 | AF2-DIS-N-081 | Haji Atta Khan Drip Irrgiatation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Kunduz | Chahar Dara | Haji Atta Khan Masjid | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Haji Hamayoon Salimi |  | 8500 | IF(AQ123="","",AQ123) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W123<>"",W123,IF(OR(T123="",V123=""),"",EDATE(T123,V123))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Haji Hamayoon Salimi | IF(F123="","",IF(COUNT(AI123:AV123)=0,IF(AA123="","Not started",AA123),SUBSTITUTE(LOOKUP(2,1/(AI123:AV123<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F123="",COUNT(AI123:AV123)=0),"",TODAY()-LOOKUP(2,1/(AI123:AV123<>""),AI123:AV123)) | IF(OR(F123="",COUNT(AI123:AV123)<2),"",LOOKUP(2,1/(AI123:AV123<>""),AI123:AV123)-MIN(AI123:AV123)) | IF(OR(AD123="",AC123="Not started",AC123=""),"",IFERROR(AD123-IF(VLOOKUP(AC123,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC123,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F123="","",IF(OR(AA123="Cancelled",AC123="Cancelled"),"Cancelled",IF(OR(AC123="Completed / Handover",Y123<>"",Z123>=100),"Completed — on track",IF(O123="Not awarded",IF(U123="",IF(X123="","No planned date",IF(TODAY()>X123,"Behind — past planned date",IF(X123-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U123,"Behind — award date passed",IF(U123-TODAY()<=30,"At risk — close to off track","On track"))),IF(X123="","No planned date",IF(AND(TODAY()>X123,OR(Z123="",Z123<100)),"Behind — past end date",IF(AND(T123<>"",X123<>"",Z123<>"",(Z123<100),((TODAY()-T123)/MAX(X123-T123,1)*100)-Z123>15),"Behind — progress lag",IF(AND(X123-TODAY()<=30,X123-TODAY()>=0,OR(Z123="",Z123<90)),"At risk — close to off track","On track")))))))) | IF(OR(F123="",AC123="Completed / Handover",AC123="Cancelled"),"",IF(O123="Not awarded",IF(U123<>"",U123-TODAY(),IF(X123="","",X123-TODAY())),IF(X123="","",X123-TODAY()))) | [14 empty] | IF(OR(F123="",AJ123=""),"",IF(COUNT(AI123:AI123)=0,"",AJ123-LOOKUP(2,1/(AI123:AI123<>""),AI123:AI123))) | IF(OR(F123="",AK123=""),"",IF(COUNT(AI123:AJ123)=0,"",AK123-LOOKUP(2,1/(AI123:AJ123<>""),AI123:AJ123))) | IF(OR(F123="",AL123=""),"",IF(COUNT(AI123:AK123)=0,"",AL123-LOOKUP(2,1/(AI123:AK123<>""),AI123:AK123))) | IF(OR(F123="",AM123=""),"",IF(COUNT(AI123:AL123)=0,"",AM123-LOOKUP(2,1/(AI123:AL123<>""),AI123:AL123))) | IF(OR(F123="",AN123=""),"",IF(COUNT(AI123:AM123)=0,"",AN123-LOOKUP(2,1/(AI123:AM123<>""),AI123:AM123))) | IF(OR(F123="",AO123=""),"",IF(COUNT(AI123:AN123)=0,"",AO123-LOOKUP(2,1/(AI123:AN123<>""),AI123:AN123))) | IF(OR(F123="",AP123=""),"",IF(COUNT(AI123:AO123)=0,"",AP123-LOOKUP(2,1/(AI123:AO123<>""),AI123:AO123))) | IF(OR(F123="",AQ123=""),"",IF(COUNT(AI123:AP123)=0,"",AQ123-LOOKUP(2,1/(AI123:AP123<>""),AI123:AP123))) | IF(OR(F123="",AR123=""),"",IF(COUNT(AI123:AQ123)=0,"",AR123-LOOKUP(2,1/(AI123:AQ123<>""),AI123:AQ123))) | IF(OR(F123="",AS123=""),"",IF(COUNT(AI123:AR123)=0,"",AS123-LOOKUP(2,1/(AI123:AR123<>""),AI123:AR123))) | IF(OR(F123="",AT123=""),"",IF(COUNT(AI123:AS123)=0,"",AT123-LOOKUP(2,1/(AI123:AS123<>""),AI123:AS123))) | IF(OR(F123="",AU123=""),"",IF(COUNT(AI123:AT123)=0,"",AU123-LOOKUP(2,1/(AI123:AT123<>""),AI123:AT123))) | IF(OR(F123="",AV123=""),"",IF(COUNT(AI123:AU123)=0,"",AV123-LOOKUP(2,1/(AI123:AU123<>""),AI123:AU123))) | IF(J123="","All_Provinces",IFERROR(VLOOKUP(J123,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K123="","All_Districts",IFERROR(VLOOKUP(K123,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F124="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 3 of 9 | AF2-DIS-N-082 | Khoja Alwan Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Dand Ghori | Khoja Alwan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Haji Amir Gul |  | 8500 | IF(AQ124="","",AQ124) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W124<>"",W124,IF(OR(T124="",V124=""),"",EDATE(T124,V124))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Haji Amir Gul | IF(F124="","",IF(COUNT(AI124:AV124)=0,IF(AA124="","Not started",AA124),SUBSTITUTE(LOOKUP(2,1/(AI124:AV124<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F124="",COUNT(AI124:AV124)=0),"",TODAY()-LOOKUP(2,1/(AI124:AV124<>""),AI124:AV124)) | IF(OR(F124="",COUNT(AI124:AV124)<2),"",LOOKUP(2,1/(AI124:AV124<>""),AI124:AV124)-MIN(AI124:AV124)) | IF(OR(AD124="",AC124="Not started",AC124=""),"",IFERROR(AD124-IF(VLOOKUP(AC124,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC124,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F124="","",IF(OR(AA124="Cancelled",AC124="Cancelled"),"Cancelled",IF(OR(AC124="Completed / Handover",Y124<>"",Z124>=100),"Completed — on track",IF(O124="Not awarded",IF(U124="",IF(X124="","No planned date",IF(TODAY()>X124,"Behind — past planned date",IF(X124-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U124,"Behind — award date passed",IF(U124-TODAY()<=30,"At risk — close to off track","On track"))),IF(X124="","No planned date",IF(AND(TODAY()>X124,OR(Z124="",Z124<100)),"Behind — past end date",IF(AND(T124<>"",X124<>"",Z124<>"",(Z124<100),((TODAY()-T124)/MAX(X124-T124,1)*100)-Z124>15),"Behind — progress lag",IF(AND(X124-TODAY()<=30,X124-TODAY()>=0,OR(Z124="",Z124<90)),"At risk — close to off track","On track")))))))) | IF(OR(F124="",AC124="Completed / Handover",AC124="Cancelled"),"",IF(O124="Not awarded",IF(U124<>"",U124-TODAY(),IF(X124="","",X124-TODAY())),IF(X124="","",X124-TODAY()))) | [14 empty] | IF(OR(F124="",AJ124=""),"",IF(COUNT(AI124:AI124)=0,"",AJ124-LOOKUP(2,1/(AI124:AI124<>""),AI124:AI124))) | IF(OR(F124="",AK124=""),"",IF(COUNT(AI124:AJ124)=0,"",AK124-LOOKUP(2,1/(AI124:AJ124<>""),AI124:AJ124))) | IF(OR(F124="",AL124=""),"",IF(COUNT(AI124:AK124)=0,"",AL124-LOOKUP(2,1/(AI124:AK124<>""),AI124:AK124))) | IF(OR(F124="",AM124=""),"",IF(COUNT(AI124:AL124)=0,"",AM124-LOOKUP(2,1/(AI124:AL124<>""),AI124:AL124))) | IF(OR(F124="",AN124=""),"",IF(COUNT(AI124:AM124)=0,"",AN124-LOOKUP(2,1/(AI124:AM124<>""),AI124:AM124))) | IF(OR(F124="",AO124=""),"",IF(COUNT(AI124:AN124)=0,"",AO124-LOOKUP(2,1/(AI124:AN124<>""),AI124:AN124))) | IF(OR(F124="",AP124=""),"",IF(COUNT(AI124:AO124)=0,"",AP124-LOOKUP(2,1/(AI124:AO124<>""),AI124:AO124))) | IF(OR(F124="",AQ124=""),"",IF(COUNT(AI124:AP124)=0,"",AQ124-LOOKUP(2,1/(AI124:AP124<>""),AI124:AP124))) | IF(OR(F124="",AR124=""),"",IF(COUNT(AI124:AQ124)=0,"",AR124-LOOKUP(2,1/(AI124:AQ124<>""),AI124:AQ124))) | IF(OR(F124="",AS124=""),"",IF(COUNT(AI124:AR124)=0,"",AS124-LOOKUP(2,1/(AI124:AR124<>""),AI124:AR124))) | IF(OR(F124="",AT124=""),"",IF(COUNT(AI124:AS124)=0,"",AT124-LOOKUP(2,1/(AI124:AS124<>""),AI124:AS124))) | IF(OR(F124="",AU124=""),"",IF(COUNT(AI124:AT124)=0,"",AU124-LOOKUP(2,1/(AI124:AT124<>""),AI124:AT124))) | IF(OR(F124="",AV124=""),"",IF(COUNT(AI124:AU124)=0,"",AV124-LOOKUP(2,1/(AI124:AU124<>""),AI124:AU124))) | IF(J124="","All_Provinces",IFERROR(VLOOKUP(J124,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K124="","All_Districts",IFERROR(VLOOKUP(K124,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F125="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 4 of 9 | AF2-DIS-N-083 | Khoja Bolak Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Kunudz | Khan Abad | Khoja Bolak | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Mohammad Qasim |  | 8500 | IF(AQ125="","",AQ125) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W125<>"",W125,IF(OR(T125="",V125=""),"",EDATE(T125,V125))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Mohammad Qasim | IF(F125="","",IF(COUNT(AI125:AV125)=0,IF(AA125="","Not started",AA125),SUBSTITUTE(LOOKUP(2,1/(AI125:AV125<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F125="",COUNT(AI125:AV125)=0),"",TODAY()-LOOKUP(2,1/(AI125:AV125<>""),AI125:AV125)) | IF(OR(F125="",COUNT(AI125:AV125)<2),"",LOOKUP(2,1/(AI125:AV125<>""),AI125:AV125)-MIN(AI125:AV125)) | IF(OR(AD125="",AC125="Not started",AC125=""),"",IFERROR(AD125-IF(VLOOKUP(AC125,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC125,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F125="","",IF(OR(AA125="Cancelled",AC125="Cancelled"),"Cancelled",IF(OR(AC125="Completed / Handover",Y125<>"",Z125>=100),"Completed — on track",IF(O125="Not awarded",IF(U125="",IF(X125="","No planned date",IF(TODAY()>X125,"Behind — past planned date",IF(X125-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U125,"Behind — award date passed",IF(U125-TODAY()<=30,"At risk — close to off track","On track"))),IF(X125="","No planned date",IF(AND(TODAY()>X125,OR(Z125="",Z125<100)),"Behind — past end date",IF(AND(T125<>"",X125<>"",Z125<>"",(Z125<100),((TODAY()-T125)/MAX(X125-T125,1)*100)-Z125>15),"Behind — progress lag",IF(AND(X125-TODAY()<=30,X125-TODAY()>=0,OR(Z125="",Z125<90)),"At risk — close to off track","On track")))))))) | IF(OR(F125="",AC125="Completed / Handover",AC125="Cancelled"),"",IF(O125="Not awarded",IF(U125<>"",U125-TODAY(),IF(X125="","",X125-TODAY())),IF(X125="","",X125-TODAY()))) | [14 empty] | IF(OR(F125="",AJ125=""),"",IF(COUNT(AI125:AI125)=0,"",AJ125-LOOKUP(2,1/(AI125:AI125<>""),AI125:AI125))) | IF(OR(F125="",AK125=""),"",IF(COUNT(AI125:AJ125)=0,"",AK125-LOOKUP(2,1/(AI125:AJ125<>""),AI125:AJ125))) | IF(OR(F125="",AL125=""),"",IF(COUNT(AI125:AK125)=0,"",AL125-LOOKUP(2,1/(AI125:AK125<>""),AI125:AK125))) | IF(OR(F125="",AM125=""),"",IF(COUNT(AI125:AL125)=0,"",AM125-LOOKUP(2,1/(AI125:AL125<>""),AI125:AL125))) | IF(OR(F125="",AN125=""),"",IF(COUNT(AI125:AM125)=0,"",AN125-LOOKUP(2,1/(AI125:AM125<>""),AI125:AM125))) | IF(OR(F125="",AO125=""),"",IF(COUNT(AI125:AN125)=0,"",AO125-LOOKUP(2,1/(AI125:AN125<>""),AI125:AN125))) | IF(OR(F125="",AP125=""),"",IF(COUNT(AI125:AO125)=0,"",AP125-LOOKUP(2,1/(AI125:AO125<>""),AI125:AO125))) | IF(OR(F125="",AQ125=""),"",IF(COUNT(AI125:AP125)=0,"",AQ125-LOOKUP(2,1/(AI125:AP125<>""),AI125:AP125))) | IF(OR(F125="",AR125=""),"",IF(COUNT(AI125:AQ125)=0,"",AR125-LOOKUP(2,1/(AI125:AQ125<>""),AI125:AQ125))) | IF(OR(F125="",AS125=""),"",IF(COUNT(AI125:AR125)=0,"",AS125-LOOKUP(2,1/(AI125:AR125<>""),AI125:AR125))) | IF(OR(F125="",AT125=""),"",IF(COUNT(AI125:AS125)=0,"",AT125-LOOKUP(2,1/(AI125:AS125<>""),AI125:AS125))) | IF(OR(F125="",AU125=""),"",IF(COUNT(AI125:AT125)=0,"",AU125-LOOKUP(2,1/(AI125:AT125<>""),AI125:AT125))) | IF(OR(F125="",AV125=""),"",IF(COUNT(AI125:AU125)=0,"",AV125-LOOKUP(2,1/(AI125:AU125<>""),AI125:AU125))) | IF(J125="","All_Provinces",IFERROR(VLOOKUP(J125,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K125="","All_Districts",IFERROR(VLOOKUP(K125,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F126="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 5 of 9 | AF2-DIS-N-084 | Masjid Dr. Shafiq Mamakhail Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Kunduz | Chahar Dara | Mamakhail | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Ziaurrahman Mohammadi |  | 4250 | IF(AQ126="","",AQ126) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W126<>"",W126,IF(OR(T126="",V126=""),"",EDATE(T126,V126))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Ziaurrahman Mohammadi | IF(F126="","",IF(COUNT(AI126:AV126)=0,IF(AA126="","Not started",AA126),SUBSTITUTE(LOOKUP(2,1/(AI126:AV126<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F126="",COUNT(AI126:AV126)=0),"",TODAY()-LOOKUP(2,1/(AI126:AV126<>""),AI126:AV126)) | IF(OR(F126="",COUNT(AI126:AV126)<2),"",LOOKUP(2,1/(AI126:AV126<>""),AI126:AV126)-MIN(AI126:AV126)) | IF(OR(AD126="",AC126="Not started",AC126=""),"",IFERROR(AD126-IF(VLOOKUP(AC126,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC126,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F126="","",IF(OR(AA126="Cancelled",AC126="Cancelled"),"Cancelled",IF(OR(AC126="Completed / Handover",Y126<>"",Z126>=100),"Completed — on track",IF(O126="Not awarded",IF(U126="",IF(X126="","No planned date",IF(TODAY()>X126,"Behind — past planned date",IF(X126-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U126,"Behind — award date passed",IF(U126-TODAY()<=30,"At risk — close to off track","On track"))),IF(X126="","No planned date",IF(AND(TODAY()>X126,OR(Z126="",Z126<100)),"Behind — past end date",IF(AND(T126<>"",X126<>"",Z126<>"",(Z126<100),((TODAY()-T126)/MAX(X126-T126,1)*100)-Z126>15),"Behind — progress lag",IF(AND(X126-TODAY()<=30,X126-TODAY()>=0,OR(Z126="",Z126<90)),"At risk — close to off track","On track")))))))) | IF(OR(F126="",AC126="Completed / Handover",AC126="Cancelled"),"",IF(O126="Not awarded",IF(U126<>"",U126-TODAY(),IF(X126="","",X126-TODAY())),IF(X126="","",X126-TODAY()))) | [14 empty] | IF(OR(F126="",AJ126=""),"",IF(COUNT(AI126:AI126)=0,"",AJ126-LOOKUP(2,1/(AI126:AI126<>""),AI126:AI126))) | IF(OR(F126="",AK126=""),"",IF(COUNT(AI126:AJ126)=0,"",AK126-LOOKUP(2,1/(AI126:AJ126<>""),AI126:AJ126))) | IF(OR(F126="",AL126=""),"",IF(COUNT(AI126:AK126)=0,"",AL126-LOOKUP(2,1/(AI126:AK126<>""),AI126:AK126))) | IF(OR(F126="",AM126=""),"",IF(COUNT(AI126:AL126)=0,"",AM126-LOOKUP(2,1/(AI126:AL126<>""),AI126:AL126))) | IF(OR(F126="",AN126=""),"",IF(COUNT(AI126:AM126)=0,"",AN126-LOOKUP(2,1/(AI126:AM126<>""),AI126:AM126))) | IF(OR(F126="",AO126=""),"",IF(COUNT(AI126:AN126)=0,"",AO126-LOOKUP(2,1/(AI126:AN126<>""),AI126:AN126))) | IF(OR(F126="",AP126=""),"",IF(COUNT(AI126:AO126)=0,"",AP126-LOOKUP(2,1/(AI126:AO126<>""),AI126:AO126))) | IF(OR(F126="",AQ126=""),"",IF(COUNT(AI126:AP126)=0,"",AQ126-LOOKUP(2,1/(AI126:AP126<>""),AI126:AP126))) | IF(OR(F126="",AR126=""),"",IF(COUNT(AI126:AQ126)=0,"",AR126-LOOKUP(2,1/(AI126:AQ126<>""),AI126:AQ126))) | IF(OR(F126="",AS126=""),"",IF(COUNT(AI126:AR126)=0,"",AS126-LOOKUP(2,1/(AI126:AR126<>""),AI126:AR126))) | IF(OR(F126="",AT126=""),"",IF(COUNT(AI126:AS126)=0,"",AT126-LOOKUP(2,1/(AI126:AS126<>""),AI126:AS126))) | IF(OR(F126="",AU126=""),"",IF(COUNT(AI126:AT126)=0,"",AU126-LOOKUP(2,1/(AI126:AT126<>""),AI126:AT126))) | IF(OR(F126="",AV126=""),"",IF(COUNT(AI126:AU126)=0,"",AV126-LOOKUP(2,1/(AI126:AU126<>""),AI126:AU126))) | IF(J126="","All_Provinces",IFERROR(VLOOKUP(J126,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K126="","All_Districts",IFERROR(VLOOKUP(K126,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F127="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 6 of 9 | AF2-DIS-N-085 | Qatar Fateh Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Dahna-e-Ghori | Qatar Fateh | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Haji Nazar Gul |  | 4250 | IF(AQ127="","",AQ127) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W127<>"",W127,IF(OR(T127="",V127=""),"",EDATE(T127,V127))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Haji Nazar Gul | IF(F127="","",IF(COUNT(AI127:AV127)=0,IF(AA127="","Not started",AA127),SUBSTITUTE(LOOKUP(2,1/(AI127:AV127<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F127="",COUNT(AI127:AV127)=0),"",TODAY()-LOOKUP(2,1/(AI127:AV127<>""),AI127:AV127)) | IF(OR(F127="",COUNT(AI127:AV127)<2),"",LOOKUP(2,1/(AI127:AV127<>""),AI127:AV127)-MIN(AI127:AV127)) | IF(OR(AD127="",AC127="Not started",AC127=""),"",IFERROR(AD127-IF(VLOOKUP(AC127,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC127,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F127="","",IF(OR(AA127="Cancelled",AC127="Cancelled"),"Cancelled",IF(OR(AC127="Completed / Handover",Y127<>"",Z127>=100),"Completed — on track",IF(O127="Not awarded",IF(U127="",IF(X127="","No planned date",IF(TODAY()>X127,"Behind — past planned date",IF(X127-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U127,"Behind — award date passed",IF(U127-TODAY()<=30,"At risk — close to off track","On track"))),IF(X127="","No planned date",IF(AND(TODAY()>X127,OR(Z127="",Z127<100)),"Behind — past end date",IF(AND(T127<>"",X127<>"",Z127<>"",(Z127<100),((TODAY()-T127)/MAX(X127-T127,1)*100)-Z127>15),"Behind — progress lag",IF(AND(X127-TODAY()<=30,X127-TODAY()>=0,OR(Z127="",Z127<90)),"At risk — close to off track","On track")))))))) | IF(OR(F127="",AC127="Completed / Handover",AC127="Cancelled"),"",IF(O127="Not awarded",IF(U127<>"",U127-TODAY(),IF(X127="","",X127-TODAY())),IF(X127="","",X127-TODAY()))) | [14 empty] | IF(OR(F127="",AJ127=""),"",IF(COUNT(AI127:AI127)=0,"",AJ127-LOOKUP(2,1/(AI127:AI127<>""),AI127:AI127))) | IF(OR(F127="",AK127=""),"",IF(COUNT(AI127:AJ127)=0,"",AK127-LOOKUP(2,1/(AI127:AJ127<>""),AI127:AJ127))) | IF(OR(F127="",AL127=""),"",IF(COUNT(AI127:AK127)=0,"",AL127-LOOKUP(2,1/(AI127:AK127<>""),AI127:AK127))) | IF(OR(F127="",AM127=""),"",IF(COUNT(AI127:AL127)=0,"",AM127-LOOKUP(2,1/(AI127:AL127<>""),AI127:AL127))) | IF(OR(F127="",AN127=""),"",IF(COUNT(AI127:AM127)=0,"",AN127-LOOKUP(2,1/(AI127:AM127<>""),AI127:AM127))) | IF(OR(F127="",AO127=""),"",IF(COUNT(AI127:AN127)=0,"",AO127-LOOKUP(2,1/(AI127:AN127<>""),AI127:AN127))) | IF(OR(F127="",AP127=""),"",IF(COUNT(AI127:AO127)=0,"",AP127-LOOKUP(2,1/(AI127:AO127<>""),AI127:AO127))) | IF(OR(F127="",AQ127=""),"",IF(COUNT(AI127:AP127)=0,"",AQ127-LOOKUP(2,1/(AI127:AP127<>""),AI127:AP127))) | IF(OR(F127="",AR127=""),"",IF(COUNT(AI127:AQ127)=0,"",AR127-LOOKUP(2,1/(AI127:AQ127<>""),AI127:AQ127))) | IF(OR(F127="",AS127=""),"",IF(COUNT(AI127:AR127)=0,"",AS127-LOOKUP(2,1/(AI127:AR127<>""),AI127:AR127))) | IF(OR(F127="",AT127=""),"",IF(COUNT(AI127:AS127)=0,"",AT127-LOOKUP(2,1/(AI127:AS127<>""),AI127:AS127))) | IF(OR(F127="",AU127=""),"",IF(COUNT(AI127:AT127)=0,"",AU127-LOOKUP(2,1/(AI127:AT127<>""),AI127:AT127))) | IF(OR(F127="",AV127=""),"",IF(COUNT(AI127:AU127)=0,"",AV127-LOOKUP(2,1/(AI127:AU127<>""),AI127:AU127))) | IF(J127="","All_Provinces",IFERROR(VLOOKUP(J127,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K127="","All_Districts",IFERROR(VLOOKUP(K127,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F128="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 7 of 9 | AF2-DIS-N-086 | Sara-e-Gharbi Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Kishem | Sara-e-Gharbi | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Haji Jamal |  | 8500 | IF(AQ128="","",AQ128) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W128<>"",W128,IF(OR(T128="",V128=""),"",EDATE(T128,V128))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Haji Jamal | IF(F128="","",IF(COUNT(AI128:AV128)=0,IF(AA128="","Not started",AA128),SUBSTITUTE(LOOKUP(2,1/(AI128:AV128<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F128="",COUNT(AI128:AV128)=0),"",TODAY()-LOOKUP(2,1/(AI128:AV128<>""),AI128:AV128)) | IF(OR(F128="",COUNT(AI128:AV128)<2),"",LOOKUP(2,1/(AI128:AV128<>""),AI128:AV128)-MIN(AI128:AV128)) | IF(OR(AD128="",AC128="Not started",AC128=""),"",IFERROR(AD128-IF(VLOOKUP(AC128,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC128,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F128="","",IF(OR(AA128="Cancelled",AC128="Cancelled"),"Cancelled",IF(OR(AC128="Completed / Handover",Y128<>"",Z128>=100),"Completed — on track",IF(O128="Not awarded",IF(U128="",IF(X128="","No planned date",IF(TODAY()>X128,"Behind — past planned date",IF(X128-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U128,"Behind — award date passed",IF(U128-TODAY()<=30,"At risk — close to off track","On track"))),IF(X128="","No planned date",IF(AND(TODAY()>X128,OR(Z128="",Z128<100)),"Behind — past end date",IF(AND(T128<>"",X128<>"",Z128<>"",(Z128<100),((TODAY()-T128)/MAX(X128-T128,1)*100)-Z128>15),"Behind — progress lag",IF(AND(X128-TODAY()<=30,X128-TODAY()>=0,OR(Z128="",Z128<90)),"At risk — close to off track","On track")))))))) | IF(OR(F128="",AC128="Completed / Handover",AC128="Cancelled"),"",IF(O128="Not awarded",IF(U128<>"",U128-TODAY(),IF(X128="","",X128-TODAY())),IF(X128="","",X128-TODAY()))) | [14 empty] | IF(OR(F128="",AJ128=""),"",IF(COUNT(AI128:AI128)=0,"",AJ128-LOOKUP(2,1/(AI128:AI128<>""),AI128:AI128))) | IF(OR(F128="",AK128=""),"",IF(COUNT(AI128:AJ128)=0,"",AK128-LOOKUP(2,1/(AI128:AJ128<>""),AI128:AJ128))) | IF(OR(F128="",AL128=""),"",IF(COUNT(AI128:AK128)=0,"",AL128-LOOKUP(2,1/(AI128:AK128<>""),AI128:AK128))) | IF(OR(F128="",AM128=""),"",IF(COUNT(AI128:AL128)=0,"",AM128-LOOKUP(2,1/(AI128:AL128<>""),AI128:AL128))) | IF(OR(F128="",AN128=""),"",IF(COUNT(AI128:AM128)=0,"",AN128-LOOKUP(2,1/(AI128:AM128<>""),AI128:AM128))) | IF(OR(F128="",AO128=""),"",IF(COUNT(AI128:AN128)=0,"",AO128-LOOKUP(2,1/(AI128:AN128<>""),AI128:AN128))) | IF(OR(F128="",AP128=""),"",IF(COUNT(AI128:AO128)=0,"",AP128-LOOKUP(2,1/(AI128:AO128<>""),AI128:AO128))) | IF(OR(F128="",AQ128=""),"",IF(COUNT(AI128:AP128)=0,"",AQ128-LOOKUP(2,1/(AI128:AP128<>""),AI128:AP128))) | IF(OR(F128="",AR128=""),"",IF(COUNT(AI128:AQ128)=0,"",AR128-LOOKUP(2,1/(AI128:AQ128<>""),AI128:AQ128))) | IF(OR(F128="",AS128=""),"",IF(COUNT(AI128:AR128)=0,"",AS128-LOOKUP(2,1/(AI128:AR128<>""),AI128:AR128))) | IF(OR(F128="",AT128=""),"",IF(COUNT(AI128:AS128)=0,"",AT128-LOOKUP(2,1/(AI128:AS128<>""),AI128:AS128))) | IF(OR(F128="",AU128=""),"",IF(COUNT(AI128:AT128)=0,"",AU128-LOOKUP(2,1/(AI128:AT128<>""),AI128:AT128))) | IF(OR(F128="",AV128=""),"",IF(COUNT(AI128:AU128)=0,"",AV128-LOOKUP(2,1/(AI128:AU128<>""),AI128:AU128))) | IF(J128="","All_Provinces",IFERROR(VLOOKUP(J128,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K128="","All_Districts",IFERROR(VLOOKUP(K128,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F129="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 8 of 9 | AF2-DIS-N-087 | Shamba Bazar Drip Irrgiatation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Kunduz | Dashte Archi | Shamba Bazar | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Shamsurahman |  | 4250 | IF(AQ129="","",AQ129) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W129<>"",W129,IF(OR(T129="",V129=""),"",EDATE(T129,V129))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Shamsurahman | IF(F129="","",IF(COUNT(AI129:AV129)=0,IF(AA129="","Not started",AA129),SUBSTITUTE(LOOKUP(2,1/(AI129:AV129<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F129="",COUNT(AI129:AV129)=0),"",TODAY()-LOOKUP(2,1/(AI129:AV129<>""),AI129:AV129)) | IF(OR(F129="",COUNT(AI129:AV129)<2),"",LOOKUP(2,1/(AI129:AV129<>""),AI129:AV129)-MIN(AI129:AV129)) | IF(OR(AD129="",AC129="Not started",AC129=""),"",IFERROR(AD129-IF(VLOOKUP(AC129,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC129,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F129="","",IF(OR(AA129="Cancelled",AC129="Cancelled"),"Cancelled",IF(OR(AC129="Completed / Handover",Y129<>"",Z129>=100),"Completed — on track",IF(O129="Not awarded",IF(U129="",IF(X129="","No planned date",IF(TODAY()>X129,"Behind — past planned date",IF(X129-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U129,"Behind — award date passed",IF(U129-TODAY()<=30,"At risk — close to off track","On track"))),IF(X129="","No planned date",IF(AND(TODAY()>X129,OR(Z129="",Z129<100)),"Behind — past end date",IF(AND(T129<>"",X129<>"",Z129<>"",(Z129<100),((TODAY()-T129)/MAX(X129-T129,1)*100)-Z129>15),"Behind — progress lag",IF(AND(X129-TODAY()<=30,X129-TODAY()>=0,OR(Z129="",Z129<90)),"At risk — close to off track","On track")))))))) | IF(OR(F129="",AC129="Completed / Handover",AC129="Cancelled"),"",IF(O129="Not awarded",IF(U129<>"",U129-TODAY(),IF(X129="","",X129-TODAY())),IF(X129="","",X129-TODAY()))) | [14 empty] | IF(OR(F129="",AJ129=""),"",IF(COUNT(AI129:AI129)=0,"",AJ129-LOOKUP(2,1/(AI129:AI129<>""),AI129:AI129))) | IF(OR(F129="",AK129=""),"",IF(COUNT(AI129:AJ129)=0,"",AK129-LOOKUP(2,1/(AI129:AJ129<>""),AI129:AJ129))) | IF(OR(F129="",AL129=""),"",IF(COUNT(AI129:AK129)=0,"",AL129-LOOKUP(2,1/(AI129:AK129<>""),AI129:AK129))) | IF(OR(F129="",AM129=""),"",IF(COUNT(AI129:AL129)=0,"",AM129-LOOKUP(2,1/(AI129:AL129<>""),AI129:AL129))) | IF(OR(F129="",AN129=""),"",IF(COUNT(AI129:AM129)=0,"",AN129-LOOKUP(2,1/(AI129:AM129<>""),AI129:AM129))) | IF(OR(F129="",AO129=""),"",IF(COUNT(AI129:AN129)=0,"",AO129-LOOKUP(2,1/(AI129:AN129<>""),AI129:AN129))) | IF(OR(F129="",AP129=""),"",IF(COUNT(AI129:AO129)=0,"",AP129-LOOKUP(2,1/(AI129:AO129<>""),AI129:AO129))) | IF(OR(F129="",AQ129=""),"",IF(COUNT(AI129:AP129)=0,"",AQ129-LOOKUP(2,1/(AI129:AP129<>""),AI129:AP129))) | IF(OR(F129="",AR129=""),"",IF(COUNT(AI129:AQ129)=0,"",AR129-LOOKUP(2,1/(AI129:AQ129<>""),AI129:AQ129))) | IF(OR(F129="",AS129=""),"",IF(COUNT(AI129:AR129)=0,"",AS129-LOOKUP(2,1/(AI129:AR129<>""),AI129:AR129))) | IF(OR(F129="",AT129=""),"",IF(COUNT(AI129:AS129)=0,"",AT129-LOOKUP(2,1/(AI129:AS129<>""),AI129:AS129))) | IF(OR(F129="",AU129=""),"",IF(COUNT(AI129:AT129)=0,"",AU129-LOOKUP(2,1/(AI129:AT129<>""),AI129:AT129))) | IF(OR(F129="",AV129=""),"",IF(COUNT(AI129:AU129)=0,"",AV129-LOOKUP(2,1/(AI129:AU129<>""),AI129:AU129))) | IF(J129="","All_Provinces",IFERROR(VLOOKUP(J129,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K129="","All_Districts",IFERROR(VLOOKUP(K129,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F130="","",ROW()-3) | AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | 9 of 9 | AF2-DIS-N-088 | Tilajat Drip Irrigation Scheme | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Rustaq | Tilajat Baloch | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems | Fida Mohammad |  | 8500 | IF(AQ130="","",AQ130) | 2027-01-25 | 6.2 | 2027-08-03 | IF(W130<>"",W130,IF(OR(T130="",V130=""),"",EDATE(T130,V130))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. ¦ Farmer: Fida Mohammad | IF(F130="","",IF(COUNT(AI130:AV130)=0,IF(AA130="","Not started",AA130),SUBSTITUTE(LOOKUP(2,1/(AI130:AV130<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F130="",COUNT(AI130:AV130)=0),"",TODAY()-LOOKUP(2,1/(AI130:AV130<>""),AI130:AV130)) | IF(OR(F130="",COUNT(AI130:AV130)<2),"",LOOKUP(2,1/(AI130:AV130<>""),AI130:AV130)-MIN(AI130:AV130)) | IF(OR(AD130="",AC130="Not started",AC130=""),"",IFERROR(AD130-IF(VLOOKUP(AC130,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC130,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F130="","",IF(OR(AA130="Cancelled",AC130="Cancelled"),"Cancelled",IF(OR(AC130="Completed / Handover",Y130<>"",Z130>=100),"Completed — on track",IF(O130="Not awarded",IF(U130="",IF(X130="","No planned date",IF(TODAY()>X130,"Behind — past planned date",IF(X130-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U130,"Behind — award date passed",IF(U130-TODAY()<=30,"At risk — close to off track","On track"))),IF(X130="","No planned date",IF(AND(TODAY()>X130,OR(Z130="",Z130<100)),"Behind — past end date",IF(AND(T130<>"",X130<>"",Z130<>"",(Z130<100),((TODAY()-T130)/MAX(X130-T130,1)*100)-Z130>15),"Behind — progress lag",IF(AND(X130-TODAY()<=30,X130-TODAY()>=0,OR(Z130="",Z130<90)),"At risk — close to off track","On track")))))))) | IF(OR(F130="",AC130="Completed / Handover",AC130="Cancelled"),"",IF(O130="Not awarded",IF(U130<>"",U130-TODAY(),IF(X130="","",X130-TODAY())),IF(X130="","",X130-TODAY()))) | [14 empty] | IF(OR(F130="",AJ130=""),"",IF(COUNT(AI130:AI130)=0,"",AJ130-LOOKUP(2,1/(AI130:AI130<>""),AI130:AI130))) | IF(OR(F130="",AK130=""),"",IF(COUNT(AI130:AJ130)=0,"",AK130-LOOKUP(2,1/(AI130:AJ130<>""),AI130:AJ130))) | IF(OR(F130="",AL130=""),"",IF(COUNT(AI130:AK130)=0,"",AL130-LOOKUP(2,1/(AI130:AK130<>""),AI130:AK130))) | IF(OR(F130="",AM130=""),"",IF(COUNT(AI130:AL130)=0,"",AM130-LOOKUP(2,1/(AI130:AL130<>""),AI130:AL130))) | IF(OR(F130="",AN130=""),"",IF(COUNT(AI130:AM130)=0,"",AN130-LOOKUP(2,1/(AI130:AM130<>""),AI130:AM130))) | IF(OR(F130="",AO130=""),"",IF(COUNT(AI130:AN130)=0,"",AO130-LOOKUP(2,1/(AI130:AN130<>""),AI130:AN130))) | IF(OR(F130="",AP130=""),"",IF(COUNT(AI130:AO130)=0,"",AP130-LOOKUP(2,1/(AI130:AO130<>""),AI130:AO130))) | IF(OR(F130="",AQ130=""),"",IF(COUNT(AI130:AP130)=0,"",AQ130-LOOKUP(2,1/(AI130:AP130<>""),AI130:AP130))) | IF(OR(F130="",AR130=""),"",IF(COUNT(AI130:AQ130)=0,"",AR130-LOOKUP(2,1/(AI130:AQ130<>""),AI130:AQ130))) | IF(OR(F130="",AS130=""),"",IF(COUNT(AI130:AR130)=0,"",AS130-LOOKUP(2,1/(AI130:AR130<>""),AI130:AR130))) | IF(OR(F130="",AT130=""),"",IF(COUNT(AI130:AS130)=0,"",AT130-LOOKUP(2,1/(AI130:AS130<>""),AI130:AS130))) | IF(OR(F130="",AU130=""),"",IF(COUNT(AI130:AT130)=0,"",AU130-LOOKUP(2,1/(AI130:AT130<>""),AI130:AT130))) | IF(OR(F130="",AV130=""),"",IF(COUNT(AI130:AU130)=0,"",AV130-LOOKUP(2,1/(AI130:AU130<>""),AI130:AU130))) | IF(J130="","All_Provinces",IFERROR(VLOOKUP(J130,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K130="","All_Districts",IFERROR(VLOOKUP(K130,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F131="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 1 of 12 | AF2-DIS-N-089 | Aybak drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Aybak | Joy Zindan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ131="","",AQ131) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W131<>"",W131,IF(OR(T131="",V131=""),"",EDATE(T131,V131))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F131="","",IF(COUNT(AI131:AV131)=0,IF(AA131="","Not started",AA131),SUBSTITUTE(LOOKUP(2,1/(AI131:AV131<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F131="",COUNT(AI131:AV131)=0),"",TODAY()-LOOKUP(2,1/(AI131:AV131<>""),AI131:AV131)) | IF(OR(F131="",COUNT(AI131:AV131)<2),"",LOOKUP(2,1/(AI131:AV131<>""),AI131:AV131)-MIN(AI131:AV131)) | IF(OR(AD131="",AC131="Not started",AC131=""),"",IFERROR(AD131-IF(VLOOKUP(AC131,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC131,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F131="","",IF(OR(AA131="Cancelled",AC131="Cancelled"),"Cancelled",IF(OR(AC131="Completed / Handover",Y131<>"",Z131>=100),"Completed — on track",IF(O131="Not awarded",IF(U131="",IF(X131="","No planned date",IF(TODAY()>X131,"Behind — past planned date",IF(X131-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U131,"Behind — award date passed",IF(U131-TODAY()<=30,"At risk — close to off track","On track"))),IF(X131="","No planned date",IF(AND(TODAY()>X131,OR(Z131="",Z131<100)),"Behind — past end date",IF(AND(T131<>"",X131<>"",Z131<>"",(Z131<100),((TODAY()-T131)/MAX(X131-T131,1)*100)-Z131>15),"Behind — progress lag",IF(AND(X131-TODAY()<=30,X131-TODAY()>=0,OR(Z131="",Z131<90)),"At risk — close to off track","On track")))))))) | IF(OR(F131="",AC131="Completed / Handover",AC131="Cancelled"),"",IF(O131="Not awarded",IF(U131<>"",U131-TODAY(),IF(X131="","",X131-TODAY())),IF(X131="","",X131-TODAY()))) | [14 empty] | IF(OR(F131="",AJ131=""),"",IF(COUNT(AI131:AI131)=0,"",AJ131-LOOKUP(2,1/(AI131:AI131<>""),AI131:AI131))) | IF(OR(F131="",AK131=""),"",IF(COUNT(AI131:AJ131)=0,"",AK131-LOOKUP(2,1/(AI131:AJ131<>""),AI131:AJ131))) | IF(OR(F131="",AL131=""),"",IF(COUNT(AI131:AK131)=0,"",AL131-LOOKUP(2,1/(AI131:AK131<>""),AI131:AK131))) | IF(OR(F131="",AM131=""),"",IF(COUNT(AI131:AL131)=0,"",AM131-LOOKUP(2,1/(AI131:AL131<>""),AI131:AL131))) | IF(OR(F131="",AN131=""),"",IF(COUNT(AI131:AM131)=0,"",AN131-LOOKUP(2,1/(AI131:AM131<>""),AI131:AM131))) | IF(OR(F131="",AO131=""),"",IF(COUNT(AI131:AN131)=0,"",AO131-LOOKUP(2,1/(AI131:AN131<>""),AI131:AN131))) | IF(OR(F131="",AP131=""),"",IF(COUNT(AI131:AO131)=0,"",AP131-LOOKUP(2,1/(AI131:AO131<>""),AI131:AO131))) | IF(OR(F131="",AQ131=""),"",IF(COUNT(AI131:AP131)=0,"",AQ131-LOOKUP(2,1/(AI131:AP131<>""),AI131:AP131))) | IF(OR(F131="",AR131=""),"",IF(COUNT(AI131:AQ131)=0,"",AR131-LOOKUP(2,1/(AI131:AQ131<>""),AI131:AQ131))) | IF(OR(F131="",AS131=""),"",IF(COUNT(AI131:AR131)=0,"",AS131-LOOKUP(2,1/(AI131:AR131<>""),AI131:AR131))) | IF(OR(F131="",AT131=""),"",IF(COUNT(AI131:AS131)=0,"",AT131-LOOKUP(2,1/(AI131:AS131<>""),AI131:AS131))) | IF(OR(F131="",AU131=""),"",IF(COUNT(AI131:AT131)=0,"",AU131-LOOKUP(2,1/(AI131:AT131<>""),AI131:AT131))) | IF(OR(F131="",AV131=""),"",IF(COUNT(AI131:AU131)=0,"",AV131-LOOKUP(2,1/(AI131:AU131<>""),AI131:AU131))) | IF(J131="","All_Provinces",IFERROR(VLOOKUP(J131,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K131="","All_Districts",IFERROR(VLOOKUP(K131,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F132="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 2 of 12 | AF2-DIS-N-090 | Balkh Agriculture and Livestock drip irrigation 3 | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Mazar-e-Sharif | Center | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ132="","",AQ132) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W132<>"",W132,IF(OR(T132="",V132=""),"",EDATE(T132,V132))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F132="","",IF(COUNT(AI132:AV132)=0,IF(AA132="","Not started",AA132),SUBSTITUTE(LOOKUP(2,1/(AI132:AV132<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F132="",COUNT(AI132:AV132)=0),"",TODAY()-LOOKUP(2,1/(AI132:AV132<>""),AI132:AV132)) | IF(OR(F132="",COUNT(AI132:AV132)<2),"",LOOKUP(2,1/(AI132:AV132<>""),AI132:AV132)-MIN(AI132:AV132)) | IF(OR(AD132="",AC132="Not started",AC132=""),"",IFERROR(AD132-IF(VLOOKUP(AC132,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC132,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F132="","",IF(OR(AA132="Cancelled",AC132="Cancelled"),"Cancelled",IF(OR(AC132="Completed / Handover",Y132<>"",Z132>=100),"Completed — on track",IF(O132="Not awarded",IF(U132="",IF(X132="","No planned date",IF(TODAY()>X132,"Behind — past planned date",IF(X132-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U132,"Behind — award date passed",IF(U132-TODAY()<=30,"At risk — close to off track","On track"))),IF(X132="","No planned date",IF(AND(TODAY()>X132,OR(Z132="",Z132<100)),"Behind — past end date",IF(AND(T132<>"",X132<>"",Z132<>"",(Z132<100),((TODAY()-T132)/MAX(X132-T132,1)*100)-Z132>15),"Behind — progress lag",IF(AND(X132-TODAY()<=30,X132-TODAY()>=0,OR(Z132="",Z132<90)),"At risk — close to off track","On track")))))))) | IF(OR(F132="",AC132="Completed / Handover",AC132="Cancelled"),"",IF(O132="Not awarded",IF(U132<>"",U132-TODAY(),IF(X132="","",X132-TODAY())),IF(X132="","",X132-TODAY()))) | [14 empty] | IF(OR(F132="",AJ132=""),"",IF(COUNT(AI132:AI132)=0,"",AJ132-LOOKUP(2,1/(AI132:AI132<>""),AI132:AI132))) | IF(OR(F132="",AK132=""),"",IF(COUNT(AI132:AJ132)=0,"",AK132-LOOKUP(2,1/(AI132:AJ132<>""),AI132:AJ132))) | IF(OR(F132="",AL132=""),"",IF(COUNT(AI132:AK132)=0,"",AL132-LOOKUP(2,1/(AI132:AK132<>""),AI132:AK132))) | IF(OR(F132="",AM132=""),"",IF(COUNT(AI132:AL132)=0,"",AM132-LOOKUP(2,1/(AI132:AL132<>""),AI132:AL132))) | IF(OR(F132="",AN132=""),"",IF(COUNT(AI132:AM132)=0,"",AN132-LOOKUP(2,1/(AI132:AM132<>""),AI132:AM132))) | IF(OR(F132="",AO132=""),"",IF(COUNT(AI132:AN132)=0,"",AO132-LOOKUP(2,1/(AI132:AN132<>""),AI132:AN132))) | IF(OR(F132="",AP132=""),"",IF(COUNT(AI132:AO132)=0,"",AP132-LOOKUP(2,1/(AI132:AO132<>""),AI132:AO132))) | IF(OR(F132="",AQ132=""),"",IF(COUNT(AI132:AP132)=0,"",AQ132-LOOKUP(2,1/(AI132:AP132<>""),AI132:AP132))) | IF(OR(F132="",AR132=""),"",IF(COUNT(AI132:AQ132)=0,"",AR132-LOOKUP(2,1/(AI132:AQ132<>""),AI132:AQ132))) | IF(OR(F132="",AS132=""),"",IF(COUNT(AI132:AR132)=0,"",AS132-LOOKUP(2,1/(AI132:AR132<>""),AI132:AR132))) | IF(OR(F132="",AT132=""),"",IF(COUNT(AI132:AS132)=0,"",AT132-LOOKUP(2,1/(AI132:AS132<>""),AI132:AS132))) | IF(OR(F132="",AU132=""),"",IF(COUNT(AI132:AT132)=0,"",AU132-LOOKUP(2,1/(AI132:AT132<>""),AI132:AT132))) | IF(OR(F132="",AV132=""),"",IF(COUNT(AI132:AU132)=0,"",AV132-LOOKUP(2,1/(AI132:AU132<>""),AI132:AU132))) | IF(J132="","All_Provinces",IFERROR(VLOOKUP(J132,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K132="","All_Districts",IFERROR(VLOOKUP(K132,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F133="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 3 of 12 | AF2-DIS-N-091 | Balkh university drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Mazar-e-Sharif | Center | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ133="","",AQ133) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W133<>"",W133,IF(OR(T133="",V133=""),"",EDATE(T133,V133))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F133="","",IF(COUNT(AI133:AV133)=0,IF(AA133="","Not started",AA133),SUBSTITUTE(LOOKUP(2,1/(AI133:AV133<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F133="",COUNT(AI133:AV133)=0),"",TODAY()-LOOKUP(2,1/(AI133:AV133<>""),AI133:AV133)) | IF(OR(F133="",COUNT(AI133:AV133)<2),"",LOOKUP(2,1/(AI133:AV133<>""),AI133:AV133)-MIN(AI133:AV133)) | IF(OR(AD133="",AC133="Not started",AC133=""),"",IFERROR(AD133-IF(VLOOKUP(AC133,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC133,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F133="","",IF(OR(AA133="Cancelled",AC133="Cancelled"),"Cancelled",IF(OR(AC133="Completed / Handover",Y133<>"",Z133>=100),"Completed — on track",IF(O133="Not awarded",IF(U133="",IF(X133="","No planned date",IF(TODAY()>X133,"Behind — past planned date",IF(X133-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U133,"Behind — award date passed",IF(U133-TODAY()<=30,"At risk — close to off track","On track"))),IF(X133="","No planned date",IF(AND(TODAY()>X133,OR(Z133="",Z133<100)),"Behind — past end date",IF(AND(T133<>"",X133<>"",Z133<>"",(Z133<100),((TODAY()-T133)/MAX(X133-T133,1)*100)-Z133>15),"Behind — progress lag",IF(AND(X133-TODAY()<=30,X133-TODAY()>=0,OR(Z133="",Z133<90)),"At risk — close to off track","On track")))))))) | IF(OR(F133="",AC133="Completed / Handover",AC133="Cancelled"),"",IF(O133="Not awarded",IF(U133<>"",U133-TODAY(),IF(X133="","",X133-TODAY())),IF(X133="","",X133-TODAY()))) | [14 empty] | IF(OR(F133="",AJ133=""),"",IF(COUNT(AI133:AI133)=0,"",AJ133-LOOKUP(2,1/(AI133:AI133<>""),AI133:AI133))) | IF(OR(F133="",AK133=""),"",IF(COUNT(AI133:AJ133)=0,"",AK133-LOOKUP(2,1/(AI133:AJ133<>""),AI133:AJ133))) | IF(OR(F133="",AL133=""),"",IF(COUNT(AI133:AK133)=0,"",AL133-LOOKUP(2,1/(AI133:AK133<>""),AI133:AK133))) | IF(OR(F133="",AM133=""),"",IF(COUNT(AI133:AL133)=0,"",AM133-LOOKUP(2,1/(AI133:AL133<>""),AI133:AL133))) | IF(OR(F133="",AN133=""),"",IF(COUNT(AI133:AM133)=0,"",AN133-LOOKUP(2,1/(AI133:AM133<>""),AI133:AM133))) | IF(OR(F133="",AO133=""),"",IF(COUNT(AI133:AN133)=0,"",AO133-LOOKUP(2,1/(AI133:AN133<>""),AI133:AN133))) | IF(OR(F133="",AP133=""),"",IF(COUNT(AI133:AO133)=0,"",AP133-LOOKUP(2,1/(AI133:AO133<>""),AI133:AO133))) | IF(OR(F133="",AQ133=""),"",IF(COUNT(AI133:AP133)=0,"",AQ133-LOOKUP(2,1/(AI133:AP133<>""),AI133:AP133))) | IF(OR(F133="",AR133=""),"",IF(COUNT(AI133:AQ133)=0,"",AR133-LOOKUP(2,1/(AI133:AQ133<>""),AI133:AQ133))) | IF(OR(F133="",AS133=""),"",IF(COUNT(AI133:AR133)=0,"",AS133-LOOKUP(2,1/(AI133:AR133<>""),AI133:AR133))) | IF(OR(F133="",AT133=""),"",IF(COUNT(AI133:AS133)=0,"",AT133-LOOKUP(2,1/(AI133:AS133<>""),AI133:AS133))) | IF(OR(F133="",AU133=""),"",IF(COUNT(AI133:AT133)=0,"",AU133-LOOKUP(2,1/(AI133:AT133<>""),AI133:AT133))) | IF(OR(F133="",AV133=""),"",IF(COUNT(AI133:AU133)=0,"",AV133-LOOKUP(2,1/(AI133:AU133<>""),AI133:AU133))) | IF(J133="","All_Provinces",IFERROR(VLOOKUP(J133,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K133="","All_Districts",IFERROR(VLOOKUP(K133,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F134="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 4 of 12 | AF2-DIS-N-092 | Charkent drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Charkent | Modafean Payen | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ134="","",AQ134) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W134<>"",W134,IF(OR(T134="",V134=""),"",EDATE(T134,V134))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F134="","",IF(COUNT(AI134:AV134)=0,IF(AA134="","Not started",AA134),SUBSTITUTE(LOOKUP(2,1/(AI134:AV134<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F134="",COUNT(AI134:AV134)=0),"",TODAY()-LOOKUP(2,1/(AI134:AV134<>""),AI134:AV134)) | IF(OR(F134="",COUNT(AI134:AV134)<2),"",LOOKUP(2,1/(AI134:AV134<>""),AI134:AV134)-MIN(AI134:AV134)) | IF(OR(AD134="",AC134="Not started",AC134=""),"",IFERROR(AD134-IF(VLOOKUP(AC134,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC134,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F134="","",IF(OR(AA134="Cancelled",AC134="Cancelled"),"Cancelled",IF(OR(AC134="Completed / Handover",Y134<>"",Z134>=100),"Completed — on track",IF(O134="Not awarded",IF(U134="",IF(X134="","No planned date",IF(TODAY()>X134,"Behind — past planned date",IF(X134-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U134,"Behind — award date passed",IF(U134-TODAY()<=30,"At risk — close to off track","On track"))),IF(X134="","No planned date",IF(AND(TODAY()>X134,OR(Z134="",Z134<100)),"Behind — past end date",IF(AND(T134<>"",X134<>"",Z134<>"",(Z134<100),((TODAY()-T134)/MAX(X134-T134,1)*100)-Z134>15),"Behind — progress lag",IF(AND(X134-TODAY()<=30,X134-TODAY()>=0,OR(Z134="",Z134<90)),"At risk — close to off track","On track")))))))) | IF(OR(F134="",AC134="Completed / Handover",AC134="Cancelled"),"",IF(O134="Not awarded",IF(U134<>"",U134-TODAY(),IF(X134="","",X134-TODAY())),IF(X134="","",X134-TODAY()))) | [14 empty] | IF(OR(F134="",AJ134=""),"",IF(COUNT(AI134:AI134)=0,"",AJ134-LOOKUP(2,1/(AI134:AI134<>""),AI134:AI134))) | IF(OR(F134="",AK134=""),"",IF(COUNT(AI134:AJ134)=0,"",AK134-LOOKUP(2,1/(AI134:AJ134<>""),AI134:AJ134))) | IF(OR(F134="",AL134=""),"",IF(COUNT(AI134:AK134)=0,"",AL134-LOOKUP(2,1/(AI134:AK134<>""),AI134:AK134))) | IF(OR(F134="",AM134=""),"",IF(COUNT(AI134:AL134)=0,"",AM134-LOOKUP(2,1/(AI134:AL134<>""),AI134:AL134))) | IF(OR(F134="",AN134=""),"",IF(COUNT(AI134:AM134)=0,"",AN134-LOOKUP(2,1/(AI134:AM134<>""),AI134:AM134))) | IF(OR(F134="",AO134=""),"",IF(COUNT(AI134:AN134)=0,"",AO134-LOOKUP(2,1/(AI134:AN134<>""),AI134:AN134))) | IF(OR(F134="",AP134=""),"",IF(COUNT(AI134:AO134)=0,"",AP134-LOOKUP(2,1/(AI134:AO134<>""),AI134:AO134))) | IF(OR(F134="",AQ134=""),"",IF(COUNT(AI134:AP134)=0,"",AQ134-LOOKUP(2,1/(AI134:AP134<>""),AI134:AP134))) | IF(OR(F134="",AR134=""),"",IF(COUNT(AI134:AQ134)=0,"",AR134-LOOKUP(2,1/(AI134:AQ134<>""),AI134:AQ134))) | IF(OR(F134="",AS134=""),"",IF(COUNT(AI134:AR134)=0,"",AS134-LOOKUP(2,1/(AI134:AR134<>""),AI134:AR134))) | IF(OR(F134="",AT134=""),"",IF(COUNT(AI134:AS134)=0,"",AT134-LOOKUP(2,1/(AI134:AS134<>""),AI134:AS134))) | IF(OR(F134="",AU134=""),"",IF(COUNT(AI134:AT134)=0,"",AU134-LOOKUP(2,1/(AI134:AT134<>""),AI134:AT134))) | IF(OR(F134="",AV134=""),"",IF(COUNT(AI134:AU134)=0,"",AV134-LOOKUP(2,1/(AI134:AU134<>""),AI134:AU134))) | IF(J134="","All_Provinces",IFERROR(VLOOKUP(J134,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K134="","All_Districts",IFERROR(VLOOKUP(K134,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F135="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 5 of 12 | AF2-DIS-N-093 | Dehdadi drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Dehdadi | Sher Abad Olya | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ135="","",AQ135) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W135<>"",W135,IF(OR(T135="",V135=""),"",EDATE(T135,V135))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F135="","",IF(COUNT(AI135:AV135)=0,IF(AA135="","Not started",AA135),SUBSTITUTE(LOOKUP(2,1/(AI135:AV135<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F135="",COUNT(AI135:AV135)=0),"",TODAY()-LOOKUP(2,1/(AI135:AV135<>""),AI135:AV135)) | IF(OR(F135="",COUNT(AI135:AV135)<2),"",LOOKUP(2,1/(AI135:AV135<>""),AI135:AV135)-MIN(AI135:AV135)) | IF(OR(AD135="",AC135="Not started",AC135=""),"",IFERROR(AD135-IF(VLOOKUP(AC135,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC135,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F135="","",IF(OR(AA135="Cancelled",AC135="Cancelled"),"Cancelled",IF(OR(AC135="Completed / Handover",Y135<>"",Z135>=100),"Completed — on track",IF(O135="Not awarded",IF(U135="",IF(X135="","No planned date",IF(TODAY()>X135,"Behind — past planned date",IF(X135-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U135,"Behind — award date passed",IF(U135-TODAY()<=30,"At risk — close to off track","On track"))),IF(X135="","No planned date",IF(AND(TODAY()>X135,OR(Z135="",Z135<100)),"Behind — past end date",IF(AND(T135<>"",X135<>"",Z135<>"",(Z135<100),((TODAY()-T135)/MAX(X135-T135,1)*100)-Z135>15),"Behind — progress lag",IF(AND(X135-TODAY()<=30,X135-TODAY()>=0,OR(Z135="",Z135<90)),"At risk — close to off track","On track")))))))) | IF(OR(F135="",AC135="Completed / Handover",AC135="Cancelled"),"",IF(O135="Not awarded",IF(U135<>"",U135-TODAY(),IF(X135="","",X135-TODAY())),IF(X135="","",X135-TODAY()))) | [14 empty] | IF(OR(F135="",AJ135=""),"",IF(COUNT(AI135:AI135)=0,"",AJ135-LOOKUP(2,1/(AI135:AI135<>""),AI135:AI135))) | IF(OR(F135="",AK135=""),"",IF(COUNT(AI135:AJ135)=0,"",AK135-LOOKUP(2,1/(AI135:AJ135<>""),AI135:AJ135))) | IF(OR(F135="",AL135=""),"",IF(COUNT(AI135:AK135)=0,"",AL135-LOOKUP(2,1/(AI135:AK135<>""),AI135:AK135))) | IF(OR(F135="",AM135=""),"",IF(COUNT(AI135:AL135)=0,"",AM135-LOOKUP(2,1/(AI135:AL135<>""),AI135:AL135))) | IF(OR(F135="",AN135=""),"",IF(COUNT(AI135:AM135)=0,"",AN135-LOOKUP(2,1/(AI135:AM135<>""),AI135:AM135))) | IF(OR(F135="",AO135=""),"",IF(COUNT(AI135:AN135)=0,"",AO135-LOOKUP(2,1/(AI135:AN135<>""),AI135:AN135))) | IF(OR(F135="",AP135=""),"",IF(COUNT(AI135:AO135)=0,"",AP135-LOOKUP(2,1/(AI135:AO135<>""),AI135:AO135))) | IF(OR(F135="",AQ135=""),"",IF(COUNT(AI135:AP135)=0,"",AQ135-LOOKUP(2,1/(AI135:AP135<>""),AI135:AP135))) | IF(OR(F135="",AR135=""),"",IF(COUNT(AI135:AQ135)=0,"",AR135-LOOKUP(2,1/(AI135:AQ135<>""),AI135:AQ135))) | IF(OR(F135="",AS135=""),"",IF(COUNT(AI135:AR135)=0,"",AS135-LOOKUP(2,1/(AI135:AR135<>""),AI135:AR135))) | IF(OR(F135="",AT135=""),"",IF(COUNT(AI135:AS135)=0,"",AT135-LOOKUP(2,1/(AI135:AS135<>""),AI135:AS135))) | IF(OR(F135="",AU135=""),"",IF(COUNT(AI135:AT135)=0,"",AU135-LOOKUP(2,1/(AI135:AT135<>""),AI135:AT135))) | IF(OR(F135="",AV135=""),"",IF(COUNT(AI135:AU135)=0,"",AV135-LOOKUP(2,1/(AI135:AU135<>""),AI135:AU135))) | IF(J135="","All_Provinces",IFERROR(VLOOKUP(J135,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K135="","All_Districts",IFERROR(VLOOKUP(K135,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F136="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 6 of 12 | AF2-DIS-N-094 | Had Bakhshy drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sari Pul | Sayed Abad | Had Bakhshy | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ136="","",AQ136) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W136<>"",W136,IF(OR(T136="",V136=""),"",EDATE(T136,V136))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F136="","",IF(COUNT(AI136:AV136)=0,IF(AA136="","Not started",AA136),SUBSTITUTE(LOOKUP(2,1/(AI136:AV136<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F136="",COUNT(AI136:AV136)=0),"",TODAY()-LOOKUP(2,1/(AI136:AV136<>""),AI136:AV136)) | IF(OR(F136="",COUNT(AI136:AV136)<2),"",LOOKUP(2,1/(AI136:AV136<>""),AI136:AV136)-MIN(AI136:AV136)) | IF(OR(AD136="",AC136="Not started",AC136=""),"",IFERROR(AD136-IF(VLOOKUP(AC136,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC136,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F136="","",IF(OR(AA136="Cancelled",AC136="Cancelled"),"Cancelled",IF(OR(AC136="Completed / Handover",Y136<>"",Z136>=100),"Completed — on track",IF(O136="Not awarded",IF(U136="",IF(X136="","No planned date",IF(TODAY()>X136,"Behind — past planned date",IF(X136-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U136,"Behind — award date passed",IF(U136-TODAY()<=30,"At risk — close to off track","On track"))),IF(X136="","No planned date",IF(AND(TODAY()>X136,OR(Z136="",Z136<100)),"Behind — past end date",IF(AND(T136<>"",X136<>"",Z136<>"",(Z136<100),((TODAY()-T136)/MAX(X136-T136,1)*100)-Z136>15),"Behind — progress lag",IF(AND(X136-TODAY()<=30,X136-TODAY()>=0,OR(Z136="",Z136<90)),"At risk — close to off track","On track")))))))) | IF(OR(F136="",AC136="Completed / Handover",AC136="Cancelled"),"",IF(O136="Not awarded",IF(U136<>"",U136-TODAY(),IF(X136="","",X136-TODAY())),IF(X136="","",X136-TODAY()))) | [14 empty] | IF(OR(F136="",AJ136=""),"",IF(COUNT(AI136:AI136)=0,"",AJ136-LOOKUP(2,1/(AI136:AI136<>""),AI136:AI136))) | IF(OR(F136="",AK136=""),"",IF(COUNT(AI136:AJ136)=0,"",AK136-LOOKUP(2,1/(AI136:AJ136<>""),AI136:AJ136))) | IF(OR(F136="",AL136=""),"",IF(COUNT(AI136:AK136)=0,"",AL136-LOOKUP(2,1/(AI136:AK136<>""),AI136:AK136))) | IF(OR(F136="",AM136=""),"",IF(COUNT(AI136:AL136)=0,"",AM136-LOOKUP(2,1/(AI136:AL136<>""),AI136:AL136))) | IF(OR(F136="",AN136=""),"",IF(COUNT(AI136:AM136)=0,"",AN136-LOOKUP(2,1/(AI136:AM136<>""),AI136:AM136))) | IF(OR(F136="",AO136=""),"",IF(COUNT(AI136:AN136)=0,"",AO136-LOOKUP(2,1/(AI136:AN136<>""),AI136:AN136))) | IF(OR(F136="",AP136=""),"",IF(COUNT(AI136:AO136)=0,"",AP136-LOOKUP(2,1/(AI136:AO136<>""),AI136:AO136))) | IF(OR(F136="",AQ136=""),"",IF(COUNT(AI136:AP136)=0,"",AQ136-LOOKUP(2,1/(AI136:AP136<>""),AI136:AP136))) | IF(OR(F136="",AR136=""),"",IF(COUNT(AI136:AQ136)=0,"",AR136-LOOKUP(2,1/(AI136:AQ136<>""),AI136:AQ136))) | IF(OR(F136="",AS136=""),"",IF(COUNT(AI136:AR136)=0,"",AS136-LOOKUP(2,1/(AI136:AR136<>""),AI136:AR136))) | IF(OR(F136="",AT136=""),"",IF(COUNT(AI136:AS136)=0,"",AT136-LOOKUP(2,1/(AI136:AS136<>""),AI136:AS136))) | IF(OR(F136="",AU136=""),"",IF(COUNT(AI136:AT136)=0,"",AU136-LOOKUP(2,1/(AI136:AT136<>""),AI136:AT136))) | IF(OR(F136="",AV136=""),"",IF(COUNT(AI136:AU136)=0,"",AV136-LOOKUP(2,1/(AI136:AU136<>""),AI136:AU136))) | IF(J136="","All_Provinces",IFERROR(VLOOKUP(J136,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K136="","All_Districts",IFERROR(VLOOKUP(K136,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F137="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 7 of 12 | AF2-DIS-N-095 | Hassan Tabin drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Jawzjan | Sheberghan | Hassan Tabin | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ137="","",AQ137) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W137<>"",W137,IF(OR(T137="",V137=""),"",EDATE(T137,V137))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F137="","",IF(COUNT(AI137:AV137)=0,IF(AA137="","Not started",AA137),SUBSTITUTE(LOOKUP(2,1/(AI137:AV137<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F137="",COUNT(AI137:AV137)=0),"",TODAY()-LOOKUP(2,1/(AI137:AV137<>""),AI137:AV137)) | IF(OR(F137="",COUNT(AI137:AV137)<2),"",LOOKUP(2,1/(AI137:AV137<>""),AI137:AV137)-MIN(AI137:AV137)) | IF(OR(AD137="",AC137="Not started",AC137=""),"",IFERROR(AD137-IF(VLOOKUP(AC137,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC137,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F137="","",IF(OR(AA137="Cancelled",AC137="Cancelled"),"Cancelled",IF(OR(AC137="Completed / Handover",Y137<>"",Z137>=100),"Completed — on track",IF(O137="Not awarded",IF(U137="",IF(X137="","No planned date",IF(TODAY()>X137,"Behind — past planned date",IF(X137-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U137,"Behind — award date passed",IF(U137-TODAY()<=30,"At risk — close to off track","On track"))),IF(X137="","No planned date",IF(AND(TODAY()>X137,OR(Z137="",Z137<100)),"Behind — past end date",IF(AND(T137<>"",X137<>"",Z137<>"",(Z137<100),((TODAY()-T137)/MAX(X137-T137,1)*100)-Z137>15),"Behind — progress lag",IF(AND(X137-TODAY()<=30,X137-TODAY()>=0,OR(Z137="",Z137<90)),"At risk — close to off track","On track")))))))) | IF(OR(F137="",AC137="Completed / Handover",AC137="Cancelled"),"",IF(O137="Not awarded",IF(U137<>"",U137-TODAY(),IF(X137="","",X137-TODAY())),IF(X137="","",X137-TODAY()))) | [14 empty] | IF(OR(F137="",AJ137=""),"",IF(COUNT(AI137:AI137)=0,"",AJ137-LOOKUP(2,1/(AI137:AI137<>""),AI137:AI137))) | IF(OR(F137="",AK137=""),"",IF(COUNT(AI137:AJ137)=0,"",AK137-LOOKUP(2,1/(AI137:AJ137<>""),AI137:AJ137))) | IF(OR(F137="",AL137=""),"",IF(COUNT(AI137:AK137)=0,"",AL137-LOOKUP(2,1/(AI137:AK137<>""),AI137:AK137))) | IF(OR(F137="",AM137=""),"",IF(COUNT(AI137:AL137)=0,"",AM137-LOOKUP(2,1/(AI137:AL137<>""),AI137:AL137))) | IF(OR(F137="",AN137=""),"",IF(COUNT(AI137:AM137)=0,"",AN137-LOOKUP(2,1/(AI137:AM137<>""),AI137:AM137))) | IF(OR(F137="",AO137=""),"",IF(COUNT(AI137:AN137)=0,"",AO137-LOOKUP(2,1/(AI137:AN137<>""),AI137:AN137))) | IF(OR(F137="",AP137=""),"",IF(COUNT(AI137:AO137)=0,"",AP137-LOOKUP(2,1/(AI137:AO137<>""),AI137:AO137))) | IF(OR(F137="",AQ137=""),"",IF(COUNT(AI137:AP137)=0,"",AQ137-LOOKUP(2,1/(AI137:AP137<>""),AI137:AP137))) | IF(OR(F137="",AR137=""),"",IF(COUNT(AI137:AQ137)=0,"",AR137-LOOKUP(2,1/(AI137:AQ137<>""),AI137:AQ137))) | IF(OR(F137="",AS137=""),"",IF(COUNT(AI137:AR137)=0,"",AS137-LOOKUP(2,1/(AI137:AR137<>""),AI137:AR137))) | IF(OR(F137="",AT137=""),"",IF(COUNT(AI137:AS137)=0,"",AT137-LOOKUP(2,1/(AI137:AS137<>""),AI137:AS137))) | IF(OR(F137="",AU137=""),"",IF(COUNT(AI137:AT137)=0,"",AU137-LOOKUP(2,1/(AI137:AT137<>""),AI137:AT137))) | IF(OR(F137="",AV137=""),"",IF(COUNT(AI137:AU137)=0,"",AV137-LOOKUP(2,1/(AI137:AU137<>""),AI137:AU137))) | IF(J137="","All_Provinces",IFERROR(VLOOKUP(J137,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K137="","All_Districts",IFERROR(VLOOKUP(K137,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F138="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 8 of 12 | AF2-DIS-N-096 | Hazrat-e-Sultan drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Hazrat-e-Sultan | Asiabad | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ138="","",AQ138) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W138<>"",W138,IF(OR(T138="",V138=""),"",EDATE(T138,V138))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F138="","",IF(COUNT(AI138:AV138)=0,IF(AA138="","Not started",AA138),SUBSTITUTE(LOOKUP(2,1/(AI138:AV138<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F138="",COUNT(AI138:AV138)=0),"",TODAY()-LOOKUP(2,1/(AI138:AV138<>""),AI138:AV138)) | IF(OR(F138="",COUNT(AI138:AV138)<2),"",LOOKUP(2,1/(AI138:AV138<>""),AI138:AV138)-MIN(AI138:AV138)) | IF(OR(AD138="",AC138="Not started",AC138=""),"",IFERROR(AD138-IF(VLOOKUP(AC138,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC138,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F138="","",IF(OR(AA138="Cancelled",AC138="Cancelled"),"Cancelled",IF(OR(AC138="Completed / Handover",Y138<>"",Z138>=100),"Completed — on track",IF(O138="Not awarded",IF(U138="",IF(X138="","No planned date",IF(TODAY()>X138,"Behind — past planned date",IF(X138-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U138,"Behind — award date passed",IF(U138-TODAY()<=30,"At risk — close to off track","On track"))),IF(X138="","No planned date",IF(AND(TODAY()>X138,OR(Z138="",Z138<100)),"Behind — past end date",IF(AND(T138<>"",X138<>"",Z138<>"",(Z138<100),((TODAY()-T138)/MAX(X138-T138,1)*100)-Z138>15),"Behind — progress lag",IF(AND(X138-TODAY()<=30,X138-TODAY()>=0,OR(Z138="",Z138<90)),"At risk — close to off track","On track")))))))) | IF(OR(F138="",AC138="Completed / Handover",AC138="Cancelled"),"",IF(O138="Not awarded",IF(U138<>"",U138-TODAY(),IF(X138="","",X138-TODAY())),IF(X138="","",X138-TODAY()))) | [14 empty] | IF(OR(F138="",AJ138=""),"",IF(COUNT(AI138:AI138)=0,"",AJ138-LOOKUP(2,1/(AI138:AI138<>""),AI138:AI138))) | IF(OR(F138="",AK138=""),"",IF(COUNT(AI138:AJ138)=0,"",AK138-LOOKUP(2,1/(AI138:AJ138<>""),AI138:AJ138))) | IF(OR(F138="",AL138=""),"",IF(COUNT(AI138:AK138)=0,"",AL138-LOOKUP(2,1/(AI138:AK138<>""),AI138:AK138))) | IF(OR(F138="",AM138=""),"",IF(COUNT(AI138:AL138)=0,"",AM138-LOOKUP(2,1/(AI138:AL138<>""),AI138:AL138))) | IF(OR(F138="",AN138=""),"",IF(COUNT(AI138:AM138)=0,"",AN138-LOOKUP(2,1/(AI138:AM138<>""),AI138:AM138))) | IF(OR(F138="",AO138=""),"",IF(COUNT(AI138:AN138)=0,"",AO138-LOOKUP(2,1/(AI138:AN138<>""),AI138:AN138))) | IF(OR(F138="",AP138=""),"",IF(COUNT(AI138:AO138)=0,"",AP138-LOOKUP(2,1/(AI138:AO138<>""),AI138:AO138))) | IF(OR(F138="",AQ138=""),"",IF(COUNT(AI138:AP138)=0,"",AQ138-LOOKUP(2,1/(AI138:AP138<>""),AI138:AP138))) | IF(OR(F138="",AR138=""),"",IF(COUNT(AI138:AQ138)=0,"",AR138-LOOKUP(2,1/(AI138:AQ138<>""),AI138:AQ138))) | IF(OR(F138="",AS138=""),"",IF(COUNT(AI138:AR138)=0,"",AS138-LOOKUP(2,1/(AI138:AR138<>""),AI138:AR138))) | IF(OR(F138="",AT138=""),"",IF(COUNT(AI138:AS138)=0,"",AT138-LOOKUP(2,1/(AI138:AS138<>""),AI138:AS138))) | IF(OR(F138="",AU138=""),"",IF(COUNT(AI138:AT138)=0,"",AU138-LOOKUP(2,1/(AI138:AT138<>""),AI138:AT138))) | IF(OR(F138="",AV138=""),"",IF(COUNT(AI138:AU138)=0,"",AV138-LOOKUP(2,1/(AI138:AU138<>""),AI138:AU138))) | IF(J138="","All_Provinces",IFERROR(VLOOKUP(J138,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K138="","All_Districts",IFERROR(VLOOKUP(K138,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F139="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 9 of 12 | AF2-DIS-N-097 | Imam Jaffar drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sari Pul | Sayed Abad | Imam Jaffar | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ139="","",AQ139) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W139<>"",W139,IF(OR(T139="",V139=""),"",EDATE(T139,V139))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F139="","",IF(COUNT(AI139:AV139)=0,IF(AA139="","Not started",AA139),SUBSTITUTE(LOOKUP(2,1/(AI139:AV139<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F139="",COUNT(AI139:AV139)=0),"",TODAY()-LOOKUP(2,1/(AI139:AV139<>""),AI139:AV139)) | IF(OR(F139="",COUNT(AI139:AV139)<2),"",LOOKUP(2,1/(AI139:AV139<>""),AI139:AV139)-MIN(AI139:AV139)) | IF(OR(AD139="",AC139="Not started",AC139=""),"",IFERROR(AD139-IF(VLOOKUP(AC139,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC139,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F139="","",IF(OR(AA139="Cancelled",AC139="Cancelled"),"Cancelled",IF(OR(AC139="Completed / Handover",Y139<>"",Z139>=100),"Completed — on track",IF(O139="Not awarded",IF(U139="",IF(X139="","No planned date",IF(TODAY()>X139,"Behind — past planned date",IF(X139-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U139,"Behind — award date passed",IF(U139-TODAY()<=30,"At risk — close to off track","On track"))),IF(X139="","No planned date",IF(AND(TODAY()>X139,OR(Z139="",Z139<100)),"Behind — past end date",IF(AND(T139<>"",X139<>"",Z139<>"",(Z139<100),((TODAY()-T139)/MAX(X139-T139,1)*100)-Z139>15),"Behind — progress lag",IF(AND(X139-TODAY()<=30,X139-TODAY()>=0,OR(Z139="",Z139<90)),"At risk — close to off track","On track")))))))) | IF(OR(F139="",AC139="Completed / Handover",AC139="Cancelled"),"",IF(O139="Not awarded",IF(U139<>"",U139-TODAY(),IF(X139="","",X139-TODAY())),IF(X139="","",X139-TODAY()))) | [14 empty] | IF(OR(F139="",AJ139=""),"",IF(COUNT(AI139:AI139)=0,"",AJ139-LOOKUP(2,1/(AI139:AI139<>""),AI139:AI139))) | IF(OR(F139="",AK139=""),"",IF(COUNT(AI139:AJ139)=0,"",AK139-LOOKUP(2,1/(AI139:AJ139<>""),AI139:AJ139))) | IF(OR(F139="",AL139=""),"",IF(COUNT(AI139:AK139)=0,"",AL139-LOOKUP(2,1/(AI139:AK139<>""),AI139:AK139))) | IF(OR(F139="",AM139=""),"",IF(COUNT(AI139:AL139)=0,"",AM139-LOOKUP(2,1/(AI139:AL139<>""),AI139:AL139))) | IF(OR(F139="",AN139=""),"",IF(COUNT(AI139:AM139)=0,"",AN139-LOOKUP(2,1/(AI139:AM139<>""),AI139:AM139))) | IF(OR(F139="",AO139=""),"",IF(COUNT(AI139:AN139)=0,"",AO139-LOOKUP(2,1/(AI139:AN139<>""),AI139:AN139))) | IF(OR(F139="",AP139=""),"",IF(COUNT(AI139:AO139)=0,"",AP139-LOOKUP(2,1/(AI139:AO139<>""),AI139:AO139))) | IF(OR(F139="",AQ139=""),"",IF(COUNT(AI139:AP139)=0,"",AQ139-LOOKUP(2,1/(AI139:AP139<>""),AI139:AP139))) | IF(OR(F139="",AR139=""),"",IF(COUNT(AI139:AQ139)=0,"",AR139-LOOKUP(2,1/(AI139:AQ139<>""),AI139:AQ139))) | IF(OR(F139="",AS139=""),"",IF(COUNT(AI139:AR139)=0,"",AS139-LOOKUP(2,1/(AI139:AR139<>""),AI139:AR139))) | IF(OR(F139="",AT139=""),"",IF(COUNT(AI139:AS139)=0,"",AT139-LOOKUP(2,1/(AI139:AS139<>""),AI139:AS139))) | IF(OR(F139="",AU139=""),"",IF(COUNT(AI139:AT139)=0,"",AU139-LOOKUP(2,1/(AI139:AT139<>""),AI139:AT139))) | IF(OR(F139="",AV139=""),"",IF(COUNT(AI139:AU139)=0,"",AV139-LOOKUP(2,1/(AI139:AU139<>""),AI139:AU139))) | IF(J139="","All_Provinces",IFERROR(VLOOKUP(J139,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K139="","All_Districts",IFERROR(VLOOKUP(K139,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F140="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 10 of 12 | AF2-DIS-N-098 | Maimana drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Faryab | Khwaja Sabz Posh | Tepa Qishlaq | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ140="","",AQ140) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W140<>"",W140,IF(OR(T140="",V140=""),"",EDATE(T140,V140))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F140="","",IF(COUNT(AI140:AV140)=0,IF(AA140="","Not started",AA140),SUBSTITUTE(LOOKUP(2,1/(AI140:AV140<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F140="",COUNT(AI140:AV140)=0),"",TODAY()-LOOKUP(2,1/(AI140:AV140<>""),AI140:AV140)) | IF(OR(F140="",COUNT(AI140:AV140)<2),"",LOOKUP(2,1/(AI140:AV140<>""),AI140:AV140)-MIN(AI140:AV140)) | IF(OR(AD140="",AC140="Not started",AC140=""),"",IFERROR(AD140-IF(VLOOKUP(AC140,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC140,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F140="","",IF(OR(AA140="Cancelled",AC140="Cancelled"),"Cancelled",IF(OR(AC140="Completed / Handover",Y140<>"",Z140>=100),"Completed — on track",IF(O140="Not awarded",IF(U140="",IF(X140="","No planned date",IF(TODAY()>X140,"Behind — past planned date",IF(X140-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U140,"Behind — award date passed",IF(U140-TODAY()<=30,"At risk — close to off track","On track"))),IF(X140="","No planned date",IF(AND(TODAY()>X140,OR(Z140="",Z140<100)),"Behind — past end date",IF(AND(T140<>"",X140<>"",Z140<>"",(Z140<100),((TODAY()-T140)/MAX(X140-T140,1)*100)-Z140>15),"Behind — progress lag",IF(AND(X140-TODAY()<=30,X140-TODAY()>=0,OR(Z140="",Z140<90)),"At risk — close to off track","On track")))))))) | IF(OR(F140="",AC140="Completed / Handover",AC140="Cancelled"),"",IF(O140="Not awarded",IF(U140<>"",U140-TODAY(),IF(X140="","",X140-TODAY())),IF(X140="","",X140-TODAY()))) | [14 empty] | IF(OR(F140="",AJ140=""),"",IF(COUNT(AI140:AI140)=0,"",AJ140-LOOKUP(2,1/(AI140:AI140<>""),AI140:AI140))) | IF(OR(F140="",AK140=""),"",IF(COUNT(AI140:AJ140)=0,"",AK140-LOOKUP(2,1/(AI140:AJ140<>""),AI140:AJ140))) | IF(OR(F140="",AL140=""),"",IF(COUNT(AI140:AK140)=0,"",AL140-LOOKUP(2,1/(AI140:AK140<>""),AI140:AK140))) | IF(OR(F140="",AM140=""),"",IF(COUNT(AI140:AL140)=0,"",AM140-LOOKUP(2,1/(AI140:AL140<>""),AI140:AL140))) | IF(OR(F140="",AN140=""),"",IF(COUNT(AI140:AM140)=0,"",AN140-LOOKUP(2,1/(AI140:AM140<>""),AI140:AM140))) | IF(OR(F140="",AO140=""),"",IF(COUNT(AI140:AN140)=0,"",AO140-LOOKUP(2,1/(AI140:AN140<>""),AI140:AN140))) | IF(OR(F140="",AP140=""),"",IF(COUNT(AI140:AO140)=0,"",AP140-LOOKUP(2,1/(AI140:AO140<>""),AI140:AO140))) | IF(OR(F140="",AQ140=""),"",IF(COUNT(AI140:AP140)=0,"",AQ140-LOOKUP(2,1/(AI140:AP140<>""),AI140:AP140))) | IF(OR(F140="",AR140=""),"",IF(COUNT(AI140:AQ140)=0,"",AR140-LOOKUP(2,1/(AI140:AQ140<>""),AI140:AQ140))) | IF(OR(F140="",AS140=""),"",IF(COUNT(AI140:AR140)=0,"",AS140-LOOKUP(2,1/(AI140:AR140<>""),AI140:AR140))) | IF(OR(F140="",AT140=""),"",IF(COUNT(AI140:AS140)=0,"",AT140-LOOKUP(2,1/(AI140:AS140<>""),AI140:AS140))) | IF(OR(F140="",AU140=""),"",IF(COUNT(AI140:AT140)=0,"",AU140-LOOKUP(2,1/(AI140:AT140<>""),AI140:AT140))) | IF(OR(F140="",AV140=""),"",IF(COUNT(AI140:AU140)=0,"",AV140-LOOKUP(2,1/(AI140:AU140<>""),AI140:AU140))) | IF(J140="","All_Provinces",IFERROR(VLOOKUP(J140,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K140="","All_Districts",IFERROR(VLOOKUP(K140,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F141="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 11 of 12 | AF2-DIS-N-099 | Nawabad Imam drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sari Pul | Center | Nawabad Imam Kalan | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 4250 | IF(AQ141="","",AQ141) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W141<>"",W141,IF(OR(T141="",V141=""),"",EDATE(T141,V141))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F141="","",IF(COUNT(AI141:AV141)=0,IF(AA141="","Not started",AA141),SUBSTITUTE(LOOKUP(2,1/(AI141:AV141<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F141="",COUNT(AI141:AV141)=0),"",TODAY()-LOOKUP(2,1/(AI141:AV141<>""),AI141:AV141)) | IF(OR(F141="",COUNT(AI141:AV141)<2),"",LOOKUP(2,1/(AI141:AV141<>""),AI141:AV141)-MIN(AI141:AV141)) | IF(OR(AD141="",AC141="Not started",AC141=""),"",IFERROR(AD141-IF(VLOOKUP(AC141,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC141,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F141="","",IF(OR(AA141="Cancelled",AC141="Cancelled"),"Cancelled",IF(OR(AC141="Completed / Handover",Y141<>"",Z141>=100),"Completed — on track",IF(O141="Not awarded",IF(U141="",IF(X141="","No planned date",IF(TODAY()>X141,"Behind — past planned date",IF(X141-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U141,"Behind — award date passed",IF(U141-TODAY()<=30,"At risk — close to off track","On track"))),IF(X141="","No planned date",IF(AND(TODAY()>X141,OR(Z141="",Z141<100)),"Behind — past end date",IF(AND(T141<>"",X141<>"",Z141<>"",(Z141<100),((TODAY()-T141)/MAX(X141-T141,1)*100)-Z141>15),"Behind — progress lag",IF(AND(X141-TODAY()<=30,X141-TODAY()>=0,OR(Z141="",Z141<90)),"At risk — close to off track","On track")))))))) | IF(OR(F141="",AC141="Completed / Handover",AC141="Cancelled"),"",IF(O141="Not awarded",IF(U141<>"",U141-TODAY(),IF(X141="","",X141-TODAY())),IF(X141="","",X141-TODAY()))) | [14 empty] | IF(OR(F141="",AJ141=""),"",IF(COUNT(AI141:AI141)=0,"",AJ141-LOOKUP(2,1/(AI141:AI141<>""),AI141:AI141))) | IF(OR(F141="",AK141=""),"",IF(COUNT(AI141:AJ141)=0,"",AK141-LOOKUP(2,1/(AI141:AJ141<>""),AI141:AJ141))) | IF(OR(F141="",AL141=""),"",IF(COUNT(AI141:AK141)=0,"",AL141-LOOKUP(2,1/(AI141:AK141<>""),AI141:AK141))) | IF(OR(F141="",AM141=""),"",IF(COUNT(AI141:AL141)=0,"",AM141-LOOKUP(2,1/(AI141:AL141<>""),AI141:AL141))) | IF(OR(F141="",AN141=""),"",IF(COUNT(AI141:AM141)=0,"",AN141-LOOKUP(2,1/(AI141:AM141<>""),AI141:AM141))) | IF(OR(F141="",AO141=""),"",IF(COUNT(AI141:AN141)=0,"",AO141-LOOKUP(2,1/(AI141:AN141<>""),AI141:AN141))) | IF(OR(F141="",AP141=""),"",IF(COUNT(AI141:AO141)=0,"",AP141-LOOKUP(2,1/(AI141:AO141<>""),AI141:AO141))) | IF(OR(F141="",AQ141=""),"",IF(COUNT(AI141:AP141)=0,"",AQ141-LOOKUP(2,1/(AI141:AP141<>""),AI141:AP141))) | IF(OR(F141="",AR141=""),"",IF(COUNT(AI141:AQ141)=0,"",AR141-LOOKUP(2,1/(AI141:AQ141<>""),AI141:AQ141))) | IF(OR(F141="",AS141=""),"",IF(COUNT(AI141:AR141)=0,"",AS141-LOOKUP(2,1/(AI141:AR141<>""),AI141:AR141))) | IF(OR(F141="",AT141=""),"",IF(COUNT(AI141:AS141)=0,"",AT141-LOOKUP(2,1/(AI141:AS141<>""),AI141:AS141))) | IF(OR(F141="",AU141=""),"",IF(COUNT(AI141:AT141)=0,"",AU141-LOOKUP(2,1/(AI141:AT141<>""),AI141:AT141))) | IF(OR(F141="",AV141=""),"",IF(COUNT(AI141:AU141)=0,"",AV141-LOOKUP(2,1/(AI141:AU141<>""),AI141:AU141))) | IF(J141="","All_Provinces",IFERROR(VLOOKUP(J141,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K141="","All_Districts",IFERROR(VLOOKUP(K141,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F142="","",ROW()-3) | AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | 12 of 12 | AF2-DIS-N-100 | Uch Tepa drip irrigation | Drip Irrigation | Drip Irrigation Plot | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Dehdadi | Uch Tepa | World Bank (WBK/AF-2) | Not awarded | 5. Drip Irrigation systems |  |  | 8500 | IF(AQ142="","",AQ142) | 2026-01-20 | 6.2 | 2026-07-29 | IF(W142<>"",W142,IF(OR(T142="",V142=""),"",EDATE(T142,V142))) |  |  | Under Review of WRI | Construction period five months starting from March 2027. | IF(F142="","",IF(COUNT(AI142:AV142)=0,IF(AA142="","Not started",AA142),SUBSTITUTE(LOOKUP(2,1/(AI142:AV142<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F142="",COUNT(AI142:AV142)=0),"",TODAY()-LOOKUP(2,1/(AI142:AV142<>""),AI142:AV142)) | IF(OR(F142="",COUNT(AI142:AV142)<2),"",LOOKUP(2,1/(AI142:AV142<>""),AI142:AV142)-MIN(AI142:AV142)) | IF(OR(AD142="",AC142="Not started",AC142=""),"",IFERROR(AD142-IF(VLOOKUP(AC142,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC142,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F142="","",IF(OR(AA142="Cancelled",AC142="Cancelled"),"Cancelled",IF(OR(AC142="Completed / Handover",Y142<>"",Z142>=100),"Completed — on track",IF(O142="Not awarded",IF(U142="",IF(X142="","No planned date",IF(TODAY()>X142,"Behind — past planned date",IF(X142-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U142,"Behind — award date passed",IF(U142-TODAY()<=30,"At risk — close to off track","On track"))),IF(X142="","No planned date",IF(AND(TODAY()>X142,OR(Z142="",Z142<100)),"Behind — past end date",IF(AND(T142<>"",X142<>"",Z142<>"",(Z142<100),((TODAY()-T142)/MAX(X142-T142,1)*100)-Z142>15),"Behind — progress lag",IF(AND(X142-TODAY()<=30,X142-TODAY()>=0,OR(Z142="",Z142<90)),"At risk — close to off track","On track")))))))) | IF(OR(F142="",AC142="Completed / Handover",AC142="Cancelled"),"",IF(O142="Not awarded",IF(U142<>"",U142-TODAY(),IF(X142="","",X142-TODAY())),IF(X142="","",X142-TODAY()))) | [14 empty] | IF(OR(F142="",AJ142=""),"",IF(COUNT(AI142:AI142)=0,"",AJ142-LOOKUP(2,1/(AI142:AI142<>""),AI142:AI142))) | IF(OR(F142="",AK142=""),"",IF(COUNT(AI142:AJ142)=0,"",AK142-LOOKUP(2,1/(AI142:AJ142<>""),AI142:AJ142))) | IF(OR(F142="",AL142=""),"",IF(COUNT(AI142:AK142)=0,"",AL142-LOOKUP(2,1/(AI142:AK142<>""),AI142:AK142))) | IF(OR(F142="",AM142=""),"",IF(COUNT(AI142:AL142)=0,"",AM142-LOOKUP(2,1/(AI142:AL142<>""),AI142:AL142))) | IF(OR(F142="",AN142=""),"",IF(COUNT(AI142:AM142)=0,"",AN142-LOOKUP(2,1/(AI142:AM142<>""),AI142:AM142))) | IF(OR(F142="",AO142=""),"",IF(COUNT(AI142:AN142)=0,"",AO142-LOOKUP(2,1/(AI142:AN142<>""),AI142:AN142))) | IF(OR(F142="",AP142=""),"",IF(COUNT(AI142:AO142)=0,"",AP142-LOOKUP(2,1/(AI142:AO142<>""),AI142:AO142))) | IF(OR(F142="",AQ142=""),"",IF(COUNT(AI142:AP142)=0,"",AQ142-LOOKUP(2,1/(AI142:AP142<>""),AI142:AP142))) | IF(OR(F142="",AR142=""),"",IF(COUNT(AI142:AQ142)=0,"",AR142-LOOKUP(2,1/(AI142:AQ142<>""),AI142:AQ142))) | IF(OR(F142="",AS142=""),"",IF(COUNT(AI142:AR142)=0,"",AS142-LOOKUP(2,1/(AI142:AR142<>""),AI142:AR142))) | IF(OR(F142="",AT142=""),"",IF(COUNT(AI142:AS142)=0,"",AT142-LOOKUP(2,1/(AI142:AS142<>""),AI142:AS142))) | IF(OR(F142="",AU142=""),"",IF(COUNT(AI142:AT142)=0,"",AU142-LOOKUP(2,1/(AI142:AT142<>""),AI142:AT142))) | IF(OR(F142="",AV142=""),"",IF(COUNT(AI142:AU142)=0,"",AV142-LOOKUP(2,1/(AI142:AU142<>""),AI142:AU142))) | IF(J142="","All_Provinces",IFERROR(VLOOKUP(J142,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K142="","All_Districts",IFERROR(VLOOKUP(K142,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F143="","",ROW()-3) | AF2-IS-01 | Package #1-AF2 IS: Rehabilitation of Joy Bazar irrigation scheme located in Obe district of Herat province. | 1 of 1 | AF2-IS-A-001 | Joy Bazar Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Obeh | Center | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Afghan Aakam Construction and Road Company C. JV with D-Amini Mashwani Construction Road Juroni and Construction Materials Production Company (AACRC&JV DAMCC) | 050/2025 | 222241.38 | IF(AQ143="","",AQ143) |  | 12 | 2026-09-15 | IF(W143<>"",W143,IF(OR(T143="",V143=""),"",EDATE(T143,V143))) |  | 100 | Completed / Handover | Completed in May 2026 ¦ Actual completion: May, 2026 | IF(F143="","",IF(COUNT(AI143:AV143)=0,IF(AA143="","Not started",AA143),SUBSTITUTE(LOOKUP(2,1/(AI143:AV143<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F143="",COUNT(AI143:AV143)=0),"",TODAY()-LOOKUP(2,1/(AI143:AV143<>""),AI143:AV143)) | IF(OR(F143="",COUNT(AI143:AV143)<2),"",LOOKUP(2,1/(AI143:AV143<>""),AI143:AV143)-MIN(AI143:AV143)) | IF(OR(AD143="",AC143="Not started",AC143=""),"",IFERROR(AD143-IF(VLOOKUP(AC143,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC143,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F143="","",IF(OR(AA143="Cancelled",AC143="Cancelled"),"Cancelled",IF(OR(AC143="Completed / Handover",Y143<>"",Z143>=100),"Completed — on track",IF(O143="Not awarded",IF(U143="",IF(X143="","No planned date",IF(TODAY()>X143,"Behind — past planned date",IF(X143-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U143,"Behind — award date passed",IF(U143-TODAY()<=30,"At risk — close to off track","On track"))),IF(X143="","No planned date",IF(AND(TODAY()>X143,OR(Z143="",Z143<100)),"Behind — past end date",IF(AND(T143<>"",X143<>"",Z143<>"",(Z143<100),((TODAY()-T143)/MAX(X143-T143,1)*100)-Z143>15),"Behind — progress lag",IF(AND(X143-TODAY()<=30,X143-TODAY()>=0,OR(Z143="",Z143<90)),"At risk — close to off track","On track")))))))) | IF(OR(F143="",AC143="Completed / Handover",AC143="Cancelled"),"",IF(O143="Not awarded",IF(U143<>"",U143-TODAY(),IF(X143="","",X143-TODAY())),IF(X143="","",X143-TODAY()))) | [8 empty] | 2025-09-16 | 2025-09-16 | 2026-09-15 |  |  |  | IF(OR(F143="",AJ143=""),"",IF(COUNT(AI143:AI143)=0,"",AJ143-LOOKUP(2,1/(AI143:AI143<>""),AI143:AI143))) | IF(OR(F143="",AK143=""),"",IF(COUNT(AI143:AJ143)=0,"",AK143-LOOKUP(2,1/(AI143:AJ143<>""),AI143:AJ143))) | IF(OR(F143="",AL143=""),"",IF(COUNT(AI143:AK143)=0,"",AL143-LOOKUP(2,1/(AI143:AK143<>""),AI143:AK143))) | IF(OR(F143="",AM143=""),"",IF(COUNT(AI143:AL143)=0,"",AM143-LOOKUP(2,1/(AI143:AL143<>""),AI143:AL143))) | IF(OR(F143="",AN143=""),"",IF(COUNT(AI143:AM143)=0,"",AN143-LOOKUP(2,1/(AI143:AM143<>""),AI143:AM143))) | IF(OR(F143="",AO143=""),"",IF(COUNT(AI143:AN143)=0,"",AO143-LOOKUP(2,1/(AI143:AN143<>""),AI143:AN143))) | IF(OR(F143="",AP143=""),"",IF(COUNT(AI143:AO143)=0,"",AP143-LOOKUP(2,1/(AI143:AO143<>""),AI143:AO143))) | IF(OR(F143="",AQ143=""),"",IF(COUNT(AI143:AP143)=0,"",AQ143-LOOKUP(2,1/(AI143:AP143<>""),AI143:AP143))) | IF(OR(F143="",AR143=""),"",IF(COUNT(AI143:AQ143)=0,"",AR143-LOOKUP(2,1/(AI143:AQ143<>""),AI143:AQ143))) | IF(OR(F143="",AS143=""),"",IF(COUNT(AI143:AR143)=0,"",AS143-LOOKUP(2,1/(AI143:AR143<>""),AI143:AR143))) | IF(OR(F143="",AT143=""),"",IF(COUNT(AI143:AS143)=0,"",AT143-LOOKUP(2,1/(AI143:AS143<>""),AI143:AS143))) | IF(OR(F143="",AU143=""),"",IF(COUNT(AI143:AT143)=0,"",AU143-LOOKUP(2,1/(AI143:AT143<>""),AI143:AT143))) | IF(OR(F143="",AV143=""),"",IF(COUNT(AI143:AU143)=0,"",AV143-LOOKUP(2,1/(AI143:AU143<>""),AI143:AU143))) | IF(J143="","All_Provinces",IFERROR(VLOOKUP(J143,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K143="","All_Districts",IFERROR(VLOOKUP(K143,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F144="","",ROW()-3) | AF2-IS-02 | Package # 2-AF2 IS: Rehabilitation of irrigation schemes of 1.Ali Mansoor Canal in Karukh district, 2.Joy Sork and 3.Sar Kari canals in Farsi districts of Herat province. | 1 of 3 | AF2-IS-A-002 | Ali Mansoor Canal Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Karukh | Dahan-e-Ghar Villages | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Arman Millad Construction Company (AMCC) | 046/2026 | 119404.61 | IF(AQ144="","",AQ144) |  | 12 | 2027-07-21 | IF(W144<>"",W144,IF(OR(T144="",V144=""),"",EDATE(T144,V144))) |  | 45 | Under Construction | on track and will be completed by July 2027 | IF(F144="","",IF(COUNT(AI144:AV144)=0,IF(AA144="","Not started",AA144),SUBSTITUTE(LOOKUP(2,1/(AI144:AV144<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F144="",COUNT(AI144:AV144)=0),"",TODAY()-LOOKUP(2,1/(AI144:AV144<>""),AI144:AV144)) | IF(OR(F144="",COUNT(AI144:AV144)<2),"",LOOKUP(2,1/(AI144:AV144<>""),AI144:AV144)-MIN(AI144:AV144)) | IF(OR(AD144="",AC144="Not started",AC144=""),"",IFERROR(AD144-IF(VLOOKUP(AC144,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC144,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F144="","",IF(OR(AA144="Cancelled",AC144="Cancelled"),"Cancelled",IF(OR(AC144="Completed / Handover",Y144<>"",Z144>=100),"Completed — on track",IF(O144="Not awarded",IF(U144="",IF(X144="","No planned date",IF(TODAY()>X144,"Behind — past planned date",IF(X144-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U144,"Behind — award date passed",IF(U144-TODAY()<=30,"At risk — close to off track","On track"))),IF(X144="","No planned date",IF(AND(TODAY()>X144,OR(Z144="",Z144<100)),"Behind — past end date",IF(AND(T144<>"",X144<>"",Z144<>"",(Z144<100),((TODAY()-T144)/MAX(X144-T144,1)*100)-Z144>15),"Behind — progress lag",IF(AND(X144-TODAY()<=30,X144-TODAY()>=0,OR(Z144="",Z144<90)),"At risk — close to off track","On track")))))))) | IF(OR(F144="",AC144="Completed / Handover",AC144="Cancelled"),"",IF(O144="Not awarded",IF(U144<>"",U144-TODAY(),IF(X144="","",X144-TODAY())),IF(X144="","",X144-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F144="",AJ144=""),"",IF(COUNT(AI144:AI144)=0,"",AJ144-LOOKUP(2,1/(AI144:AI144<>""),AI144:AI144))) | IF(OR(F144="",AK144=""),"",IF(COUNT(AI144:AJ144)=0,"",AK144-LOOKUP(2,1/(AI144:AJ144<>""),AI144:AJ144))) | IF(OR(F144="",AL144=""),"",IF(COUNT(AI144:AK144)=0,"",AL144-LOOKUP(2,1/(AI144:AK144<>""),AI144:AK144))) | IF(OR(F144="",AM144=""),"",IF(COUNT(AI144:AL144)=0,"",AM144-LOOKUP(2,1/(AI144:AL144<>""),AI144:AL144))) | IF(OR(F144="",AN144=""),"",IF(COUNT(AI144:AM144)=0,"",AN144-LOOKUP(2,1/(AI144:AM144<>""),AI144:AM144))) | IF(OR(F144="",AO144=""),"",IF(COUNT(AI144:AN144)=0,"",AO144-LOOKUP(2,1/(AI144:AN144<>""),AI144:AN144))) | IF(OR(F144="",AP144=""),"",IF(COUNT(AI144:AO144)=0,"",AP144-LOOKUP(2,1/(AI144:AO144<>""),AI144:AO144))) | IF(OR(F144="",AQ144=""),"",IF(COUNT(AI144:AP144)=0,"",AQ144-LOOKUP(2,1/(AI144:AP144<>""),AI144:AP144))) | IF(OR(F144="",AR144=""),"",IF(COUNT(AI144:AQ144)=0,"",AR144-LOOKUP(2,1/(AI144:AQ144<>""),AI144:AQ144))) | IF(OR(F144="",AS144=""),"",IF(COUNT(AI144:AR144)=0,"",AS144-LOOKUP(2,1/(AI144:AR144<>""),AI144:AR144))) | IF(OR(F144="",AT144=""),"",IF(COUNT(AI144:AS144)=0,"",AT144-LOOKUP(2,1/(AI144:AS144<>""),AI144:AS144))) | IF(OR(F144="",AU144=""),"",IF(COUNT(AI144:AT144)=0,"",AU144-LOOKUP(2,1/(AI144:AT144<>""),AI144:AT144))) | IF(OR(F144="",AV144=""),"",IF(COUNT(AI144:AU144)=0,"",AV144-LOOKUP(2,1/(AI144:AU144<>""),AI144:AU144))) | IF(J144="","All_Provinces",IFERROR(VLOOKUP(J144,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K144="","All_Districts",IFERROR(VLOOKUP(K144,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F145="","",ROW()-3) | AF2-IS-02 | Package # 2-AF2 IS: Rehabilitation of irrigation schemes of 1.Ali Mansoor Canal in Karukh district, 2.Joy Sork and 3.Sar Kari canals in Farsi districts of Herat province. | 2 of 3 | AF2-IS-A-003 | Joy Sork Irrigation Schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Farsi | Peyazak and Joy Markaz villages | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Arman Millad Construction Company (AMCC) | 046/2026 | 127771.65 | IF(AQ145="","",AQ145) |  | 12 | 2027-07-21 | IF(W145<>"",W145,IF(OR(T145="",V145=""),"",EDATE(T145,V145))) |  | 5 | Under Construction | on track and will be completed by July 2027 | IF(F145="","",IF(COUNT(AI145:AV145)=0,IF(AA145="","Not started",AA145),SUBSTITUTE(LOOKUP(2,1/(AI145:AV145<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F145="",COUNT(AI145:AV145)=0),"",TODAY()-LOOKUP(2,1/(AI145:AV145<>""),AI145:AV145)) | IF(OR(F145="",COUNT(AI145:AV145)<2),"",LOOKUP(2,1/(AI145:AV145<>""),AI145:AV145)-MIN(AI145:AV145)) | IF(OR(AD145="",AC145="Not started",AC145=""),"",IFERROR(AD145-IF(VLOOKUP(AC145,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC145,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F145="","",IF(OR(AA145="Cancelled",AC145="Cancelled"),"Cancelled",IF(OR(AC145="Completed / Handover",Y145<>"",Z145>=100),"Completed — on track",IF(O145="Not awarded",IF(U145="",IF(X145="","No planned date",IF(TODAY()>X145,"Behind — past planned date",IF(X145-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U145,"Behind — award date passed",IF(U145-TODAY()<=30,"At risk — close to off track","On track"))),IF(X145="","No planned date",IF(AND(TODAY()>X145,OR(Z145="",Z145<100)),"Behind — past end date",IF(AND(T145<>"",X145<>"",Z145<>"",(Z145<100),((TODAY()-T145)/MAX(X145-T145,1)*100)-Z145>15),"Behind — progress lag",IF(AND(X145-TODAY()<=30,X145-TODAY()>=0,OR(Z145="",Z145<90)),"At risk — close to off track","On track")))))))) | IF(OR(F145="",AC145="Completed / Handover",AC145="Cancelled"),"",IF(O145="Not awarded",IF(U145<>"",U145-TODAY(),IF(X145="","",X145-TODAY())),IF(X145="","",X145-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F145="",AJ145=""),"",IF(COUNT(AI145:AI145)=0,"",AJ145-LOOKUP(2,1/(AI145:AI145<>""),AI145:AI145))) | IF(OR(F145="",AK145=""),"",IF(COUNT(AI145:AJ145)=0,"",AK145-LOOKUP(2,1/(AI145:AJ145<>""),AI145:AJ145))) | IF(OR(F145="",AL145=""),"",IF(COUNT(AI145:AK145)=0,"",AL145-LOOKUP(2,1/(AI145:AK145<>""),AI145:AK145))) | IF(OR(F145="",AM145=""),"",IF(COUNT(AI145:AL145)=0,"",AM145-LOOKUP(2,1/(AI145:AL145<>""),AI145:AL145))) | IF(OR(F145="",AN145=""),"",IF(COUNT(AI145:AM145)=0,"",AN145-LOOKUP(2,1/(AI145:AM145<>""),AI145:AM145))) | IF(OR(F145="",AO145=""),"",IF(COUNT(AI145:AN145)=0,"",AO145-LOOKUP(2,1/(AI145:AN145<>""),AI145:AN145))) | IF(OR(F145="",AP145=""),"",IF(COUNT(AI145:AO145)=0,"",AP145-LOOKUP(2,1/(AI145:AO145<>""),AI145:AO145))) | IF(OR(F145="",AQ145=""),"",IF(COUNT(AI145:AP145)=0,"",AQ145-LOOKUP(2,1/(AI145:AP145<>""),AI145:AP145))) | IF(OR(F145="",AR145=""),"",IF(COUNT(AI145:AQ145)=0,"",AR145-LOOKUP(2,1/(AI145:AQ145<>""),AI145:AQ145))) | IF(OR(F145="",AS145=""),"",IF(COUNT(AI145:AR145)=0,"",AS145-LOOKUP(2,1/(AI145:AR145<>""),AI145:AR145))) | IF(OR(F145="",AT145=""),"",IF(COUNT(AI145:AS145)=0,"",AT145-LOOKUP(2,1/(AI145:AS145<>""),AI145:AS145))) | IF(OR(F145="",AU145=""),"",IF(COUNT(AI145:AT145)=0,"",AU145-LOOKUP(2,1/(AI145:AT145<>""),AI145:AT145))) | IF(OR(F145="",AV145=""),"",IF(COUNT(AI145:AU145)=0,"",AV145-LOOKUP(2,1/(AI145:AU145<>""),AI145:AU145))) | IF(J145="","All_Provinces",IFERROR(VLOOKUP(J145,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K145="","All_Districts",IFERROR(VLOOKUP(K145,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F146="","",ROW()-3) | AF2-IS-02 | Package # 2-AF2 IS: Rehabilitation of irrigation schemes of 1.Ali Mansoor Canal in Karukh district, 2.Joy Sork and 3.Sar Kari canals in Farsi districts of Herat province. | 3 of 3 | AF2-IS-A-004 | Sar Kari Irrigation Schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Farsi | Peyazak and Joy Markaz villages | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Arman Millad Construction Company (AMCC) | 046/2026 |  | IF(AQ146="","",AQ146) |  | 12 | 2027-07-21 | IF(W146<>"",W146,IF(OR(T146="",V146=""),"",EDATE(T146,V146))) |  | 49 | Under Construction | on track and will be completed by July 2027 | IF(F146="","",IF(COUNT(AI146:AV146)=0,IF(AA146="","Not started",AA146),SUBSTITUTE(LOOKUP(2,1/(AI146:AV146<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F146="",COUNT(AI146:AV146)=0),"",TODAY()-LOOKUP(2,1/(AI146:AV146<>""),AI146:AV146)) | IF(OR(F146="",COUNT(AI146:AV146)<2),"",LOOKUP(2,1/(AI146:AV146<>""),AI146:AV146)-MIN(AI146:AV146)) | IF(OR(AD146="",AC146="Not started",AC146=""),"",IFERROR(AD146-IF(VLOOKUP(AC146,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC146,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F146="","",IF(OR(AA146="Cancelled",AC146="Cancelled"),"Cancelled",IF(OR(AC146="Completed / Handover",Y146<>"",Z146>=100),"Completed — on track",IF(O146="Not awarded",IF(U146="",IF(X146="","No planned date",IF(TODAY()>X146,"Behind — past planned date",IF(X146-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U146,"Behind — award date passed",IF(U146-TODAY()<=30,"At risk — close to off track","On track"))),IF(X146="","No planned date",IF(AND(TODAY()>X146,OR(Z146="",Z146<100)),"Behind — past end date",IF(AND(T146<>"",X146<>"",Z146<>"",(Z146<100),((TODAY()-T146)/MAX(X146-T146,1)*100)-Z146>15),"Behind — progress lag",IF(AND(X146-TODAY()<=30,X146-TODAY()>=0,OR(Z146="",Z146<90)),"At risk — close to off track","On track")))))))) | IF(OR(F146="",AC146="Completed / Handover",AC146="Cancelled"),"",IF(O146="Not awarded",IF(U146<>"",U146-TODAY(),IF(X146="","",X146-TODAY())),IF(X146="","",X146-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F146="",AJ146=""),"",IF(COUNT(AI146:AI146)=0,"",AJ146-LOOKUP(2,1/(AI146:AI146<>""),AI146:AI146))) | IF(OR(F146="",AK146=""),"",IF(COUNT(AI146:AJ146)=0,"",AK146-LOOKUP(2,1/(AI146:AJ146<>""),AI146:AJ146))) | IF(OR(F146="",AL146=""),"",IF(COUNT(AI146:AK146)=0,"",AL146-LOOKUP(2,1/(AI146:AK146<>""),AI146:AK146))) | IF(OR(F146="",AM146=""),"",IF(COUNT(AI146:AL146)=0,"",AM146-LOOKUP(2,1/(AI146:AL146<>""),AI146:AL146))) | IF(OR(F146="",AN146=""),"",IF(COUNT(AI146:AM146)=0,"",AN146-LOOKUP(2,1/(AI146:AM146<>""),AI146:AM146))) | IF(OR(F146="",AO146=""),"",IF(COUNT(AI146:AN146)=0,"",AO146-LOOKUP(2,1/(AI146:AN146<>""),AI146:AN146))) | IF(OR(F146="",AP146=""),"",IF(COUNT(AI146:AO146)=0,"",AP146-LOOKUP(2,1/(AI146:AO146<>""),AI146:AO146))) | IF(OR(F146="",AQ146=""),"",IF(COUNT(AI146:AP146)=0,"",AQ146-LOOKUP(2,1/(AI146:AP146<>""),AI146:AP146))) | IF(OR(F146="",AR146=""),"",IF(COUNT(AI146:AQ146)=0,"",AR146-LOOKUP(2,1/(AI146:AQ146<>""),AI146:AQ146))) | IF(OR(F146="",AS146=""),"",IF(COUNT(AI146:AR146)=0,"",AS146-LOOKUP(2,1/(AI146:AR146<>""),AI146:AR146))) | IF(OR(F146="",AT146=""),"",IF(COUNT(AI146:AS146)=0,"",AT146-LOOKUP(2,1/(AI146:AS146<>""),AI146:AS146))) | IF(OR(F146="",AU146=""),"",IF(COUNT(AI146:AT146)=0,"",AU146-LOOKUP(2,1/(AI146:AT146<>""),AI146:AT146))) | IF(OR(F146="",AV146=""),"",IF(COUNT(AI146:AU146)=0,"",AV146-LOOKUP(2,1/(AI146:AU146<>""),AI146:AU146))) | IF(J146="","All_Provinces",IFERROR(VLOOKUP(J146,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K146="","All_Districts",IFERROR(VLOOKUP(K146,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F147="","",ROW()-3) | AF2-IS-03 | Package #3-AF2 IS: Rehabilitation of Yazdi irrigation scheme, located in Center Districts of Farah province. | 1 of 1 | AF2-IS-N-001 | Yazdeh Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Farah | Center | Yazdi | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 180000 | IF(AQ147="","",AQ147) | 2026-12-15 | 9 | 2027-09-14 | IF(W147<>"",W147,IF(OR(T147="",V147=""),"",EDATE(T147,V147))) |  |  | Under Review of WRI | Two months slack period Mar-Apr during the flood. Seven months construction period. Explore split into 2 lots if needed | IF(F147="","",IF(COUNT(AI147:AV147)=0,IF(AA147="","Not started",AA147),SUBSTITUTE(LOOKUP(2,1/(AI147:AV147<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F147="",COUNT(AI147:AV147)=0),"",TODAY()-LOOKUP(2,1/(AI147:AV147<>""),AI147:AV147)) | IF(OR(F147="",COUNT(AI147:AV147)<2),"",LOOKUP(2,1/(AI147:AV147<>""),AI147:AV147)-MIN(AI147:AV147)) | IF(OR(AD147="",AC147="Not started",AC147=""),"",IFERROR(AD147-IF(VLOOKUP(AC147,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC147,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F147="","",IF(OR(AA147="Cancelled",AC147="Cancelled"),"Cancelled",IF(OR(AC147="Completed / Handover",Y147<>"",Z147>=100),"Completed — on track",IF(O147="Not awarded",IF(U147="",IF(X147="","No planned date",IF(TODAY()>X147,"Behind — past planned date",IF(X147-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U147,"Behind — award date passed",IF(U147-TODAY()<=30,"At risk — close to off track","On track"))),IF(X147="","No planned date",IF(AND(TODAY()>X147,OR(Z147="",Z147<100)),"Behind — past end date",IF(AND(T147<>"",X147<>"",Z147<>"",(Z147<100),((TODAY()-T147)/MAX(X147-T147,1)*100)-Z147>15),"Behind — progress lag",IF(AND(X147-TODAY()<=30,X147-TODAY()>=0,OR(Z147="",Z147<90)),"At risk — close to off track","On track")))))))) | IF(OR(F147="",AC147="Completed / Handover",AC147="Cancelled"),"",IF(O147="Not awarded",IF(U147<>"",U147-TODAY(),IF(X147="","",X147-TODAY())),IF(X147="","",X147-TODAY()))) | [14 empty] | IF(OR(F147="",AJ147=""),"",IF(COUNT(AI147:AI147)=0,"",AJ147-LOOKUP(2,1/(AI147:AI147<>""),AI147:AI147))) | IF(OR(F147="",AK147=""),"",IF(COUNT(AI147:AJ147)=0,"",AK147-LOOKUP(2,1/(AI147:AJ147<>""),AI147:AJ147))) | IF(OR(F147="",AL147=""),"",IF(COUNT(AI147:AK147)=0,"",AL147-LOOKUP(2,1/(AI147:AK147<>""),AI147:AK147))) | IF(OR(F147="",AM147=""),"",IF(COUNT(AI147:AL147)=0,"",AM147-LOOKUP(2,1/(AI147:AL147<>""),AI147:AL147))) | IF(OR(F147="",AN147=""),"",IF(COUNT(AI147:AM147)=0,"",AN147-LOOKUP(2,1/(AI147:AM147<>""),AI147:AM147))) | IF(OR(F147="",AO147=""),"",IF(COUNT(AI147:AN147)=0,"",AO147-LOOKUP(2,1/(AI147:AN147<>""),AI147:AN147))) | IF(OR(F147="",AP147=""),"",IF(COUNT(AI147:AO147)=0,"",AP147-LOOKUP(2,1/(AI147:AO147<>""),AI147:AO147))) | IF(OR(F147="",AQ147=""),"",IF(COUNT(AI147:AP147)=0,"",AQ147-LOOKUP(2,1/(AI147:AP147<>""),AI147:AP147))) | IF(OR(F147="",AR147=""),"",IF(COUNT(AI147:AQ147)=0,"",AR147-LOOKUP(2,1/(AI147:AQ147<>""),AI147:AQ147))) | IF(OR(F147="",AS147=""),"",IF(COUNT(AI147:AR147)=0,"",AS147-LOOKUP(2,1/(AI147:AR147<>""),AI147:AR147))) | IF(OR(F147="",AT147=""),"",IF(COUNT(AI147:AS147)=0,"",AT147-LOOKUP(2,1/(AI147:AS147<>""),AI147:AS147))) | IF(OR(F147="",AU147=""),"",IF(COUNT(AI147:AT147)=0,"",AU147-LOOKUP(2,1/(AI147:AT147<>""),AI147:AT147))) | IF(OR(F147="",AV147=""),"",IF(COUNT(AI147:AU147)=0,"",AV147-LOOKUP(2,1/(AI147:AU147<>""),AI147:AU147))) | IF(J147="","All_Provinces",IFERROR(VLOOKUP(J147,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K147="","All_Districts",IFERROR(VLOOKUP(K147,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F148="","",ROW()-3) | AF2-IS-04 | Package #4-AF2 IS: Rehabilitation of Joi Gang irrigation scheme in Bala Murghab districts of Badghis provinec. | 1 of 1 | AF2-IS-N-002 | Joi Ganj Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Bala Murghab | Joi Ganj and Ludeenha | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 248511.19 | IF(AQ148="","",AQ148) | 2026-12-31 | 9.9 | 2027-10-27 | IF(W148<>"",W148,IF(OR(T148="",V148=""),"",EDATE(T148,V148))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals | IF(F148="","",IF(COUNT(AI148:AV148)=0,IF(AA148="","Not started",AA148),SUBSTITUTE(LOOKUP(2,1/(AI148:AV148<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F148="",COUNT(AI148:AV148)=0),"",TODAY()-LOOKUP(2,1/(AI148:AV148<>""),AI148:AV148)) | IF(OR(F148="",COUNT(AI148:AV148)<2),"",LOOKUP(2,1/(AI148:AV148<>""),AI148:AV148)-MIN(AI148:AV148)) | IF(OR(AD148="",AC148="Not started",AC148=""),"",IFERROR(AD148-IF(VLOOKUP(AC148,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC148,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F148="","",IF(OR(AA148="Cancelled",AC148="Cancelled"),"Cancelled",IF(OR(AC148="Completed / Handover",Y148<>"",Z148>=100),"Completed — on track",IF(O148="Not awarded",IF(U148="",IF(X148="","No planned date",IF(TODAY()>X148,"Behind — past planned date",IF(X148-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U148,"Behind — award date passed",IF(U148-TODAY()<=30,"At risk — close to off track","On track"))),IF(X148="","No planned date",IF(AND(TODAY()>X148,OR(Z148="",Z148<100)),"Behind — past end date",IF(AND(T148<>"",X148<>"",Z148<>"",(Z148<100),((TODAY()-T148)/MAX(X148-T148,1)*100)-Z148>15),"Behind — progress lag",IF(AND(X148-TODAY()<=30,X148-TODAY()>=0,OR(Z148="",Z148<90)),"At risk — close to off track","On track")))))))) | IF(OR(F148="",AC148="Completed / Handover",AC148="Cancelled"),"",IF(O148="Not awarded",IF(U148<>"",U148-TODAY(),IF(X148="","",X148-TODAY())),IF(X148="","",X148-TODAY()))) | [14 empty] | IF(OR(F148="",AJ148=""),"",IF(COUNT(AI148:AI148)=0,"",AJ148-LOOKUP(2,1/(AI148:AI148<>""),AI148:AI148))) | IF(OR(F148="",AK148=""),"",IF(COUNT(AI148:AJ148)=0,"",AK148-LOOKUP(2,1/(AI148:AJ148<>""),AI148:AJ148))) | IF(OR(F148="",AL148=""),"",IF(COUNT(AI148:AK148)=0,"",AL148-LOOKUP(2,1/(AI148:AK148<>""),AI148:AK148))) | IF(OR(F148="",AM148=""),"",IF(COUNT(AI148:AL148)=0,"",AM148-LOOKUP(2,1/(AI148:AL148<>""),AI148:AL148))) | IF(OR(F148="",AN148=""),"",IF(COUNT(AI148:AM148)=0,"",AN148-LOOKUP(2,1/(AI148:AM148<>""),AI148:AM148))) | IF(OR(F148="",AO148=""),"",IF(COUNT(AI148:AN148)=0,"",AO148-LOOKUP(2,1/(AI148:AN148<>""),AI148:AN148))) | IF(OR(F148="",AP148=""),"",IF(COUNT(AI148:AO148)=0,"",AP148-LOOKUP(2,1/(AI148:AO148<>""),AI148:AO148))) | IF(OR(F148="",AQ148=""),"",IF(COUNT(AI148:AP148)=0,"",AQ148-LOOKUP(2,1/(AI148:AP148<>""),AI148:AP148))) | IF(OR(F148="",AR148=""),"",IF(COUNT(AI148:AQ148)=0,"",AR148-LOOKUP(2,1/(AI148:AQ148<>""),AI148:AQ148))) | IF(OR(F148="",AS148=""),"",IF(COUNT(AI148:AR148)=0,"",AS148-LOOKUP(2,1/(AI148:AR148<>""),AI148:AR148))) | IF(OR(F148="",AT148=""),"",IF(COUNT(AI148:AS148)=0,"",AT148-LOOKUP(2,1/(AI148:AS148<>""),AI148:AS148))) | IF(OR(F148="",AU148=""),"",IF(COUNT(AI148:AT148)=0,"",AU148-LOOKUP(2,1/(AI148:AT148<>""),AI148:AT148))) | IF(OR(F148="",AV148=""),"",IF(COUNT(AI148:AU148)=0,"",AV148-LOOKUP(2,1/(AI148:AU148<>""),AI148:AU148))) | IF(J148="","All_Provinces",IFERROR(VLOOKUP(J148,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K148="","All_Districts",IFERROR(VLOOKUP(K148,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F149="","",ROW()-3) | AF2-IS-05 | Package #5-AF2 IS: Rehabilitation of Korakha irrigation scheme, located in Dawlatyar District of Ghor province. | 1 of 1 | AF2-IS-N-003 | Korakha Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Dawlatyar | Sumak | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 101250 | IF(AQ149="","",AQ149) | 2026-12-25 | 7.6 | 2027-08-12 | IF(W149<>"",W149,IF(OR(T149="",V149=""),"",EDATE(T149,V149))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Five months construction period required for two canals | IF(F149="","",IF(COUNT(AI149:AV149)=0,IF(AA149="","Not started",AA149),SUBSTITUTE(LOOKUP(2,1/(AI149:AV149<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F149="",COUNT(AI149:AV149)=0),"",TODAY()-LOOKUP(2,1/(AI149:AV149<>""),AI149:AV149)) | IF(OR(F149="",COUNT(AI149:AV149)<2),"",LOOKUP(2,1/(AI149:AV149<>""),AI149:AV149)-MIN(AI149:AV149)) | IF(OR(AD149="",AC149="Not started",AC149=""),"",IFERROR(AD149-IF(VLOOKUP(AC149,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC149,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F149="","",IF(OR(AA149="Cancelled",AC149="Cancelled"),"Cancelled",IF(OR(AC149="Completed / Handover",Y149<>"",Z149>=100),"Completed — on track",IF(O149="Not awarded",IF(U149="",IF(X149="","No planned date",IF(TODAY()>X149,"Behind — past planned date",IF(X149-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U149,"Behind — award date passed",IF(U149-TODAY()<=30,"At risk — close to off track","On track"))),IF(X149="","No planned date",IF(AND(TODAY()>X149,OR(Z149="",Z149<100)),"Behind — past end date",IF(AND(T149<>"",X149<>"",Z149<>"",(Z149<100),((TODAY()-T149)/MAX(X149-T149,1)*100)-Z149>15),"Behind — progress lag",IF(AND(X149-TODAY()<=30,X149-TODAY()>=0,OR(Z149="",Z149<90)),"At risk — close to off track","On track")))))))) | IF(OR(F149="",AC149="Completed / Handover",AC149="Cancelled"),"",IF(O149="Not awarded",IF(U149<>"",U149-TODAY(),IF(X149="","",X149-TODAY())),IF(X149="","",X149-TODAY()))) | [14 empty] | IF(OR(F149="",AJ149=""),"",IF(COUNT(AI149:AI149)=0,"",AJ149-LOOKUP(2,1/(AI149:AI149<>""),AI149:AI149))) | IF(OR(F149="",AK149=""),"",IF(COUNT(AI149:AJ149)=0,"",AK149-LOOKUP(2,1/(AI149:AJ149<>""),AI149:AJ149))) | IF(OR(F149="",AL149=""),"",IF(COUNT(AI149:AK149)=0,"",AL149-LOOKUP(2,1/(AI149:AK149<>""),AI149:AK149))) | IF(OR(F149="",AM149=""),"",IF(COUNT(AI149:AL149)=0,"",AM149-LOOKUP(2,1/(AI149:AL149<>""),AI149:AL149))) | IF(OR(F149="",AN149=""),"",IF(COUNT(AI149:AM149)=0,"",AN149-LOOKUP(2,1/(AI149:AM149<>""),AI149:AM149))) | IF(OR(F149="",AO149=""),"",IF(COUNT(AI149:AN149)=0,"",AO149-LOOKUP(2,1/(AI149:AN149<>""),AI149:AN149))) | IF(OR(F149="",AP149=""),"",IF(COUNT(AI149:AO149)=0,"",AP149-LOOKUP(2,1/(AI149:AO149<>""),AI149:AO149))) | IF(OR(F149="",AQ149=""),"",IF(COUNT(AI149:AP149)=0,"",AQ149-LOOKUP(2,1/(AI149:AP149<>""),AI149:AP149))) | IF(OR(F149="",AR149=""),"",IF(COUNT(AI149:AQ149)=0,"",AR149-LOOKUP(2,1/(AI149:AQ149<>""),AI149:AQ149))) | IF(OR(F149="",AS149=""),"",IF(COUNT(AI149:AR149)=0,"",AS149-LOOKUP(2,1/(AI149:AR149<>""),AI149:AR149))) | IF(OR(F149="",AT149=""),"",IF(COUNT(AI149:AS149)=0,"",AT149-LOOKUP(2,1/(AI149:AS149<>""),AI149:AS149))) | IF(OR(F149="",AU149=""),"",IF(COUNT(AI149:AT149)=0,"",AU149-LOOKUP(2,1/(AI149:AT149<>""),AI149:AT149))) | IF(OR(F149="",AV149=""),"",IF(COUNT(AI149:AU149)=0,"",AV149-LOOKUP(2,1/(AI149:AU149<>""),AI149:AU149))) | IF(J149="","All_Provinces",IFERROR(VLOOKUP(J149,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K149="","All_Districts",IFERROR(VLOOKUP(K149,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F150="","",ROW()-3) | AF2-IS-06 | Package #6-AF2 IS: Rehabilitation of Kushtal Canal, Checknawar canal, and Patikhirrki canal irrigation schemes, located in Lalpora ,Spinghar and Khogyani districts of Nangarhar province. | 1 of 3 | AF2-IS-A-005 | Checknawar canal irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Spinghar | Kushtal | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Shirali Khan Barakatzai Construction Company (SBCC) | 054/2025 | 221002.97 | IF(AQ150="","",AQ150) |  | 12 | 2026-10-24 | IF(W150<>"",W150,IF(OR(T150="",V150=""),"",EDATE(T150,V150))) |  | 90 | Under Construction | on track and will be completed by Oct. 2026 | IF(F150="","",IF(COUNT(AI150:AV150)=0,IF(AA150="","Not started",AA150),SUBSTITUTE(LOOKUP(2,1/(AI150:AV150<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F150="",COUNT(AI150:AV150)=0),"",TODAY()-LOOKUP(2,1/(AI150:AV150<>""),AI150:AV150)) | IF(OR(F150="",COUNT(AI150:AV150)<2),"",LOOKUP(2,1/(AI150:AV150<>""),AI150:AV150)-MIN(AI150:AV150)) | IF(OR(AD150="",AC150="Not started",AC150=""),"",IFERROR(AD150-IF(VLOOKUP(AC150,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC150,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F150="","",IF(OR(AA150="Cancelled",AC150="Cancelled"),"Cancelled",IF(OR(AC150="Completed / Handover",Y150<>"",Z150>=100),"Completed — on track",IF(O150="Not awarded",IF(U150="",IF(X150="","No planned date",IF(TODAY()>X150,"Behind — past planned date",IF(X150-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U150,"Behind — award date passed",IF(U150-TODAY()<=30,"At risk — close to off track","On track"))),IF(X150="","No planned date",IF(AND(TODAY()>X150,OR(Z150="",Z150<100)),"Behind — past end date",IF(AND(T150<>"",X150<>"",Z150<>"",(Z150<100),((TODAY()-T150)/MAX(X150-T150,1)*100)-Z150>15),"Behind — progress lag",IF(AND(X150-TODAY()<=30,X150-TODAY()>=0,OR(Z150="",Z150<90)),"At risk — close to off track","On track")))))))) | IF(OR(F150="",AC150="Completed / Handover",AC150="Cancelled"),"",IF(O150="Not awarded",IF(U150<>"",U150-TODAY(),IF(X150="","",X150-TODAY())),IF(X150="","",X150-TODAY()))) | [8 empty] | 2025-10-25 | 2025-10-25 |  |  |  |  | IF(OR(F150="",AJ150=""),"",IF(COUNT(AI150:AI150)=0,"",AJ150-LOOKUP(2,1/(AI150:AI150<>""),AI150:AI150))) | IF(OR(F150="",AK150=""),"",IF(COUNT(AI150:AJ150)=0,"",AK150-LOOKUP(2,1/(AI150:AJ150<>""),AI150:AJ150))) | IF(OR(F150="",AL150=""),"",IF(COUNT(AI150:AK150)=0,"",AL150-LOOKUP(2,1/(AI150:AK150<>""),AI150:AK150))) | IF(OR(F150="",AM150=""),"",IF(COUNT(AI150:AL150)=0,"",AM150-LOOKUP(2,1/(AI150:AL150<>""),AI150:AL150))) | IF(OR(F150="",AN150=""),"",IF(COUNT(AI150:AM150)=0,"",AN150-LOOKUP(2,1/(AI150:AM150<>""),AI150:AM150))) | IF(OR(F150="",AO150=""),"",IF(COUNT(AI150:AN150)=0,"",AO150-LOOKUP(2,1/(AI150:AN150<>""),AI150:AN150))) | IF(OR(F150="",AP150=""),"",IF(COUNT(AI150:AO150)=0,"",AP150-LOOKUP(2,1/(AI150:AO150<>""),AI150:AO150))) | IF(OR(F150="",AQ150=""),"",IF(COUNT(AI150:AP150)=0,"",AQ150-LOOKUP(2,1/(AI150:AP150<>""),AI150:AP150))) | IF(OR(F150="",AR150=""),"",IF(COUNT(AI150:AQ150)=0,"",AR150-LOOKUP(2,1/(AI150:AQ150<>""),AI150:AQ150))) | IF(OR(F150="",AS150=""),"",IF(COUNT(AI150:AR150)=0,"",AS150-LOOKUP(2,1/(AI150:AR150<>""),AI150:AR150))) | IF(OR(F150="",AT150=""),"",IF(COUNT(AI150:AS150)=0,"",AT150-LOOKUP(2,1/(AI150:AS150<>""),AI150:AS150))) | IF(OR(F150="",AU150=""),"",IF(COUNT(AI150:AT150)=0,"",AU150-LOOKUP(2,1/(AI150:AT150<>""),AI150:AT150))) | IF(OR(F150="",AV150=""),"",IF(COUNT(AI150:AU150)=0,"",AV150-LOOKUP(2,1/(AI150:AU150<>""),AI150:AU150))) | IF(J150="","All_Provinces",IFERROR(VLOOKUP(J150,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K150="","All_Districts",IFERROR(VLOOKUP(K150,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F151="","",ROW()-3) | AF2-IS-06 | Package #6-AF2 IS: Rehabilitation of Kushtal Canal, Checknawar canal, and Patikhirrki canal irrigation schemes, located in Lalpora ,Spinghar and Khogyani districts of Nangarhar province. | 2 of 3 | AF2-IS-A-006 | Kushtal canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Lalpora | Checknawar | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Shirali Khan Barakatzai Construction Company (SBCC) | 054/2025 | 57919.77 | IF(AQ151="","",AQ151) |  | 12 | 2026-10-24 | IF(W151<>"",W151,IF(OR(T151="",V151=""),"",EDATE(T151,V151))) |  | 95 | Under Construction | on track and will be completed by Oct. 2026 | IF(F151="","",IF(COUNT(AI151:AV151)=0,IF(AA151="","Not started",AA151),SUBSTITUTE(LOOKUP(2,1/(AI151:AV151<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F151="",COUNT(AI151:AV151)=0),"",TODAY()-LOOKUP(2,1/(AI151:AV151<>""),AI151:AV151)) | IF(OR(F151="",COUNT(AI151:AV151)<2),"",LOOKUP(2,1/(AI151:AV151<>""),AI151:AV151)-MIN(AI151:AV151)) | IF(OR(AD151="",AC151="Not started",AC151=""),"",IFERROR(AD151-IF(VLOOKUP(AC151,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC151,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F151="","",IF(OR(AA151="Cancelled",AC151="Cancelled"),"Cancelled",IF(OR(AC151="Completed / Handover",Y151<>"",Z151>=100),"Completed — on track",IF(O151="Not awarded",IF(U151="",IF(X151="","No planned date",IF(TODAY()>X151,"Behind — past planned date",IF(X151-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U151,"Behind — award date passed",IF(U151-TODAY()<=30,"At risk — close to off track","On track"))),IF(X151="","No planned date",IF(AND(TODAY()>X151,OR(Z151="",Z151<100)),"Behind — past end date",IF(AND(T151<>"",X151<>"",Z151<>"",(Z151<100),((TODAY()-T151)/MAX(X151-T151,1)*100)-Z151>15),"Behind — progress lag",IF(AND(X151-TODAY()<=30,X151-TODAY()>=0,OR(Z151="",Z151<90)),"At risk — close to off track","On track")))))))) | IF(OR(F151="",AC151="Completed / Handover",AC151="Cancelled"),"",IF(O151="Not awarded",IF(U151<>"",U151-TODAY(),IF(X151="","",X151-TODAY())),IF(X151="","",X151-TODAY()))) | [8 empty] | 2025-10-25 | 2025-10-25 |  |  |  |  | IF(OR(F151="",AJ151=""),"",IF(COUNT(AI151:AI151)=0,"",AJ151-LOOKUP(2,1/(AI151:AI151<>""),AI151:AI151))) | IF(OR(F151="",AK151=""),"",IF(COUNT(AI151:AJ151)=0,"",AK151-LOOKUP(2,1/(AI151:AJ151<>""),AI151:AJ151))) | IF(OR(F151="",AL151=""),"",IF(COUNT(AI151:AK151)=0,"",AL151-LOOKUP(2,1/(AI151:AK151<>""),AI151:AK151))) | IF(OR(F151="",AM151=""),"",IF(COUNT(AI151:AL151)=0,"",AM151-LOOKUP(2,1/(AI151:AL151<>""),AI151:AL151))) | IF(OR(F151="",AN151=""),"",IF(COUNT(AI151:AM151)=0,"",AN151-LOOKUP(2,1/(AI151:AM151<>""),AI151:AM151))) | IF(OR(F151="",AO151=""),"",IF(COUNT(AI151:AN151)=0,"",AO151-LOOKUP(2,1/(AI151:AN151<>""),AI151:AN151))) | IF(OR(F151="",AP151=""),"",IF(COUNT(AI151:AO151)=0,"",AP151-LOOKUP(2,1/(AI151:AO151<>""),AI151:AO151))) | IF(OR(F151="",AQ151=""),"",IF(COUNT(AI151:AP151)=0,"",AQ151-LOOKUP(2,1/(AI151:AP151<>""),AI151:AP151))) | IF(OR(F151="",AR151=""),"",IF(COUNT(AI151:AQ151)=0,"",AR151-LOOKUP(2,1/(AI151:AQ151<>""),AI151:AQ151))) | IF(OR(F151="",AS151=""),"",IF(COUNT(AI151:AR151)=0,"",AS151-LOOKUP(2,1/(AI151:AR151<>""),AI151:AR151))) | IF(OR(F151="",AT151=""),"",IF(COUNT(AI151:AS151)=0,"",AT151-LOOKUP(2,1/(AI151:AS151<>""),AI151:AS151))) | IF(OR(F151="",AU151=""),"",IF(COUNT(AI151:AT151)=0,"",AU151-LOOKUP(2,1/(AI151:AT151<>""),AI151:AT151))) | IF(OR(F151="",AV151=""),"",IF(COUNT(AI151:AU151)=0,"",AV151-LOOKUP(2,1/(AI151:AU151<>""),AI151:AU151))) | IF(J151="","All_Provinces",IFERROR(VLOOKUP(J151,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K151="","All_Districts",IFERROR(VLOOKUP(K151,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F152="","",ROW()-3) | AF2-IS-06 | Package #6-AF2 IS: Rehabilitation of Kushtal Canal, Checknawar canal, and Patikhirrki canal irrigation schemes, located in Lalpora ,Spinghar and Khogyani districts of Nangarhar province. | 3 of 3 | AF2-IS-A-007 | Patikhirki canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Khogyani | Patikhirrki | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Shirali Khan Barakatzai Construction Company (SBCC) | 054/2025 | 96234.4 | IF(AQ152="","",AQ152) |  | 12 | 2026-10-24 | IF(W152<>"",W152,IF(OR(T152="",V152=""),"",EDATE(T152,V152))) |  | 90 | Under Construction | on track and will be completed by Oct. 2026 | IF(F152="","",IF(COUNT(AI152:AV152)=0,IF(AA152="","Not started",AA152),SUBSTITUTE(LOOKUP(2,1/(AI152:AV152<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F152="",COUNT(AI152:AV152)=0),"",TODAY()-LOOKUP(2,1/(AI152:AV152<>""),AI152:AV152)) | IF(OR(F152="",COUNT(AI152:AV152)<2),"",LOOKUP(2,1/(AI152:AV152<>""),AI152:AV152)-MIN(AI152:AV152)) | IF(OR(AD152="",AC152="Not started",AC152=""),"",IFERROR(AD152-IF(VLOOKUP(AC152,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC152,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F152="","",IF(OR(AA152="Cancelled",AC152="Cancelled"),"Cancelled",IF(OR(AC152="Completed / Handover",Y152<>"",Z152>=100),"Completed — on track",IF(O152="Not awarded",IF(U152="",IF(X152="","No planned date",IF(TODAY()>X152,"Behind — past planned date",IF(X152-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U152,"Behind — award date passed",IF(U152-TODAY()<=30,"At risk — close to off track","On track"))),IF(X152="","No planned date",IF(AND(TODAY()>X152,OR(Z152="",Z152<100)),"Behind — past end date",IF(AND(T152<>"",X152<>"",Z152<>"",(Z152<100),((TODAY()-T152)/MAX(X152-T152,1)*100)-Z152>15),"Behind — progress lag",IF(AND(X152-TODAY()<=30,X152-TODAY()>=0,OR(Z152="",Z152<90)),"At risk — close to off track","On track")))))))) | IF(OR(F152="",AC152="Completed / Handover",AC152="Cancelled"),"",IF(O152="Not awarded",IF(U152<>"",U152-TODAY(),IF(X152="","",X152-TODAY())),IF(X152="","",X152-TODAY()))) | [8 empty] | 2025-10-25 | 2025-10-25 |  |  |  |  | IF(OR(F152="",AJ152=""),"",IF(COUNT(AI152:AI152)=0,"",AJ152-LOOKUP(2,1/(AI152:AI152<>""),AI152:AI152))) | IF(OR(F152="",AK152=""),"",IF(COUNT(AI152:AJ152)=0,"",AK152-LOOKUP(2,1/(AI152:AJ152<>""),AI152:AJ152))) | IF(OR(F152="",AL152=""),"",IF(COUNT(AI152:AK152)=0,"",AL152-LOOKUP(2,1/(AI152:AK152<>""),AI152:AK152))) | IF(OR(F152="",AM152=""),"",IF(COUNT(AI152:AL152)=0,"",AM152-LOOKUP(2,1/(AI152:AL152<>""),AI152:AL152))) | IF(OR(F152="",AN152=""),"",IF(COUNT(AI152:AM152)=0,"",AN152-LOOKUP(2,1/(AI152:AM152<>""),AI152:AM152))) | IF(OR(F152="",AO152=""),"",IF(COUNT(AI152:AN152)=0,"",AO152-LOOKUP(2,1/(AI152:AN152<>""),AI152:AN152))) | IF(OR(F152="",AP152=""),"",IF(COUNT(AI152:AO152)=0,"",AP152-LOOKUP(2,1/(AI152:AO152<>""),AI152:AO152))) | IF(OR(F152="",AQ152=""),"",IF(COUNT(AI152:AP152)=0,"",AQ152-LOOKUP(2,1/(AI152:AP152<>""),AI152:AP152))) | IF(OR(F152="",AR152=""),"",IF(COUNT(AI152:AQ152)=0,"",AR152-LOOKUP(2,1/(AI152:AQ152<>""),AI152:AQ152))) | IF(OR(F152="",AS152=""),"",IF(COUNT(AI152:AR152)=0,"",AS152-LOOKUP(2,1/(AI152:AR152<>""),AI152:AR152))) | IF(OR(F152="",AT152=""),"",IF(COUNT(AI152:AS152)=0,"",AT152-LOOKUP(2,1/(AI152:AS152<>""),AI152:AS152))) | IF(OR(F152="",AU152=""),"",IF(COUNT(AI152:AT152)=0,"",AU152-LOOKUP(2,1/(AI152:AT152<>""),AI152:AT152))) | IF(OR(F152="",AV152=""),"",IF(COUNT(AI152:AU152)=0,"",AV152-LOOKUP(2,1/(AI152:AU152<>""),AI152:AU152))) | IF(J152="","All_Provinces",IFERROR(VLOOKUP(J152,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K152="","All_Districts",IFERROR(VLOOKUP(K152,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F153="","",ROW()-3) | AF2-IS-07 | Package #7-AF2 IS: Rehabilitation of Kham Canal and Shandi Toot canal irrigation schemes, located in Dehbala and Sherzad districts of Nangarhar provinces. | 1 of 2 | AF2-IS-N-004 | Kham canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Dehbala | Kham Kali and 6 tiny villages | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 270698.1 | IF(AQ153="","",AQ153) | 2026-10-30 | 6.9 | 2027-05-28 | IF(W153<>"",W153,IF(OR(T153="",V153=""),"",EDATE(T153,V153))) |  |  | Under Technical Evaluation | Seven months construction period required for two canals | IF(F153="","",IF(COUNT(AI153:AV153)=0,IF(AA153="","Not started",AA153),SUBSTITUTE(LOOKUP(2,1/(AI153:AV153<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F153="",COUNT(AI153:AV153)=0),"",TODAY()-LOOKUP(2,1/(AI153:AV153<>""),AI153:AV153)) | IF(OR(F153="",COUNT(AI153:AV153)<2),"",LOOKUP(2,1/(AI153:AV153<>""),AI153:AV153)-MIN(AI153:AV153)) | IF(OR(AD153="",AC153="Not started",AC153=""),"",IFERROR(AD153-IF(VLOOKUP(AC153,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC153,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F153="","",IF(OR(AA153="Cancelled",AC153="Cancelled"),"Cancelled",IF(OR(AC153="Completed / Handover",Y153<>"",Z153>=100),"Completed — on track",IF(O153="Not awarded",IF(U153="",IF(X153="","No planned date",IF(TODAY()>X153,"Behind — past planned date",IF(X153-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U153,"Behind — award date passed",IF(U153-TODAY()<=30,"At risk — close to off track","On track"))),IF(X153="","No planned date",IF(AND(TODAY()>X153,OR(Z153="",Z153<100)),"Behind — past end date",IF(AND(T153<>"",X153<>"",Z153<>"",(Z153<100),((TODAY()-T153)/MAX(X153-T153,1)*100)-Z153>15),"Behind — progress lag",IF(AND(X153-TODAY()<=30,X153-TODAY()>=0,OR(Z153="",Z153<90)),"At risk — close to off track","On track")))))))) | IF(OR(F153="",AC153="Completed / Handover",AC153="Cancelled"),"",IF(O153="Not awarded",IF(U153<>"",U153-TODAY(),IF(X153="","",X153-TODAY())),IF(X153="","",X153-TODAY()))) | [14 empty] | IF(OR(F153="",AJ153=""),"",IF(COUNT(AI153:AI153)=0,"",AJ153-LOOKUP(2,1/(AI153:AI153<>""),AI153:AI153))) | IF(OR(F153="",AK153=""),"",IF(COUNT(AI153:AJ153)=0,"",AK153-LOOKUP(2,1/(AI153:AJ153<>""),AI153:AJ153))) | IF(OR(F153="",AL153=""),"",IF(COUNT(AI153:AK153)=0,"",AL153-LOOKUP(2,1/(AI153:AK153<>""),AI153:AK153))) | IF(OR(F153="",AM153=""),"",IF(COUNT(AI153:AL153)=0,"",AM153-LOOKUP(2,1/(AI153:AL153<>""),AI153:AL153))) | IF(OR(F153="",AN153=""),"",IF(COUNT(AI153:AM153)=0,"",AN153-LOOKUP(2,1/(AI153:AM153<>""),AI153:AM153))) | IF(OR(F153="",AO153=""),"",IF(COUNT(AI153:AN153)=0,"",AO153-LOOKUP(2,1/(AI153:AN153<>""),AI153:AN153))) | IF(OR(F153="",AP153=""),"",IF(COUNT(AI153:AO153)=0,"",AP153-LOOKUP(2,1/(AI153:AO153<>""),AI153:AO153))) | IF(OR(F153="",AQ153=""),"",IF(COUNT(AI153:AP153)=0,"",AQ153-LOOKUP(2,1/(AI153:AP153<>""),AI153:AP153))) | IF(OR(F153="",AR153=""),"",IF(COUNT(AI153:AQ153)=0,"",AR153-LOOKUP(2,1/(AI153:AQ153<>""),AI153:AQ153))) | IF(OR(F153="",AS153=""),"",IF(COUNT(AI153:AR153)=0,"",AS153-LOOKUP(2,1/(AI153:AR153<>""),AI153:AR153))) | IF(OR(F153="",AT153=""),"",IF(COUNT(AI153:AS153)=0,"",AT153-LOOKUP(2,1/(AI153:AS153<>""),AI153:AS153))) | IF(OR(F153="",AU153=""),"",IF(COUNT(AI153:AT153)=0,"",AU153-LOOKUP(2,1/(AI153:AT153<>""),AI153:AT153))) | IF(OR(F153="",AV153=""),"",IF(COUNT(AI153:AU153)=0,"",AV153-LOOKUP(2,1/(AI153:AU153<>""),AI153:AU153))) | IF(J153="","All_Provinces",IFERROR(VLOOKUP(J153,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K153="","All_Districts",IFERROR(VLOOKUP(K153,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F154="","",ROW()-3) | AF2-IS-07 | Package #7-AF2 IS: Rehabilitation of Kham Canal and Shandi Toot canal irrigation schemes, located in Dehbala and Sherzad districts of Nangarhar provinces. | 2 of 2 | AF2-IS-N-005 | Shandi Toot Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Sherzad | Markikhil/Shandi Toot and 14 tiny villages | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 270698.1 | IF(AQ154="","",AQ154) | 2026-10-30 | 6.9 | 2027-05-28 | IF(W154<>"",W154,IF(OR(T154="",V154=""),"",EDATE(T154,V154))) |  |  | Under Technical Evaluation | Seven months construction period required for two canals | IF(F154="","",IF(COUNT(AI154:AV154)=0,IF(AA154="","Not started",AA154),SUBSTITUTE(LOOKUP(2,1/(AI154:AV154<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F154="",COUNT(AI154:AV154)=0),"",TODAY()-LOOKUP(2,1/(AI154:AV154<>""),AI154:AV154)) | IF(OR(F154="",COUNT(AI154:AV154)<2),"",LOOKUP(2,1/(AI154:AV154<>""),AI154:AV154)-MIN(AI154:AV154)) | IF(OR(AD154="",AC154="Not started",AC154=""),"",IFERROR(AD154-IF(VLOOKUP(AC154,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC154,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F154="","",IF(OR(AA154="Cancelled",AC154="Cancelled"),"Cancelled",IF(OR(AC154="Completed / Handover",Y154<>"",Z154>=100),"Completed — on track",IF(O154="Not awarded",IF(U154="",IF(X154="","No planned date",IF(TODAY()>X154,"Behind — past planned date",IF(X154-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U154,"Behind — award date passed",IF(U154-TODAY()<=30,"At risk — close to off track","On track"))),IF(X154="","No planned date",IF(AND(TODAY()>X154,OR(Z154="",Z154<100)),"Behind — past end date",IF(AND(T154<>"",X154<>"",Z154<>"",(Z154<100),((TODAY()-T154)/MAX(X154-T154,1)*100)-Z154>15),"Behind — progress lag",IF(AND(X154-TODAY()<=30,X154-TODAY()>=0,OR(Z154="",Z154<90)),"At risk — close to off track","On track")))))))) | IF(OR(F154="",AC154="Completed / Handover",AC154="Cancelled"),"",IF(O154="Not awarded",IF(U154<>"",U154-TODAY(),IF(X154="","",X154-TODAY())),IF(X154="","",X154-TODAY()))) | [14 empty] | IF(OR(F154="",AJ154=""),"",IF(COUNT(AI154:AI154)=0,"",AJ154-LOOKUP(2,1/(AI154:AI154<>""),AI154:AI154))) | IF(OR(F154="",AK154=""),"",IF(COUNT(AI154:AJ154)=0,"",AK154-LOOKUP(2,1/(AI154:AJ154<>""),AI154:AJ154))) | IF(OR(F154="",AL154=""),"",IF(COUNT(AI154:AK154)=0,"",AL154-LOOKUP(2,1/(AI154:AK154<>""),AI154:AK154))) | IF(OR(F154="",AM154=""),"",IF(COUNT(AI154:AL154)=0,"",AM154-LOOKUP(2,1/(AI154:AL154<>""),AI154:AL154))) | IF(OR(F154="",AN154=""),"",IF(COUNT(AI154:AM154)=0,"",AN154-LOOKUP(2,1/(AI154:AM154<>""),AI154:AM154))) | IF(OR(F154="",AO154=""),"",IF(COUNT(AI154:AN154)=0,"",AO154-LOOKUP(2,1/(AI154:AN154<>""),AI154:AN154))) | IF(OR(F154="",AP154=""),"",IF(COUNT(AI154:AO154)=0,"",AP154-LOOKUP(2,1/(AI154:AO154<>""),AI154:AO154))) | IF(OR(F154="",AQ154=""),"",IF(COUNT(AI154:AP154)=0,"",AQ154-LOOKUP(2,1/(AI154:AP154<>""),AI154:AP154))) | IF(OR(F154="",AR154=""),"",IF(COUNT(AI154:AQ154)=0,"",AR154-LOOKUP(2,1/(AI154:AQ154<>""),AI154:AQ154))) | IF(OR(F154="",AS154=""),"",IF(COUNT(AI154:AR154)=0,"",AS154-LOOKUP(2,1/(AI154:AR154<>""),AI154:AR154))) | IF(OR(F154="",AT154=""),"",IF(COUNT(AI154:AS154)=0,"",AT154-LOOKUP(2,1/(AI154:AS154<>""),AI154:AS154))) | IF(OR(F154="",AU154=""),"",IF(COUNT(AI154:AT154)=0,"",AU154-LOOKUP(2,1/(AI154:AT154<>""),AI154:AT154))) | IF(OR(F154="",AV154=""),"",IF(COUNT(AI154:AU154)=0,"",AV154-LOOKUP(2,1/(AI154:AU154<>""),AI154:AU154))) | IF(J154="","All_Provinces",IFERROR(VLOOKUP(J154,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K154="","All_Districts",IFERROR(VLOOKUP(K154,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F155="","",ROW()-3) | AF2-IS-08 | Package #8-AF2 IS: Rehabilitation of Khas Kunar Lower canal and Bahrabad canal irrigation schemes, located in Khas Kunar district of Kunar and Behsood district of Nangarhar provinces. | 1 of 2 | AF2-IS-A-008 | Bahrabad Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Behsood | Bahrabad | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Awrish builder construction company (ABCC) | 055/2026 | 155202.17 | IF(AQ155="","",AQ155) |  | 12 | 2027-08-19 | IF(W155<>"",W155,IF(OR(T155="",V155=""),"",EDATE(T155,V155))) |  | 2 | Under Construction | on track and will be completed by August 2027 | IF(F155="","",IF(COUNT(AI155:AV155)=0,IF(AA155="","Not started",AA155),SUBSTITUTE(LOOKUP(2,1/(AI155:AV155<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F155="",COUNT(AI155:AV155)=0),"",TODAY()-LOOKUP(2,1/(AI155:AV155<>""),AI155:AV155)) | IF(OR(F155="",COUNT(AI155:AV155)<2),"",LOOKUP(2,1/(AI155:AV155<>""),AI155:AV155)-MIN(AI155:AV155)) | IF(OR(AD155="",AC155="Not started",AC155=""),"",IFERROR(AD155-IF(VLOOKUP(AC155,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC155,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F155="","",IF(OR(AA155="Cancelled",AC155="Cancelled"),"Cancelled",IF(OR(AC155="Completed / Handover",Y155<>"",Z155>=100),"Completed — on track",IF(O155="Not awarded",IF(U155="",IF(X155="","No planned date",IF(TODAY()>X155,"Behind — past planned date",IF(X155-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U155,"Behind — award date passed",IF(U155-TODAY()<=30,"At risk — close to off track","On track"))),IF(X155="","No planned date",IF(AND(TODAY()>X155,OR(Z155="",Z155<100)),"Behind — past end date",IF(AND(T155<>"",X155<>"",Z155<>"",(Z155<100),((TODAY()-T155)/MAX(X155-T155,1)*100)-Z155>15),"Behind — progress lag",IF(AND(X155-TODAY()<=30,X155-TODAY()>=0,OR(Z155="",Z155<90)),"At risk — close to off track","On track")))))))) | IF(OR(F155="",AC155="Completed / Handover",AC155="Cancelled"),"",IF(O155="Not awarded",IF(U155<>"",U155-TODAY(),IF(X155="","",X155-TODAY())),IF(X155="","",X155-TODAY()))) | [8 empty] | 2026-08-20 | 2026-08-20 |  |  |  |  | IF(OR(F155="",AJ155=""),"",IF(COUNT(AI155:AI155)=0,"",AJ155-LOOKUP(2,1/(AI155:AI155<>""),AI155:AI155))) | IF(OR(F155="",AK155=""),"",IF(COUNT(AI155:AJ155)=0,"",AK155-LOOKUP(2,1/(AI155:AJ155<>""),AI155:AJ155))) | IF(OR(F155="",AL155=""),"",IF(COUNT(AI155:AK155)=0,"",AL155-LOOKUP(2,1/(AI155:AK155<>""),AI155:AK155))) | IF(OR(F155="",AM155=""),"",IF(COUNT(AI155:AL155)=0,"",AM155-LOOKUP(2,1/(AI155:AL155<>""),AI155:AL155))) | IF(OR(F155="",AN155=""),"",IF(COUNT(AI155:AM155)=0,"",AN155-LOOKUP(2,1/(AI155:AM155<>""),AI155:AM155))) | IF(OR(F155="",AO155=""),"",IF(COUNT(AI155:AN155)=0,"",AO155-LOOKUP(2,1/(AI155:AN155<>""),AI155:AN155))) | IF(OR(F155="",AP155=""),"",IF(COUNT(AI155:AO155)=0,"",AP155-LOOKUP(2,1/(AI155:AO155<>""),AI155:AO155))) | IF(OR(F155="",AQ155=""),"",IF(COUNT(AI155:AP155)=0,"",AQ155-LOOKUP(2,1/(AI155:AP155<>""),AI155:AP155))) | IF(OR(F155="",AR155=""),"",IF(COUNT(AI155:AQ155)=0,"",AR155-LOOKUP(2,1/(AI155:AQ155<>""),AI155:AQ155))) | IF(OR(F155="",AS155=""),"",IF(COUNT(AI155:AR155)=0,"",AS155-LOOKUP(2,1/(AI155:AR155<>""),AI155:AR155))) | IF(OR(F155="",AT155=""),"",IF(COUNT(AI155:AS155)=0,"",AT155-LOOKUP(2,1/(AI155:AS155<>""),AI155:AS155))) | IF(OR(F155="",AU155=""),"",IF(COUNT(AI155:AT155)=0,"",AU155-LOOKUP(2,1/(AI155:AT155<>""),AI155:AT155))) | IF(OR(F155="",AV155=""),"",IF(COUNT(AI155:AU155)=0,"",AV155-LOOKUP(2,1/(AI155:AU155<>""),AI155:AU155))) | IF(J155="","All_Provinces",IFERROR(VLOOKUP(J155,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K155="","All_Districts",IFERROR(VLOOKUP(K155,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F156="","",ROW()-3) | AF2-IS-08 | Package #8-AF2 IS: Rehabilitation of Khas Kunar Lower canal and Bahrabad canal irrigation schemes, located in Khas Kunar district of Kunar and Behsood district of Nangarhar provinces. | 2 of 2 | AF2-IS-A-009 | Khas Kunar Lower Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Khas Kunar | Khas Kunar 36 tiny villages | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Awrish builder construction company (ABCC) | 055/2026 | 428653.6 | IF(AQ156="","",AQ156) |  | 12 | 2027-08-19 | IF(W156<>"",W156,IF(OR(T156="",V156=""),"",EDATE(T156,V156))) |  | 1 | Under Construction | on track and will be completed by August 2027 | IF(F156="","",IF(COUNT(AI156:AV156)=0,IF(AA156="","Not started",AA156),SUBSTITUTE(LOOKUP(2,1/(AI156:AV156<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F156="",COUNT(AI156:AV156)=0),"",TODAY()-LOOKUP(2,1/(AI156:AV156<>""),AI156:AV156)) | IF(OR(F156="",COUNT(AI156:AV156)<2),"",LOOKUP(2,1/(AI156:AV156<>""),AI156:AV156)-MIN(AI156:AV156)) | IF(OR(AD156="",AC156="Not started",AC156=""),"",IFERROR(AD156-IF(VLOOKUP(AC156,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC156,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F156="","",IF(OR(AA156="Cancelled",AC156="Cancelled"),"Cancelled",IF(OR(AC156="Completed / Handover",Y156<>"",Z156>=100),"Completed — on track",IF(O156="Not awarded",IF(U156="",IF(X156="","No planned date",IF(TODAY()>X156,"Behind — past planned date",IF(X156-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U156,"Behind — award date passed",IF(U156-TODAY()<=30,"At risk — close to off track","On track"))),IF(X156="","No planned date",IF(AND(TODAY()>X156,OR(Z156="",Z156<100)),"Behind — past end date",IF(AND(T156<>"",X156<>"",Z156<>"",(Z156<100),((TODAY()-T156)/MAX(X156-T156,1)*100)-Z156>15),"Behind — progress lag",IF(AND(X156-TODAY()<=30,X156-TODAY()>=0,OR(Z156="",Z156<90)),"At risk — close to off track","On track")))))))) | IF(OR(F156="",AC156="Completed / Handover",AC156="Cancelled"),"",IF(O156="Not awarded",IF(U156<>"",U156-TODAY(),IF(X156="","",X156-TODAY())),IF(X156="","",X156-TODAY()))) | [8 empty] | 2026-08-20 | 2026-08-20 |  |  |  |  | IF(OR(F156="",AJ156=""),"",IF(COUNT(AI156:AI156)=0,"",AJ156-LOOKUP(2,1/(AI156:AI156<>""),AI156:AI156))) | IF(OR(F156="",AK156=""),"",IF(COUNT(AI156:AJ156)=0,"",AK156-LOOKUP(2,1/(AI156:AJ156<>""),AI156:AJ156))) | IF(OR(F156="",AL156=""),"",IF(COUNT(AI156:AK156)=0,"",AL156-LOOKUP(2,1/(AI156:AK156<>""),AI156:AK156))) | IF(OR(F156="",AM156=""),"",IF(COUNT(AI156:AL156)=0,"",AM156-LOOKUP(2,1/(AI156:AL156<>""),AI156:AL156))) | IF(OR(F156="",AN156=""),"",IF(COUNT(AI156:AM156)=0,"",AN156-LOOKUP(2,1/(AI156:AM156<>""),AI156:AM156))) | IF(OR(F156="",AO156=""),"",IF(COUNT(AI156:AN156)=0,"",AO156-LOOKUP(2,1/(AI156:AN156<>""),AI156:AN156))) | IF(OR(F156="",AP156=""),"",IF(COUNT(AI156:AO156)=0,"",AP156-LOOKUP(2,1/(AI156:AO156<>""),AI156:AO156))) | IF(OR(F156="",AQ156=""),"",IF(COUNT(AI156:AP156)=0,"",AQ156-LOOKUP(2,1/(AI156:AP156<>""),AI156:AP156))) | IF(OR(F156="",AR156=""),"",IF(COUNT(AI156:AQ156)=0,"",AR156-LOOKUP(2,1/(AI156:AQ156<>""),AI156:AQ156))) | IF(OR(F156="",AS156=""),"",IF(COUNT(AI156:AR156)=0,"",AS156-LOOKUP(2,1/(AI156:AR156<>""),AI156:AR156))) | IF(OR(F156="",AT156=""),"",IF(COUNT(AI156:AS156)=0,"",AT156-LOOKUP(2,1/(AI156:AS156<>""),AI156:AS156))) | IF(OR(F156="",AU156=""),"",IF(COUNT(AI156:AT156)=0,"",AU156-LOOKUP(2,1/(AI156:AT156<>""),AI156:AT156))) | IF(OR(F156="",AV156=""),"",IF(COUNT(AI156:AU156)=0,"",AV156-LOOKUP(2,1/(AI156:AU156<>""),AI156:AU156))) | IF(J156="","All_Provinces",IFERROR(VLOOKUP(J156,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K156="","All_Districts",IFERROR(VLOOKUP(K156,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F157="","",ROW()-3) | AF2-IS-09 | Package #9-AF2 IS: Rehabilitation of Akchori canal irrigation scheme, located in Waigal districts of Nuristan provinces. | 1 of 1 | AF2-IS-N-006 | Akchori Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nuristan | Waigal | Akchori two main and 9 tiny villages | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 101175 | IF(AQ157="","",AQ157) | 2026-11-27 | 10 | 2027-09-26 | IF(W157<>"",W157,IF(OR(T157="",V157=""),"",EDATE(T157,V157))) |  |  | ITB Launched | Five months slack period Dec-Apr during winter Five months construction period required for the canals | IF(F157="","",IF(COUNT(AI157:AV157)=0,IF(AA157="","Not started",AA157),SUBSTITUTE(LOOKUP(2,1/(AI157:AV157<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F157="",COUNT(AI157:AV157)=0),"",TODAY()-LOOKUP(2,1/(AI157:AV157<>""),AI157:AV157)) | IF(OR(F157="",COUNT(AI157:AV157)<2),"",LOOKUP(2,1/(AI157:AV157<>""),AI157:AV157)-MIN(AI157:AV157)) | IF(OR(AD157="",AC157="Not started",AC157=""),"",IFERROR(AD157-IF(VLOOKUP(AC157,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC157,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F157="","",IF(OR(AA157="Cancelled",AC157="Cancelled"),"Cancelled",IF(OR(AC157="Completed / Handover",Y157<>"",Z157>=100),"Completed — on track",IF(O157="Not awarded",IF(U157="",IF(X157="","No planned date",IF(TODAY()>X157,"Behind — past planned date",IF(X157-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U157,"Behind — award date passed",IF(U157-TODAY()<=30,"At risk — close to off track","On track"))),IF(X157="","No planned date",IF(AND(TODAY()>X157,OR(Z157="",Z157<100)),"Behind — past end date",IF(AND(T157<>"",X157<>"",Z157<>"",(Z157<100),((TODAY()-T157)/MAX(X157-T157,1)*100)-Z157>15),"Behind — progress lag",IF(AND(X157-TODAY()<=30,X157-TODAY()>=0,OR(Z157="",Z157<90)),"At risk — close to off track","On track")))))))) | IF(OR(F157="",AC157="Completed / Handover",AC157="Cancelled"),"",IF(O157="Not awarded",IF(U157<>"",U157-TODAY(),IF(X157="","",X157-TODAY())),IF(X157="","",X157-TODAY()))) | [14 empty] | IF(OR(F157="",AJ157=""),"",IF(COUNT(AI157:AI157)=0,"",AJ157-LOOKUP(2,1/(AI157:AI157<>""),AI157:AI157))) | IF(OR(F157="",AK157=""),"",IF(COUNT(AI157:AJ157)=0,"",AK157-LOOKUP(2,1/(AI157:AJ157<>""),AI157:AJ157))) | IF(OR(F157="",AL157=""),"",IF(COUNT(AI157:AK157)=0,"",AL157-LOOKUP(2,1/(AI157:AK157<>""),AI157:AK157))) | IF(OR(F157="",AM157=""),"",IF(COUNT(AI157:AL157)=0,"",AM157-LOOKUP(2,1/(AI157:AL157<>""),AI157:AL157))) | IF(OR(F157="",AN157=""),"",IF(COUNT(AI157:AM157)=0,"",AN157-LOOKUP(2,1/(AI157:AM157<>""),AI157:AM157))) | IF(OR(F157="",AO157=""),"",IF(COUNT(AI157:AN157)=0,"",AO157-LOOKUP(2,1/(AI157:AN157<>""),AI157:AN157))) | IF(OR(F157="",AP157=""),"",IF(COUNT(AI157:AO157)=0,"",AP157-LOOKUP(2,1/(AI157:AO157<>""),AI157:AO157))) | IF(OR(F157="",AQ157=""),"",IF(COUNT(AI157:AP157)=0,"",AQ157-LOOKUP(2,1/(AI157:AP157<>""),AI157:AP157))) | IF(OR(F157="",AR157=""),"",IF(COUNT(AI157:AQ157)=0,"",AR157-LOOKUP(2,1/(AI157:AQ157<>""),AI157:AQ157))) | IF(OR(F157="",AS157=""),"",IF(COUNT(AI157:AR157)=0,"",AS157-LOOKUP(2,1/(AI157:AR157<>""),AI157:AR157))) | IF(OR(F157="",AT157=""),"",IF(COUNT(AI157:AS157)=0,"",AT157-LOOKUP(2,1/(AI157:AS157<>""),AI157:AS157))) | IF(OR(F157="",AU157=""),"",IF(COUNT(AI157:AT157)=0,"",AU157-LOOKUP(2,1/(AI157:AT157<>""),AI157:AT157))) | IF(OR(F157="",AV157=""),"",IF(COUNT(AI157:AU157)=0,"",AV157-LOOKUP(2,1/(AI157:AU157<>""),AI157:AU157))) | IF(J157="","All_Provinces",IFERROR(VLOOKUP(J157,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K157="","All_Districts",IFERROR(VLOOKUP(K157,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F158="","",ROW()-3) | AF2-IS-10 | Package #10-AF2 IS: Rehabilitation of 1.Baraki canal, 2. Darbal canal, 3. Nawikhar canal and 4. Mangali canal irrigation schemes, located in Sayed Abad, Chak and Jaghato districts of Wardak province. | 1 of 4 | AF2-IS-A-010 | Baraki Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Sayed Abad | Patan khil, Barat khil, Shadi khil, Sado khil and Laram | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Zahid Saeed Engineering and Construction Company (ZSCC) | 057/2025 | 112870.51 | IF(AQ158="","",AQ158) |  | 12 | 2026-11-17 | IF(W158<>"",W158,IF(OR(T158="",V158=""),"",EDATE(T158,V158))) |  | 100 | Completed / Handover | partly on track, one package will need NCE and works will be completed by May/June 2027 ¦ Actual completion: Sep, 2026 | IF(F158="","",IF(COUNT(AI158:AV158)=0,IF(AA158="","Not started",AA158),SUBSTITUTE(LOOKUP(2,1/(AI158:AV158<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F158="",COUNT(AI158:AV158)=0),"",TODAY()-LOOKUP(2,1/(AI158:AV158<>""),AI158:AV158)) | IF(OR(F158="",COUNT(AI158:AV158)<2),"",LOOKUP(2,1/(AI158:AV158<>""),AI158:AV158)-MIN(AI158:AV158)) | IF(OR(AD158="",AC158="Not started",AC158=""),"",IFERROR(AD158-IF(VLOOKUP(AC158,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC158,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F158="","",IF(OR(AA158="Cancelled",AC158="Cancelled"),"Cancelled",IF(OR(AC158="Completed / Handover",Y158<>"",Z158>=100),"Completed — on track",IF(O158="Not awarded",IF(U158="",IF(X158="","No planned date",IF(TODAY()>X158,"Behind — past planned date",IF(X158-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U158,"Behind — award date passed",IF(U158-TODAY()<=30,"At risk — close to off track","On track"))),IF(X158="","No planned date",IF(AND(TODAY()>X158,OR(Z158="",Z158<100)),"Behind — past end date",IF(AND(T158<>"",X158<>"",Z158<>"",(Z158<100),((TODAY()-T158)/MAX(X158-T158,1)*100)-Z158>15),"Behind — progress lag",IF(AND(X158-TODAY()<=30,X158-TODAY()>=0,OR(Z158="",Z158<90)),"At risk — close to off track","On track")))))))) | IF(OR(F158="",AC158="Completed / Handover",AC158="Cancelled"),"",IF(O158="Not awarded",IF(U158<>"",U158-TODAY(),IF(X158="","",X158-TODAY())),IF(X158="","",X158-TODAY()))) | [8 empty] | 2025-11-18 | 2025-11-18 | 2026-11-17 |  |  |  | IF(OR(F158="",AJ158=""),"",IF(COUNT(AI158:AI158)=0,"",AJ158-LOOKUP(2,1/(AI158:AI158<>""),AI158:AI158))) | IF(OR(F158="",AK158=""),"",IF(COUNT(AI158:AJ158)=0,"",AK158-LOOKUP(2,1/(AI158:AJ158<>""),AI158:AJ158))) | IF(OR(F158="",AL158=""),"",IF(COUNT(AI158:AK158)=0,"",AL158-LOOKUP(2,1/(AI158:AK158<>""),AI158:AK158))) | IF(OR(F158="",AM158=""),"",IF(COUNT(AI158:AL158)=0,"",AM158-LOOKUP(2,1/(AI158:AL158<>""),AI158:AL158))) | IF(OR(F158="",AN158=""),"",IF(COUNT(AI158:AM158)=0,"",AN158-LOOKUP(2,1/(AI158:AM158<>""),AI158:AM158))) | IF(OR(F158="",AO158=""),"",IF(COUNT(AI158:AN158)=0,"",AO158-LOOKUP(2,1/(AI158:AN158<>""),AI158:AN158))) | IF(OR(F158="",AP158=""),"",IF(COUNT(AI158:AO158)=0,"",AP158-LOOKUP(2,1/(AI158:AO158<>""),AI158:AO158))) | IF(OR(F158="",AQ158=""),"",IF(COUNT(AI158:AP158)=0,"",AQ158-LOOKUP(2,1/(AI158:AP158<>""),AI158:AP158))) | IF(OR(F158="",AR158=""),"",IF(COUNT(AI158:AQ158)=0,"",AR158-LOOKUP(2,1/(AI158:AQ158<>""),AI158:AQ158))) | IF(OR(F158="",AS158=""),"",IF(COUNT(AI158:AR158)=0,"",AS158-LOOKUP(2,1/(AI158:AR158<>""),AI158:AR158))) | IF(OR(F158="",AT158=""),"",IF(COUNT(AI158:AS158)=0,"",AT158-LOOKUP(2,1/(AI158:AS158<>""),AI158:AS158))) | IF(OR(F158="",AU158=""),"",IF(COUNT(AI158:AT158)=0,"",AU158-LOOKUP(2,1/(AI158:AT158<>""),AI158:AT158))) | IF(OR(F158="",AV158=""),"",IF(COUNT(AI158:AU158)=0,"",AV158-LOOKUP(2,1/(AI158:AU158<>""),AI158:AU158))) | IF(J158="","All_Provinces",IFERROR(VLOOKUP(J158,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K158="","All_Districts",IFERROR(VLOOKUP(K158,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F159="","",ROW()-3) | AF2-IS-10 | Package #10-AF2 IS: Rehabilitation of 1.Baraki canal, 2. Darbal canal, 3. Nawikhar canal and 4. Mangali canal irrigation schemes, located in Sayed Abad, Chak and Jaghato districts of Wardak province. | 2 of 4 | AF2-IS-A-011 | Darbal canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Chak | Darbal | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Zahid Saeed Engineering and Construction Company (ZSCC) | 057/2025 | 102415.9 | IF(AQ159="","",AQ159) |  | 12 | 2026-11-17 | IF(W159<>"",W159,IF(OR(T159="",V159=""),"",EDATE(T159,V159))) |  | 0 | Awarded | partly on track, one package will need NCE and works will be completed by May/June 2027 ¦ Actual completion: Sep, 2026 | IF(F159="","",IF(COUNT(AI159:AV159)=0,IF(AA159="","Not started",AA159),SUBSTITUTE(LOOKUP(2,1/(AI159:AV159<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F159="",COUNT(AI159:AV159)=0),"",TODAY()-LOOKUP(2,1/(AI159:AV159<>""),AI159:AV159)) | IF(OR(F159="",COUNT(AI159:AV159)<2),"",LOOKUP(2,1/(AI159:AV159<>""),AI159:AV159)-MIN(AI159:AV159)) | IF(OR(AD159="",AC159="Not started",AC159=""),"",IFERROR(AD159-IF(VLOOKUP(AC159,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC159,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F159="","",IF(OR(AA159="Cancelled",AC159="Cancelled"),"Cancelled",IF(OR(AC159="Completed / Handover",Y159<>"",Z159>=100),"Completed — on track",IF(O159="Not awarded",IF(U159="",IF(X159="","No planned date",IF(TODAY()>X159,"Behind — past planned date",IF(X159-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U159,"Behind — award date passed",IF(U159-TODAY()<=30,"At risk — close to off track","On track"))),IF(X159="","No planned date",IF(AND(TODAY()>X159,OR(Z159="",Z159<100)),"Behind — past end date",IF(AND(T159<>"",X159<>"",Z159<>"",(Z159<100),((TODAY()-T159)/MAX(X159-T159,1)*100)-Z159>15),"Behind — progress lag",IF(AND(X159-TODAY()<=30,X159-TODAY()>=0,OR(Z159="",Z159<90)),"At risk — close to off track","On track")))))))) | IF(OR(F159="",AC159="Completed / Handover",AC159="Cancelled"),"",IF(O159="Not awarded",IF(U159<>"",U159-TODAY(),IF(X159="","",X159-TODAY())),IF(X159="","",X159-TODAY()))) | [8 empty] | 2025-11-18 | [5 empty] | IF(OR(F159="",AJ159=""),"",IF(COUNT(AI159:AI159)=0,"",AJ159-LOOKUP(2,1/(AI159:AI159<>""),AI159:AI159))) | IF(OR(F159="",AK159=""),"",IF(COUNT(AI159:AJ159)=0,"",AK159-LOOKUP(2,1/(AI159:AJ159<>""),AI159:AJ159))) | IF(OR(F159="",AL159=""),"",IF(COUNT(AI159:AK159)=0,"",AL159-LOOKUP(2,1/(AI159:AK159<>""),AI159:AK159))) | IF(OR(F159="",AM159=""),"",IF(COUNT(AI159:AL159)=0,"",AM159-LOOKUP(2,1/(AI159:AL159<>""),AI159:AL159))) | IF(OR(F159="",AN159=""),"",IF(COUNT(AI159:AM159)=0,"",AN159-LOOKUP(2,1/(AI159:AM159<>""),AI159:AM159))) | IF(OR(F159="",AO159=""),"",IF(COUNT(AI159:AN159)=0,"",AO159-LOOKUP(2,1/(AI159:AN159<>""),AI159:AN159))) | IF(OR(F159="",AP159=""),"",IF(COUNT(AI159:AO159)=0,"",AP159-LOOKUP(2,1/(AI159:AO159<>""),AI159:AO159))) | IF(OR(F159="",AQ159=""),"",IF(COUNT(AI159:AP159)=0,"",AQ159-LOOKUP(2,1/(AI159:AP159<>""),AI159:AP159))) | IF(OR(F159="",AR159=""),"",IF(COUNT(AI159:AQ159)=0,"",AR159-LOOKUP(2,1/(AI159:AQ159<>""),AI159:AQ159))) | IF(OR(F159="",AS159=""),"",IF(COUNT(AI159:AR159)=0,"",AS159-LOOKUP(2,1/(AI159:AR159<>""),AI159:AR159))) | IF(OR(F159="",AT159=""),"",IF(COUNT(AI159:AS159)=0,"",AT159-LOOKUP(2,1/(AI159:AS159<>""),AI159:AS159))) | IF(OR(F159="",AU159=""),"",IF(COUNT(AI159:AT159)=0,"",AU159-LOOKUP(2,1/(AI159:AT159<>""),AI159:AT159))) | IF(OR(F159="",AV159=""),"",IF(COUNT(AI159:AU159)=0,"",AV159-LOOKUP(2,1/(AI159:AU159<>""),AI159:AU159))) | IF(J159="","All_Provinces",IFERROR(VLOOKUP(J159,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K159="","All_Districts",IFERROR(VLOOKUP(K159,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F160="","",ROW()-3) | AF2-IS-10 | Package #10-AF2 IS: Rehabilitation of 1.Baraki canal, 2. Darbal canal, 3. Nawikhar canal and 4. Mangali canal irrigation schemes, located in Sayed Abad, Chak and Jaghato districts of Wardak province. | 3 of 4 | AF2-IS-A-012 | Mangali Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Jaghato | Mamal khil, Mushangai, Adena and Mangali | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Zahid Saeed Engineering and Construction Company (ZSCC) | 057/2025 | 16116.33 | IF(AQ160="","",AQ160) |  | 12 | 2026-11-17 | IF(W160<>"",W160,IF(OR(T160="",V160=""),"",EDATE(T160,V160))) |  | 0 | Awarded | partly on track, one package will need NCE and works will be completed by May/June 2027 ¦ Actual completion: Sep, 2026 | IF(F160="","",IF(COUNT(AI160:AV160)=0,IF(AA160="","Not started",AA160),SUBSTITUTE(LOOKUP(2,1/(AI160:AV160<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F160="",COUNT(AI160:AV160)=0),"",TODAY()-LOOKUP(2,1/(AI160:AV160<>""),AI160:AV160)) | IF(OR(F160="",COUNT(AI160:AV160)<2),"",LOOKUP(2,1/(AI160:AV160<>""),AI160:AV160)-MIN(AI160:AV160)) | IF(OR(AD160="",AC160="Not started",AC160=""),"",IFERROR(AD160-IF(VLOOKUP(AC160,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC160,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F160="","",IF(OR(AA160="Cancelled",AC160="Cancelled"),"Cancelled",IF(OR(AC160="Completed / Handover",Y160<>"",Z160>=100),"Completed — on track",IF(O160="Not awarded",IF(U160="",IF(X160="","No planned date",IF(TODAY()>X160,"Behind — past planned date",IF(X160-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U160,"Behind — award date passed",IF(U160-TODAY()<=30,"At risk — close to off track","On track"))),IF(X160="","No planned date",IF(AND(TODAY()>X160,OR(Z160="",Z160<100)),"Behind — past end date",IF(AND(T160<>"",X160<>"",Z160<>"",(Z160<100),((TODAY()-T160)/MAX(X160-T160,1)*100)-Z160>15),"Behind — progress lag",IF(AND(X160-TODAY()<=30,X160-TODAY()>=0,OR(Z160="",Z160<90)),"At risk — close to off track","On track")))))))) | IF(OR(F160="",AC160="Completed / Handover",AC160="Cancelled"),"",IF(O160="Not awarded",IF(U160<>"",U160-TODAY(),IF(X160="","",X160-TODAY())),IF(X160="","",X160-TODAY()))) | [8 empty] | 2025-11-18 | [5 empty] | IF(OR(F160="",AJ160=""),"",IF(COUNT(AI160:AI160)=0,"",AJ160-LOOKUP(2,1/(AI160:AI160<>""),AI160:AI160))) | IF(OR(F160="",AK160=""),"",IF(COUNT(AI160:AJ160)=0,"",AK160-LOOKUP(2,1/(AI160:AJ160<>""),AI160:AJ160))) | IF(OR(F160="",AL160=""),"",IF(COUNT(AI160:AK160)=0,"",AL160-LOOKUP(2,1/(AI160:AK160<>""),AI160:AK160))) | IF(OR(F160="",AM160=""),"",IF(COUNT(AI160:AL160)=0,"",AM160-LOOKUP(2,1/(AI160:AL160<>""),AI160:AL160))) | IF(OR(F160="",AN160=""),"",IF(COUNT(AI160:AM160)=0,"",AN160-LOOKUP(2,1/(AI160:AM160<>""),AI160:AM160))) | IF(OR(F160="",AO160=""),"",IF(COUNT(AI160:AN160)=0,"",AO160-LOOKUP(2,1/(AI160:AN160<>""),AI160:AN160))) | IF(OR(F160="",AP160=""),"",IF(COUNT(AI160:AO160)=0,"",AP160-LOOKUP(2,1/(AI160:AO160<>""),AI160:AO160))) | IF(OR(F160="",AQ160=""),"",IF(COUNT(AI160:AP160)=0,"",AQ160-LOOKUP(2,1/(AI160:AP160<>""),AI160:AP160))) | IF(OR(F160="",AR160=""),"",IF(COUNT(AI160:AQ160)=0,"",AR160-LOOKUP(2,1/(AI160:AQ160<>""),AI160:AQ160))) | IF(OR(F160="",AS160=""),"",IF(COUNT(AI160:AR160)=0,"",AS160-LOOKUP(2,1/(AI160:AR160<>""),AI160:AR160))) | IF(OR(F160="",AT160=""),"",IF(COUNT(AI160:AS160)=0,"",AT160-LOOKUP(2,1/(AI160:AS160<>""),AI160:AS160))) | IF(OR(F160="",AU160=""),"",IF(COUNT(AI160:AT160)=0,"",AU160-LOOKUP(2,1/(AI160:AT160<>""),AI160:AT160))) | IF(OR(F160="",AV160=""),"",IF(COUNT(AI160:AU160)=0,"",AV160-LOOKUP(2,1/(AI160:AU160<>""),AI160:AU160))) | IF(J160="","All_Provinces",IFERROR(VLOOKUP(J160,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K160="","All_Districts",IFERROR(VLOOKUP(K160,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F161="","",ROW()-3) | AF2-IS-10 | Package #10-AF2 IS: Rehabilitation of 1.Baraki canal, 2. Darbal canal, 3. Nawikhar canal and 4. Mangali canal irrigation schemes, located in Sayed Abad, Chak and Jaghato districts of Wardak province. | 4 of 4 | AF2-IS-A-013 | Nawikhar canal irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Wardak | Jaghato | Nawikhar | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Zahid Saeed Engineering and Construction Company (ZSCC) | 057/2025 | 77263.89 | IF(AQ161="","",AQ161) |  | 12 | 2026-11-17 | IF(W161<>"",W161,IF(OR(T161="",V161=""),"",EDATE(T161,V161))) |  | 20 | Under Construction | partly on track, one package will need NCE and works will be completed by May/June 2027 ¦ Actual completion: Sep, 2026 | IF(F161="","",IF(COUNT(AI161:AV161)=0,IF(AA161="","Not started",AA161),SUBSTITUTE(LOOKUP(2,1/(AI161:AV161<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F161="",COUNT(AI161:AV161)=0),"",TODAY()-LOOKUP(2,1/(AI161:AV161<>""),AI161:AV161)) | IF(OR(F161="",COUNT(AI161:AV161)<2),"",LOOKUP(2,1/(AI161:AV161<>""),AI161:AV161)-MIN(AI161:AV161)) | IF(OR(AD161="",AC161="Not started",AC161=""),"",IFERROR(AD161-IF(VLOOKUP(AC161,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC161,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F161="","",IF(OR(AA161="Cancelled",AC161="Cancelled"),"Cancelled",IF(OR(AC161="Completed / Handover",Y161<>"",Z161>=100),"Completed — on track",IF(O161="Not awarded",IF(U161="",IF(X161="","No planned date",IF(TODAY()>X161,"Behind — past planned date",IF(X161-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U161,"Behind — award date passed",IF(U161-TODAY()<=30,"At risk — close to off track","On track"))),IF(X161="","No planned date",IF(AND(TODAY()>X161,OR(Z161="",Z161<100)),"Behind — past end date",IF(AND(T161<>"",X161<>"",Z161<>"",(Z161<100),((TODAY()-T161)/MAX(X161-T161,1)*100)-Z161>15),"Behind — progress lag",IF(AND(X161-TODAY()<=30,X161-TODAY()>=0,OR(Z161="",Z161<90)),"At risk — close to off track","On track")))))))) | IF(OR(F161="",AC161="Completed / Handover",AC161="Cancelled"),"",IF(O161="Not awarded",IF(U161<>"",U161-TODAY(),IF(X161="","",X161-TODAY())),IF(X161="","",X161-TODAY()))) | [8 empty] | 2025-11-18 | 2025-11-18 |  |  |  |  | IF(OR(F161="",AJ161=""),"",IF(COUNT(AI161:AI161)=0,"",AJ161-LOOKUP(2,1/(AI161:AI161<>""),AI161:AI161))) | IF(OR(F161="",AK161=""),"",IF(COUNT(AI161:AJ161)=0,"",AK161-LOOKUP(2,1/(AI161:AJ161<>""),AI161:AJ161))) | IF(OR(F161="",AL161=""),"",IF(COUNT(AI161:AK161)=0,"",AL161-LOOKUP(2,1/(AI161:AK161<>""),AI161:AK161))) | IF(OR(F161="",AM161=""),"",IF(COUNT(AI161:AL161)=0,"",AM161-LOOKUP(2,1/(AI161:AL161<>""),AI161:AL161))) | IF(OR(F161="",AN161=""),"",IF(COUNT(AI161:AM161)=0,"",AN161-LOOKUP(2,1/(AI161:AM161<>""),AI161:AM161))) | IF(OR(F161="",AO161=""),"",IF(COUNT(AI161:AN161)=0,"",AO161-LOOKUP(2,1/(AI161:AN161<>""),AI161:AN161))) | IF(OR(F161="",AP161=""),"",IF(COUNT(AI161:AO161)=0,"",AP161-LOOKUP(2,1/(AI161:AO161<>""),AI161:AO161))) | IF(OR(F161="",AQ161=""),"",IF(COUNT(AI161:AP161)=0,"",AQ161-LOOKUP(2,1/(AI161:AP161<>""),AI161:AP161))) | IF(OR(F161="",AR161=""),"",IF(COUNT(AI161:AQ161)=0,"",AR161-LOOKUP(2,1/(AI161:AQ161<>""),AI161:AQ161))) | IF(OR(F161="",AS161=""),"",IF(COUNT(AI161:AR161)=0,"",AS161-LOOKUP(2,1/(AI161:AR161<>""),AI161:AR161))) | IF(OR(F161="",AT161=""),"",IF(COUNT(AI161:AS161)=0,"",AT161-LOOKUP(2,1/(AI161:AS161<>""),AI161:AS161))) | IF(OR(F161="",AU161=""),"",IF(COUNT(AI161:AT161)=0,"",AU161-LOOKUP(2,1/(AI161:AT161<>""),AI161:AT161))) | IF(OR(F161="",AV161=""),"",IF(COUNT(AI161:AU161)=0,"",AV161-LOOKUP(2,1/(AI161:AU161<>""),AI161:AU161))) | IF(J161="","All_Provinces",IFERROR(VLOOKUP(J161,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K161="","All_Districts",IFERROR(VLOOKUP(K161,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F162="","",ROW()-3) | AF2-IS-11 | Package #11-AF2 IS: Rehabilitation of Musahi Sufla canal irrigation schemes, located in Musahi districts of Kabul province. | 1 of 1 | AF2-IS-A-014 | Musahi Sufla Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Musahi | Musahi Sufla | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Seddiq Amini Construction and Logistic Services (SACC) | 056/2025 | 196473.81 | IF(AQ162="","",AQ162) |  | 12 | 2026-10-26 | IF(W162<>"",W162,IF(OR(T162="",V162=""),"",EDATE(T162,V162))) |  | 98 | Under Construction | on track and will be completed in Oct. 2026 | IF(F162="","",IF(COUNT(AI162:AV162)=0,IF(AA162="","Not started",AA162),SUBSTITUTE(LOOKUP(2,1/(AI162:AV162<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F162="",COUNT(AI162:AV162)=0),"",TODAY()-LOOKUP(2,1/(AI162:AV162<>""),AI162:AV162)) | IF(OR(F162="",COUNT(AI162:AV162)<2),"",LOOKUP(2,1/(AI162:AV162<>""),AI162:AV162)-MIN(AI162:AV162)) | IF(OR(AD162="",AC162="Not started",AC162=""),"",IFERROR(AD162-IF(VLOOKUP(AC162,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC162,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F162="","",IF(OR(AA162="Cancelled",AC162="Cancelled"),"Cancelled",IF(OR(AC162="Completed / Handover",Y162<>"",Z162>=100),"Completed — on track",IF(O162="Not awarded",IF(U162="",IF(X162="","No planned date",IF(TODAY()>X162,"Behind — past planned date",IF(X162-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U162,"Behind — award date passed",IF(U162-TODAY()<=30,"At risk — close to off track","On track"))),IF(X162="","No planned date",IF(AND(TODAY()>X162,OR(Z162="",Z162<100)),"Behind — past end date",IF(AND(T162<>"",X162<>"",Z162<>"",(Z162<100),((TODAY()-T162)/MAX(X162-T162,1)*100)-Z162>15),"Behind — progress lag",IF(AND(X162-TODAY()<=30,X162-TODAY()>=0,OR(Z162="",Z162<90)),"At risk — close to off track","On track")))))))) | IF(OR(F162="",AC162="Completed / Handover",AC162="Cancelled"),"",IF(O162="Not awarded",IF(U162<>"",U162-TODAY(),IF(X162="","",X162-TODAY())),IF(X162="","",X162-TODAY()))) | [8 empty] | 2025-10-27 | 2025-10-27 |  |  |  |  | IF(OR(F162="",AJ162=""),"",IF(COUNT(AI162:AI162)=0,"",AJ162-LOOKUP(2,1/(AI162:AI162<>""),AI162:AI162))) | IF(OR(F162="",AK162=""),"",IF(COUNT(AI162:AJ162)=0,"",AK162-LOOKUP(2,1/(AI162:AJ162<>""),AI162:AJ162))) | IF(OR(F162="",AL162=""),"",IF(COUNT(AI162:AK162)=0,"",AL162-LOOKUP(2,1/(AI162:AK162<>""),AI162:AK162))) | IF(OR(F162="",AM162=""),"",IF(COUNT(AI162:AL162)=0,"",AM162-LOOKUP(2,1/(AI162:AL162<>""),AI162:AL162))) | IF(OR(F162="",AN162=""),"",IF(COUNT(AI162:AM162)=0,"",AN162-LOOKUP(2,1/(AI162:AM162<>""),AI162:AM162))) | IF(OR(F162="",AO162=""),"",IF(COUNT(AI162:AN162)=0,"",AO162-LOOKUP(2,1/(AI162:AN162<>""),AI162:AN162))) | IF(OR(F162="",AP162=""),"",IF(COUNT(AI162:AO162)=0,"",AP162-LOOKUP(2,1/(AI162:AO162<>""),AI162:AO162))) | IF(OR(F162="",AQ162=""),"",IF(COUNT(AI162:AP162)=0,"",AQ162-LOOKUP(2,1/(AI162:AP162<>""),AI162:AP162))) | IF(OR(F162="",AR162=""),"",IF(COUNT(AI162:AQ162)=0,"",AR162-LOOKUP(2,1/(AI162:AQ162<>""),AI162:AQ162))) | IF(OR(F162="",AS162=""),"",IF(COUNT(AI162:AR162)=0,"",AS162-LOOKUP(2,1/(AI162:AR162<>""),AI162:AR162))) | IF(OR(F162="",AT162=""),"",IF(COUNT(AI162:AS162)=0,"",AT162-LOOKUP(2,1/(AI162:AS162<>""),AI162:AS162))) | IF(OR(F162="",AU162=""),"",IF(COUNT(AI162:AT162)=0,"",AU162-LOOKUP(2,1/(AI162:AT162<>""),AI162:AT162))) | IF(OR(F162="",AV162=""),"",IF(COUNT(AI162:AU162)=0,"",AV162-LOOKUP(2,1/(AI162:AU162<>""),AI162:AU162))) | IF(J162="","All_Provinces",IFERROR(VLOOKUP(J162,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K162="","All_Districts",IFERROR(VLOOKUP(K162,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F163="","",ROW()-3) | AF2-IS-12 | Package #12-AF2 IS: Rehabilitation of Tapa-e-Ahmad Big canal and Shahre Beland canal irrigation schemes, located in Nijrab and Paryan districts of Kapisa and Panjsher provinces. | 1 of 2 | AF2-IS-N-007 | Shahre Beland Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Panjshir | Paryan | Shahre Beland | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 191270 | IF(AQ163="","",AQ163) | 2026-11-01 | 8.9 | 2027-07-29 | IF(W163<>"",W163,IF(OR(T163="",V163=""),"",EDATE(T163,V163))) |  |  | Under Technical Evaluation | Four months slack period Dec-Mar during winter. Five months construction period required for two canals | IF(F163="","",IF(COUNT(AI163:AV163)=0,IF(AA163="","Not started",AA163),SUBSTITUTE(LOOKUP(2,1/(AI163:AV163<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F163="",COUNT(AI163:AV163)=0),"",TODAY()-LOOKUP(2,1/(AI163:AV163<>""),AI163:AV163)) | IF(OR(F163="",COUNT(AI163:AV163)<2),"",LOOKUP(2,1/(AI163:AV163<>""),AI163:AV163)-MIN(AI163:AV163)) | IF(OR(AD163="",AC163="Not started",AC163=""),"",IFERROR(AD163-IF(VLOOKUP(AC163,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC163,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F163="","",IF(OR(AA163="Cancelled",AC163="Cancelled"),"Cancelled",IF(OR(AC163="Completed / Handover",Y163<>"",Z163>=100),"Completed — on track",IF(O163="Not awarded",IF(U163="",IF(X163="","No planned date",IF(TODAY()>X163,"Behind — past planned date",IF(X163-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U163,"Behind — award date passed",IF(U163-TODAY()<=30,"At risk — close to off track","On track"))),IF(X163="","No planned date",IF(AND(TODAY()>X163,OR(Z163="",Z163<100)),"Behind — past end date",IF(AND(T163<>"",X163<>"",Z163<>"",(Z163<100),((TODAY()-T163)/MAX(X163-T163,1)*100)-Z163>15),"Behind — progress lag",IF(AND(X163-TODAY()<=30,X163-TODAY()>=0,OR(Z163="",Z163<90)),"At risk — close to off track","On track")))))))) | IF(OR(F163="",AC163="Completed / Handover",AC163="Cancelled"),"",IF(O163="Not awarded",IF(U163<>"",U163-TODAY(),IF(X163="","",X163-TODAY())),IF(X163="","",X163-TODAY()))) | [14 empty] | IF(OR(F163="",AJ163=""),"",IF(COUNT(AI163:AI163)=0,"",AJ163-LOOKUP(2,1/(AI163:AI163<>""),AI163:AI163))) | IF(OR(F163="",AK163=""),"",IF(COUNT(AI163:AJ163)=0,"",AK163-LOOKUP(2,1/(AI163:AJ163<>""),AI163:AJ163))) | IF(OR(F163="",AL163=""),"",IF(COUNT(AI163:AK163)=0,"",AL163-LOOKUP(2,1/(AI163:AK163<>""),AI163:AK163))) | IF(OR(F163="",AM163=""),"",IF(COUNT(AI163:AL163)=0,"",AM163-LOOKUP(2,1/(AI163:AL163<>""),AI163:AL163))) | IF(OR(F163="",AN163=""),"",IF(COUNT(AI163:AM163)=0,"",AN163-LOOKUP(2,1/(AI163:AM163<>""),AI163:AM163))) | IF(OR(F163="",AO163=""),"",IF(COUNT(AI163:AN163)=0,"",AO163-LOOKUP(2,1/(AI163:AN163<>""),AI163:AN163))) | IF(OR(F163="",AP163=""),"",IF(COUNT(AI163:AO163)=0,"",AP163-LOOKUP(2,1/(AI163:AO163<>""),AI163:AO163))) | IF(OR(F163="",AQ163=""),"",IF(COUNT(AI163:AP163)=0,"",AQ163-LOOKUP(2,1/(AI163:AP163<>""),AI163:AP163))) | IF(OR(F163="",AR163=""),"",IF(COUNT(AI163:AQ163)=0,"",AR163-LOOKUP(2,1/(AI163:AQ163<>""),AI163:AQ163))) | IF(OR(F163="",AS163=""),"",IF(COUNT(AI163:AR163)=0,"",AS163-LOOKUP(2,1/(AI163:AR163<>""),AI163:AR163))) | IF(OR(F163="",AT163=""),"",IF(COUNT(AI163:AS163)=0,"",AT163-LOOKUP(2,1/(AI163:AS163<>""),AI163:AS163))) | IF(OR(F163="",AU163=""),"",IF(COUNT(AI163:AT163)=0,"",AU163-LOOKUP(2,1/(AI163:AT163<>""),AI163:AT163))) | IF(OR(F163="",AV163=""),"",IF(COUNT(AI163:AU163)=0,"",AV163-LOOKUP(2,1/(AI163:AU163<>""),AI163:AU163))) | IF(J163="","All_Provinces",IFERROR(VLOOKUP(J163,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K163="","All_Districts",IFERROR(VLOOKUP(K163,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F164="","",ROW()-3) | AF2-IS-12 | Package #12-AF2 IS: Rehabilitation of Tapa-e-Ahmad Big canal and Shahre Beland canal irrigation schemes, located in Nijrab and Paryan districts of Kapisa and Panjsher provinces. | 2 of 2 | AF2-IS-N-008 | Tapa e- Ahmad Big Canal | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Nijrab | Tapa e Ahmad Big, Shahre Naw | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 191270 | IF(AQ164="","",AQ164) | 2026-11-01 | 8.9 | 2027-07-29 | IF(W164<>"",W164,IF(OR(T164="",V164=""),"",EDATE(T164,V164))) |  |  | Under Technical Evaluation | Four months slack period Dec-Mar during winter. Five months construction period required for two canals | IF(F164="","",IF(COUNT(AI164:AV164)=0,IF(AA164="","Not started",AA164),SUBSTITUTE(LOOKUP(2,1/(AI164:AV164<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F164="",COUNT(AI164:AV164)=0),"",TODAY()-LOOKUP(2,1/(AI164:AV164<>""),AI164:AV164)) | IF(OR(F164="",COUNT(AI164:AV164)<2),"",LOOKUP(2,1/(AI164:AV164<>""),AI164:AV164)-MIN(AI164:AV164)) | IF(OR(AD164="",AC164="Not started",AC164=""),"",IFERROR(AD164-IF(VLOOKUP(AC164,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC164,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F164="","",IF(OR(AA164="Cancelled",AC164="Cancelled"),"Cancelled",IF(OR(AC164="Completed / Handover",Y164<>"",Z164>=100),"Completed — on track",IF(O164="Not awarded",IF(U164="",IF(X164="","No planned date",IF(TODAY()>X164,"Behind — past planned date",IF(X164-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U164,"Behind — award date passed",IF(U164-TODAY()<=30,"At risk — close to off track","On track"))),IF(X164="","No planned date",IF(AND(TODAY()>X164,OR(Z164="",Z164<100)),"Behind — past end date",IF(AND(T164<>"",X164<>"",Z164<>"",(Z164<100),((TODAY()-T164)/MAX(X164-T164,1)*100)-Z164>15),"Behind — progress lag",IF(AND(X164-TODAY()<=30,X164-TODAY()>=0,OR(Z164="",Z164<90)),"At risk — close to off track","On track")))))))) | IF(OR(F164="",AC164="Completed / Handover",AC164="Cancelled"),"",IF(O164="Not awarded",IF(U164<>"",U164-TODAY(),IF(X164="","",X164-TODAY())),IF(X164="","",X164-TODAY()))) | [14 empty] | IF(OR(F164="",AJ164=""),"",IF(COUNT(AI164:AI164)=0,"",AJ164-LOOKUP(2,1/(AI164:AI164<>""),AI164:AI164))) | IF(OR(F164="",AK164=""),"",IF(COUNT(AI164:AJ164)=0,"",AK164-LOOKUP(2,1/(AI164:AJ164<>""),AI164:AJ164))) | IF(OR(F164="",AL164=""),"",IF(COUNT(AI164:AK164)=0,"",AL164-LOOKUP(2,1/(AI164:AK164<>""),AI164:AK164))) | IF(OR(F164="",AM164=""),"",IF(COUNT(AI164:AL164)=0,"",AM164-LOOKUP(2,1/(AI164:AL164<>""),AI164:AL164))) | IF(OR(F164="",AN164=""),"",IF(COUNT(AI164:AM164)=0,"",AN164-LOOKUP(2,1/(AI164:AM164<>""),AI164:AM164))) | IF(OR(F164="",AO164=""),"",IF(COUNT(AI164:AN164)=0,"",AO164-LOOKUP(2,1/(AI164:AN164<>""),AI164:AN164))) | IF(OR(F164="",AP164=""),"",IF(COUNT(AI164:AO164)=0,"",AP164-LOOKUP(2,1/(AI164:AO164<>""),AI164:AO164))) | IF(OR(F164="",AQ164=""),"",IF(COUNT(AI164:AP164)=0,"",AQ164-LOOKUP(2,1/(AI164:AP164<>""),AI164:AP164))) | IF(OR(F164="",AR164=""),"",IF(COUNT(AI164:AQ164)=0,"",AR164-LOOKUP(2,1/(AI164:AQ164<>""),AI164:AQ164))) | IF(OR(F164="",AS164=""),"",IF(COUNT(AI164:AR164)=0,"",AS164-LOOKUP(2,1/(AI164:AR164<>""),AI164:AR164))) | IF(OR(F164="",AT164=""),"",IF(COUNT(AI164:AS164)=0,"",AT164-LOOKUP(2,1/(AI164:AS164<>""),AI164:AS164))) | IF(OR(F164="",AU164=""),"",IF(COUNT(AI164:AT164)=0,"",AU164-LOOKUP(2,1/(AI164:AT164<>""),AI164:AT164))) | IF(OR(F164="",AV164=""),"",IF(COUNT(AI164:AU164)=0,"",AV164-LOOKUP(2,1/(AI164:AU164<>""),AI164:AU164))) | IF(J164="","All_Provinces",IFERROR(VLOOKUP(J164,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K164="","All_Districts",IFERROR(VLOOKUP(K164,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F165="","",ROW()-3) | AF2-IS-13 | Package #13-AF2 IS: Rehabilitation of Kamar China canal, Khenkot canal, and Zargara irrigation schemes, located in Sarobi, Chahar Asiab and Paghman districts of Kabul province. | 1 of 3 | AF2-IS-N-009 | Kamar China Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Sarobi | Warkhralah | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 290000 | IF(AQ165="","",AQ165) | 2026-11-10 | 7.9 | 2027-07-08 | IF(W165<>"",W165,IF(OR(T165="",V165=""),"",EDATE(T165,V165))) |  |  | Under Technical Evaluation | Three months slack period Jan-Mar during winter. Five months construction period required for three canals | IF(F165="","",IF(COUNT(AI165:AV165)=0,IF(AA165="","Not started",AA165),SUBSTITUTE(LOOKUP(2,1/(AI165:AV165<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F165="",COUNT(AI165:AV165)=0),"",TODAY()-LOOKUP(2,1/(AI165:AV165<>""),AI165:AV165)) | IF(OR(F165="",COUNT(AI165:AV165)<2),"",LOOKUP(2,1/(AI165:AV165<>""),AI165:AV165)-MIN(AI165:AV165)) | IF(OR(AD165="",AC165="Not started",AC165=""),"",IFERROR(AD165-IF(VLOOKUP(AC165,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC165,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F165="","",IF(OR(AA165="Cancelled",AC165="Cancelled"),"Cancelled",IF(OR(AC165="Completed / Handover",Y165<>"",Z165>=100),"Completed — on track",IF(O165="Not awarded",IF(U165="",IF(X165="","No planned date",IF(TODAY()>X165,"Behind — past planned date",IF(X165-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U165,"Behind — award date passed",IF(U165-TODAY()<=30,"At risk — close to off track","On track"))),IF(X165="","No planned date",IF(AND(TODAY()>X165,OR(Z165="",Z165<100)),"Behind — past end date",IF(AND(T165<>"",X165<>"",Z165<>"",(Z165<100),((TODAY()-T165)/MAX(X165-T165,1)*100)-Z165>15),"Behind — progress lag",IF(AND(X165-TODAY()<=30,X165-TODAY()>=0,OR(Z165="",Z165<90)),"At risk — close to off track","On track")))))))) | IF(OR(F165="",AC165="Completed / Handover",AC165="Cancelled"),"",IF(O165="Not awarded",IF(U165<>"",U165-TODAY(),IF(X165="","",X165-TODAY())),IF(X165="","",X165-TODAY()))) | [14 empty] | IF(OR(F165="",AJ165=""),"",IF(COUNT(AI165:AI165)=0,"",AJ165-LOOKUP(2,1/(AI165:AI165<>""),AI165:AI165))) | IF(OR(F165="",AK165=""),"",IF(COUNT(AI165:AJ165)=0,"",AK165-LOOKUP(2,1/(AI165:AJ165<>""),AI165:AJ165))) | IF(OR(F165="",AL165=""),"",IF(COUNT(AI165:AK165)=0,"",AL165-LOOKUP(2,1/(AI165:AK165<>""),AI165:AK165))) | IF(OR(F165="",AM165=""),"",IF(COUNT(AI165:AL165)=0,"",AM165-LOOKUP(2,1/(AI165:AL165<>""),AI165:AL165))) | IF(OR(F165="",AN165=""),"",IF(COUNT(AI165:AM165)=0,"",AN165-LOOKUP(2,1/(AI165:AM165<>""),AI165:AM165))) | IF(OR(F165="",AO165=""),"",IF(COUNT(AI165:AN165)=0,"",AO165-LOOKUP(2,1/(AI165:AN165<>""),AI165:AN165))) | IF(OR(F165="",AP165=""),"",IF(COUNT(AI165:AO165)=0,"",AP165-LOOKUP(2,1/(AI165:AO165<>""),AI165:AO165))) | IF(OR(F165="",AQ165=""),"",IF(COUNT(AI165:AP165)=0,"",AQ165-LOOKUP(2,1/(AI165:AP165<>""),AI165:AP165))) | IF(OR(F165="",AR165=""),"",IF(COUNT(AI165:AQ165)=0,"",AR165-LOOKUP(2,1/(AI165:AQ165<>""),AI165:AQ165))) | IF(OR(F165="",AS165=""),"",IF(COUNT(AI165:AR165)=0,"",AS165-LOOKUP(2,1/(AI165:AR165<>""),AI165:AR165))) | IF(OR(F165="",AT165=""),"",IF(COUNT(AI165:AS165)=0,"",AT165-LOOKUP(2,1/(AI165:AS165<>""),AI165:AS165))) | IF(OR(F165="",AU165=""),"",IF(COUNT(AI165:AT165)=0,"",AU165-LOOKUP(2,1/(AI165:AT165<>""),AI165:AT165))) | IF(OR(F165="",AV165=""),"",IF(COUNT(AI165:AU165)=0,"",AV165-LOOKUP(2,1/(AI165:AU165<>""),AI165:AU165))) | IF(J165="","All_Provinces",IFERROR(VLOOKUP(J165,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K165="","All_Districts",IFERROR(VLOOKUP(K165,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F166="","",ROW()-3) | AF2-IS-13 | Package #13-AF2 IS: Rehabilitation of Kamar China canal, Khenkot canal, and Zargara irrigation schemes, located in Sarobi, Chahar Asiab and Paghman districts of Kabul province. | 2 of 3 | AF2-IS-N-010 | Khenkot irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul |  | Chahar Asiab | Shah Toot | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 290000 | IF(AQ166="","",AQ166) | 2026-11-10 | 7.9 | 2027-07-08 | IF(W166<>"",W166,IF(OR(T166="",V166=""),"",EDATE(T166,V166))) |  |  | Under Technical Evaluation | Three months slack period Jan-Mar during winter. Five months construction period required for three canals | IF(F166="","",IF(COUNT(AI166:AV166)=0,IF(AA166="","Not started",AA166),SUBSTITUTE(LOOKUP(2,1/(AI166:AV166<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F166="",COUNT(AI166:AV166)=0),"",TODAY()-LOOKUP(2,1/(AI166:AV166<>""),AI166:AV166)) | IF(OR(F166="",COUNT(AI166:AV166)<2),"",LOOKUP(2,1/(AI166:AV166<>""),AI166:AV166)-MIN(AI166:AV166)) | IF(OR(AD166="",AC166="Not started",AC166=""),"",IFERROR(AD166-IF(VLOOKUP(AC166,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC166,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F166="","",IF(OR(AA166="Cancelled",AC166="Cancelled"),"Cancelled",IF(OR(AC166="Completed / Handover",Y166<>"",Z166>=100),"Completed — on track",IF(O166="Not awarded",IF(U166="",IF(X166="","No planned date",IF(TODAY()>X166,"Behind — past planned date",IF(X166-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U166,"Behind — award date passed",IF(U166-TODAY()<=30,"At risk — close to off track","On track"))),IF(X166="","No planned date",IF(AND(TODAY()>X166,OR(Z166="",Z166<100)),"Behind — past end date",IF(AND(T166<>"",X166<>"",Z166<>"",(Z166<100),((TODAY()-T166)/MAX(X166-T166,1)*100)-Z166>15),"Behind — progress lag",IF(AND(X166-TODAY()<=30,X166-TODAY()>=0,OR(Z166="",Z166<90)),"At risk — close to off track","On track")))))))) | IF(OR(F166="",AC166="Completed / Handover",AC166="Cancelled"),"",IF(O166="Not awarded",IF(U166<>"",U166-TODAY(),IF(X166="","",X166-TODAY())),IF(X166="","",X166-TODAY()))) | [14 empty] | IF(OR(F166="",AJ166=""),"",IF(COUNT(AI166:AI166)=0,"",AJ166-LOOKUP(2,1/(AI166:AI166<>""),AI166:AI166))) | IF(OR(F166="",AK166=""),"",IF(COUNT(AI166:AJ166)=0,"",AK166-LOOKUP(2,1/(AI166:AJ166<>""),AI166:AJ166))) | IF(OR(F166="",AL166=""),"",IF(COUNT(AI166:AK166)=0,"",AL166-LOOKUP(2,1/(AI166:AK166<>""),AI166:AK166))) | IF(OR(F166="",AM166=""),"",IF(COUNT(AI166:AL166)=0,"",AM166-LOOKUP(2,1/(AI166:AL166<>""),AI166:AL166))) | IF(OR(F166="",AN166=""),"",IF(COUNT(AI166:AM166)=0,"",AN166-LOOKUP(2,1/(AI166:AM166<>""),AI166:AM166))) | IF(OR(F166="",AO166=""),"",IF(COUNT(AI166:AN166)=0,"",AO166-LOOKUP(2,1/(AI166:AN166<>""),AI166:AN166))) | IF(OR(F166="",AP166=""),"",IF(COUNT(AI166:AO166)=0,"",AP166-LOOKUP(2,1/(AI166:AO166<>""),AI166:AO166))) | IF(OR(F166="",AQ166=""),"",IF(COUNT(AI166:AP166)=0,"",AQ166-LOOKUP(2,1/(AI166:AP166<>""),AI166:AP166))) | IF(OR(F166="",AR166=""),"",IF(COUNT(AI166:AQ166)=0,"",AR166-LOOKUP(2,1/(AI166:AQ166<>""),AI166:AQ166))) | IF(OR(F166="",AS166=""),"",IF(COUNT(AI166:AR166)=0,"",AS166-LOOKUP(2,1/(AI166:AR166<>""),AI166:AR166))) | IF(OR(F166="",AT166=""),"",IF(COUNT(AI166:AS166)=0,"",AT166-LOOKUP(2,1/(AI166:AS166<>""),AI166:AS166))) | IF(OR(F166="",AU166=""),"",IF(COUNT(AI166:AT166)=0,"",AU166-LOOKUP(2,1/(AI166:AT166<>""),AI166:AT166))) | IF(OR(F166="",AV166=""),"",IF(COUNT(AI166:AU166)=0,"",AV166-LOOKUP(2,1/(AI166:AU166<>""),AI166:AU166))) | IF(J166="","All_Provinces",IFERROR(VLOOKUP(J166,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K166="","All_Districts",IFERROR(VLOOKUP(K166,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F167="","",ROW()-3) | AF2-IS-13 | Package #13-AF2 IS: Rehabilitation of Kamar China canal, Khenkot canal, and Zargara irrigation schemes, located in Sarobi, Chahar Asiab and Paghman districts of Kabul province. | 3 of 3 | AF2-IS-N-011 | Zargara canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul |  | Paghman | Qla-e- Hakeem, Somochak and Ala Bala | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 290000 | IF(AQ167="","",AQ167) | 2026-11-10 | 7.9 | 2027-07-08 | IF(W167<>"",W167,IF(OR(T167="",V167=""),"",EDATE(T167,V167))) |  |  | Under Technical Evaluation | Three months slack period Jan-Mar during winter. Five months construction period required for three canals | IF(F167="","",IF(COUNT(AI167:AV167)=0,IF(AA167="","Not started",AA167),SUBSTITUTE(LOOKUP(2,1/(AI167:AV167<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F167="",COUNT(AI167:AV167)=0),"",TODAY()-LOOKUP(2,1/(AI167:AV167<>""),AI167:AV167)) | IF(OR(F167="",COUNT(AI167:AV167)<2),"",LOOKUP(2,1/(AI167:AV167<>""),AI167:AV167)-MIN(AI167:AV167)) | IF(OR(AD167="",AC167="Not started",AC167=""),"",IFERROR(AD167-IF(VLOOKUP(AC167,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC167,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F167="","",IF(OR(AA167="Cancelled",AC167="Cancelled"),"Cancelled",IF(OR(AC167="Completed / Handover",Y167<>"",Z167>=100),"Completed — on track",IF(O167="Not awarded",IF(U167="",IF(X167="","No planned date",IF(TODAY()>X167,"Behind — past planned date",IF(X167-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U167,"Behind — award date passed",IF(U167-TODAY()<=30,"At risk — close to off track","On track"))),IF(X167="","No planned date",IF(AND(TODAY()>X167,OR(Z167="",Z167<100)),"Behind — past end date",IF(AND(T167<>"",X167<>"",Z167<>"",(Z167<100),((TODAY()-T167)/MAX(X167-T167,1)*100)-Z167>15),"Behind — progress lag",IF(AND(X167-TODAY()<=30,X167-TODAY()>=0,OR(Z167="",Z167<90)),"At risk — close to off track","On track")))))))) | IF(OR(F167="",AC167="Completed / Handover",AC167="Cancelled"),"",IF(O167="Not awarded",IF(U167<>"",U167-TODAY(),IF(X167="","",X167-TODAY())),IF(X167="","",X167-TODAY()))) | [14 empty] | IF(OR(F167="",AJ167=""),"",IF(COUNT(AI167:AI167)=0,"",AJ167-LOOKUP(2,1/(AI167:AI167<>""),AI167:AI167))) | IF(OR(F167="",AK167=""),"",IF(COUNT(AI167:AJ167)=0,"",AK167-LOOKUP(2,1/(AI167:AJ167<>""),AI167:AJ167))) | IF(OR(F167="",AL167=""),"",IF(COUNT(AI167:AK167)=0,"",AL167-LOOKUP(2,1/(AI167:AK167<>""),AI167:AK167))) | IF(OR(F167="",AM167=""),"",IF(COUNT(AI167:AL167)=0,"",AM167-LOOKUP(2,1/(AI167:AL167<>""),AI167:AL167))) | IF(OR(F167="",AN167=""),"",IF(COUNT(AI167:AM167)=0,"",AN167-LOOKUP(2,1/(AI167:AM167<>""),AI167:AM167))) | IF(OR(F167="",AO167=""),"",IF(COUNT(AI167:AN167)=0,"",AO167-LOOKUP(2,1/(AI167:AN167<>""),AI167:AN167))) | IF(OR(F167="",AP167=""),"",IF(COUNT(AI167:AO167)=0,"",AP167-LOOKUP(2,1/(AI167:AO167<>""),AI167:AO167))) | IF(OR(F167="",AQ167=""),"",IF(COUNT(AI167:AP167)=0,"",AQ167-LOOKUP(2,1/(AI167:AP167<>""),AI167:AP167))) | IF(OR(F167="",AR167=""),"",IF(COUNT(AI167:AQ167)=0,"",AR167-LOOKUP(2,1/(AI167:AQ167<>""),AI167:AQ167))) | IF(OR(F167="",AS167=""),"",IF(COUNT(AI167:AR167)=0,"",AS167-LOOKUP(2,1/(AI167:AR167<>""),AI167:AR167))) | IF(OR(F167="",AT167=""),"",IF(COUNT(AI167:AS167)=0,"",AT167-LOOKUP(2,1/(AI167:AS167<>""),AI167:AS167))) | IF(OR(F167="",AU167=""),"",IF(COUNT(AI167:AT167)=0,"",AU167-LOOKUP(2,1/(AI167:AT167<>""),AI167:AT167))) | IF(OR(F167="",AV167=""),"",IF(COUNT(AI167:AU167)=0,"",AV167-LOOKUP(2,1/(AI167:AU167<>""),AI167:AU167))) | IF(J167="","All_Provinces",IFERROR(VLOOKUP(J167,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K167="","All_Districts",IFERROR(VLOOKUP(K167,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F168="","",ROW()-3) | AF2-IS-14 | Package #14-AF2 IS: Rehabilitation of Zard Sang and Topchi Cluster Canal Irrigation scheme, located in Center district of Bamyan province. | 1 of 2 | AF2-IS-A-015 | Sar Qul Topchi canal irrigation schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Center | Topchi | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Nomae Shahr Construction Company (NSCC) | 002/2026 | 165609.67 | IF(AQ168="","",AQ168) |  | 12 | 2027-01-23 | IF(W168<>"",W168,IF(OR(T168="",V168=""),"",EDATE(T168,V168))) |  | 85 | Under Construction | on track and will be completed in 2026 | IF(F168="","",IF(COUNT(AI168:AV168)=0,IF(AA168="","Not started",AA168),SUBSTITUTE(LOOKUP(2,1/(AI168:AV168<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F168="",COUNT(AI168:AV168)=0),"",TODAY()-LOOKUP(2,1/(AI168:AV168<>""),AI168:AV168)) | IF(OR(F168="",COUNT(AI168:AV168)<2),"",LOOKUP(2,1/(AI168:AV168<>""),AI168:AV168)-MIN(AI168:AV168)) | IF(OR(AD168="",AC168="Not started",AC168=""),"",IFERROR(AD168-IF(VLOOKUP(AC168,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC168,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F168="","",IF(OR(AA168="Cancelled",AC168="Cancelled"),"Cancelled",IF(OR(AC168="Completed / Handover",Y168<>"",Z168>=100),"Completed — on track",IF(O168="Not awarded",IF(U168="",IF(X168="","No planned date",IF(TODAY()>X168,"Behind — past planned date",IF(X168-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U168,"Behind — award date passed",IF(U168-TODAY()<=30,"At risk — close to off track","On track"))),IF(X168="","No planned date",IF(AND(TODAY()>X168,OR(Z168="",Z168<100)),"Behind — past end date",IF(AND(T168<>"",X168<>"",Z168<>"",(Z168<100),((TODAY()-T168)/MAX(X168-T168,1)*100)-Z168>15),"Behind — progress lag",IF(AND(X168-TODAY()<=30,X168-TODAY()>=0,OR(Z168="",Z168<90)),"At risk — close to off track","On track")))))))) | IF(OR(F168="",AC168="Completed / Handover",AC168="Cancelled"),"",IF(O168="Not awarded",IF(U168<>"",U168-TODAY(),IF(X168="","",X168-TODAY())),IF(X168="","",X168-TODAY()))) | [8 empty] | 2026-01-24 | 2026-01-24 |  |  |  |  | IF(OR(F168="",AJ168=""),"",IF(COUNT(AI168:AI168)=0,"",AJ168-LOOKUP(2,1/(AI168:AI168<>""),AI168:AI168))) | IF(OR(F168="",AK168=""),"",IF(COUNT(AI168:AJ168)=0,"",AK168-LOOKUP(2,1/(AI168:AJ168<>""),AI168:AJ168))) | IF(OR(F168="",AL168=""),"",IF(COUNT(AI168:AK168)=0,"",AL168-LOOKUP(2,1/(AI168:AK168<>""),AI168:AK168))) | IF(OR(F168="",AM168=""),"",IF(COUNT(AI168:AL168)=0,"",AM168-LOOKUP(2,1/(AI168:AL168<>""),AI168:AL168))) | IF(OR(F168="",AN168=""),"",IF(COUNT(AI168:AM168)=0,"",AN168-LOOKUP(2,1/(AI168:AM168<>""),AI168:AM168))) | IF(OR(F168="",AO168=""),"",IF(COUNT(AI168:AN168)=0,"",AO168-LOOKUP(2,1/(AI168:AN168<>""),AI168:AN168))) | IF(OR(F168="",AP168=""),"",IF(COUNT(AI168:AO168)=0,"",AP168-LOOKUP(2,1/(AI168:AO168<>""),AI168:AO168))) | IF(OR(F168="",AQ168=""),"",IF(COUNT(AI168:AP168)=0,"",AQ168-LOOKUP(2,1/(AI168:AP168<>""),AI168:AP168))) | IF(OR(F168="",AR168=""),"",IF(COUNT(AI168:AQ168)=0,"",AR168-LOOKUP(2,1/(AI168:AQ168<>""),AI168:AQ168))) | IF(OR(F168="",AS168=""),"",IF(COUNT(AI168:AR168)=0,"",AS168-LOOKUP(2,1/(AI168:AR168<>""),AI168:AR168))) | IF(OR(F168="",AT168=""),"",IF(COUNT(AI168:AS168)=0,"",AT168-LOOKUP(2,1/(AI168:AS168<>""),AI168:AS168))) | IF(OR(F168="",AU168=""),"",IF(COUNT(AI168:AT168)=0,"",AU168-LOOKUP(2,1/(AI168:AT168<>""),AI168:AT168))) | IF(OR(F168="",AV168=""),"",IF(COUNT(AI168:AU168)=0,"",AV168-LOOKUP(2,1/(AI168:AU168<>""),AI168:AU168))) | IF(J168="","All_Provinces",IFERROR(VLOOKUP(J168,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K168="","All_Districts",IFERROR(VLOOKUP(K168,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F169="","",ROW()-3) | AF2-IS-14 | Package #14-AF2 IS: Rehabilitation of Zard Sang and Topchi Cluster Canal Irrigation scheme, located in Center district of Bamyan province. | 2 of 2 | AF2-IS-A-016 | Zard Sang canal irrigation schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan |  |  | Zard Sang | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Nomae Shahr Construction Company (NSCC) | 002/2026 | 143050.83 | IF(AQ169="","",AQ169) |  | 12 | 2027-01-23 | IF(W169<>"",W169,IF(OR(T169="",V169=""),"",EDATE(T169,V169))) |  | 70 | Under Construction | on track and will be completed in 2027 | IF(F169="","",IF(COUNT(AI169:AV169)=0,IF(AA169="","Not started",AA169),SUBSTITUTE(LOOKUP(2,1/(AI169:AV169<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F169="",COUNT(AI169:AV169)=0),"",TODAY()-LOOKUP(2,1/(AI169:AV169<>""),AI169:AV169)) | IF(OR(F169="",COUNT(AI169:AV169)<2),"",LOOKUP(2,1/(AI169:AV169<>""),AI169:AV169)-MIN(AI169:AV169)) | IF(OR(AD169="",AC169="Not started",AC169=""),"",IFERROR(AD169-IF(VLOOKUP(AC169,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC169,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F169="","",IF(OR(AA169="Cancelled",AC169="Cancelled"),"Cancelled",IF(OR(AC169="Completed / Handover",Y169<>"",Z169>=100),"Completed — on track",IF(O169="Not awarded",IF(U169="",IF(X169="","No planned date",IF(TODAY()>X169,"Behind — past planned date",IF(X169-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U169,"Behind — award date passed",IF(U169-TODAY()<=30,"At risk — close to off track","On track"))),IF(X169="","No planned date",IF(AND(TODAY()>X169,OR(Z169="",Z169<100)),"Behind — past end date",IF(AND(T169<>"",X169<>"",Z169<>"",(Z169<100),((TODAY()-T169)/MAX(X169-T169,1)*100)-Z169>15),"Behind — progress lag",IF(AND(X169-TODAY()<=30,X169-TODAY()>=0,OR(Z169="",Z169<90)),"At risk — close to off track","On track")))))))) | IF(OR(F169="",AC169="Completed / Handover",AC169="Cancelled"),"",IF(O169="Not awarded",IF(U169<>"",U169-TODAY(),IF(X169="","",X169-TODAY())),IF(X169="","",X169-TODAY()))) | [8 empty] | 2026-01-24 | 2026-01-24 |  |  |  |  | IF(OR(F169="",AJ169=""),"",IF(COUNT(AI169:AI169)=0,"",AJ169-LOOKUP(2,1/(AI169:AI169<>""),AI169:AI169))) | IF(OR(F169="",AK169=""),"",IF(COUNT(AI169:AJ169)=0,"",AK169-LOOKUP(2,1/(AI169:AJ169<>""),AI169:AJ169))) | IF(OR(F169="",AL169=""),"",IF(COUNT(AI169:AK169)=0,"",AL169-LOOKUP(2,1/(AI169:AK169<>""),AI169:AK169))) | IF(OR(F169="",AM169=""),"",IF(COUNT(AI169:AL169)=0,"",AM169-LOOKUP(2,1/(AI169:AL169<>""),AI169:AL169))) | IF(OR(F169="",AN169=""),"",IF(COUNT(AI169:AM169)=0,"",AN169-LOOKUP(2,1/(AI169:AM169<>""),AI169:AM169))) | IF(OR(F169="",AO169=""),"",IF(COUNT(AI169:AN169)=0,"",AO169-LOOKUP(2,1/(AI169:AN169<>""),AI169:AN169))) | IF(OR(F169="",AP169=""),"",IF(COUNT(AI169:AO169)=0,"",AP169-LOOKUP(2,1/(AI169:AO169<>""),AI169:AO169))) | IF(OR(F169="",AQ169=""),"",IF(COUNT(AI169:AP169)=0,"",AQ169-LOOKUP(2,1/(AI169:AP169<>""),AI169:AP169))) | IF(OR(F169="",AR169=""),"",IF(COUNT(AI169:AQ169)=0,"",AR169-LOOKUP(2,1/(AI169:AQ169<>""),AI169:AQ169))) | IF(OR(F169="",AS169=""),"",IF(COUNT(AI169:AR169)=0,"",AS169-LOOKUP(2,1/(AI169:AR169<>""),AI169:AR169))) | IF(OR(F169="",AT169=""),"",IF(COUNT(AI169:AS169)=0,"",AT169-LOOKUP(2,1/(AI169:AS169<>""),AI169:AS169))) | IF(OR(F169="",AU169=""),"",IF(COUNT(AI169:AT169)=0,"",AU169-LOOKUP(2,1/(AI169:AT169<>""),AI169:AT169))) | IF(OR(F169="",AV169=""),"",IF(COUNT(AI169:AU169)=0,"",AV169-LOOKUP(2,1/(AI169:AU169<>""),AI169:AU169))) | IF(J169="","All_Provinces",IFERROR(VLOOKUP(J169,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K169="","All_Districts",IFERROR(VLOOKUP(K169,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F170="","",ROW()-3) | AF2-IS-15 | Package #15-AF2 IS: Rehabilitation of Pitab joy and Sorkh Kawak Cluster Canal Irrigation scheme, located in Waras districts of Bamyan province. | 1 of 2 | AF2-IS-N-012 | Pitab Joy Cluster canal irrigation schemce | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Waras | Pitab and 6 tiny villages | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 335855.17 | IF(AQ170="","",AQ170) | 2026-12-15 | 9.2 | 2027-09-21 | IF(W170<>"",W170,IF(OR(T170="",V170=""),"",EDATE(T170,V170))) |  |  | Retendered (Re-ITB) | Three months slack period Jan-Mar during winter. Eight months construction period required for two canals. Explore possibility of BAFO and split to 2 contracts based on the outcome of the reITB | IF(F170="","",IF(COUNT(AI170:AV170)=0,IF(AA170="","Not started",AA170),SUBSTITUTE(LOOKUP(2,1/(AI170:AV170<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F170="",COUNT(AI170:AV170)=0),"",TODAY()-LOOKUP(2,1/(AI170:AV170<>""),AI170:AV170)) | IF(OR(F170="",COUNT(AI170:AV170)<2),"",LOOKUP(2,1/(AI170:AV170<>""),AI170:AV170)-MIN(AI170:AV170)) | IF(OR(AD170="",AC170="Not started",AC170=""),"",IFERROR(AD170-IF(VLOOKUP(AC170,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC170,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F170="","",IF(OR(AA170="Cancelled",AC170="Cancelled"),"Cancelled",IF(OR(AC170="Completed / Handover",Y170<>"",Z170>=100),"Completed — on track",IF(O170="Not awarded",IF(U170="",IF(X170="","No planned date",IF(TODAY()>X170,"Behind — past planned date",IF(X170-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U170,"Behind — award date passed",IF(U170-TODAY()<=30,"At risk — close to off track","On track"))),IF(X170="","No planned date",IF(AND(TODAY()>X170,OR(Z170="",Z170<100)),"Behind — past end date",IF(AND(T170<>"",X170<>"",Z170<>"",(Z170<100),((TODAY()-T170)/MAX(X170-T170,1)*100)-Z170>15),"Behind — progress lag",IF(AND(X170-TODAY()<=30,X170-TODAY()>=0,OR(Z170="",Z170<90)),"At risk — close to off track","On track")))))))) | IF(OR(F170="",AC170="Completed / Handover",AC170="Cancelled"),"",IF(O170="Not awarded",IF(U170<>"",U170-TODAY(),IF(X170="","",X170-TODAY())),IF(X170="","",X170-TODAY()))) | [14 empty] | IF(OR(F170="",AJ170=""),"",IF(COUNT(AI170:AI170)=0,"",AJ170-LOOKUP(2,1/(AI170:AI170<>""),AI170:AI170))) | IF(OR(F170="",AK170=""),"",IF(COUNT(AI170:AJ170)=0,"",AK170-LOOKUP(2,1/(AI170:AJ170<>""),AI170:AJ170))) | IF(OR(F170="",AL170=""),"",IF(COUNT(AI170:AK170)=0,"",AL170-LOOKUP(2,1/(AI170:AK170<>""),AI170:AK170))) | IF(OR(F170="",AM170=""),"",IF(COUNT(AI170:AL170)=0,"",AM170-LOOKUP(2,1/(AI170:AL170<>""),AI170:AL170))) | IF(OR(F170="",AN170=""),"",IF(COUNT(AI170:AM170)=0,"",AN170-LOOKUP(2,1/(AI170:AM170<>""),AI170:AM170))) | IF(OR(F170="",AO170=""),"",IF(COUNT(AI170:AN170)=0,"",AO170-LOOKUP(2,1/(AI170:AN170<>""),AI170:AN170))) | IF(OR(F170="",AP170=""),"",IF(COUNT(AI170:AO170)=0,"",AP170-LOOKUP(2,1/(AI170:AO170<>""),AI170:AO170))) | IF(OR(F170="",AQ170=""),"",IF(COUNT(AI170:AP170)=0,"",AQ170-LOOKUP(2,1/(AI170:AP170<>""),AI170:AP170))) | IF(OR(F170="",AR170=""),"",IF(COUNT(AI170:AQ170)=0,"",AR170-LOOKUP(2,1/(AI170:AQ170<>""),AI170:AQ170))) | IF(OR(F170="",AS170=""),"",IF(COUNT(AI170:AR170)=0,"",AS170-LOOKUP(2,1/(AI170:AR170<>""),AI170:AR170))) | IF(OR(F170="",AT170=""),"",IF(COUNT(AI170:AS170)=0,"",AT170-LOOKUP(2,1/(AI170:AS170<>""),AI170:AS170))) | IF(OR(F170="",AU170=""),"",IF(COUNT(AI170:AT170)=0,"",AU170-LOOKUP(2,1/(AI170:AT170<>""),AI170:AT170))) | IF(OR(F170="",AV170=""),"",IF(COUNT(AI170:AU170)=0,"",AV170-LOOKUP(2,1/(AI170:AU170<>""),AI170:AU170))) | IF(J170="","All_Provinces",IFERROR(VLOOKUP(J170,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K170="","All_Districts",IFERROR(VLOOKUP(K170,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F171="","",ROW()-3) | AF2-IS-15 | Package #15-AF2 IS: Rehabilitation of Pitab joy and Sorkh Kawak Cluster Canal Irrigation scheme, located in Waras districts of Bamyan province. | 2 of 2 | AF2-IS-N-013 | Sorkh Kawak Cluster canal irrigation schemce | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan |  |  | SorKh kawak and 6 tiny villages | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 335855.17 | IF(AQ171="","",AQ171) | 2026-12-15 | 9.2 | 2027-09-21 | IF(W171<>"",W171,IF(OR(T171="",V171=""),"",EDATE(T171,V171))) |  |  | Retendered (Re-ITB) | Three months slack period Jan-Mar during winter. Eight months construction period required for two canals. Explore possibility of BAFO and split to 2 contracts based on the outcome of the reITB | IF(F171="","",IF(COUNT(AI171:AV171)=0,IF(AA171="","Not started",AA171),SUBSTITUTE(LOOKUP(2,1/(AI171:AV171<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F171="",COUNT(AI171:AV171)=0),"",TODAY()-LOOKUP(2,1/(AI171:AV171<>""),AI171:AV171)) | IF(OR(F171="",COUNT(AI171:AV171)<2),"",LOOKUP(2,1/(AI171:AV171<>""),AI171:AV171)-MIN(AI171:AV171)) | IF(OR(AD171="",AC171="Not started",AC171=""),"",IFERROR(AD171-IF(VLOOKUP(AC171,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC171,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F171="","",IF(OR(AA171="Cancelled",AC171="Cancelled"),"Cancelled",IF(OR(AC171="Completed / Handover",Y171<>"",Z171>=100),"Completed — on track",IF(O171="Not awarded",IF(U171="",IF(X171="","No planned date",IF(TODAY()>X171,"Behind — past planned date",IF(X171-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U171,"Behind — award date passed",IF(U171-TODAY()<=30,"At risk — close to off track","On track"))),IF(X171="","No planned date",IF(AND(TODAY()>X171,OR(Z171="",Z171<100)),"Behind — past end date",IF(AND(T171<>"",X171<>"",Z171<>"",(Z171<100),((TODAY()-T171)/MAX(X171-T171,1)*100)-Z171>15),"Behind — progress lag",IF(AND(X171-TODAY()<=30,X171-TODAY()>=0,OR(Z171="",Z171<90)),"At risk — close to off track","On track")))))))) | IF(OR(F171="",AC171="Completed / Handover",AC171="Cancelled"),"",IF(O171="Not awarded",IF(U171<>"",U171-TODAY(),IF(X171="","",X171-TODAY())),IF(X171="","",X171-TODAY()))) | [14 empty] | IF(OR(F171="",AJ171=""),"",IF(COUNT(AI171:AI171)=0,"",AJ171-LOOKUP(2,1/(AI171:AI171<>""),AI171:AI171))) | IF(OR(F171="",AK171=""),"",IF(COUNT(AI171:AJ171)=0,"",AK171-LOOKUP(2,1/(AI171:AJ171<>""),AI171:AJ171))) | IF(OR(F171="",AL171=""),"",IF(COUNT(AI171:AK171)=0,"",AL171-LOOKUP(2,1/(AI171:AK171<>""),AI171:AK171))) | IF(OR(F171="",AM171=""),"",IF(COUNT(AI171:AL171)=0,"",AM171-LOOKUP(2,1/(AI171:AL171<>""),AI171:AL171))) | IF(OR(F171="",AN171=""),"",IF(COUNT(AI171:AM171)=0,"",AN171-LOOKUP(2,1/(AI171:AM171<>""),AI171:AM171))) | IF(OR(F171="",AO171=""),"",IF(COUNT(AI171:AN171)=0,"",AO171-LOOKUP(2,1/(AI171:AN171<>""),AI171:AN171))) | IF(OR(F171="",AP171=""),"",IF(COUNT(AI171:AO171)=0,"",AP171-LOOKUP(2,1/(AI171:AO171<>""),AI171:AO171))) | IF(OR(F171="",AQ171=""),"",IF(COUNT(AI171:AP171)=0,"",AQ171-LOOKUP(2,1/(AI171:AP171<>""),AI171:AP171))) | IF(OR(F171="",AR171=""),"",IF(COUNT(AI171:AQ171)=0,"",AR171-LOOKUP(2,1/(AI171:AQ171<>""),AI171:AQ171))) | IF(OR(F171="",AS171=""),"",IF(COUNT(AI171:AR171)=0,"",AS171-LOOKUP(2,1/(AI171:AR171<>""),AI171:AR171))) | IF(OR(F171="",AT171=""),"",IF(COUNT(AI171:AS171)=0,"",AT171-LOOKUP(2,1/(AI171:AS171<>""),AI171:AS171))) | IF(OR(F171="",AU171=""),"",IF(COUNT(AI171:AT171)=0,"",AU171-LOOKUP(2,1/(AI171:AT171<>""),AI171:AT171))) | IF(OR(F171="",AV171=""),"",IF(COUNT(AI171:AU171)=0,"",AV171-LOOKUP(2,1/(AI171:AU171<>""),AI171:AU171))) | IF(J171="","All_Provinces",IFERROR(VLOOKUP(J171,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K171="","All_Districts",IFERROR(VLOOKUP(K171,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F172="","",ROW()-3) | AF2-IS-16 | Package #16-AF2 IS: Rehabilitation of Pato (Paye Raqul, Sangchal Takhomak and Kadalak) Cluster canal irrigation scheme in Pato district of Daykundi province | 1 of 1 | AF2-IS-A-017 | Pato Irrigation Canal Cluster of (Paye Raqul, Sangchal Takhomak and Kadalak) | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Pato | Paye Raqul, Sangchal Takhomak and Kadalak | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Estehkam Baba Construction Company JV Tamadon Bamik Construction Company (EBCC) | 007/2026 | 232647.5 | IF(AQ172="","",AQ172) |  | 12 | 2027-01-20 | IF(W172<>"",W172,IF(OR(T172="",V172=""),"",EDATE(T172,V172))) |  | 100 | Completed / Handover | Completed in July 2026. ¦ Actual completion: July. 2026 | IF(F172="","",IF(COUNT(AI172:AV172)=0,IF(AA172="","Not started",AA172),SUBSTITUTE(LOOKUP(2,1/(AI172:AV172<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F172="",COUNT(AI172:AV172)=0),"",TODAY()-LOOKUP(2,1/(AI172:AV172<>""),AI172:AV172)) | IF(OR(F172="",COUNT(AI172:AV172)<2),"",LOOKUP(2,1/(AI172:AV172<>""),AI172:AV172)-MIN(AI172:AV172)) | IF(OR(AD172="",AC172="Not started",AC172=""),"",IFERROR(AD172-IF(VLOOKUP(AC172,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC172,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F172="","",IF(OR(AA172="Cancelled",AC172="Cancelled"),"Cancelled",IF(OR(AC172="Completed / Handover",Y172<>"",Z172>=100),"Completed — on track",IF(O172="Not awarded",IF(U172="",IF(X172="","No planned date",IF(TODAY()>X172,"Behind — past planned date",IF(X172-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U172,"Behind — award date passed",IF(U172-TODAY()<=30,"At risk — close to off track","On track"))),IF(X172="","No planned date",IF(AND(TODAY()>X172,OR(Z172="",Z172<100)),"Behind — past end date",IF(AND(T172<>"",X172<>"",Z172<>"",(Z172<100),((TODAY()-T172)/MAX(X172-T172,1)*100)-Z172>15),"Behind — progress lag",IF(AND(X172-TODAY()<=30,X172-TODAY()>=0,OR(Z172="",Z172<90)),"At risk — close to off track","On track")))))))) | IF(OR(F172="",AC172="Completed / Handover",AC172="Cancelled"),"",IF(O172="Not awarded",IF(U172<>"",U172-TODAY(),IF(X172="","",X172-TODAY())),IF(X172="","",X172-TODAY()))) | [8 empty] | 2026-01-21 | 2026-01-21 | 2027-01-20 |  |  |  | IF(OR(F172="",AJ172=""),"",IF(COUNT(AI172:AI172)=0,"",AJ172-LOOKUP(2,1/(AI172:AI172<>""),AI172:AI172))) | IF(OR(F172="",AK172=""),"",IF(COUNT(AI172:AJ172)=0,"",AK172-LOOKUP(2,1/(AI172:AJ172<>""),AI172:AJ172))) | IF(OR(F172="",AL172=""),"",IF(COUNT(AI172:AK172)=0,"",AL172-LOOKUP(2,1/(AI172:AK172<>""),AI172:AK172))) | IF(OR(F172="",AM172=""),"",IF(COUNT(AI172:AL172)=0,"",AM172-LOOKUP(2,1/(AI172:AL172<>""),AI172:AL172))) | IF(OR(F172="",AN172=""),"",IF(COUNT(AI172:AM172)=0,"",AN172-LOOKUP(2,1/(AI172:AM172<>""),AI172:AM172))) | IF(OR(F172="",AO172=""),"",IF(COUNT(AI172:AN172)=0,"",AO172-LOOKUP(2,1/(AI172:AN172<>""),AI172:AN172))) | IF(OR(F172="",AP172=""),"",IF(COUNT(AI172:AO172)=0,"",AP172-LOOKUP(2,1/(AI172:AO172<>""),AI172:AO172))) | IF(OR(F172="",AQ172=""),"",IF(COUNT(AI172:AP172)=0,"",AQ172-LOOKUP(2,1/(AI172:AP172<>""),AI172:AP172))) | IF(OR(F172="",AR172=""),"",IF(COUNT(AI172:AQ172)=0,"",AR172-LOOKUP(2,1/(AI172:AQ172<>""),AI172:AQ172))) | IF(OR(F172="",AS172=""),"",IF(COUNT(AI172:AR172)=0,"",AS172-LOOKUP(2,1/(AI172:AR172<>""),AI172:AR172))) | IF(OR(F172="",AT172=""),"",IF(COUNT(AI172:AS172)=0,"",AT172-LOOKUP(2,1/(AI172:AS172<>""),AI172:AS172))) | IF(OR(F172="",AU172=""),"",IF(COUNT(AI172:AT172)=0,"",AU172-LOOKUP(2,1/(AI172:AT172<>""),AI172:AT172))) | IF(OR(F172="",AV172=""),"",IF(COUNT(AI172:AU172)=0,"",AV172-LOOKUP(2,1/(AI172:AU172<>""),AI172:AU172))) | IF(J172="","All_Provinces",IFERROR(VLOOKUP(J172,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K172="","All_Districts",IFERROR(VLOOKUP(K172,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F173="","",ROW()-3) | AF2-IS-17 | Package #17-AF2 IS: Rehabilitation of Hezhdi- Nilli, Cluster Canal irrigation schemes, located in Nilli district of Daykundi province. | 1 of 1 | AF2-IS-N-014 | Hezhdi- Nilli Charsapan Cluster Canal irrigation schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Nilli | Hezhdi | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 94951 | IF(AQ173="","",AQ173) | 2026-12-15 | 8.9 | 2027-09-11 | IF(W173<>"",W173,IF(OR(T173="",V173=""),"",EDATE(T173,V173))) |  |  | Retendered (Re-ITB) | Three months slack period Jan-Mar during winter. Eight months construction period required for two canals. Explore possibility of BAFO and split to 2 contracts based on the outcome of the reITB | IF(F173="","",IF(COUNT(AI173:AV173)=0,IF(AA173="","Not started",AA173),SUBSTITUTE(LOOKUP(2,1/(AI173:AV173<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F173="",COUNT(AI173:AV173)=0),"",TODAY()-LOOKUP(2,1/(AI173:AV173<>""),AI173:AV173)) | IF(OR(F173="",COUNT(AI173:AV173)<2),"",LOOKUP(2,1/(AI173:AV173<>""),AI173:AV173)-MIN(AI173:AV173)) | IF(OR(AD173="",AC173="Not started",AC173=""),"",IFERROR(AD173-IF(VLOOKUP(AC173,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC173,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F173="","",IF(OR(AA173="Cancelled",AC173="Cancelled"),"Cancelled",IF(OR(AC173="Completed / Handover",Y173<>"",Z173>=100),"Completed — on track",IF(O173="Not awarded",IF(U173="",IF(X173="","No planned date",IF(TODAY()>X173,"Behind — past planned date",IF(X173-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U173,"Behind — award date passed",IF(U173-TODAY()<=30,"At risk — close to off track","On track"))),IF(X173="","No planned date",IF(AND(TODAY()>X173,OR(Z173="",Z173<100)),"Behind — past end date",IF(AND(T173<>"",X173<>"",Z173<>"",(Z173<100),((TODAY()-T173)/MAX(X173-T173,1)*100)-Z173>15),"Behind — progress lag",IF(AND(X173-TODAY()<=30,X173-TODAY()>=0,OR(Z173="",Z173<90)),"At risk — close to off track","On track")))))))) | IF(OR(F173="",AC173="Completed / Handover",AC173="Cancelled"),"",IF(O173="Not awarded",IF(U173<>"",U173-TODAY(),IF(X173="","",X173-TODAY())),IF(X173="","",X173-TODAY()))) | [14 empty] | IF(OR(F173="",AJ173=""),"",IF(COUNT(AI173:AI173)=0,"",AJ173-LOOKUP(2,1/(AI173:AI173<>""),AI173:AI173))) | IF(OR(F173="",AK173=""),"",IF(COUNT(AI173:AJ173)=0,"",AK173-LOOKUP(2,1/(AI173:AJ173<>""),AI173:AJ173))) | IF(OR(F173="",AL173=""),"",IF(COUNT(AI173:AK173)=0,"",AL173-LOOKUP(2,1/(AI173:AK173<>""),AI173:AK173))) | IF(OR(F173="",AM173=""),"",IF(COUNT(AI173:AL173)=0,"",AM173-LOOKUP(2,1/(AI173:AL173<>""),AI173:AL173))) | IF(OR(F173="",AN173=""),"",IF(COUNT(AI173:AM173)=0,"",AN173-LOOKUP(2,1/(AI173:AM173<>""),AI173:AM173))) | IF(OR(F173="",AO173=""),"",IF(COUNT(AI173:AN173)=0,"",AO173-LOOKUP(2,1/(AI173:AN173<>""),AI173:AN173))) | IF(OR(F173="",AP173=""),"",IF(COUNT(AI173:AO173)=0,"",AP173-LOOKUP(2,1/(AI173:AO173<>""),AI173:AO173))) | IF(OR(F173="",AQ173=""),"",IF(COUNT(AI173:AP173)=0,"",AQ173-LOOKUP(2,1/(AI173:AP173<>""),AI173:AP173))) | IF(OR(F173="",AR173=""),"",IF(COUNT(AI173:AQ173)=0,"",AR173-LOOKUP(2,1/(AI173:AQ173<>""),AI173:AQ173))) | IF(OR(F173="",AS173=""),"",IF(COUNT(AI173:AR173)=0,"",AS173-LOOKUP(2,1/(AI173:AR173<>""),AI173:AR173))) | IF(OR(F173="",AT173=""),"",IF(COUNT(AI173:AS173)=0,"",AT173-LOOKUP(2,1/(AI173:AS173<>""),AI173:AS173))) | IF(OR(F173="",AU173=""),"",IF(COUNT(AI173:AT173)=0,"",AU173-LOOKUP(2,1/(AI173:AT173<>""),AI173:AT173))) | IF(OR(F173="",AV173=""),"",IF(COUNT(AI173:AU173)=0,"",AV173-LOOKUP(2,1/(AI173:AU173<>""),AI173:AU173))) | IF(J173="","All_Provinces",IFERROR(VLOOKUP(J173,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K173="","All_Districts",IFERROR(VLOOKUP(K173,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F174="","",ROW()-3) | AF2-IS-18 | Package #18-AF2 IS: Rehabilitation of Drang canal irrigation schemes, located in Zurmat district of Paktya province. | 1 of 1 | AF2-IS-N-015 | Drang canal irrigation Scheme (On-FWM Project) | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Paktya | Zurmat | Drang | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 393953 | IF(AQ174="","",AQ174) | 2026-11-30 | 11 | 2027-10-29 | IF(W174<>"",W174,IF(OR(T174="",V174=""),"",EDATE(T174,V174))) |  |  | ITB Launched | Three months slack period Jan-Mar during winter. Nine months construction period required for the cluster canals in two districts | IF(F174="","",IF(COUNT(AI174:AV174)=0,IF(AA174="","Not started",AA174),SUBSTITUTE(LOOKUP(2,1/(AI174:AV174<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F174="",COUNT(AI174:AV174)=0),"",TODAY()-LOOKUP(2,1/(AI174:AV174<>""),AI174:AV174)) | IF(OR(F174="",COUNT(AI174:AV174)<2),"",LOOKUP(2,1/(AI174:AV174<>""),AI174:AV174)-MIN(AI174:AV174)) | IF(OR(AD174="",AC174="Not started",AC174=""),"",IFERROR(AD174-IF(VLOOKUP(AC174,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC174,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F174="","",IF(OR(AA174="Cancelled",AC174="Cancelled"),"Cancelled",IF(OR(AC174="Completed / Handover",Y174<>"",Z174>=100),"Completed — on track",IF(O174="Not awarded",IF(U174="",IF(X174="","No planned date",IF(TODAY()>X174,"Behind — past planned date",IF(X174-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U174,"Behind — award date passed",IF(U174-TODAY()<=30,"At risk — close to off track","On track"))),IF(X174="","No planned date",IF(AND(TODAY()>X174,OR(Z174="",Z174<100)),"Behind — past end date",IF(AND(T174<>"",X174<>"",Z174<>"",(Z174<100),((TODAY()-T174)/MAX(X174-T174,1)*100)-Z174>15),"Behind — progress lag",IF(AND(X174-TODAY()<=30,X174-TODAY()>=0,OR(Z174="",Z174<90)),"At risk — close to off track","On track")))))))) | IF(OR(F174="",AC174="Completed / Handover",AC174="Cancelled"),"",IF(O174="Not awarded",IF(U174<>"",U174-TODAY(),IF(X174="","",X174-TODAY())),IF(X174="","",X174-TODAY()))) | [14 empty] | IF(OR(F174="",AJ174=""),"",IF(COUNT(AI174:AI174)=0,"",AJ174-LOOKUP(2,1/(AI174:AI174<>""),AI174:AI174))) | IF(OR(F174="",AK174=""),"",IF(COUNT(AI174:AJ174)=0,"",AK174-LOOKUP(2,1/(AI174:AJ174<>""),AI174:AJ174))) | IF(OR(F174="",AL174=""),"",IF(COUNT(AI174:AK174)=0,"",AL174-LOOKUP(2,1/(AI174:AK174<>""),AI174:AK174))) | IF(OR(F174="",AM174=""),"",IF(COUNT(AI174:AL174)=0,"",AM174-LOOKUP(2,1/(AI174:AL174<>""),AI174:AL174))) | IF(OR(F174="",AN174=""),"",IF(COUNT(AI174:AM174)=0,"",AN174-LOOKUP(2,1/(AI174:AM174<>""),AI174:AM174))) | IF(OR(F174="",AO174=""),"",IF(COUNT(AI174:AN174)=0,"",AO174-LOOKUP(2,1/(AI174:AN174<>""),AI174:AN174))) | IF(OR(F174="",AP174=""),"",IF(COUNT(AI174:AO174)=0,"",AP174-LOOKUP(2,1/(AI174:AO174<>""),AI174:AO174))) | IF(OR(F174="",AQ174=""),"",IF(COUNT(AI174:AP174)=0,"",AQ174-LOOKUP(2,1/(AI174:AP174<>""),AI174:AP174))) | IF(OR(F174="",AR174=""),"",IF(COUNT(AI174:AQ174)=0,"",AR174-LOOKUP(2,1/(AI174:AQ174<>""),AI174:AQ174))) | IF(OR(F174="",AS174=""),"",IF(COUNT(AI174:AR174)=0,"",AS174-LOOKUP(2,1/(AI174:AR174<>""),AI174:AR174))) | IF(OR(F174="",AT174=""),"",IF(COUNT(AI174:AS174)=0,"",AT174-LOOKUP(2,1/(AI174:AS174<>""),AI174:AS174))) | IF(OR(F174="",AU174=""),"",IF(COUNT(AI174:AT174)=0,"",AU174-LOOKUP(2,1/(AI174:AT174<>""),AI174:AT174))) | IF(OR(F174="",AV174=""),"",IF(COUNT(AI174:AU174)=0,"",AV174-LOOKUP(2,1/(AI174:AU174<>""),AI174:AU174))) | IF(J174="","All_Provinces",IFERROR(VLOOKUP(J174,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K174="","All_Districts",IFERROR(VLOOKUP(K174,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F175="","",ROW()-3) | AF2-IS-19 | Package #19-AF2 IS: Rehabilitation of Khwaja Angor canal and Qalai Wazir canal irrigation schemes located in Kharwar and Pol-i-Alam districts of Logar province. | 1 of 2 | AF2-IS-A-018 | Khwaja Angor Irrigation Scheme (OFWM Project) | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Logar | Kharwar | Khwaja Angor | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Unique Wahaj Construction Company (UWCC) | 074/2026 | 143249.77 | IF(AQ175="","",AQ175) |  | 12 | 2026-12-30 | IF(W175<>"",W175,IF(OR(T175="",V175=""),"",EDATE(T175,V175))) |  | 98 | Under Construction | on track and will be completed in 2026 | IF(F175="","",IF(COUNT(AI175:AV175)=0,IF(AA175="","Not started",AA175),SUBSTITUTE(LOOKUP(2,1/(AI175:AV175<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F175="",COUNT(AI175:AV175)=0),"",TODAY()-LOOKUP(2,1/(AI175:AV175<>""),AI175:AV175)) | IF(OR(F175="",COUNT(AI175:AV175)<2),"",LOOKUP(2,1/(AI175:AV175<>""),AI175:AV175)-MIN(AI175:AV175)) | IF(OR(AD175="",AC175="Not started",AC175=""),"",IFERROR(AD175-IF(VLOOKUP(AC175,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC175,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F175="","",IF(OR(AA175="Cancelled",AC175="Cancelled"),"Cancelled",IF(OR(AC175="Completed / Handover",Y175<>"",Z175>=100),"Completed — on track",IF(O175="Not awarded",IF(U175="",IF(X175="","No planned date",IF(TODAY()>X175,"Behind — past planned date",IF(X175-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U175,"Behind — award date passed",IF(U175-TODAY()<=30,"At risk — close to off track","On track"))),IF(X175="","No planned date",IF(AND(TODAY()>X175,OR(Z175="",Z175<100)),"Behind — past end date",IF(AND(T175<>"",X175<>"",Z175<>"",(Z175<100),((TODAY()-T175)/MAX(X175-T175,1)*100)-Z175>15),"Behind — progress lag",IF(AND(X175-TODAY()<=30,X175-TODAY()>=0,OR(Z175="",Z175<90)),"At risk — close to off track","On track")))))))) | IF(OR(F175="",AC175="Completed / Handover",AC175="Cancelled"),"",IF(O175="Not awarded",IF(U175<>"",U175-TODAY(),IF(X175="","",X175-TODAY())),IF(X175="","",X175-TODAY()))) | [8 empty] | 2025-12-31 | 2025-12-31 |  |  |  |  | IF(OR(F175="",AJ175=""),"",IF(COUNT(AI175:AI175)=0,"",AJ175-LOOKUP(2,1/(AI175:AI175<>""),AI175:AI175))) | IF(OR(F175="",AK175=""),"",IF(COUNT(AI175:AJ175)=0,"",AK175-LOOKUP(2,1/(AI175:AJ175<>""),AI175:AJ175))) | IF(OR(F175="",AL175=""),"",IF(COUNT(AI175:AK175)=0,"",AL175-LOOKUP(2,1/(AI175:AK175<>""),AI175:AK175))) | IF(OR(F175="",AM175=""),"",IF(COUNT(AI175:AL175)=0,"",AM175-LOOKUP(2,1/(AI175:AL175<>""),AI175:AL175))) | IF(OR(F175="",AN175=""),"",IF(COUNT(AI175:AM175)=0,"",AN175-LOOKUP(2,1/(AI175:AM175<>""),AI175:AM175))) | IF(OR(F175="",AO175=""),"",IF(COUNT(AI175:AN175)=0,"",AO175-LOOKUP(2,1/(AI175:AN175<>""),AI175:AN175))) | IF(OR(F175="",AP175=""),"",IF(COUNT(AI175:AO175)=0,"",AP175-LOOKUP(2,1/(AI175:AO175<>""),AI175:AO175))) | IF(OR(F175="",AQ175=""),"",IF(COUNT(AI175:AP175)=0,"",AQ175-LOOKUP(2,1/(AI175:AP175<>""),AI175:AP175))) | IF(OR(F175="",AR175=""),"",IF(COUNT(AI175:AQ175)=0,"",AR175-LOOKUP(2,1/(AI175:AQ175<>""),AI175:AQ175))) | IF(OR(F175="",AS175=""),"",IF(COUNT(AI175:AR175)=0,"",AS175-LOOKUP(2,1/(AI175:AR175<>""),AI175:AR175))) | IF(OR(F175="",AT175=""),"",IF(COUNT(AI175:AS175)=0,"",AT175-LOOKUP(2,1/(AI175:AS175<>""),AI175:AS175))) | IF(OR(F175="",AU175=""),"",IF(COUNT(AI175:AT175)=0,"",AU175-LOOKUP(2,1/(AI175:AT175<>""),AI175:AT175))) | IF(OR(F175="",AV175=""),"",IF(COUNT(AI175:AU175)=0,"",AV175-LOOKUP(2,1/(AI175:AU175<>""),AI175:AU175))) | IF(J175="","All_Provinces",IFERROR(VLOOKUP(J175,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K175="","All_Districts",IFERROR(VLOOKUP(K175,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F176="","",ROW()-3) | AF2-IS-19 | Package #19-AF2 IS: Rehabilitation of Khwaja Angor canal and Qalai Wazir canal irrigation schemes located in Kharwar and Pol-i-Alam districts of Logar province. | 2 of 2 | AF2-IS-A-019 | Qalai Wazir Irrigation Scheme (OFWM Project) | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez |  | Pol-i-Alam | Qalai Wazir | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Unique Wahaj Construction Company (UWCC) | 074/2026 | 239337.2 | IF(AQ176="","",AQ176) |  | 12 | 2026-12-30 | IF(W176<>"",W176,IF(OR(T176="",V176=""),"",EDATE(T176,V176))) |  | 100 | Completed / Handover | Actual completion: Sep, 2026 | IF(F176="","",IF(COUNT(AI176:AV176)=0,IF(AA176="","Not started",AA176),SUBSTITUTE(LOOKUP(2,1/(AI176:AV176<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F176="",COUNT(AI176:AV176)=0),"",TODAY()-LOOKUP(2,1/(AI176:AV176<>""),AI176:AV176)) | IF(OR(F176="",COUNT(AI176:AV176)<2),"",LOOKUP(2,1/(AI176:AV176<>""),AI176:AV176)-MIN(AI176:AV176)) | IF(OR(AD176="",AC176="Not started",AC176=""),"",IFERROR(AD176-IF(VLOOKUP(AC176,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC176,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F176="","",IF(OR(AA176="Cancelled",AC176="Cancelled"),"Cancelled",IF(OR(AC176="Completed / Handover",Y176<>"",Z176>=100),"Completed — on track",IF(O176="Not awarded",IF(U176="",IF(X176="","No planned date",IF(TODAY()>X176,"Behind — past planned date",IF(X176-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U176,"Behind — award date passed",IF(U176-TODAY()<=30,"At risk — close to off track","On track"))),IF(X176="","No planned date",IF(AND(TODAY()>X176,OR(Z176="",Z176<100)),"Behind — past end date",IF(AND(T176<>"",X176<>"",Z176<>"",(Z176<100),((TODAY()-T176)/MAX(X176-T176,1)*100)-Z176>15),"Behind — progress lag",IF(AND(X176-TODAY()<=30,X176-TODAY()>=0,OR(Z176="",Z176<90)),"At risk — close to off track","On track")))))))) | IF(OR(F176="",AC176="Completed / Handover",AC176="Cancelled"),"",IF(O176="Not awarded",IF(U176<>"",U176-TODAY(),IF(X176="","",X176-TODAY())),IF(X176="","",X176-TODAY()))) | [8 empty] | 2025-12-31 | 2025-12-31 | 2026-12-30 |  |  |  | IF(OR(F176="",AJ176=""),"",IF(COUNT(AI176:AI176)=0,"",AJ176-LOOKUP(2,1/(AI176:AI176<>""),AI176:AI176))) | IF(OR(F176="",AK176=""),"",IF(COUNT(AI176:AJ176)=0,"",AK176-LOOKUP(2,1/(AI176:AJ176<>""),AI176:AJ176))) | IF(OR(F176="",AL176=""),"",IF(COUNT(AI176:AK176)=0,"",AL176-LOOKUP(2,1/(AI176:AK176<>""),AI176:AK176))) | IF(OR(F176="",AM176=""),"",IF(COUNT(AI176:AL176)=0,"",AM176-LOOKUP(2,1/(AI176:AL176<>""),AI176:AL176))) | IF(OR(F176="",AN176=""),"",IF(COUNT(AI176:AM176)=0,"",AN176-LOOKUP(2,1/(AI176:AM176<>""),AI176:AM176))) | IF(OR(F176="",AO176=""),"",IF(COUNT(AI176:AN176)=0,"",AO176-LOOKUP(2,1/(AI176:AN176<>""),AI176:AN176))) | IF(OR(F176="",AP176=""),"",IF(COUNT(AI176:AO176)=0,"",AP176-LOOKUP(2,1/(AI176:AO176<>""),AI176:AO176))) | IF(OR(F176="",AQ176=""),"",IF(COUNT(AI176:AP176)=0,"",AQ176-LOOKUP(2,1/(AI176:AP176<>""),AI176:AP176))) | IF(OR(F176="",AR176=""),"",IF(COUNT(AI176:AQ176)=0,"",AR176-LOOKUP(2,1/(AI176:AQ176<>""),AI176:AQ176))) | IF(OR(F176="",AS176=""),"",IF(COUNT(AI176:AR176)=0,"",AS176-LOOKUP(2,1/(AI176:AR176<>""),AI176:AR176))) | IF(OR(F176="",AT176=""),"",IF(COUNT(AI176:AS176)=0,"",AT176-LOOKUP(2,1/(AI176:AS176<>""),AI176:AS176))) | IF(OR(F176="",AU176=""),"",IF(COUNT(AI176:AT176)=0,"",AU176-LOOKUP(2,1/(AI176:AT176<>""),AI176:AT176))) | IF(OR(F176="",AV176=""),"",IF(COUNT(AI176:AU176)=0,"",AV176-LOOKUP(2,1/(AI176:AU176<>""),AI176:AU176))) | IF(J176="","All_Provinces",IFERROR(VLOOKUP(J176,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K176="","All_Districts",IFERROR(VLOOKUP(K176,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F177="","",ROW()-3) | AF2-IS-20 | Package #20-AF2 IS: Rehabilitation of Welgai irrigation system, located in Matoon district of Khost province. | 1 of 1 | AF2-IS-A-020 | Welgai (Off-Farm & On-Farm Project) | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Matoon | Shamal Piran | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Mahmood Raqi Nawin Construction & Road Building Company (MRCC) | 053/2025 | 229783.31 | IF(AQ177="","",AQ177) |  | 12 | 2026-10-11 | IF(W177<>"",W177,IF(OR(T177="",V177=""),"",EDATE(T177,V177))) |  | 100 | Completed / Handover | Completed in June 2026. ¦ Actual completion: June, 2026 | IF(F177="","",IF(COUNT(AI177:AV177)=0,IF(AA177="","Not started",AA177),SUBSTITUTE(LOOKUP(2,1/(AI177:AV177<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F177="",COUNT(AI177:AV177)=0),"",TODAY()-LOOKUP(2,1/(AI177:AV177<>""),AI177:AV177)) | IF(OR(F177="",COUNT(AI177:AV177)<2),"",LOOKUP(2,1/(AI177:AV177<>""),AI177:AV177)-MIN(AI177:AV177)) | IF(OR(AD177="",AC177="Not started",AC177=""),"",IFERROR(AD177-IF(VLOOKUP(AC177,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC177,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F177="","",IF(OR(AA177="Cancelled",AC177="Cancelled"),"Cancelled",IF(OR(AC177="Completed / Handover",Y177<>"",Z177>=100),"Completed — on track",IF(O177="Not awarded",IF(U177="",IF(X177="","No planned date",IF(TODAY()>X177,"Behind — past planned date",IF(X177-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U177,"Behind — award date passed",IF(U177-TODAY()<=30,"At risk — close to off track","On track"))),IF(X177="","No planned date",IF(AND(TODAY()>X177,OR(Z177="",Z177<100)),"Behind — past end date",IF(AND(T177<>"",X177<>"",Z177<>"",(Z177<100),((TODAY()-T177)/MAX(X177-T177,1)*100)-Z177>15),"Behind — progress lag",IF(AND(X177-TODAY()<=30,X177-TODAY()>=0,OR(Z177="",Z177<90)),"At risk — close to off track","On track")))))))) | IF(OR(F177="",AC177="Completed / Handover",AC177="Cancelled"),"",IF(O177="Not awarded",IF(U177<>"",U177-TODAY(),IF(X177="","",X177-TODAY())),IF(X177="","",X177-TODAY()))) | [8 empty] | 2025-10-12 | 2025-10-12 | 2026-10-11 |  |  |  | IF(OR(F177="",AJ177=""),"",IF(COUNT(AI177:AI177)=0,"",AJ177-LOOKUP(2,1/(AI177:AI177<>""),AI177:AI177))) | IF(OR(F177="",AK177=""),"",IF(COUNT(AI177:AJ177)=0,"",AK177-LOOKUP(2,1/(AI177:AJ177<>""),AI177:AJ177))) | IF(OR(F177="",AL177=""),"",IF(COUNT(AI177:AK177)=0,"",AL177-LOOKUP(2,1/(AI177:AK177<>""),AI177:AK177))) | IF(OR(F177="",AM177=""),"",IF(COUNT(AI177:AL177)=0,"",AM177-LOOKUP(2,1/(AI177:AL177<>""),AI177:AL177))) | IF(OR(F177="",AN177=""),"",IF(COUNT(AI177:AM177)=0,"",AN177-LOOKUP(2,1/(AI177:AM177<>""),AI177:AM177))) | IF(OR(F177="",AO177=""),"",IF(COUNT(AI177:AN177)=0,"",AO177-LOOKUP(2,1/(AI177:AN177<>""),AI177:AN177))) | IF(OR(F177="",AP177=""),"",IF(COUNT(AI177:AO177)=0,"",AP177-LOOKUP(2,1/(AI177:AO177<>""),AI177:AO177))) | IF(OR(F177="",AQ177=""),"",IF(COUNT(AI177:AP177)=0,"",AQ177-LOOKUP(2,1/(AI177:AP177<>""),AI177:AP177))) | IF(OR(F177="",AR177=""),"",IF(COUNT(AI177:AQ177)=0,"",AR177-LOOKUP(2,1/(AI177:AQ177<>""),AI177:AQ177))) | IF(OR(F177="",AS177=""),"",IF(COUNT(AI177:AR177)=0,"",AS177-LOOKUP(2,1/(AI177:AR177<>""),AI177:AR177))) | IF(OR(F177="",AT177=""),"",IF(COUNT(AI177:AS177)=0,"",AT177-LOOKUP(2,1/(AI177:AS177<>""),AI177:AS177))) | IF(OR(F177="",AU177=""),"",IF(COUNT(AI177:AT177)=0,"",AU177-LOOKUP(2,1/(AI177:AT177<>""),AI177:AT177))) | IF(OR(F177="",AV177=""),"",IF(COUNT(AI177:AU177)=0,"",AV177-LOOKUP(2,1/(AI177:AU177<>""),AI177:AU177))) | IF(J177="","All_Provinces",IFERROR(VLOOKUP(J177,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K177="","All_Districts",IFERROR(VLOOKUP(K177,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F178="","",ROW()-3) | AF2-IS-21 | Package # 21-AF2 IS: Rehabilitation of Markazi Ziruk and Mulakh canal irrigation schemes, located in Ziruk and Yousaf Khil districts of Pakteka province. | 1 of 2 | AF2-IS-A-021 | Markazi Ziruk Irrigation Scheme (Off & On-Farm Project) | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Pakteka | Ziruk | Markazi Ziruk | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Farhad Matoonyar Construction Company (FMCC) | 038/2026 | 94650.11 | IF(AQ178="","",AQ178) |  | 12 | 2027-06-05 | IF(W178<>"",W178,IF(OR(T178="",V178=""),"",EDATE(T178,V178))) |  | 20 | Under Construction | on track and will be completed by June 2027 | IF(F178="","",IF(COUNT(AI178:AV178)=0,IF(AA178="","Not started",AA178),SUBSTITUTE(LOOKUP(2,1/(AI178:AV178<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F178="",COUNT(AI178:AV178)=0),"",TODAY()-LOOKUP(2,1/(AI178:AV178<>""),AI178:AV178)) | IF(OR(F178="",COUNT(AI178:AV178)<2),"",LOOKUP(2,1/(AI178:AV178<>""),AI178:AV178)-MIN(AI178:AV178)) | IF(OR(AD178="",AC178="Not started",AC178=""),"",IFERROR(AD178-IF(VLOOKUP(AC178,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC178,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F178="","",IF(OR(AA178="Cancelled",AC178="Cancelled"),"Cancelled",IF(OR(AC178="Completed / Handover",Y178<>"",Z178>=100),"Completed — on track",IF(O178="Not awarded",IF(U178="",IF(X178="","No planned date",IF(TODAY()>X178,"Behind — past planned date",IF(X178-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U178,"Behind — award date passed",IF(U178-TODAY()<=30,"At risk — close to off track","On track"))),IF(X178="","No planned date",IF(AND(TODAY()>X178,OR(Z178="",Z178<100)),"Behind — past end date",IF(AND(T178<>"",X178<>"",Z178<>"",(Z178<100),((TODAY()-T178)/MAX(X178-T178,1)*100)-Z178>15),"Behind — progress lag",IF(AND(X178-TODAY()<=30,X178-TODAY()>=0,OR(Z178="",Z178<90)),"At risk — close to off track","On track")))))))) | IF(OR(F178="",AC178="Completed / Handover",AC178="Cancelled"),"",IF(O178="Not awarded",IF(U178<>"",U178-TODAY(),IF(X178="","",X178-TODAY())),IF(X178="","",X178-TODAY()))) | [8 empty] | 2026-06-06 | 2026-06-06 |  |  |  |  | IF(OR(F178="",AJ178=""),"",IF(COUNT(AI178:AI178)=0,"",AJ178-LOOKUP(2,1/(AI178:AI178<>""),AI178:AI178))) | IF(OR(F178="",AK178=""),"",IF(COUNT(AI178:AJ178)=0,"",AK178-LOOKUP(2,1/(AI178:AJ178<>""),AI178:AJ178))) | IF(OR(F178="",AL178=""),"",IF(COUNT(AI178:AK178)=0,"",AL178-LOOKUP(2,1/(AI178:AK178<>""),AI178:AK178))) | IF(OR(F178="",AM178=""),"",IF(COUNT(AI178:AL178)=0,"",AM178-LOOKUP(2,1/(AI178:AL178<>""),AI178:AL178))) | IF(OR(F178="",AN178=""),"",IF(COUNT(AI178:AM178)=0,"",AN178-LOOKUP(2,1/(AI178:AM178<>""),AI178:AM178))) | IF(OR(F178="",AO178=""),"",IF(COUNT(AI178:AN178)=0,"",AO178-LOOKUP(2,1/(AI178:AN178<>""),AI178:AN178))) | IF(OR(F178="",AP178=""),"",IF(COUNT(AI178:AO178)=0,"",AP178-LOOKUP(2,1/(AI178:AO178<>""),AI178:AO178))) | IF(OR(F178="",AQ178=""),"",IF(COUNT(AI178:AP178)=0,"",AQ178-LOOKUP(2,1/(AI178:AP178<>""),AI178:AP178))) | IF(OR(F178="",AR178=""),"",IF(COUNT(AI178:AQ178)=0,"",AR178-LOOKUP(2,1/(AI178:AQ178<>""),AI178:AQ178))) | IF(OR(F178="",AS178=""),"",IF(COUNT(AI178:AR178)=0,"",AS178-LOOKUP(2,1/(AI178:AR178<>""),AI178:AR178))) | IF(OR(F178="",AT178=""),"",IF(COUNT(AI178:AS178)=0,"",AT178-LOOKUP(2,1/(AI178:AS178<>""),AI178:AS178))) | IF(OR(F178="",AU178=""),"",IF(COUNT(AI178:AT178)=0,"",AU178-LOOKUP(2,1/(AI178:AT178<>""),AI178:AT178))) | IF(OR(F178="",AV178=""),"",IF(COUNT(AI178:AU178)=0,"",AV178-LOOKUP(2,1/(AI178:AU178<>""),AI178:AU178))) | IF(J178="","All_Provinces",IFERROR(VLOOKUP(J178,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K178="","All_Districts",IFERROR(VLOOKUP(K178,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F179="","",ROW()-3) | AF2-IS-21 | Package # 21-AF2 IS: Rehabilitation of Markazi Ziruk and Mulakh canal irrigation schemes, located in Ziruk and Yousaf Khil districts of Pakteka province. | 2 of 2 | AF2-IS-A-022 | Mulakh Irrigation Scheme (On- Farm Project) | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez |  | Yousaf Khil | Mest | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Farhad Matoonyar Construction Company (FMCC) | 038/2026 | 239482.14 | IF(AQ179="","",AQ179) |  | 12 | 2027-06-05 | IF(W179<>"",W179,IF(OR(T179="",V179=""),"",EDATE(T179,V179))) |  | 30 | Under Construction | on track and will be completed by June 2027 | IF(F179="","",IF(COUNT(AI179:AV179)=0,IF(AA179="","Not started",AA179),SUBSTITUTE(LOOKUP(2,1/(AI179:AV179<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F179="",COUNT(AI179:AV179)=0),"",TODAY()-LOOKUP(2,1/(AI179:AV179<>""),AI179:AV179)) | IF(OR(F179="",COUNT(AI179:AV179)<2),"",LOOKUP(2,1/(AI179:AV179<>""),AI179:AV179)-MIN(AI179:AV179)) | IF(OR(AD179="",AC179="Not started",AC179=""),"",IFERROR(AD179-IF(VLOOKUP(AC179,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC179,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F179="","",IF(OR(AA179="Cancelled",AC179="Cancelled"),"Cancelled",IF(OR(AC179="Completed / Handover",Y179<>"",Z179>=100),"Completed — on track",IF(O179="Not awarded",IF(U179="",IF(X179="","No planned date",IF(TODAY()>X179,"Behind — past planned date",IF(X179-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U179,"Behind — award date passed",IF(U179-TODAY()<=30,"At risk — close to off track","On track"))),IF(X179="","No planned date",IF(AND(TODAY()>X179,OR(Z179="",Z179<100)),"Behind — past end date",IF(AND(T179<>"",X179<>"",Z179<>"",(Z179<100),((TODAY()-T179)/MAX(X179-T179,1)*100)-Z179>15),"Behind — progress lag",IF(AND(X179-TODAY()<=30,X179-TODAY()>=0,OR(Z179="",Z179<90)),"At risk — close to off track","On track")))))))) | IF(OR(F179="",AC179="Completed / Handover",AC179="Cancelled"),"",IF(O179="Not awarded",IF(U179<>"",U179-TODAY(),IF(X179="","",X179-TODAY())),IF(X179="","",X179-TODAY()))) | [8 empty] | 2026-06-06 | 2026-06-06 |  |  |  |  | IF(OR(F179="",AJ179=""),"",IF(COUNT(AI179:AI179)=0,"",AJ179-LOOKUP(2,1/(AI179:AI179<>""),AI179:AI179))) | IF(OR(F179="",AK179=""),"",IF(COUNT(AI179:AJ179)=0,"",AK179-LOOKUP(2,1/(AI179:AJ179<>""),AI179:AJ179))) | IF(OR(F179="",AL179=""),"",IF(COUNT(AI179:AK179)=0,"",AL179-LOOKUP(2,1/(AI179:AK179<>""),AI179:AK179))) | IF(OR(F179="",AM179=""),"",IF(COUNT(AI179:AL179)=0,"",AM179-LOOKUP(2,1/(AI179:AL179<>""),AI179:AL179))) | IF(OR(F179="",AN179=""),"",IF(COUNT(AI179:AM179)=0,"",AN179-LOOKUP(2,1/(AI179:AM179<>""),AI179:AM179))) | IF(OR(F179="",AO179=""),"",IF(COUNT(AI179:AN179)=0,"",AO179-LOOKUP(2,1/(AI179:AN179<>""),AI179:AN179))) | IF(OR(F179="",AP179=""),"",IF(COUNT(AI179:AO179)=0,"",AP179-LOOKUP(2,1/(AI179:AO179<>""),AI179:AO179))) | IF(OR(F179="",AQ179=""),"",IF(COUNT(AI179:AP179)=0,"",AQ179-LOOKUP(2,1/(AI179:AP179<>""),AI179:AP179))) | IF(OR(F179="",AR179=""),"",IF(COUNT(AI179:AQ179)=0,"",AR179-LOOKUP(2,1/(AI179:AQ179<>""),AI179:AQ179))) | IF(OR(F179="",AS179=""),"",IF(COUNT(AI179:AR179)=0,"",AS179-LOOKUP(2,1/(AI179:AR179<>""),AI179:AR179))) | IF(OR(F179="",AT179=""),"",IF(COUNT(AI179:AS179)=0,"",AT179-LOOKUP(2,1/(AI179:AS179<>""),AI179:AS179))) | IF(OR(F179="",AU179=""),"",IF(COUNT(AI179:AT179)=0,"",AU179-LOOKUP(2,1/(AI179:AT179<>""),AI179:AT179))) | IF(OR(F179="",AV179=""),"",IF(COUNT(AI179:AU179)=0,"",AV179-LOOKUP(2,1/(AI179:AU179<>""),AI179:AU179))) | IF(J179="","All_Provinces",IFERROR(VLOOKUP(J179,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K179="","All_Districts",IFERROR(VLOOKUP(K179,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F180="","",ROW()-3) | AF2-IS-22 | Package # 22-AF2 IS: Rehabilitation of Gero canal irrigation scheme, located in Center and Qarabagh districts of Ghazni province. | 1 of 1 | AF2-IS-N-016 | Gero Irrigation Scheme (Off & On-Farm Project) Gero&Qarabagh | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Ghazni | Center | Gero | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 290000 | IF(AQ180="","",AQ180) | 2026-12-28 | 9.9 | 2027-10-24 | IF(W180<>"",W180,IF(OR(T180="",V180=""),"",EDATE(T180,V180))) |  |  | Under LTO Review | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals in two districts | IF(F180="","",IF(COUNT(AI180:AV180)=0,IF(AA180="","Not started",AA180),SUBSTITUTE(LOOKUP(2,1/(AI180:AV180<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F180="",COUNT(AI180:AV180)=0),"",TODAY()-LOOKUP(2,1/(AI180:AV180<>""),AI180:AV180)) | IF(OR(F180="",COUNT(AI180:AV180)<2),"",LOOKUP(2,1/(AI180:AV180<>""),AI180:AV180)-MIN(AI180:AV180)) | IF(OR(AD180="",AC180="Not started",AC180=""),"",IFERROR(AD180-IF(VLOOKUP(AC180,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC180,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F180="","",IF(OR(AA180="Cancelled",AC180="Cancelled"),"Cancelled",IF(OR(AC180="Completed / Handover",Y180<>"",Z180>=100),"Completed — on track",IF(O180="Not awarded",IF(U180="",IF(X180="","No planned date",IF(TODAY()>X180,"Behind — past planned date",IF(X180-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U180,"Behind — award date passed",IF(U180-TODAY()<=30,"At risk — close to off track","On track"))),IF(X180="","No planned date",IF(AND(TODAY()>X180,OR(Z180="",Z180<100)),"Behind — past end date",IF(AND(T180<>"",X180<>"",Z180<>"",(Z180<100),((TODAY()-T180)/MAX(X180-T180,1)*100)-Z180>15),"Behind — progress lag",IF(AND(X180-TODAY()<=30,X180-TODAY()>=0,OR(Z180="",Z180<90)),"At risk — close to off track","On track")))))))) | IF(OR(F180="",AC180="Completed / Handover",AC180="Cancelled"),"",IF(O180="Not awarded",IF(U180<>"",U180-TODAY(),IF(X180="","",X180-TODAY())),IF(X180="","",X180-TODAY()))) | [14 empty] | IF(OR(F180="",AJ180=""),"",IF(COUNT(AI180:AI180)=0,"",AJ180-LOOKUP(2,1/(AI180:AI180<>""),AI180:AI180))) | IF(OR(F180="",AK180=""),"",IF(COUNT(AI180:AJ180)=0,"",AK180-LOOKUP(2,1/(AI180:AJ180<>""),AI180:AJ180))) | IF(OR(F180="",AL180=""),"",IF(COUNT(AI180:AK180)=0,"",AL180-LOOKUP(2,1/(AI180:AK180<>""),AI180:AK180))) | IF(OR(F180="",AM180=""),"",IF(COUNT(AI180:AL180)=0,"",AM180-LOOKUP(2,1/(AI180:AL180<>""),AI180:AL180))) | IF(OR(F180="",AN180=""),"",IF(COUNT(AI180:AM180)=0,"",AN180-LOOKUP(2,1/(AI180:AM180<>""),AI180:AM180))) | IF(OR(F180="",AO180=""),"",IF(COUNT(AI180:AN180)=0,"",AO180-LOOKUP(2,1/(AI180:AN180<>""),AI180:AN180))) | IF(OR(F180="",AP180=""),"",IF(COUNT(AI180:AO180)=0,"",AP180-LOOKUP(2,1/(AI180:AO180<>""),AI180:AO180))) | IF(OR(F180="",AQ180=""),"",IF(COUNT(AI180:AP180)=0,"",AQ180-LOOKUP(2,1/(AI180:AP180<>""),AI180:AP180))) | IF(OR(F180="",AR180=""),"",IF(COUNT(AI180:AQ180)=0,"",AR180-LOOKUP(2,1/(AI180:AQ180<>""),AI180:AQ180))) | IF(OR(F180="",AS180=""),"",IF(COUNT(AI180:AR180)=0,"",AS180-LOOKUP(2,1/(AI180:AR180<>""),AI180:AR180))) | IF(OR(F180="",AT180=""),"",IF(COUNT(AI180:AS180)=0,"",AT180-LOOKUP(2,1/(AI180:AS180<>""),AI180:AS180))) | IF(OR(F180="",AU180=""),"",IF(COUNT(AI180:AT180)=0,"",AU180-LOOKUP(2,1/(AI180:AT180<>""),AI180:AT180))) | IF(OR(F180="",AV180=""),"",IF(COUNT(AI180:AU180)=0,"",AV180-LOOKUP(2,1/(AI180:AU180<>""),AI180:AU180))) | IF(J180="","All_Provinces",IFERROR(VLOOKUP(J180,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K180="","All_Districts",IFERROR(VLOOKUP(K180,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F181="","",ROW()-3) | AF2-IS-23 | Package #23-AF2 IS: Rehabilitation of Patab canal irrigation schemes, located in Khas Urozgan of Urozgan province. | 1 of 1 | AF2-IS-N-017 | Patab Irrigation Schem | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Urozgan | Khas Urozgan | Patab | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 290442.55 | IF(AQ181="","",AQ181) | 2026-12-15 | 8.9 | 2027-09-11 | IF(W181<>"",W181,IF(OR(T181="",V181=""),"",EDATE(T181,V181))) |  |  | Retendered (Re-ITB) | The submitted work plan to be revised | IF(F181="","",IF(COUNT(AI181:AV181)=0,IF(AA181="","Not started",AA181),SUBSTITUTE(LOOKUP(2,1/(AI181:AV181<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F181="",COUNT(AI181:AV181)=0),"",TODAY()-LOOKUP(2,1/(AI181:AV181<>""),AI181:AV181)) | IF(OR(F181="",COUNT(AI181:AV181)<2),"",LOOKUP(2,1/(AI181:AV181<>""),AI181:AV181)-MIN(AI181:AV181)) | IF(OR(AD181="",AC181="Not started",AC181=""),"",IFERROR(AD181-IF(VLOOKUP(AC181,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC181,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F181="","",IF(OR(AA181="Cancelled",AC181="Cancelled"),"Cancelled",IF(OR(AC181="Completed / Handover",Y181<>"",Z181>=100),"Completed — on track",IF(O181="Not awarded",IF(U181="",IF(X181="","No planned date",IF(TODAY()>X181,"Behind — past planned date",IF(X181-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U181,"Behind — award date passed",IF(U181-TODAY()<=30,"At risk — close to off track","On track"))),IF(X181="","No planned date",IF(AND(TODAY()>X181,OR(Z181="",Z181<100)),"Behind — past end date",IF(AND(T181<>"",X181<>"",Z181<>"",(Z181<100),((TODAY()-T181)/MAX(X181-T181,1)*100)-Z181>15),"Behind — progress lag",IF(AND(X181-TODAY()<=30,X181-TODAY()>=0,OR(Z181="",Z181<90)),"At risk — close to off track","On track")))))))) | IF(OR(F181="",AC181="Completed / Handover",AC181="Cancelled"),"",IF(O181="Not awarded",IF(U181<>"",U181-TODAY(),IF(X181="","",X181-TODAY())),IF(X181="","",X181-TODAY()))) | [14 empty] | IF(OR(F181="",AJ181=""),"",IF(COUNT(AI181:AI181)=0,"",AJ181-LOOKUP(2,1/(AI181:AI181<>""),AI181:AI181))) | IF(OR(F181="",AK181=""),"",IF(COUNT(AI181:AJ181)=0,"",AK181-LOOKUP(2,1/(AI181:AJ181<>""),AI181:AJ181))) | IF(OR(F181="",AL181=""),"",IF(COUNT(AI181:AK181)=0,"",AL181-LOOKUP(2,1/(AI181:AK181<>""),AI181:AK181))) | IF(OR(F181="",AM181=""),"",IF(COUNT(AI181:AL181)=0,"",AM181-LOOKUP(2,1/(AI181:AL181<>""),AI181:AL181))) | IF(OR(F181="",AN181=""),"",IF(COUNT(AI181:AM181)=0,"",AN181-LOOKUP(2,1/(AI181:AM181<>""),AI181:AM181))) | IF(OR(F181="",AO181=""),"",IF(COUNT(AI181:AN181)=0,"",AO181-LOOKUP(2,1/(AI181:AN181<>""),AI181:AN181))) | IF(OR(F181="",AP181=""),"",IF(COUNT(AI181:AO181)=0,"",AP181-LOOKUP(2,1/(AI181:AO181<>""),AI181:AO181))) | IF(OR(F181="",AQ181=""),"",IF(COUNT(AI181:AP181)=0,"",AQ181-LOOKUP(2,1/(AI181:AP181<>""),AI181:AP181))) | IF(OR(F181="",AR181=""),"",IF(COUNT(AI181:AQ181)=0,"",AR181-LOOKUP(2,1/(AI181:AQ181<>""),AI181:AQ181))) | IF(OR(F181="",AS181=""),"",IF(COUNT(AI181:AR181)=0,"",AS181-LOOKUP(2,1/(AI181:AR181<>""),AI181:AR181))) | IF(OR(F181="",AT181=""),"",IF(COUNT(AI181:AS181)=0,"",AT181-LOOKUP(2,1/(AI181:AS181<>""),AI181:AS181))) | IF(OR(F181="",AU181=""),"",IF(COUNT(AI181:AT181)=0,"",AU181-LOOKUP(2,1/(AI181:AT181<>""),AI181:AT181))) | IF(OR(F181="",AV181=""),"",IF(COUNT(AI181:AU181)=0,"",AV181-LOOKUP(2,1/(AI181:AU181<>""),AI181:AU181))) | IF(J181="","All_Provinces",IFERROR(VLOOKUP(J181,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K181="","All_Districts",IFERROR(VLOOKUP(K181,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F182="","",ROW()-3) | AF2-IS-24 | Package #24-AF2 IS: Rehabilitation of Shajoy canal irrigation scheme, located in Dayee Chopan districts of Zabul province. | 1 of 1 | AF2-IS-N-018 | Shajoy Canal Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Zabul | Dayee Chopan | - | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 155000 | IF(AQ182="","",AQ182) | 2026-12-20 | 8.9 | 2027-09-16 | IF(W182<>"",W182,IF(OR(T182="",V182=""),"",EDATE(T182,V182))) |  |  | Under Design | Three months slack period Jan-Mar during winter. Six months construction period required for two canals in two districts. Explore splitting into two lots and if one lot ready then raise PR. | IF(F182="","",IF(COUNT(AI182:AV182)=0,IF(AA182="","Not started",AA182),SUBSTITUTE(LOOKUP(2,1/(AI182:AV182<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F182="",COUNT(AI182:AV182)=0),"",TODAY()-LOOKUP(2,1/(AI182:AV182<>""),AI182:AV182)) | IF(OR(F182="",COUNT(AI182:AV182)<2),"",LOOKUP(2,1/(AI182:AV182<>""),AI182:AV182)-MIN(AI182:AV182)) | IF(OR(AD182="",AC182="Not started",AC182=""),"",IFERROR(AD182-IF(VLOOKUP(AC182,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC182,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F182="","",IF(OR(AA182="Cancelled",AC182="Cancelled"),"Cancelled",IF(OR(AC182="Completed / Handover",Y182<>"",Z182>=100),"Completed — on track",IF(O182="Not awarded",IF(U182="",IF(X182="","No planned date",IF(TODAY()>X182,"Behind — past planned date",IF(X182-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U182,"Behind — award date passed",IF(U182-TODAY()<=30,"At risk — close to off track","On track"))),IF(X182="","No planned date",IF(AND(TODAY()>X182,OR(Z182="",Z182<100)),"Behind — past end date",IF(AND(T182<>"",X182<>"",Z182<>"",(Z182<100),((TODAY()-T182)/MAX(X182-T182,1)*100)-Z182>15),"Behind — progress lag",IF(AND(X182-TODAY()<=30,X182-TODAY()>=0,OR(Z182="",Z182<90)),"At risk — close to off track","On track")))))))) | IF(OR(F182="",AC182="Completed / Handover",AC182="Cancelled"),"",IF(O182="Not awarded",IF(U182<>"",U182-TODAY(),IF(X182="","",X182-TODAY())),IF(X182="","",X182-TODAY()))) | [14 empty] | IF(OR(F182="",AJ182=""),"",IF(COUNT(AI182:AI182)=0,"",AJ182-LOOKUP(2,1/(AI182:AI182<>""),AI182:AI182))) | IF(OR(F182="",AK182=""),"",IF(COUNT(AI182:AJ182)=0,"",AK182-LOOKUP(2,1/(AI182:AJ182<>""),AI182:AJ182))) | IF(OR(F182="",AL182=""),"",IF(COUNT(AI182:AK182)=0,"",AL182-LOOKUP(2,1/(AI182:AK182<>""),AI182:AK182))) | IF(OR(F182="",AM182=""),"",IF(COUNT(AI182:AL182)=0,"",AM182-LOOKUP(2,1/(AI182:AL182<>""),AI182:AL182))) | IF(OR(F182="",AN182=""),"",IF(COUNT(AI182:AM182)=0,"",AN182-LOOKUP(2,1/(AI182:AM182<>""),AI182:AM182))) | IF(OR(F182="",AO182=""),"",IF(COUNT(AI182:AN182)=0,"",AO182-LOOKUP(2,1/(AI182:AN182<>""),AI182:AN182))) | IF(OR(F182="",AP182=""),"",IF(COUNT(AI182:AO182)=0,"",AP182-LOOKUP(2,1/(AI182:AO182<>""),AI182:AO182))) | IF(OR(F182="",AQ182=""),"",IF(COUNT(AI182:AP182)=0,"",AQ182-LOOKUP(2,1/(AI182:AP182<>""),AI182:AP182))) | IF(OR(F182="",AR182=""),"",IF(COUNT(AI182:AQ182)=0,"",AR182-LOOKUP(2,1/(AI182:AQ182<>""),AI182:AQ182))) | IF(OR(F182="",AS182=""),"",IF(COUNT(AI182:AR182)=0,"",AS182-LOOKUP(2,1/(AI182:AR182<>""),AI182:AR182))) | IF(OR(F182="",AT182=""),"",IF(COUNT(AI182:AS182)=0,"",AT182-LOOKUP(2,1/(AI182:AS182<>""),AI182:AS182))) | IF(OR(F182="",AU182=""),"",IF(COUNT(AI182:AT182)=0,"",AU182-LOOKUP(2,1/(AI182:AT182<>""),AI182:AT182))) | IF(OR(F182="",AV182=""),"",IF(COUNT(AI182:AU182)=0,"",AV182-LOOKUP(2,1/(AI182:AU182<>""),AI182:AU182))) | IF(J182="","All_Provinces",IFERROR(VLOOKUP(J182,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K182="","All_Districts",IFERROR(VLOOKUP(K182,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F183="","",ROW()-3) | AF2-IS-25 | Package #25-AF2 IS: Rehabilitation of Urdo Kas canal and Sarkay Lazhey canal irrigation schemes, located in Sha Wali Kot and Boldak districts of Kandahar province. | 1 of 2 | AF2-IS-A-023 | Sarkay Lazhey Canal Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Boldak | Sarkay Lazhey | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Wasif Construction Company | 012/2026 | 235424.79 | IF(AQ183="","",AQ183) |  | 9.9 | 2026-12-08 | IF(W183<>"",W183,IF(OR(T183="",V183=""),"",EDATE(T183,V183))) |  | 10 | Under Construction | Needs NCE and work will be completed by June 2027 | IF(F183="","",IF(COUNT(AI183:AV183)=0,IF(AA183="","Not started",AA183),SUBSTITUTE(LOOKUP(2,1/(AI183:AV183<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F183="",COUNT(AI183:AV183)=0),"",TODAY()-LOOKUP(2,1/(AI183:AV183<>""),AI183:AV183)) | IF(OR(F183="",COUNT(AI183:AV183)<2),"",LOOKUP(2,1/(AI183:AV183<>""),AI183:AV183)-MIN(AI183:AV183)) | IF(OR(AD183="",AC183="Not started",AC183=""),"",IFERROR(AD183-IF(VLOOKUP(AC183,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC183,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F183="","",IF(OR(AA183="Cancelled",AC183="Cancelled"),"Cancelled",IF(OR(AC183="Completed / Handover",Y183<>"",Z183>=100),"Completed — on track",IF(O183="Not awarded",IF(U183="",IF(X183="","No planned date",IF(TODAY()>X183,"Behind — past planned date",IF(X183-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U183,"Behind — award date passed",IF(U183-TODAY()<=30,"At risk — close to off track","On track"))),IF(X183="","No planned date",IF(AND(TODAY()>X183,OR(Z183="",Z183<100)),"Behind — past end date",IF(AND(T183<>"",X183<>"",Z183<>"",(Z183<100),((TODAY()-T183)/MAX(X183-T183,1)*100)-Z183>15),"Behind — progress lag",IF(AND(X183-TODAY()<=30,X183-TODAY()>=0,OR(Z183="",Z183<90)),"At risk — close to off track","On track")))))))) | IF(OR(F183="",AC183="Completed / Handover",AC183="Cancelled"),"",IF(O183="Not awarded",IF(U183<>"",U183-TODAY(),IF(X183="","",X183-TODAY())),IF(X183="","",X183-TODAY()))) | [8 empty] | 2026-02-09 | 2026-02-09 |  |  |  |  | IF(OR(F183="",AJ183=""),"",IF(COUNT(AI183:AI183)=0,"",AJ183-LOOKUP(2,1/(AI183:AI183<>""),AI183:AI183))) | IF(OR(F183="",AK183=""),"",IF(COUNT(AI183:AJ183)=0,"",AK183-LOOKUP(2,1/(AI183:AJ183<>""),AI183:AJ183))) | IF(OR(F183="",AL183=""),"",IF(COUNT(AI183:AK183)=0,"",AL183-LOOKUP(2,1/(AI183:AK183<>""),AI183:AK183))) | IF(OR(F183="",AM183=""),"",IF(COUNT(AI183:AL183)=0,"",AM183-LOOKUP(2,1/(AI183:AL183<>""),AI183:AL183))) | IF(OR(F183="",AN183=""),"",IF(COUNT(AI183:AM183)=0,"",AN183-LOOKUP(2,1/(AI183:AM183<>""),AI183:AM183))) | IF(OR(F183="",AO183=""),"",IF(COUNT(AI183:AN183)=0,"",AO183-LOOKUP(2,1/(AI183:AN183<>""),AI183:AN183))) | IF(OR(F183="",AP183=""),"",IF(COUNT(AI183:AO183)=0,"",AP183-LOOKUP(2,1/(AI183:AO183<>""),AI183:AO183))) | IF(OR(F183="",AQ183=""),"",IF(COUNT(AI183:AP183)=0,"",AQ183-LOOKUP(2,1/(AI183:AP183<>""),AI183:AP183))) | IF(OR(F183="",AR183=""),"",IF(COUNT(AI183:AQ183)=0,"",AR183-LOOKUP(2,1/(AI183:AQ183<>""),AI183:AQ183))) | IF(OR(F183="",AS183=""),"",IF(COUNT(AI183:AR183)=0,"",AS183-LOOKUP(2,1/(AI183:AR183<>""),AI183:AR183))) | IF(OR(F183="",AT183=""),"",IF(COUNT(AI183:AS183)=0,"",AT183-LOOKUP(2,1/(AI183:AS183<>""),AI183:AS183))) | IF(OR(F183="",AU183=""),"",IF(COUNT(AI183:AT183)=0,"",AU183-LOOKUP(2,1/(AI183:AT183<>""),AI183:AT183))) | IF(OR(F183="",AV183=""),"",IF(COUNT(AI183:AU183)=0,"",AV183-LOOKUP(2,1/(AI183:AU183<>""),AI183:AU183))) | IF(J183="","All_Provinces",IFERROR(VLOOKUP(J183,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K183="","All_Districts",IFERROR(VLOOKUP(K183,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F184="","",ROW()-3) | AF2-IS-25 | Package #25-AF2 IS: Rehabilitation of Urdo Kas canal and Sarkay Lazhey canal irrigation schemes, located in Sha Wali Kot and Boldak districts of Kandahar province. | 2 of 2 | AF2-IS-A-024 | Urdo Kas Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Sha Wali Kot | Urdo Kas | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Wasif Construction Company | 012/2026 | 90157.45 | IF(AQ184="","",AQ184) |  | 9.9 | 2026-12-08 | IF(W184<>"",W184,IF(OR(T184="",V184=""),"",EDATE(T184,V184))) |  | 15 | Under Construction | Needs NCE and work will be completed by June 2027 | IF(F184="","",IF(COUNT(AI184:AV184)=0,IF(AA184="","Not started",AA184),SUBSTITUTE(LOOKUP(2,1/(AI184:AV184<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F184="",COUNT(AI184:AV184)=0),"",TODAY()-LOOKUP(2,1/(AI184:AV184<>""),AI184:AV184)) | IF(OR(F184="",COUNT(AI184:AV184)<2),"",LOOKUP(2,1/(AI184:AV184<>""),AI184:AV184)-MIN(AI184:AV184)) | IF(OR(AD184="",AC184="Not started",AC184=""),"",IFERROR(AD184-IF(VLOOKUP(AC184,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC184,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F184="","",IF(OR(AA184="Cancelled",AC184="Cancelled"),"Cancelled",IF(OR(AC184="Completed / Handover",Y184<>"",Z184>=100),"Completed — on track",IF(O184="Not awarded",IF(U184="",IF(X184="","No planned date",IF(TODAY()>X184,"Behind — past planned date",IF(X184-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U184,"Behind — award date passed",IF(U184-TODAY()<=30,"At risk — close to off track","On track"))),IF(X184="","No planned date",IF(AND(TODAY()>X184,OR(Z184="",Z184<100)),"Behind — past end date",IF(AND(T184<>"",X184<>"",Z184<>"",(Z184<100),((TODAY()-T184)/MAX(X184-T184,1)*100)-Z184>15),"Behind — progress lag",IF(AND(X184-TODAY()<=30,X184-TODAY()>=0,OR(Z184="",Z184<90)),"At risk — close to off track","On track")))))))) | IF(OR(F184="",AC184="Completed / Handover",AC184="Cancelled"),"",IF(O184="Not awarded",IF(U184<>"",U184-TODAY(),IF(X184="","",X184-TODAY())),IF(X184="","",X184-TODAY()))) | [8 empty] | 2026-02-09 | 2026-02-09 |  |  |  |  | IF(OR(F184="",AJ184=""),"",IF(COUNT(AI184:AI184)=0,"",AJ184-LOOKUP(2,1/(AI184:AI184<>""),AI184:AI184))) | IF(OR(F184="",AK184=""),"",IF(COUNT(AI184:AJ184)=0,"",AK184-LOOKUP(2,1/(AI184:AJ184<>""),AI184:AJ184))) | IF(OR(F184="",AL184=""),"",IF(COUNT(AI184:AK184)=0,"",AL184-LOOKUP(2,1/(AI184:AK184<>""),AI184:AK184))) | IF(OR(F184="",AM184=""),"",IF(COUNT(AI184:AL184)=0,"",AM184-LOOKUP(2,1/(AI184:AL184<>""),AI184:AL184))) | IF(OR(F184="",AN184=""),"",IF(COUNT(AI184:AM184)=0,"",AN184-LOOKUP(2,1/(AI184:AM184<>""),AI184:AM184))) | IF(OR(F184="",AO184=""),"",IF(COUNT(AI184:AN184)=0,"",AO184-LOOKUP(2,1/(AI184:AN184<>""),AI184:AN184))) | IF(OR(F184="",AP184=""),"",IF(COUNT(AI184:AO184)=0,"",AP184-LOOKUP(2,1/(AI184:AO184<>""),AI184:AO184))) | IF(OR(F184="",AQ184=""),"",IF(COUNT(AI184:AP184)=0,"",AQ184-LOOKUP(2,1/(AI184:AP184<>""),AI184:AP184))) | IF(OR(F184="",AR184=""),"",IF(COUNT(AI184:AQ184)=0,"",AR184-LOOKUP(2,1/(AI184:AQ184<>""),AI184:AQ184))) | IF(OR(F184="",AS184=""),"",IF(COUNT(AI184:AR184)=0,"",AS184-LOOKUP(2,1/(AI184:AR184<>""),AI184:AR184))) | IF(OR(F184="",AT184=""),"",IF(COUNT(AI184:AS184)=0,"",AT184-LOOKUP(2,1/(AI184:AS184<>""),AI184:AS184))) | IF(OR(F184="",AU184=""),"",IF(COUNT(AI184:AT184)=0,"",AU184-LOOKUP(2,1/(AI184:AT184<>""),AI184:AT184))) | IF(OR(F184="",AV184=""),"",IF(COUNT(AI184:AU184)=0,"",AV184-LOOKUP(2,1/(AI184:AU184<>""),AI184:AU184))) | IF(J184="","All_Provinces",IFERROR(VLOOKUP(J184,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K184="","All_Districts",IFERROR(VLOOKUP(K184,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F185="","",ROW()-3) | AF2-IS-26 | Package #26-AF2 IS: Rehabilitation of Sarwan Qala canal irrigation schemes, located in Sangin district of Kandahar province. | 1 of 1 | AF2-IS-A-025 | Sarwan Qala Canal Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Sangin | Sarwan Qala | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | New Safi Zada Construction & Road Building Company JV with Elyas Aryoubi Constructin Road building and Logistic Company (NSZ&EACC) | 019/2026 | 351552.71 | IF(AQ185="","",AQ185) |  | 12 | 2027-03-02 | IF(W185<>"",W185,IF(OR(T185="",V185=""),"",EDATE(T185,V185))) |  | 0 | Cancelled | package / contract cancelled | IF(F185="","",IF(COUNT(AI185:AV185)=0,IF(AA185="","Not started",AA185),SUBSTITUTE(LOOKUP(2,1/(AI185:AV185<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F185="",COUNT(AI185:AV185)=0),"",TODAY()-LOOKUP(2,1/(AI185:AV185<>""),AI185:AV185)) | IF(OR(F185="",COUNT(AI185:AV185)<2),"",LOOKUP(2,1/(AI185:AV185<>""),AI185:AV185)-MIN(AI185:AV185)) | IF(OR(AD185="",AC185="Not started",AC185=""),"",IFERROR(AD185-IF(VLOOKUP(AC185,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC185,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F185="","",IF(OR(AA185="Cancelled",AC185="Cancelled"),"Cancelled",IF(OR(AC185="Completed / Handover",Y185<>"",Z185>=100),"Completed — on track",IF(O185="Not awarded",IF(U185="",IF(X185="","No planned date",IF(TODAY()>X185,"Behind — past planned date",IF(X185-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U185,"Behind — award date passed",IF(U185-TODAY()<=30,"At risk — close to off track","On track"))),IF(X185="","No planned date",IF(AND(TODAY()>X185,OR(Z185="",Z185<100)),"Behind — past end date",IF(AND(T185<>"",X185<>"",Z185<>"",(Z185<100),((TODAY()-T185)/MAX(X185-T185,1)*100)-Z185>15),"Behind — progress lag",IF(AND(X185-TODAY()<=30,X185-TODAY()>=0,OR(Z185="",Z185<90)),"At risk — close to off track","On track")))))))) | IF(OR(F185="",AC185="Completed / Handover",AC185="Cancelled"),"",IF(O185="Not awarded",IF(U185<>"",U185-TODAY(),IF(X185="","",X185-TODAY())),IF(X185="","",X185-TODAY()))) | [8 empty] | 2026-03-03 | [5 empty] | IF(OR(F185="",AJ185=""),"",IF(COUNT(AI185:AI185)=0,"",AJ185-LOOKUP(2,1/(AI185:AI185<>""),AI185:AI185))) | IF(OR(F185="",AK185=""),"",IF(COUNT(AI185:AJ185)=0,"",AK185-LOOKUP(2,1/(AI185:AJ185<>""),AI185:AJ185))) | IF(OR(F185="",AL185=""),"",IF(COUNT(AI185:AK185)=0,"",AL185-LOOKUP(2,1/(AI185:AK185<>""),AI185:AK185))) | IF(OR(F185="",AM185=""),"",IF(COUNT(AI185:AL185)=0,"",AM185-LOOKUP(2,1/(AI185:AL185<>""),AI185:AL185))) | IF(OR(F185="",AN185=""),"",IF(COUNT(AI185:AM185)=0,"",AN185-LOOKUP(2,1/(AI185:AM185<>""),AI185:AM185))) | IF(OR(F185="",AO185=""),"",IF(COUNT(AI185:AN185)=0,"",AO185-LOOKUP(2,1/(AI185:AN185<>""),AI185:AN185))) | IF(OR(F185="",AP185=""),"",IF(COUNT(AI185:AO185)=0,"",AP185-LOOKUP(2,1/(AI185:AO185<>""),AI185:AO185))) | IF(OR(F185="",AQ185=""),"",IF(COUNT(AI185:AP185)=0,"",AQ185-LOOKUP(2,1/(AI185:AP185<>""),AI185:AP185))) | IF(OR(F185="",AR185=""),"",IF(COUNT(AI185:AQ185)=0,"",AR185-LOOKUP(2,1/(AI185:AQ185<>""),AI185:AQ185))) | IF(OR(F185="",AS185=""),"",IF(COUNT(AI185:AR185)=0,"",AS185-LOOKUP(2,1/(AI185:AR185<>""),AI185:AR185))) | IF(OR(F185="",AT185=""),"",IF(COUNT(AI185:AS185)=0,"",AT185-LOOKUP(2,1/(AI185:AS185<>""),AI185:AS185))) | IF(OR(F185="",AU185=""),"",IF(COUNT(AI185:AT185)=0,"",AU185-LOOKUP(2,1/(AI185:AT185<>""),AI185:AT185))) | IF(OR(F185="",AV185=""),"",IF(COUNT(AI185:AU185)=0,"",AV185-LOOKUP(2,1/(AI185:AU185<>""),AI185:AU185))) | IF(J185="","All_Provinces",IFERROR(VLOOKUP(J185,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K185="","All_Districts",IFERROR(VLOOKUP(K185,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F186="","",ROW()-3) | AF2-IS-27 | Package # 27-AF2 IS: Rehabilitation of Firozi canal irrigation scheme, located in Delaram districts of Nimroz province. | 1 of 1 | AF2-IS-N-019 | Firozi Canal Irrigation Schem | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Nimruz | Delaram | - | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 195000 | IF(AQ186="","",AQ186) | 2026-12-25 | 8.9 | 2027-09-21 | IF(W186<>"",W186,IF(OR(T186="",V186=""),"",EDATE(T186,V186))) |  |  | Under Review of WRI | Nine months construction period required for the canal | IF(F186="","",IF(COUNT(AI186:AV186)=0,IF(AA186="","Not started",AA186),SUBSTITUTE(LOOKUP(2,1/(AI186:AV186<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F186="",COUNT(AI186:AV186)=0),"",TODAY()-LOOKUP(2,1/(AI186:AV186<>""),AI186:AV186)) | IF(OR(F186="",COUNT(AI186:AV186)<2),"",LOOKUP(2,1/(AI186:AV186<>""),AI186:AV186)-MIN(AI186:AV186)) | IF(OR(AD186="",AC186="Not started",AC186=""),"",IFERROR(AD186-IF(VLOOKUP(AC186,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC186,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F186="","",IF(OR(AA186="Cancelled",AC186="Cancelled"),"Cancelled",IF(OR(AC186="Completed / Handover",Y186<>"",Z186>=100),"Completed — on track",IF(O186="Not awarded",IF(U186="",IF(X186="","No planned date",IF(TODAY()>X186,"Behind — past planned date",IF(X186-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U186,"Behind — award date passed",IF(U186-TODAY()<=30,"At risk — close to off track","On track"))),IF(X186="","No planned date",IF(AND(TODAY()>X186,OR(Z186="",Z186<100)),"Behind — past end date",IF(AND(T186<>"",X186<>"",Z186<>"",(Z186<100),((TODAY()-T186)/MAX(X186-T186,1)*100)-Z186>15),"Behind — progress lag",IF(AND(X186-TODAY()<=30,X186-TODAY()>=0,OR(Z186="",Z186<90)),"At risk — close to off track","On track")))))))) | IF(OR(F186="",AC186="Completed / Handover",AC186="Cancelled"),"",IF(O186="Not awarded",IF(U186<>"",U186-TODAY(),IF(X186="","",X186-TODAY())),IF(X186="","",X186-TODAY()))) | [14 empty] | IF(OR(F186="",AJ186=""),"",IF(COUNT(AI186:AI186)=0,"",AJ186-LOOKUP(2,1/(AI186:AI186<>""),AI186:AI186))) | IF(OR(F186="",AK186=""),"",IF(COUNT(AI186:AJ186)=0,"",AK186-LOOKUP(2,1/(AI186:AJ186<>""),AI186:AJ186))) | IF(OR(F186="",AL186=""),"",IF(COUNT(AI186:AK186)=0,"",AL186-LOOKUP(2,1/(AI186:AK186<>""),AI186:AK186))) | IF(OR(F186="",AM186=""),"",IF(COUNT(AI186:AL186)=0,"",AM186-LOOKUP(2,1/(AI186:AL186<>""),AI186:AL186))) | IF(OR(F186="",AN186=""),"",IF(COUNT(AI186:AM186)=0,"",AN186-LOOKUP(2,1/(AI186:AM186<>""),AI186:AM186))) | IF(OR(F186="",AO186=""),"",IF(COUNT(AI186:AN186)=0,"",AO186-LOOKUP(2,1/(AI186:AN186<>""),AI186:AN186))) | IF(OR(F186="",AP186=""),"",IF(COUNT(AI186:AO186)=0,"",AP186-LOOKUP(2,1/(AI186:AO186<>""),AI186:AO186))) | IF(OR(F186="",AQ186=""),"",IF(COUNT(AI186:AP186)=0,"",AQ186-LOOKUP(2,1/(AI186:AP186<>""),AI186:AP186))) | IF(OR(F186="",AR186=""),"",IF(COUNT(AI186:AQ186)=0,"",AR186-LOOKUP(2,1/(AI186:AQ186<>""),AI186:AQ186))) | IF(OR(F186="",AS186=""),"",IF(COUNT(AI186:AR186)=0,"",AS186-LOOKUP(2,1/(AI186:AR186<>""),AI186:AR186))) | IF(OR(F186="",AT186=""),"",IF(COUNT(AI186:AS186)=0,"",AT186-LOOKUP(2,1/(AI186:AS186<>""),AI186:AS186))) | IF(OR(F186="",AU186=""),"",IF(COUNT(AI186:AT186)=0,"",AU186-LOOKUP(2,1/(AI186:AT186<>""),AI186:AT186))) | IF(OR(F186="",AV186=""),"",IF(COUNT(AI186:AU186)=0,"",AV186-LOOKUP(2,1/(AI186:AU186<>""),AI186:AU186))) | IF(J186="","All_Provinces",IFERROR(VLOOKUP(J186,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K186="","All_Districts",IFERROR(VLOOKUP(K186,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F187="","",ROW()-3) | AF2-IS-28 | Package # 28 – AF2 IS: Rehabilitation of Irrigation Schemes of 1. Abil Aroq (Qanjogha), 2. Shaitan Aroq Cluster Canals in Khwaja Ghar District and 3. Kalta Aroq, 4. Pacha Khail, and 5. Sayed Miran (Khar Kar) Cluster Canals in Eshkamish District of Takhar Province | 1 of 2 | AF2-IS-A-026 | Abil Aroq (Qanjugh) and Shaitan Aroq Cluster Canal Irrigation Schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Khwaja Ghar | Qanjogha | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | SHAMAL KARDAN ROAD CONSTRUCTION AND LOGISTIC SERVICES COMPANY LTD (SKRCC) | 067/2025 | 159788.8 | IF(AQ187="","",AQ187) |  | 12 | 2026-12-21 | IF(W187<>"",W187,IF(OR(T187="",V187=""),"",EDATE(T187,V187))) |  | 0 | Awarded | off track and close follow up to ensure completion by June 2027 after potential NCE | IF(F187="","",IF(COUNT(AI187:AV187)=0,IF(AA187="","Not started",AA187),SUBSTITUTE(LOOKUP(2,1/(AI187:AV187<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F187="",COUNT(AI187:AV187)=0),"",TODAY()-LOOKUP(2,1/(AI187:AV187<>""),AI187:AV187)) | IF(OR(F187="",COUNT(AI187:AV187)<2),"",LOOKUP(2,1/(AI187:AV187<>""),AI187:AV187)-MIN(AI187:AV187)) | IF(OR(AD187="",AC187="Not started",AC187=""),"",IFERROR(AD187-IF(VLOOKUP(AC187,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC187,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F187="","",IF(OR(AA187="Cancelled",AC187="Cancelled"),"Cancelled",IF(OR(AC187="Completed / Handover",Y187<>"",Z187>=100),"Completed — on track",IF(O187="Not awarded",IF(U187="",IF(X187="","No planned date",IF(TODAY()>X187,"Behind — past planned date",IF(X187-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U187,"Behind — award date passed",IF(U187-TODAY()<=30,"At risk — close to off track","On track"))),IF(X187="","No planned date",IF(AND(TODAY()>X187,OR(Z187="",Z187<100)),"Behind — past end date",IF(AND(T187<>"",X187<>"",Z187<>"",(Z187<100),((TODAY()-T187)/MAX(X187-T187,1)*100)-Z187>15),"Behind — progress lag",IF(AND(X187-TODAY()<=30,X187-TODAY()>=0,OR(Z187="",Z187<90)),"At risk — close to off track","On track")))))))) | IF(OR(F187="",AC187="Completed / Handover",AC187="Cancelled"),"",IF(O187="Not awarded",IF(U187<>"",U187-TODAY(),IF(X187="","",X187-TODAY())),IF(X187="","",X187-TODAY()))) | [8 empty] | 2025-12-22 | [5 empty] | IF(OR(F187="",AJ187=""),"",IF(COUNT(AI187:AI187)=0,"",AJ187-LOOKUP(2,1/(AI187:AI187<>""),AI187:AI187))) | IF(OR(F187="",AK187=""),"",IF(COUNT(AI187:AJ187)=0,"",AK187-LOOKUP(2,1/(AI187:AJ187<>""),AI187:AJ187))) | IF(OR(F187="",AL187=""),"",IF(COUNT(AI187:AK187)=0,"",AL187-LOOKUP(2,1/(AI187:AK187<>""),AI187:AK187))) | IF(OR(F187="",AM187=""),"",IF(COUNT(AI187:AL187)=0,"",AM187-LOOKUP(2,1/(AI187:AL187<>""),AI187:AL187))) | IF(OR(F187="",AN187=""),"",IF(COUNT(AI187:AM187)=0,"",AN187-LOOKUP(2,1/(AI187:AM187<>""),AI187:AM187))) | IF(OR(F187="",AO187=""),"",IF(COUNT(AI187:AN187)=0,"",AO187-LOOKUP(2,1/(AI187:AN187<>""),AI187:AN187))) | IF(OR(F187="",AP187=""),"",IF(COUNT(AI187:AO187)=0,"",AP187-LOOKUP(2,1/(AI187:AO187<>""),AI187:AO187))) | IF(OR(F187="",AQ187=""),"",IF(COUNT(AI187:AP187)=0,"",AQ187-LOOKUP(2,1/(AI187:AP187<>""),AI187:AP187))) | IF(OR(F187="",AR187=""),"",IF(COUNT(AI187:AQ187)=0,"",AR187-LOOKUP(2,1/(AI187:AQ187<>""),AI187:AQ187))) | IF(OR(F187="",AS187=""),"",IF(COUNT(AI187:AR187)=0,"",AS187-LOOKUP(2,1/(AI187:AR187<>""),AI187:AR187))) | IF(OR(F187="",AT187=""),"",IF(COUNT(AI187:AS187)=0,"",AT187-LOOKUP(2,1/(AI187:AS187<>""),AI187:AS187))) | IF(OR(F187="",AU187=""),"",IF(COUNT(AI187:AT187)=0,"",AU187-LOOKUP(2,1/(AI187:AT187<>""),AI187:AT187))) | IF(OR(F187="",AV187=""),"",IF(COUNT(AI187:AU187)=0,"",AV187-LOOKUP(2,1/(AI187:AU187<>""),AI187:AU187))) | IF(J187="","All_Provinces",IFERROR(VLOOKUP(J187,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K187="","All_Districts",IFERROR(VLOOKUP(K187,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F188="","",ROW()-3) | AF2-IS-28 | Package # 28 – AF2 IS: Rehabilitation of Irrigation Schemes of 1. Abil Aroq (Qanjogha), 2. Shaitan Aroq Cluster Canals in Khwaja Ghar District and 3. Kalta Aroq, 4. Pacha Khail, and 5. Sayed Miran (Khar Kar) Cluster Canals in Eshkamish District of Takhar Province | 2 of 2 | AF2-IS-A-027 | Khar Kar (Kalta Aroq, Pacha Khail and Sayed Miran) Cluster Canal Irrigation Schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Eshkamish | Kat Qurugh | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | SHAMAL KARDAN ROAD CONSTRUCTION AND LOGISTIC SERVICES COMPANY LTD (SKRCC) | 067/2025 | 89881.2 | IF(AQ188="","",AQ188) |  | 12 | 2026-12-21 | IF(W188<>"",W188,IF(OR(T188="",V188=""),"",EDATE(T188,V188))) |  | 80 | Under Construction | on track and will be completed by Dec. 2026 | IF(F188="","",IF(COUNT(AI188:AV188)=0,IF(AA188="","Not started",AA188),SUBSTITUTE(LOOKUP(2,1/(AI188:AV188<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F188="",COUNT(AI188:AV188)=0),"",TODAY()-LOOKUP(2,1/(AI188:AV188<>""),AI188:AV188)) | IF(OR(F188="",COUNT(AI188:AV188)<2),"",LOOKUP(2,1/(AI188:AV188<>""),AI188:AV188)-MIN(AI188:AV188)) | IF(OR(AD188="",AC188="Not started",AC188=""),"",IFERROR(AD188-IF(VLOOKUP(AC188,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC188,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F188="","",IF(OR(AA188="Cancelled",AC188="Cancelled"),"Cancelled",IF(OR(AC188="Completed / Handover",Y188<>"",Z188>=100),"Completed — on track",IF(O188="Not awarded",IF(U188="",IF(X188="","No planned date",IF(TODAY()>X188,"Behind — past planned date",IF(X188-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U188,"Behind — award date passed",IF(U188-TODAY()<=30,"At risk — close to off track","On track"))),IF(X188="","No planned date",IF(AND(TODAY()>X188,OR(Z188="",Z188<100)),"Behind — past end date",IF(AND(T188<>"",X188<>"",Z188<>"",(Z188<100),((TODAY()-T188)/MAX(X188-T188,1)*100)-Z188>15),"Behind — progress lag",IF(AND(X188-TODAY()<=30,X188-TODAY()>=0,OR(Z188="",Z188<90)),"At risk — close to off track","On track")))))))) | IF(OR(F188="",AC188="Completed / Handover",AC188="Cancelled"),"",IF(O188="Not awarded",IF(U188<>"",U188-TODAY(),IF(X188="","",X188-TODAY())),IF(X188="","",X188-TODAY()))) | [8 empty] | 2025-12-22 | 2025-12-22 |  |  |  |  | IF(OR(F188="",AJ188=""),"",IF(COUNT(AI188:AI188)=0,"",AJ188-LOOKUP(2,1/(AI188:AI188<>""),AI188:AI188))) | IF(OR(F188="",AK188=""),"",IF(COUNT(AI188:AJ188)=0,"",AK188-LOOKUP(2,1/(AI188:AJ188<>""),AI188:AJ188))) | IF(OR(F188="",AL188=""),"",IF(COUNT(AI188:AK188)=0,"",AL188-LOOKUP(2,1/(AI188:AK188<>""),AI188:AK188))) | IF(OR(F188="",AM188=""),"",IF(COUNT(AI188:AL188)=0,"",AM188-LOOKUP(2,1/(AI188:AL188<>""),AI188:AL188))) | IF(OR(F188="",AN188=""),"",IF(COUNT(AI188:AM188)=0,"",AN188-LOOKUP(2,1/(AI188:AM188<>""),AI188:AM188))) | IF(OR(F188="",AO188=""),"",IF(COUNT(AI188:AN188)=0,"",AO188-LOOKUP(2,1/(AI188:AN188<>""),AI188:AN188))) | IF(OR(F188="",AP188=""),"",IF(COUNT(AI188:AO188)=0,"",AP188-LOOKUP(2,1/(AI188:AO188<>""),AI188:AO188))) | IF(OR(F188="",AQ188=""),"",IF(COUNT(AI188:AP188)=0,"",AQ188-LOOKUP(2,1/(AI188:AP188<>""),AI188:AP188))) | IF(OR(F188="",AR188=""),"",IF(COUNT(AI188:AQ188)=0,"",AR188-LOOKUP(2,1/(AI188:AQ188<>""),AI188:AQ188))) | IF(OR(F188="",AS188=""),"",IF(COUNT(AI188:AR188)=0,"",AS188-LOOKUP(2,1/(AI188:AR188<>""),AI188:AR188))) | IF(OR(F188="",AT188=""),"",IF(COUNT(AI188:AS188)=0,"",AT188-LOOKUP(2,1/(AI188:AS188<>""),AI188:AS188))) | IF(OR(F188="",AU188=""),"",IF(COUNT(AI188:AT188)=0,"",AU188-LOOKUP(2,1/(AI188:AT188<>""),AI188:AT188))) | IF(OR(F188="",AV188=""),"",IF(COUNT(AI188:AU188)=0,"",AV188-LOOKUP(2,1/(AI188:AU188<>""),AI188:AU188))) | IF(J188="","All_Provinces",IFERROR(VLOOKUP(J188,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K188="","All_Districts",IFERROR(VLOOKUP(K188,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F189="","",ROW()-3) | AF2-IS-29 | Package #29-AF2 IS: Rehabilitation of Dagh Aruq canal irrigation scheme, located in Chahar Dara district of Kunduz province. | 1 of 1 | AF2-IS-N-020 | Dagh Aruq Canal Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Kunduz | Chahar Dara | Dagh Aruq | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 200000 | IF(AQ189="","",AQ189) | 2026-11-25 | 9.9 | 2027-09-21 | IF(W189<>"",W189,IF(OR(T189="",V189=""),"",EDATE(T189,V189))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals. Split into 2 lots and make 2 PRs | IF(F189="","",IF(COUNT(AI189:AV189)=0,IF(AA189="","Not started",AA189),SUBSTITUTE(LOOKUP(2,1/(AI189:AV189<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F189="",COUNT(AI189:AV189)=0),"",TODAY()-LOOKUP(2,1/(AI189:AV189<>""),AI189:AV189)) | IF(OR(F189="",COUNT(AI189:AV189)<2),"",LOOKUP(2,1/(AI189:AV189<>""),AI189:AV189)-MIN(AI189:AV189)) | IF(OR(AD189="",AC189="Not started",AC189=""),"",IFERROR(AD189-IF(VLOOKUP(AC189,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC189,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F189="","",IF(OR(AA189="Cancelled",AC189="Cancelled"),"Cancelled",IF(OR(AC189="Completed / Handover",Y189<>"",Z189>=100),"Completed — on track",IF(O189="Not awarded",IF(U189="",IF(X189="","No planned date",IF(TODAY()>X189,"Behind — past planned date",IF(X189-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U189,"Behind — award date passed",IF(U189-TODAY()<=30,"At risk — close to off track","On track"))),IF(X189="","No planned date",IF(AND(TODAY()>X189,OR(Z189="",Z189<100)),"Behind — past end date",IF(AND(T189<>"",X189<>"",Z189<>"",(Z189<100),((TODAY()-T189)/MAX(X189-T189,1)*100)-Z189>15),"Behind — progress lag",IF(AND(X189-TODAY()<=30,X189-TODAY()>=0,OR(Z189="",Z189<90)),"At risk — close to off track","On track")))))))) | IF(OR(F189="",AC189="Completed / Handover",AC189="Cancelled"),"",IF(O189="Not awarded",IF(U189<>"",U189-TODAY(),IF(X189="","",X189-TODAY())),IF(X189="","",X189-TODAY()))) | [14 empty] | IF(OR(F189="",AJ189=""),"",IF(COUNT(AI189:AI189)=0,"",AJ189-LOOKUP(2,1/(AI189:AI189<>""),AI189:AI189))) | IF(OR(F189="",AK189=""),"",IF(COUNT(AI189:AJ189)=0,"",AK189-LOOKUP(2,1/(AI189:AJ189<>""),AI189:AJ189))) | IF(OR(F189="",AL189=""),"",IF(COUNT(AI189:AK189)=0,"",AL189-LOOKUP(2,1/(AI189:AK189<>""),AI189:AK189))) | IF(OR(F189="",AM189=""),"",IF(COUNT(AI189:AL189)=0,"",AM189-LOOKUP(2,1/(AI189:AL189<>""),AI189:AL189))) | IF(OR(F189="",AN189=""),"",IF(COUNT(AI189:AM189)=0,"",AN189-LOOKUP(2,1/(AI189:AM189<>""),AI189:AM189))) | IF(OR(F189="",AO189=""),"",IF(COUNT(AI189:AN189)=0,"",AO189-LOOKUP(2,1/(AI189:AN189<>""),AI189:AN189))) | IF(OR(F189="",AP189=""),"",IF(COUNT(AI189:AO189)=0,"",AP189-LOOKUP(2,1/(AI189:AO189<>""),AI189:AO189))) | IF(OR(F189="",AQ189=""),"",IF(COUNT(AI189:AP189)=0,"",AQ189-LOOKUP(2,1/(AI189:AP189<>""),AI189:AP189))) | IF(OR(F189="",AR189=""),"",IF(COUNT(AI189:AQ189)=0,"",AR189-LOOKUP(2,1/(AI189:AQ189<>""),AI189:AQ189))) | IF(OR(F189="",AS189=""),"",IF(COUNT(AI189:AR189)=0,"",AS189-LOOKUP(2,1/(AI189:AR189<>""),AI189:AR189))) | IF(OR(F189="",AT189=""),"",IF(COUNT(AI189:AS189)=0,"",AT189-LOOKUP(2,1/(AI189:AS189<>""),AI189:AS189))) | IF(OR(F189="",AU189=""),"",IF(COUNT(AI189:AT189)=0,"",AU189-LOOKUP(2,1/(AI189:AT189<>""),AI189:AT189))) | IF(OR(F189="",AV189=""),"",IF(COUNT(AI189:AU189)=0,"",AV189-LOOKUP(2,1/(AI189:AU189<>""),AI189:AU189))) | IF(J189="","All_Provinces",IFERROR(VLOOKUP(J189,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K189="","All_Districts",IFERROR(VLOOKUP(K189,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F190="","",ROW()-3) | AF2-IS-30 | Package # 30-AF2 IS: Rehabilitation of Teshkhan canal canals irrigation scheme, located in Ishkashim districts of Badakhshan province. | 1 of 1 | AF2-IS-N-021 | Teshkhan Canal Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Badakhshan | Ishkashim | Teshkhan | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 126516.45 | IF(AQ190="","",AQ190) | 2027-01-12 | 8.9 | 2027-10-09 | IF(W190<>"",W190,IF(OR(T190="",V190=""),"",EDATE(T190,V190))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Six months construction period required for two canals | IF(F190="","",IF(COUNT(AI190:AV190)=0,IF(AA190="","Not started",AA190),SUBSTITUTE(LOOKUP(2,1/(AI190:AV190<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F190="",COUNT(AI190:AV190)=0),"",TODAY()-LOOKUP(2,1/(AI190:AV190<>""),AI190:AV190)) | IF(OR(F190="",COUNT(AI190:AV190)<2),"",LOOKUP(2,1/(AI190:AV190<>""),AI190:AV190)-MIN(AI190:AV190)) | IF(OR(AD190="",AC190="Not started",AC190=""),"",IFERROR(AD190-IF(VLOOKUP(AC190,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC190,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F190="","",IF(OR(AA190="Cancelled",AC190="Cancelled"),"Cancelled",IF(OR(AC190="Completed / Handover",Y190<>"",Z190>=100),"Completed — on track",IF(O190="Not awarded",IF(U190="",IF(X190="","No planned date",IF(TODAY()>X190,"Behind — past planned date",IF(X190-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U190,"Behind — award date passed",IF(U190-TODAY()<=30,"At risk — close to off track","On track"))),IF(X190="","No planned date",IF(AND(TODAY()>X190,OR(Z190="",Z190<100)),"Behind — past end date",IF(AND(T190<>"",X190<>"",Z190<>"",(Z190<100),((TODAY()-T190)/MAX(X190-T190,1)*100)-Z190>15),"Behind — progress lag",IF(AND(X190-TODAY()<=30,X190-TODAY()>=0,OR(Z190="",Z190<90)),"At risk — close to off track","On track")))))))) | IF(OR(F190="",AC190="Completed / Handover",AC190="Cancelled"),"",IF(O190="Not awarded",IF(U190<>"",U190-TODAY(),IF(X190="","",X190-TODAY())),IF(X190="","",X190-TODAY()))) | [14 empty] | IF(OR(F190="",AJ190=""),"",IF(COUNT(AI190:AI190)=0,"",AJ190-LOOKUP(2,1/(AI190:AI190<>""),AI190:AI190))) | IF(OR(F190="",AK190=""),"",IF(COUNT(AI190:AJ190)=0,"",AK190-LOOKUP(2,1/(AI190:AJ190<>""),AI190:AJ190))) | IF(OR(F190="",AL190=""),"",IF(COUNT(AI190:AK190)=0,"",AL190-LOOKUP(2,1/(AI190:AK190<>""),AI190:AK190))) | IF(OR(F190="",AM190=""),"",IF(COUNT(AI190:AL190)=0,"",AM190-LOOKUP(2,1/(AI190:AL190<>""),AI190:AL190))) | IF(OR(F190="",AN190=""),"",IF(COUNT(AI190:AM190)=0,"",AN190-LOOKUP(2,1/(AI190:AM190<>""),AI190:AM190))) | IF(OR(F190="",AO190=""),"",IF(COUNT(AI190:AN190)=0,"",AO190-LOOKUP(2,1/(AI190:AN190<>""),AI190:AN190))) | IF(OR(F190="",AP190=""),"",IF(COUNT(AI190:AO190)=0,"",AP190-LOOKUP(2,1/(AI190:AO190<>""),AI190:AO190))) | IF(OR(F190="",AQ190=""),"",IF(COUNT(AI190:AP190)=0,"",AQ190-LOOKUP(2,1/(AI190:AP190<>""),AI190:AP190))) | IF(OR(F190="",AR190=""),"",IF(COUNT(AI190:AQ190)=0,"",AR190-LOOKUP(2,1/(AI190:AQ190<>""),AI190:AQ190))) | IF(OR(F190="",AS190=""),"",IF(COUNT(AI190:AR190)=0,"",AS190-LOOKUP(2,1/(AI190:AR190<>""),AI190:AR190))) | IF(OR(F190="",AT190=""),"",IF(COUNT(AI190:AS190)=0,"",AT190-LOOKUP(2,1/(AI190:AS190<>""),AI190:AS190))) | IF(OR(F190="",AU190=""),"",IF(COUNT(AI190:AT190)=0,"",AU190-LOOKUP(2,1/(AI190:AT190<>""),AI190:AT190))) | IF(OR(F190="",AV190=""),"",IF(COUNT(AI190:AU190)=0,"",AV190-LOOKUP(2,1/(AI190:AU190<>""),AI190:AU190))) | IF(J190="","All_Provinces",IFERROR(VLOOKUP(J190,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K190="","All_Districts",IFERROR(VLOOKUP(K190,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F191="","",ROW()-3) | AF2-IS-31 | Package #31-AF2 IS: Rehabilitation of 1. Shahidan &Dasht-e Lajam Canal schems in Tala wa barfak district, 2.Sardar Ha canal scheme in Deh Salah district, and 3. Kambilan cluster canal schemes in Fring districts of Baghlan province. | 1 of 3 | AF2-IS-A-028 | Juybar-e-Maidan (Payendakhail), Nahr-e-Salih, Khambilan, Dara-e-Bazar Irrigation Schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Fring | Juybar-e-Maidan (Payendakhail), Salih, Khambilan, Dara-e-Bazar | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Afghan Eithad construction and Road Building company (AECC) | 009/2026 | 120795.68 | IF(AQ191="","",AQ191) |  | 10 | 2026-11-28 | IF(W191<>"",W191,IF(OR(T191="",V191=""),"",EDATE(T191,V191))) |  | 100 | Completed / Handover | Actual completion: August, 2026 | IF(F191="","",IF(COUNT(AI191:AV191)=0,IF(AA191="","Not started",AA191),SUBSTITUTE(LOOKUP(2,1/(AI191:AV191<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F191="",COUNT(AI191:AV191)=0),"",TODAY()-LOOKUP(2,1/(AI191:AV191<>""),AI191:AV191)) | IF(OR(F191="",COUNT(AI191:AV191)<2),"",LOOKUP(2,1/(AI191:AV191<>""),AI191:AV191)-MIN(AI191:AV191)) | IF(OR(AD191="",AC191="Not started",AC191=""),"",IFERROR(AD191-IF(VLOOKUP(AC191,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC191,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F191="","",IF(OR(AA191="Cancelled",AC191="Cancelled"),"Cancelled",IF(OR(AC191="Completed / Handover",Y191<>"",Z191>=100),"Completed — on track",IF(O191="Not awarded",IF(U191="",IF(X191="","No planned date",IF(TODAY()>X191,"Behind — past planned date",IF(X191-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U191,"Behind — award date passed",IF(U191-TODAY()<=30,"At risk — close to off track","On track"))),IF(X191="","No planned date",IF(AND(TODAY()>X191,OR(Z191="",Z191<100)),"Behind — past end date",IF(AND(T191<>"",X191<>"",Z191<>"",(Z191<100),((TODAY()-T191)/MAX(X191-T191,1)*100)-Z191>15),"Behind — progress lag",IF(AND(X191-TODAY()<=30,X191-TODAY()>=0,OR(Z191="",Z191<90)),"At risk — close to off track","On track")))))))) | IF(OR(F191="",AC191="Completed / Handover",AC191="Cancelled"),"",IF(O191="Not awarded",IF(U191<>"",U191-TODAY(),IF(X191="","",X191-TODAY())),IF(X191="","",X191-TODAY()))) | [8 empty] | 2026-01-29 | 2026-01-29 | 2026-11-28 |  |  |  | IF(OR(F191="",AJ191=""),"",IF(COUNT(AI191:AI191)=0,"",AJ191-LOOKUP(2,1/(AI191:AI191<>""),AI191:AI191))) | IF(OR(F191="",AK191=""),"",IF(COUNT(AI191:AJ191)=0,"",AK191-LOOKUP(2,1/(AI191:AJ191<>""),AI191:AJ191))) | IF(OR(F191="",AL191=""),"",IF(COUNT(AI191:AK191)=0,"",AL191-LOOKUP(2,1/(AI191:AK191<>""),AI191:AK191))) | IF(OR(F191="",AM191=""),"",IF(COUNT(AI191:AL191)=0,"",AM191-LOOKUP(2,1/(AI191:AL191<>""),AI191:AL191))) | IF(OR(F191="",AN191=""),"",IF(COUNT(AI191:AM191)=0,"",AN191-LOOKUP(2,1/(AI191:AM191<>""),AI191:AM191))) | IF(OR(F191="",AO191=""),"",IF(COUNT(AI191:AN191)=0,"",AO191-LOOKUP(2,1/(AI191:AN191<>""),AI191:AN191))) | IF(OR(F191="",AP191=""),"",IF(COUNT(AI191:AO191)=0,"",AP191-LOOKUP(2,1/(AI191:AO191<>""),AI191:AO191))) | IF(OR(F191="",AQ191=""),"",IF(COUNT(AI191:AP191)=0,"",AQ191-LOOKUP(2,1/(AI191:AP191<>""),AI191:AP191))) | IF(OR(F191="",AR191=""),"",IF(COUNT(AI191:AQ191)=0,"",AR191-LOOKUP(2,1/(AI191:AQ191<>""),AI191:AQ191))) | IF(OR(F191="",AS191=""),"",IF(COUNT(AI191:AR191)=0,"",AS191-LOOKUP(2,1/(AI191:AR191<>""),AI191:AR191))) | IF(OR(F191="",AT191=""),"",IF(COUNT(AI191:AS191)=0,"",AT191-LOOKUP(2,1/(AI191:AS191<>""),AI191:AS191))) | IF(OR(F191="",AU191=""),"",IF(COUNT(AI191:AT191)=0,"",AU191-LOOKUP(2,1/(AI191:AT191<>""),AI191:AT191))) | IF(OR(F191="",AV191=""),"",IF(COUNT(AI191:AU191)=0,"",AV191-LOOKUP(2,1/(AI191:AU191<>""),AI191:AU191))) | IF(J191="","All_Provinces",IFERROR(VLOOKUP(J191,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K191="","All_Districts",IFERROR(VLOOKUP(K191,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F192="","",ROW()-3) | AF2-IS-31 | Package #31-AF2 IS: Rehabilitation of 1. Shahidan &Dasht-e Lajam Canal schems in Tala wa barfak district, 2.Sardar Ha canal scheme in Deh Salah district, and 3. Kambilan cluster canal schemes in Fring districts of Baghlan province. | 2 of 3 | AF2-IS-A-029 | Sardara Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Deh Salah | Sardara | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Afghan Eithad construction and Road Building company (AECC) | 009/2026 | 167265.54 | IF(AQ192="","",AQ192) |  | 10 | 2026-11-28 | IF(W192<>"",W192,IF(OR(T192="",V192=""),"",EDATE(T192,V192))) |  | 90 | Under Construction | on track and will be completed by Nov. 2026 ¦ Actual completion: July. 2025 | IF(F192="","",IF(COUNT(AI192:AV192)=0,IF(AA192="","Not started",AA192),SUBSTITUTE(LOOKUP(2,1/(AI192:AV192<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F192="",COUNT(AI192:AV192)=0),"",TODAY()-LOOKUP(2,1/(AI192:AV192<>""),AI192:AV192)) | IF(OR(F192="",COUNT(AI192:AV192)<2),"",LOOKUP(2,1/(AI192:AV192<>""),AI192:AV192)-MIN(AI192:AV192)) | IF(OR(AD192="",AC192="Not started",AC192=""),"",IFERROR(AD192-IF(VLOOKUP(AC192,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC192,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F192="","",IF(OR(AA192="Cancelled",AC192="Cancelled"),"Cancelled",IF(OR(AC192="Completed / Handover",Y192<>"",Z192>=100),"Completed — on track",IF(O192="Not awarded",IF(U192="",IF(X192="","No planned date",IF(TODAY()>X192,"Behind — past planned date",IF(X192-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U192,"Behind — award date passed",IF(U192-TODAY()<=30,"At risk — close to off track","On track"))),IF(X192="","No planned date",IF(AND(TODAY()>X192,OR(Z192="",Z192<100)),"Behind — past end date",IF(AND(T192<>"",X192<>"",Z192<>"",(Z192<100),((TODAY()-T192)/MAX(X192-T192,1)*100)-Z192>15),"Behind — progress lag",IF(AND(X192-TODAY()<=30,X192-TODAY()>=0,OR(Z192="",Z192<90)),"At risk — close to off track","On track")))))))) | IF(OR(F192="",AC192="Completed / Handover",AC192="Cancelled"),"",IF(O192="Not awarded",IF(U192<>"",U192-TODAY(),IF(X192="","",X192-TODAY())),IF(X192="","",X192-TODAY()))) | [8 empty] | 2026-01-29 | 2026-01-29 |  |  |  |  | IF(OR(F192="",AJ192=""),"",IF(COUNT(AI192:AI192)=0,"",AJ192-LOOKUP(2,1/(AI192:AI192<>""),AI192:AI192))) | IF(OR(F192="",AK192=""),"",IF(COUNT(AI192:AJ192)=0,"",AK192-LOOKUP(2,1/(AI192:AJ192<>""),AI192:AJ192))) | IF(OR(F192="",AL192=""),"",IF(COUNT(AI192:AK192)=0,"",AL192-LOOKUP(2,1/(AI192:AK192<>""),AI192:AK192))) | IF(OR(F192="",AM192=""),"",IF(COUNT(AI192:AL192)=0,"",AM192-LOOKUP(2,1/(AI192:AL192<>""),AI192:AL192))) | IF(OR(F192="",AN192=""),"",IF(COUNT(AI192:AM192)=0,"",AN192-LOOKUP(2,1/(AI192:AM192<>""),AI192:AM192))) | IF(OR(F192="",AO192=""),"",IF(COUNT(AI192:AN192)=0,"",AO192-LOOKUP(2,1/(AI192:AN192<>""),AI192:AN192))) | IF(OR(F192="",AP192=""),"",IF(COUNT(AI192:AO192)=0,"",AP192-LOOKUP(2,1/(AI192:AO192<>""),AI192:AO192))) | IF(OR(F192="",AQ192=""),"",IF(COUNT(AI192:AP192)=0,"",AQ192-LOOKUP(2,1/(AI192:AP192<>""),AI192:AP192))) | IF(OR(F192="",AR192=""),"",IF(COUNT(AI192:AQ192)=0,"",AR192-LOOKUP(2,1/(AI192:AQ192<>""),AI192:AQ192))) | IF(OR(F192="",AS192=""),"",IF(COUNT(AI192:AR192)=0,"",AS192-LOOKUP(2,1/(AI192:AR192<>""),AI192:AR192))) | IF(OR(F192="",AT192=""),"",IF(COUNT(AI192:AS192)=0,"",AT192-LOOKUP(2,1/(AI192:AS192<>""),AI192:AS192))) | IF(OR(F192="",AU192=""),"",IF(COUNT(AI192:AT192)=0,"",AU192-LOOKUP(2,1/(AI192:AT192<>""),AI192:AT192))) | IF(OR(F192="",AV192=""),"",IF(COUNT(AI192:AU192)=0,"",AV192-LOOKUP(2,1/(AI192:AU192<>""),AI192:AU192))) | IF(J192="","All_Provinces",IFERROR(VLOOKUP(J192,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K192="","All_Districts",IFERROR(VLOOKUP(K192,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F193="","",ROW()-3) | AF2-IS-31 | Package #31-AF2 IS: Rehabilitation of 1. Shahidan &Dasht-e Lajam Canal schems in Tala wa barfak district, 2.Sardar Ha canal scheme in Deh Salah district, and 3. Kambilan cluster canal schemes in Fring districts of Baghlan province. | 3 of 3 | AF2-IS-A-030 | Shahidan & Dasht-e Lajam Canals | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Tala wa barfak | Shahidan & Dast-e-Lajam | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Afghan Eithad construction and Road Building company (AECC) | 009/2026 | 190128.77 | IF(AQ193="","",AQ193) |  | 10 | 2026-11-28 | IF(W193<>"",W193,IF(OR(T193="",V193=""),"",EDATE(T193,V193))) |  | 100 | Completed / Handover | on track and will be completed by Nov. 2026 ¦ Actual completion: July. 2025 | IF(F193="","",IF(COUNT(AI193:AV193)=0,IF(AA193="","Not started",AA193),SUBSTITUTE(LOOKUP(2,1/(AI193:AV193<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F193="",COUNT(AI193:AV193)=0),"",TODAY()-LOOKUP(2,1/(AI193:AV193<>""),AI193:AV193)) | IF(OR(F193="",COUNT(AI193:AV193)<2),"",LOOKUP(2,1/(AI193:AV193<>""),AI193:AV193)-MIN(AI193:AV193)) | IF(OR(AD193="",AC193="Not started",AC193=""),"",IFERROR(AD193-IF(VLOOKUP(AC193,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC193,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F193="","",IF(OR(AA193="Cancelled",AC193="Cancelled"),"Cancelled",IF(OR(AC193="Completed / Handover",Y193<>"",Z193>=100),"Completed — on track",IF(O193="Not awarded",IF(U193="",IF(X193="","No planned date",IF(TODAY()>X193,"Behind — past planned date",IF(X193-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U193,"Behind — award date passed",IF(U193-TODAY()<=30,"At risk — close to off track","On track"))),IF(X193="","No planned date",IF(AND(TODAY()>X193,OR(Z193="",Z193<100)),"Behind — past end date",IF(AND(T193<>"",X193<>"",Z193<>"",(Z193<100),((TODAY()-T193)/MAX(X193-T193,1)*100)-Z193>15),"Behind — progress lag",IF(AND(X193-TODAY()<=30,X193-TODAY()>=0,OR(Z193="",Z193<90)),"At risk — close to off track","On track")))))))) | IF(OR(F193="",AC193="Completed / Handover",AC193="Cancelled"),"",IF(O193="Not awarded",IF(U193<>"",U193-TODAY(),IF(X193="","",X193-TODAY())),IF(X193="","",X193-TODAY()))) | [8 empty] | 2026-01-29 | 2026-01-29 | 2026-11-28 |  |  |  | IF(OR(F193="",AJ193=""),"",IF(COUNT(AI193:AI193)=0,"",AJ193-LOOKUP(2,1/(AI193:AI193<>""),AI193:AI193))) | IF(OR(F193="",AK193=""),"",IF(COUNT(AI193:AJ193)=0,"",AK193-LOOKUP(2,1/(AI193:AJ193<>""),AI193:AJ193))) | IF(OR(F193="",AL193=""),"",IF(COUNT(AI193:AK193)=0,"",AL193-LOOKUP(2,1/(AI193:AK193<>""),AI193:AK193))) | IF(OR(F193="",AM193=""),"",IF(COUNT(AI193:AL193)=0,"",AM193-LOOKUP(2,1/(AI193:AL193<>""),AI193:AL193))) | IF(OR(F193="",AN193=""),"",IF(COUNT(AI193:AM193)=0,"",AN193-LOOKUP(2,1/(AI193:AM193<>""),AI193:AM193))) | IF(OR(F193="",AO193=""),"",IF(COUNT(AI193:AN193)=0,"",AO193-LOOKUP(2,1/(AI193:AN193<>""),AI193:AN193))) | IF(OR(F193="",AP193=""),"",IF(COUNT(AI193:AO193)=0,"",AP193-LOOKUP(2,1/(AI193:AO193<>""),AI193:AO193))) | IF(OR(F193="",AQ193=""),"",IF(COUNT(AI193:AP193)=0,"",AQ193-LOOKUP(2,1/(AI193:AP193<>""),AI193:AP193))) | IF(OR(F193="",AR193=""),"",IF(COUNT(AI193:AQ193)=0,"",AR193-LOOKUP(2,1/(AI193:AQ193<>""),AI193:AQ193))) | IF(OR(F193="",AS193=""),"",IF(COUNT(AI193:AR193)=0,"",AS193-LOOKUP(2,1/(AI193:AR193<>""),AI193:AR193))) | IF(OR(F193="",AT193=""),"",IF(COUNT(AI193:AS193)=0,"",AT193-LOOKUP(2,1/(AI193:AS193<>""),AI193:AS193))) | IF(OR(F193="",AU193=""),"",IF(COUNT(AI193:AT193)=0,"",AU193-LOOKUP(2,1/(AI193:AT193<>""),AI193:AT193))) | IF(OR(F193="",AV193=""),"",IF(COUNT(AI193:AU193)=0,"",AV193-LOOKUP(2,1/(AI193:AU193<>""),AI193:AU193))) | IF(J193="","All_Provinces",IFERROR(VLOOKUP(J193,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K193="","All_Districts",IFERROR(VLOOKUP(K193,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F194="","",ROW()-3) | AF2-IS-32 | Package #32-AF2 IS: Rehabilitation of Abdul Baqi canal and Mulla Oma canal irrigation schemes, located in Chemtal districts of Balkh province. | 1 of 2 | AF2-IS-A-031 | Abdul Baqi Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Chemtal | Sari Asiab | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Trust Grow Construction and Engineering Company (TGCC) | 075/2025 | 141012.01 | IF(AQ194="","",AQ194) |  | 11 | 2026-11-29 | IF(W194<>"",W194,IF(OR(T194="",V194=""),"",EDATE(T194,V194))) |  | 100 | Completed / Handover | Completed in July 2026. ¦ Actual completion: July, 2026 | IF(F194="","",IF(COUNT(AI194:AV194)=0,IF(AA194="","Not started",AA194),SUBSTITUTE(LOOKUP(2,1/(AI194:AV194<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F194="",COUNT(AI194:AV194)=0),"",TODAY()-LOOKUP(2,1/(AI194:AV194<>""),AI194:AV194)) | IF(OR(F194="",COUNT(AI194:AV194)<2),"",LOOKUP(2,1/(AI194:AV194<>""),AI194:AV194)-MIN(AI194:AV194)) | IF(OR(AD194="",AC194="Not started",AC194=""),"",IFERROR(AD194-IF(VLOOKUP(AC194,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC194,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F194="","",IF(OR(AA194="Cancelled",AC194="Cancelled"),"Cancelled",IF(OR(AC194="Completed / Handover",Y194<>"",Z194>=100),"Completed — on track",IF(O194="Not awarded",IF(U194="",IF(X194="","No planned date",IF(TODAY()>X194,"Behind — past planned date",IF(X194-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U194,"Behind — award date passed",IF(U194-TODAY()<=30,"At risk — close to off track","On track"))),IF(X194="","No planned date",IF(AND(TODAY()>X194,OR(Z194="",Z194<100)),"Behind — past end date",IF(AND(T194<>"",X194<>"",Z194<>"",(Z194<100),((TODAY()-T194)/MAX(X194-T194,1)*100)-Z194>15),"Behind — progress lag",IF(AND(X194-TODAY()<=30,X194-TODAY()>=0,OR(Z194="",Z194<90)),"At risk — close to off track","On track")))))))) | IF(OR(F194="",AC194="Completed / Handover",AC194="Cancelled"),"",IF(O194="Not awarded",IF(U194<>"",U194-TODAY(),IF(X194="","",X194-TODAY())),IF(X194="","",X194-TODAY()))) | [8 empty] | 2025-12-31 | 2025-12-31 | 2026-11-29 |  |  |  | IF(OR(F194="",AJ194=""),"",IF(COUNT(AI194:AI194)=0,"",AJ194-LOOKUP(2,1/(AI194:AI194<>""),AI194:AI194))) | IF(OR(F194="",AK194=""),"",IF(COUNT(AI194:AJ194)=0,"",AK194-LOOKUP(2,1/(AI194:AJ194<>""),AI194:AJ194))) | IF(OR(F194="",AL194=""),"",IF(COUNT(AI194:AK194)=0,"",AL194-LOOKUP(2,1/(AI194:AK194<>""),AI194:AK194))) | IF(OR(F194="",AM194=""),"",IF(COUNT(AI194:AL194)=0,"",AM194-LOOKUP(2,1/(AI194:AL194<>""),AI194:AL194))) | IF(OR(F194="",AN194=""),"",IF(COUNT(AI194:AM194)=0,"",AN194-LOOKUP(2,1/(AI194:AM194<>""),AI194:AM194))) | IF(OR(F194="",AO194=""),"",IF(COUNT(AI194:AN194)=0,"",AO194-LOOKUP(2,1/(AI194:AN194<>""),AI194:AN194))) | IF(OR(F194="",AP194=""),"",IF(COUNT(AI194:AO194)=0,"",AP194-LOOKUP(2,1/(AI194:AO194<>""),AI194:AO194))) | IF(OR(F194="",AQ194=""),"",IF(COUNT(AI194:AP194)=0,"",AQ194-LOOKUP(2,1/(AI194:AP194<>""),AI194:AP194))) | IF(OR(F194="",AR194=""),"",IF(COUNT(AI194:AQ194)=0,"",AR194-LOOKUP(2,1/(AI194:AQ194<>""),AI194:AQ194))) | IF(OR(F194="",AS194=""),"",IF(COUNT(AI194:AR194)=0,"",AS194-LOOKUP(2,1/(AI194:AR194<>""),AI194:AR194))) | IF(OR(F194="",AT194=""),"",IF(COUNT(AI194:AS194)=0,"",AT194-LOOKUP(2,1/(AI194:AS194<>""),AI194:AS194))) | IF(OR(F194="",AU194=""),"",IF(COUNT(AI194:AT194)=0,"",AU194-LOOKUP(2,1/(AI194:AT194<>""),AI194:AT194))) | IF(OR(F194="",AV194=""),"",IF(COUNT(AI194:AU194)=0,"",AV194-LOOKUP(2,1/(AI194:AU194<>""),AI194:AU194))) | IF(J194="","All_Provinces",IFERROR(VLOOKUP(J194,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K194="","All_Districts",IFERROR(VLOOKUP(K194,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F195="","",ROW()-3) | AF2-IS-32 | Package #32-AF2 IS: Rehabilitation of Abdul Baqi canal and Mulla Oma canal irrigation schemes, located in Chemtal districts of Balkh province. | 2 of 2 | AF2-IS-A-032 | Mulla Omar Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Chemtal | Sarkar | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Trust Grow Construction and Engineering Company (TGCC) | 075/2025 | 159013.54 | IF(AQ195="","",AQ195) |  | 11 | 2026-11-29 | IF(W195<>"",W195,IF(OR(T195="",V195=""),"",EDATE(T195,V195))) |  | 100 | Completed / Handover | Actual completion: July, 2026 | IF(F195="","",IF(COUNT(AI195:AV195)=0,IF(AA195="","Not started",AA195),SUBSTITUTE(LOOKUP(2,1/(AI195:AV195<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F195="",COUNT(AI195:AV195)=0),"",TODAY()-LOOKUP(2,1/(AI195:AV195<>""),AI195:AV195)) | IF(OR(F195="",COUNT(AI195:AV195)<2),"",LOOKUP(2,1/(AI195:AV195<>""),AI195:AV195)-MIN(AI195:AV195)) | IF(OR(AD195="",AC195="Not started",AC195=""),"",IFERROR(AD195-IF(VLOOKUP(AC195,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC195,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F195="","",IF(OR(AA195="Cancelled",AC195="Cancelled"),"Cancelled",IF(OR(AC195="Completed / Handover",Y195<>"",Z195>=100),"Completed — on track",IF(O195="Not awarded",IF(U195="",IF(X195="","No planned date",IF(TODAY()>X195,"Behind — past planned date",IF(X195-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U195,"Behind — award date passed",IF(U195-TODAY()<=30,"At risk — close to off track","On track"))),IF(X195="","No planned date",IF(AND(TODAY()>X195,OR(Z195="",Z195<100)),"Behind — past end date",IF(AND(T195<>"",X195<>"",Z195<>"",(Z195<100),((TODAY()-T195)/MAX(X195-T195,1)*100)-Z195>15),"Behind — progress lag",IF(AND(X195-TODAY()<=30,X195-TODAY()>=0,OR(Z195="",Z195<90)),"At risk — close to off track","On track")))))))) | IF(OR(F195="",AC195="Completed / Handover",AC195="Cancelled"),"",IF(O195="Not awarded",IF(U195<>"",U195-TODAY(),IF(X195="","",X195-TODAY())),IF(X195="","",X195-TODAY()))) | [8 empty] | 2025-12-31 | 2025-12-31 | 2026-11-29 |  |  |  | IF(OR(F195="",AJ195=""),"",IF(COUNT(AI195:AI195)=0,"",AJ195-LOOKUP(2,1/(AI195:AI195<>""),AI195:AI195))) | IF(OR(F195="",AK195=""),"",IF(COUNT(AI195:AJ195)=0,"",AK195-LOOKUP(2,1/(AI195:AJ195<>""),AI195:AJ195))) | IF(OR(F195="",AL195=""),"",IF(COUNT(AI195:AK195)=0,"",AL195-LOOKUP(2,1/(AI195:AK195<>""),AI195:AK195))) | IF(OR(F195="",AM195=""),"",IF(COUNT(AI195:AL195)=0,"",AM195-LOOKUP(2,1/(AI195:AL195<>""),AI195:AL195))) | IF(OR(F195="",AN195=""),"",IF(COUNT(AI195:AM195)=0,"",AN195-LOOKUP(2,1/(AI195:AM195<>""),AI195:AM195))) | IF(OR(F195="",AO195=""),"",IF(COUNT(AI195:AN195)=0,"",AO195-LOOKUP(2,1/(AI195:AN195<>""),AI195:AN195))) | IF(OR(F195="",AP195=""),"",IF(COUNT(AI195:AO195)=0,"",AP195-LOOKUP(2,1/(AI195:AO195<>""),AI195:AO195))) | IF(OR(F195="",AQ195=""),"",IF(COUNT(AI195:AP195)=0,"",AQ195-LOOKUP(2,1/(AI195:AP195<>""),AI195:AP195))) | IF(OR(F195="",AR195=""),"",IF(COUNT(AI195:AQ195)=0,"",AR195-LOOKUP(2,1/(AI195:AQ195<>""),AI195:AQ195))) | IF(OR(F195="",AS195=""),"",IF(COUNT(AI195:AR195)=0,"",AS195-LOOKUP(2,1/(AI195:AR195<>""),AI195:AR195))) | IF(OR(F195="",AT195=""),"",IF(COUNT(AI195:AS195)=0,"",AT195-LOOKUP(2,1/(AI195:AS195<>""),AI195:AS195))) | IF(OR(F195="",AU195=""),"",IF(COUNT(AI195:AT195)=0,"",AU195-LOOKUP(2,1/(AI195:AT195<>""),AI195:AT195))) | IF(OR(F195="",AV195=""),"",IF(COUNT(AI195:AU195)=0,"",AV195-LOOKUP(2,1/(AI195:AU195<>""),AI195:AU195))) | IF(J195="","All_Provinces",IFERROR(VLOOKUP(J195,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K195="","All_Districts",IFERROR(VLOOKUP(K195,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F196="","",ROW()-3) | AF2-IS-33 | Package #33-AF2 IS: Rehabilitation of Chela Mazar canal and Kushkak canal irrigation schemes, located in Dara-e- Suf-e-Bala and Dara-e-Suf-e-Payeen districts of Samangan province. | 1 of 2 | AF2-IS-A-033 | Chela Mazar Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Dara-e- Suf-e-Payeen | Chela Mazar | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | AFGHAN LUCKY CONSTRUCTION COMPANY (ALCC) | 003/2026 | 143685.36 | IF(AQ196="","",AQ196) |  | 11 | 2026-12-14 | IF(W196<>"",W196,IF(OR(T196="",V196=""),"",EDATE(T196,V196))) |  | 25 | Under Construction | one scheme will be completed by Dec. 2026 and other scheme to be completed by June 2027 after NCE | IF(F196="","",IF(COUNT(AI196:AV196)=0,IF(AA196="","Not started",AA196),SUBSTITUTE(LOOKUP(2,1/(AI196:AV196<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F196="",COUNT(AI196:AV196)=0),"",TODAY()-LOOKUP(2,1/(AI196:AV196<>""),AI196:AV196)) | IF(OR(F196="",COUNT(AI196:AV196)<2),"",LOOKUP(2,1/(AI196:AV196<>""),AI196:AV196)-MIN(AI196:AV196)) | IF(OR(AD196="",AC196="Not started",AC196=""),"",IFERROR(AD196-IF(VLOOKUP(AC196,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC196,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F196="","",IF(OR(AA196="Cancelled",AC196="Cancelled"),"Cancelled",IF(OR(AC196="Completed / Handover",Y196<>"",Z196>=100),"Completed — on track",IF(O196="Not awarded",IF(U196="",IF(X196="","No planned date",IF(TODAY()>X196,"Behind — past planned date",IF(X196-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U196,"Behind — award date passed",IF(U196-TODAY()<=30,"At risk — close to off track","On track"))),IF(X196="","No planned date",IF(AND(TODAY()>X196,OR(Z196="",Z196<100)),"Behind — past end date",IF(AND(T196<>"",X196<>"",Z196<>"",(Z196<100),((TODAY()-T196)/MAX(X196-T196,1)*100)-Z196>15),"Behind — progress lag",IF(AND(X196-TODAY()<=30,X196-TODAY()>=0,OR(Z196="",Z196<90)),"At risk — close to off track","On track")))))))) | IF(OR(F196="",AC196="Completed / Handover",AC196="Cancelled"),"",IF(O196="Not awarded",IF(U196<>"",U196-TODAY(),IF(X196="","",X196-TODAY())),IF(X196="","",X196-TODAY()))) | [8 empty] | 2026-01-15 | 2026-01-15 |  |  |  |  | IF(OR(F196="",AJ196=""),"",IF(COUNT(AI196:AI196)=0,"",AJ196-LOOKUP(2,1/(AI196:AI196<>""),AI196:AI196))) | IF(OR(F196="",AK196=""),"",IF(COUNT(AI196:AJ196)=0,"",AK196-LOOKUP(2,1/(AI196:AJ196<>""),AI196:AJ196))) | IF(OR(F196="",AL196=""),"",IF(COUNT(AI196:AK196)=0,"",AL196-LOOKUP(2,1/(AI196:AK196<>""),AI196:AK196))) | IF(OR(F196="",AM196=""),"",IF(COUNT(AI196:AL196)=0,"",AM196-LOOKUP(2,1/(AI196:AL196<>""),AI196:AL196))) | IF(OR(F196="",AN196=""),"",IF(COUNT(AI196:AM196)=0,"",AN196-LOOKUP(2,1/(AI196:AM196<>""),AI196:AM196))) | IF(OR(F196="",AO196=""),"",IF(COUNT(AI196:AN196)=0,"",AO196-LOOKUP(2,1/(AI196:AN196<>""),AI196:AN196))) | IF(OR(F196="",AP196=""),"",IF(COUNT(AI196:AO196)=0,"",AP196-LOOKUP(2,1/(AI196:AO196<>""),AI196:AO196))) | IF(OR(F196="",AQ196=""),"",IF(COUNT(AI196:AP196)=0,"",AQ196-LOOKUP(2,1/(AI196:AP196<>""),AI196:AP196))) | IF(OR(F196="",AR196=""),"",IF(COUNT(AI196:AQ196)=0,"",AR196-LOOKUP(2,1/(AI196:AQ196<>""),AI196:AQ196))) | IF(OR(F196="",AS196=""),"",IF(COUNT(AI196:AR196)=0,"",AS196-LOOKUP(2,1/(AI196:AR196<>""),AI196:AR196))) | IF(OR(F196="",AT196=""),"",IF(COUNT(AI196:AS196)=0,"",AT196-LOOKUP(2,1/(AI196:AS196<>""),AI196:AS196))) | IF(OR(F196="",AU196=""),"",IF(COUNT(AI196:AT196)=0,"",AU196-LOOKUP(2,1/(AI196:AT196<>""),AI196:AT196))) | IF(OR(F196="",AV196=""),"",IF(COUNT(AI196:AU196)=0,"",AV196-LOOKUP(2,1/(AI196:AU196<>""),AI196:AU196))) | IF(J196="","All_Provinces",IFERROR(VLOOKUP(J196,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K196="","All_Districts",IFERROR(VLOOKUP(K196,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F197="","",ROW()-3) | AF2-IS-33 | Package #33-AF2 IS: Rehabilitation of Chela Mazar canal and Kushkak canal irrigation schemes, located in Dara-e- Suf-e-Bala and Dara-e-Suf-e-Payeen districts of Samangan province. | 2 of 2 | AF2-IS-A-034 | Kushkak Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Dara-e- Suf-e-Bala | Kushkak | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | AFGHAN LUCKY CONSTRUCTION COMPANY (ALCC) | 003/2026 | 140859.94 | IF(AQ197="","",AQ197) |  | 11 | 2026-12-14 | IF(W197<>"",W197,IF(OR(T197="",V197=""),"",EDATE(T197,V197))) |  | 67 | Under Construction | one scheme will be completed by Dec. 2026 and other scheme to be completed by June 2027 after NCE | IF(F197="","",IF(COUNT(AI197:AV197)=0,IF(AA197="","Not started",AA197),SUBSTITUTE(LOOKUP(2,1/(AI197:AV197<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F197="",COUNT(AI197:AV197)=0),"",TODAY()-LOOKUP(2,1/(AI197:AV197<>""),AI197:AV197)) | IF(OR(F197="",COUNT(AI197:AV197)<2),"",LOOKUP(2,1/(AI197:AV197<>""),AI197:AV197)-MIN(AI197:AV197)) | IF(OR(AD197="",AC197="Not started",AC197=""),"",IFERROR(AD197-IF(VLOOKUP(AC197,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC197,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F197="","",IF(OR(AA197="Cancelled",AC197="Cancelled"),"Cancelled",IF(OR(AC197="Completed / Handover",Y197<>"",Z197>=100),"Completed — on track",IF(O197="Not awarded",IF(U197="",IF(X197="","No planned date",IF(TODAY()>X197,"Behind — past planned date",IF(X197-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U197,"Behind — award date passed",IF(U197-TODAY()<=30,"At risk — close to off track","On track"))),IF(X197="","No planned date",IF(AND(TODAY()>X197,OR(Z197="",Z197<100)),"Behind — past end date",IF(AND(T197<>"",X197<>"",Z197<>"",(Z197<100),((TODAY()-T197)/MAX(X197-T197,1)*100)-Z197>15),"Behind — progress lag",IF(AND(X197-TODAY()<=30,X197-TODAY()>=0,OR(Z197="",Z197<90)),"At risk — close to off track","On track")))))))) | IF(OR(F197="",AC197="Completed / Handover",AC197="Cancelled"),"",IF(O197="Not awarded",IF(U197<>"",U197-TODAY(),IF(X197="","",X197-TODAY())),IF(X197="","",X197-TODAY()))) | [8 empty] | 2026-01-15 | 2026-01-15 |  |  |  |  | IF(OR(F197="",AJ197=""),"",IF(COUNT(AI197:AI197)=0,"",AJ197-LOOKUP(2,1/(AI197:AI197<>""),AI197:AI197))) | IF(OR(F197="",AK197=""),"",IF(COUNT(AI197:AJ197)=0,"",AK197-LOOKUP(2,1/(AI197:AJ197<>""),AI197:AJ197))) | IF(OR(F197="",AL197=""),"",IF(COUNT(AI197:AK197)=0,"",AL197-LOOKUP(2,1/(AI197:AK197<>""),AI197:AK197))) | IF(OR(F197="",AM197=""),"",IF(COUNT(AI197:AL197)=0,"",AM197-LOOKUP(2,1/(AI197:AL197<>""),AI197:AL197))) | IF(OR(F197="",AN197=""),"",IF(COUNT(AI197:AM197)=0,"",AN197-LOOKUP(2,1/(AI197:AM197<>""),AI197:AM197))) | IF(OR(F197="",AO197=""),"",IF(COUNT(AI197:AN197)=0,"",AO197-LOOKUP(2,1/(AI197:AN197<>""),AI197:AN197))) | IF(OR(F197="",AP197=""),"",IF(COUNT(AI197:AO197)=0,"",AP197-LOOKUP(2,1/(AI197:AO197<>""),AI197:AO197))) | IF(OR(F197="",AQ197=""),"",IF(COUNT(AI197:AP197)=0,"",AQ197-LOOKUP(2,1/(AI197:AP197<>""),AI197:AP197))) | IF(OR(F197="",AR197=""),"",IF(COUNT(AI197:AQ197)=0,"",AR197-LOOKUP(2,1/(AI197:AQ197<>""),AI197:AQ197))) | IF(OR(F197="",AS197=""),"",IF(COUNT(AI197:AR197)=0,"",AS197-LOOKUP(2,1/(AI197:AR197<>""),AI197:AR197))) | IF(OR(F197="",AT197=""),"",IF(COUNT(AI197:AS197)=0,"",AT197-LOOKUP(2,1/(AI197:AS197<>""),AI197:AS197))) | IF(OR(F197="",AU197=""),"",IF(COUNT(AI197:AT197)=0,"",AU197-LOOKUP(2,1/(AI197:AT197<>""),AI197:AT197))) | IF(OR(F197="",AV197=""),"",IF(COUNT(AI197:AU197)=0,"",AV197-LOOKUP(2,1/(AI197:AU197<>""),AI197:AU197))) | IF(J197="","All_Provinces",IFERROR(VLOOKUP(J197,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K197="","All_Districts",IFERROR(VLOOKUP(K197,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F198="","",ROW()-3) | AF2-IS-34 | Package #34-AF2 IS: Rehabilitation of Hashtman canal and Qashqasai canal irrigation schemes, located in Qaisar district of Faryab province. | 1 of 2 | AF2-IS-N-022 | Hashtman Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Faryab | Qaisar | Chechakto Majnon and Payan Guzar | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 397007.86 | IF(AQ198="","",AQ198) | 2026-12-30 | 9.2 | 2027-10-06 | IF(W198<>"",W198,IF(OR(T198="",V198=""),"",EDATE(T198,V198))) |  |  | ITB Launched | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals | IF(F198="","",IF(COUNT(AI198:AV198)=0,IF(AA198="","Not started",AA198),SUBSTITUTE(LOOKUP(2,1/(AI198:AV198<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F198="",COUNT(AI198:AV198)=0),"",TODAY()-LOOKUP(2,1/(AI198:AV198<>""),AI198:AV198)) | IF(OR(F198="",COUNT(AI198:AV198)<2),"",LOOKUP(2,1/(AI198:AV198<>""),AI198:AV198)-MIN(AI198:AV198)) | IF(OR(AD198="",AC198="Not started",AC198=""),"",IFERROR(AD198-IF(VLOOKUP(AC198,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC198,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F198="","",IF(OR(AA198="Cancelled",AC198="Cancelled"),"Cancelled",IF(OR(AC198="Completed / Handover",Y198<>"",Z198>=100),"Completed — on track",IF(O198="Not awarded",IF(U198="",IF(X198="","No planned date",IF(TODAY()>X198,"Behind — past planned date",IF(X198-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U198,"Behind — award date passed",IF(U198-TODAY()<=30,"At risk — close to off track","On track"))),IF(X198="","No planned date",IF(AND(TODAY()>X198,OR(Z198="",Z198<100)),"Behind — past end date",IF(AND(T198<>"",X198<>"",Z198<>"",(Z198<100),((TODAY()-T198)/MAX(X198-T198,1)*100)-Z198>15),"Behind — progress lag",IF(AND(X198-TODAY()<=30,X198-TODAY()>=0,OR(Z198="",Z198<90)),"At risk — close to off track","On track")))))))) | IF(OR(F198="",AC198="Completed / Handover",AC198="Cancelled"),"",IF(O198="Not awarded",IF(U198<>"",U198-TODAY(),IF(X198="","",X198-TODAY())),IF(X198="","",X198-TODAY()))) | [14 empty] | IF(OR(F198="",AJ198=""),"",IF(COUNT(AI198:AI198)=0,"",AJ198-LOOKUP(2,1/(AI198:AI198<>""),AI198:AI198))) | IF(OR(F198="",AK198=""),"",IF(COUNT(AI198:AJ198)=0,"",AK198-LOOKUP(2,1/(AI198:AJ198<>""),AI198:AJ198))) | IF(OR(F198="",AL198=""),"",IF(COUNT(AI198:AK198)=0,"",AL198-LOOKUP(2,1/(AI198:AK198<>""),AI198:AK198))) | IF(OR(F198="",AM198=""),"",IF(COUNT(AI198:AL198)=0,"",AM198-LOOKUP(2,1/(AI198:AL198<>""),AI198:AL198))) | IF(OR(F198="",AN198=""),"",IF(COUNT(AI198:AM198)=0,"",AN198-LOOKUP(2,1/(AI198:AM198<>""),AI198:AM198))) | IF(OR(F198="",AO198=""),"",IF(COUNT(AI198:AN198)=0,"",AO198-LOOKUP(2,1/(AI198:AN198<>""),AI198:AN198))) | IF(OR(F198="",AP198=""),"",IF(COUNT(AI198:AO198)=0,"",AP198-LOOKUP(2,1/(AI198:AO198<>""),AI198:AO198))) | IF(OR(F198="",AQ198=""),"",IF(COUNT(AI198:AP198)=0,"",AQ198-LOOKUP(2,1/(AI198:AP198<>""),AI198:AP198))) | IF(OR(F198="",AR198=""),"",IF(COUNT(AI198:AQ198)=0,"",AR198-LOOKUP(2,1/(AI198:AQ198<>""),AI198:AQ198))) | IF(OR(F198="",AS198=""),"",IF(COUNT(AI198:AR198)=0,"",AS198-LOOKUP(2,1/(AI198:AR198<>""),AI198:AR198))) | IF(OR(F198="",AT198=""),"",IF(COUNT(AI198:AS198)=0,"",AT198-LOOKUP(2,1/(AI198:AS198<>""),AI198:AS198))) | IF(OR(F198="",AU198=""),"",IF(COUNT(AI198:AT198)=0,"",AU198-LOOKUP(2,1/(AI198:AT198<>""),AI198:AT198))) | IF(OR(F198="",AV198=""),"",IF(COUNT(AI198:AU198)=0,"",AV198-LOOKUP(2,1/(AI198:AU198<>""),AI198:AU198))) | IF(J198="","All_Provinces",IFERROR(VLOOKUP(J198,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K198="","All_Districts",IFERROR(VLOOKUP(K198,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F199="","",ROW()-3) | AF2-IS-34 | Package #34-AF2 IS: Rehabilitation of Hashtman canal and Qashqasai canal irrigation schemes, located in Qaisar district of Faryab province. | 2 of 2 | AF2-IS-N-023 | Qashqasai Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Faryab | Qaisar | Yaka Bagh, Kham badal, Pacha Khor, and Borghan Erak. | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 397007.86 | IF(AQ199="","",AQ199) | 2026-12-30 | 9.2 | 2027-10-06 | IF(W199<>"",W199,IF(OR(T199="",V199=""),"",EDATE(T199,V199))) |  |  | ITB Launched | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals | IF(F199="","",IF(COUNT(AI199:AV199)=0,IF(AA199="","Not started",AA199),SUBSTITUTE(LOOKUP(2,1/(AI199:AV199<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F199="",COUNT(AI199:AV199)=0),"",TODAY()-LOOKUP(2,1/(AI199:AV199<>""),AI199:AV199)) | IF(OR(F199="",COUNT(AI199:AV199)<2),"",LOOKUP(2,1/(AI199:AV199<>""),AI199:AV199)-MIN(AI199:AV199)) | IF(OR(AD199="",AC199="Not started",AC199=""),"",IFERROR(AD199-IF(VLOOKUP(AC199,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC199,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F199="","",IF(OR(AA199="Cancelled",AC199="Cancelled"),"Cancelled",IF(OR(AC199="Completed / Handover",Y199<>"",Z199>=100),"Completed — on track",IF(O199="Not awarded",IF(U199="",IF(X199="","No planned date",IF(TODAY()>X199,"Behind — past planned date",IF(X199-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U199,"Behind — award date passed",IF(U199-TODAY()<=30,"At risk — close to off track","On track"))),IF(X199="","No planned date",IF(AND(TODAY()>X199,OR(Z199="",Z199<100)),"Behind — past end date",IF(AND(T199<>"",X199<>"",Z199<>"",(Z199<100),((TODAY()-T199)/MAX(X199-T199,1)*100)-Z199>15),"Behind — progress lag",IF(AND(X199-TODAY()<=30,X199-TODAY()>=0,OR(Z199="",Z199<90)),"At risk — close to off track","On track")))))))) | IF(OR(F199="",AC199="Completed / Handover",AC199="Cancelled"),"",IF(O199="Not awarded",IF(U199<>"",U199-TODAY(),IF(X199="","",X199-TODAY())),IF(X199="","",X199-TODAY()))) | [14 empty] | IF(OR(F199="",AJ199=""),"",IF(COUNT(AI199:AI199)=0,"",AJ199-LOOKUP(2,1/(AI199:AI199<>""),AI199:AI199))) | IF(OR(F199="",AK199=""),"",IF(COUNT(AI199:AJ199)=0,"",AK199-LOOKUP(2,1/(AI199:AJ199<>""),AI199:AJ199))) | IF(OR(F199="",AL199=""),"",IF(COUNT(AI199:AK199)=0,"",AL199-LOOKUP(2,1/(AI199:AK199<>""),AI199:AK199))) | IF(OR(F199="",AM199=""),"",IF(COUNT(AI199:AL199)=0,"",AM199-LOOKUP(2,1/(AI199:AL199<>""),AI199:AL199))) | IF(OR(F199="",AN199=""),"",IF(COUNT(AI199:AM199)=0,"",AN199-LOOKUP(2,1/(AI199:AM199<>""),AI199:AM199))) | IF(OR(F199="",AO199=""),"",IF(COUNT(AI199:AN199)=0,"",AO199-LOOKUP(2,1/(AI199:AN199<>""),AI199:AN199))) | IF(OR(F199="",AP199=""),"",IF(COUNT(AI199:AO199)=0,"",AP199-LOOKUP(2,1/(AI199:AO199<>""),AI199:AO199))) | IF(OR(F199="",AQ199=""),"",IF(COUNT(AI199:AP199)=0,"",AQ199-LOOKUP(2,1/(AI199:AP199<>""),AI199:AP199))) | IF(OR(F199="",AR199=""),"",IF(COUNT(AI199:AQ199)=0,"",AR199-LOOKUP(2,1/(AI199:AQ199<>""),AI199:AQ199))) | IF(OR(F199="",AS199=""),"",IF(COUNT(AI199:AR199)=0,"",AS199-LOOKUP(2,1/(AI199:AR199<>""),AI199:AR199))) | IF(OR(F199="",AT199=""),"",IF(COUNT(AI199:AS199)=0,"",AT199-LOOKUP(2,1/(AI199:AS199<>""),AI199:AS199))) | IF(OR(F199="",AU199=""),"",IF(COUNT(AI199:AT199)=0,"",AU199-LOOKUP(2,1/(AI199:AT199<>""),AI199:AT199))) | IF(OR(F199="",AV199=""),"",IF(COUNT(AI199:AU199)=0,"",AV199-LOOKUP(2,1/(AI199:AU199<>""),AI199:AU199))) | IF(J199="","All_Provinces",IFERROR(VLOOKUP(J199,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K199="","All_Districts",IFERROR(VLOOKUP(K199,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F200="","",ROW()-3) | AF2-IS-35 | Package # 35-AF2 IS: Rehabilitation of Bahr-e Ameq canal irrigation scheme, located in Sozma Qala districts of Sar-e-Pul province. | 1 of 1 | AF2-IS-A-035 | Bahr-e Ameq Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sar-e- Pul | Sozma Qala | Bahr-e Ameq | World Bank (WBK/AF-2) | Awarded | 1.Awarded contracts_On&off-farm | Sakht shamal construction and road building company (SSCC) | 016/2026 | 249484.29 | IF(AQ200="","",AQ200) |  | 11 | 2027-01-16 | IF(W200<>"",W200,IF(OR(T200="",V200=""),"",EDATE(T200,V200))) |  | 60 | Under Construction | on track and will be completed by Jan. 2027 | IF(F200="","",IF(COUNT(AI200:AV200)=0,IF(AA200="","Not started",AA200),SUBSTITUTE(LOOKUP(2,1/(AI200:AV200<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F200="",COUNT(AI200:AV200)=0),"",TODAY()-LOOKUP(2,1/(AI200:AV200<>""),AI200:AV200)) | IF(OR(F200="",COUNT(AI200:AV200)<2),"",LOOKUP(2,1/(AI200:AV200<>""),AI200:AV200)-MIN(AI200:AV200)) | IF(OR(AD200="",AC200="Not started",AC200=""),"",IFERROR(AD200-IF(VLOOKUP(AC200,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC200,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F200="","",IF(OR(AA200="Cancelled",AC200="Cancelled"),"Cancelled",IF(OR(AC200="Completed / Handover",Y200<>"",Z200>=100),"Completed — on track",IF(O200="Not awarded",IF(U200="",IF(X200="","No planned date",IF(TODAY()>X200,"Behind — past planned date",IF(X200-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U200,"Behind — award date passed",IF(U200-TODAY()<=30,"At risk — close to off track","On track"))),IF(X200="","No planned date",IF(AND(TODAY()>X200,OR(Z200="",Z200<100)),"Behind — past end date",IF(AND(T200<>"",X200<>"",Z200<>"",(Z200<100),((TODAY()-T200)/MAX(X200-T200,1)*100)-Z200>15),"Behind — progress lag",IF(AND(X200-TODAY()<=30,X200-TODAY()>=0,OR(Z200="",Z200<90)),"At risk — close to off track","On track")))))))) | IF(OR(F200="",AC200="Completed / Handover",AC200="Cancelled"),"",IF(O200="Not awarded",IF(U200<>"",U200-TODAY(),IF(X200="","",X200-TODAY())),IF(X200="","",X200-TODAY()))) | [8 empty] | 2026-02-17 | 2026-02-17 |  |  |  |  | IF(OR(F200="",AJ200=""),"",IF(COUNT(AI200:AI200)=0,"",AJ200-LOOKUP(2,1/(AI200:AI200<>""),AI200:AI200))) | IF(OR(F200="",AK200=""),"",IF(COUNT(AI200:AJ200)=0,"",AK200-LOOKUP(2,1/(AI200:AJ200<>""),AI200:AJ200))) | IF(OR(F200="",AL200=""),"",IF(COUNT(AI200:AK200)=0,"",AL200-LOOKUP(2,1/(AI200:AK200<>""),AI200:AK200))) | IF(OR(F200="",AM200=""),"",IF(COUNT(AI200:AL200)=0,"",AM200-LOOKUP(2,1/(AI200:AL200<>""),AI200:AL200))) | IF(OR(F200="",AN200=""),"",IF(COUNT(AI200:AM200)=0,"",AN200-LOOKUP(2,1/(AI200:AM200<>""),AI200:AM200))) | IF(OR(F200="",AO200=""),"",IF(COUNT(AI200:AN200)=0,"",AO200-LOOKUP(2,1/(AI200:AN200<>""),AI200:AN200))) | IF(OR(F200="",AP200=""),"",IF(COUNT(AI200:AO200)=0,"",AP200-LOOKUP(2,1/(AI200:AO200<>""),AI200:AO200))) | IF(OR(F200="",AQ200=""),"",IF(COUNT(AI200:AP200)=0,"",AQ200-LOOKUP(2,1/(AI200:AP200<>""),AI200:AP200))) | IF(OR(F200="",AR200=""),"",IF(COUNT(AI200:AQ200)=0,"",AR200-LOOKUP(2,1/(AI200:AQ200<>""),AI200:AQ200))) | IF(OR(F200="",AS200=""),"",IF(COUNT(AI200:AR200)=0,"",AS200-LOOKUP(2,1/(AI200:AR200<>""),AI200:AR200))) | IF(OR(F200="",AT200=""),"",IF(COUNT(AI200:AS200)=0,"",AT200-LOOKUP(2,1/(AI200:AS200<>""),AI200:AS200))) | IF(OR(F200="",AU200=""),"",IF(COUNT(AI200:AT200)=0,"",AU200-LOOKUP(2,1/(AI200:AT200<>""),AI200:AT200))) | IF(OR(F200="",AV200=""),"",IF(COUNT(AI200:AU200)=0,"",AV200-LOOKUP(2,1/(AI200:AU200<>""),AI200:AU200))) | IF(J200="","All_Provinces",IFERROR(VLOOKUP(J200,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K200="","All_Districts",IFERROR(VLOOKUP(K200,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F201="","",ROW()-3) | AF2-IS-36 | Package # 36-AF2 IS: Rehabilitation of Joy Shahr canal irrigation scheme, located in Aqcha district of Jawzjan province. | 1 of 1 | AF2-IS-N-024 | Joy Shahr Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Jawzjan | Aqcha | Joy Shahr in Jiza | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 55950 | IF(AQ201="","",AQ201) | 2026-12-17 | 5.6 | 2027-06-05 | IF(W201<>"",W201,IF(OR(T201="",V201=""),"",EDATE(T201,V201))) |  |  | Under LTO Review | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals. Explore split into 2 lots | IF(F201="","",IF(COUNT(AI201:AV201)=0,IF(AA201="","Not started",AA201),SUBSTITUTE(LOOKUP(2,1/(AI201:AV201<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F201="",COUNT(AI201:AV201)=0),"",TODAY()-LOOKUP(2,1/(AI201:AV201<>""),AI201:AV201)) | IF(OR(F201="",COUNT(AI201:AV201)<2),"",LOOKUP(2,1/(AI201:AV201<>""),AI201:AV201)-MIN(AI201:AV201)) | IF(OR(AD201="",AC201="Not started",AC201=""),"",IFERROR(AD201-IF(VLOOKUP(AC201,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC201,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F201="","",IF(OR(AA201="Cancelled",AC201="Cancelled"),"Cancelled",IF(OR(AC201="Completed / Handover",Y201<>"",Z201>=100),"Completed — on track",IF(O201="Not awarded",IF(U201="",IF(X201="","No planned date",IF(TODAY()>X201,"Behind — past planned date",IF(X201-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U201,"Behind — award date passed",IF(U201-TODAY()<=30,"At risk — close to off track","On track"))),IF(X201="","No planned date",IF(AND(TODAY()>X201,OR(Z201="",Z201<100)),"Behind — past end date",IF(AND(T201<>"",X201<>"",Z201<>"",(Z201<100),((TODAY()-T201)/MAX(X201-T201,1)*100)-Z201>15),"Behind — progress lag",IF(AND(X201-TODAY()<=30,X201-TODAY()>=0,OR(Z201="",Z201<90)),"At risk — close to off track","On track")))))))) | IF(OR(F201="",AC201="Completed / Handover",AC201="Cancelled"),"",IF(O201="Not awarded",IF(U201<>"",U201-TODAY(),IF(X201="","",X201-TODAY())),IF(X201="","",X201-TODAY()))) | [14 empty] | IF(OR(F201="",AJ201=""),"",IF(COUNT(AI201:AI201)=0,"",AJ201-LOOKUP(2,1/(AI201:AI201<>""),AI201:AI201))) | IF(OR(F201="",AK201=""),"",IF(COUNT(AI201:AJ201)=0,"",AK201-LOOKUP(2,1/(AI201:AJ201<>""),AI201:AJ201))) | IF(OR(F201="",AL201=""),"",IF(COUNT(AI201:AK201)=0,"",AL201-LOOKUP(2,1/(AI201:AK201<>""),AI201:AK201))) | IF(OR(F201="",AM201=""),"",IF(COUNT(AI201:AL201)=0,"",AM201-LOOKUP(2,1/(AI201:AL201<>""),AI201:AL201))) | IF(OR(F201="",AN201=""),"",IF(COUNT(AI201:AM201)=0,"",AN201-LOOKUP(2,1/(AI201:AM201<>""),AI201:AM201))) | IF(OR(F201="",AO201=""),"",IF(COUNT(AI201:AN201)=0,"",AO201-LOOKUP(2,1/(AI201:AN201<>""),AI201:AN201))) | IF(OR(F201="",AP201=""),"",IF(COUNT(AI201:AO201)=0,"",AP201-LOOKUP(2,1/(AI201:AO201<>""),AI201:AO201))) | IF(OR(F201="",AQ201=""),"",IF(COUNT(AI201:AP201)=0,"",AQ201-LOOKUP(2,1/(AI201:AP201<>""),AI201:AP201))) | IF(OR(F201="",AR201=""),"",IF(COUNT(AI201:AQ201)=0,"",AR201-LOOKUP(2,1/(AI201:AQ201<>""),AI201:AQ201))) | IF(OR(F201="",AS201=""),"",IF(COUNT(AI201:AR201)=0,"",AS201-LOOKUP(2,1/(AI201:AR201<>""),AI201:AR201))) | IF(OR(F201="",AT201=""),"",IF(COUNT(AI201:AS201)=0,"",AT201-LOOKUP(2,1/(AI201:AS201<>""),AI201:AS201))) | IF(OR(F201="",AU201=""),"",IF(COUNT(AI201:AT201)=0,"",AU201-LOOKUP(2,1/(AI201:AT201<>""),AI201:AT201))) | IF(OR(F201="",AV201=""),"",IF(COUNT(AI201:AU201)=0,"",AV201-LOOKUP(2,1/(AI201:AU201<>""),AI201:AU201))) | IF(J201="","All_Provinces",IFERROR(VLOOKUP(J201,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K201="","All_Districts",IFERROR(VLOOKUP(K201,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F202="","",ROW()-3) | AF2-IS-37 | Package #37-AF2 IS: Rehabilitation of Oshtorkhan/Ahangaran irrigation scheme, located in Firozkoh district of Ghor province. | 1 of 1 | AF2-IS-N-025 | Oshtorkhan/Ahangaran irrigation Schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Firozkoh | Oshtorkhan, Ahangaran and Madrasa | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 128000 | IF(AQ202="","",AQ202) | 2026-12-30 | 7.6 | 2027-08-17 | IF(W202<>"",W202,IF(OR(T202="",V202=""),"",EDATE(T202,V202))) |  |  | Under Design | Three months slack period Jan-Mar during winter. Five months construction period required for two canals | IF(F202="","",IF(COUNT(AI202:AV202)=0,IF(AA202="","Not started",AA202),SUBSTITUTE(LOOKUP(2,1/(AI202:AV202<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F202="",COUNT(AI202:AV202)=0),"",TODAY()-LOOKUP(2,1/(AI202:AV202<>""),AI202:AV202)) | IF(OR(F202="",COUNT(AI202:AV202)<2),"",LOOKUP(2,1/(AI202:AV202<>""),AI202:AV202)-MIN(AI202:AV202)) | IF(OR(AD202="",AC202="Not started",AC202=""),"",IFERROR(AD202-IF(VLOOKUP(AC202,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC202,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F202="","",IF(OR(AA202="Cancelled",AC202="Cancelled"),"Cancelled",IF(OR(AC202="Completed / Handover",Y202<>"",Z202>=100),"Completed — on track",IF(O202="Not awarded",IF(U202="",IF(X202="","No planned date",IF(TODAY()>X202,"Behind — past planned date",IF(X202-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U202,"Behind — award date passed",IF(U202-TODAY()<=30,"At risk — close to off track","On track"))),IF(X202="","No planned date",IF(AND(TODAY()>X202,OR(Z202="",Z202<100)),"Behind — past end date",IF(AND(T202<>"",X202<>"",Z202<>"",(Z202<100),((TODAY()-T202)/MAX(X202-T202,1)*100)-Z202>15),"Behind — progress lag",IF(AND(X202-TODAY()<=30,X202-TODAY()>=0,OR(Z202="",Z202<90)),"At risk — close to off track","On track")))))))) | IF(OR(F202="",AC202="Completed / Handover",AC202="Cancelled"),"",IF(O202="Not awarded",IF(U202<>"",U202-TODAY(),IF(X202="","",X202-TODAY())),IF(X202="","",X202-TODAY()))) | [14 empty] | IF(OR(F202="",AJ202=""),"",IF(COUNT(AI202:AI202)=0,"",AJ202-LOOKUP(2,1/(AI202:AI202<>""),AI202:AI202))) | IF(OR(F202="",AK202=""),"",IF(COUNT(AI202:AJ202)=0,"",AK202-LOOKUP(2,1/(AI202:AJ202<>""),AI202:AJ202))) | IF(OR(F202="",AL202=""),"",IF(COUNT(AI202:AK202)=0,"",AL202-LOOKUP(2,1/(AI202:AK202<>""),AI202:AK202))) | IF(OR(F202="",AM202=""),"",IF(COUNT(AI202:AL202)=0,"",AM202-LOOKUP(2,1/(AI202:AL202<>""),AI202:AL202))) | IF(OR(F202="",AN202=""),"",IF(COUNT(AI202:AM202)=0,"",AN202-LOOKUP(2,1/(AI202:AM202<>""),AI202:AM202))) | IF(OR(F202="",AO202=""),"",IF(COUNT(AI202:AN202)=0,"",AO202-LOOKUP(2,1/(AI202:AN202<>""),AI202:AN202))) | IF(OR(F202="",AP202=""),"",IF(COUNT(AI202:AO202)=0,"",AP202-LOOKUP(2,1/(AI202:AO202<>""),AI202:AO202))) | IF(OR(F202="",AQ202=""),"",IF(COUNT(AI202:AP202)=0,"",AQ202-LOOKUP(2,1/(AI202:AP202<>""),AI202:AP202))) | IF(OR(F202="",AR202=""),"",IF(COUNT(AI202:AQ202)=0,"",AR202-LOOKUP(2,1/(AI202:AQ202<>""),AI202:AQ202))) | IF(OR(F202="",AS202=""),"",IF(COUNT(AI202:AR202)=0,"",AS202-LOOKUP(2,1/(AI202:AR202<>""),AI202:AR202))) | IF(OR(F202="",AT202=""),"",IF(COUNT(AI202:AS202)=0,"",AT202-LOOKUP(2,1/(AI202:AS202<>""),AI202:AS202))) | IF(OR(F202="",AU202=""),"",IF(COUNT(AI202:AT202)=0,"",AU202-LOOKUP(2,1/(AI202:AT202<>""),AI202:AT202))) | IF(OR(F202="",AV202=""),"",IF(COUNT(AI202:AU202)=0,"",AV202-LOOKUP(2,1/(AI202:AU202<>""),AI202:AU202))) | IF(J202="","All_Provinces",IFERROR(VLOOKUP(J202,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K202="","All_Districts",IFERROR(VLOOKUP(K202,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F203="","",ROW()-3) | AF2-IS-38 | Package #38-AF2 IS: Rehabilitation of Todanak Payen irrigation scheme, located in Farahrud Districts of Farah province. | 1 of 1 | AF2-IS-N-026 | Todanak Payen Canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Farah | Farahrud | Todanak Payen villages | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 170000 | IF(AQ203="","",AQ203) | 2026-12-15 | 9 | 2027-09-14 | IF(W203<>"",W203,IF(OR(T203="",V203=""),"",EDATE(T203,V203))) |  |  | Under Review of WRI | Two months slack period Mar-Apr during the flood. Seven months construction period. Explore split into 2 lots if needed | IF(F203="","",IF(COUNT(AI203:AV203)=0,IF(AA203="","Not started",AA203),SUBSTITUTE(LOOKUP(2,1/(AI203:AV203<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F203="",COUNT(AI203:AV203)=0),"",TODAY()-LOOKUP(2,1/(AI203:AV203<>""),AI203:AV203)) | IF(OR(F203="",COUNT(AI203:AV203)<2),"",LOOKUP(2,1/(AI203:AV203<>""),AI203:AV203)-MIN(AI203:AV203)) | IF(OR(AD203="",AC203="Not started",AC203=""),"",IFERROR(AD203-IF(VLOOKUP(AC203,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC203,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F203="","",IF(OR(AA203="Cancelled",AC203="Cancelled"),"Cancelled",IF(OR(AC203="Completed / Handover",Y203<>"",Z203>=100),"Completed — on track",IF(O203="Not awarded",IF(U203="",IF(X203="","No planned date",IF(TODAY()>X203,"Behind — past planned date",IF(X203-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U203,"Behind — award date passed",IF(U203-TODAY()<=30,"At risk — close to off track","On track"))),IF(X203="","No planned date",IF(AND(TODAY()>X203,OR(Z203="",Z203<100)),"Behind — past end date",IF(AND(T203<>"",X203<>"",Z203<>"",(Z203<100),((TODAY()-T203)/MAX(X203-T203,1)*100)-Z203>15),"Behind — progress lag",IF(AND(X203-TODAY()<=30,X203-TODAY()>=0,OR(Z203="",Z203<90)),"At risk — close to off track","On track")))))))) | IF(OR(F203="",AC203="Completed / Handover",AC203="Cancelled"),"",IF(O203="Not awarded",IF(U203<>"",U203-TODAY(),IF(X203="","",X203-TODAY())),IF(X203="","",X203-TODAY()))) | [14 empty] | IF(OR(F203="",AJ203=""),"",IF(COUNT(AI203:AI203)=0,"",AJ203-LOOKUP(2,1/(AI203:AI203<>""),AI203:AI203))) | IF(OR(F203="",AK203=""),"",IF(COUNT(AI203:AJ203)=0,"",AK203-LOOKUP(2,1/(AI203:AJ203<>""),AI203:AJ203))) | IF(OR(F203="",AL203=""),"",IF(COUNT(AI203:AK203)=0,"",AL203-LOOKUP(2,1/(AI203:AK203<>""),AI203:AK203))) | IF(OR(F203="",AM203=""),"",IF(COUNT(AI203:AL203)=0,"",AM203-LOOKUP(2,1/(AI203:AL203<>""),AI203:AL203))) | IF(OR(F203="",AN203=""),"",IF(COUNT(AI203:AM203)=0,"",AN203-LOOKUP(2,1/(AI203:AM203<>""),AI203:AM203))) | IF(OR(F203="",AO203=""),"",IF(COUNT(AI203:AN203)=0,"",AO203-LOOKUP(2,1/(AI203:AN203<>""),AI203:AN203))) | IF(OR(F203="",AP203=""),"",IF(COUNT(AI203:AO203)=0,"",AP203-LOOKUP(2,1/(AI203:AO203<>""),AI203:AO203))) | IF(OR(F203="",AQ203=""),"",IF(COUNT(AI203:AP203)=0,"",AQ203-LOOKUP(2,1/(AI203:AP203<>""),AI203:AP203))) | IF(OR(F203="",AR203=""),"",IF(COUNT(AI203:AQ203)=0,"",AR203-LOOKUP(2,1/(AI203:AQ203<>""),AI203:AQ203))) | IF(OR(F203="",AS203=""),"",IF(COUNT(AI203:AR203)=0,"",AS203-LOOKUP(2,1/(AI203:AR203<>""),AI203:AR203))) | IF(OR(F203="",AT203=""),"",IF(COUNT(AI203:AS203)=0,"",AT203-LOOKUP(2,1/(AI203:AS203<>""),AI203:AS203))) | IF(OR(F203="",AU203=""),"",IF(COUNT(AI203:AT203)=0,"",AU203-LOOKUP(2,1/(AI203:AT203<>""),AI203:AT203))) | IF(OR(F203="",AV203=""),"",IF(COUNT(AI203:AU203)=0,"",AV203-LOOKUP(2,1/(AI203:AU203<>""),AI203:AU203))) | IF(J203="","All_Provinces",IFERROR(VLOOKUP(J203,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K203="","All_Districts",IFERROR(VLOOKUP(K203,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F204="","",ROW()-3) | AF2-IS-39 | Package #39-AF2 IS: Rehabilitation of Ludeenha and Joi Kar irrigation schemes in Bala Murghab districts of Badghis provinec. | 1 of 1 | AF2-IS-N-027 | Ludeenha and Joi Kar canal irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Bala Murghab | Joi Kar | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 195488.81 | IF(AQ204="","",AQ204) | 2026-12-30 | 7.9 | 2027-08-27 | IF(W204<>"",W204,IF(OR(T204="",V204=""),"",EDATE(T204,V204))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Five months construction period required for two canals | IF(F204="","",IF(COUNT(AI204:AV204)=0,IF(AA204="","Not started",AA204),SUBSTITUTE(LOOKUP(2,1/(AI204:AV204<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F204="",COUNT(AI204:AV204)=0),"",TODAY()-LOOKUP(2,1/(AI204:AV204<>""),AI204:AV204)) | IF(OR(F204="",COUNT(AI204:AV204)<2),"",LOOKUP(2,1/(AI204:AV204<>""),AI204:AV204)-MIN(AI204:AV204)) | IF(OR(AD204="",AC204="Not started",AC204=""),"",IFERROR(AD204-IF(VLOOKUP(AC204,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC204,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F204="","",IF(OR(AA204="Cancelled",AC204="Cancelled"),"Cancelled",IF(OR(AC204="Completed / Handover",Y204<>"",Z204>=100),"Completed — on track",IF(O204="Not awarded",IF(U204="",IF(X204="","No planned date",IF(TODAY()>X204,"Behind — past planned date",IF(X204-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U204,"Behind — award date passed",IF(U204-TODAY()<=30,"At risk — close to off track","On track"))),IF(X204="","No planned date",IF(AND(TODAY()>X204,OR(Z204="",Z204<100)),"Behind — past end date",IF(AND(T204<>"",X204<>"",Z204<>"",(Z204<100),((TODAY()-T204)/MAX(X204-T204,1)*100)-Z204>15),"Behind — progress lag",IF(AND(X204-TODAY()<=30,X204-TODAY()>=0,OR(Z204="",Z204<90)),"At risk — close to off track","On track")))))))) | IF(OR(F204="",AC204="Completed / Handover",AC204="Cancelled"),"",IF(O204="Not awarded",IF(U204<>"",U204-TODAY(),IF(X204="","",X204-TODAY())),IF(X204="","",X204-TODAY()))) | [14 empty] | IF(OR(F204="",AJ204=""),"",IF(COUNT(AI204:AI204)=0,"",AJ204-LOOKUP(2,1/(AI204:AI204<>""),AI204:AI204))) | IF(OR(F204="",AK204=""),"",IF(COUNT(AI204:AJ204)=0,"",AK204-LOOKUP(2,1/(AI204:AJ204<>""),AI204:AJ204))) | IF(OR(F204="",AL204=""),"",IF(COUNT(AI204:AK204)=0,"",AL204-LOOKUP(2,1/(AI204:AK204<>""),AI204:AK204))) | IF(OR(F204="",AM204=""),"",IF(COUNT(AI204:AL204)=0,"",AM204-LOOKUP(2,1/(AI204:AL204<>""),AI204:AL204))) | IF(OR(F204="",AN204=""),"",IF(COUNT(AI204:AM204)=0,"",AN204-LOOKUP(2,1/(AI204:AM204<>""),AI204:AM204))) | IF(OR(F204="",AO204=""),"",IF(COUNT(AI204:AN204)=0,"",AO204-LOOKUP(2,1/(AI204:AN204<>""),AI204:AN204))) | IF(OR(F204="",AP204=""),"",IF(COUNT(AI204:AO204)=0,"",AP204-LOOKUP(2,1/(AI204:AO204<>""),AI204:AO204))) | IF(OR(F204="",AQ204=""),"",IF(COUNT(AI204:AP204)=0,"",AQ204-LOOKUP(2,1/(AI204:AP204<>""),AI204:AP204))) | IF(OR(F204="",AR204=""),"",IF(COUNT(AI204:AQ204)=0,"",AR204-LOOKUP(2,1/(AI204:AQ204<>""),AI204:AQ204))) | IF(OR(F204="",AS204=""),"",IF(COUNT(AI204:AR204)=0,"",AS204-LOOKUP(2,1/(AI204:AR204<>""),AI204:AR204))) | IF(OR(F204="",AT204=""),"",IF(COUNT(AI204:AS204)=0,"",AT204-LOOKUP(2,1/(AI204:AS204<>""),AI204:AS204))) | IF(OR(F204="",AU204=""),"",IF(COUNT(AI204:AT204)=0,"",AU204-LOOKUP(2,1/(AI204:AT204<>""),AI204:AT204))) | IF(OR(F204="",AV204=""),"",IF(COUNT(AI204:AU204)=0,"",AV204-LOOKUP(2,1/(AI204:AU204<>""),AI204:AU204))) | IF(J204="","All_Provinces",IFERROR(VLOOKUP(J204,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K204="","All_Districts",IFERROR(VLOOKUP(K204,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F205="","",ROW()-3) | AF2-IS-40 | Package #40-AF2 IS: Rehabilitation of Loka Mazar irrigation schemes, located in Dawlatyar District of Ghor province. | 1 of 1 | AF2-IS-N-028 | Loka Mazar Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Dawlatyar | Lokamazar | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 141250 | IF(AQ205="","",AQ205) | 2026-12-31 | 7.9 | 2027-08-28 | IF(W205<>"",W205,IF(OR(T205="",V205=""),"",EDATE(T205,V205))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Five months construction period required for two canals | IF(F205="","",IF(COUNT(AI205:AV205)=0,IF(AA205="","Not started",AA205),SUBSTITUTE(LOOKUP(2,1/(AI205:AV205<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F205="",COUNT(AI205:AV205)=0),"",TODAY()-LOOKUP(2,1/(AI205:AV205<>""),AI205:AV205)) | IF(OR(F205="",COUNT(AI205:AV205)<2),"",LOOKUP(2,1/(AI205:AV205<>""),AI205:AV205)-MIN(AI205:AV205)) | IF(OR(AD205="",AC205="Not started",AC205=""),"",IFERROR(AD205-IF(VLOOKUP(AC205,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC205,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F205="","",IF(OR(AA205="Cancelled",AC205="Cancelled"),"Cancelled",IF(OR(AC205="Completed / Handover",Y205<>"",Z205>=100),"Completed — on track",IF(O205="Not awarded",IF(U205="",IF(X205="","No planned date",IF(TODAY()>X205,"Behind — past planned date",IF(X205-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U205,"Behind — award date passed",IF(U205-TODAY()<=30,"At risk — close to off track","On track"))),IF(X205="","No planned date",IF(AND(TODAY()>X205,OR(Z205="",Z205<100)),"Behind — past end date",IF(AND(T205<>"",X205<>"",Z205<>"",(Z205<100),((TODAY()-T205)/MAX(X205-T205,1)*100)-Z205>15),"Behind — progress lag",IF(AND(X205-TODAY()<=30,X205-TODAY()>=0,OR(Z205="",Z205<90)),"At risk — close to off track","On track")))))))) | IF(OR(F205="",AC205="Completed / Handover",AC205="Cancelled"),"",IF(O205="Not awarded",IF(U205<>"",U205-TODAY(),IF(X205="","",X205-TODAY())),IF(X205="","",X205-TODAY()))) | [14 empty] | IF(OR(F205="",AJ205=""),"",IF(COUNT(AI205:AI205)=0,"",AJ205-LOOKUP(2,1/(AI205:AI205<>""),AI205:AI205))) | IF(OR(F205="",AK205=""),"",IF(COUNT(AI205:AJ205)=0,"",AK205-LOOKUP(2,1/(AI205:AJ205<>""),AI205:AJ205))) | IF(OR(F205="",AL205=""),"",IF(COUNT(AI205:AK205)=0,"",AL205-LOOKUP(2,1/(AI205:AK205<>""),AI205:AK205))) | IF(OR(F205="",AM205=""),"",IF(COUNT(AI205:AL205)=0,"",AM205-LOOKUP(2,1/(AI205:AL205<>""),AI205:AL205))) | IF(OR(F205="",AN205=""),"",IF(COUNT(AI205:AM205)=0,"",AN205-LOOKUP(2,1/(AI205:AM205<>""),AI205:AM205))) | IF(OR(F205="",AO205=""),"",IF(COUNT(AI205:AN205)=0,"",AO205-LOOKUP(2,1/(AI205:AN205<>""),AI205:AN205))) | IF(OR(F205="",AP205=""),"",IF(COUNT(AI205:AO205)=0,"",AP205-LOOKUP(2,1/(AI205:AO205<>""),AI205:AO205))) | IF(OR(F205="",AQ205=""),"",IF(COUNT(AI205:AP205)=0,"",AQ205-LOOKUP(2,1/(AI205:AP205<>""),AI205:AP205))) | IF(OR(F205="",AR205=""),"",IF(COUNT(AI205:AQ205)=0,"",AR205-LOOKUP(2,1/(AI205:AQ205<>""),AI205:AQ205))) | IF(OR(F205="",AS205=""),"",IF(COUNT(AI205:AR205)=0,"",AS205-LOOKUP(2,1/(AI205:AR205<>""),AI205:AR205))) | IF(OR(F205="",AT205=""),"",IF(COUNT(AI205:AS205)=0,"",AT205-LOOKUP(2,1/(AI205:AS205<>""),AI205:AS205))) | IF(OR(F205="",AU205=""),"",IF(COUNT(AI205:AT205)=0,"",AU205-LOOKUP(2,1/(AI205:AT205<>""),AI205:AT205))) | IF(OR(F205="",AV205=""),"",IF(COUNT(AI205:AU205)=0,"",AV205-LOOKUP(2,1/(AI205:AU205<>""),AI205:AU205))) | IF(J205="","All_Provinces",IFERROR(VLOOKUP(J205,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K205="","All_Districts",IFERROR(VLOOKUP(K205,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F206="","",ROW()-3) | AF2-IS-41 | Package #41-AF2 IS: Rehabilitation of Madrasa irrigation schemes, located in Firozkoh district of Ghor province. | 1 of 1 | AF2-IS-N-029 | Mardras irrigation Schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Firozkoh | Oshtorkhan, Ahangaran and Madrasa | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 85000 | IF(AQ206="","",AQ206) | 2026-12-20 | 7.9 | 2027-08-17 | IF(W206<>"",W206,IF(OR(T206="",V206=""),"",EDATE(T206,V206))) |  |  | Under Design | Three months slack period Jan-Mar during winter Five months construction period required for three canals. To explore 2 lots for 2 contracts and simultaneous work | IF(F206="","",IF(COUNT(AI206:AV206)=0,IF(AA206="","Not started",AA206),SUBSTITUTE(LOOKUP(2,1/(AI206:AV206<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F206="",COUNT(AI206:AV206)=0),"",TODAY()-LOOKUP(2,1/(AI206:AV206<>""),AI206:AV206)) | IF(OR(F206="",COUNT(AI206:AV206)<2),"",LOOKUP(2,1/(AI206:AV206<>""),AI206:AV206)-MIN(AI206:AV206)) | IF(OR(AD206="",AC206="Not started",AC206=""),"",IFERROR(AD206-IF(VLOOKUP(AC206,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC206,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F206="","",IF(OR(AA206="Cancelled",AC206="Cancelled"),"Cancelled",IF(OR(AC206="Completed / Handover",Y206<>"",Z206>=100),"Completed — on track",IF(O206="Not awarded",IF(U206="",IF(X206="","No planned date",IF(TODAY()>X206,"Behind — past planned date",IF(X206-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U206,"Behind — award date passed",IF(U206-TODAY()<=30,"At risk — close to off track","On track"))),IF(X206="","No planned date",IF(AND(TODAY()>X206,OR(Z206="",Z206<100)),"Behind — past end date",IF(AND(T206<>"",X206<>"",Z206<>"",(Z206<100),((TODAY()-T206)/MAX(X206-T206,1)*100)-Z206>15),"Behind — progress lag",IF(AND(X206-TODAY()<=30,X206-TODAY()>=0,OR(Z206="",Z206<90)),"At risk — close to off track","On track")))))))) | IF(OR(F206="",AC206="Completed / Handover",AC206="Cancelled"),"",IF(O206="Not awarded",IF(U206<>"",U206-TODAY(),IF(X206="","",X206-TODAY())),IF(X206="","",X206-TODAY()))) | [14 empty] | IF(OR(F206="",AJ206=""),"",IF(COUNT(AI206:AI206)=0,"",AJ206-LOOKUP(2,1/(AI206:AI206<>""),AI206:AI206))) | IF(OR(F206="",AK206=""),"",IF(COUNT(AI206:AJ206)=0,"",AK206-LOOKUP(2,1/(AI206:AJ206<>""),AI206:AJ206))) | IF(OR(F206="",AL206=""),"",IF(COUNT(AI206:AK206)=0,"",AL206-LOOKUP(2,1/(AI206:AK206<>""),AI206:AK206))) | IF(OR(F206="",AM206=""),"",IF(COUNT(AI206:AL206)=0,"",AM206-LOOKUP(2,1/(AI206:AL206<>""),AI206:AL206))) | IF(OR(F206="",AN206=""),"",IF(COUNT(AI206:AM206)=0,"",AN206-LOOKUP(2,1/(AI206:AM206<>""),AI206:AM206))) | IF(OR(F206="",AO206=""),"",IF(COUNT(AI206:AN206)=0,"",AO206-LOOKUP(2,1/(AI206:AN206<>""),AI206:AN206))) | IF(OR(F206="",AP206=""),"",IF(COUNT(AI206:AO206)=0,"",AP206-LOOKUP(2,1/(AI206:AO206<>""),AI206:AO206))) | IF(OR(F206="",AQ206=""),"",IF(COUNT(AI206:AP206)=0,"",AQ206-LOOKUP(2,1/(AI206:AP206<>""),AI206:AP206))) | IF(OR(F206="",AR206=""),"",IF(COUNT(AI206:AQ206)=0,"",AR206-LOOKUP(2,1/(AI206:AQ206<>""),AI206:AQ206))) | IF(OR(F206="",AS206=""),"",IF(COUNT(AI206:AR206)=0,"",AS206-LOOKUP(2,1/(AI206:AR206<>""),AI206:AR206))) | IF(OR(F206="",AT206=""),"",IF(COUNT(AI206:AS206)=0,"",AT206-LOOKUP(2,1/(AI206:AS206<>""),AI206:AS206))) | IF(OR(F206="",AU206=""),"",IF(COUNT(AI206:AT206)=0,"",AU206-LOOKUP(2,1/(AI206:AT206<>""),AI206:AT206))) | IF(OR(F206="",AV206=""),"",IF(COUNT(AI206:AU206)=0,"",AV206-LOOKUP(2,1/(AI206:AU206<>""),AI206:AU206))) | IF(J206="","All_Provinces",IFERROR(VLOOKUP(J206,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K206="","All_Districts",IFERROR(VLOOKUP(K206,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F207="","",ROW()-3) | AF2-IS-42 | Package #42-AF2 IS: Rehabilitation of Zard Nai Charsapan Cluster Canal irrigation schemes, located in Sharrisatan district of Daykundi province. | 1 of 1 | AF2-IS-N-030 | Zard Nai Charsapan Cluster Canal irrigation schemes | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Shahristan | Zardnai Payeen, Zardnai Bala, | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 257667 | IF(AQ207="","",AQ207) | 2026-12-15 | 10.2 | 2027-10-21 | IF(W207<>"",W207,IF(OR(T207="",V207=""),"",EDATE(T207,V207))) |  |  | Under LTO Review | 2.5 months slack period Mid Jan-Mar during winter. Eight months construction period required for the cluster canals in two districts. Explore possibility of 2 lots for PR and contract award | IF(F207="","",IF(COUNT(AI207:AV207)=0,IF(AA207="","Not started",AA207),SUBSTITUTE(LOOKUP(2,1/(AI207:AV207<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F207="",COUNT(AI207:AV207)=0),"",TODAY()-LOOKUP(2,1/(AI207:AV207<>""),AI207:AV207)) | IF(OR(F207="",COUNT(AI207:AV207)<2),"",LOOKUP(2,1/(AI207:AV207<>""),AI207:AV207)-MIN(AI207:AV207)) | IF(OR(AD207="",AC207="Not started",AC207=""),"",IFERROR(AD207-IF(VLOOKUP(AC207,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC207,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F207="","",IF(OR(AA207="Cancelled",AC207="Cancelled"),"Cancelled",IF(OR(AC207="Completed / Handover",Y207<>"",Z207>=100),"Completed — on track",IF(O207="Not awarded",IF(U207="",IF(X207="","No planned date",IF(TODAY()>X207,"Behind — past planned date",IF(X207-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U207,"Behind — award date passed",IF(U207-TODAY()<=30,"At risk — close to off track","On track"))),IF(X207="","No planned date",IF(AND(TODAY()>X207,OR(Z207="",Z207<100)),"Behind — past end date",IF(AND(T207<>"",X207<>"",Z207<>"",(Z207<100),((TODAY()-T207)/MAX(X207-T207,1)*100)-Z207>15),"Behind — progress lag",IF(AND(X207-TODAY()<=30,X207-TODAY()>=0,OR(Z207="",Z207<90)),"At risk — close to off track","On track")))))))) | IF(OR(F207="",AC207="Completed / Handover",AC207="Cancelled"),"",IF(O207="Not awarded",IF(U207<>"",U207-TODAY(),IF(X207="","",X207-TODAY())),IF(X207="","",X207-TODAY()))) | [14 empty] | IF(OR(F207="",AJ207=""),"",IF(COUNT(AI207:AI207)=0,"",AJ207-LOOKUP(2,1/(AI207:AI207<>""),AI207:AI207))) | IF(OR(F207="",AK207=""),"",IF(COUNT(AI207:AJ207)=0,"",AK207-LOOKUP(2,1/(AI207:AJ207<>""),AI207:AJ207))) | IF(OR(F207="",AL207=""),"",IF(COUNT(AI207:AK207)=0,"",AL207-LOOKUP(2,1/(AI207:AK207<>""),AI207:AK207))) | IF(OR(F207="",AM207=""),"",IF(COUNT(AI207:AL207)=0,"",AM207-LOOKUP(2,1/(AI207:AL207<>""),AI207:AL207))) | IF(OR(F207="",AN207=""),"",IF(COUNT(AI207:AM207)=0,"",AN207-LOOKUP(2,1/(AI207:AM207<>""),AI207:AM207))) | IF(OR(F207="",AO207=""),"",IF(COUNT(AI207:AN207)=0,"",AO207-LOOKUP(2,1/(AI207:AN207<>""),AI207:AN207))) | IF(OR(F207="",AP207=""),"",IF(COUNT(AI207:AO207)=0,"",AP207-LOOKUP(2,1/(AI207:AO207<>""),AI207:AO207))) | IF(OR(F207="",AQ207=""),"",IF(COUNT(AI207:AP207)=0,"",AQ207-LOOKUP(2,1/(AI207:AP207<>""),AI207:AP207))) | IF(OR(F207="",AR207=""),"",IF(COUNT(AI207:AQ207)=0,"",AR207-LOOKUP(2,1/(AI207:AQ207<>""),AI207:AQ207))) | IF(OR(F207="",AS207=""),"",IF(COUNT(AI207:AR207)=0,"",AS207-LOOKUP(2,1/(AI207:AR207<>""),AI207:AR207))) | IF(OR(F207="",AT207=""),"",IF(COUNT(AI207:AS207)=0,"",AT207-LOOKUP(2,1/(AI207:AS207<>""),AI207:AS207))) | IF(OR(F207="",AU207=""),"",IF(COUNT(AI207:AT207)=0,"",AU207-LOOKUP(2,1/(AI207:AT207<>""),AI207:AT207))) | IF(OR(F207="",AV207=""),"",IF(COUNT(AI207:AU207)=0,"",AV207-LOOKUP(2,1/(AI207:AU207<>""),AI207:AU207))) | IF(J207="","All_Provinces",IFERROR(VLOOKUP(J207,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K207="","All_Districts",IFERROR(VLOOKUP(K207,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F208="","",ROW()-3) | AF2-IS-43 | Package #43-AF2 IS: Rehabilitation of Sar Nary canal irrigation scheme, located in Arghandab districts of Zabul province. | 1 of 1 | AF2-IS-N-031 | Sar Nary Canals Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Zabul | Arghandab | - | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 160000 | IF(AQ208="","",AQ208) | 2026-12-20 | 8.9 | 2027-09-16 | IF(W208<>"",W208,IF(OR(T208="",V208=""),"",EDATE(T208,V208))) |  |  | Under Design | Three months slack period Jan-Mar during winter. Six months construction period required for two canals in two districts. Explore splitting into two lots and if one lot ready then raise PR. | IF(F208="","",IF(COUNT(AI208:AV208)=0,IF(AA208="","Not started",AA208),SUBSTITUTE(LOOKUP(2,1/(AI208:AV208<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F208="",COUNT(AI208:AV208)=0),"",TODAY()-LOOKUP(2,1/(AI208:AV208<>""),AI208:AV208)) | IF(OR(F208="",COUNT(AI208:AV208)<2),"",LOOKUP(2,1/(AI208:AV208<>""),AI208:AV208)-MIN(AI208:AV208)) | IF(OR(AD208="",AC208="Not started",AC208=""),"",IFERROR(AD208-IF(VLOOKUP(AC208,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC208,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F208="","",IF(OR(AA208="Cancelled",AC208="Cancelled"),"Cancelled",IF(OR(AC208="Completed / Handover",Y208<>"",Z208>=100),"Completed — on track",IF(O208="Not awarded",IF(U208="",IF(X208="","No planned date",IF(TODAY()>X208,"Behind — past planned date",IF(X208-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U208,"Behind — award date passed",IF(U208-TODAY()<=30,"At risk — close to off track","On track"))),IF(X208="","No planned date",IF(AND(TODAY()>X208,OR(Z208="",Z208<100)),"Behind — past end date",IF(AND(T208<>"",X208<>"",Z208<>"",(Z208<100),((TODAY()-T208)/MAX(X208-T208,1)*100)-Z208>15),"Behind — progress lag",IF(AND(X208-TODAY()<=30,X208-TODAY()>=0,OR(Z208="",Z208<90)),"At risk — close to off track","On track")))))))) | IF(OR(F208="",AC208="Completed / Handover",AC208="Cancelled"),"",IF(O208="Not awarded",IF(U208<>"",U208-TODAY(),IF(X208="","",X208-TODAY())),IF(X208="","",X208-TODAY()))) | [14 empty] | IF(OR(F208="",AJ208=""),"",IF(COUNT(AI208:AI208)=0,"",AJ208-LOOKUP(2,1/(AI208:AI208<>""),AI208:AI208))) | IF(OR(F208="",AK208=""),"",IF(COUNT(AI208:AJ208)=0,"",AK208-LOOKUP(2,1/(AI208:AJ208<>""),AI208:AJ208))) | IF(OR(F208="",AL208=""),"",IF(COUNT(AI208:AK208)=0,"",AL208-LOOKUP(2,1/(AI208:AK208<>""),AI208:AK208))) | IF(OR(F208="",AM208=""),"",IF(COUNT(AI208:AL208)=0,"",AM208-LOOKUP(2,1/(AI208:AL208<>""),AI208:AL208))) | IF(OR(F208="",AN208=""),"",IF(COUNT(AI208:AM208)=0,"",AN208-LOOKUP(2,1/(AI208:AM208<>""),AI208:AM208))) | IF(OR(F208="",AO208=""),"",IF(COUNT(AI208:AN208)=0,"",AO208-LOOKUP(2,1/(AI208:AN208<>""),AI208:AN208))) | IF(OR(F208="",AP208=""),"",IF(COUNT(AI208:AO208)=0,"",AP208-LOOKUP(2,1/(AI208:AO208<>""),AI208:AO208))) | IF(OR(F208="",AQ208=""),"",IF(COUNT(AI208:AP208)=0,"",AQ208-LOOKUP(2,1/(AI208:AP208<>""),AI208:AP208))) | IF(OR(F208="",AR208=""),"",IF(COUNT(AI208:AQ208)=0,"",AR208-LOOKUP(2,1/(AI208:AQ208<>""),AI208:AQ208))) | IF(OR(F208="",AS208=""),"",IF(COUNT(AI208:AR208)=0,"",AS208-LOOKUP(2,1/(AI208:AR208<>""),AI208:AR208))) | IF(OR(F208="",AT208=""),"",IF(COUNT(AI208:AS208)=0,"",AT208-LOOKUP(2,1/(AI208:AS208<>""),AI208:AS208))) | IF(OR(F208="",AU208=""),"",IF(COUNT(AI208:AT208)=0,"",AU208-LOOKUP(2,1/(AI208:AT208<>""),AI208:AT208))) | IF(OR(F208="",AV208=""),"",IF(COUNT(AI208:AU208)=0,"",AV208-LOOKUP(2,1/(AI208:AU208<>""),AI208:AU208))) | IF(J208="","All_Provinces",IFERROR(VLOOKUP(J208,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K208="","All_Districts",IFERROR(VLOOKUP(K208,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F209="","",ROW()-3) | AF2-IS-44 | Package #44-AF2 IS: Rehabilitation of Boghoz Qum canal irrigation schemes, located in Chahar Dara district of Kunduz province. | 1 of 1 | AF2-IS-N-032 | Boghoz Qum Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Kunduz | Chahar Dara | Boghoz Qum | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 200000 | IF(AQ209="","",AQ209) | 2026-11-25 | 9.9 | 2027-09-21 | IF(W209<>"",W209,IF(OR(T209="",V209=""),"",EDATE(T209,V209))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals. Split into 2 lots and make 2 PRs | IF(F209="","",IF(COUNT(AI209:AV209)=0,IF(AA209="","Not started",AA209),SUBSTITUTE(LOOKUP(2,1/(AI209:AV209<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F209="",COUNT(AI209:AV209)=0),"",TODAY()-LOOKUP(2,1/(AI209:AV209<>""),AI209:AV209)) | IF(OR(F209="",COUNT(AI209:AV209)<2),"",LOOKUP(2,1/(AI209:AV209<>""),AI209:AV209)-MIN(AI209:AV209)) | IF(OR(AD209="",AC209="Not started",AC209=""),"",IFERROR(AD209-IF(VLOOKUP(AC209,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC209,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F209="","",IF(OR(AA209="Cancelled",AC209="Cancelled"),"Cancelled",IF(OR(AC209="Completed / Handover",Y209<>"",Z209>=100),"Completed — on track",IF(O209="Not awarded",IF(U209="",IF(X209="","No planned date",IF(TODAY()>X209,"Behind — past planned date",IF(X209-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U209,"Behind — award date passed",IF(U209-TODAY()<=30,"At risk — close to off track","On track"))),IF(X209="","No planned date",IF(AND(TODAY()>X209,OR(Z209="",Z209<100)),"Behind — past end date",IF(AND(T209<>"",X209<>"",Z209<>"",(Z209<100),((TODAY()-T209)/MAX(X209-T209,1)*100)-Z209>15),"Behind — progress lag",IF(AND(X209-TODAY()<=30,X209-TODAY()>=0,OR(Z209="",Z209<90)),"At risk — close to off track","On track")))))))) | IF(OR(F209="",AC209="Completed / Handover",AC209="Cancelled"),"",IF(O209="Not awarded",IF(U209<>"",U209-TODAY(),IF(X209="","",X209-TODAY())),IF(X209="","",X209-TODAY()))) | [14 empty] | IF(OR(F209="",AJ209=""),"",IF(COUNT(AI209:AI209)=0,"",AJ209-LOOKUP(2,1/(AI209:AI209<>""),AI209:AI209))) | IF(OR(F209="",AK209=""),"",IF(COUNT(AI209:AJ209)=0,"",AK209-LOOKUP(2,1/(AI209:AJ209<>""),AI209:AJ209))) | IF(OR(F209="",AL209=""),"",IF(COUNT(AI209:AK209)=0,"",AL209-LOOKUP(2,1/(AI209:AK209<>""),AI209:AK209))) | IF(OR(F209="",AM209=""),"",IF(COUNT(AI209:AL209)=0,"",AM209-LOOKUP(2,1/(AI209:AL209<>""),AI209:AL209))) | IF(OR(F209="",AN209=""),"",IF(COUNT(AI209:AM209)=0,"",AN209-LOOKUP(2,1/(AI209:AM209<>""),AI209:AM209))) | IF(OR(F209="",AO209=""),"",IF(COUNT(AI209:AN209)=0,"",AO209-LOOKUP(2,1/(AI209:AN209<>""),AI209:AN209))) | IF(OR(F209="",AP209=""),"",IF(COUNT(AI209:AO209)=0,"",AP209-LOOKUP(2,1/(AI209:AO209<>""),AI209:AO209))) | IF(OR(F209="",AQ209=""),"",IF(COUNT(AI209:AP209)=0,"",AQ209-LOOKUP(2,1/(AI209:AP209<>""),AI209:AP209))) | IF(OR(F209="",AR209=""),"",IF(COUNT(AI209:AQ209)=0,"",AR209-LOOKUP(2,1/(AI209:AQ209<>""),AI209:AQ209))) | IF(OR(F209="",AS209=""),"",IF(COUNT(AI209:AR209)=0,"",AS209-LOOKUP(2,1/(AI209:AR209<>""),AI209:AR209))) | IF(OR(F209="",AT209=""),"",IF(COUNT(AI209:AS209)=0,"",AT209-LOOKUP(2,1/(AI209:AS209<>""),AI209:AS209))) | IF(OR(F209="",AU209=""),"",IF(COUNT(AI209:AT209)=0,"",AU209-LOOKUP(2,1/(AI209:AT209<>""),AI209:AT209))) | IF(OR(F209="",AV209=""),"",IF(COUNT(AI209:AU209)=0,"",AV209-LOOKUP(2,1/(AI209:AU209<>""),AI209:AU209))) | IF(J209="","All_Provinces",IFERROR(VLOOKUP(J209,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K209="","All_Districts",IFERROR(VLOOKUP(K209,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F210="","",ROW()-3) | AF2-IS-45 | Package # 45-AF2 IS: Rehabilitation of Khushpak Markazi canals irrigation scheme, located in Ishkashim districts of Badakhshan province. | 1 of 1 | AF2-IS-N-033 | Khushpak Markazi Canal Irrigation Scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Badakhshan | Ishkashim | Osas | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 85774.97 | IF(AQ210="","",AQ210) | 2027-01-13 | 6.9 | 2027-08-11 | IF(W210<>"",W210,IF(OR(T210="",V210=""),"",EDATE(T210,V210))) |  |  | PR to be Raised | Three months slack period Jan-Mar during winter. Six months construction period required for two canals | IF(F210="","",IF(COUNT(AI210:AV210)=0,IF(AA210="","Not started",AA210),SUBSTITUTE(LOOKUP(2,1/(AI210:AV210<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F210="",COUNT(AI210:AV210)=0),"",TODAY()-LOOKUP(2,1/(AI210:AV210<>""),AI210:AV210)) | IF(OR(F210="",COUNT(AI210:AV210)<2),"",LOOKUP(2,1/(AI210:AV210<>""),AI210:AV210)-MIN(AI210:AV210)) | IF(OR(AD210="",AC210="Not started",AC210=""),"",IFERROR(AD210-IF(VLOOKUP(AC210,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC210,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F210="","",IF(OR(AA210="Cancelled",AC210="Cancelled"),"Cancelled",IF(OR(AC210="Completed / Handover",Y210<>"",Z210>=100),"Completed — on track",IF(O210="Not awarded",IF(U210="",IF(X210="","No planned date",IF(TODAY()>X210,"Behind — past planned date",IF(X210-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U210,"Behind — award date passed",IF(U210-TODAY()<=30,"At risk — close to off track","On track"))),IF(X210="","No planned date",IF(AND(TODAY()>X210,OR(Z210="",Z210<100)),"Behind — past end date",IF(AND(T210<>"",X210<>"",Z210<>"",(Z210<100),((TODAY()-T210)/MAX(X210-T210,1)*100)-Z210>15),"Behind — progress lag",IF(AND(X210-TODAY()<=30,X210-TODAY()>=0,OR(Z210="",Z210<90)),"At risk — close to off track","On track")))))))) | IF(OR(F210="",AC210="Completed / Handover",AC210="Cancelled"),"",IF(O210="Not awarded",IF(U210<>"",U210-TODAY(),IF(X210="","",X210-TODAY())),IF(X210="","",X210-TODAY()))) | [14 empty] | IF(OR(F210="",AJ210=""),"",IF(COUNT(AI210:AI210)=0,"",AJ210-LOOKUP(2,1/(AI210:AI210<>""),AI210:AI210))) | IF(OR(F210="",AK210=""),"",IF(COUNT(AI210:AJ210)=0,"",AK210-LOOKUP(2,1/(AI210:AJ210<>""),AI210:AJ210))) | IF(OR(F210="",AL210=""),"",IF(COUNT(AI210:AK210)=0,"",AL210-LOOKUP(2,1/(AI210:AK210<>""),AI210:AK210))) | IF(OR(F210="",AM210=""),"",IF(COUNT(AI210:AL210)=0,"",AM210-LOOKUP(2,1/(AI210:AL210<>""),AI210:AL210))) | IF(OR(F210="",AN210=""),"",IF(COUNT(AI210:AM210)=0,"",AN210-LOOKUP(2,1/(AI210:AM210<>""),AI210:AM210))) | IF(OR(F210="",AO210=""),"",IF(COUNT(AI210:AN210)=0,"",AO210-LOOKUP(2,1/(AI210:AN210<>""),AI210:AN210))) | IF(OR(F210="",AP210=""),"",IF(COUNT(AI210:AO210)=0,"",AP210-LOOKUP(2,1/(AI210:AO210<>""),AI210:AO210))) | IF(OR(F210="",AQ210=""),"",IF(COUNT(AI210:AP210)=0,"",AQ210-LOOKUP(2,1/(AI210:AP210<>""),AI210:AP210))) | IF(OR(F210="",AR210=""),"",IF(COUNT(AI210:AQ210)=0,"",AR210-LOOKUP(2,1/(AI210:AQ210<>""),AI210:AQ210))) | IF(OR(F210="",AS210=""),"",IF(COUNT(AI210:AR210)=0,"",AS210-LOOKUP(2,1/(AI210:AR210<>""),AI210:AR210))) | IF(OR(F210="",AT210=""),"",IF(COUNT(AI210:AS210)=0,"",AT210-LOOKUP(2,1/(AI210:AS210<>""),AI210:AS210))) | IF(OR(F210="",AU210=""),"",IF(COUNT(AI210:AT210)=0,"",AU210-LOOKUP(2,1/(AI210:AT210<>""),AI210:AT210))) | IF(OR(F210="",AV210=""),"",IF(COUNT(AI210:AU210)=0,"",AV210-LOOKUP(2,1/(AI210:AU210<>""),AI210:AU210))) | IF(J210="","All_Provinces",IFERROR(VLOOKUP(J210,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K210="","All_Districts",IFERROR(VLOOKUP(K210,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F211="","",ROW()-3) | AF2-IS-46 | Package # 46-AF2 IS: Rehabilitation of Joy Shahr canal and Khanum Arabia canal irrigation schemes, located in Aqcha and Faizabad districts of Jawzjan province. | 1 of 1 | AF2-IS-N-034 | Hidar Abad Canal Irrigation scheme | Irrigation Scheme | Irrigation Canal | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Jawzjan | Faizabad | Haidar Abad and Naw Abad | World Bank (WBK/AF-2) | Not awarded | 2.Remain contracts_On&off-farm |  |  | 276650 | IF(AQ211="","",AQ211) | 2026-12-18 | 9.9 | 2027-10-14 | IF(W211<>"",W211,IF(OR(T211="",V211=""),"",EDATE(T211,V211))) |  |  | Under LTO Review | Three months slack period Jan-Mar during winter. Seven months construction period required for two canals. Explore split into 2 lots | IF(F211="","",IF(COUNT(AI211:AV211)=0,IF(AA211="","Not started",AA211),SUBSTITUTE(LOOKUP(2,1/(AI211:AV211<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F211="",COUNT(AI211:AV211)=0),"",TODAY()-LOOKUP(2,1/(AI211:AV211<>""),AI211:AV211)) | IF(OR(F211="",COUNT(AI211:AV211)<2),"",LOOKUP(2,1/(AI211:AV211<>""),AI211:AV211)-MIN(AI211:AV211)) | IF(OR(AD211="",AC211="Not started",AC211=""),"",IFERROR(AD211-IF(VLOOKUP(AC211,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC211,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F211="","",IF(OR(AA211="Cancelled",AC211="Cancelled"),"Cancelled",IF(OR(AC211="Completed / Handover",Y211<>"",Z211>=100),"Completed — on track",IF(O211="Not awarded",IF(U211="",IF(X211="","No planned date",IF(TODAY()>X211,"Behind — past planned date",IF(X211-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U211,"Behind — award date passed",IF(U211-TODAY()<=30,"At risk — close to off track","On track"))),IF(X211="","No planned date",IF(AND(TODAY()>X211,OR(Z211="",Z211<100)),"Behind — past end date",IF(AND(T211<>"",X211<>"",Z211<>"",(Z211<100),((TODAY()-T211)/MAX(X211-T211,1)*100)-Z211>15),"Behind — progress lag",IF(AND(X211-TODAY()<=30,X211-TODAY()>=0,OR(Z211="",Z211<90)),"At risk — close to off track","On track")))))))) | IF(OR(F211="",AC211="Completed / Handover",AC211="Cancelled"),"",IF(O211="Not awarded",IF(U211<>"",U211-TODAY(),IF(X211="","",X211-TODAY())),IF(X211="","",X211-TODAY()))) | [14 empty] | IF(OR(F211="",AJ211=""),"",IF(COUNT(AI211:AI211)=0,"",AJ211-LOOKUP(2,1/(AI211:AI211<>""),AI211:AI211))) | IF(OR(F211="",AK211=""),"",IF(COUNT(AI211:AJ211)=0,"",AK211-LOOKUP(2,1/(AI211:AJ211<>""),AI211:AJ211))) | IF(OR(F211="",AL211=""),"",IF(COUNT(AI211:AK211)=0,"",AL211-LOOKUP(2,1/(AI211:AK211<>""),AI211:AK211))) | IF(OR(F211="",AM211=""),"",IF(COUNT(AI211:AL211)=0,"",AM211-LOOKUP(2,1/(AI211:AL211<>""),AI211:AL211))) | IF(OR(F211="",AN211=""),"",IF(COUNT(AI211:AM211)=0,"",AN211-LOOKUP(2,1/(AI211:AM211<>""),AI211:AM211))) | IF(OR(F211="",AO211=""),"",IF(COUNT(AI211:AN211)=0,"",AO211-LOOKUP(2,1/(AI211:AN211<>""),AI211:AN211))) | IF(OR(F211="",AP211=""),"",IF(COUNT(AI211:AO211)=0,"",AP211-LOOKUP(2,1/(AI211:AO211<>""),AI211:AO211))) | IF(OR(F211="",AQ211=""),"",IF(COUNT(AI211:AP211)=0,"",AQ211-LOOKUP(2,1/(AI211:AP211<>""),AI211:AP211))) | IF(OR(F211="",AR211=""),"",IF(COUNT(AI211:AQ211)=0,"",AR211-LOOKUP(2,1/(AI211:AQ211<>""),AI211:AQ211))) | IF(OR(F211="",AS211=""),"",IF(COUNT(AI211:AR211)=0,"",AS211-LOOKUP(2,1/(AI211:AR211<>""),AI211:AR211))) | IF(OR(F211="",AT211=""),"",IF(COUNT(AI211:AS211)=0,"",AT211-LOOKUP(2,1/(AI211:AS211<>""),AI211:AS211))) | IF(OR(F211="",AU211=""),"",IF(COUNT(AI211:AT211)=0,"",AU211-LOOKUP(2,1/(AI211:AT211<>""),AI211:AT211))) | IF(OR(F211="",AV211=""),"",IF(COUNT(AI211:AU211)=0,"",AV211-LOOKUP(2,1/(AI211:AU211<>""),AI211:AU211))) | IF(J211="","All_Provinces",IFERROR(VLOOKUP(J211,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K211="","All_Districts",IFERROR(VLOOKUP(K211,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F212="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 1 of 50 | AF2-LLL-N-001 | Abdul Baqi irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balklh | Chimtal | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ212="","",AQ212) | 2026-10-30 |  | 2027-01-31 | IF(W212<>"",W212,IF(OR(T212="",V212=""),"",EDATE(T212,V212))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F212="","",IF(COUNT(AI212:AV212)=0,IF(AA212="","Not started",AA212),SUBSTITUTE(LOOKUP(2,1/(AI212:AV212<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F212="",COUNT(AI212:AV212)=0),"",TODAY()-LOOKUP(2,1/(AI212:AV212<>""),AI212:AV212)) | IF(OR(F212="",COUNT(AI212:AV212)<2),"",LOOKUP(2,1/(AI212:AV212<>""),AI212:AV212)-MIN(AI212:AV212)) | IF(OR(AD212="",AC212="Not started",AC212=""),"",IFERROR(AD212-IF(VLOOKUP(AC212,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC212,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F212="","",IF(OR(AA212="Cancelled",AC212="Cancelled"),"Cancelled",IF(OR(AC212="Completed / Handover",Y212<>"",Z212>=100),"Completed — on track",IF(O212="Not awarded",IF(U212="",IF(X212="","No planned date",IF(TODAY()>X212,"Behind — past planned date",IF(X212-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U212,"Behind — award date passed",IF(U212-TODAY()<=30,"At risk — close to off track","On track"))),IF(X212="","No planned date",IF(AND(TODAY()>X212,OR(Z212="",Z212<100)),"Behind — past end date",IF(AND(T212<>"",X212<>"",Z212<>"",(Z212<100),((TODAY()-T212)/MAX(X212-T212,1)*100)-Z212>15),"Behind — progress lag",IF(AND(X212-TODAY()<=30,X212-TODAY()>=0,OR(Z212="",Z212<90)),"At risk — close to off track","On track")))))))) | IF(OR(F212="",AC212="Completed / Handover",AC212="Cancelled"),"",IF(O212="Not awarded",IF(U212<>"",U212-TODAY(),IF(X212="","",X212-TODAY())),IF(X212="","",X212-TODAY()))) | [14 empty] | IF(OR(F212="",AJ212=""),"",IF(COUNT(AI212:AI212)=0,"",AJ212-LOOKUP(2,1/(AI212:AI212<>""),AI212:AI212))) | IF(OR(F212="",AK212=""),"",IF(COUNT(AI212:AJ212)=0,"",AK212-LOOKUP(2,1/(AI212:AJ212<>""),AI212:AJ212))) | IF(OR(F212="",AL212=""),"",IF(COUNT(AI212:AK212)=0,"",AL212-LOOKUP(2,1/(AI212:AK212<>""),AI212:AK212))) | IF(OR(F212="",AM212=""),"",IF(COUNT(AI212:AL212)=0,"",AM212-LOOKUP(2,1/(AI212:AL212<>""),AI212:AL212))) | IF(OR(F212="",AN212=""),"",IF(COUNT(AI212:AM212)=0,"",AN212-LOOKUP(2,1/(AI212:AM212<>""),AI212:AM212))) | IF(OR(F212="",AO212=""),"",IF(COUNT(AI212:AN212)=0,"",AO212-LOOKUP(2,1/(AI212:AN212<>""),AI212:AN212))) | IF(OR(F212="",AP212=""),"",IF(COUNT(AI212:AO212)=0,"",AP212-LOOKUP(2,1/(AI212:AO212<>""),AI212:AO212))) | IF(OR(F212="",AQ212=""),"",IF(COUNT(AI212:AP212)=0,"",AQ212-LOOKUP(2,1/(AI212:AP212<>""),AI212:AP212))) | IF(OR(F212="",AR212=""),"",IF(COUNT(AI212:AQ212)=0,"",AR212-LOOKUP(2,1/(AI212:AQ212<>""),AI212:AQ212))) | IF(OR(F212="",AS212=""),"",IF(COUNT(AI212:AR212)=0,"",AS212-LOOKUP(2,1/(AI212:AR212<>""),AI212:AR212))) | IF(OR(F212="",AT212=""),"",IF(COUNT(AI212:AS212)=0,"",AT212-LOOKUP(2,1/(AI212:AS212<>""),AI212:AS212))) | IF(OR(F212="",AU212=""),"",IF(COUNT(AI212:AT212)=0,"",AU212-LOOKUP(2,1/(AI212:AT212<>""),AI212:AT212))) | IF(OR(F212="",AV212=""),"",IF(COUNT(AI212:AU212)=0,"",AV212-LOOKUP(2,1/(AI212:AU212<>""),AI212:AU212))) | IF(J212="","All_Provinces",IFERROR(VLOOKUP(J212,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K212="","All_Districts",IFERROR(VLOOKUP(K212,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F213="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 2 of 50 | AF2-LLL-N-002 | Abi Aruq and Shaitan Aruq Irrigation Schemes | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Khwaja Ghar | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ213="","",AQ213) | 2026-10-30 |  | 2027-01-31 | IF(W213<>"",W213,IF(OR(T213="",V213=""),"",EDATE(T213,V213))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F213="","",IF(COUNT(AI213:AV213)=0,IF(AA213="","Not started",AA213),SUBSTITUTE(LOOKUP(2,1/(AI213:AV213<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F213="",COUNT(AI213:AV213)=0),"",TODAY()-LOOKUP(2,1/(AI213:AV213<>""),AI213:AV213)) | IF(OR(F213="",COUNT(AI213:AV213)<2),"",LOOKUP(2,1/(AI213:AV213<>""),AI213:AV213)-MIN(AI213:AV213)) | IF(OR(AD213="",AC213="Not started",AC213=""),"",IFERROR(AD213-IF(VLOOKUP(AC213,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC213,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F213="","",IF(OR(AA213="Cancelled",AC213="Cancelled"),"Cancelled",IF(OR(AC213="Completed / Handover",Y213<>"",Z213>=100),"Completed — on track",IF(O213="Not awarded",IF(U213="",IF(X213="","No planned date",IF(TODAY()>X213,"Behind — past planned date",IF(X213-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U213,"Behind — award date passed",IF(U213-TODAY()<=30,"At risk — close to off track","On track"))),IF(X213="","No planned date",IF(AND(TODAY()>X213,OR(Z213="",Z213<100)),"Behind — past end date",IF(AND(T213<>"",X213<>"",Z213<>"",(Z213<100),((TODAY()-T213)/MAX(X213-T213,1)*100)-Z213>15),"Behind — progress lag",IF(AND(X213-TODAY()<=30,X213-TODAY()>=0,OR(Z213="",Z213<90)),"At risk — close to off track","On track")))))))) | IF(OR(F213="",AC213="Completed / Handover",AC213="Cancelled"),"",IF(O213="Not awarded",IF(U213<>"",U213-TODAY(),IF(X213="","",X213-TODAY())),IF(X213="","",X213-TODAY()))) | [14 empty] | IF(OR(F213="",AJ213=""),"",IF(COUNT(AI213:AI213)=0,"",AJ213-LOOKUP(2,1/(AI213:AI213<>""),AI213:AI213))) | IF(OR(F213="",AK213=""),"",IF(COUNT(AI213:AJ213)=0,"",AK213-LOOKUP(2,1/(AI213:AJ213<>""),AI213:AJ213))) | IF(OR(F213="",AL213=""),"",IF(COUNT(AI213:AK213)=0,"",AL213-LOOKUP(2,1/(AI213:AK213<>""),AI213:AK213))) | IF(OR(F213="",AM213=""),"",IF(COUNT(AI213:AL213)=0,"",AM213-LOOKUP(2,1/(AI213:AL213<>""),AI213:AL213))) | IF(OR(F213="",AN213=""),"",IF(COUNT(AI213:AM213)=0,"",AN213-LOOKUP(2,1/(AI213:AM213<>""),AI213:AM213))) | IF(OR(F213="",AO213=""),"",IF(COUNT(AI213:AN213)=0,"",AO213-LOOKUP(2,1/(AI213:AN213<>""),AI213:AN213))) | IF(OR(F213="",AP213=""),"",IF(COUNT(AI213:AO213)=0,"",AP213-LOOKUP(2,1/(AI213:AO213<>""),AI213:AO213))) | IF(OR(F213="",AQ213=""),"",IF(COUNT(AI213:AP213)=0,"",AQ213-LOOKUP(2,1/(AI213:AP213<>""),AI213:AP213))) | IF(OR(F213="",AR213=""),"",IF(COUNT(AI213:AQ213)=0,"",AR213-LOOKUP(2,1/(AI213:AQ213<>""),AI213:AQ213))) | IF(OR(F213="",AS213=""),"",IF(COUNT(AI213:AR213)=0,"",AS213-LOOKUP(2,1/(AI213:AR213<>""),AI213:AR213))) | IF(OR(F213="",AT213=""),"",IF(COUNT(AI213:AS213)=0,"",AT213-LOOKUP(2,1/(AI213:AS213<>""),AI213:AS213))) | IF(OR(F213="",AU213=""),"",IF(COUNT(AI213:AT213)=0,"",AU213-LOOKUP(2,1/(AI213:AT213<>""),AI213:AT213))) | IF(OR(F213="",AV213=""),"",IF(COUNT(AI213:AU213)=0,"",AV213-LOOKUP(2,1/(AI213:AU213<>""),AI213:AU213))) | IF(J213="","All_Provinces",IFERROR(VLOOKUP(J213,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K213="","All_Districts",IFERROR(VLOOKUP(K213,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F214="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 3 of 50 | AF2-LLL-N-003 | Ali Mansoor Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Karukh | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ214="","",AQ214) | 2026-10-30 |  | 2027-01-31 | IF(W214<>"",W214,IF(OR(T214="",V214=""),"",EDATE(T214,V214))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F214="","",IF(COUNT(AI214:AV214)=0,IF(AA214="","Not started",AA214),SUBSTITUTE(LOOKUP(2,1/(AI214:AV214<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F214="",COUNT(AI214:AV214)=0),"",TODAY()-LOOKUP(2,1/(AI214:AV214<>""),AI214:AV214)) | IF(OR(F214="",COUNT(AI214:AV214)<2),"",LOOKUP(2,1/(AI214:AV214<>""),AI214:AV214)-MIN(AI214:AV214)) | IF(OR(AD214="",AC214="Not started",AC214=""),"",IFERROR(AD214-IF(VLOOKUP(AC214,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC214,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F214="","",IF(OR(AA214="Cancelled",AC214="Cancelled"),"Cancelled",IF(OR(AC214="Completed / Handover",Y214<>"",Z214>=100),"Completed — on track",IF(O214="Not awarded",IF(U214="",IF(X214="","No planned date",IF(TODAY()>X214,"Behind — past planned date",IF(X214-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U214,"Behind — award date passed",IF(U214-TODAY()<=30,"At risk — close to off track","On track"))),IF(X214="","No planned date",IF(AND(TODAY()>X214,OR(Z214="",Z214<100)),"Behind — past end date",IF(AND(T214<>"",X214<>"",Z214<>"",(Z214<100),((TODAY()-T214)/MAX(X214-T214,1)*100)-Z214>15),"Behind — progress lag",IF(AND(X214-TODAY()<=30,X214-TODAY()>=0,OR(Z214="",Z214<90)),"At risk — close to off track","On track")))))))) | IF(OR(F214="",AC214="Completed / Handover",AC214="Cancelled"),"",IF(O214="Not awarded",IF(U214<>"",U214-TODAY(),IF(X214="","",X214-TODAY())),IF(X214="","",X214-TODAY()))) | [14 empty] | IF(OR(F214="",AJ214=""),"",IF(COUNT(AI214:AI214)=0,"",AJ214-LOOKUP(2,1/(AI214:AI214<>""),AI214:AI214))) | IF(OR(F214="",AK214=""),"",IF(COUNT(AI214:AJ214)=0,"",AK214-LOOKUP(2,1/(AI214:AJ214<>""),AI214:AJ214))) | IF(OR(F214="",AL214=""),"",IF(COUNT(AI214:AK214)=0,"",AL214-LOOKUP(2,1/(AI214:AK214<>""),AI214:AK214))) | IF(OR(F214="",AM214=""),"",IF(COUNT(AI214:AL214)=0,"",AM214-LOOKUP(2,1/(AI214:AL214<>""),AI214:AL214))) | IF(OR(F214="",AN214=""),"",IF(COUNT(AI214:AM214)=0,"",AN214-LOOKUP(2,1/(AI214:AM214<>""),AI214:AM214))) | IF(OR(F214="",AO214=""),"",IF(COUNT(AI214:AN214)=0,"",AO214-LOOKUP(2,1/(AI214:AN214<>""),AI214:AN214))) | IF(OR(F214="",AP214=""),"",IF(COUNT(AI214:AO214)=0,"",AP214-LOOKUP(2,1/(AI214:AO214<>""),AI214:AO214))) | IF(OR(F214="",AQ214=""),"",IF(COUNT(AI214:AP214)=0,"",AQ214-LOOKUP(2,1/(AI214:AP214<>""),AI214:AP214))) | IF(OR(F214="",AR214=""),"",IF(COUNT(AI214:AQ214)=0,"",AR214-LOOKUP(2,1/(AI214:AQ214<>""),AI214:AQ214))) | IF(OR(F214="",AS214=""),"",IF(COUNT(AI214:AR214)=0,"",AS214-LOOKUP(2,1/(AI214:AR214<>""),AI214:AR214))) | IF(OR(F214="",AT214=""),"",IF(COUNT(AI214:AS214)=0,"",AT214-LOOKUP(2,1/(AI214:AS214<>""),AI214:AS214))) | IF(OR(F214="",AU214=""),"",IF(COUNT(AI214:AT214)=0,"",AU214-LOOKUP(2,1/(AI214:AT214<>""),AI214:AT214))) | IF(OR(F214="",AV214=""),"",IF(COUNT(AI214:AU214)=0,"",AV214-LOOKUP(2,1/(AI214:AU214<>""),AI214:AU214))) | IF(J214="","All_Provinces",IFERROR(VLOOKUP(J214,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K214="","All_Districts",IFERROR(VLOOKUP(K214,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F215="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 4 of 50 | AF2-LLL-N-004 | Badiabad irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Laghman | Alingar | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ215="","",AQ215) | 2026-10-30 |  | 2027-01-31 | IF(W215<>"",W215,IF(OR(T215="",V215=""),"",EDATE(T215,V215))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F215="","",IF(COUNT(AI215:AV215)=0,IF(AA215="","Not started",AA215),SUBSTITUTE(LOOKUP(2,1/(AI215:AV215<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F215="",COUNT(AI215:AV215)=0),"",TODAY()-LOOKUP(2,1/(AI215:AV215<>""),AI215:AV215)) | IF(OR(F215="",COUNT(AI215:AV215)<2),"",LOOKUP(2,1/(AI215:AV215<>""),AI215:AV215)-MIN(AI215:AV215)) | IF(OR(AD215="",AC215="Not started",AC215=""),"",IFERROR(AD215-IF(VLOOKUP(AC215,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC215,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F215="","",IF(OR(AA215="Cancelled",AC215="Cancelled"),"Cancelled",IF(OR(AC215="Completed / Handover",Y215<>"",Z215>=100),"Completed — on track",IF(O215="Not awarded",IF(U215="",IF(X215="","No planned date",IF(TODAY()>X215,"Behind — past planned date",IF(X215-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U215,"Behind — award date passed",IF(U215-TODAY()<=30,"At risk — close to off track","On track"))),IF(X215="","No planned date",IF(AND(TODAY()>X215,OR(Z215="",Z215<100)),"Behind — past end date",IF(AND(T215<>"",X215<>"",Z215<>"",(Z215<100),((TODAY()-T215)/MAX(X215-T215,1)*100)-Z215>15),"Behind — progress lag",IF(AND(X215-TODAY()<=30,X215-TODAY()>=0,OR(Z215="",Z215<90)),"At risk — close to off track","On track")))))))) | IF(OR(F215="",AC215="Completed / Handover",AC215="Cancelled"),"",IF(O215="Not awarded",IF(U215<>"",U215-TODAY(),IF(X215="","",X215-TODAY())),IF(X215="","",X215-TODAY()))) | [14 empty] | IF(OR(F215="",AJ215=""),"",IF(COUNT(AI215:AI215)=0,"",AJ215-LOOKUP(2,1/(AI215:AI215<>""),AI215:AI215))) | IF(OR(F215="",AK215=""),"",IF(COUNT(AI215:AJ215)=0,"",AK215-LOOKUP(2,1/(AI215:AJ215<>""),AI215:AJ215))) | IF(OR(F215="",AL215=""),"",IF(COUNT(AI215:AK215)=0,"",AL215-LOOKUP(2,1/(AI215:AK215<>""),AI215:AK215))) | IF(OR(F215="",AM215=""),"",IF(COUNT(AI215:AL215)=0,"",AM215-LOOKUP(2,1/(AI215:AL215<>""),AI215:AL215))) | IF(OR(F215="",AN215=""),"",IF(COUNT(AI215:AM215)=0,"",AN215-LOOKUP(2,1/(AI215:AM215<>""),AI215:AM215))) | IF(OR(F215="",AO215=""),"",IF(COUNT(AI215:AN215)=0,"",AO215-LOOKUP(2,1/(AI215:AN215<>""),AI215:AN215))) | IF(OR(F215="",AP215=""),"",IF(COUNT(AI215:AO215)=0,"",AP215-LOOKUP(2,1/(AI215:AO215<>""),AI215:AO215))) | IF(OR(F215="",AQ215=""),"",IF(COUNT(AI215:AP215)=0,"",AQ215-LOOKUP(2,1/(AI215:AP215<>""),AI215:AP215))) | IF(OR(F215="",AR215=""),"",IF(COUNT(AI215:AQ215)=0,"",AR215-LOOKUP(2,1/(AI215:AQ215<>""),AI215:AQ215))) | IF(OR(F215="",AS215=""),"",IF(COUNT(AI215:AR215)=0,"",AS215-LOOKUP(2,1/(AI215:AR215<>""),AI215:AR215))) | IF(OR(F215="",AT215=""),"",IF(COUNT(AI215:AS215)=0,"",AT215-LOOKUP(2,1/(AI215:AS215<>""),AI215:AS215))) | IF(OR(F215="",AU215=""),"",IF(COUNT(AI215:AT215)=0,"",AU215-LOOKUP(2,1/(AI215:AT215<>""),AI215:AT215))) | IF(OR(F215="",AV215=""),"",IF(COUNT(AI215:AU215)=0,"",AV215-LOOKUP(2,1/(AI215:AU215<>""),AI215:AU215))) | IF(J215="","All_Provinces",IFERROR(VLOOKUP(J215,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K215="","All_Districts",IFERROR(VLOOKUP(K215,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F216="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 5 of 50 | AF2-LLL-N-005 | Bahr-e-Ameq irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sar-E-Pul | Sozma Qala | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ216="","",AQ216) | 2026-10-30 |  | 2027-01-31 | IF(W216<>"",W216,IF(OR(T216="",V216=""),"",EDATE(T216,V216))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F216="","",IF(COUNT(AI216:AV216)=0,IF(AA216="","Not started",AA216),SUBSTITUTE(LOOKUP(2,1/(AI216:AV216<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F216="",COUNT(AI216:AV216)=0),"",TODAY()-LOOKUP(2,1/(AI216:AV216<>""),AI216:AV216)) | IF(OR(F216="",COUNT(AI216:AV216)<2),"",LOOKUP(2,1/(AI216:AV216<>""),AI216:AV216)-MIN(AI216:AV216)) | IF(OR(AD216="",AC216="Not started",AC216=""),"",IFERROR(AD216-IF(VLOOKUP(AC216,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC216,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F216="","",IF(OR(AA216="Cancelled",AC216="Cancelled"),"Cancelled",IF(OR(AC216="Completed / Handover",Y216<>"",Z216>=100),"Completed — on track",IF(O216="Not awarded",IF(U216="",IF(X216="","No planned date",IF(TODAY()>X216,"Behind — past planned date",IF(X216-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U216,"Behind — award date passed",IF(U216-TODAY()<=30,"At risk — close to off track","On track"))),IF(X216="","No planned date",IF(AND(TODAY()>X216,OR(Z216="",Z216<100)),"Behind — past end date",IF(AND(T216<>"",X216<>"",Z216<>"",(Z216<100),((TODAY()-T216)/MAX(X216-T216,1)*100)-Z216>15),"Behind — progress lag",IF(AND(X216-TODAY()<=30,X216-TODAY()>=0,OR(Z216="",Z216<90)),"At risk — close to off track","On track")))))))) | IF(OR(F216="",AC216="Completed / Handover",AC216="Cancelled"),"",IF(O216="Not awarded",IF(U216<>"",U216-TODAY(),IF(X216="","",X216-TODAY())),IF(X216="","",X216-TODAY()))) | [14 empty] | IF(OR(F216="",AJ216=""),"",IF(COUNT(AI216:AI216)=0,"",AJ216-LOOKUP(2,1/(AI216:AI216<>""),AI216:AI216))) | IF(OR(F216="",AK216=""),"",IF(COUNT(AI216:AJ216)=0,"",AK216-LOOKUP(2,1/(AI216:AJ216<>""),AI216:AJ216))) | IF(OR(F216="",AL216=""),"",IF(COUNT(AI216:AK216)=0,"",AL216-LOOKUP(2,1/(AI216:AK216<>""),AI216:AK216))) | IF(OR(F216="",AM216=""),"",IF(COUNT(AI216:AL216)=0,"",AM216-LOOKUP(2,1/(AI216:AL216<>""),AI216:AL216))) | IF(OR(F216="",AN216=""),"",IF(COUNT(AI216:AM216)=0,"",AN216-LOOKUP(2,1/(AI216:AM216<>""),AI216:AM216))) | IF(OR(F216="",AO216=""),"",IF(COUNT(AI216:AN216)=0,"",AO216-LOOKUP(2,1/(AI216:AN216<>""),AI216:AN216))) | IF(OR(F216="",AP216=""),"",IF(COUNT(AI216:AO216)=0,"",AP216-LOOKUP(2,1/(AI216:AO216<>""),AI216:AO216))) | IF(OR(F216="",AQ216=""),"",IF(COUNT(AI216:AP216)=0,"",AQ216-LOOKUP(2,1/(AI216:AP216<>""),AI216:AP216))) | IF(OR(F216="",AR216=""),"",IF(COUNT(AI216:AQ216)=0,"",AR216-LOOKUP(2,1/(AI216:AQ216<>""),AI216:AQ216))) | IF(OR(F216="",AS216=""),"",IF(COUNT(AI216:AR216)=0,"",AS216-LOOKUP(2,1/(AI216:AR216<>""),AI216:AR216))) | IF(OR(F216="",AT216=""),"",IF(COUNT(AI216:AS216)=0,"",AT216-LOOKUP(2,1/(AI216:AS216<>""),AI216:AS216))) | IF(OR(F216="",AU216=""),"",IF(COUNT(AI216:AT216)=0,"",AU216-LOOKUP(2,1/(AI216:AT216<>""),AI216:AT216))) | IF(OR(F216="",AV216=""),"",IF(COUNT(AI216:AU216)=0,"",AV216-LOOKUP(2,1/(AI216:AU216<>""),AI216:AU216))) | IF(J216="","All_Provinces",IFERROR(VLOOKUP(J216,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K216="","All_Districts",IFERROR(VLOOKUP(K216,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F217="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 6 of 50 | AF2-LLL-N-006 | Boghos Qum Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Kunduz | Char Dara | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ217="","",AQ217) | 2026-10-30 |  | 2027-01-31 | IF(W217<>"",W217,IF(OR(T217="",V217=""),"",EDATE(T217,V217))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F217="","",IF(COUNT(AI217:AV217)=0,IF(AA217="","Not started",AA217),SUBSTITUTE(LOOKUP(2,1/(AI217:AV217<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F217="",COUNT(AI217:AV217)=0),"",TODAY()-LOOKUP(2,1/(AI217:AV217<>""),AI217:AV217)) | IF(OR(F217="",COUNT(AI217:AV217)<2),"",LOOKUP(2,1/(AI217:AV217<>""),AI217:AV217)-MIN(AI217:AV217)) | IF(OR(AD217="",AC217="Not started",AC217=""),"",IFERROR(AD217-IF(VLOOKUP(AC217,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC217,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F217="","",IF(OR(AA217="Cancelled",AC217="Cancelled"),"Cancelled",IF(OR(AC217="Completed / Handover",Y217<>"",Z217>=100),"Completed — on track",IF(O217="Not awarded",IF(U217="",IF(X217="","No planned date",IF(TODAY()>X217,"Behind — past planned date",IF(X217-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U217,"Behind — award date passed",IF(U217-TODAY()<=30,"At risk — close to off track","On track"))),IF(X217="","No planned date",IF(AND(TODAY()>X217,OR(Z217="",Z217<100)),"Behind — past end date",IF(AND(T217<>"",X217<>"",Z217<>"",(Z217<100),((TODAY()-T217)/MAX(X217-T217,1)*100)-Z217>15),"Behind — progress lag",IF(AND(X217-TODAY()<=30,X217-TODAY()>=0,OR(Z217="",Z217<90)),"At risk — close to off track","On track")))))))) | IF(OR(F217="",AC217="Completed / Handover",AC217="Cancelled"),"",IF(O217="Not awarded",IF(U217<>"",U217-TODAY(),IF(X217="","",X217-TODAY())),IF(X217="","",X217-TODAY()))) | [14 empty] | IF(OR(F217="",AJ217=""),"",IF(COUNT(AI217:AI217)=0,"",AJ217-LOOKUP(2,1/(AI217:AI217<>""),AI217:AI217))) | IF(OR(F217="",AK217=""),"",IF(COUNT(AI217:AJ217)=0,"",AK217-LOOKUP(2,1/(AI217:AJ217<>""),AI217:AJ217))) | IF(OR(F217="",AL217=""),"",IF(COUNT(AI217:AK217)=0,"",AL217-LOOKUP(2,1/(AI217:AK217<>""),AI217:AK217))) | IF(OR(F217="",AM217=""),"",IF(COUNT(AI217:AL217)=0,"",AM217-LOOKUP(2,1/(AI217:AL217<>""),AI217:AL217))) | IF(OR(F217="",AN217=""),"",IF(COUNT(AI217:AM217)=0,"",AN217-LOOKUP(2,1/(AI217:AM217<>""),AI217:AM217))) | IF(OR(F217="",AO217=""),"",IF(COUNT(AI217:AN217)=0,"",AO217-LOOKUP(2,1/(AI217:AN217<>""),AI217:AN217))) | IF(OR(F217="",AP217=""),"",IF(COUNT(AI217:AO217)=0,"",AP217-LOOKUP(2,1/(AI217:AO217<>""),AI217:AO217))) | IF(OR(F217="",AQ217=""),"",IF(COUNT(AI217:AP217)=0,"",AQ217-LOOKUP(2,1/(AI217:AP217<>""),AI217:AP217))) | IF(OR(F217="",AR217=""),"",IF(COUNT(AI217:AQ217)=0,"",AR217-LOOKUP(2,1/(AI217:AQ217<>""),AI217:AQ217))) | IF(OR(F217="",AS217=""),"",IF(COUNT(AI217:AR217)=0,"",AS217-LOOKUP(2,1/(AI217:AR217<>""),AI217:AR217))) | IF(OR(F217="",AT217=""),"",IF(COUNT(AI217:AS217)=0,"",AT217-LOOKUP(2,1/(AI217:AS217<>""),AI217:AS217))) | IF(OR(F217="",AU217=""),"",IF(COUNT(AI217:AT217)=0,"",AU217-LOOKUP(2,1/(AI217:AT217<>""),AI217:AT217))) | IF(OR(F217="",AV217=""),"",IF(COUNT(AI217:AU217)=0,"",AV217-LOOKUP(2,1/(AI217:AU217<>""),AI217:AU217))) | IF(J217="","All_Provinces",IFERROR(VLOOKUP(J217,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K217="","All_Districts",IFERROR(VLOOKUP(K217,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F218="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 7 of 50 | AF2-LLL-N-007 | Cheknawar irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Lalpoora | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ218="","",AQ218) | 2026-10-30 |  | 2027-01-31 | IF(W218<>"",W218,IF(OR(T218="",V218=""),"",EDATE(T218,V218))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F218="","",IF(COUNT(AI218:AV218)=0,IF(AA218="","Not started",AA218),SUBSTITUTE(LOOKUP(2,1/(AI218:AV218<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F218="",COUNT(AI218:AV218)=0),"",TODAY()-LOOKUP(2,1/(AI218:AV218<>""),AI218:AV218)) | IF(OR(F218="",COUNT(AI218:AV218)<2),"",LOOKUP(2,1/(AI218:AV218<>""),AI218:AV218)-MIN(AI218:AV218)) | IF(OR(AD218="",AC218="Not started",AC218=""),"",IFERROR(AD218-IF(VLOOKUP(AC218,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC218,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F218="","",IF(OR(AA218="Cancelled",AC218="Cancelled"),"Cancelled",IF(OR(AC218="Completed / Handover",Y218<>"",Z218>=100),"Completed — on track",IF(O218="Not awarded",IF(U218="",IF(X218="","No planned date",IF(TODAY()>X218,"Behind — past planned date",IF(X218-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U218,"Behind — award date passed",IF(U218-TODAY()<=30,"At risk — close to off track","On track"))),IF(X218="","No planned date",IF(AND(TODAY()>X218,OR(Z218="",Z218<100)),"Behind — past end date",IF(AND(T218<>"",X218<>"",Z218<>"",(Z218<100),((TODAY()-T218)/MAX(X218-T218,1)*100)-Z218>15),"Behind — progress lag",IF(AND(X218-TODAY()<=30,X218-TODAY()>=0,OR(Z218="",Z218<90)),"At risk — close to off track","On track")))))))) | IF(OR(F218="",AC218="Completed / Handover",AC218="Cancelled"),"",IF(O218="Not awarded",IF(U218<>"",U218-TODAY(),IF(X218="","",X218-TODAY())),IF(X218="","",X218-TODAY()))) | [14 empty] | IF(OR(F218="",AJ218=""),"",IF(COUNT(AI218:AI218)=0,"",AJ218-LOOKUP(2,1/(AI218:AI218<>""),AI218:AI218))) | IF(OR(F218="",AK218=""),"",IF(COUNT(AI218:AJ218)=0,"",AK218-LOOKUP(2,1/(AI218:AJ218<>""),AI218:AJ218))) | IF(OR(F218="",AL218=""),"",IF(COUNT(AI218:AK218)=0,"",AL218-LOOKUP(2,1/(AI218:AK218<>""),AI218:AK218))) | IF(OR(F218="",AM218=""),"",IF(COUNT(AI218:AL218)=0,"",AM218-LOOKUP(2,1/(AI218:AL218<>""),AI218:AL218))) | IF(OR(F218="",AN218=""),"",IF(COUNT(AI218:AM218)=0,"",AN218-LOOKUP(2,1/(AI218:AM218<>""),AI218:AM218))) | IF(OR(F218="",AO218=""),"",IF(COUNT(AI218:AN218)=0,"",AO218-LOOKUP(2,1/(AI218:AN218<>""),AI218:AN218))) | IF(OR(F218="",AP218=""),"",IF(COUNT(AI218:AO218)=0,"",AP218-LOOKUP(2,1/(AI218:AO218<>""),AI218:AO218))) | IF(OR(F218="",AQ218=""),"",IF(COUNT(AI218:AP218)=0,"",AQ218-LOOKUP(2,1/(AI218:AP218<>""),AI218:AP218))) | IF(OR(F218="",AR218=""),"",IF(COUNT(AI218:AQ218)=0,"",AR218-LOOKUP(2,1/(AI218:AQ218<>""),AI218:AQ218))) | IF(OR(F218="",AS218=""),"",IF(COUNT(AI218:AR218)=0,"",AS218-LOOKUP(2,1/(AI218:AR218<>""),AI218:AR218))) | IF(OR(F218="",AT218=""),"",IF(COUNT(AI218:AS218)=0,"",AT218-LOOKUP(2,1/(AI218:AS218<>""),AI218:AS218))) | IF(OR(F218="",AU218=""),"",IF(COUNT(AI218:AT218)=0,"",AU218-LOOKUP(2,1/(AI218:AT218<>""),AI218:AT218))) | IF(OR(F218="",AV218=""),"",IF(COUNT(AI218:AU218)=0,"",AV218-LOOKUP(2,1/(AI218:AU218<>""),AI218:AU218))) | IF(J218="","All_Provinces",IFERROR(VLOOKUP(J218,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K218="","All_Districts",IFERROR(VLOOKUP(K218,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F219="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 8 of 50 | AF2-LLL-N-008 | Chela Mazar irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Dara-e-Suf-e-Payeen | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ219="","",AQ219) | 2026-10-30 |  | 2027-01-31 | IF(W219<>"",W219,IF(OR(T219="",V219=""),"",EDATE(T219,V219))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F219="","",IF(COUNT(AI219:AV219)=0,IF(AA219="","Not started",AA219),SUBSTITUTE(LOOKUP(2,1/(AI219:AV219<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F219="",COUNT(AI219:AV219)=0),"",TODAY()-LOOKUP(2,1/(AI219:AV219<>""),AI219:AV219)) | IF(OR(F219="",COUNT(AI219:AV219)<2),"",LOOKUP(2,1/(AI219:AV219<>""),AI219:AV219)-MIN(AI219:AV219)) | IF(OR(AD219="",AC219="Not started",AC219=""),"",IFERROR(AD219-IF(VLOOKUP(AC219,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC219,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F219="","",IF(OR(AA219="Cancelled",AC219="Cancelled"),"Cancelled",IF(OR(AC219="Completed / Handover",Y219<>"",Z219>=100),"Completed — on track",IF(O219="Not awarded",IF(U219="",IF(X219="","No planned date",IF(TODAY()>X219,"Behind — past planned date",IF(X219-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U219,"Behind — award date passed",IF(U219-TODAY()<=30,"At risk — close to off track","On track"))),IF(X219="","No planned date",IF(AND(TODAY()>X219,OR(Z219="",Z219<100)),"Behind — past end date",IF(AND(T219<>"",X219<>"",Z219<>"",(Z219<100),((TODAY()-T219)/MAX(X219-T219,1)*100)-Z219>15),"Behind — progress lag",IF(AND(X219-TODAY()<=30,X219-TODAY()>=0,OR(Z219="",Z219<90)),"At risk — close to off track","On track")))))))) | IF(OR(F219="",AC219="Completed / Handover",AC219="Cancelled"),"",IF(O219="Not awarded",IF(U219<>"",U219-TODAY(),IF(X219="","",X219-TODAY())),IF(X219="","",X219-TODAY()))) | [14 empty] | IF(OR(F219="",AJ219=""),"",IF(COUNT(AI219:AI219)=0,"",AJ219-LOOKUP(2,1/(AI219:AI219<>""),AI219:AI219))) | IF(OR(F219="",AK219=""),"",IF(COUNT(AI219:AJ219)=0,"",AK219-LOOKUP(2,1/(AI219:AJ219<>""),AI219:AJ219))) | IF(OR(F219="",AL219=""),"",IF(COUNT(AI219:AK219)=0,"",AL219-LOOKUP(2,1/(AI219:AK219<>""),AI219:AK219))) | IF(OR(F219="",AM219=""),"",IF(COUNT(AI219:AL219)=0,"",AM219-LOOKUP(2,1/(AI219:AL219<>""),AI219:AL219))) | IF(OR(F219="",AN219=""),"",IF(COUNT(AI219:AM219)=0,"",AN219-LOOKUP(2,1/(AI219:AM219<>""),AI219:AM219))) | IF(OR(F219="",AO219=""),"",IF(COUNT(AI219:AN219)=0,"",AO219-LOOKUP(2,1/(AI219:AN219<>""),AI219:AN219))) | IF(OR(F219="",AP219=""),"",IF(COUNT(AI219:AO219)=0,"",AP219-LOOKUP(2,1/(AI219:AO219<>""),AI219:AO219))) | IF(OR(F219="",AQ219=""),"",IF(COUNT(AI219:AP219)=0,"",AQ219-LOOKUP(2,1/(AI219:AP219<>""),AI219:AP219))) | IF(OR(F219="",AR219=""),"",IF(COUNT(AI219:AQ219)=0,"",AR219-LOOKUP(2,1/(AI219:AQ219<>""),AI219:AQ219))) | IF(OR(F219="",AS219=""),"",IF(COUNT(AI219:AR219)=0,"",AS219-LOOKUP(2,1/(AI219:AR219<>""),AI219:AR219))) | IF(OR(F219="",AT219=""),"",IF(COUNT(AI219:AS219)=0,"",AT219-LOOKUP(2,1/(AI219:AS219<>""),AI219:AS219))) | IF(OR(F219="",AU219=""),"",IF(COUNT(AI219:AT219)=0,"",AU219-LOOKUP(2,1/(AI219:AT219<>""),AI219:AT219))) | IF(OR(F219="",AV219=""),"",IF(COUNT(AI219:AU219)=0,"",AV219-LOOKUP(2,1/(AI219:AU219<>""),AI219:AU219))) | IF(J219="","All_Provinces",IFERROR(VLOOKUP(J219,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K219="","All_Districts",IFERROR(VLOOKUP(K219,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F220="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 9 of 50 | AF2-LLL-N-009 | Dagh Aruq Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Kunduz | Char Dara | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ220="","",AQ220) | 2026-10-30 |  | 2027-01-31 | IF(W220<>"",W220,IF(OR(T220="",V220=""),"",EDATE(T220,V220))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F220="","",IF(COUNT(AI220:AV220)=0,IF(AA220="","Not started",AA220),SUBSTITUTE(LOOKUP(2,1/(AI220:AV220<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F220="",COUNT(AI220:AV220)=0),"",TODAY()-LOOKUP(2,1/(AI220:AV220<>""),AI220:AV220)) | IF(OR(F220="",COUNT(AI220:AV220)<2),"",LOOKUP(2,1/(AI220:AV220<>""),AI220:AV220)-MIN(AI220:AV220)) | IF(OR(AD220="",AC220="Not started",AC220=""),"",IFERROR(AD220-IF(VLOOKUP(AC220,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC220,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F220="","",IF(OR(AA220="Cancelled",AC220="Cancelled"),"Cancelled",IF(OR(AC220="Completed / Handover",Y220<>"",Z220>=100),"Completed — on track",IF(O220="Not awarded",IF(U220="",IF(X220="","No planned date",IF(TODAY()>X220,"Behind — past planned date",IF(X220-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U220,"Behind — award date passed",IF(U220-TODAY()<=30,"At risk — close to off track","On track"))),IF(X220="","No planned date",IF(AND(TODAY()>X220,OR(Z220="",Z220<100)),"Behind — past end date",IF(AND(T220<>"",X220<>"",Z220<>"",(Z220<100),((TODAY()-T220)/MAX(X220-T220,1)*100)-Z220>15),"Behind — progress lag",IF(AND(X220-TODAY()<=30,X220-TODAY()>=0,OR(Z220="",Z220<90)),"At risk — close to off track","On track")))))))) | IF(OR(F220="",AC220="Completed / Handover",AC220="Cancelled"),"",IF(O220="Not awarded",IF(U220<>"",U220-TODAY(),IF(X220="","",X220-TODAY())),IF(X220="","",X220-TODAY()))) | [14 empty] | IF(OR(F220="",AJ220=""),"",IF(COUNT(AI220:AI220)=0,"",AJ220-LOOKUP(2,1/(AI220:AI220<>""),AI220:AI220))) | IF(OR(F220="",AK220=""),"",IF(COUNT(AI220:AJ220)=0,"",AK220-LOOKUP(2,1/(AI220:AJ220<>""),AI220:AJ220))) | IF(OR(F220="",AL220=""),"",IF(COUNT(AI220:AK220)=0,"",AL220-LOOKUP(2,1/(AI220:AK220<>""),AI220:AK220))) | IF(OR(F220="",AM220=""),"",IF(COUNT(AI220:AL220)=0,"",AM220-LOOKUP(2,1/(AI220:AL220<>""),AI220:AL220))) | IF(OR(F220="",AN220=""),"",IF(COUNT(AI220:AM220)=0,"",AN220-LOOKUP(2,1/(AI220:AM220<>""),AI220:AM220))) | IF(OR(F220="",AO220=""),"",IF(COUNT(AI220:AN220)=0,"",AO220-LOOKUP(2,1/(AI220:AN220<>""),AI220:AN220))) | IF(OR(F220="",AP220=""),"",IF(COUNT(AI220:AO220)=0,"",AP220-LOOKUP(2,1/(AI220:AO220<>""),AI220:AO220))) | IF(OR(F220="",AQ220=""),"",IF(COUNT(AI220:AP220)=0,"",AQ220-LOOKUP(2,1/(AI220:AP220<>""),AI220:AP220))) | IF(OR(F220="",AR220=""),"",IF(COUNT(AI220:AQ220)=0,"",AR220-LOOKUP(2,1/(AI220:AQ220<>""),AI220:AQ220))) | IF(OR(F220="",AS220=""),"",IF(COUNT(AI220:AR220)=0,"",AS220-LOOKUP(2,1/(AI220:AR220<>""),AI220:AR220))) | IF(OR(F220="",AT220=""),"",IF(COUNT(AI220:AS220)=0,"",AT220-LOOKUP(2,1/(AI220:AS220<>""),AI220:AS220))) | IF(OR(F220="",AU220=""),"",IF(COUNT(AI220:AT220)=0,"",AU220-LOOKUP(2,1/(AI220:AT220<>""),AI220:AT220))) | IF(OR(F220="",AV220=""),"",IF(COUNT(AI220:AU220)=0,"",AV220-LOOKUP(2,1/(AI220:AU220<>""),AI220:AU220))) | IF(J220="","All_Provinces",IFERROR(VLOOKUP(J220,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K220="","All_Districts",IFERROR(VLOOKUP(K220,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F221="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 10 of 50 | AF2-LLL-N-010 | Drang Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktya | Zurmat | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ221="","",AQ221) | 2026-10-30 |  | 2027-01-31 | IF(W221<>"",W221,IF(OR(T221="",V221=""),"",EDATE(T221,V221))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F221="","",IF(COUNT(AI221:AV221)=0,IF(AA221="","Not started",AA221),SUBSTITUTE(LOOKUP(2,1/(AI221:AV221<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F221="",COUNT(AI221:AV221)=0),"",TODAY()-LOOKUP(2,1/(AI221:AV221<>""),AI221:AV221)) | IF(OR(F221="",COUNT(AI221:AV221)<2),"",LOOKUP(2,1/(AI221:AV221<>""),AI221:AV221)-MIN(AI221:AV221)) | IF(OR(AD221="",AC221="Not started",AC221=""),"",IFERROR(AD221-IF(VLOOKUP(AC221,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC221,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F221="","",IF(OR(AA221="Cancelled",AC221="Cancelled"),"Cancelled",IF(OR(AC221="Completed / Handover",Y221<>"",Z221>=100),"Completed — on track",IF(O221="Not awarded",IF(U221="",IF(X221="","No planned date",IF(TODAY()>X221,"Behind — past planned date",IF(X221-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U221,"Behind — award date passed",IF(U221-TODAY()<=30,"At risk — close to off track","On track"))),IF(X221="","No planned date",IF(AND(TODAY()>X221,OR(Z221="",Z221<100)),"Behind — past end date",IF(AND(T221<>"",X221<>"",Z221<>"",(Z221<100),((TODAY()-T221)/MAX(X221-T221,1)*100)-Z221>15),"Behind — progress lag",IF(AND(X221-TODAY()<=30,X221-TODAY()>=0,OR(Z221="",Z221<90)),"At risk — close to off track","On track")))))))) | IF(OR(F221="",AC221="Completed / Handover",AC221="Cancelled"),"",IF(O221="Not awarded",IF(U221<>"",U221-TODAY(),IF(X221="","",X221-TODAY())),IF(X221="","",X221-TODAY()))) | [14 empty] | IF(OR(F221="",AJ221=""),"",IF(COUNT(AI221:AI221)=0,"",AJ221-LOOKUP(2,1/(AI221:AI221<>""),AI221:AI221))) | IF(OR(F221="",AK221=""),"",IF(COUNT(AI221:AJ221)=0,"",AK221-LOOKUP(2,1/(AI221:AJ221<>""),AI221:AJ221))) | IF(OR(F221="",AL221=""),"",IF(COUNT(AI221:AK221)=0,"",AL221-LOOKUP(2,1/(AI221:AK221<>""),AI221:AK221))) | IF(OR(F221="",AM221=""),"",IF(COUNT(AI221:AL221)=0,"",AM221-LOOKUP(2,1/(AI221:AL221<>""),AI221:AL221))) | IF(OR(F221="",AN221=""),"",IF(COUNT(AI221:AM221)=0,"",AN221-LOOKUP(2,1/(AI221:AM221<>""),AI221:AM221))) | IF(OR(F221="",AO221=""),"",IF(COUNT(AI221:AN221)=0,"",AO221-LOOKUP(2,1/(AI221:AN221<>""),AI221:AN221))) | IF(OR(F221="",AP221=""),"",IF(COUNT(AI221:AO221)=0,"",AP221-LOOKUP(2,1/(AI221:AO221<>""),AI221:AO221))) | IF(OR(F221="",AQ221=""),"",IF(COUNT(AI221:AP221)=0,"",AQ221-LOOKUP(2,1/(AI221:AP221<>""),AI221:AP221))) | IF(OR(F221="",AR221=""),"",IF(COUNT(AI221:AQ221)=0,"",AR221-LOOKUP(2,1/(AI221:AQ221<>""),AI221:AQ221))) | IF(OR(F221="",AS221=""),"",IF(COUNT(AI221:AR221)=0,"",AS221-LOOKUP(2,1/(AI221:AR221<>""),AI221:AR221))) | IF(OR(F221="",AT221=""),"",IF(COUNT(AI221:AS221)=0,"",AT221-LOOKUP(2,1/(AI221:AS221<>""),AI221:AS221))) | IF(OR(F221="",AU221=""),"",IF(COUNT(AI221:AT221)=0,"",AU221-LOOKUP(2,1/(AI221:AT221<>""),AI221:AT221))) | IF(OR(F221="",AV221=""),"",IF(COUNT(AI221:AU221)=0,"",AV221-LOOKUP(2,1/(AI221:AU221<>""),AI221:AU221))) | IF(J221="","All_Provinces",IFERROR(VLOOKUP(J221,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K221="","All_Districts",IFERROR(VLOOKUP(K221,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F222="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 11 of 50 | AF2-LLL-N-011 | Eshq Abad canal | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Parwan | Jabul Saraj | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ222="","",AQ222) | 2026-10-30 |  | 2027-01-31 | IF(W222<>"",W222,IF(OR(T222="",V222=""),"",EDATE(T222,V222))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F222="","",IF(COUNT(AI222:AV222)=0,IF(AA222="","Not started",AA222),SUBSTITUTE(LOOKUP(2,1/(AI222:AV222<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F222="",COUNT(AI222:AV222)=0),"",TODAY()-LOOKUP(2,1/(AI222:AV222<>""),AI222:AV222)) | IF(OR(F222="",COUNT(AI222:AV222)<2),"",LOOKUP(2,1/(AI222:AV222<>""),AI222:AV222)-MIN(AI222:AV222)) | IF(OR(AD222="",AC222="Not started",AC222=""),"",IFERROR(AD222-IF(VLOOKUP(AC222,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC222,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F222="","",IF(OR(AA222="Cancelled",AC222="Cancelled"),"Cancelled",IF(OR(AC222="Completed / Handover",Y222<>"",Z222>=100),"Completed — on track",IF(O222="Not awarded",IF(U222="",IF(X222="","No planned date",IF(TODAY()>X222,"Behind — past planned date",IF(X222-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U222,"Behind — award date passed",IF(U222-TODAY()<=30,"At risk — close to off track","On track"))),IF(X222="","No planned date",IF(AND(TODAY()>X222,OR(Z222="",Z222<100)),"Behind — past end date",IF(AND(T222<>"",X222<>"",Z222<>"",(Z222<100),((TODAY()-T222)/MAX(X222-T222,1)*100)-Z222>15),"Behind — progress lag",IF(AND(X222-TODAY()<=30,X222-TODAY()>=0,OR(Z222="",Z222<90)),"At risk — close to off track","On track")))))))) | IF(OR(F222="",AC222="Completed / Handover",AC222="Cancelled"),"",IF(O222="Not awarded",IF(U222<>"",U222-TODAY(),IF(X222="","",X222-TODAY())),IF(X222="","",X222-TODAY()))) | [14 empty] | IF(OR(F222="",AJ222=""),"",IF(COUNT(AI222:AI222)=0,"",AJ222-LOOKUP(2,1/(AI222:AI222<>""),AI222:AI222))) | IF(OR(F222="",AK222=""),"",IF(COUNT(AI222:AJ222)=0,"",AK222-LOOKUP(2,1/(AI222:AJ222<>""),AI222:AJ222))) | IF(OR(F222="",AL222=""),"",IF(COUNT(AI222:AK222)=0,"",AL222-LOOKUP(2,1/(AI222:AK222<>""),AI222:AK222))) | IF(OR(F222="",AM222=""),"",IF(COUNT(AI222:AL222)=0,"",AM222-LOOKUP(2,1/(AI222:AL222<>""),AI222:AL222))) | IF(OR(F222="",AN222=""),"",IF(COUNT(AI222:AM222)=0,"",AN222-LOOKUP(2,1/(AI222:AM222<>""),AI222:AM222))) | IF(OR(F222="",AO222=""),"",IF(COUNT(AI222:AN222)=0,"",AO222-LOOKUP(2,1/(AI222:AN222<>""),AI222:AN222))) | IF(OR(F222="",AP222=""),"",IF(COUNT(AI222:AO222)=0,"",AP222-LOOKUP(2,1/(AI222:AO222<>""),AI222:AO222))) | IF(OR(F222="",AQ222=""),"",IF(COUNT(AI222:AP222)=0,"",AQ222-LOOKUP(2,1/(AI222:AP222<>""),AI222:AP222))) | IF(OR(F222="",AR222=""),"",IF(COUNT(AI222:AQ222)=0,"",AR222-LOOKUP(2,1/(AI222:AQ222<>""),AI222:AQ222))) | IF(OR(F222="",AS222=""),"",IF(COUNT(AI222:AR222)=0,"",AS222-LOOKUP(2,1/(AI222:AR222<>""),AI222:AR222))) | IF(OR(F222="",AT222=""),"",IF(COUNT(AI222:AS222)=0,"",AT222-LOOKUP(2,1/(AI222:AS222<>""),AI222:AS222))) | IF(OR(F222="",AU222=""),"",IF(COUNT(AI222:AT222)=0,"",AU222-LOOKUP(2,1/(AI222:AT222<>""),AI222:AT222))) | IF(OR(F222="",AV222=""),"",IF(COUNT(AI222:AU222)=0,"",AV222-LOOKUP(2,1/(AI222:AU222<>""),AI222:AU222))) | IF(J222="","All_Provinces",IFERROR(VLOOKUP(J222,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K222="","All_Districts",IFERROR(VLOOKUP(K222,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F223="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 12 of 50 | AF2-LLL-N-012 | Hashtman Canal Irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Faryab | Qaisar | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ223="","",AQ223) | 2026-10-30 |  | 2027-01-31 | IF(W223<>"",W223,IF(OR(T223="",V223=""),"",EDATE(T223,V223))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F223="","",IF(COUNT(AI223:AV223)=0,IF(AA223="","Not started",AA223),SUBSTITUTE(LOOKUP(2,1/(AI223:AV223<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F223="",COUNT(AI223:AV223)=0),"",TODAY()-LOOKUP(2,1/(AI223:AV223<>""),AI223:AV223)) | IF(OR(F223="",COUNT(AI223:AV223)<2),"",LOOKUP(2,1/(AI223:AV223<>""),AI223:AV223)-MIN(AI223:AV223)) | IF(OR(AD223="",AC223="Not started",AC223=""),"",IFERROR(AD223-IF(VLOOKUP(AC223,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC223,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F223="","",IF(OR(AA223="Cancelled",AC223="Cancelled"),"Cancelled",IF(OR(AC223="Completed / Handover",Y223<>"",Z223>=100),"Completed — on track",IF(O223="Not awarded",IF(U223="",IF(X223="","No planned date",IF(TODAY()>X223,"Behind — past planned date",IF(X223-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U223,"Behind — award date passed",IF(U223-TODAY()<=30,"At risk — close to off track","On track"))),IF(X223="","No planned date",IF(AND(TODAY()>X223,OR(Z223="",Z223<100)),"Behind — past end date",IF(AND(T223<>"",X223<>"",Z223<>"",(Z223<100),((TODAY()-T223)/MAX(X223-T223,1)*100)-Z223>15),"Behind — progress lag",IF(AND(X223-TODAY()<=30,X223-TODAY()>=0,OR(Z223="",Z223<90)),"At risk — close to off track","On track")))))))) | IF(OR(F223="",AC223="Completed / Handover",AC223="Cancelled"),"",IF(O223="Not awarded",IF(U223<>"",U223-TODAY(),IF(X223="","",X223-TODAY())),IF(X223="","",X223-TODAY()))) | [14 empty] | IF(OR(F223="",AJ223=""),"",IF(COUNT(AI223:AI223)=0,"",AJ223-LOOKUP(2,1/(AI223:AI223<>""),AI223:AI223))) | IF(OR(F223="",AK223=""),"",IF(COUNT(AI223:AJ223)=0,"",AK223-LOOKUP(2,1/(AI223:AJ223<>""),AI223:AJ223))) | IF(OR(F223="",AL223=""),"",IF(COUNT(AI223:AK223)=0,"",AL223-LOOKUP(2,1/(AI223:AK223<>""),AI223:AK223))) | IF(OR(F223="",AM223=""),"",IF(COUNT(AI223:AL223)=0,"",AM223-LOOKUP(2,1/(AI223:AL223<>""),AI223:AL223))) | IF(OR(F223="",AN223=""),"",IF(COUNT(AI223:AM223)=0,"",AN223-LOOKUP(2,1/(AI223:AM223<>""),AI223:AM223))) | IF(OR(F223="",AO223=""),"",IF(COUNT(AI223:AN223)=0,"",AO223-LOOKUP(2,1/(AI223:AN223<>""),AI223:AN223))) | IF(OR(F223="",AP223=""),"",IF(COUNT(AI223:AO223)=0,"",AP223-LOOKUP(2,1/(AI223:AO223<>""),AI223:AO223))) | IF(OR(F223="",AQ223=""),"",IF(COUNT(AI223:AP223)=0,"",AQ223-LOOKUP(2,1/(AI223:AP223<>""),AI223:AP223))) | IF(OR(F223="",AR223=""),"",IF(COUNT(AI223:AQ223)=0,"",AR223-LOOKUP(2,1/(AI223:AQ223<>""),AI223:AQ223))) | IF(OR(F223="",AS223=""),"",IF(COUNT(AI223:AR223)=0,"",AS223-LOOKUP(2,1/(AI223:AR223<>""),AI223:AR223))) | IF(OR(F223="",AT223=""),"",IF(COUNT(AI223:AS223)=0,"",AT223-LOOKUP(2,1/(AI223:AS223<>""),AI223:AS223))) | IF(OR(F223="",AU223=""),"",IF(COUNT(AI223:AT223)=0,"",AU223-LOOKUP(2,1/(AI223:AT223<>""),AI223:AT223))) | IF(OR(F223="",AV223=""),"",IF(COUNT(AI223:AU223)=0,"",AV223-LOOKUP(2,1/(AI223:AU223<>""),AI223:AU223))) | IF(J223="","All_Provinces",IFERROR(VLOOKUP(J223,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K223="","All_Districts",IFERROR(VLOOKUP(K223,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F224="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 13 of 50 | AF2-LLL-N-013 | Joi Baratha Ulya IS | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Dawlatyar | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ224="","",AQ224) | 2026-10-30 |  | 2027-01-31 | IF(W224<>"",W224,IF(OR(T224="",V224=""),"",EDATE(T224,V224))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F224="","",IF(COUNT(AI224:AV224)=0,IF(AA224="","Not started",AA224),SUBSTITUTE(LOOKUP(2,1/(AI224:AV224<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F224="",COUNT(AI224:AV224)=0),"",TODAY()-LOOKUP(2,1/(AI224:AV224<>""),AI224:AV224)) | IF(OR(F224="",COUNT(AI224:AV224)<2),"",LOOKUP(2,1/(AI224:AV224<>""),AI224:AV224)-MIN(AI224:AV224)) | IF(OR(AD224="",AC224="Not started",AC224=""),"",IFERROR(AD224-IF(VLOOKUP(AC224,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC224,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F224="","",IF(OR(AA224="Cancelled",AC224="Cancelled"),"Cancelled",IF(OR(AC224="Completed / Handover",Y224<>"",Z224>=100),"Completed — on track",IF(O224="Not awarded",IF(U224="",IF(X224="","No planned date",IF(TODAY()>X224,"Behind — past planned date",IF(X224-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U224,"Behind — award date passed",IF(U224-TODAY()<=30,"At risk — close to off track","On track"))),IF(X224="","No planned date",IF(AND(TODAY()>X224,OR(Z224="",Z224<100)),"Behind — past end date",IF(AND(T224<>"",X224<>"",Z224<>"",(Z224<100),((TODAY()-T224)/MAX(X224-T224,1)*100)-Z224>15),"Behind — progress lag",IF(AND(X224-TODAY()<=30,X224-TODAY()>=0,OR(Z224="",Z224<90)),"At risk — close to off track","On track")))))))) | IF(OR(F224="",AC224="Completed / Handover",AC224="Cancelled"),"",IF(O224="Not awarded",IF(U224<>"",U224-TODAY(),IF(X224="","",X224-TODAY())),IF(X224="","",X224-TODAY()))) | [14 empty] | IF(OR(F224="",AJ224=""),"",IF(COUNT(AI224:AI224)=0,"",AJ224-LOOKUP(2,1/(AI224:AI224<>""),AI224:AI224))) | IF(OR(F224="",AK224=""),"",IF(COUNT(AI224:AJ224)=0,"",AK224-LOOKUP(2,1/(AI224:AJ224<>""),AI224:AJ224))) | IF(OR(F224="",AL224=""),"",IF(COUNT(AI224:AK224)=0,"",AL224-LOOKUP(2,1/(AI224:AK224<>""),AI224:AK224))) | IF(OR(F224="",AM224=""),"",IF(COUNT(AI224:AL224)=0,"",AM224-LOOKUP(2,1/(AI224:AL224<>""),AI224:AL224))) | IF(OR(F224="",AN224=""),"",IF(COUNT(AI224:AM224)=0,"",AN224-LOOKUP(2,1/(AI224:AM224<>""),AI224:AM224))) | IF(OR(F224="",AO224=""),"",IF(COUNT(AI224:AN224)=0,"",AO224-LOOKUP(2,1/(AI224:AN224<>""),AI224:AN224))) | IF(OR(F224="",AP224=""),"",IF(COUNT(AI224:AO224)=0,"",AP224-LOOKUP(2,1/(AI224:AO224<>""),AI224:AO224))) | IF(OR(F224="",AQ224=""),"",IF(COUNT(AI224:AP224)=0,"",AQ224-LOOKUP(2,1/(AI224:AP224<>""),AI224:AP224))) | IF(OR(F224="",AR224=""),"",IF(COUNT(AI224:AQ224)=0,"",AR224-LOOKUP(2,1/(AI224:AQ224<>""),AI224:AQ224))) | IF(OR(F224="",AS224=""),"",IF(COUNT(AI224:AR224)=0,"",AS224-LOOKUP(2,1/(AI224:AR224<>""),AI224:AR224))) | IF(OR(F224="",AT224=""),"",IF(COUNT(AI224:AS224)=0,"",AT224-LOOKUP(2,1/(AI224:AS224<>""),AI224:AS224))) | IF(OR(F224="",AU224=""),"",IF(COUNT(AI224:AT224)=0,"",AU224-LOOKUP(2,1/(AI224:AT224<>""),AI224:AT224))) | IF(OR(F224="",AV224=""),"",IF(COUNT(AI224:AU224)=0,"",AV224-LOOKUP(2,1/(AI224:AU224<>""),AI224:AU224))) | IF(J224="","All_Provinces",IFERROR(VLOOKUP(J224,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K224="","All_Districts",IFERROR(VLOOKUP(K224,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F225="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 14 of 50 | AF2-LLL-N-014 | Joi Bazar irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Obe | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ225="","",AQ225) | 2026-10-30 |  | 2027-01-31 | IF(W225<>"",W225,IF(OR(T225="",V225=""),"",EDATE(T225,V225))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F225="","",IF(COUNT(AI225:AV225)=0,IF(AA225="","Not started",AA225),SUBSTITUTE(LOOKUP(2,1/(AI225:AV225<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F225="",COUNT(AI225:AV225)=0),"",TODAY()-LOOKUP(2,1/(AI225:AV225<>""),AI225:AV225)) | IF(OR(F225="",COUNT(AI225:AV225)<2),"",LOOKUP(2,1/(AI225:AV225<>""),AI225:AV225)-MIN(AI225:AV225)) | IF(OR(AD225="",AC225="Not started",AC225=""),"",IFERROR(AD225-IF(VLOOKUP(AC225,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC225,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F225="","",IF(OR(AA225="Cancelled",AC225="Cancelled"),"Cancelled",IF(OR(AC225="Completed / Handover",Y225<>"",Z225>=100),"Completed — on track",IF(O225="Not awarded",IF(U225="",IF(X225="","No planned date",IF(TODAY()>X225,"Behind — past planned date",IF(X225-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U225,"Behind — award date passed",IF(U225-TODAY()<=30,"At risk — close to off track","On track"))),IF(X225="","No planned date",IF(AND(TODAY()>X225,OR(Z225="",Z225<100)),"Behind — past end date",IF(AND(T225<>"",X225<>"",Z225<>"",(Z225<100),((TODAY()-T225)/MAX(X225-T225,1)*100)-Z225>15),"Behind — progress lag",IF(AND(X225-TODAY()<=30,X225-TODAY()>=0,OR(Z225="",Z225<90)),"At risk — close to off track","On track")))))))) | IF(OR(F225="",AC225="Completed / Handover",AC225="Cancelled"),"",IF(O225="Not awarded",IF(U225<>"",U225-TODAY(),IF(X225="","",X225-TODAY())),IF(X225="","",X225-TODAY()))) | [14 empty] | IF(OR(F225="",AJ225=""),"",IF(COUNT(AI225:AI225)=0,"",AJ225-LOOKUP(2,1/(AI225:AI225<>""),AI225:AI225))) | IF(OR(F225="",AK225=""),"",IF(COUNT(AI225:AJ225)=0,"",AK225-LOOKUP(2,1/(AI225:AJ225<>""),AI225:AJ225))) | IF(OR(F225="",AL225=""),"",IF(COUNT(AI225:AK225)=0,"",AL225-LOOKUP(2,1/(AI225:AK225<>""),AI225:AK225))) | IF(OR(F225="",AM225=""),"",IF(COUNT(AI225:AL225)=0,"",AM225-LOOKUP(2,1/(AI225:AL225<>""),AI225:AL225))) | IF(OR(F225="",AN225=""),"",IF(COUNT(AI225:AM225)=0,"",AN225-LOOKUP(2,1/(AI225:AM225<>""),AI225:AM225))) | IF(OR(F225="",AO225=""),"",IF(COUNT(AI225:AN225)=0,"",AO225-LOOKUP(2,1/(AI225:AN225<>""),AI225:AN225))) | IF(OR(F225="",AP225=""),"",IF(COUNT(AI225:AO225)=0,"",AP225-LOOKUP(2,1/(AI225:AO225<>""),AI225:AO225))) | IF(OR(F225="",AQ225=""),"",IF(COUNT(AI225:AP225)=0,"",AQ225-LOOKUP(2,1/(AI225:AP225<>""),AI225:AP225))) | IF(OR(F225="",AR225=""),"",IF(COUNT(AI225:AQ225)=0,"",AR225-LOOKUP(2,1/(AI225:AQ225<>""),AI225:AQ225))) | IF(OR(F225="",AS225=""),"",IF(COUNT(AI225:AR225)=0,"",AS225-LOOKUP(2,1/(AI225:AR225<>""),AI225:AR225))) | IF(OR(F225="",AT225=""),"",IF(COUNT(AI225:AS225)=0,"",AT225-LOOKUP(2,1/(AI225:AS225<>""),AI225:AS225))) | IF(OR(F225="",AU225=""),"",IF(COUNT(AI225:AT225)=0,"",AU225-LOOKUP(2,1/(AI225:AT225<>""),AI225:AT225))) | IF(OR(F225="",AV225=""),"",IF(COUNT(AI225:AU225)=0,"",AV225-LOOKUP(2,1/(AI225:AU225<>""),AI225:AU225))) | IF(J225="","All_Provinces",IFERROR(VLOOKUP(J225,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K225="","All_Districts",IFERROR(VLOOKUP(K225,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F226="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 15 of 50 | AF2-LLL-N-015 | Joi Ganj Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Balamorghab | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ226="","",AQ226) | 2026-10-30 |  | 2027-01-31 | IF(W226<>"",W226,IF(OR(T226="",V226=""),"",EDATE(T226,V226))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F226="","",IF(COUNT(AI226:AV226)=0,IF(AA226="","Not started",AA226),SUBSTITUTE(LOOKUP(2,1/(AI226:AV226<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F226="",COUNT(AI226:AV226)=0),"",TODAY()-LOOKUP(2,1/(AI226:AV226<>""),AI226:AV226)) | IF(OR(F226="",COUNT(AI226:AV226)<2),"",LOOKUP(2,1/(AI226:AV226<>""),AI226:AV226)-MIN(AI226:AV226)) | IF(OR(AD226="",AC226="Not started",AC226=""),"",IFERROR(AD226-IF(VLOOKUP(AC226,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC226,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F226="","",IF(OR(AA226="Cancelled",AC226="Cancelled"),"Cancelled",IF(OR(AC226="Completed / Handover",Y226<>"",Z226>=100),"Completed — on track",IF(O226="Not awarded",IF(U226="",IF(X226="","No planned date",IF(TODAY()>X226,"Behind — past planned date",IF(X226-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U226,"Behind — award date passed",IF(U226-TODAY()<=30,"At risk — close to off track","On track"))),IF(X226="","No planned date",IF(AND(TODAY()>X226,OR(Z226="",Z226<100)),"Behind — past end date",IF(AND(T226<>"",X226<>"",Z226<>"",(Z226<100),((TODAY()-T226)/MAX(X226-T226,1)*100)-Z226>15),"Behind — progress lag",IF(AND(X226-TODAY()<=30,X226-TODAY()>=0,OR(Z226="",Z226<90)),"At risk — close to off track","On track")))))))) | IF(OR(F226="",AC226="Completed / Handover",AC226="Cancelled"),"",IF(O226="Not awarded",IF(U226<>"",U226-TODAY(),IF(X226="","",X226-TODAY())),IF(X226="","",X226-TODAY()))) | [14 empty] | IF(OR(F226="",AJ226=""),"",IF(COUNT(AI226:AI226)=0,"",AJ226-LOOKUP(2,1/(AI226:AI226<>""),AI226:AI226))) | IF(OR(F226="",AK226=""),"",IF(COUNT(AI226:AJ226)=0,"",AK226-LOOKUP(2,1/(AI226:AJ226<>""),AI226:AJ226))) | IF(OR(F226="",AL226=""),"",IF(COUNT(AI226:AK226)=0,"",AL226-LOOKUP(2,1/(AI226:AK226<>""),AI226:AK226))) | IF(OR(F226="",AM226=""),"",IF(COUNT(AI226:AL226)=0,"",AM226-LOOKUP(2,1/(AI226:AL226<>""),AI226:AL226))) | IF(OR(F226="",AN226=""),"",IF(COUNT(AI226:AM226)=0,"",AN226-LOOKUP(2,1/(AI226:AM226<>""),AI226:AM226))) | IF(OR(F226="",AO226=""),"",IF(COUNT(AI226:AN226)=0,"",AO226-LOOKUP(2,1/(AI226:AN226<>""),AI226:AN226))) | IF(OR(F226="",AP226=""),"",IF(COUNT(AI226:AO226)=0,"",AP226-LOOKUP(2,1/(AI226:AO226<>""),AI226:AO226))) | IF(OR(F226="",AQ226=""),"",IF(COUNT(AI226:AP226)=0,"",AQ226-LOOKUP(2,1/(AI226:AP226<>""),AI226:AP226))) | IF(OR(F226="",AR226=""),"",IF(COUNT(AI226:AQ226)=0,"",AR226-LOOKUP(2,1/(AI226:AQ226<>""),AI226:AQ226))) | IF(OR(F226="",AS226=""),"",IF(COUNT(AI226:AR226)=0,"",AS226-LOOKUP(2,1/(AI226:AR226<>""),AI226:AR226))) | IF(OR(F226="",AT226=""),"",IF(COUNT(AI226:AS226)=0,"",AT226-LOOKUP(2,1/(AI226:AS226<>""),AI226:AS226))) | IF(OR(F226="",AU226=""),"",IF(COUNT(AI226:AT226)=0,"",AU226-LOOKUP(2,1/(AI226:AT226<>""),AI226:AT226))) | IF(OR(F226="",AV226=""),"",IF(COUNT(AI226:AU226)=0,"",AV226-LOOKUP(2,1/(AI226:AU226<>""),AI226:AU226))) | IF(J226="","All_Provinces",IFERROR(VLOOKUP(J226,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K226="","All_Districts",IFERROR(VLOOKUP(K226,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F227="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 16 of 50 | AF2-LLL-N-016 | Joi Kar Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Balamorghab | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ227="","",AQ227) | 2026-10-30 |  | 2027-01-31 | IF(W227<>"",W227,IF(OR(T227="",V227=""),"",EDATE(T227,V227))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F227="","",IF(COUNT(AI227:AV227)=0,IF(AA227="","Not started",AA227),SUBSTITUTE(LOOKUP(2,1/(AI227:AV227<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F227="",COUNT(AI227:AV227)=0),"",TODAY()-LOOKUP(2,1/(AI227:AV227<>""),AI227:AV227)) | IF(OR(F227="",COUNT(AI227:AV227)<2),"",LOOKUP(2,1/(AI227:AV227<>""),AI227:AV227)-MIN(AI227:AV227)) | IF(OR(AD227="",AC227="Not started",AC227=""),"",IFERROR(AD227-IF(VLOOKUP(AC227,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC227,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F227="","",IF(OR(AA227="Cancelled",AC227="Cancelled"),"Cancelled",IF(OR(AC227="Completed / Handover",Y227<>"",Z227>=100),"Completed — on track",IF(O227="Not awarded",IF(U227="",IF(X227="","No planned date",IF(TODAY()>X227,"Behind — past planned date",IF(X227-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U227,"Behind — award date passed",IF(U227-TODAY()<=30,"At risk — close to off track","On track"))),IF(X227="","No planned date",IF(AND(TODAY()>X227,OR(Z227="",Z227<100)),"Behind — past end date",IF(AND(T227<>"",X227<>"",Z227<>"",(Z227<100),((TODAY()-T227)/MAX(X227-T227,1)*100)-Z227>15),"Behind — progress lag",IF(AND(X227-TODAY()<=30,X227-TODAY()>=0,OR(Z227="",Z227<90)),"At risk — close to off track","On track")))))))) | IF(OR(F227="",AC227="Completed / Handover",AC227="Cancelled"),"",IF(O227="Not awarded",IF(U227<>"",U227-TODAY(),IF(X227="","",X227-TODAY())),IF(X227="","",X227-TODAY()))) | [14 empty] | IF(OR(F227="",AJ227=""),"",IF(COUNT(AI227:AI227)=0,"",AJ227-LOOKUP(2,1/(AI227:AI227<>""),AI227:AI227))) | IF(OR(F227="",AK227=""),"",IF(COUNT(AI227:AJ227)=0,"",AK227-LOOKUP(2,1/(AI227:AJ227<>""),AI227:AJ227))) | IF(OR(F227="",AL227=""),"",IF(COUNT(AI227:AK227)=0,"",AL227-LOOKUP(2,1/(AI227:AK227<>""),AI227:AK227))) | IF(OR(F227="",AM227=""),"",IF(COUNT(AI227:AL227)=0,"",AM227-LOOKUP(2,1/(AI227:AL227<>""),AI227:AL227))) | IF(OR(F227="",AN227=""),"",IF(COUNT(AI227:AM227)=0,"",AN227-LOOKUP(2,1/(AI227:AM227<>""),AI227:AM227))) | IF(OR(F227="",AO227=""),"",IF(COUNT(AI227:AN227)=0,"",AO227-LOOKUP(2,1/(AI227:AN227<>""),AI227:AN227))) | IF(OR(F227="",AP227=""),"",IF(COUNT(AI227:AO227)=0,"",AP227-LOOKUP(2,1/(AI227:AO227<>""),AI227:AO227))) | IF(OR(F227="",AQ227=""),"",IF(COUNT(AI227:AP227)=0,"",AQ227-LOOKUP(2,1/(AI227:AP227<>""),AI227:AP227))) | IF(OR(F227="",AR227=""),"",IF(COUNT(AI227:AQ227)=0,"",AR227-LOOKUP(2,1/(AI227:AQ227<>""),AI227:AQ227))) | IF(OR(F227="",AS227=""),"",IF(COUNT(AI227:AR227)=0,"",AS227-LOOKUP(2,1/(AI227:AR227<>""),AI227:AR227))) | IF(OR(F227="",AT227=""),"",IF(COUNT(AI227:AS227)=0,"",AT227-LOOKUP(2,1/(AI227:AS227<>""),AI227:AS227))) | IF(OR(F227="",AU227=""),"",IF(COUNT(AI227:AT227)=0,"",AU227-LOOKUP(2,1/(AI227:AT227<>""),AI227:AT227))) | IF(OR(F227="",AV227=""),"",IF(COUNT(AI227:AU227)=0,"",AV227-LOOKUP(2,1/(AI227:AU227<>""),AI227:AU227))) | IF(J227="","All_Provinces",IFERROR(VLOOKUP(J227,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K227="","All_Districts",IFERROR(VLOOKUP(K227,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F228="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 17 of 50 | AF2-LLL-N-017 | Joy Shahr Canal Irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Jawzjan | Aqcha | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ228="","",AQ228) | 2026-10-30 |  | 2027-01-31 | IF(W228<>"",W228,IF(OR(T228="",V228=""),"",EDATE(T228,V228))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F228="","",IF(COUNT(AI228:AV228)=0,IF(AA228="","Not started",AA228),SUBSTITUTE(LOOKUP(2,1/(AI228:AV228<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F228="",COUNT(AI228:AV228)=0),"",TODAY()-LOOKUP(2,1/(AI228:AV228<>""),AI228:AV228)) | IF(OR(F228="",COUNT(AI228:AV228)<2),"",LOOKUP(2,1/(AI228:AV228<>""),AI228:AV228)-MIN(AI228:AV228)) | IF(OR(AD228="",AC228="Not started",AC228=""),"",IFERROR(AD228-IF(VLOOKUP(AC228,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC228,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F228="","",IF(OR(AA228="Cancelled",AC228="Cancelled"),"Cancelled",IF(OR(AC228="Completed / Handover",Y228<>"",Z228>=100),"Completed — on track",IF(O228="Not awarded",IF(U228="",IF(X228="","No planned date",IF(TODAY()>X228,"Behind — past planned date",IF(X228-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U228,"Behind — award date passed",IF(U228-TODAY()<=30,"At risk — close to off track","On track"))),IF(X228="","No planned date",IF(AND(TODAY()>X228,OR(Z228="",Z228<100)),"Behind — past end date",IF(AND(T228<>"",X228<>"",Z228<>"",(Z228<100),((TODAY()-T228)/MAX(X228-T228,1)*100)-Z228>15),"Behind — progress lag",IF(AND(X228-TODAY()<=30,X228-TODAY()>=0,OR(Z228="",Z228<90)),"At risk — close to off track","On track")))))))) | IF(OR(F228="",AC228="Completed / Handover",AC228="Cancelled"),"",IF(O228="Not awarded",IF(U228<>"",U228-TODAY(),IF(X228="","",X228-TODAY())),IF(X228="","",X228-TODAY()))) | [14 empty] | IF(OR(F228="",AJ228=""),"",IF(COUNT(AI228:AI228)=0,"",AJ228-LOOKUP(2,1/(AI228:AI228<>""),AI228:AI228))) | IF(OR(F228="",AK228=""),"",IF(COUNT(AI228:AJ228)=0,"",AK228-LOOKUP(2,1/(AI228:AJ228<>""),AI228:AJ228))) | IF(OR(F228="",AL228=""),"",IF(COUNT(AI228:AK228)=0,"",AL228-LOOKUP(2,1/(AI228:AK228<>""),AI228:AK228))) | IF(OR(F228="",AM228=""),"",IF(COUNT(AI228:AL228)=0,"",AM228-LOOKUP(2,1/(AI228:AL228<>""),AI228:AL228))) | IF(OR(F228="",AN228=""),"",IF(COUNT(AI228:AM228)=0,"",AN228-LOOKUP(2,1/(AI228:AM228<>""),AI228:AM228))) | IF(OR(F228="",AO228=""),"",IF(COUNT(AI228:AN228)=0,"",AO228-LOOKUP(2,1/(AI228:AN228<>""),AI228:AN228))) | IF(OR(F228="",AP228=""),"",IF(COUNT(AI228:AO228)=0,"",AP228-LOOKUP(2,1/(AI228:AO228<>""),AI228:AO228))) | IF(OR(F228="",AQ228=""),"",IF(COUNT(AI228:AP228)=0,"",AQ228-LOOKUP(2,1/(AI228:AP228<>""),AI228:AP228))) | IF(OR(F228="",AR228=""),"",IF(COUNT(AI228:AQ228)=0,"",AR228-LOOKUP(2,1/(AI228:AQ228<>""),AI228:AQ228))) | IF(OR(F228="",AS228=""),"",IF(COUNT(AI228:AR228)=0,"",AS228-LOOKUP(2,1/(AI228:AR228<>""),AI228:AR228))) | IF(OR(F228="",AT228=""),"",IF(COUNT(AI228:AS228)=0,"",AT228-LOOKUP(2,1/(AI228:AS228<>""),AI228:AS228))) | IF(OR(F228="",AU228=""),"",IF(COUNT(AI228:AT228)=0,"",AU228-LOOKUP(2,1/(AI228:AT228<>""),AI228:AT228))) | IF(OR(F228="",AV228=""),"",IF(COUNT(AI228:AU228)=0,"",AV228-LOOKUP(2,1/(AI228:AU228<>""),AI228:AU228))) | IF(J228="","All_Provinces",IFERROR(VLOOKUP(J228,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K228="","All_Districts",IFERROR(VLOOKUP(K228,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F229="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 18 of 50 | AF2-LLL-N-018 | Kamary Canal | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Qarabagh | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ229="","",AQ229) | 2026-10-30 | 3.1 | 2027-01-31 | IF(W229<>"",W229,IF(OR(T229="",V229=""),"",EDATE(T229,V229))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F229="","",IF(COUNT(AI229:AV229)=0,IF(AA229="","Not started",AA229),SUBSTITUTE(LOOKUP(2,1/(AI229:AV229<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F229="",COUNT(AI229:AV229)=0),"",TODAY()-LOOKUP(2,1/(AI229:AV229<>""),AI229:AV229)) | IF(OR(F229="",COUNT(AI229:AV229)<2),"",LOOKUP(2,1/(AI229:AV229<>""),AI229:AV229)-MIN(AI229:AV229)) | IF(OR(AD229="",AC229="Not started",AC229=""),"",IFERROR(AD229-IF(VLOOKUP(AC229,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC229,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F229="","",IF(OR(AA229="Cancelled",AC229="Cancelled"),"Cancelled",IF(OR(AC229="Completed / Handover",Y229<>"",Z229>=100),"Completed — on track",IF(O229="Not awarded",IF(U229="",IF(X229="","No planned date",IF(TODAY()>X229,"Behind — past planned date",IF(X229-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U229,"Behind — award date passed",IF(U229-TODAY()<=30,"At risk — close to off track","On track"))),IF(X229="","No planned date",IF(AND(TODAY()>X229,OR(Z229="",Z229<100)),"Behind — past end date",IF(AND(T229<>"",X229<>"",Z229<>"",(Z229<100),((TODAY()-T229)/MAX(X229-T229,1)*100)-Z229>15),"Behind — progress lag",IF(AND(X229-TODAY()<=30,X229-TODAY()>=0,OR(Z229="",Z229<90)),"At risk — close to off track","On track")))))))) | IF(OR(F229="",AC229="Completed / Handover",AC229="Cancelled"),"",IF(O229="Not awarded",IF(U229<>"",U229-TODAY(),IF(X229="","",X229-TODAY())),IF(X229="","",X229-TODAY()))) | [14 empty] | IF(OR(F229="",AJ229=""),"",IF(COUNT(AI229:AI229)=0,"",AJ229-LOOKUP(2,1/(AI229:AI229<>""),AI229:AI229))) | IF(OR(F229="",AK229=""),"",IF(COUNT(AI229:AJ229)=0,"",AK229-LOOKUP(2,1/(AI229:AJ229<>""),AI229:AJ229))) | IF(OR(F229="",AL229=""),"",IF(COUNT(AI229:AK229)=0,"",AL229-LOOKUP(2,1/(AI229:AK229<>""),AI229:AK229))) | IF(OR(F229="",AM229=""),"",IF(COUNT(AI229:AL229)=0,"",AM229-LOOKUP(2,1/(AI229:AL229<>""),AI229:AL229))) | IF(OR(F229="",AN229=""),"",IF(COUNT(AI229:AM229)=0,"",AN229-LOOKUP(2,1/(AI229:AM229<>""),AI229:AM229))) | IF(OR(F229="",AO229=""),"",IF(COUNT(AI229:AN229)=0,"",AO229-LOOKUP(2,1/(AI229:AN229<>""),AI229:AN229))) | IF(OR(F229="",AP229=""),"",IF(COUNT(AI229:AO229)=0,"",AP229-LOOKUP(2,1/(AI229:AO229<>""),AI229:AO229))) | IF(OR(F229="",AQ229=""),"",IF(COUNT(AI229:AP229)=0,"",AQ229-LOOKUP(2,1/(AI229:AP229<>""),AI229:AP229))) | IF(OR(F229="",AR229=""),"",IF(COUNT(AI229:AQ229)=0,"",AR229-LOOKUP(2,1/(AI229:AQ229<>""),AI229:AQ229))) | IF(OR(F229="",AS229=""),"",IF(COUNT(AI229:AR229)=0,"",AS229-LOOKUP(2,1/(AI229:AR229<>""),AI229:AR229))) | IF(OR(F229="",AT229=""),"",IF(COUNT(AI229:AS229)=0,"",AT229-LOOKUP(2,1/(AI229:AS229<>""),AI229:AS229))) | IF(OR(F229="",AU229=""),"",IF(COUNT(AI229:AT229)=0,"",AU229-LOOKUP(2,1/(AI229:AT229<>""),AI229:AT229))) | IF(OR(F229="",AV229=""),"",IF(COUNT(AI229:AU229)=0,"",AV229-LOOKUP(2,1/(AI229:AU229<>""),AI229:AU229))) | IF(J229="","All_Provinces",IFERROR(VLOOKUP(J229,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K229="","All_Districts",IFERROR(VLOOKUP(K229,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F230="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 19 of 50 | AF2-LLL-N-019 | Khambilan, Nahr-e-Saleh and Dara-e-Bazar IS | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Firing | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ230="","",AQ230) | 2026-10-30 |  | 2027-01-31 | IF(W230<>"",W230,IF(OR(T230="",V230=""),"",EDATE(T230,V230))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F230="","",IF(COUNT(AI230:AV230)=0,IF(AA230="","Not started",AA230),SUBSTITUTE(LOOKUP(2,1/(AI230:AV230<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F230="",COUNT(AI230:AV230)=0),"",TODAY()-LOOKUP(2,1/(AI230:AV230<>""),AI230:AV230)) | IF(OR(F230="",COUNT(AI230:AV230)<2),"",LOOKUP(2,1/(AI230:AV230<>""),AI230:AV230)-MIN(AI230:AV230)) | IF(OR(AD230="",AC230="Not started",AC230=""),"",IFERROR(AD230-IF(VLOOKUP(AC230,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC230,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F230="","",IF(OR(AA230="Cancelled",AC230="Cancelled"),"Cancelled",IF(OR(AC230="Completed / Handover",Y230<>"",Z230>=100),"Completed — on track",IF(O230="Not awarded",IF(U230="",IF(X230="","No planned date",IF(TODAY()>X230,"Behind — past planned date",IF(X230-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U230,"Behind — award date passed",IF(U230-TODAY()<=30,"At risk — close to off track","On track"))),IF(X230="","No planned date",IF(AND(TODAY()>X230,OR(Z230="",Z230<100)),"Behind — past end date",IF(AND(T230<>"",X230<>"",Z230<>"",(Z230<100),((TODAY()-T230)/MAX(X230-T230,1)*100)-Z230>15),"Behind — progress lag",IF(AND(X230-TODAY()<=30,X230-TODAY()>=0,OR(Z230="",Z230<90)),"At risk — close to off track","On track")))))))) | IF(OR(F230="",AC230="Completed / Handover",AC230="Cancelled"),"",IF(O230="Not awarded",IF(U230<>"",U230-TODAY(),IF(X230="","",X230-TODAY())),IF(X230="","",X230-TODAY()))) | [14 empty] | IF(OR(F230="",AJ230=""),"",IF(COUNT(AI230:AI230)=0,"",AJ230-LOOKUP(2,1/(AI230:AI230<>""),AI230:AI230))) | IF(OR(F230="",AK230=""),"",IF(COUNT(AI230:AJ230)=0,"",AK230-LOOKUP(2,1/(AI230:AJ230<>""),AI230:AJ230))) | IF(OR(F230="",AL230=""),"",IF(COUNT(AI230:AK230)=0,"",AL230-LOOKUP(2,1/(AI230:AK230<>""),AI230:AK230))) | IF(OR(F230="",AM230=""),"",IF(COUNT(AI230:AL230)=0,"",AM230-LOOKUP(2,1/(AI230:AL230<>""),AI230:AL230))) | IF(OR(F230="",AN230=""),"",IF(COUNT(AI230:AM230)=0,"",AN230-LOOKUP(2,1/(AI230:AM230<>""),AI230:AM230))) | IF(OR(F230="",AO230=""),"",IF(COUNT(AI230:AN230)=0,"",AO230-LOOKUP(2,1/(AI230:AN230<>""),AI230:AN230))) | IF(OR(F230="",AP230=""),"",IF(COUNT(AI230:AO230)=0,"",AP230-LOOKUP(2,1/(AI230:AO230<>""),AI230:AO230))) | IF(OR(F230="",AQ230=""),"",IF(COUNT(AI230:AP230)=0,"",AQ230-LOOKUP(2,1/(AI230:AP230<>""),AI230:AP230))) | IF(OR(F230="",AR230=""),"",IF(COUNT(AI230:AQ230)=0,"",AR230-LOOKUP(2,1/(AI230:AQ230<>""),AI230:AQ230))) | IF(OR(F230="",AS230=""),"",IF(COUNT(AI230:AR230)=0,"",AS230-LOOKUP(2,1/(AI230:AR230<>""),AI230:AR230))) | IF(OR(F230="",AT230=""),"",IF(COUNT(AI230:AS230)=0,"",AT230-LOOKUP(2,1/(AI230:AS230<>""),AI230:AS230))) | IF(OR(F230="",AU230=""),"",IF(COUNT(AI230:AT230)=0,"",AU230-LOOKUP(2,1/(AI230:AT230<>""),AI230:AT230))) | IF(OR(F230="",AV230=""),"",IF(COUNT(AI230:AU230)=0,"",AV230-LOOKUP(2,1/(AI230:AU230<>""),AI230:AU230))) | IF(J230="","All_Provinces",IFERROR(VLOOKUP(J230,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K230="","All_Districts",IFERROR(VLOOKUP(K230,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F231="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 20 of 50 | AF2-LLL-N-020 | Khanum Arabia Canal Irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Jawzjan | Faizabad | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ231="","",AQ231) | 2026-10-30 |  | 2027-01-31 | IF(W231<>"",W231,IF(OR(T231="",V231=""),"",EDATE(T231,V231))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F231="","",IF(COUNT(AI231:AV231)=0,IF(AA231="","Not started",AA231),SUBSTITUTE(LOOKUP(2,1/(AI231:AV231<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F231="",COUNT(AI231:AV231)=0),"",TODAY()-LOOKUP(2,1/(AI231:AV231<>""),AI231:AV231)) | IF(OR(F231="",COUNT(AI231:AV231)<2),"",LOOKUP(2,1/(AI231:AV231<>""),AI231:AV231)-MIN(AI231:AV231)) | IF(OR(AD231="",AC231="Not started",AC231=""),"",IFERROR(AD231-IF(VLOOKUP(AC231,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC231,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F231="","",IF(OR(AA231="Cancelled",AC231="Cancelled"),"Cancelled",IF(OR(AC231="Completed / Handover",Y231<>"",Z231>=100),"Completed — on track",IF(O231="Not awarded",IF(U231="",IF(X231="","No planned date",IF(TODAY()>X231,"Behind — past planned date",IF(X231-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U231,"Behind — award date passed",IF(U231-TODAY()<=30,"At risk — close to off track","On track"))),IF(X231="","No planned date",IF(AND(TODAY()>X231,OR(Z231="",Z231<100)),"Behind — past end date",IF(AND(T231<>"",X231<>"",Z231<>"",(Z231<100),((TODAY()-T231)/MAX(X231-T231,1)*100)-Z231>15),"Behind — progress lag",IF(AND(X231-TODAY()<=30,X231-TODAY()>=0,OR(Z231="",Z231<90)),"At risk — close to off track","On track")))))))) | IF(OR(F231="",AC231="Completed / Handover",AC231="Cancelled"),"",IF(O231="Not awarded",IF(U231<>"",U231-TODAY(),IF(X231="","",X231-TODAY())),IF(X231="","",X231-TODAY()))) | [14 empty] | IF(OR(F231="",AJ231=""),"",IF(COUNT(AI231:AI231)=0,"",AJ231-LOOKUP(2,1/(AI231:AI231<>""),AI231:AI231))) | IF(OR(F231="",AK231=""),"",IF(COUNT(AI231:AJ231)=0,"",AK231-LOOKUP(2,1/(AI231:AJ231<>""),AI231:AJ231))) | IF(OR(F231="",AL231=""),"",IF(COUNT(AI231:AK231)=0,"",AL231-LOOKUP(2,1/(AI231:AK231<>""),AI231:AK231))) | IF(OR(F231="",AM231=""),"",IF(COUNT(AI231:AL231)=0,"",AM231-LOOKUP(2,1/(AI231:AL231<>""),AI231:AL231))) | IF(OR(F231="",AN231=""),"",IF(COUNT(AI231:AM231)=0,"",AN231-LOOKUP(2,1/(AI231:AM231<>""),AI231:AM231))) | IF(OR(F231="",AO231=""),"",IF(COUNT(AI231:AN231)=0,"",AO231-LOOKUP(2,1/(AI231:AN231<>""),AI231:AN231))) | IF(OR(F231="",AP231=""),"",IF(COUNT(AI231:AO231)=0,"",AP231-LOOKUP(2,1/(AI231:AO231<>""),AI231:AO231))) | IF(OR(F231="",AQ231=""),"",IF(COUNT(AI231:AP231)=0,"",AQ231-LOOKUP(2,1/(AI231:AP231<>""),AI231:AP231))) | IF(OR(F231="",AR231=""),"",IF(COUNT(AI231:AQ231)=0,"",AR231-LOOKUP(2,1/(AI231:AQ231<>""),AI231:AQ231))) | IF(OR(F231="",AS231=""),"",IF(COUNT(AI231:AR231)=0,"",AS231-LOOKUP(2,1/(AI231:AR231<>""),AI231:AR231))) | IF(OR(F231="",AT231=""),"",IF(COUNT(AI231:AS231)=0,"",AT231-LOOKUP(2,1/(AI231:AS231<>""),AI231:AS231))) | IF(OR(F231="",AU231=""),"",IF(COUNT(AI231:AT231)=0,"",AU231-LOOKUP(2,1/(AI231:AT231<>""),AI231:AT231))) | IF(OR(F231="",AV231=""),"",IF(COUNT(AI231:AU231)=0,"",AV231-LOOKUP(2,1/(AI231:AU231<>""),AI231:AU231))) | IF(J231="","All_Provinces",IFERROR(VLOOKUP(J231,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K231="","All_Districts",IFERROR(VLOOKUP(K231,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F232="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 21 of 50 | AF2-LLL-N-021 | Khar Kar and Sayed Miran IS | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Eshkamish | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ232="","",AQ232) | 2026-10-30 |  | 2027-01-31 | IF(W232<>"",W232,IF(OR(T232="",V232=""),"",EDATE(T232,V232))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F232="","",IF(COUNT(AI232:AV232)=0,IF(AA232="","Not started",AA232),SUBSTITUTE(LOOKUP(2,1/(AI232:AV232<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F232="",COUNT(AI232:AV232)=0),"",TODAY()-LOOKUP(2,1/(AI232:AV232<>""),AI232:AV232)) | IF(OR(F232="",COUNT(AI232:AV232)<2),"",LOOKUP(2,1/(AI232:AV232<>""),AI232:AV232)-MIN(AI232:AV232)) | IF(OR(AD232="",AC232="Not started",AC232=""),"",IFERROR(AD232-IF(VLOOKUP(AC232,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC232,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F232="","",IF(OR(AA232="Cancelled",AC232="Cancelled"),"Cancelled",IF(OR(AC232="Completed / Handover",Y232<>"",Z232>=100),"Completed — on track",IF(O232="Not awarded",IF(U232="",IF(X232="","No planned date",IF(TODAY()>X232,"Behind — past planned date",IF(X232-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U232,"Behind — award date passed",IF(U232-TODAY()<=30,"At risk — close to off track","On track"))),IF(X232="","No planned date",IF(AND(TODAY()>X232,OR(Z232="",Z232<100)),"Behind — past end date",IF(AND(T232<>"",X232<>"",Z232<>"",(Z232<100),((TODAY()-T232)/MAX(X232-T232,1)*100)-Z232>15),"Behind — progress lag",IF(AND(X232-TODAY()<=30,X232-TODAY()>=0,OR(Z232="",Z232<90)),"At risk — close to off track","On track")))))))) | IF(OR(F232="",AC232="Completed / Handover",AC232="Cancelled"),"",IF(O232="Not awarded",IF(U232<>"",U232-TODAY(),IF(X232="","",X232-TODAY())),IF(X232="","",X232-TODAY()))) | [14 empty] | IF(OR(F232="",AJ232=""),"",IF(COUNT(AI232:AI232)=0,"",AJ232-LOOKUP(2,1/(AI232:AI232<>""),AI232:AI232))) | IF(OR(F232="",AK232=""),"",IF(COUNT(AI232:AJ232)=0,"",AK232-LOOKUP(2,1/(AI232:AJ232<>""),AI232:AJ232))) | IF(OR(F232="",AL232=""),"",IF(COUNT(AI232:AK232)=0,"",AL232-LOOKUP(2,1/(AI232:AK232<>""),AI232:AK232))) | IF(OR(F232="",AM232=""),"",IF(COUNT(AI232:AL232)=0,"",AM232-LOOKUP(2,1/(AI232:AL232<>""),AI232:AL232))) | IF(OR(F232="",AN232=""),"",IF(COUNT(AI232:AM232)=0,"",AN232-LOOKUP(2,1/(AI232:AM232<>""),AI232:AM232))) | IF(OR(F232="",AO232=""),"",IF(COUNT(AI232:AN232)=0,"",AO232-LOOKUP(2,1/(AI232:AN232<>""),AI232:AN232))) | IF(OR(F232="",AP232=""),"",IF(COUNT(AI232:AO232)=0,"",AP232-LOOKUP(2,1/(AI232:AO232<>""),AI232:AO232))) | IF(OR(F232="",AQ232=""),"",IF(COUNT(AI232:AP232)=0,"",AQ232-LOOKUP(2,1/(AI232:AP232<>""),AI232:AP232))) | IF(OR(F232="",AR232=""),"",IF(COUNT(AI232:AQ232)=0,"",AR232-LOOKUP(2,1/(AI232:AQ232<>""),AI232:AQ232))) | IF(OR(F232="",AS232=""),"",IF(COUNT(AI232:AR232)=0,"",AS232-LOOKUP(2,1/(AI232:AR232<>""),AI232:AR232))) | IF(OR(F232="",AT232=""),"",IF(COUNT(AI232:AS232)=0,"",AT232-LOOKUP(2,1/(AI232:AS232<>""),AI232:AS232))) | IF(OR(F232="",AU232=""),"",IF(COUNT(AI232:AT232)=0,"",AU232-LOOKUP(2,1/(AI232:AT232<>""),AI232:AT232))) | IF(OR(F232="",AV232=""),"",IF(COUNT(AI232:AU232)=0,"",AV232-LOOKUP(2,1/(AI232:AU232<>""),AI232:AU232))) | IF(J232="","All_Provinces",IFERROR(VLOOKUP(J232,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K232="","All_Districts",IFERROR(VLOOKUP(K232,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F233="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 22 of 50 | AF2-LLL-N-022 | Khas kunar irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Khas kunar | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ233="","",AQ233) | 2026-10-30 |  | 2027-01-31 | IF(W233<>"",W233,IF(OR(T233="",V233=""),"",EDATE(T233,V233))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F233="","",IF(COUNT(AI233:AV233)=0,IF(AA233="","Not started",AA233),SUBSTITUTE(LOOKUP(2,1/(AI233:AV233<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F233="",COUNT(AI233:AV233)=0),"",TODAY()-LOOKUP(2,1/(AI233:AV233<>""),AI233:AV233)) | IF(OR(F233="",COUNT(AI233:AV233)<2),"",LOOKUP(2,1/(AI233:AV233<>""),AI233:AV233)-MIN(AI233:AV233)) | IF(OR(AD233="",AC233="Not started",AC233=""),"",IFERROR(AD233-IF(VLOOKUP(AC233,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC233,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F233="","",IF(OR(AA233="Cancelled",AC233="Cancelled"),"Cancelled",IF(OR(AC233="Completed / Handover",Y233<>"",Z233>=100),"Completed — on track",IF(O233="Not awarded",IF(U233="",IF(X233="","No planned date",IF(TODAY()>X233,"Behind — past planned date",IF(X233-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U233,"Behind — award date passed",IF(U233-TODAY()<=30,"At risk — close to off track","On track"))),IF(X233="","No planned date",IF(AND(TODAY()>X233,OR(Z233="",Z233<100)),"Behind — past end date",IF(AND(T233<>"",X233<>"",Z233<>"",(Z233<100),((TODAY()-T233)/MAX(X233-T233,1)*100)-Z233>15),"Behind — progress lag",IF(AND(X233-TODAY()<=30,X233-TODAY()>=0,OR(Z233="",Z233<90)),"At risk — close to off track","On track")))))))) | IF(OR(F233="",AC233="Completed / Handover",AC233="Cancelled"),"",IF(O233="Not awarded",IF(U233<>"",U233-TODAY(),IF(X233="","",X233-TODAY())),IF(X233="","",X233-TODAY()))) | [14 empty] | IF(OR(F233="",AJ233=""),"",IF(COUNT(AI233:AI233)=0,"",AJ233-LOOKUP(2,1/(AI233:AI233<>""),AI233:AI233))) | IF(OR(F233="",AK233=""),"",IF(COUNT(AI233:AJ233)=0,"",AK233-LOOKUP(2,1/(AI233:AJ233<>""),AI233:AJ233))) | IF(OR(F233="",AL233=""),"",IF(COUNT(AI233:AK233)=0,"",AL233-LOOKUP(2,1/(AI233:AK233<>""),AI233:AK233))) | IF(OR(F233="",AM233=""),"",IF(COUNT(AI233:AL233)=0,"",AM233-LOOKUP(2,1/(AI233:AL233<>""),AI233:AL233))) | IF(OR(F233="",AN233=""),"",IF(COUNT(AI233:AM233)=0,"",AN233-LOOKUP(2,1/(AI233:AM233<>""),AI233:AM233))) | IF(OR(F233="",AO233=""),"",IF(COUNT(AI233:AN233)=0,"",AO233-LOOKUP(2,1/(AI233:AN233<>""),AI233:AN233))) | IF(OR(F233="",AP233=""),"",IF(COUNT(AI233:AO233)=0,"",AP233-LOOKUP(2,1/(AI233:AO233<>""),AI233:AO233))) | IF(OR(F233="",AQ233=""),"",IF(COUNT(AI233:AP233)=0,"",AQ233-LOOKUP(2,1/(AI233:AP233<>""),AI233:AP233))) | IF(OR(F233="",AR233=""),"",IF(COUNT(AI233:AQ233)=0,"",AR233-LOOKUP(2,1/(AI233:AQ233<>""),AI233:AQ233))) | IF(OR(F233="",AS233=""),"",IF(COUNT(AI233:AR233)=0,"",AS233-LOOKUP(2,1/(AI233:AR233<>""),AI233:AR233))) | IF(OR(F233="",AT233=""),"",IF(COUNT(AI233:AS233)=0,"",AT233-LOOKUP(2,1/(AI233:AS233<>""),AI233:AS233))) | IF(OR(F233="",AU233=""),"",IF(COUNT(AI233:AT233)=0,"",AU233-LOOKUP(2,1/(AI233:AT233<>""),AI233:AT233))) | IF(OR(F233="",AV233=""),"",IF(COUNT(AI233:AU233)=0,"",AV233-LOOKUP(2,1/(AI233:AU233<>""),AI233:AU233))) | IF(J233="","All_Provinces",IFERROR(VLOOKUP(J233,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K233="","All_Districts",IFERROR(VLOOKUP(K233,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F234="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 23 of 50 | AF2-LLL-N-023 | Khuspak-e-Markazi | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Ishkashim | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ234="","",AQ234) | 2026-10-30 |  | 2027-01-31 | IF(W234<>"",W234,IF(OR(T234="",V234=""),"",EDATE(T234,V234))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F234="","",IF(COUNT(AI234:AV234)=0,IF(AA234="","Not started",AA234),SUBSTITUTE(LOOKUP(2,1/(AI234:AV234<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F234="",COUNT(AI234:AV234)=0),"",TODAY()-LOOKUP(2,1/(AI234:AV234<>""),AI234:AV234)) | IF(OR(F234="",COUNT(AI234:AV234)<2),"",LOOKUP(2,1/(AI234:AV234<>""),AI234:AV234)-MIN(AI234:AV234)) | IF(OR(AD234="",AC234="Not started",AC234=""),"",IFERROR(AD234-IF(VLOOKUP(AC234,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC234,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F234="","",IF(OR(AA234="Cancelled",AC234="Cancelled"),"Cancelled",IF(OR(AC234="Completed / Handover",Y234<>"",Z234>=100),"Completed — on track",IF(O234="Not awarded",IF(U234="",IF(X234="","No planned date",IF(TODAY()>X234,"Behind — past planned date",IF(X234-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U234,"Behind — award date passed",IF(U234-TODAY()<=30,"At risk — close to off track","On track"))),IF(X234="","No planned date",IF(AND(TODAY()>X234,OR(Z234="",Z234<100)),"Behind — past end date",IF(AND(T234<>"",X234<>"",Z234<>"",(Z234<100),((TODAY()-T234)/MAX(X234-T234,1)*100)-Z234>15),"Behind — progress lag",IF(AND(X234-TODAY()<=30,X234-TODAY()>=0,OR(Z234="",Z234<90)),"At risk — close to off track","On track")))))))) | IF(OR(F234="",AC234="Completed / Handover",AC234="Cancelled"),"",IF(O234="Not awarded",IF(U234<>"",U234-TODAY(),IF(X234="","",X234-TODAY())),IF(X234="","",X234-TODAY()))) | [14 empty] | IF(OR(F234="",AJ234=""),"",IF(COUNT(AI234:AI234)=0,"",AJ234-LOOKUP(2,1/(AI234:AI234<>""),AI234:AI234))) | IF(OR(F234="",AK234=""),"",IF(COUNT(AI234:AJ234)=0,"",AK234-LOOKUP(2,1/(AI234:AJ234<>""),AI234:AJ234))) | IF(OR(F234="",AL234=""),"",IF(COUNT(AI234:AK234)=0,"",AL234-LOOKUP(2,1/(AI234:AK234<>""),AI234:AK234))) | IF(OR(F234="",AM234=""),"",IF(COUNT(AI234:AL234)=0,"",AM234-LOOKUP(2,1/(AI234:AL234<>""),AI234:AL234))) | IF(OR(F234="",AN234=""),"",IF(COUNT(AI234:AM234)=0,"",AN234-LOOKUP(2,1/(AI234:AM234<>""),AI234:AM234))) | IF(OR(F234="",AO234=""),"",IF(COUNT(AI234:AN234)=0,"",AO234-LOOKUP(2,1/(AI234:AN234<>""),AI234:AN234))) | IF(OR(F234="",AP234=""),"",IF(COUNT(AI234:AO234)=0,"",AP234-LOOKUP(2,1/(AI234:AO234<>""),AI234:AO234))) | IF(OR(F234="",AQ234=""),"",IF(COUNT(AI234:AP234)=0,"",AQ234-LOOKUP(2,1/(AI234:AP234<>""),AI234:AP234))) | IF(OR(F234="",AR234=""),"",IF(COUNT(AI234:AQ234)=0,"",AR234-LOOKUP(2,1/(AI234:AQ234<>""),AI234:AQ234))) | IF(OR(F234="",AS234=""),"",IF(COUNT(AI234:AR234)=0,"",AS234-LOOKUP(2,1/(AI234:AR234<>""),AI234:AR234))) | IF(OR(F234="",AT234=""),"",IF(COUNT(AI234:AS234)=0,"",AT234-LOOKUP(2,1/(AI234:AS234<>""),AI234:AS234))) | IF(OR(F234="",AU234=""),"",IF(COUNT(AI234:AT234)=0,"",AU234-LOOKUP(2,1/(AI234:AT234<>""),AI234:AT234))) | IF(OR(F234="",AV234=""),"",IF(COUNT(AI234:AU234)=0,"",AV234-LOOKUP(2,1/(AI234:AU234<>""),AI234:AU234))) | IF(J234="","All_Provinces",IFERROR(VLOOKUP(J234,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K234="","All_Districts",IFERROR(VLOOKUP(K234,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F235="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 24 of 50 | AF2-LLL-N-024 | Khwaja Angor Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Logar | Kharwar | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ235="","",AQ235) | 2026-10-30 |  | 2027-01-31 | IF(W235<>"",W235,IF(OR(T235="",V235=""),"",EDATE(T235,V235))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F235="","",IF(COUNT(AI235:AV235)=0,IF(AA235="","Not started",AA235),SUBSTITUTE(LOOKUP(2,1/(AI235:AV235<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F235="",COUNT(AI235:AV235)=0),"",TODAY()-LOOKUP(2,1/(AI235:AV235<>""),AI235:AV235)) | IF(OR(F235="",COUNT(AI235:AV235)<2),"",LOOKUP(2,1/(AI235:AV235<>""),AI235:AV235)-MIN(AI235:AV235)) | IF(OR(AD235="",AC235="Not started",AC235=""),"",IFERROR(AD235-IF(VLOOKUP(AC235,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC235,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F235="","",IF(OR(AA235="Cancelled",AC235="Cancelled"),"Cancelled",IF(OR(AC235="Completed / Handover",Y235<>"",Z235>=100),"Completed — on track",IF(O235="Not awarded",IF(U235="",IF(X235="","No planned date",IF(TODAY()>X235,"Behind — past planned date",IF(X235-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U235,"Behind — award date passed",IF(U235-TODAY()<=30,"At risk — close to off track","On track"))),IF(X235="","No planned date",IF(AND(TODAY()>X235,OR(Z235="",Z235<100)),"Behind — past end date",IF(AND(T235<>"",X235<>"",Z235<>"",(Z235<100),((TODAY()-T235)/MAX(X235-T235,1)*100)-Z235>15),"Behind — progress lag",IF(AND(X235-TODAY()<=30,X235-TODAY()>=0,OR(Z235="",Z235<90)),"At risk — close to off track","On track")))))))) | IF(OR(F235="",AC235="Completed / Handover",AC235="Cancelled"),"",IF(O235="Not awarded",IF(U235<>"",U235-TODAY(),IF(X235="","",X235-TODAY())),IF(X235="","",X235-TODAY()))) | [14 empty] | IF(OR(F235="",AJ235=""),"",IF(COUNT(AI235:AI235)=0,"",AJ235-LOOKUP(2,1/(AI235:AI235<>""),AI235:AI235))) | IF(OR(F235="",AK235=""),"",IF(COUNT(AI235:AJ235)=0,"",AK235-LOOKUP(2,1/(AI235:AJ235<>""),AI235:AJ235))) | IF(OR(F235="",AL235=""),"",IF(COUNT(AI235:AK235)=0,"",AL235-LOOKUP(2,1/(AI235:AK235<>""),AI235:AK235))) | IF(OR(F235="",AM235=""),"",IF(COUNT(AI235:AL235)=0,"",AM235-LOOKUP(2,1/(AI235:AL235<>""),AI235:AL235))) | IF(OR(F235="",AN235=""),"",IF(COUNT(AI235:AM235)=0,"",AN235-LOOKUP(2,1/(AI235:AM235<>""),AI235:AM235))) | IF(OR(F235="",AO235=""),"",IF(COUNT(AI235:AN235)=0,"",AO235-LOOKUP(2,1/(AI235:AN235<>""),AI235:AN235))) | IF(OR(F235="",AP235=""),"",IF(COUNT(AI235:AO235)=0,"",AP235-LOOKUP(2,1/(AI235:AO235<>""),AI235:AO235))) | IF(OR(F235="",AQ235=""),"",IF(COUNT(AI235:AP235)=0,"",AQ235-LOOKUP(2,1/(AI235:AP235<>""),AI235:AP235))) | IF(OR(F235="",AR235=""),"",IF(COUNT(AI235:AQ235)=0,"",AR235-LOOKUP(2,1/(AI235:AQ235<>""),AI235:AQ235))) | IF(OR(F235="",AS235=""),"",IF(COUNT(AI235:AR235)=0,"",AS235-LOOKUP(2,1/(AI235:AR235<>""),AI235:AR235))) | IF(OR(F235="",AT235=""),"",IF(COUNT(AI235:AS235)=0,"",AT235-LOOKUP(2,1/(AI235:AS235<>""),AI235:AS235))) | IF(OR(F235="",AU235=""),"",IF(COUNT(AI235:AT235)=0,"",AU235-LOOKUP(2,1/(AI235:AT235<>""),AI235:AT235))) | IF(OR(F235="",AV235=""),"",IF(COUNT(AI235:AU235)=0,"",AV235-LOOKUP(2,1/(AI235:AU235<>""),AI235:AU235))) | IF(J235="","All_Provinces",IFERROR(VLOOKUP(J235,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K235="","All_Districts",IFERROR(VLOOKUP(K235,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F236="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 25 of 50 | AF2-LLL-N-025 | Kushkak irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Dara-e-Suf-e-Bala | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ236="","",AQ236) | 2026-10-30 |  | 2027-01-31 | IF(W236<>"",W236,IF(OR(T236="",V236=""),"",EDATE(T236,V236))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F236="","",IF(COUNT(AI236:AV236)=0,IF(AA236="","Not started",AA236),SUBSTITUTE(LOOKUP(2,1/(AI236:AV236<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F236="",COUNT(AI236:AV236)=0),"",TODAY()-LOOKUP(2,1/(AI236:AV236<>""),AI236:AV236)) | IF(OR(F236="",COUNT(AI236:AV236)<2),"",LOOKUP(2,1/(AI236:AV236<>""),AI236:AV236)-MIN(AI236:AV236)) | IF(OR(AD236="",AC236="Not started",AC236=""),"",IFERROR(AD236-IF(VLOOKUP(AC236,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC236,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F236="","",IF(OR(AA236="Cancelled",AC236="Cancelled"),"Cancelled",IF(OR(AC236="Completed / Handover",Y236<>"",Z236>=100),"Completed — on track",IF(O236="Not awarded",IF(U236="",IF(X236="","No planned date",IF(TODAY()>X236,"Behind — past planned date",IF(X236-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U236,"Behind — award date passed",IF(U236-TODAY()<=30,"At risk — close to off track","On track"))),IF(X236="","No planned date",IF(AND(TODAY()>X236,OR(Z236="",Z236<100)),"Behind — past end date",IF(AND(T236<>"",X236<>"",Z236<>"",(Z236<100),((TODAY()-T236)/MAX(X236-T236,1)*100)-Z236>15),"Behind — progress lag",IF(AND(X236-TODAY()<=30,X236-TODAY()>=0,OR(Z236="",Z236<90)),"At risk — close to off track","On track")))))))) | IF(OR(F236="",AC236="Completed / Handover",AC236="Cancelled"),"",IF(O236="Not awarded",IF(U236<>"",U236-TODAY(),IF(X236="","",X236-TODAY())),IF(X236="","",X236-TODAY()))) | [14 empty] | IF(OR(F236="",AJ236=""),"",IF(COUNT(AI236:AI236)=0,"",AJ236-LOOKUP(2,1/(AI236:AI236<>""),AI236:AI236))) | IF(OR(F236="",AK236=""),"",IF(COUNT(AI236:AJ236)=0,"",AK236-LOOKUP(2,1/(AI236:AJ236<>""),AI236:AJ236))) | IF(OR(F236="",AL236=""),"",IF(COUNT(AI236:AK236)=0,"",AL236-LOOKUP(2,1/(AI236:AK236<>""),AI236:AK236))) | IF(OR(F236="",AM236=""),"",IF(COUNT(AI236:AL236)=0,"",AM236-LOOKUP(2,1/(AI236:AL236<>""),AI236:AL236))) | IF(OR(F236="",AN236=""),"",IF(COUNT(AI236:AM236)=0,"",AN236-LOOKUP(2,1/(AI236:AM236<>""),AI236:AM236))) | IF(OR(F236="",AO236=""),"",IF(COUNT(AI236:AN236)=0,"",AO236-LOOKUP(2,1/(AI236:AN236<>""),AI236:AN236))) | IF(OR(F236="",AP236=""),"",IF(COUNT(AI236:AO236)=0,"",AP236-LOOKUP(2,1/(AI236:AO236<>""),AI236:AO236))) | IF(OR(F236="",AQ236=""),"",IF(COUNT(AI236:AP236)=0,"",AQ236-LOOKUP(2,1/(AI236:AP236<>""),AI236:AP236))) | IF(OR(F236="",AR236=""),"",IF(COUNT(AI236:AQ236)=0,"",AR236-LOOKUP(2,1/(AI236:AQ236<>""),AI236:AQ236))) | IF(OR(F236="",AS236=""),"",IF(COUNT(AI236:AR236)=0,"",AS236-LOOKUP(2,1/(AI236:AR236<>""),AI236:AR236))) | IF(OR(F236="",AT236=""),"",IF(COUNT(AI236:AS236)=0,"",AT236-LOOKUP(2,1/(AI236:AS236<>""),AI236:AS236))) | IF(OR(F236="",AU236=""),"",IF(COUNT(AI236:AT236)=0,"",AU236-LOOKUP(2,1/(AI236:AT236<>""),AI236:AT236))) | IF(OR(F236="",AV236=""),"",IF(COUNT(AI236:AU236)=0,"",AV236-LOOKUP(2,1/(AI236:AU236<>""),AI236:AU236))) | IF(J236="","All_Provinces",IFERROR(VLOOKUP(J236,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K236="","All_Districts",IFERROR(VLOOKUP(K236,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F237="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 26 of 50 | AF2-LLL-N-026 | Mandaliat -e-Tanor canal | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Midan Wardak | Hesa Awal Behsood | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ237="","",AQ237) | 2026-10-30 |  | 2027-01-31 | IF(W237<>"",W237,IF(OR(T237="",V237=""),"",EDATE(T237,V237))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F237="","",IF(COUNT(AI237:AV237)=0,IF(AA237="","Not started",AA237),SUBSTITUTE(LOOKUP(2,1/(AI237:AV237<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F237="",COUNT(AI237:AV237)=0),"",TODAY()-LOOKUP(2,1/(AI237:AV237<>""),AI237:AV237)) | IF(OR(F237="",COUNT(AI237:AV237)<2),"",LOOKUP(2,1/(AI237:AV237<>""),AI237:AV237)-MIN(AI237:AV237)) | IF(OR(AD237="",AC237="Not started",AC237=""),"",IFERROR(AD237-IF(VLOOKUP(AC237,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC237,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F237="","",IF(OR(AA237="Cancelled",AC237="Cancelled"),"Cancelled",IF(OR(AC237="Completed / Handover",Y237<>"",Z237>=100),"Completed — on track",IF(O237="Not awarded",IF(U237="",IF(X237="","No planned date",IF(TODAY()>X237,"Behind — past planned date",IF(X237-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U237,"Behind — award date passed",IF(U237-TODAY()<=30,"At risk — close to off track","On track"))),IF(X237="","No planned date",IF(AND(TODAY()>X237,OR(Z237="",Z237<100)),"Behind — past end date",IF(AND(T237<>"",X237<>"",Z237<>"",(Z237<100),((TODAY()-T237)/MAX(X237-T237,1)*100)-Z237>15),"Behind — progress lag",IF(AND(X237-TODAY()<=30,X237-TODAY()>=0,OR(Z237="",Z237<90)),"At risk — close to off track","On track")))))))) | IF(OR(F237="",AC237="Completed / Handover",AC237="Cancelled"),"",IF(O237="Not awarded",IF(U237<>"",U237-TODAY(),IF(X237="","",X237-TODAY())),IF(X237="","",X237-TODAY()))) | [14 empty] | IF(OR(F237="",AJ237=""),"",IF(COUNT(AI237:AI237)=0,"",AJ237-LOOKUP(2,1/(AI237:AI237<>""),AI237:AI237))) | IF(OR(F237="",AK237=""),"",IF(COUNT(AI237:AJ237)=0,"",AK237-LOOKUP(2,1/(AI237:AJ237<>""),AI237:AJ237))) | IF(OR(F237="",AL237=""),"",IF(COUNT(AI237:AK237)=0,"",AL237-LOOKUP(2,1/(AI237:AK237<>""),AI237:AK237))) | IF(OR(F237="",AM237=""),"",IF(COUNT(AI237:AL237)=0,"",AM237-LOOKUP(2,1/(AI237:AL237<>""),AI237:AL237))) | IF(OR(F237="",AN237=""),"",IF(COUNT(AI237:AM237)=0,"",AN237-LOOKUP(2,1/(AI237:AM237<>""),AI237:AM237))) | IF(OR(F237="",AO237=""),"",IF(COUNT(AI237:AN237)=0,"",AO237-LOOKUP(2,1/(AI237:AN237<>""),AI237:AN237))) | IF(OR(F237="",AP237=""),"",IF(COUNT(AI237:AO237)=0,"",AP237-LOOKUP(2,1/(AI237:AO237<>""),AI237:AO237))) | IF(OR(F237="",AQ237=""),"",IF(COUNT(AI237:AP237)=0,"",AQ237-LOOKUP(2,1/(AI237:AP237<>""),AI237:AP237))) | IF(OR(F237="",AR237=""),"",IF(COUNT(AI237:AQ237)=0,"",AR237-LOOKUP(2,1/(AI237:AQ237<>""),AI237:AQ237))) | IF(OR(F237="",AS237=""),"",IF(COUNT(AI237:AR237)=0,"",AS237-LOOKUP(2,1/(AI237:AR237<>""),AI237:AR237))) | IF(OR(F237="",AT237=""),"",IF(COUNT(AI237:AS237)=0,"",AT237-LOOKUP(2,1/(AI237:AS237<>""),AI237:AS237))) | IF(OR(F237="",AU237=""),"",IF(COUNT(AI237:AT237)=0,"",AU237-LOOKUP(2,1/(AI237:AT237<>""),AI237:AT237))) | IF(OR(F237="",AV237=""),"",IF(COUNT(AI237:AU237)=0,"",AV237-LOOKUP(2,1/(AI237:AU237<>""),AI237:AU237))) | IF(J237="","All_Provinces",IFERROR(VLOOKUP(J237,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K237="","All_Districts",IFERROR(VLOOKUP(K237,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F238="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 27 of 50 | AF2-LLL-N-027 | Mulakh Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktika | Yousif Khail | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ238="","",AQ238) | 2026-10-30 |  | 2027-01-31 | IF(W238<>"",W238,IF(OR(T238="",V238=""),"",EDATE(T238,V238))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F238="","",IF(COUNT(AI238:AV238)=0,IF(AA238="","Not started",AA238),SUBSTITUTE(LOOKUP(2,1/(AI238:AV238<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F238="",COUNT(AI238:AV238)=0),"",TODAY()-LOOKUP(2,1/(AI238:AV238<>""),AI238:AV238)) | IF(OR(F238="",COUNT(AI238:AV238)<2),"",LOOKUP(2,1/(AI238:AV238<>""),AI238:AV238)-MIN(AI238:AV238)) | IF(OR(AD238="",AC238="Not started",AC238=""),"",IFERROR(AD238-IF(VLOOKUP(AC238,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC238,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F238="","",IF(OR(AA238="Cancelled",AC238="Cancelled"),"Cancelled",IF(OR(AC238="Completed / Handover",Y238<>"",Z238>=100),"Completed — on track",IF(O238="Not awarded",IF(U238="",IF(X238="","No planned date",IF(TODAY()>X238,"Behind — past planned date",IF(X238-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U238,"Behind — award date passed",IF(U238-TODAY()<=30,"At risk — close to off track","On track"))),IF(X238="","No planned date",IF(AND(TODAY()>X238,OR(Z238="",Z238<100)),"Behind — past end date",IF(AND(T238<>"",X238<>"",Z238<>"",(Z238<100),((TODAY()-T238)/MAX(X238-T238,1)*100)-Z238>15),"Behind — progress lag",IF(AND(X238-TODAY()<=30,X238-TODAY()>=0,OR(Z238="",Z238<90)),"At risk — close to off track","On track")))))))) | IF(OR(F238="",AC238="Completed / Handover",AC238="Cancelled"),"",IF(O238="Not awarded",IF(U238<>"",U238-TODAY(),IF(X238="","",X238-TODAY())),IF(X238="","",X238-TODAY()))) | [14 empty] | IF(OR(F238="",AJ238=""),"",IF(COUNT(AI238:AI238)=0,"",AJ238-LOOKUP(2,1/(AI238:AI238<>""),AI238:AI238))) | IF(OR(F238="",AK238=""),"",IF(COUNT(AI238:AJ238)=0,"",AK238-LOOKUP(2,1/(AI238:AJ238<>""),AI238:AJ238))) | IF(OR(F238="",AL238=""),"",IF(COUNT(AI238:AK238)=0,"",AL238-LOOKUP(2,1/(AI238:AK238<>""),AI238:AK238))) | IF(OR(F238="",AM238=""),"",IF(COUNT(AI238:AL238)=0,"",AM238-LOOKUP(2,1/(AI238:AL238<>""),AI238:AL238))) | IF(OR(F238="",AN238=""),"",IF(COUNT(AI238:AM238)=0,"",AN238-LOOKUP(2,1/(AI238:AM238<>""),AI238:AM238))) | IF(OR(F238="",AO238=""),"",IF(COUNT(AI238:AN238)=0,"",AO238-LOOKUP(2,1/(AI238:AN238<>""),AI238:AN238))) | IF(OR(F238="",AP238=""),"",IF(COUNT(AI238:AO238)=0,"",AP238-LOOKUP(2,1/(AI238:AO238<>""),AI238:AO238))) | IF(OR(F238="",AQ238=""),"",IF(COUNT(AI238:AP238)=0,"",AQ238-LOOKUP(2,1/(AI238:AP238<>""),AI238:AP238))) | IF(OR(F238="",AR238=""),"",IF(COUNT(AI238:AQ238)=0,"",AR238-LOOKUP(2,1/(AI238:AQ238<>""),AI238:AQ238))) | IF(OR(F238="",AS238=""),"",IF(COUNT(AI238:AR238)=0,"",AS238-LOOKUP(2,1/(AI238:AR238<>""),AI238:AR238))) | IF(OR(F238="",AT238=""),"",IF(COUNT(AI238:AS238)=0,"",AT238-LOOKUP(2,1/(AI238:AS238<>""),AI238:AS238))) | IF(OR(F238="",AU238=""),"",IF(COUNT(AI238:AT238)=0,"",AU238-LOOKUP(2,1/(AI238:AT238<>""),AI238:AT238))) | IF(OR(F238="",AV238=""),"",IF(COUNT(AI238:AU238)=0,"",AV238-LOOKUP(2,1/(AI238:AU238<>""),AI238:AU238))) | IF(J238="","All_Provinces",IFERROR(VLOOKUP(J238,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K238="","All_Districts",IFERROR(VLOOKUP(K238,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F239="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 28 of 50 | AF2-LLL-N-028 | Mulla Omar irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balklh | Chimtal | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ239="","",AQ239) | 2026-10-30 |  | 2027-01-31 | IF(W239<>"",W239,IF(OR(T239="",V239=""),"",EDATE(T239,V239))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F239="","",IF(COUNT(AI239:AV239)=0,IF(AA239="","Not started",AA239),SUBSTITUTE(LOOKUP(2,1/(AI239:AV239<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F239="",COUNT(AI239:AV239)=0),"",TODAY()-LOOKUP(2,1/(AI239:AV239<>""),AI239:AV239)) | IF(OR(F239="",COUNT(AI239:AV239)<2),"",LOOKUP(2,1/(AI239:AV239<>""),AI239:AV239)-MIN(AI239:AV239)) | IF(OR(AD239="",AC239="Not started",AC239=""),"",IFERROR(AD239-IF(VLOOKUP(AC239,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC239,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F239="","",IF(OR(AA239="Cancelled",AC239="Cancelled"),"Cancelled",IF(OR(AC239="Completed / Handover",Y239<>"",Z239>=100),"Completed — on track",IF(O239="Not awarded",IF(U239="",IF(X239="","No planned date",IF(TODAY()>X239,"Behind — past planned date",IF(X239-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U239,"Behind — award date passed",IF(U239-TODAY()<=30,"At risk — close to off track","On track"))),IF(X239="","No planned date",IF(AND(TODAY()>X239,OR(Z239="",Z239<100)),"Behind — past end date",IF(AND(T239<>"",X239<>"",Z239<>"",(Z239<100),((TODAY()-T239)/MAX(X239-T239,1)*100)-Z239>15),"Behind — progress lag",IF(AND(X239-TODAY()<=30,X239-TODAY()>=0,OR(Z239="",Z239<90)),"At risk — close to off track","On track")))))))) | IF(OR(F239="",AC239="Completed / Handover",AC239="Cancelled"),"",IF(O239="Not awarded",IF(U239<>"",U239-TODAY(),IF(X239="","",X239-TODAY())),IF(X239="","",X239-TODAY()))) | [14 empty] | IF(OR(F239="",AJ239=""),"",IF(COUNT(AI239:AI239)=0,"",AJ239-LOOKUP(2,1/(AI239:AI239<>""),AI239:AI239))) | IF(OR(F239="",AK239=""),"",IF(COUNT(AI239:AJ239)=0,"",AK239-LOOKUP(2,1/(AI239:AJ239<>""),AI239:AJ239))) | IF(OR(F239="",AL239=""),"",IF(COUNT(AI239:AK239)=0,"",AL239-LOOKUP(2,1/(AI239:AK239<>""),AI239:AK239))) | IF(OR(F239="",AM239=""),"",IF(COUNT(AI239:AL239)=0,"",AM239-LOOKUP(2,1/(AI239:AL239<>""),AI239:AL239))) | IF(OR(F239="",AN239=""),"",IF(COUNT(AI239:AM239)=0,"",AN239-LOOKUP(2,1/(AI239:AM239<>""),AI239:AM239))) | IF(OR(F239="",AO239=""),"",IF(COUNT(AI239:AN239)=0,"",AO239-LOOKUP(2,1/(AI239:AN239<>""),AI239:AN239))) | IF(OR(F239="",AP239=""),"",IF(COUNT(AI239:AO239)=0,"",AP239-LOOKUP(2,1/(AI239:AO239<>""),AI239:AO239))) | IF(OR(F239="",AQ239=""),"",IF(COUNT(AI239:AP239)=0,"",AQ239-LOOKUP(2,1/(AI239:AP239<>""),AI239:AP239))) | IF(OR(F239="",AR239=""),"",IF(COUNT(AI239:AQ239)=0,"",AR239-LOOKUP(2,1/(AI239:AQ239<>""),AI239:AQ239))) | IF(OR(F239="",AS239=""),"",IF(COUNT(AI239:AR239)=0,"",AS239-LOOKUP(2,1/(AI239:AR239<>""),AI239:AR239))) | IF(OR(F239="",AT239=""),"",IF(COUNT(AI239:AS239)=0,"",AT239-LOOKUP(2,1/(AI239:AS239<>""),AI239:AS239))) | IF(OR(F239="",AU239=""),"",IF(COUNT(AI239:AT239)=0,"",AU239-LOOKUP(2,1/(AI239:AT239<>""),AI239:AT239))) | IF(OR(F239="",AV239=""),"",IF(COUNT(AI239:AU239)=0,"",AV239-LOOKUP(2,1/(AI239:AU239<>""),AI239:AU239))) | IF(J239="","All_Provinces",IFERROR(VLOOKUP(J239,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K239="","All_Districts",IFERROR(VLOOKUP(K239,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F240="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 29 of 50 | AF2-LLL-N-029 | Nahri Siraj irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helamand | Nahri Siraj | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ240="","",AQ240) | 2026-10-30 |  | 2027-01-31 | IF(W240<>"",W240,IF(OR(T240="",V240=""),"",EDATE(T240,V240))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F240="","",IF(COUNT(AI240:AV240)=0,IF(AA240="","Not started",AA240),SUBSTITUTE(LOOKUP(2,1/(AI240:AV240<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F240="",COUNT(AI240:AV240)=0),"",TODAY()-LOOKUP(2,1/(AI240:AV240<>""),AI240:AV240)) | IF(OR(F240="",COUNT(AI240:AV240)<2),"",LOOKUP(2,1/(AI240:AV240<>""),AI240:AV240)-MIN(AI240:AV240)) | IF(OR(AD240="",AC240="Not started",AC240=""),"",IFERROR(AD240-IF(VLOOKUP(AC240,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC240,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F240="","",IF(OR(AA240="Cancelled",AC240="Cancelled"),"Cancelled",IF(OR(AC240="Completed / Handover",Y240<>"",Z240>=100),"Completed — on track",IF(O240="Not awarded",IF(U240="",IF(X240="","No planned date",IF(TODAY()>X240,"Behind — past planned date",IF(X240-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U240,"Behind — award date passed",IF(U240-TODAY()<=30,"At risk — close to off track","On track"))),IF(X240="","No planned date",IF(AND(TODAY()>X240,OR(Z240="",Z240<100)),"Behind — past end date",IF(AND(T240<>"",X240<>"",Z240<>"",(Z240<100),((TODAY()-T240)/MAX(X240-T240,1)*100)-Z240>15),"Behind — progress lag",IF(AND(X240-TODAY()<=30,X240-TODAY()>=0,OR(Z240="",Z240<90)),"At risk — close to off track","On track")))))))) | IF(OR(F240="",AC240="Completed / Handover",AC240="Cancelled"),"",IF(O240="Not awarded",IF(U240<>"",U240-TODAY(),IF(X240="","",X240-TODAY())),IF(X240="","",X240-TODAY()))) | [14 empty] | IF(OR(F240="",AJ240=""),"",IF(COUNT(AI240:AI240)=0,"",AJ240-LOOKUP(2,1/(AI240:AI240<>""),AI240:AI240))) | IF(OR(F240="",AK240=""),"",IF(COUNT(AI240:AJ240)=0,"",AK240-LOOKUP(2,1/(AI240:AJ240<>""),AI240:AJ240))) | IF(OR(F240="",AL240=""),"",IF(COUNT(AI240:AK240)=0,"",AL240-LOOKUP(2,1/(AI240:AK240<>""),AI240:AK240))) | IF(OR(F240="",AM240=""),"",IF(COUNT(AI240:AL240)=0,"",AM240-LOOKUP(2,1/(AI240:AL240<>""),AI240:AL240))) | IF(OR(F240="",AN240=""),"",IF(COUNT(AI240:AM240)=0,"",AN240-LOOKUP(2,1/(AI240:AM240<>""),AI240:AM240))) | IF(OR(F240="",AO240=""),"",IF(COUNT(AI240:AN240)=0,"",AO240-LOOKUP(2,1/(AI240:AN240<>""),AI240:AN240))) | IF(OR(F240="",AP240=""),"",IF(COUNT(AI240:AO240)=0,"",AP240-LOOKUP(2,1/(AI240:AO240<>""),AI240:AO240))) | IF(OR(F240="",AQ240=""),"",IF(COUNT(AI240:AP240)=0,"",AQ240-LOOKUP(2,1/(AI240:AP240<>""),AI240:AP240))) | IF(OR(F240="",AR240=""),"",IF(COUNT(AI240:AQ240)=0,"",AR240-LOOKUP(2,1/(AI240:AQ240<>""),AI240:AQ240))) | IF(OR(F240="",AS240=""),"",IF(COUNT(AI240:AR240)=0,"",AS240-LOOKUP(2,1/(AI240:AR240<>""),AI240:AR240))) | IF(OR(F240="",AT240=""),"",IF(COUNT(AI240:AS240)=0,"",AT240-LOOKUP(2,1/(AI240:AS240<>""),AI240:AS240))) | IF(OR(F240="",AU240=""),"",IF(COUNT(AI240:AT240)=0,"",AU240-LOOKUP(2,1/(AI240:AT240<>""),AI240:AT240))) | IF(OR(F240="",AV240=""),"",IF(COUNT(AI240:AU240)=0,"",AV240-LOOKUP(2,1/(AI240:AU240<>""),AI240:AU240))) | IF(J240="","All_Provinces",IFERROR(VLOOKUP(J240,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K240="","All_Districts",IFERROR(VLOOKUP(K240,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F241="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 30 of 50 | AF2-LLL-N-030 | Naw Deh Irrigation Canal | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Farah | Farah | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ241="","",AQ241) | 2026-10-30 |  | 2027-01-31 | IF(W241<>"",W241,IF(OR(T241="",V241=""),"",EDATE(T241,V241))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F241="","",IF(COUNT(AI241:AV241)=0,IF(AA241="","Not started",AA241),SUBSTITUTE(LOOKUP(2,1/(AI241:AV241<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F241="",COUNT(AI241:AV241)=0),"",TODAY()-LOOKUP(2,1/(AI241:AV241<>""),AI241:AV241)) | IF(OR(F241="",COUNT(AI241:AV241)<2),"",LOOKUP(2,1/(AI241:AV241<>""),AI241:AV241)-MIN(AI241:AV241)) | IF(OR(AD241="",AC241="Not started",AC241=""),"",IFERROR(AD241-IF(VLOOKUP(AC241,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC241,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F241="","",IF(OR(AA241="Cancelled",AC241="Cancelled"),"Cancelled",IF(OR(AC241="Completed / Handover",Y241<>"",Z241>=100),"Completed — on track",IF(O241="Not awarded",IF(U241="",IF(X241="","No planned date",IF(TODAY()>X241,"Behind — past planned date",IF(X241-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U241,"Behind — award date passed",IF(U241-TODAY()<=30,"At risk — close to off track","On track"))),IF(X241="","No planned date",IF(AND(TODAY()>X241,OR(Z241="",Z241<100)),"Behind — past end date",IF(AND(T241<>"",X241<>"",Z241<>"",(Z241<100),((TODAY()-T241)/MAX(X241-T241,1)*100)-Z241>15),"Behind — progress lag",IF(AND(X241-TODAY()<=30,X241-TODAY()>=0,OR(Z241="",Z241<90)),"At risk — close to off track","On track")))))))) | IF(OR(F241="",AC241="Completed / Handover",AC241="Cancelled"),"",IF(O241="Not awarded",IF(U241<>"",U241-TODAY(),IF(X241="","",X241-TODAY())),IF(X241="","",X241-TODAY()))) | [14 empty] | IF(OR(F241="",AJ241=""),"",IF(COUNT(AI241:AI241)=0,"",AJ241-LOOKUP(2,1/(AI241:AI241<>""),AI241:AI241))) | IF(OR(F241="",AK241=""),"",IF(COUNT(AI241:AJ241)=0,"",AK241-LOOKUP(2,1/(AI241:AJ241<>""),AI241:AJ241))) | IF(OR(F241="",AL241=""),"",IF(COUNT(AI241:AK241)=0,"",AL241-LOOKUP(2,1/(AI241:AK241<>""),AI241:AK241))) | IF(OR(F241="",AM241=""),"",IF(COUNT(AI241:AL241)=0,"",AM241-LOOKUP(2,1/(AI241:AL241<>""),AI241:AL241))) | IF(OR(F241="",AN241=""),"",IF(COUNT(AI241:AM241)=0,"",AN241-LOOKUP(2,1/(AI241:AM241<>""),AI241:AM241))) | IF(OR(F241="",AO241=""),"",IF(COUNT(AI241:AN241)=0,"",AO241-LOOKUP(2,1/(AI241:AN241<>""),AI241:AN241))) | IF(OR(F241="",AP241=""),"",IF(COUNT(AI241:AO241)=0,"",AP241-LOOKUP(2,1/(AI241:AO241<>""),AI241:AO241))) | IF(OR(F241="",AQ241=""),"",IF(COUNT(AI241:AP241)=0,"",AQ241-LOOKUP(2,1/(AI241:AP241<>""),AI241:AP241))) | IF(OR(F241="",AR241=""),"",IF(COUNT(AI241:AQ241)=0,"",AR241-LOOKUP(2,1/(AI241:AQ241<>""),AI241:AQ241))) | IF(OR(F241="",AS241=""),"",IF(COUNT(AI241:AR241)=0,"",AS241-LOOKUP(2,1/(AI241:AR241<>""),AI241:AR241))) | IF(OR(F241="",AT241=""),"",IF(COUNT(AI241:AS241)=0,"",AT241-LOOKUP(2,1/(AI241:AS241<>""),AI241:AS241))) | IF(OR(F241="",AU241=""),"",IF(COUNT(AI241:AT241)=0,"",AU241-LOOKUP(2,1/(AI241:AT241<>""),AI241:AT241))) | IF(OR(F241="",AV241=""),"",IF(COUNT(AI241:AU241)=0,"",AV241-LOOKUP(2,1/(AI241:AU241<>""),AI241:AU241))) | IF(J241="","All_Provinces",IFERROR(VLOOKUP(J241,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K241="","All_Districts",IFERROR(VLOOKUP(K241,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F242="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 31 of 50 | AF2-LLL-N-031 | Noghi Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Ghazni | Ghazni | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ242="","",AQ242) | 2026-10-30 |  | 2027-01-31 | IF(W242<>"",W242,IF(OR(T242="",V242=""),"",EDATE(T242,V242))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F242="","",IF(COUNT(AI242:AV242)=0,IF(AA242="","Not started",AA242),SUBSTITUTE(LOOKUP(2,1/(AI242:AV242<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F242="",COUNT(AI242:AV242)=0),"",TODAY()-LOOKUP(2,1/(AI242:AV242<>""),AI242:AV242)) | IF(OR(F242="",COUNT(AI242:AV242)<2),"",LOOKUP(2,1/(AI242:AV242<>""),AI242:AV242)-MIN(AI242:AV242)) | IF(OR(AD242="",AC242="Not started",AC242=""),"",IFERROR(AD242-IF(VLOOKUP(AC242,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC242,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F242="","",IF(OR(AA242="Cancelled",AC242="Cancelled"),"Cancelled",IF(OR(AC242="Completed / Handover",Y242<>"",Z242>=100),"Completed — on track",IF(O242="Not awarded",IF(U242="",IF(X242="","No planned date",IF(TODAY()>X242,"Behind — past planned date",IF(X242-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U242,"Behind — award date passed",IF(U242-TODAY()<=30,"At risk — close to off track","On track"))),IF(X242="","No planned date",IF(AND(TODAY()>X242,OR(Z242="",Z242<100)),"Behind — past end date",IF(AND(T242<>"",X242<>"",Z242<>"",(Z242<100),((TODAY()-T242)/MAX(X242-T242,1)*100)-Z242>15),"Behind — progress lag",IF(AND(X242-TODAY()<=30,X242-TODAY()>=0,OR(Z242="",Z242<90)),"At risk — close to off track","On track")))))))) | IF(OR(F242="",AC242="Completed / Handover",AC242="Cancelled"),"",IF(O242="Not awarded",IF(U242<>"",U242-TODAY(),IF(X242="","",X242-TODAY())),IF(X242="","",X242-TODAY()))) | [14 empty] | IF(OR(F242="",AJ242=""),"",IF(COUNT(AI242:AI242)=0,"",AJ242-LOOKUP(2,1/(AI242:AI242<>""),AI242:AI242))) | IF(OR(F242="",AK242=""),"",IF(COUNT(AI242:AJ242)=0,"",AK242-LOOKUP(2,1/(AI242:AJ242<>""),AI242:AJ242))) | IF(OR(F242="",AL242=""),"",IF(COUNT(AI242:AK242)=0,"",AL242-LOOKUP(2,1/(AI242:AK242<>""),AI242:AK242))) | IF(OR(F242="",AM242=""),"",IF(COUNT(AI242:AL242)=0,"",AM242-LOOKUP(2,1/(AI242:AL242<>""),AI242:AL242))) | IF(OR(F242="",AN242=""),"",IF(COUNT(AI242:AM242)=0,"",AN242-LOOKUP(2,1/(AI242:AM242<>""),AI242:AM242))) | IF(OR(F242="",AO242=""),"",IF(COUNT(AI242:AN242)=0,"",AO242-LOOKUP(2,1/(AI242:AN242<>""),AI242:AN242))) | IF(OR(F242="",AP242=""),"",IF(COUNT(AI242:AO242)=0,"",AP242-LOOKUP(2,1/(AI242:AO242<>""),AI242:AO242))) | IF(OR(F242="",AQ242=""),"",IF(COUNT(AI242:AP242)=0,"",AQ242-LOOKUP(2,1/(AI242:AP242<>""),AI242:AP242))) | IF(OR(F242="",AR242=""),"",IF(COUNT(AI242:AQ242)=0,"",AR242-LOOKUP(2,1/(AI242:AQ242<>""),AI242:AQ242))) | IF(OR(F242="",AS242=""),"",IF(COUNT(AI242:AR242)=0,"",AS242-LOOKUP(2,1/(AI242:AR242<>""),AI242:AR242))) | IF(OR(F242="",AT242=""),"",IF(COUNT(AI242:AS242)=0,"",AT242-LOOKUP(2,1/(AI242:AS242<>""),AI242:AS242))) | IF(OR(F242="",AU242=""),"",IF(COUNT(AI242:AT242)=0,"",AU242-LOOKUP(2,1/(AI242:AT242<>""),AI242:AT242))) | IF(OR(F242="",AV242=""),"",IF(COUNT(AI242:AU242)=0,"",AV242-LOOKUP(2,1/(AI242:AU242<>""),AI242:AU242))) | IF(J242="","All_Provinces",IFERROR(VLOOKUP(J242,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K242="","All_Districts",IFERROR(VLOOKUP(K242,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F243="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 32 of 50 | AF2-LLL-N-032 | Pachajoy irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Laghman | Mehtherlam | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ243="","",AQ243) | 2026-10-30 |  | 2027-01-31 | IF(W243<>"",W243,IF(OR(T243="",V243=""),"",EDATE(T243,V243))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F243="","",IF(COUNT(AI243:AV243)=0,IF(AA243="","Not started",AA243),SUBSTITUTE(LOOKUP(2,1/(AI243:AV243<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F243="",COUNT(AI243:AV243)=0),"",TODAY()-LOOKUP(2,1/(AI243:AV243<>""),AI243:AV243)) | IF(OR(F243="",COUNT(AI243:AV243)<2),"",LOOKUP(2,1/(AI243:AV243<>""),AI243:AV243)-MIN(AI243:AV243)) | IF(OR(AD243="",AC243="Not started",AC243=""),"",IFERROR(AD243-IF(VLOOKUP(AC243,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC243,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F243="","",IF(OR(AA243="Cancelled",AC243="Cancelled"),"Cancelled",IF(OR(AC243="Completed / Handover",Y243<>"",Z243>=100),"Completed — on track",IF(O243="Not awarded",IF(U243="",IF(X243="","No planned date",IF(TODAY()>X243,"Behind — past planned date",IF(X243-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U243,"Behind — award date passed",IF(U243-TODAY()<=30,"At risk — close to off track","On track"))),IF(X243="","No planned date",IF(AND(TODAY()>X243,OR(Z243="",Z243<100)),"Behind — past end date",IF(AND(T243<>"",X243<>"",Z243<>"",(Z243<100),((TODAY()-T243)/MAX(X243-T243,1)*100)-Z243>15),"Behind — progress lag",IF(AND(X243-TODAY()<=30,X243-TODAY()>=0,OR(Z243="",Z243<90)),"At risk — close to off track","On track")))))))) | IF(OR(F243="",AC243="Completed / Handover",AC243="Cancelled"),"",IF(O243="Not awarded",IF(U243<>"",U243-TODAY(),IF(X243="","",X243-TODAY())),IF(X243="","",X243-TODAY()))) | [14 empty] | IF(OR(F243="",AJ243=""),"",IF(COUNT(AI243:AI243)=0,"",AJ243-LOOKUP(2,1/(AI243:AI243<>""),AI243:AI243))) | IF(OR(F243="",AK243=""),"",IF(COUNT(AI243:AJ243)=0,"",AK243-LOOKUP(2,1/(AI243:AJ243<>""),AI243:AJ243))) | IF(OR(F243="",AL243=""),"",IF(COUNT(AI243:AK243)=0,"",AL243-LOOKUP(2,1/(AI243:AK243<>""),AI243:AK243))) | IF(OR(F243="",AM243=""),"",IF(COUNT(AI243:AL243)=0,"",AM243-LOOKUP(2,1/(AI243:AL243<>""),AI243:AL243))) | IF(OR(F243="",AN243=""),"",IF(COUNT(AI243:AM243)=0,"",AN243-LOOKUP(2,1/(AI243:AM243<>""),AI243:AM243))) | IF(OR(F243="",AO243=""),"",IF(COUNT(AI243:AN243)=0,"",AO243-LOOKUP(2,1/(AI243:AN243<>""),AI243:AN243))) | IF(OR(F243="",AP243=""),"",IF(COUNT(AI243:AO243)=0,"",AP243-LOOKUP(2,1/(AI243:AO243<>""),AI243:AO243))) | IF(OR(F243="",AQ243=""),"",IF(COUNT(AI243:AP243)=0,"",AQ243-LOOKUP(2,1/(AI243:AP243<>""),AI243:AP243))) | IF(OR(F243="",AR243=""),"",IF(COUNT(AI243:AQ243)=0,"",AR243-LOOKUP(2,1/(AI243:AQ243<>""),AI243:AQ243))) | IF(OR(F243="",AS243=""),"",IF(COUNT(AI243:AR243)=0,"",AS243-LOOKUP(2,1/(AI243:AR243<>""),AI243:AR243))) | IF(OR(F243="",AT243=""),"",IF(COUNT(AI243:AS243)=0,"",AT243-LOOKUP(2,1/(AI243:AS243<>""),AI243:AS243))) | IF(OR(F243="",AU243=""),"",IF(COUNT(AI243:AT243)=0,"",AU243-LOOKUP(2,1/(AI243:AT243<>""),AI243:AT243))) | IF(OR(F243="",AV243=""),"",IF(COUNT(AI243:AU243)=0,"",AV243-LOOKUP(2,1/(AI243:AU243<>""),AI243:AU243))) | IF(J243="","All_Provinces",IFERROR(VLOOKUP(J243,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K243="","All_Districts",IFERROR(VLOOKUP(K243,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F244="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 33 of 50 | AF2-LLL-N-033 | Patab irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Urozgan | Khas Urozgan | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ244="","",AQ244) | 2026-10-30 |  | 2027-01-31 | IF(W244<>"",W244,IF(OR(T244="",V244=""),"",EDATE(T244,V244))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F244="","",IF(COUNT(AI244:AV244)=0,IF(AA244="","Not started",AA244),SUBSTITUTE(LOOKUP(2,1/(AI244:AV244<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F244="",COUNT(AI244:AV244)=0),"",TODAY()-LOOKUP(2,1/(AI244:AV244<>""),AI244:AV244)) | IF(OR(F244="",COUNT(AI244:AV244)<2),"",LOOKUP(2,1/(AI244:AV244<>""),AI244:AV244)-MIN(AI244:AV244)) | IF(OR(AD244="",AC244="Not started",AC244=""),"",IFERROR(AD244-IF(VLOOKUP(AC244,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC244,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F244="","",IF(OR(AA244="Cancelled",AC244="Cancelled"),"Cancelled",IF(OR(AC244="Completed / Handover",Y244<>"",Z244>=100),"Completed — on track",IF(O244="Not awarded",IF(U244="",IF(X244="","No planned date",IF(TODAY()>X244,"Behind — past planned date",IF(X244-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U244,"Behind — award date passed",IF(U244-TODAY()<=30,"At risk — close to off track","On track"))),IF(X244="","No planned date",IF(AND(TODAY()>X244,OR(Z244="",Z244<100)),"Behind — past end date",IF(AND(T244<>"",X244<>"",Z244<>"",(Z244<100),((TODAY()-T244)/MAX(X244-T244,1)*100)-Z244>15),"Behind — progress lag",IF(AND(X244-TODAY()<=30,X244-TODAY()>=0,OR(Z244="",Z244<90)),"At risk — close to off track","On track")))))))) | IF(OR(F244="",AC244="Completed / Handover",AC244="Cancelled"),"",IF(O244="Not awarded",IF(U244<>"",U244-TODAY(),IF(X244="","",X244-TODAY())),IF(X244="","",X244-TODAY()))) | [14 empty] | IF(OR(F244="",AJ244=""),"",IF(COUNT(AI244:AI244)=0,"",AJ244-LOOKUP(2,1/(AI244:AI244<>""),AI244:AI244))) | IF(OR(F244="",AK244=""),"",IF(COUNT(AI244:AJ244)=0,"",AK244-LOOKUP(2,1/(AI244:AJ244<>""),AI244:AJ244))) | IF(OR(F244="",AL244=""),"",IF(COUNT(AI244:AK244)=0,"",AL244-LOOKUP(2,1/(AI244:AK244<>""),AI244:AK244))) | IF(OR(F244="",AM244=""),"",IF(COUNT(AI244:AL244)=0,"",AM244-LOOKUP(2,1/(AI244:AL244<>""),AI244:AL244))) | IF(OR(F244="",AN244=""),"",IF(COUNT(AI244:AM244)=0,"",AN244-LOOKUP(2,1/(AI244:AM244<>""),AI244:AM244))) | IF(OR(F244="",AO244=""),"",IF(COUNT(AI244:AN244)=0,"",AO244-LOOKUP(2,1/(AI244:AN244<>""),AI244:AN244))) | IF(OR(F244="",AP244=""),"",IF(COUNT(AI244:AO244)=0,"",AP244-LOOKUP(2,1/(AI244:AO244<>""),AI244:AO244))) | IF(OR(F244="",AQ244=""),"",IF(COUNT(AI244:AP244)=0,"",AQ244-LOOKUP(2,1/(AI244:AP244<>""),AI244:AP244))) | IF(OR(F244="",AR244=""),"",IF(COUNT(AI244:AQ244)=0,"",AR244-LOOKUP(2,1/(AI244:AQ244<>""),AI244:AQ244))) | IF(OR(F244="",AS244=""),"",IF(COUNT(AI244:AR244)=0,"",AS244-LOOKUP(2,1/(AI244:AR244<>""),AI244:AR244))) | IF(OR(F244="",AT244=""),"",IF(COUNT(AI244:AS244)=0,"",AT244-LOOKUP(2,1/(AI244:AS244<>""),AI244:AS244))) | IF(OR(F244="",AU244=""),"",IF(COUNT(AI244:AT244)=0,"",AU244-LOOKUP(2,1/(AI244:AT244<>""),AI244:AT244))) | IF(OR(F244="",AV244=""),"",IF(COUNT(AI244:AU244)=0,"",AV244-LOOKUP(2,1/(AI244:AU244<>""),AI244:AU244))) | IF(J244="","All_Provinces",IFERROR(VLOOKUP(J244,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K244="","All_Districts",IFERROR(VLOOKUP(K244,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F245="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 34 of 50 | AF2-LLL-N-034 | Patikharkay irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Khogiani | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ245="","",AQ245) | 2026-10-30 |  | 2027-01-31 | IF(W245<>"",W245,IF(OR(T245="",V245=""),"",EDATE(T245,V245))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F245="","",IF(COUNT(AI245:AV245)=0,IF(AA245="","Not started",AA245),SUBSTITUTE(LOOKUP(2,1/(AI245:AV245<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F245="",COUNT(AI245:AV245)=0),"",TODAY()-LOOKUP(2,1/(AI245:AV245<>""),AI245:AV245)) | IF(OR(F245="",COUNT(AI245:AV245)<2),"",LOOKUP(2,1/(AI245:AV245<>""),AI245:AV245)-MIN(AI245:AV245)) | IF(OR(AD245="",AC245="Not started",AC245=""),"",IFERROR(AD245-IF(VLOOKUP(AC245,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC245,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F245="","",IF(OR(AA245="Cancelled",AC245="Cancelled"),"Cancelled",IF(OR(AC245="Completed / Handover",Y245<>"",Z245>=100),"Completed — on track",IF(O245="Not awarded",IF(U245="",IF(X245="","No planned date",IF(TODAY()>X245,"Behind — past planned date",IF(X245-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U245,"Behind — award date passed",IF(U245-TODAY()<=30,"At risk — close to off track","On track"))),IF(X245="","No planned date",IF(AND(TODAY()>X245,OR(Z245="",Z245<100)),"Behind — past end date",IF(AND(T245<>"",X245<>"",Z245<>"",(Z245<100),((TODAY()-T245)/MAX(X245-T245,1)*100)-Z245>15),"Behind — progress lag",IF(AND(X245-TODAY()<=30,X245-TODAY()>=0,OR(Z245="",Z245<90)),"At risk — close to off track","On track")))))))) | IF(OR(F245="",AC245="Completed / Handover",AC245="Cancelled"),"",IF(O245="Not awarded",IF(U245<>"",U245-TODAY(),IF(X245="","",X245-TODAY())),IF(X245="","",X245-TODAY()))) | [14 empty] | IF(OR(F245="",AJ245=""),"",IF(COUNT(AI245:AI245)=0,"",AJ245-LOOKUP(2,1/(AI245:AI245<>""),AI245:AI245))) | IF(OR(F245="",AK245=""),"",IF(COUNT(AI245:AJ245)=0,"",AK245-LOOKUP(2,1/(AI245:AJ245<>""),AI245:AJ245))) | IF(OR(F245="",AL245=""),"",IF(COUNT(AI245:AK245)=0,"",AL245-LOOKUP(2,1/(AI245:AK245<>""),AI245:AK245))) | IF(OR(F245="",AM245=""),"",IF(COUNT(AI245:AL245)=0,"",AM245-LOOKUP(2,1/(AI245:AL245<>""),AI245:AL245))) | IF(OR(F245="",AN245=""),"",IF(COUNT(AI245:AM245)=0,"",AN245-LOOKUP(2,1/(AI245:AM245<>""),AI245:AM245))) | IF(OR(F245="",AO245=""),"",IF(COUNT(AI245:AN245)=0,"",AO245-LOOKUP(2,1/(AI245:AN245<>""),AI245:AN245))) | IF(OR(F245="",AP245=""),"",IF(COUNT(AI245:AO245)=0,"",AP245-LOOKUP(2,1/(AI245:AO245<>""),AI245:AO245))) | IF(OR(F245="",AQ245=""),"",IF(COUNT(AI245:AP245)=0,"",AQ245-LOOKUP(2,1/(AI245:AP245<>""),AI245:AP245))) | IF(OR(F245="",AR245=""),"",IF(COUNT(AI245:AQ245)=0,"",AR245-LOOKUP(2,1/(AI245:AQ245<>""),AI245:AQ245))) | IF(OR(F245="",AS245=""),"",IF(COUNT(AI245:AR245)=0,"",AS245-LOOKUP(2,1/(AI245:AR245<>""),AI245:AR245))) | IF(OR(F245="",AT245=""),"",IF(COUNT(AI245:AS245)=0,"",AT245-LOOKUP(2,1/(AI245:AS245<>""),AI245:AS245))) | IF(OR(F245="",AU245=""),"",IF(COUNT(AI245:AT245)=0,"",AU245-LOOKUP(2,1/(AI245:AT245<>""),AI245:AT245))) | IF(OR(F245="",AV245=""),"",IF(COUNT(AI245:AU245)=0,"",AV245-LOOKUP(2,1/(AI245:AU245<>""),AI245:AU245))) | IF(J245="","All_Provinces",IFERROR(VLOOKUP(J245,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K245="","All_Districts",IFERROR(VLOOKUP(K245,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F246="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 35 of 50 | AF2-LLL-N-035 | Qala-E-Wazir Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Logar | Qala-E-Wazir | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ246="","",AQ246) | 2026-10-30 |  | 2027-01-31 | IF(W246<>"",W246,IF(OR(T246="",V246=""),"",EDATE(T246,V246))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F246="","",IF(COUNT(AI246:AV246)=0,IF(AA246="","Not started",AA246),SUBSTITUTE(LOOKUP(2,1/(AI246:AV246<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F246="",COUNT(AI246:AV246)=0),"",TODAY()-LOOKUP(2,1/(AI246:AV246<>""),AI246:AV246)) | IF(OR(F246="",COUNT(AI246:AV246)<2),"",LOOKUP(2,1/(AI246:AV246<>""),AI246:AV246)-MIN(AI246:AV246)) | IF(OR(AD246="",AC246="Not started",AC246=""),"",IFERROR(AD246-IF(VLOOKUP(AC246,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC246,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F246="","",IF(OR(AA246="Cancelled",AC246="Cancelled"),"Cancelled",IF(OR(AC246="Completed / Handover",Y246<>"",Z246>=100),"Completed — on track",IF(O246="Not awarded",IF(U246="",IF(X246="","No planned date",IF(TODAY()>X246,"Behind — past planned date",IF(X246-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U246,"Behind — award date passed",IF(U246-TODAY()<=30,"At risk — close to off track","On track"))),IF(X246="","No planned date",IF(AND(TODAY()>X246,OR(Z246="",Z246<100)),"Behind — past end date",IF(AND(T246<>"",X246<>"",Z246<>"",(Z246<100),((TODAY()-T246)/MAX(X246-T246,1)*100)-Z246>15),"Behind — progress lag",IF(AND(X246-TODAY()<=30,X246-TODAY()>=0,OR(Z246="",Z246<90)),"At risk — close to off track","On track")))))))) | IF(OR(F246="",AC246="Completed / Handover",AC246="Cancelled"),"",IF(O246="Not awarded",IF(U246<>"",U246-TODAY(),IF(X246="","",X246-TODAY())),IF(X246="","",X246-TODAY()))) | [14 empty] | IF(OR(F246="",AJ246=""),"",IF(COUNT(AI246:AI246)=0,"",AJ246-LOOKUP(2,1/(AI246:AI246<>""),AI246:AI246))) | IF(OR(F246="",AK246=""),"",IF(COUNT(AI246:AJ246)=0,"",AK246-LOOKUP(2,1/(AI246:AJ246<>""),AI246:AJ246))) | IF(OR(F246="",AL246=""),"",IF(COUNT(AI246:AK246)=0,"",AL246-LOOKUP(2,1/(AI246:AK246<>""),AI246:AK246))) | IF(OR(F246="",AM246=""),"",IF(COUNT(AI246:AL246)=0,"",AM246-LOOKUP(2,1/(AI246:AL246<>""),AI246:AL246))) | IF(OR(F246="",AN246=""),"",IF(COUNT(AI246:AM246)=0,"",AN246-LOOKUP(2,1/(AI246:AM246<>""),AI246:AM246))) | IF(OR(F246="",AO246=""),"",IF(COUNT(AI246:AN246)=0,"",AO246-LOOKUP(2,1/(AI246:AN246<>""),AI246:AN246))) | IF(OR(F246="",AP246=""),"",IF(COUNT(AI246:AO246)=0,"",AP246-LOOKUP(2,1/(AI246:AO246<>""),AI246:AO246))) | IF(OR(F246="",AQ246=""),"",IF(COUNT(AI246:AP246)=0,"",AQ246-LOOKUP(2,1/(AI246:AP246<>""),AI246:AP246))) | IF(OR(F246="",AR246=""),"",IF(COUNT(AI246:AQ246)=0,"",AR246-LOOKUP(2,1/(AI246:AQ246<>""),AI246:AQ246))) | IF(OR(F246="",AS246=""),"",IF(COUNT(AI246:AR246)=0,"",AS246-LOOKUP(2,1/(AI246:AR246<>""),AI246:AR246))) | IF(OR(F246="",AT246=""),"",IF(COUNT(AI246:AS246)=0,"",AT246-LOOKUP(2,1/(AI246:AS246<>""),AI246:AS246))) | IF(OR(F246="",AU246=""),"",IF(COUNT(AI246:AT246)=0,"",AU246-LOOKUP(2,1/(AI246:AT246<>""),AI246:AT246))) | IF(OR(F246="",AV246=""),"",IF(COUNT(AI246:AU246)=0,"",AV246-LOOKUP(2,1/(AI246:AU246<>""),AI246:AU246))) | IF(J246="","All_Provinces",IFERROR(VLOOKUP(J246,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K246="","All_Districts",IFERROR(VLOOKUP(K246,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F247="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 36 of 50 | AF2-LLL-N-036 | Qala-e-Ahmad Big Canal | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Nijrab | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ247="","",AQ247) | 2026-10-30 |  | 2027-01-31 | IF(W247<>"",W247,IF(OR(T247="",V247=""),"",EDATE(T247,V247))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F247="","",IF(COUNT(AI247:AV247)=0,IF(AA247="","Not started",AA247),SUBSTITUTE(LOOKUP(2,1/(AI247:AV247<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F247="",COUNT(AI247:AV247)=0),"",TODAY()-LOOKUP(2,1/(AI247:AV247<>""),AI247:AV247)) | IF(OR(F247="",COUNT(AI247:AV247)<2),"",LOOKUP(2,1/(AI247:AV247<>""),AI247:AV247)-MIN(AI247:AV247)) | IF(OR(AD247="",AC247="Not started",AC247=""),"",IFERROR(AD247-IF(VLOOKUP(AC247,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC247,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F247="","",IF(OR(AA247="Cancelled",AC247="Cancelled"),"Cancelled",IF(OR(AC247="Completed / Handover",Y247<>"",Z247>=100),"Completed — on track",IF(O247="Not awarded",IF(U247="",IF(X247="","No planned date",IF(TODAY()>X247,"Behind — past planned date",IF(X247-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U247,"Behind — award date passed",IF(U247-TODAY()<=30,"At risk — close to off track","On track"))),IF(X247="","No planned date",IF(AND(TODAY()>X247,OR(Z247="",Z247<100)),"Behind — past end date",IF(AND(T247<>"",X247<>"",Z247<>"",(Z247<100),((TODAY()-T247)/MAX(X247-T247,1)*100)-Z247>15),"Behind — progress lag",IF(AND(X247-TODAY()<=30,X247-TODAY()>=0,OR(Z247="",Z247<90)),"At risk — close to off track","On track")))))))) | IF(OR(F247="",AC247="Completed / Handover",AC247="Cancelled"),"",IF(O247="Not awarded",IF(U247<>"",U247-TODAY(),IF(X247="","",X247-TODAY())),IF(X247="","",X247-TODAY()))) | [14 empty] | IF(OR(F247="",AJ247=""),"",IF(COUNT(AI247:AI247)=0,"",AJ247-LOOKUP(2,1/(AI247:AI247<>""),AI247:AI247))) | IF(OR(F247="",AK247=""),"",IF(COUNT(AI247:AJ247)=0,"",AK247-LOOKUP(2,1/(AI247:AJ247<>""),AI247:AJ247))) | IF(OR(F247="",AL247=""),"",IF(COUNT(AI247:AK247)=0,"",AL247-LOOKUP(2,1/(AI247:AK247<>""),AI247:AK247))) | IF(OR(F247="",AM247=""),"",IF(COUNT(AI247:AL247)=0,"",AM247-LOOKUP(2,1/(AI247:AL247<>""),AI247:AL247))) | IF(OR(F247="",AN247=""),"",IF(COUNT(AI247:AM247)=0,"",AN247-LOOKUP(2,1/(AI247:AM247<>""),AI247:AM247))) | IF(OR(F247="",AO247=""),"",IF(COUNT(AI247:AN247)=0,"",AO247-LOOKUP(2,1/(AI247:AN247<>""),AI247:AN247))) | IF(OR(F247="",AP247=""),"",IF(COUNT(AI247:AO247)=0,"",AP247-LOOKUP(2,1/(AI247:AO247<>""),AI247:AO247))) | IF(OR(F247="",AQ247=""),"",IF(COUNT(AI247:AP247)=0,"",AQ247-LOOKUP(2,1/(AI247:AP247<>""),AI247:AP247))) | IF(OR(F247="",AR247=""),"",IF(COUNT(AI247:AQ247)=0,"",AR247-LOOKUP(2,1/(AI247:AQ247<>""),AI247:AQ247))) | IF(OR(F247="",AS247=""),"",IF(COUNT(AI247:AR247)=0,"",AS247-LOOKUP(2,1/(AI247:AR247<>""),AI247:AR247))) | IF(OR(F247="",AT247=""),"",IF(COUNT(AI247:AS247)=0,"",AT247-LOOKUP(2,1/(AI247:AS247<>""),AI247:AS247))) | IF(OR(F247="",AU247=""),"",IF(COUNT(AI247:AT247)=0,"",AU247-LOOKUP(2,1/(AI247:AT247<>""),AI247:AT247))) | IF(OR(F247="",AV247=""),"",IF(COUNT(AI247:AU247)=0,"",AV247-LOOKUP(2,1/(AI247:AU247<>""),AI247:AU247))) | IF(J247="","All_Provinces",IFERROR(VLOOKUP(J247,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K247="","All_Districts",IFERROR(VLOOKUP(K247,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F248="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 37 of 50 | AF2-LLL-N-037 | Qashqasai Canal Irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Faryab | Qaisar | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ248="","",AQ248) | 2026-10-30 |  | 2027-01-31 | IF(W248<>"",W248,IF(OR(T248="",V248=""),"",EDATE(T248,V248))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F248="","",IF(COUNT(AI248:AV248)=0,IF(AA248="","Not started",AA248),SUBSTITUTE(LOOKUP(2,1/(AI248:AV248<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F248="",COUNT(AI248:AV248)=0),"",TODAY()-LOOKUP(2,1/(AI248:AV248<>""),AI248:AV248)) | IF(OR(F248="",COUNT(AI248:AV248)<2),"",LOOKUP(2,1/(AI248:AV248<>""),AI248:AV248)-MIN(AI248:AV248)) | IF(OR(AD248="",AC248="Not started",AC248=""),"",IFERROR(AD248-IF(VLOOKUP(AC248,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC248,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F248="","",IF(OR(AA248="Cancelled",AC248="Cancelled"),"Cancelled",IF(OR(AC248="Completed / Handover",Y248<>"",Z248>=100),"Completed — on track",IF(O248="Not awarded",IF(U248="",IF(X248="","No planned date",IF(TODAY()>X248,"Behind — past planned date",IF(X248-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U248,"Behind — award date passed",IF(U248-TODAY()<=30,"At risk — close to off track","On track"))),IF(X248="","No planned date",IF(AND(TODAY()>X248,OR(Z248="",Z248<100)),"Behind — past end date",IF(AND(T248<>"",X248<>"",Z248<>"",(Z248<100),((TODAY()-T248)/MAX(X248-T248,1)*100)-Z248>15),"Behind — progress lag",IF(AND(X248-TODAY()<=30,X248-TODAY()>=0,OR(Z248="",Z248<90)),"At risk — close to off track","On track")))))))) | IF(OR(F248="",AC248="Completed / Handover",AC248="Cancelled"),"",IF(O248="Not awarded",IF(U248<>"",U248-TODAY(),IF(X248="","",X248-TODAY())),IF(X248="","",X248-TODAY()))) | [14 empty] | IF(OR(F248="",AJ248=""),"",IF(COUNT(AI248:AI248)=0,"",AJ248-LOOKUP(2,1/(AI248:AI248<>""),AI248:AI248))) | IF(OR(F248="",AK248=""),"",IF(COUNT(AI248:AJ248)=0,"",AK248-LOOKUP(2,1/(AI248:AJ248<>""),AI248:AJ248))) | IF(OR(F248="",AL248=""),"",IF(COUNT(AI248:AK248)=0,"",AL248-LOOKUP(2,1/(AI248:AK248<>""),AI248:AK248))) | IF(OR(F248="",AM248=""),"",IF(COUNT(AI248:AL248)=0,"",AM248-LOOKUP(2,1/(AI248:AL248<>""),AI248:AL248))) | IF(OR(F248="",AN248=""),"",IF(COUNT(AI248:AM248)=0,"",AN248-LOOKUP(2,1/(AI248:AM248<>""),AI248:AM248))) | IF(OR(F248="",AO248=""),"",IF(COUNT(AI248:AN248)=0,"",AO248-LOOKUP(2,1/(AI248:AN248<>""),AI248:AN248))) | IF(OR(F248="",AP248=""),"",IF(COUNT(AI248:AO248)=0,"",AP248-LOOKUP(2,1/(AI248:AO248<>""),AI248:AO248))) | IF(OR(F248="",AQ248=""),"",IF(COUNT(AI248:AP248)=0,"",AQ248-LOOKUP(2,1/(AI248:AP248<>""),AI248:AP248))) | IF(OR(F248="",AR248=""),"",IF(COUNT(AI248:AQ248)=0,"",AR248-LOOKUP(2,1/(AI248:AQ248<>""),AI248:AQ248))) | IF(OR(F248="",AS248=""),"",IF(COUNT(AI248:AR248)=0,"",AS248-LOOKUP(2,1/(AI248:AR248<>""),AI248:AR248))) | IF(OR(F248="",AT248=""),"",IF(COUNT(AI248:AS248)=0,"",AT248-LOOKUP(2,1/(AI248:AS248<>""),AI248:AS248))) | IF(OR(F248="",AU248=""),"",IF(COUNT(AI248:AT248)=0,"",AU248-LOOKUP(2,1/(AI248:AT248<>""),AI248:AT248))) | IF(OR(F248="",AV248=""),"",IF(COUNT(AI248:AU248)=0,"",AV248-LOOKUP(2,1/(AI248:AU248<>""),AI248:AU248))) | IF(J248="","All_Provinces",IFERROR(VLOOKUP(J248,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K248="","All_Districts",IFERROR(VLOOKUP(K248,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F249="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 38 of 50 | AF2-LLL-N-038 | Sang Bast Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Zinda Jan | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ249="","",AQ249) | 2026-10-30 |  | 2027-01-31 | IF(W249<>"",W249,IF(OR(T249="",V249=""),"",EDATE(T249,V249))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F249="","",IF(COUNT(AI249:AV249)=0,IF(AA249="","Not started",AA249),SUBSTITUTE(LOOKUP(2,1/(AI249:AV249<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F249="",COUNT(AI249:AV249)=0),"",TODAY()-LOOKUP(2,1/(AI249:AV249<>""),AI249:AV249)) | IF(OR(F249="",COUNT(AI249:AV249)<2),"",LOOKUP(2,1/(AI249:AV249<>""),AI249:AV249)-MIN(AI249:AV249)) | IF(OR(AD249="",AC249="Not started",AC249=""),"",IFERROR(AD249-IF(VLOOKUP(AC249,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC249,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F249="","",IF(OR(AA249="Cancelled",AC249="Cancelled"),"Cancelled",IF(OR(AC249="Completed / Handover",Y249<>"",Z249>=100),"Completed — on track",IF(O249="Not awarded",IF(U249="",IF(X249="","No planned date",IF(TODAY()>X249,"Behind — past planned date",IF(X249-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U249,"Behind — award date passed",IF(U249-TODAY()<=30,"At risk — close to off track","On track"))),IF(X249="","No planned date",IF(AND(TODAY()>X249,OR(Z249="",Z249<100)),"Behind — past end date",IF(AND(T249<>"",X249<>"",Z249<>"",(Z249<100),((TODAY()-T249)/MAX(X249-T249,1)*100)-Z249>15),"Behind — progress lag",IF(AND(X249-TODAY()<=30,X249-TODAY()>=0,OR(Z249="",Z249<90)),"At risk — close to off track","On track")))))))) | IF(OR(F249="",AC249="Completed / Handover",AC249="Cancelled"),"",IF(O249="Not awarded",IF(U249<>"",U249-TODAY(),IF(X249="","",X249-TODAY())),IF(X249="","",X249-TODAY()))) | [14 empty] | IF(OR(F249="",AJ249=""),"",IF(COUNT(AI249:AI249)=0,"",AJ249-LOOKUP(2,1/(AI249:AI249<>""),AI249:AI249))) | IF(OR(F249="",AK249=""),"",IF(COUNT(AI249:AJ249)=0,"",AK249-LOOKUP(2,1/(AI249:AJ249<>""),AI249:AJ249))) | IF(OR(F249="",AL249=""),"",IF(COUNT(AI249:AK249)=0,"",AL249-LOOKUP(2,1/(AI249:AK249<>""),AI249:AK249))) | IF(OR(F249="",AM249=""),"",IF(COUNT(AI249:AL249)=0,"",AM249-LOOKUP(2,1/(AI249:AL249<>""),AI249:AL249))) | IF(OR(F249="",AN249=""),"",IF(COUNT(AI249:AM249)=0,"",AN249-LOOKUP(2,1/(AI249:AM249<>""),AI249:AM249))) | IF(OR(F249="",AO249=""),"",IF(COUNT(AI249:AN249)=0,"",AO249-LOOKUP(2,1/(AI249:AN249<>""),AI249:AN249))) | IF(OR(F249="",AP249=""),"",IF(COUNT(AI249:AO249)=0,"",AP249-LOOKUP(2,1/(AI249:AO249<>""),AI249:AO249))) | IF(OR(F249="",AQ249=""),"",IF(COUNT(AI249:AP249)=0,"",AQ249-LOOKUP(2,1/(AI249:AP249<>""),AI249:AP249))) | IF(OR(F249="",AR249=""),"",IF(COUNT(AI249:AQ249)=0,"",AR249-LOOKUP(2,1/(AI249:AQ249<>""),AI249:AQ249))) | IF(OR(F249="",AS249=""),"",IF(COUNT(AI249:AR249)=0,"",AS249-LOOKUP(2,1/(AI249:AR249<>""),AI249:AR249))) | IF(OR(F249="",AT249=""),"",IF(COUNT(AI249:AS249)=0,"",AT249-LOOKUP(2,1/(AI249:AS249<>""),AI249:AS249))) | IF(OR(F249="",AU249=""),"",IF(COUNT(AI249:AT249)=0,"",AU249-LOOKUP(2,1/(AI249:AT249<>""),AI249:AT249))) | IF(OR(F249="",AV249=""),"",IF(COUNT(AI249:AU249)=0,"",AV249-LOOKUP(2,1/(AI249:AU249<>""),AI249:AU249))) | IF(J249="","All_Provinces",IFERROR(VLOOKUP(J249,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K249="","All_Districts",IFERROR(VLOOKUP(K249,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F250="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 39 of 50 | AF2-LLL-N-039 | Sardar Ha IS | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Deh Sala | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ250="","",AQ250) | 2026-10-30 |  | 2027-01-31 | IF(W250<>"",W250,IF(OR(T250="",V250=""),"",EDATE(T250,V250))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F250="","",IF(COUNT(AI250:AV250)=0,IF(AA250="","Not started",AA250),SUBSTITUTE(LOOKUP(2,1/(AI250:AV250<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F250="",COUNT(AI250:AV250)=0),"",TODAY()-LOOKUP(2,1/(AI250:AV250<>""),AI250:AV250)) | IF(OR(F250="",COUNT(AI250:AV250)<2),"",LOOKUP(2,1/(AI250:AV250<>""),AI250:AV250)-MIN(AI250:AV250)) | IF(OR(AD250="",AC250="Not started",AC250=""),"",IFERROR(AD250-IF(VLOOKUP(AC250,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC250,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F250="","",IF(OR(AA250="Cancelled",AC250="Cancelled"),"Cancelled",IF(OR(AC250="Completed / Handover",Y250<>"",Z250>=100),"Completed — on track",IF(O250="Not awarded",IF(U250="",IF(X250="","No planned date",IF(TODAY()>X250,"Behind — past planned date",IF(X250-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U250,"Behind — award date passed",IF(U250-TODAY()<=30,"At risk — close to off track","On track"))),IF(X250="","No planned date",IF(AND(TODAY()>X250,OR(Z250="",Z250<100)),"Behind — past end date",IF(AND(T250<>"",X250<>"",Z250<>"",(Z250<100),((TODAY()-T250)/MAX(X250-T250,1)*100)-Z250>15),"Behind — progress lag",IF(AND(X250-TODAY()<=30,X250-TODAY()>=0,OR(Z250="",Z250<90)),"At risk — close to off track","On track")))))))) | IF(OR(F250="",AC250="Completed / Handover",AC250="Cancelled"),"",IF(O250="Not awarded",IF(U250<>"",U250-TODAY(),IF(X250="","",X250-TODAY())),IF(X250="","",X250-TODAY()))) | [14 empty] | IF(OR(F250="",AJ250=""),"",IF(COUNT(AI250:AI250)=0,"",AJ250-LOOKUP(2,1/(AI250:AI250<>""),AI250:AI250))) | IF(OR(F250="",AK250=""),"",IF(COUNT(AI250:AJ250)=0,"",AK250-LOOKUP(2,1/(AI250:AJ250<>""),AI250:AJ250))) | IF(OR(F250="",AL250=""),"",IF(COUNT(AI250:AK250)=0,"",AL250-LOOKUP(2,1/(AI250:AK250<>""),AI250:AK250))) | IF(OR(F250="",AM250=""),"",IF(COUNT(AI250:AL250)=0,"",AM250-LOOKUP(2,1/(AI250:AL250<>""),AI250:AL250))) | IF(OR(F250="",AN250=""),"",IF(COUNT(AI250:AM250)=0,"",AN250-LOOKUP(2,1/(AI250:AM250<>""),AI250:AM250))) | IF(OR(F250="",AO250=""),"",IF(COUNT(AI250:AN250)=0,"",AO250-LOOKUP(2,1/(AI250:AN250<>""),AI250:AN250))) | IF(OR(F250="",AP250=""),"",IF(COUNT(AI250:AO250)=0,"",AP250-LOOKUP(2,1/(AI250:AO250<>""),AI250:AO250))) | IF(OR(F250="",AQ250=""),"",IF(COUNT(AI250:AP250)=0,"",AQ250-LOOKUP(2,1/(AI250:AP250<>""),AI250:AP250))) | IF(OR(F250="",AR250=""),"",IF(COUNT(AI250:AQ250)=0,"",AR250-LOOKUP(2,1/(AI250:AQ250<>""),AI250:AQ250))) | IF(OR(F250="",AS250=""),"",IF(COUNT(AI250:AR250)=0,"",AS250-LOOKUP(2,1/(AI250:AR250<>""),AI250:AR250))) | IF(OR(F250="",AT250=""),"",IF(COUNT(AI250:AS250)=0,"",AT250-LOOKUP(2,1/(AI250:AS250<>""),AI250:AS250))) | IF(OR(F250="",AU250=""),"",IF(COUNT(AI250:AT250)=0,"",AU250-LOOKUP(2,1/(AI250:AT250<>""),AI250:AT250))) | IF(OR(F250="",AV250=""),"",IF(COUNT(AI250:AU250)=0,"",AV250-LOOKUP(2,1/(AI250:AU250<>""),AI250:AU250))) | IF(J250="","All_Provinces",IFERROR(VLOOKUP(J250,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K250="","All_Districts",IFERROR(VLOOKUP(K250,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F251="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 40 of 50 | AF2-LLL-N-040 | Sarkay Lazhey irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Spin Boldak | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ251="","",AQ251) | 2026-10-30 |  | 2027-01-31 | IF(W251<>"",W251,IF(OR(T251="",V251=""),"",EDATE(T251,V251))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F251="","",IF(COUNT(AI251:AV251)=0,IF(AA251="","Not started",AA251),SUBSTITUTE(LOOKUP(2,1/(AI251:AV251<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F251="",COUNT(AI251:AV251)=0),"",TODAY()-LOOKUP(2,1/(AI251:AV251<>""),AI251:AV251)) | IF(OR(F251="",COUNT(AI251:AV251)<2),"",LOOKUP(2,1/(AI251:AV251<>""),AI251:AV251)-MIN(AI251:AV251)) | IF(OR(AD251="",AC251="Not started",AC251=""),"",IFERROR(AD251-IF(VLOOKUP(AC251,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC251,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F251="","",IF(OR(AA251="Cancelled",AC251="Cancelled"),"Cancelled",IF(OR(AC251="Completed / Handover",Y251<>"",Z251>=100),"Completed — on track",IF(O251="Not awarded",IF(U251="",IF(X251="","No planned date",IF(TODAY()>X251,"Behind — past planned date",IF(X251-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U251,"Behind — award date passed",IF(U251-TODAY()<=30,"At risk — close to off track","On track"))),IF(X251="","No planned date",IF(AND(TODAY()>X251,OR(Z251="",Z251<100)),"Behind — past end date",IF(AND(T251<>"",X251<>"",Z251<>"",(Z251<100),((TODAY()-T251)/MAX(X251-T251,1)*100)-Z251>15),"Behind — progress lag",IF(AND(X251-TODAY()<=30,X251-TODAY()>=0,OR(Z251="",Z251<90)),"At risk — close to off track","On track")))))))) | IF(OR(F251="",AC251="Completed / Handover",AC251="Cancelled"),"",IF(O251="Not awarded",IF(U251<>"",U251-TODAY(),IF(X251="","",X251-TODAY())),IF(X251="","",X251-TODAY()))) | [14 empty] | IF(OR(F251="",AJ251=""),"",IF(COUNT(AI251:AI251)=0,"",AJ251-LOOKUP(2,1/(AI251:AI251<>""),AI251:AI251))) | IF(OR(F251="",AK251=""),"",IF(COUNT(AI251:AJ251)=0,"",AK251-LOOKUP(2,1/(AI251:AJ251<>""),AI251:AJ251))) | IF(OR(F251="",AL251=""),"",IF(COUNT(AI251:AK251)=0,"",AL251-LOOKUP(2,1/(AI251:AK251<>""),AI251:AK251))) | IF(OR(F251="",AM251=""),"",IF(COUNT(AI251:AL251)=0,"",AM251-LOOKUP(2,1/(AI251:AL251<>""),AI251:AL251))) | IF(OR(F251="",AN251=""),"",IF(COUNT(AI251:AM251)=0,"",AN251-LOOKUP(2,1/(AI251:AM251<>""),AI251:AM251))) | IF(OR(F251="",AO251=""),"",IF(COUNT(AI251:AN251)=0,"",AO251-LOOKUP(2,1/(AI251:AN251<>""),AI251:AN251))) | IF(OR(F251="",AP251=""),"",IF(COUNT(AI251:AO251)=0,"",AP251-LOOKUP(2,1/(AI251:AO251<>""),AI251:AO251))) | IF(OR(F251="",AQ251=""),"",IF(COUNT(AI251:AP251)=0,"",AQ251-LOOKUP(2,1/(AI251:AP251<>""),AI251:AP251))) | IF(OR(F251="",AR251=""),"",IF(COUNT(AI251:AQ251)=0,"",AR251-LOOKUP(2,1/(AI251:AQ251<>""),AI251:AQ251))) | IF(OR(F251="",AS251=""),"",IF(COUNT(AI251:AR251)=0,"",AS251-LOOKUP(2,1/(AI251:AR251<>""),AI251:AR251))) | IF(OR(F251="",AT251=""),"",IF(COUNT(AI251:AS251)=0,"",AT251-LOOKUP(2,1/(AI251:AS251<>""),AI251:AS251))) | IF(OR(F251="",AU251=""),"",IF(COUNT(AI251:AT251)=0,"",AU251-LOOKUP(2,1/(AI251:AT251<>""),AI251:AT251))) | IF(OR(F251="",AV251=""),"",IF(COUNT(AI251:AU251)=0,"",AV251-LOOKUP(2,1/(AI251:AU251<>""),AI251:AU251))) | IF(J251="","All_Provinces",IFERROR(VLOOKUP(J251,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K251="","All_Districts",IFERROR(VLOOKUP(K251,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F252="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 41 of 50 | AF2-LLL-N-041 | Shaflan Irrigation Canal | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Pashton Zarghon | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ252="","",AQ252) | 2026-10-30 |  | 2027-01-31 | IF(W252<>"",W252,IF(OR(T252="",V252=""),"",EDATE(T252,V252))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F252="","",IF(COUNT(AI252:AV252)=0,IF(AA252="","Not started",AA252),SUBSTITUTE(LOOKUP(2,1/(AI252:AV252<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F252="",COUNT(AI252:AV252)=0),"",TODAY()-LOOKUP(2,1/(AI252:AV252<>""),AI252:AV252)) | IF(OR(F252="",COUNT(AI252:AV252)<2),"",LOOKUP(2,1/(AI252:AV252<>""),AI252:AV252)-MIN(AI252:AV252)) | IF(OR(AD252="",AC252="Not started",AC252=""),"",IFERROR(AD252-IF(VLOOKUP(AC252,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC252,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F252="","",IF(OR(AA252="Cancelled",AC252="Cancelled"),"Cancelled",IF(OR(AC252="Completed / Handover",Y252<>"",Z252>=100),"Completed — on track",IF(O252="Not awarded",IF(U252="",IF(X252="","No planned date",IF(TODAY()>X252,"Behind — past planned date",IF(X252-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U252,"Behind — award date passed",IF(U252-TODAY()<=30,"At risk — close to off track","On track"))),IF(X252="","No planned date",IF(AND(TODAY()>X252,OR(Z252="",Z252<100)),"Behind — past end date",IF(AND(T252<>"",X252<>"",Z252<>"",(Z252<100),((TODAY()-T252)/MAX(X252-T252,1)*100)-Z252>15),"Behind — progress lag",IF(AND(X252-TODAY()<=30,X252-TODAY()>=0,OR(Z252="",Z252<90)),"At risk — close to off track","On track")))))))) | IF(OR(F252="",AC252="Completed / Handover",AC252="Cancelled"),"",IF(O252="Not awarded",IF(U252<>"",U252-TODAY(),IF(X252="","",X252-TODAY())),IF(X252="","",X252-TODAY()))) | [14 empty] | IF(OR(F252="",AJ252=""),"",IF(COUNT(AI252:AI252)=0,"",AJ252-LOOKUP(2,1/(AI252:AI252<>""),AI252:AI252))) | IF(OR(F252="",AK252=""),"",IF(COUNT(AI252:AJ252)=0,"",AK252-LOOKUP(2,1/(AI252:AJ252<>""),AI252:AJ252))) | IF(OR(F252="",AL252=""),"",IF(COUNT(AI252:AK252)=0,"",AL252-LOOKUP(2,1/(AI252:AK252<>""),AI252:AK252))) | IF(OR(F252="",AM252=""),"",IF(COUNT(AI252:AL252)=0,"",AM252-LOOKUP(2,1/(AI252:AL252<>""),AI252:AL252))) | IF(OR(F252="",AN252=""),"",IF(COUNT(AI252:AM252)=0,"",AN252-LOOKUP(2,1/(AI252:AM252<>""),AI252:AM252))) | IF(OR(F252="",AO252=""),"",IF(COUNT(AI252:AN252)=0,"",AO252-LOOKUP(2,1/(AI252:AN252<>""),AI252:AN252))) | IF(OR(F252="",AP252=""),"",IF(COUNT(AI252:AO252)=0,"",AP252-LOOKUP(2,1/(AI252:AO252<>""),AI252:AO252))) | IF(OR(F252="",AQ252=""),"",IF(COUNT(AI252:AP252)=0,"",AQ252-LOOKUP(2,1/(AI252:AP252<>""),AI252:AP252))) | IF(OR(F252="",AR252=""),"",IF(COUNT(AI252:AQ252)=0,"",AR252-LOOKUP(2,1/(AI252:AQ252<>""),AI252:AQ252))) | IF(OR(F252="",AS252=""),"",IF(COUNT(AI252:AR252)=0,"",AS252-LOOKUP(2,1/(AI252:AR252<>""),AI252:AR252))) | IF(OR(F252="",AT252=""),"",IF(COUNT(AI252:AS252)=0,"",AT252-LOOKUP(2,1/(AI252:AS252<>""),AI252:AS252))) | IF(OR(F252="",AU252=""),"",IF(COUNT(AI252:AT252)=0,"",AU252-LOOKUP(2,1/(AI252:AT252<>""),AI252:AT252))) | IF(OR(F252="",AV252=""),"",IF(COUNT(AI252:AU252)=0,"",AV252-LOOKUP(2,1/(AI252:AU252<>""),AI252:AU252))) | IF(J252="","All_Provinces",IFERROR(VLOOKUP(J252,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K252="","All_Districts",IFERROR(VLOOKUP(K252,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F253="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 42 of 50 | AF2-LLL-N-042 | Shahidan, Dasht-e Lajam IS | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Tala Wa Barfak | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ253="","",AQ253) | 2026-10-30 |  | 2027-01-31 | IF(W253<>"",W253,IF(OR(T253="",V253=""),"",EDATE(T253,V253))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F253="","",IF(COUNT(AI253:AV253)=0,IF(AA253="","Not started",AA253),SUBSTITUTE(LOOKUP(2,1/(AI253:AV253<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F253="",COUNT(AI253:AV253)=0),"",TODAY()-LOOKUP(2,1/(AI253:AV253<>""),AI253:AV253)) | IF(OR(F253="",COUNT(AI253:AV253)<2),"",LOOKUP(2,1/(AI253:AV253<>""),AI253:AV253)-MIN(AI253:AV253)) | IF(OR(AD253="",AC253="Not started",AC253=""),"",IFERROR(AD253-IF(VLOOKUP(AC253,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC253,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F253="","",IF(OR(AA253="Cancelled",AC253="Cancelled"),"Cancelled",IF(OR(AC253="Completed / Handover",Y253<>"",Z253>=100),"Completed — on track",IF(O253="Not awarded",IF(U253="",IF(X253="","No planned date",IF(TODAY()>X253,"Behind — past planned date",IF(X253-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U253,"Behind — award date passed",IF(U253-TODAY()<=30,"At risk — close to off track","On track"))),IF(X253="","No planned date",IF(AND(TODAY()>X253,OR(Z253="",Z253<100)),"Behind — past end date",IF(AND(T253<>"",X253<>"",Z253<>"",(Z253<100),((TODAY()-T253)/MAX(X253-T253,1)*100)-Z253>15),"Behind — progress lag",IF(AND(X253-TODAY()<=30,X253-TODAY()>=0,OR(Z253="",Z253<90)),"At risk — close to off track","On track")))))))) | IF(OR(F253="",AC253="Completed / Handover",AC253="Cancelled"),"",IF(O253="Not awarded",IF(U253<>"",U253-TODAY(),IF(X253="","",X253-TODAY())),IF(X253="","",X253-TODAY()))) | [14 empty] | IF(OR(F253="",AJ253=""),"",IF(COUNT(AI253:AI253)=0,"",AJ253-LOOKUP(2,1/(AI253:AI253<>""),AI253:AI253))) | IF(OR(F253="",AK253=""),"",IF(COUNT(AI253:AJ253)=0,"",AK253-LOOKUP(2,1/(AI253:AJ253<>""),AI253:AJ253))) | IF(OR(F253="",AL253=""),"",IF(COUNT(AI253:AK253)=0,"",AL253-LOOKUP(2,1/(AI253:AK253<>""),AI253:AK253))) | IF(OR(F253="",AM253=""),"",IF(COUNT(AI253:AL253)=0,"",AM253-LOOKUP(2,1/(AI253:AL253<>""),AI253:AL253))) | IF(OR(F253="",AN253=""),"",IF(COUNT(AI253:AM253)=0,"",AN253-LOOKUP(2,1/(AI253:AM253<>""),AI253:AM253))) | IF(OR(F253="",AO253=""),"",IF(COUNT(AI253:AN253)=0,"",AO253-LOOKUP(2,1/(AI253:AN253<>""),AI253:AN253))) | IF(OR(F253="",AP253=""),"",IF(COUNT(AI253:AO253)=0,"",AP253-LOOKUP(2,1/(AI253:AO253<>""),AI253:AO253))) | IF(OR(F253="",AQ253=""),"",IF(COUNT(AI253:AP253)=0,"",AQ253-LOOKUP(2,1/(AI253:AP253<>""),AI253:AP253))) | IF(OR(F253="",AR253=""),"",IF(COUNT(AI253:AQ253)=0,"",AR253-LOOKUP(2,1/(AI253:AQ253<>""),AI253:AQ253))) | IF(OR(F253="",AS253=""),"",IF(COUNT(AI253:AR253)=0,"",AS253-LOOKUP(2,1/(AI253:AR253<>""),AI253:AR253))) | IF(OR(F253="",AT253=""),"",IF(COUNT(AI253:AS253)=0,"",AT253-LOOKUP(2,1/(AI253:AS253<>""),AI253:AS253))) | IF(OR(F253="",AU253=""),"",IF(COUNT(AI253:AT253)=0,"",AU253-LOOKUP(2,1/(AI253:AT253<>""),AI253:AT253))) | IF(OR(F253="",AV253=""),"",IF(COUNT(AI253:AU253)=0,"",AV253-LOOKUP(2,1/(AI253:AU253<>""),AI253:AU253))) | IF(J253="","All_Provinces",IFERROR(VLOOKUP(J253,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K253="","All_Districts",IFERROR(VLOOKUP(K253,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F254="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 43 of 50 | AF2-LLL-N-043 | Shawarooz irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Zabul | Khak e Afghan | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ254="","",AQ254) | 2026-10-30 |  | 2027-01-31 | IF(W254<>"",W254,IF(OR(T254="",V254=""),"",EDATE(T254,V254))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F254="","",IF(COUNT(AI254:AV254)=0,IF(AA254="","Not started",AA254),SUBSTITUTE(LOOKUP(2,1/(AI254:AV254<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F254="",COUNT(AI254:AV254)=0),"",TODAY()-LOOKUP(2,1/(AI254:AV254<>""),AI254:AV254)) | IF(OR(F254="",COUNT(AI254:AV254)<2),"",LOOKUP(2,1/(AI254:AV254<>""),AI254:AV254)-MIN(AI254:AV254)) | IF(OR(AD254="",AC254="Not started",AC254=""),"",IFERROR(AD254-IF(VLOOKUP(AC254,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC254,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F254="","",IF(OR(AA254="Cancelled",AC254="Cancelled"),"Cancelled",IF(OR(AC254="Completed / Handover",Y254<>"",Z254>=100),"Completed — on track",IF(O254="Not awarded",IF(U254="",IF(X254="","No planned date",IF(TODAY()>X254,"Behind — past planned date",IF(X254-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U254,"Behind — award date passed",IF(U254-TODAY()<=30,"At risk — close to off track","On track"))),IF(X254="","No planned date",IF(AND(TODAY()>X254,OR(Z254="",Z254<100)),"Behind — past end date",IF(AND(T254<>"",X254<>"",Z254<>"",(Z254<100),((TODAY()-T254)/MAX(X254-T254,1)*100)-Z254>15),"Behind — progress lag",IF(AND(X254-TODAY()<=30,X254-TODAY()>=0,OR(Z254="",Z254<90)),"At risk — close to off track","On track")))))))) | IF(OR(F254="",AC254="Completed / Handover",AC254="Cancelled"),"",IF(O254="Not awarded",IF(U254<>"",U254-TODAY(),IF(X254="","",X254-TODAY())),IF(X254="","",X254-TODAY()))) | [14 empty] | IF(OR(F254="",AJ254=""),"",IF(COUNT(AI254:AI254)=0,"",AJ254-LOOKUP(2,1/(AI254:AI254<>""),AI254:AI254))) | IF(OR(F254="",AK254=""),"",IF(COUNT(AI254:AJ254)=0,"",AK254-LOOKUP(2,1/(AI254:AJ254<>""),AI254:AJ254))) | IF(OR(F254="",AL254=""),"",IF(COUNT(AI254:AK254)=0,"",AL254-LOOKUP(2,1/(AI254:AK254<>""),AI254:AK254))) | IF(OR(F254="",AM254=""),"",IF(COUNT(AI254:AL254)=0,"",AM254-LOOKUP(2,1/(AI254:AL254<>""),AI254:AL254))) | IF(OR(F254="",AN254=""),"",IF(COUNT(AI254:AM254)=0,"",AN254-LOOKUP(2,1/(AI254:AM254<>""),AI254:AM254))) | IF(OR(F254="",AO254=""),"",IF(COUNT(AI254:AN254)=0,"",AO254-LOOKUP(2,1/(AI254:AN254<>""),AI254:AN254))) | IF(OR(F254="",AP254=""),"",IF(COUNT(AI254:AO254)=0,"",AP254-LOOKUP(2,1/(AI254:AO254<>""),AI254:AO254))) | IF(OR(F254="",AQ254=""),"",IF(COUNT(AI254:AP254)=0,"",AQ254-LOOKUP(2,1/(AI254:AP254<>""),AI254:AP254))) | IF(OR(F254="",AR254=""),"",IF(COUNT(AI254:AQ254)=0,"",AR254-LOOKUP(2,1/(AI254:AQ254<>""),AI254:AQ254))) | IF(OR(F254="",AS254=""),"",IF(COUNT(AI254:AR254)=0,"",AS254-LOOKUP(2,1/(AI254:AR254<>""),AI254:AR254))) | IF(OR(F254="",AT254=""),"",IF(COUNT(AI254:AS254)=0,"",AT254-LOOKUP(2,1/(AI254:AS254<>""),AI254:AS254))) | IF(OR(F254="",AU254=""),"",IF(COUNT(AI254:AT254)=0,"",AU254-LOOKUP(2,1/(AI254:AT254<>""),AI254:AT254))) | IF(OR(F254="",AV254=""),"",IF(COUNT(AI254:AU254)=0,"",AV254-LOOKUP(2,1/(AI254:AU254<>""),AI254:AU254))) | IF(J254="","All_Provinces",IFERROR(VLOOKUP(J254,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K254="","All_Districts",IFERROR(VLOOKUP(K254,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F255="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 44 of 50 | AF2-LLL-N-044 | Shir Abad Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Ghazni | Qarabagh | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ255="","",AQ255) | 2026-10-30 |  | 2027-01-31 | IF(W255<>"",W255,IF(OR(T255="",V255=""),"",EDATE(T255,V255))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F255="","",IF(COUNT(AI255:AV255)=0,IF(AA255="","Not started",AA255),SUBSTITUTE(LOOKUP(2,1/(AI255:AV255<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F255="",COUNT(AI255:AV255)=0),"",TODAY()-LOOKUP(2,1/(AI255:AV255<>""),AI255:AV255)) | IF(OR(F255="",COUNT(AI255:AV255)<2),"",LOOKUP(2,1/(AI255:AV255<>""),AI255:AV255)-MIN(AI255:AV255)) | IF(OR(AD255="",AC255="Not started",AC255=""),"",IFERROR(AD255-IF(VLOOKUP(AC255,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC255,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F255="","",IF(OR(AA255="Cancelled",AC255="Cancelled"),"Cancelled",IF(OR(AC255="Completed / Handover",Y255<>"",Z255>=100),"Completed — on track",IF(O255="Not awarded",IF(U255="",IF(X255="","No planned date",IF(TODAY()>X255,"Behind — past planned date",IF(X255-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U255,"Behind — award date passed",IF(U255-TODAY()<=30,"At risk — close to off track","On track"))),IF(X255="","No planned date",IF(AND(TODAY()>X255,OR(Z255="",Z255<100)),"Behind — past end date",IF(AND(T255<>"",X255<>"",Z255<>"",(Z255<100),((TODAY()-T255)/MAX(X255-T255,1)*100)-Z255>15),"Behind — progress lag",IF(AND(X255-TODAY()<=30,X255-TODAY()>=0,OR(Z255="",Z255<90)),"At risk — close to off track","On track")))))))) | IF(OR(F255="",AC255="Completed / Handover",AC255="Cancelled"),"",IF(O255="Not awarded",IF(U255<>"",U255-TODAY(),IF(X255="","",X255-TODAY())),IF(X255="","",X255-TODAY()))) | [14 empty] | IF(OR(F255="",AJ255=""),"",IF(COUNT(AI255:AI255)=0,"",AJ255-LOOKUP(2,1/(AI255:AI255<>""),AI255:AI255))) | IF(OR(F255="",AK255=""),"",IF(COUNT(AI255:AJ255)=0,"",AK255-LOOKUP(2,1/(AI255:AJ255<>""),AI255:AJ255))) | IF(OR(F255="",AL255=""),"",IF(COUNT(AI255:AK255)=0,"",AL255-LOOKUP(2,1/(AI255:AK255<>""),AI255:AK255))) | IF(OR(F255="",AM255=""),"",IF(COUNT(AI255:AL255)=0,"",AM255-LOOKUP(2,1/(AI255:AL255<>""),AI255:AL255))) | IF(OR(F255="",AN255=""),"",IF(COUNT(AI255:AM255)=0,"",AN255-LOOKUP(2,1/(AI255:AM255<>""),AI255:AM255))) | IF(OR(F255="",AO255=""),"",IF(COUNT(AI255:AN255)=0,"",AO255-LOOKUP(2,1/(AI255:AN255<>""),AI255:AN255))) | IF(OR(F255="",AP255=""),"",IF(COUNT(AI255:AO255)=0,"",AP255-LOOKUP(2,1/(AI255:AO255<>""),AI255:AO255))) | IF(OR(F255="",AQ255=""),"",IF(COUNT(AI255:AP255)=0,"",AQ255-LOOKUP(2,1/(AI255:AP255<>""),AI255:AP255))) | IF(OR(F255="",AR255=""),"",IF(COUNT(AI255:AQ255)=0,"",AR255-LOOKUP(2,1/(AI255:AQ255<>""),AI255:AQ255))) | IF(OR(F255="",AS255=""),"",IF(COUNT(AI255:AR255)=0,"",AS255-LOOKUP(2,1/(AI255:AR255<>""),AI255:AR255))) | IF(OR(F255="",AT255=""),"",IF(COUNT(AI255:AS255)=0,"",AT255-LOOKUP(2,1/(AI255:AS255<>""),AI255:AS255))) | IF(OR(F255="",AU255=""),"",IF(COUNT(AI255:AT255)=0,"",AU255-LOOKUP(2,1/(AI255:AT255<>""),AI255:AT255))) | IF(OR(F255="",AV255=""),"",IF(COUNT(AI255:AU255)=0,"",AV255-LOOKUP(2,1/(AI255:AU255<>""),AI255:AU255))) | IF(J255="","All_Provinces",IFERROR(VLOOKUP(J255,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K255="","All_Districts",IFERROR(VLOOKUP(K255,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F256="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 45 of 50 | AF2-LLL-N-045 | Teshkhan Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Ishkashim | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ256="","",AQ256) | 2026-10-30 |  | 2027-01-31 | IF(W256<>"",W256,IF(OR(T256="",V256=""),"",EDATE(T256,V256))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F256="","",IF(COUNT(AI256:AV256)=0,IF(AA256="","Not started",AA256),SUBSTITUTE(LOOKUP(2,1/(AI256:AV256<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F256="",COUNT(AI256:AV256)=0),"",TODAY()-LOOKUP(2,1/(AI256:AV256<>""),AI256:AV256)) | IF(OR(F256="",COUNT(AI256:AV256)<2),"",LOOKUP(2,1/(AI256:AV256<>""),AI256:AV256)-MIN(AI256:AV256)) | IF(OR(AD256="",AC256="Not started",AC256=""),"",IFERROR(AD256-IF(VLOOKUP(AC256,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC256,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F256="","",IF(OR(AA256="Cancelled",AC256="Cancelled"),"Cancelled",IF(OR(AC256="Completed / Handover",Y256<>"",Z256>=100),"Completed — on track",IF(O256="Not awarded",IF(U256="",IF(X256="","No planned date",IF(TODAY()>X256,"Behind — past planned date",IF(X256-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U256,"Behind — award date passed",IF(U256-TODAY()<=30,"At risk — close to off track","On track"))),IF(X256="","No planned date",IF(AND(TODAY()>X256,OR(Z256="",Z256<100)),"Behind — past end date",IF(AND(T256<>"",X256<>"",Z256<>"",(Z256<100),((TODAY()-T256)/MAX(X256-T256,1)*100)-Z256>15),"Behind — progress lag",IF(AND(X256-TODAY()<=30,X256-TODAY()>=0,OR(Z256="",Z256<90)),"At risk — close to off track","On track")))))))) | IF(OR(F256="",AC256="Completed / Handover",AC256="Cancelled"),"",IF(O256="Not awarded",IF(U256<>"",U256-TODAY(),IF(X256="","",X256-TODAY())),IF(X256="","",X256-TODAY()))) | [14 empty] | IF(OR(F256="",AJ256=""),"",IF(COUNT(AI256:AI256)=0,"",AJ256-LOOKUP(2,1/(AI256:AI256<>""),AI256:AI256))) | IF(OR(F256="",AK256=""),"",IF(COUNT(AI256:AJ256)=0,"",AK256-LOOKUP(2,1/(AI256:AJ256<>""),AI256:AJ256))) | IF(OR(F256="",AL256=""),"",IF(COUNT(AI256:AK256)=0,"",AL256-LOOKUP(2,1/(AI256:AK256<>""),AI256:AK256))) | IF(OR(F256="",AM256=""),"",IF(COUNT(AI256:AL256)=0,"",AM256-LOOKUP(2,1/(AI256:AL256<>""),AI256:AL256))) | IF(OR(F256="",AN256=""),"",IF(COUNT(AI256:AM256)=0,"",AN256-LOOKUP(2,1/(AI256:AM256<>""),AI256:AM256))) | IF(OR(F256="",AO256=""),"",IF(COUNT(AI256:AN256)=0,"",AO256-LOOKUP(2,1/(AI256:AN256<>""),AI256:AN256))) | IF(OR(F256="",AP256=""),"",IF(COUNT(AI256:AO256)=0,"",AP256-LOOKUP(2,1/(AI256:AO256<>""),AI256:AO256))) | IF(OR(F256="",AQ256=""),"",IF(COUNT(AI256:AP256)=0,"",AQ256-LOOKUP(2,1/(AI256:AP256<>""),AI256:AP256))) | IF(OR(F256="",AR256=""),"",IF(COUNT(AI256:AQ256)=0,"",AR256-LOOKUP(2,1/(AI256:AQ256<>""),AI256:AQ256))) | IF(OR(F256="",AS256=""),"",IF(COUNT(AI256:AR256)=0,"",AS256-LOOKUP(2,1/(AI256:AR256<>""),AI256:AR256))) | IF(OR(F256="",AT256=""),"",IF(COUNT(AI256:AS256)=0,"",AT256-LOOKUP(2,1/(AI256:AS256<>""),AI256:AS256))) | IF(OR(F256="",AU256=""),"",IF(COUNT(AI256:AT256)=0,"",AU256-LOOKUP(2,1/(AI256:AT256<>""),AI256:AT256))) | IF(OR(F256="",AV256=""),"",IF(COUNT(AI256:AU256)=0,"",AV256-LOOKUP(2,1/(AI256:AU256<>""),AI256:AU256))) | IF(J256="","All_Provinces",IFERROR(VLOOKUP(J256,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K256="","All_Districts",IFERROR(VLOOKUP(K256,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F257="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 46 of 50 | AF2-LLL-N-046 | Urdokas irrigation scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Shawalikot | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ257="","",AQ257) | 2026-10-30 |  | 2027-01-31 | IF(W257<>"",W257,IF(OR(T257="",V257=""),"",EDATE(T257,V257))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F257="","",IF(COUNT(AI257:AV257)=0,IF(AA257="","Not started",AA257),SUBSTITUTE(LOOKUP(2,1/(AI257:AV257<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F257="",COUNT(AI257:AV257)=0),"",TODAY()-LOOKUP(2,1/(AI257:AV257<>""),AI257:AV257)) | IF(OR(F257="",COUNT(AI257:AV257)<2),"",LOOKUP(2,1/(AI257:AV257<>""),AI257:AV257)-MIN(AI257:AV257)) | IF(OR(AD257="",AC257="Not started",AC257=""),"",IFERROR(AD257-IF(VLOOKUP(AC257,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC257,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F257="","",IF(OR(AA257="Cancelled",AC257="Cancelled"),"Cancelled",IF(OR(AC257="Completed / Handover",Y257<>"",Z257>=100),"Completed — on track",IF(O257="Not awarded",IF(U257="",IF(X257="","No planned date",IF(TODAY()>X257,"Behind — past planned date",IF(X257-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U257,"Behind — award date passed",IF(U257-TODAY()<=30,"At risk — close to off track","On track"))),IF(X257="","No planned date",IF(AND(TODAY()>X257,OR(Z257="",Z257<100)),"Behind — past end date",IF(AND(T257<>"",X257<>"",Z257<>"",(Z257<100),((TODAY()-T257)/MAX(X257-T257,1)*100)-Z257>15),"Behind — progress lag",IF(AND(X257-TODAY()<=30,X257-TODAY()>=0,OR(Z257="",Z257<90)),"At risk — close to off track","On track")))))))) | IF(OR(F257="",AC257="Completed / Handover",AC257="Cancelled"),"",IF(O257="Not awarded",IF(U257<>"",U257-TODAY(),IF(X257="","",X257-TODAY())),IF(X257="","",X257-TODAY()))) | [14 empty] | IF(OR(F257="",AJ257=""),"",IF(COUNT(AI257:AI257)=0,"",AJ257-LOOKUP(2,1/(AI257:AI257<>""),AI257:AI257))) | IF(OR(F257="",AK257=""),"",IF(COUNT(AI257:AJ257)=0,"",AK257-LOOKUP(2,1/(AI257:AJ257<>""),AI257:AJ257))) | IF(OR(F257="",AL257=""),"",IF(COUNT(AI257:AK257)=0,"",AL257-LOOKUP(2,1/(AI257:AK257<>""),AI257:AK257))) | IF(OR(F257="",AM257=""),"",IF(COUNT(AI257:AL257)=0,"",AM257-LOOKUP(2,1/(AI257:AL257<>""),AI257:AL257))) | IF(OR(F257="",AN257=""),"",IF(COUNT(AI257:AM257)=0,"",AN257-LOOKUP(2,1/(AI257:AM257<>""),AI257:AM257))) | IF(OR(F257="",AO257=""),"",IF(COUNT(AI257:AN257)=0,"",AO257-LOOKUP(2,1/(AI257:AN257<>""),AI257:AN257))) | IF(OR(F257="",AP257=""),"",IF(COUNT(AI257:AO257)=0,"",AP257-LOOKUP(2,1/(AI257:AO257<>""),AI257:AO257))) | IF(OR(F257="",AQ257=""),"",IF(COUNT(AI257:AP257)=0,"",AQ257-LOOKUP(2,1/(AI257:AP257<>""),AI257:AP257))) | IF(OR(F257="",AR257=""),"",IF(COUNT(AI257:AQ257)=0,"",AR257-LOOKUP(2,1/(AI257:AQ257<>""),AI257:AQ257))) | IF(OR(F257="",AS257=""),"",IF(COUNT(AI257:AR257)=0,"",AS257-LOOKUP(2,1/(AI257:AR257<>""),AI257:AR257))) | IF(OR(F257="",AT257=""),"",IF(COUNT(AI257:AS257)=0,"",AT257-LOOKUP(2,1/(AI257:AS257<>""),AI257:AS257))) | IF(OR(F257="",AU257=""),"",IF(COUNT(AI257:AT257)=0,"",AU257-LOOKUP(2,1/(AI257:AT257<>""),AI257:AT257))) | IF(OR(F257="",AV257=""),"",IF(COUNT(AI257:AU257)=0,"",AV257-LOOKUP(2,1/(AI257:AU257<>""),AI257:AU257))) | IF(J257="","All_Provinces",IFERROR(VLOOKUP(J257,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K257="","All_Districts",IFERROR(VLOOKUP(K257,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F258="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 47 of 50 | AF2-LLL-N-047 | Welgai Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Matoon | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ258="","",AQ258) | 2026-10-30 |  | 2027-01-31 | IF(W258<>"",W258,IF(OR(T258="",V258=""),"",EDATE(T258,V258))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F258="","",IF(COUNT(AI258:AV258)=0,IF(AA258="","Not started",AA258),SUBSTITUTE(LOOKUP(2,1/(AI258:AV258<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F258="",COUNT(AI258:AV258)=0),"",TODAY()-LOOKUP(2,1/(AI258:AV258<>""),AI258:AV258)) | IF(OR(F258="",COUNT(AI258:AV258)<2),"",LOOKUP(2,1/(AI258:AV258<>""),AI258:AV258)-MIN(AI258:AV258)) | IF(OR(AD258="",AC258="Not started",AC258=""),"",IFERROR(AD258-IF(VLOOKUP(AC258,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC258,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F258="","",IF(OR(AA258="Cancelled",AC258="Cancelled"),"Cancelled",IF(OR(AC258="Completed / Handover",Y258<>"",Z258>=100),"Completed — on track",IF(O258="Not awarded",IF(U258="",IF(X258="","No planned date",IF(TODAY()>X258,"Behind — past planned date",IF(X258-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U258,"Behind — award date passed",IF(U258-TODAY()<=30,"At risk — close to off track","On track"))),IF(X258="","No planned date",IF(AND(TODAY()>X258,OR(Z258="",Z258<100)),"Behind — past end date",IF(AND(T258<>"",X258<>"",Z258<>"",(Z258<100),((TODAY()-T258)/MAX(X258-T258,1)*100)-Z258>15),"Behind — progress lag",IF(AND(X258-TODAY()<=30,X258-TODAY()>=0,OR(Z258="",Z258<90)),"At risk — close to off track","On track")))))))) | IF(OR(F258="",AC258="Completed / Handover",AC258="Cancelled"),"",IF(O258="Not awarded",IF(U258<>"",U258-TODAY(),IF(X258="","",X258-TODAY())),IF(X258="","",X258-TODAY()))) | [14 empty] | IF(OR(F258="",AJ258=""),"",IF(COUNT(AI258:AI258)=0,"",AJ258-LOOKUP(2,1/(AI258:AI258<>""),AI258:AI258))) | IF(OR(F258="",AK258=""),"",IF(COUNT(AI258:AJ258)=0,"",AK258-LOOKUP(2,1/(AI258:AJ258<>""),AI258:AJ258))) | IF(OR(F258="",AL258=""),"",IF(COUNT(AI258:AK258)=0,"",AL258-LOOKUP(2,1/(AI258:AK258<>""),AI258:AK258))) | IF(OR(F258="",AM258=""),"",IF(COUNT(AI258:AL258)=0,"",AM258-LOOKUP(2,1/(AI258:AL258<>""),AI258:AL258))) | IF(OR(F258="",AN258=""),"",IF(COUNT(AI258:AM258)=0,"",AN258-LOOKUP(2,1/(AI258:AM258<>""),AI258:AM258))) | IF(OR(F258="",AO258=""),"",IF(COUNT(AI258:AN258)=0,"",AO258-LOOKUP(2,1/(AI258:AN258<>""),AI258:AN258))) | IF(OR(F258="",AP258=""),"",IF(COUNT(AI258:AO258)=0,"",AP258-LOOKUP(2,1/(AI258:AO258<>""),AI258:AO258))) | IF(OR(F258="",AQ258=""),"",IF(COUNT(AI258:AP258)=0,"",AQ258-LOOKUP(2,1/(AI258:AP258<>""),AI258:AP258))) | IF(OR(F258="",AR258=""),"",IF(COUNT(AI258:AQ258)=0,"",AR258-LOOKUP(2,1/(AI258:AQ258<>""),AI258:AQ258))) | IF(OR(F258="",AS258=""),"",IF(COUNT(AI258:AR258)=0,"",AS258-LOOKUP(2,1/(AI258:AR258<>""),AI258:AR258))) | IF(OR(F258="",AT258=""),"",IF(COUNT(AI258:AS258)=0,"",AT258-LOOKUP(2,1/(AI258:AS258<>""),AI258:AS258))) | IF(OR(F258="",AU258=""),"",IF(COUNT(AI258:AT258)=0,"",AU258-LOOKUP(2,1/(AI258:AT258<>""),AI258:AT258))) | IF(OR(F258="",AV258=""),"",IF(COUNT(AI258:AU258)=0,"",AV258-LOOKUP(2,1/(AI258:AU258<>""),AI258:AU258))) | IF(J258="","All_Provinces",IFERROR(VLOOKUP(J258,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K258="","All_Districts",IFERROR(VLOOKUP(K258,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F259="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 48 of 50 | AF2-LLL-N-048 | Yar Mohammad Khan Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Obe | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ259="","",AQ259) | 2026-10-30 |  | 2027-01-31 | IF(W259<>"",W259,IF(OR(T259="",V259=""),"",EDATE(T259,V259))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F259="","",IF(COUNT(AI259:AV259)=0,IF(AA259="","Not started",AA259),SUBSTITUTE(LOOKUP(2,1/(AI259:AV259<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F259="",COUNT(AI259:AV259)=0),"",TODAY()-LOOKUP(2,1/(AI259:AV259<>""),AI259:AV259)) | IF(OR(F259="",COUNT(AI259:AV259)<2),"",LOOKUP(2,1/(AI259:AV259<>""),AI259:AV259)-MIN(AI259:AV259)) | IF(OR(AD259="",AC259="Not started",AC259=""),"",IFERROR(AD259-IF(VLOOKUP(AC259,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC259,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F259="","",IF(OR(AA259="Cancelled",AC259="Cancelled"),"Cancelled",IF(OR(AC259="Completed / Handover",Y259<>"",Z259>=100),"Completed — on track",IF(O259="Not awarded",IF(U259="",IF(X259="","No planned date",IF(TODAY()>X259,"Behind — past planned date",IF(X259-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U259,"Behind — award date passed",IF(U259-TODAY()<=30,"At risk — close to off track","On track"))),IF(X259="","No planned date",IF(AND(TODAY()>X259,OR(Z259="",Z259<100)),"Behind — past end date",IF(AND(T259<>"",X259<>"",Z259<>"",(Z259<100),((TODAY()-T259)/MAX(X259-T259,1)*100)-Z259>15),"Behind — progress lag",IF(AND(X259-TODAY()<=30,X259-TODAY()>=0,OR(Z259="",Z259<90)),"At risk — close to off track","On track")))))))) | IF(OR(F259="",AC259="Completed / Handover",AC259="Cancelled"),"",IF(O259="Not awarded",IF(U259<>"",U259-TODAY(),IF(X259="","",X259-TODAY())),IF(X259="","",X259-TODAY()))) | [14 empty] | IF(OR(F259="",AJ259=""),"",IF(COUNT(AI259:AI259)=0,"",AJ259-LOOKUP(2,1/(AI259:AI259<>""),AI259:AI259))) | IF(OR(F259="",AK259=""),"",IF(COUNT(AI259:AJ259)=0,"",AK259-LOOKUP(2,1/(AI259:AJ259<>""),AI259:AJ259))) | IF(OR(F259="",AL259=""),"",IF(COUNT(AI259:AK259)=0,"",AL259-LOOKUP(2,1/(AI259:AK259<>""),AI259:AK259))) | IF(OR(F259="",AM259=""),"",IF(COUNT(AI259:AL259)=0,"",AM259-LOOKUP(2,1/(AI259:AL259<>""),AI259:AL259))) | IF(OR(F259="",AN259=""),"",IF(COUNT(AI259:AM259)=0,"",AN259-LOOKUP(2,1/(AI259:AM259<>""),AI259:AM259))) | IF(OR(F259="",AO259=""),"",IF(COUNT(AI259:AN259)=0,"",AO259-LOOKUP(2,1/(AI259:AN259<>""),AI259:AN259))) | IF(OR(F259="",AP259=""),"",IF(COUNT(AI259:AO259)=0,"",AP259-LOOKUP(2,1/(AI259:AO259<>""),AI259:AO259))) | IF(OR(F259="",AQ259=""),"",IF(COUNT(AI259:AP259)=0,"",AQ259-LOOKUP(2,1/(AI259:AP259<>""),AI259:AP259))) | IF(OR(F259="",AR259=""),"",IF(COUNT(AI259:AQ259)=0,"",AR259-LOOKUP(2,1/(AI259:AQ259<>""),AI259:AQ259))) | IF(OR(F259="",AS259=""),"",IF(COUNT(AI259:AR259)=0,"",AS259-LOOKUP(2,1/(AI259:AR259<>""),AI259:AR259))) | IF(OR(F259="",AT259=""),"",IF(COUNT(AI259:AS259)=0,"",AT259-LOOKUP(2,1/(AI259:AS259<>""),AI259:AS259))) | IF(OR(F259="",AU259=""),"",IF(COUNT(AI259:AT259)=0,"",AU259-LOOKUP(2,1/(AI259:AT259<>""),AI259:AT259))) | IF(OR(F259="",AV259=""),"",IF(COUNT(AI259:AU259)=0,"",AV259-LOOKUP(2,1/(AI259:AU259<>""),AI259:AU259))) | IF(J259="","All_Provinces",IFERROR(VLOOKUP(J259,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K259="","All_Districts",IFERROR(VLOOKUP(K259,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F260="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 49 of 50 | AF2-LLL-N-049 | Zard Sang Irrigation Scheme | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Bamiyan | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ260="","",AQ260) | 2026-10-30 |  | 2027-01-31 | IF(W260<>"",W260,IF(OR(T260="",V260=""),"",EDATE(T260,V260))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F260="","",IF(COUNT(AI260:AV260)=0,IF(AA260="","Not started",AA260),SUBSTITUTE(LOOKUP(2,1/(AI260:AV260<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F260="",COUNT(AI260:AV260)=0),"",TODAY()-LOOKUP(2,1/(AI260:AV260<>""),AI260:AV260)) | IF(OR(F260="",COUNT(AI260:AV260)<2),"",LOOKUP(2,1/(AI260:AV260<>""),AI260:AV260)-MIN(AI260:AV260)) | IF(OR(AD260="",AC260="Not started",AC260=""),"",IFERROR(AD260-IF(VLOOKUP(AC260,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC260,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F260="","",IF(OR(AA260="Cancelled",AC260="Cancelled"),"Cancelled",IF(OR(AC260="Completed / Handover",Y260<>"",Z260>=100),"Completed — on track",IF(O260="Not awarded",IF(U260="",IF(X260="","No planned date",IF(TODAY()>X260,"Behind — past planned date",IF(X260-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U260,"Behind — award date passed",IF(U260-TODAY()<=30,"At risk — close to off track","On track"))),IF(X260="","No planned date",IF(AND(TODAY()>X260,OR(Z260="",Z260<100)),"Behind — past end date",IF(AND(T260<>"",X260<>"",Z260<>"",(Z260<100),((TODAY()-T260)/MAX(X260-T260,1)*100)-Z260>15),"Behind — progress lag",IF(AND(X260-TODAY()<=30,X260-TODAY()>=0,OR(Z260="",Z260<90)),"At risk — close to off track","On track")))))))) | IF(OR(F260="",AC260="Completed / Handover",AC260="Cancelled"),"",IF(O260="Not awarded",IF(U260<>"",U260-TODAY(),IF(X260="","",X260-TODAY())),IF(X260="","",X260-TODAY()))) | [14 empty] | IF(OR(F260="",AJ260=""),"",IF(COUNT(AI260:AI260)=0,"",AJ260-LOOKUP(2,1/(AI260:AI260<>""),AI260:AI260))) | IF(OR(F260="",AK260=""),"",IF(COUNT(AI260:AJ260)=0,"",AK260-LOOKUP(2,1/(AI260:AJ260<>""),AI260:AJ260))) | IF(OR(F260="",AL260=""),"",IF(COUNT(AI260:AK260)=0,"",AL260-LOOKUP(2,1/(AI260:AK260<>""),AI260:AK260))) | IF(OR(F260="",AM260=""),"",IF(COUNT(AI260:AL260)=0,"",AM260-LOOKUP(2,1/(AI260:AL260<>""),AI260:AL260))) | IF(OR(F260="",AN260=""),"",IF(COUNT(AI260:AM260)=0,"",AN260-LOOKUP(2,1/(AI260:AM260<>""),AI260:AM260))) | IF(OR(F260="",AO260=""),"",IF(COUNT(AI260:AN260)=0,"",AO260-LOOKUP(2,1/(AI260:AN260<>""),AI260:AN260))) | IF(OR(F260="",AP260=""),"",IF(COUNT(AI260:AO260)=0,"",AP260-LOOKUP(2,1/(AI260:AO260<>""),AI260:AO260))) | IF(OR(F260="",AQ260=""),"",IF(COUNT(AI260:AP260)=0,"",AQ260-LOOKUP(2,1/(AI260:AP260<>""),AI260:AP260))) | IF(OR(F260="",AR260=""),"",IF(COUNT(AI260:AQ260)=0,"",AR260-LOOKUP(2,1/(AI260:AQ260<>""),AI260:AQ260))) | IF(OR(F260="",AS260=""),"",IF(COUNT(AI260:AR260)=0,"",AS260-LOOKUP(2,1/(AI260:AR260<>""),AI260:AR260))) | IF(OR(F260="",AT260=""),"",IF(COUNT(AI260:AS260)=0,"",AT260-LOOKUP(2,1/(AI260:AS260<>""),AI260:AS260))) | IF(OR(F260="",AU260=""),"",IF(COUNT(AI260:AT260)=0,"",AU260-LOOKUP(2,1/(AI260:AT260<>""),AI260:AT260))) | IF(OR(F260="",AV260=""),"",IF(COUNT(AI260:AU260)=0,"",AV260-LOOKUP(2,1/(AI260:AU260<>""),AI260:AU260))) | IF(J260="","All_Provinces",IFERROR(VLOOKUP(J260,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K260="","All_Districts",IFERROR(VLOOKUP(K260,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F261="","",ROW()-3) | AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | 50 of 50 | AF2-LLL-N-050 | Zema Canal | Laser Land Leveler (LLL) | LLL unit | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Kalakan | 1 unit(s) | World Bank (WBK/AF-2) | Not awarded | 6. Supply and delivery of LLL |  |  |  | IF(AQ261="","",AQ261) | 2026-10-30 |  | 2027-01-31 | IF(W261<>"",W261,IF(OR(T261="",V261=""),"",EDATE(T261,V261))) |  |  | Under Awarding | The Procurement process is initiated in April and PO will be issued late October 2026. and delivery will be done by End of December 2026 and onward in January 2027 it is planned to be distributed to the selected beneficiaries. | IF(F261="","",IF(COUNT(AI261:AV261)=0,IF(AA261="","Not started",AA261),SUBSTITUTE(LOOKUP(2,1/(AI261:AV261<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F261="",COUNT(AI261:AV261)=0),"",TODAY()-LOOKUP(2,1/(AI261:AV261<>""),AI261:AV261)) | IF(OR(F261="",COUNT(AI261:AV261)<2),"",LOOKUP(2,1/(AI261:AV261<>""),AI261:AV261)-MIN(AI261:AV261)) | IF(OR(AD261="",AC261="Not started",AC261=""),"",IFERROR(AD261-IF(VLOOKUP(AC261,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC261,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F261="","",IF(OR(AA261="Cancelled",AC261="Cancelled"),"Cancelled",IF(OR(AC261="Completed / Handover",Y261<>"",Z261>=100),"Completed — on track",IF(O261="Not awarded",IF(U261="",IF(X261="","No planned date",IF(TODAY()>X261,"Behind — past planned date",IF(X261-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U261,"Behind — award date passed",IF(U261-TODAY()<=30,"At risk — close to off track","On track"))),IF(X261="","No planned date",IF(AND(TODAY()>X261,OR(Z261="",Z261<100)),"Behind — past end date",IF(AND(T261<>"",X261<>"",Z261<>"",(Z261<100),((TODAY()-T261)/MAX(X261-T261,1)*100)-Z261>15),"Behind — progress lag",IF(AND(X261-TODAY()<=30,X261-TODAY()>=0,OR(Z261="",Z261<90)),"At risk — close to off track","On track")))))))) | IF(OR(F261="",AC261="Completed / Handover",AC261="Cancelled"),"",IF(O261="Not awarded",IF(U261<>"",U261-TODAY(),IF(X261="","",X261-TODAY())),IF(X261="","",X261-TODAY()))) | [14 empty] | IF(OR(F261="",AJ261=""),"",IF(COUNT(AI261:AI261)=0,"",AJ261-LOOKUP(2,1/(AI261:AI261<>""),AI261:AI261))) | IF(OR(F261="",AK261=""),"",IF(COUNT(AI261:AJ261)=0,"",AK261-LOOKUP(2,1/(AI261:AJ261<>""),AI261:AJ261))) | IF(OR(F261="",AL261=""),"",IF(COUNT(AI261:AK261)=0,"",AL261-LOOKUP(2,1/(AI261:AK261<>""),AI261:AK261))) | IF(OR(F261="",AM261=""),"",IF(COUNT(AI261:AL261)=0,"",AM261-LOOKUP(2,1/(AI261:AL261<>""),AI261:AL261))) | IF(OR(F261="",AN261=""),"",IF(COUNT(AI261:AM261)=0,"",AN261-LOOKUP(2,1/(AI261:AM261<>""),AI261:AM261))) | IF(OR(F261="",AO261=""),"",IF(COUNT(AI261:AN261)=0,"",AO261-LOOKUP(2,1/(AI261:AN261<>""),AI261:AN261))) | IF(OR(F261="",AP261=""),"",IF(COUNT(AI261:AO261)=0,"",AP261-LOOKUP(2,1/(AI261:AO261<>""),AI261:AO261))) | IF(OR(F261="",AQ261=""),"",IF(COUNT(AI261:AP261)=0,"",AQ261-LOOKUP(2,1/(AI261:AP261<>""),AI261:AP261))) | IF(OR(F261="",AR261=""),"",IF(COUNT(AI261:AQ261)=0,"",AR261-LOOKUP(2,1/(AI261:AQ261<>""),AI261:AQ261))) | IF(OR(F261="",AS261=""),"",IF(COUNT(AI261:AR261)=0,"",AS261-LOOKUP(2,1/(AI261:AR261<>""),AI261:AR261))) | IF(OR(F261="",AT261=""),"",IF(COUNT(AI261:AS261)=0,"",AT261-LOOKUP(2,1/(AI261:AS261<>""),AI261:AS261))) | IF(OR(F261="",AU261=""),"",IF(COUNT(AI261:AT261)=0,"",AU261-LOOKUP(2,1/(AI261:AT261<>""),AI261:AT261))) | IF(OR(F261="",AV261=""),"",IF(COUNT(AI261:AU261)=0,"",AV261-LOOKUP(2,1/(AI261:AU261<>""),AI261:AU261))) | IF(J261="","All_Provinces",IFERROR(VLOOKUP(J261,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K261="","All_Districts",IFERROR(VLOOKUP(K261,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F262="","",ROW()-3) | AF2-WSM-01 | Package #1-AF2 WSM: Construction of Dara Garmak Check dam, located in Qadis districts of Badghis province | 1 of 1 | AF2-WSM-N-001 | Dara Garmak Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Qadis | Langar | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 131000 | IF(AQ262="","",AQ262) | 2026-12-05 | 8.9 | 2027-09-01 | IF(W262<>"",W262,IF(OR(T262="",V262=""),"",EDATE(T262,V262))) |  |  | PR to be Raised | Construction of the check dam will be completed in six months. Additional three months have been kept as slack period during Jan-March. | IF(F262="","",IF(COUNT(AI262:AV262)=0,IF(AA262="","Not started",AA262),SUBSTITUTE(LOOKUP(2,1/(AI262:AV262<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F262="",COUNT(AI262:AV262)=0),"",TODAY()-LOOKUP(2,1/(AI262:AV262<>""),AI262:AV262)) | IF(OR(F262="",COUNT(AI262:AV262)<2),"",LOOKUP(2,1/(AI262:AV262<>""),AI262:AV262)-MIN(AI262:AV262)) | IF(OR(AD262="",AC262="Not started",AC262=""),"",IFERROR(AD262-IF(VLOOKUP(AC262,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC262,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F262="","",IF(OR(AA262="Cancelled",AC262="Cancelled"),"Cancelled",IF(OR(AC262="Completed / Handover",Y262<>"",Z262>=100),"Completed — on track",IF(O262="Not awarded",IF(U262="",IF(X262="","No planned date",IF(TODAY()>X262,"Behind — past planned date",IF(X262-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U262,"Behind — award date passed",IF(U262-TODAY()<=30,"At risk — close to off track","On track"))),IF(X262="","No planned date",IF(AND(TODAY()>X262,OR(Z262="",Z262<100)),"Behind — past end date",IF(AND(T262<>"",X262<>"",Z262<>"",(Z262<100),((TODAY()-T262)/MAX(X262-T262,1)*100)-Z262>15),"Behind — progress lag",IF(AND(X262-TODAY()<=30,X262-TODAY()>=0,OR(Z262="",Z262<90)),"At risk — close to off track","On track")))))))) | IF(OR(F262="",AC262="Completed / Handover",AC262="Cancelled"),"",IF(O262="Not awarded",IF(U262<>"",U262-TODAY(),IF(X262="","",X262-TODAY())),IF(X262="","",X262-TODAY()))) | [14 empty] | IF(OR(F262="",AJ262=""),"",IF(COUNT(AI262:AI262)=0,"",AJ262-LOOKUP(2,1/(AI262:AI262<>""),AI262:AI262))) | IF(OR(F262="",AK262=""),"",IF(COUNT(AI262:AJ262)=0,"",AK262-LOOKUP(2,1/(AI262:AJ262<>""),AI262:AJ262))) | IF(OR(F262="",AL262=""),"",IF(COUNT(AI262:AK262)=0,"",AL262-LOOKUP(2,1/(AI262:AK262<>""),AI262:AK262))) | IF(OR(F262="",AM262=""),"",IF(COUNT(AI262:AL262)=0,"",AM262-LOOKUP(2,1/(AI262:AL262<>""),AI262:AL262))) | IF(OR(F262="",AN262=""),"",IF(COUNT(AI262:AM262)=0,"",AN262-LOOKUP(2,1/(AI262:AM262<>""),AI262:AM262))) | IF(OR(F262="",AO262=""),"",IF(COUNT(AI262:AN262)=0,"",AO262-LOOKUP(2,1/(AI262:AN262<>""),AI262:AN262))) | IF(OR(F262="",AP262=""),"",IF(COUNT(AI262:AO262)=0,"",AP262-LOOKUP(2,1/(AI262:AO262<>""),AI262:AO262))) | IF(OR(F262="",AQ262=""),"",IF(COUNT(AI262:AP262)=0,"",AQ262-LOOKUP(2,1/(AI262:AP262<>""),AI262:AP262))) | IF(OR(F262="",AR262=""),"",IF(COUNT(AI262:AQ262)=0,"",AR262-LOOKUP(2,1/(AI262:AQ262<>""),AI262:AQ262))) | IF(OR(F262="",AS262=""),"",IF(COUNT(AI262:AR262)=0,"",AS262-LOOKUP(2,1/(AI262:AR262<>""),AI262:AR262))) | IF(OR(F262="",AT262=""),"",IF(COUNT(AI262:AS262)=0,"",AT262-LOOKUP(2,1/(AI262:AS262<>""),AI262:AS262))) | IF(OR(F262="",AU262=""),"",IF(COUNT(AI262:AT262)=0,"",AU262-LOOKUP(2,1/(AI262:AT262<>""),AI262:AT262))) | IF(OR(F262="",AV262=""),"",IF(COUNT(AI262:AU262)=0,"",AV262-LOOKUP(2,1/(AI262:AU262<>""),AI262:AU262))) | IF(J262="","All_Provinces",IFERROR(VLOOKUP(J262,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K262="","All_Districts",IFERROR(VLOOKUP(K262,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F263="","",ROW()-3) | AF2-WSM-02 | Package #2 -AF2 WSM: Construction of 1. Dareh Shah Toot-1, 2. Dareh ShahToot-2, and 3. Jar Sono check dams in Obe District of Herat Province | 1 of 3 | AF2-WSM-A-001 | Dareh Shah Toot Check dam-1 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Obe | Gonabad, Qala Yar Mohammad Khan, Zori ha, Dasht Servan | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shams Afghan Vision Construction and Logistic Services (SAVCC) | 014/2026 | 194033 | IF(AQ263="","",AQ263) |  | 9.9 | 2026-12-08 | IF(W263<>"",W263,IF(OR(T263="",V263=""),"",EDATE(T263,V263))) |  | 95 | Under Construction | Expected to complete by the end of the contract NTE. | IF(F263="","",IF(COUNT(AI263:AV263)=0,IF(AA263="","Not started",AA263),SUBSTITUTE(LOOKUP(2,1/(AI263:AV263<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F263="",COUNT(AI263:AV263)=0),"",TODAY()-LOOKUP(2,1/(AI263:AV263<>""),AI263:AV263)) | IF(OR(F263="",COUNT(AI263:AV263)<2),"",LOOKUP(2,1/(AI263:AV263<>""),AI263:AV263)-MIN(AI263:AV263)) | IF(OR(AD263="",AC263="Not started",AC263=""),"",IFERROR(AD263-IF(VLOOKUP(AC263,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC263,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F263="","",IF(OR(AA263="Cancelled",AC263="Cancelled"),"Cancelled",IF(OR(AC263="Completed / Handover",Y263<>"",Z263>=100),"Completed — on track",IF(O263="Not awarded",IF(U263="",IF(X263="","No planned date",IF(TODAY()>X263,"Behind — past planned date",IF(X263-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U263,"Behind — award date passed",IF(U263-TODAY()<=30,"At risk — close to off track","On track"))),IF(X263="","No planned date",IF(AND(TODAY()>X263,OR(Z263="",Z263<100)),"Behind — past end date",IF(AND(T263<>"",X263<>"",Z263<>"",(Z263<100),((TODAY()-T263)/MAX(X263-T263,1)*100)-Z263>15),"Behind — progress lag",IF(AND(X263-TODAY()<=30,X263-TODAY()>=0,OR(Z263="",Z263<90)),"At risk — close to off track","On track")))))))) | IF(OR(F263="",AC263="Completed / Handover",AC263="Cancelled"),"",IF(O263="Not awarded",IF(U263<>"",U263-TODAY(),IF(X263="","",X263-TODAY())),IF(X263="","",X263-TODAY()))) | [8 empty] | 2026-02-09 | 2026-02-09 |  |  |  |  | IF(OR(F263="",AJ263=""),"",IF(COUNT(AI263:AI263)=0,"",AJ263-LOOKUP(2,1/(AI263:AI263<>""),AI263:AI263))) | IF(OR(F263="",AK263=""),"",IF(COUNT(AI263:AJ263)=0,"",AK263-LOOKUP(2,1/(AI263:AJ263<>""),AI263:AJ263))) | IF(OR(F263="",AL263=""),"",IF(COUNT(AI263:AK263)=0,"",AL263-LOOKUP(2,1/(AI263:AK263<>""),AI263:AK263))) | IF(OR(F263="",AM263=""),"",IF(COUNT(AI263:AL263)=0,"",AM263-LOOKUP(2,1/(AI263:AL263<>""),AI263:AL263))) | IF(OR(F263="",AN263=""),"",IF(COUNT(AI263:AM263)=0,"",AN263-LOOKUP(2,1/(AI263:AM263<>""),AI263:AM263))) | IF(OR(F263="",AO263=""),"",IF(COUNT(AI263:AN263)=0,"",AO263-LOOKUP(2,1/(AI263:AN263<>""),AI263:AN263))) | IF(OR(F263="",AP263=""),"",IF(COUNT(AI263:AO263)=0,"",AP263-LOOKUP(2,1/(AI263:AO263<>""),AI263:AO263))) | IF(OR(F263="",AQ263=""),"",IF(COUNT(AI263:AP263)=0,"",AQ263-LOOKUP(2,1/(AI263:AP263<>""),AI263:AP263))) | IF(OR(F263="",AR263=""),"",IF(COUNT(AI263:AQ263)=0,"",AR263-LOOKUP(2,1/(AI263:AQ263<>""),AI263:AQ263))) | IF(OR(F263="",AS263=""),"",IF(COUNT(AI263:AR263)=0,"",AS263-LOOKUP(2,1/(AI263:AR263<>""),AI263:AR263))) | IF(OR(F263="",AT263=""),"",IF(COUNT(AI263:AS263)=0,"",AT263-LOOKUP(2,1/(AI263:AS263<>""),AI263:AS263))) | IF(OR(F263="",AU263=""),"",IF(COUNT(AI263:AT263)=0,"",AU263-LOOKUP(2,1/(AI263:AT263<>""),AI263:AT263))) | IF(OR(F263="",AV263=""),"",IF(COUNT(AI263:AU263)=0,"",AV263-LOOKUP(2,1/(AI263:AU263<>""),AI263:AU263))) | IF(J263="","All_Provinces",IFERROR(VLOOKUP(J263,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K263="","All_Districts",IFERROR(VLOOKUP(K263,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F264="","",ROW()-3) | AF2-WSM-02 | Package #2 -AF2 WSM: Construction of 1. Dareh Shah Toot-1, 2. Dareh ShahToot-2, and 3. Jar Sono check dams in Obe District of Herat Province | 2 of 3 | AF2-WSM-A-002 | Dareh Shah Toot Check dam-2 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Obe |  | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shams Afghan Vision Construction and Logistic Services (SAVCC) | 014/2026 |  | IF(AQ264="","",AQ264) |  | 9.9 | 2026-12-08 | IF(W264<>"",W264,IF(OR(T264="",V264=""),"",EDATE(T264,V264))) |  | 75 | Under Construction | Expected to complete by the end of the contract NTE. | IF(F264="","",IF(COUNT(AI264:AV264)=0,IF(AA264="","Not started",AA264),SUBSTITUTE(LOOKUP(2,1/(AI264:AV264<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F264="",COUNT(AI264:AV264)=0),"",TODAY()-LOOKUP(2,1/(AI264:AV264<>""),AI264:AV264)) | IF(OR(F264="",COUNT(AI264:AV264)<2),"",LOOKUP(2,1/(AI264:AV264<>""),AI264:AV264)-MIN(AI264:AV264)) | IF(OR(AD264="",AC264="Not started",AC264=""),"",IFERROR(AD264-IF(VLOOKUP(AC264,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC264,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F264="","",IF(OR(AA264="Cancelled",AC264="Cancelled"),"Cancelled",IF(OR(AC264="Completed / Handover",Y264<>"",Z264>=100),"Completed — on track",IF(O264="Not awarded",IF(U264="",IF(X264="","No planned date",IF(TODAY()>X264,"Behind — past planned date",IF(X264-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U264,"Behind — award date passed",IF(U264-TODAY()<=30,"At risk — close to off track","On track"))),IF(X264="","No planned date",IF(AND(TODAY()>X264,OR(Z264="",Z264<100)),"Behind — past end date",IF(AND(T264<>"",X264<>"",Z264<>"",(Z264<100),((TODAY()-T264)/MAX(X264-T264,1)*100)-Z264>15),"Behind — progress lag",IF(AND(X264-TODAY()<=30,X264-TODAY()>=0,OR(Z264="",Z264<90)),"At risk — close to off track","On track")))))))) | IF(OR(F264="",AC264="Completed / Handover",AC264="Cancelled"),"",IF(O264="Not awarded",IF(U264<>"",U264-TODAY(),IF(X264="","",X264-TODAY())),IF(X264="","",X264-TODAY()))) | [8 empty] | 2026-02-09 | 2026-02-09 |  |  |  |  | IF(OR(F264="",AJ264=""),"",IF(COUNT(AI264:AI264)=0,"",AJ264-LOOKUP(2,1/(AI264:AI264<>""),AI264:AI264))) | IF(OR(F264="",AK264=""),"",IF(COUNT(AI264:AJ264)=0,"",AK264-LOOKUP(2,1/(AI264:AJ264<>""),AI264:AJ264))) | IF(OR(F264="",AL264=""),"",IF(COUNT(AI264:AK264)=0,"",AL264-LOOKUP(2,1/(AI264:AK264<>""),AI264:AK264))) | IF(OR(F264="",AM264=""),"",IF(COUNT(AI264:AL264)=0,"",AM264-LOOKUP(2,1/(AI264:AL264<>""),AI264:AL264))) | IF(OR(F264="",AN264=""),"",IF(COUNT(AI264:AM264)=0,"",AN264-LOOKUP(2,1/(AI264:AM264<>""),AI264:AM264))) | IF(OR(F264="",AO264=""),"",IF(COUNT(AI264:AN264)=0,"",AO264-LOOKUP(2,1/(AI264:AN264<>""),AI264:AN264))) | IF(OR(F264="",AP264=""),"",IF(COUNT(AI264:AO264)=0,"",AP264-LOOKUP(2,1/(AI264:AO264<>""),AI264:AO264))) | IF(OR(F264="",AQ264=""),"",IF(COUNT(AI264:AP264)=0,"",AQ264-LOOKUP(2,1/(AI264:AP264<>""),AI264:AP264))) | IF(OR(F264="",AR264=""),"",IF(COUNT(AI264:AQ264)=0,"",AR264-LOOKUP(2,1/(AI264:AQ264<>""),AI264:AQ264))) | IF(OR(F264="",AS264=""),"",IF(COUNT(AI264:AR264)=0,"",AS264-LOOKUP(2,1/(AI264:AR264<>""),AI264:AR264))) | IF(OR(F264="",AT264=""),"",IF(COUNT(AI264:AS264)=0,"",AT264-LOOKUP(2,1/(AI264:AS264<>""),AI264:AS264))) | IF(OR(F264="",AU264=""),"",IF(COUNT(AI264:AT264)=0,"",AU264-LOOKUP(2,1/(AI264:AT264<>""),AI264:AT264))) | IF(OR(F264="",AV264=""),"",IF(COUNT(AI264:AU264)=0,"",AV264-LOOKUP(2,1/(AI264:AU264<>""),AI264:AU264))) | IF(J264="","All_Provinces",IFERROR(VLOOKUP(J264,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K264="","All_Districts",IFERROR(VLOOKUP(K264,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F265="","",ROW()-3) | AF2-WSM-02 | Package #2 -AF2 WSM: Construction of 1. Dareh Shah Toot-1, 2. Dareh ShahToot-2, and 3. Jar Sono check dams in Obe District of Herat Province | 3 of 3 | AF2-WSM-A-003 | Jar Sunu Check dam-3 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Obe |  | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shams Afghan Vision Construction and Logistic Services (SAVCC) | 014/2026 |  | IF(AQ265="","",AQ265) |  | 9.9 | 2026-12-08 | IF(W265<>"",W265,IF(OR(T265="",V265=""),"",EDATE(T265,V265))) |  | 55 | Under Construction | Expected to complete by the end of the contract NTE. | IF(F265="","",IF(COUNT(AI265:AV265)=0,IF(AA265="","Not started",AA265),SUBSTITUTE(LOOKUP(2,1/(AI265:AV265<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F265="",COUNT(AI265:AV265)=0),"",TODAY()-LOOKUP(2,1/(AI265:AV265<>""),AI265:AV265)) | IF(OR(F265="",COUNT(AI265:AV265)<2),"",LOOKUP(2,1/(AI265:AV265<>""),AI265:AV265)-MIN(AI265:AV265)) | IF(OR(AD265="",AC265="Not started",AC265=""),"",IFERROR(AD265-IF(VLOOKUP(AC265,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC265,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F265="","",IF(OR(AA265="Cancelled",AC265="Cancelled"),"Cancelled",IF(OR(AC265="Completed / Handover",Y265<>"",Z265>=100),"Completed — on track",IF(O265="Not awarded",IF(U265="",IF(X265="","No planned date",IF(TODAY()>X265,"Behind — past planned date",IF(X265-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U265,"Behind — award date passed",IF(U265-TODAY()<=30,"At risk — close to off track","On track"))),IF(X265="","No planned date",IF(AND(TODAY()>X265,OR(Z265="",Z265<100)),"Behind — past end date",IF(AND(T265<>"",X265<>"",Z265<>"",(Z265<100),((TODAY()-T265)/MAX(X265-T265,1)*100)-Z265>15),"Behind — progress lag",IF(AND(X265-TODAY()<=30,X265-TODAY()>=0,OR(Z265="",Z265<90)),"At risk — close to off track","On track")))))))) | IF(OR(F265="",AC265="Completed / Handover",AC265="Cancelled"),"",IF(O265="Not awarded",IF(U265<>"",U265-TODAY(),IF(X265="","",X265-TODAY())),IF(X265="","",X265-TODAY()))) | [8 empty] | 2026-02-09 | 2026-02-09 |  |  |  |  | IF(OR(F265="",AJ265=""),"",IF(COUNT(AI265:AI265)=0,"",AJ265-LOOKUP(2,1/(AI265:AI265<>""),AI265:AI265))) | IF(OR(F265="",AK265=""),"",IF(COUNT(AI265:AJ265)=0,"",AK265-LOOKUP(2,1/(AI265:AJ265<>""),AI265:AJ265))) | IF(OR(F265="",AL265=""),"",IF(COUNT(AI265:AK265)=0,"",AL265-LOOKUP(2,1/(AI265:AK265<>""),AI265:AK265))) | IF(OR(F265="",AM265=""),"",IF(COUNT(AI265:AL265)=0,"",AM265-LOOKUP(2,1/(AI265:AL265<>""),AI265:AL265))) | IF(OR(F265="",AN265=""),"",IF(COUNT(AI265:AM265)=0,"",AN265-LOOKUP(2,1/(AI265:AM265<>""),AI265:AM265))) | IF(OR(F265="",AO265=""),"",IF(COUNT(AI265:AN265)=0,"",AO265-LOOKUP(2,1/(AI265:AN265<>""),AI265:AN265))) | IF(OR(F265="",AP265=""),"",IF(COUNT(AI265:AO265)=0,"",AP265-LOOKUP(2,1/(AI265:AO265<>""),AI265:AO265))) | IF(OR(F265="",AQ265=""),"",IF(COUNT(AI265:AP265)=0,"",AQ265-LOOKUP(2,1/(AI265:AP265<>""),AI265:AP265))) | IF(OR(F265="",AR265=""),"",IF(COUNT(AI265:AQ265)=0,"",AR265-LOOKUP(2,1/(AI265:AQ265<>""),AI265:AQ265))) | IF(OR(F265="",AS265=""),"",IF(COUNT(AI265:AR265)=0,"",AS265-LOOKUP(2,1/(AI265:AR265<>""),AI265:AR265))) | IF(OR(F265="",AT265=""),"",IF(COUNT(AI265:AS265)=0,"",AT265-LOOKUP(2,1/(AI265:AS265<>""),AI265:AS265))) | IF(OR(F265="",AU265=""),"",IF(COUNT(AI265:AT265)=0,"",AU265-LOOKUP(2,1/(AI265:AT265<>""),AI265:AT265))) | IF(OR(F265="",AV265=""),"",IF(COUNT(AI265:AU265)=0,"",AV265-LOOKUP(2,1/(AI265:AU265<>""),AI265:AU265))) | IF(J265="","All_Provinces",IFERROR(VLOOKUP(J265,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K265="","All_Districts",IFERROR(VLOOKUP(K265,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F266="","",ROW()-3) | AF2-WSM-03 | Package #3 -AF2 WSM: Construction of Koklam three Check Dams (# 1, # 2 and # 3 ) in Kushk-e-Kohna District of Herat Province | 1 of 3 | AF2-WSM-A-004 | Baland Bazar, Jar Ahmad Check Dam # 2 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Koshk-e-Kohna |  | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Afghan Aakam Construction and Road Company. JV with D- Amini Mashwani Construction Company (AACC) | 006/2026 | 68058.6 | IF(AQ266="","",AQ266) |  | 10 | 2026-11-20 | IF(W266<>"",W266,IF(OR(T266="",V266=""),"",EDATE(T266,V266))) |  | 70 | Under Construction | Expected to complete by the end of the contract NTE. | IF(F266="","",IF(COUNT(AI266:AV266)=0,IF(AA266="","Not started",AA266),SUBSTITUTE(LOOKUP(2,1/(AI266:AV266<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F266="",COUNT(AI266:AV266)=0),"",TODAY()-LOOKUP(2,1/(AI266:AV266<>""),AI266:AV266)) | IF(OR(F266="",COUNT(AI266:AV266)<2),"",LOOKUP(2,1/(AI266:AV266<>""),AI266:AV266)-MIN(AI266:AV266)) | IF(OR(AD266="",AC266="Not started",AC266=""),"",IFERROR(AD266-IF(VLOOKUP(AC266,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC266,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F266="","",IF(OR(AA266="Cancelled",AC266="Cancelled"),"Cancelled",IF(OR(AC266="Completed / Handover",Y266<>"",Z266>=100),"Completed — on track",IF(O266="Not awarded",IF(U266="",IF(X266="","No planned date",IF(TODAY()>X266,"Behind — past planned date",IF(X266-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U266,"Behind — award date passed",IF(U266-TODAY()<=30,"At risk — close to off track","On track"))),IF(X266="","No planned date",IF(AND(TODAY()>X266,OR(Z266="",Z266<100)),"Behind — past end date",IF(AND(T266<>"",X266<>"",Z266<>"",(Z266<100),((TODAY()-T266)/MAX(X266-T266,1)*100)-Z266>15),"Behind — progress lag",IF(AND(X266-TODAY()<=30,X266-TODAY()>=0,OR(Z266="",Z266<90)),"At risk — close to off track","On track")))))))) | IF(OR(F266="",AC266="Completed / Handover",AC266="Cancelled"),"",IF(O266="Not awarded",IF(U266<>"",U266-TODAY(),IF(X266="","",X266-TODAY())),IF(X266="","",X266-TODAY()))) | [8 empty] | 2026-01-21 | 2026-01-21 |  |  |  |  | IF(OR(F266="",AJ266=""),"",IF(COUNT(AI266:AI266)=0,"",AJ266-LOOKUP(2,1/(AI266:AI266<>""),AI266:AI266))) | IF(OR(F266="",AK266=""),"",IF(COUNT(AI266:AJ266)=0,"",AK266-LOOKUP(2,1/(AI266:AJ266<>""),AI266:AJ266))) | IF(OR(F266="",AL266=""),"",IF(COUNT(AI266:AK266)=0,"",AL266-LOOKUP(2,1/(AI266:AK266<>""),AI266:AK266))) | IF(OR(F266="",AM266=""),"",IF(COUNT(AI266:AL266)=0,"",AM266-LOOKUP(2,1/(AI266:AL266<>""),AI266:AL266))) | IF(OR(F266="",AN266=""),"",IF(COUNT(AI266:AM266)=0,"",AN266-LOOKUP(2,1/(AI266:AM266<>""),AI266:AM266))) | IF(OR(F266="",AO266=""),"",IF(COUNT(AI266:AN266)=0,"",AO266-LOOKUP(2,1/(AI266:AN266<>""),AI266:AN266))) | IF(OR(F266="",AP266=""),"",IF(COUNT(AI266:AO266)=0,"",AP266-LOOKUP(2,1/(AI266:AO266<>""),AI266:AO266))) | IF(OR(F266="",AQ266=""),"",IF(COUNT(AI266:AP266)=0,"",AQ266-LOOKUP(2,1/(AI266:AP266<>""),AI266:AP266))) | IF(OR(F266="",AR266=""),"",IF(COUNT(AI266:AQ266)=0,"",AR266-LOOKUP(2,1/(AI266:AQ266<>""),AI266:AQ266))) | IF(OR(F266="",AS266=""),"",IF(COUNT(AI266:AR266)=0,"",AS266-LOOKUP(2,1/(AI266:AR266<>""),AI266:AR266))) | IF(OR(F266="",AT266=""),"",IF(COUNT(AI266:AS266)=0,"",AT266-LOOKUP(2,1/(AI266:AS266<>""),AI266:AS266))) | IF(OR(F266="",AU266=""),"",IF(COUNT(AI266:AT266)=0,"",AU266-LOOKUP(2,1/(AI266:AT266<>""),AI266:AT266))) | IF(OR(F266="",AV266=""),"",IF(COUNT(AI266:AU266)=0,"",AV266-LOOKUP(2,1/(AI266:AU266<>""),AI266:AU266))) | IF(J266="","All_Provinces",IFERROR(VLOOKUP(J266,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K266="","All_Districts",IFERROR(VLOOKUP(K266,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F267="","",ROW()-3) | AF2-WSM-03 | Package #3 -AF2 WSM: Construction of Koklam three Check Dams (# 1, # 2 and # 3 ) in Kushk-e-Kohna District of Herat Province | 2 of 3 | AF2-WSM-A-005 | Jar Koklam, Dara Koklam Bala Check Dam # 1 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Koshk-e-Kohna | Koklam village (Jar Koklam, Dara Koklam Bala, Baland Bazar, Jar Ahmad and Pastaliq Bazar) | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Afghan Aakam Construction and Road Company. JV with D- Amini Mashwani Construction Company (AACC) | 006/2026 | 71140.92 | IF(AQ267="","",AQ267) |  | 10 | 2026-11-20 | IF(W267<>"",W267,IF(OR(T267="",V267=""),"",EDATE(T267,V267))) |  | 89 | Under Construction | Expected to complete by the end of the contract NTE. | IF(F267="","",IF(COUNT(AI267:AV267)=0,IF(AA267="","Not started",AA267),SUBSTITUTE(LOOKUP(2,1/(AI267:AV267<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F267="",COUNT(AI267:AV267)=0),"",TODAY()-LOOKUP(2,1/(AI267:AV267<>""),AI267:AV267)) | IF(OR(F267="",COUNT(AI267:AV267)<2),"",LOOKUP(2,1/(AI267:AV267<>""),AI267:AV267)-MIN(AI267:AV267)) | IF(OR(AD267="",AC267="Not started",AC267=""),"",IFERROR(AD267-IF(VLOOKUP(AC267,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC267,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F267="","",IF(OR(AA267="Cancelled",AC267="Cancelled"),"Cancelled",IF(OR(AC267="Completed / Handover",Y267<>"",Z267>=100),"Completed — on track",IF(O267="Not awarded",IF(U267="",IF(X267="","No planned date",IF(TODAY()>X267,"Behind — past planned date",IF(X267-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U267,"Behind — award date passed",IF(U267-TODAY()<=30,"At risk — close to off track","On track"))),IF(X267="","No planned date",IF(AND(TODAY()>X267,OR(Z267="",Z267<100)),"Behind — past end date",IF(AND(T267<>"",X267<>"",Z267<>"",(Z267<100),((TODAY()-T267)/MAX(X267-T267,1)*100)-Z267>15),"Behind — progress lag",IF(AND(X267-TODAY()<=30,X267-TODAY()>=0,OR(Z267="",Z267<90)),"At risk — close to off track","On track")))))))) | IF(OR(F267="",AC267="Completed / Handover",AC267="Cancelled"),"",IF(O267="Not awarded",IF(U267<>"",U267-TODAY(),IF(X267="","",X267-TODAY())),IF(X267="","",X267-TODAY()))) | [8 empty] | 2026-01-21 | 2026-01-21 |  |  |  |  | IF(OR(F267="",AJ267=""),"",IF(COUNT(AI267:AI267)=0,"",AJ267-LOOKUP(2,1/(AI267:AI267<>""),AI267:AI267))) | IF(OR(F267="",AK267=""),"",IF(COUNT(AI267:AJ267)=0,"",AK267-LOOKUP(2,1/(AI267:AJ267<>""),AI267:AJ267))) | IF(OR(F267="",AL267=""),"",IF(COUNT(AI267:AK267)=0,"",AL267-LOOKUP(2,1/(AI267:AK267<>""),AI267:AK267))) | IF(OR(F267="",AM267=""),"",IF(COUNT(AI267:AL267)=0,"",AM267-LOOKUP(2,1/(AI267:AL267<>""),AI267:AL267))) | IF(OR(F267="",AN267=""),"",IF(COUNT(AI267:AM267)=0,"",AN267-LOOKUP(2,1/(AI267:AM267<>""),AI267:AM267))) | IF(OR(F267="",AO267=""),"",IF(COUNT(AI267:AN267)=0,"",AO267-LOOKUP(2,1/(AI267:AN267<>""),AI267:AN267))) | IF(OR(F267="",AP267=""),"",IF(COUNT(AI267:AO267)=0,"",AP267-LOOKUP(2,1/(AI267:AO267<>""),AI267:AO267))) | IF(OR(F267="",AQ267=""),"",IF(COUNT(AI267:AP267)=0,"",AQ267-LOOKUP(2,1/(AI267:AP267<>""),AI267:AP267))) | IF(OR(F267="",AR267=""),"",IF(COUNT(AI267:AQ267)=0,"",AR267-LOOKUP(2,1/(AI267:AQ267<>""),AI267:AQ267))) | IF(OR(F267="",AS267=""),"",IF(COUNT(AI267:AR267)=0,"",AS267-LOOKUP(2,1/(AI267:AR267<>""),AI267:AR267))) | IF(OR(F267="",AT267=""),"",IF(COUNT(AI267:AS267)=0,"",AT267-LOOKUP(2,1/(AI267:AS267<>""),AI267:AS267))) | IF(OR(F267="",AU267=""),"",IF(COUNT(AI267:AT267)=0,"",AU267-LOOKUP(2,1/(AI267:AT267<>""),AI267:AT267))) | IF(OR(F267="",AV267=""),"",IF(COUNT(AI267:AU267)=0,"",AV267-LOOKUP(2,1/(AI267:AU267<>""),AI267:AU267))) | IF(J267="","All_Provinces",IFERROR(VLOOKUP(J267,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K267="","All_Districts",IFERROR(VLOOKUP(K267,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F268="","",ROW()-3) | AF2-WSM-03 | Package #3 -AF2 WSM: Construction of Koklam three Check Dams (# 1, # 2 and # 3 ) in Kushk-e-Kohna District of Herat Province | 3 of 3 | AF2-WSM-A-006 | Pastaliq Bazar Check Dam # 3 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Herat | Koshk-e-Kohna |  | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Afghan Aakam Construction and Road Company. JV with D- Amini Mashwani Construction Company (AACC) | 006/2026 | 74256.68 | IF(AQ268="","",AQ268) |  | 10 | 2026-11-20 | IF(W268<>"",W268,IF(OR(T268="",V268=""),"",EDATE(T268,V268))) |  | 30 | Under Construction | Expected to complete by the end of the contract NTE. | IF(F268="","",IF(COUNT(AI268:AV268)=0,IF(AA268="","Not started",AA268),SUBSTITUTE(LOOKUP(2,1/(AI268:AV268<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F268="",COUNT(AI268:AV268)=0),"",TODAY()-LOOKUP(2,1/(AI268:AV268<>""),AI268:AV268)) | IF(OR(F268="",COUNT(AI268:AV268)<2),"",LOOKUP(2,1/(AI268:AV268<>""),AI268:AV268)-MIN(AI268:AV268)) | IF(OR(AD268="",AC268="Not started",AC268=""),"",IFERROR(AD268-IF(VLOOKUP(AC268,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC268,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F268="","",IF(OR(AA268="Cancelled",AC268="Cancelled"),"Cancelled",IF(OR(AC268="Completed / Handover",Y268<>"",Z268>=100),"Completed — on track",IF(O268="Not awarded",IF(U268="",IF(X268="","No planned date",IF(TODAY()>X268,"Behind — past planned date",IF(X268-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U268,"Behind — award date passed",IF(U268-TODAY()<=30,"At risk — close to off track","On track"))),IF(X268="","No planned date",IF(AND(TODAY()>X268,OR(Z268="",Z268<100)),"Behind — past end date",IF(AND(T268<>"",X268<>"",Z268<>"",(Z268<100),((TODAY()-T268)/MAX(X268-T268,1)*100)-Z268>15),"Behind — progress lag",IF(AND(X268-TODAY()<=30,X268-TODAY()>=0,OR(Z268="",Z268<90)),"At risk — close to off track","On track")))))))) | IF(OR(F268="",AC268="Completed / Handover",AC268="Cancelled"),"",IF(O268="Not awarded",IF(U268<>"",U268-TODAY(),IF(X268="","",X268-TODAY())),IF(X268="","",X268-TODAY()))) | [8 empty] | 2026-01-21 | 2026-01-21 |  |  |  |  | IF(OR(F268="",AJ268=""),"",IF(COUNT(AI268:AI268)=0,"",AJ268-LOOKUP(2,1/(AI268:AI268<>""),AI268:AI268))) | IF(OR(F268="",AK268=""),"",IF(COUNT(AI268:AJ268)=0,"",AK268-LOOKUP(2,1/(AI268:AJ268<>""),AI268:AJ268))) | IF(OR(F268="",AL268=""),"",IF(COUNT(AI268:AK268)=0,"",AL268-LOOKUP(2,1/(AI268:AK268<>""),AI268:AK268))) | IF(OR(F268="",AM268=""),"",IF(COUNT(AI268:AL268)=0,"",AM268-LOOKUP(2,1/(AI268:AL268<>""),AI268:AL268))) | IF(OR(F268="",AN268=""),"",IF(COUNT(AI268:AM268)=0,"",AN268-LOOKUP(2,1/(AI268:AM268<>""),AI268:AM268))) | IF(OR(F268="",AO268=""),"",IF(COUNT(AI268:AN268)=0,"",AO268-LOOKUP(2,1/(AI268:AN268<>""),AI268:AN268))) | IF(OR(F268="",AP268=""),"",IF(COUNT(AI268:AO268)=0,"",AP268-LOOKUP(2,1/(AI268:AO268<>""),AI268:AO268))) | IF(OR(F268="",AQ268=""),"",IF(COUNT(AI268:AP268)=0,"",AQ268-LOOKUP(2,1/(AI268:AP268<>""),AI268:AP268))) | IF(OR(F268="",AR268=""),"",IF(COUNT(AI268:AQ268)=0,"",AR268-LOOKUP(2,1/(AI268:AQ268<>""),AI268:AQ268))) | IF(OR(F268="",AS268=""),"",IF(COUNT(AI268:AR268)=0,"",AS268-LOOKUP(2,1/(AI268:AR268<>""),AI268:AR268))) | IF(OR(F268="",AT268=""),"",IF(COUNT(AI268:AS268)=0,"",AT268-LOOKUP(2,1/(AI268:AS268<>""),AI268:AS268))) | IF(OR(F268="",AU268=""),"",IF(COUNT(AI268:AT268)=0,"",AU268-LOOKUP(2,1/(AI268:AT268<>""),AI268:AT268))) | IF(OR(F268="",AV268=""),"",IF(COUNT(AI268:AU268)=0,"",AV268-LOOKUP(2,1/(AI268:AU268<>""),AI268:AU268))) | IF(J268="","All_Provinces",IFERROR(VLOOKUP(J268,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K268="","All_Districts",IFERROR(VLOOKUP(K268,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F269="","",ROW()-3) | AF2-WSM-04 | Package #4-AF2 WSM: Construction of .Qalai Gerd check dam in Firozkoh dustrict of Ghor province. | 1 of 1 | AF2-WSM-N-002 | Qalai Gerd Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Ghor | Firozkoh | Qalai Gerd | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 219000 | IF(AQ269="","",AQ269) | 2026-12-10 | 9.9 | 2027-10-06 | IF(W269<>"",W269,IF(OR(T269="",V269=""),"",EDATE(T269,V269))) |  |  | PR to be Raised | Construction of the check dam will be completed in seven months. Additional three months have been kept as slack period during Jan-March. | IF(F269="","",IF(COUNT(AI269:AV269)=0,IF(AA269="","Not started",AA269),SUBSTITUTE(LOOKUP(2,1/(AI269:AV269<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F269="",COUNT(AI269:AV269)=0),"",TODAY()-LOOKUP(2,1/(AI269:AV269<>""),AI269:AV269)) | IF(OR(F269="",COUNT(AI269:AV269)<2),"",LOOKUP(2,1/(AI269:AV269<>""),AI269:AV269)-MIN(AI269:AV269)) | IF(OR(AD269="",AC269="Not started",AC269=""),"",IFERROR(AD269-IF(VLOOKUP(AC269,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC269,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F269="","",IF(OR(AA269="Cancelled",AC269="Cancelled"),"Cancelled",IF(OR(AC269="Completed / Handover",Y269<>"",Z269>=100),"Completed — on track",IF(O269="Not awarded",IF(U269="",IF(X269="","No planned date",IF(TODAY()>X269,"Behind — past planned date",IF(X269-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U269,"Behind — award date passed",IF(U269-TODAY()<=30,"At risk — close to off track","On track"))),IF(X269="","No planned date",IF(AND(TODAY()>X269,OR(Z269="",Z269<100)),"Behind — past end date",IF(AND(T269<>"",X269<>"",Z269<>"",(Z269<100),((TODAY()-T269)/MAX(X269-T269,1)*100)-Z269>15),"Behind — progress lag",IF(AND(X269-TODAY()<=30,X269-TODAY()>=0,OR(Z269="",Z269<90)),"At risk — close to off track","On track")))))))) | IF(OR(F269="",AC269="Completed / Handover",AC269="Cancelled"),"",IF(O269="Not awarded",IF(U269<>"",U269-TODAY(),IF(X269="","",X269-TODAY())),IF(X269="","",X269-TODAY()))) | [14 empty] | IF(OR(F269="",AJ269=""),"",IF(COUNT(AI269:AI269)=0,"",AJ269-LOOKUP(2,1/(AI269:AI269<>""),AI269:AI269))) | IF(OR(F269="",AK269=""),"",IF(COUNT(AI269:AJ269)=0,"",AK269-LOOKUP(2,1/(AI269:AJ269<>""),AI269:AJ269))) | IF(OR(F269="",AL269=""),"",IF(COUNT(AI269:AK269)=0,"",AL269-LOOKUP(2,1/(AI269:AK269<>""),AI269:AK269))) | IF(OR(F269="",AM269=""),"",IF(COUNT(AI269:AL269)=0,"",AM269-LOOKUP(2,1/(AI269:AL269<>""),AI269:AL269))) | IF(OR(F269="",AN269=""),"",IF(COUNT(AI269:AM269)=0,"",AN269-LOOKUP(2,1/(AI269:AM269<>""),AI269:AM269))) | IF(OR(F269="",AO269=""),"",IF(COUNT(AI269:AN269)=0,"",AO269-LOOKUP(2,1/(AI269:AN269<>""),AI269:AN269))) | IF(OR(F269="",AP269=""),"",IF(COUNT(AI269:AO269)=0,"",AP269-LOOKUP(2,1/(AI269:AO269<>""),AI269:AO269))) | IF(OR(F269="",AQ269=""),"",IF(COUNT(AI269:AP269)=0,"",AQ269-LOOKUP(2,1/(AI269:AP269<>""),AI269:AP269))) | IF(OR(F269="",AR269=""),"",IF(COUNT(AI269:AQ269)=0,"",AR269-LOOKUP(2,1/(AI269:AQ269<>""),AI269:AQ269))) | IF(OR(F269="",AS269=""),"",IF(COUNT(AI269:AR269)=0,"",AS269-LOOKUP(2,1/(AI269:AR269<>""),AI269:AR269))) | IF(OR(F269="",AT269=""),"",IF(COUNT(AI269:AS269)=0,"",AT269-LOOKUP(2,1/(AI269:AS269<>""),AI269:AS269))) | IF(OR(F269="",AU269=""),"",IF(COUNT(AI269:AT269)=0,"",AU269-LOOKUP(2,1/(AI269:AT269<>""),AI269:AT269))) | IF(OR(F269="",AV269=""),"",IF(COUNT(AI269:AU269)=0,"",AV269-LOOKUP(2,1/(AI269:AU269<>""),AI269:AU269))) | IF(J269="","All_Provinces",IFERROR(VLOOKUP(J269,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K269="","All_Districts",IFERROR(VLOOKUP(K269,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F270="","",ROW()-3) | AF2-WSM-05 | Package #5-AF2 WSM/Part-2: Construction of 4 Check dams of 1.Farman Khil and 2.Kharoti in Qarghaee district of Laghman province; 3. Lokhy Solozi and 4. Lala Kali in Chaparhar districts of Nangarhar province. | 1 of 4 | AF2-WSM-A-007 | 1. Farman khill Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Laghman | Qarghaee | Farmankhil | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Khaliqi Building & Road Construction Company (KBRCC) | 040/2026 | 29781.88 | IF(AQ270="","",AQ270) |  | 5 | 2026-10-29 | IF(W270<>"",W270,IF(OR(T270="",V270=""),"",EDATE(T270,V270))) |  | 50 | Under Construction | A check dam, a pond and a social structure. Contract extension needs to be sought. | IF(F270="","",IF(COUNT(AI270:AV270)=0,IF(AA270="","Not started",AA270),SUBSTITUTE(LOOKUP(2,1/(AI270:AV270<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F270="",COUNT(AI270:AV270)=0),"",TODAY()-LOOKUP(2,1/(AI270:AV270<>""),AI270:AV270)) | IF(OR(F270="",COUNT(AI270:AV270)<2),"",LOOKUP(2,1/(AI270:AV270<>""),AI270:AV270)-MIN(AI270:AV270)) | IF(OR(AD270="",AC270="Not started",AC270=""),"",IFERROR(AD270-IF(VLOOKUP(AC270,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC270,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F270="","",IF(OR(AA270="Cancelled",AC270="Cancelled"),"Cancelled",IF(OR(AC270="Completed / Handover",Y270<>"",Z270>=100),"Completed — on track",IF(O270="Not awarded",IF(U270="",IF(X270="","No planned date",IF(TODAY()>X270,"Behind — past planned date",IF(X270-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U270,"Behind — award date passed",IF(U270-TODAY()<=30,"At risk — close to off track","On track"))),IF(X270="","No planned date",IF(AND(TODAY()>X270,OR(Z270="",Z270<100)),"Behind — past end date",IF(AND(T270<>"",X270<>"",Z270<>"",(Z270<100),((TODAY()-T270)/MAX(X270-T270,1)*100)-Z270>15),"Behind — progress lag",IF(AND(X270-TODAY()<=30,X270-TODAY()>=0,OR(Z270="",Z270<90)),"At risk — close to off track","On track")))))))) | IF(OR(F270="",AC270="Completed / Handover",AC270="Cancelled"),"",IF(O270="Not awarded",IF(U270<>"",U270-TODAY(),IF(X270="","",X270-TODAY())),IF(X270="","",X270-TODAY()))) | [8 empty] | 2026-05-30 | 2026-05-30 |  |  |  |  | IF(OR(F270="",AJ270=""),"",IF(COUNT(AI270:AI270)=0,"",AJ270-LOOKUP(2,1/(AI270:AI270<>""),AI270:AI270))) | IF(OR(F270="",AK270=""),"",IF(COUNT(AI270:AJ270)=0,"",AK270-LOOKUP(2,1/(AI270:AJ270<>""),AI270:AJ270))) | IF(OR(F270="",AL270=""),"",IF(COUNT(AI270:AK270)=0,"",AL270-LOOKUP(2,1/(AI270:AK270<>""),AI270:AK270))) | IF(OR(F270="",AM270=""),"",IF(COUNT(AI270:AL270)=0,"",AM270-LOOKUP(2,1/(AI270:AL270<>""),AI270:AL270))) | IF(OR(F270="",AN270=""),"",IF(COUNT(AI270:AM270)=0,"",AN270-LOOKUP(2,1/(AI270:AM270<>""),AI270:AM270))) | IF(OR(F270="",AO270=""),"",IF(COUNT(AI270:AN270)=0,"",AO270-LOOKUP(2,1/(AI270:AN270<>""),AI270:AN270))) | IF(OR(F270="",AP270=""),"",IF(COUNT(AI270:AO270)=0,"",AP270-LOOKUP(2,1/(AI270:AO270<>""),AI270:AO270))) | IF(OR(F270="",AQ270=""),"",IF(COUNT(AI270:AP270)=0,"",AQ270-LOOKUP(2,1/(AI270:AP270<>""),AI270:AP270))) | IF(OR(F270="",AR270=""),"",IF(COUNT(AI270:AQ270)=0,"",AR270-LOOKUP(2,1/(AI270:AQ270<>""),AI270:AQ270))) | IF(OR(F270="",AS270=""),"",IF(COUNT(AI270:AR270)=0,"",AS270-LOOKUP(2,1/(AI270:AR270<>""),AI270:AR270))) | IF(OR(F270="",AT270=""),"",IF(COUNT(AI270:AS270)=0,"",AT270-LOOKUP(2,1/(AI270:AS270<>""),AI270:AS270))) | IF(OR(F270="",AU270=""),"",IF(COUNT(AI270:AT270)=0,"",AU270-LOOKUP(2,1/(AI270:AT270<>""),AI270:AT270))) | IF(OR(F270="",AV270=""),"",IF(COUNT(AI270:AU270)=0,"",AV270-LOOKUP(2,1/(AI270:AU270<>""),AI270:AU270))) | IF(J270="","All_Provinces",IFERROR(VLOOKUP(J270,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K270="","All_Districts",IFERROR(VLOOKUP(K270,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F271="","",ROW()-3) | AF2-WSM-05 | Package #5-AF2 WSM/Part-2: Construction of 4 Check dams of 1.Farman Khil and 2.Kharoti in Qarghaee district of Laghman province; 3. Lokhy Solozi and 4. Lala Kali in Chaparhar districts of Nangarhar province. | 2 of 4 | AF2-WSM-A-008 | 2. Kharoti Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Laghman | Qarghaee | Kharoti | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Khaliqi Building & Road Construction Company (KBRCC) | 040/2026 | 24682.65 | IF(AQ271="","",AQ271) |  | 5 | 2026-10-29 | IF(W271<>"",W271,IF(OR(T271="",V271=""),"",EDATE(T271,V271))) |  | 68 | Under Construction | A check dam, a pond and a social structure. Contract extension needs to be sought. | IF(F271="","",IF(COUNT(AI271:AV271)=0,IF(AA271="","Not started",AA271),SUBSTITUTE(LOOKUP(2,1/(AI271:AV271<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F271="",COUNT(AI271:AV271)=0),"",TODAY()-LOOKUP(2,1/(AI271:AV271<>""),AI271:AV271)) | IF(OR(F271="",COUNT(AI271:AV271)<2),"",LOOKUP(2,1/(AI271:AV271<>""),AI271:AV271)-MIN(AI271:AV271)) | IF(OR(AD271="",AC271="Not started",AC271=""),"",IFERROR(AD271-IF(VLOOKUP(AC271,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC271,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F271="","",IF(OR(AA271="Cancelled",AC271="Cancelled"),"Cancelled",IF(OR(AC271="Completed / Handover",Y271<>"",Z271>=100),"Completed — on track",IF(O271="Not awarded",IF(U271="",IF(X271="","No planned date",IF(TODAY()>X271,"Behind — past planned date",IF(X271-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U271,"Behind — award date passed",IF(U271-TODAY()<=30,"At risk — close to off track","On track"))),IF(X271="","No planned date",IF(AND(TODAY()>X271,OR(Z271="",Z271<100)),"Behind — past end date",IF(AND(T271<>"",X271<>"",Z271<>"",(Z271<100),((TODAY()-T271)/MAX(X271-T271,1)*100)-Z271>15),"Behind — progress lag",IF(AND(X271-TODAY()<=30,X271-TODAY()>=0,OR(Z271="",Z271<90)),"At risk — close to off track","On track")))))))) | IF(OR(F271="",AC271="Completed / Handover",AC271="Cancelled"),"",IF(O271="Not awarded",IF(U271<>"",U271-TODAY(),IF(X271="","",X271-TODAY())),IF(X271="","",X271-TODAY()))) | [8 empty] | 2026-05-30 | 2026-05-30 |  |  |  |  | IF(OR(F271="",AJ271=""),"",IF(COUNT(AI271:AI271)=0,"",AJ271-LOOKUP(2,1/(AI271:AI271<>""),AI271:AI271))) | IF(OR(F271="",AK271=""),"",IF(COUNT(AI271:AJ271)=0,"",AK271-LOOKUP(2,1/(AI271:AJ271<>""),AI271:AJ271))) | IF(OR(F271="",AL271=""),"",IF(COUNT(AI271:AK271)=0,"",AL271-LOOKUP(2,1/(AI271:AK271<>""),AI271:AK271))) | IF(OR(F271="",AM271=""),"",IF(COUNT(AI271:AL271)=0,"",AM271-LOOKUP(2,1/(AI271:AL271<>""),AI271:AL271))) | IF(OR(F271="",AN271=""),"",IF(COUNT(AI271:AM271)=0,"",AN271-LOOKUP(2,1/(AI271:AM271<>""),AI271:AM271))) | IF(OR(F271="",AO271=""),"",IF(COUNT(AI271:AN271)=0,"",AO271-LOOKUP(2,1/(AI271:AN271<>""),AI271:AN271))) | IF(OR(F271="",AP271=""),"",IF(COUNT(AI271:AO271)=0,"",AP271-LOOKUP(2,1/(AI271:AO271<>""),AI271:AO271))) | IF(OR(F271="",AQ271=""),"",IF(COUNT(AI271:AP271)=0,"",AQ271-LOOKUP(2,1/(AI271:AP271<>""),AI271:AP271))) | IF(OR(F271="",AR271=""),"",IF(COUNT(AI271:AQ271)=0,"",AR271-LOOKUP(2,1/(AI271:AQ271<>""),AI271:AQ271))) | IF(OR(F271="",AS271=""),"",IF(COUNT(AI271:AR271)=0,"",AS271-LOOKUP(2,1/(AI271:AR271<>""),AI271:AR271))) | IF(OR(F271="",AT271=""),"",IF(COUNT(AI271:AS271)=0,"",AT271-LOOKUP(2,1/(AI271:AS271<>""),AI271:AS271))) | IF(OR(F271="",AU271=""),"",IF(COUNT(AI271:AT271)=0,"",AU271-LOOKUP(2,1/(AI271:AT271<>""),AI271:AT271))) | IF(OR(F271="",AV271=""),"",IF(COUNT(AI271:AU271)=0,"",AV271-LOOKUP(2,1/(AI271:AU271<>""),AI271:AU271))) | IF(J271="","All_Provinces",IFERROR(VLOOKUP(J271,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K271="","All_Districts",IFERROR(VLOOKUP(K271,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F272="","",ROW()-3) | AF2-WSM-05 | Package #5-AF2 WSM/Part-2: Construction of 4 Check dams of 1.Farman Khil and 2.Kharoti in Qarghaee district of Laghman province; 3. Lokhy Solozi and 4. Lala Kali in Chaparhar districts of Nangarhar province. | 3 of 4 | AF2-WSM-A-009 | 3. Lokhy Solozi Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Chaparhar | Lokhy Solozi | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Khaliqi Building & Road Construction Company (KBRCC) | 040/2026 | 38189.61 | IF(AQ272="","",AQ272) |  | 5 | 2026-10-29 | IF(W272<>"",W272,IF(OR(T272="",V272=""),"",EDATE(T272,V272))) |  | 60 | Under Construction | A check dam, a pond and a social structure. Contract extension needs to be sought. | IF(F272="","",IF(COUNT(AI272:AV272)=0,IF(AA272="","Not started",AA272),SUBSTITUTE(LOOKUP(2,1/(AI272:AV272<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F272="",COUNT(AI272:AV272)=0),"",TODAY()-LOOKUP(2,1/(AI272:AV272<>""),AI272:AV272)) | IF(OR(F272="",COUNT(AI272:AV272)<2),"",LOOKUP(2,1/(AI272:AV272<>""),AI272:AV272)-MIN(AI272:AV272)) | IF(OR(AD272="",AC272="Not started",AC272=""),"",IFERROR(AD272-IF(VLOOKUP(AC272,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC272,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F272="","",IF(OR(AA272="Cancelled",AC272="Cancelled"),"Cancelled",IF(OR(AC272="Completed / Handover",Y272<>"",Z272>=100),"Completed — on track",IF(O272="Not awarded",IF(U272="",IF(X272="","No planned date",IF(TODAY()>X272,"Behind — past planned date",IF(X272-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U272,"Behind — award date passed",IF(U272-TODAY()<=30,"At risk — close to off track","On track"))),IF(X272="","No planned date",IF(AND(TODAY()>X272,OR(Z272="",Z272<100)),"Behind — past end date",IF(AND(T272<>"",X272<>"",Z272<>"",(Z272<100),((TODAY()-T272)/MAX(X272-T272,1)*100)-Z272>15),"Behind — progress lag",IF(AND(X272-TODAY()<=30,X272-TODAY()>=0,OR(Z272="",Z272<90)),"At risk — close to off track","On track")))))))) | IF(OR(F272="",AC272="Completed / Handover",AC272="Cancelled"),"",IF(O272="Not awarded",IF(U272<>"",U272-TODAY(),IF(X272="","",X272-TODAY())),IF(X272="","",X272-TODAY()))) | [8 empty] | 2026-05-30 | 2026-05-30 |  |  |  |  | IF(OR(F272="",AJ272=""),"",IF(COUNT(AI272:AI272)=0,"",AJ272-LOOKUP(2,1/(AI272:AI272<>""),AI272:AI272))) | IF(OR(F272="",AK272=""),"",IF(COUNT(AI272:AJ272)=0,"",AK272-LOOKUP(2,1/(AI272:AJ272<>""),AI272:AJ272))) | IF(OR(F272="",AL272=""),"",IF(COUNT(AI272:AK272)=0,"",AL272-LOOKUP(2,1/(AI272:AK272<>""),AI272:AK272))) | IF(OR(F272="",AM272=""),"",IF(COUNT(AI272:AL272)=0,"",AM272-LOOKUP(2,1/(AI272:AL272<>""),AI272:AL272))) | IF(OR(F272="",AN272=""),"",IF(COUNT(AI272:AM272)=0,"",AN272-LOOKUP(2,1/(AI272:AM272<>""),AI272:AM272))) | IF(OR(F272="",AO272=""),"",IF(COUNT(AI272:AN272)=0,"",AO272-LOOKUP(2,1/(AI272:AN272<>""),AI272:AN272))) | IF(OR(F272="",AP272=""),"",IF(COUNT(AI272:AO272)=0,"",AP272-LOOKUP(2,1/(AI272:AO272<>""),AI272:AO272))) | IF(OR(F272="",AQ272=""),"",IF(COUNT(AI272:AP272)=0,"",AQ272-LOOKUP(2,1/(AI272:AP272<>""),AI272:AP272))) | IF(OR(F272="",AR272=""),"",IF(COUNT(AI272:AQ272)=0,"",AR272-LOOKUP(2,1/(AI272:AQ272<>""),AI272:AQ272))) | IF(OR(F272="",AS272=""),"",IF(COUNT(AI272:AR272)=0,"",AS272-LOOKUP(2,1/(AI272:AR272<>""),AI272:AR272))) | IF(OR(F272="",AT272=""),"",IF(COUNT(AI272:AS272)=0,"",AT272-LOOKUP(2,1/(AI272:AS272<>""),AI272:AS272))) | IF(OR(F272="",AU272=""),"",IF(COUNT(AI272:AT272)=0,"",AU272-LOOKUP(2,1/(AI272:AT272<>""),AI272:AT272))) | IF(OR(F272="",AV272=""),"",IF(COUNT(AI272:AU272)=0,"",AV272-LOOKUP(2,1/(AI272:AU272<>""),AI272:AU272))) | IF(J272="","All_Provinces",IFERROR(VLOOKUP(J272,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K272="","All_Districts",IFERROR(VLOOKUP(K272,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F273="","",ROW()-3) | AF2-WSM-05 | Package #5-AF2 WSM/Part-2: Construction of 4 Check dams of 1.Farman Khil and 2.Kharoti in Qarghaee district of Laghman province; 3. Lokhy Solozi and 4. Lala Kali in Chaparhar districts of Nangarhar province. | 4 of 4 | AF2-WSM-A-010 | 4. Lala Kali/Ranju Ghar Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Chaparhar | Lala Kali/Ranjo ghar | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Khaliqi Building & Road Construction Company (KBRCC) | 040/2026 | 17344.51 | IF(AQ273="","",AQ273) |  | 5 | 2026-10-29 | IF(W273<>"",W273,IF(OR(T273="",V273=""),"",EDATE(T273,V273))) |  | 0 | Awarded | A check dam, a pond and a social structure. Contract extension needs to be sought. | IF(F273="","",IF(COUNT(AI273:AV273)=0,IF(AA273="","Not started",AA273),SUBSTITUTE(LOOKUP(2,1/(AI273:AV273<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F273="",COUNT(AI273:AV273)=0),"",TODAY()-LOOKUP(2,1/(AI273:AV273<>""),AI273:AV273)) | IF(OR(F273="",COUNT(AI273:AV273)<2),"",LOOKUP(2,1/(AI273:AV273<>""),AI273:AV273)-MIN(AI273:AV273)) | IF(OR(AD273="",AC273="Not started",AC273=""),"",IFERROR(AD273-IF(VLOOKUP(AC273,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC273,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F273="","",IF(OR(AA273="Cancelled",AC273="Cancelled"),"Cancelled",IF(OR(AC273="Completed / Handover",Y273<>"",Z273>=100),"Completed — on track",IF(O273="Not awarded",IF(U273="",IF(X273="","No planned date",IF(TODAY()>X273,"Behind — past planned date",IF(X273-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U273,"Behind — award date passed",IF(U273-TODAY()<=30,"At risk — close to off track","On track"))),IF(X273="","No planned date",IF(AND(TODAY()>X273,OR(Z273="",Z273<100)),"Behind — past end date",IF(AND(T273<>"",X273<>"",Z273<>"",(Z273<100),((TODAY()-T273)/MAX(X273-T273,1)*100)-Z273>15),"Behind — progress lag",IF(AND(X273-TODAY()<=30,X273-TODAY()>=0,OR(Z273="",Z273<90)),"At risk — close to off track","On track")))))))) | IF(OR(F273="",AC273="Completed / Handover",AC273="Cancelled"),"",IF(O273="Not awarded",IF(U273<>"",U273-TODAY(),IF(X273="","",X273-TODAY())),IF(X273="","",X273-TODAY()))) | [8 empty] | 2026-05-30 | [5 empty] | IF(OR(F273="",AJ273=""),"",IF(COUNT(AI273:AI273)=0,"",AJ273-LOOKUP(2,1/(AI273:AI273<>""),AI273:AI273))) | IF(OR(F273="",AK273=""),"",IF(COUNT(AI273:AJ273)=0,"",AK273-LOOKUP(2,1/(AI273:AJ273<>""),AI273:AJ273))) | IF(OR(F273="",AL273=""),"",IF(COUNT(AI273:AK273)=0,"",AL273-LOOKUP(2,1/(AI273:AK273<>""),AI273:AK273))) | IF(OR(F273="",AM273=""),"",IF(COUNT(AI273:AL273)=0,"",AM273-LOOKUP(2,1/(AI273:AL273<>""),AI273:AL273))) | IF(OR(F273="",AN273=""),"",IF(COUNT(AI273:AM273)=0,"",AN273-LOOKUP(2,1/(AI273:AM273<>""),AI273:AM273))) | IF(OR(F273="",AO273=""),"",IF(COUNT(AI273:AN273)=0,"",AO273-LOOKUP(2,1/(AI273:AN273<>""),AI273:AN273))) | IF(OR(F273="",AP273=""),"",IF(COUNT(AI273:AO273)=0,"",AP273-LOOKUP(2,1/(AI273:AO273<>""),AI273:AO273))) | IF(OR(F273="",AQ273=""),"",IF(COUNT(AI273:AP273)=0,"",AQ273-LOOKUP(2,1/(AI273:AP273<>""),AI273:AP273))) | IF(OR(F273="",AR273=""),"",IF(COUNT(AI273:AQ273)=0,"",AR273-LOOKUP(2,1/(AI273:AQ273<>""),AI273:AQ273))) | IF(OR(F273="",AS273=""),"",IF(COUNT(AI273:AR273)=0,"",AS273-LOOKUP(2,1/(AI273:AR273<>""),AI273:AR273))) | IF(OR(F273="",AT273=""),"",IF(COUNT(AI273:AS273)=0,"",AT273-LOOKUP(2,1/(AI273:AS273<>""),AI273:AS273))) | IF(OR(F273="",AU273=""),"",IF(COUNT(AI273:AT273)=0,"",AU273-LOOKUP(2,1/(AI273:AT273<>""),AI273:AT273))) | IF(OR(F273="",AV273=""),"",IF(COUNT(AI273:AU273)=0,"",AV273-LOOKUP(2,1/(AI273:AU273<>""),AI273:AU273))) | IF(J273="","All_Provinces",IFERROR(VLOOKUP(J273,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K273="","All_Districts",IFERROR(VLOOKUP(K273,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F274="","",ROW()-3) | AF2-WSM-06 | Package #6-AF2 WSM: Construction of Jarobi Tangi, Chaghari and Adore check dams, located in Shirzad, Rodat, and Khogyani, districts of Nangarhar province. | 1 of 3 | AF2-WSM-A-011 | 1. Markikhil/Jarobi Tangi Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Sherzad | Jarobi Tangi | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Naeemi Safi Construction & Construction Material Company (NSCC) | 065/2026 | 51209.99 | IF(AQ274="","",AQ274) |  | 6.9 | 2026-07-22 | IF(W274<>"",W274,IF(OR(T274="",V274=""),"",EDATE(T274,V274))) |  | 100 | Completed / Handover | Completed on July, 2026 | IF(F274="","",IF(COUNT(AI274:AV274)=0,IF(AA274="","Not started",AA274),SUBSTITUTE(LOOKUP(2,1/(AI274:AV274<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F274="",COUNT(AI274:AV274)=0),"",TODAY()-LOOKUP(2,1/(AI274:AV274<>""),AI274:AV274)) | IF(OR(F274="",COUNT(AI274:AV274)<2),"",LOOKUP(2,1/(AI274:AV274<>""),AI274:AV274)-MIN(AI274:AV274)) | IF(OR(AD274="",AC274="Not started",AC274=""),"",IFERROR(AD274-IF(VLOOKUP(AC274,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC274,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F274="","",IF(OR(AA274="Cancelled",AC274="Cancelled"),"Cancelled",IF(OR(AC274="Completed / Handover",Y274<>"",Z274>=100),"Completed — on track",IF(O274="Not awarded",IF(U274="",IF(X274="","No planned date",IF(TODAY()>X274,"Behind — past planned date",IF(X274-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U274,"Behind — award date passed",IF(U274-TODAY()<=30,"At risk — close to off track","On track"))),IF(X274="","No planned date",IF(AND(TODAY()>X274,OR(Z274="",Z274<100)),"Behind — past end date",IF(AND(T274<>"",X274<>"",Z274<>"",(Z274<100),((TODAY()-T274)/MAX(X274-T274,1)*100)-Z274>15),"Behind — progress lag",IF(AND(X274-TODAY()<=30,X274-TODAY()>=0,OR(Z274="",Z274<90)),"At risk — close to off track","On track")))))))) | IF(OR(F274="",AC274="Completed / Handover",AC274="Cancelled"),"",IF(O274="Not awarded",IF(U274<>"",U274-TODAY(),IF(X274="","",X274-TODAY())),IF(X274="","",X274-TODAY()))) | [8 empty] | 2025-12-23 | 2025-12-23 | 2026-07-22 |  |  |  | IF(OR(F274="",AJ274=""),"",IF(COUNT(AI274:AI274)=0,"",AJ274-LOOKUP(2,1/(AI274:AI274<>""),AI274:AI274))) | IF(OR(F274="",AK274=""),"",IF(COUNT(AI274:AJ274)=0,"",AK274-LOOKUP(2,1/(AI274:AJ274<>""),AI274:AJ274))) | IF(OR(F274="",AL274=""),"",IF(COUNT(AI274:AK274)=0,"",AL274-LOOKUP(2,1/(AI274:AK274<>""),AI274:AK274))) | IF(OR(F274="",AM274=""),"",IF(COUNT(AI274:AL274)=0,"",AM274-LOOKUP(2,1/(AI274:AL274<>""),AI274:AL274))) | IF(OR(F274="",AN274=""),"",IF(COUNT(AI274:AM274)=0,"",AN274-LOOKUP(2,1/(AI274:AM274<>""),AI274:AM274))) | IF(OR(F274="",AO274=""),"",IF(COUNT(AI274:AN274)=0,"",AO274-LOOKUP(2,1/(AI274:AN274<>""),AI274:AN274))) | IF(OR(F274="",AP274=""),"",IF(COUNT(AI274:AO274)=0,"",AP274-LOOKUP(2,1/(AI274:AO274<>""),AI274:AO274))) | IF(OR(F274="",AQ274=""),"",IF(COUNT(AI274:AP274)=0,"",AQ274-LOOKUP(2,1/(AI274:AP274<>""),AI274:AP274))) | IF(OR(F274="",AR274=""),"",IF(COUNT(AI274:AQ274)=0,"",AR274-LOOKUP(2,1/(AI274:AQ274<>""),AI274:AQ274))) | IF(OR(F274="",AS274=""),"",IF(COUNT(AI274:AR274)=0,"",AS274-LOOKUP(2,1/(AI274:AR274<>""),AI274:AR274))) | IF(OR(F274="",AT274=""),"",IF(COUNT(AI274:AS274)=0,"",AT274-LOOKUP(2,1/(AI274:AS274<>""),AI274:AS274))) | IF(OR(F274="",AU274=""),"",IF(COUNT(AI274:AT274)=0,"",AU274-LOOKUP(2,1/(AI274:AT274<>""),AI274:AT274))) | IF(OR(F274="",AV274=""),"",IF(COUNT(AI274:AU274)=0,"",AV274-LOOKUP(2,1/(AI274:AU274<>""),AI274:AU274))) | IF(J274="","All_Provinces",IFERROR(VLOOKUP(J274,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K274="","All_Districts",IFERROR(VLOOKUP(K274,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F275="","",ROW()-3) | AF2-WSM-06 | Package #6-AF2 WSM: Construction of Jarobi Tangi, Chaghari and Adore check dams, located in Shirzad, Rodat, and Khogyani, districts of Nangarhar province. | 2 of 3 | AF2-WSM-A-012 | 2. Chaghari Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Rodat | Chaghari | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Naeemi Safi Construction & Construction Material Company (NSCC) | 065/2026 | 27989.43 | IF(AQ275="","",AQ275) |  | 6.9 | 2026-07-22 | IF(W275<>"",W275,IF(OR(T275="",V275=""),"",EDATE(T275,V275))) |  | 100 | Completed / Handover | Completed on July, 2026 | IF(F275="","",IF(COUNT(AI275:AV275)=0,IF(AA275="","Not started",AA275),SUBSTITUTE(LOOKUP(2,1/(AI275:AV275<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F275="",COUNT(AI275:AV275)=0),"",TODAY()-LOOKUP(2,1/(AI275:AV275<>""),AI275:AV275)) | IF(OR(F275="",COUNT(AI275:AV275)<2),"",LOOKUP(2,1/(AI275:AV275<>""),AI275:AV275)-MIN(AI275:AV275)) | IF(OR(AD275="",AC275="Not started",AC275=""),"",IFERROR(AD275-IF(VLOOKUP(AC275,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC275,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F275="","",IF(OR(AA275="Cancelled",AC275="Cancelled"),"Cancelled",IF(OR(AC275="Completed / Handover",Y275<>"",Z275>=100),"Completed — on track",IF(O275="Not awarded",IF(U275="",IF(X275="","No planned date",IF(TODAY()>X275,"Behind — past planned date",IF(X275-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U275,"Behind — award date passed",IF(U275-TODAY()<=30,"At risk — close to off track","On track"))),IF(X275="","No planned date",IF(AND(TODAY()>X275,OR(Z275="",Z275<100)),"Behind — past end date",IF(AND(T275<>"",X275<>"",Z275<>"",(Z275<100),((TODAY()-T275)/MAX(X275-T275,1)*100)-Z275>15),"Behind — progress lag",IF(AND(X275-TODAY()<=30,X275-TODAY()>=0,OR(Z275="",Z275<90)),"At risk — close to off track","On track")))))))) | IF(OR(F275="",AC275="Completed / Handover",AC275="Cancelled"),"",IF(O275="Not awarded",IF(U275<>"",U275-TODAY(),IF(X275="","",X275-TODAY())),IF(X275="","",X275-TODAY()))) | [8 empty] | 2025-12-23 | 2025-12-23 | 2026-07-22 |  |  |  | IF(OR(F275="",AJ275=""),"",IF(COUNT(AI275:AI275)=0,"",AJ275-LOOKUP(2,1/(AI275:AI275<>""),AI275:AI275))) | IF(OR(F275="",AK275=""),"",IF(COUNT(AI275:AJ275)=0,"",AK275-LOOKUP(2,1/(AI275:AJ275<>""),AI275:AJ275))) | IF(OR(F275="",AL275=""),"",IF(COUNT(AI275:AK275)=0,"",AL275-LOOKUP(2,1/(AI275:AK275<>""),AI275:AK275))) | IF(OR(F275="",AM275=""),"",IF(COUNT(AI275:AL275)=0,"",AM275-LOOKUP(2,1/(AI275:AL275<>""),AI275:AL275))) | IF(OR(F275="",AN275=""),"",IF(COUNT(AI275:AM275)=0,"",AN275-LOOKUP(2,1/(AI275:AM275<>""),AI275:AM275))) | IF(OR(F275="",AO275=""),"",IF(COUNT(AI275:AN275)=0,"",AO275-LOOKUP(2,1/(AI275:AN275<>""),AI275:AN275))) | IF(OR(F275="",AP275=""),"",IF(COUNT(AI275:AO275)=0,"",AP275-LOOKUP(2,1/(AI275:AO275<>""),AI275:AO275))) | IF(OR(F275="",AQ275=""),"",IF(COUNT(AI275:AP275)=0,"",AQ275-LOOKUP(2,1/(AI275:AP275<>""),AI275:AP275))) | IF(OR(F275="",AR275=""),"",IF(COUNT(AI275:AQ275)=0,"",AR275-LOOKUP(2,1/(AI275:AQ275<>""),AI275:AQ275))) | IF(OR(F275="",AS275=""),"",IF(COUNT(AI275:AR275)=0,"",AS275-LOOKUP(2,1/(AI275:AR275<>""),AI275:AR275))) | IF(OR(F275="",AT275=""),"",IF(COUNT(AI275:AS275)=0,"",AT275-LOOKUP(2,1/(AI275:AS275<>""),AI275:AS275))) | IF(OR(F275="",AU275=""),"",IF(COUNT(AI275:AT275)=0,"",AU275-LOOKUP(2,1/(AI275:AT275<>""),AI275:AT275))) | IF(OR(F275="",AV275=""),"",IF(COUNT(AI275:AU275)=0,"",AV275-LOOKUP(2,1/(AI275:AU275<>""),AI275:AU275))) | IF(J275="","All_Provinces",IFERROR(VLOOKUP(J275,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K275="","All_Districts",IFERROR(VLOOKUP(K275,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F276="","",ROW()-3) | AF2-WSM-06 | Package #6-AF2 WSM: Construction of Jarobi Tangi, Chaghari and Adore check dams, located in Shirzad, Rodat, and Khogyani, districts of Nangarhar province. | 3 of 3 | AF2-WSM-A-013 | 3. Adore check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Nangarhar | Khogyani | Adore | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Naeemi Safi Construction & Construction Material Company (NSCC) | 065/2026 | 50713.55 | IF(AQ276="","",AQ276) |  | 6.9 | 2026-07-22 | IF(W276<>"",W276,IF(OR(T276="",V276=""),"",EDATE(T276,V276))) |  | 100 | Completed / Handover | Completed on July, 2026 | IF(F276="","",IF(COUNT(AI276:AV276)=0,IF(AA276="","Not started",AA276),SUBSTITUTE(LOOKUP(2,1/(AI276:AV276<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F276="",COUNT(AI276:AV276)=0),"",TODAY()-LOOKUP(2,1/(AI276:AV276<>""),AI276:AV276)) | IF(OR(F276="",COUNT(AI276:AV276)<2),"",LOOKUP(2,1/(AI276:AV276<>""),AI276:AV276)-MIN(AI276:AV276)) | IF(OR(AD276="",AC276="Not started",AC276=""),"",IFERROR(AD276-IF(VLOOKUP(AC276,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC276,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F276="","",IF(OR(AA276="Cancelled",AC276="Cancelled"),"Cancelled",IF(OR(AC276="Completed / Handover",Y276<>"",Z276>=100),"Completed — on track",IF(O276="Not awarded",IF(U276="",IF(X276="","No planned date",IF(TODAY()>X276,"Behind — past planned date",IF(X276-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U276,"Behind — award date passed",IF(U276-TODAY()<=30,"At risk — close to off track","On track"))),IF(X276="","No planned date",IF(AND(TODAY()>X276,OR(Z276="",Z276<100)),"Behind — past end date",IF(AND(T276<>"",X276<>"",Z276<>"",(Z276<100),((TODAY()-T276)/MAX(X276-T276,1)*100)-Z276>15),"Behind — progress lag",IF(AND(X276-TODAY()<=30,X276-TODAY()>=0,OR(Z276="",Z276<90)),"At risk — close to off track","On track")))))))) | IF(OR(F276="",AC276="Completed / Handover",AC276="Cancelled"),"",IF(O276="Not awarded",IF(U276<>"",U276-TODAY(),IF(X276="","",X276-TODAY())),IF(X276="","",X276-TODAY()))) | [8 empty] | 2025-12-23 | 2025-12-23 | 2026-07-22 |  |  |  | IF(OR(F276="",AJ276=""),"",IF(COUNT(AI276:AI276)=0,"",AJ276-LOOKUP(2,1/(AI276:AI276<>""),AI276:AI276))) | IF(OR(F276="",AK276=""),"",IF(COUNT(AI276:AJ276)=0,"",AK276-LOOKUP(2,1/(AI276:AJ276<>""),AI276:AJ276))) | IF(OR(F276="",AL276=""),"",IF(COUNT(AI276:AK276)=0,"",AL276-LOOKUP(2,1/(AI276:AK276<>""),AI276:AK276))) | IF(OR(F276="",AM276=""),"",IF(COUNT(AI276:AL276)=0,"",AM276-LOOKUP(2,1/(AI276:AL276<>""),AI276:AL276))) | IF(OR(F276="",AN276=""),"",IF(COUNT(AI276:AM276)=0,"",AN276-LOOKUP(2,1/(AI276:AM276<>""),AI276:AM276))) | IF(OR(F276="",AO276=""),"",IF(COUNT(AI276:AN276)=0,"",AO276-LOOKUP(2,1/(AI276:AN276<>""),AI276:AN276))) | IF(OR(F276="",AP276=""),"",IF(COUNT(AI276:AO276)=0,"",AP276-LOOKUP(2,1/(AI276:AO276<>""),AI276:AO276))) | IF(OR(F276="",AQ276=""),"",IF(COUNT(AI276:AP276)=0,"",AQ276-LOOKUP(2,1/(AI276:AP276<>""),AI276:AP276))) | IF(OR(F276="",AR276=""),"",IF(COUNT(AI276:AQ276)=0,"",AR276-LOOKUP(2,1/(AI276:AQ276<>""),AI276:AQ276))) | IF(OR(F276="",AS276=""),"",IF(COUNT(AI276:AR276)=0,"",AS276-LOOKUP(2,1/(AI276:AR276<>""),AI276:AR276))) | IF(OR(F276="",AT276=""),"",IF(COUNT(AI276:AS276)=0,"",AT276-LOOKUP(2,1/(AI276:AS276<>""),AI276:AS276))) | IF(OR(F276="",AU276=""),"",IF(COUNT(AI276:AT276)=0,"",AU276-LOOKUP(2,1/(AI276:AT276<>""),AI276:AT276))) | IF(OR(F276="",AV276=""),"",IF(COUNT(AI276:AU276)=0,"",AV276-LOOKUP(2,1/(AI276:AU276<>""),AI276:AU276))) | IF(J276="","All_Provinces",IFERROR(VLOOKUP(J276,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K276="","All_Districts",IFERROR(VLOOKUP(K276,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F277="","",ROW()-3) | AF2-WSM-07 | Package #7-AF2 WSM: Construction of 3 Check dams of 1.Dargrak, 2. Migano, and 3.Lachagali the Sawkai, Khas Kunar and Narang districts of Kunar province. | 1 of 3 | AF2-WSM-A-014 | Dargarak Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Sawkai | Daar Garak | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Green Bentley construction Company (GBCC) | 064/2026 |  | IF(AQ277="","",AQ277) |  | 4.9 | 2027-03-10 | IF(W277<>"",W277,IF(OR(T277="",V277=""),"",EDATE(T277,V277))) |  | 0 | Awarded | Awarded on 11 oct.2026 | IF(F277="","",IF(COUNT(AI277:AV277)=0,IF(AA277="","Not started",AA277),SUBSTITUTE(LOOKUP(2,1/(AI277:AV277<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F277="",COUNT(AI277:AV277)=0),"",TODAY()-LOOKUP(2,1/(AI277:AV277<>""),AI277:AV277)) | IF(OR(F277="",COUNT(AI277:AV277)<2),"",LOOKUP(2,1/(AI277:AV277<>""),AI277:AV277)-MIN(AI277:AV277)) | IF(OR(AD277="",AC277="Not started",AC277=""),"",IFERROR(AD277-IF(VLOOKUP(AC277,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC277,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F277="","",IF(OR(AA277="Cancelled",AC277="Cancelled"),"Cancelled",IF(OR(AC277="Completed / Handover",Y277<>"",Z277>=100),"Completed — on track",IF(O277="Not awarded",IF(U277="",IF(X277="","No planned date",IF(TODAY()>X277,"Behind — past planned date",IF(X277-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U277,"Behind — award date passed",IF(U277-TODAY()<=30,"At risk — close to off track","On track"))),IF(X277="","No planned date",IF(AND(TODAY()>X277,OR(Z277="",Z277<100)),"Behind — past end date",IF(AND(T277<>"",X277<>"",Z277<>"",(Z277<100),((TODAY()-T277)/MAX(X277-T277,1)*100)-Z277>15),"Behind — progress lag",IF(AND(X277-TODAY()<=30,X277-TODAY()>=0,OR(Z277="",Z277<90)),"At risk — close to off track","On track")))))))) | IF(OR(F277="",AC277="Completed / Handover",AC277="Cancelled"),"",IF(O277="Not awarded",IF(U277<>"",U277-TODAY(),IF(X277="","",X277-TODAY())),IF(X277="","",X277-TODAY()))) | [8 empty] | 2026-10-11 | [5 empty] | IF(OR(F277="",AJ277=""),"",IF(COUNT(AI277:AI277)=0,"",AJ277-LOOKUP(2,1/(AI277:AI277<>""),AI277:AI277))) | IF(OR(F277="",AK277=""),"",IF(COUNT(AI277:AJ277)=0,"",AK277-LOOKUP(2,1/(AI277:AJ277<>""),AI277:AJ277))) | IF(OR(F277="",AL277=""),"",IF(COUNT(AI277:AK277)=0,"",AL277-LOOKUP(2,1/(AI277:AK277<>""),AI277:AK277))) | IF(OR(F277="",AM277=""),"",IF(COUNT(AI277:AL277)=0,"",AM277-LOOKUP(2,1/(AI277:AL277<>""),AI277:AL277))) | IF(OR(F277="",AN277=""),"",IF(COUNT(AI277:AM277)=0,"",AN277-LOOKUP(2,1/(AI277:AM277<>""),AI277:AM277))) | IF(OR(F277="",AO277=""),"",IF(COUNT(AI277:AN277)=0,"",AO277-LOOKUP(2,1/(AI277:AN277<>""),AI277:AN277))) | IF(OR(F277="",AP277=""),"",IF(COUNT(AI277:AO277)=0,"",AP277-LOOKUP(2,1/(AI277:AO277<>""),AI277:AO277))) | IF(OR(F277="",AQ277=""),"",IF(COUNT(AI277:AP277)=0,"",AQ277-LOOKUP(2,1/(AI277:AP277<>""),AI277:AP277))) | IF(OR(F277="",AR277=""),"",IF(COUNT(AI277:AQ277)=0,"",AR277-LOOKUP(2,1/(AI277:AQ277<>""),AI277:AQ277))) | IF(OR(F277="",AS277=""),"",IF(COUNT(AI277:AR277)=0,"",AS277-LOOKUP(2,1/(AI277:AR277<>""),AI277:AR277))) | IF(OR(F277="",AT277=""),"",IF(COUNT(AI277:AS277)=0,"",AT277-LOOKUP(2,1/(AI277:AS277<>""),AI277:AS277))) | IF(OR(F277="",AU277=""),"",IF(COUNT(AI277:AT277)=0,"",AU277-LOOKUP(2,1/(AI277:AT277<>""),AI277:AT277))) | IF(OR(F277="",AV277=""),"",IF(COUNT(AI277:AU277)=0,"",AV277-LOOKUP(2,1/(AI277:AU277<>""),AI277:AU277))) | IF(J277="","All_Provinces",IFERROR(VLOOKUP(J277,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K277="","All_Districts",IFERROR(VLOOKUP(K277,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F278="","",ROW()-3) | AF2-WSM-07 | Package #7-AF2 WSM: Construction of 3 Check dams of 1.Dargrak, 2. Migano, and 3.Lachagali the Sawkai, Khas Kunar and Narang districts of Kunar province. | 2 of 3 | AF2-WSM-A-015 | Lachagali Boulder Check Dam and Water Pond | Watershed Management | Check Dam and Water Pond | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Narang | Lachagali/ Jaroobi | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Green Bentley construction Company (GBCC) | 064/2026 | 99590 | IF(AQ278="","",AQ278) |  | 4.9 | 2027-03-10 | IF(W278<>"",W278,IF(OR(T278="",V278=""),"",EDATE(T278,V278))) |  | 0 | Awarded | Completed on July, 2026 | IF(F278="","",IF(COUNT(AI278:AV278)=0,IF(AA278="","Not started",AA278),SUBSTITUTE(LOOKUP(2,1/(AI278:AV278<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F278="",COUNT(AI278:AV278)=0),"",TODAY()-LOOKUP(2,1/(AI278:AV278<>""),AI278:AV278)) | IF(OR(F278="",COUNT(AI278:AV278)<2),"",LOOKUP(2,1/(AI278:AV278<>""),AI278:AV278)-MIN(AI278:AV278)) | IF(OR(AD278="",AC278="Not started",AC278=""),"",IFERROR(AD278-IF(VLOOKUP(AC278,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC278,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F278="","",IF(OR(AA278="Cancelled",AC278="Cancelled"),"Cancelled",IF(OR(AC278="Completed / Handover",Y278<>"",Z278>=100),"Completed — on track",IF(O278="Not awarded",IF(U278="",IF(X278="","No planned date",IF(TODAY()>X278,"Behind — past planned date",IF(X278-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U278,"Behind — award date passed",IF(U278-TODAY()<=30,"At risk — close to off track","On track"))),IF(X278="","No planned date",IF(AND(TODAY()>X278,OR(Z278="",Z278<100)),"Behind — past end date",IF(AND(T278<>"",X278<>"",Z278<>"",(Z278<100),((TODAY()-T278)/MAX(X278-T278,1)*100)-Z278>15),"Behind — progress lag",IF(AND(X278-TODAY()<=30,X278-TODAY()>=0,OR(Z278="",Z278<90)),"At risk — close to off track","On track")))))))) | IF(OR(F278="",AC278="Completed / Handover",AC278="Cancelled"),"",IF(O278="Not awarded",IF(U278<>"",U278-TODAY(),IF(X278="","",X278-TODAY())),IF(X278="","",X278-TODAY()))) | [8 empty] | 2026-10-11 | [5 empty] | IF(OR(F278="",AJ278=""),"",IF(COUNT(AI278:AI278)=0,"",AJ278-LOOKUP(2,1/(AI278:AI278<>""),AI278:AI278))) | IF(OR(F278="",AK278=""),"",IF(COUNT(AI278:AJ278)=0,"",AK278-LOOKUP(2,1/(AI278:AJ278<>""),AI278:AJ278))) | IF(OR(F278="",AL278=""),"",IF(COUNT(AI278:AK278)=0,"",AL278-LOOKUP(2,1/(AI278:AK278<>""),AI278:AK278))) | IF(OR(F278="",AM278=""),"",IF(COUNT(AI278:AL278)=0,"",AM278-LOOKUP(2,1/(AI278:AL278<>""),AI278:AL278))) | IF(OR(F278="",AN278=""),"",IF(COUNT(AI278:AM278)=0,"",AN278-LOOKUP(2,1/(AI278:AM278<>""),AI278:AM278))) | IF(OR(F278="",AO278=""),"",IF(COUNT(AI278:AN278)=0,"",AO278-LOOKUP(2,1/(AI278:AN278<>""),AI278:AN278))) | IF(OR(F278="",AP278=""),"",IF(COUNT(AI278:AO278)=0,"",AP278-LOOKUP(2,1/(AI278:AO278<>""),AI278:AO278))) | IF(OR(F278="",AQ278=""),"",IF(COUNT(AI278:AP278)=0,"",AQ278-LOOKUP(2,1/(AI278:AP278<>""),AI278:AP278))) | IF(OR(F278="",AR278=""),"",IF(COUNT(AI278:AQ278)=0,"",AR278-LOOKUP(2,1/(AI278:AQ278<>""),AI278:AQ278))) | IF(OR(F278="",AS278=""),"",IF(COUNT(AI278:AR278)=0,"",AS278-LOOKUP(2,1/(AI278:AR278<>""),AI278:AR278))) | IF(OR(F278="",AT278=""),"",IF(COUNT(AI278:AS278)=0,"",AT278-LOOKUP(2,1/(AI278:AS278<>""),AI278:AS278))) | IF(OR(F278="",AU278=""),"",IF(COUNT(AI278:AT278)=0,"",AU278-LOOKUP(2,1/(AI278:AT278<>""),AI278:AT278))) | IF(OR(F278="",AV278=""),"",IF(COUNT(AI278:AU278)=0,"",AV278-LOOKUP(2,1/(AI278:AU278<>""),AI278:AU278))) | IF(J278="","All_Provinces",IFERROR(VLOOKUP(J278,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K278="","All_Districts",IFERROR(VLOOKUP(K278,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F279="","",ROW()-3) | AF2-WSM-07 | Package #7-AF2 WSM: Construction of 3 Check dams of 1.Dargrak, 2. Migano, and 3.Lachagali the Sawkai, Khas Kunar and Narang districts of Kunar province. | 3 of 3 | AF2-WSM-A-016 | Miagan Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Khas Kunar | Miagan Kali | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Green Bentley construction Company (GBCC) | 064/2026 |  | IF(AQ279="","",AQ279) |  | 4.9 | 2027-03-10 | IF(W279<>"",W279,IF(OR(T279="",V279=""),"",EDATE(T279,V279))) |  | 0 | Awarded | Awarded on 11 oct.2026 | IF(F279="","",IF(COUNT(AI279:AV279)=0,IF(AA279="","Not started",AA279),SUBSTITUTE(LOOKUP(2,1/(AI279:AV279<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F279="",COUNT(AI279:AV279)=0),"",TODAY()-LOOKUP(2,1/(AI279:AV279<>""),AI279:AV279)) | IF(OR(F279="",COUNT(AI279:AV279)<2),"",LOOKUP(2,1/(AI279:AV279<>""),AI279:AV279)-MIN(AI279:AV279)) | IF(OR(AD279="",AC279="Not started",AC279=""),"",IFERROR(AD279-IF(VLOOKUP(AC279,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC279,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F279="","",IF(OR(AA279="Cancelled",AC279="Cancelled"),"Cancelled",IF(OR(AC279="Completed / Handover",Y279<>"",Z279>=100),"Completed — on track",IF(O279="Not awarded",IF(U279="",IF(X279="","No planned date",IF(TODAY()>X279,"Behind — past planned date",IF(X279-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U279,"Behind — award date passed",IF(U279-TODAY()<=30,"At risk — close to off track","On track"))),IF(X279="","No planned date",IF(AND(TODAY()>X279,OR(Z279="",Z279<100)),"Behind — past end date",IF(AND(T279<>"",X279<>"",Z279<>"",(Z279<100),((TODAY()-T279)/MAX(X279-T279,1)*100)-Z279>15),"Behind — progress lag",IF(AND(X279-TODAY()<=30,X279-TODAY()>=0,OR(Z279="",Z279<90)),"At risk — close to off track","On track")))))))) | IF(OR(F279="",AC279="Completed / Handover",AC279="Cancelled"),"",IF(O279="Not awarded",IF(U279<>"",U279-TODAY(),IF(X279="","",X279-TODAY())),IF(X279="","",X279-TODAY()))) | [8 empty] | 2026-10-11 | [5 empty] | IF(OR(F279="",AJ279=""),"",IF(COUNT(AI279:AI279)=0,"",AJ279-LOOKUP(2,1/(AI279:AI279<>""),AI279:AI279))) | IF(OR(F279="",AK279=""),"",IF(COUNT(AI279:AJ279)=0,"",AK279-LOOKUP(2,1/(AI279:AJ279<>""),AI279:AJ279))) | IF(OR(F279="",AL279=""),"",IF(COUNT(AI279:AK279)=0,"",AL279-LOOKUP(2,1/(AI279:AK279<>""),AI279:AK279))) | IF(OR(F279="",AM279=""),"",IF(COUNT(AI279:AL279)=0,"",AM279-LOOKUP(2,1/(AI279:AL279<>""),AI279:AL279))) | IF(OR(F279="",AN279=""),"",IF(COUNT(AI279:AM279)=0,"",AN279-LOOKUP(2,1/(AI279:AM279<>""),AI279:AM279))) | IF(OR(F279="",AO279=""),"",IF(COUNT(AI279:AN279)=0,"",AO279-LOOKUP(2,1/(AI279:AN279<>""),AI279:AN279))) | IF(OR(F279="",AP279=""),"",IF(COUNT(AI279:AO279)=0,"",AP279-LOOKUP(2,1/(AI279:AO279<>""),AI279:AO279))) | IF(OR(F279="",AQ279=""),"",IF(COUNT(AI279:AP279)=0,"",AQ279-LOOKUP(2,1/(AI279:AP279<>""),AI279:AP279))) | IF(OR(F279="",AR279=""),"",IF(COUNT(AI279:AQ279)=0,"",AR279-LOOKUP(2,1/(AI279:AQ279<>""),AI279:AQ279))) | IF(OR(F279="",AS279=""),"",IF(COUNT(AI279:AR279)=0,"",AS279-LOOKUP(2,1/(AI279:AR279<>""),AI279:AR279))) | IF(OR(F279="",AT279=""),"",IF(COUNT(AI279:AS279)=0,"",AT279-LOOKUP(2,1/(AI279:AS279<>""),AI279:AS279))) | IF(OR(F279="",AU279=""),"",IF(COUNT(AI279:AT279)=0,"",AU279-LOOKUP(2,1/(AI279:AT279<>""),AI279:AT279))) | IF(OR(F279="",AV279=""),"",IF(COUNT(AI279:AU279)=0,"",AV279-LOOKUP(2,1/(AI279:AU279<>""),AI279:AU279))) | IF(J279="","All_Provinces",IFERROR(VLOOKUP(J279,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K279="","All_Districts",IFERROR(VLOOKUP(K279,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F280="","",ROW()-3) | AF2-WSM-08 | Package #8-AF2 WSM: Construction of 1.Ghazgai Check dam in Khake Jabar districts, 2.Toop Dara Check dam and 3.Toot Dara Check dam in Center/ 13th City district Kabul province. | 1 of 3 | AF2-WSM-A-017 | 1.Toop Dara Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Center | 13th district | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | ALTIN CONSTRUCTION AND ROAD BUILDING COMPANY (ACC) | 005/2026 | 65749 | IF(AQ280="","",AQ280) |  | 6.9 | 2026-08-19 | IF(W280<>"",W280,IF(OR(T280="",V280=""),"",EDATE(T280,V280))) |  | 100 | Completed / Handover | Completed on July, 2026 | IF(F280="","",IF(COUNT(AI280:AV280)=0,IF(AA280="","Not started",AA280),SUBSTITUTE(LOOKUP(2,1/(AI280:AV280<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F280="",COUNT(AI280:AV280)=0),"",TODAY()-LOOKUP(2,1/(AI280:AV280<>""),AI280:AV280)) | IF(OR(F280="",COUNT(AI280:AV280)<2),"",LOOKUP(2,1/(AI280:AV280<>""),AI280:AV280)-MIN(AI280:AV280)) | IF(OR(AD280="",AC280="Not started",AC280=""),"",IFERROR(AD280-IF(VLOOKUP(AC280,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC280,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F280="","",IF(OR(AA280="Cancelled",AC280="Cancelled"),"Cancelled",IF(OR(AC280="Completed / Handover",Y280<>"",Z280>=100),"Completed — on track",IF(O280="Not awarded",IF(U280="",IF(X280="","No planned date",IF(TODAY()>X280,"Behind — past planned date",IF(X280-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U280,"Behind — award date passed",IF(U280-TODAY()<=30,"At risk — close to off track","On track"))),IF(X280="","No planned date",IF(AND(TODAY()>X280,OR(Z280="",Z280<100)),"Behind — past end date",IF(AND(T280<>"",X280<>"",Z280<>"",(Z280<100),((TODAY()-T280)/MAX(X280-T280,1)*100)-Z280>15),"Behind — progress lag",IF(AND(X280-TODAY()<=30,X280-TODAY()>=0,OR(Z280="",Z280<90)),"At risk — close to off track","On track")))))))) | IF(OR(F280="",AC280="Completed / Handover",AC280="Cancelled"),"",IF(O280="Not awarded",IF(U280<>"",U280-TODAY(),IF(X280="","",X280-TODAY())),IF(X280="","",X280-TODAY()))) | [8 empty] | 2026-01-20 | 2026-01-20 | 2026-08-19 |  |  |  | IF(OR(F280="",AJ280=""),"",IF(COUNT(AI280:AI280)=0,"",AJ280-LOOKUP(2,1/(AI280:AI280<>""),AI280:AI280))) | IF(OR(F280="",AK280=""),"",IF(COUNT(AI280:AJ280)=0,"",AK280-LOOKUP(2,1/(AI280:AJ280<>""),AI280:AJ280))) | IF(OR(F280="",AL280=""),"",IF(COUNT(AI280:AK280)=0,"",AL280-LOOKUP(2,1/(AI280:AK280<>""),AI280:AK280))) | IF(OR(F280="",AM280=""),"",IF(COUNT(AI280:AL280)=0,"",AM280-LOOKUP(2,1/(AI280:AL280<>""),AI280:AL280))) | IF(OR(F280="",AN280=""),"",IF(COUNT(AI280:AM280)=0,"",AN280-LOOKUP(2,1/(AI280:AM280<>""),AI280:AM280))) | IF(OR(F280="",AO280=""),"",IF(COUNT(AI280:AN280)=0,"",AO280-LOOKUP(2,1/(AI280:AN280<>""),AI280:AN280))) | IF(OR(F280="",AP280=""),"",IF(COUNT(AI280:AO280)=0,"",AP280-LOOKUP(2,1/(AI280:AO280<>""),AI280:AO280))) | IF(OR(F280="",AQ280=""),"",IF(COUNT(AI280:AP280)=0,"",AQ280-LOOKUP(2,1/(AI280:AP280<>""),AI280:AP280))) | IF(OR(F280="",AR280=""),"",IF(COUNT(AI280:AQ280)=0,"",AR280-LOOKUP(2,1/(AI280:AQ280<>""),AI280:AQ280))) | IF(OR(F280="",AS280=""),"",IF(COUNT(AI280:AR280)=0,"",AS280-LOOKUP(2,1/(AI280:AR280<>""),AI280:AR280))) | IF(OR(F280="",AT280=""),"",IF(COUNT(AI280:AS280)=0,"",AT280-LOOKUP(2,1/(AI280:AS280<>""),AI280:AS280))) | IF(OR(F280="",AU280=""),"",IF(COUNT(AI280:AT280)=0,"",AU280-LOOKUP(2,1/(AI280:AT280<>""),AI280:AT280))) | IF(OR(F280="",AV280=""),"",IF(COUNT(AI280:AU280)=0,"",AV280-LOOKUP(2,1/(AI280:AU280<>""),AI280:AU280))) | IF(J280="","All_Provinces",IFERROR(VLOOKUP(J280,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K280="","All_Districts",IFERROR(VLOOKUP(K280,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F281="","",ROW()-3) | AF2-WSM-08 | Package #8-AF2 WSM: Construction of 1.Ghazgai Check dam in Khake Jabar districts, 2.Toop Dara Check dam and 3.Toot Dara Check dam in Center/ 13th City district Kabul province. | 2 of 3 | AF2-WSM-A-018 | 2.Toot Dara Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Center | 13th district | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | ALTIN CONSTRUCTION AND ROAD BUILDING COMPANY (ACC) | 005/2026 |  | IF(AQ281="","",AQ281) |  | 6.9 | 2026-08-19 | IF(W281<>"",W281,IF(OR(T281="",V281=""),"",EDATE(T281,V281))) |  | 100 | Completed / Handover | Completed on July, 2026 | IF(F281="","",IF(COUNT(AI281:AV281)=0,IF(AA281="","Not started",AA281),SUBSTITUTE(LOOKUP(2,1/(AI281:AV281<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F281="",COUNT(AI281:AV281)=0),"",TODAY()-LOOKUP(2,1/(AI281:AV281<>""),AI281:AV281)) | IF(OR(F281="",COUNT(AI281:AV281)<2),"",LOOKUP(2,1/(AI281:AV281<>""),AI281:AV281)-MIN(AI281:AV281)) | IF(OR(AD281="",AC281="Not started",AC281=""),"",IFERROR(AD281-IF(VLOOKUP(AC281,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC281,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F281="","",IF(OR(AA281="Cancelled",AC281="Cancelled"),"Cancelled",IF(OR(AC281="Completed / Handover",Y281<>"",Z281>=100),"Completed — on track",IF(O281="Not awarded",IF(U281="",IF(X281="","No planned date",IF(TODAY()>X281,"Behind — past planned date",IF(X281-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U281,"Behind — award date passed",IF(U281-TODAY()<=30,"At risk — close to off track","On track"))),IF(X281="","No planned date",IF(AND(TODAY()>X281,OR(Z281="",Z281<100)),"Behind — past end date",IF(AND(T281<>"",X281<>"",Z281<>"",(Z281<100),((TODAY()-T281)/MAX(X281-T281,1)*100)-Z281>15),"Behind — progress lag",IF(AND(X281-TODAY()<=30,X281-TODAY()>=0,OR(Z281="",Z281<90)),"At risk — close to off track","On track")))))))) | IF(OR(F281="",AC281="Completed / Handover",AC281="Cancelled"),"",IF(O281="Not awarded",IF(U281<>"",U281-TODAY(),IF(X281="","",X281-TODAY())),IF(X281="","",X281-TODAY()))) | [8 empty] | 2026-01-20 | 2026-01-20 | 2026-08-19 |  |  |  | IF(OR(F281="",AJ281=""),"",IF(COUNT(AI281:AI281)=0,"",AJ281-LOOKUP(2,1/(AI281:AI281<>""),AI281:AI281))) | IF(OR(F281="",AK281=""),"",IF(COUNT(AI281:AJ281)=0,"",AK281-LOOKUP(2,1/(AI281:AJ281<>""),AI281:AJ281))) | IF(OR(F281="",AL281=""),"",IF(COUNT(AI281:AK281)=0,"",AL281-LOOKUP(2,1/(AI281:AK281<>""),AI281:AK281))) | IF(OR(F281="",AM281=""),"",IF(COUNT(AI281:AL281)=0,"",AM281-LOOKUP(2,1/(AI281:AL281<>""),AI281:AL281))) | IF(OR(F281="",AN281=""),"",IF(COUNT(AI281:AM281)=0,"",AN281-LOOKUP(2,1/(AI281:AM281<>""),AI281:AM281))) | IF(OR(F281="",AO281=""),"",IF(COUNT(AI281:AN281)=0,"",AO281-LOOKUP(2,1/(AI281:AN281<>""),AI281:AN281))) | IF(OR(F281="",AP281=""),"",IF(COUNT(AI281:AO281)=0,"",AP281-LOOKUP(2,1/(AI281:AO281<>""),AI281:AO281))) | IF(OR(F281="",AQ281=""),"",IF(COUNT(AI281:AP281)=0,"",AQ281-LOOKUP(2,1/(AI281:AP281<>""),AI281:AP281))) | IF(OR(F281="",AR281=""),"",IF(COUNT(AI281:AQ281)=0,"",AR281-LOOKUP(2,1/(AI281:AQ281<>""),AI281:AQ281))) | IF(OR(F281="",AS281=""),"",IF(COUNT(AI281:AR281)=0,"",AS281-LOOKUP(2,1/(AI281:AR281<>""),AI281:AR281))) | IF(OR(F281="",AT281=""),"",IF(COUNT(AI281:AS281)=0,"",AT281-LOOKUP(2,1/(AI281:AS281<>""),AI281:AS281))) | IF(OR(F281="",AU281=""),"",IF(COUNT(AI281:AT281)=0,"",AU281-LOOKUP(2,1/(AI281:AT281<>""),AI281:AT281))) | IF(OR(F281="",AV281=""),"",IF(COUNT(AI281:AU281)=0,"",AV281-LOOKUP(2,1/(AI281:AU281<>""),AI281:AU281))) | IF(J281="","All_Provinces",IFERROR(VLOOKUP(J281,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K281="","All_Districts",IFERROR(VLOOKUP(K281,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F282="","",ROW()-3) | AF2-WSM-08 | Package #8-AF2 WSM: Construction of 1.Ghazgai Check dam in Khake Jabar districts, 2.Toop Dara Check dam and 3.Toot Dara Check dam in Center/ 13th City district Kabul province. | 3 of 3 | AF2-WSM-A-019 | 3.Ghazgi Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Khake Jabar | Ghazgai | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | ALTIN CONSTRUCTION AND ROAD BUILDING COMPANY (ACC) | 005/2026 |  | IF(AQ282="","",AQ282) |  | 6.9 | 2026-08-19 | IF(W282<>"",W282,IF(OR(T282="",V282=""),"",EDATE(T282,V282))) |  | 100 | Completed / Handover | Completed on July, 2026 | IF(F282="","",IF(COUNT(AI282:AV282)=0,IF(AA282="","Not started",AA282),SUBSTITUTE(LOOKUP(2,1/(AI282:AV282<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F282="",COUNT(AI282:AV282)=0),"",TODAY()-LOOKUP(2,1/(AI282:AV282<>""),AI282:AV282)) | IF(OR(F282="",COUNT(AI282:AV282)<2),"",LOOKUP(2,1/(AI282:AV282<>""),AI282:AV282)-MIN(AI282:AV282)) | IF(OR(AD282="",AC282="Not started",AC282=""),"",IFERROR(AD282-IF(VLOOKUP(AC282,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC282,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F282="","",IF(OR(AA282="Cancelled",AC282="Cancelled"),"Cancelled",IF(OR(AC282="Completed / Handover",Y282<>"",Z282>=100),"Completed — on track",IF(O282="Not awarded",IF(U282="",IF(X282="","No planned date",IF(TODAY()>X282,"Behind — past planned date",IF(X282-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U282,"Behind — award date passed",IF(U282-TODAY()<=30,"At risk — close to off track","On track"))),IF(X282="","No planned date",IF(AND(TODAY()>X282,OR(Z282="",Z282<100)),"Behind — past end date",IF(AND(T282<>"",X282<>"",Z282<>"",(Z282<100),((TODAY()-T282)/MAX(X282-T282,1)*100)-Z282>15),"Behind — progress lag",IF(AND(X282-TODAY()<=30,X282-TODAY()>=0,OR(Z282="",Z282<90)),"At risk — close to off track","On track")))))))) | IF(OR(F282="",AC282="Completed / Handover",AC282="Cancelled"),"",IF(O282="Not awarded",IF(U282<>"",U282-TODAY(),IF(X282="","",X282-TODAY())),IF(X282="","",X282-TODAY()))) | [8 empty] | 2026-01-20 | 2026-01-20 | 2026-08-19 |  |  |  | IF(OR(F282="",AJ282=""),"",IF(COUNT(AI282:AI282)=0,"",AJ282-LOOKUP(2,1/(AI282:AI282<>""),AI282:AI282))) | IF(OR(F282="",AK282=""),"",IF(COUNT(AI282:AJ282)=0,"",AK282-LOOKUP(2,1/(AI282:AJ282<>""),AI282:AJ282))) | IF(OR(F282="",AL282=""),"",IF(COUNT(AI282:AK282)=0,"",AL282-LOOKUP(2,1/(AI282:AK282<>""),AI282:AK282))) | IF(OR(F282="",AM282=""),"",IF(COUNT(AI282:AL282)=0,"",AM282-LOOKUP(2,1/(AI282:AL282<>""),AI282:AL282))) | IF(OR(F282="",AN282=""),"",IF(COUNT(AI282:AM282)=0,"",AN282-LOOKUP(2,1/(AI282:AM282<>""),AI282:AM282))) | IF(OR(F282="",AO282=""),"",IF(COUNT(AI282:AN282)=0,"",AO282-LOOKUP(2,1/(AI282:AN282<>""),AI282:AN282))) | IF(OR(F282="",AP282=""),"",IF(COUNT(AI282:AO282)=0,"",AP282-LOOKUP(2,1/(AI282:AO282<>""),AI282:AO282))) | IF(OR(F282="",AQ282=""),"",IF(COUNT(AI282:AP282)=0,"",AQ282-LOOKUP(2,1/(AI282:AP282<>""),AI282:AP282))) | IF(OR(F282="",AR282=""),"",IF(COUNT(AI282:AQ282)=0,"",AR282-LOOKUP(2,1/(AI282:AQ282<>""),AI282:AQ282))) | IF(OR(F282="",AS282=""),"",IF(COUNT(AI282:AR282)=0,"",AS282-LOOKUP(2,1/(AI282:AR282<>""),AI282:AR282))) | IF(OR(F282="",AT282=""),"",IF(COUNT(AI282:AS282)=0,"",AT282-LOOKUP(2,1/(AI282:AS282<>""),AI282:AS282))) | IF(OR(F282="",AU282=""),"",IF(COUNT(AI282:AT282)=0,"",AU282-LOOKUP(2,1/(AI282:AT282<>""),AI282:AT282))) | IF(OR(F282="",AV282=""),"",IF(COUNT(AI282:AU282)=0,"",AV282-LOOKUP(2,1/(AI282:AU282<>""),AI282:AU282))) | IF(J282="","All_Provinces",IFERROR(VLOOKUP(J282,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K282="","All_Districts",IFERROR(VLOOKUP(K282,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F283="","",ROW()-3) | AF2-WSM-09 | Package #9-AF2 WSM: Construction of 1.Aka Khil Check dam and 2. Sra Qala Check dam in Sayed district, 3.Khar Check dam and 4.Mardala Check dam, located in Jaghatu districts of Wardak province. | 1 of 4 | AF2-WSM-A-020 | 1.Aka Khil Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Maidan Wardak | Sayed Abad | Aka Khil | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Sayed Abad Construction Company (SACC) | 021/2026 | 68618.92 | IF(AQ283="","",AQ283) |  | 7 | 2026-10-08 | IF(W283<>"",W283,IF(OR(T283="",V283=""),"",EDATE(T283,V283))) |  | 100 | Completed / Handover | Completed on August, 2026 | IF(F283="","",IF(COUNT(AI283:AV283)=0,IF(AA283="","Not started",AA283),SUBSTITUTE(LOOKUP(2,1/(AI283:AV283<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F283="",COUNT(AI283:AV283)=0),"",TODAY()-LOOKUP(2,1/(AI283:AV283<>""),AI283:AV283)) | IF(OR(F283="",COUNT(AI283:AV283)<2),"",LOOKUP(2,1/(AI283:AV283<>""),AI283:AV283)-MIN(AI283:AV283)) | IF(OR(AD283="",AC283="Not started",AC283=""),"",IFERROR(AD283-IF(VLOOKUP(AC283,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC283,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F283="","",IF(OR(AA283="Cancelled",AC283="Cancelled"),"Cancelled",IF(OR(AC283="Completed / Handover",Y283<>"",Z283>=100),"Completed — on track",IF(O283="Not awarded",IF(U283="",IF(X283="","No planned date",IF(TODAY()>X283,"Behind — past planned date",IF(X283-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U283,"Behind — award date passed",IF(U283-TODAY()<=30,"At risk — close to off track","On track"))),IF(X283="","No planned date",IF(AND(TODAY()>X283,OR(Z283="",Z283<100)),"Behind — past end date",IF(AND(T283<>"",X283<>"",Z283<>"",(Z283<100),((TODAY()-T283)/MAX(X283-T283,1)*100)-Z283>15),"Behind — progress lag",IF(AND(X283-TODAY()<=30,X283-TODAY()>=0,OR(Z283="",Z283<90)),"At risk — close to off track","On track")))))))) | IF(OR(F283="",AC283="Completed / Handover",AC283="Cancelled"),"",IF(O283="Not awarded",IF(U283<>"",U283-TODAY(),IF(X283="","",X283-TODAY())),IF(X283="","",X283-TODAY()))) | [8 empty] | 2026-03-10 | 2026-03-10 | 2026-10-08 |  |  |  | IF(OR(F283="",AJ283=""),"",IF(COUNT(AI283:AI283)=0,"",AJ283-LOOKUP(2,1/(AI283:AI283<>""),AI283:AI283))) | IF(OR(F283="",AK283=""),"",IF(COUNT(AI283:AJ283)=0,"",AK283-LOOKUP(2,1/(AI283:AJ283<>""),AI283:AJ283))) | IF(OR(F283="",AL283=""),"",IF(COUNT(AI283:AK283)=0,"",AL283-LOOKUP(2,1/(AI283:AK283<>""),AI283:AK283))) | IF(OR(F283="",AM283=""),"",IF(COUNT(AI283:AL283)=0,"",AM283-LOOKUP(2,1/(AI283:AL283<>""),AI283:AL283))) | IF(OR(F283="",AN283=""),"",IF(COUNT(AI283:AM283)=0,"",AN283-LOOKUP(2,1/(AI283:AM283<>""),AI283:AM283))) | IF(OR(F283="",AO283=""),"",IF(COUNT(AI283:AN283)=0,"",AO283-LOOKUP(2,1/(AI283:AN283<>""),AI283:AN283))) | IF(OR(F283="",AP283=""),"",IF(COUNT(AI283:AO283)=0,"",AP283-LOOKUP(2,1/(AI283:AO283<>""),AI283:AO283))) | IF(OR(F283="",AQ283=""),"",IF(COUNT(AI283:AP283)=0,"",AQ283-LOOKUP(2,1/(AI283:AP283<>""),AI283:AP283))) | IF(OR(F283="",AR283=""),"",IF(COUNT(AI283:AQ283)=0,"",AR283-LOOKUP(2,1/(AI283:AQ283<>""),AI283:AQ283))) | IF(OR(F283="",AS283=""),"",IF(COUNT(AI283:AR283)=0,"",AS283-LOOKUP(2,1/(AI283:AR283<>""),AI283:AR283))) | IF(OR(F283="",AT283=""),"",IF(COUNT(AI283:AS283)=0,"",AT283-LOOKUP(2,1/(AI283:AS283<>""),AI283:AS283))) | IF(OR(F283="",AU283=""),"",IF(COUNT(AI283:AT283)=0,"",AU283-LOOKUP(2,1/(AI283:AT283<>""),AI283:AT283))) | IF(OR(F283="",AV283=""),"",IF(COUNT(AI283:AU283)=0,"",AV283-LOOKUP(2,1/(AI283:AU283<>""),AI283:AU283))) | IF(J283="","All_Provinces",IFERROR(VLOOKUP(J283,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K283="","All_Districts",IFERROR(VLOOKUP(K283,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F284="","",ROW()-3) | AF2-WSM-09 | Package #9-AF2 WSM: Construction of 1.Aka Khil Check dam and 2. Sra Qala Check dam in Sayed district, 3.Khar Check dam and 4.Mardala Check dam, located in Jaghatu districts of Wardak province. | 2 of 4 | AF2-WSM-A-021 | 2.Sra Qala Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Maidan Wardak | Sayed Abad | Sra Qala | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Sayed Abad Construction Company (SACC) | 021/2026 |  | IF(AQ284="","",AQ284) |  | 7 | 2026-10-08 | IF(W284<>"",W284,IF(OR(T284="",V284=""),"",EDATE(T284,V284))) |  | 100 | Completed / Handover | Completed on August, 2026 | IF(F284="","",IF(COUNT(AI284:AV284)=0,IF(AA284="","Not started",AA284),SUBSTITUTE(LOOKUP(2,1/(AI284:AV284<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F284="",COUNT(AI284:AV284)=0),"",TODAY()-LOOKUP(2,1/(AI284:AV284<>""),AI284:AV284)) | IF(OR(F284="",COUNT(AI284:AV284)<2),"",LOOKUP(2,1/(AI284:AV284<>""),AI284:AV284)-MIN(AI284:AV284)) | IF(OR(AD284="",AC284="Not started",AC284=""),"",IFERROR(AD284-IF(VLOOKUP(AC284,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC284,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F284="","",IF(OR(AA284="Cancelled",AC284="Cancelled"),"Cancelled",IF(OR(AC284="Completed / Handover",Y284<>"",Z284>=100),"Completed — on track",IF(O284="Not awarded",IF(U284="",IF(X284="","No planned date",IF(TODAY()>X284,"Behind — past planned date",IF(X284-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U284,"Behind — award date passed",IF(U284-TODAY()<=30,"At risk — close to off track","On track"))),IF(X284="","No planned date",IF(AND(TODAY()>X284,OR(Z284="",Z284<100)),"Behind — past end date",IF(AND(T284<>"",X284<>"",Z284<>"",(Z284<100),((TODAY()-T284)/MAX(X284-T284,1)*100)-Z284>15),"Behind — progress lag",IF(AND(X284-TODAY()<=30,X284-TODAY()>=0,OR(Z284="",Z284<90)),"At risk — close to off track","On track")))))))) | IF(OR(F284="",AC284="Completed / Handover",AC284="Cancelled"),"",IF(O284="Not awarded",IF(U284<>"",U284-TODAY(),IF(X284="","",X284-TODAY())),IF(X284="","",X284-TODAY()))) | [8 empty] | 2026-03-10 | 2026-03-10 | 2026-10-08 |  |  |  | IF(OR(F284="",AJ284=""),"",IF(COUNT(AI284:AI284)=0,"",AJ284-LOOKUP(2,1/(AI284:AI284<>""),AI284:AI284))) | IF(OR(F284="",AK284=""),"",IF(COUNT(AI284:AJ284)=0,"",AK284-LOOKUP(2,1/(AI284:AJ284<>""),AI284:AJ284))) | IF(OR(F284="",AL284=""),"",IF(COUNT(AI284:AK284)=0,"",AL284-LOOKUP(2,1/(AI284:AK284<>""),AI284:AK284))) | IF(OR(F284="",AM284=""),"",IF(COUNT(AI284:AL284)=0,"",AM284-LOOKUP(2,1/(AI284:AL284<>""),AI284:AL284))) | IF(OR(F284="",AN284=""),"",IF(COUNT(AI284:AM284)=0,"",AN284-LOOKUP(2,1/(AI284:AM284<>""),AI284:AM284))) | IF(OR(F284="",AO284=""),"",IF(COUNT(AI284:AN284)=0,"",AO284-LOOKUP(2,1/(AI284:AN284<>""),AI284:AN284))) | IF(OR(F284="",AP284=""),"",IF(COUNT(AI284:AO284)=0,"",AP284-LOOKUP(2,1/(AI284:AO284<>""),AI284:AO284))) | IF(OR(F284="",AQ284=""),"",IF(COUNT(AI284:AP284)=0,"",AQ284-LOOKUP(2,1/(AI284:AP284<>""),AI284:AP284))) | IF(OR(F284="",AR284=""),"",IF(COUNT(AI284:AQ284)=0,"",AR284-LOOKUP(2,1/(AI284:AQ284<>""),AI284:AQ284))) | IF(OR(F284="",AS284=""),"",IF(COUNT(AI284:AR284)=0,"",AS284-LOOKUP(2,1/(AI284:AR284<>""),AI284:AR284))) | IF(OR(F284="",AT284=""),"",IF(COUNT(AI284:AS284)=0,"",AT284-LOOKUP(2,1/(AI284:AS284<>""),AI284:AS284))) | IF(OR(F284="",AU284=""),"",IF(COUNT(AI284:AT284)=0,"",AU284-LOOKUP(2,1/(AI284:AT284<>""),AI284:AT284))) | IF(OR(F284="",AV284=""),"",IF(COUNT(AI284:AU284)=0,"",AV284-LOOKUP(2,1/(AI284:AU284<>""),AI284:AU284))) | IF(J284="","All_Provinces",IFERROR(VLOOKUP(J284,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K284="","All_Districts",IFERROR(VLOOKUP(K284,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F285="","",ROW()-3) | AF2-WSM-09 | Package #9-AF2 WSM: Construction of 1.Aka Khil Check dam and 2. Sra Qala Check dam in Sayed district, 3.Khar Check dam and 4.Mardala Check dam, located in Jaghatu districts of Wardak province. | 3 of 4 | AF2-WSM-A-022 | 3.Khar Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Maidan Wardak | Jaghatu | Khar | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Sayed Abad Construction Company (SACC) | 021/2026 |  | IF(AQ285="","",AQ285) |  | 7 | 2026-10-08 | IF(W285<>"",W285,IF(OR(T285="",V285=""),"",EDATE(T285,V285))) |  | 100 | Completed / Handover | Completed on August, 2026 | IF(F285="","",IF(COUNT(AI285:AV285)=0,IF(AA285="","Not started",AA285),SUBSTITUTE(LOOKUP(2,1/(AI285:AV285<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F285="",COUNT(AI285:AV285)=0),"",TODAY()-LOOKUP(2,1/(AI285:AV285<>""),AI285:AV285)) | IF(OR(F285="",COUNT(AI285:AV285)<2),"",LOOKUP(2,1/(AI285:AV285<>""),AI285:AV285)-MIN(AI285:AV285)) | IF(OR(AD285="",AC285="Not started",AC285=""),"",IFERROR(AD285-IF(VLOOKUP(AC285,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC285,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F285="","",IF(OR(AA285="Cancelled",AC285="Cancelled"),"Cancelled",IF(OR(AC285="Completed / Handover",Y285<>"",Z285>=100),"Completed — on track",IF(O285="Not awarded",IF(U285="",IF(X285="","No planned date",IF(TODAY()>X285,"Behind — past planned date",IF(X285-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U285,"Behind — award date passed",IF(U285-TODAY()<=30,"At risk — close to off track","On track"))),IF(X285="","No planned date",IF(AND(TODAY()>X285,OR(Z285="",Z285<100)),"Behind — past end date",IF(AND(T285<>"",X285<>"",Z285<>"",(Z285<100),((TODAY()-T285)/MAX(X285-T285,1)*100)-Z285>15),"Behind — progress lag",IF(AND(X285-TODAY()<=30,X285-TODAY()>=0,OR(Z285="",Z285<90)),"At risk — close to off track","On track")))))))) | IF(OR(F285="",AC285="Completed / Handover",AC285="Cancelled"),"",IF(O285="Not awarded",IF(U285<>"",U285-TODAY(),IF(X285="","",X285-TODAY())),IF(X285="","",X285-TODAY()))) | [8 empty] | 2026-03-10 | 2026-03-10 | 2026-10-08 |  |  |  | IF(OR(F285="",AJ285=""),"",IF(COUNT(AI285:AI285)=0,"",AJ285-LOOKUP(2,1/(AI285:AI285<>""),AI285:AI285))) | IF(OR(F285="",AK285=""),"",IF(COUNT(AI285:AJ285)=0,"",AK285-LOOKUP(2,1/(AI285:AJ285<>""),AI285:AJ285))) | IF(OR(F285="",AL285=""),"",IF(COUNT(AI285:AK285)=0,"",AL285-LOOKUP(2,1/(AI285:AK285<>""),AI285:AK285))) | IF(OR(F285="",AM285=""),"",IF(COUNT(AI285:AL285)=0,"",AM285-LOOKUP(2,1/(AI285:AL285<>""),AI285:AL285))) | IF(OR(F285="",AN285=""),"",IF(COUNT(AI285:AM285)=0,"",AN285-LOOKUP(2,1/(AI285:AM285<>""),AI285:AM285))) | IF(OR(F285="",AO285=""),"",IF(COUNT(AI285:AN285)=0,"",AO285-LOOKUP(2,1/(AI285:AN285<>""),AI285:AN285))) | IF(OR(F285="",AP285=""),"",IF(COUNT(AI285:AO285)=0,"",AP285-LOOKUP(2,1/(AI285:AO285<>""),AI285:AO285))) | IF(OR(F285="",AQ285=""),"",IF(COUNT(AI285:AP285)=0,"",AQ285-LOOKUP(2,1/(AI285:AP285<>""),AI285:AP285))) | IF(OR(F285="",AR285=""),"",IF(COUNT(AI285:AQ285)=0,"",AR285-LOOKUP(2,1/(AI285:AQ285<>""),AI285:AQ285))) | IF(OR(F285="",AS285=""),"",IF(COUNT(AI285:AR285)=0,"",AS285-LOOKUP(2,1/(AI285:AR285<>""),AI285:AR285))) | IF(OR(F285="",AT285=""),"",IF(COUNT(AI285:AS285)=0,"",AT285-LOOKUP(2,1/(AI285:AS285<>""),AI285:AS285))) | IF(OR(F285="",AU285=""),"",IF(COUNT(AI285:AT285)=0,"",AU285-LOOKUP(2,1/(AI285:AT285<>""),AI285:AT285))) | IF(OR(F285="",AV285=""),"",IF(COUNT(AI285:AU285)=0,"",AV285-LOOKUP(2,1/(AI285:AU285<>""),AI285:AU285))) | IF(J285="","All_Provinces",IFERROR(VLOOKUP(J285,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K285="","All_Districts",IFERROR(VLOOKUP(K285,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F286="","",ROW()-3) | AF2-WSM-09 | Package #9-AF2 WSM: Construction of 1.Aka Khil Check dam and 2. Sra Qala Check dam in Sayed district, 3.Khar Check dam and 4.Mardala Check dam, located in Jaghatu districts of Wardak province. | 4 of 4 | AF2-WSM-A-023 | 4.Mardala Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Maidan Wardak | Jaghatu | Mardala | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Sayed Abad Construction Company (SACC) | 021/2026 |  | IF(AQ286="","",AQ286) |  | 7 | 2026-10-08 | IF(W286<>"",W286,IF(OR(T286="",V286=""),"",EDATE(T286,V286))) |  | 100 | Completed / Handover | Completed on August, 2026 | IF(F286="","",IF(COUNT(AI286:AV286)=0,IF(AA286="","Not started",AA286),SUBSTITUTE(LOOKUP(2,1/(AI286:AV286<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F286="",COUNT(AI286:AV286)=0),"",TODAY()-LOOKUP(2,1/(AI286:AV286<>""),AI286:AV286)) | IF(OR(F286="",COUNT(AI286:AV286)<2),"",LOOKUP(2,1/(AI286:AV286<>""),AI286:AV286)-MIN(AI286:AV286)) | IF(OR(AD286="",AC286="Not started",AC286=""),"",IFERROR(AD286-IF(VLOOKUP(AC286,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC286,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F286="","",IF(OR(AA286="Cancelled",AC286="Cancelled"),"Cancelled",IF(OR(AC286="Completed / Handover",Y286<>"",Z286>=100),"Completed — on track",IF(O286="Not awarded",IF(U286="",IF(X286="","No planned date",IF(TODAY()>X286,"Behind — past planned date",IF(X286-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U286,"Behind — award date passed",IF(U286-TODAY()<=30,"At risk — close to off track","On track"))),IF(X286="","No planned date",IF(AND(TODAY()>X286,OR(Z286="",Z286<100)),"Behind — past end date",IF(AND(T286<>"",X286<>"",Z286<>"",(Z286<100),((TODAY()-T286)/MAX(X286-T286,1)*100)-Z286>15),"Behind — progress lag",IF(AND(X286-TODAY()<=30,X286-TODAY()>=0,OR(Z286="",Z286<90)),"At risk — close to off track","On track")))))))) | IF(OR(F286="",AC286="Completed / Handover",AC286="Cancelled"),"",IF(O286="Not awarded",IF(U286<>"",U286-TODAY(),IF(X286="","",X286-TODAY())),IF(X286="","",X286-TODAY()))) | [8 empty] | 2026-03-10 | 2026-03-10 | 2026-10-08 |  |  |  | IF(OR(F286="",AJ286=""),"",IF(COUNT(AI286:AI286)=0,"",AJ286-LOOKUP(2,1/(AI286:AI286<>""),AI286:AI286))) | IF(OR(F286="",AK286=""),"",IF(COUNT(AI286:AJ286)=0,"",AK286-LOOKUP(2,1/(AI286:AJ286<>""),AI286:AJ286))) | IF(OR(F286="",AL286=""),"",IF(COUNT(AI286:AK286)=0,"",AL286-LOOKUP(2,1/(AI286:AK286<>""),AI286:AK286))) | IF(OR(F286="",AM286=""),"",IF(COUNT(AI286:AL286)=0,"",AM286-LOOKUP(2,1/(AI286:AL286<>""),AI286:AL286))) | IF(OR(F286="",AN286=""),"",IF(COUNT(AI286:AM286)=0,"",AN286-LOOKUP(2,1/(AI286:AM286<>""),AI286:AM286))) | IF(OR(F286="",AO286=""),"",IF(COUNT(AI286:AN286)=0,"",AO286-LOOKUP(2,1/(AI286:AN286<>""),AI286:AN286))) | IF(OR(F286="",AP286=""),"",IF(COUNT(AI286:AO286)=0,"",AP286-LOOKUP(2,1/(AI286:AO286<>""),AI286:AO286))) | IF(OR(F286="",AQ286=""),"",IF(COUNT(AI286:AP286)=0,"",AQ286-LOOKUP(2,1/(AI286:AP286<>""),AI286:AP286))) | IF(OR(F286="",AR286=""),"",IF(COUNT(AI286:AQ286)=0,"",AR286-LOOKUP(2,1/(AI286:AQ286<>""),AI286:AQ286))) | IF(OR(F286="",AS286=""),"",IF(COUNT(AI286:AR286)=0,"",AS286-LOOKUP(2,1/(AI286:AR286<>""),AI286:AR286))) | IF(OR(F286="",AT286=""),"",IF(COUNT(AI286:AS286)=0,"",AT286-LOOKUP(2,1/(AI286:AS286<>""),AI286:AS286))) | IF(OR(F286="",AU286=""),"",IF(COUNT(AI286:AT286)=0,"",AU286-LOOKUP(2,1/(AI286:AT286<>""),AI286:AT286))) | IF(OR(F286="",AV286=""),"",IF(COUNT(AI286:AU286)=0,"",AV286-LOOKUP(2,1/(AI286:AU286<>""),AI286:AU286))) | IF(J286="","All_Provinces",IFERROR(VLOOKUP(J286,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K286="","All_Districts",IFERROR(VLOOKUP(K286,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F287="","",ROW()-3) | AF2-WSM-10 | Package #10-AF2 WSM: Construction of Loy Shenkai Check dams # 1 and # 2 in Tagab district, and Shahr-e-Naw Check dam # 3 located in Nijrab districts of Kapisa province. | 1 of 3 | AF2-WSM-A-024 | 1. Loy Shenkai Check dams-1 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Tagab | Loy Shenkai-1 | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Kapisa Kohna Dah Construction Company (KKCC) | 020/2026 | 44028.02 | IF(AQ287="","",AQ287) |  | 6 | 2026-09-08 | IF(W287<>"",W287,IF(OR(T287="",V287=""),"",EDATE(T287,V287))) |  | 100 | Completed / Handover | Completed on August 2026 | IF(F287="","",IF(COUNT(AI287:AV287)=0,IF(AA287="","Not started",AA287),SUBSTITUTE(LOOKUP(2,1/(AI287:AV287<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F287="",COUNT(AI287:AV287)=0),"",TODAY()-LOOKUP(2,1/(AI287:AV287<>""),AI287:AV287)) | IF(OR(F287="",COUNT(AI287:AV287)<2),"",LOOKUP(2,1/(AI287:AV287<>""),AI287:AV287)-MIN(AI287:AV287)) | IF(OR(AD287="",AC287="Not started",AC287=""),"",IFERROR(AD287-IF(VLOOKUP(AC287,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC287,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F287="","",IF(OR(AA287="Cancelled",AC287="Cancelled"),"Cancelled",IF(OR(AC287="Completed / Handover",Y287<>"",Z287>=100),"Completed — on track",IF(O287="Not awarded",IF(U287="",IF(X287="","No planned date",IF(TODAY()>X287,"Behind — past planned date",IF(X287-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U287,"Behind — award date passed",IF(U287-TODAY()<=30,"At risk — close to off track","On track"))),IF(X287="","No planned date",IF(AND(TODAY()>X287,OR(Z287="",Z287<100)),"Behind — past end date",IF(AND(T287<>"",X287<>"",Z287<>"",(Z287<100),((TODAY()-T287)/MAX(X287-T287,1)*100)-Z287>15),"Behind — progress lag",IF(AND(X287-TODAY()<=30,X287-TODAY()>=0,OR(Z287="",Z287<90)),"At risk — close to off track","On track")))))))) | IF(OR(F287="",AC287="Completed / Handover",AC287="Cancelled"),"",IF(O287="Not awarded",IF(U287<>"",U287-TODAY(),IF(X287="","",X287-TODAY())),IF(X287="","",X287-TODAY()))) | [8 empty] | 2026-03-09 | 2026-03-09 | 2026-09-08 |  |  |  | IF(OR(F287="",AJ287=""),"",IF(COUNT(AI287:AI287)=0,"",AJ287-LOOKUP(2,1/(AI287:AI287<>""),AI287:AI287))) | IF(OR(F287="",AK287=""),"",IF(COUNT(AI287:AJ287)=0,"",AK287-LOOKUP(2,1/(AI287:AJ287<>""),AI287:AJ287))) | IF(OR(F287="",AL287=""),"",IF(COUNT(AI287:AK287)=0,"",AL287-LOOKUP(2,1/(AI287:AK287<>""),AI287:AK287))) | IF(OR(F287="",AM287=""),"",IF(COUNT(AI287:AL287)=0,"",AM287-LOOKUP(2,1/(AI287:AL287<>""),AI287:AL287))) | IF(OR(F287="",AN287=""),"",IF(COUNT(AI287:AM287)=0,"",AN287-LOOKUP(2,1/(AI287:AM287<>""),AI287:AM287))) | IF(OR(F287="",AO287=""),"",IF(COUNT(AI287:AN287)=0,"",AO287-LOOKUP(2,1/(AI287:AN287<>""),AI287:AN287))) | IF(OR(F287="",AP287=""),"",IF(COUNT(AI287:AO287)=0,"",AP287-LOOKUP(2,1/(AI287:AO287<>""),AI287:AO287))) | IF(OR(F287="",AQ287=""),"",IF(COUNT(AI287:AP287)=0,"",AQ287-LOOKUP(2,1/(AI287:AP287<>""),AI287:AP287))) | IF(OR(F287="",AR287=""),"",IF(COUNT(AI287:AQ287)=0,"",AR287-LOOKUP(2,1/(AI287:AQ287<>""),AI287:AQ287))) | IF(OR(F287="",AS287=""),"",IF(COUNT(AI287:AR287)=0,"",AS287-LOOKUP(2,1/(AI287:AR287<>""),AI287:AR287))) | IF(OR(F287="",AT287=""),"",IF(COUNT(AI287:AS287)=0,"",AT287-LOOKUP(2,1/(AI287:AS287<>""),AI287:AS287))) | IF(OR(F287="",AU287=""),"",IF(COUNT(AI287:AT287)=0,"",AU287-LOOKUP(2,1/(AI287:AT287<>""),AI287:AT287))) | IF(OR(F287="",AV287=""),"",IF(COUNT(AI287:AU287)=0,"",AV287-LOOKUP(2,1/(AI287:AU287<>""),AI287:AU287))) | IF(J287="","All_Provinces",IFERROR(VLOOKUP(J287,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K287="","All_Districts",IFERROR(VLOOKUP(K287,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F288="","",ROW()-3) | AF2-WSM-10 | Package #10-AF2 WSM: Construction of Loy Shenkai Check dams # 1 and # 2 in Tagab district, and Shahr-e-Naw Check dam # 3 located in Nijrab districts of Kapisa province. | 2 of 3 | AF2-WSM-A-025 | 2. Loy Shenkai Check dams-2 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Tagab | Loy Shenkai-2 | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Kapisa Kohna Dah Construction Company (KKCC) | 020/2026 |  | IF(AQ288="","",AQ288) |  | 6 | 2026-09-08 | IF(W288<>"",W288,IF(OR(T288="",V288=""),"",EDATE(T288,V288))) |  | 100 | Completed / Handover | Completed on August 2026 | IF(F288="","",IF(COUNT(AI288:AV288)=0,IF(AA288="","Not started",AA288),SUBSTITUTE(LOOKUP(2,1/(AI288:AV288<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F288="",COUNT(AI288:AV288)=0),"",TODAY()-LOOKUP(2,1/(AI288:AV288<>""),AI288:AV288)) | IF(OR(F288="",COUNT(AI288:AV288)<2),"",LOOKUP(2,1/(AI288:AV288<>""),AI288:AV288)-MIN(AI288:AV288)) | IF(OR(AD288="",AC288="Not started",AC288=""),"",IFERROR(AD288-IF(VLOOKUP(AC288,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC288,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F288="","",IF(OR(AA288="Cancelled",AC288="Cancelled"),"Cancelled",IF(OR(AC288="Completed / Handover",Y288<>"",Z288>=100),"Completed — on track",IF(O288="Not awarded",IF(U288="",IF(X288="","No planned date",IF(TODAY()>X288,"Behind — past planned date",IF(X288-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U288,"Behind — award date passed",IF(U288-TODAY()<=30,"At risk — close to off track","On track"))),IF(X288="","No planned date",IF(AND(TODAY()>X288,OR(Z288="",Z288<100)),"Behind — past end date",IF(AND(T288<>"",X288<>"",Z288<>"",(Z288<100),((TODAY()-T288)/MAX(X288-T288,1)*100)-Z288>15),"Behind — progress lag",IF(AND(X288-TODAY()<=30,X288-TODAY()>=0,OR(Z288="",Z288<90)),"At risk — close to off track","On track")))))))) | IF(OR(F288="",AC288="Completed / Handover",AC288="Cancelled"),"",IF(O288="Not awarded",IF(U288<>"",U288-TODAY(),IF(X288="","",X288-TODAY())),IF(X288="","",X288-TODAY()))) | [8 empty] | 2026-03-09 | 2026-03-09 | 2026-09-08 |  |  |  | IF(OR(F288="",AJ288=""),"",IF(COUNT(AI288:AI288)=0,"",AJ288-LOOKUP(2,1/(AI288:AI288<>""),AI288:AI288))) | IF(OR(F288="",AK288=""),"",IF(COUNT(AI288:AJ288)=0,"",AK288-LOOKUP(2,1/(AI288:AJ288<>""),AI288:AJ288))) | IF(OR(F288="",AL288=""),"",IF(COUNT(AI288:AK288)=0,"",AL288-LOOKUP(2,1/(AI288:AK288<>""),AI288:AK288))) | IF(OR(F288="",AM288=""),"",IF(COUNT(AI288:AL288)=0,"",AM288-LOOKUP(2,1/(AI288:AL288<>""),AI288:AL288))) | IF(OR(F288="",AN288=""),"",IF(COUNT(AI288:AM288)=0,"",AN288-LOOKUP(2,1/(AI288:AM288<>""),AI288:AM288))) | IF(OR(F288="",AO288=""),"",IF(COUNT(AI288:AN288)=0,"",AO288-LOOKUP(2,1/(AI288:AN288<>""),AI288:AN288))) | IF(OR(F288="",AP288=""),"",IF(COUNT(AI288:AO288)=0,"",AP288-LOOKUP(2,1/(AI288:AO288<>""),AI288:AO288))) | IF(OR(F288="",AQ288=""),"",IF(COUNT(AI288:AP288)=0,"",AQ288-LOOKUP(2,1/(AI288:AP288<>""),AI288:AP288))) | IF(OR(F288="",AR288=""),"",IF(COUNT(AI288:AQ288)=0,"",AR288-LOOKUP(2,1/(AI288:AQ288<>""),AI288:AQ288))) | IF(OR(F288="",AS288=""),"",IF(COUNT(AI288:AR288)=0,"",AS288-LOOKUP(2,1/(AI288:AR288<>""),AI288:AR288))) | IF(OR(F288="",AT288=""),"",IF(COUNT(AI288:AS288)=0,"",AT288-LOOKUP(2,1/(AI288:AS288<>""),AI288:AS288))) | IF(OR(F288="",AU288=""),"",IF(COUNT(AI288:AT288)=0,"",AU288-LOOKUP(2,1/(AI288:AT288<>""),AI288:AT288))) | IF(OR(F288="",AV288=""),"",IF(COUNT(AI288:AU288)=0,"",AV288-LOOKUP(2,1/(AI288:AU288<>""),AI288:AU288))) | IF(J288="","All_Provinces",IFERROR(VLOOKUP(J288,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K288="","All_Districts",IFERROR(VLOOKUP(K288,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F289="","",ROW()-3) | AF2-WSM-10 | Package #10-AF2 WSM: Construction of Loy Shenkai Check dams # 1 and # 2 in Tagab district, and Shahr-e-Naw Check dam # 3 located in Nijrab districts of Kapisa province. | 3 of 3 | AF2-WSM-A-026 | 3. Shahr-e-Naw Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kapisa | Nijrab | Shahr-e-Naw | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Kapisa Kohna Dah Construction Company (KKCC) | 020/2026 |  | IF(AQ289="","",AQ289) |  | 6 | 2026-09-08 | IF(W289<>"",W289,IF(OR(T289="",V289=""),"",EDATE(T289,V289))) |  | 100 | Completed / Handover | Completed on August 2026 | IF(F289="","",IF(COUNT(AI289:AV289)=0,IF(AA289="","Not started",AA289),SUBSTITUTE(LOOKUP(2,1/(AI289:AV289<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F289="",COUNT(AI289:AV289)=0),"",TODAY()-LOOKUP(2,1/(AI289:AV289<>""),AI289:AV289)) | IF(OR(F289="",COUNT(AI289:AV289)<2),"",LOOKUP(2,1/(AI289:AV289<>""),AI289:AV289)-MIN(AI289:AV289)) | IF(OR(AD289="",AC289="Not started",AC289=""),"",IFERROR(AD289-IF(VLOOKUP(AC289,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC289,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F289="","",IF(OR(AA289="Cancelled",AC289="Cancelled"),"Cancelled",IF(OR(AC289="Completed / Handover",Y289<>"",Z289>=100),"Completed — on track",IF(O289="Not awarded",IF(U289="",IF(X289="","No planned date",IF(TODAY()>X289,"Behind — past planned date",IF(X289-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U289,"Behind — award date passed",IF(U289-TODAY()<=30,"At risk — close to off track","On track"))),IF(X289="","No planned date",IF(AND(TODAY()>X289,OR(Z289="",Z289<100)),"Behind — past end date",IF(AND(T289<>"",X289<>"",Z289<>"",(Z289<100),((TODAY()-T289)/MAX(X289-T289,1)*100)-Z289>15),"Behind — progress lag",IF(AND(X289-TODAY()<=30,X289-TODAY()>=0,OR(Z289="",Z289<90)),"At risk — close to off track","On track")))))))) | IF(OR(F289="",AC289="Completed / Handover",AC289="Cancelled"),"",IF(O289="Not awarded",IF(U289<>"",U289-TODAY(),IF(X289="","",X289-TODAY())),IF(X289="","",X289-TODAY()))) | [8 empty] | 2026-03-09 | 2026-03-09 | 2026-09-08 |  |  |  | IF(OR(F289="",AJ289=""),"",IF(COUNT(AI289:AI289)=0,"",AJ289-LOOKUP(2,1/(AI289:AI289<>""),AI289:AI289))) | IF(OR(F289="",AK289=""),"",IF(COUNT(AI289:AJ289)=0,"",AK289-LOOKUP(2,1/(AI289:AJ289<>""),AI289:AJ289))) | IF(OR(F289="",AL289=""),"",IF(COUNT(AI289:AK289)=0,"",AL289-LOOKUP(2,1/(AI289:AK289<>""),AI289:AK289))) | IF(OR(F289="",AM289=""),"",IF(COUNT(AI289:AL289)=0,"",AM289-LOOKUP(2,1/(AI289:AL289<>""),AI289:AL289))) | IF(OR(F289="",AN289=""),"",IF(COUNT(AI289:AM289)=0,"",AN289-LOOKUP(2,1/(AI289:AM289<>""),AI289:AM289))) | IF(OR(F289="",AO289=""),"",IF(COUNT(AI289:AN289)=0,"",AO289-LOOKUP(2,1/(AI289:AN289<>""),AI289:AN289))) | IF(OR(F289="",AP289=""),"",IF(COUNT(AI289:AO289)=0,"",AP289-LOOKUP(2,1/(AI289:AO289<>""),AI289:AO289))) | IF(OR(F289="",AQ289=""),"",IF(COUNT(AI289:AP289)=0,"",AQ289-LOOKUP(2,1/(AI289:AP289<>""),AI289:AP289))) | IF(OR(F289="",AR289=""),"",IF(COUNT(AI289:AQ289)=0,"",AR289-LOOKUP(2,1/(AI289:AQ289<>""),AI289:AQ289))) | IF(OR(F289="",AS289=""),"",IF(COUNT(AI289:AR289)=0,"",AS289-LOOKUP(2,1/(AI289:AR289<>""),AI289:AR289))) | IF(OR(F289="",AT289=""),"",IF(COUNT(AI289:AS289)=0,"",AT289-LOOKUP(2,1/(AI289:AS289<>""),AI289:AS289))) | IF(OR(F289="",AU289=""),"",IF(COUNT(AI289:AT289)=0,"",AU289-LOOKUP(2,1/(AI289:AT289<>""),AI289:AT289))) | IF(OR(F289="",AV289=""),"",IF(COUNT(AI289:AU289)=0,"",AV289-LOOKUP(2,1/(AI289:AU289<>""),AI289:AU289))) | IF(J289="","All_Provinces",IFERROR(VLOOKUP(J289,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K289="","All_Districts",IFERROR(VLOOKUP(K289,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F290="","",ROW()-3) | AF2-WSM-11 | Package #11-AF2 WSM: Construction of 3 Check dams 1.Wolangak in Shikh Ali, 2.Sanzalai, and 3.Sharkai Olia in Koh-e-Safi district of Parwan province. | 1 of 3 | AF2-WSM-A-027 | Sanzalai and Sharki Olia | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Parwan | Koh-e-Safi | Sanzalai | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Hemat Ghorzang Construction & Logistic Service Company (HGCC) | 043/2026 |  | IF(AQ290="","",AQ290) |  | 5 | 2026-11-23 | IF(W290<>"",W290,IF(OR(T290="",V290=""),"",EDATE(T290,V290))) |  | 20 | Under Construction | Completed on August 2026 | IF(F290="","",IF(COUNT(AI290:AV290)=0,IF(AA290="","Not started",AA290),SUBSTITUTE(LOOKUP(2,1/(AI290:AV290<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F290="",COUNT(AI290:AV290)=0),"",TODAY()-LOOKUP(2,1/(AI290:AV290<>""),AI290:AV290)) | IF(OR(F290="",COUNT(AI290:AV290)<2),"",LOOKUP(2,1/(AI290:AV290<>""),AI290:AV290)-MIN(AI290:AV290)) | IF(OR(AD290="",AC290="Not started",AC290=""),"",IFERROR(AD290-IF(VLOOKUP(AC290,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC290,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F290="","",IF(OR(AA290="Cancelled",AC290="Cancelled"),"Cancelled",IF(OR(AC290="Completed / Handover",Y290<>"",Z290>=100),"Completed — on track",IF(O290="Not awarded",IF(U290="",IF(X290="","No planned date",IF(TODAY()>X290,"Behind — past planned date",IF(X290-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U290,"Behind — award date passed",IF(U290-TODAY()<=30,"At risk — close to off track","On track"))),IF(X290="","No planned date",IF(AND(TODAY()>X290,OR(Z290="",Z290<100)),"Behind — past end date",IF(AND(T290<>"",X290<>"",Z290<>"",(Z290<100),((TODAY()-T290)/MAX(X290-T290,1)*100)-Z290>15),"Behind — progress lag",IF(AND(X290-TODAY()<=30,X290-TODAY()>=0,OR(Z290="",Z290<90)),"At risk — close to off track","On track")))))))) | IF(OR(F290="",AC290="Completed / Handover",AC290="Cancelled"),"",IF(O290="Not awarded",IF(U290<>"",U290-TODAY(),IF(X290="","",X290-TODAY())),IF(X290="","",X290-TODAY()))) | [8 empty] | 2026-06-24 | 2026-06-24 |  |  |  |  | IF(OR(F290="",AJ290=""),"",IF(COUNT(AI290:AI290)=0,"",AJ290-LOOKUP(2,1/(AI290:AI290<>""),AI290:AI290))) | IF(OR(F290="",AK290=""),"",IF(COUNT(AI290:AJ290)=0,"",AK290-LOOKUP(2,1/(AI290:AJ290<>""),AI290:AJ290))) | IF(OR(F290="",AL290=""),"",IF(COUNT(AI290:AK290)=0,"",AL290-LOOKUP(2,1/(AI290:AK290<>""),AI290:AK290))) | IF(OR(F290="",AM290=""),"",IF(COUNT(AI290:AL290)=0,"",AM290-LOOKUP(2,1/(AI290:AL290<>""),AI290:AL290))) | IF(OR(F290="",AN290=""),"",IF(COUNT(AI290:AM290)=0,"",AN290-LOOKUP(2,1/(AI290:AM290<>""),AI290:AM290))) | IF(OR(F290="",AO290=""),"",IF(COUNT(AI290:AN290)=0,"",AO290-LOOKUP(2,1/(AI290:AN290<>""),AI290:AN290))) | IF(OR(F290="",AP290=""),"",IF(COUNT(AI290:AO290)=0,"",AP290-LOOKUP(2,1/(AI290:AO290<>""),AI290:AO290))) | IF(OR(F290="",AQ290=""),"",IF(COUNT(AI290:AP290)=0,"",AQ290-LOOKUP(2,1/(AI290:AP290<>""),AI290:AP290))) | IF(OR(F290="",AR290=""),"",IF(COUNT(AI290:AQ290)=0,"",AR290-LOOKUP(2,1/(AI290:AQ290<>""),AI290:AQ290))) | IF(OR(F290="",AS290=""),"",IF(COUNT(AI290:AR290)=0,"",AS290-LOOKUP(2,1/(AI290:AR290<>""),AI290:AR290))) | IF(OR(F290="",AT290=""),"",IF(COUNT(AI290:AS290)=0,"",AT290-LOOKUP(2,1/(AI290:AS290<>""),AI290:AS290))) | IF(OR(F290="",AU290=""),"",IF(COUNT(AI290:AT290)=0,"",AU290-LOOKUP(2,1/(AI290:AT290<>""),AI290:AT290))) | IF(OR(F290="",AV290=""),"",IF(COUNT(AI290:AU290)=0,"",AV290-LOOKUP(2,1/(AI290:AU290<>""),AI290:AU290))) | IF(J290="","All_Provinces",IFERROR(VLOOKUP(J290,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K290="","All_Districts",IFERROR(VLOOKUP(K290,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F291="","",ROW()-3) | AF2-WSM-11 | Package #11-AF2 WSM: Construction of 3 Check dams 1.Wolangak in Shikh Ali, 2.Sanzalai, and 3.Sharkai Olia in Koh-e-Safi district of Parwan province. | 2 of 3 | AF2-WSM-A-028 | Sharkai Olia Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Parwan | Koh-e-Safi | Sharki Olia | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Hemat Ghorzang Construction & Logistic Service Company (HGCC) | 043/2026 |  | IF(AQ291="","",AQ291) |  | 5 | 2026-11-23 | IF(W291<>"",W291,IF(OR(T291="",V291=""),"",EDATE(T291,V291))) |  | 5 | Under Construction | Completed on August 2026 | IF(F291="","",IF(COUNT(AI291:AV291)=0,IF(AA291="","Not started",AA291),SUBSTITUTE(LOOKUP(2,1/(AI291:AV291<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F291="",COUNT(AI291:AV291)=0),"",TODAY()-LOOKUP(2,1/(AI291:AV291<>""),AI291:AV291)) | IF(OR(F291="",COUNT(AI291:AV291)<2),"",LOOKUP(2,1/(AI291:AV291<>""),AI291:AV291)-MIN(AI291:AV291)) | IF(OR(AD291="",AC291="Not started",AC291=""),"",IFERROR(AD291-IF(VLOOKUP(AC291,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC291,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F291="","",IF(OR(AA291="Cancelled",AC291="Cancelled"),"Cancelled",IF(OR(AC291="Completed / Handover",Y291<>"",Z291>=100),"Completed — on track",IF(O291="Not awarded",IF(U291="",IF(X291="","No planned date",IF(TODAY()>X291,"Behind — past planned date",IF(X291-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U291,"Behind — award date passed",IF(U291-TODAY()<=30,"At risk — close to off track","On track"))),IF(X291="","No planned date",IF(AND(TODAY()>X291,OR(Z291="",Z291<100)),"Behind — past end date",IF(AND(T291<>"",X291<>"",Z291<>"",(Z291<100),((TODAY()-T291)/MAX(X291-T291,1)*100)-Z291>15),"Behind — progress lag",IF(AND(X291-TODAY()<=30,X291-TODAY()>=0,OR(Z291="",Z291<90)),"At risk — close to off track","On track")))))))) | IF(OR(F291="",AC291="Completed / Handover",AC291="Cancelled"),"",IF(O291="Not awarded",IF(U291<>"",U291-TODAY(),IF(X291="","",X291-TODAY())),IF(X291="","",X291-TODAY()))) | [8 empty] | 2026-06-24 | 2026-06-24 |  |  |  |  | IF(OR(F291="",AJ291=""),"",IF(COUNT(AI291:AI291)=0,"",AJ291-LOOKUP(2,1/(AI291:AI291<>""),AI291:AI291))) | IF(OR(F291="",AK291=""),"",IF(COUNT(AI291:AJ291)=0,"",AK291-LOOKUP(2,1/(AI291:AJ291<>""),AI291:AJ291))) | IF(OR(F291="",AL291=""),"",IF(COUNT(AI291:AK291)=0,"",AL291-LOOKUP(2,1/(AI291:AK291<>""),AI291:AK291))) | IF(OR(F291="",AM291=""),"",IF(COUNT(AI291:AL291)=0,"",AM291-LOOKUP(2,1/(AI291:AL291<>""),AI291:AL291))) | IF(OR(F291="",AN291=""),"",IF(COUNT(AI291:AM291)=0,"",AN291-LOOKUP(2,1/(AI291:AM291<>""),AI291:AM291))) | IF(OR(F291="",AO291=""),"",IF(COUNT(AI291:AN291)=0,"",AO291-LOOKUP(2,1/(AI291:AN291<>""),AI291:AN291))) | IF(OR(F291="",AP291=""),"",IF(COUNT(AI291:AO291)=0,"",AP291-LOOKUP(2,1/(AI291:AO291<>""),AI291:AO291))) | IF(OR(F291="",AQ291=""),"",IF(COUNT(AI291:AP291)=0,"",AQ291-LOOKUP(2,1/(AI291:AP291<>""),AI291:AP291))) | IF(OR(F291="",AR291=""),"",IF(COUNT(AI291:AQ291)=0,"",AR291-LOOKUP(2,1/(AI291:AQ291<>""),AI291:AQ291))) | IF(OR(F291="",AS291=""),"",IF(COUNT(AI291:AR291)=0,"",AS291-LOOKUP(2,1/(AI291:AR291<>""),AI291:AR291))) | IF(OR(F291="",AT291=""),"",IF(COUNT(AI291:AS291)=0,"",AT291-LOOKUP(2,1/(AI291:AS291<>""),AI291:AS291))) | IF(OR(F291="",AU291=""),"",IF(COUNT(AI291:AT291)=0,"",AU291-LOOKUP(2,1/(AI291:AT291<>""),AI291:AT291))) | IF(OR(F291="",AV291=""),"",IF(COUNT(AI291:AU291)=0,"",AV291-LOOKUP(2,1/(AI291:AU291<>""),AI291:AU291))) | IF(J291="","All_Provinces",IFERROR(VLOOKUP(J291,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K291="","All_Districts",IFERROR(VLOOKUP(K291,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F292="","",ROW()-3) | AF2-WSM-11 | Package #11-AF2 WSM: Construction of 3 Check dams 1.Wolangak in Shikh Ali, 2.Sanzalai, and 3.Sharkai Olia in Koh-e-Safi district of Parwan province. | 3 of 3 | AF2-WSM-A-029 | Wolangak Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Parwan | Shikh Ali | Wolangak | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Hemat Ghorzang Construction & Logistic Service Company (HGCC) | 043/2026 | 77145 | IF(AQ292="","",AQ292) |  | 5 | 2026-11-23 | IF(W292<>"",W292,IF(OR(T292="",V292=""),"",EDATE(T292,V292))) |  | 0 | Awarded | Completed on August 2026 | IF(F292="","",IF(COUNT(AI292:AV292)=0,IF(AA292="","Not started",AA292),SUBSTITUTE(LOOKUP(2,1/(AI292:AV292<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F292="",COUNT(AI292:AV292)=0),"",TODAY()-LOOKUP(2,1/(AI292:AV292<>""),AI292:AV292)) | IF(OR(F292="",COUNT(AI292:AV292)<2),"",LOOKUP(2,1/(AI292:AV292<>""),AI292:AV292)-MIN(AI292:AV292)) | IF(OR(AD292="",AC292="Not started",AC292=""),"",IFERROR(AD292-IF(VLOOKUP(AC292,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC292,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F292="","",IF(OR(AA292="Cancelled",AC292="Cancelled"),"Cancelled",IF(OR(AC292="Completed / Handover",Y292<>"",Z292>=100),"Completed — on track",IF(O292="Not awarded",IF(U292="",IF(X292="","No planned date",IF(TODAY()>X292,"Behind — past planned date",IF(X292-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U292,"Behind — award date passed",IF(U292-TODAY()<=30,"At risk — close to off track","On track"))),IF(X292="","No planned date",IF(AND(TODAY()>X292,OR(Z292="",Z292<100)),"Behind — past end date",IF(AND(T292<>"",X292<>"",Z292<>"",(Z292<100),((TODAY()-T292)/MAX(X292-T292,1)*100)-Z292>15),"Behind — progress lag",IF(AND(X292-TODAY()<=30,X292-TODAY()>=0,OR(Z292="",Z292<90)),"At risk — close to off track","On track")))))))) | IF(OR(F292="",AC292="Completed / Handover",AC292="Cancelled"),"",IF(O292="Not awarded",IF(U292<>"",U292-TODAY(),IF(X292="","",X292-TODAY())),IF(X292="","",X292-TODAY()))) | [8 empty] | 2026-06-24 | [5 empty] | IF(OR(F292="",AJ292=""),"",IF(COUNT(AI292:AI292)=0,"",AJ292-LOOKUP(2,1/(AI292:AI292<>""),AI292:AI292))) | IF(OR(F292="",AK292=""),"",IF(COUNT(AI292:AJ292)=0,"",AK292-LOOKUP(2,1/(AI292:AJ292<>""),AI292:AJ292))) | IF(OR(F292="",AL292=""),"",IF(COUNT(AI292:AK292)=0,"",AL292-LOOKUP(2,1/(AI292:AK292<>""),AI292:AK292))) | IF(OR(F292="",AM292=""),"",IF(COUNT(AI292:AL292)=0,"",AM292-LOOKUP(2,1/(AI292:AL292<>""),AI292:AL292))) | IF(OR(F292="",AN292=""),"",IF(COUNT(AI292:AM292)=0,"",AN292-LOOKUP(2,1/(AI292:AM292<>""),AI292:AM292))) | IF(OR(F292="",AO292=""),"",IF(COUNT(AI292:AN292)=0,"",AO292-LOOKUP(2,1/(AI292:AN292<>""),AI292:AN292))) | IF(OR(F292="",AP292=""),"",IF(COUNT(AI292:AO292)=0,"",AP292-LOOKUP(2,1/(AI292:AO292<>""),AI292:AO292))) | IF(OR(F292="",AQ292=""),"",IF(COUNT(AI292:AP292)=0,"",AQ292-LOOKUP(2,1/(AI292:AP292<>""),AI292:AP292))) | IF(OR(F292="",AR292=""),"",IF(COUNT(AI292:AQ292)=0,"",AR292-LOOKUP(2,1/(AI292:AQ292<>""),AI292:AQ292))) | IF(OR(F292="",AS292=""),"",IF(COUNT(AI292:AR292)=0,"",AS292-LOOKUP(2,1/(AI292:AR292<>""),AI292:AR292))) | IF(OR(F292="",AT292=""),"",IF(COUNT(AI292:AS292)=0,"",AT292-LOOKUP(2,1/(AI292:AS292<>""),AI292:AS292))) | IF(OR(F292="",AU292=""),"",IF(COUNT(AI292:AT292)=0,"",AU292-LOOKUP(2,1/(AI292:AT292<>""),AI292:AT292))) | IF(OR(F292="",AV292=""),"",IF(COUNT(AI292:AU292)=0,"",AV292-LOOKUP(2,1/(AI292:AU292<>""),AI292:AU292))) | IF(J292="","All_Provinces",IFERROR(VLOOKUP(J292,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K292="","All_Districts",IFERROR(VLOOKUP(K292,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F293="","",ROW()-3) | AF2-WSM-12 | Package #12-AF2 WSM: Construction of 4 Check dams 1. Qoli Ghafoor, 2. Dara-e-Qala-e-Qazi in PD#13 Kabul city, 3.Gul Mohammad and 4.Qala-e-Shah Mahmood in Deh Sabz district of Kabul province. | 1 of 2 | AF2-WSM-N-003 | Gul Mohammad, Qalai e Shah mohammad Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | Deh Sabz | Gul Mohammad, Qalai e Shah mohammad | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 197430 | IF(AQ293="","",AQ293) | 2026-12-15 | 8.9 | 2027-09-11 | IF(W293<>"",W293,IF(OR(T293="",V293=""),"",EDATE(T293,V293))) |  |  | PR to be Raised | Construction of the check dam will be completed in seven months. Additional three months have been kept as slack period during Jan-March. | IF(F293="","",IF(COUNT(AI293:AV293)=0,IF(AA293="","Not started",AA293),SUBSTITUTE(LOOKUP(2,1/(AI293:AV293<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F293="",COUNT(AI293:AV293)=0),"",TODAY()-LOOKUP(2,1/(AI293:AV293<>""),AI293:AV293)) | IF(OR(F293="",COUNT(AI293:AV293)<2),"",LOOKUP(2,1/(AI293:AV293<>""),AI293:AV293)-MIN(AI293:AV293)) | IF(OR(AD293="",AC293="Not started",AC293=""),"",IFERROR(AD293-IF(VLOOKUP(AC293,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC293,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F293="","",IF(OR(AA293="Cancelled",AC293="Cancelled"),"Cancelled",IF(OR(AC293="Completed / Handover",Y293<>"",Z293>=100),"Completed — on track",IF(O293="Not awarded",IF(U293="",IF(X293="","No planned date",IF(TODAY()>X293,"Behind — past planned date",IF(X293-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U293,"Behind — award date passed",IF(U293-TODAY()<=30,"At risk — close to off track","On track"))),IF(X293="","No planned date",IF(AND(TODAY()>X293,OR(Z293="",Z293<100)),"Behind — past end date",IF(AND(T293<>"",X293<>"",Z293<>"",(Z293<100),((TODAY()-T293)/MAX(X293-T293,1)*100)-Z293>15),"Behind — progress lag",IF(AND(X293-TODAY()<=30,X293-TODAY()>=0,OR(Z293="",Z293<90)),"At risk — close to off track","On track")))))))) | IF(OR(F293="",AC293="Completed / Handover",AC293="Cancelled"),"",IF(O293="Not awarded",IF(U293<>"",U293-TODAY(),IF(X293="","",X293-TODAY())),IF(X293="","",X293-TODAY()))) | [14 empty] | IF(OR(F293="",AJ293=""),"",IF(COUNT(AI293:AI293)=0,"",AJ293-LOOKUP(2,1/(AI293:AI293<>""),AI293:AI293))) | IF(OR(F293="",AK293=""),"",IF(COUNT(AI293:AJ293)=0,"",AK293-LOOKUP(2,1/(AI293:AJ293<>""),AI293:AJ293))) | IF(OR(F293="",AL293=""),"",IF(COUNT(AI293:AK293)=0,"",AL293-LOOKUP(2,1/(AI293:AK293<>""),AI293:AK293))) | IF(OR(F293="",AM293=""),"",IF(COUNT(AI293:AL293)=0,"",AM293-LOOKUP(2,1/(AI293:AL293<>""),AI293:AL293))) | IF(OR(F293="",AN293=""),"",IF(COUNT(AI293:AM293)=0,"",AN293-LOOKUP(2,1/(AI293:AM293<>""),AI293:AM293))) | IF(OR(F293="",AO293=""),"",IF(COUNT(AI293:AN293)=0,"",AO293-LOOKUP(2,1/(AI293:AN293<>""),AI293:AN293))) | IF(OR(F293="",AP293=""),"",IF(COUNT(AI293:AO293)=0,"",AP293-LOOKUP(2,1/(AI293:AO293<>""),AI293:AO293))) | IF(OR(F293="",AQ293=""),"",IF(COUNT(AI293:AP293)=0,"",AQ293-LOOKUP(2,1/(AI293:AP293<>""),AI293:AP293))) | IF(OR(F293="",AR293=""),"",IF(COUNT(AI293:AQ293)=0,"",AR293-LOOKUP(2,1/(AI293:AQ293<>""),AI293:AQ293))) | IF(OR(F293="",AS293=""),"",IF(COUNT(AI293:AR293)=0,"",AS293-LOOKUP(2,1/(AI293:AR293<>""),AI293:AR293))) | IF(OR(F293="",AT293=""),"",IF(COUNT(AI293:AS293)=0,"",AT293-LOOKUP(2,1/(AI293:AS293<>""),AI293:AS293))) | IF(OR(F293="",AU293=""),"",IF(COUNT(AI293:AT293)=0,"",AU293-LOOKUP(2,1/(AI293:AT293<>""),AI293:AT293))) | IF(OR(F293="",AV293=""),"",IF(COUNT(AI293:AU293)=0,"",AV293-LOOKUP(2,1/(AI293:AU293<>""),AI293:AU293))) | IF(J293="","All_Provinces",IFERROR(VLOOKUP(J293,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K293="","All_Districts",IFERROR(VLOOKUP(K293,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F294="","",ROW()-3) | AF2-WSM-12 | Package #12-AF2 WSM: Construction of 4 Check dams 1. Qoli Ghafoor, 2. Dara-e-Qala-e-Qazi in PD#13 Kabul city, 3.Gul Mohammad and 4.Qala-e-Shah Mahmood in Deh Sabz district of Kabul province. | 2 of 2 | AF2-WSM-N-004 | Qoli Ghafoor, Dara-e-Qala-e-Qazi Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central / Kabul | Kabul | PD#13 Kabul | Qoli Ghafoor, Dara-e-Qala-e-Qazi | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 197430 | IF(AQ294="","",AQ294) | 2026-12-15 | 8.9 | 2027-09-11 | IF(W294<>"",W294,IF(OR(T294="",V294=""),"",EDATE(T294,V294))) |  |  | PR to be Raised | Construction of the check dam will be completed in seven months. Additional three months have been kept as slack period during Jan-March. | IF(F294="","",IF(COUNT(AI294:AV294)=0,IF(AA294="","Not started",AA294),SUBSTITUTE(LOOKUP(2,1/(AI294:AV294<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F294="",COUNT(AI294:AV294)=0),"",TODAY()-LOOKUP(2,1/(AI294:AV294<>""),AI294:AV294)) | IF(OR(F294="",COUNT(AI294:AV294)<2),"",LOOKUP(2,1/(AI294:AV294<>""),AI294:AV294)-MIN(AI294:AV294)) | IF(OR(AD294="",AC294="Not started",AC294=""),"",IFERROR(AD294-IF(VLOOKUP(AC294,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC294,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F294="","",IF(OR(AA294="Cancelled",AC294="Cancelled"),"Cancelled",IF(OR(AC294="Completed / Handover",Y294<>"",Z294>=100),"Completed — on track",IF(O294="Not awarded",IF(U294="",IF(X294="","No planned date",IF(TODAY()>X294,"Behind — past planned date",IF(X294-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U294,"Behind — award date passed",IF(U294-TODAY()<=30,"At risk — close to off track","On track"))),IF(X294="","No planned date",IF(AND(TODAY()>X294,OR(Z294="",Z294<100)),"Behind — past end date",IF(AND(T294<>"",X294<>"",Z294<>"",(Z294<100),((TODAY()-T294)/MAX(X294-T294,1)*100)-Z294>15),"Behind — progress lag",IF(AND(X294-TODAY()<=30,X294-TODAY()>=0,OR(Z294="",Z294<90)),"At risk — close to off track","On track")))))))) | IF(OR(F294="",AC294="Completed / Handover",AC294="Cancelled"),"",IF(O294="Not awarded",IF(U294<>"",U294-TODAY(),IF(X294="","",X294-TODAY())),IF(X294="","",X294-TODAY()))) | [14 empty] | IF(OR(F294="",AJ294=""),"",IF(COUNT(AI294:AI294)=0,"",AJ294-LOOKUP(2,1/(AI294:AI294<>""),AI294:AI294))) | IF(OR(F294="",AK294=""),"",IF(COUNT(AI294:AJ294)=0,"",AK294-LOOKUP(2,1/(AI294:AJ294<>""),AI294:AJ294))) | IF(OR(F294="",AL294=""),"",IF(COUNT(AI294:AK294)=0,"",AL294-LOOKUP(2,1/(AI294:AK294<>""),AI294:AK294))) | IF(OR(F294="",AM294=""),"",IF(COUNT(AI294:AL294)=0,"",AM294-LOOKUP(2,1/(AI294:AL294<>""),AI294:AL294))) | IF(OR(F294="",AN294=""),"",IF(COUNT(AI294:AM294)=0,"",AN294-LOOKUP(2,1/(AI294:AM294<>""),AI294:AM294))) | IF(OR(F294="",AO294=""),"",IF(COUNT(AI294:AN294)=0,"",AO294-LOOKUP(2,1/(AI294:AN294<>""),AI294:AN294))) | IF(OR(F294="",AP294=""),"",IF(COUNT(AI294:AO294)=0,"",AP294-LOOKUP(2,1/(AI294:AO294<>""),AI294:AO294))) | IF(OR(F294="",AQ294=""),"",IF(COUNT(AI294:AP294)=0,"",AQ294-LOOKUP(2,1/(AI294:AP294<>""),AI294:AP294))) | IF(OR(F294="",AR294=""),"",IF(COUNT(AI294:AQ294)=0,"",AR294-LOOKUP(2,1/(AI294:AQ294<>""),AI294:AQ294))) | IF(OR(F294="",AS294=""),"",IF(COUNT(AI294:AR294)=0,"",AS294-LOOKUP(2,1/(AI294:AR294<>""),AI294:AR294))) | IF(OR(F294="",AT294=""),"",IF(COUNT(AI294:AS294)=0,"",AT294-LOOKUP(2,1/(AI294:AS294<>""),AI294:AS294))) | IF(OR(F294="",AU294=""),"",IF(COUNT(AI294:AT294)=0,"",AU294-LOOKUP(2,1/(AI294:AT294<>""),AI294:AT294))) | IF(OR(F294="",AV294=""),"",IF(COUNT(AI294:AU294)=0,"",AV294-LOOKUP(2,1/(AI294:AU294<>""),AI294:AU294))) | IF(J294="","All_Provinces",IFERROR(VLOOKUP(J294,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K294="","All_Districts",IFERROR(VLOOKUP(K294,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F295="","",ROW()-3) | AF2-WSM-13 | Package #13-AF2 WSM: Construction of 4 Check Dams in 4 district sites of 1.Kata Khana in Yakawlang , 2. Nawora in Panjab, 3.Nahorak in Waras, and 4.Bayani in Sayghan districts of Bamyan province | 1 of 4 | AF2-WSM-A-030 | 1.Kata Khana Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Yakawalang | Kata Khana, Check dam | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Estehkam Baba Construction and Road Construction Company (EBCC) | 051/2026 | 66705.51 | IF(AQ295="","",AQ295) |  | 7 | 2027-02-21 | IF(W295<>"",W295,IF(OR(T295="",V295=""),"",EDATE(T295,V295))) |  | 35 | Under Construction | Completed on August 2026 | IF(F295="","",IF(COUNT(AI295:AV295)=0,IF(AA295="","Not started",AA295),SUBSTITUTE(LOOKUP(2,1/(AI295:AV295<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F295="",COUNT(AI295:AV295)=0),"",TODAY()-LOOKUP(2,1/(AI295:AV295<>""),AI295:AV295)) | IF(OR(F295="",COUNT(AI295:AV295)<2),"",LOOKUP(2,1/(AI295:AV295<>""),AI295:AV295)-MIN(AI295:AV295)) | IF(OR(AD295="",AC295="Not started",AC295=""),"",IFERROR(AD295-IF(VLOOKUP(AC295,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC295,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F295="","",IF(OR(AA295="Cancelled",AC295="Cancelled"),"Cancelled",IF(OR(AC295="Completed / Handover",Y295<>"",Z295>=100),"Completed — on track",IF(O295="Not awarded",IF(U295="",IF(X295="","No planned date",IF(TODAY()>X295,"Behind — past planned date",IF(X295-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U295,"Behind — award date passed",IF(U295-TODAY()<=30,"At risk — close to off track","On track"))),IF(X295="","No planned date",IF(AND(TODAY()>X295,OR(Z295="",Z295<100)),"Behind — past end date",IF(AND(T295<>"",X295<>"",Z295<>"",(Z295<100),((TODAY()-T295)/MAX(X295-T295,1)*100)-Z295>15),"Behind — progress lag",IF(AND(X295-TODAY()<=30,X295-TODAY()>=0,OR(Z295="",Z295<90)),"At risk — close to off track","On track")))))))) | IF(OR(F295="",AC295="Completed / Handover",AC295="Cancelled"),"",IF(O295="Not awarded",IF(U295<>"",U295-TODAY(),IF(X295="","",X295-TODAY())),IF(X295="","",X295-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F295="",AJ295=""),"",IF(COUNT(AI295:AI295)=0,"",AJ295-LOOKUP(2,1/(AI295:AI295<>""),AI295:AI295))) | IF(OR(F295="",AK295=""),"",IF(COUNT(AI295:AJ295)=0,"",AK295-LOOKUP(2,1/(AI295:AJ295<>""),AI295:AJ295))) | IF(OR(F295="",AL295=""),"",IF(COUNT(AI295:AK295)=0,"",AL295-LOOKUP(2,1/(AI295:AK295<>""),AI295:AK295))) | IF(OR(F295="",AM295=""),"",IF(COUNT(AI295:AL295)=0,"",AM295-LOOKUP(2,1/(AI295:AL295<>""),AI295:AL295))) | IF(OR(F295="",AN295=""),"",IF(COUNT(AI295:AM295)=0,"",AN295-LOOKUP(2,1/(AI295:AM295<>""),AI295:AM295))) | IF(OR(F295="",AO295=""),"",IF(COUNT(AI295:AN295)=0,"",AO295-LOOKUP(2,1/(AI295:AN295<>""),AI295:AN295))) | IF(OR(F295="",AP295=""),"",IF(COUNT(AI295:AO295)=0,"",AP295-LOOKUP(2,1/(AI295:AO295<>""),AI295:AO295))) | IF(OR(F295="",AQ295=""),"",IF(COUNT(AI295:AP295)=0,"",AQ295-LOOKUP(2,1/(AI295:AP295<>""),AI295:AP295))) | IF(OR(F295="",AR295=""),"",IF(COUNT(AI295:AQ295)=0,"",AR295-LOOKUP(2,1/(AI295:AQ295<>""),AI295:AQ295))) | IF(OR(F295="",AS295=""),"",IF(COUNT(AI295:AR295)=0,"",AS295-LOOKUP(2,1/(AI295:AR295<>""),AI295:AR295))) | IF(OR(F295="",AT295=""),"",IF(COUNT(AI295:AS295)=0,"",AT295-LOOKUP(2,1/(AI295:AS295<>""),AI295:AS295))) | IF(OR(F295="",AU295=""),"",IF(COUNT(AI295:AT295)=0,"",AU295-LOOKUP(2,1/(AI295:AT295<>""),AI295:AT295))) | IF(OR(F295="",AV295=""),"",IF(COUNT(AI295:AU295)=0,"",AV295-LOOKUP(2,1/(AI295:AU295<>""),AI295:AU295))) | IF(J295="","All_Provinces",IFERROR(VLOOKUP(J295,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K295="","All_Districts",IFERROR(VLOOKUP(K295,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F296="","",ROW()-3) | AF2-WSM-13 | Package #13-AF2 WSM: Construction of 4 Check Dams in 4 district sites of 1.Kata Khana in Yakawlang , 2. Nawora in Panjab, 3.Nahorak in Waras, and 4.Bayani in Sayghan districts of Bamyan province | 2 of 4 | AF2-WSM-A-031 | 2.Nawora Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Panjab | Nawora | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Estehkam Baba Construction and Road Construction Company (EBCC) | 051/2026 | 52796.76 | IF(AQ296="","",AQ296) |  | 7 | 2027-02-21 | IF(W296<>"",W296,IF(OR(T296="",V296=""),"",EDATE(T296,V296))) |  | 45 | Under Construction | Completed on August 2026 | IF(F296="","",IF(COUNT(AI296:AV296)=0,IF(AA296="","Not started",AA296),SUBSTITUTE(LOOKUP(2,1/(AI296:AV296<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F296="",COUNT(AI296:AV296)=0),"",TODAY()-LOOKUP(2,1/(AI296:AV296<>""),AI296:AV296)) | IF(OR(F296="",COUNT(AI296:AV296)<2),"",LOOKUP(2,1/(AI296:AV296<>""),AI296:AV296)-MIN(AI296:AV296)) | IF(OR(AD296="",AC296="Not started",AC296=""),"",IFERROR(AD296-IF(VLOOKUP(AC296,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC296,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F296="","",IF(OR(AA296="Cancelled",AC296="Cancelled"),"Cancelled",IF(OR(AC296="Completed / Handover",Y296<>"",Z296>=100),"Completed — on track",IF(O296="Not awarded",IF(U296="",IF(X296="","No planned date",IF(TODAY()>X296,"Behind — past planned date",IF(X296-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U296,"Behind — award date passed",IF(U296-TODAY()<=30,"At risk — close to off track","On track"))),IF(X296="","No planned date",IF(AND(TODAY()>X296,OR(Z296="",Z296<100)),"Behind — past end date",IF(AND(T296<>"",X296<>"",Z296<>"",(Z296<100),((TODAY()-T296)/MAX(X296-T296,1)*100)-Z296>15),"Behind — progress lag",IF(AND(X296-TODAY()<=30,X296-TODAY()>=0,OR(Z296="",Z296<90)),"At risk — close to off track","On track")))))))) | IF(OR(F296="",AC296="Completed / Handover",AC296="Cancelled"),"",IF(O296="Not awarded",IF(U296<>"",U296-TODAY(),IF(X296="","",X296-TODAY())),IF(X296="","",X296-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F296="",AJ296=""),"",IF(COUNT(AI296:AI296)=0,"",AJ296-LOOKUP(2,1/(AI296:AI296<>""),AI296:AI296))) | IF(OR(F296="",AK296=""),"",IF(COUNT(AI296:AJ296)=0,"",AK296-LOOKUP(2,1/(AI296:AJ296<>""),AI296:AJ296))) | IF(OR(F296="",AL296=""),"",IF(COUNT(AI296:AK296)=0,"",AL296-LOOKUP(2,1/(AI296:AK296<>""),AI296:AK296))) | IF(OR(F296="",AM296=""),"",IF(COUNT(AI296:AL296)=0,"",AM296-LOOKUP(2,1/(AI296:AL296<>""),AI296:AL296))) | IF(OR(F296="",AN296=""),"",IF(COUNT(AI296:AM296)=0,"",AN296-LOOKUP(2,1/(AI296:AM296<>""),AI296:AM296))) | IF(OR(F296="",AO296=""),"",IF(COUNT(AI296:AN296)=0,"",AO296-LOOKUP(2,1/(AI296:AN296<>""),AI296:AN296))) | IF(OR(F296="",AP296=""),"",IF(COUNT(AI296:AO296)=0,"",AP296-LOOKUP(2,1/(AI296:AO296<>""),AI296:AO296))) | IF(OR(F296="",AQ296=""),"",IF(COUNT(AI296:AP296)=0,"",AQ296-LOOKUP(2,1/(AI296:AP296<>""),AI296:AP296))) | IF(OR(F296="",AR296=""),"",IF(COUNT(AI296:AQ296)=0,"",AR296-LOOKUP(2,1/(AI296:AQ296<>""),AI296:AQ296))) | IF(OR(F296="",AS296=""),"",IF(COUNT(AI296:AR296)=0,"",AS296-LOOKUP(2,1/(AI296:AR296<>""),AI296:AR296))) | IF(OR(F296="",AT296=""),"",IF(COUNT(AI296:AS296)=0,"",AT296-LOOKUP(2,1/(AI296:AS296<>""),AI296:AS296))) | IF(OR(F296="",AU296=""),"",IF(COUNT(AI296:AT296)=0,"",AU296-LOOKUP(2,1/(AI296:AT296<>""),AI296:AT296))) | IF(OR(F296="",AV296=""),"",IF(COUNT(AI296:AU296)=0,"",AV296-LOOKUP(2,1/(AI296:AU296<>""),AI296:AU296))) | IF(J296="","All_Provinces",IFERROR(VLOOKUP(J296,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K296="","All_Districts",IFERROR(VLOOKUP(K296,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F297="","",ROW()-3) | AF2-WSM-13 | Package #13-AF2 WSM: Construction of 4 Check Dams in 4 district sites of 1.Kata Khana in Yakawlang , 2. Nawora in Panjab, 3.Nahorak in Waras, and 4.Bayani in Sayghan districts of Bamyan province | 3 of 4 | AF2-WSM-A-032 | 3.Nahorak Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Waras | Nahorak | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Estehkam Baba Construction and Road Construction Company (EBCC) | 051/2026 | 54600.65 | IF(AQ297="","",AQ297) |  | 7 | 2027-02-21 | IF(W297<>"",W297,IF(OR(T297="",V297=""),"",EDATE(T297,V297))) |  | 60 | Under Construction | Completed on August 2026 | IF(F297="","",IF(COUNT(AI297:AV297)=0,IF(AA297="","Not started",AA297),SUBSTITUTE(LOOKUP(2,1/(AI297:AV297<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F297="",COUNT(AI297:AV297)=0),"",TODAY()-LOOKUP(2,1/(AI297:AV297<>""),AI297:AV297)) | IF(OR(F297="",COUNT(AI297:AV297)<2),"",LOOKUP(2,1/(AI297:AV297<>""),AI297:AV297)-MIN(AI297:AV297)) | IF(OR(AD297="",AC297="Not started",AC297=""),"",IFERROR(AD297-IF(VLOOKUP(AC297,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC297,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F297="","",IF(OR(AA297="Cancelled",AC297="Cancelled"),"Cancelled",IF(OR(AC297="Completed / Handover",Y297<>"",Z297>=100),"Completed — on track",IF(O297="Not awarded",IF(U297="",IF(X297="","No planned date",IF(TODAY()>X297,"Behind — past planned date",IF(X297-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U297,"Behind — award date passed",IF(U297-TODAY()<=30,"At risk — close to off track","On track"))),IF(X297="","No planned date",IF(AND(TODAY()>X297,OR(Z297="",Z297<100)),"Behind — past end date",IF(AND(T297<>"",X297<>"",Z297<>"",(Z297<100),((TODAY()-T297)/MAX(X297-T297,1)*100)-Z297>15),"Behind — progress lag",IF(AND(X297-TODAY()<=30,X297-TODAY()>=0,OR(Z297="",Z297<90)),"At risk — close to off track","On track")))))))) | IF(OR(F297="",AC297="Completed / Handover",AC297="Cancelled"),"",IF(O297="Not awarded",IF(U297<>"",U297-TODAY(),IF(X297="","",X297-TODAY())),IF(X297="","",X297-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F297="",AJ297=""),"",IF(COUNT(AI297:AI297)=0,"",AJ297-LOOKUP(2,1/(AI297:AI297<>""),AI297:AI297))) | IF(OR(F297="",AK297=""),"",IF(COUNT(AI297:AJ297)=0,"",AK297-LOOKUP(2,1/(AI297:AJ297<>""),AI297:AJ297))) | IF(OR(F297="",AL297=""),"",IF(COUNT(AI297:AK297)=0,"",AL297-LOOKUP(2,1/(AI297:AK297<>""),AI297:AK297))) | IF(OR(F297="",AM297=""),"",IF(COUNT(AI297:AL297)=0,"",AM297-LOOKUP(2,1/(AI297:AL297<>""),AI297:AL297))) | IF(OR(F297="",AN297=""),"",IF(COUNT(AI297:AM297)=0,"",AN297-LOOKUP(2,1/(AI297:AM297<>""),AI297:AM297))) | IF(OR(F297="",AO297=""),"",IF(COUNT(AI297:AN297)=0,"",AO297-LOOKUP(2,1/(AI297:AN297<>""),AI297:AN297))) | IF(OR(F297="",AP297=""),"",IF(COUNT(AI297:AO297)=0,"",AP297-LOOKUP(2,1/(AI297:AO297<>""),AI297:AO297))) | IF(OR(F297="",AQ297=""),"",IF(COUNT(AI297:AP297)=0,"",AQ297-LOOKUP(2,1/(AI297:AP297<>""),AI297:AP297))) | IF(OR(F297="",AR297=""),"",IF(COUNT(AI297:AQ297)=0,"",AR297-LOOKUP(2,1/(AI297:AQ297<>""),AI297:AQ297))) | IF(OR(F297="",AS297=""),"",IF(COUNT(AI297:AR297)=0,"",AS297-LOOKUP(2,1/(AI297:AR297<>""),AI297:AR297))) | IF(OR(F297="",AT297=""),"",IF(COUNT(AI297:AS297)=0,"",AT297-LOOKUP(2,1/(AI297:AS297<>""),AI297:AS297))) | IF(OR(F297="",AU297=""),"",IF(COUNT(AI297:AT297)=0,"",AU297-LOOKUP(2,1/(AI297:AT297<>""),AI297:AT297))) | IF(OR(F297="",AV297=""),"",IF(COUNT(AI297:AU297)=0,"",AV297-LOOKUP(2,1/(AI297:AU297<>""),AI297:AU297))) | IF(J297="","All_Provinces",IFERROR(VLOOKUP(J297,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K297="","All_Districts",IFERROR(VLOOKUP(K297,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F298="","",ROW()-3) | AF2-WSM-13 | Package #13-AF2 WSM: Construction of 4 Check Dams in 4 district sites of 1.Kata Khana in Yakawlang , 2. Nawora in Panjab, 3.Nahorak in Waras, and 4.Bayani in Sayghan districts of Bamyan province | 4 of 4 | AF2-WSM-A-033 | 4.Bayani Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Bamyan | Sayghan | Bayani | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Estehkam Baba Construction and Road Construction Company (EBCC) | 051/2026 | 35843.07 | IF(AQ298="","",AQ298) |  | 7 | 2027-02-21 | IF(W298<>"",W298,IF(OR(T298="",V298=""),"",EDATE(T298,V298))) |  | 50 | Under Construction | Completed on August 2026 | IF(F298="","",IF(COUNT(AI298:AV298)=0,IF(AA298="","Not started",AA298),SUBSTITUTE(LOOKUP(2,1/(AI298:AV298<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F298="",COUNT(AI298:AV298)=0),"",TODAY()-LOOKUP(2,1/(AI298:AV298<>""),AI298:AV298)) | IF(OR(F298="",COUNT(AI298:AV298)<2),"",LOOKUP(2,1/(AI298:AV298<>""),AI298:AV298)-MIN(AI298:AV298)) | IF(OR(AD298="",AC298="Not started",AC298=""),"",IFERROR(AD298-IF(VLOOKUP(AC298,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC298,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F298="","",IF(OR(AA298="Cancelled",AC298="Cancelled"),"Cancelled",IF(OR(AC298="Completed / Handover",Y298<>"",Z298>=100),"Completed — on track",IF(O298="Not awarded",IF(U298="",IF(X298="","No planned date",IF(TODAY()>X298,"Behind — past planned date",IF(X298-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U298,"Behind — award date passed",IF(U298-TODAY()<=30,"At risk — close to off track","On track"))),IF(X298="","No planned date",IF(AND(TODAY()>X298,OR(Z298="",Z298<100)),"Behind — past end date",IF(AND(T298<>"",X298<>"",Z298<>"",(Z298<100),((TODAY()-T298)/MAX(X298-T298,1)*100)-Z298>15),"Behind — progress lag",IF(AND(X298-TODAY()<=30,X298-TODAY()>=0,OR(Z298="",Z298<90)),"At risk — close to off track","On track")))))))) | IF(OR(F298="",AC298="Completed / Handover",AC298="Cancelled"),"",IF(O298="Not awarded",IF(U298<>"",U298-TODAY(),IF(X298="","",X298-TODAY())),IF(X298="","",X298-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F298="",AJ298=""),"",IF(COUNT(AI298:AI298)=0,"",AJ298-LOOKUP(2,1/(AI298:AI298<>""),AI298:AI298))) | IF(OR(F298="",AK298=""),"",IF(COUNT(AI298:AJ298)=0,"",AK298-LOOKUP(2,1/(AI298:AJ298<>""),AI298:AJ298))) | IF(OR(F298="",AL298=""),"",IF(COUNT(AI298:AK298)=0,"",AL298-LOOKUP(2,1/(AI298:AK298<>""),AI298:AK298))) | IF(OR(F298="",AM298=""),"",IF(COUNT(AI298:AL298)=0,"",AM298-LOOKUP(2,1/(AI298:AL298<>""),AI298:AL298))) | IF(OR(F298="",AN298=""),"",IF(COUNT(AI298:AM298)=0,"",AN298-LOOKUP(2,1/(AI298:AM298<>""),AI298:AM298))) | IF(OR(F298="",AO298=""),"",IF(COUNT(AI298:AN298)=0,"",AO298-LOOKUP(2,1/(AI298:AN298<>""),AI298:AN298))) | IF(OR(F298="",AP298=""),"",IF(COUNT(AI298:AO298)=0,"",AP298-LOOKUP(2,1/(AI298:AO298<>""),AI298:AO298))) | IF(OR(F298="",AQ298=""),"",IF(COUNT(AI298:AP298)=0,"",AQ298-LOOKUP(2,1/(AI298:AP298<>""),AI298:AP298))) | IF(OR(F298="",AR298=""),"",IF(COUNT(AI298:AQ298)=0,"",AR298-LOOKUP(2,1/(AI298:AQ298<>""),AI298:AQ298))) | IF(OR(F298="",AS298=""),"",IF(COUNT(AI298:AR298)=0,"",AS298-LOOKUP(2,1/(AI298:AR298<>""),AI298:AR298))) | IF(OR(F298="",AT298=""),"",IF(COUNT(AI298:AS298)=0,"",AT298-LOOKUP(2,1/(AI298:AS298<>""),AI298:AS298))) | IF(OR(F298="",AU298=""),"",IF(COUNT(AI298:AT298)=0,"",AU298-LOOKUP(2,1/(AI298:AT298<>""),AI298:AT298))) | IF(OR(F298="",AV298=""),"",IF(COUNT(AI298:AU298)=0,"",AV298-LOOKUP(2,1/(AI298:AU298<>""),AI298:AU298))) | IF(J298="","All_Provinces",IFERROR(VLOOKUP(J298,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K298="","All_Districts",IFERROR(VLOOKUP(K298,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F299="","",ROW()-3) | AF2-WSM-14 | Package #14-AF2 WSM: Construction of 1.Shahristan Check dama in Shahristan district, 2.Miramor Check dam in Miramor district, and 3.Khidir Check dams in Khidir districts of Daykundi province. | 1 of 3 | AF2-WSM-A-034 | 1. Shahristan Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Shahristan | Dar Band, Dasht-e Safid, Madar, Lorange | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Da Maidan Zawahnono Construction Company (DMZCC) | 025/2026 | 52946.05 | IF(AQ299="","",AQ299) |  | 7 | 2026-10-30 | IF(W299<>"",W299,IF(OR(T299="",V299=""),"",EDATE(T299,V299))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F299="","",IF(COUNT(AI299:AV299)=0,IF(AA299="","Not started",AA299),SUBSTITUTE(LOOKUP(2,1/(AI299:AV299<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F299="",COUNT(AI299:AV299)=0),"",TODAY()-LOOKUP(2,1/(AI299:AV299<>""),AI299:AV299)) | IF(OR(F299="",COUNT(AI299:AV299)<2),"",LOOKUP(2,1/(AI299:AV299<>""),AI299:AV299)-MIN(AI299:AV299)) | IF(OR(AD299="",AC299="Not started",AC299=""),"",IFERROR(AD299-IF(VLOOKUP(AC299,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC299,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F299="","",IF(OR(AA299="Cancelled",AC299="Cancelled"),"Cancelled",IF(OR(AC299="Completed / Handover",Y299<>"",Z299>=100),"Completed — on track",IF(O299="Not awarded",IF(U299="",IF(X299="","No planned date",IF(TODAY()>X299,"Behind — past planned date",IF(X299-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U299,"Behind — award date passed",IF(U299-TODAY()<=30,"At risk — close to off track","On track"))),IF(X299="","No planned date",IF(AND(TODAY()>X299,OR(Z299="",Z299<100)),"Behind — past end date",IF(AND(T299<>"",X299<>"",Z299<>"",(Z299<100),((TODAY()-T299)/MAX(X299-T299,1)*100)-Z299>15),"Behind — progress lag",IF(AND(X299-TODAY()<=30,X299-TODAY()>=0,OR(Z299="",Z299<90)),"At risk — close to off track","On track")))))))) | IF(OR(F299="",AC299="Completed / Handover",AC299="Cancelled"),"",IF(O299="Not awarded",IF(U299<>"",U299-TODAY(),IF(X299="","",X299-TODAY())),IF(X299="","",X299-TODAY()))) | [8 empty] | 2026-04-01 | 2026-04-01 | 2026-10-30 |  |  |  | IF(OR(F299="",AJ299=""),"",IF(COUNT(AI299:AI299)=0,"",AJ299-LOOKUP(2,1/(AI299:AI299<>""),AI299:AI299))) | IF(OR(F299="",AK299=""),"",IF(COUNT(AI299:AJ299)=0,"",AK299-LOOKUP(2,1/(AI299:AJ299<>""),AI299:AJ299))) | IF(OR(F299="",AL299=""),"",IF(COUNT(AI299:AK299)=0,"",AL299-LOOKUP(2,1/(AI299:AK299<>""),AI299:AK299))) | IF(OR(F299="",AM299=""),"",IF(COUNT(AI299:AL299)=0,"",AM299-LOOKUP(2,1/(AI299:AL299<>""),AI299:AL299))) | IF(OR(F299="",AN299=""),"",IF(COUNT(AI299:AM299)=0,"",AN299-LOOKUP(2,1/(AI299:AM299<>""),AI299:AM299))) | IF(OR(F299="",AO299=""),"",IF(COUNT(AI299:AN299)=0,"",AO299-LOOKUP(2,1/(AI299:AN299<>""),AI299:AN299))) | IF(OR(F299="",AP299=""),"",IF(COUNT(AI299:AO299)=0,"",AP299-LOOKUP(2,1/(AI299:AO299<>""),AI299:AO299))) | IF(OR(F299="",AQ299=""),"",IF(COUNT(AI299:AP299)=0,"",AQ299-LOOKUP(2,1/(AI299:AP299<>""),AI299:AP299))) | IF(OR(F299="",AR299=""),"",IF(COUNT(AI299:AQ299)=0,"",AR299-LOOKUP(2,1/(AI299:AQ299<>""),AI299:AQ299))) | IF(OR(F299="",AS299=""),"",IF(COUNT(AI299:AR299)=0,"",AS299-LOOKUP(2,1/(AI299:AR299<>""),AI299:AR299))) | IF(OR(F299="",AT299=""),"",IF(COUNT(AI299:AS299)=0,"",AT299-LOOKUP(2,1/(AI299:AS299<>""),AI299:AS299))) | IF(OR(F299="",AU299=""),"",IF(COUNT(AI299:AT299)=0,"",AU299-LOOKUP(2,1/(AI299:AT299<>""),AI299:AT299))) | IF(OR(F299="",AV299=""),"",IF(COUNT(AI299:AU299)=0,"",AV299-LOOKUP(2,1/(AI299:AU299<>""),AI299:AU299))) | IF(J299="","All_Provinces",IFERROR(VLOOKUP(J299,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K299="","All_Districts",IFERROR(VLOOKUP(K299,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F300="","",ROW()-3) | AF2-WSM-14 | Package #14-AF2 WSM: Construction of 1.Shahristan Check dama in Shahristan district, 2.Miramor Check dam in Miramor district, and 3.Khidir Check dams in Khidir districts of Daykundi province. | 2 of 3 | AF2-WSM-A-035 | 2. Miramor Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Miramor | Folad, Deh Ghulam, | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Da Maidan Zawahnono Construction Company (DMZCC) | 025/2026 | 48360.86 | IF(AQ300="","",AQ300) |  | 7 | 2026-10-30 | IF(W300<>"",W300,IF(OR(T300="",V300=""),"",EDATE(T300,V300))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F300="","",IF(COUNT(AI300:AV300)=0,IF(AA300="","Not started",AA300),SUBSTITUTE(LOOKUP(2,1/(AI300:AV300<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F300="",COUNT(AI300:AV300)=0),"",TODAY()-LOOKUP(2,1/(AI300:AV300<>""),AI300:AV300)) | IF(OR(F300="",COUNT(AI300:AV300)<2),"",LOOKUP(2,1/(AI300:AV300<>""),AI300:AV300)-MIN(AI300:AV300)) | IF(OR(AD300="",AC300="Not started",AC300=""),"",IFERROR(AD300-IF(VLOOKUP(AC300,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC300,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F300="","",IF(OR(AA300="Cancelled",AC300="Cancelled"),"Cancelled",IF(OR(AC300="Completed / Handover",Y300<>"",Z300>=100),"Completed — on track",IF(O300="Not awarded",IF(U300="",IF(X300="","No planned date",IF(TODAY()>X300,"Behind — past planned date",IF(X300-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U300,"Behind — award date passed",IF(U300-TODAY()<=30,"At risk — close to off track","On track"))),IF(X300="","No planned date",IF(AND(TODAY()>X300,OR(Z300="",Z300<100)),"Behind — past end date",IF(AND(T300<>"",X300<>"",Z300<>"",(Z300<100),((TODAY()-T300)/MAX(X300-T300,1)*100)-Z300>15),"Behind — progress lag",IF(AND(X300-TODAY()<=30,X300-TODAY()>=0,OR(Z300="",Z300<90)),"At risk — close to off track","On track")))))))) | IF(OR(F300="",AC300="Completed / Handover",AC300="Cancelled"),"",IF(O300="Not awarded",IF(U300<>"",U300-TODAY(),IF(X300="","",X300-TODAY())),IF(X300="","",X300-TODAY()))) | [8 empty] | 2026-04-01 | 2026-04-01 | 2026-10-30 |  |  |  | IF(OR(F300="",AJ300=""),"",IF(COUNT(AI300:AI300)=0,"",AJ300-LOOKUP(2,1/(AI300:AI300<>""),AI300:AI300))) | IF(OR(F300="",AK300=""),"",IF(COUNT(AI300:AJ300)=0,"",AK300-LOOKUP(2,1/(AI300:AJ300<>""),AI300:AJ300))) | IF(OR(F300="",AL300=""),"",IF(COUNT(AI300:AK300)=0,"",AL300-LOOKUP(2,1/(AI300:AK300<>""),AI300:AK300))) | IF(OR(F300="",AM300=""),"",IF(COUNT(AI300:AL300)=0,"",AM300-LOOKUP(2,1/(AI300:AL300<>""),AI300:AL300))) | IF(OR(F300="",AN300=""),"",IF(COUNT(AI300:AM300)=0,"",AN300-LOOKUP(2,1/(AI300:AM300<>""),AI300:AM300))) | IF(OR(F300="",AO300=""),"",IF(COUNT(AI300:AN300)=0,"",AO300-LOOKUP(2,1/(AI300:AN300<>""),AI300:AN300))) | IF(OR(F300="",AP300=""),"",IF(COUNT(AI300:AO300)=0,"",AP300-LOOKUP(2,1/(AI300:AO300<>""),AI300:AO300))) | IF(OR(F300="",AQ300=""),"",IF(COUNT(AI300:AP300)=0,"",AQ300-LOOKUP(2,1/(AI300:AP300<>""),AI300:AP300))) | IF(OR(F300="",AR300=""),"",IF(COUNT(AI300:AQ300)=0,"",AR300-LOOKUP(2,1/(AI300:AQ300<>""),AI300:AQ300))) | IF(OR(F300="",AS300=""),"",IF(COUNT(AI300:AR300)=0,"",AS300-LOOKUP(2,1/(AI300:AR300<>""),AI300:AR300))) | IF(OR(F300="",AT300=""),"",IF(COUNT(AI300:AS300)=0,"",AT300-LOOKUP(2,1/(AI300:AS300<>""),AI300:AS300))) | IF(OR(F300="",AU300=""),"",IF(COUNT(AI300:AT300)=0,"",AU300-LOOKUP(2,1/(AI300:AT300<>""),AI300:AT300))) | IF(OR(F300="",AV300=""),"",IF(COUNT(AI300:AU300)=0,"",AV300-LOOKUP(2,1/(AI300:AU300<>""),AI300:AU300))) | IF(J300="","All_Provinces",IFERROR(VLOOKUP(J300,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K300="","All_Districts",IFERROR(VLOOKUP(K300,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F301="","",ROW()-3) | AF2-WSM-14 | Package #14-AF2 WSM: Construction of 1.Shahristan Check dama in Shahristan district, 2.Miramor Check dam in Miramor district, and 3.Khidir Check dams in Khidir districts of Daykundi province. | 3 of 3 | AF2-WSM-A-036 | 3. Khidir Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Khidir | Dahan-e Degshoyak, Dahan-e Mardakmoda | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Da Maidan Zawahnono Construction Company (DMZCC) | 025/2026 | 40132.5 | IF(AQ301="","",AQ301) |  | 7 | 2026-10-30 | IF(W301<>"",W301,IF(OR(T301="",V301=""),"",EDATE(T301,V301))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F301="","",IF(COUNT(AI301:AV301)=0,IF(AA301="","Not started",AA301),SUBSTITUTE(LOOKUP(2,1/(AI301:AV301<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F301="",COUNT(AI301:AV301)=0),"",TODAY()-LOOKUP(2,1/(AI301:AV301<>""),AI301:AV301)) | IF(OR(F301="",COUNT(AI301:AV301)<2),"",LOOKUP(2,1/(AI301:AV301<>""),AI301:AV301)-MIN(AI301:AV301)) | IF(OR(AD301="",AC301="Not started",AC301=""),"",IFERROR(AD301-IF(VLOOKUP(AC301,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC301,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F301="","",IF(OR(AA301="Cancelled",AC301="Cancelled"),"Cancelled",IF(OR(AC301="Completed / Handover",Y301<>"",Z301>=100),"Completed — on track",IF(O301="Not awarded",IF(U301="",IF(X301="","No planned date",IF(TODAY()>X301,"Behind — past planned date",IF(X301-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U301,"Behind — award date passed",IF(U301-TODAY()<=30,"At risk — close to off track","On track"))),IF(X301="","No planned date",IF(AND(TODAY()>X301,OR(Z301="",Z301<100)),"Behind — past end date",IF(AND(T301<>"",X301<>"",Z301<>"",(Z301<100),((TODAY()-T301)/MAX(X301-T301,1)*100)-Z301>15),"Behind — progress lag",IF(AND(X301-TODAY()<=30,X301-TODAY()>=0,OR(Z301="",Z301<90)),"At risk — close to off track","On track")))))))) | IF(OR(F301="",AC301="Completed / Handover",AC301="Cancelled"),"",IF(O301="Not awarded",IF(U301<>"",U301-TODAY(),IF(X301="","",X301-TODAY())),IF(X301="","",X301-TODAY()))) | [8 empty] | 2026-04-01 | 2026-04-01 | 2026-10-30 |  |  |  | IF(OR(F301="",AJ301=""),"",IF(COUNT(AI301:AI301)=0,"",AJ301-LOOKUP(2,1/(AI301:AI301<>""),AI301:AI301))) | IF(OR(F301="",AK301=""),"",IF(COUNT(AI301:AJ301)=0,"",AK301-LOOKUP(2,1/(AI301:AJ301<>""),AI301:AJ301))) | IF(OR(F301="",AL301=""),"",IF(COUNT(AI301:AK301)=0,"",AL301-LOOKUP(2,1/(AI301:AK301<>""),AI301:AK301))) | IF(OR(F301="",AM301=""),"",IF(COUNT(AI301:AL301)=0,"",AM301-LOOKUP(2,1/(AI301:AL301<>""),AI301:AL301))) | IF(OR(F301="",AN301=""),"",IF(COUNT(AI301:AM301)=0,"",AN301-LOOKUP(2,1/(AI301:AM301<>""),AI301:AM301))) | IF(OR(F301="",AO301=""),"",IF(COUNT(AI301:AN301)=0,"",AO301-LOOKUP(2,1/(AI301:AN301<>""),AI301:AN301))) | IF(OR(F301="",AP301=""),"",IF(COUNT(AI301:AO301)=0,"",AP301-LOOKUP(2,1/(AI301:AO301<>""),AI301:AO301))) | IF(OR(F301="",AQ301=""),"",IF(COUNT(AI301:AP301)=0,"",AQ301-LOOKUP(2,1/(AI301:AP301<>""),AI301:AP301))) | IF(OR(F301="",AR301=""),"",IF(COUNT(AI301:AQ301)=0,"",AR301-LOOKUP(2,1/(AI301:AQ301<>""),AI301:AQ301))) | IF(OR(F301="",AS301=""),"",IF(COUNT(AI301:AR301)=0,"",AS301-LOOKUP(2,1/(AI301:AR301<>""),AI301:AR301))) | IF(OR(F301="",AT301=""),"",IF(COUNT(AI301:AS301)=0,"",AT301-LOOKUP(2,1/(AI301:AS301<>""),AI301:AS301))) | IF(OR(F301="",AU301=""),"",IF(COUNT(AI301:AT301)=0,"",AU301-LOOKUP(2,1/(AI301:AT301<>""),AI301:AT301))) | IF(OR(F301="",AV301=""),"",IF(COUNT(AI301:AU301)=0,"",AV301-LOOKUP(2,1/(AI301:AU301<>""),AI301:AU301))) | IF(J301="","All_Provinces",IFERROR(VLOOKUP(J301,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K301="","All_Districts",IFERROR(VLOOKUP(K301,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F302="","",ROW()-3) | AF2-WSM-15 | Package #15-AF2 WSM: Construction of 3 Check dams of 1. Sangmom, 2. Shilan Korga, and 3.Khulbar in Nili, Ashtarlay, and Sang Takhta districts of Daykundi province. | 1 of 3 | AF2-WSM-A-037 | Khulbarg Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Sang Takht wa Bandar | Shamshir Sang, Dughur Ulya & Sufla | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Bahartamadun Construction Company (BCC) | 065/2026 |  | IF(AQ302="","",AQ302) |  | 4.9 | 2027-03-07 | IF(W302<>"",W302,IF(OR(T302="",V302=""),"",EDATE(T302,V302))) |  |  | Awarded | Completed on Sep, 2026 | IF(F302="","",IF(COUNT(AI302:AV302)=0,IF(AA302="","Not started",AA302),SUBSTITUTE(LOOKUP(2,1/(AI302:AV302<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F302="",COUNT(AI302:AV302)=0),"",TODAY()-LOOKUP(2,1/(AI302:AV302<>""),AI302:AV302)) | IF(OR(F302="",COUNT(AI302:AV302)<2),"",LOOKUP(2,1/(AI302:AV302<>""),AI302:AV302)-MIN(AI302:AV302)) | IF(OR(AD302="",AC302="Not started",AC302=""),"",IFERROR(AD302-IF(VLOOKUP(AC302,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC302,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F302="","",IF(OR(AA302="Cancelled",AC302="Cancelled"),"Cancelled",IF(OR(AC302="Completed / Handover",Y302<>"",Z302>=100),"Completed — on track",IF(O302="Not awarded",IF(U302="",IF(X302="","No planned date",IF(TODAY()>X302,"Behind — past planned date",IF(X302-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U302,"Behind — award date passed",IF(U302-TODAY()<=30,"At risk — close to off track","On track"))),IF(X302="","No planned date",IF(AND(TODAY()>X302,OR(Z302="",Z302<100)),"Behind — past end date",IF(AND(T302<>"",X302<>"",Z302<>"",(Z302<100),((TODAY()-T302)/MAX(X302-T302,1)*100)-Z302>15),"Behind — progress lag",IF(AND(X302-TODAY()<=30,X302-TODAY()>=0,OR(Z302="",Z302<90)),"At risk — close to off track","On track")))))))) | IF(OR(F302="",AC302="Completed / Handover",AC302="Cancelled"),"",IF(O302="Not awarded",IF(U302<>"",U302-TODAY(),IF(X302="","",X302-TODAY())),IF(X302="","",X302-TODAY()))) | [8 empty] | 2026-10-08 | [5 empty] | IF(OR(F302="",AJ302=""),"",IF(COUNT(AI302:AI302)=0,"",AJ302-LOOKUP(2,1/(AI302:AI302<>""),AI302:AI302))) | IF(OR(F302="",AK302=""),"",IF(COUNT(AI302:AJ302)=0,"",AK302-LOOKUP(2,1/(AI302:AJ302<>""),AI302:AJ302))) | IF(OR(F302="",AL302=""),"",IF(COUNT(AI302:AK302)=0,"",AL302-LOOKUP(2,1/(AI302:AK302<>""),AI302:AK302))) | IF(OR(F302="",AM302=""),"",IF(COUNT(AI302:AL302)=0,"",AM302-LOOKUP(2,1/(AI302:AL302<>""),AI302:AL302))) | IF(OR(F302="",AN302=""),"",IF(COUNT(AI302:AM302)=0,"",AN302-LOOKUP(2,1/(AI302:AM302<>""),AI302:AM302))) | IF(OR(F302="",AO302=""),"",IF(COUNT(AI302:AN302)=0,"",AO302-LOOKUP(2,1/(AI302:AN302<>""),AI302:AN302))) | IF(OR(F302="",AP302=""),"",IF(COUNT(AI302:AO302)=0,"",AP302-LOOKUP(2,1/(AI302:AO302<>""),AI302:AO302))) | IF(OR(F302="",AQ302=""),"",IF(COUNT(AI302:AP302)=0,"",AQ302-LOOKUP(2,1/(AI302:AP302<>""),AI302:AP302))) | IF(OR(F302="",AR302=""),"",IF(COUNT(AI302:AQ302)=0,"",AR302-LOOKUP(2,1/(AI302:AQ302<>""),AI302:AQ302))) | IF(OR(F302="",AS302=""),"",IF(COUNT(AI302:AR302)=0,"",AS302-LOOKUP(2,1/(AI302:AR302<>""),AI302:AR302))) | IF(OR(F302="",AT302=""),"",IF(COUNT(AI302:AS302)=0,"",AT302-LOOKUP(2,1/(AI302:AS302<>""),AI302:AS302))) | IF(OR(F302="",AU302=""),"",IF(COUNT(AI302:AT302)=0,"",AU302-LOOKUP(2,1/(AI302:AT302<>""),AI302:AT302))) | IF(OR(F302="",AV302=""),"",IF(COUNT(AI302:AU302)=0,"",AV302-LOOKUP(2,1/(AI302:AU302<>""),AI302:AU302))) | IF(J302="","All_Provinces",IFERROR(VLOOKUP(J302,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K302="","All_Districts",IFERROR(VLOOKUP(K302,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F303="","",ROW()-3) | AF2-WSM-15 | Package #15-AF2 WSM: Construction of 3 Check dams of 1. Sangmom, 2. Shilan Korga, and 3.Khulbar in Nili, Ashtarlay, and Sang Takhta districts of Daykundi province. | 2 of 3 | AF2-WSM-A-038 | Sangmom Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Nili | Sangmom | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Bahartamadun Construction Company (BCC) | 065/2026 | 179455 | IF(AQ303="","",AQ303) |  | 4.9 | 2027-03-07 | IF(W303<>"",W303,IF(OR(T303="",V303=""),"",EDATE(T303,V303))) |  |  | Awarded | Completed on Sep, 2026 | IF(F303="","",IF(COUNT(AI303:AV303)=0,IF(AA303="","Not started",AA303),SUBSTITUTE(LOOKUP(2,1/(AI303:AV303<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F303="",COUNT(AI303:AV303)=0),"",TODAY()-LOOKUP(2,1/(AI303:AV303<>""),AI303:AV303)) | IF(OR(F303="",COUNT(AI303:AV303)<2),"",LOOKUP(2,1/(AI303:AV303<>""),AI303:AV303)-MIN(AI303:AV303)) | IF(OR(AD303="",AC303="Not started",AC303=""),"",IFERROR(AD303-IF(VLOOKUP(AC303,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC303,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F303="","",IF(OR(AA303="Cancelled",AC303="Cancelled"),"Cancelled",IF(OR(AC303="Completed / Handover",Y303<>"",Z303>=100),"Completed — on track",IF(O303="Not awarded",IF(U303="",IF(X303="","No planned date",IF(TODAY()>X303,"Behind — past planned date",IF(X303-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U303,"Behind — award date passed",IF(U303-TODAY()<=30,"At risk — close to off track","On track"))),IF(X303="","No planned date",IF(AND(TODAY()>X303,OR(Z303="",Z303<100)),"Behind — past end date",IF(AND(T303<>"",X303<>"",Z303<>"",(Z303<100),((TODAY()-T303)/MAX(X303-T303,1)*100)-Z303>15),"Behind — progress lag",IF(AND(X303-TODAY()<=30,X303-TODAY()>=0,OR(Z303="",Z303<90)),"At risk — close to off track","On track")))))))) | IF(OR(F303="",AC303="Completed / Handover",AC303="Cancelled"),"",IF(O303="Not awarded",IF(U303<>"",U303-TODAY(),IF(X303="","",X303-TODAY())),IF(X303="","",X303-TODAY()))) | [8 empty] | 2026-10-08 | [5 empty] | IF(OR(F303="",AJ303=""),"",IF(COUNT(AI303:AI303)=0,"",AJ303-LOOKUP(2,1/(AI303:AI303<>""),AI303:AI303))) | IF(OR(F303="",AK303=""),"",IF(COUNT(AI303:AJ303)=0,"",AK303-LOOKUP(2,1/(AI303:AJ303<>""),AI303:AJ303))) | IF(OR(F303="",AL303=""),"",IF(COUNT(AI303:AK303)=0,"",AL303-LOOKUP(2,1/(AI303:AK303<>""),AI303:AK303))) | IF(OR(F303="",AM303=""),"",IF(COUNT(AI303:AL303)=0,"",AM303-LOOKUP(2,1/(AI303:AL303<>""),AI303:AL303))) | IF(OR(F303="",AN303=""),"",IF(COUNT(AI303:AM303)=0,"",AN303-LOOKUP(2,1/(AI303:AM303<>""),AI303:AM303))) | IF(OR(F303="",AO303=""),"",IF(COUNT(AI303:AN303)=0,"",AO303-LOOKUP(2,1/(AI303:AN303<>""),AI303:AN303))) | IF(OR(F303="",AP303=""),"",IF(COUNT(AI303:AO303)=0,"",AP303-LOOKUP(2,1/(AI303:AO303<>""),AI303:AO303))) | IF(OR(F303="",AQ303=""),"",IF(COUNT(AI303:AP303)=0,"",AQ303-LOOKUP(2,1/(AI303:AP303<>""),AI303:AP303))) | IF(OR(F303="",AR303=""),"",IF(COUNT(AI303:AQ303)=0,"",AR303-LOOKUP(2,1/(AI303:AQ303<>""),AI303:AQ303))) | IF(OR(F303="",AS303=""),"",IF(COUNT(AI303:AR303)=0,"",AS303-LOOKUP(2,1/(AI303:AR303<>""),AI303:AR303))) | IF(OR(F303="",AT303=""),"",IF(COUNT(AI303:AS303)=0,"",AT303-LOOKUP(2,1/(AI303:AS303<>""),AI303:AS303))) | IF(OR(F303="",AU303=""),"",IF(COUNT(AI303:AT303)=0,"",AU303-LOOKUP(2,1/(AI303:AT303<>""),AI303:AT303))) | IF(OR(F303="",AV303=""),"",IF(COUNT(AI303:AU303)=0,"",AV303-LOOKUP(2,1/(AI303:AU303<>""),AI303:AU303))) | IF(J303="","All_Provinces",IFERROR(VLOOKUP(J303,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K303="","All_Districts",IFERROR(VLOOKUP(K303,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F304="","",ROW()-3) | AF2-WSM-15 | Package #15-AF2 WSM: Construction of 3 Check dams of 1. Sangmom, 2. Shilan Korga, and 3.Khulbar in Nili, Ashtarlay, and Sang Takhta districts of Daykundi province. | 3 of 3 | AF2-WSM-A-039 | Shilan Korga Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Central Highland / Bamyan | Daykundi | Ashtarlay | Korga-e Shelan, Naiak-e Shelan | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Bahartamadun Construction Company (BCC) | 065/2026 |  | IF(AQ304="","",AQ304) |  | 4.9 | 2027-03-07 | IF(W304<>"",W304,IF(OR(T304="",V304=""),"",EDATE(T304,V304))) |  |  | Awarded | Completed on Sep, 2026 | IF(F304="","",IF(COUNT(AI304:AV304)=0,IF(AA304="","Not started",AA304),SUBSTITUTE(LOOKUP(2,1/(AI304:AV304<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F304="",COUNT(AI304:AV304)=0),"",TODAY()-LOOKUP(2,1/(AI304:AV304<>""),AI304:AV304)) | IF(OR(F304="",COUNT(AI304:AV304)<2),"",LOOKUP(2,1/(AI304:AV304<>""),AI304:AV304)-MIN(AI304:AV304)) | IF(OR(AD304="",AC304="Not started",AC304=""),"",IFERROR(AD304-IF(VLOOKUP(AC304,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC304,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F304="","",IF(OR(AA304="Cancelled",AC304="Cancelled"),"Cancelled",IF(OR(AC304="Completed / Handover",Y304<>"",Z304>=100),"Completed — on track",IF(O304="Not awarded",IF(U304="",IF(X304="","No planned date",IF(TODAY()>X304,"Behind — past planned date",IF(X304-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U304,"Behind — award date passed",IF(U304-TODAY()<=30,"At risk — close to off track","On track"))),IF(X304="","No planned date",IF(AND(TODAY()>X304,OR(Z304="",Z304<100)),"Behind — past end date",IF(AND(T304<>"",X304<>"",Z304<>"",(Z304<100),((TODAY()-T304)/MAX(X304-T304,1)*100)-Z304>15),"Behind — progress lag",IF(AND(X304-TODAY()<=30,X304-TODAY()>=0,OR(Z304="",Z304<90)),"At risk — close to off track","On track")))))))) | IF(OR(F304="",AC304="Completed / Handover",AC304="Cancelled"),"",IF(O304="Not awarded",IF(U304<>"",U304-TODAY(),IF(X304="","",X304-TODAY())),IF(X304="","",X304-TODAY()))) | [8 empty] | 2026-10-08 | [5 empty] | IF(OR(F304="",AJ304=""),"",IF(COUNT(AI304:AI304)=0,"",AJ304-LOOKUP(2,1/(AI304:AI304<>""),AI304:AI304))) | IF(OR(F304="",AK304=""),"",IF(COUNT(AI304:AJ304)=0,"",AK304-LOOKUP(2,1/(AI304:AJ304<>""),AI304:AJ304))) | IF(OR(F304="",AL304=""),"",IF(COUNT(AI304:AK304)=0,"",AL304-LOOKUP(2,1/(AI304:AK304<>""),AI304:AK304))) | IF(OR(F304="",AM304=""),"",IF(COUNT(AI304:AL304)=0,"",AM304-LOOKUP(2,1/(AI304:AL304<>""),AI304:AL304))) | IF(OR(F304="",AN304=""),"",IF(COUNT(AI304:AM304)=0,"",AN304-LOOKUP(2,1/(AI304:AM304<>""),AI304:AM304))) | IF(OR(F304="",AO304=""),"",IF(COUNT(AI304:AN304)=0,"",AO304-LOOKUP(2,1/(AI304:AN304<>""),AI304:AN304))) | IF(OR(F304="",AP304=""),"",IF(COUNT(AI304:AO304)=0,"",AP304-LOOKUP(2,1/(AI304:AO304<>""),AI304:AO304))) | IF(OR(F304="",AQ304=""),"",IF(COUNT(AI304:AP304)=0,"",AQ304-LOOKUP(2,1/(AI304:AP304<>""),AI304:AP304))) | IF(OR(F304="",AR304=""),"",IF(COUNT(AI304:AQ304)=0,"",AR304-LOOKUP(2,1/(AI304:AQ304<>""),AI304:AQ304))) | IF(OR(F304="",AS304=""),"",IF(COUNT(AI304:AR304)=0,"",AS304-LOOKUP(2,1/(AI304:AR304<>""),AI304:AR304))) | IF(OR(F304="",AT304=""),"",IF(COUNT(AI304:AS304)=0,"",AT304-LOOKUP(2,1/(AI304:AS304<>""),AI304:AS304))) | IF(OR(F304="",AU304=""),"",IF(COUNT(AI304:AT304)=0,"",AU304-LOOKUP(2,1/(AI304:AT304<>""),AI304:AT304))) | IF(OR(F304="",AV304=""),"",IF(COUNT(AI304:AU304)=0,"",AV304-LOOKUP(2,1/(AI304:AU304<>""),AI304:AU304))) | IF(J304="","All_Provinces",IFERROR(VLOOKUP(J304,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K304="","All_Districts",IFERROR(VLOOKUP(K304,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F305="","",ROW()-3) | AF2-WSM-16 | Package #16-AF2 WSM: Construction of Panami Check dams, located in Mohammad Agha district of Logar province. | 1 of 1 | AF2-WSM-A-040 | Panami Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Logar | M.Agha | Ab Bazak (Panami) | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Sayed Shirazi Construction and Road Building Company (SCRC) | 030/2026 | 109583.21 | IF(AQ305="","",AQ305) |  | 7 | 2026-11-17 | IF(W305<>"",W305,IF(OR(T305="",V305=""),"",EDATE(T305,V305))) |  | 64 | Under Construction | Completed on Sep, 2026 | IF(F305="","",IF(COUNT(AI305:AV305)=0,IF(AA305="","Not started",AA305),SUBSTITUTE(LOOKUP(2,1/(AI305:AV305<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F305="",COUNT(AI305:AV305)=0),"",TODAY()-LOOKUP(2,1/(AI305:AV305<>""),AI305:AV305)) | IF(OR(F305="",COUNT(AI305:AV305)<2),"",LOOKUP(2,1/(AI305:AV305<>""),AI305:AV305)-MIN(AI305:AV305)) | IF(OR(AD305="",AC305="Not started",AC305=""),"",IFERROR(AD305-IF(VLOOKUP(AC305,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC305,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F305="","",IF(OR(AA305="Cancelled",AC305="Cancelled"),"Cancelled",IF(OR(AC305="Completed / Handover",Y305<>"",Z305>=100),"Completed — on track",IF(O305="Not awarded",IF(U305="",IF(X305="","No planned date",IF(TODAY()>X305,"Behind — past planned date",IF(X305-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U305,"Behind — award date passed",IF(U305-TODAY()<=30,"At risk — close to off track","On track"))),IF(X305="","No planned date",IF(AND(TODAY()>X305,OR(Z305="",Z305<100)),"Behind — past end date",IF(AND(T305<>"",X305<>"",Z305<>"",(Z305<100),((TODAY()-T305)/MAX(X305-T305,1)*100)-Z305>15),"Behind — progress lag",IF(AND(X305-TODAY()<=30,X305-TODAY()>=0,OR(Z305="",Z305<90)),"At risk — close to off track","On track")))))))) | IF(OR(F305="",AC305="Completed / Handover",AC305="Cancelled"),"",IF(O305="Not awarded",IF(U305<>"",U305-TODAY(),IF(X305="","",X305-TODAY())),IF(X305="","",X305-TODAY()))) | [8 empty] | 2026-04-18 | 2026-04-18 |  |  |  |  | IF(OR(F305="",AJ305=""),"",IF(COUNT(AI305:AI305)=0,"",AJ305-LOOKUP(2,1/(AI305:AI305<>""),AI305:AI305))) | IF(OR(F305="",AK305=""),"",IF(COUNT(AI305:AJ305)=0,"",AK305-LOOKUP(2,1/(AI305:AJ305<>""),AI305:AJ305))) | IF(OR(F305="",AL305=""),"",IF(COUNT(AI305:AK305)=0,"",AL305-LOOKUP(2,1/(AI305:AK305<>""),AI305:AK305))) | IF(OR(F305="",AM305=""),"",IF(COUNT(AI305:AL305)=0,"",AM305-LOOKUP(2,1/(AI305:AL305<>""),AI305:AL305))) | IF(OR(F305="",AN305=""),"",IF(COUNT(AI305:AM305)=0,"",AN305-LOOKUP(2,1/(AI305:AM305<>""),AI305:AM305))) | IF(OR(F305="",AO305=""),"",IF(COUNT(AI305:AN305)=0,"",AO305-LOOKUP(2,1/(AI305:AN305<>""),AI305:AN305))) | IF(OR(F305="",AP305=""),"",IF(COUNT(AI305:AO305)=0,"",AP305-LOOKUP(2,1/(AI305:AO305<>""),AI305:AO305))) | IF(OR(F305="",AQ305=""),"",IF(COUNT(AI305:AP305)=0,"",AQ305-LOOKUP(2,1/(AI305:AP305<>""),AI305:AP305))) | IF(OR(F305="",AR305=""),"",IF(COUNT(AI305:AQ305)=0,"",AR305-LOOKUP(2,1/(AI305:AQ305<>""),AI305:AQ305))) | IF(OR(F305="",AS305=""),"",IF(COUNT(AI305:AR305)=0,"",AS305-LOOKUP(2,1/(AI305:AR305<>""),AI305:AR305))) | IF(OR(F305="",AT305=""),"",IF(COUNT(AI305:AS305)=0,"",AT305-LOOKUP(2,1/(AI305:AS305<>""),AI305:AS305))) | IF(OR(F305="",AU305=""),"",IF(COUNT(AI305:AT305)=0,"",AU305-LOOKUP(2,1/(AI305:AT305<>""),AI305:AT305))) | IF(OR(F305="",AV305=""),"",IF(COUNT(AI305:AU305)=0,"",AV305-LOOKUP(2,1/(AI305:AU305<>""),AI305:AU305))) | IF(J305="","All_Provinces",IFERROR(VLOOKUP(J305,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K305="","All_Districts",IFERROR(VLOOKUP(K305,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F306="","",ROW()-3) | AF2-WSM-17 | Package #17-AF2 WSM: Construction of Ghoriza Check dams, located in Sayed Karam districts of Paktya province. | 1 of 1 | AF2-WSM-N-005 | Ghawreza Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktya | Sayed Karam | Bara Ghoriza | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 86330 | IF(AQ306="","",AQ306) | 2026-11-20 | 7.2 | 2027-06-28 | IF(W306<>"",W306,IF(OR(T306="",V306=""),"",EDATE(T306,V306))) |  |  | PR to be Raised | Construction of the check dam will be completed in four months. 20-Dec to March end as the slack period. | IF(F306="","",IF(COUNT(AI306:AV306)=0,IF(AA306="","Not started",AA306),SUBSTITUTE(LOOKUP(2,1/(AI306:AV306<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F306="",COUNT(AI306:AV306)=0),"",TODAY()-LOOKUP(2,1/(AI306:AV306<>""),AI306:AV306)) | IF(OR(F306="",COUNT(AI306:AV306)<2),"",LOOKUP(2,1/(AI306:AV306<>""),AI306:AV306)-MIN(AI306:AV306)) | IF(OR(AD306="",AC306="Not started",AC306=""),"",IFERROR(AD306-IF(VLOOKUP(AC306,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC306,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F306="","",IF(OR(AA306="Cancelled",AC306="Cancelled"),"Cancelled",IF(OR(AC306="Completed / Handover",Y306<>"",Z306>=100),"Completed — on track",IF(O306="Not awarded",IF(U306="",IF(X306="","No planned date",IF(TODAY()>X306,"Behind — past planned date",IF(X306-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U306,"Behind — award date passed",IF(U306-TODAY()<=30,"At risk — close to off track","On track"))),IF(X306="","No planned date",IF(AND(TODAY()>X306,OR(Z306="",Z306<100)),"Behind — past end date",IF(AND(T306<>"",X306<>"",Z306<>"",(Z306<100),((TODAY()-T306)/MAX(X306-T306,1)*100)-Z306>15),"Behind — progress lag",IF(AND(X306-TODAY()<=30,X306-TODAY()>=0,OR(Z306="",Z306<90)),"At risk — close to off track","On track")))))))) | IF(OR(F306="",AC306="Completed / Handover",AC306="Cancelled"),"",IF(O306="Not awarded",IF(U306<>"",U306-TODAY(),IF(X306="","",X306-TODAY())),IF(X306="","",X306-TODAY()))) | [14 empty] | IF(OR(F306="",AJ306=""),"",IF(COUNT(AI306:AI306)=0,"",AJ306-LOOKUP(2,1/(AI306:AI306<>""),AI306:AI306))) | IF(OR(F306="",AK306=""),"",IF(COUNT(AI306:AJ306)=0,"",AK306-LOOKUP(2,1/(AI306:AJ306<>""),AI306:AJ306))) | IF(OR(F306="",AL306=""),"",IF(COUNT(AI306:AK306)=0,"",AL306-LOOKUP(2,1/(AI306:AK306<>""),AI306:AK306))) | IF(OR(F306="",AM306=""),"",IF(COUNT(AI306:AL306)=0,"",AM306-LOOKUP(2,1/(AI306:AL306<>""),AI306:AL306))) | IF(OR(F306="",AN306=""),"",IF(COUNT(AI306:AM306)=0,"",AN306-LOOKUP(2,1/(AI306:AM306<>""),AI306:AM306))) | IF(OR(F306="",AO306=""),"",IF(COUNT(AI306:AN306)=0,"",AO306-LOOKUP(2,1/(AI306:AN306<>""),AI306:AN306))) | IF(OR(F306="",AP306=""),"",IF(COUNT(AI306:AO306)=0,"",AP306-LOOKUP(2,1/(AI306:AO306<>""),AI306:AO306))) | IF(OR(F306="",AQ306=""),"",IF(COUNT(AI306:AP306)=0,"",AQ306-LOOKUP(2,1/(AI306:AP306<>""),AI306:AP306))) | IF(OR(F306="",AR306=""),"",IF(COUNT(AI306:AQ306)=0,"",AR306-LOOKUP(2,1/(AI306:AQ306<>""),AI306:AQ306))) | IF(OR(F306="",AS306=""),"",IF(COUNT(AI306:AR306)=0,"",AS306-LOOKUP(2,1/(AI306:AR306<>""),AI306:AR306))) | IF(OR(F306="",AT306=""),"",IF(COUNT(AI306:AS306)=0,"",AT306-LOOKUP(2,1/(AI306:AS306<>""),AI306:AS306))) | IF(OR(F306="",AU306=""),"",IF(COUNT(AI306:AT306)=0,"",AU306-LOOKUP(2,1/(AI306:AT306<>""),AI306:AT306))) | IF(OR(F306="",AV306=""),"",IF(COUNT(AI306:AU306)=0,"",AV306-LOOKUP(2,1/(AI306:AU306<>""),AI306:AU306))) | IF(J306="","All_Provinces",IFERROR(VLOOKUP(J306,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K306="","All_Districts",IFERROR(VLOOKUP(K306,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F307="","",ROW()-3) | AF2-WSM-18 | Package #18-AF2 WSM: Construction of Muqarab Check dams, located in Gelan districts of Ghazni province. | 1 of 1 | AF2-WSM-A-041 | Muqarab Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Ghazni | Gelan | Muqarab | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Hemat safi construction company (HSCC) | 047/2026 | 79567.97 | IF(AQ307="","",AQ307) |  | 6 | 2027-01-22 | IF(W307<>"",W307,IF(OR(T307="",V307=""),"",EDATE(T307,V307))) |  | 36 | Under Construction | Completed on Sep, 2026 | IF(F307="","",IF(COUNT(AI307:AV307)=0,IF(AA307="","Not started",AA307),SUBSTITUTE(LOOKUP(2,1/(AI307:AV307<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F307="",COUNT(AI307:AV307)=0),"",TODAY()-LOOKUP(2,1/(AI307:AV307<>""),AI307:AV307)) | IF(OR(F307="",COUNT(AI307:AV307)<2),"",LOOKUP(2,1/(AI307:AV307<>""),AI307:AV307)-MIN(AI307:AV307)) | IF(OR(AD307="",AC307="Not started",AC307=""),"",IFERROR(AD307-IF(VLOOKUP(AC307,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC307,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F307="","",IF(OR(AA307="Cancelled",AC307="Cancelled"),"Cancelled",IF(OR(AC307="Completed / Handover",Y307<>"",Z307>=100),"Completed — on track",IF(O307="Not awarded",IF(U307="",IF(X307="","No planned date",IF(TODAY()>X307,"Behind — past planned date",IF(X307-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U307,"Behind — award date passed",IF(U307-TODAY()<=30,"At risk — close to off track","On track"))),IF(X307="","No planned date",IF(AND(TODAY()>X307,OR(Z307="",Z307<100)),"Behind — past end date",IF(AND(T307<>"",X307<>"",Z307<>"",(Z307<100),((TODAY()-T307)/MAX(X307-T307,1)*100)-Z307>15),"Behind — progress lag",IF(AND(X307-TODAY()<=30,X307-TODAY()>=0,OR(Z307="",Z307<90)),"At risk — close to off track","On track")))))))) | IF(OR(F307="",AC307="Completed / Handover",AC307="Cancelled"),"",IF(O307="Not awarded",IF(U307<>"",U307-TODAY(),IF(X307="","",X307-TODAY())),IF(X307="","",X307-TODAY()))) | [8 empty] | 2026-07-23 | 2026-07-23 |  |  |  |  | IF(OR(F307="",AJ307=""),"",IF(COUNT(AI307:AI307)=0,"",AJ307-LOOKUP(2,1/(AI307:AI307<>""),AI307:AI307))) | IF(OR(F307="",AK307=""),"",IF(COUNT(AI307:AJ307)=0,"",AK307-LOOKUP(2,1/(AI307:AJ307<>""),AI307:AJ307))) | IF(OR(F307="",AL307=""),"",IF(COUNT(AI307:AK307)=0,"",AL307-LOOKUP(2,1/(AI307:AK307<>""),AI307:AK307))) | IF(OR(F307="",AM307=""),"",IF(COUNT(AI307:AL307)=0,"",AM307-LOOKUP(2,1/(AI307:AL307<>""),AI307:AL307))) | IF(OR(F307="",AN307=""),"",IF(COUNT(AI307:AM307)=0,"",AN307-LOOKUP(2,1/(AI307:AM307<>""),AI307:AM307))) | IF(OR(F307="",AO307=""),"",IF(COUNT(AI307:AN307)=0,"",AO307-LOOKUP(2,1/(AI307:AN307<>""),AI307:AN307))) | IF(OR(F307="",AP307=""),"",IF(COUNT(AI307:AO307)=0,"",AP307-LOOKUP(2,1/(AI307:AO307<>""),AI307:AO307))) | IF(OR(F307="",AQ307=""),"",IF(COUNT(AI307:AP307)=0,"",AQ307-LOOKUP(2,1/(AI307:AP307<>""),AI307:AP307))) | IF(OR(F307="",AR307=""),"",IF(COUNT(AI307:AQ307)=0,"",AR307-LOOKUP(2,1/(AI307:AQ307<>""),AI307:AQ307))) | IF(OR(F307="",AS307=""),"",IF(COUNT(AI307:AR307)=0,"",AS307-LOOKUP(2,1/(AI307:AR307<>""),AI307:AR307))) | IF(OR(F307="",AT307=""),"",IF(COUNT(AI307:AS307)=0,"",AT307-LOOKUP(2,1/(AI307:AS307<>""),AI307:AS307))) | IF(OR(F307="",AU307=""),"",IF(COUNT(AI307:AT307)=0,"",AU307-LOOKUP(2,1/(AI307:AT307<>""),AI307:AT307))) | IF(OR(F307="",AV307=""),"",IF(COUNT(AI307:AU307)=0,"",AV307-LOOKUP(2,1/(AI307:AU307<>""),AI307:AU307))) | IF(J307="","All_Provinces",IFERROR(VLOOKUP(J307,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K307="","All_Districts",IFERROR(VLOOKUP(K307,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F308="","",ROW()-3) | AF2-WSM-19 | Package #19-AF2 WSM: Construction of two Check dams 1. Wazgarai and 2. Chenargai in Zazai Maidan districts of Khost province. | 1 of 1 | AF2-WSM-N-006 | Wozgarai and Chenargai Check dams | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Khost | Zazai Maidan | 3.Wozgarai, Majbor Abad and Chenargai | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 85715.76 | IF(AQ308="","",AQ308) | 2026-11-30 | 6.9 | 2027-06-28 | IF(W308<>"",W308,IF(OR(T308="",V308=""),"",EDATE(T308,V308))) |  |  | ITB Launched | Construction of the check dam will be completed in four months. Jan to March end as the slack period. | IF(F308="","",IF(COUNT(AI308:AV308)=0,IF(AA308="","Not started",AA308),SUBSTITUTE(LOOKUP(2,1/(AI308:AV308<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F308="",COUNT(AI308:AV308)=0),"",TODAY()-LOOKUP(2,1/(AI308:AV308<>""),AI308:AV308)) | IF(OR(F308="",COUNT(AI308:AV308)<2),"",LOOKUP(2,1/(AI308:AV308<>""),AI308:AV308)-MIN(AI308:AV308)) | IF(OR(AD308="",AC308="Not started",AC308=""),"",IFERROR(AD308-IF(VLOOKUP(AC308,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC308,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F308="","",IF(OR(AA308="Cancelled",AC308="Cancelled"),"Cancelled",IF(OR(AC308="Completed / Handover",Y308<>"",Z308>=100),"Completed — on track",IF(O308="Not awarded",IF(U308="",IF(X308="","No planned date",IF(TODAY()>X308,"Behind — past planned date",IF(X308-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U308,"Behind — award date passed",IF(U308-TODAY()<=30,"At risk — close to off track","On track"))),IF(X308="","No planned date",IF(AND(TODAY()>X308,OR(Z308="",Z308<100)),"Behind — past end date",IF(AND(T308<>"",X308<>"",Z308<>"",(Z308<100),((TODAY()-T308)/MAX(X308-T308,1)*100)-Z308>15),"Behind — progress lag",IF(AND(X308-TODAY()<=30,X308-TODAY()>=0,OR(Z308="",Z308<90)),"At risk — close to off track","On track")))))))) | IF(OR(F308="",AC308="Completed / Handover",AC308="Cancelled"),"",IF(O308="Not awarded",IF(U308<>"",U308-TODAY(),IF(X308="","",X308-TODAY())),IF(X308="","",X308-TODAY()))) | [14 empty] | IF(OR(F308="",AJ308=""),"",IF(COUNT(AI308:AI308)=0,"",AJ308-LOOKUP(2,1/(AI308:AI308<>""),AI308:AI308))) | IF(OR(F308="",AK308=""),"",IF(COUNT(AI308:AJ308)=0,"",AK308-LOOKUP(2,1/(AI308:AJ308<>""),AI308:AJ308))) | IF(OR(F308="",AL308=""),"",IF(COUNT(AI308:AK308)=0,"",AL308-LOOKUP(2,1/(AI308:AK308<>""),AI308:AK308))) | IF(OR(F308="",AM308=""),"",IF(COUNT(AI308:AL308)=0,"",AM308-LOOKUP(2,1/(AI308:AL308<>""),AI308:AL308))) | IF(OR(F308="",AN308=""),"",IF(COUNT(AI308:AM308)=0,"",AN308-LOOKUP(2,1/(AI308:AM308<>""),AI308:AM308))) | IF(OR(F308="",AO308=""),"",IF(COUNT(AI308:AN308)=0,"",AO308-LOOKUP(2,1/(AI308:AN308<>""),AI308:AN308))) | IF(OR(F308="",AP308=""),"",IF(COUNT(AI308:AO308)=0,"",AP308-LOOKUP(2,1/(AI308:AO308<>""),AI308:AO308))) | IF(OR(F308="",AQ308=""),"",IF(COUNT(AI308:AP308)=0,"",AQ308-LOOKUP(2,1/(AI308:AP308<>""),AI308:AP308))) | IF(OR(F308="",AR308=""),"",IF(COUNT(AI308:AQ308)=0,"",AR308-LOOKUP(2,1/(AI308:AQ308<>""),AI308:AQ308))) | IF(OR(F308="",AS308=""),"",IF(COUNT(AI308:AR308)=0,"",AS308-LOOKUP(2,1/(AI308:AR308<>""),AI308:AR308))) | IF(OR(F308="",AT308=""),"",IF(COUNT(AI308:AS308)=0,"",AT308-LOOKUP(2,1/(AI308:AS308<>""),AI308:AS308))) | IF(OR(F308="",AU308=""),"",IF(COUNT(AI308:AT308)=0,"",AU308-LOOKUP(2,1/(AI308:AT308<>""),AI308:AT308))) | IF(OR(F308="",AV308=""),"",IF(COUNT(AI308:AU308)=0,"",AV308-LOOKUP(2,1/(AI308:AU308<>""),AI308:AU308))) | IF(J308="","All_Provinces",IFERROR(VLOOKUP(J308,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K308="","All_Districts",IFERROR(VLOOKUP(K308,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F309="","",ROW()-3) | AF2-WSM-20 | Package #20-AF2 WSM: Construction of Sapari Check dams, located in Sarubi districts of Paktika province. | 1 of 1 | AF2-WSM-N-007 | Sapari Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Southeast / Gardez | Paktika | Sarubi | Abas Khil | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 84683 | IF(AQ309="","",AQ309) | 2026-11-25 | 7.2 | 2027-07-03 | IF(W309<>"",W309,IF(OR(T309="",V309=""),"",EDATE(T309,V309))) |  |  | PR to be Raised | Construction of the check dam will be completed in four months. Jan to March end as the slack period. | IF(F309="","",IF(COUNT(AI309:AV309)=0,IF(AA309="","Not started",AA309),SUBSTITUTE(LOOKUP(2,1/(AI309:AV309<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F309="",COUNT(AI309:AV309)=0),"",TODAY()-LOOKUP(2,1/(AI309:AV309<>""),AI309:AV309)) | IF(OR(F309="",COUNT(AI309:AV309)<2),"",LOOKUP(2,1/(AI309:AV309<>""),AI309:AV309)-MIN(AI309:AV309)) | IF(OR(AD309="",AC309="Not started",AC309=""),"",IFERROR(AD309-IF(VLOOKUP(AC309,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC309,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F309="","",IF(OR(AA309="Cancelled",AC309="Cancelled"),"Cancelled",IF(OR(AC309="Completed / Handover",Y309<>"",Z309>=100),"Completed — on track",IF(O309="Not awarded",IF(U309="",IF(X309="","No planned date",IF(TODAY()>X309,"Behind — past planned date",IF(X309-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U309,"Behind — award date passed",IF(U309-TODAY()<=30,"At risk — close to off track","On track"))),IF(X309="","No planned date",IF(AND(TODAY()>X309,OR(Z309="",Z309<100)),"Behind — past end date",IF(AND(T309<>"",X309<>"",Z309<>"",(Z309<100),((TODAY()-T309)/MAX(X309-T309,1)*100)-Z309>15),"Behind — progress lag",IF(AND(X309-TODAY()<=30,X309-TODAY()>=0,OR(Z309="",Z309<90)),"At risk — close to off track","On track")))))))) | IF(OR(F309="",AC309="Completed / Handover",AC309="Cancelled"),"",IF(O309="Not awarded",IF(U309<>"",U309-TODAY(),IF(X309="","",X309-TODAY())),IF(X309="","",X309-TODAY()))) | [14 empty] | IF(OR(F309="",AJ309=""),"",IF(COUNT(AI309:AI309)=0,"",AJ309-LOOKUP(2,1/(AI309:AI309<>""),AI309:AI309))) | IF(OR(F309="",AK309=""),"",IF(COUNT(AI309:AJ309)=0,"",AK309-LOOKUP(2,1/(AI309:AJ309<>""),AI309:AJ309))) | IF(OR(F309="",AL309=""),"",IF(COUNT(AI309:AK309)=0,"",AL309-LOOKUP(2,1/(AI309:AK309<>""),AI309:AK309))) | IF(OR(F309="",AM309=""),"",IF(COUNT(AI309:AL309)=0,"",AM309-LOOKUP(2,1/(AI309:AL309<>""),AI309:AL309))) | IF(OR(F309="",AN309=""),"",IF(COUNT(AI309:AM309)=0,"",AN309-LOOKUP(2,1/(AI309:AM309<>""),AI309:AM309))) | IF(OR(F309="",AO309=""),"",IF(COUNT(AI309:AN309)=0,"",AO309-LOOKUP(2,1/(AI309:AN309<>""),AI309:AN309))) | IF(OR(F309="",AP309=""),"",IF(COUNT(AI309:AO309)=0,"",AP309-LOOKUP(2,1/(AI309:AO309<>""),AI309:AO309))) | IF(OR(F309="",AQ309=""),"",IF(COUNT(AI309:AP309)=0,"",AQ309-LOOKUP(2,1/(AI309:AP309<>""),AI309:AP309))) | IF(OR(F309="",AR309=""),"",IF(COUNT(AI309:AQ309)=0,"",AR309-LOOKUP(2,1/(AI309:AQ309<>""),AI309:AQ309))) | IF(OR(F309="",AS309=""),"",IF(COUNT(AI309:AR309)=0,"",AS309-LOOKUP(2,1/(AI309:AR309<>""),AI309:AR309))) | IF(OR(F309="",AT309=""),"",IF(COUNT(AI309:AS309)=0,"",AT309-LOOKUP(2,1/(AI309:AS309<>""),AI309:AS309))) | IF(OR(F309="",AU309=""),"",IF(COUNT(AI309:AT309)=0,"",AU309-LOOKUP(2,1/(AI309:AT309<>""),AI309:AT309))) | IF(OR(F309="",AV309=""),"",IF(COUNT(AI309:AU309)=0,"",AV309-LOOKUP(2,1/(AI309:AU309<>""),AI309:AU309))) | IF(J309="","All_Provinces",IFERROR(VLOOKUP(J309,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K309="","All_Districts",IFERROR(VLOOKUP(K309,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F310="","",ROW()-3) | AF2-WSM-21 | Package #21-AF2 WSM: Construction of 4 Check Dams 1.Choghazey and 2.Sardarkey in Arghistan, 3. Loy Laher in Spin Boldak and 4.Ab Samad Aka in Takhta Pull districts of Kandahar province. | 1 of 4 | AF2-WSM-A-042 | Ab Samad Aka Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Takhta Pul | Choghazey | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Bakhter Pairoz Construction Company (BPCC) | 031/2026 | 38337.07 | IF(AQ310="","",AQ310) |  | 5 | 2026-09-27 | IF(W310<>"",W310,IF(OR(T310="",V310=""),"",EDATE(T310,V310))) |  | 10 | Under Construction | Completed on Sep, 2026 | IF(F310="","",IF(COUNT(AI310:AV310)=0,IF(AA310="","Not started",AA310),SUBSTITUTE(LOOKUP(2,1/(AI310:AV310<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F310="",COUNT(AI310:AV310)=0),"",TODAY()-LOOKUP(2,1/(AI310:AV310<>""),AI310:AV310)) | IF(OR(F310="",COUNT(AI310:AV310)<2),"",LOOKUP(2,1/(AI310:AV310<>""),AI310:AV310)-MIN(AI310:AV310)) | IF(OR(AD310="",AC310="Not started",AC310=""),"",IFERROR(AD310-IF(VLOOKUP(AC310,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC310,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F310="","",IF(OR(AA310="Cancelled",AC310="Cancelled"),"Cancelled",IF(OR(AC310="Completed / Handover",Y310<>"",Z310>=100),"Completed — on track",IF(O310="Not awarded",IF(U310="",IF(X310="","No planned date",IF(TODAY()>X310,"Behind — past planned date",IF(X310-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U310,"Behind — award date passed",IF(U310-TODAY()<=30,"At risk — close to off track","On track"))),IF(X310="","No planned date",IF(AND(TODAY()>X310,OR(Z310="",Z310<100)),"Behind — past end date",IF(AND(T310<>"",X310<>"",Z310<>"",(Z310<100),((TODAY()-T310)/MAX(X310-T310,1)*100)-Z310>15),"Behind — progress lag",IF(AND(X310-TODAY()<=30,X310-TODAY()>=0,OR(Z310="",Z310<90)),"At risk — close to off track","On track")))))))) | IF(OR(F310="",AC310="Completed / Handover",AC310="Cancelled"),"",IF(O310="Not awarded",IF(U310<>"",U310-TODAY(),IF(X310="","",X310-TODAY())),IF(X310="","",X310-TODAY()))) | [8 empty] | 2026-04-28 | 2026-04-28 |  |  |  |  | IF(OR(F310="",AJ310=""),"",IF(COUNT(AI310:AI310)=0,"",AJ310-LOOKUP(2,1/(AI310:AI310<>""),AI310:AI310))) | IF(OR(F310="",AK310=""),"",IF(COUNT(AI310:AJ310)=0,"",AK310-LOOKUP(2,1/(AI310:AJ310<>""),AI310:AJ310))) | IF(OR(F310="",AL310=""),"",IF(COUNT(AI310:AK310)=0,"",AL310-LOOKUP(2,1/(AI310:AK310<>""),AI310:AK310))) | IF(OR(F310="",AM310=""),"",IF(COUNT(AI310:AL310)=0,"",AM310-LOOKUP(2,1/(AI310:AL310<>""),AI310:AL310))) | IF(OR(F310="",AN310=""),"",IF(COUNT(AI310:AM310)=0,"",AN310-LOOKUP(2,1/(AI310:AM310<>""),AI310:AM310))) | IF(OR(F310="",AO310=""),"",IF(COUNT(AI310:AN310)=0,"",AO310-LOOKUP(2,1/(AI310:AN310<>""),AI310:AN310))) | IF(OR(F310="",AP310=""),"",IF(COUNT(AI310:AO310)=0,"",AP310-LOOKUP(2,1/(AI310:AO310<>""),AI310:AO310))) | IF(OR(F310="",AQ310=""),"",IF(COUNT(AI310:AP310)=0,"",AQ310-LOOKUP(2,1/(AI310:AP310<>""),AI310:AP310))) | IF(OR(F310="",AR310=""),"",IF(COUNT(AI310:AQ310)=0,"",AR310-LOOKUP(2,1/(AI310:AQ310<>""),AI310:AQ310))) | IF(OR(F310="",AS310=""),"",IF(COUNT(AI310:AR310)=0,"",AS310-LOOKUP(2,1/(AI310:AR310<>""),AI310:AR310))) | IF(OR(F310="",AT310=""),"",IF(COUNT(AI310:AS310)=0,"",AT310-LOOKUP(2,1/(AI310:AS310<>""),AI310:AS310))) | IF(OR(F310="",AU310=""),"",IF(COUNT(AI310:AT310)=0,"",AU310-LOOKUP(2,1/(AI310:AT310<>""),AI310:AT310))) | IF(OR(F310="",AV310=""),"",IF(COUNT(AI310:AU310)=0,"",AV310-LOOKUP(2,1/(AI310:AU310<>""),AI310:AU310))) | IF(J310="","All_Provinces",IFERROR(VLOOKUP(J310,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K310="","All_Districts",IFERROR(VLOOKUP(K310,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F311="","",ROW()-3) | AF2-WSM-21 | Package #21-AF2 WSM: Construction of 4 Check Dams 1.Choghazey and 2.Sardarkey in Arghistan, 3. Loy Laher in Spin Boldak and 4.Ab Samad Aka in Takhta Pull districts of Kandahar province. | 2 of 4 | AF2-WSM-A-043 | Choghazey Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Arghistan | Ab Samad Aka | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Bakhter Pairoz Construction Company (BPCC) | 031/2026 | 12021.06 | IF(AQ311="","",AQ311) |  | 5 | 2026-09-27 | IF(W311<>"",W311,IF(OR(T311="",V311=""),"",EDATE(T311,V311))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F311="","",IF(COUNT(AI311:AV311)=0,IF(AA311="","Not started",AA311),SUBSTITUTE(LOOKUP(2,1/(AI311:AV311<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F311="",COUNT(AI311:AV311)=0),"",TODAY()-LOOKUP(2,1/(AI311:AV311<>""),AI311:AV311)) | IF(OR(F311="",COUNT(AI311:AV311)<2),"",LOOKUP(2,1/(AI311:AV311<>""),AI311:AV311)-MIN(AI311:AV311)) | IF(OR(AD311="",AC311="Not started",AC311=""),"",IFERROR(AD311-IF(VLOOKUP(AC311,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC311,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F311="","",IF(OR(AA311="Cancelled",AC311="Cancelled"),"Cancelled",IF(OR(AC311="Completed / Handover",Y311<>"",Z311>=100),"Completed — on track",IF(O311="Not awarded",IF(U311="",IF(X311="","No planned date",IF(TODAY()>X311,"Behind — past planned date",IF(X311-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U311,"Behind — award date passed",IF(U311-TODAY()<=30,"At risk — close to off track","On track"))),IF(X311="","No planned date",IF(AND(TODAY()>X311,OR(Z311="",Z311<100)),"Behind — past end date",IF(AND(T311<>"",X311<>"",Z311<>"",(Z311<100),((TODAY()-T311)/MAX(X311-T311,1)*100)-Z311>15),"Behind — progress lag",IF(AND(X311-TODAY()<=30,X311-TODAY()>=0,OR(Z311="",Z311<90)),"At risk — close to off track","On track")))))))) | IF(OR(F311="",AC311="Completed / Handover",AC311="Cancelled"),"",IF(O311="Not awarded",IF(U311<>"",U311-TODAY(),IF(X311="","",X311-TODAY())),IF(X311="","",X311-TODAY()))) | [8 empty] | 2026-04-28 | 2026-04-28 | 2026-09-27 |  |  |  | IF(OR(F311="",AJ311=""),"",IF(COUNT(AI311:AI311)=0,"",AJ311-LOOKUP(2,1/(AI311:AI311<>""),AI311:AI311))) | IF(OR(F311="",AK311=""),"",IF(COUNT(AI311:AJ311)=0,"",AK311-LOOKUP(2,1/(AI311:AJ311<>""),AI311:AJ311))) | IF(OR(F311="",AL311=""),"",IF(COUNT(AI311:AK311)=0,"",AL311-LOOKUP(2,1/(AI311:AK311<>""),AI311:AK311))) | IF(OR(F311="",AM311=""),"",IF(COUNT(AI311:AL311)=0,"",AM311-LOOKUP(2,1/(AI311:AL311<>""),AI311:AL311))) | IF(OR(F311="",AN311=""),"",IF(COUNT(AI311:AM311)=0,"",AN311-LOOKUP(2,1/(AI311:AM311<>""),AI311:AM311))) | IF(OR(F311="",AO311=""),"",IF(COUNT(AI311:AN311)=0,"",AO311-LOOKUP(2,1/(AI311:AN311<>""),AI311:AN311))) | IF(OR(F311="",AP311=""),"",IF(COUNT(AI311:AO311)=0,"",AP311-LOOKUP(2,1/(AI311:AO311<>""),AI311:AO311))) | IF(OR(F311="",AQ311=""),"",IF(COUNT(AI311:AP311)=0,"",AQ311-LOOKUP(2,1/(AI311:AP311<>""),AI311:AP311))) | IF(OR(F311="",AR311=""),"",IF(COUNT(AI311:AQ311)=0,"",AR311-LOOKUP(2,1/(AI311:AQ311<>""),AI311:AQ311))) | IF(OR(F311="",AS311=""),"",IF(COUNT(AI311:AR311)=0,"",AS311-LOOKUP(2,1/(AI311:AR311<>""),AI311:AR311))) | IF(OR(F311="",AT311=""),"",IF(COUNT(AI311:AS311)=0,"",AT311-LOOKUP(2,1/(AI311:AS311<>""),AI311:AS311))) | IF(OR(F311="",AU311=""),"",IF(COUNT(AI311:AT311)=0,"",AU311-LOOKUP(2,1/(AI311:AT311<>""),AI311:AT311))) | IF(OR(F311="",AV311=""),"",IF(COUNT(AI311:AU311)=0,"",AV311-LOOKUP(2,1/(AI311:AU311<>""),AI311:AU311))) | IF(J311="","All_Provinces",IFERROR(VLOOKUP(J311,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K311="","All_Districts",IFERROR(VLOOKUP(K311,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F312="","",ROW()-3) | AF2-WSM-21 | Package #21-AF2 WSM: Construction of 4 Check Dams 1.Choghazey and 2.Sardarkey in Arghistan, 3. Loy Laher in Spin Boldak and 4.Ab Samad Aka in Takhta Pull districts of Kandahar province. | 3 of 4 | AF2-WSM-A-044 | Loy Laher Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Spin Boldak | Sardarkey | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Bakhter Pairoz Construction Company (BPCC) | 031/2026 | 30196.08 | IF(AQ312="","",AQ312) |  | 5 | 2026-09-27 | IF(W312<>"",W312,IF(OR(T312="",V312=""),"",EDATE(T312,V312))) |  | 15 | Under Construction | Completed on Sep, 2026 | IF(F312="","",IF(COUNT(AI312:AV312)=0,IF(AA312="","Not started",AA312),SUBSTITUTE(LOOKUP(2,1/(AI312:AV312<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F312="",COUNT(AI312:AV312)=0),"",TODAY()-LOOKUP(2,1/(AI312:AV312<>""),AI312:AV312)) | IF(OR(F312="",COUNT(AI312:AV312)<2),"",LOOKUP(2,1/(AI312:AV312<>""),AI312:AV312)-MIN(AI312:AV312)) | IF(OR(AD312="",AC312="Not started",AC312=""),"",IFERROR(AD312-IF(VLOOKUP(AC312,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC312,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F312="","",IF(OR(AA312="Cancelled",AC312="Cancelled"),"Cancelled",IF(OR(AC312="Completed / Handover",Y312<>"",Z312>=100),"Completed — on track",IF(O312="Not awarded",IF(U312="",IF(X312="","No planned date",IF(TODAY()>X312,"Behind — past planned date",IF(X312-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U312,"Behind — award date passed",IF(U312-TODAY()<=30,"At risk — close to off track","On track"))),IF(X312="","No planned date",IF(AND(TODAY()>X312,OR(Z312="",Z312<100)),"Behind — past end date",IF(AND(T312<>"",X312<>"",Z312<>"",(Z312<100),((TODAY()-T312)/MAX(X312-T312,1)*100)-Z312>15),"Behind — progress lag",IF(AND(X312-TODAY()<=30,X312-TODAY()>=0,OR(Z312="",Z312<90)),"At risk — close to off track","On track")))))))) | IF(OR(F312="",AC312="Completed / Handover",AC312="Cancelled"),"",IF(O312="Not awarded",IF(U312<>"",U312-TODAY(),IF(X312="","",X312-TODAY())),IF(X312="","",X312-TODAY()))) | [8 empty] | 2026-04-28 | 2026-04-28 |  |  |  |  | IF(OR(F312="",AJ312=""),"",IF(COUNT(AI312:AI312)=0,"",AJ312-LOOKUP(2,1/(AI312:AI312<>""),AI312:AI312))) | IF(OR(F312="",AK312=""),"",IF(COUNT(AI312:AJ312)=0,"",AK312-LOOKUP(2,1/(AI312:AJ312<>""),AI312:AJ312))) | IF(OR(F312="",AL312=""),"",IF(COUNT(AI312:AK312)=0,"",AL312-LOOKUP(2,1/(AI312:AK312<>""),AI312:AK312))) | IF(OR(F312="",AM312=""),"",IF(COUNT(AI312:AL312)=0,"",AM312-LOOKUP(2,1/(AI312:AL312<>""),AI312:AL312))) | IF(OR(F312="",AN312=""),"",IF(COUNT(AI312:AM312)=0,"",AN312-LOOKUP(2,1/(AI312:AM312<>""),AI312:AM312))) | IF(OR(F312="",AO312=""),"",IF(COUNT(AI312:AN312)=0,"",AO312-LOOKUP(2,1/(AI312:AN312<>""),AI312:AN312))) | IF(OR(F312="",AP312=""),"",IF(COUNT(AI312:AO312)=0,"",AP312-LOOKUP(2,1/(AI312:AO312<>""),AI312:AO312))) | IF(OR(F312="",AQ312=""),"",IF(COUNT(AI312:AP312)=0,"",AQ312-LOOKUP(2,1/(AI312:AP312<>""),AI312:AP312))) | IF(OR(F312="",AR312=""),"",IF(COUNT(AI312:AQ312)=0,"",AR312-LOOKUP(2,1/(AI312:AQ312<>""),AI312:AQ312))) | IF(OR(F312="",AS312=""),"",IF(COUNT(AI312:AR312)=0,"",AS312-LOOKUP(2,1/(AI312:AR312<>""),AI312:AR312))) | IF(OR(F312="",AT312=""),"",IF(COUNT(AI312:AS312)=0,"",AT312-LOOKUP(2,1/(AI312:AS312<>""),AI312:AS312))) | IF(OR(F312="",AU312=""),"",IF(COUNT(AI312:AT312)=0,"",AU312-LOOKUP(2,1/(AI312:AT312<>""),AI312:AT312))) | IF(OR(F312="",AV312=""),"",IF(COUNT(AI312:AU312)=0,"",AV312-LOOKUP(2,1/(AI312:AU312<>""),AI312:AU312))) | IF(J312="","All_Provinces",IFERROR(VLOOKUP(J312,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K312="","All_Districts",IFERROR(VLOOKUP(K312,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F313="","",ROW()-3) | AF2-WSM-21 | Package #21-AF2 WSM: Construction of 4 Check Dams 1.Choghazey and 2.Sardarkey in Arghistan, 3. Loy Laher in Spin Boldak and 4.Ab Samad Aka in Takhta Pull districts of Kandahar province. | 4 of 4 | AF2-WSM-A-045 | Sardarkey Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Arghistan | Loy Laher | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Bakhter Pairoz Construction Company (BPCC) | 031/2026 | 34095.16 | IF(AQ313="","",AQ313) |  | 5 | 2026-09-27 | IF(W313<>"",W313,IF(OR(T313="",V313=""),"",EDATE(T313,V313))) |  | 95 | Under Construction | Completed on Sep, 2026 | IF(F313="","",IF(COUNT(AI313:AV313)=0,IF(AA313="","Not started",AA313),SUBSTITUTE(LOOKUP(2,1/(AI313:AV313<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F313="",COUNT(AI313:AV313)=0),"",TODAY()-LOOKUP(2,1/(AI313:AV313<>""),AI313:AV313)) | IF(OR(F313="",COUNT(AI313:AV313)<2),"",LOOKUP(2,1/(AI313:AV313<>""),AI313:AV313)-MIN(AI313:AV313)) | IF(OR(AD313="",AC313="Not started",AC313=""),"",IFERROR(AD313-IF(VLOOKUP(AC313,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC313,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F313="","",IF(OR(AA313="Cancelled",AC313="Cancelled"),"Cancelled",IF(OR(AC313="Completed / Handover",Y313<>"",Z313>=100),"Completed — on track",IF(O313="Not awarded",IF(U313="",IF(X313="","No planned date",IF(TODAY()>X313,"Behind — past planned date",IF(X313-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U313,"Behind — award date passed",IF(U313-TODAY()<=30,"At risk — close to off track","On track"))),IF(X313="","No planned date",IF(AND(TODAY()>X313,OR(Z313="",Z313<100)),"Behind — past end date",IF(AND(T313<>"",X313<>"",Z313<>"",(Z313<100),((TODAY()-T313)/MAX(X313-T313,1)*100)-Z313>15),"Behind — progress lag",IF(AND(X313-TODAY()<=30,X313-TODAY()>=0,OR(Z313="",Z313<90)),"At risk — close to off track","On track")))))))) | IF(OR(F313="",AC313="Completed / Handover",AC313="Cancelled"),"",IF(O313="Not awarded",IF(U313<>"",U313-TODAY(),IF(X313="","",X313-TODAY())),IF(X313="","",X313-TODAY()))) | [8 empty] | 2026-04-28 | 2026-04-28 |  |  |  |  | IF(OR(F313="",AJ313=""),"",IF(COUNT(AI313:AI313)=0,"",AJ313-LOOKUP(2,1/(AI313:AI313<>""),AI313:AI313))) | IF(OR(F313="",AK313=""),"",IF(COUNT(AI313:AJ313)=0,"",AK313-LOOKUP(2,1/(AI313:AJ313<>""),AI313:AJ313))) | IF(OR(F313="",AL313=""),"",IF(COUNT(AI313:AK313)=0,"",AL313-LOOKUP(2,1/(AI313:AK313<>""),AI313:AK313))) | IF(OR(F313="",AM313=""),"",IF(COUNT(AI313:AL313)=0,"",AM313-LOOKUP(2,1/(AI313:AL313<>""),AI313:AL313))) | IF(OR(F313="",AN313=""),"",IF(COUNT(AI313:AM313)=0,"",AN313-LOOKUP(2,1/(AI313:AM313<>""),AI313:AM313))) | IF(OR(F313="",AO313=""),"",IF(COUNT(AI313:AN313)=0,"",AO313-LOOKUP(2,1/(AI313:AN313<>""),AI313:AN313))) | IF(OR(F313="",AP313=""),"",IF(COUNT(AI313:AO313)=0,"",AP313-LOOKUP(2,1/(AI313:AO313<>""),AI313:AO313))) | IF(OR(F313="",AQ313=""),"",IF(COUNT(AI313:AP313)=0,"",AQ313-LOOKUP(2,1/(AI313:AP313<>""),AI313:AP313))) | IF(OR(F313="",AR313=""),"",IF(COUNT(AI313:AQ313)=0,"",AR313-LOOKUP(2,1/(AI313:AQ313<>""),AI313:AQ313))) | IF(OR(F313="",AS313=""),"",IF(COUNT(AI313:AR313)=0,"",AS313-LOOKUP(2,1/(AI313:AR313<>""),AI313:AR313))) | IF(OR(F313="",AT313=""),"",IF(COUNT(AI313:AS313)=0,"",AT313-LOOKUP(2,1/(AI313:AS313<>""),AI313:AS313))) | IF(OR(F313="",AU313=""),"",IF(COUNT(AI313:AT313)=0,"",AU313-LOOKUP(2,1/(AI313:AT313<>""),AI313:AT313))) | IF(OR(F313="",AV313=""),"",IF(COUNT(AI313:AU313)=0,"",AV313-LOOKUP(2,1/(AI313:AU313<>""),AI313:AU313))) | IF(J313="","All_Provinces",IFERROR(VLOOKUP(J313,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K313="","All_Districts",IFERROR(VLOOKUP(K313,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F314="","",ROW()-3) | AF2-WSM-22 | Package #22-AF2 WSM: Construction of 5 Check dams 1.Kocni Karez , 2.By Khosh , 3. Ghul Khani, 4. Chy Dara in Ghorak district , and 5. Khanjak Mastan Aka in Nesh district of Kandahar province. | 1 of 5 | AF2-WSM-N-008 | By Khosh Dara Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Ghorak | By Khosh Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 135000 | IF(AQ314="","",AQ314) | 2026-11-30 | 5.9 | 2027-05-29 | IF(W314<>"",W314,IF(OR(T314="",V314=""),"",EDATE(T314,V314))) |  |  | Under Design | Technical clearance is expected to receive at end October. PR raised and ITB launched by the first week of November and award of contract by the end of November. Construction period for six months | IF(F314="","",IF(COUNT(AI314:AV314)=0,IF(AA314="","Not started",AA314),SUBSTITUTE(LOOKUP(2,1/(AI314:AV314<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F314="",COUNT(AI314:AV314)=0),"",TODAY()-LOOKUP(2,1/(AI314:AV314<>""),AI314:AV314)) | IF(OR(F314="",COUNT(AI314:AV314)<2),"",LOOKUP(2,1/(AI314:AV314<>""),AI314:AV314)-MIN(AI314:AV314)) | IF(OR(AD314="",AC314="Not started",AC314=""),"",IFERROR(AD314-IF(VLOOKUP(AC314,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC314,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F314="","",IF(OR(AA314="Cancelled",AC314="Cancelled"),"Cancelled",IF(OR(AC314="Completed / Handover",Y314<>"",Z314>=100),"Completed — on track",IF(O314="Not awarded",IF(U314="",IF(X314="","No planned date",IF(TODAY()>X314,"Behind — past planned date",IF(X314-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U314,"Behind — award date passed",IF(U314-TODAY()<=30,"At risk — close to off track","On track"))),IF(X314="","No planned date",IF(AND(TODAY()>X314,OR(Z314="",Z314<100)),"Behind — past end date",IF(AND(T314<>"",X314<>"",Z314<>"",(Z314<100),((TODAY()-T314)/MAX(X314-T314,1)*100)-Z314>15),"Behind — progress lag",IF(AND(X314-TODAY()<=30,X314-TODAY()>=0,OR(Z314="",Z314<90)),"At risk — close to off track","On track")))))))) | IF(OR(F314="",AC314="Completed / Handover",AC314="Cancelled"),"",IF(O314="Not awarded",IF(U314<>"",U314-TODAY(),IF(X314="","",X314-TODAY())),IF(X314="","",X314-TODAY()))) | [14 empty] | IF(OR(F314="",AJ314=""),"",IF(COUNT(AI314:AI314)=0,"",AJ314-LOOKUP(2,1/(AI314:AI314<>""),AI314:AI314))) | IF(OR(F314="",AK314=""),"",IF(COUNT(AI314:AJ314)=0,"",AK314-LOOKUP(2,1/(AI314:AJ314<>""),AI314:AJ314))) | IF(OR(F314="",AL314=""),"",IF(COUNT(AI314:AK314)=0,"",AL314-LOOKUP(2,1/(AI314:AK314<>""),AI314:AK314))) | IF(OR(F314="",AM314=""),"",IF(COUNT(AI314:AL314)=0,"",AM314-LOOKUP(2,1/(AI314:AL314<>""),AI314:AL314))) | IF(OR(F314="",AN314=""),"",IF(COUNT(AI314:AM314)=0,"",AN314-LOOKUP(2,1/(AI314:AM314<>""),AI314:AM314))) | IF(OR(F314="",AO314=""),"",IF(COUNT(AI314:AN314)=0,"",AO314-LOOKUP(2,1/(AI314:AN314<>""),AI314:AN314))) | IF(OR(F314="",AP314=""),"",IF(COUNT(AI314:AO314)=0,"",AP314-LOOKUP(2,1/(AI314:AO314<>""),AI314:AO314))) | IF(OR(F314="",AQ314=""),"",IF(COUNT(AI314:AP314)=0,"",AQ314-LOOKUP(2,1/(AI314:AP314<>""),AI314:AP314))) | IF(OR(F314="",AR314=""),"",IF(COUNT(AI314:AQ314)=0,"",AR314-LOOKUP(2,1/(AI314:AQ314<>""),AI314:AQ314))) | IF(OR(F314="",AS314=""),"",IF(COUNT(AI314:AR314)=0,"",AS314-LOOKUP(2,1/(AI314:AR314<>""),AI314:AR314))) | IF(OR(F314="",AT314=""),"",IF(COUNT(AI314:AS314)=0,"",AT314-LOOKUP(2,1/(AI314:AS314<>""),AI314:AS314))) | IF(OR(F314="",AU314=""),"",IF(COUNT(AI314:AT314)=0,"",AU314-LOOKUP(2,1/(AI314:AT314<>""),AI314:AT314))) | IF(OR(F314="",AV314=""),"",IF(COUNT(AI314:AU314)=0,"",AV314-LOOKUP(2,1/(AI314:AU314<>""),AI314:AU314))) | IF(J314="","All_Provinces",IFERROR(VLOOKUP(J314,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K314="","All_Districts",IFERROR(VLOOKUP(K314,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F315="","",ROW()-3) | AF2-WSM-22 | Package #22-AF2 WSM: Construction of 5 Check dams 1.Kocni Karez , 2.By Khosh , 3. Ghul Khani, 4. Chy Dara in Ghorak district , and 5. Khanjak Mastan Aka in Nesh district of Kandahar province. | 2 of 5 | AF2-WSM-N-009 | Chy Dara Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Ghorak | Chy dar Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 135000 | IF(AQ315="","",AQ315) | 2026-11-30 | 5.9 | 2027-05-29 | IF(W315<>"",W315,IF(OR(T315="",V315=""),"",EDATE(T315,V315))) |  |  | Under Design | Technical clearance is expected to receive at end October. PR raised and ITB launched by the first week of November and award of contract by the end of November. Construction period for six months | IF(F315="","",IF(COUNT(AI315:AV315)=0,IF(AA315="","Not started",AA315),SUBSTITUTE(LOOKUP(2,1/(AI315:AV315<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F315="",COUNT(AI315:AV315)=0),"",TODAY()-LOOKUP(2,1/(AI315:AV315<>""),AI315:AV315)) | IF(OR(F315="",COUNT(AI315:AV315)<2),"",LOOKUP(2,1/(AI315:AV315<>""),AI315:AV315)-MIN(AI315:AV315)) | IF(OR(AD315="",AC315="Not started",AC315=""),"",IFERROR(AD315-IF(VLOOKUP(AC315,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC315,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F315="","",IF(OR(AA315="Cancelled",AC315="Cancelled"),"Cancelled",IF(OR(AC315="Completed / Handover",Y315<>"",Z315>=100),"Completed — on track",IF(O315="Not awarded",IF(U315="",IF(X315="","No planned date",IF(TODAY()>X315,"Behind — past planned date",IF(X315-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U315,"Behind — award date passed",IF(U315-TODAY()<=30,"At risk — close to off track","On track"))),IF(X315="","No planned date",IF(AND(TODAY()>X315,OR(Z315="",Z315<100)),"Behind — past end date",IF(AND(T315<>"",X315<>"",Z315<>"",(Z315<100),((TODAY()-T315)/MAX(X315-T315,1)*100)-Z315>15),"Behind — progress lag",IF(AND(X315-TODAY()<=30,X315-TODAY()>=0,OR(Z315="",Z315<90)),"At risk — close to off track","On track")))))))) | IF(OR(F315="",AC315="Completed / Handover",AC315="Cancelled"),"",IF(O315="Not awarded",IF(U315<>"",U315-TODAY(),IF(X315="","",X315-TODAY())),IF(X315="","",X315-TODAY()))) | [14 empty] | IF(OR(F315="",AJ315=""),"",IF(COUNT(AI315:AI315)=0,"",AJ315-LOOKUP(2,1/(AI315:AI315<>""),AI315:AI315))) | IF(OR(F315="",AK315=""),"",IF(COUNT(AI315:AJ315)=0,"",AK315-LOOKUP(2,1/(AI315:AJ315<>""),AI315:AJ315))) | IF(OR(F315="",AL315=""),"",IF(COUNT(AI315:AK315)=0,"",AL315-LOOKUP(2,1/(AI315:AK315<>""),AI315:AK315))) | IF(OR(F315="",AM315=""),"",IF(COUNT(AI315:AL315)=0,"",AM315-LOOKUP(2,1/(AI315:AL315<>""),AI315:AL315))) | IF(OR(F315="",AN315=""),"",IF(COUNT(AI315:AM315)=0,"",AN315-LOOKUP(2,1/(AI315:AM315<>""),AI315:AM315))) | IF(OR(F315="",AO315=""),"",IF(COUNT(AI315:AN315)=0,"",AO315-LOOKUP(2,1/(AI315:AN315<>""),AI315:AN315))) | IF(OR(F315="",AP315=""),"",IF(COUNT(AI315:AO315)=0,"",AP315-LOOKUP(2,1/(AI315:AO315<>""),AI315:AO315))) | IF(OR(F315="",AQ315=""),"",IF(COUNT(AI315:AP315)=0,"",AQ315-LOOKUP(2,1/(AI315:AP315<>""),AI315:AP315))) | IF(OR(F315="",AR315=""),"",IF(COUNT(AI315:AQ315)=0,"",AR315-LOOKUP(2,1/(AI315:AQ315<>""),AI315:AQ315))) | IF(OR(F315="",AS315=""),"",IF(COUNT(AI315:AR315)=0,"",AS315-LOOKUP(2,1/(AI315:AR315<>""),AI315:AR315))) | IF(OR(F315="",AT315=""),"",IF(COUNT(AI315:AS315)=0,"",AT315-LOOKUP(2,1/(AI315:AS315<>""),AI315:AS315))) | IF(OR(F315="",AU315=""),"",IF(COUNT(AI315:AT315)=0,"",AU315-LOOKUP(2,1/(AI315:AT315<>""),AI315:AT315))) | IF(OR(F315="",AV315=""),"",IF(COUNT(AI315:AU315)=0,"",AV315-LOOKUP(2,1/(AI315:AU315<>""),AI315:AU315))) | IF(J315="","All_Provinces",IFERROR(VLOOKUP(J315,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K315="","All_Districts",IFERROR(VLOOKUP(K315,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F316="","",ROW()-3) | AF2-WSM-22 | Package #22-AF2 WSM: Construction of 5 Check dams 1.Kocni Karez , 2.By Khosh , 3. Ghul Khani, 4. Chy Dara in Ghorak district , and 5. Khanjak Mastan Aka in Nesh district of Kandahar province. | 3 of 5 | AF2-WSM-N-010 | Ghul Khani Dara Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Ghorak | Ghul Khani Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 135000 | IF(AQ316="","",AQ316) | 2026-11-30 | 5.9 | 2027-05-29 | IF(W316<>"",W316,IF(OR(T316="",V316=""),"",EDATE(T316,V316))) |  |  | Under Design | Technical clearance is expected to receive at end October. PR raised and ITB launched by the first week of November and award of contract by the end of November. Construction period for six months | IF(F316="","",IF(COUNT(AI316:AV316)=0,IF(AA316="","Not started",AA316),SUBSTITUTE(LOOKUP(2,1/(AI316:AV316<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F316="",COUNT(AI316:AV316)=0),"",TODAY()-LOOKUP(2,1/(AI316:AV316<>""),AI316:AV316)) | IF(OR(F316="",COUNT(AI316:AV316)<2),"",LOOKUP(2,1/(AI316:AV316<>""),AI316:AV316)-MIN(AI316:AV316)) | IF(OR(AD316="",AC316="Not started",AC316=""),"",IFERROR(AD316-IF(VLOOKUP(AC316,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC316,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F316="","",IF(OR(AA316="Cancelled",AC316="Cancelled"),"Cancelled",IF(OR(AC316="Completed / Handover",Y316<>"",Z316>=100),"Completed — on track",IF(O316="Not awarded",IF(U316="",IF(X316="","No planned date",IF(TODAY()>X316,"Behind — past planned date",IF(X316-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U316,"Behind — award date passed",IF(U316-TODAY()<=30,"At risk — close to off track","On track"))),IF(X316="","No planned date",IF(AND(TODAY()>X316,OR(Z316="",Z316<100)),"Behind — past end date",IF(AND(T316<>"",X316<>"",Z316<>"",(Z316<100),((TODAY()-T316)/MAX(X316-T316,1)*100)-Z316>15),"Behind — progress lag",IF(AND(X316-TODAY()<=30,X316-TODAY()>=0,OR(Z316="",Z316<90)),"At risk — close to off track","On track")))))))) | IF(OR(F316="",AC316="Completed / Handover",AC316="Cancelled"),"",IF(O316="Not awarded",IF(U316<>"",U316-TODAY(),IF(X316="","",X316-TODAY())),IF(X316="","",X316-TODAY()))) | [14 empty] | IF(OR(F316="",AJ316=""),"",IF(COUNT(AI316:AI316)=0,"",AJ316-LOOKUP(2,1/(AI316:AI316<>""),AI316:AI316))) | IF(OR(F316="",AK316=""),"",IF(COUNT(AI316:AJ316)=0,"",AK316-LOOKUP(2,1/(AI316:AJ316<>""),AI316:AJ316))) | IF(OR(F316="",AL316=""),"",IF(COUNT(AI316:AK316)=0,"",AL316-LOOKUP(2,1/(AI316:AK316<>""),AI316:AK316))) | IF(OR(F316="",AM316=""),"",IF(COUNT(AI316:AL316)=0,"",AM316-LOOKUP(2,1/(AI316:AL316<>""),AI316:AL316))) | IF(OR(F316="",AN316=""),"",IF(COUNT(AI316:AM316)=0,"",AN316-LOOKUP(2,1/(AI316:AM316<>""),AI316:AM316))) | IF(OR(F316="",AO316=""),"",IF(COUNT(AI316:AN316)=0,"",AO316-LOOKUP(2,1/(AI316:AN316<>""),AI316:AN316))) | IF(OR(F316="",AP316=""),"",IF(COUNT(AI316:AO316)=0,"",AP316-LOOKUP(2,1/(AI316:AO316<>""),AI316:AO316))) | IF(OR(F316="",AQ316=""),"",IF(COUNT(AI316:AP316)=0,"",AQ316-LOOKUP(2,1/(AI316:AP316<>""),AI316:AP316))) | IF(OR(F316="",AR316=""),"",IF(COUNT(AI316:AQ316)=0,"",AR316-LOOKUP(2,1/(AI316:AQ316<>""),AI316:AQ316))) | IF(OR(F316="",AS316=""),"",IF(COUNT(AI316:AR316)=0,"",AS316-LOOKUP(2,1/(AI316:AR316<>""),AI316:AR316))) | IF(OR(F316="",AT316=""),"",IF(COUNT(AI316:AS316)=0,"",AT316-LOOKUP(2,1/(AI316:AS316<>""),AI316:AS316))) | IF(OR(F316="",AU316=""),"",IF(COUNT(AI316:AT316)=0,"",AU316-LOOKUP(2,1/(AI316:AT316<>""),AI316:AT316))) | IF(OR(F316="",AV316=""),"",IF(COUNT(AI316:AU316)=0,"",AV316-LOOKUP(2,1/(AI316:AU316<>""),AI316:AU316))) | IF(J316="","All_Provinces",IFERROR(VLOOKUP(J316,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K316="","All_Districts",IFERROR(VLOOKUP(K316,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F317="","",ROW()-3) | AF2-WSM-22 | Package #22-AF2 WSM: Construction of 5 Check dams 1.Kocni Karez , 2.By Khosh , 3. Ghul Khani, 4. Chy Dara in Ghorak district , and 5. Khanjak Mastan Aka in Nesh district of Kandahar province. | 4 of 5 | AF2-WSM-N-011 | Khanjak Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Nesh | Khanjak Mastan Aka | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 135000 | IF(AQ317="","",AQ317) | 2026-11-30 | 5.9 | 2027-05-29 | IF(W317<>"",W317,IF(OR(T317="",V317=""),"",EDATE(T317,V317))) |  |  | Under Design | Technical clearance is expected to receive at end October. PR raised and ITB launched by the first week of November and award of contract by the end of November. Construction period for six months | IF(F317="","",IF(COUNT(AI317:AV317)=0,IF(AA317="","Not started",AA317),SUBSTITUTE(LOOKUP(2,1/(AI317:AV317<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F317="",COUNT(AI317:AV317)=0),"",TODAY()-LOOKUP(2,1/(AI317:AV317<>""),AI317:AV317)) | IF(OR(F317="",COUNT(AI317:AV317)<2),"",LOOKUP(2,1/(AI317:AV317<>""),AI317:AV317)-MIN(AI317:AV317)) | IF(OR(AD317="",AC317="Not started",AC317=""),"",IFERROR(AD317-IF(VLOOKUP(AC317,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC317,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F317="","",IF(OR(AA317="Cancelled",AC317="Cancelled"),"Cancelled",IF(OR(AC317="Completed / Handover",Y317<>"",Z317>=100),"Completed — on track",IF(O317="Not awarded",IF(U317="",IF(X317="","No planned date",IF(TODAY()>X317,"Behind — past planned date",IF(X317-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U317,"Behind — award date passed",IF(U317-TODAY()<=30,"At risk — close to off track","On track"))),IF(X317="","No planned date",IF(AND(TODAY()>X317,OR(Z317="",Z317<100)),"Behind — past end date",IF(AND(T317<>"",X317<>"",Z317<>"",(Z317<100),((TODAY()-T317)/MAX(X317-T317,1)*100)-Z317>15),"Behind — progress lag",IF(AND(X317-TODAY()<=30,X317-TODAY()>=0,OR(Z317="",Z317<90)),"At risk — close to off track","On track")))))))) | IF(OR(F317="",AC317="Completed / Handover",AC317="Cancelled"),"",IF(O317="Not awarded",IF(U317<>"",U317-TODAY(),IF(X317="","",X317-TODAY())),IF(X317="","",X317-TODAY()))) | [14 empty] | IF(OR(F317="",AJ317=""),"",IF(COUNT(AI317:AI317)=0,"",AJ317-LOOKUP(2,1/(AI317:AI317<>""),AI317:AI317))) | IF(OR(F317="",AK317=""),"",IF(COUNT(AI317:AJ317)=0,"",AK317-LOOKUP(2,1/(AI317:AJ317<>""),AI317:AJ317))) | IF(OR(F317="",AL317=""),"",IF(COUNT(AI317:AK317)=0,"",AL317-LOOKUP(2,1/(AI317:AK317<>""),AI317:AK317))) | IF(OR(F317="",AM317=""),"",IF(COUNT(AI317:AL317)=0,"",AM317-LOOKUP(2,1/(AI317:AL317<>""),AI317:AL317))) | IF(OR(F317="",AN317=""),"",IF(COUNT(AI317:AM317)=0,"",AN317-LOOKUP(2,1/(AI317:AM317<>""),AI317:AM317))) | IF(OR(F317="",AO317=""),"",IF(COUNT(AI317:AN317)=0,"",AO317-LOOKUP(2,1/(AI317:AN317<>""),AI317:AN317))) | IF(OR(F317="",AP317=""),"",IF(COUNT(AI317:AO317)=0,"",AP317-LOOKUP(2,1/(AI317:AO317<>""),AI317:AO317))) | IF(OR(F317="",AQ317=""),"",IF(COUNT(AI317:AP317)=0,"",AQ317-LOOKUP(2,1/(AI317:AP317<>""),AI317:AP317))) | IF(OR(F317="",AR317=""),"",IF(COUNT(AI317:AQ317)=0,"",AR317-LOOKUP(2,1/(AI317:AQ317<>""),AI317:AQ317))) | IF(OR(F317="",AS317=""),"",IF(COUNT(AI317:AR317)=0,"",AS317-LOOKUP(2,1/(AI317:AR317<>""),AI317:AR317))) | IF(OR(F317="",AT317=""),"",IF(COUNT(AI317:AS317)=0,"",AT317-LOOKUP(2,1/(AI317:AS317<>""),AI317:AS317))) | IF(OR(F317="",AU317=""),"",IF(COUNT(AI317:AT317)=0,"",AU317-LOOKUP(2,1/(AI317:AT317<>""),AI317:AT317))) | IF(OR(F317="",AV317=""),"",IF(COUNT(AI317:AU317)=0,"",AV317-LOOKUP(2,1/(AI317:AU317<>""),AI317:AU317))) | IF(J317="","All_Provinces",IFERROR(VLOOKUP(J317,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K317="","All_Districts",IFERROR(VLOOKUP(K317,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F318="","",ROW()-3) | AF2-WSM-22 | Package #22-AF2 WSM: Construction of 5 Check dams 1.Kocni Karez , 2.By Khosh , 3. Ghul Khani, 4. Chy Dara in Ghorak district , and 5. Khanjak Mastan Aka in Nesh district of Kandahar province. | 5 of 5 | AF2-WSM-N-012 | Kocni Karez Check Dam | Watershed Management | Karez Rehabilitation | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Ghorak | Kocni Karez Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 135000 | IF(AQ318="","",AQ318) | 2026-11-30 | 5.9 | 2027-05-29 | IF(W318<>"",W318,IF(OR(T318="",V318=""),"",EDATE(T318,V318))) |  |  | Under Design | Technical clearance is expected to receive at end October. PR raised and ITB launched by the first week of November and award of contract by the end of November. Construction period for six months | IF(F318="","",IF(COUNT(AI318:AV318)=0,IF(AA318="","Not started",AA318),SUBSTITUTE(LOOKUP(2,1/(AI318:AV318<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F318="",COUNT(AI318:AV318)=0),"",TODAY()-LOOKUP(2,1/(AI318:AV318<>""),AI318:AV318)) | IF(OR(F318="",COUNT(AI318:AV318)<2),"",LOOKUP(2,1/(AI318:AV318<>""),AI318:AV318)-MIN(AI318:AV318)) | IF(OR(AD318="",AC318="Not started",AC318=""),"",IFERROR(AD318-IF(VLOOKUP(AC318,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC318,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F318="","",IF(OR(AA318="Cancelled",AC318="Cancelled"),"Cancelled",IF(OR(AC318="Completed / Handover",Y318<>"",Z318>=100),"Completed — on track",IF(O318="Not awarded",IF(U318="",IF(X318="","No planned date",IF(TODAY()>X318,"Behind — past planned date",IF(X318-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U318,"Behind — award date passed",IF(U318-TODAY()<=30,"At risk — close to off track","On track"))),IF(X318="","No planned date",IF(AND(TODAY()>X318,OR(Z318="",Z318<100)),"Behind — past end date",IF(AND(T318<>"",X318<>"",Z318<>"",(Z318<100),((TODAY()-T318)/MAX(X318-T318,1)*100)-Z318>15),"Behind — progress lag",IF(AND(X318-TODAY()<=30,X318-TODAY()>=0,OR(Z318="",Z318<90)),"At risk — close to off track","On track")))))))) | IF(OR(F318="",AC318="Completed / Handover",AC318="Cancelled"),"",IF(O318="Not awarded",IF(U318<>"",U318-TODAY(),IF(X318="","",X318-TODAY())),IF(X318="","",X318-TODAY()))) | [14 empty] | IF(OR(F318="",AJ318=""),"",IF(COUNT(AI318:AI318)=0,"",AJ318-LOOKUP(2,1/(AI318:AI318<>""),AI318:AI318))) | IF(OR(F318="",AK318=""),"",IF(COUNT(AI318:AJ318)=0,"",AK318-LOOKUP(2,1/(AI318:AJ318<>""),AI318:AJ318))) | IF(OR(F318="",AL318=""),"",IF(COUNT(AI318:AK318)=0,"",AL318-LOOKUP(2,1/(AI318:AK318<>""),AI318:AK318))) | IF(OR(F318="",AM318=""),"",IF(COUNT(AI318:AL318)=0,"",AM318-LOOKUP(2,1/(AI318:AL318<>""),AI318:AL318))) | IF(OR(F318="",AN318=""),"",IF(COUNT(AI318:AM318)=0,"",AN318-LOOKUP(2,1/(AI318:AM318<>""),AI318:AM318))) | IF(OR(F318="",AO318=""),"",IF(COUNT(AI318:AN318)=0,"",AO318-LOOKUP(2,1/(AI318:AN318<>""),AI318:AN318))) | IF(OR(F318="",AP318=""),"",IF(COUNT(AI318:AO318)=0,"",AP318-LOOKUP(2,1/(AI318:AO318<>""),AI318:AO318))) | IF(OR(F318="",AQ318=""),"",IF(COUNT(AI318:AP318)=0,"",AQ318-LOOKUP(2,1/(AI318:AP318<>""),AI318:AP318))) | IF(OR(F318="",AR318=""),"",IF(COUNT(AI318:AQ318)=0,"",AR318-LOOKUP(2,1/(AI318:AQ318<>""),AI318:AQ318))) | IF(OR(F318="",AS318=""),"",IF(COUNT(AI318:AR318)=0,"",AS318-LOOKUP(2,1/(AI318:AR318<>""),AI318:AR318))) | IF(OR(F318="",AT318=""),"",IF(COUNT(AI318:AS318)=0,"",AT318-LOOKUP(2,1/(AI318:AS318<>""),AI318:AS318))) | IF(OR(F318="",AU318=""),"",IF(COUNT(AI318:AT318)=0,"",AU318-LOOKUP(2,1/(AI318:AT318<>""),AI318:AT318))) | IF(OR(F318="",AV318=""),"",IF(COUNT(AI318:AU318)=0,"",AV318-LOOKUP(2,1/(AI318:AU318<>""),AI318:AU318))) | IF(J318="","All_Provinces",IFERROR(VLOOKUP(J318,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K318="","All_Districts",IFERROR(VLOOKUP(K318,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F319="","",ROW()-3) | AF2-WSM-23 | Package #23-AF2 WSM: Construction of 1,Payazak, 2.Sharak, 3.Khairtot, and 4. Mula Hanifiya Check Dams, located in Shawalikot district of Kandahar province. | 1 of 4 | AF2-WSM-A-046 | Khairtot Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Shawalikot | Khairtot | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Afghan Laser Engineering and Construction Company (ALCC) | 057/2026 | 34668.62 | IF(AQ319="","",AQ319) |  | 5 | 2026-02-26 | IF(W319<>"",W319,IF(OR(T319="",V319=""),"",EDATE(T319,V319))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F319="","",IF(COUNT(AI319:AV319)=0,IF(AA319="","Not started",AA319),SUBSTITUTE(LOOKUP(2,1/(AI319:AV319<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F319="",COUNT(AI319:AV319)=0),"",TODAY()-LOOKUP(2,1/(AI319:AV319<>""),AI319:AV319)) | IF(OR(F319="",COUNT(AI319:AV319)<2),"",LOOKUP(2,1/(AI319:AV319<>""),AI319:AV319)-MIN(AI319:AV319)) | IF(OR(AD319="",AC319="Not started",AC319=""),"",IFERROR(AD319-IF(VLOOKUP(AC319,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC319,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F319="","",IF(OR(AA319="Cancelled",AC319="Cancelled"),"Cancelled",IF(OR(AC319="Completed / Handover",Y319<>"",Z319>=100),"Completed — on track",IF(O319="Not awarded",IF(U319="",IF(X319="","No planned date",IF(TODAY()>X319,"Behind — past planned date",IF(X319-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U319,"Behind — award date passed",IF(U319-TODAY()<=30,"At risk — close to off track","On track"))),IF(X319="","No planned date",IF(AND(TODAY()>X319,OR(Z319="",Z319<100)),"Behind — past end date",IF(AND(T319<>"",X319<>"",Z319<>"",(Z319<100),((TODAY()-T319)/MAX(X319-T319,1)*100)-Z319>15),"Behind — progress lag",IF(AND(X319-TODAY()<=30,X319-TODAY()>=0,OR(Z319="",Z319<90)),"At risk — close to off track","On track")))))))) | IF(OR(F319="",AC319="Completed / Handover",AC319="Cancelled"),"",IF(O319="Not awarded",IF(U319<>"",U319-TODAY(),IF(X319="","",X319-TODAY())),IF(X319="","",X319-TODAY()))) | [8 empty] | 2026-08-27 | [5 empty] | IF(OR(F319="",AJ319=""),"",IF(COUNT(AI319:AI319)=0,"",AJ319-LOOKUP(2,1/(AI319:AI319<>""),AI319:AI319))) | IF(OR(F319="",AK319=""),"",IF(COUNT(AI319:AJ319)=0,"",AK319-LOOKUP(2,1/(AI319:AJ319<>""),AI319:AJ319))) | IF(OR(F319="",AL319=""),"",IF(COUNT(AI319:AK319)=0,"",AL319-LOOKUP(2,1/(AI319:AK319<>""),AI319:AK319))) | IF(OR(F319="",AM319=""),"",IF(COUNT(AI319:AL319)=0,"",AM319-LOOKUP(2,1/(AI319:AL319<>""),AI319:AL319))) | IF(OR(F319="",AN319=""),"",IF(COUNT(AI319:AM319)=0,"",AN319-LOOKUP(2,1/(AI319:AM319<>""),AI319:AM319))) | IF(OR(F319="",AO319=""),"",IF(COUNT(AI319:AN319)=0,"",AO319-LOOKUP(2,1/(AI319:AN319<>""),AI319:AN319))) | IF(OR(F319="",AP319=""),"",IF(COUNT(AI319:AO319)=0,"",AP319-LOOKUP(2,1/(AI319:AO319<>""),AI319:AO319))) | IF(OR(F319="",AQ319=""),"",IF(COUNT(AI319:AP319)=0,"",AQ319-LOOKUP(2,1/(AI319:AP319<>""),AI319:AP319))) | IF(OR(F319="",AR319=""),"",IF(COUNT(AI319:AQ319)=0,"",AR319-LOOKUP(2,1/(AI319:AQ319<>""),AI319:AQ319))) | IF(OR(F319="",AS319=""),"",IF(COUNT(AI319:AR319)=0,"",AS319-LOOKUP(2,1/(AI319:AR319<>""),AI319:AR319))) | IF(OR(F319="",AT319=""),"",IF(COUNT(AI319:AS319)=0,"",AT319-LOOKUP(2,1/(AI319:AS319<>""),AI319:AS319))) | IF(OR(F319="",AU319=""),"",IF(COUNT(AI319:AT319)=0,"",AU319-LOOKUP(2,1/(AI319:AT319<>""),AI319:AT319))) | IF(OR(F319="",AV319=""),"",IF(COUNT(AI319:AU319)=0,"",AV319-LOOKUP(2,1/(AI319:AU319<>""),AI319:AU319))) | IF(J319="","All_Provinces",IFERROR(VLOOKUP(J319,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K319="","All_Districts",IFERROR(VLOOKUP(K319,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F320="","",ROW()-3) | AF2-WSM-23 | Package #23-AF2 WSM: Construction of 1,Payazak, 2.Sharak, 3.Khairtot, and 4. Mula Hanifiya Check Dams, located in Shawalikot district of Kandahar province. | 2 of 4 | AF2-WSM-A-047 | Mula Hanifiya Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Shawalikot | Mula Hanifiya | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Afghan Laser Engineering and Construction Company (ALCC) | 057/2026 | 27314.98 | IF(AQ320="","",AQ320) |  | 5 | 2026-02-26 | IF(W320<>"",W320,IF(OR(T320="",V320=""),"",EDATE(T320,V320))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F320="","",IF(COUNT(AI320:AV320)=0,IF(AA320="","Not started",AA320),SUBSTITUTE(LOOKUP(2,1/(AI320:AV320<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F320="",COUNT(AI320:AV320)=0),"",TODAY()-LOOKUP(2,1/(AI320:AV320<>""),AI320:AV320)) | IF(OR(F320="",COUNT(AI320:AV320)<2),"",LOOKUP(2,1/(AI320:AV320<>""),AI320:AV320)-MIN(AI320:AV320)) | IF(OR(AD320="",AC320="Not started",AC320=""),"",IFERROR(AD320-IF(VLOOKUP(AC320,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC320,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F320="","",IF(OR(AA320="Cancelled",AC320="Cancelled"),"Cancelled",IF(OR(AC320="Completed / Handover",Y320<>"",Z320>=100),"Completed — on track",IF(O320="Not awarded",IF(U320="",IF(X320="","No planned date",IF(TODAY()>X320,"Behind — past planned date",IF(X320-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U320,"Behind — award date passed",IF(U320-TODAY()<=30,"At risk — close to off track","On track"))),IF(X320="","No planned date",IF(AND(TODAY()>X320,OR(Z320="",Z320<100)),"Behind — past end date",IF(AND(T320<>"",X320<>"",Z320<>"",(Z320<100),((TODAY()-T320)/MAX(X320-T320,1)*100)-Z320>15),"Behind — progress lag",IF(AND(X320-TODAY()<=30,X320-TODAY()>=0,OR(Z320="",Z320<90)),"At risk — close to off track","On track")))))))) | IF(OR(F320="",AC320="Completed / Handover",AC320="Cancelled"),"",IF(O320="Not awarded",IF(U320<>"",U320-TODAY(),IF(X320="","",X320-TODAY())),IF(X320="","",X320-TODAY()))) | [8 empty] | 2026-08-27 | [5 empty] | IF(OR(F320="",AJ320=""),"",IF(COUNT(AI320:AI320)=0,"",AJ320-LOOKUP(2,1/(AI320:AI320<>""),AI320:AI320))) | IF(OR(F320="",AK320=""),"",IF(COUNT(AI320:AJ320)=0,"",AK320-LOOKUP(2,1/(AI320:AJ320<>""),AI320:AJ320))) | IF(OR(F320="",AL320=""),"",IF(COUNT(AI320:AK320)=0,"",AL320-LOOKUP(2,1/(AI320:AK320<>""),AI320:AK320))) | IF(OR(F320="",AM320=""),"",IF(COUNT(AI320:AL320)=0,"",AM320-LOOKUP(2,1/(AI320:AL320<>""),AI320:AL320))) | IF(OR(F320="",AN320=""),"",IF(COUNT(AI320:AM320)=0,"",AN320-LOOKUP(2,1/(AI320:AM320<>""),AI320:AM320))) | IF(OR(F320="",AO320=""),"",IF(COUNT(AI320:AN320)=0,"",AO320-LOOKUP(2,1/(AI320:AN320<>""),AI320:AN320))) | IF(OR(F320="",AP320=""),"",IF(COUNT(AI320:AO320)=0,"",AP320-LOOKUP(2,1/(AI320:AO320<>""),AI320:AO320))) | IF(OR(F320="",AQ320=""),"",IF(COUNT(AI320:AP320)=0,"",AQ320-LOOKUP(2,1/(AI320:AP320<>""),AI320:AP320))) | IF(OR(F320="",AR320=""),"",IF(COUNT(AI320:AQ320)=0,"",AR320-LOOKUP(2,1/(AI320:AQ320<>""),AI320:AQ320))) | IF(OR(F320="",AS320=""),"",IF(COUNT(AI320:AR320)=0,"",AS320-LOOKUP(2,1/(AI320:AR320<>""),AI320:AR320))) | IF(OR(F320="",AT320=""),"",IF(COUNT(AI320:AS320)=0,"",AT320-LOOKUP(2,1/(AI320:AS320<>""),AI320:AS320))) | IF(OR(F320="",AU320=""),"",IF(COUNT(AI320:AT320)=0,"",AU320-LOOKUP(2,1/(AI320:AT320<>""),AI320:AT320))) | IF(OR(F320="",AV320=""),"",IF(COUNT(AI320:AU320)=0,"",AV320-LOOKUP(2,1/(AI320:AU320<>""),AI320:AU320))) | IF(J320="","All_Provinces",IFERROR(VLOOKUP(J320,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K320="","All_Districts",IFERROR(VLOOKUP(K320,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F321="","",ROW()-3) | AF2-WSM-23 | Package #23-AF2 WSM: Construction of 1,Payazak, 2.Sharak, 3.Khairtot, and 4. Mula Hanifiya Check Dams, located in Shawalikot district of Kandahar province. | 3 of 4 | AF2-WSM-A-048 | Payazak Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Shawalikot | Payazak | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Afghan Laser Engineering and Construction Company (ALCC) | 057/2026 | 28065.1 | IF(AQ321="","",AQ321) |  | 5 | 2026-02-26 | IF(W321<>"",W321,IF(OR(T321="",V321=""),"",EDATE(T321,V321))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F321="","",IF(COUNT(AI321:AV321)=0,IF(AA321="","Not started",AA321),SUBSTITUTE(LOOKUP(2,1/(AI321:AV321<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F321="",COUNT(AI321:AV321)=0),"",TODAY()-LOOKUP(2,1/(AI321:AV321<>""),AI321:AV321)) | IF(OR(F321="",COUNT(AI321:AV321)<2),"",LOOKUP(2,1/(AI321:AV321<>""),AI321:AV321)-MIN(AI321:AV321)) | IF(OR(AD321="",AC321="Not started",AC321=""),"",IFERROR(AD321-IF(VLOOKUP(AC321,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC321,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F321="","",IF(OR(AA321="Cancelled",AC321="Cancelled"),"Cancelled",IF(OR(AC321="Completed / Handover",Y321<>"",Z321>=100),"Completed — on track",IF(O321="Not awarded",IF(U321="",IF(X321="","No planned date",IF(TODAY()>X321,"Behind — past planned date",IF(X321-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U321,"Behind — award date passed",IF(U321-TODAY()<=30,"At risk — close to off track","On track"))),IF(X321="","No planned date",IF(AND(TODAY()>X321,OR(Z321="",Z321<100)),"Behind — past end date",IF(AND(T321<>"",X321<>"",Z321<>"",(Z321<100),((TODAY()-T321)/MAX(X321-T321,1)*100)-Z321>15),"Behind — progress lag",IF(AND(X321-TODAY()<=30,X321-TODAY()>=0,OR(Z321="",Z321<90)),"At risk — close to off track","On track")))))))) | IF(OR(F321="",AC321="Completed / Handover",AC321="Cancelled"),"",IF(O321="Not awarded",IF(U321<>"",U321-TODAY(),IF(X321="","",X321-TODAY())),IF(X321="","",X321-TODAY()))) | [8 empty] | 2026-08-27 | [5 empty] | IF(OR(F321="",AJ321=""),"",IF(COUNT(AI321:AI321)=0,"",AJ321-LOOKUP(2,1/(AI321:AI321<>""),AI321:AI321))) | IF(OR(F321="",AK321=""),"",IF(COUNT(AI321:AJ321)=0,"",AK321-LOOKUP(2,1/(AI321:AJ321<>""),AI321:AJ321))) | IF(OR(F321="",AL321=""),"",IF(COUNT(AI321:AK321)=0,"",AL321-LOOKUP(2,1/(AI321:AK321<>""),AI321:AK321))) | IF(OR(F321="",AM321=""),"",IF(COUNT(AI321:AL321)=0,"",AM321-LOOKUP(2,1/(AI321:AL321<>""),AI321:AL321))) | IF(OR(F321="",AN321=""),"",IF(COUNT(AI321:AM321)=0,"",AN321-LOOKUP(2,1/(AI321:AM321<>""),AI321:AM321))) | IF(OR(F321="",AO321=""),"",IF(COUNT(AI321:AN321)=0,"",AO321-LOOKUP(2,1/(AI321:AN321<>""),AI321:AN321))) | IF(OR(F321="",AP321=""),"",IF(COUNT(AI321:AO321)=0,"",AP321-LOOKUP(2,1/(AI321:AO321<>""),AI321:AO321))) | IF(OR(F321="",AQ321=""),"",IF(COUNT(AI321:AP321)=0,"",AQ321-LOOKUP(2,1/(AI321:AP321<>""),AI321:AP321))) | IF(OR(F321="",AR321=""),"",IF(COUNT(AI321:AQ321)=0,"",AR321-LOOKUP(2,1/(AI321:AQ321<>""),AI321:AQ321))) | IF(OR(F321="",AS321=""),"",IF(COUNT(AI321:AR321)=0,"",AS321-LOOKUP(2,1/(AI321:AR321<>""),AI321:AR321))) | IF(OR(F321="",AT321=""),"",IF(COUNT(AI321:AS321)=0,"",AT321-LOOKUP(2,1/(AI321:AS321<>""),AI321:AS321))) | IF(OR(F321="",AU321=""),"",IF(COUNT(AI321:AT321)=0,"",AU321-LOOKUP(2,1/(AI321:AT321<>""),AI321:AT321))) | IF(OR(F321="",AV321=""),"",IF(COUNT(AI321:AU321)=0,"",AV321-LOOKUP(2,1/(AI321:AU321<>""),AI321:AU321))) | IF(J321="","All_Provinces",IFERROR(VLOOKUP(J321,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K321="","All_Districts",IFERROR(VLOOKUP(K321,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F322="","",ROW()-3) | AF2-WSM-23 | Package #23-AF2 WSM: Construction of 1,Payazak, 2.Sharak, 3.Khairtot, and 4. Mula Hanifiya Check Dams, located in Shawalikot district of Kandahar province. | 4 of 4 | AF2-WSM-A-049 | Sharak Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kandahar | Shawalikot | Sharak | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Afghan Laser Engineering and Construction Company (ALCC) | 057/2026 | 34142.26 | IF(AQ322="","",AQ322) |  | 5 | 2026-02-26 | IF(W322<>"",W322,IF(OR(T322="",V322=""),"",EDATE(T322,V322))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F322="","",IF(COUNT(AI322:AV322)=0,IF(AA322="","Not started",AA322),SUBSTITUTE(LOOKUP(2,1/(AI322:AV322<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F322="",COUNT(AI322:AV322)=0),"",TODAY()-LOOKUP(2,1/(AI322:AV322<>""),AI322:AV322)) | IF(OR(F322="",COUNT(AI322:AV322)<2),"",LOOKUP(2,1/(AI322:AV322<>""),AI322:AV322)-MIN(AI322:AV322)) | IF(OR(AD322="",AC322="Not started",AC322=""),"",IFERROR(AD322-IF(VLOOKUP(AC322,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC322,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F322="","",IF(OR(AA322="Cancelled",AC322="Cancelled"),"Cancelled",IF(OR(AC322="Completed / Handover",Y322<>"",Z322>=100),"Completed — on track",IF(O322="Not awarded",IF(U322="",IF(X322="","No planned date",IF(TODAY()>X322,"Behind — past planned date",IF(X322-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U322,"Behind — award date passed",IF(U322-TODAY()<=30,"At risk — close to off track","On track"))),IF(X322="","No planned date",IF(AND(TODAY()>X322,OR(Z322="",Z322<100)),"Behind — past end date",IF(AND(T322<>"",X322<>"",Z322<>"",(Z322<100),((TODAY()-T322)/MAX(X322-T322,1)*100)-Z322>15),"Behind — progress lag",IF(AND(X322-TODAY()<=30,X322-TODAY()>=0,OR(Z322="",Z322<90)),"At risk — close to off track","On track")))))))) | IF(OR(F322="",AC322="Completed / Handover",AC322="Cancelled"),"",IF(O322="Not awarded",IF(U322<>"",U322-TODAY(),IF(X322="","",X322-TODAY())),IF(X322="","",X322-TODAY()))) | [8 empty] | 2026-08-27 | [5 empty] | IF(OR(F322="",AJ322=""),"",IF(COUNT(AI322:AI322)=0,"",AJ322-LOOKUP(2,1/(AI322:AI322<>""),AI322:AI322))) | IF(OR(F322="",AK322=""),"",IF(COUNT(AI322:AJ322)=0,"",AK322-LOOKUP(2,1/(AI322:AJ322<>""),AI322:AJ322))) | IF(OR(F322="",AL322=""),"",IF(COUNT(AI322:AK322)=0,"",AL322-LOOKUP(2,1/(AI322:AK322<>""),AI322:AK322))) | IF(OR(F322="",AM322=""),"",IF(COUNT(AI322:AL322)=0,"",AM322-LOOKUP(2,1/(AI322:AL322<>""),AI322:AL322))) | IF(OR(F322="",AN322=""),"",IF(COUNT(AI322:AM322)=0,"",AN322-LOOKUP(2,1/(AI322:AM322<>""),AI322:AM322))) | IF(OR(F322="",AO322=""),"",IF(COUNT(AI322:AN322)=0,"",AO322-LOOKUP(2,1/(AI322:AN322<>""),AI322:AN322))) | IF(OR(F322="",AP322=""),"",IF(COUNT(AI322:AO322)=0,"",AP322-LOOKUP(2,1/(AI322:AO322<>""),AI322:AO322))) | IF(OR(F322="",AQ322=""),"",IF(COUNT(AI322:AP322)=0,"",AQ322-LOOKUP(2,1/(AI322:AP322<>""),AI322:AP322))) | IF(OR(F322="",AR322=""),"",IF(COUNT(AI322:AQ322)=0,"",AR322-LOOKUP(2,1/(AI322:AQ322<>""),AI322:AQ322))) | IF(OR(F322="",AS322=""),"",IF(COUNT(AI322:AR322)=0,"",AS322-LOOKUP(2,1/(AI322:AR322<>""),AI322:AR322))) | IF(OR(F322="",AT322=""),"",IF(COUNT(AI322:AS322)=0,"",AT322-LOOKUP(2,1/(AI322:AS322<>""),AI322:AS322))) | IF(OR(F322="",AU322=""),"",IF(COUNT(AI322:AT322)=0,"",AU322-LOOKUP(2,1/(AI322:AT322<>""),AI322:AT322))) | IF(OR(F322="",AV322=""),"",IF(COUNT(AI322:AU322)=0,"",AV322-LOOKUP(2,1/(AI322:AU322<>""),AI322:AU322))) | IF(J322="","All_Provinces",IFERROR(VLOOKUP(J322,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K322="","All_Districts",IFERROR(VLOOKUP(K322,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F323="","",ROW()-3) | AF2-WSM-24 | Package #24-AF2 WSM: Construction of 5 Check dams 1. Kashata Tangi, 2. Forodi, 3. Valary in Nawzad district, 4.Band Khawanin, and 5.Tykhoghi in Washer district of Helmand province. | 1 of 5 | AF2-WSM-N-013 | Band Khawanin check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Washer | Shaposhta Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 125000 | IF(AQ323="","",AQ323) | 2026-12-03 | 5.9 | 2027-06-01 | IF(W323<>"",W323,IF(OR(T323="",V323=""),"",EDATE(T323,V323))) |  |  | Under Design | Technical clearance is expected to receive at first week of November. PR raised and ITB launched by the second week of November and award of contract by the first week of December. Construction period for six months | IF(F323="","",IF(COUNT(AI323:AV323)=0,IF(AA323="","Not started",AA323),SUBSTITUTE(LOOKUP(2,1/(AI323:AV323<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F323="",COUNT(AI323:AV323)=0),"",TODAY()-LOOKUP(2,1/(AI323:AV323<>""),AI323:AV323)) | IF(OR(F323="",COUNT(AI323:AV323)<2),"",LOOKUP(2,1/(AI323:AV323<>""),AI323:AV323)-MIN(AI323:AV323)) | IF(OR(AD323="",AC323="Not started",AC323=""),"",IFERROR(AD323-IF(VLOOKUP(AC323,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC323,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F323="","",IF(OR(AA323="Cancelled",AC323="Cancelled"),"Cancelled",IF(OR(AC323="Completed / Handover",Y323<>"",Z323>=100),"Completed — on track",IF(O323="Not awarded",IF(U323="",IF(X323="","No planned date",IF(TODAY()>X323,"Behind — past planned date",IF(X323-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U323,"Behind — award date passed",IF(U323-TODAY()<=30,"At risk — close to off track","On track"))),IF(X323="","No planned date",IF(AND(TODAY()>X323,OR(Z323="",Z323<100)),"Behind — past end date",IF(AND(T323<>"",X323<>"",Z323<>"",(Z323<100),((TODAY()-T323)/MAX(X323-T323,1)*100)-Z323>15),"Behind — progress lag",IF(AND(X323-TODAY()<=30,X323-TODAY()>=0,OR(Z323="",Z323<90)),"At risk — close to off track","On track")))))))) | IF(OR(F323="",AC323="Completed / Handover",AC323="Cancelled"),"",IF(O323="Not awarded",IF(U323<>"",U323-TODAY(),IF(X323="","",X323-TODAY())),IF(X323="","",X323-TODAY()))) | [14 empty] | IF(OR(F323="",AJ323=""),"",IF(COUNT(AI323:AI323)=0,"",AJ323-LOOKUP(2,1/(AI323:AI323<>""),AI323:AI323))) | IF(OR(F323="",AK323=""),"",IF(COUNT(AI323:AJ323)=0,"",AK323-LOOKUP(2,1/(AI323:AJ323<>""),AI323:AJ323))) | IF(OR(F323="",AL323=""),"",IF(COUNT(AI323:AK323)=0,"",AL323-LOOKUP(2,1/(AI323:AK323<>""),AI323:AK323))) | IF(OR(F323="",AM323=""),"",IF(COUNT(AI323:AL323)=0,"",AM323-LOOKUP(2,1/(AI323:AL323<>""),AI323:AL323))) | IF(OR(F323="",AN323=""),"",IF(COUNT(AI323:AM323)=0,"",AN323-LOOKUP(2,1/(AI323:AM323<>""),AI323:AM323))) | IF(OR(F323="",AO323=""),"",IF(COUNT(AI323:AN323)=0,"",AO323-LOOKUP(2,1/(AI323:AN323<>""),AI323:AN323))) | IF(OR(F323="",AP323=""),"",IF(COUNT(AI323:AO323)=0,"",AP323-LOOKUP(2,1/(AI323:AO323<>""),AI323:AO323))) | IF(OR(F323="",AQ323=""),"",IF(COUNT(AI323:AP323)=0,"",AQ323-LOOKUP(2,1/(AI323:AP323<>""),AI323:AP323))) | IF(OR(F323="",AR323=""),"",IF(COUNT(AI323:AQ323)=0,"",AR323-LOOKUP(2,1/(AI323:AQ323<>""),AI323:AQ323))) | IF(OR(F323="",AS323=""),"",IF(COUNT(AI323:AR323)=0,"",AS323-LOOKUP(2,1/(AI323:AR323<>""),AI323:AR323))) | IF(OR(F323="",AT323=""),"",IF(COUNT(AI323:AS323)=0,"",AT323-LOOKUP(2,1/(AI323:AS323<>""),AI323:AS323))) | IF(OR(F323="",AU323=""),"",IF(COUNT(AI323:AT323)=0,"",AU323-LOOKUP(2,1/(AI323:AT323<>""),AI323:AT323))) | IF(OR(F323="",AV323=""),"",IF(COUNT(AI323:AU323)=0,"",AV323-LOOKUP(2,1/(AI323:AU323<>""),AI323:AU323))) | IF(J323="","All_Provinces",IFERROR(VLOOKUP(J323,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K323="","All_Districts",IFERROR(VLOOKUP(K323,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F324="","",ROW()-3) | AF2-WSM-24 | Package #24-AF2 WSM: Construction of 5 Check dams 1. Kashata Tangi, 2. Forodi, 3. Valary in Nawzad district, 4.Band Khawanin, and 5.Tykhoghi in Washer district of Helmand province. | 2 of 5 | AF2-WSM-N-014 | Forodi Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Nawzad | Zoroji Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 125000 | IF(AQ324="","",AQ324) | 2026-12-03 | 5.9 | 2027-06-01 | IF(W324<>"",W324,IF(OR(T324="",V324=""),"",EDATE(T324,V324))) |  |  | Under Design | Technical clearance is expected to receive at first week of November. PR raised and ITB launched by the second week of November and award of contract by the first week of December. Construction period for six months | IF(F324="","",IF(COUNT(AI324:AV324)=0,IF(AA324="","Not started",AA324),SUBSTITUTE(LOOKUP(2,1/(AI324:AV324<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F324="",COUNT(AI324:AV324)=0),"",TODAY()-LOOKUP(2,1/(AI324:AV324<>""),AI324:AV324)) | IF(OR(F324="",COUNT(AI324:AV324)<2),"",LOOKUP(2,1/(AI324:AV324<>""),AI324:AV324)-MIN(AI324:AV324)) | IF(OR(AD324="",AC324="Not started",AC324=""),"",IFERROR(AD324-IF(VLOOKUP(AC324,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC324,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F324="","",IF(OR(AA324="Cancelled",AC324="Cancelled"),"Cancelled",IF(OR(AC324="Completed / Handover",Y324<>"",Z324>=100),"Completed — on track",IF(O324="Not awarded",IF(U324="",IF(X324="","No planned date",IF(TODAY()>X324,"Behind — past planned date",IF(X324-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U324,"Behind — award date passed",IF(U324-TODAY()<=30,"At risk — close to off track","On track"))),IF(X324="","No planned date",IF(AND(TODAY()>X324,OR(Z324="",Z324<100)),"Behind — past end date",IF(AND(T324<>"",X324<>"",Z324<>"",(Z324<100),((TODAY()-T324)/MAX(X324-T324,1)*100)-Z324>15),"Behind — progress lag",IF(AND(X324-TODAY()<=30,X324-TODAY()>=0,OR(Z324="",Z324<90)),"At risk — close to off track","On track")))))))) | IF(OR(F324="",AC324="Completed / Handover",AC324="Cancelled"),"",IF(O324="Not awarded",IF(U324<>"",U324-TODAY(),IF(X324="","",X324-TODAY())),IF(X324="","",X324-TODAY()))) | [14 empty] | IF(OR(F324="",AJ324=""),"",IF(COUNT(AI324:AI324)=0,"",AJ324-LOOKUP(2,1/(AI324:AI324<>""),AI324:AI324))) | IF(OR(F324="",AK324=""),"",IF(COUNT(AI324:AJ324)=0,"",AK324-LOOKUP(2,1/(AI324:AJ324<>""),AI324:AJ324))) | IF(OR(F324="",AL324=""),"",IF(COUNT(AI324:AK324)=0,"",AL324-LOOKUP(2,1/(AI324:AK324<>""),AI324:AK324))) | IF(OR(F324="",AM324=""),"",IF(COUNT(AI324:AL324)=0,"",AM324-LOOKUP(2,1/(AI324:AL324<>""),AI324:AL324))) | IF(OR(F324="",AN324=""),"",IF(COUNT(AI324:AM324)=0,"",AN324-LOOKUP(2,1/(AI324:AM324<>""),AI324:AM324))) | IF(OR(F324="",AO324=""),"",IF(COUNT(AI324:AN324)=0,"",AO324-LOOKUP(2,1/(AI324:AN324<>""),AI324:AN324))) | IF(OR(F324="",AP324=""),"",IF(COUNT(AI324:AO324)=0,"",AP324-LOOKUP(2,1/(AI324:AO324<>""),AI324:AO324))) | IF(OR(F324="",AQ324=""),"",IF(COUNT(AI324:AP324)=0,"",AQ324-LOOKUP(2,1/(AI324:AP324<>""),AI324:AP324))) | IF(OR(F324="",AR324=""),"",IF(COUNT(AI324:AQ324)=0,"",AR324-LOOKUP(2,1/(AI324:AQ324<>""),AI324:AQ324))) | IF(OR(F324="",AS324=""),"",IF(COUNT(AI324:AR324)=0,"",AS324-LOOKUP(2,1/(AI324:AR324<>""),AI324:AR324))) | IF(OR(F324="",AT324=""),"",IF(COUNT(AI324:AS324)=0,"",AT324-LOOKUP(2,1/(AI324:AS324<>""),AI324:AS324))) | IF(OR(F324="",AU324=""),"",IF(COUNT(AI324:AT324)=0,"",AU324-LOOKUP(2,1/(AI324:AT324<>""),AI324:AT324))) | IF(OR(F324="",AV324=""),"",IF(COUNT(AI324:AU324)=0,"",AV324-LOOKUP(2,1/(AI324:AU324<>""),AI324:AU324))) | IF(J324="","All_Provinces",IFERROR(VLOOKUP(J324,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K324="","All_Districts",IFERROR(VLOOKUP(K324,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F325="","",ROW()-3) | AF2-WSM-24 | Package #24-AF2 WSM: Construction of 5 Check dams 1. Kashata Tangi, 2. Forodi, 3. Valary in Nawzad district, 4.Band Khawanin, and 5.Tykhoghi in Washer district of Helmand province. | 3 of 5 | AF2-WSM-N-015 | Kashata Tangi Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Nawzad | Kashata Tangi Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 125000 | IF(AQ325="","",AQ325) | 2026-12-03 | 5.9 | 2027-06-01 | IF(W325<>"",W325,IF(OR(T325="",V325=""),"",EDATE(T325,V325))) |  |  | Under Design | Technical clearance is expected to receive at first week of November. PR raised and ITB launched by the second week of November and award of contract by the first week of December. Construction period for six months | IF(F325="","",IF(COUNT(AI325:AV325)=0,IF(AA325="","Not started",AA325),SUBSTITUTE(LOOKUP(2,1/(AI325:AV325<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F325="",COUNT(AI325:AV325)=0),"",TODAY()-LOOKUP(2,1/(AI325:AV325<>""),AI325:AV325)) | IF(OR(F325="",COUNT(AI325:AV325)<2),"",LOOKUP(2,1/(AI325:AV325<>""),AI325:AV325)-MIN(AI325:AV325)) | IF(OR(AD325="",AC325="Not started",AC325=""),"",IFERROR(AD325-IF(VLOOKUP(AC325,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC325,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F325="","",IF(OR(AA325="Cancelled",AC325="Cancelled"),"Cancelled",IF(OR(AC325="Completed / Handover",Y325<>"",Z325>=100),"Completed — on track",IF(O325="Not awarded",IF(U325="",IF(X325="","No planned date",IF(TODAY()>X325,"Behind — past planned date",IF(X325-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U325,"Behind — award date passed",IF(U325-TODAY()<=30,"At risk — close to off track","On track"))),IF(X325="","No planned date",IF(AND(TODAY()>X325,OR(Z325="",Z325<100)),"Behind — past end date",IF(AND(T325<>"",X325<>"",Z325<>"",(Z325<100),((TODAY()-T325)/MAX(X325-T325,1)*100)-Z325>15),"Behind — progress lag",IF(AND(X325-TODAY()<=30,X325-TODAY()>=0,OR(Z325="",Z325<90)),"At risk — close to off track","On track")))))))) | IF(OR(F325="",AC325="Completed / Handover",AC325="Cancelled"),"",IF(O325="Not awarded",IF(U325<>"",U325-TODAY(),IF(X325="","",X325-TODAY())),IF(X325="","",X325-TODAY()))) | [14 empty] | IF(OR(F325="",AJ325=""),"",IF(COUNT(AI325:AI325)=0,"",AJ325-LOOKUP(2,1/(AI325:AI325<>""),AI325:AI325))) | IF(OR(F325="",AK325=""),"",IF(COUNT(AI325:AJ325)=0,"",AK325-LOOKUP(2,1/(AI325:AJ325<>""),AI325:AJ325))) | IF(OR(F325="",AL325=""),"",IF(COUNT(AI325:AK325)=0,"",AL325-LOOKUP(2,1/(AI325:AK325<>""),AI325:AK325))) | IF(OR(F325="",AM325=""),"",IF(COUNT(AI325:AL325)=0,"",AM325-LOOKUP(2,1/(AI325:AL325<>""),AI325:AL325))) | IF(OR(F325="",AN325=""),"",IF(COUNT(AI325:AM325)=0,"",AN325-LOOKUP(2,1/(AI325:AM325<>""),AI325:AM325))) | IF(OR(F325="",AO325=""),"",IF(COUNT(AI325:AN325)=0,"",AO325-LOOKUP(2,1/(AI325:AN325<>""),AI325:AN325))) | IF(OR(F325="",AP325=""),"",IF(COUNT(AI325:AO325)=0,"",AP325-LOOKUP(2,1/(AI325:AO325<>""),AI325:AO325))) | IF(OR(F325="",AQ325=""),"",IF(COUNT(AI325:AP325)=0,"",AQ325-LOOKUP(2,1/(AI325:AP325<>""),AI325:AP325))) | IF(OR(F325="",AR325=""),"",IF(COUNT(AI325:AQ325)=0,"",AR325-LOOKUP(2,1/(AI325:AQ325<>""),AI325:AQ325))) | IF(OR(F325="",AS325=""),"",IF(COUNT(AI325:AR325)=0,"",AS325-LOOKUP(2,1/(AI325:AR325<>""),AI325:AR325))) | IF(OR(F325="",AT325=""),"",IF(COUNT(AI325:AS325)=0,"",AT325-LOOKUP(2,1/(AI325:AS325<>""),AI325:AS325))) | IF(OR(F325="",AU325=""),"",IF(COUNT(AI325:AT325)=0,"",AU325-LOOKUP(2,1/(AI325:AT325<>""),AI325:AT325))) | IF(OR(F325="",AV325=""),"",IF(COUNT(AI325:AU325)=0,"",AV325-LOOKUP(2,1/(AI325:AU325<>""),AI325:AU325))) | IF(J325="","All_Provinces",IFERROR(VLOOKUP(J325,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K325="","All_Districts",IFERROR(VLOOKUP(K325,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F326="","",ROW()-3) | AF2-WSM-24 | Package #24-AF2 WSM: Construction of 5 Check dams 1. Kashata Tangi, 2. Forodi, 3. Valary in Nawzad district, 4.Band Khawanin, and 5.Tykhoghi in Washer district of Helmand province. | 4 of 5 | AF2-WSM-N-016 | Tykhoghi Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Washer | Koshki Spid Villag | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 125000 | IF(AQ326="","",AQ326) | 2026-12-03 | 5.9 | 2027-06-01 | IF(W326<>"",W326,IF(OR(T326="",V326=""),"",EDATE(T326,V326))) |  |  | Under Design | Technical clearance is expected to receive at first week of November. PR raised and ITB launched by the second week of November and award of contract by the first week of December. Construction period for six months | IF(F326="","",IF(COUNT(AI326:AV326)=0,IF(AA326="","Not started",AA326),SUBSTITUTE(LOOKUP(2,1/(AI326:AV326<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F326="",COUNT(AI326:AV326)=0),"",TODAY()-LOOKUP(2,1/(AI326:AV326<>""),AI326:AV326)) | IF(OR(F326="",COUNT(AI326:AV326)<2),"",LOOKUP(2,1/(AI326:AV326<>""),AI326:AV326)-MIN(AI326:AV326)) | IF(OR(AD326="",AC326="Not started",AC326=""),"",IFERROR(AD326-IF(VLOOKUP(AC326,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC326,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F326="","",IF(OR(AA326="Cancelled",AC326="Cancelled"),"Cancelled",IF(OR(AC326="Completed / Handover",Y326<>"",Z326>=100),"Completed — on track",IF(O326="Not awarded",IF(U326="",IF(X326="","No planned date",IF(TODAY()>X326,"Behind — past planned date",IF(X326-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U326,"Behind — award date passed",IF(U326-TODAY()<=30,"At risk — close to off track","On track"))),IF(X326="","No planned date",IF(AND(TODAY()>X326,OR(Z326="",Z326<100)),"Behind — past end date",IF(AND(T326<>"",X326<>"",Z326<>"",(Z326<100),((TODAY()-T326)/MAX(X326-T326,1)*100)-Z326>15),"Behind — progress lag",IF(AND(X326-TODAY()<=30,X326-TODAY()>=0,OR(Z326="",Z326<90)),"At risk — close to off track","On track")))))))) | IF(OR(F326="",AC326="Completed / Handover",AC326="Cancelled"),"",IF(O326="Not awarded",IF(U326<>"",U326-TODAY(),IF(X326="","",X326-TODAY())),IF(X326="","",X326-TODAY()))) | [14 empty] | IF(OR(F326="",AJ326=""),"",IF(COUNT(AI326:AI326)=0,"",AJ326-LOOKUP(2,1/(AI326:AI326<>""),AI326:AI326))) | IF(OR(F326="",AK326=""),"",IF(COUNT(AI326:AJ326)=0,"",AK326-LOOKUP(2,1/(AI326:AJ326<>""),AI326:AJ326))) | IF(OR(F326="",AL326=""),"",IF(COUNT(AI326:AK326)=0,"",AL326-LOOKUP(2,1/(AI326:AK326<>""),AI326:AK326))) | IF(OR(F326="",AM326=""),"",IF(COUNT(AI326:AL326)=0,"",AM326-LOOKUP(2,1/(AI326:AL326<>""),AI326:AL326))) | IF(OR(F326="",AN326=""),"",IF(COUNT(AI326:AM326)=0,"",AN326-LOOKUP(2,1/(AI326:AM326<>""),AI326:AM326))) | IF(OR(F326="",AO326=""),"",IF(COUNT(AI326:AN326)=0,"",AO326-LOOKUP(2,1/(AI326:AN326<>""),AI326:AN326))) | IF(OR(F326="",AP326=""),"",IF(COUNT(AI326:AO326)=0,"",AP326-LOOKUP(2,1/(AI326:AO326<>""),AI326:AO326))) | IF(OR(F326="",AQ326=""),"",IF(COUNT(AI326:AP326)=0,"",AQ326-LOOKUP(2,1/(AI326:AP326<>""),AI326:AP326))) | IF(OR(F326="",AR326=""),"",IF(COUNT(AI326:AQ326)=0,"",AR326-LOOKUP(2,1/(AI326:AQ326<>""),AI326:AQ326))) | IF(OR(F326="",AS326=""),"",IF(COUNT(AI326:AR326)=0,"",AS326-LOOKUP(2,1/(AI326:AR326<>""),AI326:AR326))) | IF(OR(F326="",AT326=""),"",IF(COUNT(AI326:AS326)=0,"",AT326-LOOKUP(2,1/(AI326:AS326<>""),AI326:AS326))) | IF(OR(F326="",AU326=""),"",IF(COUNT(AI326:AT326)=0,"",AU326-LOOKUP(2,1/(AI326:AT326<>""),AI326:AT326))) | IF(OR(F326="",AV326=""),"",IF(COUNT(AI326:AU326)=0,"",AV326-LOOKUP(2,1/(AI326:AU326<>""),AI326:AU326))) | IF(J326="","All_Provinces",IFERROR(VLOOKUP(J326,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K326="","All_Districts",IFERROR(VLOOKUP(K326,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F327="","",ROW()-3) | AF2-WSM-24 | Package #24-AF2 WSM: Construction of 5 Check dams 1. Kashata Tangi, 2. Forodi, 3. Valary in Nawzad district, 4.Band Khawanin, and 5.Tykhoghi in Washer district of Helmand province. | 5 of 5 | AF2-WSM-N-017 | Valary Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Helmand | Nawzad | Valary village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 125000 | IF(AQ327="","",AQ327) | 2026-12-03 | 5.9 | 2027-06-01 | IF(W327<>"",W327,IF(OR(T327="",V327=""),"",EDATE(T327,V327))) |  |  | Under Design | Technical clearance is expected to receive at first week of November. PR raised and ITB launched by the second week of November and award of contract by the first week of December. Construction period for six months | IF(F327="","",IF(COUNT(AI327:AV327)=0,IF(AA327="","Not started",AA327),SUBSTITUTE(LOOKUP(2,1/(AI327:AV327<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F327="",COUNT(AI327:AV327)=0),"",TODAY()-LOOKUP(2,1/(AI327:AV327<>""),AI327:AV327)) | IF(OR(F327="",COUNT(AI327:AV327)<2),"",LOOKUP(2,1/(AI327:AV327<>""),AI327:AV327)-MIN(AI327:AV327)) | IF(OR(AD327="",AC327="Not started",AC327=""),"",IFERROR(AD327-IF(VLOOKUP(AC327,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC327,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F327="","",IF(OR(AA327="Cancelled",AC327="Cancelled"),"Cancelled",IF(OR(AC327="Completed / Handover",Y327<>"",Z327>=100),"Completed — on track",IF(O327="Not awarded",IF(U327="",IF(X327="","No planned date",IF(TODAY()>X327,"Behind — past planned date",IF(X327-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U327,"Behind — award date passed",IF(U327-TODAY()<=30,"At risk — close to off track","On track"))),IF(X327="","No planned date",IF(AND(TODAY()>X327,OR(Z327="",Z327<100)),"Behind — past end date",IF(AND(T327<>"",X327<>"",Z327<>"",(Z327<100),((TODAY()-T327)/MAX(X327-T327,1)*100)-Z327>15),"Behind — progress lag",IF(AND(X327-TODAY()<=30,X327-TODAY()>=0,OR(Z327="",Z327<90)),"At risk — close to off track","On track")))))))) | IF(OR(F327="",AC327="Completed / Handover",AC327="Cancelled"),"",IF(O327="Not awarded",IF(U327<>"",U327-TODAY(),IF(X327="","",X327-TODAY())),IF(X327="","",X327-TODAY()))) | [14 empty] | IF(OR(F327="",AJ327=""),"",IF(COUNT(AI327:AI327)=0,"",AJ327-LOOKUP(2,1/(AI327:AI327<>""),AI327:AI327))) | IF(OR(F327="",AK327=""),"",IF(COUNT(AI327:AJ327)=0,"",AK327-LOOKUP(2,1/(AI327:AJ327<>""),AI327:AJ327))) | IF(OR(F327="",AL327=""),"",IF(COUNT(AI327:AK327)=0,"",AL327-LOOKUP(2,1/(AI327:AK327<>""),AI327:AK327))) | IF(OR(F327="",AM327=""),"",IF(COUNT(AI327:AL327)=0,"",AM327-LOOKUP(2,1/(AI327:AL327<>""),AI327:AL327))) | IF(OR(F327="",AN327=""),"",IF(COUNT(AI327:AM327)=0,"",AN327-LOOKUP(2,1/(AI327:AM327<>""),AI327:AM327))) | IF(OR(F327="",AO327=""),"",IF(COUNT(AI327:AN327)=0,"",AO327-LOOKUP(2,1/(AI327:AN327<>""),AI327:AN327))) | IF(OR(F327="",AP327=""),"",IF(COUNT(AI327:AO327)=0,"",AP327-LOOKUP(2,1/(AI327:AO327<>""),AI327:AO327))) | IF(OR(F327="",AQ327=""),"",IF(COUNT(AI327:AP327)=0,"",AQ327-LOOKUP(2,1/(AI327:AP327<>""),AI327:AP327))) | IF(OR(F327="",AR327=""),"",IF(COUNT(AI327:AQ327)=0,"",AR327-LOOKUP(2,1/(AI327:AQ327<>""),AI327:AQ327))) | IF(OR(F327="",AS327=""),"",IF(COUNT(AI327:AR327)=0,"",AS327-LOOKUP(2,1/(AI327:AR327<>""),AI327:AR327))) | IF(OR(F327="",AT327=""),"",IF(COUNT(AI327:AS327)=0,"",AT327-LOOKUP(2,1/(AI327:AS327<>""),AI327:AS327))) | IF(OR(F327="",AU327=""),"",IF(COUNT(AI327:AT327)=0,"",AU327-LOOKUP(2,1/(AI327:AT327<>""),AI327:AT327))) | IF(OR(F327="",AV327=""),"",IF(COUNT(AI327:AU327)=0,"",AV327-LOOKUP(2,1/(AI327:AU327<>""),AI327:AU327))) | IF(J327="","All_Provinces",IFERROR(VLOOKUP(J327,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K327="","All_Districts",IFERROR(VLOOKUP(K327,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F328="","",ROW()-3) | AF2-WSM-25 | Package #25-AF2 WSM: Construction of Qali Gaz, Ghobana, and Nawi Kach Check dams, located in Mizana district of Zabul province. | 1 of 3 | AF2-WSM-N-018 | Ghobana Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Zabul | Mizana | Takhom Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 97679 | IF(AQ328="","",AQ328) | 2026-11-25 | 6.9 | 2027-06-23 | IF(W328<>"",W328,IF(OR(T328="",V328=""),"",EDATE(T328,V328))) |  |  | PR to be Raised | Construction period seven months including slack period. | IF(F328="","",IF(COUNT(AI328:AV328)=0,IF(AA328="","Not started",AA328),SUBSTITUTE(LOOKUP(2,1/(AI328:AV328<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F328="",COUNT(AI328:AV328)=0),"",TODAY()-LOOKUP(2,1/(AI328:AV328<>""),AI328:AV328)) | IF(OR(F328="",COUNT(AI328:AV328)<2),"",LOOKUP(2,1/(AI328:AV328<>""),AI328:AV328)-MIN(AI328:AV328)) | IF(OR(AD328="",AC328="Not started",AC328=""),"",IFERROR(AD328-IF(VLOOKUP(AC328,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC328,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F328="","",IF(OR(AA328="Cancelled",AC328="Cancelled"),"Cancelled",IF(OR(AC328="Completed / Handover",Y328<>"",Z328>=100),"Completed — on track",IF(O328="Not awarded",IF(U328="",IF(X328="","No planned date",IF(TODAY()>X328,"Behind — past planned date",IF(X328-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U328,"Behind — award date passed",IF(U328-TODAY()<=30,"At risk — close to off track","On track"))),IF(X328="","No planned date",IF(AND(TODAY()>X328,OR(Z328="",Z328<100)),"Behind — past end date",IF(AND(T328<>"",X328<>"",Z328<>"",(Z328<100),((TODAY()-T328)/MAX(X328-T328,1)*100)-Z328>15),"Behind — progress lag",IF(AND(X328-TODAY()<=30,X328-TODAY()>=0,OR(Z328="",Z328<90)),"At risk — close to off track","On track")))))))) | IF(OR(F328="",AC328="Completed / Handover",AC328="Cancelled"),"",IF(O328="Not awarded",IF(U328<>"",U328-TODAY(),IF(X328="","",X328-TODAY())),IF(X328="","",X328-TODAY()))) | [14 empty] | IF(OR(F328="",AJ328=""),"",IF(COUNT(AI328:AI328)=0,"",AJ328-LOOKUP(2,1/(AI328:AI328<>""),AI328:AI328))) | IF(OR(F328="",AK328=""),"",IF(COUNT(AI328:AJ328)=0,"",AK328-LOOKUP(2,1/(AI328:AJ328<>""),AI328:AJ328))) | IF(OR(F328="",AL328=""),"",IF(COUNT(AI328:AK328)=0,"",AL328-LOOKUP(2,1/(AI328:AK328<>""),AI328:AK328))) | IF(OR(F328="",AM328=""),"",IF(COUNT(AI328:AL328)=0,"",AM328-LOOKUP(2,1/(AI328:AL328<>""),AI328:AL328))) | IF(OR(F328="",AN328=""),"",IF(COUNT(AI328:AM328)=0,"",AN328-LOOKUP(2,1/(AI328:AM328<>""),AI328:AM328))) | IF(OR(F328="",AO328=""),"",IF(COUNT(AI328:AN328)=0,"",AO328-LOOKUP(2,1/(AI328:AN328<>""),AI328:AN328))) | IF(OR(F328="",AP328=""),"",IF(COUNT(AI328:AO328)=0,"",AP328-LOOKUP(2,1/(AI328:AO328<>""),AI328:AO328))) | IF(OR(F328="",AQ328=""),"",IF(COUNT(AI328:AP328)=0,"",AQ328-LOOKUP(2,1/(AI328:AP328<>""),AI328:AP328))) | IF(OR(F328="",AR328=""),"",IF(COUNT(AI328:AQ328)=0,"",AR328-LOOKUP(2,1/(AI328:AQ328<>""),AI328:AQ328))) | IF(OR(F328="",AS328=""),"",IF(COUNT(AI328:AR328)=0,"",AS328-LOOKUP(2,1/(AI328:AR328<>""),AI328:AR328))) | IF(OR(F328="",AT328=""),"",IF(COUNT(AI328:AS328)=0,"",AT328-LOOKUP(2,1/(AI328:AS328<>""),AI328:AS328))) | IF(OR(F328="",AU328=""),"",IF(COUNT(AI328:AT328)=0,"",AU328-LOOKUP(2,1/(AI328:AT328<>""),AI328:AT328))) | IF(OR(F328="",AV328=""),"",IF(COUNT(AI328:AU328)=0,"",AV328-LOOKUP(2,1/(AI328:AU328<>""),AI328:AU328))) | IF(J328="","All_Provinces",IFERROR(VLOOKUP(J328,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K328="","All_Districts",IFERROR(VLOOKUP(K328,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F329="","",ROW()-3) | AF2-WSM-25 | Package #25-AF2 WSM: Construction of Qali Gaz, Ghobana, and Nawi Kach Check dams, located in Mizana district of Zabul province. | 2 of 3 | AF2-WSM-N-019 | Nawi Kach Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Zabul | Mizana | Landi Nawa Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 97679 | IF(AQ329="","",AQ329) | 2026-11-25 | 6.9 | 2027-06-23 | IF(W329<>"",W329,IF(OR(T329="",V329=""),"",EDATE(T329,V329))) |  |  | PR to be Raised | Construction period seven months including slack period. | IF(F329="","",IF(COUNT(AI329:AV329)=0,IF(AA329="","Not started",AA329),SUBSTITUTE(LOOKUP(2,1/(AI329:AV329<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F329="",COUNT(AI329:AV329)=0),"",TODAY()-LOOKUP(2,1/(AI329:AV329<>""),AI329:AV329)) | IF(OR(F329="",COUNT(AI329:AV329)<2),"",LOOKUP(2,1/(AI329:AV329<>""),AI329:AV329)-MIN(AI329:AV329)) | IF(OR(AD329="",AC329="Not started",AC329=""),"",IFERROR(AD329-IF(VLOOKUP(AC329,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC329,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F329="","",IF(OR(AA329="Cancelled",AC329="Cancelled"),"Cancelled",IF(OR(AC329="Completed / Handover",Y329<>"",Z329>=100),"Completed — on track",IF(O329="Not awarded",IF(U329="",IF(X329="","No planned date",IF(TODAY()>X329,"Behind — past planned date",IF(X329-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U329,"Behind — award date passed",IF(U329-TODAY()<=30,"At risk — close to off track","On track"))),IF(X329="","No planned date",IF(AND(TODAY()>X329,OR(Z329="",Z329<100)),"Behind — past end date",IF(AND(T329<>"",X329<>"",Z329<>"",(Z329<100),((TODAY()-T329)/MAX(X329-T329,1)*100)-Z329>15),"Behind — progress lag",IF(AND(X329-TODAY()<=30,X329-TODAY()>=0,OR(Z329="",Z329<90)),"At risk — close to off track","On track")))))))) | IF(OR(F329="",AC329="Completed / Handover",AC329="Cancelled"),"",IF(O329="Not awarded",IF(U329<>"",U329-TODAY(),IF(X329="","",X329-TODAY())),IF(X329="","",X329-TODAY()))) | [14 empty] | IF(OR(F329="",AJ329=""),"",IF(COUNT(AI329:AI329)=0,"",AJ329-LOOKUP(2,1/(AI329:AI329<>""),AI329:AI329))) | IF(OR(F329="",AK329=""),"",IF(COUNT(AI329:AJ329)=0,"",AK329-LOOKUP(2,1/(AI329:AJ329<>""),AI329:AJ329))) | IF(OR(F329="",AL329=""),"",IF(COUNT(AI329:AK329)=0,"",AL329-LOOKUP(2,1/(AI329:AK329<>""),AI329:AK329))) | IF(OR(F329="",AM329=""),"",IF(COUNT(AI329:AL329)=0,"",AM329-LOOKUP(2,1/(AI329:AL329<>""),AI329:AL329))) | IF(OR(F329="",AN329=""),"",IF(COUNT(AI329:AM329)=0,"",AN329-LOOKUP(2,1/(AI329:AM329<>""),AI329:AM329))) | IF(OR(F329="",AO329=""),"",IF(COUNT(AI329:AN329)=0,"",AO329-LOOKUP(2,1/(AI329:AN329<>""),AI329:AN329))) | IF(OR(F329="",AP329=""),"",IF(COUNT(AI329:AO329)=0,"",AP329-LOOKUP(2,1/(AI329:AO329<>""),AI329:AO329))) | IF(OR(F329="",AQ329=""),"",IF(COUNT(AI329:AP329)=0,"",AQ329-LOOKUP(2,1/(AI329:AP329<>""),AI329:AP329))) | IF(OR(F329="",AR329=""),"",IF(COUNT(AI329:AQ329)=0,"",AR329-LOOKUP(2,1/(AI329:AQ329<>""),AI329:AQ329))) | IF(OR(F329="",AS329=""),"",IF(COUNT(AI329:AR329)=0,"",AS329-LOOKUP(2,1/(AI329:AR329<>""),AI329:AR329))) | IF(OR(F329="",AT329=""),"",IF(COUNT(AI329:AS329)=0,"",AT329-LOOKUP(2,1/(AI329:AS329<>""),AI329:AS329))) | IF(OR(F329="",AU329=""),"",IF(COUNT(AI329:AT329)=0,"",AU329-LOOKUP(2,1/(AI329:AT329<>""),AI329:AT329))) | IF(OR(F329="",AV329=""),"",IF(COUNT(AI329:AU329)=0,"",AV329-LOOKUP(2,1/(AI329:AU329<>""),AI329:AU329))) | IF(J329="","All_Provinces",IFERROR(VLOOKUP(J329,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K329="","All_Districts",IFERROR(VLOOKUP(K329,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F330="","",ROW()-3) | AF2-WSM-25 | Package #25-AF2 WSM: Construction of Qali Gaz, Ghobana, and Nawi Kach Check dams, located in Mizana district of Zabul province. | 3 of 3 | AF2-WSM-N-020 | Qali Gaz Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Zabul | Mizana | Qali Gaz Village | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 97679 | IF(AQ330="","",AQ330) | 2026-11-25 | 6.9 | 2027-06-23 | IF(W330<>"",W330,IF(OR(T330="",V330=""),"",EDATE(T330,V330))) |  |  | PR to be Raised | Construction period seven months including slack period. | IF(F330="","",IF(COUNT(AI330:AV330)=0,IF(AA330="","Not started",AA330),SUBSTITUTE(LOOKUP(2,1/(AI330:AV330<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F330="",COUNT(AI330:AV330)=0),"",TODAY()-LOOKUP(2,1/(AI330:AV330<>""),AI330:AV330)) | IF(OR(F330="",COUNT(AI330:AV330)<2),"",LOOKUP(2,1/(AI330:AV330<>""),AI330:AV330)-MIN(AI330:AV330)) | IF(OR(AD330="",AC330="Not started",AC330=""),"",IFERROR(AD330-IF(VLOOKUP(AC330,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC330,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F330="","",IF(OR(AA330="Cancelled",AC330="Cancelled"),"Cancelled",IF(OR(AC330="Completed / Handover",Y330<>"",Z330>=100),"Completed — on track",IF(O330="Not awarded",IF(U330="",IF(X330="","No planned date",IF(TODAY()>X330,"Behind — past planned date",IF(X330-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U330,"Behind — award date passed",IF(U330-TODAY()<=30,"At risk — close to off track","On track"))),IF(X330="","No planned date",IF(AND(TODAY()>X330,OR(Z330="",Z330<100)),"Behind — past end date",IF(AND(T330<>"",X330<>"",Z330<>"",(Z330<100),((TODAY()-T330)/MAX(X330-T330,1)*100)-Z330>15),"Behind — progress lag",IF(AND(X330-TODAY()<=30,X330-TODAY()>=0,OR(Z330="",Z330<90)),"At risk — close to off track","On track")))))))) | IF(OR(F330="",AC330="Completed / Handover",AC330="Cancelled"),"",IF(O330="Not awarded",IF(U330<>"",U330-TODAY(),IF(X330="","",X330-TODAY())),IF(X330="","",X330-TODAY()))) | [14 empty] | IF(OR(F330="",AJ330=""),"",IF(COUNT(AI330:AI330)=0,"",AJ330-LOOKUP(2,1/(AI330:AI330<>""),AI330:AI330))) | IF(OR(F330="",AK330=""),"",IF(COUNT(AI330:AJ330)=0,"",AK330-LOOKUP(2,1/(AI330:AJ330<>""),AI330:AJ330))) | IF(OR(F330="",AL330=""),"",IF(COUNT(AI330:AK330)=0,"",AL330-LOOKUP(2,1/(AI330:AK330<>""),AI330:AK330))) | IF(OR(F330="",AM330=""),"",IF(COUNT(AI330:AL330)=0,"",AM330-LOOKUP(2,1/(AI330:AL330<>""),AI330:AL330))) | IF(OR(F330="",AN330=""),"",IF(COUNT(AI330:AM330)=0,"",AN330-LOOKUP(2,1/(AI330:AM330<>""),AI330:AM330))) | IF(OR(F330="",AO330=""),"",IF(COUNT(AI330:AN330)=0,"",AO330-LOOKUP(2,1/(AI330:AN330<>""),AI330:AN330))) | IF(OR(F330="",AP330=""),"",IF(COUNT(AI330:AO330)=0,"",AP330-LOOKUP(2,1/(AI330:AO330<>""),AI330:AO330))) | IF(OR(F330="",AQ330=""),"",IF(COUNT(AI330:AP330)=0,"",AQ330-LOOKUP(2,1/(AI330:AP330<>""),AI330:AP330))) | IF(OR(F330="",AR330=""),"",IF(COUNT(AI330:AQ330)=0,"",AR330-LOOKUP(2,1/(AI330:AQ330<>""),AI330:AQ330))) | IF(OR(F330="",AS330=""),"",IF(COUNT(AI330:AR330)=0,"",AS330-LOOKUP(2,1/(AI330:AR330<>""),AI330:AR330))) | IF(OR(F330="",AT330=""),"",IF(COUNT(AI330:AS330)=0,"",AT330-LOOKUP(2,1/(AI330:AS330<>""),AI330:AS330))) | IF(OR(F330="",AU330=""),"",IF(COUNT(AI330:AT330)=0,"",AU330-LOOKUP(2,1/(AI330:AT330<>""),AI330:AT330))) | IF(OR(F330="",AV330=""),"",IF(COUNT(AI330:AU330)=0,"",AV330-LOOKUP(2,1/(AI330:AU330<>""),AI330:AU330))) | IF(J330="","All_Provinces",IFERROR(VLOOKUP(J330,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K330="","All_Districts",IFERROR(VLOOKUP(K330,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F331="","",ROW()-3) | AF2-WSM-26 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | 1 of 6 | AF2-WSM-A-050 | 1. Yawol Ha Check Dam-1 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Teshkan | Yawol Ha-1 | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Faiz Qurbani Construction Company (FQCC) | 027/2026 | 28489.9 | IF(AQ331="","",AQ331) |  | 7 | 2026-11-08 | IF(W331<>"",W331,IF(OR(T331="",V331=""),"",EDATE(T331,V331))) |  | 10 | Under Construction | Completed on Sep, 2026 | IF(F331="","",IF(COUNT(AI331:AV331)=0,IF(AA331="","Not started",AA331),SUBSTITUTE(LOOKUP(2,1/(AI331:AV331<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F331="",COUNT(AI331:AV331)=0),"",TODAY()-LOOKUP(2,1/(AI331:AV331<>""),AI331:AV331)) | IF(OR(F331="",COUNT(AI331:AV331)<2),"",LOOKUP(2,1/(AI331:AV331<>""),AI331:AV331)-MIN(AI331:AV331)) | IF(OR(AD331="",AC331="Not started",AC331=""),"",IFERROR(AD331-IF(VLOOKUP(AC331,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC331,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F331="","",IF(OR(AA331="Cancelled",AC331="Cancelled"),"Cancelled",IF(OR(AC331="Completed / Handover",Y331<>"",Z331>=100),"Completed — on track",IF(O331="Not awarded",IF(U331="",IF(X331="","No planned date",IF(TODAY()>X331,"Behind — past planned date",IF(X331-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U331,"Behind — award date passed",IF(U331-TODAY()<=30,"At risk — close to off track","On track"))),IF(X331="","No planned date",IF(AND(TODAY()>X331,OR(Z331="",Z331<100)),"Behind — past end date",IF(AND(T331<>"",X331<>"",Z331<>"",(Z331<100),((TODAY()-T331)/MAX(X331-T331,1)*100)-Z331>15),"Behind — progress lag",IF(AND(X331-TODAY()<=30,X331-TODAY()>=0,OR(Z331="",Z331<90)),"At risk — close to off track","On track")))))))) | IF(OR(F331="",AC331="Completed / Handover",AC331="Cancelled"),"",IF(O331="Not awarded",IF(U331<>"",U331-TODAY(),IF(X331="","",X331-TODAY())),IF(X331="","",X331-TODAY()))) | [8 empty] | 2026-04-09 | 2026-04-09 |  |  |  |  | IF(OR(F331="",AJ331=""),"",IF(COUNT(AI331:AI331)=0,"",AJ331-LOOKUP(2,1/(AI331:AI331<>""),AI331:AI331))) | IF(OR(F331="",AK331=""),"",IF(COUNT(AI331:AJ331)=0,"",AK331-LOOKUP(2,1/(AI331:AJ331<>""),AI331:AJ331))) | IF(OR(F331="",AL331=""),"",IF(COUNT(AI331:AK331)=0,"",AL331-LOOKUP(2,1/(AI331:AK331<>""),AI331:AK331))) | IF(OR(F331="",AM331=""),"",IF(COUNT(AI331:AL331)=0,"",AM331-LOOKUP(2,1/(AI331:AL331<>""),AI331:AL331))) | IF(OR(F331="",AN331=""),"",IF(COUNT(AI331:AM331)=0,"",AN331-LOOKUP(2,1/(AI331:AM331<>""),AI331:AM331))) | IF(OR(F331="",AO331=""),"",IF(COUNT(AI331:AN331)=0,"",AO331-LOOKUP(2,1/(AI331:AN331<>""),AI331:AN331))) | IF(OR(F331="",AP331=""),"",IF(COUNT(AI331:AO331)=0,"",AP331-LOOKUP(2,1/(AI331:AO331<>""),AI331:AO331))) | IF(OR(F331="",AQ331=""),"",IF(COUNT(AI331:AP331)=0,"",AQ331-LOOKUP(2,1/(AI331:AP331<>""),AI331:AP331))) | IF(OR(F331="",AR331=""),"",IF(COUNT(AI331:AQ331)=0,"",AR331-LOOKUP(2,1/(AI331:AQ331<>""),AI331:AQ331))) | IF(OR(F331="",AS331=""),"",IF(COUNT(AI331:AR331)=0,"",AS331-LOOKUP(2,1/(AI331:AR331<>""),AI331:AR331))) | IF(OR(F331="",AT331=""),"",IF(COUNT(AI331:AS331)=0,"",AT331-LOOKUP(2,1/(AI331:AS331<>""),AI331:AS331))) | IF(OR(F331="",AU331=""),"",IF(COUNT(AI331:AT331)=0,"",AU331-LOOKUP(2,1/(AI331:AT331<>""),AI331:AT331))) | IF(OR(F331="",AV331=""),"",IF(COUNT(AI331:AU331)=0,"",AV331-LOOKUP(2,1/(AI331:AU331<>""),AI331:AU331))) | IF(J331="","All_Provinces",IFERROR(VLOOKUP(J331,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K331="","All_Districts",IFERROR(VLOOKUP(K331,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F332="","",ROW()-3) | AF2-WSM-26 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | 2 of 6 | AF2-WSM-A-051 | 2. Yawol Ha Check Dam-2 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Teshkan | Yawol Ha-2 | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Faiz Qurbani Construction Company (FQCC) | 027/2026 | 29242.96 | IF(AQ332="","",AQ332) |  | 7 | 2026-11-08 | IF(W332<>"",W332,IF(OR(T332="",V332=""),"",EDATE(T332,V332))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F332="","",IF(COUNT(AI332:AV332)=0,IF(AA332="","Not started",AA332),SUBSTITUTE(LOOKUP(2,1/(AI332:AV332<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F332="",COUNT(AI332:AV332)=0),"",TODAY()-LOOKUP(2,1/(AI332:AV332<>""),AI332:AV332)) | IF(OR(F332="",COUNT(AI332:AV332)<2),"",LOOKUP(2,1/(AI332:AV332<>""),AI332:AV332)-MIN(AI332:AV332)) | IF(OR(AD332="",AC332="Not started",AC332=""),"",IFERROR(AD332-IF(VLOOKUP(AC332,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC332,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F332="","",IF(OR(AA332="Cancelled",AC332="Cancelled"),"Cancelled",IF(OR(AC332="Completed / Handover",Y332<>"",Z332>=100),"Completed — on track",IF(O332="Not awarded",IF(U332="",IF(X332="","No planned date",IF(TODAY()>X332,"Behind — past planned date",IF(X332-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U332,"Behind — award date passed",IF(U332-TODAY()<=30,"At risk — close to off track","On track"))),IF(X332="","No planned date",IF(AND(TODAY()>X332,OR(Z332="",Z332<100)),"Behind — past end date",IF(AND(T332<>"",X332<>"",Z332<>"",(Z332<100),((TODAY()-T332)/MAX(X332-T332,1)*100)-Z332>15),"Behind — progress lag",IF(AND(X332-TODAY()<=30,X332-TODAY()>=0,OR(Z332="",Z332<90)),"At risk — close to off track","On track")))))))) | IF(OR(F332="",AC332="Completed / Handover",AC332="Cancelled"),"",IF(O332="Not awarded",IF(U332<>"",U332-TODAY(),IF(X332="","",X332-TODAY())),IF(X332="","",X332-TODAY()))) | [8 empty] | 2026-04-09 | [5 empty] | IF(OR(F332="",AJ332=""),"",IF(COUNT(AI332:AI332)=0,"",AJ332-LOOKUP(2,1/(AI332:AI332<>""),AI332:AI332))) | IF(OR(F332="",AK332=""),"",IF(COUNT(AI332:AJ332)=0,"",AK332-LOOKUP(2,1/(AI332:AJ332<>""),AI332:AJ332))) | IF(OR(F332="",AL332=""),"",IF(COUNT(AI332:AK332)=0,"",AL332-LOOKUP(2,1/(AI332:AK332<>""),AI332:AK332))) | IF(OR(F332="",AM332=""),"",IF(COUNT(AI332:AL332)=0,"",AM332-LOOKUP(2,1/(AI332:AL332<>""),AI332:AL332))) | IF(OR(F332="",AN332=""),"",IF(COUNT(AI332:AM332)=0,"",AN332-LOOKUP(2,1/(AI332:AM332<>""),AI332:AM332))) | IF(OR(F332="",AO332=""),"",IF(COUNT(AI332:AN332)=0,"",AO332-LOOKUP(2,1/(AI332:AN332<>""),AI332:AN332))) | IF(OR(F332="",AP332=""),"",IF(COUNT(AI332:AO332)=0,"",AP332-LOOKUP(2,1/(AI332:AO332<>""),AI332:AO332))) | IF(OR(F332="",AQ332=""),"",IF(COUNT(AI332:AP332)=0,"",AQ332-LOOKUP(2,1/(AI332:AP332<>""),AI332:AP332))) | IF(OR(F332="",AR332=""),"",IF(COUNT(AI332:AQ332)=0,"",AR332-LOOKUP(2,1/(AI332:AQ332<>""),AI332:AQ332))) | IF(OR(F332="",AS332=""),"",IF(COUNT(AI332:AR332)=0,"",AS332-LOOKUP(2,1/(AI332:AR332<>""),AI332:AR332))) | IF(OR(F332="",AT332=""),"",IF(COUNT(AI332:AS332)=0,"",AT332-LOOKUP(2,1/(AI332:AS332<>""),AI332:AS332))) | IF(OR(F332="",AU332=""),"",IF(COUNT(AI332:AT332)=0,"",AU332-LOOKUP(2,1/(AI332:AT332<>""),AI332:AT332))) | IF(OR(F332="",AV332=""),"",IF(COUNT(AI332:AU332)=0,"",AV332-LOOKUP(2,1/(AI332:AU332<>""),AI332:AU332))) | IF(J332="","All_Provinces",IFERROR(VLOOKUP(J332,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K332="","All_Districts",IFERROR(VLOOKUP(K332,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F333="","",ROW()-3) | AF2-WSM-26 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | 3 of 6 | AF2-WSM-A-052 | 3.Sewak Dara Kelaki Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Darayim | Sewak Dara | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Faiz Qurbani Construction Company (FQCC) | 027/2026 | 59018.99 | IF(AQ333="","",AQ333) |  | 7 | 2026-11-08 | IF(W333<>"",W333,IF(OR(T333="",V333=""),"",EDATE(T333,V333))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F333="","",IF(COUNT(AI333:AV333)=0,IF(AA333="","Not started",AA333),SUBSTITUTE(LOOKUP(2,1/(AI333:AV333<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F333="",COUNT(AI333:AV333)=0),"",TODAY()-LOOKUP(2,1/(AI333:AV333<>""),AI333:AV333)) | IF(OR(F333="",COUNT(AI333:AV333)<2),"",LOOKUP(2,1/(AI333:AV333<>""),AI333:AV333)-MIN(AI333:AV333)) | IF(OR(AD333="",AC333="Not started",AC333=""),"",IFERROR(AD333-IF(VLOOKUP(AC333,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC333,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F333="","",IF(OR(AA333="Cancelled",AC333="Cancelled"),"Cancelled",IF(OR(AC333="Completed / Handover",Y333<>"",Z333>=100),"Completed — on track",IF(O333="Not awarded",IF(U333="",IF(X333="","No planned date",IF(TODAY()>X333,"Behind — past planned date",IF(X333-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U333,"Behind — award date passed",IF(U333-TODAY()<=30,"At risk — close to off track","On track"))),IF(X333="","No planned date",IF(AND(TODAY()>X333,OR(Z333="",Z333<100)),"Behind — past end date",IF(AND(T333<>"",X333<>"",Z333<>"",(Z333<100),((TODAY()-T333)/MAX(X333-T333,1)*100)-Z333>15),"Behind — progress lag",IF(AND(X333-TODAY()<=30,X333-TODAY()>=0,OR(Z333="",Z333<90)),"At risk — close to off track","On track")))))))) | IF(OR(F333="",AC333="Completed / Handover",AC333="Cancelled"),"",IF(O333="Not awarded",IF(U333<>"",U333-TODAY(),IF(X333="","",X333-TODAY())),IF(X333="","",X333-TODAY()))) | [8 empty] | 2026-04-09 | 2026-04-09 | 2026-11-08 |  |  |  | IF(OR(F333="",AJ333=""),"",IF(COUNT(AI333:AI333)=0,"",AJ333-LOOKUP(2,1/(AI333:AI333<>""),AI333:AI333))) | IF(OR(F333="",AK333=""),"",IF(COUNT(AI333:AJ333)=0,"",AK333-LOOKUP(2,1/(AI333:AJ333<>""),AI333:AJ333))) | IF(OR(F333="",AL333=""),"",IF(COUNT(AI333:AK333)=0,"",AL333-LOOKUP(2,1/(AI333:AK333<>""),AI333:AK333))) | IF(OR(F333="",AM333=""),"",IF(COUNT(AI333:AL333)=0,"",AM333-LOOKUP(2,1/(AI333:AL333<>""),AI333:AL333))) | IF(OR(F333="",AN333=""),"",IF(COUNT(AI333:AM333)=0,"",AN333-LOOKUP(2,1/(AI333:AM333<>""),AI333:AM333))) | IF(OR(F333="",AO333=""),"",IF(COUNT(AI333:AN333)=0,"",AO333-LOOKUP(2,1/(AI333:AN333<>""),AI333:AN333))) | IF(OR(F333="",AP333=""),"",IF(COUNT(AI333:AO333)=0,"",AP333-LOOKUP(2,1/(AI333:AO333<>""),AI333:AO333))) | IF(OR(F333="",AQ333=""),"",IF(COUNT(AI333:AP333)=0,"",AQ333-LOOKUP(2,1/(AI333:AP333<>""),AI333:AP333))) | IF(OR(F333="",AR333=""),"",IF(COUNT(AI333:AQ333)=0,"",AR333-LOOKUP(2,1/(AI333:AQ333<>""),AI333:AQ333))) | IF(OR(F333="",AS333=""),"",IF(COUNT(AI333:AR333)=0,"",AS333-LOOKUP(2,1/(AI333:AR333<>""),AI333:AR333))) | IF(OR(F333="",AT333=""),"",IF(COUNT(AI333:AS333)=0,"",AT333-LOOKUP(2,1/(AI333:AS333<>""),AI333:AS333))) | IF(OR(F333="",AU333=""),"",IF(COUNT(AI333:AT333)=0,"",AU333-LOOKUP(2,1/(AI333:AT333<>""),AI333:AT333))) | IF(OR(F333="",AV333=""),"",IF(COUNT(AI333:AU333)=0,"",AV333-LOOKUP(2,1/(AI333:AU333<>""),AI333:AU333))) | IF(J333="","All_Provinces",IFERROR(VLOOKUP(J333,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K333="","All_Districts",IFERROR(VLOOKUP(K333,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F334="","",ROW()-3) | AF2-WSM-26 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | 4 of 6 | AF2-WSM-A-053 | 4. Golaki Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Darayim | Golaki | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Faiz Qurbani Construction Company (FQCC) | 027/2026 | 62408.88 | IF(AQ334="","",AQ334) |  | 7 | 2026-11-08 | IF(W334<>"",W334,IF(OR(T334="",V334=""),"",EDATE(T334,V334))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F334="","",IF(COUNT(AI334:AV334)=0,IF(AA334="","Not started",AA334),SUBSTITUTE(LOOKUP(2,1/(AI334:AV334<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F334="",COUNT(AI334:AV334)=0),"",TODAY()-LOOKUP(2,1/(AI334:AV334<>""),AI334:AV334)) | IF(OR(F334="",COUNT(AI334:AV334)<2),"",LOOKUP(2,1/(AI334:AV334<>""),AI334:AV334)-MIN(AI334:AV334)) | IF(OR(AD334="",AC334="Not started",AC334=""),"",IFERROR(AD334-IF(VLOOKUP(AC334,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC334,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F334="","",IF(OR(AA334="Cancelled",AC334="Cancelled"),"Cancelled",IF(OR(AC334="Completed / Handover",Y334<>"",Z334>=100),"Completed — on track",IF(O334="Not awarded",IF(U334="",IF(X334="","No planned date",IF(TODAY()>X334,"Behind — past planned date",IF(X334-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U334,"Behind — award date passed",IF(U334-TODAY()<=30,"At risk — close to off track","On track"))),IF(X334="","No planned date",IF(AND(TODAY()>X334,OR(Z334="",Z334<100)),"Behind — past end date",IF(AND(T334<>"",X334<>"",Z334<>"",(Z334<100),((TODAY()-T334)/MAX(X334-T334,1)*100)-Z334>15),"Behind — progress lag",IF(AND(X334-TODAY()<=30,X334-TODAY()>=0,OR(Z334="",Z334<90)),"At risk — close to off track","On track")))))))) | IF(OR(F334="",AC334="Completed / Handover",AC334="Cancelled"),"",IF(O334="Not awarded",IF(U334<>"",U334-TODAY(),IF(X334="","",X334-TODAY())),IF(X334="","",X334-TODAY()))) | [8 empty] | 2026-04-09 | 2026-04-09 | 2026-11-08 |  |  |  | IF(OR(F334="",AJ334=""),"",IF(COUNT(AI334:AI334)=0,"",AJ334-LOOKUP(2,1/(AI334:AI334<>""),AI334:AI334))) | IF(OR(F334="",AK334=""),"",IF(COUNT(AI334:AJ334)=0,"",AK334-LOOKUP(2,1/(AI334:AJ334<>""),AI334:AJ334))) | IF(OR(F334="",AL334=""),"",IF(COUNT(AI334:AK334)=0,"",AL334-LOOKUP(2,1/(AI334:AK334<>""),AI334:AK334))) | IF(OR(F334="",AM334=""),"",IF(COUNT(AI334:AL334)=0,"",AM334-LOOKUP(2,1/(AI334:AL334<>""),AI334:AL334))) | IF(OR(F334="",AN334=""),"",IF(COUNT(AI334:AM334)=0,"",AN334-LOOKUP(2,1/(AI334:AM334<>""),AI334:AM334))) | IF(OR(F334="",AO334=""),"",IF(COUNT(AI334:AN334)=0,"",AO334-LOOKUP(2,1/(AI334:AN334<>""),AI334:AN334))) | IF(OR(F334="",AP334=""),"",IF(COUNT(AI334:AO334)=0,"",AP334-LOOKUP(2,1/(AI334:AO334<>""),AI334:AO334))) | IF(OR(F334="",AQ334=""),"",IF(COUNT(AI334:AP334)=0,"",AQ334-LOOKUP(2,1/(AI334:AP334<>""),AI334:AP334))) | IF(OR(F334="",AR334=""),"",IF(COUNT(AI334:AQ334)=0,"",AR334-LOOKUP(2,1/(AI334:AQ334<>""),AI334:AQ334))) | IF(OR(F334="",AS334=""),"",IF(COUNT(AI334:AR334)=0,"",AS334-LOOKUP(2,1/(AI334:AR334<>""),AI334:AR334))) | IF(OR(F334="",AT334=""),"",IF(COUNT(AI334:AS334)=0,"",AT334-LOOKUP(2,1/(AI334:AS334<>""),AI334:AS334))) | IF(OR(F334="",AU334=""),"",IF(COUNT(AI334:AT334)=0,"",AU334-LOOKUP(2,1/(AI334:AT334<>""),AI334:AT334))) | IF(OR(F334="",AV334=""),"",IF(COUNT(AI334:AU334)=0,"",AV334-LOOKUP(2,1/(AI334:AU334<>""),AI334:AU334))) | IF(J334="","All_Provinces",IFERROR(VLOOKUP(J334,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K334="","All_Districts",IFERROR(VLOOKUP(K334,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F335="","",ROW()-3) | AF2-WSM-26 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | 5 of 6 | AF2-WSM-A-054 | 5. Khanaqa Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Arghanj Khwah | Khanaqa | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Faiz Qurbani Construction Company (FQCC) | 027/2026 | 29058.49 | IF(AQ335="","",AQ335) |  | 7 | 2026-11-08 | IF(W335<>"",W335,IF(OR(T335="",V335=""),"",EDATE(T335,V335))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F335="","",IF(COUNT(AI335:AV335)=0,IF(AA335="","Not started",AA335),SUBSTITUTE(LOOKUP(2,1/(AI335:AV335<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F335="",COUNT(AI335:AV335)=0),"",TODAY()-LOOKUP(2,1/(AI335:AV335<>""),AI335:AV335)) | IF(OR(F335="",COUNT(AI335:AV335)<2),"",LOOKUP(2,1/(AI335:AV335<>""),AI335:AV335)-MIN(AI335:AV335)) | IF(OR(AD335="",AC335="Not started",AC335=""),"",IFERROR(AD335-IF(VLOOKUP(AC335,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC335,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F335="","",IF(OR(AA335="Cancelled",AC335="Cancelled"),"Cancelled",IF(OR(AC335="Completed / Handover",Y335<>"",Z335>=100),"Completed — on track",IF(O335="Not awarded",IF(U335="",IF(X335="","No planned date",IF(TODAY()>X335,"Behind — past planned date",IF(X335-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U335,"Behind — award date passed",IF(U335-TODAY()<=30,"At risk — close to off track","On track"))),IF(X335="","No planned date",IF(AND(TODAY()>X335,OR(Z335="",Z335<100)),"Behind — past end date",IF(AND(T335<>"",X335<>"",Z335<>"",(Z335<100),((TODAY()-T335)/MAX(X335-T335,1)*100)-Z335>15),"Behind — progress lag",IF(AND(X335-TODAY()<=30,X335-TODAY()>=0,OR(Z335="",Z335<90)),"At risk — close to off track","On track")))))))) | IF(OR(F335="",AC335="Completed / Handover",AC335="Cancelled"),"",IF(O335="Not awarded",IF(U335<>"",U335-TODAY(),IF(X335="","",X335-TODAY())),IF(X335="","",X335-TODAY()))) | [8 empty] | 2026-04-09 | [5 empty] | IF(OR(F335="",AJ335=""),"",IF(COUNT(AI335:AI335)=0,"",AJ335-LOOKUP(2,1/(AI335:AI335<>""),AI335:AI335))) | IF(OR(F335="",AK335=""),"",IF(COUNT(AI335:AJ335)=0,"",AK335-LOOKUP(2,1/(AI335:AJ335<>""),AI335:AJ335))) | IF(OR(F335="",AL335=""),"",IF(COUNT(AI335:AK335)=0,"",AL335-LOOKUP(2,1/(AI335:AK335<>""),AI335:AK335))) | IF(OR(F335="",AM335=""),"",IF(COUNT(AI335:AL335)=0,"",AM335-LOOKUP(2,1/(AI335:AL335<>""),AI335:AL335))) | IF(OR(F335="",AN335=""),"",IF(COUNT(AI335:AM335)=0,"",AN335-LOOKUP(2,1/(AI335:AM335<>""),AI335:AM335))) | IF(OR(F335="",AO335=""),"",IF(COUNT(AI335:AN335)=0,"",AO335-LOOKUP(2,1/(AI335:AN335<>""),AI335:AN335))) | IF(OR(F335="",AP335=""),"",IF(COUNT(AI335:AO335)=0,"",AP335-LOOKUP(2,1/(AI335:AO335<>""),AI335:AO335))) | IF(OR(F335="",AQ335=""),"",IF(COUNT(AI335:AP335)=0,"",AQ335-LOOKUP(2,1/(AI335:AP335<>""),AI335:AP335))) | IF(OR(F335="",AR335=""),"",IF(COUNT(AI335:AQ335)=0,"",AR335-LOOKUP(2,1/(AI335:AQ335<>""),AI335:AQ335))) | IF(OR(F335="",AS335=""),"",IF(COUNT(AI335:AR335)=0,"",AS335-LOOKUP(2,1/(AI335:AR335<>""),AI335:AR335))) | IF(OR(F335="",AT335=""),"",IF(COUNT(AI335:AS335)=0,"",AT335-LOOKUP(2,1/(AI335:AS335<>""),AI335:AS335))) | IF(OR(F335="",AU335=""),"",IF(COUNT(AI335:AT335)=0,"",AU335-LOOKUP(2,1/(AI335:AT335<>""),AI335:AT335))) | IF(OR(F335="",AV335=""),"",IF(COUNT(AI335:AU335)=0,"",AV335-LOOKUP(2,1/(AI335:AU335<>""),AI335:AU335))) | IF(J335="","All_Provinces",IFERROR(VLOOKUP(J335,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K335="","All_Districts",IFERROR(VLOOKUP(K335,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F336="","",ROW()-3) | AF2-WSM-26 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | 6 of 6 | AF2-WSM-A-055 | 6. Sum Darra Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Badakhshan | Arghanj Khwah | Sum Dara | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Faiz Qurbani Construction Company (FQCC) | 027/2026 | 31519.9 | IF(AQ336="","",AQ336) |  | 7 | 2026-11-08 | IF(W336<>"",W336,IF(OR(T336="",V336=""),"",EDATE(T336,V336))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F336="","",IF(COUNT(AI336:AV336)=0,IF(AA336="","Not started",AA336),SUBSTITUTE(LOOKUP(2,1/(AI336:AV336<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F336="",COUNT(AI336:AV336)=0),"",TODAY()-LOOKUP(2,1/(AI336:AV336<>""),AI336:AV336)) | IF(OR(F336="",COUNT(AI336:AV336)<2),"",LOOKUP(2,1/(AI336:AV336<>""),AI336:AV336)-MIN(AI336:AV336)) | IF(OR(AD336="",AC336="Not started",AC336=""),"",IFERROR(AD336-IF(VLOOKUP(AC336,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC336,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F336="","",IF(OR(AA336="Cancelled",AC336="Cancelled"),"Cancelled",IF(OR(AC336="Completed / Handover",Y336<>"",Z336>=100),"Completed — on track",IF(O336="Not awarded",IF(U336="",IF(X336="","No planned date",IF(TODAY()>X336,"Behind — past planned date",IF(X336-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U336,"Behind — award date passed",IF(U336-TODAY()<=30,"At risk — close to off track","On track"))),IF(X336="","No planned date",IF(AND(TODAY()>X336,OR(Z336="",Z336<100)),"Behind — past end date",IF(AND(T336<>"",X336<>"",Z336<>"",(Z336<100),((TODAY()-T336)/MAX(X336-T336,1)*100)-Z336>15),"Behind — progress lag",IF(AND(X336-TODAY()<=30,X336-TODAY()>=0,OR(Z336="",Z336<90)),"At risk — close to off track","On track")))))))) | IF(OR(F336="",AC336="Completed / Handover",AC336="Cancelled"),"",IF(O336="Not awarded",IF(U336<>"",U336-TODAY(),IF(X336="","",X336-TODAY())),IF(X336="","",X336-TODAY()))) | [8 empty] | 2026-04-09 | [5 empty] | IF(OR(F336="",AJ336=""),"",IF(COUNT(AI336:AI336)=0,"",AJ336-LOOKUP(2,1/(AI336:AI336<>""),AI336:AI336))) | IF(OR(F336="",AK336=""),"",IF(COUNT(AI336:AJ336)=0,"",AK336-LOOKUP(2,1/(AI336:AJ336<>""),AI336:AJ336))) | IF(OR(F336="",AL336=""),"",IF(COUNT(AI336:AK336)=0,"",AL336-LOOKUP(2,1/(AI336:AK336<>""),AI336:AK336))) | IF(OR(F336="",AM336=""),"",IF(COUNT(AI336:AL336)=0,"",AM336-LOOKUP(2,1/(AI336:AL336<>""),AI336:AL336))) | IF(OR(F336="",AN336=""),"",IF(COUNT(AI336:AM336)=0,"",AN336-LOOKUP(2,1/(AI336:AM336<>""),AI336:AM336))) | IF(OR(F336="",AO336=""),"",IF(COUNT(AI336:AN336)=0,"",AO336-LOOKUP(2,1/(AI336:AN336<>""),AI336:AN336))) | IF(OR(F336="",AP336=""),"",IF(COUNT(AI336:AO336)=0,"",AP336-LOOKUP(2,1/(AI336:AO336<>""),AI336:AO336))) | IF(OR(F336="",AQ336=""),"",IF(COUNT(AI336:AP336)=0,"",AQ336-LOOKUP(2,1/(AI336:AP336<>""),AI336:AP336))) | IF(OR(F336="",AR336=""),"",IF(COUNT(AI336:AQ336)=0,"",AR336-LOOKUP(2,1/(AI336:AQ336<>""),AI336:AQ336))) | IF(OR(F336="",AS336=""),"",IF(COUNT(AI336:AR336)=0,"",AS336-LOOKUP(2,1/(AI336:AR336<>""),AI336:AR336))) | IF(OR(F336="",AT336=""),"",IF(COUNT(AI336:AS336)=0,"",AT336-LOOKUP(2,1/(AI336:AS336<>""),AI336:AS336))) | IF(OR(F336="",AU336=""),"",IF(COUNT(AI336:AT336)=0,"",AU336-LOOKUP(2,1/(AI336:AT336<>""),AI336:AT336))) | IF(OR(F336="",AV336=""),"",IF(COUNT(AI336:AU336)=0,"",AV336-LOOKUP(2,1/(AI336:AU336<>""),AI336:AU336))) | IF(J336="","All_Provinces",IFERROR(VLOOKUP(J336,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K336="","All_Districts",IFERROR(VLOOKUP(K336,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F337="","",ROW()-3) | AF2-WSM-27 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | 1 of 5 | AF2-WSM-A-056 | 1.Sholish Darra Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Namak Ab | Sholish Darra | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shafiqullah Wahidi Construction Company (SWCC) | 037/2026 | 29465.27 | IF(AQ337="","",AQ337) |  | 6 | 2026-11-20 | IF(W337<>"",W337,IF(OR(T337="",V337=""),"",EDATE(T337,V337))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F337="","",IF(COUNT(AI337:AV337)=0,IF(AA337="","Not started",AA337),SUBSTITUTE(LOOKUP(2,1/(AI337:AV337<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F337="",COUNT(AI337:AV337)=0),"",TODAY()-LOOKUP(2,1/(AI337:AV337<>""),AI337:AV337)) | IF(OR(F337="",COUNT(AI337:AV337)<2),"",LOOKUP(2,1/(AI337:AV337<>""),AI337:AV337)-MIN(AI337:AV337)) | IF(OR(AD337="",AC337="Not started",AC337=""),"",IFERROR(AD337-IF(VLOOKUP(AC337,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC337,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F337="","",IF(OR(AA337="Cancelled",AC337="Cancelled"),"Cancelled",IF(OR(AC337="Completed / Handover",Y337<>"",Z337>=100),"Completed — on track",IF(O337="Not awarded",IF(U337="",IF(X337="","No planned date",IF(TODAY()>X337,"Behind — past planned date",IF(X337-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U337,"Behind — award date passed",IF(U337-TODAY()<=30,"At risk — close to off track","On track"))),IF(X337="","No planned date",IF(AND(TODAY()>X337,OR(Z337="",Z337<100)),"Behind — past end date",IF(AND(T337<>"",X337<>"",Z337<>"",(Z337<100),((TODAY()-T337)/MAX(X337-T337,1)*100)-Z337>15),"Behind — progress lag",IF(AND(X337-TODAY()<=30,X337-TODAY()>=0,OR(Z337="",Z337<90)),"At risk — close to off track","On track")))))))) | IF(OR(F337="",AC337="Completed / Handover",AC337="Cancelled"),"",IF(O337="Not awarded",IF(U337<>"",U337-TODAY(),IF(X337="","",X337-TODAY())),IF(X337="","",X337-TODAY()))) | [8 empty] | 2026-05-21 | [5 empty] | IF(OR(F337="",AJ337=""),"",IF(COUNT(AI337:AI337)=0,"",AJ337-LOOKUP(2,1/(AI337:AI337<>""),AI337:AI337))) | IF(OR(F337="",AK337=""),"",IF(COUNT(AI337:AJ337)=0,"",AK337-LOOKUP(2,1/(AI337:AJ337<>""),AI337:AJ337))) | IF(OR(F337="",AL337=""),"",IF(COUNT(AI337:AK337)=0,"",AL337-LOOKUP(2,1/(AI337:AK337<>""),AI337:AK337))) | IF(OR(F337="",AM337=""),"",IF(COUNT(AI337:AL337)=0,"",AM337-LOOKUP(2,1/(AI337:AL337<>""),AI337:AL337))) | IF(OR(F337="",AN337=""),"",IF(COUNT(AI337:AM337)=0,"",AN337-LOOKUP(2,1/(AI337:AM337<>""),AI337:AM337))) | IF(OR(F337="",AO337=""),"",IF(COUNT(AI337:AN337)=0,"",AO337-LOOKUP(2,1/(AI337:AN337<>""),AI337:AN337))) | IF(OR(F337="",AP337=""),"",IF(COUNT(AI337:AO337)=0,"",AP337-LOOKUP(2,1/(AI337:AO337<>""),AI337:AO337))) | IF(OR(F337="",AQ337=""),"",IF(COUNT(AI337:AP337)=0,"",AQ337-LOOKUP(2,1/(AI337:AP337<>""),AI337:AP337))) | IF(OR(F337="",AR337=""),"",IF(COUNT(AI337:AQ337)=0,"",AR337-LOOKUP(2,1/(AI337:AQ337<>""),AI337:AQ337))) | IF(OR(F337="",AS337=""),"",IF(COUNT(AI337:AR337)=0,"",AS337-LOOKUP(2,1/(AI337:AR337<>""),AI337:AR337))) | IF(OR(F337="",AT337=""),"",IF(COUNT(AI337:AS337)=0,"",AT337-LOOKUP(2,1/(AI337:AS337<>""),AI337:AS337))) | IF(OR(F337="",AU337=""),"",IF(COUNT(AI337:AT337)=0,"",AU337-LOOKUP(2,1/(AI337:AT337<>""),AI337:AT337))) | IF(OR(F337="",AV337=""),"",IF(COUNT(AI337:AU337)=0,"",AV337-LOOKUP(2,1/(AI337:AU337<>""),AI337:AU337))) | IF(J337="","All_Provinces",IFERROR(VLOOKUP(J337,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K337="","All_Districts",IFERROR(VLOOKUP(K337,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F338="","",ROW()-3) | AF2-WSM-27 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | 2 of 5 | AF2-WSM-A-057 | 2.Gaji Darra Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Hazar Sumoch | Gaji Darra | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shafiqullah Wahidi Construction Company (SWCC) | 037/2026 | 28776.59 | IF(AQ338="","",AQ338) |  | 6 | 2026-11-20 | IF(W338<>"",W338,IF(OR(T338="",V338=""),"",EDATE(T338,V338))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F338="","",IF(COUNT(AI338:AV338)=0,IF(AA338="","Not started",AA338),SUBSTITUTE(LOOKUP(2,1/(AI338:AV338<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F338="",COUNT(AI338:AV338)=0),"",TODAY()-LOOKUP(2,1/(AI338:AV338<>""),AI338:AV338)) | IF(OR(F338="",COUNT(AI338:AV338)<2),"",LOOKUP(2,1/(AI338:AV338<>""),AI338:AV338)-MIN(AI338:AV338)) | IF(OR(AD338="",AC338="Not started",AC338=""),"",IFERROR(AD338-IF(VLOOKUP(AC338,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC338,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F338="","",IF(OR(AA338="Cancelled",AC338="Cancelled"),"Cancelled",IF(OR(AC338="Completed / Handover",Y338<>"",Z338>=100),"Completed — on track",IF(O338="Not awarded",IF(U338="",IF(X338="","No planned date",IF(TODAY()>X338,"Behind — past planned date",IF(X338-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U338,"Behind — award date passed",IF(U338-TODAY()<=30,"At risk — close to off track","On track"))),IF(X338="","No planned date",IF(AND(TODAY()>X338,OR(Z338="",Z338<100)),"Behind — past end date",IF(AND(T338<>"",X338<>"",Z338<>"",(Z338<100),((TODAY()-T338)/MAX(X338-T338,1)*100)-Z338>15),"Behind — progress lag",IF(AND(X338-TODAY()<=30,X338-TODAY()>=0,OR(Z338="",Z338<90)),"At risk — close to off track","On track")))))))) | IF(OR(F338="",AC338="Completed / Handover",AC338="Cancelled"),"",IF(O338="Not awarded",IF(U338<>"",U338-TODAY(),IF(X338="","",X338-TODAY())),IF(X338="","",X338-TODAY()))) | [8 empty] | 2026-05-21 | [5 empty] | IF(OR(F338="",AJ338=""),"",IF(COUNT(AI338:AI338)=0,"",AJ338-LOOKUP(2,1/(AI338:AI338<>""),AI338:AI338))) | IF(OR(F338="",AK338=""),"",IF(COUNT(AI338:AJ338)=0,"",AK338-LOOKUP(2,1/(AI338:AJ338<>""),AI338:AJ338))) | IF(OR(F338="",AL338=""),"",IF(COUNT(AI338:AK338)=0,"",AL338-LOOKUP(2,1/(AI338:AK338<>""),AI338:AK338))) | IF(OR(F338="",AM338=""),"",IF(COUNT(AI338:AL338)=0,"",AM338-LOOKUP(2,1/(AI338:AL338<>""),AI338:AL338))) | IF(OR(F338="",AN338=""),"",IF(COUNT(AI338:AM338)=0,"",AN338-LOOKUP(2,1/(AI338:AM338<>""),AI338:AM338))) | IF(OR(F338="",AO338=""),"",IF(COUNT(AI338:AN338)=0,"",AO338-LOOKUP(2,1/(AI338:AN338<>""),AI338:AN338))) | IF(OR(F338="",AP338=""),"",IF(COUNT(AI338:AO338)=0,"",AP338-LOOKUP(2,1/(AI338:AO338<>""),AI338:AO338))) | IF(OR(F338="",AQ338=""),"",IF(COUNT(AI338:AP338)=0,"",AQ338-LOOKUP(2,1/(AI338:AP338<>""),AI338:AP338))) | IF(OR(F338="",AR338=""),"",IF(COUNT(AI338:AQ338)=0,"",AR338-LOOKUP(2,1/(AI338:AQ338<>""),AI338:AQ338))) | IF(OR(F338="",AS338=""),"",IF(COUNT(AI338:AR338)=0,"",AS338-LOOKUP(2,1/(AI338:AR338<>""),AI338:AR338))) | IF(OR(F338="",AT338=""),"",IF(COUNT(AI338:AS338)=0,"",AT338-LOOKUP(2,1/(AI338:AS338<>""),AI338:AS338))) | IF(OR(F338="",AU338=""),"",IF(COUNT(AI338:AT338)=0,"",AU338-LOOKUP(2,1/(AI338:AT338<>""),AI338:AT338))) | IF(OR(F338="",AV338=""),"",IF(COUNT(AI338:AU338)=0,"",AV338-LOOKUP(2,1/(AI338:AU338<>""),AI338:AU338))) | IF(J338="","All_Provinces",IFERROR(VLOOKUP(J338,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K338="","All_Districts",IFERROR(VLOOKUP(K338,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F339="","",ROW()-3) | AF2-WSM-27 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | 3 of 5 | AF2-WSM-A-058 | 3.Silaba Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Khwaja Ghar | Charagh Sai-e, Silaba | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shafiqullah Wahidi Construction Company (SWCC) | 037/2026 | 17455.39 | IF(AQ339="","",AQ339) |  | 6 | 2026-11-20 | IF(W339<>"",W339,IF(OR(T339="",V339=""),"",EDATE(T339,V339))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F339="","",IF(COUNT(AI339:AV339)=0,IF(AA339="","Not started",AA339),SUBSTITUTE(LOOKUP(2,1/(AI339:AV339<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F339="",COUNT(AI339:AV339)=0),"",TODAY()-LOOKUP(2,1/(AI339:AV339<>""),AI339:AV339)) | IF(OR(F339="",COUNT(AI339:AV339)<2),"",LOOKUP(2,1/(AI339:AV339<>""),AI339:AV339)-MIN(AI339:AV339)) | IF(OR(AD339="",AC339="Not started",AC339=""),"",IFERROR(AD339-IF(VLOOKUP(AC339,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC339,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F339="","",IF(OR(AA339="Cancelled",AC339="Cancelled"),"Cancelled",IF(OR(AC339="Completed / Handover",Y339<>"",Z339>=100),"Completed — on track",IF(O339="Not awarded",IF(U339="",IF(X339="","No planned date",IF(TODAY()>X339,"Behind — past planned date",IF(X339-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U339,"Behind — award date passed",IF(U339-TODAY()<=30,"At risk — close to off track","On track"))),IF(X339="","No planned date",IF(AND(TODAY()>X339,OR(Z339="",Z339<100)),"Behind — past end date",IF(AND(T339<>"",X339<>"",Z339<>"",(Z339<100),((TODAY()-T339)/MAX(X339-T339,1)*100)-Z339>15),"Behind — progress lag",IF(AND(X339-TODAY()<=30,X339-TODAY()>=0,OR(Z339="",Z339<90)),"At risk — close to off track","On track")))))))) | IF(OR(F339="",AC339="Completed / Handover",AC339="Cancelled"),"",IF(O339="Not awarded",IF(U339<>"",U339-TODAY(),IF(X339="","",X339-TODAY())),IF(X339="","",X339-TODAY()))) | [8 empty] | 2026-05-21 | 2026-05-21 | 2026-11-20 |  |  |  | IF(OR(F339="",AJ339=""),"",IF(COUNT(AI339:AI339)=0,"",AJ339-LOOKUP(2,1/(AI339:AI339<>""),AI339:AI339))) | IF(OR(F339="",AK339=""),"",IF(COUNT(AI339:AJ339)=0,"",AK339-LOOKUP(2,1/(AI339:AJ339<>""),AI339:AJ339))) | IF(OR(F339="",AL339=""),"",IF(COUNT(AI339:AK339)=0,"",AL339-LOOKUP(2,1/(AI339:AK339<>""),AI339:AK339))) | IF(OR(F339="",AM339=""),"",IF(COUNT(AI339:AL339)=0,"",AM339-LOOKUP(2,1/(AI339:AL339<>""),AI339:AL339))) | IF(OR(F339="",AN339=""),"",IF(COUNT(AI339:AM339)=0,"",AN339-LOOKUP(2,1/(AI339:AM339<>""),AI339:AM339))) | IF(OR(F339="",AO339=""),"",IF(COUNT(AI339:AN339)=0,"",AO339-LOOKUP(2,1/(AI339:AN339<>""),AI339:AN339))) | IF(OR(F339="",AP339=""),"",IF(COUNT(AI339:AO339)=0,"",AP339-LOOKUP(2,1/(AI339:AO339<>""),AI339:AO339))) | IF(OR(F339="",AQ339=""),"",IF(COUNT(AI339:AP339)=0,"",AQ339-LOOKUP(2,1/(AI339:AP339<>""),AI339:AP339))) | IF(OR(F339="",AR339=""),"",IF(COUNT(AI339:AQ339)=0,"",AR339-LOOKUP(2,1/(AI339:AQ339<>""),AI339:AQ339))) | IF(OR(F339="",AS339=""),"",IF(COUNT(AI339:AR339)=0,"",AS339-LOOKUP(2,1/(AI339:AR339<>""),AI339:AR339))) | IF(OR(F339="",AT339=""),"",IF(COUNT(AI339:AS339)=0,"",AT339-LOOKUP(2,1/(AI339:AS339<>""),AI339:AS339))) | IF(OR(F339="",AU339=""),"",IF(COUNT(AI339:AT339)=0,"",AU339-LOOKUP(2,1/(AI339:AT339<>""),AI339:AT339))) | IF(OR(F339="",AV339=""),"",IF(COUNT(AI339:AU339)=0,"",AV339-LOOKUP(2,1/(AI339:AU339<>""),AI339:AU339))) | IF(J339="","All_Provinces",IFERROR(VLOOKUP(J339,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K339="","All_Districts",IFERROR(VLOOKUP(K339,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F340="","",ROW()-3) | AF2-WSM-27 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | 4 of 5 | AF2-WSM-A-059 | 4.Shoor Toghai Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Khwaja Bahawuddin | Shoor Toghai and Koratam | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shafiqullah Wahidi Construction Company (SWCC) | 037/2026 | 93678.9 | IF(AQ340="","",AQ340) |  | 6 | 2026-11-20 | IF(W340<>"",W340,IF(OR(T340="",V340=""),"",EDATE(T340,V340))) |  | 80 | Under Construction | Completed on Sep, 2026 | IF(F340="","",IF(COUNT(AI340:AV340)=0,IF(AA340="","Not started",AA340),SUBSTITUTE(LOOKUP(2,1/(AI340:AV340<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F340="",COUNT(AI340:AV340)=0),"",TODAY()-LOOKUP(2,1/(AI340:AV340<>""),AI340:AV340)) | IF(OR(F340="",COUNT(AI340:AV340)<2),"",LOOKUP(2,1/(AI340:AV340<>""),AI340:AV340)-MIN(AI340:AV340)) | IF(OR(AD340="",AC340="Not started",AC340=""),"",IFERROR(AD340-IF(VLOOKUP(AC340,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC340,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F340="","",IF(OR(AA340="Cancelled",AC340="Cancelled"),"Cancelled",IF(OR(AC340="Completed / Handover",Y340<>"",Z340>=100),"Completed — on track",IF(O340="Not awarded",IF(U340="",IF(X340="","No planned date",IF(TODAY()>X340,"Behind — past planned date",IF(X340-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U340,"Behind — award date passed",IF(U340-TODAY()<=30,"At risk — close to off track","On track"))),IF(X340="","No planned date",IF(AND(TODAY()>X340,OR(Z340="",Z340<100)),"Behind — past end date",IF(AND(T340<>"",X340<>"",Z340<>"",(Z340<100),((TODAY()-T340)/MAX(X340-T340,1)*100)-Z340>15),"Behind — progress lag",IF(AND(X340-TODAY()<=30,X340-TODAY()>=0,OR(Z340="",Z340<90)),"At risk — close to off track","On track")))))))) | IF(OR(F340="",AC340="Completed / Handover",AC340="Cancelled"),"",IF(O340="Not awarded",IF(U340<>"",U340-TODAY(),IF(X340="","",X340-TODAY())),IF(X340="","",X340-TODAY()))) | [8 empty] | 2026-05-21 | 2026-05-21 |  |  |  |  | IF(OR(F340="",AJ340=""),"",IF(COUNT(AI340:AI340)=0,"",AJ340-LOOKUP(2,1/(AI340:AI340<>""),AI340:AI340))) | IF(OR(F340="",AK340=""),"",IF(COUNT(AI340:AJ340)=0,"",AK340-LOOKUP(2,1/(AI340:AJ340<>""),AI340:AJ340))) | IF(OR(F340="",AL340=""),"",IF(COUNT(AI340:AK340)=0,"",AL340-LOOKUP(2,1/(AI340:AK340<>""),AI340:AK340))) | IF(OR(F340="",AM340=""),"",IF(COUNT(AI340:AL340)=0,"",AM340-LOOKUP(2,1/(AI340:AL340<>""),AI340:AL340))) | IF(OR(F340="",AN340=""),"",IF(COUNT(AI340:AM340)=0,"",AN340-LOOKUP(2,1/(AI340:AM340<>""),AI340:AM340))) | IF(OR(F340="",AO340=""),"",IF(COUNT(AI340:AN340)=0,"",AO340-LOOKUP(2,1/(AI340:AN340<>""),AI340:AN340))) | IF(OR(F340="",AP340=""),"",IF(COUNT(AI340:AO340)=0,"",AP340-LOOKUP(2,1/(AI340:AO340<>""),AI340:AO340))) | IF(OR(F340="",AQ340=""),"",IF(COUNT(AI340:AP340)=0,"",AQ340-LOOKUP(2,1/(AI340:AP340<>""),AI340:AP340))) | IF(OR(F340="",AR340=""),"",IF(COUNT(AI340:AQ340)=0,"",AR340-LOOKUP(2,1/(AI340:AQ340<>""),AI340:AQ340))) | IF(OR(F340="",AS340=""),"",IF(COUNT(AI340:AR340)=0,"",AS340-LOOKUP(2,1/(AI340:AR340<>""),AI340:AR340))) | IF(OR(F340="",AT340=""),"",IF(COUNT(AI340:AS340)=0,"",AT340-LOOKUP(2,1/(AI340:AS340<>""),AI340:AS340))) | IF(OR(F340="",AU340=""),"",IF(COUNT(AI340:AT340)=0,"",AU340-LOOKUP(2,1/(AI340:AT340<>""),AI340:AT340))) | IF(OR(F340="",AV340=""),"",IF(COUNT(AI340:AU340)=0,"",AV340-LOOKUP(2,1/(AI340:AU340<>""),AI340:AU340))) | IF(J340="","All_Provinces",IFERROR(VLOOKUP(J340,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K340="","All_Districts",IFERROR(VLOOKUP(K340,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F341="","",ROW()-3) | AF2-WSM-27 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | 5 of 5 | AF2-WSM-A-060 | 5.Khalyazi Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Takhar | Yangi Qala | Khalyazi | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Shafiqullah Wahidi Construction Company (SWCC) | 037/2026 | 30229.57 | IF(AQ341="","",AQ341) |  | 6 | 2026-11-20 | IF(W341<>"",W341,IF(OR(T341="",V341=""),"",EDATE(T341,V341))) |  | 0 | Awarded | Completed on Sep, 2026 | IF(F341="","",IF(COUNT(AI341:AV341)=0,IF(AA341="","Not started",AA341),SUBSTITUTE(LOOKUP(2,1/(AI341:AV341<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F341="",COUNT(AI341:AV341)=0),"",TODAY()-LOOKUP(2,1/(AI341:AV341<>""),AI341:AV341)) | IF(OR(F341="",COUNT(AI341:AV341)<2),"",LOOKUP(2,1/(AI341:AV341<>""),AI341:AV341)-MIN(AI341:AV341)) | IF(OR(AD341="",AC341="Not started",AC341=""),"",IFERROR(AD341-IF(VLOOKUP(AC341,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC341,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F341="","",IF(OR(AA341="Cancelled",AC341="Cancelled"),"Cancelled",IF(OR(AC341="Completed / Handover",Y341<>"",Z341>=100),"Completed — on track",IF(O341="Not awarded",IF(U341="",IF(X341="","No planned date",IF(TODAY()>X341,"Behind — past planned date",IF(X341-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U341,"Behind — award date passed",IF(U341-TODAY()<=30,"At risk — close to off track","On track"))),IF(X341="","No planned date",IF(AND(TODAY()>X341,OR(Z341="",Z341<100)),"Behind — past end date",IF(AND(T341<>"",X341<>"",Z341<>"",(Z341<100),((TODAY()-T341)/MAX(X341-T341,1)*100)-Z341>15),"Behind — progress lag",IF(AND(X341-TODAY()<=30,X341-TODAY()>=0,OR(Z341="",Z341<90)),"At risk — close to off track","On track")))))))) | IF(OR(F341="",AC341="Completed / Handover",AC341="Cancelled"),"",IF(O341="Not awarded",IF(U341<>"",U341-TODAY(),IF(X341="","",X341-TODAY())),IF(X341="","",X341-TODAY()))) | [8 empty] | 2026-05-21 | [5 empty] | IF(OR(F341="",AJ341=""),"",IF(COUNT(AI341:AI341)=0,"",AJ341-LOOKUP(2,1/(AI341:AI341<>""),AI341:AI341))) | IF(OR(F341="",AK341=""),"",IF(COUNT(AI341:AJ341)=0,"",AK341-LOOKUP(2,1/(AI341:AJ341<>""),AI341:AJ341))) | IF(OR(F341="",AL341=""),"",IF(COUNT(AI341:AK341)=0,"",AL341-LOOKUP(2,1/(AI341:AK341<>""),AI341:AK341))) | IF(OR(F341="",AM341=""),"",IF(COUNT(AI341:AL341)=0,"",AM341-LOOKUP(2,1/(AI341:AL341<>""),AI341:AL341))) | IF(OR(F341="",AN341=""),"",IF(COUNT(AI341:AM341)=0,"",AN341-LOOKUP(2,1/(AI341:AM341<>""),AI341:AM341))) | IF(OR(F341="",AO341=""),"",IF(COUNT(AI341:AN341)=0,"",AO341-LOOKUP(2,1/(AI341:AN341<>""),AI341:AN341))) | IF(OR(F341="",AP341=""),"",IF(COUNT(AI341:AO341)=0,"",AP341-LOOKUP(2,1/(AI341:AO341<>""),AI341:AO341))) | IF(OR(F341="",AQ341=""),"",IF(COUNT(AI341:AP341)=0,"",AQ341-LOOKUP(2,1/(AI341:AP341<>""),AI341:AP341))) | IF(OR(F341="",AR341=""),"",IF(COUNT(AI341:AQ341)=0,"",AR341-LOOKUP(2,1/(AI341:AQ341<>""),AI341:AQ341))) | IF(OR(F341="",AS341=""),"",IF(COUNT(AI341:AR341)=0,"",AS341-LOOKUP(2,1/(AI341:AR341<>""),AI341:AR341))) | IF(OR(F341="",AT341=""),"",IF(COUNT(AI341:AS341)=0,"",AT341-LOOKUP(2,1/(AI341:AS341<>""),AI341:AS341))) | IF(OR(F341="",AU341=""),"",IF(COUNT(AI341:AT341)=0,"",AU341-LOOKUP(2,1/(AI341:AT341<>""),AI341:AT341))) | IF(OR(F341="",AV341=""),"",IF(COUNT(AI341:AU341)=0,"",AV341-LOOKUP(2,1/(AI341:AU341<>""),AI341:AU341))) | IF(J341="","All_Provinces",IFERROR(VLOOKUP(J341,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K341="","All_Districts",IFERROR(VLOOKUP(K341,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F342="","",ROW()-3) | AF2-WSM-28 | Package #28-AF2 WSM: Construction of 2 Check dams of 1. Chatqa Sai in Dahna-e-Ghori and 2.Tahiryan in Baghlan Markazi districts of Baghlan province. | 1 of 2 | AF2-WSM-A-061 | Chatqa Sai Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Dahna-e-Ghori | Chatqa Sai | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Arman Sharq Construction Company ASCC) | 054/2026 | 62969 | IF(AQ342="","",AQ342) |  | 4 | 2026-12-07 | IF(W342<>"",W342,IF(OR(T342="",V342=""),"",EDATE(T342,V342))) |  | 70 | Under Construction | Completed on Sep, 2026 | IF(F342="","",IF(COUNT(AI342:AV342)=0,IF(AA342="","Not started",AA342),SUBSTITUTE(LOOKUP(2,1/(AI342:AV342<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F342="",COUNT(AI342:AV342)=0),"",TODAY()-LOOKUP(2,1/(AI342:AV342<>""),AI342:AV342)) | IF(OR(F342="",COUNT(AI342:AV342)<2),"",LOOKUP(2,1/(AI342:AV342<>""),AI342:AV342)-MIN(AI342:AV342)) | IF(OR(AD342="",AC342="Not started",AC342=""),"",IFERROR(AD342-IF(VLOOKUP(AC342,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC342,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F342="","",IF(OR(AA342="Cancelled",AC342="Cancelled"),"Cancelled",IF(OR(AC342="Completed / Handover",Y342<>"",Z342>=100),"Completed — on track",IF(O342="Not awarded",IF(U342="",IF(X342="","No planned date",IF(TODAY()>X342,"Behind — past planned date",IF(X342-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U342,"Behind — award date passed",IF(U342-TODAY()<=30,"At risk — close to off track","On track"))),IF(X342="","No planned date",IF(AND(TODAY()>X342,OR(Z342="",Z342<100)),"Behind — past end date",IF(AND(T342<>"",X342<>"",Z342<>"",(Z342<100),((TODAY()-T342)/MAX(X342-T342,1)*100)-Z342>15),"Behind — progress lag",IF(AND(X342-TODAY()<=30,X342-TODAY()>=0,OR(Z342="",Z342<90)),"At risk — close to off track","On track")))))))) | IF(OR(F342="",AC342="Completed / Handover",AC342="Cancelled"),"",IF(O342="Not awarded",IF(U342<>"",U342-TODAY(),IF(X342="","",X342-TODAY())),IF(X342="","",X342-TODAY()))) | [8 empty] | 2026-08-08 | 2026-08-08 |  |  |  |  | IF(OR(F342="",AJ342=""),"",IF(COUNT(AI342:AI342)=0,"",AJ342-LOOKUP(2,1/(AI342:AI342<>""),AI342:AI342))) | IF(OR(F342="",AK342=""),"",IF(COUNT(AI342:AJ342)=0,"",AK342-LOOKUP(2,1/(AI342:AJ342<>""),AI342:AJ342))) | IF(OR(F342="",AL342=""),"",IF(COUNT(AI342:AK342)=0,"",AL342-LOOKUP(2,1/(AI342:AK342<>""),AI342:AK342))) | IF(OR(F342="",AM342=""),"",IF(COUNT(AI342:AL342)=0,"",AM342-LOOKUP(2,1/(AI342:AL342<>""),AI342:AL342))) | IF(OR(F342="",AN342=""),"",IF(COUNT(AI342:AM342)=0,"",AN342-LOOKUP(2,1/(AI342:AM342<>""),AI342:AM342))) | IF(OR(F342="",AO342=""),"",IF(COUNT(AI342:AN342)=0,"",AO342-LOOKUP(2,1/(AI342:AN342<>""),AI342:AN342))) | IF(OR(F342="",AP342=""),"",IF(COUNT(AI342:AO342)=0,"",AP342-LOOKUP(2,1/(AI342:AO342<>""),AI342:AO342))) | IF(OR(F342="",AQ342=""),"",IF(COUNT(AI342:AP342)=0,"",AQ342-LOOKUP(2,1/(AI342:AP342<>""),AI342:AP342))) | IF(OR(F342="",AR342=""),"",IF(COUNT(AI342:AQ342)=0,"",AR342-LOOKUP(2,1/(AI342:AQ342<>""),AI342:AQ342))) | IF(OR(F342="",AS342=""),"",IF(COUNT(AI342:AR342)=0,"",AS342-LOOKUP(2,1/(AI342:AR342<>""),AI342:AR342))) | IF(OR(F342="",AT342=""),"",IF(COUNT(AI342:AS342)=0,"",AT342-LOOKUP(2,1/(AI342:AS342<>""),AI342:AS342))) | IF(OR(F342="",AU342=""),"",IF(COUNT(AI342:AT342)=0,"",AU342-LOOKUP(2,1/(AI342:AT342<>""),AI342:AT342))) | IF(OR(F342="",AV342=""),"",IF(COUNT(AI342:AU342)=0,"",AV342-LOOKUP(2,1/(AI342:AU342<>""),AI342:AU342))) | IF(J342="","All_Provinces",IFERROR(VLOOKUP(J342,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K342="","All_Districts",IFERROR(VLOOKUP(K342,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F343="","",ROW()-3) | AF2-WSM-28 | Package #28-AF2 WSM: Construction of 2 Check dams of 1. Chatqa Sai in Dahna-e-Ghori and 2.Tahiryan in Baghlan Markazi districts of Baghlan province. | 2 of 2 | AF2-WSM-A-062 | Tahiryan Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | Northeast / Kunduz | Baghlan | Baghlan Markazi | Tahiryan | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Arman Sharq Construction Company ASCC) | 054/2026 | 36531 | IF(AQ343="","",AQ343) |  | 4 | 2026-12-07 | IF(W343<>"",W343,IF(OR(T343="",V343=""),"",EDATE(T343,V343))) |  | 5 | Under Construction | Completed on Sep, 2026 | IF(F343="","",IF(COUNT(AI343:AV343)=0,IF(AA343="","Not started",AA343),SUBSTITUTE(LOOKUP(2,1/(AI343:AV343<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F343="",COUNT(AI343:AV343)=0),"",TODAY()-LOOKUP(2,1/(AI343:AV343<>""),AI343:AV343)) | IF(OR(F343="",COUNT(AI343:AV343)<2),"",LOOKUP(2,1/(AI343:AV343<>""),AI343:AV343)-MIN(AI343:AV343)) | IF(OR(AD343="",AC343="Not started",AC343=""),"",IFERROR(AD343-IF(VLOOKUP(AC343,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC343,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F343="","",IF(OR(AA343="Cancelled",AC343="Cancelled"),"Cancelled",IF(OR(AC343="Completed / Handover",Y343<>"",Z343>=100),"Completed — on track",IF(O343="Not awarded",IF(U343="",IF(X343="","No planned date",IF(TODAY()>X343,"Behind — past planned date",IF(X343-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U343,"Behind — award date passed",IF(U343-TODAY()<=30,"At risk — close to off track","On track"))),IF(X343="","No planned date",IF(AND(TODAY()>X343,OR(Z343="",Z343<100)),"Behind — past end date",IF(AND(T343<>"",X343<>"",Z343<>"",(Z343<100),((TODAY()-T343)/MAX(X343-T343,1)*100)-Z343>15),"Behind — progress lag",IF(AND(X343-TODAY()<=30,X343-TODAY()>=0,OR(Z343="",Z343<90)),"At risk — close to off track","On track")))))))) | IF(OR(F343="",AC343="Completed / Handover",AC343="Cancelled"),"",IF(O343="Not awarded",IF(U343<>"",U343-TODAY(),IF(X343="","",X343-TODAY())),IF(X343="","",X343-TODAY()))) | [8 empty] | 2026-08-08 | 2026-08-08 |  |  |  |  | IF(OR(F343="",AJ343=""),"",IF(COUNT(AI343:AI343)=0,"",AJ343-LOOKUP(2,1/(AI343:AI343<>""),AI343:AI343))) | IF(OR(F343="",AK343=""),"",IF(COUNT(AI343:AJ343)=0,"",AK343-LOOKUP(2,1/(AI343:AJ343<>""),AI343:AJ343))) | IF(OR(F343="",AL343=""),"",IF(COUNT(AI343:AK343)=0,"",AL343-LOOKUP(2,1/(AI343:AK343<>""),AI343:AK343))) | IF(OR(F343="",AM343=""),"",IF(COUNT(AI343:AL343)=0,"",AM343-LOOKUP(2,1/(AI343:AL343<>""),AI343:AL343))) | IF(OR(F343="",AN343=""),"",IF(COUNT(AI343:AM343)=0,"",AN343-LOOKUP(2,1/(AI343:AM343<>""),AI343:AM343))) | IF(OR(F343="",AO343=""),"",IF(COUNT(AI343:AN343)=0,"",AO343-LOOKUP(2,1/(AI343:AN343<>""),AI343:AN343))) | IF(OR(F343="",AP343=""),"",IF(COUNT(AI343:AO343)=0,"",AP343-LOOKUP(2,1/(AI343:AO343<>""),AI343:AO343))) | IF(OR(F343="",AQ343=""),"",IF(COUNT(AI343:AP343)=0,"",AQ343-LOOKUP(2,1/(AI343:AP343<>""),AI343:AP343))) | IF(OR(F343="",AR343=""),"",IF(COUNT(AI343:AQ343)=0,"",AR343-LOOKUP(2,1/(AI343:AQ343<>""),AI343:AQ343))) | IF(OR(F343="",AS343=""),"",IF(COUNT(AI343:AR343)=0,"",AS343-LOOKUP(2,1/(AI343:AR343<>""),AI343:AR343))) | IF(OR(F343="",AT343=""),"",IF(COUNT(AI343:AS343)=0,"",AT343-LOOKUP(2,1/(AI343:AS343<>""),AI343:AS343))) | IF(OR(F343="",AU343=""),"",IF(COUNT(AI343:AT343)=0,"",AU343-LOOKUP(2,1/(AI343:AT343<>""),AI343:AT343))) | IF(OR(F343="",AV343=""),"",IF(COUNT(AI343:AU343)=0,"",AV343-LOOKUP(2,1/(AI343:AU343<>""),AI343:AU343))) | IF(J343="","All_Provinces",IFERROR(VLOOKUP(J343,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K343="","All_Districts",IFERROR(VLOOKUP(K343,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F344="","",ROW()-3) | AF2-WSM-29 | Package # 29-AF2 WSM: Construction 1. Alburs and 2. Marmul Check dams, located in Marmul and Alburs districts of Balkh province | 1 of 2 | AF2-WSM-A-063 | Alburz Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Alburz | Barga Turkmaniya, Tagab-e-Emam Sahib Fatima Khail, Khedr Khail | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Omar Mortaza Construction & Road Building JV Karwan Seraji Construction and Road Building Company (OMCC&KSCC) | 034/2026 | 54628.26 | IF(AQ344="","",AQ344) |  | 5 | 2026-10-11 | IF(W344<>"",W344,IF(OR(T344="",V344=""),"",EDATE(T344,V344))) |  | 100 | Completed / Handover | Completed on Sep, 2026 | IF(F344="","",IF(COUNT(AI344:AV344)=0,IF(AA344="","Not started",AA344),SUBSTITUTE(LOOKUP(2,1/(AI344:AV344<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F344="",COUNT(AI344:AV344)=0),"",TODAY()-LOOKUP(2,1/(AI344:AV344<>""),AI344:AV344)) | IF(OR(F344="",COUNT(AI344:AV344)<2),"",LOOKUP(2,1/(AI344:AV344<>""),AI344:AV344)-MIN(AI344:AV344)) | IF(OR(AD344="",AC344="Not started",AC344=""),"",IFERROR(AD344-IF(VLOOKUP(AC344,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC344,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F344="","",IF(OR(AA344="Cancelled",AC344="Cancelled"),"Cancelled",IF(OR(AC344="Completed / Handover",Y344<>"",Z344>=100),"Completed — on track",IF(O344="Not awarded",IF(U344="",IF(X344="","No planned date",IF(TODAY()>X344,"Behind — past planned date",IF(X344-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U344,"Behind — award date passed",IF(U344-TODAY()<=30,"At risk — close to off track","On track"))),IF(X344="","No planned date",IF(AND(TODAY()>X344,OR(Z344="",Z344<100)),"Behind — past end date",IF(AND(T344<>"",X344<>"",Z344<>"",(Z344<100),((TODAY()-T344)/MAX(X344-T344,1)*100)-Z344>15),"Behind — progress lag",IF(AND(X344-TODAY()<=30,X344-TODAY()>=0,OR(Z344="",Z344<90)),"At risk — close to off track","On track")))))))) | IF(OR(F344="",AC344="Completed / Handover",AC344="Cancelled"),"",IF(O344="Not awarded",IF(U344<>"",U344-TODAY(),IF(X344="","",X344-TODAY())),IF(X344="","",X344-TODAY()))) | [8 empty] | 2026-05-12 | 2026-05-12 | 2026-10-11 |  |  |  | IF(OR(F344="",AJ344=""),"",IF(COUNT(AI344:AI344)=0,"",AJ344-LOOKUP(2,1/(AI344:AI344<>""),AI344:AI344))) | IF(OR(F344="",AK344=""),"",IF(COUNT(AI344:AJ344)=0,"",AK344-LOOKUP(2,1/(AI344:AJ344<>""),AI344:AJ344))) | IF(OR(F344="",AL344=""),"",IF(COUNT(AI344:AK344)=0,"",AL344-LOOKUP(2,1/(AI344:AK344<>""),AI344:AK344))) | IF(OR(F344="",AM344=""),"",IF(COUNT(AI344:AL344)=0,"",AM344-LOOKUP(2,1/(AI344:AL344<>""),AI344:AL344))) | IF(OR(F344="",AN344=""),"",IF(COUNT(AI344:AM344)=0,"",AN344-LOOKUP(2,1/(AI344:AM344<>""),AI344:AM344))) | IF(OR(F344="",AO344=""),"",IF(COUNT(AI344:AN344)=0,"",AO344-LOOKUP(2,1/(AI344:AN344<>""),AI344:AN344))) | IF(OR(F344="",AP344=""),"",IF(COUNT(AI344:AO344)=0,"",AP344-LOOKUP(2,1/(AI344:AO344<>""),AI344:AO344))) | IF(OR(F344="",AQ344=""),"",IF(COUNT(AI344:AP344)=0,"",AQ344-LOOKUP(2,1/(AI344:AP344<>""),AI344:AP344))) | IF(OR(F344="",AR344=""),"",IF(COUNT(AI344:AQ344)=0,"",AR344-LOOKUP(2,1/(AI344:AQ344<>""),AI344:AQ344))) | IF(OR(F344="",AS344=""),"",IF(COUNT(AI344:AR344)=0,"",AS344-LOOKUP(2,1/(AI344:AR344<>""),AI344:AR344))) | IF(OR(F344="",AT344=""),"",IF(COUNT(AI344:AS344)=0,"",AT344-LOOKUP(2,1/(AI344:AS344<>""),AI344:AS344))) | IF(OR(F344="",AU344=""),"",IF(COUNT(AI344:AT344)=0,"",AU344-LOOKUP(2,1/(AI344:AT344<>""),AI344:AT344))) | IF(OR(F344="",AV344=""),"",IF(COUNT(AI344:AU344)=0,"",AV344-LOOKUP(2,1/(AI344:AU344<>""),AI344:AU344))) | IF(J344="","All_Provinces",IFERROR(VLOOKUP(J344,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K344="","All_Districts",IFERROR(VLOOKUP(K344,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F345="","",ROW()-3) | AF2-WSM-29 | Package # 29-AF2 WSM: Construction 1. Alburs and 2. Marmul Check dams, located in Marmul and Alburs districts of Balkh province | 2 of 2 | AF2-WSM-A-064 | Marmul Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Marmul | Pusht-e-Baghcha and Charmaghz Say | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Omar Mortaza Construction & Road Building JV Karwan Seraji Construction and Road Building Company (OMCC&KSCC) | 034/2026 | 45083.74 | IF(AQ345="","",AQ345) |  | 5 | 2026-10-11 | IF(W345<>"",W345,IF(OR(T345="",V345=""),"",EDATE(T345,V345))) |  | 98 | Under Construction | Completed on Sep, 2026 | IF(F345="","",IF(COUNT(AI345:AV345)=0,IF(AA345="","Not started",AA345),SUBSTITUTE(LOOKUP(2,1/(AI345:AV345<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F345="",COUNT(AI345:AV345)=0),"",TODAY()-LOOKUP(2,1/(AI345:AV345<>""),AI345:AV345)) | IF(OR(F345="",COUNT(AI345:AV345)<2),"",LOOKUP(2,1/(AI345:AV345<>""),AI345:AV345)-MIN(AI345:AV345)) | IF(OR(AD345="",AC345="Not started",AC345=""),"",IFERROR(AD345-IF(VLOOKUP(AC345,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC345,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F345="","",IF(OR(AA345="Cancelled",AC345="Cancelled"),"Cancelled",IF(OR(AC345="Completed / Handover",Y345<>"",Z345>=100),"Completed — on track",IF(O345="Not awarded",IF(U345="",IF(X345="","No planned date",IF(TODAY()>X345,"Behind — past planned date",IF(X345-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U345,"Behind — award date passed",IF(U345-TODAY()<=30,"At risk — close to off track","On track"))),IF(X345="","No planned date",IF(AND(TODAY()>X345,OR(Z345="",Z345<100)),"Behind — past end date",IF(AND(T345<>"",X345<>"",Z345<>"",(Z345<100),((TODAY()-T345)/MAX(X345-T345,1)*100)-Z345>15),"Behind — progress lag",IF(AND(X345-TODAY()<=30,X345-TODAY()>=0,OR(Z345="",Z345<90)),"At risk — close to off track","On track")))))))) | IF(OR(F345="",AC345="Completed / Handover",AC345="Cancelled"),"",IF(O345="Not awarded",IF(U345<>"",U345-TODAY(),IF(X345="","",X345-TODAY())),IF(X345="","",X345-TODAY()))) | [8 empty] | 2026-05-12 | 2026-05-12 |  |  |  |  | IF(OR(F345="",AJ345=""),"",IF(COUNT(AI345:AI345)=0,"",AJ345-LOOKUP(2,1/(AI345:AI345<>""),AI345:AI345))) | IF(OR(F345="",AK345=""),"",IF(COUNT(AI345:AJ345)=0,"",AK345-LOOKUP(2,1/(AI345:AJ345<>""),AI345:AJ345))) | IF(OR(F345="",AL345=""),"",IF(COUNT(AI345:AK345)=0,"",AL345-LOOKUP(2,1/(AI345:AK345<>""),AI345:AK345))) | IF(OR(F345="",AM345=""),"",IF(COUNT(AI345:AL345)=0,"",AM345-LOOKUP(2,1/(AI345:AL345<>""),AI345:AL345))) | IF(OR(F345="",AN345=""),"",IF(COUNT(AI345:AM345)=0,"",AN345-LOOKUP(2,1/(AI345:AM345<>""),AI345:AM345))) | IF(OR(F345="",AO345=""),"",IF(COUNT(AI345:AN345)=0,"",AO345-LOOKUP(2,1/(AI345:AN345<>""),AI345:AN345))) | IF(OR(F345="",AP345=""),"",IF(COUNT(AI345:AO345)=0,"",AP345-LOOKUP(2,1/(AI345:AO345<>""),AI345:AO345))) | IF(OR(F345="",AQ345=""),"",IF(COUNT(AI345:AP345)=0,"",AQ345-LOOKUP(2,1/(AI345:AP345<>""),AI345:AP345))) | IF(OR(F345="",AR345=""),"",IF(COUNT(AI345:AQ345)=0,"",AR345-LOOKUP(2,1/(AI345:AQ345<>""),AI345:AQ345))) | IF(OR(F345="",AS345=""),"",IF(COUNT(AI345:AR345)=0,"",AS345-LOOKUP(2,1/(AI345:AR345<>""),AI345:AR345))) | IF(OR(F345="",AT345=""),"",IF(COUNT(AI345:AS345)=0,"",AT345-LOOKUP(2,1/(AI345:AS345<>""),AI345:AS345))) | IF(OR(F345="",AU345=""),"",IF(COUNT(AI345:AT345)=0,"",AU345-LOOKUP(2,1/(AI345:AT345<>""),AI345:AT345))) | IF(OR(F345="",AV345=""),"",IF(COUNT(AI345:AU345)=0,"",AV345-LOOKUP(2,1/(AI345:AU345<>""),AI345:AU345))) | IF(J345="","All_Provinces",IFERROR(VLOOKUP(J345,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K345="","All_Districts",IFERROR(VLOOKUP(K345,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F346="","",ROW()-3) | AF2-WSM-30 | Package #30-AF2 WSM: Construction of 5 Check Damas of A. Majar site # 1 and site # 2; B.Elyasgar site # 3, site 4 and site # 5, located in Aljahad district of Sar-e-Pul province. | 1 of 2 | AF2-WSM-A-065 | Elyasgar Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sar-e-Pul | Aljahad | Ayob, Jar Abdara, Mula Salam, Haji Talib, Hajib Pirak | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Waheed Wahaj Construction Company (WWCC) | 050/2026 | 48085.97 | IF(AQ346="","",AQ346) |  | 4 | 2026-11-22 | IF(W346<>"",W346,IF(OR(T346="",V346=""),"",EDATE(T346,V346))) |  | 6 | Under Construction | The contract has recently been awarded. Mobilization is being carried out by the contractor. | IF(F346="","",IF(COUNT(AI346:AV346)=0,IF(AA346="","Not started",AA346),SUBSTITUTE(LOOKUP(2,1/(AI346:AV346<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F346="",COUNT(AI346:AV346)=0),"",TODAY()-LOOKUP(2,1/(AI346:AV346<>""),AI346:AV346)) | IF(OR(F346="",COUNT(AI346:AV346)<2),"",LOOKUP(2,1/(AI346:AV346<>""),AI346:AV346)-MIN(AI346:AV346)) | IF(OR(AD346="",AC346="Not started",AC346=""),"",IFERROR(AD346-IF(VLOOKUP(AC346,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC346,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F346="","",IF(OR(AA346="Cancelled",AC346="Cancelled"),"Cancelled",IF(OR(AC346="Completed / Handover",Y346<>"",Z346>=100),"Completed — on track",IF(O346="Not awarded",IF(U346="",IF(X346="","No planned date",IF(TODAY()>X346,"Behind — past planned date",IF(X346-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U346,"Behind — award date passed",IF(U346-TODAY()<=30,"At risk — close to off track","On track"))),IF(X346="","No planned date",IF(AND(TODAY()>X346,OR(Z346="",Z346<100)),"Behind — past end date",IF(AND(T346<>"",X346<>"",Z346<>"",(Z346<100),((TODAY()-T346)/MAX(X346-T346,1)*100)-Z346>15),"Behind — progress lag",IF(AND(X346-TODAY()<=30,X346-TODAY()>=0,OR(Z346="",Z346<90)),"At risk — close to off track","On track")))))))) | IF(OR(F346="",AC346="Completed / Handover",AC346="Cancelled"),"",IF(O346="Not awarded",IF(U346<>"",U346-TODAY(),IF(X346="","",X346-TODAY())),IF(X346="","",X346-TODAY()))) | [8 empty] | 2026-07-23 | 2026-07-23 |  |  |  |  | IF(OR(F346="",AJ346=""),"",IF(COUNT(AI346:AI346)=0,"",AJ346-LOOKUP(2,1/(AI346:AI346<>""),AI346:AI346))) | IF(OR(F346="",AK346=""),"",IF(COUNT(AI346:AJ346)=0,"",AK346-LOOKUP(2,1/(AI346:AJ346<>""),AI346:AJ346))) | IF(OR(F346="",AL346=""),"",IF(COUNT(AI346:AK346)=0,"",AL346-LOOKUP(2,1/(AI346:AK346<>""),AI346:AK346))) | IF(OR(F346="",AM346=""),"",IF(COUNT(AI346:AL346)=0,"",AM346-LOOKUP(2,1/(AI346:AL346<>""),AI346:AL346))) | IF(OR(F346="",AN346=""),"",IF(COUNT(AI346:AM346)=0,"",AN346-LOOKUP(2,1/(AI346:AM346<>""),AI346:AM346))) | IF(OR(F346="",AO346=""),"",IF(COUNT(AI346:AN346)=0,"",AO346-LOOKUP(2,1/(AI346:AN346<>""),AI346:AN346))) | IF(OR(F346="",AP346=""),"",IF(COUNT(AI346:AO346)=0,"",AP346-LOOKUP(2,1/(AI346:AO346<>""),AI346:AO346))) | IF(OR(F346="",AQ346=""),"",IF(COUNT(AI346:AP346)=0,"",AQ346-LOOKUP(2,1/(AI346:AP346<>""),AI346:AP346))) | IF(OR(F346="",AR346=""),"",IF(COUNT(AI346:AQ346)=0,"",AR346-LOOKUP(2,1/(AI346:AQ346<>""),AI346:AQ346))) | IF(OR(F346="",AS346=""),"",IF(COUNT(AI346:AR346)=0,"",AS346-LOOKUP(2,1/(AI346:AR346<>""),AI346:AR346))) | IF(OR(F346="",AT346=""),"",IF(COUNT(AI346:AS346)=0,"",AT346-LOOKUP(2,1/(AI346:AS346<>""),AI346:AS346))) | IF(OR(F346="",AU346=""),"",IF(COUNT(AI346:AT346)=0,"",AU346-LOOKUP(2,1/(AI346:AT346<>""),AI346:AT346))) | IF(OR(F346="",AV346=""),"",IF(COUNT(AI346:AU346)=0,"",AV346-LOOKUP(2,1/(AI346:AU346<>""),AI346:AU346))) | IF(J346="","All_Provinces",IFERROR(VLOOKUP(J346,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K346="","All_Districts",IFERROR(VLOOKUP(K346,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F347="","",ROW()-3) | AF2-WSM-30 | Package #30-AF2 WSM: Construction of 5 Check Damas of A. Majar site # 1 and site # 2; B.Elyasgar site # 3, site 4 and site # 5, located in Aljahad district of Sar-e-Pul province. | 2 of 2 | AF2-WSM-A-066 | Majar Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Sar-e-Pul | Aljahad | Mullah Baba, Bahauden, Katlo Soy, Majar Ulia, Majar Aji | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Waheed Wahaj Construction Company (WWCC) | 050/2026 | 22485.14 | IF(AQ347="","",AQ347) |  | 4 | 2026-11-22 | IF(W347<>"",W347,IF(OR(T347="",V347=""),"",EDATE(T347,V347))) |  | 6 | Under Construction | The contract has recently been awarded. Mobilization is being carried out by the contractor. | IF(F347="","",IF(COUNT(AI347:AV347)=0,IF(AA347="","Not started",AA347),SUBSTITUTE(LOOKUP(2,1/(AI347:AV347<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F347="",COUNT(AI347:AV347)=0),"",TODAY()-LOOKUP(2,1/(AI347:AV347<>""),AI347:AV347)) | IF(OR(F347="",COUNT(AI347:AV347)<2),"",LOOKUP(2,1/(AI347:AV347<>""),AI347:AV347)-MIN(AI347:AV347)) | IF(OR(AD347="",AC347="Not started",AC347=""),"",IFERROR(AD347-IF(VLOOKUP(AC347,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC347,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F347="","",IF(OR(AA347="Cancelled",AC347="Cancelled"),"Cancelled",IF(OR(AC347="Completed / Handover",Y347<>"",Z347>=100),"Completed — on track",IF(O347="Not awarded",IF(U347="",IF(X347="","No planned date",IF(TODAY()>X347,"Behind — past planned date",IF(X347-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U347,"Behind — award date passed",IF(U347-TODAY()<=30,"At risk — close to off track","On track"))),IF(X347="","No planned date",IF(AND(TODAY()>X347,OR(Z347="",Z347<100)),"Behind — past end date",IF(AND(T347<>"",X347<>"",Z347<>"",(Z347<100),((TODAY()-T347)/MAX(X347-T347,1)*100)-Z347>15),"Behind — progress lag",IF(AND(X347-TODAY()<=30,X347-TODAY()>=0,OR(Z347="",Z347<90)),"At risk — close to off track","On track")))))))) | IF(OR(F347="",AC347="Completed / Handover",AC347="Cancelled"),"",IF(O347="Not awarded",IF(U347<>"",U347-TODAY(),IF(X347="","",X347-TODAY())),IF(X347="","",X347-TODAY()))) | [8 empty] | 2026-07-23 | 2026-07-23 |  |  |  |  | IF(OR(F347="",AJ347=""),"",IF(COUNT(AI347:AI347)=0,"",AJ347-LOOKUP(2,1/(AI347:AI347<>""),AI347:AI347))) | IF(OR(F347="",AK347=""),"",IF(COUNT(AI347:AJ347)=0,"",AK347-LOOKUP(2,1/(AI347:AJ347<>""),AI347:AJ347))) | IF(OR(F347="",AL347=""),"",IF(COUNT(AI347:AK347)=0,"",AL347-LOOKUP(2,1/(AI347:AK347<>""),AI347:AK347))) | IF(OR(F347="",AM347=""),"",IF(COUNT(AI347:AL347)=0,"",AM347-LOOKUP(2,1/(AI347:AL347<>""),AI347:AL347))) | IF(OR(F347="",AN347=""),"",IF(COUNT(AI347:AM347)=0,"",AN347-LOOKUP(2,1/(AI347:AM347<>""),AI347:AM347))) | IF(OR(F347="",AO347=""),"",IF(COUNT(AI347:AN347)=0,"",AO347-LOOKUP(2,1/(AI347:AN347<>""),AI347:AN347))) | IF(OR(F347="",AP347=""),"",IF(COUNT(AI347:AO347)=0,"",AP347-LOOKUP(2,1/(AI347:AO347<>""),AI347:AO347))) | IF(OR(F347="",AQ347=""),"",IF(COUNT(AI347:AP347)=0,"",AQ347-LOOKUP(2,1/(AI347:AP347<>""),AI347:AP347))) | IF(OR(F347="",AR347=""),"",IF(COUNT(AI347:AQ347)=0,"",AR347-LOOKUP(2,1/(AI347:AQ347<>""),AI347:AQ347))) | IF(OR(F347="",AS347=""),"",IF(COUNT(AI347:AR347)=0,"",AS347-LOOKUP(2,1/(AI347:AR347<>""),AI347:AR347))) | IF(OR(F347="",AT347=""),"",IF(COUNT(AI347:AS347)=0,"",AT347-LOOKUP(2,1/(AI347:AS347<>""),AI347:AS347))) | IF(OR(F347="",AU347=""),"",IF(COUNT(AI347:AT347)=0,"",AU347-LOOKUP(2,1/(AI347:AT347<>""),AI347:AT347))) | IF(OR(F347="",AV347=""),"",IF(COUNT(AI347:AU347)=0,"",AV347-LOOKUP(2,1/(AI347:AU347<>""),AI347:AU347))) | IF(J347="","All_Provinces",IFERROR(VLOOKUP(J347,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K347="","All_Districts",IFERROR(VLOOKUP(K347,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F348="","",ROW()-3) | AF2-WSM-31 | Package # 31-AF2 WSM: Construction of 1. Khaibar and 2. Chelgazi Check dams, located in Khaibar and Chelgazi districts of Faryab province. | 1 of 2 | AF2-WSM-A-067 | Chelgazi Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Faryab | Chelgazi | Hazar qala and Aq Mazar | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Malik Hajdar Construction and Road Company (MHCC) | 033/2026 | 36101.03 | IF(AQ348="","",AQ348) |  | 4 | 2026-09-06 | IF(W348<>"",W348,IF(OR(T348="",V348=""),"",EDATE(T348,V348))) |  | 100 | Completed / Handover | Completed on Aug, 2026 | IF(F348="","",IF(COUNT(AI348:AV348)=0,IF(AA348="","Not started",AA348),SUBSTITUTE(LOOKUP(2,1/(AI348:AV348<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F348="",COUNT(AI348:AV348)=0),"",TODAY()-LOOKUP(2,1/(AI348:AV348<>""),AI348:AV348)) | IF(OR(F348="",COUNT(AI348:AV348)<2),"",LOOKUP(2,1/(AI348:AV348<>""),AI348:AV348)-MIN(AI348:AV348)) | IF(OR(AD348="",AC348="Not started",AC348=""),"",IFERROR(AD348-IF(VLOOKUP(AC348,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC348,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F348="","",IF(OR(AA348="Cancelled",AC348="Cancelled"),"Cancelled",IF(OR(AC348="Completed / Handover",Y348<>"",Z348>=100),"Completed — on track",IF(O348="Not awarded",IF(U348="",IF(X348="","No planned date",IF(TODAY()>X348,"Behind — past planned date",IF(X348-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U348,"Behind — award date passed",IF(U348-TODAY()<=30,"At risk — close to off track","On track"))),IF(X348="","No planned date",IF(AND(TODAY()>X348,OR(Z348="",Z348<100)),"Behind — past end date",IF(AND(T348<>"",X348<>"",Z348<>"",(Z348<100),((TODAY()-T348)/MAX(X348-T348,1)*100)-Z348>15),"Behind — progress lag",IF(AND(X348-TODAY()<=30,X348-TODAY()>=0,OR(Z348="",Z348<90)),"At risk — close to off track","On track")))))))) | IF(OR(F348="",AC348="Completed / Handover",AC348="Cancelled"),"",IF(O348="Not awarded",IF(U348<>"",U348-TODAY(),IF(X348="","",X348-TODAY())),IF(X348="","",X348-TODAY()))) | [8 empty] | 2026-05-07 | 2026-05-07 | 2026-09-06 |  |  |  | IF(OR(F348="",AJ348=""),"",IF(COUNT(AI348:AI348)=0,"",AJ348-LOOKUP(2,1/(AI348:AI348<>""),AI348:AI348))) | IF(OR(F348="",AK348=""),"",IF(COUNT(AI348:AJ348)=0,"",AK348-LOOKUP(2,1/(AI348:AJ348<>""),AI348:AJ348))) | IF(OR(F348="",AL348=""),"",IF(COUNT(AI348:AK348)=0,"",AL348-LOOKUP(2,1/(AI348:AK348<>""),AI348:AK348))) | IF(OR(F348="",AM348=""),"",IF(COUNT(AI348:AL348)=0,"",AM348-LOOKUP(2,1/(AI348:AL348<>""),AI348:AL348))) | IF(OR(F348="",AN348=""),"",IF(COUNT(AI348:AM348)=0,"",AN348-LOOKUP(2,1/(AI348:AM348<>""),AI348:AM348))) | IF(OR(F348="",AO348=""),"",IF(COUNT(AI348:AN348)=0,"",AO348-LOOKUP(2,1/(AI348:AN348<>""),AI348:AN348))) | IF(OR(F348="",AP348=""),"",IF(COUNT(AI348:AO348)=0,"",AP348-LOOKUP(2,1/(AI348:AO348<>""),AI348:AO348))) | IF(OR(F348="",AQ348=""),"",IF(COUNT(AI348:AP348)=0,"",AQ348-LOOKUP(2,1/(AI348:AP348<>""),AI348:AP348))) | IF(OR(F348="",AR348=""),"",IF(COUNT(AI348:AQ348)=0,"",AR348-LOOKUP(2,1/(AI348:AQ348<>""),AI348:AQ348))) | IF(OR(F348="",AS348=""),"",IF(COUNT(AI348:AR348)=0,"",AS348-LOOKUP(2,1/(AI348:AR348<>""),AI348:AR348))) | IF(OR(F348="",AT348=""),"",IF(COUNT(AI348:AS348)=0,"",AT348-LOOKUP(2,1/(AI348:AS348<>""),AI348:AS348))) | IF(OR(F348="",AU348=""),"",IF(COUNT(AI348:AT348)=0,"",AU348-LOOKUP(2,1/(AI348:AT348<>""),AI348:AT348))) | IF(OR(F348="",AV348=""),"",IF(COUNT(AI348:AU348)=0,"",AV348-LOOKUP(2,1/(AI348:AU348<>""),AI348:AU348))) | IF(J348="","All_Provinces",IFERROR(VLOOKUP(J348,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K348="","All_Districts",IFERROR(VLOOKUP(K348,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F349="","",ROW()-3) | AF2-WSM-31 | Package # 31-AF2 WSM: Construction of 1. Khaibar and 2. Chelgazi Check dams, located in Khaibar and Chelgazi districts of Faryab province. | 2 of 2 | AF2-WSM-A-068 | Khaibar Check dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Faryab | Khaibar | Mesh mast and Pasha Khan Abdal | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Malik Hajdar Construction and Road Company (MHCC) | 033/2026 | 44507.76 | IF(AQ349="","",AQ349) |  | 4 | 2026-09-06 | IF(W349<>"",W349,IF(OR(T349="",V349=""),"",EDATE(T349,V349))) |  | 100 | Completed / Handover | Completed on Aug, 2026 | IF(F349="","",IF(COUNT(AI349:AV349)=0,IF(AA349="","Not started",AA349),SUBSTITUTE(LOOKUP(2,1/(AI349:AV349<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F349="",COUNT(AI349:AV349)=0),"",TODAY()-LOOKUP(2,1/(AI349:AV349<>""),AI349:AV349)) | IF(OR(F349="",COUNT(AI349:AV349)<2),"",LOOKUP(2,1/(AI349:AV349<>""),AI349:AV349)-MIN(AI349:AV349)) | IF(OR(AD349="",AC349="Not started",AC349=""),"",IFERROR(AD349-IF(VLOOKUP(AC349,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC349,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F349="","",IF(OR(AA349="Cancelled",AC349="Cancelled"),"Cancelled",IF(OR(AC349="Completed / Handover",Y349<>"",Z349>=100),"Completed — on track",IF(O349="Not awarded",IF(U349="",IF(X349="","No planned date",IF(TODAY()>X349,"Behind — past planned date",IF(X349-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U349,"Behind — award date passed",IF(U349-TODAY()<=30,"At risk — close to off track","On track"))),IF(X349="","No planned date",IF(AND(TODAY()>X349,OR(Z349="",Z349<100)),"Behind — past end date",IF(AND(T349<>"",X349<>"",Z349<>"",(Z349<100),((TODAY()-T349)/MAX(X349-T349,1)*100)-Z349>15),"Behind — progress lag",IF(AND(X349-TODAY()<=30,X349-TODAY()>=0,OR(Z349="",Z349<90)),"At risk — close to off track","On track")))))))) | IF(OR(F349="",AC349="Completed / Handover",AC349="Cancelled"),"",IF(O349="Not awarded",IF(U349<>"",U349-TODAY(),IF(X349="","",X349-TODAY())),IF(X349="","",X349-TODAY()))) | [8 empty] | 2026-05-07 | 2026-05-07 | 2026-09-06 |  |  |  | IF(OR(F349="",AJ349=""),"",IF(COUNT(AI349:AI349)=0,"",AJ349-LOOKUP(2,1/(AI349:AI349<>""),AI349:AI349))) | IF(OR(F349="",AK349=""),"",IF(COUNT(AI349:AJ349)=0,"",AK349-LOOKUP(2,1/(AI349:AJ349<>""),AI349:AJ349))) | IF(OR(F349="",AL349=""),"",IF(COUNT(AI349:AK349)=0,"",AL349-LOOKUP(2,1/(AI349:AK349<>""),AI349:AK349))) | IF(OR(F349="",AM349=""),"",IF(COUNT(AI349:AL349)=0,"",AM349-LOOKUP(2,1/(AI349:AL349<>""),AI349:AL349))) | IF(OR(F349="",AN349=""),"",IF(COUNT(AI349:AM349)=0,"",AN349-LOOKUP(2,1/(AI349:AM349<>""),AI349:AM349))) | IF(OR(F349="",AO349=""),"",IF(COUNT(AI349:AN349)=0,"",AO349-LOOKUP(2,1/(AI349:AN349<>""),AI349:AN349))) | IF(OR(F349="",AP349=""),"",IF(COUNT(AI349:AO349)=0,"",AP349-LOOKUP(2,1/(AI349:AO349<>""),AI349:AO349))) | IF(OR(F349="",AQ349=""),"",IF(COUNT(AI349:AP349)=0,"",AQ349-LOOKUP(2,1/(AI349:AP349<>""),AI349:AP349))) | IF(OR(F349="",AR349=""),"",IF(COUNT(AI349:AQ349)=0,"",AR349-LOOKUP(2,1/(AI349:AQ349<>""),AI349:AQ349))) | IF(OR(F349="",AS349=""),"",IF(COUNT(AI349:AR349)=0,"",AS349-LOOKUP(2,1/(AI349:AR349<>""),AI349:AR349))) | IF(OR(F349="",AT349=""),"",IF(COUNT(AI349:AS349)=0,"",AT349-LOOKUP(2,1/(AI349:AS349<>""),AI349:AS349))) | IF(OR(F349="",AU349=""),"",IF(COUNT(AI349:AT349)=0,"",AU349-LOOKUP(2,1/(AI349:AT349<>""),AI349:AT349))) | IF(OR(F349="",AV349=""),"",IF(COUNT(AI349:AU349)=0,"",AV349-LOOKUP(2,1/(AI349:AU349<>""),AI349:AU349))) | IF(J349="","All_Provinces",IFERROR(VLOOKUP(J349,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K349="","All_Districts",IFERROR(VLOOKUP(K349,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F350="","",ROW()-3) | AF2-WSM-32 | Package #32-AF2 WSM: Construction of Tai Khunak 4 Check dams of A. Khoja Momin site # 1 and site # 2, B. Sari Shor site # 3 and site #4, located in Aybak district of Samangan province. | 1 of 2 | AF2-WSM-A-069 | Taikhunak (Khoja Momen) Check dams site # 1 and #2 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Aybak | Shorabak, Khoja Momen. | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Mudeser Bigmurad Construction Company (MBCC) | 045/2026 | 61755.98 | IF(AQ350="","",AQ350) |  | 4 | 2026-11-21 | IF(W350<>"",W350,IF(OR(T350="",V350=""),"",EDATE(T350,V350))) |  | 30 | Under Construction | The contract has recently been awarded; Mobilzation has started. | IF(F350="","",IF(COUNT(AI350:AV350)=0,IF(AA350="","Not started",AA350),SUBSTITUTE(LOOKUP(2,1/(AI350:AV350<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F350="",COUNT(AI350:AV350)=0),"",TODAY()-LOOKUP(2,1/(AI350:AV350<>""),AI350:AV350)) | IF(OR(F350="",COUNT(AI350:AV350)<2),"",LOOKUP(2,1/(AI350:AV350<>""),AI350:AV350)-MIN(AI350:AV350)) | IF(OR(AD350="",AC350="Not started",AC350=""),"",IFERROR(AD350-IF(VLOOKUP(AC350,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC350,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F350="","",IF(OR(AA350="Cancelled",AC350="Cancelled"),"Cancelled",IF(OR(AC350="Completed / Handover",Y350<>"",Z350>=100),"Completed — on track",IF(O350="Not awarded",IF(U350="",IF(X350="","No planned date",IF(TODAY()>X350,"Behind — past planned date",IF(X350-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U350,"Behind — award date passed",IF(U350-TODAY()<=30,"At risk — close to off track","On track"))),IF(X350="","No planned date",IF(AND(TODAY()>X350,OR(Z350="",Z350<100)),"Behind — past end date",IF(AND(T350<>"",X350<>"",Z350<>"",(Z350<100),((TODAY()-T350)/MAX(X350-T350,1)*100)-Z350>15),"Behind — progress lag",IF(AND(X350-TODAY()<=30,X350-TODAY()>=0,OR(Z350="",Z350<90)),"At risk — close to off track","On track")))))))) | IF(OR(F350="",AC350="Completed / Handover",AC350="Cancelled"),"",IF(O350="Not awarded",IF(U350<>"",U350-TODAY(),IF(X350="","",X350-TODAY())),IF(X350="","",X350-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F350="",AJ350=""),"",IF(COUNT(AI350:AI350)=0,"",AJ350-LOOKUP(2,1/(AI350:AI350<>""),AI350:AI350))) | IF(OR(F350="",AK350=""),"",IF(COUNT(AI350:AJ350)=0,"",AK350-LOOKUP(2,1/(AI350:AJ350<>""),AI350:AJ350))) | IF(OR(F350="",AL350=""),"",IF(COUNT(AI350:AK350)=0,"",AL350-LOOKUP(2,1/(AI350:AK350<>""),AI350:AK350))) | IF(OR(F350="",AM350=""),"",IF(COUNT(AI350:AL350)=0,"",AM350-LOOKUP(2,1/(AI350:AL350<>""),AI350:AL350))) | IF(OR(F350="",AN350=""),"",IF(COUNT(AI350:AM350)=0,"",AN350-LOOKUP(2,1/(AI350:AM350<>""),AI350:AM350))) | IF(OR(F350="",AO350=""),"",IF(COUNT(AI350:AN350)=0,"",AO350-LOOKUP(2,1/(AI350:AN350<>""),AI350:AN350))) | IF(OR(F350="",AP350=""),"",IF(COUNT(AI350:AO350)=0,"",AP350-LOOKUP(2,1/(AI350:AO350<>""),AI350:AO350))) | IF(OR(F350="",AQ350=""),"",IF(COUNT(AI350:AP350)=0,"",AQ350-LOOKUP(2,1/(AI350:AP350<>""),AI350:AP350))) | IF(OR(F350="",AR350=""),"",IF(COUNT(AI350:AQ350)=0,"",AR350-LOOKUP(2,1/(AI350:AQ350<>""),AI350:AQ350))) | IF(OR(F350="",AS350=""),"",IF(COUNT(AI350:AR350)=0,"",AS350-LOOKUP(2,1/(AI350:AR350<>""),AI350:AR350))) | IF(OR(F350="",AT350=""),"",IF(COUNT(AI350:AS350)=0,"",AT350-LOOKUP(2,1/(AI350:AS350<>""),AI350:AS350))) | IF(OR(F350="",AU350=""),"",IF(COUNT(AI350:AT350)=0,"",AU350-LOOKUP(2,1/(AI350:AT350<>""),AI350:AT350))) | IF(OR(F350="",AV350=""),"",IF(COUNT(AI350:AU350)=0,"",AV350-LOOKUP(2,1/(AI350:AU350<>""),AI350:AU350))) | IF(J350="","All_Provinces",IFERROR(VLOOKUP(J350,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K350="","All_Districts",IFERROR(VLOOKUP(K350,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F351="","",ROW()-3) | AF2-WSM-32 | Package #32-AF2 WSM: Construction of Tai Khunak 4 Check dams of A. Khoja Momin site # 1 and site # 2, B. Sari Shor site # 3 and site #4, located in Aybak district of Samangan province. | 2 of 2 | AF2-WSM-A-070 | Taikhunak (Sari Shor) 2 Check dams site # 3 and # 4 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Samangan | Aybak | Sar-i-Shor, Ozon Say | World Bank (WBK/AF-2) | Awarded | 3.WSM awarded contracts | Mudeser Bigmurad Construction Company (MBCC) | 045/2026 | 53185.5 | IF(AQ351="","",AQ351) |  | 4 | 2026-11-21 | IF(W351<>"",W351,IF(OR(T351="",V351=""),"",EDATE(T351,V351))) |  | 19.5 | Under Construction | The contract has recently been awarded; Mobilzation has started. | IF(F351="","",IF(COUNT(AI351:AV351)=0,IF(AA351="","Not started",AA351),SUBSTITUTE(LOOKUP(2,1/(AI351:AV351<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F351="",COUNT(AI351:AV351)=0),"",TODAY()-LOOKUP(2,1/(AI351:AV351<>""),AI351:AV351)) | IF(OR(F351="",COUNT(AI351:AV351)<2),"",LOOKUP(2,1/(AI351:AV351<>""),AI351:AV351)-MIN(AI351:AV351)) | IF(OR(AD351="",AC351="Not started",AC351=""),"",IFERROR(AD351-IF(VLOOKUP(AC351,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC351,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F351="","",IF(OR(AA351="Cancelled",AC351="Cancelled"),"Cancelled",IF(OR(AC351="Completed / Handover",Y351<>"",Z351>=100),"Completed — on track",IF(O351="Not awarded",IF(U351="",IF(X351="","No planned date",IF(TODAY()>X351,"Behind — past planned date",IF(X351-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U351,"Behind — award date passed",IF(U351-TODAY()<=30,"At risk — close to off track","On track"))),IF(X351="","No planned date",IF(AND(TODAY()>X351,OR(Z351="",Z351<100)),"Behind — past end date",IF(AND(T351<>"",X351<>"",Z351<>"",(Z351<100),((TODAY()-T351)/MAX(X351-T351,1)*100)-Z351>15),"Behind — progress lag",IF(AND(X351-TODAY()<=30,X351-TODAY()>=0,OR(Z351="",Z351<90)),"At risk — close to off track","On track")))))))) | IF(OR(F351="",AC351="Completed / Handover",AC351="Cancelled"),"",IF(O351="Not awarded",IF(U351<>"",U351-TODAY(),IF(X351="","",X351-TODAY())),IF(X351="","",X351-TODAY()))) | [8 empty] | 2026-07-22 | 2026-07-22 |  |  |  |  | IF(OR(F351="",AJ351=""),"",IF(COUNT(AI351:AI351)=0,"",AJ351-LOOKUP(2,1/(AI351:AI351<>""),AI351:AI351))) | IF(OR(F351="",AK351=""),"",IF(COUNT(AI351:AJ351)=0,"",AK351-LOOKUP(2,1/(AI351:AJ351<>""),AI351:AJ351))) | IF(OR(F351="",AL351=""),"",IF(COUNT(AI351:AK351)=0,"",AL351-LOOKUP(2,1/(AI351:AK351<>""),AI351:AK351))) | IF(OR(F351="",AM351=""),"",IF(COUNT(AI351:AL351)=0,"",AM351-LOOKUP(2,1/(AI351:AL351<>""),AI351:AL351))) | IF(OR(F351="",AN351=""),"",IF(COUNT(AI351:AM351)=0,"",AN351-LOOKUP(2,1/(AI351:AM351<>""),AI351:AM351))) | IF(OR(F351="",AO351=""),"",IF(COUNT(AI351:AN351)=0,"",AO351-LOOKUP(2,1/(AI351:AN351<>""),AI351:AN351))) | IF(OR(F351="",AP351=""),"",IF(COUNT(AI351:AO351)=0,"",AP351-LOOKUP(2,1/(AI351:AO351<>""),AI351:AO351))) | IF(OR(F351="",AQ351=""),"",IF(COUNT(AI351:AP351)=0,"",AQ351-LOOKUP(2,1/(AI351:AP351<>""),AI351:AP351))) | IF(OR(F351="",AR351=""),"",IF(COUNT(AI351:AQ351)=0,"",AR351-LOOKUP(2,1/(AI351:AQ351<>""),AI351:AQ351))) | IF(OR(F351="",AS351=""),"",IF(COUNT(AI351:AR351)=0,"",AS351-LOOKUP(2,1/(AI351:AR351<>""),AI351:AR351))) | IF(OR(F351="",AT351=""),"",IF(COUNT(AI351:AS351)=0,"",AT351-LOOKUP(2,1/(AI351:AS351<>""),AI351:AS351))) | IF(OR(F351="",AU351=""),"",IF(COUNT(AI351:AT351)=0,"",AU351-LOOKUP(2,1/(AI351:AT351<>""),AI351:AT351))) | IF(OR(F351="",AV351=""),"",IF(COUNT(AI351:AU351)=0,"",AV351-LOOKUP(2,1/(AI351:AU351<>""),AI351:AU351))) | IF(J351="","All_Provinces",IFERROR(VLOOKUP(J351,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K351="","All_Districts",IFERROR(VLOOKUP(K351,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F352="","",ROW()-3) | AF2-WSM-33 | Package #33-AF2 WSM: Construction of 2 Check dams of Ala Taba-1 and Ala Taba-2 in Ablurz district of Balkh province. | 1 of 2 | AF2-WSM-N-021 | Ala Taba-1 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Alburz | Chashma Gudar and Ala Tawa | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 55029 | IF(AQ352="","",AQ352) | 2026-11-25 | 5.9 | 2027-05-24 | IF(W352<>"",W352,IF(OR(T352="",V352=""),"",EDATE(T352,V352))) |  |  | PR to be Raised | Construction period six months including slack period (Dec-Jan). | IF(F352="","",IF(COUNT(AI352:AV352)=0,IF(AA352="","Not started",AA352),SUBSTITUTE(LOOKUP(2,1/(AI352:AV352<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F352="",COUNT(AI352:AV352)=0),"",TODAY()-LOOKUP(2,1/(AI352:AV352<>""),AI352:AV352)) | IF(OR(F352="",COUNT(AI352:AV352)<2),"",LOOKUP(2,1/(AI352:AV352<>""),AI352:AV352)-MIN(AI352:AV352)) | IF(OR(AD352="",AC352="Not started",AC352=""),"",IFERROR(AD352-IF(VLOOKUP(AC352,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC352,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F352="","",IF(OR(AA352="Cancelled",AC352="Cancelled"),"Cancelled",IF(OR(AC352="Completed / Handover",Y352<>"",Z352>=100),"Completed — on track",IF(O352="Not awarded",IF(U352="",IF(X352="","No planned date",IF(TODAY()>X352,"Behind — past planned date",IF(X352-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U352,"Behind — award date passed",IF(U352-TODAY()<=30,"At risk — close to off track","On track"))),IF(X352="","No planned date",IF(AND(TODAY()>X352,OR(Z352="",Z352<100)),"Behind — past end date",IF(AND(T352<>"",X352<>"",Z352<>"",(Z352<100),((TODAY()-T352)/MAX(X352-T352,1)*100)-Z352>15),"Behind — progress lag",IF(AND(X352-TODAY()<=30,X352-TODAY()>=0,OR(Z352="",Z352<90)),"At risk — close to off track","On track")))))))) | IF(OR(F352="",AC352="Completed / Handover",AC352="Cancelled"),"",IF(O352="Not awarded",IF(U352<>"",U352-TODAY(),IF(X352="","",X352-TODAY())),IF(X352="","",X352-TODAY()))) | [14 empty] | IF(OR(F352="",AJ352=""),"",IF(COUNT(AI352:AI352)=0,"",AJ352-LOOKUP(2,1/(AI352:AI352<>""),AI352:AI352))) | IF(OR(F352="",AK352=""),"",IF(COUNT(AI352:AJ352)=0,"",AK352-LOOKUP(2,1/(AI352:AJ352<>""),AI352:AJ352))) | IF(OR(F352="",AL352=""),"",IF(COUNT(AI352:AK352)=0,"",AL352-LOOKUP(2,1/(AI352:AK352<>""),AI352:AK352))) | IF(OR(F352="",AM352=""),"",IF(COUNT(AI352:AL352)=0,"",AM352-LOOKUP(2,1/(AI352:AL352<>""),AI352:AL352))) | IF(OR(F352="",AN352=""),"",IF(COUNT(AI352:AM352)=0,"",AN352-LOOKUP(2,1/(AI352:AM352<>""),AI352:AM352))) | IF(OR(F352="",AO352=""),"",IF(COUNT(AI352:AN352)=0,"",AO352-LOOKUP(2,1/(AI352:AN352<>""),AI352:AN352))) | IF(OR(F352="",AP352=""),"",IF(COUNT(AI352:AO352)=0,"",AP352-LOOKUP(2,1/(AI352:AO352<>""),AI352:AO352))) | IF(OR(F352="",AQ352=""),"",IF(COUNT(AI352:AP352)=0,"",AQ352-LOOKUP(2,1/(AI352:AP352<>""),AI352:AP352))) | IF(OR(F352="",AR352=""),"",IF(COUNT(AI352:AQ352)=0,"",AR352-LOOKUP(2,1/(AI352:AQ352<>""),AI352:AQ352))) | IF(OR(F352="",AS352=""),"",IF(COUNT(AI352:AR352)=0,"",AS352-LOOKUP(2,1/(AI352:AR352<>""),AI352:AR352))) | IF(OR(F352="",AT352=""),"",IF(COUNT(AI352:AS352)=0,"",AT352-LOOKUP(2,1/(AI352:AS352<>""),AI352:AS352))) | IF(OR(F352="",AU352=""),"",IF(COUNT(AI352:AT352)=0,"",AU352-LOOKUP(2,1/(AI352:AT352<>""),AI352:AT352))) | IF(OR(F352="",AV352=""),"",IF(COUNT(AI352:AU352)=0,"",AV352-LOOKUP(2,1/(AI352:AU352<>""),AI352:AU352))) | IF(J352="","All_Provinces",IFERROR(VLOOKUP(J352,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K352="","All_Districts",IFERROR(VLOOKUP(K352,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F353="","",ROW()-3) | AF2-WSM-33 | Package #33-AF2 WSM: Construction of 2 Check dams of Ala Taba-1 and Ala Taba-2 in Ablurz district of Balkh province. | 2 of 2 | AF2-WSM-N-022 | Ala Taba-2 | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | North / Mazar | Balkh | Alburz | Sang Toda and Charso | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 55029 | IF(AQ353="","",AQ353) | 2026-11-25 | 5.9 | 2027-05-24 | IF(W353<>"",W353,IF(OR(T353="",V353=""),"",EDATE(T353,V353))) |  |  | PR to be Raised | Construction period six months including slack period (Dec-Jan). | IF(F353="","",IF(COUNT(AI353:AV353)=0,IF(AA353="","Not started",AA353),SUBSTITUTE(LOOKUP(2,1/(AI353:AV353<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F353="",COUNT(AI353:AV353)=0),"",TODAY()-LOOKUP(2,1/(AI353:AV353<>""),AI353:AV353)) | IF(OR(F353="",COUNT(AI353:AV353)<2),"",LOOKUP(2,1/(AI353:AV353<>""),AI353:AV353)-MIN(AI353:AV353)) | IF(OR(AD353="",AC353="Not started",AC353=""),"",IFERROR(AD353-IF(VLOOKUP(AC353,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC353,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F353="","",IF(OR(AA353="Cancelled",AC353="Cancelled"),"Cancelled",IF(OR(AC353="Completed / Handover",Y353<>"",Z353>=100),"Completed — on track",IF(O353="Not awarded",IF(U353="",IF(X353="","No planned date",IF(TODAY()>X353,"Behind — past planned date",IF(X353-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U353,"Behind — award date passed",IF(U353-TODAY()<=30,"At risk — close to off track","On track"))),IF(X353="","No planned date",IF(AND(TODAY()>X353,OR(Z353="",Z353<100)),"Behind — past end date",IF(AND(T353<>"",X353<>"",Z353<>"",(Z353<100),((TODAY()-T353)/MAX(X353-T353,1)*100)-Z353>15),"Behind — progress lag",IF(AND(X353-TODAY()<=30,X353-TODAY()>=0,OR(Z353="",Z353<90)),"At risk — close to off track","On track")))))))) | IF(OR(F353="",AC353="Completed / Handover",AC353="Cancelled"),"",IF(O353="Not awarded",IF(U353<>"",U353-TODAY(),IF(X353="","",X353-TODAY())),IF(X353="","",X353-TODAY()))) | [14 empty] | IF(OR(F353="",AJ353=""),"",IF(COUNT(AI353:AI353)=0,"",AJ353-LOOKUP(2,1/(AI353:AI353<>""),AI353:AI353))) | IF(OR(F353="",AK353=""),"",IF(COUNT(AI353:AJ353)=0,"",AK353-LOOKUP(2,1/(AI353:AJ353<>""),AI353:AJ353))) | IF(OR(F353="",AL353=""),"",IF(COUNT(AI353:AK353)=0,"",AL353-LOOKUP(2,1/(AI353:AK353<>""),AI353:AK353))) | IF(OR(F353="",AM353=""),"",IF(COUNT(AI353:AL353)=0,"",AM353-LOOKUP(2,1/(AI353:AL353<>""),AI353:AL353))) | IF(OR(F353="",AN353=""),"",IF(COUNT(AI353:AM353)=0,"",AN353-LOOKUP(2,1/(AI353:AM353<>""),AI353:AM353))) | IF(OR(F353="",AO353=""),"",IF(COUNT(AI353:AN353)=0,"",AO353-LOOKUP(2,1/(AI353:AN353<>""),AI353:AN353))) | IF(OR(F353="",AP353=""),"",IF(COUNT(AI353:AO353)=0,"",AP353-LOOKUP(2,1/(AI353:AO353<>""),AI353:AO353))) | IF(OR(F353="",AQ353=""),"",IF(COUNT(AI353:AP353)=0,"",AQ353-LOOKUP(2,1/(AI353:AP353<>""),AI353:AP353))) | IF(OR(F353="",AR353=""),"",IF(COUNT(AI353:AQ353)=0,"",AR353-LOOKUP(2,1/(AI353:AQ353<>""),AI353:AQ353))) | IF(OR(F353="",AS353=""),"",IF(COUNT(AI353:AR353)=0,"",AS353-LOOKUP(2,1/(AI353:AR353<>""),AI353:AR353))) | IF(OR(F353="",AT353=""),"",IF(COUNT(AI353:AS353)=0,"",AT353-LOOKUP(2,1/(AI353:AS353<>""),AI353:AS353))) | IF(OR(F353="",AU353=""),"",IF(COUNT(AI353:AT353)=0,"",AU353-LOOKUP(2,1/(AI353:AT353<>""),AI353:AT353))) | IF(OR(F353="",AV353=""),"",IF(COUNT(AI353:AU353)=0,"",AV353-LOOKUP(2,1/(AI353:AU353<>""),AI353:AU353))) | IF(J353="","All_Provinces",IFERROR(VLOOKUP(J353,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K353="","All_Districts",IFERROR(VLOOKUP(K353,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F354="","",ROW()-3) | AF2-WSM-34 | Package #34-AF2 WSM: Construction of two Check dams, 1.Tawqus Sangaw and 2. Khalkoma in Kalbad and Ali Abad district of Kunduz province. | 1 of 2 | AF2-WSM-N-023 | Khalkoma Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kunduz | Ali Abad | Khalkoma | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 66984.58 | IF(AQ354="","",AQ354) | 2026-10-31 | 5.9 | 2027-04-29 | IF(W354<>"",W354,IF(OR(T354="",V354=""),"",EDATE(T354,V354))) |  |  | ITB Launched | Construction period six months including slack period (Dec-Jan). | IF(F354="","",IF(COUNT(AI354:AV354)=0,IF(AA354="","Not started",AA354),SUBSTITUTE(LOOKUP(2,1/(AI354:AV354<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F354="",COUNT(AI354:AV354)=0),"",TODAY()-LOOKUP(2,1/(AI354:AV354<>""),AI354:AV354)) | IF(OR(F354="",COUNT(AI354:AV354)<2),"",LOOKUP(2,1/(AI354:AV354<>""),AI354:AV354)-MIN(AI354:AV354)) | IF(OR(AD354="",AC354="Not started",AC354=""),"",IFERROR(AD354-IF(VLOOKUP(AC354,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC354,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F354="","",IF(OR(AA354="Cancelled",AC354="Cancelled"),"Cancelled",IF(OR(AC354="Completed / Handover",Y354<>"",Z354>=100),"Completed — on track",IF(O354="Not awarded",IF(U354="",IF(X354="","No planned date",IF(TODAY()>X354,"Behind — past planned date",IF(X354-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U354,"Behind — award date passed",IF(U354-TODAY()<=30,"At risk — close to off track","On track"))),IF(X354="","No planned date",IF(AND(TODAY()>X354,OR(Z354="",Z354<100)),"Behind — past end date",IF(AND(T354<>"",X354<>"",Z354<>"",(Z354<100),((TODAY()-T354)/MAX(X354-T354,1)*100)-Z354>15),"Behind — progress lag",IF(AND(X354-TODAY()<=30,X354-TODAY()>=0,OR(Z354="",Z354<90)),"At risk — close to off track","On track")))))))) | IF(OR(F354="",AC354="Completed / Handover",AC354="Cancelled"),"",IF(O354="Not awarded",IF(U354<>"",U354-TODAY(),IF(X354="","",X354-TODAY())),IF(X354="","",X354-TODAY()))) | [14 empty] | IF(OR(F354="",AJ354=""),"",IF(COUNT(AI354:AI354)=0,"",AJ354-LOOKUP(2,1/(AI354:AI354<>""),AI354:AI354))) | IF(OR(F354="",AK354=""),"",IF(COUNT(AI354:AJ354)=0,"",AK354-LOOKUP(2,1/(AI354:AJ354<>""),AI354:AJ354))) | IF(OR(F354="",AL354=""),"",IF(COUNT(AI354:AK354)=0,"",AL354-LOOKUP(2,1/(AI354:AK354<>""),AI354:AK354))) | IF(OR(F354="",AM354=""),"",IF(COUNT(AI354:AL354)=0,"",AM354-LOOKUP(2,1/(AI354:AL354<>""),AI354:AL354))) | IF(OR(F354="",AN354=""),"",IF(COUNT(AI354:AM354)=0,"",AN354-LOOKUP(2,1/(AI354:AM354<>""),AI354:AM354))) | IF(OR(F354="",AO354=""),"",IF(COUNT(AI354:AN354)=0,"",AO354-LOOKUP(2,1/(AI354:AN354<>""),AI354:AN354))) | IF(OR(F354="",AP354=""),"",IF(COUNT(AI354:AO354)=0,"",AP354-LOOKUP(2,1/(AI354:AO354<>""),AI354:AO354))) | IF(OR(F354="",AQ354=""),"",IF(COUNT(AI354:AP354)=0,"",AQ354-LOOKUP(2,1/(AI354:AP354<>""),AI354:AP354))) | IF(OR(F354="",AR354=""),"",IF(COUNT(AI354:AQ354)=0,"",AR354-LOOKUP(2,1/(AI354:AQ354<>""),AI354:AQ354))) | IF(OR(F354="",AS354=""),"",IF(COUNT(AI354:AR354)=0,"",AS354-LOOKUP(2,1/(AI354:AR354<>""),AI354:AR354))) | IF(OR(F354="",AT354=""),"",IF(COUNT(AI354:AS354)=0,"",AT354-LOOKUP(2,1/(AI354:AS354<>""),AI354:AS354))) | IF(OR(F354="",AU354=""),"",IF(COUNT(AI354:AT354)=0,"",AU354-LOOKUP(2,1/(AI354:AT354<>""),AI354:AT354))) | IF(OR(F354="",AV354=""),"",IF(COUNT(AI354:AU354)=0,"",AV354-LOOKUP(2,1/(AI354:AU354<>""),AI354:AU354))) | IF(J354="","All_Provinces",IFERROR(VLOOKUP(J354,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K354="","All_Districts",IFERROR(VLOOKUP(K354,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F355="","",ROW()-3) | AF2-WSM-34 | Package #34-AF2 WSM: Construction of two Check dams, 1.Tawqus Sangaw and 2. Khalkoma in Kalbad and Ali Abad district of Kunduz province. | 2 of 2 | AF2-WSM-N-024 | Tawqus Sangaw Check Dam | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | South / Kandahar | Kunduz | Kalbad | Tawqus Sangaw | World Bank (WBK/AF-2) | Not awarded | 4.WSM remaining contracts |  |  | 66984.58 | IF(AQ355="","",AQ355) | 2026-10-31 | 5.9 | 2027-04-29 | IF(W355<>"",W355,IF(OR(T355="",V355=""),"",EDATE(T355,V355))) |  |  | ITB Launched | Construction period six months including slack period (Dec-Jan). | IF(F355="","",IF(COUNT(AI355:AV355)=0,IF(AA355="","Not started",AA355),SUBSTITUTE(LOOKUP(2,1/(AI355:AV355<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F355="",COUNT(AI355:AV355)=0),"",TODAY()-LOOKUP(2,1/(AI355:AV355<>""),AI355:AV355)) | IF(OR(F355="",COUNT(AI355:AV355)<2),"",LOOKUP(2,1/(AI355:AV355<>""),AI355:AV355)-MIN(AI355:AV355)) | IF(OR(AD355="",AC355="Not started",AC355=""),"",IFERROR(AD355-IF(VLOOKUP(AC355,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC355,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F355="","",IF(OR(AA355="Cancelled",AC355="Cancelled"),"Cancelled",IF(OR(AC355="Completed / Handover",Y355<>"",Z355>=100),"Completed — on track",IF(O355="Not awarded",IF(U355="",IF(X355="","No planned date",IF(TODAY()>X355,"Behind — past planned date",IF(X355-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U355,"Behind — award date passed",IF(U355-TODAY()<=30,"At risk — close to off track","On track"))),IF(X355="","No planned date",IF(AND(TODAY()>X355,OR(Z355="",Z355<100)),"Behind — past end date",IF(AND(T355<>"",X355<>"",Z355<>"",(Z355<100),((TODAY()-T355)/MAX(X355-T355,1)*100)-Z355>15),"Behind — progress lag",IF(AND(X355-TODAY()<=30,X355-TODAY()>=0,OR(Z355="",Z355<90)),"At risk — close to off track","On track")))))))) | IF(OR(F355="",AC355="Completed / Handover",AC355="Cancelled"),"",IF(O355="Not awarded",IF(U355<>"",U355-TODAY(),IF(X355="","",X355-TODAY())),IF(X355="","",X355-TODAY()))) | [14 empty] | IF(OR(F355="",AJ355=""),"",IF(COUNT(AI355:AI355)=0,"",AJ355-LOOKUP(2,1/(AI355:AI355<>""),AI355:AI355))) | IF(OR(F355="",AK355=""),"",IF(COUNT(AI355:AJ355)=0,"",AK355-LOOKUP(2,1/(AI355:AJ355<>""),AI355:AJ355))) | IF(OR(F355="",AL355=""),"",IF(COUNT(AI355:AK355)=0,"",AL355-LOOKUP(2,1/(AI355:AK355<>""),AI355:AK355))) | IF(OR(F355="",AM355=""),"",IF(COUNT(AI355:AL355)=0,"",AM355-LOOKUP(2,1/(AI355:AL355<>""),AI355:AL355))) | IF(OR(F355="",AN355=""),"",IF(COUNT(AI355:AM355)=0,"",AN355-LOOKUP(2,1/(AI355:AM355<>""),AI355:AM355))) | IF(OR(F355="",AO355=""),"",IF(COUNT(AI355:AN355)=0,"",AO355-LOOKUP(2,1/(AI355:AN355<>""),AI355:AN355))) | IF(OR(F355="",AP355=""),"",IF(COUNT(AI355:AO355)=0,"",AP355-LOOKUP(2,1/(AI355:AO355<>""),AI355:AO355))) | IF(OR(F355="",AQ355=""),"",IF(COUNT(AI355:AP355)=0,"",AQ355-LOOKUP(2,1/(AI355:AP355<>""),AI355:AP355))) | IF(OR(F355="",AR355=""),"",IF(COUNT(AI355:AQ355)=0,"",AR355-LOOKUP(2,1/(AI355:AQ355<>""),AI355:AQ355))) | IF(OR(F355="",AS355=""),"",IF(COUNT(AI355:AR355)=0,"",AS355-LOOKUP(2,1/(AI355:AR355<>""),AI355:AR355))) | IF(OR(F355="",AT355=""),"",IF(COUNT(AI355:AS355)=0,"",AT355-LOOKUP(2,1/(AI355:AS355<>""),AI355:AS355))) | IF(OR(F355="",AU355=""),"",IF(COUNT(AI355:AT355)=0,"",AU355-LOOKUP(2,1/(AI355:AT355<>""),AI355:AT355))) | IF(OR(F355="",AV355=""),"",IF(COUNT(AI355:AU355)=0,"",AV355-LOOKUP(2,1/(AI355:AU355<>""),AI355:AU355))) | IF(J355="","All_Provinces",IFERROR(VLOOKUP(J355,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K355="","All_Districts",IFERROR(VLOOKUP(K355,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F356="","",ROW()-3) | [18 empty] | IF(AQ356="","",AQ356) |  |  |  | IF(W356<>"",W356,IF(OR(T356="",V356=""),"",EDATE(T356,V356))) |  |  |  |  | IF(F356="","",IF(COUNT(AI356:AV356)=0,IF(AA356="","Not started",AA356),SUBSTITUTE(LOOKUP(2,1/(AI356:AV356<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F356="",COUNT(AI356:AV356)=0),"",TODAY()-LOOKUP(2,1/(AI356:AV356<>""),AI356:AV356)) | IF(OR(F356="",COUNT(AI356:AV356)<2),"",LOOKUP(2,1/(AI356:AV356<>""),AI356:AV356)-MIN(AI356:AV356)) | IF(OR(AD356="",AC356="Not started",AC356=""),"",IFERROR(AD356-IF(VLOOKUP(AC356,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC356,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F356="","",IF(OR(AA356="Cancelled",AC356="Cancelled"),"Cancelled",IF(OR(AC356="Completed / Handover",Y356<>"",Z356>=100),"Completed — on track",IF(O356="Not awarded",IF(U356="",IF(X356="","No planned date",IF(TODAY()>X356,"Behind — past planned date",IF(X356-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U356,"Behind — award date passed",IF(U356-TODAY()<=30,"At risk — close to off track","On track"))),IF(X356="","No planned date",IF(AND(TODAY()>X356,OR(Z356="",Z356<100)),"Behind — past end date",IF(AND(T356<>"",X356<>"",Z356<>"",(Z356<100),((TODAY()-T356)/MAX(X356-T356,1)*100)-Z356>15),"Behind — progress lag",IF(AND(X356-TODAY()<=30,X356-TODAY()>=0,OR(Z356="",Z356<90)),"At risk — close to off track","On track")))))))) | IF(OR(F356="",AC356="Completed / Handover",AC356="Cancelled"),"",IF(O356="Not awarded",IF(U356<>"",U356-TODAY(),IF(X356="","",X356-TODAY())),IF(X356="","",X356-TODAY()))) | [14 empty] | IF(OR(F356="",AJ356=""),"",IF(COUNT(AI356:AI356)=0,"",AJ356-LOOKUP(2,1/(AI356:AI356<>""),AI356:AI356))) | IF(OR(F356="",AK356=""),"",IF(COUNT(AI356:AJ356)=0,"",AK356-LOOKUP(2,1/(AI356:AJ356<>""),AI356:AJ356))) | IF(OR(F356="",AL356=""),"",IF(COUNT(AI356:AK356)=0,"",AL356-LOOKUP(2,1/(AI356:AK356<>""),AI356:AK356))) | IF(OR(F356="",AM356=""),"",IF(COUNT(AI356:AL356)=0,"",AM356-LOOKUP(2,1/(AI356:AL356<>""),AI356:AL356))) | IF(OR(F356="",AN356=""),"",IF(COUNT(AI356:AM356)=0,"",AN356-LOOKUP(2,1/(AI356:AM356<>""),AI356:AM356))) | IF(OR(F356="",AO356=""),"",IF(COUNT(AI356:AN356)=0,"",AO356-LOOKUP(2,1/(AI356:AN356<>""),AI356:AN356))) | IF(OR(F356="",AP356=""),"",IF(COUNT(AI356:AO356)=0,"",AP356-LOOKUP(2,1/(AI356:AO356<>""),AI356:AO356))) | IF(OR(F356="",AQ356=""),"",IF(COUNT(AI356:AP356)=0,"",AQ356-LOOKUP(2,1/(AI356:AP356<>""),AI356:AP356))) | IF(OR(F356="",AR356=""),"",IF(COUNT(AI356:AQ356)=0,"",AR356-LOOKUP(2,1/(AI356:AQ356<>""),AI356:AQ356))) | IF(OR(F356="",AS356=""),"",IF(COUNT(AI356:AR356)=0,"",AS356-LOOKUP(2,1/(AI356:AR356<>""),AI356:AR356))) | IF(OR(F356="",AT356=""),"",IF(COUNT(AI356:AS356)=0,"",AT356-LOOKUP(2,1/(AI356:AS356<>""),AI356:AS356))) | IF(OR(F356="",AU356=""),"",IF(COUNT(AI356:AT356)=0,"",AU356-LOOKUP(2,1/(AI356:AT356<>""),AI356:AT356))) | IF(OR(F356="",AV356=""),"",IF(COUNT(AI356:AU356)=0,"",AV356-LOOKUP(2,1/(AI356:AU356<>""),AI356:AU356))) | IF(J356="","All_Provinces",IFERROR(VLOOKUP(J356,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K356="","All_Districts",IFERROR(VLOOKUP(K356,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F357="","",ROW()-3) | [18 empty] | IF(AQ357="","",AQ357) |  |  |  | IF(W357<>"",W357,IF(OR(T357="",V357=""),"",EDATE(T357,V357))) |  |  |  |  | IF(F357="","",IF(COUNT(AI357:AV357)=0,IF(AA357="","Not started",AA357),SUBSTITUTE(LOOKUP(2,1/(AI357:AV357<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F357="",COUNT(AI357:AV357)=0),"",TODAY()-LOOKUP(2,1/(AI357:AV357<>""),AI357:AV357)) | IF(OR(F357="",COUNT(AI357:AV357)<2),"",LOOKUP(2,1/(AI357:AV357<>""),AI357:AV357)-MIN(AI357:AV357)) | IF(OR(AD357="",AC357="Not started",AC357=""),"",IFERROR(AD357-IF(VLOOKUP(AC357,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC357,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F357="","",IF(OR(AA357="Cancelled",AC357="Cancelled"),"Cancelled",IF(OR(AC357="Completed / Handover",Y357<>"",Z357>=100),"Completed — on track",IF(O357="Not awarded",IF(U357="",IF(X357="","No planned date",IF(TODAY()>X357,"Behind — past planned date",IF(X357-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U357,"Behind — award date passed",IF(U357-TODAY()<=30,"At risk — close to off track","On track"))),IF(X357="","No planned date",IF(AND(TODAY()>X357,OR(Z357="",Z357<100)),"Behind — past end date",IF(AND(T357<>"",X357<>"",Z357<>"",(Z357<100),((TODAY()-T357)/MAX(X357-T357,1)*100)-Z357>15),"Behind — progress lag",IF(AND(X357-TODAY()<=30,X357-TODAY()>=0,OR(Z357="",Z357<90)),"At risk — close to off track","On track")))))))) | IF(OR(F357="",AC357="Completed / Handover",AC357="Cancelled"),"",IF(O357="Not awarded",IF(U357<>"",U357-TODAY(),IF(X357="","",X357-TODAY())),IF(X357="","",X357-TODAY()))) | [14 empty] | IF(OR(F357="",AJ357=""),"",IF(COUNT(AI357:AI357)=0,"",AJ357-LOOKUP(2,1/(AI357:AI357<>""),AI357:AI357))) | IF(OR(F357="",AK357=""),"",IF(COUNT(AI357:AJ357)=0,"",AK357-LOOKUP(2,1/(AI357:AJ357<>""),AI357:AJ357))) | IF(OR(F357="",AL357=""),"",IF(COUNT(AI357:AK357)=0,"",AL357-LOOKUP(2,1/(AI357:AK357<>""),AI357:AK357))) | IF(OR(F357="",AM357=""),"",IF(COUNT(AI357:AL357)=0,"",AM357-LOOKUP(2,1/(AI357:AL357<>""),AI357:AL357))) | IF(OR(F357="",AN357=""),"",IF(COUNT(AI357:AM357)=0,"",AN357-LOOKUP(2,1/(AI357:AM357<>""),AI357:AM357))) | IF(OR(F357="",AO357=""),"",IF(COUNT(AI357:AN357)=0,"",AO357-LOOKUP(2,1/(AI357:AN357<>""),AI357:AN357))) | IF(OR(F357="",AP357=""),"",IF(COUNT(AI357:AO357)=0,"",AP357-LOOKUP(2,1/(AI357:AO357<>""),AI357:AO357))) | IF(OR(F357="",AQ357=""),"",IF(COUNT(AI357:AP357)=0,"",AQ357-LOOKUP(2,1/(AI357:AP357<>""),AI357:AP357))) | IF(OR(F357="",AR357=""),"",IF(COUNT(AI357:AQ357)=0,"",AR357-LOOKUP(2,1/(AI357:AQ357<>""),AI357:AQ357))) | IF(OR(F357="",AS357=""),"",IF(COUNT(AI357:AR357)=0,"",AS357-LOOKUP(2,1/(AI357:AR357<>""),AI357:AR357))) | IF(OR(F357="",AT357=""),"",IF(COUNT(AI357:AS357)=0,"",AT357-LOOKUP(2,1/(AI357:AS357<>""),AI357:AS357))) | IF(OR(F357="",AU357=""),"",IF(COUNT(AI357:AT357)=0,"",AU357-LOOKUP(2,1/(AI357:AT357<>""),AI357:AT357))) | IF(OR(F357="",AV357=""),"",IF(COUNT(AI357:AU357)=0,"",AV357-LOOKUP(2,1/(AI357:AU357<>""),AI357:AU357))) | IF(J357="","All_Provinces",IFERROR(VLOOKUP(J357,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K357="","All_Districts",IFERROR(VLOOKUP(K357,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F358="","",ROW()-3) | [18 empty] | IF(AQ358="","",AQ358) |  |  |  | IF(W358<>"",W358,IF(OR(T358="",V358=""),"",EDATE(T358,V358))) |  |  |  |  | IF(F358="","",IF(COUNT(AI358:AV358)=0,IF(AA358="","Not started",AA358),SUBSTITUTE(LOOKUP(2,1/(AI358:AV358<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F358="",COUNT(AI358:AV358)=0),"",TODAY()-LOOKUP(2,1/(AI358:AV358<>""),AI358:AV358)) | IF(OR(F358="",COUNT(AI358:AV358)<2),"",LOOKUP(2,1/(AI358:AV358<>""),AI358:AV358)-MIN(AI358:AV358)) | IF(OR(AD358="",AC358="Not started",AC358=""),"",IFERROR(AD358-IF(VLOOKUP(AC358,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC358,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F358="","",IF(OR(AA358="Cancelled",AC358="Cancelled"),"Cancelled",IF(OR(AC358="Completed / Handover",Y358<>"",Z358>=100),"Completed — on track",IF(O358="Not awarded",IF(U358="",IF(X358="","No planned date",IF(TODAY()>X358,"Behind — past planned date",IF(X358-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U358,"Behind — award date passed",IF(U358-TODAY()<=30,"At risk — close to off track","On track"))),IF(X358="","No planned date",IF(AND(TODAY()>X358,OR(Z358="",Z358<100)),"Behind — past end date",IF(AND(T358<>"",X358<>"",Z358<>"",(Z358<100),((TODAY()-T358)/MAX(X358-T358,1)*100)-Z358>15),"Behind — progress lag",IF(AND(X358-TODAY()<=30,X358-TODAY()>=0,OR(Z358="",Z358<90)),"At risk — close to off track","On track")))))))) | IF(OR(F358="",AC358="Completed / Handover",AC358="Cancelled"),"",IF(O358="Not awarded",IF(U358<>"",U358-TODAY(),IF(X358="","",X358-TODAY())),IF(X358="","",X358-TODAY()))) | [14 empty] | IF(OR(F358="",AJ358=""),"",IF(COUNT(AI358:AI358)=0,"",AJ358-LOOKUP(2,1/(AI358:AI358<>""),AI358:AI358))) | IF(OR(F358="",AK358=""),"",IF(COUNT(AI358:AJ358)=0,"",AK358-LOOKUP(2,1/(AI358:AJ358<>""),AI358:AJ358))) | IF(OR(F358="",AL358=""),"",IF(COUNT(AI358:AK358)=0,"",AL358-LOOKUP(2,1/(AI358:AK358<>""),AI358:AK358))) | IF(OR(F358="",AM358=""),"",IF(COUNT(AI358:AL358)=0,"",AM358-LOOKUP(2,1/(AI358:AL358<>""),AI358:AL358))) | IF(OR(F358="",AN358=""),"",IF(COUNT(AI358:AM358)=0,"",AN358-LOOKUP(2,1/(AI358:AM358<>""),AI358:AM358))) | IF(OR(F358="",AO358=""),"",IF(COUNT(AI358:AN358)=0,"",AO358-LOOKUP(2,1/(AI358:AN358<>""),AI358:AN358))) | IF(OR(F358="",AP358=""),"",IF(COUNT(AI358:AO358)=0,"",AP358-LOOKUP(2,1/(AI358:AO358<>""),AI358:AO358))) | IF(OR(F358="",AQ358=""),"",IF(COUNT(AI358:AP358)=0,"",AQ358-LOOKUP(2,1/(AI358:AP358<>""),AI358:AP358))) | IF(OR(F358="",AR358=""),"",IF(COUNT(AI358:AQ358)=0,"",AR358-LOOKUP(2,1/(AI358:AQ358<>""),AI358:AQ358))) | IF(OR(F358="",AS358=""),"",IF(COUNT(AI358:AR358)=0,"",AS358-LOOKUP(2,1/(AI358:AR358<>""),AI358:AR358))) | IF(OR(F358="",AT358=""),"",IF(COUNT(AI358:AS358)=0,"",AT358-LOOKUP(2,1/(AI358:AS358<>""),AI358:AS358))) | IF(OR(F358="",AU358=""),"",IF(COUNT(AI358:AT358)=0,"",AU358-LOOKUP(2,1/(AI358:AT358<>""),AI358:AT358))) | IF(OR(F358="",AV358=""),"",IF(COUNT(AI358:AU358)=0,"",AV358-LOOKUP(2,1/(AI358:AU358<>""),AI358:AU358))) | IF(J358="","All_Provinces",IFERROR(VLOOKUP(J358,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K358="","All_Districts",IFERROR(VLOOKUP(K358,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F359="","",ROW()-3) | [18 empty] | IF(AQ359="","",AQ359) |  |  |  | IF(W359<>"",W359,IF(OR(T359="",V359=""),"",EDATE(T359,V359))) |  |  |  |  | IF(F359="","",IF(COUNT(AI359:AV359)=0,IF(AA359="","Not started",AA359),SUBSTITUTE(LOOKUP(2,1/(AI359:AV359<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F359="",COUNT(AI359:AV359)=0),"",TODAY()-LOOKUP(2,1/(AI359:AV359<>""),AI359:AV359)) | IF(OR(F359="",COUNT(AI359:AV359)<2),"",LOOKUP(2,1/(AI359:AV359<>""),AI359:AV359)-MIN(AI359:AV359)) | IF(OR(AD359="",AC359="Not started",AC359=""),"",IFERROR(AD359-IF(VLOOKUP(AC359,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC359,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F359="","",IF(OR(AA359="Cancelled",AC359="Cancelled"),"Cancelled",IF(OR(AC359="Completed / Handover",Y359<>"",Z359>=100),"Completed — on track",IF(O359="Not awarded",IF(U359="",IF(X359="","No planned date",IF(TODAY()>X359,"Behind — past planned date",IF(X359-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U359,"Behind — award date passed",IF(U359-TODAY()<=30,"At risk — close to off track","On track"))),IF(X359="","No planned date",IF(AND(TODAY()>X359,OR(Z359="",Z359<100)),"Behind — past end date",IF(AND(T359<>"",X359<>"",Z359<>"",(Z359<100),((TODAY()-T359)/MAX(X359-T359,1)*100)-Z359>15),"Behind — progress lag",IF(AND(X359-TODAY()<=30,X359-TODAY()>=0,OR(Z359="",Z359<90)),"At risk — close to off track","On track")))))))) | IF(OR(F359="",AC359="Completed / Handover",AC359="Cancelled"),"",IF(O359="Not awarded",IF(U359<>"",U359-TODAY(),IF(X359="","",X359-TODAY())),IF(X359="","",X359-TODAY()))) | [14 empty] | IF(OR(F359="",AJ359=""),"",IF(COUNT(AI359:AI359)=0,"",AJ359-LOOKUP(2,1/(AI359:AI359<>""),AI359:AI359))) | IF(OR(F359="",AK359=""),"",IF(COUNT(AI359:AJ359)=0,"",AK359-LOOKUP(2,1/(AI359:AJ359<>""),AI359:AJ359))) | IF(OR(F359="",AL359=""),"",IF(COUNT(AI359:AK359)=0,"",AL359-LOOKUP(2,1/(AI359:AK359<>""),AI359:AK359))) | IF(OR(F359="",AM359=""),"",IF(COUNT(AI359:AL359)=0,"",AM359-LOOKUP(2,1/(AI359:AL359<>""),AI359:AL359))) | IF(OR(F359="",AN359=""),"",IF(COUNT(AI359:AM359)=0,"",AN359-LOOKUP(2,1/(AI359:AM359<>""),AI359:AM359))) | IF(OR(F359="",AO359=""),"",IF(COUNT(AI359:AN359)=0,"",AO359-LOOKUP(2,1/(AI359:AN359<>""),AI359:AN359))) | IF(OR(F359="",AP359=""),"",IF(COUNT(AI359:AO359)=0,"",AP359-LOOKUP(2,1/(AI359:AO359<>""),AI359:AO359))) | IF(OR(F359="",AQ359=""),"",IF(COUNT(AI359:AP359)=0,"",AQ359-LOOKUP(2,1/(AI359:AP359<>""),AI359:AP359))) | IF(OR(F359="",AR359=""),"",IF(COUNT(AI359:AQ359)=0,"",AR359-LOOKUP(2,1/(AI359:AQ359<>""),AI359:AQ359))) | IF(OR(F359="",AS359=""),"",IF(COUNT(AI359:AR359)=0,"",AS359-LOOKUP(2,1/(AI359:AR359<>""),AI359:AR359))) | IF(OR(F359="",AT359=""),"",IF(COUNT(AI359:AS359)=0,"",AT359-LOOKUP(2,1/(AI359:AS359<>""),AI359:AS359))) | IF(OR(F359="",AU359=""),"",IF(COUNT(AI359:AT359)=0,"",AU359-LOOKUP(2,1/(AI359:AT359<>""),AI359:AT359))) | IF(OR(F359="",AV359=""),"",IF(COUNT(AI359:AU359)=0,"",AV359-LOOKUP(2,1/(AI359:AU359<>""),AI359:AU359))) | IF(J359="","All_Provinces",IFERROR(VLOOKUP(J359,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K359="","All_Districts",IFERROR(VLOOKUP(K359,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F360="","",ROW()-3) | [18 empty] | IF(AQ360="","",AQ360) |  |  |  | IF(W360<>"",W360,IF(OR(T360="",V360=""),"",EDATE(T360,V360))) |  |  |  |  | IF(F360="","",IF(COUNT(AI360:AV360)=0,IF(AA360="","Not started",AA360),SUBSTITUTE(LOOKUP(2,1/(AI360:AV360<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F360="",COUNT(AI360:AV360)=0),"",TODAY()-LOOKUP(2,1/(AI360:AV360<>""),AI360:AV360)) | IF(OR(F360="",COUNT(AI360:AV360)<2),"",LOOKUP(2,1/(AI360:AV360<>""),AI360:AV360)-MIN(AI360:AV360)) | IF(OR(AD360="",AC360="Not started",AC360=""),"",IFERROR(AD360-IF(VLOOKUP(AC360,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC360,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F360="","",IF(OR(AA360="Cancelled",AC360="Cancelled"),"Cancelled",IF(OR(AC360="Completed / Handover",Y360<>"",Z360>=100),"Completed — on track",IF(O360="Not awarded",IF(U360="",IF(X360="","No planned date",IF(TODAY()>X360,"Behind — past planned date",IF(X360-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U360,"Behind — award date passed",IF(U360-TODAY()<=30,"At risk — close to off track","On track"))),IF(X360="","No planned date",IF(AND(TODAY()>X360,OR(Z360="",Z360<100)),"Behind — past end date",IF(AND(T360<>"",X360<>"",Z360<>"",(Z360<100),((TODAY()-T360)/MAX(X360-T360,1)*100)-Z360>15),"Behind — progress lag",IF(AND(X360-TODAY()<=30,X360-TODAY()>=0,OR(Z360="",Z360<90)),"At risk — close to off track","On track")))))))) | IF(OR(F360="",AC360="Completed / Handover",AC360="Cancelled"),"",IF(O360="Not awarded",IF(U360<>"",U360-TODAY(),IF(X360="","",X360-TODAY())),IF(X360="","",X360-TODAY()))) | [14 empty] | IF(OR(F360="",AJ360=""),"",IF(COUNT(AI360:AI360)=0,"",AJ360-LOOKUP(2,1/(AI360:AI360<>""),AI360:AI360))) | IF(OR(F360="",AK360=""),"",IF(COUNT(AI360:AJ360)=0,"",AK360-LOOKUP(2,1/(AI360:AJ360<>""),AI360:AJ360))) | IF(OR(F360="",AL360=""),"",IF(COUNT(AI360:AK360)=0,"",AL360-LOOKUP(2,1/(AI360:AK360<>""),AI360:AK360))) | IF(OR(F360="",AM360=""),"",IF(COUNT(AI360:AL360)=0,"",AM360-LOOKUP(2,1/(AI360:AL360<>""),AI360:AL360))) | IF(OR(F360="",AN360=""),"",IF(COUNT(AI360:AM360)=0,"",AN360-LOOKUP(2,1/(AI360:AM360<>""),AI360:AM360))) | IF(OR(F360="",AO360=""),"",IF(COUNT(AI360:AN360)=0,"",AO360-LOOKUP(2,1/(AI360:AN360<>""),AI360:AN360))) | IF(OR(F360="",AP360=""),"",IF(COUNT(AI360:AO360)=0,"",AP360-LOOKUP(2,1/(AI360:AO360<>""),AI360:AO360))) | IF(OR(F360="",AQ360=""),"",IF(COUNT(AI360:AP360)=0,"",AQ360-LOOKUP(2,1/(AI360:AP360<>""),AI360:AP360))) | IF(OR(F360="",AR360=""),"",IF(COUNT(AI360:AQ360)=0,"",AR360-LOOKUP(2,1/(AI360:AQ360<>""),AI360:AQ360))) | IF(OR(F360="",AS360=""),"",IF(COUNT(AI360:AR360)=0,"",AS360-LOOKUP(2,1/(AI360:AR360<>""),AI360:AR360))) | IF(OR(F360="",AT360=""),"",IF(COUNT(AI360:AS360)=0,"",AT360-LOOKUP(2,1/(AI360:AS360<>""),AI360:AS360))) | IF(OR(F360="",AU360=""),"",IF(COUNT(AI360:AT360)=0,"",AU360-LOOKUP(2,1/(AI360:AT360<>""),AI360:AT360))) | IF(OR(F360="",AV360=""),"",IF(COUNT(AI360:AU360)=0,"",AV360-LOOKUP(2,1/(AI360:AU360<>""),AI360:AU360))) | IF(J360="","All_Provinces",IFERROR(VLOOKUP(J360,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K360="","All_Districts",IFERROR(VLOOKUP(K360,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F361="","",ROW()-3) | [18 empty] | IF(AQ361="","",AQ361) |  |  |  | IF(W361<>"",W361,IF(OR(T361="",V361=""),"",EDATE(T361,V361))) |  |  |  |  | IF(F361="","",IF(COUNT(AI361:AV361)=0,IF(AA361="","Not started",AA361),SUBSTITUTE(LOOKUP(2,1/(AI361:AV361<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F361="",COUNT(AI361:AV361)=0),"",TODAY()-LOOKUP(2,1/(AI361:AV361<>""),AI361:AV361)) | IF(OR(F361="",COUNT(AI361:AV361)<2),"",LOOKUP(2,1/(AI361:AV361<>""),AI361:AV361)-MIN(AI361:AV361)) | IF(OR(AD361="",AC361="Not started",AC361=""),"",IFERROR(AD361-IF(VLOOKUP(AC361,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC361,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F361="","",IF(OR(AA361="Cancelled",AC361="Cancelled"),"Cancelled",IF(OR(AC361="Completed / Handover",Y361<>"",Z361>=100),"Completed — on track",IF(O361="Not awarded",IF(U361="",IF(X361="","No planned date",IF(TODAY()>X361,"Behind — past planned date",IF(X361-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U361,"Behind — award date passed",IF(U361-TODAY()<=30,"At risk — close to off track","On track"))),IF(X361="","No planned date",IF(AND(TODAY()>X361,OR(Z361="",Z361<100)),"Behind — past end date",IF(AND(T361<>"",X361<>"",Z361<>"",(Z361<100),((TODAY()-T361)/MAX(X361-T361,1)*100)-Z361>15),"Behind — progress lag",IF(AND(X361-TODAY()<=30,X361-TODAY()>=0,OR(Z361="",Z361<90)),"At risk — close to off track","On track")))))))) | IF(OR(F361="",AC361="Completed / Handover",AC361="Cancelled"),"",IF(O361="Not awarded",IF(U361<>"",U361-TODAY(),IF(X361="","",X361-TODAY())),IF(X361="","",X361-TODAY()))) | [14 empty] | IF(OR(F361="",AJ361=""),"",IF(COUNT(AI361:AI361)=0,"",AJ361-LOOKUP(2,1/(AI361:AI361<>""),AI361:AI361))) | IF(OR(F361="",AK361=""),"",IF(COUNT(AI361:AJ361)=0,"",AK361-LOOKUP(2,1/(AI361:AJ361<>""),AI361:AJ361))) | IF(OR(F361="",AL361=""),"",IF(COUNT(AI361:AK361)=0,"",AL361-LOOKUP(2,1/(AI361:AK361<>""),AI361:AK361))) | IF(OR(F361="",AM361=""),"",IF(COUNT(AI361:AL361)=0,"",AM361-LOOKUP(2,1/(AI361:AL361<>""),AI361:AL361))) | IF(OR(F361="",AN361=""),"",IF(COUNT(AI361:AM361)=0,"",AN361-LOOKUP(2,1/(AI361:AM361<>""),AI361:AM361))) | IF(OR(F361="",AO361=""),"",IF(COUNT(AI361:AN361)=0,"",AO361-LOOKUP(2,1/(AI361:AN361<>""),AI361:AN361))) | IF(OR(F361="",AP361=""),"",IF(COUNT(AI361:AO361)=0,"",AP361-LOOKUP(2,1/(AI361:AO361<>""),AI361:AO361))) | IF(OR(F361="",AQ361=""),"",IF(COUNT(AI361:AP361)=0,"",AQ361-LOOKUP(2,1/(AI361:AP361<>""),AI361:AP361))) | IF(OR(F361="",AR361=""),"",IF(COUNT(AI361:AQ361)=0,"",AR361-LOOKUP(2,1/(AI361:AQ361<>""),AI361:AQ361))) | IF(OR(F361="",AS361=""),"",IF(COUNT(AI361:AR361)=0,"",AS361-LOOKUP(2,1/(AI361:AR361<>""),AI361:AR361))) | IF(OR(F361="",AT361=""),"",IF(COUNT(AI361:AS361)=0,"",AT361-LOOKUP(2,1/(AI361:AS361<>""),AI361:AS361))) | IF(OR(F361="",AU361=""),"",IF(COUNT(AI361:AT361)=0,"",AU361-LOOKUP(2,1/(AI361:AT361<>""),AI361:AT361))) | IF(OR(F361="",AV361=""),"",IF(COUNT(AI361:AU361)=0,"",AV361-LOOKUP(2,1/(AI361:AU361<>""),AI361:AU361))) | IF(J361="","All_Provinces",IFERROR(VLOOKUP(J361,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K361="","All_Districts",IFERROR(VLOOKUP(K361,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F362="","",ROW()-3) | [18 empty] | IF(AQ362="","",AQ362) |  |  |  | IF(W362<>"",W362,IF(OR(T362="",V362=""),"",EDATE(T362,V362))) |  |  |  |  | IF(F362="","",IF(COUNT(AI362:AV362)=0,IF(AA362="","Not started",AA362),SUBSTITUTE(LOOKUP(2,1/(AI362:AV362<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F362="",COUNT(AI362:AV362)=0),"",TODAY()-LOOKUP(2,1/(AI362:AV362<>""),AI362:AV362)) | IF(OR(F362="",COUNT(AI362:AV362)<2),"",LOOKUP(2,1/(AI362:AV362<>""),AI362:AV362)-MIN(AI362:AV362)) | IF(OR(AD362="",AC362="Not started",AC362=""),"",IFERROR(AD362-IF(VLOOKUP(AC362,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC362,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F362="","",IF(OR(AA362="Cancelled",AC362="Cancelled"),"Cancelled",IF(OR(AC362="Completed / Handover",Y362<>"",Z362>=100),"Completed — on track",IF(O362="Not awarded",IF(U362="",IF(X362="","No planned date",IF(TODAY()>X362,"Behind — past planned date",IF(X362-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U362,"Behind — award date passed",IF(U362-TODAY()<=30,"At risk — close to off track","On track"))),IF(X362="","No planned date",IF(AND(TODAY()>X362,OR(Z362="",Z362<100)),"Behind — past end date",IF(AND(T362<>"",X362<>"",Z362<>"",(Z362<100),((TODAY()-T362)/MAX(X362-T362,1)*100)-Z362>15),"Behind — progress lag",IF(AND(X362-TODAY()<=30,X362-TODAY()>=0,OR(Z362="",Z362<90)),"At risk — close to off track","On track")))))))) | IF(OR(F362="",AC362="Completed / Handover",AC362="Cancelled"),"",IF(O362="Not awarded",IF(U362<>"",U362-TODAY(),IF(X362="","",X362-TODAY())),IF(X362="","",X362-TODAY()))) | [14 empty] | IF(OR(F362="",AJ362=""),"",IF(COUNT(AI362:AI362)=0,"",AJ362-LOOKUP(2,1/(AI362:AI362<>""),AI362:AI362))) | IF(OR(F362="",AK362=""),"",IF(COUNT(AI362:AJ362)=0,"",AK362-LOOKUP(2,1/(AI362:AJ362<>""),AI362:AJ362))) | IF(OR(F362="",AL362=""),"",IF(COUNT(AI362:AK362)=0,"",AL362-LOOKUP(2,1/(AI362:AK362<>""),AI362:AK362))) | IF(OR(F362="",AM362=""),"",IF(COUNT(AI362:AL362)=0,"",AM362-LOOKUP(2,1/(AI362:AL362<>""),AI362:AL362))) | IF(OR(F362="",AN362=""),"",IF(COUNT(AI362:AM362)=0,"",AN362-LOOKUP(2,1/(AI362:AM362<>""),AI362:AM362))) | IF(OR(F362="",AO362=""),"",IF(COUNT(AI362:AN362)=0,"",AO362-LOOKUP(2,1/(AI362:AN362<>""),AI362:AN362))) | IF(OR(F362="",AP362=""),"",IF(COUNT(AI362:AO362)=0,"",AP362-LOOKUP(2,1/(AI362:AO362<>""),AI362:AO362))) | IF(OR(F362="",AQ362=""),"",IF(COUNT(AI362:AP362)=0,"",AQ362-LOOKUP(2,1/(AI362:AP362<>""),AI362:AP362))) | IF(OR(F362="",AR362=""),"",IF(COUNT(AI362:AQ362)=0,"",AR362-LOOKUP(2,1/(AI362:AQ362<>""),AI362:AQ362))) | IF(OR(F362="",AS362=""),"",IF(COUNT(AI362:AR362)=0,"",AS362-LOOKUP(2,1/(AI362:AR362<>""),AI362:AR362))) | IF(OR(F362="",AT362=""),"",IF(COUNT(AI362:AS362)=0,"",AT362-LOOKUP(2,1/(AI362:AS362<>""),AI362:AS362))) | IF(OR(F362="",AU362=""),"",IF(COUNT(AI362:AT362)=0,"",AU362-LOOKUP(2,1/(AI362:AT362<>""),AI362:AT362))) | IF(OR(F362="",AV362=""),"",IF(COUNT(AI362:AU362)=0,"",AV362-LOOKUP(2,1/(AI362:AU362<>""),AI362:AU362))) | IF(J362="","All_Provinces",IFERROR(VLOOKUP(J362,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K362="","All_Districts",IFERROR(VLOOKUP(K362,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F363="","",ROW()-3) | [18 empty] | IF(AQ363="","",AQ363) |  |  |  | IF(W363<>"",W363,IF(OR(T363="",V363=""),"",EDATE(T363,V363))) |  |  |  |  | IF(F363="","",IF(COUNT(AI363:AV363)=0,IF(AA363="","Not started",AA363),SUBSTITUTE(LOOKUP(2,1/(AI363:AV363<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F363="",COUNT(AI363:AV363)=0),"",TODAY()-LOOKUP(2,1/(AI363:AV363<>""),AI363:AV363)) | IF(OR(F363="",COUNT(AI363:AV363)<2),"",LOOKUP(2,1/(AI363:AV363<>""),AI363:AV363)-MIN(AI363:AV363)) | IF(OR(AD363="",AC363="Not started",AC363=""),"",IFERROR(AD363-IF(VLOOKUP(AC363,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC363,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F363="","",IF(OR(AA363="Cancelled",AC363="Cancelled"),"Cancelled",IF(OR(AC363="Completed / Handover",Y363<>"",Z363>=100),"Completed — on track",IF(O363="Not awarded",IF(U363="",IF(X363="","No planned date",IF(TODAY()>X363,"Behind — past planned date",IF(X363-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U363,"Behind — award date passed",IF(U363-TODAY()<=30,"At risk — close to off track","On track"))),IF(X363="","No planned date",IF(AND(TODAY()>X363,OR(Z363="",Z363<100)),"Behind — past end date",IF(AND(T363<>"",X363<>"",Z363<>"",(Z363<100),((TODAY()-T363)/MAX(X363-T363,1)*100)-Z363>15),"Behind — progress lag",IF(AND(X363-TODAY()<=30,X363-TODAY()>=0,OR(Z363="",Z363<90)),"At risk — close to off track","On track")))))))) | IF(OR(F363="",AC363="Completed / Handover",AC363="Cancelled"),"",IF(O363="Not awarded",IF(U363<>"",U363-TODAY(),IF(X363="","",X363-TODAY())),IF(X363="","",X363-TODAY()))) | [14 empty] | IF(OR(F363="",AJ363=""),"",IF(COUNT(AI363:AI363)=0,"",AJ363-LOOKUP(2,1/(AI363:AI363<>""),AI363:AI363))) | IF(OR(F363="",AK363=""),"",IF(COUNT(AI363:AJ363)=0,"",AK363-LOOKUP(2,1/(AI363:AJ363<>""),AI363:AJ363))) | IF(OR(F363="",AL363=""),"",IF(COUNT(AI363:AK363)=0,"",AL363-LOOKUP(2,1/(AI363:AK363<>""),AI363:AK363))) | IF(OR(F363="",AM363=""),"",IF(COUNT(AI363:AL363)=0,"",AM363-LOOKUP(2,1/(AI363:AL363<>""),AI363:AL363))) | IF(OR(F363="",AN363=""),"",IF(COUNT(AI363:AM363)=0,"",AN363-LOOKUP(2,1/(AI363:AM363<>""),AI363:AM363))) | IF(OR(F363="",AO363=""),"",IF(COUNT(AI363:AN363)=0,"",AO363-LOOKUP(2,1/(AI363:AN363<>""),AI363:AN363))) | IF(OR(F363="",AP363=""),"",IF(COUNT(AI363:AO363)=0,"",AP363-LOOKUP(2,1/(AI363:AO363<>""),AI363:AO363))) | IF(OR(F363="",AQ363=""),"",IF(COUNT(AI363:AP363)=0,"",AQ363-LOOKUP(2,1/(AI363:AP363<>""),AI363:AP363))) | IF(OR(F363="",AR363=""),"",IF(COUNT(AI363:AQ363)=0,"",AR363-LOOKUP(2,1/(AI363:AQ363<>""),AI363:AQ363))) | IF(OR(F363="",AS363=""),"",IF(COUNT(AI363:AR363)=0,"",AS363-LOOKUP(2,1/(AI363:AR363<>""),AI363:AR363))) | IF(OR(F363="",AT363=""),"",IF(COUNT(AI363:AS363)=0,"",AT363-LOOKUP(2,1/(AI363:AS363<>""),AI363:AS363))) | IF(OR(F363="",AU363=""),"",IF(COUNT(AI363:AT363)=0,"",AU363-LOOKUP(2,1/(AI363:AT363<>""),AI363:AT363))) | IF(OR(F363="",AV363=""),"",IF(COUNT(AI363:AU363)=0,"",AV363-LOOKUP(2,1/(AI363:AU363<>""),AI363:AU363))) | IF(J363="","All_Provinces",IFERROR(VLOOKUP(J363,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K363="","All_Districts",IFERROR(VLOOKUP(K363,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F364="","",ROW()-3) | [18 empty] | IF(AQ364="","",AQ364) |  |  |  | IF(W364<>"",W364,IF(OR(T364="",V364=""),"",EDATE(T364,V364))) |  |  |  |  | IF(F364="","",IF(COUNT(AI364:AV364)=0,IF(AA364="","Not started",AA364),SUBSTITUTE(LOOKUP(2,1/(AI364:AV364<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F364="",COUNT(AI364:AV364)=0),"",TODAY()-LOOKUP(2,1/(AI364:AV364<>""),AI364:AV364)) | IF(OR(F364="",COUNT(AI364:AV364)<2),"",LOOKUP(2,1/(AI364:AV364<>""),AI364:AV364)-MIN(AI364:AV364)) | IF(OR(AD364="",AC364="Not started",AC364=""),"",IFERROR(AD364-IF(VLOOKUP(AC364,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC364,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F364="","",IF(OR(AA364="Cancelled",AC364="Cancelled"),"Cancelled",IF(OR(AC364="Completed / Handover",Y364<>"",Z364>=100),"Completed — on track",IF(O364="Not awarded",IF(U364="",IF(X364="","No planned date",IF(TODAY()>X364,"Behind — past planned date",IF(X364-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U364,"Behind — award date passed",IF(U364-TODAY()<=30,"At risk — close to off track","On track"))),IF(X364="","No planned date",IF(AND(TODAY()>X364,OR(Z364="",Z364<100)),"Behind — past end date",IF(AND(T364<>"",X364<>"",Z364<>"",(Z364<100),((TODAY()-T364)/MAX(X364-T364,1)*100)-Z364>15),"Behind — progress lag",IF(AND(X364-TODAY()<=30,X364-TODAY()>=0,OR(Z364="",Z364<90)),"At risk — close to off track","On track")))))))) | IF(OR(F364="",AC364="Completed / Handover",AC364="Cancelled"),"",IF(O364="Not awarded",IF(U364<>"",U364-TODAY(),IF(X364="","",X364-TODAY())),IF(X364="","",X364-TODAY()))) | [14 empty] | IF(OR(F364="",AJ364=""),"",IF(COUNT(AI364:AI364)=0,"",AJ364-LOOKUP(2,1/(AI364:AI364<>""),AI364:AI364))) | IF(OR(F364="",AK364=""),"",IF(COUNT(AI364:AJ364)=0,"",AK364-LOOKUP(2,1/(AI364:AJ364<>""),AI364:AJ364))) | IF(OR(F364="",AL364=""),"",IF(COUNT(AI364:AK364)=0,"",AL364-LOOKUP(2,1/(AI364:AK364<>""),AI364:AK364))) | IF(OR(F364="",AM364=""),"",IF(COUNT(AI364:AL364)=0,"",AM364-LOOKUP(2,1/(AI364:AL364<>""),AI364:AL364))) | IF(OR(F364="",AN364=""),"",IF(COUNT(AI364:AM364)=0,"",AN364-LOOKUP(2,1/(AI364:AM364<>""),AI364:AM364))) | IF(OR(F364="",AO364=""),"",IF(COUNT(AI364:AN364)=0,"",AO364-LOOKUP(2,1/(AI364:AN364<>""),AI364:AN364))) | IF(OR(F364="",AP364=""),"",IF(COUNT(AI364:AO364)=0,"",AP364-LOOKUP(2,1/(AI364:AO364<>""),AI364:AO364))) | IF(OR(F364="",AQ364=""),"",IF(COUNT(AI364:AP364)=0,"",AQ364-LOOKUP(2,1/(AI364:AP364<>""),AI364:AP364))) | IF(OR(F364="",AR364=""),"",IF(COUNT(AI364:AQ364)=0,"",AR364-LOOKUP(2,1/(AI364:AQ364<>""),AI364:AQ364))) | IF(OR(F364="",AS364=""),"",IF(COUNT(AI364:AR364)=0,"",AS364-LOOKUP(2,1/(AI364:AR364<>""),AI364:AR364))) | IF(OR(F364="",AT364=""),"",IF(COUNT(AI364:AS364)=0,"",AT364-LOOKUP(2,1/(AI364:AS364<>""),AI364:AS364))) | IF(OR(F364="",AU364=""),"",IF(COUNT(AI364:AT364)=0,"",AU364-LOOKUP(2,1/(AI364:AT364<>""),AI364:AT364))) | IF(OR(F364="",AV364=""),"",IF(COUNT(AI364:AU364)=0,"",AV364-LOOKUP(2,1/(AI364:AU364<>""),AI364:AU364))) | IF(J364="","All_Provinces",IFERROR(VLOOKUP(J364,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K364="","All_Districts",IFERROR(VLOOKUP(K364,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F365="","",ROW()-3) | [18 empty] | IF(AQ365="","",AQ365) |  |  |  | IF(W365<>"",W365,IF(OR(T365="",V365=""),"",EDATE(T365,V365))) |  |  |  |  | IF(F365="","",IF(COUNT(AI365:AV365)=0,IF(AA365="","Not started",AA365),SUBSTITUTE(LOOKUP(2,1/(AI365:AV365<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F365="",COUNT(AI365:AV365)=0),"",TODAY()-LOOKUP(2,1/(AI365:AV365<>""),AI365:AV365)) | IF(OR(F365="",COUNT(AI365:AV365)<2),"",LOOKUP(2,1/(AI365:AV365<>""),AI365:AV365)-MIN(AI365:AV365)) | IF(OR(AD365="",AC365="Not started",AC365=""),"",IFERROR(AD365-IF(VLOOKUP(AC365,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC365,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F365="","",IF(OR(AA365="Cancelled",AC365="Cancelled"),"Cancelled",IF(OR(AC365="Completed / Handover",Y365<>"",Z365>=100),"Completed — on track",IF(O365="Not awarded",IF(U365="",IF(X365="","No planned date",IF(TODAY()>X365,"Behind — past planned date",IF(X365-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U365,"Behind — award date passed",IF(U365-TODAY()<=30,"At risk — close to off track","On track"))),IF(X365="","No planned date",IF(AND(TODAY()>X365,OR(Z365="",Z365<100)),"Behind — past end date",IF(AND(T365<>"",X365<>"",Z365<>"",(Z365<100),((TODAY()-T365)/MAX(X365-T365,1)*100)-Z365>15),"Behind — progress lag",IF(AND(X365-TODAY()<=30,X365-TODAY()>=0,OR(Z365="",Z365<90)),"At risk — close to off track","On track")))))))) | IF(OR(F365="",AC365="Completed / Handover",AC365="Cancelled"),"",IF(O365="Not awarded",IF(U365<>"",U365-TODAY(),IF(X365="","",X365-TODAY())),IF(X365="","",X365-TODAY()))) | [14 empty] | IF(OR(F365="",AJ365=""),"",IF(COUNT(AI365:AI365)=0,"",AJ365-LOOKUP(2,1/(AI365:AI365<>""),AI365:AI365))) | IF(OR(F365="",AK365=""),"",IF(COUNT(AI365:AJ365)=0,"",AK365-LOOKUP(2,1/(AI365:AJ365<>""),AI365:AJ365))) | IF(OR(F365="",AL365=""),"",IF(COUNT(AI365:AK365)=0,"",AL365-LOOKUP(2,1/(AI365:AK365<>""),AI365:AK365))) | IF(OR(F365="",AM365=""),"",IF(COUNT(AI365:AL365)=0,"",AM365-LOOKUP(2,1/(AI365:AL365<>""),AI365:AL365))) | IF(OR(F365="",AN365=""),"",IF(COUNT(AI365:AM365)=0,"",AN365-LOOKUP(2,1/(AI365:AM365<>""),AI365:AM365))) | IF(OR(F365="",AO365=""),"",IF(COUNT(AI365:AN365)=0,"",AO365-LOOKUP(2,1/(AI365:AN365<>""),AI365:AN365))) | IF(OR(F365="",AP365=""),"",IF(COUNT(AI365:AO365)=0,"",AP365-LOOKUP(2,1/(AI365:AO365<>""),AI365:AO365))) | IF(OR(F365="",AQ365=""),"",IF(COUNT(AI365:AP365)=0,"",AQ365-LOOKUP(2,1/(AI365:AP365<>""),AI365:AP365))) | IF(OR(F365="",AR365=""),"",IF(COUNT(AI365:AQ365)=0,"",AR365-LOOKUP(2,1/(AI365:AQ365<>""),AI365:AQ365))) | IF(OR(F365="",AS365=""),"",IF(COUNT(AI365:AR365)=0,"",AS365-LOOKUP(2,1/(AI365:AR365<>""),AI365:AR365))) | IF(OR(F365="",AT365=""),"",IF(COUNT(AI365:AS365)=0,"",AT365-LOOKUP(2,1/(AI365:AS365<>""),AI365:AS365))) | IF(OR(F365="",AU365=""),"",IF(COUNT(AI365:AT365)=0,"",AU365-LOOKUP(2,1/(AI365:AT365<>""),AI365:AT365))) | IF(OR(F365="",AV365=""),"",IF(COUNT(AI365:AU365)=0,"",AV365-LOOKUP(2,1/(AI365:AU365<>""),AI365:AU365))) | IF(J365="","All_Provinces",IFERROR(VLOOKUP(J365,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K365="","All_Districts",IFERROR(VLOOKUP(K365,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F366="","",ROW()-3) | [18 empty] | IF(AQ366="","",AQ366) |  |  |  | IF(W366<>"",W366,IF(OR(T366="",V366=""),"",EDATE(T366,V366))) |  |  |  |  | IF(F366="","",IF(COUNT(AI366:AV366)=0,IF(AA366="","Not started",AA366),SUBSTITUTE(LOOKUP(2,1/(AI366:AV366<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F366="",COUNT(AI366:AV366)=0),"",TODAY()-LOOKUP(2,1/(AI366:AV366<>""),AI366:AV366)) | IF(OR(F366="",COUNT(AI366:AV366)<2),"",LOOKUP(2,1/(AI366:AV366<>""),AI366:AV366)-MIN(AI366:AV366)) | IF(OR(AD366="",AC366="Not started",AC366=""),"",IFERROR(AD366-IF(VLOOKUP(AC366,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC366,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F366="","",IF(OR(AA366="Cancelled",AC366="Cancelled"),"Cancelled",IF(OR(AC366="Completed / Handover",Y366<>"",Z366>=100),"Completed — on track",IF(O366="Not awarded",IF(U366="",IF(X366="","No planned date",IF(TODAY()>X366,"Behind — past planned date",IF(X366-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U366,"Behind — award date passed",IF(U366-TODAY()<=30,"At risk — close to off track","On track"))),IF(X366="","No planned date",IF(AND(TODAY()>X366,OR(Z366="",Z366<100)),"Behind — past end date",IF(AND(T366<>"",X366<>"",Z366<>"",(Z366<100),((TODAY()-T366)/MAX(X366-T366,1)*100)-Z366>15),"Behind — progress lag",IF(AND(X366-TODAY()<=30,X366-TODAY()>=0,OR(Z366="",Z366<90)),"At risk — close to off track","On track")))))))) | IF(OR(F366="",AC366="Completed / Handover",AC366="Cancelled"),"",IF(O366="Not awarded",IF(U366<>"",U366-TODAY(),IF(X366="","",X366-TODAY())),IF(X366="","",X366-TODAY()))) | [14 empty] | IF(OR(F366="",AJ366=""),"",IF(COUNT(AI366:AI366)=0,"",AJ366-LOOKUP(2,1/(AI366:AI366<>""),AI366:AI366))) | IF(OR(F366="",AK366=""),"",IF(COUNT(AI366:AJ366)=0,"",AK366-LOOKUP(2,1/(AI366:AJ366<>""),AI366:AJ366))) | IF(OR(F366="",AL366=""),"",IF(COUNT(AI366:AK366)=0,"",AL366-LOOKUP(2,1/(AI366:AK366<>""),AI366:AK366))) | IF(OR(F366="",AM366=""),"",IF(COUNT(AI366:AL366)=0,"",AM366-LOOKUP(2,1/(AI366:AL366<>""),AI366:AL366))) | IF(OR(F366="",AN366=""),"",IF(COUNT(AI366:AM366)=0,"",AN366-LOOKUP(2,1/(AI366:AM366<>""),AI366:AM366))) | IF(OR(F366="",AO366=""),"",IF(COUNT(AI366:AN366)=0,"",AO366-LOOKUP(2,1/(AI366:AN366<>""),AI366:AN366))) | IF(OR(F366="",AP366=""),"",IF(COUNT(AI366:AO366)=0,"",AP366-LOOKUP(2,1/(AI366:AO366<>""),AI366:AO366))) | IF(OR(F366="",AQ366=""),"",IF(COUNT(AI366:AP366)=0,"",AQ366-LOOKUP(2,1/(AI366:AP366<>""),AI366:AP366))) | IF(OR(F366="",AR366=""),"",IF(COUNT(AI366:AQ366)=0,"",AR366-LOOKUP(2,1/(AI366:AQ366<>""),AI366:AQ366))) | IF(OR(F366="",AS366=""),"",IF(COUNT(AI366:AR366)=0,"",AS366-LOOKUP(2,1/(AI366:AR366<>""),AI366:AR366))) | IF(OR(F366="",AT366=""),"",IF(COUNT(AI366:AS366)=0,"",AT366-LOOKUP(2,1/(AI366:AS366<>""),AI366:AS366))) | IF(OR(F366="",AU366=""),"",IF(COUNT(AI366:AT366)=0,"",AU366-LOOKUP(2,1/(AI366:AT366<>""),AI366:AT366))) | IF(OR(F366="",AV366=""),"",IF(COUNT(AI366:AU366)=0,"",AV366-LOOKUP(2,1/(AI366:AU366<>""),AI366:AU366))) | IF(J366="","All_Provinces",IFERROR(VLOOKUP(J366,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K366="","All_Districts",IFERROR(VLOOKUP(K366,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F367="","",ROW()-3) | [18 empty] | IF(AQ367="","",AQ367) |  |  |  | IF(W367<>"",W367,IF(OR(T367="",V367=""),"",EDATE(T367,V367))) |  |  |  |  | IF(F367="","",IF(COUNT(AI367:AV367)=0,IF(AA367="","Not started",AA367),SUBSTITUTE(LOOKUP(2,1/(AI367:AV367<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F367="",COUNT(AI367:AV367)=0),"",TODAY()-LOOKUP(2,1/(AI367:AV367<>""),AI367:AV367)) | IF(OR(F367="",COUNT(AI367:AV367)<2),"",LOOKUP(2,1/(AI367:AV367<>""),AI367:AV367)-MIN(AI367:AV367)) | IF(OR(AD367="",AC367="Not started",AC367=""),"",IFERROR(AD367-IF(VLOOKUP(AC367,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC367,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F367="","",IF(OR(AA367="Cancelled",AC367="Cancelled"),"Cancelled",IF(OR(AC367="Completed / Handover",Y367<>"",Z367>=100),"Completed — on track",IF(O367="Not awarded",IF(U367="",IF(X367="","No planned date",IF(TODAY()>X367,"Behind — past planned date",IF(X367-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U367,"Behind — award date passed",IF(U367-TODAY()<=30,"At risk — close to off track","On track"))),IF(X367="","No planned date",IF(AND(TODAY()>X367,OR(Z367="",Z367<100)),"Behind — past end date",IF(AND(T367<>"",X367<>"",Z367<>"",(Z367<100),((TODAY()-T367)/MAX(X367-T367,1)*100)-Z367>15),"Behind — progress lag",IF(AND(X367-TODAY()<=30,X367-TODAY()>=0,OR(Z367="",Z367<90)),"At risk — close to off track","On track")))))))) | IF(OR(F367="",AC367="Completed / Handover",AC367="Cancelled"),"",IF(O367="Not awarded",IF(U367<>"",U367-TODAY(),IF(X367="","",X367-TODAY())),IF(X367="","",X367-TODAY()))) | [14 empty] | IF(OR(F367="",AJ367=""),"",IF(COUNT(AI367:AI367)=0,"",AJ367-LOOKUP(2,1/(AI367:AI367<>""),AI367:AI367))) | IF(OR(F367="",AK367=""),"",IF(COUNT(AI367:AJ367)=0,"",AK367-LOOKUP(2,1/(AI367:AJ367<>""),AI367:AJ367))) | IF(OR(F367="",AL367=""),"",IF(COUNT(AI367:AK367)=0,"",AL367-LOOKUP(2,1/(AI367:AK367<>""),AI367:AK367))) | IF(OR(F367="",AM367=""),"",IF(COUNT(AI367:AL367)=0,"",AM367-LOOKUP(2,1/(AI367:AL367<>""),AI367:AL367))) | IF(OR(F367="",AN367=""),"",IF(COUNT(AI367:AM367)=0,"",AN367-LOOKUP(2,1/(AI367:AM367<>""),AI367:AM367))) | IF(OR(F367="",AO367=""),"",IF(COUNT(AI367:AN367)=0,"",AO367-LOOKUP(2,1/(AI367:AN367<>""),AI367:AN367))) | IF(OR(F367="",AP367=""),"",IF(COUNT(AI367:AO367)=0,"",AP367-LOOKUP(2,1/(AI367:AO367<>""),AI367:AO367))) | IF(OR(F367="",AQ367=""),"",IF(COUNT(AI367:AP367)=0,"",AQ367-LOOKUP(2,1/(AI367:AP367<>""),AI367:AP367))) | IF(OR(F367="",AR367=""),"",IF(COUNT(AI367:AQ367)=0,"",AR367-LOOKUP(2,1/(AI367:AQ367<>""),AI367:AQ367))) | IF(OR(F367="",AS367=""),"",IF(COUNT(AI367:AR367)=0,"",AS367-LOOKUP(2,1/(AI367:AR367<>""),AI367:AR367))) | IF(OR(F367="",AT367=""),"",IF(COUNT(AI367:AS367)=0,"",AT367-LOOKUP(2,1/(AI367:AS367<>""),AI367:AS367))) | IF(OR(F367="",AU367=""),"",IF(COUNT(AI367:AT367)=0,"",AU367-LOOKUP(2,1/(AI367:AT367<>""),AI367:AT367))) | IF(OR(F367="",AV367=""),"",IF(COUNT(AI367:AU367)=0,"",AV367-LOOKUP(2,1/(AI367:AU367<>""),AI367:AU367))) | IF(J367="","All_Provinces",IFERROR(VLOOKUP(J367,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K367="","All_Districts",IFERROR(VLOOKUP(K367,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F368="","",ROW()-3) | [18 empty] | IF(AQ368="","",AQ368) |  |  |  | IF(W368<>"",W368,IF(OR(T368="",V368=""),"",EDATE(T368,V368))) |  |  |  |  | IF(F368="","",IF(COUNT(AI368:AV368)=0,IF(AA368="","Not started",AA368),SUBSTITUTE(LOOKUP(2,1/(AI368:AV368<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F368="",COUNT(AI368:AV368)=0),"",TODAY()-LOOKUP(2,1/(AI368:AV368<>""),AI368:AV368)) | IF(OR(F368="",COUNT(AI368:AV368)<2),"",LOOKUP(2,1/(AI368:AV368<>""),AI368:AV368)-MIN(AI368:AV368)) | IF(OR(AD368="",AC368="Not started",AC368=""),"",IFERROR(AD368-IF(VLOOKUP(AC368,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC368,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F368="","",IF(OR(AA368="Cancelled",AC368="Cancelled"),"Cancelled",IF(OR(AC368="Completed / Handover",Y368<>"",Z368>=100),"Completed — on track",IF(O368="Not awarded",IF(U368="",IF(X368="","No planned date",IF(TODAY()>X368,"Behind — past planned date",IF(X368-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U368,"Behind — award date passed",IF(U368-TODAY()<=30,"At risk — close to off track","On track"))),IF(X368="","No planned date",IF(AND(TODAY()>X368,OR(Z368="",Z368<100)),"Behind — past end date",IF(AND(T368<>"",X368<>"",Z368<>"",(Z368<100),((TODAY()-T368)/MAX(X368-T368,1)*100)-Z368>15),"Behind — progress lag",IF(AND(X368-TODAY()<=30,X368-TODAY()>=0,OR(Z368="",Z368<90)),"At risk — close to off track","On track")))))))) | IF(OR(F368="",AC368="Completed / Handover",AC368="Cancelled"),"",IF(O368="Not awarded",IF(U368<>"",U368-TODAY(),IF(X368="","",X368-TODAY())),IF(X368="","",X368-TODAY()))) | [14 empty] | IF(OR(F368="",AJ368=""),"",IF(COUNT(AI368:AI368)=0,"",AJ368-LOOKUP(2,1/(AI368:AI368<>""),AI368:AI368))) | IF(OR(F368="",AK368=""),"",IF(COUNT(AI368:AJ368)=0,"",AK368-LOOKUP(2,1/(AI368:AJ368<>""),AI368:AJ368))) | IF(OR(F368="",AL368=""),"",IF(COUNT(AI368:AK368)=0,"",AL368-LOOKUP(2,1/(AI368:AK368<>""),AI368:AK368))) | IF(OR(F368="",AM368=""),"",IF(COUNT(AI368:AL368)=0,"",AM368-LOOKUP(2,1/(AI368:AL368<>""),AI368:AL368))) | IF(OR(F368="",AN368=""),"",IF(COUNT(AI368:AM368)=0,"",AN368-LOOKUP(2,1/(AI368:AM368<>""),AI368:AM368))) | IF(OR(F368="",AO368=""),"",IF(COUNT(AI368:AN368)=0,"",AO368-LOOKUP(2,1/(AI368:AN368<>""),AI368:AN368))) | IF(OR(F368="",AP368=""),"",IF(COUNT(AI368:AO368)=0,"",AP368-LOOKUP(2,1/(AI368:AO368<>""),AI368:AO368))) | IF(OR(F368="",AQ368=""),"",IF(COUNT(AI368:AP368)=0,"",AQ368-LOOKUP(2,1/(AI368:AP368<>""),AI368:AP368))) | IF(OR(F368="",AR368=""),"",IF(COUNT(AI368:AQ368)=0,"",AR368-LOOKUP(2,1/(AI368:AQ368<>""),AI368:AQ368))) | IF(OR(F368="",AS368=""),"",IF(COUNT(AI368:AR368)=0,"",AS368-LOOKUP(2,1/(AI368:AR368<>""),AI368:AR368))) | IF(OR(F368="",AT368=""),"",IF(COUNT(AI368:AS368)=0,"",AT368-LOOKUP(2,1/(AI368:AS368<>""),AI368:AS368))) | IF(OR(F368="",AU368=""),"",IF(COUNT(AI368:AT368)=0,"",AU368-LOOKUP(2,1/(AI368:AT368<>""),AI368:AT368))) | IF(OR(F368="",AV368=""),"",IF(COUNT(AI368:AU368)=0,"",AV368-LOOKUP(2,1/(AI368:AU368<>""),AI368:AU368))) | IF(J368="","All_Provinces",IFERROR(VLOOKUP(J368,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K368="","All_Districts",IFERROR(VLOOKUP(K368,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F369="","",ROW()-3) | [18 empty] | IF(AQ369="","",AQ369) |  |  |  | IF(W369<>"",W369,IF(OR(T369="",V369=""),"",EDATE(T369,V369))) |  |  |  |  | IF(F369="","",IF(COUNT(AI369:AV369)=0,IF(AA369="","Not started",AA369),SUBSTITUTE(LOOKUP(2,1/(AI369:AV369<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F369="",COUNT(AI369:AV369)=0),"",TODAY()-LOOKUP(2,1/(AI369:AV369<>""),AI369:AV369)) | IF(OR(F369="",COUNT(AI369:AV369)<2),"",LOOKUP(2,1/(AI369:AV369<>""),AI369:AV369)-MIN(AI369:AV369)) | IF(OR(AD369="",AC369="Not started",AC369=""),"",IFERROR(AD369-IF(VLOOKUP(AC369,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC369,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F369="","",IF(OR(AA369="Cancelled",AC369="Cancelled"),"Cancelled",IF(OR(AC369="Completed / Handover",Y369<>"",Z369>=100),"Completed — on track",IF(O369="Not awarded",IF(U369="",IF(X369="","No planned date",IF(TODAY()>X369,"Behind — past planned date",IF(X369-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U369,"Behind — award date passed",IF(U369-TODAY()<=30,"At risk — close to off track","On track"))),IF(X369="","No planned date",IF(AND(TODAY()>X369,OR(Z369="",Z369<100)),"Behind — past end date",IF(AND(T369<>"",X369<>"",Z369<>"",(Z369<100),((TODAY()-T369)/MAX(X369-T369,1)*100)-Z369>15),"Behind — progress lag",IF(AND(X369-TODAY()<=30,X369-TODAY()>=0,OR(Z369="",Z369<90)),"At risk — close to off track","On track")))))))) | IF(OR(F369="",AC369="Completed / Handover",AC369="Cancelled"),"",IF(O369="Not awarded",IF(U369<>"",U369-TODAY(),IF(X369="","",X369-TODAY())),IF(X369="","",X369-TODAY()))) | [14 empty] | IF(OR(F369="",AJ369=""),"",IF(COUNT(AI369:AI369)=0,"",AJ369-LOOKUP(2,1/(AI369:AI369<>""),AI369:AI369))) | IF(OR(F369="",AK369=""),"",IF(COUNT(AI369:AJ369)=0,"",AK369-LOOKUP(2,1/(AI369:AJ369<>""),AI369:AJ369))) | IF(OR(F369="",AL369=""),"",IF(COUNT(AI369:AK369)=0,"",AL369-LOOKUP(2,1/(AI369:AK369<>""),AI369:AK369))) | IF(OR(F369="",AM369=""),"",IF(COUNT(AI369:AL369)=0,"",AM369-LOOKUP(2,1/(AI369:AL369<>""),AI369:AL369))) | IF(OR(F369="",AN369=""),"",IF(COUNT(AI369:AM369)=0,"",AN369-LOOKUP(2,1/(AI369:AM369<>""),AI369:AM369))) | IF(OR(F369="",AO369=""),"",IF(COUNT(AI369:AN369)=0,"",AO369-LOOKUP(2,1/(AI369:AN369<>""),AI369:AN369))) | IF(OR(F369="",AP369=""),"",IF(COUNT(AI369:AO369)=0,"",AP369-LOOKUP(2,1/(AI369:AO369<>""),AI369:AO369))) | IF(OR(F369="",AQ369=""),"",IF(COUNT(AI369:AP369)=0,"",AQ369-LOOKUP(2,1/(AI369:AP369<>""),AI369:AP369))) | IF(OR(F369="",AR369=""),"",IF(COUNT(AI369:AQ369)=0,"",AR369-LOOKUP(2,1/(AI369:AQ369<>""),AI369:AQ369))) | IF(OR(F369="",AS369=""),"",IF(COUNT(AI369:AR369)=0,"",AS369-LOOKUP(2,1/(AI369:AR369<>""),AI369:AR369))) | IF(OR(F369="",AT369=""),"",IF(COUNT(AI369:AS369)=0,"",AT369-LOOKUP(2,1/(AI369:AS369<>""),AI369:AS369))) | IF(OR(F369="",AU369=""),"",IF(COUNT(AI369:AT369)=0,"",AU369-LOOKUP(2,1/(AI369:AT369<>""),AI369:AT369))) | IF(OR(F369="",AV369=""),"",IF(COUNT(AI369:AU369)=0,"",AV369-LOOKUP(2,1/(AI369:AU369<>""),AI369:AU369))) | IF(J369="","All_Provinces",IFERROR(VLOOKUP(J369,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K369="","All_Districts",IFERROR(VLOOKUP(K369,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F370="","",ROW()-3) | [18 empty] | IF(AQ370="","",AQ370) |  |  |  | IF(W370<>"",W370,IF(OR(T370="",V370=""),"",EDATE(T370,V370))) |  |  |  |  | IF(F370="","",IF(COUNT(AI370:AV370)=0,IF(AA370="","Not started",AA370),SUBSTITUTE(LOOKUP(2,1/(AI370:AV370<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F370="",COUNT(AI370:AV370)=0),"",TODAY()-LOOKUP(2,1/(AI370:AV370<>""),AI370:AV370)) | IF(OR(F370="",COUNT(AI370:AV370)<2),"",LOOKUP(2,1/(AI370:AV370<>""),AI370:AV370)-MIN(AI370:AV370)) | IF(OR(AD370="",AC370="Not started",AC370=""),"",IFERROR(AD370-IF(VLOOKUP(AC370,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC370,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F370="","",IF(OR(AA370="Cancelled",AC370="Cancelled"),"Cancelled",IF(OR(AC370="Completed / Handover",Y370<>"",Z370>=100),"Completed — on track",IF(O370="Not awarded",IF(U370="",IF(X370="","No planned date",IF(TODAY()>X370,"Behind — past planned date",IF(X370-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U370,"Behind — award date passed",IF(U370-TODAY()<=30,"At risk — close to off track","On track"))),IF(X370="","No planned date",IF(AND(TODAY()>X370,OR(Z370="",Z370<100)),"Behind — past end date",IF(AND(T370<>"",X370<>"",Z370<>"",(Z370<100),((TODAY()-T370)/MAX(X370-T370,1)*100)-Z370>15),"Behind — progress lag",IF(AND(X370-TODAY()<=30,X370-TODAY()>=0,OR(Z370="",Z370<90)),"At risk — close to off track","On track")))))))) | IF(OR(F370="",AC370="Completed / Handover",AC370="Cancelled"),"",IF(O370="Not awarded",IF(U370<>"",U370-TODAY(),IF(X370="","",X370-TODAY())),IF(X370="","",X370-TODAY()))) | [14 empty] | IF(OR(F370="",AJ370=""),"",IF(COUNT(AI370:AI370)=0,"",AJ370-LOOKUP(2,1/(AI370:AI370<>""),AI370:AI370))) | IF(OR(F370="",AK370=""),"",IF(COUNT(AI370:AJ370)=0,"",AK370-LOOKUP(2,1/(AI370:AJ370<>""),AI370:AJ370))) | IF(OR(F370="",AL370=""),"",IF(COUNT(AI370:AK370)=0,"",AL370-LOOKUP(2,1/(AI370:AK370<>""),AI370:AK370))) | IF(OR(F370="",AM370=""),"",IF(COUNT(AI370:AL370)=0,"",AM370-LOOKUP(2,1/(AI370:AL370<>""),AI370:AL370))) | IF(OR(F370="",AN370=""),"",IF(COUNT(AI370:AM370)=0,"",AN370-LOOKUP(2,1/(AI370:AM370<>""),AI370:AM370))) | IF(OR(F370="",AO370=""),"",IF(COUNT(AI370:AN370)=0,"",AO370-LOOKUP(2,1/(AI370:AN370<>""),AI370:AN370))) | IF(OR(F370="",AP370=""),"",IF(COUNT(AI370:AO370)=0,"",AP370-LOOKUP(2,1/(AI370:AO370<>""),AI370:AO370))) | IF(OR(F370="",AQ370=""),"",IF(COUNT(AI370:AP370)=0,"",AQ370-LOOKUP(2,1/(AI370:AP370<>""),AI370:AP370))) | IF(OR(F370="",AR370=""),"",IF(COUNT(AI370:AQ370)=0,"",AR370-LOOKUP(2,1/(AI370:AQ370<>""),AI370:AQ370))) | IF(OR(F370="",AS370=""),"",IF(COUNT(AI370:AR370)=0,"",AS370-LOOKUP(2,1/(AI370:AR370<>""),AI370:AR370))) | IF(OR(F370="",AT370=""),"",IF(COUNT(AI370:AS370)=0,"",AT370-LOOKUP(2,1/(AI370:AS370<>""),AI370:AS370))) | IF(OR(F370="",AU370=""),"",IF(COUNT(AI370:AT370)=0,"",AU370-LOOKUP(2,1/(AI370:AT370<>""),AI370:AT370))) | IF(OR(F370="",AV370=""),"",IF(COUNT(AI370:AU370)=0,"",AV370-LOOKUP(2,1/(AI370:AU370<>""),AI370:AU370))) | IF(J370="","All_Provinces",IFERROR(VLOOKUP(J370,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K370="","All_Districts",IFERROR(VLOOKUP(K370,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F371="","",ROW()-3) | [18 empty] | IF(AQ371="","",AQ371) |  |  |  | IF(W371<>"",W371,IF(OR(T371="",V371=""),"",EDATE(T371,V371))) |  |  |  |  | IF(F371="","",IF(COUNT(AI371:AV371)=0,IF(AA371="","Not started",AA371),SUBSTITUTE(LOOKUP(2,1/(AI371:AV371<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F371="",COUNT(AI371:AV371)=0),"",TODAY()-LOOKUP(2,1/(AI371:AV371<>""),AI371:AV371)) | IF(OR(F371="",COUNT(AI371:AV371)<2),"",LOOKUP(2,1/(AI371:AV371<>""),AI371:AV371)-MIN(AI371:AV371)) | IF(OR(AD371="",AC371="Not started",AC371=""),"",IFERROR(AD371-IF(VLOOKUP(AC371,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC371,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F371="","",IF(OR(AA371="Cancelled",AC371="Cancelled"),"Cancelled",IF(OR(AC371="Completed / Handover",Y371<>"",Z371>=100),"Completed — on track",IF(O371="Not awarded",IF(U371="",IF(X371="","No planned date",IF(TODAY()>X371,"Behind — past planned date",IF(X371-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U371,"Behind — award date passed",IF(U371-TODAY()<=30,"At risk — close to off track","On track"))),IF(X371="","No planned date",IF(AND(TODAY()>X371,OR(Z371="",Z371<100)),"Behind — past end date",IF(AND(T371<>"",X371<>"",Z371<>"",(Z371<100),((TODAY()-T371)/MAX(X371-T371,1)*100)-Z371>15),"Behind — progress lag",IF(AND(X371-TODAY()<=30,X371-TODAY()>=0,OR(Z371="",Z371<90)),"At risk — close to off track","On track")))))))) | IF(OR(F371="",AC371="Completed / Handover",AC371="Cancelled"),"",IF(O371="Not awarded",IF(U371<>"",U371-TODAY(),IF(X371="","",X371-TODAY())),IF(X371="","",X371-TODAY()))) | [14 empty] | IF(OR(F371="",AJ371=""),"",IF(COUNT(AI371:AI371)=0,"",AJ371-LOOKUP(2,1/(AI371:AI371<>""),AI371:AI371))) | IF(OR(F371="",AK371=""),"",IF(COUNT(AI371:AJ371)=0,"",AK371-LOOKUP(2,1/(AI371:AJ371<>""),AI371:AJ371))) | IF(OR(F371="",AL371=""),"",IF(COUNT(AI371:AK371)=0,"",AL371-LOOKUP(2,1/(AI371:AK371<>""),AI371:AK371))) | IF(OR(F371="",AM371=""),"",IF(COUNT(AI371:AL371)=0,"",AM371-LOOKUP(2,1/(AI371:AL371<>""),AI371:AL371))) | IF(OR(F371="",AN371=""),"",IF(COUNT(AI371:AM371)=0,"",AN371-LOOKUP(2,1/(AI371:AM371<>""),AI371:AM371))) | IF(OR(F371="",AO371=""),"",IF(COUNT(AI371:AN371)=0,"",AO371-LOOKUP(2,1/(AI371:AN371<>""),AI371:AN371))) | IF(OR(F371="",AP371=""),"",IF(COUNT(AI371:AO371)=0,"",AP371-LOOKUP(2,1/(AI371:AO371<>""),AI371:AO371))) | IF(OR(F371="",AQ371=""),"",IF(COUNT(AI371:AP371)=0,"",AQ371-LOOKUP(2,1/(AI371:AP371<>""),AI371:AP371))) | IF(OR(F371="",AR371=""),"",IF(COUNT(AI371:AQ371)=0,"",AR371-LOOKUP(2,1/(AI371:AQ371<>""),AI371:AQ371))) | IF(OR(F371="",AS371=""),"",IF(COUNT(AI371:AR371)=0,"",AS371-LOOKUP(2,1/(AI371:AR371<>""),AI371:AR371))) | IF(OR(F371="",AT371=""),"",IF(COUNT(AI371:AS371)=0,"",AT371-LOOKUP(2,1/(AI371:AS371<>""),AI371:AS371))) | IF(OR(F371="",AU371=""),"",IF(COUNT(AI371:AT371)=0,"",AU371-LOOKUP(2,1/(AI371:AT371<>""),AI371:AT371))) | IF(OR(F371="",AV371=""),"",IF(COUNT(AI371:AU371)=0,"",AV371-LOOKUP(2,1/(AI371:AU371<>""),AI371:AU371))) | IF(J371="","All_Provinces",IFERROR(VLOOKUP(J371,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K371="","All_Districts",IFERROR(VLOOKUP(K371,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F372="","",ROW()-3) | [18 empty] | IF(AQ372="","",AQ372) |  |  |  | IF(W372<>"",W372,IF(OR(T372="",V372=""),"",EDATE(T372,V372))) |  |  |  |  | IF(F372="","",IF(COUNT(AI372:AV372)=0,IF(AA372="","Not started",AA372),SUBSTITUTE(LOOKUP(2,1/(AI372:AV372<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F372="",COUNT(AI372:AV372)=0),"",TODAY()-LOOKUP(2,1/(AI372:AV372<>""),AI372:AV372)) | IF(OR(F372="",COUNT(AI372:AV372)<2),"",LOOKUP(2,1/(AI372:AV372<>""),AI372:AV372)-MIN(AI372:AV372)) | IF(OR(AD372="",AC372="Not started",AC372=""),"",IFERROR(AD372-IF(VLOOKUP(AC372,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC372,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F372="","",IF(OR(AA372="Cancelled",AC372="Cancelled"),"Cancelled",IF(OR(AC372="Completed / Handover",Y372<>"",Z372>=100),"Completed — on track",IF(O372="Not awarded",IF(U372="",IF(X372="","No planned date",IF(TODAY()>X372,"Behind — past planned date",IF(X372-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U372,"Behind — award date passed",IF(U372-TODAY()<=30,"At risk — close to off track","On track"))),IF(X372="","No planned date",IF(AND(TODAY()>X372,OR(Z372="",Z372<100)),"Behind — past end date",IF(AND(T372<>"",X372<>"",Z372<>"",(Z372<100),((TODAY()-T372)/MAX(X372-T372,1)*100)-Z372>15),"Behind — progress lag",IF(AND(X372-TODAY()<=30,X372-TODAY()>=0,OR(Z372="",Z372<90)),"At risk — close to off track","On track")))))))) | IF(OR(F372="",AC372="Completed / Handover",AC372="Cancelled"),"",IF(O372="Not awarded",IF(U372<>"",U372-TODAY(),IF(X372="","",X372-TODAY())),IF(X372="","",X372-TODAY()))) | [14 empty] | IF(OR(F372="",AJ372=""),"",IF(COUNT(AI372:AI372)=0,"",AJ372-LOOKUP(2,1/(AI372:AI372<>""),AI372:AI372))) | IF(OR(F372="",AK372=""),"",IF(COUNT(AI372:AJ372)=0,"",AK372-LOOKUP(2,1/(AI372:AJ372<>""),AI372:AJ372))) | IF(OR(F372="",AL372=""),"",IF(COUNT(AI372:AK372)=0,"",AL372-LOOKUP(2,1/(AI372:AK372<>""),AI372:AK372))) | IF(OR(F372="",AM372=""),"",IF(COUNT(AI372:AL372)=0,"",AM372-LOOKUP(2,1/(AI372:AL372<>""),AI372:AL372))) | IF(OR(F372="",AN372=""),"",IF(COUNT(AI372:AM372)=0,"",AN372-LOOKUP(2,1/(AI372:AM372<>""),AI372:AM372))) | IF(OR(F372="",AO372=""),"",IF(COUNT(AI372:AN372)=0,"",AO372-LOOKUP(2,1/(AI372:AN372<>""),AI372:AN372))) | IF(OR(F372="",AP372=""),"",IF(COUNT(AI372:AO372)=0,"",AP372-LOOKUP(2,1/(AI372:AO372<>""),AI372:AO372))) | IF(OR(F372="",AQ372=""),"",IF(COUNT(AI372:AP372)=0,"",AQ372-LOOKUP(2,1/(AI372:AP372<>""),AI372:AP372))) | IF(OR(F372="",AR372=""),"",IF(COUNT(AI372:AQ372)=0,"",AR372-LOOKUP(2,1/(AI372:AQ372<>""),AI372:AQ372))) | IF(OR(F372="",AS372=""),"",IF(COUNT(AI372:AR372)=0,"",AS372-LOOKUP(2,1/(AI372:AR372<>""),AI372:AR372))) | IF(OR(F372="",AT372=""),"",IF(COUNT(AI372:AS372)=0,"",AT372-LOOKUP(2,1/(AI372:AS372<>""),AI372:AS372))) | IF(OR(F372="",AU372=""),"",IF(COUNT(AI372:AT372)=0,"",AU372-LOOKUP(2,1/(AI372:AT372<>""),AI372:AT372))) | IF(OR(F372="",AV372=""),"",IF(COUNT(AI372:AU372)=0,"",AV372-LOOKUP(2,1/(AI372:AU372<>""),AI372:AU372))) | IF(J372="","All_Provinces",IFERROR(VLOOKUP(J372,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K372="","All_Districts",IFERROR(VLOOKUP(K372,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F373="","",ROW()-3) | [18 empty] | IF(AQ373="","",AQ373) |  |  |  | IF(W373<>"",W373,IF(OR(T373="",V373=""),"",EDATE(T373,V373))) |  |  |  |  | IF(F373="","",IF(COUNT(AI373:AV373)=0,IF(AA373="","Not started",AA373),SUBSTITUTE(LOOKUP(2,1/(AI373:AV373<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F373="",COUNT(AI373:AV373)=0),"",TODAY()-LOOKUP(2,1/(AI373:AV373<>""),AI373:AV373)) | IF(OR(F373="",COUNT(AI373:AV373)<2),"",LOOKUP(2,1/(AI373:AV373<>""),AI373:AV373)-MIN(AI373:AV373)) | IF(OR(AD373="",AC373="Not started",AC373=""),"",IFERROR(AD373-IF(VLOOKUP(AC373,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC373,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F373="","",IF(OR(AA373="Cancelled",AC373="Cancelled"),"Cancelled",IF(OR(AC373="Completed / Handover",Y373<>"",Z373>=100),"Completed — on track",IF(O373="Not awarded",IF(U373="",IF(X373="","No planned date",IF(TODAY()>X373,"Behind — past planned date",IF(X373-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U373,"Behind — award date passed",IF(U373-TODAY()<=30,"At risk — close to off track","On track"))),IF(X373="","No planned date",IF(AND(TODAY()>X373,OR(Z373="",Z373<100)),"Behind — past end date",IF(AND(T373<>"",X373<>"",Z373<>"",(Z373<100),((TODAY()-T373)/MAX(X373-T373,1)*100)-Z373>15),"Behind — progress lag",IF(AND(X373-TODAY()<=30,X373-TODAY()>=0,OR(Z373="",Z373<90)),"At risk — close to off track","On track")))))))) | IF(OR(F373="",AC373="Completed / Handover",AC373="Cancelled"),"",IF(O373="Not awarded",IF(U373<>"",U373-TODAY(),IF(X373="","",X373-TODAY())),IF(X373="","",X373-TODAY()))) | [14 empty] | IF(OR(F373="",AJ373=""),"",IF(COUNT(AI373:AI373)=0,"",AJ373-LOOKUP(2,1/(AI373:AI373<>""),AI373:AI373))) | IF(OR(F373="",AK373=""),"",IF(COUNT(AI373:AJ373)=0,"",AK373-LOOKUP(2,1/(AI373:AJ373<>""),AI373:AJ373))) | IF(OR(F373="",AL373=""),"",IF(COUNT(AI373:AK373)=0,"",AL373-LOOKUP(2,1/(AI373:AK373<>""),AI373:AK373))) | IF(OR(F373="",AM373=""),"",IF(COUNT(AI373:AL373)=0,"",AM373-LOOKUP(2,1/(AI373:AL373<>""),AI373:AL373))) | IF(OR(F373="",AN373=""),"",IF(COUNT(AI373:AM373)=0,"",AN373-LOOKUP(2,1/(AI373:AM373<>""),AI373:AM373))) | IF(OR(F373="",AO373=""),"",IF(COUNT(AI373:AN373)=0,"",AO373-LOOKUP(2,1/(AI373:AN373<>""),AI373:AN373))) | IF(OR(F373="",AP373=""),"",IF(COUNT(AI373:AO373)=0,"",AP373-LOOKUP(2,1/(AI373:AO373<>""),AI373:AO373))) | IF(OR(F373="",AQ373=""),"",IF(COUNT(AI373:AP373)=0,"",AQ373-LOOKUP(2,1/(AI373:AP373<>""),AI373:AP373))) | IF(OR(F373="",AR373=""),"",IF(COUNT(AI373:AQ373)=0,"",AR373-LOOKUP(2,1/(AI373:AQ373<>""),AI373:AQ373))) | IF(OR(F373="",AS373=""),"",IF(COUNT(AI373:AR373)=0,"",AS373-LOOKUP(2,1/(AI373:AR373<>""),AI373:AR373))) | IF(OR(F373="",AT373=""),"",IF(COUNT(AI373:AS373)=0,"",AT373-LOOKUP(2,1/(AI373:AS373<>""),AI373:AS373))) | IF(OR(F373="",AU373=""),"",IF(COUNT(AI373:AT373)=0,"",AU373-LOOKUP(2,1/(AI373:AT373<>""),AI373:AT373))) | IF(OR(F373="",AV373=""),"",IF(COUNT(AI373:AU373)=0,"",AV373-LOOKUP(2,1/(AI373:AU373<>""),AI373:AU373))) | IF(J373="","All_Provinces",IFERROR(VLOOKUP(J373,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K373="","All_Districts",IFERROR(VLOOKUP(K373,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F374="","",ROW()-3) | [18 empty] | IF(AQ374="","",AQ374) |  |  |  | IF(W374<>"",W374,IF(OR(T374="",V374=""),"",EDATE(T374,V374))) |  |  |  |  | IF(F374="","",IF(COUNT(AI374:AV374)=0,IF(AA374="","Not started",AA374),SUBSTITUTE(LOOKUP(2,1/(AI374:AV374<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F374="",COUNT(AI374:AV374)=0),"",TODAY()-LOOKUP(2,1/(AI374:AV374<>""),AI374:AV374)) | IF(OR(F374="",COUNT(AI374:AV374)<2),"",LOOKUP(2,1/(AI374:AV374<>""),AI374:AV374)-MIN(AI374:AV374)) | IF(OR(AD374="",AC374="Not started",AC374=""),"",IFERROR(AD374-IF(VLOOKUP(AC374,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC374,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F374="","",IF(OR(AA374="Cancelled",AC374="Cancelled"),"Cancelled",IF(OR(AC374="Completed / Handover",Y374<>"",Z374>=100),"Completed — on track",IF(O374="Not awarded",IF(U374="",IF(X374="","No planned date",IF(TODAY()>X374,"Behind — past planned date",IF(X374-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U374,"Behind — award date passed",IF(U374-TODAY()<=30,"At risk — close to off track","On track"))),IF(X374="","No planned date",IF(AND(TODAY()>X374,OR(Z374="",Z374<100)),"Behind — past end date",IF(AND(T374<>"",X374<>"",Z374<>"",(Z374<100),((TODAY()-T374)/MAX(X374-T374,1)*100)-Z374>15),"Behind — progress lag",IF(AND(X374-TODAY()<=30,X374-TODAY()>=0,OR(Z374="",Z374<90)),"At risk — close to off track","On track")))))))) | IF(OR(F374="",AC374="Completed / Handover",AC374="Cancelled"),"",IF(O374="Not awarded",IF(U374<>"",U374-TODAY(),IF(X374="","",X374-TODAY())),IF(X374="","",X374-TODAY()))) | [14 empty] | IF(OR(F374="",AJ374=""),"",IF(COUNT(AI374:AI374)=0,"",AJ374-LOOKUP(2,1/(AI374:AI374<>""),AI374:AI374))) | IF(OR(F374="",AK374=""),"",IF(COUNT(AI374:AJ374)=0,"",AK374-LOOKUP(2,1/(AI374:AJ374<>""),AI374:AJ374))) | IF(OR(F374="",AL374=""),"",IF(COUNT(AI374:AK374)=0,"",AL374-LOOKUP(2,1/(AI374:AK374<>""),AI374:AK374))) | IF(OR(F374="",AM374=""),"",IF(COUNT(AI374:AL374)=0,"",AM374-LOOKUP(2,1/(AI374:AL374<>""),AI374:AL374))) | IF(OR(F374="",AN374=""),"",IF(COUNT(AI374:AM374)=0,"",AN374-LOOKUP(2,1/(AI374:AM374<>""),AI374:AM374))) | IF(OR(F374="",AO374=""),"",IF(COUNT(AI374:AN374)=0,"",AO374-LOOKUP(2,1/(AI374:AN374<>""),AI374:AN374))) | IF(OR(F374="",AP374=""),"",IF(COUNT(AI374:AO374)=0,"",AP374-LOOKUP(2,1/(AI374:AO374<>""),AI374:AO374))) | IF(OR(F374="",AQ374=""),"",IF(COUNT(AI374:AP374)=0,"",AQ374-LOOKUP(2,1/(AI374:AP374<>""),AI374:AP374))) | IF(OR(F374="",AR374=""),"",IF(COUNT(AI374:AQ374)=0,"",AR374-LOOKUP(2,1/(AI374:AQ374<>""),AI374:AQ374))) | IF(OR(F374="",AS374=""),"",IF(COUNT(AI374:AR374)=0,"",AS374-LOOKUP(2,1/(AI374:AR374<>""),AI374:AR374))) | IF(OR(F374="",AT374=""),"",IF(COUNT(AI374:AS374)=0,"",AT374-LOOKUP(2,1/(AI374:AS374<>""),AI374:AS374))) | IF(OR(F374="",AU374=""),"",IF(COUNT(AI374:AT374)=0,"",AU374-LOOKUP(2,1/(AI374:AT374<>""),AI374:AT374))) | IF(OR(F374="",AV374=""),"",IF(COUNT(AI374:AU374)=0,"",AV374-LOOKUP(2,1/(AI374:AU374<>""),AI374:AU374))) | IF(J374="","All_Provinces",IFERROR(VLOOKUP(J374,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K374="","All_Districts",IFERROR(VLOOKUP(K374,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F375="","",ROW()-3) | [18 empty] | IF(AQ375="","",AQ375) |  |  |  | IF(W375<>"",W375,IF(OR(T375="",V375=""),"",EDATE(T375,V375))) |  |  |  |  | IF(F375="","",IF(COUNT(AI375:AV375)=0,IF(AA375="","Not started",AA375),SUBSTITUTE(LOOKUP(2,1/(AI375:AV375<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F375="",COUNT(AI375:AV375)=0),"",TODAY()-LOOKUP(2,1/(AI375:AV375<>""),AI375:AV375)) | IF(OR(F375="",COUNT(AI375:AV375)<2),"",LOOKUP(2,1/(AI375:AV375<>""),AI375:AV375)-MIN(AI375:AV375)) | IF(OR(AD375="",AC375="Not started",AC375=""),"",IFERROR(AD375-IF(VLOOKUP(AC375,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC375,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F375="","",IF(OR(AA375="Cancelled",AC375="Cancelled"),"Cancelled",IF(OR(AC375="Completed / Handover",Y375<>"",Z375>=100),"Completed — on track",IF(O375="Not awarded",IF(U375="",IF(X375="","No planned date",IF(TODAY()>X375,"Behind — past planned date",IF(X375-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U375,"Behind — award date passed",IF(U375-TODAY()<=30,"At risk — close to off track","On track"))),IF(X375="","No planned date",IF(AND(TODAY()>X375,OR(Z375="",Z375<100)),"Behind — past end date",IF(AND(T375<>"",X375<>"",Z375<>"",(Z375<100),((TODAY()-T375)/MAX(X375-T375,1)*100)-Z375>15),"Behind — progress lag",IF(AND(X375-TODAY()<=30,X375-TODAY()>=0,OR(Z375="",Z375<90)),"At risk — close to off track","On track")))))))) | IF(OR(F375="",AC375="Completed / Handover",AC375="Cancelled"),"",IF(O375="Not awarded",IF(U375<>"",U375-TODAY(),IF(X375="","",X375-TODAY())),IF(X375="","",X375-TODAY()))) | [14 empty] | IF(OR(F375="",AJ375=""),"",IF(COUNT(AI375:AI375)=0,"",AJ375-LOOKUP(2,1/(AI375:AI375<>""),AI375:AI375))) | IF(OR(F375="",AK375=""),"",IF(COUNT(AI375:AJ375)=0,"",AK375-LOOKUP(2,1/(AI375:AJ375<>""),AI375:AJ375))) | IF(OR(F375="",AL375=""),"",IF(COUNT(AI375:AK375)=0,"",AL375-LOOKUP(2,1/(AI375:AK375<>""),AI375:AK375))) | IF(OR(F375="",AM375=""),"",IF(COUNT(AI375:AL375)=0,"",AM375-LOOKUP(2,1/(AI375:AL375<>""),AI375:AL375))) | IF(OR(F375="",AN375=""),"",IF(COUNT(AI375:AM375)=0,"",AN375-LOOKUP(2,1/(AI375:AM375<>""),AI375:AM375))) | IF(OR(F375="",AO375=""),"",IF(COUNT(AI375:AN375)=0,"",AO375-LOOKUP(2,1/(AI375:AN375<>""),AI375:AN375))) | IF(OR(F375="",AP375=""),"",IF(COUNT(AI375:AO375)=0,"",AP375-LOOKUP(2,1/(AI375:AO375<>""),AI375:AO375))) | IF(OR(F375="",AQ375=""),"",IF(COUNT(AI375:AP375)=0,"",AQ375-LOOKUP(2,1/(AI375:AP375<>""),AI375:AP375))) | IF(OR(F375="",AR375=""),"",IF(COUNT(AI375:AQ375)=0,"",AR375-LOOKUP(2,1/(AI375:AQ375<>""),AI375:AQ375))) | IF(OR(F375="",AS375=""),"",IF(COUNT(AI375:AR375)=0,"",AS375-LOOKUP(2,1/(AI375:AR375<>""),AI375:AR375))) | IF(OR(F375="",AT375=""),"",IF(COUNT(AI375:AS375)=0,"",AT375-LOOKUP(2,1/(AI375:AS375<>""),AI375:AS375))) | IF(OR(F375="",AU375=""),"",IF(COUNT(AI375:AT375)=0,"",AU375-LOOKUP(2,1/(AI375:AT375<>""),AI375:AT375))) | IF(OR(F375="",AV375=""),"",IF(COUNT(AI375:AU375)=0,"",AV375-LOOKUP(2,1/(AI375:AU375<>""),AI375:AU375))) | IF(J375="","All_Provinces",IFERROR(VLOOKUP(J375,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K375="","All_Districts",IFERROR(VLOOKUP(K375,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F376="","",ROW()-3) | [18 empty] | IF(AQ376="","",AQ376) |  |  |  | IF(W376<>"",W376,IF(OR(T376="",V376=""),"",EDATE(T376,V376))) |  |  |  |  | IF(F376="","",IF(COUNT(AI376:AV376)=0,IF(AA376="","Not started",AA376),SUBSTITUTE(LOOKUP(2,1/(AI376:AV376<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F376="",COUNT(AI376:AV376)=0),"",TODAY()-LOOKUP(2,1/(AI376:AV376<>""),AI376:AV376)) | IF(OR(F376="",COUNT(AI376:AV376)<2),"",LOOKUP(2,1/(AI376:AV376<>""),AI376:AV376)-MIN(AI376:AV376)) | IF(OR(AD376="",AC376="Not started",AC376=""),"",IFERROR(AD376-IF(VLOOKUP(AC376,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC376,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F376="","",IF(OR(AA376="Cancelled",AC376="Cancelled"),"Cancelled",IF(OR(AC376="Completed / Handover",Y376<>"",Z376>=100),"Completed — on track",IF(O376="Not awarded",IF(U376="",IF(X376="","No planned date",IF(TODAY()>X376,"Behind — past planned date",IF(X376-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U376,"Behind — award date passed",IF(U376-TODAY()<=30,"At risk — close to off track","On track"))),IF(X376="","No planned date",IF(AND(TODAY()>X376,OR(Z376="",Z376<100)),"Behind — past end date",IF(AND(T376<>"",X376<>"",Z376<>"",(Z376<100),((TODAY()-T376)/MAX(X376-T376,1)*100)-Z376>15),"Behind — progress lag",IF(AND(X376-TODAY()<=30,X376-TODAY()>=0,OR(Z376="",Z376<90)),"At risk — close to off track","On track")))))))) | IF(OR(F376="",AC376="Completed / Handover",AC376="Cancelled"),"",IF(O376="Not awarded",IF(U376<>"",U376-TODAY(),IF(X376="","",X376-TODAY())),IF(X376="","",X376-TODAY()))) | [14 empty] | IF(OR(F376="",AJ376=""),"",IF(COUNT(AI376:AI376)=0,"",AJ376-LOOKUP(2,1/(AI376:AI376<>""),AI376:AI376))) | IF(OR(F376="",AK376=""),"",IF(COUNT(AI376:AJ376)=0,"",AK376-LOOKUP(2,1/(AI376:AJ376<>""),AI376:AJ376))) | IF(OR(F376="",AL376=""),"",IF(COUNT(AI376:AK376)=0,"",AL376-LOOKUP(2,1/(AI376:AK376<>""),AI376:AK376))) | IF(OR(F376="",AM376=""),"",IF(COUNT(AI376:AL376)=0,"",AM376-LOOKUP(2,1/(AI376:AL376<>""),AI376:AL376))) | IF(OR(F376="",AN376=""),"",IF(COUNT(AI376:AM376)=0,"",AN376-LOOKUP(2,1/(AI376:AM376<>""),AI376:AM376))) | IF(OR(F376="",AO376=""),"",IF(COUNT(AI376:AN376)=0,"",AO376-LOOKUP(2,1/(AI376:AN376<>""),AI376:AN376))) | IF(OR(F376="",AP376=""),"",IF(COUNT(AI376:AO376)=0,"",AP376-LOOKUP(2,1/(AI376:AO376<>""),AI376:AO376))) | IF(OR(F376="",AQ376=""),"",IF(COUNT(AI376:AP376)=0,"",AQ376-LOOKUP(2,1/(AI376:AP376<>""),AI376:AP376))) | IF(OR(F376="",AR376=""),"",IF(COUNT(AI376:AQ376)=0,"",AR376-LOOKUP(2,1/(AI376:AQ376<>""),AI376:AQ376))) | IF(OR(F376="",AS376=""),"",IF(COUNT(AI376:AR376)=0,"",AS376-LOOKUP(2,1/(AI376:AR376<>""),AI376:AR376))) | IF(OR(F376="",AT376=""),"",IF(COUNT(AI376:AS376)=0,"",AT376-LOOKUP(2,1/(AI376:AS376<>""),AI376:AS376))) | IF(OR(F376="",AU376=""),"",IF(COUNT(AI376:AT376)=0,"",AU376-LOOKUP(2,1/(AI376:AT376<>""),AI376:AT376))) | IF(OR(F376="",AV376=""),"",IF(COUNT(AI376:AU376)=0,"",AV376-LOOKUP(2,1/(AI376:AU376<>""),AI376:AU376))) | IF(J376="","All_Provinces",IFERROR(VLOOKUP(J376,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K376="","All_Districts",IFERROR(VLOOKUP(K376,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F377="","",ROW()-3) | [18 empty] | IF(AQ377="","",AQ377) |  |  |  | IF(W377<>"",W377,IF(OR(T377="",V377=""),"",EDATE(T377,V377))) |  |  |  |  | IF(F377="","",IF(COUNT(AI377:AV377)=0,IF(AA377="","Not started",AA377),SUBSTITUTE(LOOKUP(2,1/(AI377:AV377<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F377="",COUNT(AI377:AV377)=0),"",TODAY()-LOOKUP(2,1/(AI377:AV377<>""),AI377:AV377)) | IF(OR(F377="",COUNT(AI377:AV377)<2),"",LOOKUP(2,1/(AI377:AV377<>""),AI377:AV377)-MIN(AI377:AV377)) | IF(OR(AD377="",AC377="Not started",AC377=""),"",IFERROR(AD377-IF(VLOOKUP(AC377,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC377,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F377="","",IF(OR(AA377="Cancelled",AC377="Cancelled"),"Cancelled",IF(OR(AC377="Completed / Handover",Y377<>"",Z377>=100),"Completed — on track",IF(O377="Not awarded",IF(U377="",IF(X377="","No planned date",IF(TODAY()>X377,"Behind — past planned date",IF(X377-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U377,"Behind — award date passed",IF(U377-TODAY()<=30,"At risk — close to off track","On track"))),IF(X377="","No planned date",IF(AND(TODAY()>X377,OR(Z377="",Z377<100)),"Behind — past end date",IF(AND(T377<>"",X377<>"",Z377<>"",(Z377<100),((TODAY()-T377)/MAX(X377-T377,1)*100)-Z377>15),"Behind — progress lag",IF(AND(X377-TODAY()<=30,X377-TODAY()>=0,OR(Z377="",Z377<90)),"At risk — close to off track","On track")))))))) | IF(OR(F377="",AC377="Completed / Handover",AC377="Cancelled"),"",IF(O377="Not awarded",IF(U377<>"",U377-TODAY(),IF(X377="","",X377-TODAY())),IF(X377="","",X377-TODAY()))) | [14 empty] | IF(OR(F377="",AJ377=""),"",IF(COUNT(AI377:AI377)=0,"",AJ377-LOOKUP(2,1/(AI377:AI377<>""),AI377:AI377))) | IF(OR(F377="",AK377=""),"",IF(COUNT(AI377:AJ377)=0,"",AK377-LOOKUP(2,1/(AI377:AJ377<>""),AI377:AJ377))) | IF(OR(F377="",AL377=""),"",IF(COUNT(AI377:AK377)=0,"",AL377-LOOKUP(2,1/(AI377:AK377<>""),AI377:AK377))) | IF(OR(F377="",AM377=""),"",IF(COUNT(AI377:AL377)=0,"",AM377-LOOKUP(2,1/(AI377:AL377<>""),AI377:AL377))) | IF(OR(F377="",AN377=""),"",IF(COUNT(AI377:AM377)=0,"",AN377-LOOKUP(2,1/(AI377:AM377<>""),AI377:AM377))) | IF(OR(F377="",AO377=""),"",IF(COUNT(AI377:AN377)=0,"",AO377-LOOKUP(2,1/(AI377:AN377<>""),AI377:AN377))) | IF(OR(F377="",AP377=""),"",IF(COUNT(AI377:AO377)=0,"",AP377-LOOKUP(2,1/(AI377:AO377<>""),AI377:AO377))) | IF(OR(F377="",AQ377=""),"",IF(COUNT(AI377:AP377)=0,"",AQ377-LOOKUP(2,1/(AI377:AP377<>""),AI377:AP377))) | IF(OR(F377="",AR377=""),"",IF(COUNT(AI377:AQ377)=0,"",AR377-LOOKUP(2,1/(AI377:AQ377<>""),AI377:AQ377))) | IF(OR(F377="",AS377=""),"",IF(COUNT(AI377:AR377)=0,"",AS377-LOOKUP(2,1/(AI377:AR377<>""),AI377:AR377))) | IF(OR(F377="",AT377=""),"",IF(COUNT(AI377:AS377)=0,"",AT377-LOOKUP(2,1/(AI377:AS377<>""),AI377:AS377))) | IF(OR(F377="",AU377=""),"",IF(COUNT(AI377:AT377)=0,"",AU377-LOOKUP(2,1/(AI377:AT377<>""),AI377:AT377))) | IF(OR(F377="",AV377=""),"",IF(COUNT(AI377:AU377)=0,"",AV377-LOOKUP(2,1/(AI377:AU377<>""),AI377:AU377))) | IF(J377="","All_Provinces",IFERROR(VLOOKUP(J377,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K377="","All_Districts",IFERROR(VLOOKUP(K377,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F378="","",ROW()-3) | [18 empty] | IF(AQ378="","",AQ378) |  |  |  | IF(W378<>"",W378,IF(OR(T378="",V378=""),"",EDATE(T378,V378))) |  |  |  |  | IF(F378="","",IF(COUNT(AI378:AV378)=0,IF(AA378="","Not started",AA378),SUBSTITUTE(LOOKUP(2,1/(AI378:AV378<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F378="",COUNT(AI378:AV378)=0),"",TODAY()-LOOKUP(2,1/(AI378:AV378<>""),AI378:AV378)) | IF(OR(F378="",COUNT(AI378:AV378)<2),"",LOOKUP(2,1/(AI378:AV378<>""),AI378:AV378)-MIN(AI378:AV378)) | IF(OR(AD378="",AC378="Not started",AC378=""),"",IFERROR(AD378-IF(VLOOKUP(AC378,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC378,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F378="","",IF(OR(AA378="Cancelled",AC378="Cancelled"),"Cancelled",IF(OR(AC378="Completed / Handover",Y378<>"",Z378>=100),"Completed — on track",IF(O378="Not awarded",IF(U378="",IF(X378="","No planned date",IF(TODAY()>X378,"Behind — past planned date",IF(X378-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U378,"Behind — award date passed",IF(U378-TODAY()<=30,"At risk — close to off track","On track"))),IF(X378="","No planned date",IF(AND(TODAY()>X378,OR(Z378="",Z378<100)),"Behind — past end date",IF(AND(T378<>"",X378<>"",Z378<>"",(Z378<100),((TODAY()-T378)/MAX(X378-T378,1)*100)-Z378>15),"Behind — progress lag",IF(AND(X378-TODAY()<=30,X378-TODAY()>=0,OR(Z378="",Z378<90)),"At risk — close to off track","On track")))))))) | IF(OR(F378="",AC378="Completed / Handover",AC378="Cancelled"),"",IF(O378="Not awarded",IF(U378<>"",U378-TODAY(),IF(X378="","",X378-TODAY())),IF(X378="","",X378-TODAY()))) | [14 empty] | IF(OR(F378="",AJ378=""),"",IF(COUNT(AI378:AI378)=0,"",AJ378-LOOKUP(2,1/(AI378:AI378<>""),AI378:AI378))) | IF(OR(F378="",AK378=""),"",IF(COUNT(AI378:AJ378)=0,"",AK378-LOOKUP(2,1/(AI378:AJ378<>""),AI378:AJ378))) | IF(OR(F378="",AL378=""),"",IF(COUNT(AI378:AK378)=0,"",AL378-LOOKUP(2,1/(AI378:AK378<>""),AI378:AK378))) | IF(OR(F378="",AM378=""),"",IF(COUNT(AI378:AL378)=0,"",AM378-LOOKUP(2,1/(AI378:AL378<>""),AI378:AL378))) | IF(OR(F378="",AN378=""),"",IF(COUNT(AI378:AM378)=0,"",AN378-LOOKUP(2,1/(AI378:AM378<>""),AI378:AM378))) | IF(OR(F378="",AO378=""),"",IF(COUNT(AI378:AN378)=0,"",AO378-LOOKUP(2,1/(AI378:AN378<>""),AI378:AN378))) | IF(OR(F378="",AP378=""),"",IF(COUNT(AI378:AO378)=0,"",AP378-LOOKUP(2,1/(AI378:AO378<>""),AI378:AO378))) | IF(OR(F378="",AQ378=""),"",IF(COUNT(AI378:AP378)=0,"",AQ378-LOOKUP(2,1/(AI378:AP378<>""),AI378:AP378))) | IF(OR(F378="",AR378=""),"",IF(COUNT(AI378:AQ378)=0,"",AR378-LOOKUP(2,1/(AI378:AQ378<>""),AI378:AQ378))) | IF(OR(F378="",AS378=""),"",IF(COUNT(AI378:AR378)=0,"",AS378-LOOKUP(2,1/(AI378:AR378<>""),AI378:AR378))) | IF(OR(F378="",AT378=""),"",IF(COUNT(AI378:AS378)=0,"",AT378-LOOKUP(2,1/(AI378:AS378<>""),AI378:AS378))) | IF(OR(F378="",AU378=""),"",IF(COUNT(AI378:AT378)=0,"",AU378-LOOKUP(2,1/(AI378:AT378<>""),AI378:AT378))) | IF(OR(F378="",AV378=""),"",IF(COUNT(AI378:AU378)=0,"",AV378-LOOKUP(2,1/(AI378:AU378<>""),AI378:AU378))) | IF(J378="","All_Provinces",IFERROR(VLOOKUP(J378,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K378="","All_Districts",IFERROR(VLOOKUP(K378,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F379="","",ROW()-3) | [18 empty] | IF(AQ379="","",AQ379) |  |  |  | IF(W379<>"",W379,IF(OR(T379="",V379=""),"",EDATE(T379,V379))) |  |  |  |  | IF(F379="","",IF(COUNT(AI379:AV379)=0,IF(AA379="","Not started",AA379),SUBSTITUTE(LOOKUP(2,1/(AI379:AV379<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F379="",COUNT(AI379:AV379)=0),"",TODAY()-LOOKUP(2,1/(AI379:AV379<>""),AI379:AV379)) | IF(OR(F379="",COUNT(AI379:AV379)<2),"",LOOKUP(2,1/(AI379:AV379<>""),AI379:AV379)-MIN(AI379:AV379)) | IF(OR(AD379="",AC379="Not started",AC379=""),"",IFERROR(AD379-IF(VLOOKUP(AC379,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC379,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F379="","",IF(OR(AA379="Cancelled",AC379="Cancelled"),"Cancelled",IF(OR(AC379="Completed / Handover",Y379<>"",Z379>=100),"Completed — on track",IF(O379="Not awarded",IF(U379="",IF(X379="","No planned date",IF(TODAY()>X379,"Behind — past planned date",IF(X379-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U379,"Behind — award date passed",IF(U379-TODAY()<=30,"At risk — close to off track","On track"))),IF(X379="","No planned date",IF(AND(TODAY()>X379,OR(Z379="",Z379<100)),"Behind — past end date",IF(AND(T379<>"",X379<>"",Z379<>"",(Z379<100),((TODAY()-T379)/MAX(X379-T379,1)*100)-Z379>15),"Behind — progress lag",IF(AND(X379-TODAY()<=30,X379-TODAY()>=0,OR(Z379="",Z379<90)),"At risk — close to off track","On track")))))))) | IF(OR(F379="",AC379="Completed / Handover",AC379="Cancelled"),"",IF(O379="Not awarded",IF(U379<>"",U379-TODAY(),IF(X379="","",X379-TODAY())),IF(X379="","",X379-TODAY()))) | [14 empty] | IF(OR(F379="",AJ379=""),"",IF(COUNT(AI379:AI379)=0,"",AJ379-LOOKUP(2,1/(AI379:AI379<>""),AI379:AI379))) | IF(OR(F379="",AK379=""),"",IF(COUNT(AI379:AJ379)=0,"",AK379-LOOKUP(2,1/(AI379:AJ379<>""),AI379:AJ379))) | IF(OR(F379="",AL379=""),"",IF(COUNT(AI379:AK379)=0,"",AL379-LOOKUP(2,1/(AI379:AK379<>""),AI379:AK379))) | IF(OR(F379="",AM379=""),"",IF(COUNT(AI379:AL379)=0,"",AM379-LOOKUP(2,1/(AI379:AL379<>""),AI379:AL379))) | IF(OR(F379="",AN379=""),"",IF(COUNT(AI379:AM379)=0,"",AN379-LOOKUP(2,1/(AI379:AM379<>""),AI379:AM379))) | IF(OR(F379="",AO379=""),"",IF(COUNT(AI379:AN379)=0,"",AO379-LOOKUP(2,1/(AI379:AN379<>""),AI379:AN379))) | IF(OR(F379="",AP379=""),"",IF(COUNT(AI379:AO379)=0,"",AP379-LOOKUP(2,1/(AI379:AO379<>""),AI379:AO379))) | IF(OR(F379="",AQ379=""),"",IF(COUNT(AI379:AP379)=0,"",AQ379-LOOKUP(2,1/(AI379:AP379<>""),AI379:AP379))) | IF(OR(F379="",AR379=""),"",IF(COUNT(AI379:AQ379)=0,"",AR379-LOOKUP(2,1/(AI379:AQ379<>""),AI379:AQ379))) | IF(OR(F379="",AS379=""),"",IF(COUNT(AI379:AR379)=0,"",AS379-LOOKUP(2,1/(AI379:AR379<>""),AI379:AR379))) | IF(OR(F379="",AT379=""),"",IF(COUNT(AI379:AS379)=0,"",AT379-LOOKUP(2,1/(AI379:AS379<>""),AI379:AS379))) | IF(OR(F379="",AU379=""),"",IF(COUNT(AI379:AT379)=0,"",AU379-LOOKUP(2,1/(AI379:AT379<>""),AI379:AT379))) | IF(OR(F379="",AV379=""),"",IF(COUNT(AI379:AU379)=0,"",AV379-LOOKUP(2,1/(AI379:AU379<>""),AI379:AU379))) | IF(J379="","All_Provinces",IFERROR(VLOOKUP(J379,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K379="","All_Districts",IFERROR(VLOOKUP(K379,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F380="","",ROW()-3) | [18 empty] | IF(AQ380="","",AQ380) |  |  |  | IF(W380<>"",W380,IF(OR(T380="",V380=""),"",EDATE(T380,V380))) |  |  |  |  | IF(F380="","",IF(COUNT(AI380:AV380)=0,IF(AA380="","Not started",AA380),SUBSTITUTE(LOOKUP(2,1/(AI380:AV380<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F380="",COUNT(AI380:AV380)=0),"",TODAY()-LOOKUP(2,1/(AI380:AV380<>""),AI380:AV380)) | IF(OR(F380="",COUNT(AI380:AV380)<2),"",LOOKUP(2,1/(AI380:AV380<>""),AI380:AV380)-MIN(AI380:AV380)) | IF(OR(AD380="",AC380="Not started",AC380=""),"",IFERROR(AD380-IF(VLOOKUP(AC380,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC380,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F380="","",IF(OR(AA380="Cancelled",AC380="Cancelled"),"Cancelled",IF(OR(AC380="Completed / Handover",Y380<>"",Z380>=100),"Completed — on track",IF(O380="Not awarded",IF(U380="",IF(X380="","No planned date",IF(TODAY()>X380,"Behind — past planned date",IF(X380-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U380,"Behind — award date passed",IF(U380-TODAY()<=30,"At risk — close to off track","On track"))),IF(X380="","No planned date",IF(AND(TODAY()>X380,OR(Z380="",Z380<100)),"Behind — past end date",IF(AND(T380<>"",X380<>"",Z380<>"",(Z380<100),((TODAY()-T380)/MAX(X380-T380,1)*100)-Z380>15),"Behind — progress lag",IF(AND(X380-TODAY()<=30,X380-TODAY()>=0,OR(Z380="",Z380<90)),"At risk — close to off track","On track")))))))) | IF(OR(F380="",AC380="Completed / Handover",AC380="Cancelled"),"",IF(O380="Not awarded",IF(U380<>"",U380-TODAY(),IF(X380="","",X380-TODAY())),IF(X380="","",X380-TODAY()))) | [14 empty] | IF(OR(F380="",AJ380=""),"",IF(COUNT(AI380:AI380)=0,"",AJ380-LOOKUP(2,1/(AI380:AI380<>""),AI380:AI380))) | IF(OR(F380="",AK380=""),"",IF(COUNT(AI380:AJ380)=0,"",AK380-LOOKUP(2,1/(AI380:AJ380<>""),AI380:AJ380))) | IF(OR(F380="",AL380=""),"",IF(COUNT(AI380:AK380)=0,"",AL380-LOOKUP(2,1/(AI380:AK380<>""),AI380:AK380))) | IF(OR(F380="",AM380=""),"",IF(COUNT(AI380:AL380)=0,"",AM380-LOOKUP(2,1/(AI380:AL380<>""),AI380:AL380))) | IF(OR(F380="",AN380=""),"",IF(COUNT(AI380:AM380)=0,"",AN380-LOOKUP(2,1/(AI380:AM380<>""),AI380:AM380))) | IF(OR(F380="",AO380=""),"",IF(COUNT(AI380:AN380)=0,"",AO380-LOOKUP(2,1/(AI380:AN380<>""),AI380:AN380))) | IF(OR(F380="",AP380=""),"",IF(COUNT(AI380:AO380)=0,"",AP380-LOOKUP(2,1/(AI380:AO380<>""),AI380:AO380))) | IF(OR(F380="",AQ380=""),"",IF(COUNT(AI380:AP380)=0,"",AQ380-LOOKUP(2,1/(AI380:AP380<>""),AI380:AP380))) | IF(OR(F380="",AR380=""),"",IF(COUNT(AI380:AQ380)=0,"",AR380-LOOKUP(2,1/(AI380:AQ380<>""),AI380:AQ380))) | IF(OR(F380="",AS380=""),"",IF(COUNT(AI380:AR380)=0,"",AS380-LOOKUP(2,1/(AI380:AR380<>""),AI380:AR380))) | IF(OR(F380="",AT380=""),"",IF(COUNT(AI380:AS380)=0,"",AT380-LOOKUP(2,1/(AI380:AS380<>""),AI380:AS380))) | IF(OR(F380="",AU380=""),"",IF(COUNT(AI380:AT380)=0,"",AU380-LOOKUP(2,1/(AI380:AT380<>""),AI380:AT380))) | IF(OR(F380="",AV380=""),"",IF(COUNT(AI380:AU380)=0,"",AV380-LOOKUP(2,1/(AI380:AU380<>""),AI380:AU380))) | IF(J380="","All_Provinces",IFERROR(VLOOKUP(J380,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K380="","All_Districts",IFERROR(VLOOKUP(K380,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F381="","",ROW()-3) | [18 empty] | IF(AQ381="","",AQ381) |  |  |  | IF(W381<>"",W381,IF(OR(T381="",V381=""),"",EDATE(T381,V381))) |  |  |  |  | IF(F381="","",IF(COUNT(AI381:AV381)=0,IF(AA381="","Not started",AA381),SUBSTITUTE(LOOKUP(2,1/(AI381:AV381<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F381="",COUNT(AI381:AV381)=0),"",TODAY()-LOOKUP(2,1/(AI381:AV381<>""),AI381:AV381)) | IF(OR(F381="",COUNT(AI381:AV381)<2),"",LOOKUP(2,1/(AI381:AV381<>""),AI381:AV381)-MIN(AI381:AV381)) | IF(OR(AD381="",AC381="Not started",AC381=""),"",IFERROR(AD381-IF(VLOOKUP(AC381,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC381,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F381="","",IF(OR(AA381="Cancelled",AC381="Cancelled"),"Cancelled",IF(OR(AC381="Completed / Handover",Y381<>"",Z381>=100),"Completed — on track",IF(O381="Not awarded",IF(U381="",IF(X381="","No planned date",IF(TODAY()>X381,"Behind — past planned date",IF(X381-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U381,"Behind — award date passed",IF(U381-TODAY()<=30,"At risk — close to off track","On track"))),IF(X381="","No planned date",IF(AND(TODAY()>X381,OR(Z381="",Z381<100)),"Behind — past end date",IF(AND(T381<>"",X381<>"",Z381<>"",(Z381<100),((TODAY()-T381)/MAX(X381-T381,1)*100)-Z381>15),"Behind — progress lag",IF(AND(X381-TODAY()<=30,X381-TODAY()>=0,OR(Z381="",Z381<90)),"At risk — close to off track","On track")))))))) | IF(OR(F381="",AC381="Completed / Handover",AC381="Cancelled"),"",IF(O381="Not awarded",IF(U381<>"",U381-TODAY(),IF(X381="","",X381-TODAY())),IF(X381="","",X381-TODAY()))) | [14 empty] | IF(OR(F381="",AJ381=""),"",IF(COUNT(AI381:AI381)=0,"",AJ381-LOOKUP(2,1/(AI381:AI381<>""),AI381:AI381))) | IF(OR(F381="",AK381=""),"",IF(COUNT(AI381:AJ381)=0,"",AK381-LOOKUP(2,1/(AI381:AJ381<>""),AI381:AJ381))) | IF(OR(F381="",AL381=""),"",IF(COUNT(AI381:AK381)=0,"",AL381-LOOKUP(2,1/(AI381:AK381<>""),AI381:AK381))) | IF(OR(F381="",AM381=""),"",IF(COUNT(AI381:AL381)=0,"",AM381-LOOKUP(2,1/(AI381:AL381<>""),AI381:AL381))) | IF(OR(F381="",AN381=""),"",IF(COUNT(AI381:AM381)=0,"",AN381-LOOKUP(2,1/(AI381:AM381<>""),AI381:AM381))) | IF(OR(F381="",AO381=""),"",IF(COUNT(AI381:AN381)=0,"",AO381-LOOKUP(2,1/(AI381:AN381<>""),AI381:AN381))) | IF(OR(F381="",AP381=""),"",IF(COUNT(AI381:AO381)=0,"",AP381-LOOKUP(2,1/(AI381:AO381<>""),AI381:AO381))) | IF(OR(F381="",AQ381=""),"",IF(COUNT(AI381:AP381)=0,"",AQ381-LOOKUP(2,1/(AI381:AP381<>""),AI381:AP381))) | IF(OR(F381="",AR381=""),"",IF(COUNT(AI381:AQ381)=0,"",AR381-LOOKUP(2,1/(AI381:AQ381<>""),AI381:AQ381))) | IF(OR(F381="",AS381=""),"",IF(COUNT(AI381:AR381)=0,"",AS381-LOOKUP(2,1/(AI381:AR381<>""),AI381:AR381))) | IF(OR(F381="",AT381=""),"",IF(COUNT(AI381:AS381)=0,"",AT381-LOOKUP(2,1/(AI381:AS381<>""),AI381:AS381))) | IF(OR(F381="",AU381=""),"",IF(COUNT(AI381:AT381)=0,"",AU381-LOOKUP(2,1/(AI381:AT381<>""),AI381:AT381))) | IF(OR(F381="",AV381=""),"",IF(COUNT(AI381:AU381)=0,"",AV381-LOOKUP(2,1/(AI381:AU381<>""),AI381:AU381))) | IF(J381="","All_Provinces",IFERROR(VLOOKUP(J381,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K381="","All_Districts",IFERROR(VLOOKUP(K381,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F382="","",ROW()-3) | [18 empty] | IF(AQ382="","",AQ382) |  |  |  | IF(W382<>"",W382,IF(OR(T382="",V382=""),"",EDATE(T382,V382))) |  |  |  |  | IF(F382="","",IF(COUNT(AI382:AV382)=0,IF(AA382="","Not started",AA382),SUBSTITUTE(LOOKUP(2,1/(AI382:AV382<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F382="",COUNT(AI382:AV382)=0),"",TODAY()-LOOKUP(2,1/(AI382:AV382<>""),AI382:AV382)) | IF(OR(F382="",COUNT(AI382:AV382)<2),"",LOOKUP(2,1/(AI382:AV382<>""),AI382:AV382)-MIN(AI382:AV382)) | IF(OR(AD382="",AC382="Not started",AC382=""),"",IFERROR(AD382-IF(VLOOKUP(AC382,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC382,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F382="","",IF(OR(AA382="Cancelled",AC382="Cancelled"),"Cancelled",IF(OR(AC382="Completed / Handover",Y382<>"",Z382>=100),"Completed — on track",IF(O382="Not awarded",IF(U382="",IF(X382="","No planned date",IF(TODAY()>X382,"Behind — past planned date",IF(X382-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U382,"Behind — award date passed",IF(U382-TODAY()<=30,"At risk — close to off track","On track"))),IF(X382="","No planned date",IF(AND(TODAY()>X382,OR(Z382="",Z382<100)),"Behind — past end date",IF(AND(T382<>"",X382<>"",Z382<>"",(Z382<100),((TODAY()-T382)/MAX(X382-T382,1)*100)-Z382>15),"Behind — progress lag",IF(AND(X382-TODAY()<=30,X382-TODAY()>=0,OR(Z382="",Z382<90)),"At risk — close to off track","On track")))))))) | IF(OR(F382="",AC382="Completed / Handover",AC382="Cancelled"),"",IF(O382="Not awarded",IF(U382<>"",U382-TODAY(),IF(X382="","",X382-TODAY())),IF(X382="","",X382-TODAY()))) | [14 empty] | IF(OR(F382="",AJ382=""),"",IF(COUNT(AI382:AI382)=0,"",AJ382-LOOKUP(2,1/(AI382:AI382<>""),AI382:AI382))) | IF(OR(F382="",AK382=""),"",IF(COUNT(AI382:AJ382)=0,"",AK382-LOOKUP(2,1/(AI382:AJ382<>""),AI382:AJ382))) | IF(OR(F382="",AL382=""),"",IF(COUNT(AI382:AK382)=0,"",AL382-LOOKUP(2,1/(AI382:AK382<>""),AI382:AK382))) | IF(OR(F382="",AM382=""),"",IF(COUNT(AI382:AL382)=0,"",AM382-LOOKUP(2,1/(AI382:AL382<>""),AI382:AL382))) | IF(OR(F382="",AN382=""),"",IF(COUNT(AI382:AM382)=0,"",AN382-LOOKUP(2,1/(AI382:AM382<>""),AI382:AM382))) | IF(OR(F382="",AO382=""),"",IF(COUNT(AI382:AN382)=0,"",AO382-LOOKUP(2,1/(AI382:AN382<>""),AI382:AN382))) | IF(OR(F382="",AP382=""),"",IF(COUNT(AI382:AO382)=0,"",AP382-LOOKUP(2,1/(AI382:AO382<>""),AI382:AO382))) | IF(OR(F382="",AQ382=""),"",IF(COUNT(AI382:AP382)=0,"",AQ382-LOOKUP(2,1/(AI382:AP382<>""),AI382:AP382))) | IF(OR(F382="",AR382=""),"",IF(COUNT(AI382:AQ382)=0,"",AR382-LOOKUP(2,1/(AI382:AQ382<>""),AI382:AQ382))) | IF(OR(F382="",AS382=""),"",IF(COUNT(AI382:AR382)=0,"",AS382-LOOKUP(2,1/(AI382:AR382<>""),AI382:AR382))) | IF(OR(F382="",AT382=""),"",IF(COUNT(AI382:AS382)=0,"",AT382-LOOKUP(2,1/(AI382:AS382<>""),AI382:AS382))) | IF(OR(F382="",AU382=""),"",IF(COUNT(AI382:AT382)=0,"",AU382-LOOKUP(2,1/(AI382:AT382<>""),AI382:AT382))) | IF(OR(F382="",AV382=""),"",IF(COUNT(AI382:AU382)=0,"",AV382-LOOKUP(2,1/(AI382:AU382<>""),AI382:AU382))) | IF(J382="","All_Provinces",IFERROR(VLOOKUP(J382,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K382="","All_Districts",IFERROR(VLOOKUP(K382,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F383="","",ROW()-3) | [18 empty] | IF(AQ383="","",AQ383) |  |  |  | IF(W383<>"",W383,IF(OR(T383="",V383=""),"",EDATE(T383,V383))) |  |  |  |  | IF(F383="","",IF(COUNT(AI383:AV383)=0,IF(AA383="","Not started",AA383),SUBSTITUTE(LOOKUP(2,1/(AI383:AV383<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F383="",COUNT(AI383:AV383)=0),"",TODAY()-LOOKUP(2,1/(AI383:AV383<>""),AI383:AV383)) | IF(OR(F383="",COUNT(AI383:AV383)<2),"",LOOKUP(2,1/(AI383:AV383<>""),AI383:AV383)-MIN(AI383:AV383)) | IF(OR(AD383="",AC383="Not started",AC383=""),"",IFERROR(AD383-IF(VLOOKUP(AC383,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC383,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F383="","",IF(OR(AA383="Cancelled",AC383="Cancelled"),"Cancelled",IF(OR(AC383="Completed / Handover",Y383<>"",Z383>=100),"Completed — on track",IF(O383="Not awarded",IF(U383="",IF(X383="","No planned date",IF(TODAY()>X383,"Behind — past planned date",IF(X383-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U383,"Behind — award date passed",IF(U383-TODAY()<=30,"At risk — close to off track","On track"))),IF(X383="","No planned date",IF(AND(TODAY()>X383,OR(Z383="",Z383<100)),"Behind — past end date",IF(AND(T383<>"",X383<>"",Z383<>"",(Z383<100),((TODAY()-T383)/MAX(X383-T383,1)*100)-Z383>15),"Behind — progress lag",IF(AND(X383-TODAY()<=30,X383-TODAY()>=0,OR(Z383="",Z383<90)),"At risk — close to off track","On track")))))))) | IF(OR(F383="",AC383="Completed / Handover",AC383="Cancelled"),"",IF(O383="Not awarded",IF(U383<>"",U383-TODAY(),IF(X383="","",X383-TODAY())),IF(X383="","",X383-TODAY()))) | [14 empty] | IF(OR(F383="",AJ383=""),"",IF(COUNT(AI383:AI383)=0,"",AJ383-LOOKUP(2,1/(AI383:AI383<>""),AI383:AI383))) | IF(OR(F383="",AK383=""),"",IF(COUNT(AI383:AJ383)=0,"",AK383-LOOKUP(2,1/(AI383:AJ383<>""),AI383:AJ383))) | IF(OR(F383="",AL383=""),"",IF(COUNT(AI383:AK383)=0,"",AL383-LOOKUP(2,1/(AI383:AK383<>""),AI383:AK383))) | IF(OR(F383="",AM383=""),"",IF(COUNT(AI383:AL383)=0,"",AM383-LOOKUP(2,1/(AI383:AL383<>""),AI383:AL383))) | IF(OR(F383="",AN383=""),"",IF(COUNT(AI383:AM383)=0,"",AN383-LOOKUP(2,1/(AI383:AM383<>""),AI383:AM383))) | IF(OR(F383="",AO383=""),"",IF(COUNT(AI383:AN383)=0,"",AO383-LOOKUP(2,1/(AI383:AN383<>""),AI383:AN383))) | IF(OR(F383="",AP383=""),"",IF(COUNT(AI383:AO383)=0,"",AP383-LOOKUP(2,1/(AI383:AO383<>""),AI383:AO383))) | IF(OR(F383="",AQ383=""),"",IF(COUNT(AI383:AP383)=0,"",AQ383-LOOKUP(2,1/(AI383:AP383<>""),AI383:AP383))) | IF(OR(F383="",AR383=""),"",IF(COUNT(AI383:AQ383)=0,"",AR383-LOOKUP(2,1/(AI383:AQ383<>""),AI383:AQ383))) | IF(OR(F383="",AS383=""),"",IF(COUNT(AI383:AR383)=0,"",AS383-LOOKUP(2,1/(AI383:AR383<>""),AI383:AR383))) | IF(OR(F383="",AT383=""),"",IF(COUNT(AI383:AS383)=0,"",AT383-LOOKUP(2,1/(AI383:AS383<>""),AI383:AS383))) | IF(OR(F383="",AU383=""),"",IF(COUNT(AI383:AT383)=0,"",AU383-LOOKUP(2,1/(AI383:AT383<>""),AI383:AT383))) | IF(OR(F383="",AV383=""),"",IF(COUNT(AI383:AU383)=0,"",AV383-LOOKUP(2,1/(AI383:AU383<>""),AI383:AU383))) | IF(J383="","All_Provinces",IFERROR(VLOOKUP(J383,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K383="","All_Districts",IFERROR(VLOOKUP(K383,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F384="","",ROW()-3) | [18 empty] | IF(AQ384="","",AQ384) |  |  |  | IF(W384<>"",W384,IF(OR(T384="",V384=""),"",EDATE(T384,V384))) |  |  |  |  | IF(F384="","",IF(COUNT(AI384:AV384)=0,IF(AA384="","Not started",AA384),SUBSTITUTE(LOOKUP(2,1/(AI384:AV384<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F384="",COUNT(AI384:AV384)=0),"",TODAY()-LOOKUP(2,1/(AI384:AV384<>""),AI384:AV384)) | IF(OR(F384="",COUNT(AI384:AV384)<2),"",LOOKUP(2,1/(AI384:AV384<>""),AI384:AV384)-MIN(AI384:AV384)) | IF(OR(AD384="",AC384="Not started",AC384=""),"",IFERROR(AD384-IF(VLOOKUP(AC384,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC384,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F384="","",IF(OR(AA384="Cancelled",AC384="Cancelled"),"Cancelled",IF(OR(AC384="Completed / Handover",Y384<>"",Z384>=100),"Completed — on track",IF(O384="Not awarded",IF(U384="",IF(X384="","No planned date",IF(TODAY()>X384,"Behind — past planned date",IF(X384-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U384,"Behind — award date passed",IF(U384-TODAY()<=30,"At risk — close to off track","On track"))),IF(X384="","No planned date",IF(AND(TODAY()>X384,OR(Z384="",Z384<100)),"Behind — past end date",IF(AND(T384<>"",X384<>"",Z384<>"",(Z384<100),((TODAY()-T384)/MAX(X384-T384,1)*100)-Z384>15),"Behind — progress lag",IF(AND(X384-TODAY()<=30,X384-TODAY()>=0,OR(Z384="",Z384<90)),"At risk — close to off track","On track")))))))) | IF(OR(F384="",AC384="Completed / Handover",AC384="Cancelled"),"",IF(O384="Not awarded",IF(U384<>"",U384-TODAY(),IF(X384="","",X384-TODAY())),IF(X384="","",X384-TODAY()))) | [14 empty] | IF(OR(F384="",AJ384=""),"",IF(COUNT(AI384:AI384)=0,"",AJ384-LOOKUP(2,1/(AI384:AI384<>""),AI384:AI384))) | IF(OR(F384="",AK384=""),"",IF(COUNT(AI384:AJ384)=0,"",AK384-LOOKUP(2,1/(AI384:AJ384<>""),AI384:AJ384))) | IF(OR(F384="",AL384=""),"",IF(COUNT(AI384:AK384)=0,"",AL384-LOOKUP(2,1/(AI384:AK384<>""),AI384:AK384))) | IF(OR(F384="",AM384=""),"",IF(COUNT(AI384:AL384)=0,"",AM384-LOOKUP(2,1/(AI384:AL384<>""),AI384:AL384))) | IF(OR(F384="",AN384=""),"",IF(COUNT(AI384:AM384)=0,"",AN384-LOOKUP(2,1/(AI384:AM384<>""),AI384:AM384))) | IF(OR(F384="",AO384=""),"",IF(COUNT(AI384:AN384)=0,"",AO384-LOOKUP(2,1/(AI384:AN384<>""),AI384:AN384))) | IF(OR(F384="",AP384=""),"",IF(COUNT(AI384:AO384)=0,"",AP384-LOOKUP(2,1/(AI384:AO384<>""),AI384:AO384))) | IF(OR(F384="",AQ384=""),"",IF(COUNT(AI384:AP384)=0,"",AQ384-LOOKUP(2,1/(AI384:AP384<>""),AI384:AP384))) | IF(OR(F384="",AR384=""),"",IF(COUNT(AI384:AQ384)=0,"",AR384-LOOKUP(2,1/(AI384:AQ384<>""),AI384:AQ384))) | IF(OR(F384="",AS384=""),"",IF(COUNT(AI384:AR384)=0,"",AS384-LOOKUP(2,1/(AI384:AR384<>""),AI384:AR384))) | IF(OR(F384="",AT384=""),"",IF(COUNT(AI384:AS384)=0,"",AT384-LOOKUP(2,1/(AI384:AS384<>""),AI384:AS384))) | IF(OR(F384="",AU384=""),"",IF(COUNT(AI384:AT384)=0,"",AU384-LOOKUP(2,1/(AI384:AT384<>""),AI384:AT384))) | IF(OR(F384="",AV384=""),"",IF(COUNT(AI384:AU384)=0,"",AV384-LOOKUP(2,1/(AI384:AU384<>""),AI384:AU384))) | IF(J384="","All_Provinces",IFERROR(VLOOKUP(J384,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K384="","All_Districts",IFERROR(VLOOKUP(K384,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F385="","",ROW()-3) | [18 empty] | IF(AQ385="","",AQ385) |  |  |  | IF(W385<>"",W385,IF(OR(T385="",V385=""),"",EDATE(T385,V385))) |  |  |  |  | IF(F385="","",IF(COUNT(AI385:AV385)=0,IF(AA385="","Not started",AA385),SUBSTITUTE(LOOKUP(2,1/(AI385:AV385<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F385="",COUNT(AI385:AV385)=0),"",TODAY()-LOOKUP(2,1/(AI385:AV385<>""),AI385:AV385)) | IF(OR(F385="",COUNT(AI385:AV385)<2),"",LOOKUP(2,1/(AI385:AV385<>""),AI385:AV385)-MIN(AI385:AV385)) | IF(OR(AD385="",AC385="Not started",AC385=""),"",IFERROR(AD385-IF(VLOOKUP(AC385,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC385,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F385="","",IF(OR(AA385="Cancelled",AC385="Cancelled"),"Cancelled",IF(OR(AC385="Completed / Handover",Y385<>"",Z385>=100),"Completed — on track",IF(O385="Not awarded",IF(U385="",IF(X385="","No planned date",IF(TODAY()>X385,"Behind — past planned date",IF(X385-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U385,"Behind — award date passed",IF(U385-TODAY()<=30,"At risk — close to off track","On track"))),IF(X385="","No planned date",IF(AND(TODAY()>X385,OR(Z385="",Z385<100)),"Behind — past end date",IF(AND(T385<>"",X385<>"",Z385<>"",(Z385<100),((TODAY()-T385)/MAX(X385-T385,1)*100)-Z385>15),"Behind — progress lag",IF(AND(X385-TODAY()<=30,X385-TODAY()>=0,OR(Z385="",Z385<90)),"At risk — close to off track","On track")))))))) | IF(OR(F385="",AC385="Completed / Handover",AC385="Cancelled"),"",IF(O385="Not awarded",IF(U385<>"",U385-TODAY(),IF(X385="","",X385-TODAY())),IF(X385="","",X385-TODAY()))) | [14 empty] | IF(OR(F385="",AJ385=""),"",IF(COUNT(AI385:AI385)=0,"",AJ385-LOOKUP(2,1/(AI385:AI385<>""),AI385:AI385))) | IF(OR(F385="",AK385=""),"",IF(COUNT(AI385:AJ385)=0,"",AK385-LOOKUP(2,1/(AI385:AJ385<>""),AI385:AJ385))) | IF(OR(F385="",AL385=""),"",IF(COUNT(AI385:AK385)=0,"",AL385-LOOKUP(2,1/(AI385:AK385<>""),AI385:AK385))) | IF(OR(F385="",AM385=""),"",IF(COUNT(AI385:AL385)=0,"",AM385-LOOKUP(2,1/(AI385:AL385<>""),AI385:AL385))) | IF(OR(F385="",AN385=""),"",IF(COUNT(AI385:AM385)=0,"",AN385-LOOKUP(2,1/(AI385:AM385<>""),AI385:AM385))) | IF(OR(F385="",AO385=""),"",IF(COUNT(AI385:AN385)=0,"",AO385-LOOKUP(2,1/(AI385:AN385<>""),AI385:AN385))) | IF(OR(F385="",AP385=""),"",IF(COUNT(AI385:AO385)=0,"",AP385-LOOKUP(2,1/(AI385:AO385<>""),AI385:AO385))) | IF(OR(F385="",AQ385=""),"",IF(COUNT(AI385:AP385)=0,"",AQ385-LOOKUP(2,1/(AI385:AP385<>""),AI385:AP385))) | IF(OR(F385="",AR385=""),"",IF(COUNT(AI385:AQ385)=0,"",AR385-LOOKUP(2,1/(AI385:AQ385<>""),AI385:AQ385))) | IF(OR(F385="",AS385=""),"",IF(COUNT(AI385:AR385)=0,"",AS385-LOOKUP(2,1/(AI385:AR385<>""),AI385:AR385))) | IF(OR(F385="",AT385=""),"",IF(COUNT(AI385:AS385)=0,"",AT385-LOOKUP(2,1/(AI385:AS385<>""),AI385:AS385))) | IF(OR(F385="",AU385=""),"",IF(COUNT(AI385:AT385)=0,"",AU385-LOOKUP(2,1/(AI385:AT385<>""),AI385:AT385))) | IF(OR(F385="",AV385=""),"",IF(COUNT(AI385:AU385)=0,"",AV385-LOOKUP(2,1/(AI385:AU385<>""),AI385:AU385))) | IF(J385="","All_Provinces",IFERROR(VLOOKUP(J385,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K385="","All_Districts",IFERROR(VLOOKUP(K385,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F386="","",ROW()-3) | [18 empty] | IF(AQ386="","",AQ386) |  |  |  | IF(W386<>"",W386,IF(OR(T386="",V386=""),"",EDATE(T386,V386))) |  |  |  |  | IF(F386="","",IF(COUNT(AI386:AV386)=0,IF(AA386="","Not started",AA386),SUBSTITUTE(LOOKUP(2,1/(AI386:AV386<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F386="",COUNT(AI386:AV386)=0),"",TODAY()-LOOKUP(2,1/(AI386:AV386<>""),AI386:AV386)) | IF(OR(F386="",COUNT(AI386:AV386)<2),"",LOOKUP(2,1/(AI386:AV386<>""),AI386:AV386)-MIN(AI386:AV386)) | IF(OR(AD386="",AC386="Not started",AC386=""),"",IFERROR(AD386-IF(VLOOKUP(AC386,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC386,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F386="","",IF(OR(AA386="Cancelled",AC386="Cancelled"),"Cancelled",IF(OR(AC386="Completed / Handover",Y386<>"",Z386>=100),"Completed — on track",IF(O386="Not awarded",IF(U386="",IF(X386="","No planned date",IF(TODAY()>X386,"Behind — past planned date",IF(X386-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U386,"Behind — award date passed",IF(U386-TODAY()<=30,"At risk — close to off track","On track"))),IF(X386="","No planned date",IF(AND(TODAY()>X386,OR(Z386="",Z386<100)),"Behind — past end date",IF(AND(T386<>"",X386<>"",Z386<>"",(Z386<100),((TODAY()-T386)/MAX(X386-T386,1)*100)-Z386>15),"Behind — progress lag",IF(AND(X386-TODAY()<=30,X386-TODAY()>=0,OR(Z386="",Z386<90)),"At risk — close to off track","On track")))))))) | IF(OR(F386="",AC386="Completed / Handover",AC386="Cancelled"),"",IF(O386="Not awarded",IF(U386<>"",U386-TODAY(),IF(X386="","",X386-TODAY())),IF(X386="","",X386-TODAY()))) | [14 empty] | IF(OR(F386="",AJ386=""),"",IF(COUNT(AI386:AI386)=0,"",AJ386-LOOKUP(2,1/(AI386:AI386<>""),AI386:AI386))) | IF(OR(F386="",AK386=""),"",IF(COUNT(AI386:AJ386)=0,"",AK386-LOOKUP(2,1/(AI386:AJ386<>""),AI386:AJ386))) | IF(OR(F386="",AL386=""),"",IF(COUNT(AI386:AK386)=0,"",AL386-LOOKUP(2,1/(AI386:AK386<>""),AI386:AK386))) | IF(OR(F386="",AM386=""),"",IF(COUNT(AI386:AL386)=0,"",AM386-LOOKUP(2,1/(AI386:AL386<>""),AI386:AL386))) | IF(OR(F386="",AN386=""),"",IF(COUNT(AI386:AM386)=0,"",AN386-LOOKUP(2,1/(AI386:AM386<>""),AI386:AM386))) | IF(OR(F386="",AO386=""),"",IF(COUNT(AI386:AN386)=0,"",AO386-LOOKUP(2,1/(AI386:AN386<>""),AI386:AN386))) | IF(OR(F386="",AP386=""),"",IF(COUNT(AI386:AO386)=0,"",AP386-LOOKUP(2,1/(AI386:AO386<>""),AI386:AO386))) | IF(OR(F386="",AQ386=""),"",IF(COUNT(AI386:AP386)=0,"",AQ386-LOOKUP(2,1/(AI386:AP386<>""),AI386:AP386))) | IF(OR(F386="",AR386=""),"",IF(COUNT(AI386:AQ386)=0,"",AR386-LOOKUP(2,1/(AI386:AQ386<>""),AI386:AQ386))) | IF(OR(F386="",AS386=""),"",IF(COUNT(AI386:AR386)=0,"",AS386-LOOKUP(2,1/(AI386:AR386<>""),AI386:AR386))) | IF(OR(F386="",AT386=""),"",IF(COUNT(AI386:AS386)=0,"",AT386-LOOKUP(2,1/(AI386:AS386<>""),AI386:AS386))) | IF(OR(F386="",AU386=""),"",IF(COUNT(AI386:AT386)=0,"",AU386-LOOKUP(2,1/(AI386:AT386<>""),AI386:AT386))) | IF(OR(F386="",AV386=""),"",IF(COUNT(AI386:AU386)=0,"",AV386-LOOKUP(2,1/(AI386:AU386<>""),AI386:AU386))) | IF(J386="","All_Provinces",IFERROR(VLOOKUP(J386,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K386="","All_Districts",IFERROR(VLOOKUP(K386,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F387="","",ROW()-3) | [18 empty] | IF(AQ387="","",AQ387) |  |  |  | IF(W387<>"",W387,IF(OR(T387="",V387=""),"",EDATE(T387,V387))) |  |  |  |  | IF(F387="","",IF(COUNT(AI387:AV387)=0,IF(AA387="","Not started",AA387),SUBSTITUTE(LOOKUP(2,1/(AI387:AV387<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F387="",COUNT(AI387:AV387)=0),"",TODAY()-LOOKUP(2,1/(AI387:AV387<>""),AI387:AV387)) | IF(OR(F387="",COUNT(AI387:AV387)<2),"",LOOKUP(2,1/(AI387:AV387<>""),AI387:AV387)-MIN(AI387:AV387)) | IF(OR(AD387="",AC387="Not started",AC387=""),"",IFERROR(AD387-IF(VLOOKUP(AC387,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC387,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F387="","",IF(OR(AA387="Cancelled",AC387="Cancelled"),"Cancelled",IF(OR(AC387="Completed / Handover",Y387<>"",Z387>=100),"Completed — on track",IF(O387="Not awarded",IF(U387="",IF(X387="","No planned date",IF(TODAY()>X387,"Behind — past planned date",IF(X387-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U387,"Behind — award date passed",IF(U387-TODAY()<=30,"At risk — close to off track","On track"))),IF(X387="","No planned date",IF(AND(TODAY()>X387,OR(Z387="",Z387<100)),"Behind — past end date",IF(AND(T387<>"",X387<>"",Z387<>"",(Z387<100),((TODAY()-T387)/MAX(X387-T387,1)*100)-Z387>15),"Behind — progress lag",IF(AND(X387-TODAY()<=30,X387-TODAY()>=0,OR(Z387="",Z387<90)),"At risk — close to off track","On track")))))))) | IF(OR(F387="",AC387="Completed / Handover",AC387="Cancelled"),"",IF(O387="Not awarded",IF(U387<>"",U387-TODAY(),IF(X387="","",X387-TODAY())),IF(X387="","",X387-TODAY()))) | [14 empty] | IF(OR(F387="",AJ387=""),"",IF(COUNT(AI387:AI387)=0,"",AJ387-LOOKUP(2,1/(AI387:AI387<>""),AI387:AI387))) | IF(OR(F387="",AK387=""),"",IF(COUNT(AI387:AJ387)=0,"",AK387-LOOKUP(2,1/(AI387:AJ387<>""),AI387:AJ387))) | IF(OR(F387="",AL387=""),"",IF(COUNT(AI387:AK387)=0,"",AL387-LOOKUP(2,1/(AI387:AK387<>""),AI387:AK387))) | IF(OR(F387="",AM387=""),"",IF(COUNT(AI387:AL387)=0,"",AM387-LOOKUP(2,1/(AI387:AL387<>""),AI387:AL387))) | IF(OR(F387="",AN387=""),"",IF(COUNT(AI387:AM387)=0,"",AN387-LOOKUP(2,1/(AI387:AM387<>""),AI387:AM387))) | IF(OR(F387="",AO387=""),"",IF(COUNT(AI387:AN387)=0,"",AO387-LOOKUP(2,1/(AI387:AN387<>""),AI387:AN387))) | IF(OR(F387="",AP387=""),"",IF(COUNT(AI387:AO387)=0,"",AP387-LOOKUP(2,1/(AI387:AO387<>""),AI387:AO387))) | IF(OR(F387="",AQ387=""),"",IF(COUNT(AI387:AP387)=0,"",AQ387-LOOKUP(2,1/(AI387:AP387<>""),AI387:AP387))) | IF(OR(F387="",AR387=""),"",IF(COUNT(AI387:AQ387)=0,"",AR387-LOOKUP(2,1/(AI387:AQ387<>""),AI387:AQ387))) | IF(OR(F387="",AS387=""),"",IF(COUNT(AI387:AR387)=0,"",AS387-LOOKUP(2,1/(AI387:AR387<>""),AI387:AR387))) | IF(OR(F387="",AT387=""),"",IF(COUNT(AI387:AS387)=0,"",AT387-LOOKUP(2,1/(AI387:AS387<>""),AI387:AS387))) | IF(OR(F387="",AU387=""),"",IF(COUNT(AI387:AT387)=0,"",AU387-LOOKUP(2,1/(AI387:AT387<>""),AI387:AT387))) | IF(OR(F387="",AV387=""),"",IF(COUNT(AI387:AU387)=0,"",AV387-LOOKUP(2,1/(AI387:AU387<>""),AI387:AU387))) | IF(J387="","All_Provinces",IFERROR(VLOOKUP(J387,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K387="","All_Districts",IFERROR(VLOOKUP(K387,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F388="","",ROW()-3) | [18 empty] | IF(AQ388="","",AQ388) |  |  |  | IF(W388<>"",W388,IF(OR(T388="",V388=""),"",EDATE(T388,V388))) |  |  |  |  | IF(F388="","",IF(COUNT(AI388:AV388)=0,IF(AA388="","Not started",AA388),SUBSTITUTE(LOOKUP(2,1/(AI388:AV388<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F388="",COUNT(AI388:AV388)=0),"",TODAY()-LOOKUP(2,1/(AI388:AV388<>""),AI388:AV388)) | IF(OR(F388="",COUNT(AI388:AV388)<2),"",LOOKUP(2,1/(AI388:AV388<>""),AI388:AV388)-MIN(AI388:AV388)) | IF(OR(AD388="",AC388="Not started",AC388=""),"",IFERROR(AD388-IF(VLOOKUP(AC388,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC388,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F388="","",IF(OR(AA388="Cancelled",AC388="Cancelled"),"Cancelled",IF(OR(AC388="Completed / Handover",Y388<>"",Z388>=100),"Completed — on track",IF(O388="Not awarded",IF(U388="",IF(X388="","No planned date",IF(TODAY()>X388,"Behind — past planned date",IF(X388-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U388,"Behind — award date passed",IF(U388-TODAY()<=30,"At risk — close to off track","On track"))),IF(X388="","No planned date",IF(AND(TODAY()>X388,OR(Z388="",Z388<100)),"Behind — past end date",IF(AND(T388<>"",X388<>"",Z388<>"",(Z388<100),((TODAY()-T388)/MAX(X388-T388,1)*100)-Z388>15),"Behind — progress lag",IF(AND(X388-TODAY()<=30,X388-TODAY()>=0,OR(Z388="",Z388<90)),"At risk — close to off track","On track")))))))) | IF(OR(F388="",AC388="Completed / Handover",AC388="Cancelled"),"",IF(O388="Not awarded",IF(U388<>"",U388-TODAY(),IF(X388="","",X388-TODAY())),IF(X388="","",X388-TODAY()))) | [14 empty] | IF(OR(F388="",AJ388=""),"",IF(COUNT(AI388:AI388)=0,"",AJ388-LOOKUP(2,1/(AI388:AI388<>""),AI388:AI388))) | IF(OR(F388="",AK388=""),"",IF(COUNT(AI388:AJ388)=0,"",AK388-LOOKUP(2,1/(AI388:AJ388<>""),AI388:AJ388))) | IF(OR(F388="",AL388=""),"",IF(COUNT(AI388:AK388)=0,"",AL388-LOOKUP(2,1/(AI388:AK388<>""),AI388:AK388))) | IF(OR(F388="",AM388=""),"",IF(COUNT(AI388:AL388)=0,"",AM388-LOOKUP(2,1/(AI388:AL388<>""),AI388:AL388))) | IF(OR(F388="",AN388=""),"",IF(COUNT(AI388:AM388)=0,"",AN388-LOOKUP(2,1/(AI388:AM388<>""),AI388:AM388))) | IF(OR(F388="",AO388=""),"",IF(COUNT(AI388:AN388)=0,"",AO388-LOOKUP(2,1/(AI388:AN388<>""),AI388:AN388))) | IF(OR(F388="",AP388=""),"",IF(COUNT(AI388:AO388)=0,"",AP388-LOOKUP(2,1/(AI388:AO388<>""),AI388:AO388))) | IF(OR(F388="",AQ388=""),"",IF(COUNT(AI388:AP388)=0,"",AQ388-LOOKUP(2,1/(AI388:AP388<>""),AI388:AP388))) | IF(OR(F388="",AR388=""),"",IF(COUNT(AI388:AQ388)=0,"",AR388-LOOKUP(2,1/(AI388:AQ388<>""),AI388:AQ388))) | IF(OR(F388="",AS388=""),"",IF(COUNT(AI388:AR388)=0,"",AS388-LOOKUP(2,1/(AI388:AR388<>""),AI388:AR388))) | IF(OR(F388="",AT388=""),"",IF(COUNT(AI388:AS388)=0,"",AT388-LOOKUP(2,1/(AI388:AS388<>""),AI388:AS388))) | IF(OR(F388="",AU388=""),"",IF(COUNT(AI388:AT388)=0,"",AU388-LOOKUP(2,1/(AI388:AT388<>""),AI388:AT388))) | IF(OR(F388="",AV388=""),"",IF(COUNT(AI388:AU388)=0,"",AV388-LOOKUP(2,1/(AI388:AU388<>""),AI388:AU388))) | IF(J388="","All_Provinces",IFERROR(VLOOKUP(J388,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K388="","All_Districts",IFERROR(VLOOKUP(K388,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F389="","",ROW()-3) | [18 empty] | IF(AQ389="","",AQ389) |  |  |  | IF(W389<>"",W389,IF(OR(T389="",V389=""),"",EDATE(T389,V389))) |  |  |  |  | IF(F389="","",IF(COUNT(AI389:AV389)=0,IF(AA389="","Not started",AA389),SUBSTITUTE(LOOKUP(2,1/(AI389:AV389<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F389="",COUNT(AI389:AV389)=0),"",TODAY()-LOOKUP(2,1/(AI389:AV389<>""),AI389:AV389)) | IF(OR(F389="",COUNT(AI389:AV389)<2),"",LOOKUP(2,1/(AI389:AV389<>""),AI389:AV389)-MIN(AI389:AV389)) | IF(OR(AD389="",AC389="Not started",AC389=""),"",IFERROR(AD389-IF(VLOOKUP(AC389,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC389,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F389="","",IF(OR(AA389="Cancelled",AC389="Cancelled"),"Cancelled",IF(OR(AC389="Completed / Handover",Y389<>"",Z389>=100),"Completed — on track",IF(O389="Not awarded",IF(U389="",IF(X389="","No planned date",IF(TODAY()>X389,"Behind — past planned date",IF(X389-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U389,"Behind — award date passed",IF(U389-TODAY()<=30,"At risk — close to off track","On track"))),IF(X389="","No planned date",IF(AND(TODAY()>X389,OR(Z389="",Z389<100)),"Behind — past end date",IF(AND(T389<>"",X389<>"",Z389<>"",(Z389<100),((TODAY()-T389)/MAX(X389-T389,1)*100)-Z389>15),"Behind — progress lag",IF(AND(X389-TODAY()<=30,X389-TODAY()>=0,OR(Z389="",Z389<90)),"At risk — close to off track","On track")))))))) | IF(OR(F389="",AC389="Completed / Handover",AC389="Cancelled"),"",IF(O389="Not awarded",IF(U389<>"",U389-TODAY(),IF(X389="","",X389-TODAY())),IF(X389="","",X389-TODAY()))) | [14 empty] | IF(OR(F389="",AJ389=""),"",IF(COUNT(AI389:AI389)=0,"",AJ389-LOOKUP(2,1/(AI389:AI389<>""),AI389:AI389))) | IF(OR(F389="",AK389=""),"",IF(COUNT(AI389:AJ389)=0,"",AK389-LOOKUP(2,1/(AI389:AJ389<>""),AI389:AJ389))) | IF(OR(F389="",AL389=""),"",IF(COUNT(AI389:AK389)=0,"",AL389-LOOKUP(2,1/(AI389:AK389<>""),AI389:AK389))) | IF(OR(F389="",AM389=""),"",IF(COUNT(AI389:AL389)=0,"",AM389-LOOKUP(2,1/(AI389:AL389<>""),AI389:AL389))) | IF(OR(F389="",AN389=""),"",IF(COUNT(AI389:AM389)=0,"",AN389-LOOKUP(2,1/(AI389:AM389<>""),AI389:AM389))) | IF(OR(F389="",AO389=""),"",IF(COUNT(AI389:AN389)=0,"",AO389-LOOKUP(2,1/(AI389:AN389<>""),AI389:AN389))) | IF(OR(F389="",AP389=""),"",IF(COUNT(AI389:AO389)=0,"",AP389-LOOKUP(2,1/(AI389:AO389<>""),AI389:AO389))) | IF(OR(F389="",AQ389=""),"",IF(COUNT(AI389:AP389)=0,"",AQ389-LOOKUP(2,1/(AI389:AP389<>""),AI389:AP389))) | IF(OR(F389="",AR389=""),"",IF(COUNT(AI389:AQ389)=0,"",AR389-LOOKUP(2,1/(AI389:AQ389<>""),AI389:AQ389))) | IF(OR(F389="",AS389=""),"",IF(COUNT(AI389:AR389)=0,"",AS389-LOOKUP(2,1/(AI389:AR389<>""),AI389:AR389))) | IF(OR(F389="",AT389=""),"",IF(COUNT(AI389:AS389)=0,"",AT389-LOOKUP(2,1/(AI389:AS389<>""),AI389:AS389))) | IF(OR(F389="",AU389=""),"",IF(COUNT(AI389:AT389)=0,"",AU389-LOOKUP(2,1/(AI389:AT389<>""),AI389:AT389))) | IF(OR(F389="",AV389=""),"",IF(COUNT(AI389:AU389)=0,"",AV389-LOOKUP(2,1/(AI389:AU389<>""),AI389:AU389))) | IF(J389="","All_Provinces",IFERROR(VLOOKUP(J389,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K389="","All_Districts",IFERROR(VLOOKUP(K389,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F390="","",ROW()-3) | [18 empty] | IF(AQ390="","",AQ390) |  |  |  | IF(W390<>"",W390,IF(OR(T390="",V390=""),"",EDATE(T390,V390))) |  |  |  |  | IF(F390="","",IF(COUNT(AI390:AV390)=0,IF(AA390="","Not started",AA390),SUBSTITUTE(LOOKUP(2,1/(AI390:AV390<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F390="",COUNT(AI390:AV390)=0),"",TODAY()-LOOKUP(2,1/(AI390:AV390<>""),AI390:AV390)) | IF(OR(F390="",COUNT(AI390:AV390)<2),"",LOOKUP(2,1/(AI390:AV390<>""),AI390:AV390)-MIN(AI390:AV390)) | IF(OR(AD390="",AC390="Not started",AC390=""),"",IFERROR(AD390-IF(VLOOKUP(AC390,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC390,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F390="","",IF(OR(AA390="Cancelled",AC390="Cancelled"),"Cancelled",IF(OR(AC390="Completed / Handover",Y390<>"",Z390>=100),"Completed — on track",IF(O390="Not awarded",IF(U390="",IF(X390="","No planned date",IF(TODAY()>X390,"Behind — past planned date",IF(X390-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U390,"Behind — award date passed",IF(U390-TODAY()<=30,"At risk — close to off track","On track"))),IF(X390="","No planned date",IF(AND(TODAY()>X390,OR(Z390="",Z390<100)),"Behind — past end date",IF(AND(T390<>"",X390<>"",Z390<>"",(Z390<100),((TODAY()-T390)/MAX(X390-T390,1)*100)-Z390>15),"Behind — progress lag",IF(AND(X390-TODAY()<=30,X390-TODAY()>=0,OR(Z390="",Z390<90)),"At risk — close to off track","On track")))))))) | IF(OR(F390="",AC390="Completed / Handover",AC390="Cancelled"),"",IF(O390="Not awarded",IF(U390<>"",U390-TODAY(),IF(X390="","",X390-TODAY())),IF(X390="","",X390-TODAY()))) | [14 empty] | IF(OR(F390="",AJ390=""),"",IF(COUNT(AI390:AI390)=0,"",AJ390-LOOKUP(2,1/(AI390:AI390<>""),AI390:AI390))) | IF(OR(F390="",AK390=""),"",IF(COUNT(AI390:AJ390)=0,"",AK390-LOOKUP(2,1/(AI390:AJ390<>""),AI390:AJ390))) | IF(OR(F390="",AL390=""),"",IF(COUNT(AI390:AK390)=0,"",AL390-LOOKUP(2,1/(AI390:AK390<>""),AI390:AK390))) | IF(OR(F390="",AM390=""),"",IF(COUNT(AI390:AL390)=0,"",AM390-LOOKUP(2,1/(AI390:AL390<>""),AI390:AL390))) | IF(OR(F390="",AN390=""),"",IF(COUNT(AI390:AM390)=0,"",AN390-LOOKUP(2,1/(AI390:AM390<>""),AI390:AM390))) | IF(OR(F390="",AO390=""),"",IF(COUNT(AI390:AN390)=0,"",AO390-LOOKUP(2,1/(AI390:AN390<>""),AI390:AN390))) | IF(OR(F390="",AP390=""),"",IF(COUNT(AI390:AO390)=0,"",AP390-LOOKUP(2,1/(AI390:AO390<>""),AI390:AO390))) | IF(OR(F390="",AQ390=""),"",IF(COUNT(AI390:AP390)=0,"",AQ390-LOOKUP(2,1/(AI390:AP390<>""),AI390:AP390))) | IF(OR(F390="",AR390=""),"",IF(COUNT(AI390:AQ390)=0,"",AR390-LOOKUP(2,1/(AI390:AQ390<>""),AI390:AQ390))) | IF(OR(F390="",AS390=""),"",IF(COUNT(AI390:AR390)=0,"",AS390-LOOKUP(2,1/(AI390:AR390<>""),AI390:AR390))) | IF(OR(F390="",AT390=""),"",IF(COUNT(AI390:AS390)=0,"",AT390-LOOKUP(2,1/(AI390:AS390<>""),AI390:AS390))) | IF(OR(F390="",AU390=""),"",IF(COUNT(AI390:AT390)=0,"",AU390-LOOKUP(2,1/(AI390:AT390<>""),AI390:AT390))) | IF(OR(F390="",AV390=""),"",IF(COUNT(AI390:AU390)=0,"",AV390-LOOKUP(2,1/(AI390:AU390<>""),AI390:AU390))) | IF(J390="","All_Provinces",IFERROR(VLOOKUP(J390,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K390="","All_Districts",IFERROR(VLOOKUP(K390,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F391="","",ROW()-3) | [18 empty] | IF(AQ391="","",AQ391) |  |  |  | IF(W391<>"",W391,IF(OR(T391="",V391=""),"",EDATE(T391,V391))) |  |  |  |  | IF(F391="","",IF(COUNT(AI391:AV391)=0,IF(AA391="","Not started",AA391),SUBSTITUTE(LOOKUP(2,1/(AI391:AV391<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F391="",COUNT(AI391:AV391)=0),"",TODAY()-LOOKUP(2,1/(AI391:AV391<>""),AI391:AV391)) | IF(OR(F391="",COUNT(AI391:AV391)<2),"",LOOKUP(2,1/(AI391:AV391<>""),AI391:AV391)-MIN(AI391:AV391)) | IF(OR(AD391="",AC391="Not started",AC391=""),"",IFERROR(AD391-IF(VLOOKUP(AC391,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC391,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F391="","",IF(OR(AA391="Cancelled",AC391="Cancelled"),"Cancelled",IF(OR(AC391="Completed / Handover",Y391<>"",Z391>=100),"Completed — on track",IF(O391="Not awarded",IF(U391="",IF(X391="","No planned date",IF(TODAY()>X391,"Behind — past planned date",IF(X391-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U391,"Behind — award date passed",IF(U391-TODAY()<=30,"At risk — close to off track","On track"))),IF(X391="","No planned date",IF(AND(TODAY()>X391,OR(Z391="",Z391<100)),"Behind — past end date",IF(AND(T391<>"",X391<>"",Z391<>"",(Z391<100),((TODAY()-T391)/MAX(X391-T391,1)*100)-Z391>15),"Behind — progress lag",IF(AND(X391-TODAY()<=30,X391-TODAY()>=0,OR(Z391="",Z391<90)),"At risk — close to off track","On track")))))))) | IF(OR(F391="",AC391="Completed / Handover",AC391="Cancelled"),"",IF(O391="Not awarded",IF(U391<>"",U391-TODAY(),IF(X391="","",X391-TODAY())),IF(X391="","",X391-TODAY()))) | [14 empty] | IF(OR(F391="",AJ391=""),"",IF(COUNT(AI391:AI391)=0,"",AJ391-LOOKUP(2,1/(AI391:AI391<>""),AI391:AI391))) | IF(OR(F391="",AK391=""),"",IF(COUNT(AI391:AJ391)=0,"",AK391-LOOKUP(2,1/(AI391:AJ391<>""),AI391:AJ391))) | IF(OR(F391="",AL391=""),"",IF(COUNT(AI391:AK391)=0,"",AL391-LOOKUP(2,1/(AI391:AK391<>""),AI391:AK391))) | IF(OR(F391="",AM391=""),"",IF(COUNT(AI391:AL391)=0,"",AM391-LOOKUP(2,1/(AI391:AL391<>""),AI391:AL391))) | IF(OR(F391="",AN391=""),"",IF(COUNT(AI391:AM391)=0,"",AN391-LOOKUP(2,1/(AI391:AM391<>""),AI391:AM391))) | IF(OR(F391="",AO391=""),"",IF(COUNT(AI391:AN391)=0,"",AO391-LOOKUP(2,1/(AI391:AN391<>""),AI391:AN391))) | IF(OR(F391="",AP391=""),"",IF(COUNT(AI391:AO391)=0,"",AP391-LOOKUP(2,1/(AI391:AO391<>""),AI391:AO391))) | IF(OR(F391="",AQ391=""),"",IF(COUNT(AI391:AP391)=0,"",AQ391-LOOKUP(2,1/(AI391:AP391<>""),AI391:AP391))) | IF(OR(F391="",AR391=""),"",IF(COUNT(AI391:AQ391)=0,"",AR391-LOOKUP(2,1/(AI391:AQ391<>""),AI391:AQ391))) | IF(OR(F391="",AS391=""),"",IF(COUNT(AI391:AR391)=0,"",AS391-LOOKUP(2,1/(AI391:AR391<>""),AI391:AR391))) | IF(OR(F391="",AT391=""),"",IF(COUNT(AI391:AS391)=0,"",AT391-LOOKUP(2,1/(AI391:AS391<>""),AI391:AS391))) | IF(OR(F391="",AU391=""),"",IF(COUNT(AI391:AT391)=0,"",AU391-LOOKUP(2,1/(AI391:AT391<>""),AI391:AT391))) | IF(OR(F391="",AV391=""),"",IF(COUNT(AI391:AU391)=0,"",AV391-LOOKUP(2,1/(AI391:AU391<>""),AI391:AU391))) | IF(J391="","All_Provinces",IFERROR(VLOOKUP(J391,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K391="","All_Districts",IFERROR(VLOOKUP(K391,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F392="","",ROW()-3) | [18 empty] | IF(AQ392="","",AQ392) |  |  |  | IF(W392<>"",W392,IF(OR(T392="",V392=""),"",EDATE(T392,V392))) |  |  |  |  | IF(F392="","",IF(COUNT(AI392:AV392)=0,IF(AA392="","Not started",AA392),SUBSTITUTE(LOOKUP(2,1/(AI392:AV392<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F392="",COUNT(AI392:AV392)=0),"",TODAY()-LOOKUP(2,1/(AI392:AV392<>""),AI392:AV392)) | IF(OR(F392="",COUNT(AI392:AV392)<2),"",LOOKUP(2,1/(AI392:AV392<>""),AI392:AV392)-MIN(AI392:AV392)) | IF(OR(AD392="",AC392="Not started",AC392=""),"",IFERROR(AD392-IF(VLOOKUP(AC392,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC392,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F392="","",IF(OR(AA392="Cancelled",AC392="Cancelled"),"Cancelled",IF(OR(AC392="Completed / Handover",Y392<>"",Z392>=100),"Completed — on track",IF(O392="Not awarded",IF(U392="",IF(X392="","No planned date",IF(TODAY()>X392,"Behind — past planned date",IF(X392-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U392,"Behind — award date passed",IF(U392-TODAY()<=30,"At risk — close to off track","On track"))),IF(X392="","No planned date",IF(AND(TODAY()>X392,OR(Z392="",Z392<100)),"Behind — past end date",IF(AND(T392<>"",X392<>"",Z392<>"",(Z392<100),((TODAY()-T392)/MAX(X392-T392,1)*100)-Z392>15),"Behind — progress lag",IF(AND(X392-TODAY()<=30,X392-TODAY()>=0,OR(Z392="",Z392<90)),"At risk — close to off track","On track")))))))) | IF(OR(F392="",AC392="Completed / Handover",AC392="Cancelled"),"",IF(O392="Not awarded",IF(U392<>"",U392-TODAY(),IF(X392="","",X392-TODAY())),IF(X392="","",X392-TODAY()))) | [14 empty] | IF(OR(F392="",AJ392=""),"",IF(COUNT(AI392:AI392)=0,"",AJ392-LOOKUP(2,1/(AI392:AI392<>""),AI392:AI392))) | IF(OR(F392="",AK392=""),"",IF(COUNT(AI392:AJ392)=0,"",AK392-LOOKUP(2,1/(AI392:AJ392<>""),AI392:AJ392))) | IF(OR(F392="",AL392=""),"",IF(COUNT(AI392:AK392)=0,"",AL392-LOOKUP(2,1/(AI392:AK392<>""),AI392:AK392))) | IF(OR(F392="",AM392=""),"",IF(COUNT(AI392:AL392)=0,"",AM392-LOOKUP(2,1/(AI392:AL392<>""),AI392:AL392))) | IF(OR(F392="",AN392=""),"",IF(COUNT(AI392:AM392)=0,"",AN392-LOOKUP(2,1/(AI392:AM392<>""),AI392:AM392))) | IF(OR(F392="",AO392=""),"",IF(COUNT(AI392:AN392)=0,"",AO392-LOOKUP(2,1/(AI392:AN392<>""),AI392:AN392))) | IF(OR(F392="",AP392=""),"",IF(COUNT(AI392:AO392)=0,"",AP392-LOOKUP(2,1/(AI392:AO392<>""),AI392:AO392))) | IF(OR(F392="",AQ392=""),"",IF(COUNT(AI392:AP392)=0,"",AQ392-LOOKUP(2,1/(AI392:AP392<>""),AI392:AP392))) | IF(OR(F392="",AR392=""),"",IF(COUNT(AI392:AQ392)=0,"",AR392-LOOKUP(2,1/(AI392:AQ392<>""),AI392:AQ392))) | IF(OR(F392="",AS392=""),"",IF(COUNT(AI392:AR392)=0,"",AS392-LOOKUP(2,1/(AI392:AR392<>""),AI392:AR392))) | IF(OR(F392="",AT392=""),"",IF(COUNT(AI392:AS392)=0,"",AT392-LOOKUP(2,1/(AI392:AS392<>""),AI392:AS392))) | IF(OR(F392="",AU392=""),"",IF(COUNT(AI392:AT392)=0,"",AU392-LOOKUP(2,1/(AI392:AT392<>""),AI392:AT392))) | IF(OR(F392="",AV392=""),"",IF(COUNT(AI392:AU392)=0,"",AV392-LOOKUP(2,1/(AI392:AU392<>""),AI392:AU392))) | IF(J392="","All_Provinces",IFERROR(VLOOKUP(J392,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K392="","All_Districts",IFERROR(VLOOKUP(K392,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F393="","",ROW()-3) | [18 empty] | IF(AQ393="","",AQ393) |  |  |  | IF(W393<>"",W393,IF(OR(T393="",V393=""),"",EDATE(T393,V393))) |  |  |  |  | IF(F393="","",IF(COUNT(AI393:AV393)=0,IF(AA393="","Not started",AA393),SUBSTITUTE(LOOKUP(2,1/(AI393:AV393<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F393="",COUNT(AI393:AV393)=0),"",TODAY()-LOOKUP(2,1/(AI393:AV393<>""),AI393:AV393)) | IF(OR(F393="",COUNT(AI393:AV393)<2),"",LOOKUP(2,1/(AI393:AV393<>""),AI393:AV393)-MIN(AI393:AV393)) | IF(OR(AD393="",AC393="Not started",AC393=""),"",IFERROR(AD393-IF(VLOOKUP(AC393,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC393,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F393="","",IF(OR(AA393="Cancelled",AC393="Cancelled"),"Cancelled",IF(OR(AC393="Completed / Handover",Y393<>"",Z393>=100),"Completed — on track",IF(O393="Not awarded",IF(U393="",IF(X393="","No planned date",IF(TODAY()>X393,"Behind — past planned date",IF(X393-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U393,"Behind — award date passed",IF(U393-TODAY()<=30,"At risk — close to off track","On track"))),IF(X393="","No planned date",IF(AND(TODAY()>X393,OR(Z393="",Z393<100)),"Behind — past end date",IF(AND(T393<>"",X393<>"",Z393<>"",(Z393<100),((TODAY()-T393)/MAX(X393-T393,1)*100)-Z393>15),"Behind — progress lag",IF(AND(X393-TODAY()<=30,X393-TODAY()>=0,OR(Z393="",Z393<90)),"At risk — close to off track","On track")))))))) | IF(OR(F393="",AC393="Completed / Handover",AC393="Cancelled"),"",IF(O393="Not awarded",IF(U393<>"",U393-TODAY(),IF(X393="","",X393-TODAY())),IF(X393="","",X393-TODAY()))) | [14 empty] | IF(OR(F393="",AJ393=""),"",IF(COUNT(AI393:AI393)=0,"",AJ393-LOOKUP(2,1/(AI393:AI393<>""),AI393:AI393))) | IF(OR(F393="",AK393=""),"",IF(COUNT(AI393:AJ393)=0,"",AK393-LOOKUP(2,1/(AI393:AJ393<>""),AI393:AJ393))) | IF(OR(F393="",AL393=""),"",IF(COUNT(AI393:AK393)=0,"",AL393-LOOKUP(2,1/(AI393:AK393<>""),AI393:AK393))) | IF(OR(F393="",AM393=""),"",IF(COUNT(AI393:AL393)=0,"",AM393-LOOKUP(2,1/(AI393:AL393<>""),AI393:AL393))) | IF(OR(F393="",AN393=""),"",IF(COUNT(AI393:AM393)=0,"",AN393-LOOKUP(2,1/(AI393:AM393<>""),AI393:AM393))) | IF(OR(F393="",AO393=""),"",IF(COUNT(AI393:AN393)=0,"",AO393-LOOKUP(2,1/(AI393:AN393<>""),AI393:AN393))) | IF(OR(F393="",AP393=""),"",IF(COUNT(AI393:AO393)=0,"",AP393-LOOKUP(2,1/(AI393:AO393<>""),AI393:AO393))) | IF(OR(F393="",AQ393=""),"",IF(COUNT(AI393:AP393)=0,"",AQ393-LOOKUP(2,1/(AI393:AP393<>""),AI393:AP393))) | IF(OR(F393="",AR393=""),"",IF(COUNT(AI393:AQ393)=0,"",AR393-LOOKUP(2,1/(AI393:AQ393<>""),AI393:AQ393))) | IF(OR(F393="",AS393=""),"",IF(COUNT(AI393:AR393)=0,"",AS393-LOOKUP(2,1/(AI393:AR393<>""),AI393:AR393))) | IF(OR(F393="",AT393=""),"",IF(COUNT(AI393:AS393)=0,"",AT393-LOOKUP(2,1/(AI393:AS393<>""),AI393:AS393))) | IF(OR(F393="",AU393=""),"",IF(COUNT(AI393:AT393)=0,"",AU393-LOOKUP(2,1/(AI393:AT393<>""),AI393:AT393))) | IF(OR(F393="",AV393=""),"",IF(COUNT(AI393:AU393)=0,"",AV393-LOOKUP(2,1/(AI393:AU393<>""),AI393:AU393))) | IF(J393="","All_Provinces",IFERROR(VLOOKUP(J393,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K393="","All_Districts",IFERROR(VLOOKUP(K393,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F394="","",ROW()-3) | [18 empty] | IF(AQ394="","",AQ394) |  |  |  | IF(W394<>"",W394,IF(OR(T394="",V394=""),"",EDATE(T394,V394))) |  |  |  |  | IF(F394="","",IF(COUNT(AI394:AV394)=0,IF(AA394="","Not started",AA394),SUBSTITUTE(LOOKUP(2,1/(AI394:AV394<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F394="",COUNT(AI394:AV394)=0),"",TODAY()-LOOKUP(2,1/(AI394:AV394<>""),AI394:AV394)) | IF(OR(F394="",COUNT(AI394:AV394)<2),"",LOOKUP(2,1/(AI394:AV394<>""),AI394:AV394)-MIN(AI394:AV394)) | IF(OR(AD394="",AC394="Not started",AC394=""),"",IFERROR(AD394-IF(VLOOKUP(AC394,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC394,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F394="","",IF(OR(AA394="Cancelled",AC394="Cancelled"),"Cancelled",IF(OR(AC394="Completed / Handover",Y394<>"",Z394>=100),"Completed — on track",IF(O394="Not awarded",IF(U394="",IF(X394="","No planned date",IF(TODAY()>X394,"Behind — past planned date",IF(X394-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U394,"Behind — award date passed",IF(U394-TODAY()<=30,"At risk — close to off track","On track"))),IF(X394="","No planned date",IF(AND(TODAY()>X394,OR(Z394="",Z394<100)),"Behind — past end date",IF(AND(T394<>"",X394<>"",Z394<>"",(Z394<100),((TODAY()-T394)/MAX(X394-T394,1)*100)-Z394>15),"Behind — progress lag",IF(AND(X394-TODAY()<=30,X394-TODAY()>=0,OR(Z394="",Z394<90)),"At risk — close to off track","On track")))))))) | IF(OR(F394="",AC394="Completed / Handover",AC394="Cancelled"),"",IF(O394="Not awarded",IF(U394<>"",U394-TODAY(),IF(X394="","",X394-TODAY())),IF(X394="","",X394-TODAY()))) | [14 empty] | IF(OR(F394="",AJ394=""),"",IF(COUNT(AI394:AI394)=0,"",AJ394-LOOKUP(2,1/(AI394:AI394<>""),AI394:AI394))) | IF(OR(F394="",AK394=""),"",IF(COUNT(AI394:AJ394)=0,"",AK394-LOOKUP(2,1/(AI394:AJ394<>""),AI394:AJ394))) | IF(OR(F394="",AL394=""),"",IF(COUNT(AI394:AK394)=0,"",AL394-LOOKUP(2,1/(AI394:AK394<>""),AI394:AK394))) | IF(OR(F394="",AM394=""),"",IF(COUNT(AI394:AL394)=0,"",AM394-LOOKUP(2,1/(AI394:AL394<>""),AI394:AL394))) | IF(OR(F394="",AN394=""),"",IF(COUNT(AI394:AM394)=0,"",AN394-LOOKUP(2,1/(AI394:AM394<>""),AI394:AM394))) | IF(OR(F394="",AO394=""),"",IF(COUNT(AI394:AN394)=0,"",AO394-LOOKUP(2,1/(AI394:AN394<>""),AI394:AN394))) | IF(OR(F394="",AP394=""),"",IF(COUNT(AI394:AO394)=0,"",AP394-LOOKUP(2,1/(AI394:AO394<>""),AI394:AO394))) | IF(OR(F394="",AQ394=""),"",IF(COUNT(AI394:AP394)=0,"",AQ394-LOOKUP(2,1/(AI394:AP394<>""),AI394:AP394))) | IF(OR(F394="",AR394=""),"",IF(COUNT(AI394:AQ394)=0,"",AR394-LOOKUP(2,1/(AI394:AQ394<>""),AI394:AQ394))) | IF(OR(F394="",AS394=""),"",IF(COUNT(AI394:AR394)=0,"",AS394-LOOKUP(2,1/(AI394:AR394<>""),AI394:AR394))) | IF(OR(F394="",AT394=""),"",IF(COUNT(AI394:AS394)=0,"",AT394-LOOKUP(2,1/(AI394:AS394<>""),AI394:AS394))) | IF(OR(F394="",AU394=""),"",IF(COUNT(AI394:AT394)=0,"",AU394-LOOKUP(2,1/(AI394:AT394<>""),AI394:AT394))) | IF(OR(F394="",AV394=""),"",IF(COUNT(AI394:AU394)=0,"",AV394-LOOKUP(2,1/(AI394:AU394<>""),AI394:AU394))) | IF(J394="","All_Provinces",IFERROR(VLOOKUP(J394,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K394="","All_Districts",IFERROR(VLOOKUP(K394,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F395="","",ROW()-3) | [18 empty] | IF(AQ395="","",AQ395) |  |  |  | IF(W395<>"",W395,IF(OR(T395="",V395=""),"",EDATE(T395,V395))) |  |  |  |  | IF(F395="","",IF(COUNT(AI395:AV395)=0,IF(AA395="","Not started",AA395),SUBSTITUTE(LOOKUP(2,1/(AI395:AV395<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F395="",COUNT(AI395:AV395)=0),"",TODAY()-LOOKUP(2,1/(AI395:AV395<>""),AI395:AV395)) | IF(OR(F395="",COUNT(AI395:AV395)<2),"",LOOKUP(2,1/(AI395:AV395<>""),AI395:AV395)-MIN(AI395:AV395)) | IF(OR(AD395="",AC395="Not started",AC395=""),"",IFERROR(AD395-IF(VLOOKUP(AC395,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC395,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F395="","",IF(OR(AA395="Cancelled",AC395="Cancelled"),"Cancelled",IF(OR(AC395="Completed / Handover",Y395<>"",Z395>=100),"Completed — on track",IF(O395="Not awarded",IF(U395="",IF(X395="","No planned date",IF(TODAY()>X395,"Behind — past planned date",IF(X395-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U395,"Behind — award date passed",IF(U395-TODAY()<=30,"At risk — close to off track","On track"))),IF(X395="","No planned date",IF(AND(TODAY()>X395,OR(Z395="",Z395<100)),"Behind — past end date",IF(AND(T395<>"",X395<>"",Z395<>"",(Z395<100),((TODAY()-T395)/MAX(X395-T395,1)*100)-Z395>15),"Behind — progress lag",IF(AND(X395-TODAY()<=30,X395-TODAY()>=0,OR(Z395="",Z395<90)),"At risk — close to off track","On track")))))))) | IF(OR(F395="",AC395="Completed / Handover",AC395="Cancelled"),"",IF(O395="Not awarded",IF(U395<>"",U395-TODAY(),IF(X395="","",X395-TODAY())),IF(X395="","",X395-TODAY()))) | [14 empty] | IF(OR(F395="",AJ395=""),"",IF(COUNT(AI395:AI395)=0,"",AJ395-LOOKUP(2,1/(AI395:AI395<>""),AI395:AI395))) | IF(OR(F395="",AK395=""),"",IF(COUNT(AI395:AJ395)=0,"",AK395-LOOKUP(2,1/(AI395:AJ395<>""),AI395:AJ395))) | IF(OR(F395="",AL395=""),"",IF(COUNT(AI395:AK395)=0,"",AL395-LOOKUP(2,1/(AI395:AK395<>""),AI395:AK395))) | IF(OR(F395="",AM395=""),"",IF(COUNT(AI395:AL395)=0,"",AM395-LOOKUP(2,1/(AI395:AL395<>""),AI395:AL395))) | IF(OR(F395="",AN395=""),"",IF(COUNT(AI395:AM395)=0,"",AN395-LOOKUP(2,1/(AI395:AM395<>""),AI395:AM395))) | IF(OR(F395="",AO395=""),"",IF(COUNT(AI395:AN395)=0,"",AO395-LOOKUP(2,1/(AI395:AN395<>""),AI395:AN395))) | IF(OR(F395="",AP395=""),"",IF(COUNT(AI395:AO395)=0,"",AP395-LOOKUP(2,1/(AI395:AO395<>""),AI395:AO395))) | IF(OR(F395="",AQ395=""),"",IF(COUNT(AI395:AP395)=0,"",AQ395-LOOKUP(2,1/(AI395:AP395<>""),AI395:AP395))) | IF(OR(F395="",AR395=""),"",IF(COUNT(AI395:AQ395)=0,"",AR395-LOOKUP(2,1/(AI395:AQ395<>""),AI395:AQ395))) | IF(OR(F395="",AS395=""),"",IF(COUNT(AI395:AR395)=0,"",AS395-LOOKUP(2,1/(AI395:AR395<>""),AI395:AR395))) | IF(OR(F395="",AT395=""),"",IF(COUNT(AI395:AS395)=0,"",AT395-LOOKUP(2,1/(AI395:AS395<>""),AI395:AS395))) | IF(OR(F395="",AU395=""),"",IF(COUNT(AI395:AT395)=0,"",AU395-LOOKUP(2,1/(AI395:AT395<>""),AI395:AT395))) | IF(OR(F395="",AV395=""),"",IF(COUNT(AI395:AU395)=0,"",AV395-LOOKUP(2,1/(AI395:AU395<>""),AI395:AU395))) | IF(J395="","All_Provinces",IFERROR(VLOOKUP(J395,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K395="","All_Districts",IFERROR(VLOOKUP(K395,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F396="","",ROW()-3) | [18 empty] | IF(AQ396="","",AQ396) |  |  |  | IF(W396<>"",W396,IF(OR(T396="",V396=""),"",EDATE(T396,V396))) |  |  |  |  | IF(F396="","",IF(COUNT(AI396:AV396)=0,IF(AA396="","Not started",AA396),SUBSTITUTE(LOOKUP(2,1/(AI396:AV396<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F396="",COUNT(AI396:AV396)=0),"",TODAY()-LOOKUP(2,1/(AI396:AV396<>""),AI396:AV396)) | IF(OR(F396="",COUNT(AI396:AV396)<2),"",LOOKUP(2,1/(AI396:AV396<>""),AI396:AV396)-MIN(AI396:AV396)) | IF(OR(AD396="",AC396="Not started",AC396=""),"",IFERROR(AD396-IF(VLOOKUP(AC396,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC396,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F396="","",IF(OR(AA396="Cancelled",AC396="Cancelled"),"Cancelled",IF(OR(AC396="Completed / Handover",Y396<>"",Z396>=100),"Completed — on track",IF(O396="Not awarded",IF(U396="",IF(X396="","No planned date",IF(TODAY()>X396,"Behind — past planned date",IF(X396-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U396,"Behind — award date passed",IF(U396-TODAY()<=30,"At risk — close to off track","On track"))),IF(X396="","No planned date",IF(AND(TODAY()>X396,OR(Z396="",Z396<100)),"Behind — past end date",IF(AND(T396<>"",X396<>"",Z396<>"",(Z396<100),((TODAY()-T396)/MAX(X396-T396,1)*100)-Z396>15),"Behind — progress lag",IF(AND(X396-TODAY()<=30,X396-TODAY()>=0,OR(Z396="",Z396<90)),"At risk — close to off track","On track")))))))) | IF(OR(F396="",AC396="Completed / Handover",AC396="Cancelled"),"",IF(O396="Not awarded",IF(U396<>"",U396-TODAY(),IF(X396="","",X396-TODAY())),IF(X396="","",X396-TODAY()))) | [14 empty] | IF(OR(F396="",AJ396=""),"",IF(COUNT(AI396:AI396)=0,"",AJ396-LOOKUP(2,1/(AI396:AI396<>""),AI396:AI396))) | IF(OR(F396="",AK396=""),"",IF(COUNT(AI396:AJ396)=0,"",AK396-LOOKUP(2,1/(AI396:AJ396<>""),AI396:AJ396))) | IF(OR(F396="",AL396=""),"",IF(COUNT(AI396:AK396)=0,"",AL396-LOOKUP(2,1/(AI396:AK396<>""),AI396:AK396))) | IF(OR(F396="",AM396=""),"",IF(COUNT(AI396:AL396)=0,"",AM396-LOOKUP(2,1/(AI396:AL396<>""),AI396:AL396))) | IF(OR(F396="",AN396=""),"",IF(COUNT(AI396:AM396)=0,"",AN396-LOOKUP(2,1/(AI396:AM396<>""),AI396:AM396))) | IF(OR(F396="",AO396=""),"",IF(COUNT(AI396:AN396)=0,"",AO396-LOOKUP(2,1/(AI396:AN396<>""),AI396:AN396))) | IF(OR(F396="",AP396=""),"",IF(COUNT(AI396:AO396)=0,"",AP396-LOOKUP(2,1/(AI396:AO396<>""),AI396:AO396))) | IF(OR(F396="",AQ396=""),"",IF(COUNT(AI396:AP396)=0,"",AQ396-LOOKUP(2,1/(AI396:AP396<>""),AI396:AP396))) | IF(OR(F396="",AR396=""),"",IF(COUNT(AI396:AQ396)=0,"",AR396-LOOKUP(2,1/(AI396:AQ396<>""),AI396:AQ396))) | IF(OR(F396="",AS396=""),"",IF(COUNT(AI396:AR396)=0,"",AS396-LOOKUP(2,1/(AI396:AR396<>""),AI396:AR396))) | IF(OR(F396="",AT396=""),"",IF(COUNT(AI396:AS396)=0,"",AT396-LOOKUP(2,1/(AI396:AS396<>""),AI396:AS396))) | IF(OR(F396="",AU396=""),"",IF(COUNT(AI396:AT396)=0,"",AU396-LOOKUP(2,1/(AI396:AT396<>""),AI396:AT396))) | IF(OR(F396="",AV396=""),"",IF(COUNT(AI396:AU396)=0,"",AV396-LOOKUP(2,1/(AI396:AU396<>""),AI396:AU396))) | IF(J396="","All_Provinces",IFERROR(VLOOKUP(J396,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K396="","All_Districts",IFERROR(VLOOKUP(K396,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F397="","",ROW()-3) | [18 empty] | IF(AQ397="","",AQ397) |  |  |  | IF(W397<>"",W397,IF(OR(T397="",V397=""),"",EDATE(T397,V397))) |  |  |  |  | IF(F397="","",IF(COUNT(AI397:AV397)=0,IF(AA397="","Not started",AA397),SUBSTITUTE(LOOKUP(2,1/(AI397:AV397<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F397="",COUNT(AI397:AV397)=0),"",TODAY()-LOOKUP(2,1/(AI397:AV397<>""),AI397:AV397)) | IF(OR(F397="",COUNT(AI397:AV397)<2),"",LOOKUP(2,1/(AI397:AV397<>""),AI397:AV397)-MIN(AI397:AV397)) | IF(OR(AD397="",AC397="Not started",AC397=""),"",IFERROR(AD397-IF(VLOOKUP(AC397,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC397,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F397="","",IF(OR(AA397="Cancelled",AC397="Cancelled"),"Cancelled",IF(OR(AC397="Completed / Handover",Y397<>"",Z397>=100),"Completed — on track",IF(O397="Not awarded",IF(U397="",IF(X397="","No planned date",IF(TODAY()>X397,"Behind — past planned date",IF(X397-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U397,"Behind — award date passed",IF(U397-TODAY()<=30,"At risk — close to off track","On track"))),IF(X397="","No planned date",IF(AND(TODAY()>X397,OR(Z397="",Z397<100)),"Behind — past end date",IF(AND(T397<>"",X397<>"",Z397<>"",(Z397<100),((TODAY()-T397)/MAX(X397-T397,1)*100)-Z397>15),"Behind — progress lag",IF(AND(X397-TODAY()<=30,X397-TODAY()>=0,OR(Z397="",Z397<90)),"At risk — close to off track","On track")))))))) | IF(OR(F397="",AC397="Completed / Handover",AC397="Cancelled"),"",IF(O397="Not awarded",IF(U397<>"",U397-TODAY(),IF(X397="","",X397-TODAY())),IF(X397="","",X397-TODAY()))) | [14 empty] | IF(OR(F397="",AJ397=""),"",IF(COUNT(AI397:AI397)=0,"",AJ397-LOOKUP(2,1/(AI397:AI397<>""),AI397:AI397))) | IF(OR(F397="",AK397=""),"",IF(COUNT(AI397:AJ397)=0,"",AK397-LOOKUP(2,1/(AI397:AJ397<>""),AI397:AJ397))) | IF(OR(F397="",AL397=""),"",IF(COUNT(AI397:AK397)=0,"",AL397-LOOKUP(2,1/(AI397:AK397<>""),AI397:AK397))) | IF(OR(F397="",AM397=""),"",IF(COUNT(AI397:AL397)=0,"",AM397-LOOKUP(2,1/(AI397:AL397<>""),AI397:AL397))) | IF(OR(F397="",AN397=""),"",IF(COUNT(AI397:AM397)=0,"",AN397-LOOKUP(2,1/(AI397:AM397<>""),AI397:AM397))) | IF(OR(F397="",AO397=""),"",IF(COUNT(AI397:AN397)=0,"",AO397-LOOKUP(2,1/(AI397:AN397<>""),AI397:AN397))) | IF(OR(F397="",AP397=""),"",IF(COUNT(AI397:AO397)=0,"",AP397-LOOKUP(2,1/(AI397:AO397<>""),AI397:AO397))) | IF(OR(F397="",AQ397=""),"",IF(COUNT(AI397:AP397)=0,"",AQ397-LOOKUP(2,1/(AI397:AP397<>""),AI397:AP397))) | IF(OR(F397="",AR397=""),"",IF(COUNT(AI397:AQ397)=0,"",AR397-LOOKUP(2,1/(AI397:AQ397<>""),AI397:AQ397))) | IF(OR(F397="",AS397=""),"",IF(COUNT(AI397:AR397)=0,"",AS397-LOOKUP(2,1/(AI397:AR397<>""),AI397:AR397))) | IF(OR(F397="",AT397=""),"",IF(COUNT(AI397:AS397)=0,"",AT397-LOOKUP(2,1/(AI397:AS397<>""),AI397:AS397))) | IF(OR(F397="",AU397=""),"",IF(COUNT(AI397:AT397)=0,"",AU397-LOOKUP(2,1/(AI397:AT397<>""),AI397:AT397))) | IF(OR(F397="",AV397=""),"",IF(COUNT(AI397:AU397)=0,"",AV397-LOOKUP(2,1/(AI397:AU397<>""),AI397:AU397))) | IF(J397="","All_Provinces",IFERROR(VLOOKUP(J397,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K397="","All_Districts",IFERROR(VLOOKUP(K397,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F398="","",ROW()-3) | [18 empty] | IF(AQ398="","",AQ398) |  |  |  | IF(W398<>"",W398,IF(OR(T398="",V398=""),"",EDATE(T398,V398))) |  |  |  |  | IF(F398="","",IF(COUNT(AI398:AV398)=0,IF(AA398="","Not started",AA398),SUBSTITUTE(LOOKUP(2,1/(AI398:AV398<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F398="",COUNT(AI398:AV398)=0),"",TODAY()-LOOKUP(2,1/(AI398:AV398<>""),AI398:AV398)) | IF(OR(F398="",COUNT(AI398:AV398)<2),"",LOOKUP(2,1/(AI398:AV398<>""),AI398:AV398)-MIN(AI398:AV398)) | IF(OR(AD398="",AC398="Not started",AC398=""),"",IFERROR(AD398-IF(VLOOKUP(AC398,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC398,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F398="","",IF(OR(AA398="Cancelled",AC398="Cancelled"),"Cancelled",IF(OR(AC398="Completed / Handover",Y398<>"",Z398>=100),"Completed — on track",IF(O398="Not awarded",IF(U398="",IF(X398="","No planned date",IF(TODAY()>X398,"Behind — past planned date",IF(X398-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U398,"Behind — award date passed",IF(U398-TODAY()<=30,"At risk — close to off track","On track"))),IF(X398="","No planned date",IF(AND(TODAY()>X398,OR(Z398="",Z398<100)),"Behind — past end date",IF(AND(T398<>"",X398<>"",Z398<>"",(Z398<100),((TODAY()-T398)/MAX(X398-T398,1)*100)-Z398>15),"Behind — progress lag",IF(AND(X398-TODAY()<=30,X398-TODAY()>=0,OR(Z398="",Z398<90)),"At risk — close to off track","On track")))))))) | IF(OR(F398="",AC398="Completed / Handover",AC398="Cancelled"),"",IF(O398="Not awarded",IF(U398<>"",U398-TODAY(),IF(X398="","",X398-TODAY())),IF(X398="","",X398-TODAY()))) | [14 empty] | IF(OR(F398="",AJ398=""),"",IF(COUNT(AI398:AI398)=0,"",AJ398-LOOKUP(2,1/(AI398:AI398<>""),AI398:AI398))) | IF(OR(F398="",AK398=""),"",IF(COUNT(AI398:AJ398)=0,"",AK398-LOOKUP(2,1/(AI398:AJ398<>""),AI398:AJ398))) | IF(OR(F398="",AL398=""),"",IF(COUNT(AI398:AK398)=0,"",AL398-LOOKUP(2,1/(AI398:AK398<>""),AI398:AK398))) | IF(OR(F398="",AM398=""),"",IF(COUNT(AI398:AL398)=0,"",AM398-LOOKUP(2,1/(AI398:AL398<>""),AI398:AL398))) | IF(OR(F398="",AN398=""),"",IF(COUNT(AI398:AM398)=0,"",AN398-LOOKUP(2,1/(AI398:AM398<>""),AI398:AM398))) | IF(OR(F398="",AO398=""),"",IF(COUNT(AI398:AN398)=0,"",AO398-LOOKUP(2,1/(AI398:AN398<>""),AI398:AN398))) | IF(OR(F398="",AP398=""),"",IF(COUNT(AI398:AO398)=0,"",AP398-LOOKUP(2,1/(AI398:AO398<>""),AI398:AO398))) | IF(OR(F398="",AQ398=""),"",IF(COUNT(AI398:AP398)=0,"",AQ398-LOOKUP(2,1/(AI398:AP398<>""),AI398:AP398))) | IF(OR(F398="",AR398=""),"",IF(COUNT(AI398:AQ398)=0,"",AR398-LOOKUP(2,1/(AI398:AQ398<>""),AI398:AQ398))) | IF(OR(F398="",AS398=""),"",IF(COUNT(AI398:AR398)=0,"",AS398-LOOKUP(2,1/(AI398:AR398<>""),AI398:AR398))) | IF(OR(F398="",AT398=""),"",IF(COUNT(AI398:AS398)=0,"",AT398-LOOKUP(2,1/(AI398:AS398<>""),AI398:AS398))) | IF(OR(F398="",AU398=""),"",IF(COUNT(AI398:AT398)=0,"",AU398-LOOKUP(2,1/(AI398:AT398<>""),AI398:AT398))) | IF(OR(F398="",AV398=""),"",IF(COUNT(AI398:AU398)=0,"",AV398-LOOKUP(2,1/(AI398:AU398<>""),AI398:AU398))) | IF(J398="","All_Provinces",IFERROR(VLOOKUP(J398,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K398="","All_Districts",IFERROR(VLOOKUP(K398,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F399="","",ROW()-3) | [18 empty] | IF(AQ399="","",AQ399) |  |  |  | IF(W399<>"",W399,IF(OR(T399="",V399=""),"",EDATE(T399,V399))) |  |  |  |  | IF(F399="","",IF(COUNT(AI399:AV399)=0,IF(AA399="","Not started",AA399),SUBSTITUTE(LOOKUP(2,1/(AI399:AV399<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F399="",COUNT(AI399:AV399)=0),"",TODAY()-LOOKUP(2,1/(AI399:AV399<>""),AI399:AV399)) | IF(OR(F399="",COUNT(AI399:AV399)<2),"",LOOKUP(2,1/(AI399:AV399<>""),AI399:AV399)-MIN(AI399:AV399)) | IF(OR(AD399="",AC399="Not started",AC399=""),"",IFERROR(AD399-IF(VLOOKUP(AC399,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC399,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F399="","",IF(OR(AA399="Cancelled",AC399="Cancelled"),"Cancelled",IF(OR(AC399="Completed / Handover",Y399<>"",Z399>=100),"Completed — on track",IF(O399="Not awarded",IF(U399="",IF(X399="","No planned date",IF(TODAY()>X399,"Behind — past planned date",IF(X399-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U399,"Behind — award date passed",IF(U399-TODAY()<=30,"At risk — close to off track","On track"))),IF(X399="","No planned date",IF(AND(TODAY()>X399,OR(Z399="",Z399<100)),"Behind — past end date",IF(AND(T399<>"",X399<>"",Z399<>"",(Z399<100),((TODAY()-T399)/MAX(X399-T399,1)*100)-Z399>15),"Behind — progress lag",IF(AND(X399-TODAY()<=30,X399-TODAY()>=0,OR(Z399="",Z399<90)),"At risk — close to off track","On track")))))))) | IF(OR(F399="",AC399="Completed / Handover",AC399="Cancelled"),"",IF(O399="Not awarded",IF(U399<>"",U399-TODAY(),IF(X399="","",X399-TODAY())),IF(X399="","",X399-TODAY()))) | [14 empty] | IF(OR(F399="",AJ399=""),"",IF(COUNT(AI399:AI399)=0,"",AJ399-LOOKUP(2,1/(AI399:AI399<>""),AI399:AI399))) | IF(OR(F399="",AK399=""),"",IF(COUNT(AI399:AJ399)=0,"",AK399-LOOKUP(2,1/(AI399:AJ399<>""),AI399:AJ399))) | IF(OR(F399="",AL399=""),"",IF(COUNT(AI399:AK399)=0,"",AL399-LOOKUP(2,1/(AI399:AK399<>""),AI399:AK399))) | IF(OR(F399="",AM399=""),"",IF(COUNT(AI399:AL399)=0,"",AM399-LOOKUP(2,1/(AI399:AL399<>""),AI399:AL399))) | IF(OR(F399="",AN399=""),"",IF(COUNT(AI399:AM399)=0,"",AN399-LOOKUP(2,1/(AI399:AM399<>""),AI399:AM399))) | IF(OR(F399="",AO399=""),"",IF(COUNT(AI399:AN399)=0,"",AO399-LOOKUP(2,1/(AI399:AN399<>""),AI399:AN399))) | IF(OR(F399="",AP399=""),"",IF(COUNT(AI399:AO399)=0,"",AP399-LOOKUP(2,1/(AI399:AO399<>""),AI399:AO399))) | IF(OR(F399="",AQ399=""),"",IF(COUNT(AI399:AP399)=0,"",AQ399-LOOKUP(2,1/(AI399:AP399<>""),AI399:AP399))) | IF(OR(F399="",AR399=""),"",IF(COUNT(AI399:AQ399)=0,"",AR399-LOOKUP(2,1/(AI399:AQ399<>""),AI399:AQ399))) | IF(OR(F399="",AS399=""),"",IF(COUNT(AI399:AR399)=0,"",AS399-LOOKUP(2,1/(AI399:AR399<>""),AI399:AR399))) | IF(OR(F399="",AT399=""),"",IF(COUNT(AI399:AS399)=0,"",AT399-LOOKUP(2,1/(AI399:AS399<>""),AI399:AS399))) | IF(OR(F399="",AU399=""),"",IF(COUNT(AI399:AT399)=0,"",AU399-LOOKUP(2,1/(AI399:AT399<>""),AI399:AT399))) | IF(OR(F399="",AV399=""),"",IF(COUNT(AI399:AU399)=0,"",AV399-LOOKUP(2,1/(AI399:AU399<>""),AI399:AU399))) | IF(J399="","All_Provinces",IFERROR(VLOOKUP(J399,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K399="","All_Districts",IFERROR(VLOOKUP(K399,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F400="","",ROW()-3) | [18 empty] | IF(AQ400="","",AQ400) |  |  |  | IF(W400<>"",W400,IF(OR(T400="",V400=""),"",EDATE(T400,V400))) |  |  |  |  | IF(F400="","",IF(COUNT(AI400:AV400)=0,IF(AA400="","Not started",AA400),SUBSTITUTE(LOOKUP(2,1/(AI400:AV400<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F400="",COUNT(AI400:AV400)=0),"",TODAY()-LOOKUP(2,1/(AI400:AV400<>""),AI400:AV400)) | IF(OR(F400="",COUNT(AI400:AV400)<2),"",LOOKUP(2,1/(AI400:AV400<>""),AI400:AV400)-MIN(AI400:AV400)) | IF(OR(AD400="",AC400="Not started",AC400=""),"",IFERROR(AD400-IF(VLOOKUP(AC400,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC400,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F400="","",IF(OR(AA400="Cancelled",AC400="Cancelled"),"Cancelled",IF(OR(AC400="Completed / Handover",Y400<>"",Z400>=100),"Completed — on track",IF(O400="Not awarded",IF(U400="",IF(X400="","No planned date",IF(TODAY()>X400,"Behind — past planned date",IF(X400-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U400,"Behind — award date passed",IF(U400-TODAY()<=30,"At risk — close to off track","On track"))),IF(X400="","No planned date",IF(AND(TODAY()>X400,OR(Z400="",Z400<100)),"Behind — past end date",IF(AND(T400<>"",X400<>"",Z400<>"",(Z400<100),((TODAY()-T400)/MAX(X400-T400,1)*100)-Z400>15),"Behind — progress lag",IF(AND(X400-TODAY()<=30,X400-TODAY()>=0,OR(Z400="",Z400<90)),"At risk — close to off track","On track")))))))) | IF(OR(F400="",AC400="Completed / Handover",AC400="Cancelled"),"",IF(O400="Not awarded",IF(U400<>"",U400-TODAY(),IF(X400="","",X400-TODAY())),IF(X400="","",X400-TODAY()))) | [14 empty] | IF(OR(F400="",AJ400=""),"",IF(COUNT(AI400:AI400)=0,"",AJ400-LOOKUP(2,1/(AI400:AI400<>""),AI400:AI400))) | IF(OR(F400="",AK400=""),"",IF(COUNT(AI400:AJ400)=0,"",AK400-LOOKUP(2,1/(AI400:AJ400<>""),AI400:AJ400))) | IF(OR(F400="",AL400=""),"",IF(COUNT(AI400:AK400)=0,"",AL400-LOOKUP(2,1/(AI400:AK400<>""),AI400:AK400))) | IF(OR(F400="",AM400=""),"",IF(COUNT(AI400:AL400)=0,"",AM400-LOOKUP(2,1/(AI400:AL400<>""),AI400:AL400))) | IF(OR(F400="",AN400=""),"",IF(COUNT(AI400:AM400)=0,"",AN400-LOOKUP(2,1/(AI400:AM400<>""),AI400:AM400))) | IF(OR(F400="",AO400=""),"",IF(COUNT(AI400:AN400)=0,"",AO400-LOOKUP(2,1/(AI400:AN400<>""),AI400:AN400))) | IF(OR(F400="",AP400=""),"",IF(COUNT(AI400:AO400)=0,"",AP400-LOOKUP(2,1/(AI400:AO400<>""),AI400:AO400))) | IF(OR(F400="",AQ400=""),"",IF(COUNT(AI400:AP400)=0,"",AQ400-LOOKUP(2,1/(AI400:AP400<>""),AI400:AP400))) | IF(OR(F400="",AR400=""),"",IF(COUNT(AI400:AQ400)=0,"",AR400-LOOKUP(2,1/(AI400:AQ400<>""),AI400:AQ400))) | IF(OR(F400="",AS400=""),"",IF(COUNT(AI400:AR400)=0,"",AS400-LOOKUP(2,1/(AI400:AR400<>""),AI400:AR400))) | IF(OR(F400="",AT400=""),"",IF(COUNT(AI400:AS400)=0,"",AT400-LOOKUP(2,1/(AI400:AS400<>""),AI400:AS400))) | IF(OR(F400="",AU400=""),"",IF(COUNT(AI400:AT400)=0,"",AU400-LOOKUP(2,1/(AI400:AT400<>""),AI400:AT400))) | IF(OR(F400="",AV400=""),"",IF(COUNT(AI400:AU400)=0,"",AV400-LOOKUP(2,1/(AI400:AU400<>""),AI400:AU400))) | IF(J400="","All_Provinces",IFERROR(VLOOKUP(J400,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K400="","All_Districts",IFERROR(VLOOKUP(K400,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F401="","",ROW()-3) | [18 empty] | IF(AQ401="","",AQ401) |  |  |  | IF(W401<>"",W401,IF(OR(T401="",V401=""),"",EDATE(T401,V401))) |  |  |  |  | IF(F401="","",IF(COUNT(AI401:AV401)=0,IF(AA401="","Not started",AA401),SUBSTITUTE(LOOKUP(2,1/(AI401:AV401<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F401="",COUNT(AI401:AV401)=0),"",TODAY()-LOOKUP(2,1/(AI401:AV401<>""),AI401:AV401)) | IF(OR(F401="",COUNT(AI401:AV401)<2),"",LOOKUP(2,1/(AI401:AV401<>""),AI401:AV401)-MIN(AI401:AV401)) | IF(OR(AD401="",AC401="Not started",AC401=""),"",IFERROR(AD401-IF(VLOOKUP(AC401,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC401,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F401="","",IF(OR(AA401="Cancelled",AC401="Cancelled"),"Cancelled",IF(OR(AC401="Completed / Handover",Y401<>"",Z401>=100),"Completed — on track",IF(O401="Not awarded",IF(U401="",IF(X401="","No planned date",IF(TODAY()>X401,"Behind — past planned date",IF(X401-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U401,"Behind — award date passed",IF(U401-TODAY()<=30,"At risk — close to off track","On track"))),IF(X401="","No planned date",IF(AND(TODAY()>X401,OR(Z401="",Z401<100)),"Behind — past end date",IF(AND(T401<>"",X401<>"",Z401<>"",(Z401<100),((TODAY()-T401)/MAX(X401-T401,1)*100)-Z401>15),"Behind — progress lag",IF(AND(X401-TODAY()<=30,X401-TODAY()>=0,OR(Z401="",Z401<90)),"At risk — close to off track","On track")))))))) | IF(OR(F401="",AC401="Completed / Handover",AC401="Cancelled"),"",IF(O401="Not awarded",IF(U401<>"",U401-TODAY(),IF(X401="","",X401-TODAY())),IF(X401="","",X401-TODAY()))) | [14 empty] | IF(OR(F401="",AJ401=""),"",IF(COUNT(AI401:AI401)=0,"",AJ401-LOOKUP(2,1/(AI401:AI401<>""),AI401:AI401))) | IF(OR(F401="",AK401=""),"",IF(COUNT(AI401:AJ401)=0,"",AK401-LOOKUP(2,1/(AI401:AJ401<>""),AI401:AJ401))) | IF(OR(F401="",AL401=""),"",IF(COUNT(AI401:AK401)=0,"",AL401-LOOKUP(2,1/(AI401:AK401<>""),AI401:AK401))) | IF(OR(F401="",AM401=""),"",IF(COUNT(AI401:AL401)=0,"",AM401-LOOKUP(2,1/(AI401:AL401<>""),AI401:AL401))) | IF(OR(F401="",AN401=""),"",IF(COUNT(AI401:AM401)=0,"",AN401-LOOKUP(2,1/(AI401:AM401<>""),AI401:AM401))) | IF(OR(F401="",AO401=""),"",IF(COUNT(AI401:AN401)=0,"",AO401-LOOKUP(2,1/(AI401:AN401<>""),AI401:AN401))) | IF(OR(F401="",AP401=""),"",IF(COUNT(AI401:AO401)=0,"",AP401-LOOKUP(2,1/(AI401:AO401<>""),AI401:AO401))) | IF(OR(F401="",AQ401=""),"",IF(COUNT(AI401:AP401)=0,"",AQ401-LOOKUP(2,1/(AI401:AP401<>""),AI401:AP401))) | IF(OR(F401="",AR401=""),"",IF(COUNT(AI401:AQ401)=0,"",AR401-LOOKUP(2,1/(AI401:AQ401<>""),AI401:AQ401))) | IF(OR(F401="",AS401=""),"",IF(COUNT(AI401:AR401)=0,"",AS401-LOOKUP(2,1/(AI401:AR401<>""),AI401:AR401))) | IF(OR(F401="",AT401=""),"",IF(COUNT(AI401:AS401)=0,"",AT401-LOOKUP(2,1/(AI401:AS401<>""),AI401:AS401))) | IF(OR(F401="",AU401=""),"",IF(COUNT(AI401:AT401)=0,"",AU401-LOOKUP(2,1/(AI401:AT401<>""),AI401:AT401))) | IF(OR(F401="",AV401=""),"",IF(COUNT(AI401:AU401)=0,"",AV401-LOOKUP(2,1/(AI401:AU401<>""),AI401:AU401))) | IF(J401="","All_Provinces",IFERROR(VLOOKUP(J401,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K401="","All_Districts",IFERROR(VLOOKUP(K401,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F402="","",ROW()-3) | [18 empty] | IF(AQ402="","",AQ402) |  |  |  | IF(W402<>"",W402,IF(OR(T402="",V402=""),"",EDATE(T402,V402))) |  |  |  |  | IF(F402="","",IF(COUNT(AI402:AV402)=0,IF(AA402="","Not started",AA402),SUBSTITUTE(LOOKUP(2,1/(AI402:AV402<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F402="",COUNT(AI402:AV402)=0),"",TODAY()-LOOKUP(2,1/(AI402:AV402<>""),AI402:AV402)) | IF(OR(F402="",COUNT(AI402:AV402)<2),"",LOOKUP(2,1/(AI402:AV402<>""),AI402:AV402)-MIN(AI402:AV402)) | IF(OR(AD402="",AC402="Not started",AC402=""),"",IFERROR(AD402-IF(VLOOKUP(AC402,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC402,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F402="","",IF(OR(AA402="Cancelled",AC402="Cancelled"),"Cancelled",IF(OR(AC402="Completed / Handover",Y402<>"",Z402>=100),"Completed — on track",IF(O402="Not awarded",IF(U402="",IF(X402="","No planned date",IF(TODAY()>X402,"Behind — past planned date",IF(X402-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U402,"Behind — award date passed",IF(U402-TODAY()<=30,"At risk — close to off track","On track"))),IF(X402="","No planned date",IF(AND(TODAY()>X402,OR(Z402="",Z402<100)),"Behind — past end date",IF(AND(T402<>"",X402<>"",Z402<>"",(Z402<100),((TODAY()-T402)/MAX(X402-T402,1)*100)-Z402>15),"Behind — progress lag",IF(AND(X402-TODAY()<=30,X402-TODAY()>=0,OR(Z402="",Z402<90)),"At risk — close to off track","On track")))))))) | IF(OR(F402="",AC402="Completed / Handover",AC402="Cancelled"),"",IF(O402="Not awarded",IF(U402<>"",U402-TODAY(),IF(X402="","",X402-TODAY())),IF(X402="","",X402-TODAY()))) | [14 empty] | IF(OR(F402="",AJ402=""),"",IF(COUNT(AI402:AI402)=0,"",AJ402-LOOKUP(2,1/(AI402:AI402<>""),AI402:AI402))) | IF(OR(F402="",AK402=""),"",IF(COUNT(AI402:AJ402)=0,"",AK402-LOOKUP(2,1/(AI402:AJ402<>""),AI402:AJ402))) | IF(OR(F402="",AL402=""),"",IF(COUNT(AI402:AK402)=0,"",AL402-LOOKUP(2,1/(AI402:AK402<>""),AI402:AK402))) | IF(OR(F402="",AM402=""),"",IF(COUNT(AI402:AL402)=0,"",AM402-LOOKUP(2,1/(AI402:AL402<>""),AI402:AL402))) | IF(OR(F402="",AN402=""),"",IF(COUNT(AI402:AM402)=0,"",AN402-LOOKUP(2,1/(AI402:AM402<>""),AI402:AM402))) | IF(OR(F402="",AO402=""),"",IF(COUNT(AI402:AN402)=0,"",AO402-LOOKUP(2,1/(AI402:AN402<>""),AI402:AN402))) | IF(OR(F402="",AP402=""),"",IF(COUNT(AI402:AO402)=0,"",AP402-LOOKUP(2,1/(AI402:AO402<>""),AI402:AO402))) | IF(OR(F402="",AQ402=""),"",IF(COUNT(AI402:AP402)=0,"",AQ402-LOOKUP(2,1/(AI402:AP402<>""),AI402:AP402))) | IF(OR(F402="",AR402=""),"",IF(COUNT(AI402:AQ402)=0,"",AR402-LOOKUP(2,1/(AI402:AQ402<>""),AI402:AQ402))) | IF(OR(F402="",AS402=""),"",IF(COUNT(AI402:AR402)=0,"",AS402-LOOKUP(2,1/(AI402:AR402<>""),AI402:AR402))) | IF(OR(F402="",AT402=""),"",IF(COUNT(AI402:AS402)=0,"",AT402-LOOKUP(2,1/(AI402:AS402<>""),AI402:AS402))) | IF(OR(F402="",AU402=""),"",IF(COUNT(AI402:AT402)=0,"",AU402-LOOKUP(2,1/(AI402:AT402<>""),AI402:AT402))) | IF(OR(F402="",AV402=""),"",IF(COUNT(AI402:AU402)=0,"",AV402-LOOKUP(2,1/(AI402:AU402<>""),AI402:AU402))) | IF(J402="","All_Provinces",IFERROR(VLOOKUP(J402,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K402="","All_Districts",IFERROR(VLOOKUP(K402,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F403="","",ROW()-3) | [18 empty] | IF(AQ403="","",AQ403) |  |  |  | IF(W403<>"",W403,IF(OR(T403="",V403=""),"",EDATE(T403,V403))) |  |  |  |  | IF(F403="","",IF(COUNT(AI403:AV403)=0,IF(AA403="","Not started",AA403),SUBSTITUTE(LOOKUP(2,1/(AI403:AV403<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F403="",COUNT(AI403:AV403)=0),"",TODAY()-LOOKUP(2,1/(AI403:AV403<>""),AI403:AV403)) | IF(OR(F403="",COUNT(AI403:AV403)<2),"",LOOKUP(2,1/(AI403:AV403<>""),AI403:AV403)-MIN(AI403:AV403)) | IF(OR(AD403="",AC403="Not started",AC403=""),"",IFERROR(AD403-IF(VLOOKUP(AC403,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC403,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F403="","",IF(OR(AA403="Cancelled",AC403="Cancelled"),"Cancelled",IF(OR(AC403="Completed / Handover",Y403<>"",Z403>=100),"Completed — on track",IF(O403="Not awarded",IF(U403="",IF(X403="","No planned date",IF(TODAY()>X403,"Behind — past planned date",IF(X403-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U403,"Behind — award date passed",IF(U403-TODAY()<=30,"At risk — close to off track","On track"))),IF(X403="","No planned date",IF(AND(TODAY()>X403,OR(Z403="",Z403<100)),"Behind — past end date",IF(AND(T403<>"",X403<>"",Z403<>"",(Z403<100),((TODAY()-T403)/MAX(X403-T403,1)*100)-Z403>15),"Behind — progress lag",IF(AND(X403-TODAY()<=30,X403-TODAY()>=0,OR(Z403="",Z403<90)),"At risk — close to off track","On track")))))))) | IF(OR(F403="",AC403="Completed / Handover",AC403="Cancelled"),"",IF(O403="Not awarded",IF(U403<>"",U403-TODAY(),IF(X403="","",X403-TODAY())),IF(X403="","",X403-TODAY()))) | [14 empty] | IF(OR(F403="",AJ403=""),"",IF(COUNT(AI403:AI403)=0,"",AJ403-LOOKUP(2,1/(AI403:AI403<>""),AI403:AI403))) | IF(OR(F403="",AK403=""),"",IF(COUNT(AI403:AJ403)=0,"",AK403-LOOKUP(2,1/(AI403:AJ403<>""),AI403:AJ403))) | IF(OR(F403="",AL403=""),"",IF(COUNT(AI403:AK403)=0,"",AL403-LOOKUP(2,1/(AI403:AK403<>""),AI403:AK403))) | IF(OR(F403="",AM403=""),"",IF(COUNT(AI403:AL403)=0,"",AM403-LOOKUP(2,1/(AI403:AL403<>""),AI403:AL403))) | IF(OR(F403="",AN403=""),"",IF(COUNT(AI403:AM403)=0,"",AN403-LOOKUP(2,1/(AI403:AM403<>""),AI403:AM403))) | IF(OR(F403="",AO403=""),"",IF(COUNT(AI403:AN403)=0,"",AO403-LOOKUP(2,1/(AI403:AN403<>""),AI403:AN403))) | IF(OR(F403="",AP403=""),"",IF(COUNT(AI403:AO403)=0,"",AP403-LOOKUP(2,1/(AI403:AO403<>""),AI403:AO403))) | IF(OR(F403="",AQ403=""),"",IF(COUNT(AI403:AP403)=0,"",AQ403-LOOKUP(2,1/(AI403:AP403<>""),AI403:AP403))) | IF(OR(F403="",AR403=""),"",IF(COUNT(AI403:AQ403)=0,"",AR403-LOOKUP(2,1/(AI403:AQ403<>""),AI403:AQ403))) | IF(OR(F403="",AS403=""),"",IF(COUNT(AI403:AR403)=0,"",AS403-LOOKUP(2,1/(AI403:AR403<>""),AI403:AR403))) | IF(OR(F403="",AT403=""),"",IF(COUNT(AI403:AS403)=0,"",AT403-LOOKUP(2,1/(AI403:AS403<>""),AI403:AS403))) | IF(OR(F403="",AU403=""),"",IF(COUNT(AI403:AT403)=0,"",AU403-LOOKUP(2,1/(AI403:AT403<>""),AI403:AT403))) | IF(OR(F403="",AV403=""),"",IF(COUNT(AI403:AU403)=0,"",AV403-LOOKUP(2,1/(AI403:AU403<>""),AI403:AU403))) | IF(J403="","All_Provinces",IFERROR(VLOOKUP(J403,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K403="","All_Districts",IFERROR(VLOOKUP(K403,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F404="","",ROW()-3) | [18 empty] | IF(AQ404="","",AQ404) |  |  |  | IF(W404<>"",W404,IF(OR(T404="",V404=""),"",EDATE(T404,V404))) |  |  |  |  | IF(F404="","",IF(COUNT(AI404:AV404)=0,IF(AA404="","Not started",AA404),SUBSTITUTE(LOOKUP(2,1/(AI404:AV404<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F404="",COUNT(AI404:AV404)=0),"",TODAY()-LOOKUP(2,1/(AI404:AV404<>""),AI404:AV404)) | IF(OR(F404="",COUNT(AI404:AV404)<2),"",LOOKUP(2,1/(AI404:AV404<>""),AI404:AV404)-MIN(AI404:AV404)) | IF(OR(AD404="",AC404="Not started",AC404=""),"",IFERROR(AD404-IF(VLOOKUP(AC404,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC404,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F404="","",IF(OR(AA404="Cancelled",AC404="Cancelled"),"Cancelled",IF(OR(AC404="Completed / Handover",Y404<>"",Z404>=100),"Completed — on track",IF(O404="Not awarded",IF(U404="",IF(X404="","No planned date",IF(TODAY()>X404,"Behind — past planned date",IF(X404-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U404,"Behind — award date passed",IF(U404-TODAY()<=30,"At risk — close to off track","On track"))),IF(X404="","No planned date",IF(AND(TODAY()>X404,OR(Z404="",Z404<100)),"Behind — past end date",IF(AND(T404<>"",X404<>"",Z404<>"",(Z404<100),((TODAY()-T404)/MAX(X404-T404,1)*100)-Z404>15),"Behind — progress lag",IF(AND(X404-TODAY()<=30,X404-TODAY()>=0,OR(Z404="",Z404<90)),"At risk — close to off track","On track")))))))) | IF(OR(F404="",AC404="Completed / Handover",AC404="Cancelled"),"",IF(O404="Not awarded",IF(U404<>"",U404-TODAY(),IF(X404="","",X404-TODAY())),IF(X404="","",X404-TODAY()))) | [14 empty] | IF(OR(F404="",AJ404=""),"",IF(COUNT(AI404:AI404)=0,"",AJ404-LOOKUP(2,1/(AI404:AI404<>""),AI404:AI404))) | IF(OR(F404="",AK404=""),"",IF(COUNT(AI404:AJ404)=0,"",AK404-LOOKUP(2,1/(AI404:AJ404<>""),AI404:AJ404))) | IF(OR(F404="",AL404=""),"",IF(COUNT(AI404:AK404)=0,"",AL404-LOOKUP(2,1/(AI404:AK404<>""),AI404:AK404))) | IF(OR(F404="",AM404=""),"",IF(COUNT(AI404:AL404)=0,"",AM404-LOOKUP(2,1/(AI404:AL404<>""),AI404:AL404))) | IF(OR(F404="",AN404=""),"",IF(COUNT(AI404:AM404)=0,"",AN404-LOOKUP(2,1/(AI404:AM404<>""),AI404:AM404))) | IF(OR(F404="",AO404=""),"",IF(COUNT(AI404:AN404)=0,"",AO404-LOOKUP(2,1/(AI404:AN404<>""),AI404:AN404))) | IF(OR(F404="",AP404=""),"",IF(COUNT(AI404:AO404)=0,"",AP404-LOOKUP(2,1/(AI404:AO404<>""),AI404:AO404))) | IF(OR(F404="",AQ404=""),"",IF(COUNT(AI404:AP404)=0,"",AQ404-LOOKUP(2,1/(AI404:AP404<>""),AI404:AP404))) | IF(OR(F404="",AR404=""),"",IF(COUNT(AI404:AQ404)=0,"",AR404-LOOKUP(2,1/(AI404:AQ404<>""),AI404:AQ404))) | IF(OR(F404="",AS404=""),"",IF(COUNT(AI404:AR404)=0,"",AS404-LOOKUP(2,1/(AI404:AR404<>""),AI404:AR404))) | IF(OR(F404="",AT404=""),"",IF(COUNT(AI404:AS404)=0,"",AT404-LOOKUP(2,1/(AI404:AS404<>""),AI404:AS404))) | IF(OR(F404="",AU404=""),"",IF(COUNT(AI404:AT404)=0,"",AU404-LOOKUP(2,1/(AI404:AT404<>""),AI404:AT404))) | IF(OR(F404="",AV404=""),"",IF(COUNT(AI404:AU404)=0,"",AV404-LOOKUP(2,1/(AI404:AU404<>""),AI404:AU404))) | IF(J404="","All_Provinces",IFERROR(VLOOKUP(J404,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K404="","All_Districts",IFERROR(VLOOKUP(K404,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F405="","",ROW()-3) | [18 empty] | IF(AQ405="","",AQ405) |  |  |  | IF(W405<>"",W405,IF(OR(T405="",V405=""),"",EDATE(T405,V405))) |  |  |  |  | IF(F405="","",IF(COUNT(AI405:AV405)=0,IF(AA405="","Not started",AA405),SUBSTITUTE(LOOKUP(2,1/(AI405:AV405<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F405="",COUNT(AI405:AV405)=0),"",TODAY()-LOOKUP(2,1/(AI405:AV405<>""),AI405:AV405)) | IF(OR(F405="",COUNT(AI405:AV405)<2),"",LOOKUP(2,1/(AI405:AV405<>""),AI405:AV405)-MIN(AI405:AV405)) | IF(OR(AD405="",AC405="Not started",AC405=""),"",IFERROR(AD405-IF(VLOOKUP(AC405,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC405,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F405="","",IF(OR(AA405="Cancelled",AC405="Cancelled"),"Cancelled",IF(OR(AC405="Completed / Handover",Y405<>"",Z405>=100),"Completed — on track",IF(O405="Not awarded",IF(U405="",IF(X405="","No planned date",IF(TODAY()>X405,"Behind — past planned date",IF(X405-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U405,"Behind — award date passed",IF(U405-TODAY()<=30,"At risk — close to off track","On track"))),IF(X405="","No planned date",IF(AND(TODAY()>X405,OR(Z405="",Z405<100)),"Behind — past end date",IF(AND(T405<>"",X405<>"",Z405<>"",(Z405<100),((TODAY()-T405)/MAX(X405-T405,1)*100)-Z405>15),"Behind — progress lag",IF(AND(X405-TODAY()<=30,X405-TODAY()>=0,OR(Z405="",Z405<90)),"At risk — close to off track","On track")))))))) | IF(OR(F405="",AC405="Completed / Handover",AC405="Cancelled"),"",IF(O405="Not awarded",IF(U405<>"",U405-TODAY(),IF(X405="","",X405-TODAY())),IF(X405="","",X405-TODAY()))) | [14 empty] | IF(OR(F405="",AJ405=""),"",IF(COUNT(AI405:AI405)=0,"",AJ405-LOOKUP(2,1/(AI405:AI405<>""),AI405:AI405))) | IF(OR(F405="",AK405=""),"",IF(COUNT(AI405:AJ405)=0,"",AK405-LOOKUP(2,1/(AI405:AJ405<>""),AI405:AJ405))) | IF(OR(F405="",AL405=""),"",IF(COUNT(AI405:AK405)=0,"",AL405-LOOKUP(2,1/(AI405:AK405<>""),AI405:AK405))) | IF(OR(F405="",AM405=""),"",IF(COUNT(AI405:AL405)=0,"",AM405-LOOKUP(2,1/(AI405:AL405<>""),AI405:AL405))) | IF(OR(F405="",AN405=""),"",IF(COUNT(AI405:AM405)=0,"",AN405-LOOKUP(2,1/(AI405:AM405<>""),AI405:AM405))) | IF(OR(F405="",AO405=""),"",IF(COUNT(AI405:AN405)=0,"",AO405-LOOKUP(2,1/(AI405:AN405<>""),AI405:AN405))) | IF(OR(F405="",AP405=""),"",IF(COUNT(AI405:AO405)=0,"",AP405-LOOKUP(2,1/(AI405:AO405<>""),AI405:AO405))) | IF(OR(F405="",AQ405=""),"",IF(COUNT(AI405:AP405)=0,"",AQ405-LOOKUP(2,1/(AI405:AP405<>""),AI405:AP405))) | IF(OR(F405="",AR405=""),"",IF(COUNT(AI405:AQ405)=0,"",AR405-LOOKUP(2,1/(AI405:AQ405<>""),AI405:AQ405))) | IF(OR(F405="",AS405=""),"",IF(COUNT(AI405:AR405)=0,"",AS405-LOOKUP(2,1/(AI405:AR405<>""),AI405:AR405))) | IF(OR(F405="",AT405=""),"",IF(COUNT(AI405:AS405)=0,"",AT405-LOOKUP(2,1/(AI405:AS405<>""),AI405:AS405))) | IF(OR(F405="",AU405=""),"",IF(COUNT(AI405:AT405)=0,"",AU405-LOOKUP(2,1/(AI405:AT405<>""),AI405:AT405))) | IF(OR(F405="",AV405=""),"",IF(COUNT(AI405:AU405)=0,"",AV405-LOOKUP(2,1/(AI405:AU405<>""),AI405:AU405))) | IF(J405="","All_Provinces",IFERROR(VLOOKUP(J405,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K405="","All_Districts",IFERROR(VLOOKUP(K405,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F406="","",ROW()-3) | [18 empty] | IF(AQ406="","",AQ406) |  |  |  | IF(W406<>"",W406,IF(OR(T406="",V406=""),"",EDATE(T406,V406))) |  |  |  |  | IF(F406="","",IF(COUNT(AI406:AV406)=0,IF(AA406="","Not started",AA406),SUBSTITUTE(LOOKUP(2,1/(AI406:AV406<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F406="",COUNT(AI406:AV406)=0),"",TODAY()-LOOKUP(2,1/(AI406:AV406<>""),AI406:AV406)) | IF(OR(F406="",COUNT(AI406:AV406)<2),"",LOOKUP(2,1/(AI406:AV406<>""),AI406:AV406)-MIN(AI406:AV406)) | IF(OR(AD406="",AC406="Not started",AC406=""),"",IFERROR(AD406-IF(VLOOKUP(AC406,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC406,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F406="","",IF(OR(AA406="Cancelled",AC406="Cancelled"),"Cancelled",IF(OR(AC406="Completed / Handover",Y406<>"",Z406>=100),"Completed — on track",IF(O406="Not awarded",IF(U406="",IF(X406="","No planned date",IF(TODAY()>X406,"Behind — past planned date",IF(X406-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U406,"Behind — award date passed",IF(U406-TODAY()<=30,"At risk — close to off track","On track"))),IF(X406="","No planned date",IF(AND(TODAY()>X406,OR(Z406="",Z406<100)),"Behind — past end date",IF(AND(T406<>"",X406<>"",Z406<>"",(Z406<100),((TODAY()-T406)/MAX(X406-T406,1)*100)-Z406>15),"Behind — progress lag",IF(AND(X406-TODAY()<=30,X406-TODAY()>=0,OR(Z406="",Z406<90)),"At risk — close to off track","On track")))))))) | IF(OR(F406="",AC406="Completed / Handover",AC406="Cancelled"),"",IF(O406="Not awarded",IF(U406<>"",U406-TODAY(),IF(X406="","",X406-TODAY())),IF(X406="","",X406-TODAY()))) | [14 empty] | IF(OR(F406="",AJ406=""),"",IF(COUNT(AI406:AI406)=0,"",AJ406-LOOKUP(2,1/(AI406:AI406<>""),AI406:AI406))) | IF(OR(F406="",AK406=""),"",IF(COUNT(AI406:AJ406)=0,"",AK406-LOOKUP(2,1/(AI406:AJ406<>""),AI406:AJ406))) | IF(OR(F406="",AL406=""),"",IF(COUNT(AI406:AK406)=0,"",AL406-LOOKUP(2,1/(AI406:AK406<>""),AI406:AK406))) | IF(OR(F406="",AM406=""),"",IF(COUNT(AI406:AL406)=0,"",AM406-LOOKUP(2,1/(AI406:AL406<>""),AI406:AL406))) | IF(OR(F406="",AN406=""),"",IF(COUNT(AI406:AM406)=0,"",AN406-LOOKUP(2,1/(AI406:AM406<>""),AI406:AM406))) | IF(OR(F406="",AO406=""),"",IF(COUNT(AI406:AN406)=0,"",AO406-LOOKUP(2,1/(AI406:AN406<>""),AI406:AN406))) | IF(OR(F406="",AP406=""),"",IF(COUNT(AI406:AO406)=0,"",AP406-LOOKUP(2,1/(AI406:AO406<>""),AI406:AO406))) | IF(OR(F406="",AQ406=""),"",IF(COUNT(AI406:AP406)=0,"",AQ406-LOOKUP(2,1/(AI406:AP406<>""),AI406:AP406))) | IF(OR(F406="",AR406=""),"",IF(COUNT(AI406:AQ406)=0,"",AR406-LOOKUP(2,1/(AI406:AQ406<>""),AI406:AQ406))) | IF(OR(F406="",AS406=""),"",IF(COUNT(AI406:AR406)=0,"",AS406-LOOKUP(2,1/(AI406:AR406<>""),AI406:AR406))) | IF(OR(F406="",AT406=""),"",IF(COUNT(AI406:AS406)=0,"",AT406-LOOKUP(2,1/(AI406:AS406<>""),AI406:AS406))) | IF(OR(F406="",AU406=""),"",IF(COUNT(AI406:AT406)=0,"",AU406-LOOKUP(2,1/(AI406:AT406<>""),AI406:AT406))) | IF(OR(F406="",AV406=""),"",IF(COUNT(AI406:AU406)=0,"",AV406-LOOKUP(2,1/(AI406:AU406<>""),AI406:AU406))) | IF(J406="","All_Provinces",IFERROR(VLOOKUP(J406,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K406="","All_Districts",IFERROR(VLOOKUP(K406,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F407="","",ROW()-3) | [18 empty] | IF(AQ407="","",AQ407) |  |  |  | IF(W407<>"",W407,IF(OR(T407="",V407=""),"",EDATE(T407,V407))) |  |  |  |  | IF(F407="","",IF(COUNT(AI407:AV407)=0,IF(AA407="","Not started",AA407),SUBSTITUTE(LOOKUP(2,1/(AI407:AV407<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F407="",COUNT(AI407:AV407)=0),"",TODAY()-LOOKUP(2,1/(AI407:AV407<>""),AI407:AV407)) | IF(OR(F407="",COUNT(AI407:AV407)<2),"",LOOKUP(2,1/(AI407:AV407<>""),AI407:AV407)-MIN(AI407:AV407)) | IF(OR(AD407="",AC407="Not started",AC407=""),"",IFERROR(AD407-IF(VLOOKUP(AC407,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC407,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F407="","",IF(OR(AA407="Cancelled",AC407="Cancelled"),"Cancelled",IF(OR(AC407="Completed / Handover",Y407<>"",Z407>=100),"Completed — on track",IF(O407="Not awarded",IF(U407="",IF(X407="","No planned date",IF(TODAY()>X407,"Behind — past planned date",IF(X407-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U407,"Behind — award date passed",IF(U407-TODAY()<=30,"At risk — close to off track","On track"))),IF(X407="","No planned date",IF(AND(TODAY()>X407,OR(Z407="",Z407<100)),"Behind — past end date",IF(AND(T407<>"",X407<>"",Z407<>"",(Z407<100),((TODAY()-T407)/MAX(X407-T407,1)*100)-Z407>15),"Behind — progress lag",IF(AND(X407-TODAY()<=30,X407-TODAY()>=0,OR(Z407="",Z407<90)),"At risk — close to off track","On track")))))))) | IF(OR(F407="",AC407="Completed / Handover",AC407="Cancelled"),"",IF(O407="Not awarded",IF(U407<>"",U407-TODAY(),IF(X407="","",X407-TODAY())),IF(X407="","",X407-TODAY()))) | [14 empty] | IF(OR(F407="",AJ407=""),"",IF(COUNT(AI407:AI407)=0,"",AJ407-LOOKUP(2,1/(AI407:AI407<>""),AI407:AI407))) | IF(OR(F407="",AK407=""),"",IF(COUNT(AI407:AJ407)=0,"",AK407-LOOKUP(2,1/(AI407:AJ407<>""),AI407:AJ407))) | IF(OR(F407="",AL407=""),"",IF(COUNT(AI407:AK407)=0,"",AL407-LOOKUP(2,1/(AI407:AK407<>""),AI407:AK407))) | IF(OR(F407="",AM407=""),"",IF(COUNT(AI407:AL407)=0,"",AM407-LOOKUP(2,1/(AI407:AL407<>""),AI407:AL407))) | IF(OR(F407="",AN407=""),"",IF(COUNT(AI407:AM407)=0,"",AN407-LOOKUP(2,1/(AI407:AM407<>""),AI407:AM407))) | IF(OR(F407="",AO407=""),"",IF(COUNT(AI407:AN407)=0,"",AO407-LOOKUP(2,1/(AI407:AN407<>""),AI407:AN407))) | IF(OR(F407="",AP407=""),"",IF(COUNT(AI407:AO407)=0,"",AP407-LOOKUP(2,1/(AI407:AO407<>""),AI407:AO407))) | IF(OR(F407="",AQ407=""),"",IF(COUNT(AI407:AP407)=0,"",AQ407-LOOKUP(2,1/(AI407:AP407<>""),AI407:AP407))) | IF(OR(F407="",AR407=""),"",IF(COUNT(AI407:AQ407)=0,"",AR407-LOOKUP(2,1/(AI407:AQ407<>""),AI407:AQ407))) | IF(OR(F407="",AS407=""),"",IF(COUNT(AI407:AR407)=0,"",AS407-LOOKUP(2,1/(AI407:AR407<>""),AI407:AR407))) | IF(OR(F407="",AT407=""),"",IF(COUNT(AI407:AS407)=0,"",AT407-LOOKUP(2,1/(AI407:AS407<>""),AI407:AS407))) | IF(OR(F407="",AU407=""),"",IF(COUNT(AI407:AT407)=0,"",AU407-LOOKUP(2,1/(AI407:AT407<>""),AI407:AT407))) | IF(OR(F407="",AV407=""),"",IF(COUNT(AI407:AU407)=0,"",AV407-LOOKUP(2,1/(AI407:AU407<>""),AI407:AU407))) | IF(J407="","All_Provinces",IFERROR(VLOOKUP(J407,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K407="","All_Districts",IFERROR(VLOOKUP(K407,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F408="","",ROW()-3) | [18 empty] | IF(AQ408="","",AQ408) |  |  |  | IF(W408<>"",W408,IF(OR(T408="",V408=""),"",EDATE(T408,V408))) |  |  |  |  | IF(F408="","",IF(COUNT(AI408:AV408)=0,IF(AA408="","Not started",AA408),SUBSTITUTE(LOOKUP(2,1/(AI408:AV408<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F408="",COUNT(AI408:AV408)=0),"",TODAY()-LOOKUP(2,1/(AI408:AV408<>""),AI408:AV408)) | IF(OR(F408="",COUNT(AI408:AV408)<2),"",LOOKUP(2,1/(AI408:AV408<>""),AI408:AV408)-MIN(AI408:AV408)) | IF(OR(AD408="",AC408="Not started",AC408=""),"",IFERROR(AD408-IF(VLOOKUP(AC408,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC408,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F408="","",IF(OR(AA408="Cancelled",AC408="Cancelled"),"Cancelled",IF(OR(AC408="Completed / Handover",Y408<>"",Z408>=100),"Completed — on track",IF(O408="Not awarded",IF(U408="",IF(X408="","No planned date",IF(TODAY()>X408,"Behind — past planned date",IF(X408-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U408,"Behind — award date passed",IF(U408-TODAY()<=30,"At risk — close to off track","On track"))),IF(X408="","No planned date",IF(AND(TODAY()>X408,OR(Z408="",Z408<100)),"Behind — past end date",IF(AND(T408<>"",X408<>"",Z408<>"",(Z408<100),((TODAY()-T408)/MAX(X408-T408,1)*100)-Z408>15),"Behind — progress lag",IF(AND(X408-TODAY()<=30,X408-TODAY()>=0,OR(Z408="",Z408<90)),"At risk — close to off track","On track")))))))) | IF(OR(F408="",AC408="Completed / Handover",AC408="Cancelled"),"",IF(O408="Not awarded",IF(U408<>"",U408-TODAY(),IF(X408="","",X408-TODAY())),IF(X408="","",X408-TODAY()))) | [14 empty] | IF(OR(F408="",AJ408=""),"",IF(COUNT(AI408:AI408)=0,"",AJ408-LOOKUP(2,1/(AI408:AI408<>""),AI408:AI408))) | IF(OR(F408="",AK408=""),"",IF(COUNT(AI408:AJ408)=0,"",AK408-LOOKUP(2,1/(AI408:AJ408<>""),AI408:AJ408))) | IF(OR(F408="",AL408=""),"",IF(COUNT(AI408:AK408)=0,"",AL408-LOOKUP(2,1/(AI408:AK408<>""),AI408:AK408))) | IF(OR(F408="",AM408=""),"",IF(COUNT(AI408:AL408)=0,"",AM408-LOOKUP(2,1/(AI408:AL408<>""),AI408:AL408))) | IF(OR(F408="",AN408=""),"",IF(COUNT(AI408:AM408)=0,"",AN408-LOOKUP(2,1/(AI408:AM408<>""),AI408:AM408))) | IF(OR(F408="",AO408=""),"",IF(COUNT(AI408:AN408)=0,"",AO408-LOOKUP(2,1/(AI408:AN408<>""),AI408:AN408))) | IF(OR(F408="",AP408=""),"",IF(COUNT(AI408:AO408)=0,"",AP408-LOOKUP(2,1/(AI408:AO408<>""),AI408:AO408))) | IF(OR(F408="",AQ408=""),"",IF(COUNT(AI408:AP408)=0,"",AQ408-LOOKUP(2,1/(AI408:AP408<>""),AI408:AP408))) | IF(OR(F408="",AR408=""),"",IF(COUNT(AI408:AQ408)=0,"",AR408-LOOKUP(2,1/(AI408:AQ408<>""),AI408:AQ408))) | IF(OR(F408="",AS408=""),"",IF(COUNT(AI408:AR408)=0,"",AS408-LOOKUP(2,1/(AI408:AR408<>""),AI408:AR408))) | IF(OR(F408="",AT408=""),"",IF(COUNT(AI408:AS408)=0,"",AT408-LOOKUP(2,1/(AI408:AS408<>""),AI408:AS408))) | IF(OR(F408="",AU408=""),"",IF(COUNT(AI408:AT408)=0,"",AU408-LOOKUP(2,1/(AI408:AT408<>""),AI408:AT408))) | IF(OR(F408="",AV408=""),"",IF(COUNT(AI408:AU408)=0,"",AV408-LOOKUP(2,1/(AI408:AU408<>""),AI408:AU408))) | IF(J408="","All_Provinces",IFERROR(VLOOKUP(J408,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K408="","All_Districts",IFERROR(VLOOKUP(K408,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F409="","",ROW()-3) | [18 empty] | IF(AQ409="","",AQ409) |  |  |  | IF(W409<>"",W409,IF(OR(T409="",V409=""),"",EDATE(T409,V409))) |  |  |  |  | IF(F409="","",IF(COUNT(AI409:AV409)=0,IF(AA409="","Not started",AA409),SUBSTITUTE(LOOKUP(2,1/(AI409:AV409<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F409="",COUNT(AI409:AV409)=0),"",TODAY()-LOOKUP(2,1/(AI409:AV409<>""),AI409:AV409)) | IF(OR(F409="",COUNT(AI409:AV409)<2),"",LOOKUP(2,1/(AI409:AV409<>""),AI409:AV409)-MIN(AI409:AV409)) | IF(OR(AD409="",AC409="Not started",AC409=""),"",IFERROR(AD409-IF(VLOOKUP(AC409,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC409,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F409="","",IF(OR(AA409="Cancelled",AC409="Cancelled"),"Cancelled",IF(OR(AC409="Completed / Handover",Y409<>"",Z409>=100),"Completed — on track",IF(O409="Not awarded",IF(U409="",IF(X409="","No planned date",IF(TODAY()>X409,"Behind — past planned date",IF(X409-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U409,"Behind — award date passed",IF(U409-TODAY()<=30,"At risk — close to off track","On track"))),IF(X409="","No planned date",IF(AND(TODAY()>X409,OR(Z409="",Z409<100)),"Behind — past end date",IF(AND(T409<>"",X409<>"",Z409<>"",(Z409<100),((TODAY()-T409)/MAX(X409-T409,1)*100)-Z409>15),"Behind — progress lag",IF(AND(X409-TODAY()<=30,X409-TODAY()>=0,OR(Z409="",Z409<90)),"At risk — close to off track","On track")))))))) | IF(OR(F409="",AC409="Completed / Handover",AC409="Cancelled"),"",IF(O409="Not awarded",IF(U409<>"",U409-TODAY(),IF(X409="","",X409-TODAY())),IF(X409="","",X409-TODAY()))) | [14 empty] | IF(OR(F409="",AJ409=""),"",IF(COUNT(AI409:AI409)=0,"",AJ409-LOOKUP(2,1/(AI409:AI409<>""),AI409:AI409))) | IF(OR(F409="",AK409=""),"",IF(COUNT(AI409:AJ409)=0,"",AK409-LOOKUP(2,1/(AI409:AJ409<>""),AI409:AJ409))) | IF(OR(F409="",AL409=""),"",IF(COUNT(AI409:AK409)=0,"",AL409-LOOKUP(2,1/(AI409:AK409<>""),AI409:AK409))) | IF(OR(F409="",AM409=""),"",IF(COUNT(AI409:AL409)=0,"",AM409-LOOKUP(2,1/(AI409:AL409<>""),AI409:AL409))) | IF(OR(F409="",AN409=""),"",IF(COUNT(AI409:AM409)=0,"",AN409-LOOKUP(2,1/(AI409:AM409<>""),AI409:AM409))) | IF(OR(F409="",AO409=""),"",IF(COUNT(AI409:AN409)=0,"",AO409-LOOKUP(2,1/(AI409:AN409<>""),AI409:AN409))) | IF(OR(F409="",AP409=""),"",IF(COUNT(AI409:AO409)=0,"",AP409-LOOKUP(2,1/(AI409:AO409<>""),AI409:AO409))) | IF(OR(F409="",AQ409=""),"",IF(COUNT(AI409:AP409)=0,"",AQ409-LOOKUP(2,1/(AI409:AP409<>""),AI409:AP409))) | IF(OR(F409="",AR409=""),"",IF(COUNT(AI409:AQ409)=0,"",AR409-LOOKUP(2,1/(AI409:AQ409<>""),AI409:AQ409))) | IF(OR(F409="",AS409=""),"",IF(COUNT(AI409:AR409)=0,"",AS409-LOOKUP(2,1/(AI409:AR409<>""),AI409:AR409))) | IF(OR(F409="",AT409=""),"",IF(COUNT(AI409:AS409)=0,"",AT409-LOOKUP(2,1/(AI409:AS409<>""),AI409:AS409))) | IF(OR(F409="",AU409=""),"",IF(COUNT(AI409:AT409)=0,"",AU409-LOOKUP(2,1/(AI409:AT409<>""),AI409:AT409))) | IF(OR(F409="",AV409=""),"",IF(COUNT(AI409:AU409)=0,"",AV409-LOOKUP(2,1/(AI409:AU409<>""),AI409:AU409))) | IF(J409="","All_Provinces",IFERROR(VLOOKUP(J409,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K409="","All_Districts",IFERROR(VLOOKUP(K409,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F410="","",ROW()-3) | [18 empty] | IF(AQ410="","",AQ410) |  |  |  | IF(W410<>"",W410,IF(OR(T410="",V410=""),"",EDATE(T410,V410))) |  |  |  |  | IF(F410="","",IF(COUNT(AI410:AV410)=0,IF(AA410="","Not started",AA410),SUBSTITUTE(LOOKUP(2,1/(AI410:AV410<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F410="",COUNT(AI410:AV410)=0),"",TODAY()-LOOKUP(2,1/(AI410:AV410<>""),AI410:AV410)) | IF(OR(F410="",COUNT(AI410:AV410)<2),"",LOOKUP(2,1/(AI410:AV410<>""),AI410:AV410)-MIN(AI410:AV410)) | IF(OR(AD410="",AC410="Not started",AC410=""),"",IFERROR(AD410-IF(VLOOKUP(AC410,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC410,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F410="","",IF(OR(AA410="Cancelled",AC410="Cancelled"),"Cancelled",IF(OR(AC410="Completed / Handover",Y410<>"",Z410>=100),"Completed — on track",IF(O410="Not awarded",IF(U410="",IF(X410="","No planned date",IF(TODAY()>X410,"Behind — past planned date",IF(X410-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U410,"Behind — award date passed",IF(U410-TODAY()<=30,"At risk — close to off track","On track"))),IF(X410="","No planned date",IF(AND(TODAY()>X410,OR(Z410="",Z410<100)),"Behind — past end date",IF(AND(T410<>"",X410<>"",Z410<>"",(Z410<100),((TODAY()-T410)/MAX(X410-T410,1)*100)-Z410>15),"Behind — progress lag",IF(AND(X410-TODAY()<=30,X410-TODAY()>=0,OR(Z410="",Z410<90)),"At risk — close to off track","On track")))))))) | IF(OR(F410="",AC410="Completed / Handover",AC410="Cancelled"),"",IF(O410="Not awarded",IF(U410<>"",U410-TODAY(),IF(X410="","",X410-TODAY())),IF(X410="","",X410-TODAY()))) | [14 empty] | IF(OR(F410="",AJ410=""),"",IF(COUNT(AI410:AI410)=0,"",AJ410-LOOKUP(2,1/(AI410:AI410<>""),AI410:AI410))) | IF(OR(F410="",AK410=""),"",IF(COUNT(AI410:AJ410)=0,"",AK410-LOOKUP(2,1/(AI410:AJ410<>""),AI410:AJ410))) | IF(OR(F410="",AL410=""),"",IF(COUNT(AI410:AK410)=0,"",AL410-LOOKUP(2,1/(AI410:AK410<>""),AI410:AK410))) | IF(OR(F410="",AM410=""),"",IF(COUNT(AI410:AL410)=0,"",AM410-LOOKUP(2,1/(AI410:AL410<>""),AI410:AL410))) | IF(OR(F410="",AN410=""),"",IF(COUNT(AI410:AM410)=0,"",AN410-LOOKUP(2,1/(AI410:AM410<>""),AI410:AM410))) | IF(OR(F410="",AO410=""),"",IF(COUNT(AI410:AN410)=0,"",AO410-LOOKUP(2,1/(AI410:AN410<>""),AI410:AN410))) | IF(OR(F410="",AP410=""),"",IF(COUNT(AI410:AO410)=0,"",AP410-LOOKUP(2,1/(AI410:AO410<>""),AI410:AO410))) | IF(OR(F410="",AQ410=""),"",IF(COUNT(AI410:AP410)=0,"",AQ410-LOOKUP(2,1/(AI410:AP410<>""),AI410:AP410))) | IF(OR(F410="",AR410=""),"",IF(COUNT(AI410:AQ410)=0,"",AR410-LOOKUP(2,1/(AI410:AQ410<>""),AI410:AQ410))) | IF(OR(F410="",AS410=""),"",IF(COUNT(AI410:AR410)=0,"",AS410-LOOKUP(2,1/(AI410:AR410<>""),AI410:AR410))) | IF(OR(F410="",AT410=""),"",IF(COUNT(AI410:AS410)=0,"",AT410-LOOKUP(2,1/(AI410:AS410<>""),AI410:AS410))) | IF(OR(F410="",AU410=""),"",IF(COUNT(AI410:AT410)=0,"",AU410-LOOKUP(2,1/(AI410:AT410<>""),AI410:AT410))) | IF(OR(F410="",AV410=""),"",IF(COUNT(AI410:AU410)=0,"",AV410-LOOKUP(2,1/(AI410:AU410<>""),AI410:AU410))) | IF(J410="","All_Provinces",IFERROR(VLOOKUP(J410,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K410="","All_Districts",IFERROR(VLOOKUP(K410,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F411="","",ROW()-3) | [18 empty] | IF(AQ411="","",AQ411) |  |  |  | IF(W411<>"",W411,IF(OR(T411="",V411=""),"",EDATE(T411,V411))) |  |  |  |  | IF(F411="","",IF(COUNT(AI411:AV411)=0,IF(AA411="","Not started",AA411),SUBSTITUTE(LOOKUP(2,1/(AI411:AV411<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F411="",COUNT(AI411:AV411)=0),"",TODAY()-LOOKUP(2,1/(AI411:AV411<>""),AI411:AV411)) | IF(OR(F411="",COUNT(AI411:AV411)<2),"",LOOKUP(2,1/(AI411:AV411<>""),AI411:AV411)-MIN(AI411:AV411)) | IF(OR(AD411="",AC411="Not started",AC411=""),"",IFERROR(AD411-IF(VLOOKUP(AC411,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC411,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F411="","",IF(OR(AA411="Cancelled",AC411="Cancelled"),"Cancelled",IF(OR(AC411="Completed / Handover",Y411<>"",Z411>=100),"Completed — on track",IF(O411="Not awarded",IF(U411="",IF(X411="","No planned date",IF(TODAY()>X411,"Behind — past planned date",IF(X411-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U411,"Behind — award date passed",IF(U411-TODAY()<=30,"At risk — close to off track","On track"))),IF(X411="","No planned date",IF(AND(TODAY()>X411,OR(Z411="",Z411<100)),"Behind — past end date",IF(AND(T411<>"",X411<>"",Z411<>"",(Z411<100),((TODAY()-T411)/MAX(X411-T411,1)*100)-Z411>15),"Behind — progress lag",IF(AND(X411-TODAY()<=30,X411-TODAY()>=0,OR(Z411="",Z411<90)),"At risk — close to off track","On track")))))))) | IF(OR(F411="",AC411="Completed / Handover",AC411="Cancelled"),"",IF(O411="Not awarded",IF(U411<>"",U411-TODAY(),IF(X411="","",X411-TODAY())),IF(X411="","",X411-TODAY()))) | [14 empty] | IF(OR(F411="",AJ411=""),"",IF(COUNT(AI411:AI411)=0,"",AJ411-LOOKUP(2,1/(AI411:AI411<>""),AI411:AI411))) | IF(OR(F411="",AK411=""),"",IF(COUNT(AI411:AJ411)=0,"",AK411-LOOKUP(2,1/(AI411:AJ411<>""),AI411:AJ411))) | IF(OR(F411="",AL411=""),"",IF(COUNT(AI411:AK411)=0,"",AL411-LOOKUP(2,1/(AI411:AK411<>""),AI411:AK411))) | IF(OR(F411="",AM411=""),"",IF(COUNT(AI411:AL411)=0,"",AM411-LOOKUP(2,1/(AI411:AL411<>""),AI411:AL411))) | IF(OR(F411="",AN411=""),"",IF(COUNT(AI411:AM411)=0,"",AN411-LOOKUP(2,1/(AI411:AM411<>""),AI411:AM411))) | IF(OR(F411="",AO411=""),"",IF(COUNT(AI411:AN411)=0,"",AO411-LOOKUP(2,1/(AI411:AN411<>""),AI411:AN411))) | IF(OR(F411="",AP411=""),"",IF(COUNT(AI411:AO411)=0,"",AP411-LOOKUP(2,1/(AI411:AO411<>""),AI411:AO411))) | IF(OR(F411="",AQ411=""),"",IF(COUNT(AI411:AP411)=0,"",AQ411-LOOKUP(2,1/(AI411:AP411<>""),AI411:AP411))) | IF(OR(F411="",AR411=""),"",IF(COUNT(AI411:AQ411)=0,"",AR411-LOOKUP(2,1/(AI411:AQ411<>""),AI411:AQ411))) | IF(OR(F411="",AS411=""),"",IF(COUNT(AI411:AR411)=0,"",AS411-LOOKUP(2,1/(AI411:AR411<>""),AI411:AR411))) | IF(OR(F411="",AT411=""),"",IF(COUNT(AI411:AS411)=0,"",AT411-LOOKUP(2,1/(AI411:AS411<>""),AI411:AS411))) | IF(OR(F411="",AU411=""),"",IF(COUNT(AI411:AT411)=0,"",AU411-LOOKUP(2,1/(AI411:AT411<>""),AI411:AT411))) | IF(OR(F411="",AV411=""),"",IF(COUNT(AI411:AU411)=0,"",AV411-LOOKUP(2,1/(AI411:AU411<>""),AI411:AU411))) | IF(J411="","All_Provinces",IFERROR(VLOOKUP(J411,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K411="","All_Districts",IFERROR(VLOOKUP(K411,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F412="","",ROW()-3) | [18 empty] | IF(AQ412="","",AQ412) |  |  |  | IF(W412<>"",W412,IF(OR(T412="",V412=""),"",EDATE(T412,V412))) |  |  |  |  | IF(F412="","",IF(COUNT(AI412:AV412)=0,IF(AA412="","Not started",AA412),SUBSTITUTE(LOOKUP(2,1/(AI412:AV412<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F412="",COUNT(AI412:AV412)=0),"",TODAY()-LOOKUP(2,1/(AI412:AV412<>""),AI412:AV412)) | IF(OR(F412="",COUNT(AI412:AV412)<2),"",LOOKUP(2,1/(AI412:AV412<>""),AI412:AV412)-MIN(AI412:AV412)) | IF(OR(AD412="",AC412="Not started",AC412=""),"",IFERROR(AD412-IF(VLOOKUP(AC412,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC412,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F412="","",IF(OR(AA412="Cancelled",AC412="Cancelled"),"Cancelled",IF(OR(AC412="Completed / Handover",Y412<>"",Z412>=100),"Completed — on track",IF(O412="Not awarded",IF(U412="",IF(X412="","No planned date",IF(TODAY()>X412,"Behind — past planned date",IF(X412-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U412,"Behind — award date passed",IF(U412-TODAY()<=30,"At risk — close to off track","On track"))),IF(X412="","No planned date",IF(AND(TODAY()>X412,OR(Z412="",Z412<100)),"Behind — past end date",IF(AND(T412<>"",X412<>"",Z412<>"",(Z412<100),((TODAY()-T412)/MAX(X412-T412,1)*100)-Z412>15),"Behind — progress lag",IF(AND(X412-TODAY()<=30,X412-TODAY()>=0,OR(Z412="",Z412<90)),"At risk — close to off track","On track")))))))) | IF(OR(F412="",AC412="Completed / Handover",AC412="Cancelled"),"",IF(O412="Not awarded",IF(U412<>"",U412-TODAY(),IF(X412="","",X412-TODAY())),IF(X412="","",X412-TODAY()))) | [14 empty] | IF(OR(F412="",AJ412=""),"",IF(COUNT(AI412:AI412)=0,"",AJ412-LOOKUP(2,1/(AI412:AI412<>""),AI412:AI412))) | IF(OR(F412="",AK412=""),"",IF(COUNT(AI412:AJ412)=0,"",AK412-LOOKUP(2,1/(AI412:AJ412<>""),AI412:AJ412))) | IF(OR(F412="",AL412=""),"",IF(COUNT(AI412:AK412)=0,"",AL412-LOOKUP(2,1/(AI412:AK412<>""),AI412:AK412))) | IF(OR(F412="",AM412=""),"",IF(COUNT(AI412:AL412)=0,"",AM412-LOOKUP(2,1/(AI412:AL412<>""),AI412:AL412))) | IF(OR(F412="",AN412=""),"",IF(COUNT(AI412:AM412)=0,"",AN412-LOOKUP(2,1/(AI412:AM412<>""),AI412:AM412))) | IF(OR(F412="",AO412=""),"",IF(COUNT(AI412:AN412)=0,"",AO412-LOOKUP(2,1/(AI412:AN412<>""),AI412:AN412))) | IF(OR(F412="",AP412=""),"",IF(COUNT(AI412:AO412)=0,"",AP412-LOOKUP(2,1/(AI412:AO412<>""),AI412:AO412))) | IF(OR(F412="",AQ412=""),"",IF(COUNT(AI412:AP412)=0,"",AQ412-LOOKUP(2,1/(AI412:AP412<>""),AI412:AP412))) | IF(OR(F412="",AR412=""),"",IF(COUNT(AI412:AQ412)=0,"",AR412-LOOKUP(2,1/(AI412:AQ412<>""),AI412:AQ412))) | IF(OR(F412="",AS412=""),"",IF(COUNT(AI412:AR412)=0,"",AS412-LOOKUP(2,1/(AI412:AR412<>""),AI412:AR412))) | IF(OR(F412="",AT412=""),"",IF(COUNT(AI412:AS412)=0,"",AT412-LOOKUP(2,1/(AI412:AS412<>""),AI412:AS412))) | IF(OR(F412="",AU412=""),"",IF(COUNT(AI412:AT412)=0,"",AU412-LOOKUP(2,1/(AI412:AT412<>""),AI412:AT412))) | IF(OR(F412="",AV412=""),"",IF(COUNT(AI412:AU412)=0,"",AV412-LOOKUP(2,1/(AI412:AU412<>""),AI412:AU412))) | IF(J412="","All_Provinces",IFERROR(VLOOKUP(J412,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K412="","All_Districts",IFERROR(VLOOKUP(K412,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F413="","",ROW()-3) | [18 empty] | IF(AQ413="","",AQ413) |  |  |  | IF(W413<>"",W413,IF(OR(T413="",V413=""),"",EDATE(T413,V413))) |  |  |  |  | IF(F413="","",IF(COUNT(AI413:AV413)=0,IF(AA413="","Not started",AA413),SUBSTITUTE(LOOKUP(2,1/(AI413:AV413<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F413="",COUNT(AI413:AV413)=0),"",TODAY()-LOOKUP(2,1/(AI413:AV413<>""),AI413:AV413)) | IF(OR(F413="",COUNT(AI413:AV413)<2),"",LOOKUP(2,1/(AI413:AV413<>""),AI413:AV413)-MIN(AI413:AV413)) | IF(OR(AD413="",AC413="Not started",AC413=""),"",IFERROR(AD413-IF(VLOOKUP(AC413,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC413,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F413="","",IF(OR(AA413="Cancelled",AC413="Cancelled"),"Cancelled",IF(OR(AC413="Completed / Handover",Y413<>"",Z413>=100),"Completed — on track",IF(O413="Not awarded",IF(U413="",IF(X413="","No planned date",IF(TODAY()>X413,"Behind — past planned date",IF(X413-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U413,"Behind — award date passed",IF(U413-TODAY()<=30,"At risk — close to off track","On track"))),IF(X413="","No planned date",IF(AND(TODAY()>X413,OR(Z413="",Z413<100)),"Behind — past end date",IF(AND(T413<>"",X413<>"",Z413<>"",(Z413<100),((TODAY()-T413)/MAX(X413-T413,1)*100)-Z413>15),"Behind — progress lag",IF(AND(X413-TODAY()<=30,X413-TODAY()>=0,OR(Z413="",Z413<90)),"At risk — close to off track","On track")))))))) | IF(OR(F413="",AC413="Completed / Handover",AC413="Cancelled"),"",IF(O413="Not awarded",IF(U413<>"",U413-TODAY(),IF(X413="","",X413-TODAY())),IF(X413="","",X413-TODAY()))) | [14 empty] | IF(OR(F413="",AJ413=""),"",IF(COUNT(AI413:AI413)=0,"",AJ413-LOOKUP(2,1/(AI413:AI413<>""),AI413:AI413))) | IF(OR(F413="",AK413=""),"",IF(COUNT(AI413:AJ413)=0,"",AK413-LOOKUP(2,1/(AI413:AJ413<>""),AI413:AJ413))) | IF(OR(F413="",AL413=""),"",IF(COUNT(AI413:AK413)=0,"",AL413-LOOKUP(2,1/(AI413:AK413<>""),AI413:AK413))) | IF(OR(F413="",AM413=""),"",IF(COUNT(AI413:AL413)=0,"",AM413-LOOKUP(2,1/(AI413:AL413<>""),AI413:AL413))) | IF(OR(F413="",AN413=""),"",IF(COUNT(AI413:AM413)=0,"",AN413-LOOKUP(2,1/(AI413:AM413<>""),AI413:AM413))) | IF(OR(F413="",AO413=""),"",IF(COUNT(AI413:AN413)=0,"",AO413-LOOKUP(2,1/(AI413:AN413<>""),AI413:AN413))) | IF(OR(F413="",AP413=""),"",IF(COUNT(AI413:AO413)=0,"",AP413-LOOKUP(2,1/(AI413:AO413<>""),AI413:AO413))) | IF(OR(F413="",AQ413=""),"",IF(COUNT(AI413:AP413)=0,"",AQ413-LOOKUP(2,1/(AI413:AP413<>""),AI413:AP413))) | IF(OR(F413="",AR413=""),"",IF(COUNT(AI413:AQ413)=0,"",AR413-LOOKUP(2,1/(AI413:AQ413<>""),AI413:AQ413))) | IF(OR(F413="",AS413=""),"",IF(COUNT(AI413:AR413)=0,"",AS413-LOOKUP(2,1/(AI413:AR413<>""),AI413:AR413))) | IF(OR(F413="",AT413=""),"",IF(COUNT(AI413:AS413)=0,"",AT413-LOOKUP(2,1/(AI413:AS413<>""),AI413:AS413))) | IF(OR(F413="",AU413=""),"",IF(COUNT(AI413:AT413)=0,"",AU413-LOOKUP(2,1/(AI413:AT413<>""),AI413:AT413))) | IF(OR(F413="",AV413=""),"",IF(COUNT(AI413:AU413)=0,"",AV413-LOOKUP(2,1/(AI413:AU413<>""),AI413:AU413))) | IF(J413="","All_Provinces",IFERROR(VLOOKUP(J413,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K413="","All_Districts",IFERROR(VLOOKUP(K413,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F414="","",ROW()-3) | [18 empty] | IF(AQ414="","",AQ414) |  |  |  | IF(W414<>"",W414,IF(OR(T414="",V414=""),"",EDATE(T414,V414))) |  |  |  |  | IF(F414="","",IF(COUNT(AI414:AV414)=0,IF(AA414="","Not started",AA414),SUBSTITUTE(LOOKUP(2,1/(AI414:AV414<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F414="",COUNT(AI414:AV414)=0),"",TODAY()-LOOKUP(2,1/(AI414:AV414<>""),AI414:AV414)) | IF(OR(F414="",COUNT(AI414:AV414)<2),"",LOOKUP(2,1/(AI414:AV414<>""),AI414:AV414)-MIN(AI414:AV414)) | IF(OR(AD414="",AC414="Not started",AC414=""),"",IFERROR(AD414-IF(VLOOKUP(AC414,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC414,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F414="","",IF(OR(AA414="Cancelled",AC414="Cancelled"),"Cancelled",IF(OR(AC414="Completed / Handover",Y414<>"",Z414>=100),"Completed — on track",IF(O414="Not awarded",IF(U414="",IF(X414="","No planned date",IF(TODAY()>X414,"Behind — past planned date",IF(X414-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U414,"Behind — award date passed",IF(U414-TODAY()<=30,"At risk — close to off track","On track"))),IF(X414="","No planned date",IF(AND(TODAY()>X414,OR(Z414="",Z414<100)),"Behind — past end date",IF(AND(T414<>"",X414<>"",Z414<>"",(Z414<100),((TODAY()-T414)/MAX(X414-T414,1)*100)-Z414>15),"Behind — progress lag",IF(AND(X414-TODAY()<=30,X414-TODAY()>=0,OR(Z414="",Z414<90)),"At risk — close to off track","On track")))))))) | IF(OR(F414="",AC414="Completed / Handover",AC414="Cancelled"),"",IF(O414="Not awarded",IF(U414<>"",U414-TODAY(),IF(X414="","",X414-TODAY())),IF(X414="","",X414-TODAY()))) | [14 empty] | IF(OR(F414="",AJ414=""),"",IF(COUNT(AI414:AI414)=0,"",AJ414-LOOKUP(2,1/(AI414:AI414<>""),AI414:AI414))) | IF(OR(F414="",AK414=""),"",IF(COUNT(AI414:AJ414)=0,"",AK414-LOOKUP(2,1/(AI414:AJ414<>""),AI414:AJ414))) | IF(OR(F414="",AL414=""),"",IF(COUNT(AI414:AK414)=0,"",AL414-LOOKUP(2,1/(AI414:AK414<>""),AI414:AK414))) | IF(OR(F414="",AM414=""),"",IF(COUNT(AI414:AL414)=0,"",AM414-LOOKUP(2,1/(AI414:AL414<>""),AI414:AL414))) | IF(OR(F414="",AN414=""),"",IF(COUNT(AI414:AM414)=0,"",AN414-LOOKUP(2,1/(AI414:AM414<>""),AI414:AM414))) | IF(OR(F414="",AO414=""),"",IF(COUNT(AI414:AN414)=0,"",AO414-LOOKUP(2,1/(AI414:AN414<>""),AI414:AN414))) | IF(OR(F414="",AP414=""),"",IF(COUNT(AI414:AO414)=0,"",AP414-LOOKUP(2,1/(AI414:AO414<>""),AI414:AO414))) | IF(OR(F414="",AQ414=""),"",IF(COUNT(AI414:AP414)=0,"",AQ414-LOOKUP(2,1/(AI414:AP414<>""),AI414:AP414))) | IF(OR(F414="",AR414=""),"",IF(COUNT(AI414:AQ414)=0,"",AR414-LOOKUP(2,1/(AI414:AQ414<>""),AI414:AQ414))) | IF(OR(F414="",AS414=""),"",IF(COUNT(AI414:AR414)=0,"",AS414-LOOKUP(2,1/(AI414:AR414<>""),AI414:AR414))) | IF(OR(F414="",AT414=""),"",IF(COUNT(AI414:AS414)=0,"",AT414-LOOKUP(2,1/(AI414:AS414<>""),AI414:AS414))) | IF(OR(F414="",AU414=""),"",IF(COUNT(AI414:AT414)=0,"",AU414-LOOKUP(2,1/(AI414:AT414<>""),AI414:AT414))) | IF(OR(F414="",AV414=""),"",IF(COUNT(AI414:AU414)=0,"",AV414-LOOKUP(2,1/(AI414:AU414<>""),AI414:AU414))) | IF(J414="","All_Provinces",IFERROR(VLOOKUP(J414,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K414="","All_Districts",IFERROR(VLOOKUP(K414,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F415="","",ROW()-3) | [18 empty] | IF(AQ415="","",AQ415) |  |  |  | IF(W415<>"",W415,IF(OR(T415="",V415=""),"",EDATE(T415,V415))) |  |  |  |  | IF(F415="","",IF(COUNT(AI415:AV415)=0,IF(AA415="","Not started",AA415),SUBSTITUTE(LOOKUP(2,1/(AI415:AV415<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F415="",COUNT(AI415:AV415)=0),"",TODAY()-LOOKUP(2,1/(AI415:AV415<>""),AI415:AV415)) | IF(OR(F415="",COUNT(AI415:AV415)<2),"",LOOKUP(2,1/(AI415:AV415<>""),AI415:AV415)-MIN(AI415:AV415)) | IF(OR(AD415="",AC415="Not started",AC415=""),"",IFERROR(AD415-IF(VLOOKUP(AC415,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC415,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F415="","",IF(OR(AA415="Cancelled",AC415="Cancelled"),"Cancelled",IF(OR(AC415="Completed / Handover",Y415<>"",Z415>=100),"Completed — on track",IF(O415="Not awarded",IF(U415="",IF(X415="","No planned date",IF(TODAY()>X415,"Behind — past planned date",IF(X415-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U415,"Behind — award date passed",IF(U415-TODAY()<=30,"At risk — close to off track","On track"))),IF(X415="","No planned date",IF(AND(TODAY()>X415,OR(Z415="",Z415<100)),"Behind — past end date",IF(AND(T415<>"",X415<>"",Z415<>"",(Z415<100),((TODAY()-T415)/MAX(X415-T415,1)*100)-Z415>15),"Behind — progress lag",IF(AND(X415-TODAY()<=30,X415-TODAY()>=0,OR(Z415="",Z415<90)),"At risk — close to off track","On track")))))))) | IF(OR(F415="",AC415="Completed / Handover",AC415="Cancelled"),"",IF(O415="Not awarded",IF(U415<>"",U415-TODAY(),IF(X415="","",X415-TODAY())),IF(X415="","",X415-TODAY()))) | [14 empty] | IF(OR(F415="",AJ415=""),"",IF(COUNT(AI415:AI415)=0,"",AJ415-LOOKUP(2,1/(AI415:AI415<>""),AI415:AI415))) | IF(OR(F415="",AK415=""),"",IF(COUNT(AI415:AJ415)=0,"",AK415-LOOKUP(2,1/(AI415:AJ415<>""),AI415:AJ415))) | IF(OR(F415="",AL415=""),"",IF(COUNT(AI415:AK415)=0,"",AL415-LOOKUP(2,1/(AI415:AK415<>""),AI415:AK415))) | IF(OR(F415="",AM415=""),"",IF(COUNT(AI415:AL415)=0,"",AM415-LOOKUP(2,1/(AI415:AL415<>""),AI415:AL415))) | IF(OR(F415="",AN415=""),"",IF(COUNT(AI415:AM415)=0,"",AN415-LOOKUP(2,1/(AI415:AM415<>""),AI415:AM415))) | IF(OR(F415="",AO415=""),"",IF(COUNT(AI415:AN415)=0,"",AO415-LOOKUP(2,1/(AI415:AN415<>""),AI415:AN415))) | IF(OR(F415="",AP415=""),"",IF(COUNT(AI415:AO415)=0,"",AP415-LOOKUP(2,1/(AI415:AO415<>""),AI415:AO415))) | IF(OR(F415="",AQ415=""),"",IF(COUNT(AI415:AP415)=0,"",AQ415-LOOKUP(2,1/(AI415:AP415<>""),AI415:AP415))) | IF(OR(F415="",AR415=""),"",IF(COUNT(AI415:AQ415)=0,"",AR415-LOOKUP(2,1/(AI415:AQ415<>""),AI415:AQ415))) | IF(OR(F415="",AS415=""),"",IF(COUNT(AI415:AR415)=0,"",AS415-LOOKUP(2,1/(AI415:AR415<>""),AI415:AR415))) | IF(OR(F415="",AT415=""),"",IF(COUNT(AI415:AS415)=0,"",AT415-LOOKUP(2,1/(AI415:AS415<>""),AI415:AS415))) | IF(OR(F415="",AU415=""),"",IF(COUNT(AI415:AT415)=0,"",AU415-LOOKUP(2,1/(AI415:AT415<>""),AI415:AT415))) | IF(OR(F415="",AV415=""),"",IF(COUNT(AI415:AU415)=0,"",AV415-LOOKUP(2,1/(AI415:AU415<>""),AI415:AU415))) | IF(J415="","All_Provinces",IFERROR(VLOOKUP(J415,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K415="","All_Districts",IFERROR(VLOOKUP(K415,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F416="","",ROW()-3) | [18 empty] | IF(AQ416="","",AQ416) |  |  |  | IF(W416<>"",W416,IF(OR(T416="",V416=""),"",EDATE(T416,V416))) |  |  |  |  | IF(F416="","",IF(COUNT(AI416:AV416)=0,IF(AA416="","Not started",AA416),SUBSTITUTE(LOOKUP(2,1/(AI416:AV416<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F416="",COUNT(AI416:AV416)=0),"",TODAY()-LOOKUP(2,1/(AI416:AV416<>""),AI416:AV416)) | IF(OR(F416="",COUNT(AI416:AV416)<2),"",LOOKUP(2,1/(AI416:AV416<>""),AI416:AV416)-MIN(AI416:AV416)) | IF(OR(AD416="",AC416="Not started",AC416=""),"",IFERROR(AD416-IF(VLOOKUP(AC416,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC416,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F416="","",IF(OR(AA416="Cancelled",AC416="Cancelled"),"Cancelled",IF(OR(AC416="Completed / Handover",Y416<>"",Z416>=100),"Completed — on track",IF(O416="Not awarded",IF(U416="",IF(X416="","No planned date",IF(TODAY()>X416,"Behind — past planned date",IF(X416-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U416,"Behind — award date passed",IF(U416-TODAY()<=30,"At risk — close to off track","On track"))),IF(X416="","No planned date",IF(AND(TODAY()>X416,OR(Z416="",Z416<100)),"Behind — past end date",IF(AND(T416<>"",X416<>"",Z416<>"",(Z416<100),((TODAY()-T416)/MAX(X416-T416,1)*100)-Z416>15),"Behind — progress lag",IF(AND(X416-TODAY()<=30,X416-TODAY()>=0,OR(Z416="",Z416<90)),"At risk — close to off track","On track")))))))) | IF(OR(F416="",AC416="Completed / Handover",AC416="Cancelled"),"",IF(O416="Not awarded",IF(U416<>"",U416-TODAY(),IF(X416="","",X416-TODAY())),IF(X416="","",X416-TODAY()))) | [14 empty] | IF(OR(F416="",AJ416=""),"",IF(COUNT(AI416:AI416)=0,"",AJ416-LOOKUP(2,1/(AI416:AI416<>""),AI416:AI416))) | IF(OR(F416="",AK416=""),"",IF(COUNT(AI416:AJ416)=0,"",AK416-LOOKUP(2,1/(AI416:AJ416<>""),AI416:AJ416))) | IF(OR(F416="",AL416=""),"",IF(COUNT(AI416:AK416)=0,"",AL416-LOOKUP(2,1/(AI416:AK416<>""),AI416:AK416))) | IF(OR(F416="",AM416=""),"",IF(COUNT(AI416:AL416)=0,"",AM416-LOOKUP(2,1/(AI416:AL416<>""),AI416:AL416))) | IF(OR(F416="",AN416=""),"",IF(COUNT(AI416:AM416)=0,"",AN416-LOOKUP(2,1/(AI416:AM416<>""),AI416:AM416))) | IF(OR(F416="",AO416=""),"",IF(COUNT(AI416:AN416)=0,"",AO416-LOOKUP(2,1/(AI416:AN416<>""),AI416:AN416))) | IF(OR(F416="",AP416=""),"",IF(COUNT(AI416:AO416)=0,"",AP416-LOOKUP(2,1/(AI416:AO416<>""),AI416:AO416))) | IF(OR(F416="",AQ416=""),"",IF(COUNT(AI416:AP416)=0,"",AQ416-LOOKUP(2,1/(AI416:AP416<>""),AI416:AP416))) | IF(OR(F416="",AR416=""),"",IF(COUNT(AI416:AQ416)=0,"",AR416-LOOKUP(2,1/(AI416:AQ416<>""),AI416:AQ416))) | IF(OR(F416="",AS416=""),"",IF(COUNT(AI416:AR416)=0,"",AS416-LOOKUP(2,1/(AI416:AR416<>""),AI416:AR416))) | IF(OR(F416="",AT416=""),"",IF(COUNT(AI416:AS416)=0,"",AT416-LOOKUP(2,1/(AI416:AS416<>""),AI416:AS416))) | IF(OR(F416="",AU416=""),"",IF(COUNT(AI416:AT416)=0,"",AU416-LOOKUP(2,1/(AI416:AT416<>""),AI416:AT416))) | IF(OR(F416="",AV416=""),"",IF(COUNT(AI416:AU416)=0,"",AV416-LOOKUP(2,1/(AI416:AU416<>""),AI416:AU416))) | IF(J416="","All_Provinces",IFERROR(VLOOKUP(J416,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K416="","All_Districts",IFERROR(VLOOKUP(K416,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F417="","",ROW()-3) | [18 empty] | IF(AQ417="","",AQ417) |  |  |  | IF(W417<>"",W417,IF(OR(T417="",V417=""),"",EDATE(T417,V417))) |  |  |  |  | IF(F417="","",IF(COUNT(AI417:AV417)=0,IF(AA417="","Not started",AA417),SUBSTITUTE(LOOKUP(2,1/(AI417:AV417<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F417="",COUNT(AI417:AV417)=0),"",TODAY()-LOOKUP(2,1/(AI417:AV417<>""),AI417:AV417)) | IF(OR(F417="",COUNT(AI417:AV417)<2),"",LOOKUP(2,1/(AI417:AV417<>""),AI417:AV417)-MIN(AI417:AV417)) | IF(OR(AD417="",AC417="Not started",AC417=""),"",IFERROR(AD417-IF(VLOOKUP(AC417,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC417,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F417="","",IF(OR(AA417="Cancelled",AC417="Cancelled"),"Cancelled",IF(OR(AC417="Completed / Handover",Y417<>"",Z417>=100),"Completed — on track",IF(O417="Not awarded",IF(U417="",IF(X417="","No planned date",IF(TODAY()>X417,"Behind — past planned date",IF(X417-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U417,"Behind — award date passed",IF(U417-TODAY()<=30,"At risk — close to off track","On track"))),IF(X417="","No planned date",IF(AND(TODAY()>X417,OR(Z417="",Z417<100)),"Behind — past end date",IF(AND(T417<>"",X417<>"",Z417<>"",(Z417<100),((TODAY()-T417)/MAX(X417-T417,1)*100)-Z417>15),"Behind — progress lag",IF(AND(X417-TODAY()<=30,X417-TODAY()>=0,OR(Z417="",Z417<90)),"At risk — close to off track","On track")))))))) | IF(OR(F417="",AC417="Completed / Handover",AC417="Cancelled"),"",IF(O417="Not awarded",IF(U417<>"",U417-TODAY(),IF(X417="","",X417-TODAY())),IF(X417="","",X417-TODAY()))) | [14 empty] | IF(OR(F417="",AJ417=""),"",IF(COUNT(AI417:AI417)=0,"",AJ417-LOOKUP(2,1/(AI417:AI417<>""),AI417:AI417))) | IF(OR(F417="",AK417=""),"",IF(COUNT(AI417:AJ417)=0,"",AK417-LOOKUP(2,1/(AI417:AJ417<>""),AI417:AJ417))) | IF(OR(F417="",AL417=""),"",IF(COUNT(AI417:AK417)=0,"",AL417-LOOKUP(2,1/(AI417:AK417<>""),AI417:AK417))) | IF(OR(F417="",AM417=""),"",IF(COUNT(AI417:AL417)=0,"",AM417-LOOKUP(2,1/(AI417:AL417<>""),AI417:AL417))) | IF(OR(F417="",AN417=""),"",IF(COUNT(AI417:AM417)=0,"",AN417-LOOKUP(2,1/(AI417:AM417<>""),AI417:AM417))) | IF(OR(F417="",AO417=""),"",IF(COUNT(AI417:AN417)=0,"",AO417-LOOKUP(2,1/(AI417:AN417<>""),AI417:AN417))) | IF(OR(F417="",AP417=""),"",IF(COUNT(AI417:AO417)=0,"",AP417-LOOKUP(2,1/(AI417:AO417<>""),AI417:AO417))) | IF(OR(F417="",AQ417=""),"",IF(COUNT(AI417:AP417)=0,"",AQ417-LOOKUP(2,1/(AI417:AP417<>""),AI417:AP417))) | IF(OR(F417="",AR417=""),"",IF(COUNT(AI417:AQ417)=0,"",AR417-LOOKUP(2,1/(AI417:AQ417<>""),AI417:AQ417))) | IF(OR(F417="",AS417=""),"",IF(COUNT(AI417:AR417)=0,"",AS417-LOOKUP(2,1/(AI417:AR417<>""),AI417:AR417))) | IF(OR(F417="",AT417=""),"",IF(COUNT(AI417:AS417)=0,"",AT417-LOOKUP(2,1/(AI417:AS417<>""),AI417:AS417))) | IF(OR(F417="",AU417=""),"",IF(COUNT(AI417:AT417)=0,"",AU417-LOOKUP(2,1/(AI417:AT417<>""),AI417:AT417))) | IF(OR(F417="",AV417=""),"",IF(COUNT(AI417:AU417)=0,"",AV417-LOOKUP(2,1/(AI417:AU417<>""),AI417:AU417))) | IF(J417="","All_Provinces",IFERROR(VLOOKUP(J417,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K417="","All_Districts",IFERROR(VLOOKUP(K417,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F418="","",ROW()-3) | [18 empty] | IF(AQ418="","",AQ418) |  |  |  | IF(W418<>"",W418,IF(OR(T418="",V418=""),"",EDATE(T418,V418))) |  |  |  |  | IF(F418="","",IF(COUNT(AI418:AV418)=0,IF(AA418="","Not started",AA418),SUBSTITUTE(LOOKUP(2,1/(AI418:AV418<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F418="",COUNT(AI418:AV418)=0),"",TODAY()-LOOKUP(2,1/(AI418:AV418<>""),AI418:AV418)) | IF(OR(F418="",COUNT(AI418:AV418)<2),"",LOOKUP(2,1/(AI418:AV418<>""),AI418:AV418)-MIN(AI418:AV418)) | IF(OR(AD418="",AC418="Not started",AC418=""),"",IFERROR(AD418-IF(VLOOKUP(AC418,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC418,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F418="","",IF(OR(AA418="Cancelled",AC418="Cancelled"),"Cancelled",IF(OR(AC418="Completed / Handover",Y418<>"",Z418>=100),"Completed — on track",IF(O418="Not awarded",IF(U418="",IF(X418="","No planned date",IF(TODAY()>X418,"Behind — past planned date",IF(X418-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U418,"Behind — award date passed",IF(U418-TODAY()<=30,"At risk — close to off track","On track"))),IF(X418="","No planned date",IF(AND(TODAY()>X418,OR(Z418="",Z418<100)),"Behind — past end date",IF(AND(T418<>"",X418<>"",Z418<>"",(Z418<100),((TODAY()-T418)/MAX(X418-T418,1)*100)-Z418>15),"Behind — progress lag",IF(AND(X418-TODAY()<=30,X418-TODAY()>=0,OR(Z418="",Z418<90)),"At risk — close to off track","On track")))))))) | IF(OR(F418="",AC418="Completed / Handover",AC418="Cancelled"),"",IF(O418="Not awarded",IF(U418<>"",U418-TODAY(),IF(X418="","",X418-TODAY())),IF(X418="","",X418-TODAY()))) | [14 empty] | IF(OR(F418="",AJ418=""),"",IF(COUNT(AI418:AI418)=0,"",AJ418-LOOKUP(2,1/(AI418:AI418<>""),AI418:AI418))) | IF(OR(F418="",AK418=""),"",IF(COUNT(AI418:AJ418)=0,"",AK418-LOOKUP(2,1/(AI418:AJ418<>""),AI418:AJ418))) | IF(OR(F418="",AL418=""),"",IF(COUNT(AI418:AK418)=0,"",AL418-LOOKUP(2,1/(AI418:AK418<>""),AI418:AK418))) | IF(OR(F418="",AM418=""),"",IF(COUNT(AI418:AL418)=0,"",AM418-LOOKUP(2,1/(AI418:AL418<>""),AI418:AL418))) | IF(OR(F418="",AN418=""),"",IF(COUNT(AI418:AM418)=0,"",AN418-LOOKUP(2,1/(AI418:AM418<>""),AI418:AM418))) | IF(OR(F418="",AO418=""),"",IF(COUNT(AI418:AN418)=0,"",AO418-LOOKUP(2,1/(AI418:AN418<>""),AI418:AN418))) | IF(OR(F418="",AP418=""),"",IF(COUNT(AI418:AO418)=0,"",AP418-LOOKUP(2,1/(AI418:AO418<>""),AI418:AO418))) | IF(OR(F418="",AQ418=""),"",IF(COUNT(AI418:AP418)=0,"",AQ418-LOOKUP(2,1/(AI418:AP418<>""),AI418:AP418))) | IF(OR(F418="",AR418=""),"",IF(COUNT(AI418:AQ418)=0,"",AR418-LOOKUP(2,1/(AI418:AQ418<>""),AI418:AQ418))) | IF(OR(F418="",AS418=""),"",IF(COUNT(AI418:AR418)=0,"",AS418-LOOKUP(2,1/(AI418:AR418<>""),AI418:AR418))) | IF(OR(F418="",AT418=""),"",IF(COUNT(AI418:AS418)=0,"",AT418-LOOKUP(2,1/(AI418:AS418<>""),AI418:AS418))) | IF(OR(F418="",AU418=""),"",IF(COUNT(AI418:AT418)=0,"",AU418-LOOKUP(2,1/(AI418:AT418<>""),AI418:AT418))) | IF(OR(F418="",AV418=""),"",IF(COUNT(AI418:AU418)=0,"",AV418-LOOKUP(2,1/(AI418:AU418<>""),AI418:AU418))) | IF(J418="","All_Provinces",IFERROR(VLOOKUP(J418,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K418="","All_Districts",IFERROR(VLOOKUP(K418,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F419="","",ROW()-3) | [18 empty] | IF(AQ419="","",AQ419) |  |  |  | IF(W419<>"",W419,IF(OR(T419="",V419=""),"",EDATE(T419,V419))) |  |  |  |  | IF(F419="","",IF(COUNT(AI419:AV419)=0,IF(AA419="","Not started",AA419),SUBSTITUTE(LOOKUP(2,1/(AI419:AV419<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F419="",COUNT(AI419:AV419)=0),"",TODAY()-LOOKUP(2,1/(AI419:AV419<>""),AI419:AV419)) | IF(OR(F419="",COUNT(AI419:AV419)<2),"",LOOKUP(2,1/(AI419:AV419<>""),AI419:AV419)-MIN(AI419:AV419)) | IF(OR(AD419="",AC419="Not started",AC419=""),"",IFERROR(AD419-IF(VLOOKUP(AC419,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC419,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F419="","",IF(OR(AA419="Cancelled",AC419="Cancelled"),"Cancelled",IF(OR(AC419="Completed / Handover",Y419<>"",Z419>=100),"Completed — on track",IF(O419="Not awarded",IF(U419="",IF(X419="","No planned date",IF(TODAY()>X419,"Behind — past planned date",IF(X419-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U419,"Behind — award date passed",IF(U419-TODAY()<=30,"At risk — close to off track","On track"))),IF(X419="","No planned date",IF(AND(TODAY()>X419,OR(Z419="",Z419<100)),"Behind — past end date",IF(AND(T419<>"",X419<>"",Z419<>"",(Z419<100),((TODAY()-T419)/MAX(X419-T419,1)*100)-Z419>15),"Behind — progress lag",IF(AND(X419-TODAY()<=30,X419-TODAY()>=0,OR(Z419="",Z419<90)),"At risk — close to off track","On track")))))))) | IF(OR(F419="",AC419="Completed / Handover",AC419="Cancelled"),"",IF(O419="Not awarded",IF(U419<>"",U419-TODAY(),IF(X419="","",X419-TODAY())),IF(X419="","",X419-TODAY()))) | [14 empty] | IF(OR(F419="",AJ419=""),"",IF(COUNT(AI419:AI419)=0,"",AJ419-LOOKUP(2,1/(AI419:AI419<>""),AI419:AI419))) | IF(OR(F419="",AK419=""),"",IF(COUNT(AI419:AJ419)=0,"",AK419-LOOKUP(2,1/(AI419:AJ419<>""),AI419:AJ419))) | IF(OR(F419="",AL419=""),"",IF(COUNT(AI419:AK419)=0,"",AL419-LOOKUP(2,1/(AI419:AK419<>""),AI419:AK419))) | IF(OR(F419="",AM419=""),"",IF(COUNT(AI419:AL419)=0,"",AM419-LOOKUP(2,1/(AI419:AL419<>""),AI419:AL419))) | IF(OR(F419="",AN419=""),"",IF(COUNT(AI419:AM419)=0,"",AN419-LOOKUP(2,1/(AI419:AM419<>""),AI419:AM419))) | IF(OR(F419="",AO419=""),"",IF(COUNT(AI419:AN419)=0,"",AO419-LOOKUP(2,1/(AI419:AN419<>""),AI419:AN419))) | IF(OR(F419="",AP419=""),"",IF(COUNT(AI419:AO419)=0,"",AP419-LOOKUP(2,1/(AI419:AO419<>""),AI419:AO419))) | IF(OR(F419="",AQ419=""),"",IF(COUNT(AI419:AP419)=0,"",AQ419-LOOKUP(2,1/(AI419:AP419<>""),AI419:AP419))) | IF(OR(F419="",AR419=""),"",IF(COUNT(AI419:AQ419)=0,"",AR419-LOOKUP(2,1/(AI419:AQ419<>""),AI419:AQ419))) | IF(OR(F419="",AS419=""),"",IF(COUNT(AI419:AR419)=0,"",AS419-LOOKUP(2,1/(AI419:AR419<>""),AI419:AR419))) | IF(OR(F419="",AT419=""),"",IF(COUNT(AI419:AS419)=0,"",AT419-LOOKUP(2,1/(AI419:AS419<>""),AI419:AS419))) | IF(OR(F419="",AU419=""),"",IF(COUNT(AI419:AT419)=0,"",AU419-LOOKUP(2,1/(AI419:AT419<>""),AI419:AT419))) | IF(OR(F419="",AV419=""),"",IF(COUNT(AI419:AU419)=0,"",AV419-LOOKUP(2,1/(AI419:AU419<>""),AI419:AU419))) | IF(J419="","All_Provinces",IFERROR(VLOOKUP(J419,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K419="","All_Districts",IFERROR(VLOOKUP(K419,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F420="","",ROW()-3) | [18 empty] | IF(AQ420="","",AQ420) |  |  |  | IF(W420<>"",W420,IF(OR(T420="",V420=""),"",EDATE(T420,V420))) |  |  |  |  | IF(F420="","",IF(COUNT(AI420:AV420)=0,IF(AA420="","Not started",AA420),SUBSTITUTE(LOOKUP(2,1/(AI420:AV420<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F420="",COUNT(AI420:AV420)=0),"",TODAY()-LOOKUP(2,1/(AI420:AV420<>""),AI420:AV420)) | IF(OR(F420="",COUNT(AI420:AV420)<2),"",LOOKUP(2,1/(AI420:AV420<>""),AI420:AV420)-MIN(AI420:AV420)) | IF(OR(AD420="",AC420="Not started",AC420=""),"",IFERROR(AD420-IF(VLOOKUP(AC420,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC420,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F420="","",IF(OR(AA420="Cancelled",AC420="Cancelled"),"Cancelled",IF(OR(AC420="Completed / Handover",Y420<>"",Z420>=100),"Completed — on track",IF(O420="Not awarded",IF(U420="",IF(X420="","No planned date",IF(TODAY()>X420,"Behind — past planned date",IF(X420-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U420,"Behind — award date passed",IF(U420-TODAY()<=30,"At risk — close to off track","On track"))),IF(X420="","No planned date",IF(AND(TODAY()>X420,OR(Z420="",Z420<100)),"Behind — past end date",IF(AND(T420<>"",X420<>"",Z420<>"",(Z420<100),((TODAY()-T420)/MAX(X420-T420,1)*100)-Z420>15),"Behind — progress lag",IF(AND(X420-TODAY()<=30,X420-TODAY()>=0,OR(Z420="",Z420<90)),"At risk — close to off track","On track")))))))) | IF(OR(F420="",AC420="Completed / Handover",AC420="Cancelled"),"",IF(O420="Not awarded",IF(U420<>"",U420-TODAY(),IF(X420="","",X420-TODAY())),IF(X420="","",X420-TODAY()))) | [14 empty] | IF(OR(F420="",AJ420=""),"",IF(COUNT(AI420:AI420)=0,"",AJ420-LOOKUP(2,1/(AI420:AI420<>""),AI420:AI420))) | IF(OR(F420="",AK420=""),"",IF(COUNT(AI420:AJ420)=0,"",AK420-LOOKUP(2,1/(AI420:AJ420<>""),AI420:AJ420))) | IF(OR(F420="",AL420=""),"",IF(COUNT(AI420:AK420)=0,"",AL420-LOOKUP(2,1/(AI420:AK420<>""),AI420:AK420))) | IF(OR(F420="",AM420=""),"",IF(COUNT(AI420:AL420)=0,"",AM420-LOOKUP(2,1/(AI420:AL420<>""),AI420:AL420))) | IF(OR(F420="",AN420=""),"",IF(COUNT(AI420:AM420)=0,"",AN420-LOOKUP(2,1/(AI420:AM420<>""),AI420:AM420))) | IF(OR(F420="",AO420=""),"",IF(COUNT(AI420:AN420)=0,"",AO420-LOOKUP(2,1/(AI420:AN420<>""),AI420:AN420))) | IF(OR(F420="",AP420=""),"",IF(COUNT(AI420:AO420)=0,"",AP420-LOOKUP(2,1/(AI420:AO420<>""),AI420:AO420))) | IF(OR(F420="",AQ420=""),"",IF(COUNT(AI420:AP420)=0,"",AQ420-LOOKUP(2,1/(AI420:AP420<>""),AI420:AP420))) | IF(OR(F420="",AR420=""),"",IF(COUNT(AI420:AQ420)=0,"",AR420-LOOKUP(2,1/(AI420:AQ420<>""),AI420:AQ420))) | IF(OR(F420="",AS420=""),"",IF(COUNT(AI420:AR420)=0,"",AS420-LOOKUP(2,1/(AI420:AR420<>""),AI420:AR420))) | IF(OR(F420="",AT420=""),"",IF(COUNT(AI420:AS420)=0,"",AT420-LOOKUP(2,1/(AI420:AS420<>""),AI420:AS420))) | IF(OR(F420="",AU420=""),"",IF(COUNT(AI420:AT420)=0,"",AU420-LOOKUP(2,1/(AI420:AT420<>""),AI420:AT420))) | IF(OR(F420="",AV420=""),"",IF(COUNT(AI420:AU420)=0,"",AV420-LOOKUP(2,1/(AI420:AU420<>""),AI420:AU420))) | IF(J420="","All_Provinces",IFERROR(VLOOKUP(J420,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K420="","All_Districts",IFERROR(VLOOKUP(K420,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F421="","",ROW()-3) | [18 empty] | IF(AQ421="","",AQ421) |  |  |  | IF(W421<>"",W421,IF(OR(T421="",V421=""),"",EDATE(T421,V421))) |  |  |  |  | IF(F421="","",IF(COUNT(AI421:AV421)=0,IF(AA421="","Not started",AA421),SUBSTITUTE(LOOKUP(2,1/(AI421:AV421<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F421="",COUNT(AI421:AV421)=0),"",TODAY()-LOOKUP(2,1/(AI421:AV421<>""),AI421:AV421)) | IF(OR(F421="",COUNT(AI421:AV421)<2),"",LOOKUP(2,1/(AI421:AV421<>""),AI421:AV421)-MIN(AI421:AV421)) | IF(OR(AD421="",AC421="Not started",AC421=""),"",IFERROR(AD421-IF(VLOOKUP(AC421,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC421,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F421="","",IF(OR(AA421="Cancelled",AC421="Cancelled"),"Cancelled",IF(OR(AC421="Completed / Handover",Y421<>"",Z421>=100),"Completed — on track",IF(O421="Not awarded",IF(U421="",IF(X421="","No planned date",IF(TODAY()>X421,"Behind — past planned date",IF(X421-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U421,"Behind — award date passed",IF(U421-TODAY()<=30,"At risk — close to off track","On track"))),IF(X421="","No planned date",IF(AND(TODAY()>X421,OR(Z421="",Z421<100)),"Behind — past end date",IF(AND(T421<>"",X421<>"",Z421<>"",(Z421<100),((TODAY()-T421)/MAX(X421-T421,1)*100)-Z421>15),"Behind — progress lag",IF(AND(X421-TODAY()<=30,X421-TODAY()>=0,OR(Z421="",Z421<90)),"At risk — close to off track","On track")))))))) | IF(OR(F421="",AC421="Completed / Handover",AC421="Cancelled"),"",IF(O421="Not awarded",IF(U421<>"",U421-TODAY(),IF(X421="","",X421-TODAY())),IF(X421="","",X421-TODAY()))) | [14 empty] | IF(OR(F421="",AJ421=""),"",IF(COUNT(AI421:AI421)=0,"",AJ421-LOOKUP(2,1/(AI421:AI421<>""),AI421:AI421))) | IF(OR(F421="",AK421=""),"",IF(COUNT(AI421:AJ421)=0,"",AK421-LOOKUP(2,1/(AI421:AJ421<>""),AI421:AJ421))) | IF(OR(F421="",AL421=""),"",IF(COUNT(AI421:AK421)=0,"",AL421-LOOKUP(2,1/(AI421:AK421<>""),AI421:AK421))) | IF(OR(F421="",AM421=""),"",IF(COUNT(AI421:AL421)=0,"",AM421-LOOKUP(2,1/(AI421:AL421<>""),AI421:AL421))) | IF(OR(F421="",AN421=""),"",IF(COUNT(AI421:AM421)=0,"",AN421-LOOKUP(2,1/(AI421:AM421<>""),AI421:AM421))) | IF(OR(F421="",AO421=""),"",IF(COUNT(AI421:AN421)=0,"",AO421-LOOKUP(2,1/(AI421:AN421<>""),AI421:AN421))) | IF(OR(F421="",AP421=""),"",IF(COUNT(AI421:AO421)=0,"",AP421-LOOKUP(2,1/(AI421:AO421<>""),AI421:AO421))) | IF(OR(F421="",AQ421=""),"",IF(COUNT(AI421:AP421)=0,"",AQ421-LOOKUP(2,1/(AI421:AP421<>""),AI421:AP421))) | IF(OR(F421="",AR421=""),"",IF(COUNT(AI421:AQ421)=0,"",AR421-LOOKUP(2,1/(AI421:AQ421<>""),AI421:AQ421))) | IF(OR(F421="",AS421=""),"",IF(COUNT(AI421:AR421)=0,"",AS421-LOOKUP(2,1/(AI421:AR421<>""),AI421:AR421))) | IF(OR(F421="",AT421=""),"",IF(COUNT(AI421:AS421)=0,"",AT421-LOOKUP(2,1/(AI421:AS421<>""),AI421:AS421))) | IF(OR(F421="",AU421=""),"",IF(COUNT(AI421:AT421)=0,"",AU421-LOOKUP(2,1/(AI421:AT421<>""),AI421:AT421))) | IF(OR(F421="",AV421=""),"",IF(COUNT(AI421:AU421)=0,"",AV421-LOOKUP(2,1/(AI421:AU421<>""),AI421:AU421))) | IF(J421="","All_Provinces",IFERROR(VLOOKUP(J421,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K421="","All_Districts",IFERROR(VLOOKUP(K421,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F422="","",ROW()-3) | [18 empty] | IF(AQ422="","",AQ422) |  |  |  | IF(W422<>"",W422,IF(OR(T422="",V422=""),"",EDATE(T422,V422))) |  |  |  |  | IF(F422="","",IF(COUNT(AI422:AV422)=0,IF(AA422="","Not started",AA422),SUBSTITUTE(LOOKUP(2,1/(AI422:AV422<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F422="",COUNT(AI422:AV422)=0),"",TODAY()-LOOKUP(2,1/(AI422:AV422<>""),AI422:AV422)) | IF(OR(F422="",COUNT(AI422:AV422)<2),"",LOOKUP(2,1/(AI422:AV422<>""),AI422:AV422)-MIN(AI422:AV422)) | IF(OR(AD422="",AC422="Not started",AC422=""),"",IFERROR(AD422-IF(VLOOKUP(AC422,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC422,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F422="","",IF(OR(AA422="Cancelled",AC422="Cancelled"),"Cancelled",IF(OR(AC422="Completed / Handover",Y422<>"",Z422>=100),"Completed — on track",IF(O422="Not awarded",IF(U422="",IF(X422="","No planned date",IF(TODAY()>X422,"Behind — past planned date",IF(X422-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U422,"Behind — award date passed",IF(U422-TODAY()<=30,"At risk — close to off track","On track"))),IF(X422="","No planned date",IF(AND(TODAY()>X422,OR(Z422="",Z422<100)),"Behind — past end date",IF(AND(T422<>"",X422<>"",Z422<>"",(Z422<100),((TODAY()-T422)/MAX(X422-T422,1)*100)-Z422>15),"Behind — progress lag",IF(AND(X422-TODAY()<=30,X422-TODAY()>=0,OR(Z422="",Z422<90)),"At risk — close to off track","On track")))))))) | IF(OR(F422="",AC422="Completed / Handover",AC422="Cancelled"),"",IF(O422="Not awarded",IF(U422<>"",U422-TODAY(),IF(X422="","",X422-TODAY())),IF(X422="","",X422-TODAY()))) | [14 empty] | IF(OR(F422="",AJ422=""),"",IF(COUNT(AI422:AI422)=0,"",AJ422-LOOKUP(2,1/(AI422:AI422<>""),AI422:AI422))) | IF(OR(F422="",AK422=""),"",IF(COUNT(AI422:AJ422)=0,"",AK422-LOOKUP(2,1/(AI422:AJ422<>""),AI422:AJ422))) | IF(OR(F422="",AL422=""),"",IF(COUNT(AI422:AK422)=0,"",AL422-LOOKUP(2,1/(AI422:AK422<>""),AI422:AK422))) | IF(OR(F422="",AM422=""),"",IF(COUNT(AI422:AL422)=0,"",AM422-LOOKUP(2,1/(AI422:AL422<>""),AI422:AL422))) | IF(OR(F422="",AN422=""),"",IF(COUNT(AI422:AM422)=0,"",AN422-LOOKUP(2,1/(AI422:AM422<>""),AI422:AM422))) | IF(OR(F422="",AO422=""),"",IF(COUNT(AI422:AN422)=0,"",AO422-LOOKUP(2,1/(AI422:AN422<>""),AI422:AN422))) | IF(OR(F422="",AP422=""),"",IF(COUNT(AI422:AO422)=0,"",AP422-LOOKUP(2,1/(AI422:AO422<>""),AI422:AO422))) | IF(OR(F422="",AQ422=""),"",IF(COUNT(AI422:AP422)=0,"",AQ422-LOOKUP(2,1/(AI422:AP422<>""),AI422:AP422))) | IF(OR(F422="",AR422=""),"",IF(COUNT(AI422:AQ422)=0,"",AR422-LOOKUP(2,1/(AI422:AQ422<>""),AI422:AQ422))) | IF(OR(F422="",AS422=""),"",IF(COUNT(AI422:AR422)=0,"",AS422-LOOKUP(2,1/(AI422:AR422<>""),AI422:AR422))) | IF(OR(F422="",AT422=""),"",IF(COUNT(AI422:AS422)=0,"",AT422-LOOKUP(2,1/(AI422:AS422<>""),AI422:AS422))) | IF(OR(F422="",AU422=""),"",IF(COUNT(AI422:AT422)=0,"",AU422-LOOKUP(2,1/(AI422:AT422<>""),AI422:AT422))) | IF(OR(F422="",AV422=""),"",IF(COUNT(AI422:AU422)=0,"",AV422-LOOKUP(2,1/(AI422:AU422<>""),AI422:AU422))) | IF(J422="","All_Provinces",IFERROR(VLOOKUP(J422,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K422="","All_Districts",IFERROR(VLOOKUP(K422,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F423="","",ROW()-3) | [18 empty] | IF(AQ423="","",AQ423) |  |  |  | IF(W423<>"",W423,IF(OR(T423="",V423=""),"",EDATE(T423,V423))) |  |  |  |  | IF(F423="","",IF(COUNT(AI423:AV423)=0,IF(AA423="","Not started",AA423),SUBSTITUTE(LOOKUP(2,1/(AI423:AV423<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F423="",COUNT(AI423:AV423)=0),"",TODAY()-LOOKUP(2,1/(AI423:AV423<>""),AI423:AV423)) | IF(OR(F423="",COUNT(AI423:AV423)<2),"",LOOKUP(2,1/(AI423:AV423<>""),AI423:AV423)-MIN(AI423:AV423)) | IF(OR(AD423="",AC423="Not started",AC423=""),"",IFERROR(AD423-IF(VLOOKUP(AC423,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC423,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F423="","",IF(OR(AA423="Cancelled",AC423="Cancelled"),"Cancelled",IF(OR(AC423="Completed / Handover",Y423<>"",Z423>=100),"Completed — on track",IF(O423="Not awarded",IF(U423="",IF(X423="","No planned date",IF(TODAY()>X423,"Behind — past planned date",IF(X423-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U423,"Behind — award date passed",IF(U423-TODAY()<=30,"At risk — close to off track","On track"))),IF(X423="","No planned date",IF(AND(TODAY()>X423,OR(Z423="",Z423<100)),"Behind — past end date",IF(AND(T423<>"",X423<>"",Z423<>"",(Z423<100),((TODAY()-T423)/MAX(X423-T423,1)*100)-Z423>15),"Behind — progress lag",IF(AND(X423-TODAY()<=30,X423-TODAY()>=0,OR(Z423="",Z423<90)),"At risk — close to off track","On track")))))))) | IF(OR(F423="",AC423="Completed / Handover",AC423="Cancelled"),"",IF(O423="Not awarded",IF(U423<>"",U423-TODAY(),IF(X423="","",X423-TODAY())),IF(X423="","",X423-TODAY()))) | [14 empty] | IF(OR(F423="",AJ423=""),"",IF(COUNT(AI423:AI423)=0,"",AJ423-LOOKUP(2,1/(AI423:AI423<>""),AI423:AI423))) | IF(OR(F423="",AK423=""),"",IF(COUNT(AI423:AJ423)=0,"",AK423-LOOKUP(2,1/(AI423:AJ423<>""),AI423:AJ423))) | IF(OR(F423="",AL423=""),"",IF(COUNT(AI423:AK423)=0,"",AL423-LOOKUP(2,1/(AI423:AK423<>""),AI423:AK423))) | IF(OR(F423="",AM423=""),"",IF(COUNT(AI423:AL423)=0,"",AM423-LOOKUP(2,1/(AI423:AL423<>""),AI423:AL423))) | IF(OR(F423="",AN423=""),"",IF(COUNT(AI423:AM423)=0,"",AN423-LOOKUP(2,1/(AI423:AM423<>""),AI423:AM423))) | IF(OR(F423="",AO423=""),"",IF(COUNT(AI423:AN423)=0,"",AO423-LOOKUP(2,1/(AI423:AN423<>""),AI423:AN423))) | IF(OR(F423="",AP423=""),"",IF(COUNT(AI423:AO423)=0,"",AP423-LOOKUP(2,1/(AI423:AO423<>""),AI423:AO423))) | IF(OR(F423="",AQ423=""),"",IF(COUNT(AI423:AP423)=0,"",AQ423-LOOKUP(2,1/(AI423:AP423<>""),AI423:AP423))) | IF(OR(F423="",AR423=""),"",IF(COUNT(AI423:AQ423)=0,"",AR423-LOOKUP(2,1/(AI423:AQ423<>""),AI423:AQ423))) | IF(OR(F423="",AS423=""),"",IF(COUNT(AI423:AR423)=0,"",AS423-LOOKUP(2,1/(AI423:AR423<>""),AI423:AR423))) | IF(OR(F423="",AT423=""),"",IF(COUNT(AI423:AS423)=0,"",AT423-LOOKUP(2,1/(AI423:AS423<>""),AI423:AS423))) | IF(OR(F423="",AU423=""),"",IF(COUNT(AI423:AT423)=0,"",AU423-LOOKUP(2,1/(AI423:AT423<>""),AI423:AT423))) | IF(OR(F423="",AV423=""),"",IF(COUNT(AI423:AU423)=0,"",AV423-LOOKUP(2,1/(AI423:AU423<>""),AI423:AU423))) | IF(J423="","All_Provinces",IFERROR(VLOOKUP(J423,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K423="","All_Districts",IFERROR(VLOOKUP(K423,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F424="","",ROW()-3) | [18 empty] | IF(AQ424="","",AQ424) |  |  |  | IF(W424<>"",W424,IF(OR(T424="",V424=""),"",EDATE(T424,V424))) |  |  |  |  | IF(F424="","",IF(COUNT(AI424:AV424)=0,IF(AA424="","Not started",AA424),SUBSTITUTE(LOOKUP(2,1/(AI424:AV424<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F424="",COUNT(AI424:AV424)=0),"",TODAY()-LOOKUP(2,1/(AI424:AV424<>""),AI424:AV424)) | IF(OR(F424="",COUNT(AI424:AV424)<2),"",LOOKUP(2,1/(AI424:AV424<>""),AI424:AV424)-MIN(AI424:AV424)) | IF(OR(AD424="",AC424="Not started",AC424=""),"",IFERROR(AD424-IF(VLOOKUP(AC424,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC424,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F424="","",IF(OR(AA424="Cancelled",AC424="Cancelled"),"Cancelled",IF(OR(AC424="Completed / Handover",Y424<>"",Z424>=100),"Completed — on track",IF(O424="Not awarded",IF(U424="",IF(X424="","No planned date",IF(TODAY()>X424,"Behind — past planned date",IF(X424-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U424,"Behind — award date passed",IF(U424-TODAY()<=30,"At risk — close to off track","On track"))),IF(X424="","No planned date",IF(AND(TODAY()>X424,OR(Z424="",Z424<100)),"Behind — past end date",IF(AND(T424<>"",X424<>"",Z424<>"",(Z424<100),((TODAY()-T424)/MAX(X424-T424,1)*100)-Z424>15),"Behind — progress lag",IF(AND(X424-TODAY()<=30,X424-TODAY()>=0,OR(Z424="",Z424<90)),"At risk — close to off track","On track")))))))) | IF(OR(F424="",AC424="Completed / Handover",AC424="Cancelled"),"",IF(O424="Not awarded",IF(U424<>"",U424-TODAY(),IF(X424="","",X424-TODAY())),IF(X424="","",X424-TODAY()))) | [14 empty] | IF(OR(F424="",AJ424=""),"",IF(COUNT(AI424:AI424)=0,"",AJ424-LOOKUP(2,1/(AI424:AI424<>""),AI424:AI424))) | IF(OR(F424="",AK424=""),"",IF(COUNT(AI424:AJ424)=0,"",AK424-LOOKUP(2,1/(AI424:AJ424<>""),AI424:AJ424))) | IF(OR(F424="",AL424=""),"",IF(COUNT(AI424:AK424)=0,"",AL424-LOOKUP(2,1/(AI424:AK424<>""),AI424:AK424))) | IF(OR(F424="",AM424=""),"",IF(COUNT(AI424:AL424)=0,"",AM424-LOOKUP(2,1/(AI424:AL424<>""),AI424:AL424))) | IF(OR(F424="",AN424=""),"",IF(COUNT(AI424:AM424)=0,"",AN424-LOOKUP(2,1/(AI424:AM424<>""),AI424:AM424))) | IF(OR(F424="",AO424=""),"",IF(COUNT(AI424:AN424)=0,"",AO424-LOOKUP(2,1/(AI424:AN424<>""),AI424:AN424))) | IF(OR(F424="",AP424=""),"",IF(COUNT(AI424:AO424)=0,"",AP424-LOOKUP(2,1/(AI424:AO424<>""),AI424:AO424))) | IF(OR(F424="",AQ424=""),"",IF(COUNT(AI424:AP424)=0,"",AQ424-LOOKUP(2,1/(AI424:AP424<>""),AI424:AP424))) | IF(OR(F424="",AR424=""),"",IF(COUNT(AI424:AQ424)=0,"",AR424-LOOKUP(2,1/(AI424:AQ424<>""),AI424:AQ424))) | IF(OR(F424="",AS424=""),"",IF(COUNT(AI424:AR424)=0,"",AS424-LOOKUP(2,1/(AI424:AR424<>""),AI424:AR424))) | IF(OR(F424="",AT424=""),"",IF(COUNT(AI424:AS424)=0,"",AT424-LOOKUP(2,1/(AI424:AS424<>""),AI424:AS424))) | IF(OR(F424="",AU424=""),"",IF(COUNT(AI424:AT424)=0,"",AU424-LOOKUP(2,1/(AI424:AT424<>""),AI424:AT424))) | IF(OR(F424="",AV424=""),"",IF(COUNT(AI424:AU424)=0,"",AV424-LOOKUP(2,1/(AI424:AU424<>""),AI424:AU424))) | IF(J424="","All_Provinces",IFERROR(VLOOKUP(J424,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K424="","All_Districts",IFERROR(VLOOKUP(K424,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F425="","",ROW()-3) | [18 empty] | IF(AQ425="","",AQ425) |  |  |  | IF(W425<>"",W425,IF(OR(T425="",V425=""),"",EDATE(T425,V425))) |  |  |  |  | IF(F425="","",IF(COUNT(AI425:AV425)=0,IF(AA425="","Not started",AA425),SUBSTITUTE(LOOKUP(2,1/(AI425:AV425<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F425="",COUNT(AI425:AV425)=0),"",TODAY()-LOOKUP(2,1/(AI425:AV425<>""),AI425:AV425)) | IF(OR(F425="",COUNT(AI425:AV425)<2),"",LOOKUP(2,1/(AI425:AV425<>""),AI425:AV425)-MIN(AI425:AV425)) | IF(OR(AD425="",AC425="Not started",AC425=""),"",IFERROR(AD425-IF(VLOOKUP(AC425,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC425,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F425="","",IF(OR(AA425="Cancelled",AC425="Cancelled"),"Cancelled",IF(OR(AC425="Completed / Handover",Y425<>"",Z425>=100),"Completed — on track",IF(O425="Not awarded",IF(U425="",IF(X425="","No planned date",IF(TODAY()>X425,"Behind — past planned date",IF(X425-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U425,"Behind — award date passed",IF(U425-TODAY()<=30,"At risk — close to off track","On track"))),IF(X425="","No planned date",IF(AND(TODAY()>X425,OR(Z425="",Z425<100)),"Behind — past end date",IF(AND(T425<>"",X425<>"",Z425<>"",(Z425<100),((TODAY()-T425)/MAX(X425-T425,1)*100)-Z425>15),"Behind — progress lag",IF(AND(X425-TODAY()<=30,X425-TODAY()>=0,OR(Z425="",Z425<90)),"At risk — close to off track","On track")))))))) | IF(OR(F425="",AC425="Completed / Handover",AC425="Cancelled"),"",IF(O425="Not awarded",IF(U425<>"",U425-TODAY(),IF(X425="","",X425-TODAY())),IF(X425="","",X425-TODAY()))) | [14 empty] | IF(OR(F425="",AJ425=""),"",IF(COUNT(AI425:AI425)=0,"",AJ425-LOOKUP(2,1/(AI425:AI425<>""),AI425:AI425))) | IF(OR(F425="",AK425=""),"",IF(COUNT(AI425:AJ425)=0,"",AK425-LOOKUP(2,1/(AI425:AJ425<>""),AI425:AJ425))) | IF(OR(F425="",AL425=""),"",IF(COUNT(AI425:AK425)=0,"",AL425-LOOKUP(2,1/(AI425:AK425<>""),AI425:AK425))) | IF(OR(F425="",AM425=""),"",IF(COUNT(AI425:AL425)=0,"",AM425-LOOKUP(2,1/(AI425:AL425<>""),AI425:AL425))) | IF(OR(F425="",AN425=""),"",IF(COUNT(AI425:AM425)=0,"",AN425-LOOKUP(2,1/(AI425:AM425<>""),AI425:AM425))) | IF(OR(F425="",AO425=""),"",IF(COUNT(AI425:AN425)=0,"",AO425-LOOKUP(2,1/(AI425:AN425<>""),AI425:AN425))) | IF(OR(F425="",AP425=""),"",IF(COUNT(AI425:AO425)=0,"",AP425-LOOKUP(2,1/(AI425:AO425<>""),AI425:AO425))) | IF(OR(F425="",AQ425=""),"",IF(COUNT(AI425:AP425)=0,"",AQ425-LOOKUP(2,1/(AI425:AP425<>""),AI425:AP425))) | IF(OR(F425="",AR425=""),"",IF(COUNT(AI425:AQ425)=0,"",AR425-LOOKUP(2,1/(AI425:AQ425<>""),AI425:AQ425))) | IF(OR(F425="",AS425=""),"",IF(COUNT(AI425:AR425)=0,"",AS425-LOOKUP(2,1/(AI425:AR425<>""),AI425:AR425))) | IF(OR(F425="",AT425=""),"",IF(COUNT(AI425:AS425)=0,"",AT425-LOOKUP(2,1/(AI425:AS425<>""),AI425:AS425))) | IF(OR(F425="",AU425=""),"",IF(COUNT(AI425:AT425)=0,"",AU425-LOOKUP(2,1/(AI425:AT425<>""),AI425:AT425))) | IF(OR(F425="",AV425=""),"",IF(COUNT(AI425:AU425)=0,"",AV425-LOOKUP(2,1/(AI425:AU425<>""),AI425:AU425))) | IF(J425="","All_Provinces",IFERROR(VLOOKUP(J425,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K425="","All_Districts",IFERROR(VLOOKUP(K425,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F426="","",ROW()-3) | [18 empty] | IF(AQ426="","",AQ426) |  |  |  | IF(W426<>"",W426,IF(OR(T426="",V426=""),"",EDATE(T426,V426))) |  |  |  |  | IF(F426="","",IF(COUNT(AI426:AV426)=0,IF(AA426="","Not started",AA426),SUBSTITUTE(LOOKUP(2,1/(AI426:AV426<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F426="",COUNT(AI426:AV426)=0),"",TODAY()-LOOKUP(2,1/(AI426:AV426<>""),AI426:AV426)) | IF(OR(F426="",COUNT(AI426:AV426)<2),"",LOOKUP(2,1/(AI426:AV426<>""),AI426:AV426)-MIN(AI426:AV426)) | IF(OR(AD426="",AC426="Not started",AC426=""),"",IFERROR(AD426-IF(VLOOKUP(AC426,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC426,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F426="","",IF(OR(AA426="Cancelled",AC426="Cancelled"),"Cancelled",IF(OR(AC426="Completed / Handover",Y426<>"",Z426>=100),"Completed — on track",IF(O426="Not awarded",IF(U426="",IF(X426="","No planned date",IF(TODAY()>X426,"Behind — past planned date",IF(X426-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U426,"Behind — award date passed",IF(U426-TODAY()<=30,"At risk — close to off track","On track"))),IF(X426="","No planned date",IF(AND(TODAY()>X426,OR(Z426="",Z426<100)),"Behind — past end date",IF(AND(T426<>"",X426<>"",Z426<>"",(Z426<100),((TODAY()-T426)/MAX(X426-T426,1)*100)-Z426>15),"Behind — progress lag",IF(AND(X426-TODAY()<=30,X426-TODAY()>=0,OR(Z426="",Z426<90)),"At risk — close to off track","On track")))))))) | IF(OR(F426="",AC426="Completed / Handover",AC426="Cancelled"),"",IF(O426="Not awarded",IF(U426<>"",U426-TODAY(),IF(X426="","",X426-TODAY())),IF(X426="","",X426-TODAY()))) | [14 empty] | IF(OR(F426="",AJ426=""),"",IF(COUNT(AI426:AI426)=0,"",AJ426-LOOKUP(2,1/(AI426:AI426<>""),AI426:AI426))) | IF(OR(F426="",AK426=""),"",IF(COUNT(AI426:AJ426)=0,"",AK426-LOOKUP(2,1/(AI426:AJ426<>""),AI426:AJ426))) | IF(OR(F426="",AL426=""),"",IF(COUNT(AI426:AK426)=0,"",AL426-LOOKUP(2,1/(AI426:AK426<>""),AI426:AK426))) | IF(OR(F426="",AM426=""),"",IF(COUNT(AI426:AL426)=0,"",AM426-LOOKUP(2,1/(AI426:AL426<>""),AI426:AL426))) | IF(OR(F426="",AN426=""),"",IF(COUNT(AI426:AM426)=0,"",AN426-LOOKUP(2,1/(AI426:AM426<>""),AI426:AM426))) | IF(OR(F426="",AO426=""),"",IF(COUNT(AI426:AN426)=0,"",AO426-LOOKUP(2,1/(AI426:AN426<>""),AI426:AN426))) | IF(OR(F426="",AP426=""),"",IF(COUNT(AI426:AO426)=0,"",AP426-LOOKUP(2,1/(AI426:AO426<>""),AI426:AO426))) | IF(OR(F426="",AQ426=""),"",IF(COUNT(AI426:AP426)=0,"",AQ426-LOOKUP(2,1/(AI426:AP426<>""),AI426:AP426))) | IF(OR(F426="",AR426=""),"",IF(COUNT(AI426:AQ426)=0,"",AR426-LOOKUP(2,1/(AI426:AQ426<>""),AI426:AQ426))) | IF(OR(F426="",AS426=""),"",IF(COUNT(AI426:AR426)=0,"",AS426-LOOKUP(2,1/(AI426:AR426<>""),AI426:AR426))) | IF(OR(F426="",AT426=""),"",IF(COUNT(AI426:AS426)=0,"",AT426-LOOKUP(2,1/(AI426:AS426<>""),AI426:AS426))) | IF(OR(F426="",AU426=""),"",IF(COUNT(AI426:AT426)=0,"",AU426-LOOKUP(2,1/(AI426:AT426<>""),AI426:AT426))) | IF(OR(F426="",AV426=""),"",IF(COUNT(AI426:AU426)=0,"",AV426-LOOKUP(2,1/(AI426:AU426<>""),AI426:AU426))) | IF(J426="","All_Provinces",IFERROR(VLOOKUP(J426,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K426="","All_Districts",IFERROR(VLOOKUP(K426,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F427="","",ROW()-3) | [18 empty] | IF(AQ427="","",AQ427) |  |  |  | IF(W427<>"",W427,IF(OR(T427="",V427=""),"",EDATE(T427,V427))) |  |  |  |  | IF(F427="","",IF(COUNT(AI427:AV427)=0,IF(AA427="","Not started",AA427),SUBSTITUTE(LOOKUP(2,1/(AI427:AV427<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F427="",COUNT(AI427:AV427)=0),"",TODAY()-LOOKUP(2,1/(AI427:AV427<>""),AI427:AV427)) | IF(OR(F427="",COUNT(AI427:AV427)<2),"",LOOKUP(2,1/(AI427:AV427<>""),AI427:AV427)-MIN(AI427:AV427)) | IF(OR(AD427="",AC427="Not started",AC427=""),"",IFERROR(AD427-IF(VLOOKUP(AC427,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC427,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F427="","",IF(OR(AA427="Cancelled",AC427="Cancelled"),"Cancelled",IF(OR(AC427="Completed / Handover",Y427<>"",Z427>=100),"Completed — on track",IF(O427="Not awarded",IF(U427="",IF(X427="","No planned date",IF(TODAY()>X427,"Behind — past planned date",IF(X427-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U427,"Behind — award date passed",IF(U427-TODAY()<=30,"At risk — close to off track","On track"))),IF(X427="","No planned date",IF(AND(TODAY()>X427,OR(Z427="",Z427<100)),"Behind — past end date",IF(AND(T427<>"",X427<>"",Z427<>"",(Z427<100),((TODAY()-T427)/MAX(X427-T427,1)*100)-Z427>15),"Behind — progress lag",IF(AND(X427-TODAY()<=30,X427-TODAY()>=0,OR(Z427="",Z427<90)),"At risk — close to off track","On track")))))))) | IF(OR(F427="",AC427="Completed / Handover",AC427="Cancelled"),"",IF(O427="Not awarded",IF(U427<>"",U427-TODAY(),IF(X427="","",X427-TODAY())),IF(X427="","",X427-TODAY()))) | [14 empty] | IF(OR(F427="",AJ427=""),"",IF(COUNT(AI427:AI427)=0,"",AJ427-LOOKUP(2,1/(AI427:AI427<>""),AI427:AI427))) | IF(OR(F427="",AK427=""),"",IF(COUNT(AI427:AJ427)=0,"",AK427-LOOKUP(2,1/(AI427:AJ427<>""),AI427:AJ427))) | IF(OR(F427="",AL427=""),"",IF(COUNT(AI427:AK427)=0,"",AL427-LOOKUP(2,1/(AI427:AK427<>""),AI427:AK427))) | IF(OR(F427="",AM427=""),"",IF(COUNT(AI427:AL427)=0,"",AM427-LOOKUP(2,1/(AI427:AL427<>""),AI427:AL427))) | IF(OR(F427="",AN427=""),"",IF(COUNT(AI427:AM427)=0,"",AN427-LOOKUP(2,1/(AI427:AM427<>""),AI427:AM427))) | IF(OR(F427="",AO427=""),"",IF(COUNT(AI427:AN427)=0,"",AO427-LOOKUP(2,1/(AI427:AN427<>""),AI427:AN427))) | IF(OR(F427="",AP427=""),"",IF(COUNT(AI427:AO427)=0,"",AP427-LOOKUP(2,1/(AI427:AO427<>""),AI427:AO427))) | IF(OR(F427="",AQ427=""),"",IF(COUNT(AI427:AP427)=0,"",AQ427-LOOKUP(2,1/(AI427:AP427<>""),AI427:AP427))) | IF(OR(F427="",AR427=""),"",IF(COUNT(AI427:AQ427)=0,"",AR427-LOOKUP(2,1/(AI427:AQ427<>""),AI427:AQ427))) | IF(OR(F427="",AS427=""),"",IF(COUNT(AI427:AR427)=0,"",AS427-LOOKUP(2,1/(AI427:AR427<>""),AI427:AR427))) | IF(OR(F427="",AT427=""),"",IF(COUNT(AI427:AS427)=0,"",AT427-LOOKUP(2,1/(AI427:AS427<>""),AI427:AS427))) | IF(OR(F427="",AU427=""),"",IF(COUNT(AI427:AT427)=0,"",AU427-LOOKUP(2,1/(AI427:AT427<>""),AI427:AT427))) | IF(OR(F427="",AV427=""),"",IF(COUNT(AI427:AU427)=0,"",AV427-LOOKUP(2,1/(AI427:AU427<>""),AI427:AU427))) | IF(J427="","All_Provinces",IFERROR(VLOOKUP(J427,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K427="","All_Districts",IFERROR(VLOOKUP(K427,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F428="","",ROW()-3) | [18 empty] | IF(AQ428="","",AQ428) |  |  |  | IF(W428<>"",W428,IF(OR(T428="",V428=""),"",EDATE(T428,V428))) |  |  |  |  | IF(F428="","",IF(COUNT(AI428:AV428)=0,IF(AA428="","Not started",AA428),SUBSTITUTE(LOOKUP(2,1/(AI428:AV428<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F428="",COUNT(AI428:AV428)=0),"",TODAY()-LOOKUP(2,1/(AI428:AV428<>""),AI428:AV428)) | IF(OR(F428="",COUNT(AI428:AV428)<2),"",LOOKUP(2,1/(AI428:AV428<>""),AI428:AV428)-MIN(AI428:AV428)) | IF(OR(AD428="",AC428="Not started",AC428=""),"",IFERROR(AD428-IF(VLOOKUP(AC428,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC428,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F428="","",IF(OR(AA428="Cancelled",AC428="Cancelled"),"Cancelled",IF(OR(AC428="Completed / Handover",Y428<>"",Z428>=100),"Completed — on track",IF(O428="Not awarded",IF(U428="",IF(X428="","No planned date",IF(TODAY()>X428,"Behind — past planned date",IF(X428-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U428,"Behind — award date passed",IF(U428-TODAY()<=30,"At risk — close to off track","On track"))),IF(X428="","No planned date",IF(AND(TODAY()>X428,OR(Z428="",Z428<100)),"Behind — past end date",IF(AND(T428<>"",X428<>"",Z428<>"",(Z428<100),((TODAY()-T428)/MAX(X428-T428,1)*100)-Z428>15),"Behind — progress lag",IF(AND(X428-TODAY()<=30,X428-TODAY()>=0,OR(Z428="",Z428<90)),"At risk — close to off track","On track")))))))) | IF(OR(F428="",AC428="Completed / Handover",AC428="Cancelled"),"",IF(O428="Not awarded",IF(U428<>"",U428-TODAY(),IF(X428="","",X428-TODAY())),IF(X428="","",X428-TODAY()))) | [14 empty] | IF(OR(F428="",AJ428=""),"",IF(COUNT(AI428:AI428)=0,"",AJ428-LOOKUP(2,1/(AI428:AI428<>""),AI428:AI428))) | IF(OR(F428="",AK428=""),"",IF(COUNT(AI428:AJ428)=0,"",AK428-LOOKUP(2,1/(AI428:AJ428<>""),AI428:AJ428))) | IF(OR(F428="",AL428=""),"",IF(COUNT(AI428:AK428)=0,"",AL428-LOOKUP(2,1/(AI428:AK428<>""),AI428:AK428))) | IF(OR(F428="",AM428=""),"",IF(COUNT(AI428:AL428)=0,"",AM428-LOOKUP(2,1/(AI428:AL428<>""),AI428:AL428))) | IF(OR(F428="",AN428=""),"",IF(COUNT(AI428:AM428)=0,"",AN428-LOOKUP(2,1/(AI428:AM428<>""),AI428:AM428))) | IF(OR(F428="",AO428=""),"",IF(COUNT(AI428:AN428)=0,"",AO428-LOOKUP(2,1/(AI428:AN428<>""),AI428:AN428))) | IF(OR(F428="",AP428=""),"",IF(COUNT(AI428:AO428)=0,"",AP428-LOOKUP(2,1/(AI428:AO428<>""),AI428:AO428))) | IF(OR(F428="",AQ428=""),"",IF(COUNT(AI428:AP428)=0,"",AQ428-LOOKUP(2,1/(AI428:AP428<>""),AI428:AP428))) | IF(OR(F428="",AR428=""),"",IF(COUNT(AI428:AQ428)=0,"",AR428-LOOKUP(2,1/(AI428:AQ428<>""),AI428:AQ428))) | IF(OR(F428="",AS428=""),"",IF(COUNT(AI428:AR428)=0,"",AS428-LOOKUP(2,1/(AI428:AR428<>""),AI428:AR428))) | IF(OR(F428="",AT428=""),"",IF(COUNT(AI428:AS428)=0,"",AT428-LOOKUP(2,1/(AI428:AS428<>""),AI428:AS428))) | IF(OR(F428="",AU428=""),"",IF(COUNT(AI428:AT428)=0,"",AU428-LOOKUP(2,1/(AI428:AT428<>""),AI428:AT428))) | IF(OR(F428="",AV428=""),"",IF(COUNT(AI428:AU428)=0,"",AV428-LOOKUP(2,1/(AI428:AU428<>""),AI428:AU428))) | IF(J428="","All_Provinces",IFERROR(VLOOKUP(J428,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K428="","All_Districts",IFERROR(VLOOKUP(K428,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F429="","",ROW()-3) | [18 empty] | IF(AQ429="","",AQ429) |  |  |  | IF(W429<>"",W429,IF(OR(T429="",V429=""),"",EDATE(T429,V429))) |  |  |  |  | IF(F429="","",IF(COUNT(AI429:AV429)=0,IF(AA429="","Not started",AA429),SUBSTITUTE(LOOKUP(2,1/(AI429:AV429<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F429="",COUNT(AI429:AV429)=0),"",TODAY()-LOOKUP(2,1/(AI429:AV429<>""),AI429:AV429)) | IF(OR(F429="",COUNT(AI429:AV429)<2),"",LOOKUP(2,1/(AI429:AV429<>""),AI429:AV429)-MIN(AI429:AV429)) | IF(OR(AD429="",AC429="Not started",AC429=""),"",IFERROR(AD429-IF(VLOOKUP(AC429,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC429,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F429="","",IF(OR(AA429="Cancelled",AC429="Cancelled"),"Cancelled",IF(OR(AC429="Completed / Handover",Y429<>"",Z429>=100),"Completed — on track",IF(O429="Not awarded",IF(U429="",IF(X429="","No planned date",IF(TODAY()>X429,"Behind — past planned date",IF(X429-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U429,"Behind — award date passed",IF(U429-TODAY()<=30,"At risk — close to off track","On track"))),IF(X429="","No planned date",IF(AND(TODAY()>X429,OR(Z429="",Z429<100)),"Behind — past end date",IF(AND(T429<>"",X429<>"",Z429<>"",(Z429<100),((TODAY()-T429)/MAX(X429-T429,1)*100)-Z429>15),"Behind — progress lag",IF(AND(X429-TODAY()<=30,X429-TODAY()>=0,OR(Z429="",Z429<90)),"At risk — close to off track","On track")))))))) | IF(OR(F429="",AC429="Completed / Handover",AC429="Cancelled"),"",IF(O429="Not awarded",IF(U429<>"",U429-TODAY(),IF(X429="","",X429-TODAY())),IF(X429="","",X429-TODAY()))) | [14 empty] | IF(OR(F429="",AJ429=""),"",IF(COUNT(AI429:AI429)=0,"",AJ429-LOOKUP(2,1/(AI429:AI429<>""),AI429:AI429))) | IF(OR(F429="",AK429=""),"",IF(COUNT(AI429:AJ429)=0,"",AK429-LOOKUP(2,1/(AI429:AJ429<>""),AI429:AJ429))) | IF(OR(F429="",AL429=""),"",IF(COUNT(AI429:AK429)=0,"",AL429-LOOKUP(2,1/(AI429:AK429<>""),AI429:AK429))) | IF(OR(F429="",AM429=""),"",IF(COUNT(AI429:AL429)=0,"",AM429-LOOKUP(2,1/(AI429:AL429<>""),AI429:AL429))) | IF(OR(F429="",AN429=""),"",IF(COUNT(AI429:AM429)=0,"",AN429-LOOKUP(2,1/(AI429:AM429<>""),AI429:AM429))) | IF(OR(F429="",AO429=""),"",IF(COUNT(AI429:AN429)=0,"",AO429-LOOKUP(2,1/(AI429:AN429<>""),AI429:AN429))) | IF(OR(F429="",AP429=""),"",IF(COUNT(AI429:AO429)=0,"",AP429-LOOKUP(2,1/(AI429:AO429<>""),AI429:AO429))) | IF(OR(F429="",AQ429=""),"",IF(COUNT(AI429:AP429)=0,"",AQ429-LOOKUP(2,1/(AI429:AP429<>""),AI429:AP429))) | IF(OR(F429="",AR429=""),"",IF(COUNT(AI429:AQ429)=0,"",AR429-LOOKUP(2,1/(AI429:AQ429<>""),AI429:AQ429))) | IF(OR(F429="",AS429=""),"",IF(COUNT(AI429:AR429)=0,"",AS429-LOOKUP(2,1/(AI429:AR429<>""),AI429:AR429))) | IF(OR(F429="",AT429=""),"",IF(COUNT(AI429:AS429)=0,"",AT429-LOOKUP(2,1/(AI429:AS429<>""),AI429:AS429))) | IF(OR(F429="",AU429=""),"",IF(COUNT(AI429:AT429)=0,"",AU429-LOOKUP(2,1/(AI429:AT429<>""),AI429:AT429))) | IF(OR(F429="",AV429=""),"",IF(COUNT(AI429:AU429)=0,"",AV429-LOOKUP(2,1/(AI429:AU429<>""),AI429:AU429))) | IF(J429="","All_Provinces",IFERROR(VLOOKUP(J429,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K429="","All_Districts",IFERROR(VLOOKUP(K429,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F430="","",ROW()-3) | [18 empty] | IF(AQ430="","",AQ430) |  |  |  | IF(W430<>"",W430,IF(OR(T430="",V430=""),"",EDATE(T430,V430))) |  |  |  |  | IF(F430="","",IF(COUNT(AI430:AV430)=0,IF(AA430="","Not started",AA430),SUBSTITUTE(LOOKUP(2,1/(AI430:AV430<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F430="",COUNT(AI430:AV430)=0),"",TODAY()-LOOKUP(2,1/(AI430:AV430<>""),AI430:AV430)) | IF(OR(F430="",COUNT(AI430:AV430)<2),"",LOOKUP(2,1/(AI430:AV430<>""),AI430:AV430)-MIN(AI430:AV430)) | IF(OR(AD430="",AC430="Not started",AC430=""),"",IFERROR(AD430-IF(VLOOKUP(AC430,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC430,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F430="","",IF(OR(AA430="Cancelled",AC430="Cancelled"),"Cancelled",IF(OR(AC430="Completed / Handover",Y430<>"",Z430>=100),"Completed — on track",IF(O430="Not awarded",IF(U430="",IF(X430="","No planned date",IF(TODAY()>X430,"Behind — past planned date",IF(X430-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U430,"Behind — award date passed",IF(U430-TODAY()<=30,"At risk — close to off track","On track"))),IF(X430="","No planned date",IF(AND(TODAY()>X430,OR(Z430="",Z430<100)),"Behind — past end date",IF(AND(T430<>"",X430<>"",Z430<>"",(Z430<100),((TODAY()-T430)/MAX(X430-T430,1)*100)-Z430>15),"Behind — progress lag",IF(AND(X430-TODAY()<=30,X430-TODAY()>=0,OR(Z430="",Z430<90)),"At risk — close to off track","On track")))))))) | IF(OR(F430="",AC430="Completed / Handover",AC430="Cancelled"),"",IF(O430="Not awarded",IF(U430<>"",U430-TODAY(),IF(X430="","",X430-TODAY())),IF(X430="","",X430-TODAY()))) | [14 empty] | IF(OR(F430="",AJ430=""),"",IF(COUNT(AI430:AI430)=0,"",AJ430-LOOKUP(2,1/(AI430:AI430<>""),AI430:AI430))) | IF(OR(F430="",AK430=""),"",IF(COUNT(AI430:AJ430)=0,"",AK430-LOOKUP(2,1/(AI430:AJ430<>""),AI430:AJ430))) | IF(OR(F430="",AL430=""),"",IF(COUNT(AI430:AK430)=0,"",AL430-LOOKUP(2,1/(AI430:AK430<>""),AI430:AK430))) | IF(OR(F430="",AM430=""),"",IF(COUNT(AI430:AL430)=0,"",AM430-LOOKUP(2,1/(AI430:AL430<>""),AI430:AL430))) | IF(OR(F430="",AN430=""),"",IF(COUNT(AI430:AM430)=0,"",AN430-LOOKUP(2,1/(AI430:AM430<>""),AI430:AM430))) | IF(OR(F430="",AO430=""),"",IF(COUNT(AI430:AN430)=0,"",AO430-LOOKUP(2,1/(AI430:AN430<>""),AI430:AN430))) | IF(OR(F430="",AP430=""),"",IF(COUNT(AI430:AO430)=0,"",AP430-LOOKUP(2,1/(AI430:AO430<>""),AI430:AO430))) | IF(OR(F430="",AQ430=""),"",IF(COUNT(AI430:AP430)=0,"",AQ430-LOOKUP(2,1/(AI430:AP430<>""),AI430:AP430))) | IF(OR(F430="",AR430=""),"",IF(COUNT(AI430:AQ430)=0,"",AR430-LOOKUP(2,1/(AI430:AQ430<>""),AI430:AQ430))) | IF(OR(F430="",AS430=""),"",IF(COUNT(AI430:AR430)=0,"",AS430-LOOKUP(2,1/(AI430:AR430<>""),AI430:AR430))) | IF(OR(F430="",AT430=""),"",IF(COUNT(AI430:AS430)=0,"",AT430-LOOKUP(2,1/(AI430:AS430<>""),AI430:AS430))) | IF(OR(F430="",AU430=""),"",IF(COUNT(AI430:AT430)=0,"",AU430-LOOKUP(2,1/(AI430:AT430<>""),AI430:AT430))) | IF(OR(F430="",AV430=""),"",IF(COUNT(AI430:AU430)=0,"",AV430-LOOKUP(2,1/(AI430:AU430<>""),AI430:AU430))) | IF(J430="","All_Provinces",IFERROR(VLOOKUP(J430,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K430="","All_Districts",IFERROR(VLOOKUP(K430,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F431="","",ROW()-3) | [18 empty] | IF(AQ431="","",AQ431) |  |  |  | IF(W431<>"",W431,IF(OR(T431="",V431=""),"",EDATE(T431,V431))) |  |  |  |  | IF(F431="","",IF(COUNT(AI431:AV431)=0,IF(AA431="","Not started",AA431),SUBSTITUTE(LOOKUP(2,1/(AI431:AV431<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F431="",COUNT(AI431:AV431)=0),"",TODAY()-LOOKUP(2,1/(AI431:AV431<>""),AI431:AV431)) | IF(OR(F431="",COUNT(AI431:AV431)<2),"",LOOKUP(2,1/(AI431:AV431<>""),AI431:AV431)-MIN(AI431:AV431)) | IF(OR(AD431="",AC431="Not started",AC431=""),"",IFERROR(AD431-IF(VLOOKUP(AC431,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC431,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F431="","",IF(OR(AA431="Cancelled",AC431="Cancelled"),"Cancelled",IF(OR(AC431="Completed / Handover",Y431<>"",Z431>=100),"Completed — on track",IF(O431="Not awarded",IF(U431="",IF(X431="","No planned date",IF(TODAY()>X431,"Behind — past planned date",IF(X431-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U431,"Behind — award date passed",IF(U431-TODAY()<=30,"At risk — close to off track","On track"))),IF(X431="","No planned date",IF(AND(TODAY()>X431,OR(Z431="",Z431<100)),"Behind — past end date",IF(AND(T431<>"",X431<>"",Z431<>"",(Z431<100),((TODAY()-T431)/MAX(X431-T431,1)*100)-Z431>15),"Behind — progress lag",IF(AND(X431-TODAY()<=30,X431-TODAY()>=0,OR(Z431="",Z431<90)),"At risk — close to off track","On track")))))))) | IF(OR(F431="",AC431="Completed / Handover",AC431="Cancelled"),"",IF(O431="Not awarded",IF(U431<>"",U431-TODAY(),IF(X431="","",X431-TODAY())),IF(X431="","",X431-TODAY()))) | [14 empty] | IF(OR(F431="",AJ431=""),"",IF(COUNT(AI431:AI431)=0,"",AJ431-LOOKUP(2,1/(AI431:AI431<>""),AI431:AI431))) | IF(OR(F431="",AK431=""),"",IF(COUNT(AI431:AJ431)=0,"",AK431-LOOKUP(2,1/(AI431:AJ431<>""),AI431:AJ431))) | IF(OR(F431="",AL431=""),"",IF(COUNT(AI431:AK431)=0,"",AL431-LOOKUP(2,1/(AI431:AK431<>""),AI431:AK431))) | IF(OR(F431="",AM431=""),"",IF(COUNT(AI431:AL431)=0,"",AM431-LOOKUP(2,1/(AI431:AL431<>""),AI431:AL431))) | IF(OR(F431="",AN431=""),"",IF(COUNT(AI431:AM431)=0,"",AN431-LOOKUP(2,1/(AI431:AM431<>""),AI431:AM431))) | IF(OR(F431="",AO431=""),"",IF(COUNT(AI431:AN431)=0,"",AO431-LOOKUP(2,1/(AI431:AN431<>""),AI431:AN431))) | IF(OR(F431="",AP431=""),"",IF(COUNT(AI431:AO431)=0,"",AP431-LOOKUP(2,1/(AI431:AO431<>""),AI431:AO431))) | IF(OR(F431="",AQ431=""),"",IF(COUNT(AI431:AP431)=0,"",AQ431-LOOKUP(2,1/(AI431:AP431<>""),AI431:AP431))) | IF(OR(F431="",AR431=""),"",IF(COUNT(AI431:AQ431)=0,"",AR431-LOOKUP(2,1/(AI431:AQ431<>""),AI431:AQ431))) | IF(OR(F431="",AS431=""),"",IF(COUNT(AI431:AR431)=0,"",AS431-LOOKUP(2,1/(AI431:AR431<>""),AI431:AR431))) | IF(OR(F431="",AT431=""),"",IF(COUNT(AI431:AS431)=0,"",AT431-LOOKUP(2,1/(AI431:AS431<>""),AI431:AS431))) | IF(OR(F431="",AU431=""),"",IF(COUNT(AI431:AT431)=0,"",AU431-LOOKUP(2,1/(AI431:AT431<>""),AI431:AT431))) | IF(OR(F431="",AV431=""),"",IF(COUNT(AI431:AU431)=0,"",AV431-LOOKUP(2,1/(AI431:AU431<>""),AI431:AU431))) | IF(J431="","All_Provinces",IFERROR(VLOOKUP(J431,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K431="","All_Districts",IFERROR(VLOOKUP(K431,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F432="","",ROW()-3) | [18 empty] | IF(AQ432="","",AQ432) |  |  |  | IF(W432<>"",W432,IF(OR(T432="",V432=""),"",EDATE(T432,V432))) |  |  |  |  | IF(F432="","",IF(COUNT(AI432:AV432)=0,IF(AA432="","Not started",AA432),SUBSTITUTE(LOOKUP(2,1/(AI432:AV432<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F432="",COUNT(AI432:AV432)=0),"",TODAY()-LOOKUP(2,1/(AI432:AV432<>""),AI432:AV432)) | IF(OR(F432="",COUNT(AI432:AV432)<2),"",LOOKUP(2,1/(AI432:AV432<>""),AI432:AV432)-MIN(AI432:AV432)) | IF(OR(AD432="",AC432="Not started",AC432=""),"",IFERROR(AD432-IF(VLOOKUP(AC432,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC432,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F432="","",IF(OR(AA432="Cancelled",AC432="Cancelled"),"Cancelled",IF(OR(AC432="Completed / Handover",Y432<>"",Z432>=100),"Completed — on track",IF(O432="Not awarded",IF(U432="",IF(X432="","No planned date",IF(TODAY()>X432,"Behind — past planned date",IF(X432-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U432,"Behind — award date passed",IF(U432-TODAY()<=30,"At risk — close to off track","On track"))),IF(X432="","No planned date",IF(AND(TODAY()>X432,OR(Z432="",Z432<100)),"Behind — past end date",IF(AND(T432<>"",X432<>"",Z432<>"",(Z432<100),((TODAY()-T432)/MAX(X432-T432,1)*100)-Z432>15),"Behind — progress lag",IF(AND(X432-TODAY()<=30,X432-TODAY()>=0,OR(Z432="",Z432<90)),"At risk — close to off track","On track")))))))) | IF(OR(F432="",AC432="Completed / Handover",AC432="Cancelled"),"",IF(O432="Not awarded",IF(U432<>"",U432-TODAY(),IF(X432="","",X432-TODAY())),IF(X432="","",X432-TODAY()))) | [14 empty] | IF(OR(F432="",AJ432=""),"",IF(COUNT(AI432:AI432)=0,"",AJ432-LOOKUP(2,1/(AI432:AI432<>""),AI432:AI432))) | IF(OR(F432="",AK432=""),"",IF(COUNT(AI432:AJ432)=0,"",AK432-LOOKUP(2,1/(AI432:AJ432<>""),AI432:AJ432))) | IF(OR(F432="",AL432=""),"",IF(COUNT(AI432:AK432)=0,"",AL432-LOOKUP(2,1/(AI432:AK432<>""),AI432:AK432))) | IF(OR(F432="",AM432=""),"",IF(COUNT(AI432:AL432)=0,"",AM432-LOOKUP(2,1/(AI432:AL432<>""),AI432:AL432))) | IF(OR(F432="",AN432=""),"",IF(COUNT(AI432:AM432)=0,"",AN432-LOOKUP(2,1/(AI432:AM432<>""),AI432:AM432))) | IF(OR(F432="",AO432=""),"",IF(COUNT(AI432:AN432)=0,"",AO432-LOOKUP(2,1/(AI432:AN432<>""),AI432:AN432))) | IF(OR(F432="",AP432=""),"",IF(COUNT(AI432:AO432)=0,"",AP432-LOOKUP(2,1/(AI432:AO432<>""),AI432:AO432))) | IF(OR(F432="",AQ432=""),"",IF(COUNT(AI432:AP432)=0,"",AQ432-LOOKUP(2,1/(AI432:AP432<>""),AI432:AP432))) | IF(OR(F432="",AR432=""),"",IF(COUNT(AI432:AQ432)=0,"",AR432-LOOKUP(2,1/(AI432:AQ432<>""),AI432:AQ432))) | IF(OR(F432="",AS432=""),"",IF(COUNT(AI432:AR432)=0,"",AS432-LOOKUP(2,1/(AI432:AR432<>""),AI432:AR432))) | IF(OR(F432="",AT432=""),"",IF(COUNT(AI432:AS432)=0,"",AT432-LOOKUP(2,1/(AI432:AS432<>""),AI432:AS432))) | IF(OR(F432="",AU432=""),"",IF(COUNT(AI432:AT432)=0,"",AU432-LOOKUP(2,1/(AI432:AT432<>""),AI432:AT432))) | IF(OR(F432="",AV432=""),"",IF(COUNT(AI432:AU432)=0,"",AV432-LOOKUP(2,1/(AI432:AU432<>""),AI432:AU432))) | IF(J432="","All_Provinces",IFERROR(VLOOKUP(J432,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K432="","All_Districts",IFERROR(VLOOKUP(K432,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F433="","",ROW()-3) | [18 empty] | IF(AQ433="","",AQ433) |  |  |  | IF(W433<>"",W433,IF(OR(T433="",V433=""),"",EDATE(T433,V433))) |  |  |  |  | IF(F433="","",IF(COUNT(AI433:AV433)=0,IF(AA433="","Not started",AA433),SUBSTITUTE(LOOKUP(2,1/(AI433:AV433<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F433="",COUNT(AI433:AV433)=0),"",TODAY()-LOOKUP(2,1/(AI433:AV433<>""),AI433:AV433)) | IF(OR(F433="",COUNT(AI433:AV433)<2),"",LOOKUP(2,1/(AI433:AV433<>""),AI433:AV433)-MIN(AI433:AV433)) | IF(OR(AD433="",AC433="Not started",AC433=""),"",IFERROR(AD433-IF(VLOOKUP(AC433,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC433,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F433="","",IF(OR(AA433="Cancelled",AC433="Cancelled"),"Cancelled",IF(OR(AC433="Completed / Handover",Y433<>"",Z433>=100),"Completed — on track",IF(O433="Not awarded",IF(U433="",IF(X433="","No planned date",IF(TODAY()>X433,"Behind — past planned date",IF(X433-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U433,"Behind — award date passed",IF(U433-TODAY()<=30,"At risk — close to off track","On track"))),IF(X433="","No planned date",IF(AND(TODAY()>X433,OR(Z433="",Z433<100)),"Behind — past end date",IF(AND(T433<>"",X433<>"",Z433<>"",(Z433<100),((TODAY()-T433)/MAX(X433-T433,1)*100)-Z433>15),"Behind — progress lag",IF(AND(X433-TODAY()<=30,X433-TODAY()>=0,OR(Z433="",Z433<90)),"At risk — close to off track","On track")))))))) | IF(OR(F433="",AC433="Completed / Handover",AC433="Cancelled"),"",IF(O433="Not awarded",IF(U433<>"",U433-TODAY(),IF(X433="","",X433-TODAY())),IF(X433="","",X433-TODAY()))) | [14 empty] | IF(OR(F433="",AJ433=""),"",IF(COUNT(AI433:AI433)=0,"",AJ433-LOOKUP(2,1/(AI433:AI433<>""),AI433:AI433))) | IF(OR(F433="",AK433=""),"",IF(COUNT(AI433:AJ433)=0,"",AK433-LOOKUP(2,1/(AI433:AJ433<>""),AI433:AJ433))) | IF(OR(F433="",AL433=""),"",IF(COUNT(AI433:AK433)=0,"",AL433-LOOKUP(2,1/(AI433:AK433<>""),AI433:AK433))) | IF(OR(F433="",AM433=""),"",IF(COUNT(AI433:AL433)=0,"",AM433-LOOKUP(2,1/(AI433:AL433<>""),AI433:AL433))) | IF(OR(F433="",AN433=""),"",IF(COUNT(AI433:AM433)=0,"",AN433-LOOKUP(2,1/(AI433:AM433<>""),AI433:AM433))) | IF(OR(F433="",AO433=""),"",IF(COUNT(AI433:AN433)=0,"",AO433-LOOKUP(2,1/(AI433:AN433<>""),AI433:AN433))) | IF(OR(F433="",AP433=""),"",IF(COUNT(AI433:AO433)=0,"",AP433-LOOKUP(2,1/(AI433:AO433<>""),AI433:AO433))) | IF(OR(F433="",AQ433=""),"",IF(COUNT(AI433:AP433)=0,"",AQ433-LOOKUP(2,1/(AI433:AP433<>""),AI433:AP433))) | IF(OR(F433="",AR433=""),"",IF(COUNT(AI433:AQ433)=0,"",AR433-LOOKUP(2,1/(AI433:AQ433<>""),AI433:AQ433))) | IF(OR(F433="",AS433=""),"",IF(COUNT(AI433:AR433)=0,"",AS433-LOOKUP(2,1/(AI433:AR433<>""),AI433:AR433))) | IF(OR(F433="",AT433=""),"",IF(COUNT(AI433:AS433)=0,"",AT433-LOOKUP(2,1/(AI433:AS433<>""),AI433:AS433))) | IF(OR(F433="",AU433=""),"",IF(COUNT(AI433:AT433)=0,"",AU433-LOOKUP(2,1/(AI433:AT433<>""),AI433:AT433))) | IF(OR(F433="",AV433=""),"",IF(COUNT(AI433:AU433)=0,"",AV433-LOOKUP(2,1/(AI433:AU433<>""),AI433:AU433))) | IF(J433="","All_Provinces",IFERROR(VLOOKUP(J433,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K433="","All_Districts",IFERROR(VLOOKUP(K433,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F434="","",ROW()-3) | [18 empty] | IF(AQ434="","",AQ434) |  |  |  | IF(W434<>"",W434,IF(OR(T434="",V434=""),"",EDATE(T434,V434))) |  |  |  |  | IF(F434="","",IF(COUNT(AI434:AV434)=0,IF(AA434="","Not started",AA434),SUBSTITUTE(LOOKUP(2,1/(AI434:AV434<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F434="",COUNT(AI434:AV434)=0),"",TODAY()-LOOKUP(2,1/(AI434:AV434<>""),AI434:AV434)) | IF(OR(F434="",COUNT(AI434:AV434)<2),"",LOOKUP(2,1/(AI434:AV434<>""),AI434:AV434)-MIN(AI434:AV434)) | IF(OR(AD434="",AC434="Not started",AC434=""),"",IFERROR(AD434-IF(VLOOKUP(AC434,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC434,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F434="","",IF(OR(AA434="Cancelled",AC434="Cancelled"),"Cancelled",IF(OR(AC434="Completed / Handover",Y434<>"",Z434>=100),"Completed — on track",IF(O434="Not awarded",IF(U434="",IF(X434="","No planned date",IF(TODAY()>X434,"Behind — past planned date",IF(X434-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U434,"Behind — award date passed",IF(U434-TODAY()<=30,"At risk — close to off track","On track"))),IF(X434="","No planned date",IF(AND(TODAY()>X434,OR(Z434="",Z434<100)),"Behind — past end date",IF(AND(T434<>"",X434<>"",Z434<>"",(Z434<100),((TODAY()-T434)/MAX(X434-T434,1)*100)-Z434>15),"Behind — progress lag",IF(AND(X434-TODAY()<=30,X434-TODAY()>=0,OR(Z434="",Z434<90)),"At risk — close to off track","On track")))))))) | IF(OR(F434="",AC434="Completed / Handover",AC434="Cancelled"),"",IF(O434="Not awarded",IF(U434<>"",U434-TODAY(),IF(X434="","",X434-TODAY())),IF(X434="","",X434-TODAY()))) | [14 empty] | IF(OR(F434="",AJ434=""),"",IF(COUNT(AI434:AI434)=0,"",AJ434-LOOKUP(2,1/(AI434:AI434<>""),AI434:AI434))) | IF(OR(F434="",AK434=""),"",IF(COUNT(AI434:AJ434)=0,"",AK434-LOOKUP(2,1/(AI434:AJ434<>""),AI434:AJ434))) | IF(OR(F434="",AL434=""),"",IF(COUNT(AI434:AK434)=0,"",AL434-LOOKUP(2,1/(AI434:AK434<>""),AI434:AK434))) | IF(OR(F434="",AM434=""),"",IF(COUNT(AI434:AL434)=0,"",AM434-LOOKUP(2,1/(AI434:AL434<>""),AI434:AL434))) | IF(OR(F434="",AN434=""),"",IF(COUNT(AI434:AM434)=0,"",AN434-LOOKUP(2,1/(AI434:AM434<>""),AI434:AM434))) | IF(OR(F434="",AO434=""),"",IF(COUNT(AI434:AN434)=0,"",AO434-LOOKUP(2,1/(AI434:AN434<>""),AI434:AN434))) | IF(OR(F434="",AP434=""),"",IF(COUNT(AI434:AO434)=0,"",AP434-LOOKUP(2,1/(AI434:AO434<>""),AI434:AO434))) | IF(OR(F434="",AQ434=""),"",IF(COUNT(AI434:AP434)=0,"",AQ434-LOOKUP(2,1/(AI434:AP434<>""),AI434:AP434))) | IF(OR(F434="",AR434=""),"",IF(COUNT(AI434:AQ434)=0,"",AR434-LOOKUP(2,1/(AI434:AQ434<>""),AI434:AQ434))) | IF(OR(F434="",AS434=""),"",IF(COUNT(AI434:AR434)=0,"",AS434-LOOKUP(2,1/(AI434:AR434<>""),AI434:AR434))) | IF(OR(F434="",AT434=""),"",IF(COUNT(AI434:AS434)=0,"",AT434-LOOKUP(2,1/(AI434:AS434<>""),AI434:AS434))) | IF(OR(F434="",AU434=""),"",IF(COUNT(AI434:AT434)=0,"",AU434-LOOKUP(2,1/(AI434:AT434<>""),AI434:AT434))) | IF(OR(F434="",AV434=""),"",IF(COUNT(AI434:AU434)=0,"",AV434-LOOKUP(2,1/(AI434:AU434<>""),AI434:AU434))) | IF(J434="","All_Provinces",IFERROR(VLOOKUP(J434,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K434="","All_Districts",IFERROR(VLOOKUP(K434,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F435="","",ROW()-3) | [18 empty] | IF(AQ435="","",AQ435) |  |  |  | IF(W435<>"",W435,IF(OR(T435="",V435=""),"",EDATE(T435,V435))) |  |  |  |  | IF(F435="","",IF(COUNT(AI435:AV435)=0,IF(AA435="","Not started",AA435),SUBSTITUTE(LOOKUP(2,1/(AI435:AV435<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F435="",COUNT(AI435:AV435)=0),"",TODAY()-LOOKUP(2,1/(AI435:AV435<>""),AI435:AV435)) | IF(OR(F435="",COUNT(AI435:AV435)<2),"",LOOKUP(2,1/(AI435:AV435<>""),AI435:AV435)-MIN(AI435:AV435)) | IF(OR(AD435="",AC435="Not started",AC435=""),"",IFERROR(AD435-IF(VLOOKUP(AC435,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC435,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F435="","",IF(OR(AA435="Cancelled",AC435="Cancelled"),"Cancelled",IF(OR(AC435="Completed / Handover",Y435<>"",Z435>=100),"Completed — on track",IF(O435="Not awarded",IF(U435="",IF(X435="","No planned date",IF(TODAY()>X435,"Behind — past planned date",IF(X435-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U435,"Behind — award date passed",IF(U435-TODAY()<=30,"At risk — close to off track","On track"))),IF(X435="","No planned date",IF(AND(TODAY()>X435,OR(Z435="",Z435<100)),"Behind — past end date",IF(AND(T435<>"",X435<>"",Z435<>"",(Z435<100),((TODAY()-T435)/MAX(X435-T435,1)*100)-Z435>15),"Behind — progress lag",IF(AND(X435-TODAY()<=30,X435-TODAY()>=0,OR(Z435="",Z435<90)),"At risk — close to off track","On track")))))))) | IF(OR(F435="",AC435="Completed / Handover",AC435="Cancelled"),"",IF(O435="Not awarded",IF(U435<>"",U435-TODAY(),IF(X435="","",X435-TODAY())),IF(X435="","",X435-TODAY()))) | [14 empty] | IF(OR(F435="",AJ435=""),"",IF(COUNT(AI435:AI435)=0,"",AJ435-LOOKUP(2,1/(AI435:AI435<>""),AI435:AI435))) | IF(OR(F435="",AK435=""),"",IF(COUNT(AI435:AJ435)=0,"",AK435-LOOKUP(2,1/(AI435:AJ435<>""),AI435:AJ435))) | IF(OR(F435="",AL435=""),"",IF(COUNT(AI435:AK435)=0,"",AL435-LOOKUP(2,1/(AI435:AK435<>""),AI435:AK435))) | IF(OR(F435="",AM435=""),"",IF(COUNT(AI435:AL435)=0,"",AM435-LOOKUP(2,1/(AI435:AL435<>""),AI435:AL435))) | IF(OR(F435="",AN435=""),"",IF(COUNT(AI435:AM435)=0,"",AN435-LOOKUP(2,1/(AI435:AM435<>""),AI435:AM435))) | IF(OR(F435="",AO435=""),"",IF(COUNT(AI435:AN435)=0,"",AO435-LOOKUP(2,1/(AI435:AN435<>""),AI435:AN435))) | IF(OR(F435="",AP435=""),"",IF(COUNT(AI435:AO435)=0,"",AP435-LOOKUP(2,1/(AI435:AO435<>""),AI435:AO435))) | IF(OR(F435="",AQ435=""),"",IF(COUNT(AI435:AP435)=0,"",AQ435-LOOKUP(2,1/(AI435:AP435<>""),AI435:AP435))) | IF(OR(F435="",AR435=""),"",IF(COUNT(AI435:AQ435)=0,"",AR435-LOOKUP(2,1/(AI435:AQ435<>""),AI435:AQ435))) | IF(OR(F435="",AS435=""),"",IF(COUNT(AI435:AR435)=0,"",AS435-LOOKUP(2,1/(AI435:AR435<>""),AI435:AR435))) | IF(OR(F435="",AT435=""),"",IF(COUNT(AI435:AS435)=0,"",AT435-LOOKUP(2,1/(AI435:AS435<>""),AI435:AS435))) | IF(OR(F435="",AU435=""),"",IF(COUNT(AI435:AT435)=0,"",AU435-LOOKUP(2,1/(AI435:AT435<>""),AI435:AT435))) | IF(OR(F435="",AV435=""),"",IF(COUNT(AI435:AU435)=0,"",AV435-LOOKUP(2,1/(AI435:AU435<>""),AI435:AU435))) | IF(J435="","All_Provinces",IFERROR(VLOOKUP(J435,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K435="","All_Districts",IFERROR(VLOOKUP(K435,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F436="","",ROW()-3) | [18 empty] | IF(AQ436="","",AQ436) |  |  |  | IF(W436<>"",W436,IF(OR(T436="",V436=""),"",EDATE(T436,V436))) |  |  |  |  | IF(F436="","",IF(COUNT(AI436:AV436)=0,IF(AA436="","Not started",AA436),SUBSTITUTE(LOOKUP(2,1/(AI436:AV436<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F436="",COUNT(AI436:AV436)=0),"",TODAY()-LOOKUP(2,1/(AI436:AV436<>""),AI436:AV436)) | IF(OR(F436="",COUNT(AI436:AV436)<2),"",LOOKUP(2,1/(AI436:AV436<>""),AI436:AV436)-MIN(AI436:AV436)) | IF(OR(AD436="",AC436="Not started",AC436=""),"",IFERROR(AD436-IF(VLOOKUP(AC436,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC436,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F436="","",IF(OR(AA436="Cancelled",AC436="Cancelled"),"Cancelled",IF(OR(AC436="Completed / Handover",Y436<>"",Z436>=100),"Completed — on track",IF(O436="Not awarded",IF(U436="",IF(X436="","No planned date",IF(TODAY()>X436,"Behind — past planned date",IF(X436-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U436,"Behind — award date passed",IF(U436-TODAY()<=30,"At risk — close to off track","On track"))),IF(X436="","No planned date",IF(AND(TODAY()>X436,OR(Z436="",Z436<100)),"Behind — past end date",IF(AND(T436<>"",X436<>"",Z436<>"",(Z436<100),((TODAY()-T436)/MAX(X436-T436,1)*100)-Z436>15),"Behind — progress lag",IF(AND(X436-TODAY()<=30,X436-TODAY()>=0,OR(Z436="",Z436<90)),"At risk — close to off track","On track")))))))) | IF(OR(F436="",AC436="Completed / Handover",AC436="Cancelled"),"",IF(O436="Not awarded",IF(U436<>"",U436-TODAY(),IF(X436="","",X436-TODAY())),IF(X436="","",X436-TODAY()))) | [14 empty] | IF(OR(F436="",AJ436=""),"",IF(COUNT(AI436:AI436)=0,"",AJ436-LOOKUP(2,1/(AI436:AI436<>""),AI436:AI436))) | IF(OR(F436="",AK436=""),"",IF(COUNT(AI436:AJ436)=0,"",AK436-LOOKUP(2,1/(AI436:AJ436<>""),AI436:AJ436))) | IF(OR(F436="",AL436=""),"",IF(COUNT(AI436:AK436)=0,"",AL436-LOOKUP(2,1/(AI436:AK436<>""),AI436:AK436))) | IF(OR(F436="",AM436=""),"",IF(COUNT(AI436:AL436)=0,"",AM436-LOOKUP(2,1/(AI436:AL436<>""),AI436:AL436))) | IF(OR(F436="",AN436=""),"",IF(COUNT(AI436:AM436)=0,"",AN436-LOOKUP(2,1/(AI436:AM436<>""),AI436:AM436))) | IF(OR(F436="",AO436=""),"",IF(COUNT(AI436:AN436)=0,"",AO436-LOOKUP(2,1/(AI436:AN436<>""),AI436:AN436))) | IF(OR(F436="",AP436=""),"",IF(COUNT(AI436:AO436)=0,"",AP436-LOOKUP(2,1/(AI436:AO436<>""),AI436:AO436))) | IF(OR(F436="",AQ436=""),"",IF(COUNT(AI436:AP436)=0,"",AQ436-LOOKUP(2,1/(AI436:AP436<>""),AI436:AP436))) | IF(OR(F436="",AR436=""),"",IF(COUNT(AI436:AQ436)=0,"",AR436-LOOKUP(2,1/(AI436:AQ436<>""),AI436:AQ436))) | IF(OR(F436="",AS436=""),"",IF(COUNT(AI436:AR436)=0,"",AS436-LOOKUP(2,1/(AI436:AR436<>""),AI436:AR436))) | IF(OR(F436="",AT436=""),"",IF(COUNT(AI436:AS436)=0,"",AT436-LOOKUP(2,1/(AI436:AS436<>""),AI436:AS436))) | IF(OR(F436="",AU436=""),"",IF(COUNT(AI436:AT436)=0,"",AU436-LOOKUP(2,1/(AI436:AT436<>""),AI436:AT436))) | IF(OR(F436="",AV436=""),"",IF(COUNT(AI436:AU436)=0,"",AV436-LOOKUP(2,1/(AI436:AU436<>""),AI436:AU436))) | IF(J436="","All_Provinces",IFERROR(VLOOKUP(J436,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K436="","All_Districts",IFERROR(VLOOKUP(K436,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F437="","",ROW()-3) | [18 empty] | IF(AQ437="","",AQ437) |  |  |  | IF(W437<>"",W437,IF(OR(T437="",V437=""),"",EDATE(T437,V437))) |  |  |  |  | IF(F437="","",IF(COUNT(AI437:AV437)=0,IF(AA437="","Not started",AA437),SUBSTITUTE(LOOKUP(2,1/(AI437:AV437<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F437="",COUNT(AI437:AV437)=0),"",TODAY()-LOOKUP(2,1/(AI437:AV437<>""),AI437:AV437)) | IF(OR(F437="",COUNT(AI437:AV437)<2),"",LOOKUP(2,1/(AI437:AV437<>""),AI437:AV437)-MIN(AI437:AV437)) | IF(OR(AD437="",AC437="Not started",AC437=""),"",IFERROR(AD437-IF(VLOOKUP(AC437,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC437,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F437="","",IF(OR(AA437="Cancelled",AC437="Cancelled"),"Cancelled",IF(OR(AC437="Completed / Handover",Y437<>"",Z437>=100),"Completed — on track",IF(O437="Not awarded",IF(U437="",IF(X437="","No planned date",IF(TODAY()>X437,"Behind — past planned date",IF(X437-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U437,"Behind — award date passed",IF(U437-TODAY()<=30,"At risk — close to off track","On track"))),IF(X437="","No planned date",IF(AND(TODAY()>X437,OR(Z437="",Z437<100)),"Behind — past end date",IF(AND(T437<>"",X437<>"",Z437<>"",(Z437<100),((TODAY()-T437)/MAX(X437-T437,1)*100)-Z437>15),"Behind — progress lag",IF(AND(X437-TODAY()<=30,X437-TODAY()>=0,OR(Z437="",Z437<90)),"At risk — close to off track","On track")))))))) | IF(OR(F437="",AC437="Completed / Handover",AC437="Cancelled"),"",IF(O437="Not awarded",IF(U437<>"",U437-TODAY(),IF(X437="","",X437-TODAY())),IF(X437="","",X437-TODAY()))) | [14 empty] | IF(OR(F437="",AJ437=""),"",IF(COUNT(AI437:AI437)=0,"",AJ437-LOOKUP(2,1/(AI437:AI437<>""),AI437:AI437))) | IF(OR(F437="",AK437=""),"",IF(COUNT(AI437:AJ437)=0,"",AK437-LOOKUP(2,1/(AI437:AJ437<>""),AI437:AJ437))) | IF(OR(F437="",AL437=""),"",IF(COUNT(AI437:AK437)=0,"",AL437-LOOKUP(2,1/(AI437:AK437<>""),AI437:AK437))) | IF(OR(F437="",AM437=""),"",IF(COUNT(AI437:AL437)=0,"",AM437-LOOKUP(2,1/(AI437:AL437<>""),AI437:AL437))) | IF(OR(F437="",AN437=""),"",IF(COUNT(AI437:AM437)=0,"",AN437-LOOKUP(2,1/(AI437:AM437<>""),AI437:AM437))) | IF(OR(F437="",AO437=""),"",IF(COUNT(AI437:AN437)=0,"",AO437-LOOKUP(2,1/(AI437:AN437<>""),AI437:AN437))) | IF(OR(F437="",AP437=""),"",IF(COUNT(AI437:AO437)=0,"",AP437-LOOKUP(2,1/(AI437:AO437<>""),AI437:AO437))) | IF(OR(F437="",AQ437=""),"",IF(COUNT(AI437:AP437)=0,"",AQ437-LOOKUP(2,1/(AI437:AP437<>""),AI437:AP437))) | IF(OR(F437="",AR437=""),"",IF(COUNT(AI437:AQ437)=0,"",AR437-LOOKUP(2,1/(AI437:AQ437<>""),AI437:AQ437))) | IF(OR(F437="",AS437=""),"",IF(COUNT(AI437:AR437)=0,"",AS437-LOOKUP(2,1/(AI437:AR437<>""),AI437:AR437))) | IF(OR(F437="",AT437=""),"",IF(COUNT(AI437:AS437)=0,"",AT437-LOOKUP(2,1/(AI437:AS437<>""),AI437:AS437))) | IF(OR(F437="",AU437=""),"",IF(COUNT(AI437:AT437)=0,"",AU437-LOOKUP(2,1/(AI437:AT437<>""),AI437:AT437))) | IF(OR(F437="",AV437=""),"",IF(COUNT(AI437:AU437)=0,"",AV437-LOOKUP(2,1/(AI437:AU437<>""),AI437:AU437))) | IF(J437="","All_Provinces",IFERROR(VLOOKUP(J437,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K437="","All_Districts",IFERROR(VLOOKUP(K437,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F438="","",ROW()-3) | [18 empty] | IF(AQ438="","",AQ438) |  |  |  | IF(W438<>"",W438,IF(OR(T438="",V438=""),"",EDATE(T438,V438))) |  |  |  |  | IF(F438="","",IF(COUNT(AI438:AV438)=0,IF(AA438="","Not started",AA438),SUBSTITUTE(LOOKUP(2,1/(AI438:AV438<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F438="",COUNT(AI438:AV438)=0),"",TODAY()-LOOKUP(2,1/(AI438:AV438<>""),AI438:AV438)) | IF(OR(F438="",COUNT(AI438:AV438)<2),"",LOOKUP(2,1/(AI438:AV438<>""),AI438:AV438)-MIN(AI438:AV438)) | IF(OR(AD438="",AC438="Not started",AC438=""),"",IFERROR(AD438-IF(VLOOKUP(AC438,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC438,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F438="","",IF(OR(AA438="Cancelled",AC438="Cancelled"),"Cancelled",IF(OR(AC438="Completed / Handover",Y438<>"",Z438>=100),"Completed — on track",IF(O438="Not awarded",IF(U438="",IF(X438="","No planned date",IF(TODAY()>X438,"Behind — past planned date",IF(X438-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U438,"Behind — award date passed",IF(U438-TODAY()<=30,"At risk — close to off track","On track"))),IF(X438="","No planned date",IF(AND(TODAY()>X438,OR(Z438="",Z438<100)),"Behind — past end date",IF(AND(T438<>"",X438<>"",Z438<>"",(Z438<100),((TODAY()-T438)/MAX(X438-T438,1)*100)-Z438>15),"Behind — progress lag",IF(AND(X438-TODAY()<=30,X438-TODAY()>=0,OR(Z438="",Z438<90)),"At risk — close to off track","On track")))))))) | IF(OR(F438="",AC438="Completed / Handover",AC438="Cancelled"),"",IF(O438="Not awarded",IF(U438<>"",U438-TODAY(),IF(X438="","",X438-TODAY())),IF(X438="","",X438-TODAY()))) | [14 empty] | IF(OR(F438="",AJ438=""),"",IF(COUNT(AI438:AI438)=0,"",AJ438-LOOKUP(2,1/(AI438:AI438<>""),AI438:AI438))) | IF(OR(F438="",AK438=""),"",IF(COUNT(AI438:AJ438)=0,"",AK438-LOOKUP(2,1/(AI438:AJ438<>""),AI438:AJ438))) | IF(OR(F438="",AL438=""),"",IF(COUNT(AI438:AK438)=0,"",AL438-LOOKUP(2,1/(AI438:AK438<>""),AI438:AK438))) | IF(OR(F438="",AM438=""),"",IF(COUNT(AI438:AL438)=0,"",AM438-LOOKUP(2,1/(AI438:AL438<>""),AI438:AL438))) | IF(OR(F438="",AN438=""),"",IF(COUNT(AI438:AM438)=0,"",AN438-LOOKUP(2,1/(AI438:AM438<>""),AI438:AM438))) | IF(OR(F438="",AO438=""),"",IF(COUNT(AI438:AN438)=0,"",AO438-LOOKUP(2,1/(AI438:AN438<>""),AI438:AN438))) | IF(OR(F438="",AP438=""),"",IF(COUNT(AI438:AO438)=0,"",AP438-LOOKUP(2,1/(AI438:AO438<>""),AI438:AO438))) | IF(OR(F438="",AQ438=""),"",IF(COUNT(AI438:AP438)=0,"",AQ438-LOOKUP(2,1/(AI438:AP438<>""),AI438:AP438))) | IF(OR(F438="",AR438=""),"",IF(COUNT(AI438:AQ438)=0,"",AR438-LOOKUP(2,1/(AI438:AQ438<>""),AI438:AQ438))) | IF(OR(F438="",AS438=""),"",IF(COUNT(AI438:AR438)=0,"",AS438-LOOKUP(2,1/(AI438:AR438<>""),AI438:AR438))) | IF(OR(F438="",AT438=""),"",IF(COUNT(AI438:AS438)=0,"",AT438-LOOKUP(2,1/(AI438:AS438<>""),AI438:AS438))) | IF(OR(F438="",AU438=""),"",IF(COUNT(AI438:AT438)=0,"",AU438-LOOKUP(2,1/(AI438:AT438<>""),AI438:AT438))) | IF(OR(F438="",AV438=""),"",IF(COUNT(AI438:AU438)=0,"",AV438-LOOKUP(2,1/(AI438:AU438<>""),AI438:AU438))) | IF(J438="","All_Provinces",IFERROR(VLOOKUP(J438,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K438="","All_Districts",IFERROR(VLOOKUP(K438,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F439="","",ROW()-3) | [18 empty] | IF(AQ439="","",AQ439) |  |  |  | IF(W439<>"",W439,IF(OR(T439="",V439=""),"",EDATE(T439,V439))) |  |  |  |  | IF(F439="","",IF(COUNT(AI439:AV439)=0,IF(AA439="","Not started",AA439),SUBSTITUTE(LOOKUP(2,1/(AI439:AV439<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F439="",COUNT(AI439:AV439)=0),"",TODAY()-LOOKUP(2,1/(AI439:AV439<>""),AI439:AV439)) | IF(OR(F439="",COUNT(AI439:AV439)<2),"",LOOKUP(2,1/(AI439:AV439<>""),AI439:AV439)-MIN(AI439:AV439)) | IF(OR(AD439="",AC439="Not started",AC439=""),"",IFERROR(AD439-IF(VLOOKUP(AC439,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC439,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F439="","",IF(OR(AA439="Cancelled",AC439="Cancelled"),"Cancelled",IF(OR(AC439="Completed / Handover",Y439<>"",Z439>=100),"Completed — on track",IF(O439="Not awarded",IF(U439="",IF(X439="","No planned date",IF(TODAY()>X439,"Behind — past planned date",IF(X439-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U439,"Behind — award date passed",IF(U439-TODAY()<=30,"At risk — close to off track","On track"))),IF(X439="","No planned date",IF(AND(TODAY()>X439,OR(Z439="",Z439<100)),"Behind — past end date",IF(AND(T439<>"",X439<>"",Z439<>"",(Z439<100),((TODAY()-T439)/MAX(X439-T439,1)*100)-Z439>15),"Behind — progress lag",IF(AND(X439-TODAY()<=30,X439-TODAY()>=0,OR(Z439="",Z439<90)),"At risk — close to off track","On track")))))))) | IF(OR(F439="",AC439="Completed / Handover",AC439="Cancelled"),"",IF(O439="Not awarded",IF(U439<>"",U439-TODAY(),IF(X439="","",X439-TODAY())),IF(X439="","",X439-TODAY()))) | [14 empty] | IF(OR(F439="",AJ439=""),"",IF(COUNT(AI439:AI439)=0,"",AJ439-LOOKUP(2,1/(AI439:AI439<>""),AI439:AI439))) | IF(OR(F439="",AK439=""),"",IF(COUNT(AI439:AJ439)=0,"",AK439-LOOKUP(2,1/(AI439:AJ439<>""),AI439:AJ439))) | IF(OR(F439="",AL439=""),"",IF(COUNT(AI439:AK439)=0,"",AL439-LOOKUP(2,1/(AI439:AK439<>""),AI439:AK439))) | IF(OR(F439="",AM439=""),"",IF(COUNT(AI439:AL439)=0,"",AM439-LOOKUP(2,1/(AI439:AL439<>""),AI439:AL439))) | IF(OR(F439="",AN439=""),"",IF(COUNT(AI439:AM439)=0,"",AN439-LOOKUP(2,1/(AI439:AM439<>""),AI439:AM439))) | IF(OR(F439="",AO439=""),"",IF(COUNT(AI439:AN439)=0,"",AO439-LOOKUP(2,1/(AI439:AN439<>""),AI439:AN439))) | IF(OR(F439="",AP439=""),"",IF(COUNT(AI439:AO439)=0,"",AP439-LOOKUP(2,1/(AI439:AO439<>""),AI439:AO439))) | IF(OR(F439="",AQ439=""),"",IF(COUNT(AI439:AP439)=0,"",AQ439-LOOKUP(2,1/(AI439:AP439<>""),AI439:AP439))) | IF(OR(F439="",AR439=""),"",IF(COUNT(AI439:AQ439)=0,"",AR439-LOOKUP(2,1/(AI439:AQ439<>""),AI439:AQ439))) | IF(OR(F439="",AS439=""),"",IF(COUNT(AI439:AR439)=0,"",AS439-LOOKUP(2,1/(AI439:AR439<>""),AI439:AR439))) | IF(OR(F439="",AT439=""),"",IF(COUNT(AI439:AS439)=0,"",AT439-LOOKUP(2,1/(AI439:AS439<>""),AI439:AS439))) | IF(OR(F439="",AU439=""),"",IF(COUNT(AI439:AT439)=0,"",AU439-LOOKUP(2,1/(AI439:AT439<>""),AI439:AT439))) | IF(OR(F439="",AV439=""),"",IF(COUNT(AI439:AU439)=0,"",AV439-LOOKUP(2,1/(AI439:AU439<>""),AI439:AU439))) | IF(J439="","All_Provinces",IFERROR(VLOOKUP(J439,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K439="","All_Districts",IFERROR(VLOOKUP(K439,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F440="","",ROW()-3) | [18 empty] | IF(AQ440="","",AQ440) |  |  |  | IF(W440<>"",W440,IF(OR(T440="",V440=""),"",EDATE(T440,V440))) |  |  |  |  | IF(F440="","",IF(COUNT(AI440:AV440)=0,IF(AA440="","Not started",AA440),SUBSTITUTE(LOOKUP(2,1/(AI440:AV440<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F440="",COUNT(AI440:AV440)=0),"",TODAY()-LOOKUP(2,1/(AI440:AV440<>""),AI440:AV440)) | IF(OR(F440="",COUNT(AI440:AV440)<2),"",LOOKUP(2,1/(AI440:AV440<>""),AI440:AV440)-MIN(AI440:AV440)) | IF(OR(AD440="",AC440="Not started",AC440=""),"",IFERROR(AD440-IF(VLOOKUP(AC440,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC440,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F440="","",IF(OR(AA440="Cancelled",AC440="Cancelled"),"Cancelled",IF(OR(AC440="Completed / Handover",Y440<>"",Z440>=100),"Completed — on track",IF(O440="Not awarded",IF(U440="",IF(X440="","No planned date",IF(TODAY()>X440,"Behind — past planned date",IF(X440-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U440,"Behind — award date passed",IF(U440-TODAY()<=30,"At risk — close to off track","On track"))),IF(X440="","No planned date",IF(AND(TODAY()>X440,OR(Z440="",Z440<100)),"Behind — past end date",IF(AND(T440<>"",X440<>"",Z440<>"",(Z440<100),((TODAY()-T440)/MAX(X440-T440,1)*100)-Z440>15),"Behind — progress lag",IF(AND(X440-TODAY()<=30,X440-TODAY()>=0,OR(Z440="",Z440<90)),"At risk — close to off track","On track")))))))) | IF(OR(F440="",AC440="Completed / Handover",AC440="Cancelled"),"",IF(O440="Not awarded",IF(U440<>"",U440-TODAY(),IF(X440="","",X440-TODAY())),IF(X440="","",X440-TODAY()))) | [14 empty] | IF(OR(F440="",AJ440=""),"",IF(COUNT(AI440:AI440)=0,"",AJ440-LOOKUP(2,1/(AI440:AI440<>""),AI440:AI440))) | IF(OR(F440="",AK440=""),"",IF(COUNT(AI440:AJ440)=0,"",AK440-LOOKUP(2,1/(AI440:AJ440<>""),AI440:AJ440))) | IF(OR(F440="",AL440=""),"",IF(COUNT(AI440:AK440)=0,"",AL440-LOOKUP(2,1/(AI440:AK440<>""),AI440:AK440))) | IF(OR(F440="",AM440=""),"",IF(COUNT(AI440:AL440)=0,"",AM440-LOOKUP(2,1/(AI440:AL440<>""),AI440:AL440))) | IF(OR(F440="",AN440=""),"",IF(COUNT(AI440:AM440)=0,"",AN440-LOOKUP(2,1/(AI440:AM440<>""),AI440:AM440))) | IF(OR(F440="",AO440=""),"",IF(COUNT(AI440:AN440)=0,"",AO440-LOOKUP(2,1/(AI440:AN440<>""),AI440:AN440))) | IF(OR(F440="",AP440=""),"",IF(COUNT(AI440:AO440)=0,"",AP440-LOOKUP(2,1/(AI440:AO440<>""),AI440:AO440))) | IF(OR(F440="",AQ440=""),"",IF(COUNT(AI440:AP440)=0,"",AQ440-LOOKUP(2,1/(AI440:AP440<>""),AI440:AP440))) | IF(OR(F440="",AR440=""),"",IF(COUNT(AI440:AQ440)=0,"",AR440-LOOKUP(2,1/(AI440:AQ440<>""),AI440:AQ440))) | IF(OR(F440="",AS440=""),"",IF(COUNT(AI440:AR440)=0,"",AS440-LOOKUP(2,1/(AI440:AR440<>""),AI440:AR440))) | IF(OR(F440="",AT440=""),"",IF(COUNT(AI440:AS440)=0,"",AT440-LOOKUP(2,1/(AI440:AS440<>""),AI440:AS440))) | IF(OR(F440="",AU440=""),"",IF(COUNT(AI440:AT440)=0,"",AU440-LOOKUP(2,1/(AI440:AT440<>""),AI440:AT440))) | IF(OR(F440="",AV440=""),"",IF(COUNT(AI440:AU440)=0,"",AV440-LOOKUP(2,1/(AI440:AU440<>""),AI440:AU440))) | IF(J440="","All_Provinces",IFERROR(VLOOKUP(J440,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K440="","All_Districts",IFERROR(VLOOKUP(K440,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F441="","",ROW()-3) | [18 empty] | IF(AQ441="","",AQ441) |  |  |  | IF(W441<>"",W441,IF(OR(T441="",V441=""),"",EDATE(T441,V441))) |  |  |  |  | IF(F441="","",IF(COUNT(AI441:AV441)=0,IF(AA441="","Not started",AA441),SUBSTITUTE(LOOKUP(2,1/(AI441:AV441<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F441="",COUNT(AI441:AV441)=0),"",TODAY()-LOOKUP(2,1/(AI441:AV441<>""),AI441:AV441)) | IF(OR(F441="",COUNT(AI441:AV441)<2),"",LOOKUP(2,1/(AI441:AV441<>""),AI441:AV441)-MIN(AI441:AV441)) | IF(OR(AD441="",AC441="Not started",AC441=""),"",IFERROR(AD441-IF(VLOOKUP(AC441,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC441,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F441="","",IF(OR(AA441="Cancelled",AC441="Cancelled"),"Cancelled",IF(OR(AC441="Completed / Handover",Y441<>"",Z441>=100),"Completed — on track",IF(O441="Not awarded",IF(U441="",IF(X441="","No planned date",IF(TODAY()>X441,"Behind — past planned date",IF(X441-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U441,"Behind — award date passed",IF(U441-TODAY()<=30,"At risk — close to off track","On track"))),IF(X441="","No planned date",IF(AND(TODAY()>X441,OR(Z441="",Z441<100)),"Behind — past end date",IF(AND(T441<>"",X441<>"",Z441<>"",(Z441<100),((TODAY()-T441)/MAX(X441-T441,1)*100)-Z441>15),"Behind — progress lag",IF(AND(X441-TODAY()<=30,X441-TODAY()>=0,OR(Z441="",Z441<90)),"At risk — close to off track","On track")))))))) | IF(OR(F441="",AC441="Completed / Handover",AC441="Cancelled"),"",IF(O441="Not awarded",IF(U441<>"",U441-TODAY(),IF(X441="","",X441-TODAY())),IF(X441="","",X441-TODAY()))) | [14 empty] | IF(OR(F441="",AJ441=""),"",IF(COUNT(AI441:AI441)=0,"",AJ441-LOOKUP(2,1/(AI441:AI441<>""),AI441:AI441))) | IF(OR(F441="",AK441=""),"",IF(COUNT(AI441:AJ441)=0,"",AK441-LOOKUP(2,1/(AI441:AJ441<>""),AI441:AJ441))) | IF(OR(F441="",AL441=""),"",IF(COUNT(AI441:AK441)=0,"",AL441-LOOKUP(2,1/(AI441:AK441<>""),AI441:AK441))) | IF(OR(F441="",AM441=""),"",IF(COUNT(AI441:AL441)=0,"",AM441-LOOKUP(2,1/(AI441:AL441<>""),AI441:AL441))) | IF(OR(F441="",AN441=""),"",IF(COUNT(AI441:AM441)=0,"",AN441-LOOKUP(2,1/(AI441:AM441<>""),AI441:AM441))) | IF(OR(F441="",AO441=""),"",IF(COUNT(AI441:AN441)=0,"",AO441-LOOKUP(2,1/(AI441:AN441<>""),AI441:AN441))) | IF(OR(F441="",AP441=""),"",IF(COUNT(AI441:AO441)=0,"",AP441-LOOKUP(2,1/(AI441:AO441<>""),AI441:AO441))) | IF(OR(F441="",AQ441=""),"",IF(COUNT(AI441:AP441)=0,"",AQ441-LOOKUP(2,1/(AI441:AP441<>""),AI441:AP441))) | IF(OR(F441="",AR441=""),"",IF(COUNT(AI441:AQ441)=0,"",AR441-LOOKUP(2,1/(AI441:AQ441<>""),AI441:AQ441))) | IF(OR(F441="",AS441=""),"",IF(COUNT(AI441:AR441)=0,"",AS441-LOOKUP(2,1/(AI441:AR441<>""),AI441:AR441))) | IF(OR(F441="",AT441=""),"",IF(COUNT(AI441:AS441)=0,"",AT441-LOOKUP(2,1/(AI441:AS441<>""),AI441:AS441))) | IF(OR(F441="",AU441=""),"",IF(COUNT(AI441:AT441)=0,"",AU441-LOOKUP(2,1/(AI441:AT441<>""),AI441:AT441))) | IF(OR(F441="",AV441=""),"",IF(COUNT(AI441:AU441)=0,"",AV441-LOOKUP(2,1/(AI441:AU441<>""),AI441:AU441))) | IF(J441="","All_Provinces",IFERROR(VLOOKUP(J441,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K441="","All_Districts",IFERROR(VLOOKUP(K441,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F442="","",ROW()-3) | [18 empty] | IF(AQ442="","",AQ442) |  |  |  | IF(W442<>"",W442,IF(OR(T442="",V442=""),"",EDATE(T442,V442))) |  |  |  |  | IF(F442="","",IF(COUNT(AI442:AV442)=0,IF(AA442="","Not started",AA442),SUBSTITUTE(LOOKUP(2,1/(AI442:AV442<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F442="",COUNT(AI442:AV442)=0),"",TODAY()-LOOKUP(2,1/(AI442:AV442<>""),AI442:AV442)) | IF(OR(F442="",COUNT(AI442:AV442)<2),"",LOOKUP(2,1/(AI442:AV442<>""),AI442:AV442)-MIN(AI442:AV442)) | IF(OR(AD442="",AC442="Not started",AC442=""),"",IFERROR(AD442-IF(VLOOKUP(AC442,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC442,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F442="","",IF(OR(AA442="Cancelled",AC442="Cancelled"),"Cancelled",IF(OR(AC442="Completed / Handover",Y442<>"",Z442>=100),"Completed — on track",IF(O442="Not awarded",IF(U442="",IF(X442="","No planned date",IF(TODAY()>X442,"Behind — past planned date",IF(X442-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U442,"Behind — award date passed",IF(U442-TODAY()<=30,"At risk — close to off track","On track"))),IF(X442="","No planned date",IF(AND(TODAY()>X442,OR(Z442="",Z442<100)),"Behind — past end date",IF(AND(T442<>"",X442<>"",Z442<>"",(Z442<100),((TODAY()-T442)/MAX(X442-T442,1)*100)-Z442>15),"Behind — progress lag",IF(AND(X442-TODAY()<=30,X442-TODAY()>=0,OR(Z442="",Z442<90)),"At risk — close to off track","On track")))))))) | IF(OR(F442="",AC442="Completed / Handover",AC442="Cancelled"),"",IF(O442="Not awarded",IF(U442<>"",U442-TODAY(),IF(X442="","",X442-TODAY())),IF(X442="","",X442-TODAY()))) | [14 empty] | IF(OR(F442="",AJ442=""),"",IF(COUNT(AI442:AI442)=0,"",AJ442-LOOKUP(2,1/(AI442:AI442<>""),AI442:AI442))) | IF(OR(F442="",AK442=""),"",IF(COUNT(AI442:AJ442)=0,"",AK442-LOOKUP(2,1/(AI442:AJ442<>""),AI442:AJ442))) | IF(OR(F442="",AL442=""),"",IF(COUNT(AI442:AK442)=0,"",AL442-LOOKUP(2,1/(AI442:AK442<>""),AI442:AK442))) | IF(OR(F442="",AM442=""),"",IF(COUNT(AI442:AL442)=0,"",AM442-LOOKUP(2,1/(AI442:AL442<>""),AI442:AL442))) | IF(OR(F442="",AN442=""),"",IF(COUNT(AI442:AM442)=0,"",AN442-LOOKUP(2,1/(AI442:AM442<>""),AI442:AM442))) | IF(OR(F442="",AO442=""),"",IF(COUNT(AI442:AN442)=0,"",AO442-LOOKUP(2,1/(AI442:AN442<>""),AI442:AN442))) | IF(OR(F442="",AP442=""),"",IF(COUNT(AI442:AO442)=0,"",AP442-LOOKUP(2,1/(AI442:AO442<>""),AI442:AO442))) | IF(OR(F442="",AQ442=""),"",IF(COUNT(AI442:AP442)=0,"",AQ442-LOOKUP(2,1/(AI442:AP442<>""),AI442:AP442))) | IF(OR(F442="",AR442=""),"",IF(COUNT(AI442:AQ442)=0,"",AR442-LOOKUP(2,1/(AI442:AQ442<>""),AI442:AQ442))) | IF(OR(F442="",AS442=""),"",IF(COUNT(AI442:AR442)=0,"",AS442-LOOKUP(2,1/(AI442:AR442<>""),AI442:AR442))) | IF(OR(F442="",AT442=""),"",IF(COUNT(AI442:AS442)=0,"",AT442-LOOKUP(2,1/(AI442:AS442<>""),AI442:AS442))) | IF(OR(F442="",AU442=""),"",IF(COUNT(AI442:AT442)=0,"",AU442-LOOKUP(2,1/(AI442:AT442<>""),AI442:AT442))) | IF(OR(F442="",AV442=""),"",IF(COUNT(AI442:AU442)=0,"",AV442-LOOKUP(2,1/(AI442:AU442<>""),AI442:AU442))) | IF(J442="","All_Provinces",IFERROR(VLOOKUP(J442,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K442="","All_Districts",IFERROR(VLOOKUP(K442,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F443="","",ROW()-3) | [18 empty] | IF(AQ443="","",AQ443) |  |  |  | IF(W443<>"",W443,IF(OR(T443="",V443=""),"",EDATE(T443,V443))) |  |  |  |  | IF(F443="","",IF(COUNT(AI443:AV443)=0,IF(AA443="","Not started",AA443),SUBSTITUTE(LOOKUP(2,1/(AI443:AV443<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F443="",COUNT(AI443:AV443)=0),"",TODAY()-LOOKUP(2,1/(AI443:AV443<>""),AI443:AV443)) | IF(OR(F443="",COUNT(AI443:AV443)<2),"",LOOKUP(2,1/(AI443:AV443<>""),AI443:AV443)-MIN(AI443:AV443)) | IF(OR(AD443="",AC443="Not started",AC443=""),"",IFERROR(AD443-IF(VLOOKUP(AC443,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC443,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F443="","",IF(OR(AA443="Cancelled",AC443="Cancelled"),"Cancelled",IF(OR(AC443="Completed / Handover",Y443<>"",Z443>=100),"Completed — on track",IF(O443="Not awarded",IF(U443="",IF(X443="","No planned date",IF(TODAY()>X443,"Behind — past planned date",IF(X443-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U443,"Behind — award date passed",IF(U443-TODAY()<=30,"At risk — close to off track","On track"))),IF(X443="","No planned date",IF(AND(TODAY()>X443,OR(Z443="",Z443<100)),"Behind — past end date",IF(AND(T443<>"",X443<>"",Z443<>"",(Z443<100),((TODAY()-T443)/MAX(X443-T443,1)*100)-Z443>15),"Behind — progress lag",IF(AND(X443-TODAY()<=30,X443-TODAY()>=0,OR(Z443="",Z443<90)),"At risk — close to off track","On track")))))))) | IF(OR(F443="",AC443="Completed / Handover",AC443="Cancelled"),"",IF(O443="Not awarded",IF(U443<>"",U443-TODAY(),IF(X443="","",X443-TODAY())),IF(X443="","",X443-TODAY()))) | [14 empty] | IF(OR(F443="",AJ443=""),"",IF(COUNT(AI443:AI443)=0,"",AJ443-LOOKUP(2,1/(AI443:AI443<>""),AI443:AI443))) | IF(OR(F443="",AK443=""),"",IF(COUNT(AI443:AJ443)=0,"",AK443-LOOKUP(2,1/(AI443:AJ443<>""),AI443:AJ443))) | IF(OR(F443="",AL443=""),"",IF(COUNT(AI443:AK443)=0,"",AL443-LOOKUP(2,1/(AI443:AK443<>""),AI443:AK443))) | IF(OR(F443="",AM443=""),"",IF(COUNT(AI443:AL443)=0,"",AM443-LOOKUP(2,1/(AI443:AL443<>""),AI443:AL443))) | IF(OR(F443="",AN443=""),"",IF(COUNT(AI443:AM443)=0,"",AN443-LOOKUP(2,1/(AI443:AM443<>""),AI443:AM443))) | IF(OR(F443="",AO443=""),"",IF(COUNT(AI443:AN443)=0,"",AO443-LOOKUP(2,1/(AI443:AN443<>""),AI443:AN443))) | IF(OR(F443="",AP443=""),"",IF(COUNT(AI443:AO443)=0,"",AP443-LOOKUP(2,1/(AI443:AO443<>""),AI443:AO443))) | IF(OR(F443="",AQ443=""),"",IF(COUNT(AI443:AP443)=0,"",AQ443-LOOKUP(2,1/(AI443:AP443<>""),AI443:AP443))) | IF(OR(F443="",AR443=""),"",IF(COUNT(AI443:AQ443)=0,"",AR443-LOOKUP(2,1/(AI443:AQ443<>""),AI443:AQ443))) | IF(OR(F443="",AS443=""),"",IF(COUNT(AI443:AR443)=0,"",AS443-LOOKUP(2,1/(AI443:AR443<>""),AI443:AR443))) | IF(OR(F443="",AT443=""),"",IF(COUNT(AI443:AS443)=0,"",AT443-LOOKUP(2,1/(AI443:AS443<>""),AI443:AS443))) | IF(OR(F443="",AU443=""),"",IF(COUNT(AI443:AT443)=0,"",AU443-LOOKUP(2,1/(AI443:AT443<>""),AI443:AT443))) | IF(OR(F443="",AV443=""),"",IF(COUNT(AI443:AU443)=0,"",AV443-LOOKUP(2,1/(AI443:AU443<>""),AI443:AU443))) | IF(J443="","All_Provinces",IFERROR(VLOOKUP(J443,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K443="","All_Districts",IFERROR(VLOOKUP(K443,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F444="","",ROW()-3) | [18 empty] | IF(AQ444="","",AQ444) |  |  |  | IF(W444<>"",W444,IF(OR(T444="",V444=""),"",EDATE(T444,V444))) |  |  |  |  | IF(F444="","",IF(COUNT(AI444:AV444)=0,IF(AA444="","Not started",AA444),SUBSTITUTE(LOOKUP(2,1/(AI444:AV444<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F444="",COUNT(AI444:AV444)=0),"",TODAY()-LOOKUP(2,1/(AI444:AV444<>""),AI444:AV444)) | IF(OR(F444="",COUNT(AI444:AV444)<2),"",LOOKUP(2,1/(AI444:AV444<>""),AI444:AV444)-MIN(AI444:AV444)) | IF(OR(AD444="",AC444="Not started",AC444=""),"",IFERROR(AD444-IF(VLOOKUP(AC444,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC444,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F444="","",IF(OR(AA444="Cancelled",AC444="Cancelled"),"Cancelled",IF(OR(AC444="Completed / Handover",Y444<>"",Z444>=100),"Completed — on track",IF(O444="Not awarded",IF(U444="",IF(X444="","No planned date",IF(TODAY()>X444,"Behind — past planned date",IF(X444-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U444,"Behind — award date passed",IF(U444-TODAY()<=30,"At risk — close to off track","On track"))),IF(X444="","No planned date",IF(AND(TODAY()>X444,OR(Z444="",Z444<100)),"Behind — past end date",IF(AND(T444<>"",X444<>"",Z444<>"",(Z444<100),((TODAY()-T444)/MAX(X444-T444,1)*100)-Z444>15),"Behind — progress lag",IF(AND(X444-TODAY()<=30,X444-TODAY()>=0,OR(Z444="",Z444<90)),"At risk — close to off track","On track")))))))) | IF(OR(F444="",AC444="Completed / Handover",AC444="Cancelled"),"",IF(O444="Not awarded",IF(U444<>"",U444-TODAY(),IF(X444="","",X444-TODAY())),IF(X444="","",X444-TODAY()))) | [14 empty] | IF(OR(F444="",AJ444=""),"",IF(COUNT(AI444:AI444)=0,"",AJ444-LOOKUP(2,1/(AI444:AI444<>""),AI444:AI444))) | IF(OR(F444="",AK444=""),"",IF(COUNT(AI444:AJ444)=0,"",AK444-LOOKUP(2,1/(AI444:AJ444<>""),AI444:AJ444))) | IF(OR(F444="",AL444=""),"",IF(COUNT(AI444:AK444)=0,"",AL444-LOOKUP(2,1/(AI444:AK444<>""),AI444:AK444))) | IF(OR(F444="",AM444=""),"",IF(COUNT(AI444:AL444)=0,"",AM444-LOOKUP(2,1/(AI444:AL444<>""),AI444:AL444))) | IF(OR(F444="",AN444=""),"",IF(COUNT(AI444:AM444)=0,"",AN444-LOOKUP(2,1/(AI444:AM444<>""),AI444:AM444))) | IF(OR(F444="",AO444=""),"",IF(COUNT(AI444:AN444)=0,"",AO444-LOOKUP(2,1/(AI444:AN444<>""),AI444:AN444))) | IF(OR(F444="",AP444=""),"",IF(COUNT(AI444:AO444)=0,"",AP444-LOOKUP(2,1/(AI444:AO444<>""),AI444:AO444))) | IF(OR(F444="",AQ444=""),"",IF(COUNT(AI444:AP444)=0,"",AQ444-LOOKUP(2,1/(AI444:AP444<>""),AI444:AP444))) | IF(OR(F444="",AR444=""),"",IF(COUNT(AI444:AQ444)=0,"",AR444-LOOKUP(2,1/(AI444:AQ444<>""),AI444:AQ444))) | IF(OR(F444="",AS444=""),"",IF(COUNT(AI444:AR444)=0,"",AS444-LOOKUP(2,1/(AI444:AR444<>""),AI444:AR444))) | IF(OR(F444="",AT444=""),"",IF(COUNT(AI444:AS444)=0,"",AT444-LOOKUP(2,1/(AI444:AS444<>""),AI444:AS444))) | IF(OR(F444="",AU444=""),"",IF(COUNT(AI444:AT444)=0,"",AU444-LOOKUP(2,1/(AI444:AT444<>""),AI444:AT444))) | IF(OR(F444="",AV444=""),"",IF(COUNT(AI444:AU444)=0,"",AV444-LOOKUP(2,1/(AI444:AU444<>""),AI444:AU444))) | IF(J444="","All_Provinces",IFERROR(VLOOKUP(J444,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K444="","All_Districts",IFERROR(VLOOKUP(K444,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F445="","",ROW()-3) | [18 empty] | IF(AQ445="","",AQ445) |  |  |  | IF(W445<>"",W445,IF(OR(T445="",V445=""),"",EDATE(T445,V445))) |  |  |  |  | IF(F445="","",IF(COUNT(AI445:AV445)=0,IF(AA445="","Not started",AA445),SUBSTITUTE(LOOKUP(2,1/(AI445:AV445<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F445="",COUNT(AI445:AV445)=0),"",TODAY()-LOOKUP(2,1/(AI445:AV445<>""),AI445:AV445)) | IF(OR(F445="",COUNT(AI445:AV445)<2),"",LOOKUP(2,1/(AI445:AV445<>""),AI445:AV445)-MIN(AI445:AV445)) | IF(OR(AD445="",AC445="Not started",AC445=""),"",IFERROR(AD445-IF(VLOOKUP(AC445,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC445,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F445="","",IF(OR(AA445="Cancelled",AC445="Cancelled"),"Cancelled",IF(OR(AC445="Completed / Handover",Y445<>"",Z445>=100),"Completed — on track",IF(O445="Not awarded",IF(U445="",IF(X445="","No planned date",IF(TODAY()>X445,"Behind — past planned date",IF(X445-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U445,"Behind — award date passed",IF(U445-TODAY()<=30,"At risk — close to off track","On track"))),IF(X445="","No planned date",IF(AND(TODAY()>X445,OR(Z445="",Z445<100)),"Behind — past end date",IF(AND(T445<>"",X445<>"",Z445<>"",(Z445<100),((TODAY()-T445)/MAX(X445-T445,1)*100)-Z445>15),"Behind — progress lag",IF(AND(X445-TODAY()<=30,X445-TODAY()>=0,OR(Z445="",Z445<90)),"At risk — close to off track","On track")))))))) | IF(OR(F445="",AC445="Completed / Handover",AC445="Cancelled"),"",IF(O445="Not awarded",IF(U445<>"",U445-TODAY(),IF(X445="","",X445-TODAY())),IF(X445="","",X445-TODAY()))) | [14 empty] | IF(OR(F445="",AJ445=""),"",IF(COUNT(AI445:AI445)=0,"",AJ445-LOOKUP(2,1/(AI445:AI445<>""),AI445:AI445))) | IF(OR(F445="",AK445=""),"",IF(COUNT(AI445:AJ445)=0,"",AK445-LOOKUP(2,1/(AI445:AJ445<>""),AI445:AJ445))) | IF(OR(F445="",AL445=""),"",IF(COUNT(AI445:AK445)=0,"",AL445-LOOKUP(2,1/(AI445:AK445<>""),AI445:AK445))) | IF(OR(F445="",AM445=""),"",IF(COUNT(AI445:AL445)=0,"",AM445-LOOKUP(2,1/(AI445:AL445<>""),AI445:AL445))) | IF(OR(F445="",AN445=""),"",IF(COUNT(AI445:AM445)=0,"",AN445-LOOKUP(2,1/(AI445:AM445<>""),AI445:AM445))) | IF(OR(F445="",AO445=""),"",IF(COUNT(AI445:AN445)=0,"",AO445-LOOKUP(2,1/(AI445:AN445<>""),AI445:AN445))) | IF(OR(F445="",AP445=""),"",IF(COUNT(AI445:AO445)=0,"",AP445-LOOKUP(2,1/(AI445:AO445<>""),AI445:AO445))) | IF(OR(F445="",AQ445=""),"",IF(COUNT(AI445:AP445)=0,"",AQ445-LOOKUP(2,1/(AI445:AP445<>""),AI445:AP445))) | IF(OR(F445="",AR445=""),"",IF(COUNT(AI445:AQ445)=0,"",AR445-LOOKUP(2,1/(AI445:AQ445<>""),AI445:AQ445))) | IF(OR(F445="",AS445=""),"",IF(COUNT(AI445:AR445)=0,"",AS445-LOOKUP(2,1/(AI445:AR445<>""),AI445:AR445))) | IF(OR(F445="",AT445=""),"",IF(COUNT(AI445:AS445)=0,"",AT445-LOOKUP(2,1/(AI445:AS445<>""),AI445:AS445))) | IF(OR(F445="",AU445=""),"",IF(COUNT(AI445:AT445)=0,"",AU445-LOOKUP(2,1/(AI445:AT445<>""),AI445:AT445))) | IF(OR(F445="",AV445=""),"",IF(COUNT(AI445:AU445)=0,"",AV445-LOOKUP(2,1/(AI445:AU445<>""),AI445:AU445))) | IF(J445="","All_Provinces",IFERROR(VLOOKUP(J445,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K445="","All_Districts",IFERROR(VLOOKUP(K445,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F446="","",ROW()-3) | [18 empty] | IF(AQ446="","",AQ446) |  |  |  | IF(W446<>"",W446,IF(OR(T446="",V446=""),"",EDATE(T446,V446))) |  |  |  |  | IF(F446="","",IF(COUNT(AI446:AV446)=0,IF(AA446="","Not started",AA446),SUBSTITUTE(LOOKUP(2,1/(AI446:AV446<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F446="",COUNT(AI446:AV446)=0),"",TODAY()-LOOKUP(2,1/(AI446:AV446<>""),AI446:AV446)) | IF(OR(F446="",COUNT(AI446:AV446)<2),"",LOOKUP(2,1/(AI446:AV446<>""),AI446:AV446)-MIN(AI446:AV446)) | IF(OR(AD446="",AC446="Not started",AC446=""),"",IFERROR(AD446-IF(VLOOKUP(AC446,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC446,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F446="","",IF(OR(AA446="Cancelled",AC446="Cancelled"),"Cancelled",IF(OR(AC446="Completed / Handover",Y446<>"",Z446>=100),"Completed — on track",IF(O446="Not awarded",IF(U446="",IF(X446="","No planned date",IF(TODAY()>X446,"Behind — past planned date",IF(X446-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U446,"Behind — award date passed",IF(U446-TODAY()<=30,"At risk — close to off track","On track"))),IF(X446="","No planned date",IF(AND(TODAY()>X446,OR(Z446="",Z446<100)),"Behind — past end date",IF(AND(T446<>"",X446<>"",Z446<>"",(Z446<100),((TODAY()-T446)/MAX(X446-T446,1)*100)-Z446>15),"Behind — progress lag",IF(AND(X446-TODAY()<=30,X446-TODAY()>=0,OR(Z446="",Z446<90)),"At risk — close to off track","On track")))))))) | IF(OR(F446="",AC446="Completed / Handover",AC446="Cancelled"),"",IF(O446="Not awarded",IF(U446<>"",U446-TODAY(),IF(X446="","",X446-TODAY())),IF(X446="","",X446-TODAY()))) | [14 empty] | IF(OR(F446="",AJ446=""),"",IF(COUNT(AI446:AI446)=0,"",AJ446-LOOKUP(2,1/(AI446:AI446<>""),AI446:AI446))) | IF(OR(F446="",AK446=""),"",IF(COUNT(AI446:AJ446)=0,"",AK446-LOOKUP(2,1/(AI446:AJ446<>""),AI446:AJ446))) | IF(OR(F446="",AL446=""),"",IF(COUNT(AI446:AK446)=0,"",AL446-LOOKUP(2,1/(AI446:AK446<>""),AI446:AK446))) | IF(OR(F446="",AM446=""),"",IF(COUNT(AI446:AL446)=0,"",AM446-LOOKUP(2,1/(AI446:AL446<>""),AI446:AL446))) | IF(OR(F446="",AN446=""),"",IF(COUNT(AI446:AM446)=0,"",AN446-LOOKUP(2,1/(AI446:AM446<>""),AI446:AM446))) | IF(OR(F446="",AO446=""),"",IF(COUNT(AI446:AN446)=0,"",AO446-LOOKUP(2,1/(AI446:AN446<>""),AI446:AN446))) | IF(OR(F446="",AP446=""),"",IF(COUNT(AI446:AO446)=0,"",AP446-LOOKUP(2,1/(AI446:AO446<>""),AI446:AO446))) | IF(OR(F446="",AQ446=""),"",IF(COUNT(AI446:AP446)=0,"",AQ446-LOOKUP(2,1/(AI446:AP446<>""),AI446:AP446))) | IF(OR(F446="",AR446=""),"",IF(COUNT(AI446:AQ446)=0,"",AR446-LOOKUP(2,1/(AI446:AQ446<>""),AI446:AQ446))) | IF(OR(F446="",AS446=""),"",IF(COUNT(AI446:AR446)=0,"",AS446-LOOKUP(2,1/(AI446:AR446<>""),AI446:AR446))) | IF(OR(F446="",AT446=""),"",IF(COUNT(AI446:AS446)=0,"",AT446-LOOKUP(2,1/(AI446:AS446<>""),AI446:AS446))) | IF(OR(F446="",AU446=""),"",IF(COUNT(AI446:AT446)=0,"",AU446-LOOKUP(2,1/(AI446:AT446<>""),AI446:AT446))) | IF(OR(F446="",AV446=""),"",IF(COUNT(AI446:AU446)=0,"",AV446-LOOKUP(2,1/(AI446:AU446<>""),AI446:AU446))) | IF(J446="","All_Provinces",IFERROR(VLOOKUP(J446,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K446="","All_Districts",IFERROR(VLOOKUP(K446,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F447="","",ROW()-3) | [18 empty] | IF(AQ447="","",AQ447) |  |  |  | IF(W447<>"",W447,IF(OR(T447="",V447=""),"",EDATE(T447,V447))) |  |  |  |  | IF(F447="","",IF(COUNT(AI447:AV447)=0,IF(AA447="","Not started",AA447),SUBSTITUTE(LOOKUP(2,1/(AI447:AV447<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F447="",COUNT(AI447:AV447)=0),"",TODAY()-LOOKUP(2,1/(AI447:AV447<>""),AI447:AV447)) | IF(OR(F447="",COUNT(AI447:AV447)<2),"",LOOKUP(2,1/(AI447:AV447<>""),AI447:AV447)-MIN(AI447:AV447)) | IF(OR(AD447="",AC447="Not started",AC447=""),"",IFERROR(AD447-IF(VLOOKUP(AC447,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC447,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F447="","",IF(OR(AA447="Cancelled",AC447="Cancelled"),"Cancelled",IF(OR(AC447="Completed / Handover",Y447<>"",Z447>=100),"Completed — on track",IF(O447="Not awarded",IF(U447="",IF(X447="","No planned date",IF(TODAY()>X447,"Behind — past planned date",IF(X447-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U447,"Behind — award date passed",IF(U447-TODAY()<=30,"At risk — close to off track","On track"))),IF(X447="","No planned date",IF(AND(TODAY()>X447,OR(Z447="",Z447<100)),"Behind — past end date",IF(AND(T447<>"",X447<>"",Z447<>"",(Z447<100),((TODAY()-T447)/MAX(X447-T447,1)*100)-Z447>15),"Behind — progress lag",IF(AND(X447-TODAY()<=30,X447-TODAY()>=0,OR(Z447="",Z447<90)),"At risk — close to off track","On track")))))))) | IF(OR(F447="",AC447="Completed / Handover",AC447="Cancelled"),"",IF(O447="Not awarded",IF(U447<>"",U447-TODAY(),IF(X447="","",X447-TODAY())),IF(X447="","",X447-TODAY()))) | [14 empty] | IF(OR(F447="",AJ447=""),"",IF(COUNT(AI447:AI447)=0,"",AJ447-LOOKUP(2,1/(AI447:AI447<>""),AI447:AI447))) | IF(OR(F447="",AK447=""),"",IF(COUNT(AI447:AJ447)=0,"",AK447-LOOKUP(2,1/(AI447:AJ447<>""),AI447:AJ447))) | IF(OR(F447="",AL447=""),"",IF(COUNT(AI447:AK447)=0,"",AL447-LOOKUP(2,1/(AI447:AK447<>""),AI447:AK447))) | IF(OR(F447="",AM447=""),"",IF(COUNT(AI447:AL447)=0,"",AM447-LOOKUP(2,1/(AI447:AL447<>""),AI447:AL447))) | IF(OR(F447="",AN447=""),"",IF(COUNT(AI447:AM447)=0,"",AN447-LOOKUP(2,1/(AI447:AM447<>""),AI447:AM447))) | IF(OR(F447="",AO447=""),"",IF(COUNT(AI447:AN447)=0,"",AO447-LOOKUP(2,1/(AI447:AN447<>""),AI447:AN447))) | IF(OR(F447="",AP447=""),"",IF(COUNT(AI447:AO447)=0,"",AP447-LOOKUP(2,1/(AI447:AO447<>""),AI447:AO447))) | IF(OR(F447="",AQ447=""),"",IF(COUNT(AI447:AP447)=0,"",AQ447-LOOKUP(2,1/(AI447:AP447<>""),AI447:AP447))) | IF(OR(F447="",AR447=""),"",IF(COUNT(AI447:AQ447)=0,"",AR447-LOOKUP(2,1/(AI447:AQ447<>""),AI447:AQ447))) | IF(OR(F447="",AS447=""),"",IF(COUNT(AI447:AR447)=0,"",AS447-LOOKUP(2,1/(AI447:AR447<>""),AI447:AR447))) | IF(OR(F447="",AT447=""),"",IF(COUNT(AI447:AS447)=0,"",AT447-LOOKUP(2,1/(AI447:AS447<>""),AI447:AS447))) | IF(OR(F447="",AU447=""),"",IF(COUNT(AI447:AT447)=0,"",AU447-LOOKUP(2,1/(AI447:AT447<>""),AI447:AT447))) | IF(OR(F447="",AV447=""),"",IF(COUNT(AI447:AU447)=0,"",AV447-LOOKUP(2,1/(AI447:AU447<>""),AI447:AU447))) | IF(J447="","All_Provinces",IFERROR(VLOOKUP(J447,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K447="","All_Districts",IFERROR(VLOOKUP(K447,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F448="","",ROW()-3) | [18 empty] | IF(AQ448="","",AQ448) |  |  |  | IF(W448<>"",W448,IF(OR(T448="",V448=""),"",EDATE(T448,V448))) |  |  |  |  | IF(F448="","",IF(COUNT(AI448:AV448)=0,IF(AA448="","Not started",AA448),SUBSTITUTE(LOOKUP(2,1/(AI448:AV448<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F448="",COUNT(AI448:AV448)=0),"",TODAY()-LOOKUP(2,1/(AI448:AV448<>""),AI448:AV448)) | IF(OR(F448="",COUNT(AI448:AV448)<2),"",LOOKUP(2,1/(AI448:AV448<>""),AI448:AV448)-MIN(AI448:AV448)) | IF(OR(AD448="",AC448="Not started",AC448=""),"",IFERROR(AD448-IF(VLOOKUP(AC448,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC448,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F448="","",IF(OR(AA448="Cancelled",AC448="Cancelled"),"Cancelled",IF(OR(AC448="Completed / Handover",Y448<>"",Z448>=100),"Completed — on track",IF(O448="Not awarded",IF(U448="",IF(X448="","No planned date",IF(TODAY()>X448,"Behind — past planned date",IF(X448-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U448,"Behind — award date passed",IF(U448-TODAY()<=30,"At risk — close to off track","On track"))),IF(X448="","No planned date",IF(AND(TODAY()>X448,OR(Z448="",Z448<100)),"Behind — past end date",IF(AND(T448<>"",X448<>"",Z448<>"",(Z448<100),((TODAY()-T448)/MAX(X448-T448,1)*100)-Z448>15),"Behind — progress lag",IF(AND(X448-TODAY()<=30,X448-TODAY()>=0,OR(Z448="",Z448<90)),"At risk — close to off track","On track")))))))) | IF(OR(F448="",AC448="Completed / Handover",AC448="Cancelled"),"",IF(O448="Not awarded",IF(U448<>"",U448-TODAY(),IF(X448="","",X448-TODAY())),IF(X448="","",X448-TODAY()))) | [14 empty] | IF(OR(F448="",AJ448=""),"",IF(COUNT(AI448:AI448)=0,"",AJ448-LOOKUP(2,1/(AI448:AI448<>""),AI448:AI448))) | IF(OR(F448="",AK448=""),"",IF(COUNT(AI448:AJ448)=0,"",AK448-LOOKUP(2,1/(AI448:AJ448<>""),AI448:AJ448))) | IF(OR(F448="",AL448=""),"",IF(COUNT(AI448:AK448)=0,"",AL448-LOOKUP(2,1/(AI448:AK448<>""),AI448:AK448))) | IF(OR(F448="",AM448=""),"",IF(COUNT(AI448:AL448)=0,"",AM448-LOOKUP(2,1/(AI448:AL448<>""),AI448:AL448))) | IF(OR(F448="",AN448=""),"",IF(COUNT(AI448:AM448)=0,"",AN448-LOOKUP(2,1/(AI448:AM448<>""),AI448:AM448))) | IF(OR(F448="",AO448=""),"",IF(COUNT(AI448:AN448)=0,"",AO448-LOOKUP(2,1/(AI448:AN448<>""),AI448:AN448))) | IF(OR(F448="",AP448=""),"",IF(COUNT(AI448:AO448)=0,"",AP448-LOOKUP(2,1/(AI448:AO448<>""),AI448:AO448))) | IF(OR(F448="",AQ448=""),"",IF(COUNT(AI448:AP448)=0,"",AQ448-LOOKUP(2,1/(AI448:AP448<>""),AI448:AP448))) | IF(OR(F448="",AR448=""),"",IF(COUNT(AI448:AQ448)=0,"",AR448-LOOKUP(2,1/(AI448:AQ448<>""),AI448:AQ448))) | IF(OR(F448="",AS448=""),"",IF(COUNT(AI448:AR448)=0,"",AS448-LOOKUP(2,1/(AI448:AR448<>""),AI448:AR448))) | IF(OR(F448="",AT448=""),"",IF(COUNT(AI448:AS448)=0,"",AT448-LOOKUP(2,1/(AI448:AS448<>""),AI448:AS448))) | IF(OR(F448="",AU448=""),"",IF(COUNT(AI448:AT448)=0,"",AU448-LOOKUP(2,1/(AI448:AT448<>""),AI448:AT448))) | IF(OR(F448="",AV448=""),"",IF(COUNT(AI448:AU448)=0,"",AV448-LOOKUP(2,1/(AI448:AU448<>""),AI448:AU448))) | IF(J448="","All_Provinces",IFERROR(VLOOKUP(J448,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K448="","All_Districts",IFERROR(VLOOKUP(K448,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F449="","",ROW()-3) | [18 empty] | IF(AQ449="","",AQ449) |  |  |  | IF(W449<>"",W449,IF(OR(T449="",V449=""),"",EDATE(T449,V449))) |  |  |  |  | IF(F449="","",IF(COUNT(AI449:AV449)=0,IF(AA449="","Not started",AA449),SUBSTITUTE(LOOKUP(2,1/(AI449:AV449<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F449="",COUNT(AI449:AV449)=0),"",TODAY()-LOOKUP(2,1/(AI449:AV449<>""),AI449:AV449)) | IF(OR(F449="",COUNT(AI449:AV449)<2),"",LOOKUP(2,1/(AI449:AV449<>""),AI449:AV449)-MIN(AI449:AV449)) | IF(OR(AD449="",AC449="Not started",AC449=""),"",IFERROR(AD449-IF(VLOOKUP(AC449,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC449,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F449="","",IF(OR(AA449="Cancelled",AC449="Cancelled"),"Cancelled",IF(OR(AC449="Completed / Handover",Y449<>"",Z449>=100),"Completed — on track",IF(O449="Not awarded",IF(U449="",IF(X449="","No planned date",IF(TODAY()>X449,"Behind — past planned date",IF(X449-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U449,"Behind — award date passed",IF(U449-TODAY()<=30,"At risk — close to off track","On track"))),IF(X449="","No planned date",IF(AND(TODAY()>X449,OR(Z449="",Z449<100)),"Behind — past end date",IF(AND(T449<>"",X449<>"",Z449<>"",(Z449<100),((TODAY()-T449)/MAX(X449-T449,1)*100)-Z449>15),"Behind — progress lag",IF(AND(X449-TODAY()<=30,X449-TODAY()>=0,OR(Z449="",Z449<90)),"At risk — close to off track","On track")))))))) | IF(OR(F449="",AC449="Completed / Handover",AC449="Cancelled"),"",IF(O449="Not awarded",IF(U449<>"",U449-TODAY(),IF(X449="","",X449-TODAY())),IF(X449="","",X449-TODAY()))) | [14 empty] | IF(OR(F449="",AJ449=""),"",IF(COUNT(AI449:AI449)=0,"",AJ449-LOOKUP(2,1/(AI449:AI449<>""),AI449:AI449))) | IF(OR(F449="",AK449=""),"",IF(COUNT(AI449:AJ449)=0,"",AK449-LOOKUP(2,1/(AI449:AJ449<>""),AI449:AJ449))) | IF(OR(F449="",AL449=""),"",IF(COUNT(AI449:AK449)=0,"",AL449-LOOKUP(2,1/(AI449:AK449<>""),AI449:AK449))) | IF(OR(F449="",AM449=""),"",IF(COUNT(AI449:AL449)=0,"",AM449-LOOKUP(2,1/(AI449:AL449<>""),AI449:AL449))) | IF(OR(F449="",AN449=""),"",IF(COUNT(AI449:AM449)=0,"",AN449-LOOKUP(2,1/(AI449:AM449<>""),AI449:AM449))) | IF(OR(F449="",AO449=""),"",IF(COUNT(AI449:AN449)=0,"",AO449-LOOKUP(2,1/(AI449:AN449<>""),AI449:AN449))) | IF(OR(F449="",AP449=""),"",IF(COUNT(AI449:AO449)=0,"",AP449-LOOKUP(2,1/(AI449:AO449<>""),AI449:AO449))) | IF(OR(F449="",AQ449=""),"",IF(COUNT(AI449:AP449)=0,"",AQ449-LOOKUP(2,1/(AI449:AP449<>""),AI449:AP449))) | IF(OR(F449="",AR449=""),"",IF(COUNT(AI449:AQ449)=0,"",AR449-LOOKUP(2,1/(AI449:AQ449<>""),AI449:AQ449))) | IF(OR(F449="",AS449=""),"",IF(COUNT(AI449:AR449)=0,"",AS449-LOOKUP(2,1/(AI449:AR449<>""),AI449:AR449))) | IF(OR(F449="",AT449=""),"",IF(COUNT(AI449:AS449)=0,"",AT449-LOOKUP(2,1/(AI449:AS449<>""),AI449:AS449))) | IF(OR(F449="",AU449=""),"",IF(COUNT(AI449:AT449)=0,"",AU449-LOOKUP(2,1/(AI449:AT449<>""),AI449:AT449))) | IF(OR(F449="",AV449=""),"",IF(COUNT(AI449:AU449)=0,"",AV449-LOOKUP(2,1/(AI449:AU449<>""),AI449:AU449))) | IF(J449="","All_Provinces",IFERROR(VLOOKUP(J449,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K449="","All_Districts",IFERROR(VLOOKUP(K449,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F450="","",ROW()-3) | [18 empty] | IF(AQ450="","",AQ450) |  |  |  | IF(W450<>"",W450,IF(OR(T450="",V450=""),"",EDATE(T450,V450))) |  |  |  |  | IF(F450="","",IF(COUNT(AI450:AV450)=0,IF(AA450="","Not started",AA450),SUBSTITUTE(LOOKUP(2,1/(AI450:AV450<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F450="",COUNT(AI450:AV450)=0),"",TODAY()-LOOKUP(2,1/(AI450:AV450<>""),AI450:AV450)) | IF(OR(F450="",COUNT(AI450:AV450)<2),"",LOOKUP(2,1/(AI450:AV450<>""),AI450:AV450)-MIN(AI450:AV450)) | IF(OR(AD450="",AC450="Not started",AC450=""),"",IFERROR(AD450-IF(VLOOKUP(AC450,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC450,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F450="","",IF(OR(AA450="Cancelled",AC450="Cancelled"),"Cancelled",IF(OR(AC450="Completed / Handover",Y450<>"",Z450>=100),"Completed — on track",IF(O450="Not awarded",IF(U450="",IF(X450="","No planned date",IF(TODAY()>X450,"Behind — past planned date",IF(X450-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U450,"Behind — award date passed",IF(U450-TODAY()<=30,"At risk — close to off track","On track"))),IF(X450="","No planned date",IF(AND(TODAY()>X450,OR(Z450="",Z450<100)),"Behind — past end date",IF(AND(T450<>"",X450<>"",Z450<>"",(Z450<100),((TODAY()-T450)/MAX(X450-T450,1)*100)-Z450>15),"Behind — progress lag",IF(AND(X450-TODAY()<=30,X450-TODAY()>=0,OR(Z450="",Z450<90)),"At risk — close to off track","On track")))))))) | IF(OR(F450="",AC450="Completed / Handover",AC450="Cancelled"),"",IF(O450="Not awarded",IF(U450<>"",U450-TODAY(),IF(X450="","",X450-TODAY())),IF(X450="","",X450-TODAY()))) | [14 empty] | IF(OR(F450="",AJ450=""),"",IF(COUNT(AI450:AI450)=0,"",AJ450-LOOKUP(2,1/(AI450:AI450<>""),AI450:AI450))) | IF(OR(F450="",AK450=""),"",IF(COUNT(AI450:AJ450)=0,"",AK450-LOOKUP(2,1/(AI450:AJ450<>""),AI450:AJ450))) | IF(OR(F450="",AL450=""),"",IF(COUNT(AI450:AK450)=0,"",AL450-LOOKUP(2,1/(AI450:AK450<>""),AI450:AK450))) | IF(OR(F450="",AM450=""),"",IF(COUNT(AI450:AL450)=0,"",AM450-LOOKUP(2,1/(AI450:AL450<>""),AI450:AL450))) | IF(OR(F450="",AN450=""),"",IF(COUNT(AI450:AM450)=0,"",AN450-LOOKUP(2,1/(AI450:AM450<>""),AI450:AM450))) | IF(OR(F450="",AO450=""),"",IF(COUNT(AI450:AN450)=0,"",AO450-LOOKUP(2,1/(AI450:AN450<>""),AI450:AN450))) | IF(OR(F450="",AP450=""),"",IF(COUNT(AI450:AO450)=0,"",AP450-LOOKUP(2,1/(AI450:AO450<>""),AI450:AO450))) | IF(OR(F450="",AQ450=""),"",IF(COUNT(AI450:AP450)=0,"",AQ450-LOOKUP(2,1/(AI450:AP450<>""),AI450:AP450))) | IF(OR(F450="",AR450=""),"",IF(COUNT(AI450:AQ450)=0,"",AR450-LOOKUP(2,1/(AI450:AQ450<>""),AI450:AQ450))) | IF(OR(F450="",AS450=""),"",IF(COUNT(AI450:AR450)=0,"",AS450-LOOKUP(2,1/(AI450:AR450<>""),AI450:AR450))) | IF(OR(F450="",AT450=""),"",IF(COUNT(AI450:AS450)=0,"",AT450-LOOKUP(2,1/(AI450:AS450<>""),AI450:AS450))) | IF(OR(F450="",AU450=""),"",IF(COUNT(AI450:AT450)=0,"",AU450-LOOKUP(2,1/(AI450:AT450<>""),AI450:AT450))) | IF(OR(F450="",AV450=""),"",IF(COUNT(AI450:AU450)=0,"",AV450-LOOKUP(2,1/(AI450:AU450<>""),AI450:AU450))) | IF(J450="","All_Provinces",IFERROR(VLOOKUP(J450,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K450="","All_Districts",IFERROR(VLOOKUP(K450,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F451="","",ROW()-3) | [18 empty] | IF(AQ451="","",AQ451) |  |  |  | IF(W451<>"",W451,IF(OR(T451="",V451=""),"",EDATE(T451,V451))) |  |  |  |  | IF(F451="","",IF(COUNT(AI451:AV451)=0,IF(AA451="","Not started",AA451),SUBSTITUTE(LOOKUP(2,1/(AI451:AV451<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F451="",COUNT(AI451:AV451)=0),"",TODAY()-LOOKUP(2,1/(AI451:AV451<>""),AI451:AV451)) | IF(OR(F451="",COUNT(AI451:AV451)<2),"",LOOKUP(2,1/(AI451:AV451<>""),AI451:AV451)-MIN(AI451:AV451)) | IF(OR(AD451="",AC451="Not started",AC451=""),"",IFERROR(AD451-IF(VLOOKUP(AC451,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC451,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F451="","",IF(OR(AA451="Cancelled",AC451="Cancelled"),"Cancelled",IF(OR(AC451="Completed / Handover",Y451<>"",Z451>=100),"Completed — on track",IF(O451="Not awarded",IF(U451="",IF(X451="","No planned date",IF(TODAY()>X451,"Behind — past planned date",IF(X451-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U451,"Behind — award date passed",IF(U451-TODAY()<=30,"At risk — close to off track","On track"))),IF(X451="","No planned date",IF(AND(TODAY()>X451,OR(Z451="",Z451<100)),"Behind — past end date",IF(AND(T451<>"",X451<>"",Z451<>"",(Z451<100),((TODAY()-T451)/MAX(X451-T451,1)*100)-Z451>15),"Behind — progress lag",IF(AND(X451-TODAY()<=30,X451-TODAY()>=0,OR(Z451="",Z451<90)),"At risk — close to off track","On track")))))))) | IF(OR(F451="",AC451="Completed / Handover",AC451="Cancelled"),"",IF(O451="Not awarded",IF(U451<>"",U451-TODAY(),IF(X451="","",X451-TODAY())),IF(X451="","",X451-TODAY()))) | [14 empty] | IF(OR(F451="",AJ451=""),"",IF(COUNT(AI451:AI451)=0,"",AJ451-LOOKUP(2,1/(AI451:AI451<>""),AI451:AI451))) | IF(OR(F451="",AK451=""),"",IF(COUNT(AI451:AJ451)=0,"",AK451-LOOKUP(2,1/(AI451:AJ451<>""),AI451:AJ451))) | IF(OR(F451="",AL451=""),"",IF(COUNT(AI451:AK451)=0,"",AL451-LOOKUP(2,1/(AI451:AK451<>""),AI451:AK451))) | IF(OR(F451="",AM451=""),"",IF(COUNT(AI451:AL451)=0,"",AM451-LOOKUP(2,1/(AI451:AL451<>""),AI451:AL451))) | IF(OR(F451="",AN451=""),"",IF(COUNT(AI451:AM451)=0,"",AN451-LOOKUP(2,1/(AI451:AM451<>""),AI451:AM451))) | IF(OR(F451="",AO451=""),"",IF(COUNT(AI451:AN451)=0,"",AO451-LOOKUP(2,1/(AI451:AN451<>""),AI451:AN451))) | IF(OR(F451="",AP451=""),"",IF(COUNT(AI451:AO451)=0,"",AP451-LOOKUP(2,1/(AI451:AO451<>""),AI451:AO451))) | IF(OR(F451="",AQ451=""),"",IF(COUNT(AI451:AP451)=0,"",AQ451-LOOKUP(2,1/(AI451:AP451<>""),AI451:AP451))) | IF(OR(F451="",AR451=""),"",IF(COUNT(AI451:AQ451)=0,"",AR451-LOOKUP(2,1/(AI451:AQ451<>""),AI451:AQ451))) | IF(OR(F451="",AS451=""),"",IF(COUNT(AI451:AR451)=0,"",AS451-LOOKUP(2,1/(AI451:AR451<>""),AI451:AR451))) | IF(OR(F451="",AT451=""),"",IF(COUNT(AI451:AS451)=0,"",AT451-LOOKUP(2,1/(AI451:AS451<>""),AI451:AS451))) | IF(OR(F451="",AU451=""),"",IF(COUNT(AI451:AT451)=0,"",AU451-LOOKUP(2,1/(AI451:AT451<>""),AI451:AT451))) | IF(OR(F451="",AV451=""),"",IF(COUNT(AI451:AU451)=0,"",AV451-LOOKUP(2,1/(AI451:AU451<>""),AI451:AU451))) | IF(J451="","All_Provinces",IFERROR(VLOOKUP(J451,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K451="","All_Districts",IFERROR(VLOOKUP(K451,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F452="","",ROW()-3) | [18 empty] | IF(AQ452="","",AQ452) |  |  |  | IF(W452<>"",W452,IF(OR(T452="",V452=""),"",EDATE(T452,V452))) |  |  |  |  | IF(F452="","",IF(COUNT(AI452:AV452)=0,IF(AA452="","Not started",AA452),SUBSTITUTE(LOOKUP(2,1/(AI452:AV452<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F452="",COUNT(AI452:AV452)=0),"",TODAY()-LOOKUP(2,1/(AI452:AV452<>""),AI452:AV452)) | IF(OR(F452="",COUNT(AI452:AV452)<2),"",LOOKUP(2,1/(AI452:AV452<>""),AI452:AV452)-MIN(AI452:AV452)) | IF(OR(AD452="",AC452="Not started",AC452=""),"",IFERROR(AD452-IF(VLOOKUP(AC452,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC452,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F452="","",IF(OR(AA452="Cancelled",AC452="Cancelled"),"Cancelled",IF(OR(AC452="Completed / Handover",Y452<>"",Z452>=100),"Completed — on track",IF(O452="Not awarded",IF(U452="",IF(X452="","No planned date",IF(TODAY()>X452,"Behind — past planned date",IF(X452-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U452,"Behind — award date passed",IF(U452-TODAY()<=30,"At risk — close to off track","On track"))),IF(X452="","No planned date",IF(AND(TODAY()>X452,OR(Z452="",Z452<100)),"Behind — past end date",IF(AND(T452<>"",X452<>"",Z452<>"",(Z452<100),((TODAY()-T452)/MAX(X452-T452,1)*100)-Z452>15),"Behind — progress lag",IF(AND(X452-TODAY()<=30,X452-TODAY()>=0,OR(Z452="",Z452<90)),"At risk — close to off track","On track")))))))) | IF(OR(F452="",AC452="Completed / Handover",AC452="Cancelled"),"",IF(O452="Not awarded",IF(U452<>"",U452-TODAY(),IF(X452="","",X452-TODAY())),IF(X452="","",X452-TODAY()))) | [14 empty] | IF(OR(F452="",AJ452=""),"",IF(COUNT(AI452:AI452)=0,"",AJ452-LOOKUP(2,1/(AI452:AI452<>""),AI452:AI452))) | IF(OR(F452="",AK452=""),"",IF(COUNT(AI452:AJ452)=0,"",AK452-LOOKUP(2,1/(AI452:AJ452<>""),AI452:AJ452))) | IF(OR(F452="",AL452=""),"",IF(COUNT(AI452:AK452)=0,"",AL452-LOOKUP(2,1/(AI452:AK452<>""),AI452:AK452))) | IF(OR(F452="",AM452=""),"",IF(COUNT(AI452:AL452)=0,"",AM452-LOOKUP(2,1/(AI452:AL452<>""),AI452:AL452))) | IF(OR(F452="",AN452=""),"",IF(COUNT(AI452:AM452)=0,"",AN452-LOOKUP(2,1/(AI452:AM452<>""),AI452:AM452))) | IF(OR(F452="",AO452=""),"",IF(COUNT(AI452:AN452)=0,"",AO452-LOOKUP(2,1/(AI452:AN452<>""),AI452:AN452))) | IF(OR(F452="",AP452=""),"",IF(COUNT(AI452:AO452)=0,"",AP452-LOOKUP(2,1/(AI452:AO452<>""),AI452:AO452))) | IF(OR(F452="",AQ452=""),"",IF(COUNT(AI452:AP452)=0,"",AQ452-LOOKUP(2,1/(AI452:AP452<>""),AI452:AP452))) | IF(OR(F452="",AR452=""),"",IF(COUNT(AI452:AQ452)=0,"",AR452-LOOKUP(2,1/(AI452:AQ452<>""),AI452:AQ452))) | IF(OR(F452="",AS452=""),"",IF(COUNT(AI452:AR452)=0,"",AS452-LOOKUP(2,1/(AI452:AR452<>""),AI452:AR452))) | IF(OR(F452="",AT452=""),"",IF(COUNT(AI452:AS452)=0,"",AT452-LOOKUP(2,1/(AI452:AS452<>""),AI452:AS452))) | IF(OR(F452="",AU452=""),"",IF(COUNT(AI452:AT452)=0,"",AU452-LOOKUP(2,1/(AI452:AT452<>""),AI452:AT452))) | IF(OR(F452="",AV452=""),"",IF(COUNT(AI452:AU452)=0,"",AV452-LOOKUP(2,1/(AI452:AU452<>""),AI452:AU452))) | IF(J452="","All_Provinces",IFERROR(VLOOKUP(J452,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K452="","All_Districts",IFERROR(VLOOKUP(K452,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F453="","",ROW()-3) | [18 empty] | IF(AQ453="","",AQ453) |  |  |  | IF(W453<>"",W453,IF(OR(T453="",V453=""),"",EDATE(T453,V453))) |  |  |  |  | IF(F453="","",IF(COUNT(AI453:AV453)=0,IF(AA453="","Not started",AA453),SUBSTITUTE(LOOKUP(2,1/(AI453:AV453<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F453="",COUNT(AI453:AV453)=0),"",TODAY()-LOOKUP(2,1/(AI453:AV453<>""),AI453:AV453)) | IF(OR(F453="",COUNT(AI453:AV453)<2),"",LOOKUP(2,1/(AI453:AV453<>""),AI453:AV453)-MIN(AI453:AV453)) | IF(OR(AD453="",AC453="Not started",AC453=""),"",IFERROR(AD453-IF(VLOOKUP(AC453,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC453,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F453="","",IF(OR(AA453="Cancelled",AC453="Cancelled"),"Cancelled",IF(OR(AC453="Completed / Handover",Y453<>"",Z453>=100),"Completed — on track",IF(O453="Not awarded",IF(U453="",IF(X453="","No planned date",IF(TODAY()>X453,"Behind — past planned date",IF(X453-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U453,"Behind — award date passed",IF(U453-TODAY()<=30,"At risk — close to off track","On track"))),IF(X453="","No planned date",IF(AND(TODAY()>X453,OR(Z453="",Z453<100)),"Behind — past end date",IF(AND(T453<>"",X453<>"",Z453<>"",(Z453<100),((TODAY()-T453)/MAX(X453-T453,1)*100)-Z453>15),"Behind — progress lag",IF(AND(X453-TODAY()<=30,X453-TODAY()>=0,OR(Z453="",Z453<90)),"At risk — close to off track","On track")))))))) | IF(OR(F453="",AC453="Completed / Handover",AC453="Cancelled"),"",IF(O453="Not awarded",IF(U453<>"",U453-TODAY(),IF(X453="","",X453-TODAY())),IF(X453="","",X453-TODAY()))) | [14 empty] | IF(OR(F453="",AJ453=""),"",IF(COUNT(AI453:AI453)=0,"",AJ453-LOOKUP(2,1/(AI453:AI453<>""),AI453:AI453))) | IF(OR(F453="",AK453=""),"",IF(COUNT(AI453:AJ453)=0,"",AK453-LOOKUP(2,1/(AI453:AJ453<>""),AI453:AJ453))) | IF(OR(F453="",AL453=""),"",IF(COUNT(AI453:AK453)=0,"",AL453-LOOKUP(2,1/(AI453:AK453<>""),AI453:AK453))) | IF(OR(F453="",AM453=""),"",IF(COUNT(AI453:AL453)=0,"",AM453-LOOKUP(2,1/(AI453:AL453<>""),AI453:AL453))) | IF(OR(F453="",AN453=""),"",IF(COUNT(AI453:AM453)=0,"",AN453-LOOKUP(2,1/(AI453:AM453<>""),AI453:AM453))) | IF(OR(F453="",AO453=""),"",IF(COUNT(AI453:AN453)=0,"",AO453-LOOKUP(2,1/(AI453:AN453<>""),AI453:AN453))) | IF(OR(F453="",AP453=""),"",IF(COUNT(AI453:AO453)=0,"",AP453-LOOKUP(2,1/(AI453:AO453<>""),AI453:AO453))) | IF(OR(F453="",AQ453=""),"",IF(COUNT(AI453:AP453)=0,"",AQ453-LOOKUP(2,1/(AI453:AP453<>""),AI453:AP453))) | IF(OR(F453="",AR453=""),"",IF(COUNT(AI453:AQ453)=0,"",AR453-LOOKUP(2,1/(AI453:AQ453<>""),AI453:AQ453))) | IF(OR(F453="",AS453=""),"",IF(COUNT(AI453:AR453)=0,"",AS453-LOOKUP(2,1/(AI453:AR453<>""),AI453:AR453))) | IF(OR(F453="",AT453=""),"",IF(COUNT(AI453:AS453)=0,"",AT453-LOOKUP(2,1/(AI453:AS453<>""),AI453:AS453))) | IF(OR(F453="",AU453=""),"",IF(COUNT(AI453:AT453)=0,"",AU453-LOOKUP(2,1/(AI453:AT453<>""),AI453:AT453))) | IF(OR(F453="",AV453=""),"",IF(COUNT(AI453:AU453)=0,"",AV453-LOOKUP(2,1/(AI453:AU453<>""),AI453:AU453))) | IF(J453="","All_Provinces",IFERROR(VLOOKUP(J453,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K453="","All_Districts",IFERROR(VLOOKUP(K453,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
Note on B3: Same Package ID on every sub-project of one contract. Package #8-AF2 IS is two canals / two rows; Package #10-AF2 IS is four canals / four rows. Use the outline +/- on the left to collapse extra sites.
Note on C3: Full Package / Contract Name from the master file. Repeated on every sub-project row of that package.
Note on D3: Position of this site inside the package, for example 2 of 4.
Note on G3: Major type: Watershed Management, Irrigation Scheme, Drip Irrigation, Agroforestry saplings / seeds, or Laser Land Leveler (LLL).
Note on H3: Sub-type under the major intervention: irrigation canal, protection wall, check dam, and so on.
Note on O3: Awarded = contract signed. Not awarded = still in design / procurement.
Note on Q3: Repeated on every sub-project of the same contract. To count unique contracts for this company, filter 10_By_Contractor or 03_Package_Summary — do not count the number of rows here. ZSCC on Package #10 is one contract / four canals.
Note on T3: Copies Date: Awarded. Enter the contract signature date in the Awarded status-date column.
Note on AA3: Use this until official step dates are entered. Current Status follows dates once they exist.
Note on AC3: Latest step that has a date. If no dates are entered, uses Reported Status.
Note on AD3: TODAY minus the latest status date. Turns red after 30 days.
Note on AG3: Green = on track. Amber = within 30 days of a planned date (close to off track). Red = behind the planned award or end date, or physical progress lagging the elapsed contract time by more than 15 points.
Note on AH3: Positive = days remaining until the planned award (Not awarded) or contract end (Awarded). Negative = days behind that date.

## 02_Dashboard
Dashboard — scheme counts and time spent in each step
Counts use Current Status (auto). Average days ignore blanks. Schemes with no scheme name are ignored. Red threshold for 'stuck' is 30 days.
Schemes registered |  |  | On track / completed |  |  | At risk — close to off track |  | Behind planned date
Schemes by current status · Packages = unique contracts (see 11_Package_Status) |  |  |  | Schemes by region |  |  | Average days between steps
Status | Sub-projects | Share of rows | Packages | Region | Count | Share | Step | Average days | Schemes with this step dated | Target days
Under Design |  |  |  | West / Herat
Under Review of WRI |  |  |  | East / Jalalabad
Under LTO Review |  |  |  | Central / Kabul
PR to be Raised |  |  |  | Central Highland / Bamyan
ITB Launched |  |  |  | Southeast / Gardez
Retendered (Re-ITB) |  |  |  | South / Kandahar
Under Technical Evaluation |  |  |  | North / Mazar
Under Awarding |  |  |  | Northeast / Kunduz
Awarded
Under Construction
Completed / Handover
Not started
Schemes by major intervention |  |  |  | Average total pipeline days (first → last dated step)
Major intervention | Count
Irrigation Scheme
Watershed Management |  |  |  | How to read this dashboard
Drip Irrigation |  |  |  | Current Status follows the latest date typed on 01_Scheme_Tracker. Until dates are entered, schemes sit under whatever you chose as Reported Status (or Not started). Average days between steps populate only after both ends of a step have dates — see 05_Example_Filled for a complete worked pipeline. Add or rename a status on 06_Status_Pipeline; this average-days table uses the tracker headers, so it follows. Awarded / Not awarded and major intervention counts are on this sheet; one row per contract is on 03_Package_Summary.
Laser Land Leveler (LLL)
Agroforestry saplings / seeds
Awarded / Not awarded
Group | Count
Awarded
Not awarded
Schemes by intervention sub-type
Intervention sub-type | Count
Irrigation Canal
Protection Wall
Karez Rehabilitation
Intake / Diversion
Check Dam
Boulder Check Dam
Check Dam and Water Pond
Gabion Structure
Flood Protection
Drip Irrigation Plot
LLL unit
Saplings and seeds
Water Supply Scheme
Other

## 03_Package_Summary
Package summary — one row per contract. Filter Contractor Name to see unique contracts awarded to a company (Zahid Saeed / ZSCC is one package, not four).
Example: Package #8-AF2 IS (Khas Kunar Lower canal + Bahrabad canal) is one package / two sub-projects. Package #10-AF2 IS (Baraki, Darbal, Nawikhar, Mangali) is one package / four sub-projects. Open 01_Scheme_Tracker and filter Package ID, or collapse the outline +/- on the left of that sheet. To list a company's contracts, filter this Contractor Name column or use 10_By_Contractor. Package status is the contract-level step (least-advanced unfinished site). Filter it, or use 11_Package_Status, to count packages under review / awarding / construction. Sub-project count and total cost are live formulas.
Package ID | Package / Contract Name | Major intervention | Awarded / Not awarded | Package status | Mixed sites? | Sub-projects | Total cost (USD) | Provinces | Districts | Statuses on sites | Awarded / expected award | Contract / expected end | Contractor Name | Contract Number | Source sheet
AF2-AGF-ALL | Agroforestry saplings and seeds 2026/27 | Agroforestry saplings / seeds | Not awarded | Under Awarding | No |  |  | Badakhshan, Badghis, Baghlan, Balkh, Daikundi, Faryab, Ghor, Helmand, Herat, Jawzgan, Kabul, Khost, Laghman, Logar, Nangarhar, Nuristan, Oruzgan, Paktia, Paktika, Panjsher, Samangan, Sari Pul, Takhar | Wardoj, Sang Atish, Banu, Charkent, Dehdadi, Kishendeh, Marmul, Nahre Shahi, Khedir, Meramour, Sharistan, Almar, Khoja Sabz Posh, Allahyar, Shahrak, Nawzad, Koshk-e-kohna, Rabat Sangi, Sheberghan, Surubi, Musa Khil, Qalander, Alishing, Azra, Pachiragam, Kamdish, Tarinkot, Zazi Aryoub, Zurmat, Surobi, Khinj, Paryan, Unaba, Aybak, Hazrat-e-Sultan, Balkhab, Center, Kohistanat, Bangi | Under Awarding | 2026-04-30 | 2027-04-01 |  |  | 7. Agroforestry Saplings-seeds
AF2-DIS-01 | Package #1.B-WBK/AF2 DIS: Demonstration 7 Drip irrigation schemes of 1. Doormishi, 2. Khodrawan, 3. Karez Naw, 4.Koklam Olia, 5. Koklam Sofla, 6 Joi Sultani and 7. Kushk Kohna in Kushk Rabat Sangi and Kushk e Kohna Districts of Herat Province. | Drip Irrigation | Not awarded | Retendered (Re-ITB) | No |  |  | Herat | Kushk e Rabat Sangi, Kushk e Kohna | Retendered (Re-ITB) | 2026-12-15 | 2027-04-29 | Abdul Qayum, Habiburahman, Ghulam Mahboob, Sadullah, Fazl Ahmad, Nesar Ahmad, Koklam, Mohammad Ibrahim |  | 5. Drip Irrigation systems
AF2-DIS-01A | Package #1 A -WBK/AF2 DIS: Demonstration of 7 Drip Irrigation schemes at 5 district sites of 1.Jakana, 2.Kharistan in Moqor, 3.Baghak in Qala-e-Naw of Badghis; 4. Ahangaran in Firozkoh, 5. Hamaye Khan in Dawlatyar districts of Ghor ; 6.Shadeh Olia, and 7.Shadeh Sofla in Zinda Jan district of Herat provinces | Drip Irrigation | Not awarded | Retendered (Re-ITB) | No |  |  | Ghor, Badghis, Herat | Firozkoh, Qala-e-Naw, Dawlatyar, Moqur, Zinda Jan | Retendered (Re-ITB) | 2026-12-05 | 2027-05-30 | Haji Yaqoub, Edi Mohammad, Haji Abdul Qaiyom, Sobhan, Saifuddin, Abdul Ghafour, Ahmad Zia |  | 5. Drip Irrigation systems
AF2-DIS-02A | Package #2 A&B-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes of 1. Abdul Qadir, 2.Abdul Raqib, 3.Nazar Khan, 4.Khas Kunar, 5.Asmar, 6.Manogai, 7.Kunar University, 8.Parun, 9.Mateeullah, 10..Habibullah, 11.Surkhrood, and 12.Khewa, located in Alishing,Pacheragam, Batikot,Khas Kunar, Asmar, Manogai, Asadabad, Parun, Barg-e-Matal, Sorkhrud and Khewa districts of Laghman, Nangarhar, Kunar and Nuristan provinces. | Drip Irrigation | Not awarded | Retendered (Re-ITB) | No |  |  | Laghman, Nuristan, Nangarhar, Kunar | Alishing, Barg-e-Matal, Sorkhrud, Khewa, Pacheragam, Batikot, Khas Kunar, Asmar, Manogai, Asadabad, Parun | Retendered (Re-ITB) | 2026-12-24 | 2027-05-23 | Abdul Qadeer, Habibullah, Ehsanullah, Ramin, Abdur Raqeeb, Nazar Khan, M. Nabi, Malik Rostam, M. Afzal, Kunar University, Mateeullah |  | 5. Drip Irrigation systems
AF2-DIS-03 | Package #3-WBK/AF2 DIS: Demonstration of 14 Drip irrigation schemes at 13 district sites of 1. Parwan, 2. Kabul, 3. Wardak and 4. Kapisa provinces. | Drip Irrigation | Not awarded | Retendered (Re-ITB) | No |  |  | Kapisa, Kabul, Parwan, Wardak | Hesa-e- Awal Kohistan, Paghman, Shikh Ali, Saydabad, Nirkh, Sarobi, Jaghatu, Surkh Parsa, Chack, Tagab, Khak-e-Jabar, Bagram, Mahmood Raqi | Retendered (Re-ITB) | 2026-12-20 | 2027-07-05 | Alberoni University, Mohammad Yousaf, Abdullah, Wardak University, Fazel Rahman, Hayatullah, Mohammad Akbar, Ghulam Haider Shah, Mohammad Qasim, Najeebullah, Jalal, Mohammad Waseem, Reg-e-Rawa park, Khairullah Zia |  | 5. Drip Irrigation systems
AF2-DIS-04 | Package #4-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 4 district sites of 1. Miramor, 2. Shahristan, 3.Nilli, and 4.Sayghan in Daykundi and Bamyan provinces | Drip Irrigation | Not awarded | Retendered (Re-ITB) | No |  |  | Daykundi, Bamyan | Miramor, Shahristan, Sayghan, Nilli | Retendered (Re-ITB) | 2026-12-20 | 2027-06-28 | Ghulam, Mohammad Arif, Mohammad Ibrahim, Ahmad, Mohammad Ali, Ali Dost, Mohammad Hashim, Abdul Rahman, Sayed Mohammad, Ghulam Hussain, Sayed Hassan, Reza |  | 5. Drip Irrigation systems
AF2-DIS-05 | Package # 5 - AF2 DIS: Demonstration of 15 Drip irrigation schemes of 1.Hassan Khail-A, 2.Hasan Khail-B, , 3.Ghafoor Khail, 4.Paktia university, 5.Nughi, 6.Deya, 7.Basana, 8.Nawe patana, 9.Sultani, 10.Gir, 11.Milma Kot Bagh, 12.Sahra Bagh, 13.Agriculture Research, 14.Logar University, and 15.Dabar Allu, located in Ahmad Aba, Provincial Centers, Ander, Sharana, Sarhawz, Matoon, Pul-e-Alam and Charkh districts of Paktia, Ghazni, Pakteka, Khost and Logar provinces. | Drip Irrigation | Not awarded | Retendered (Re-ITB) | No |  |  | Khost, Ghazni, Logar, Paktya, Pakteka | Matoon, Andar, Charkh, Deyak, Center, Sharana, Ahmad Aba, Pole Alam, Gardez_center, Sarhawza | Retendered (Re-ITB) | 2026-12-25 | 2027-07-03 | Hazrat Wali, Mohammad Naim, Mohammad Akbar, Naser Khan, Salam Jan, Fazal Din, Zabihullah, Hasan Khil, Islam Gul, Saifullah, Ghazi Khan, Hakim Khan, Mohammad Rasool Gharani, Gafoor Jan, Akhtar Mohammad |  | 5. Drip Irrigation systems
AF2-DIS-06 | Package #6-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 11 district sites of 1. Momand in Daman, 2.Garmaw Kali in Panjwai, and 3.Serdagh Kali in Naish districts of Kandahar province; 4.Rud Kali in Tarnak- Jaldak, 5.Omarzai and 6. Bahu Kali in Seyure districts of Zabul province; 7. Kona Kala in Chinarto and 8.Khair Abad in Terinkot districts of Urozgan province; 9. Badam Kali in Nawzad and 10.Takhtapool Kali in Musa Qala districts of Helmand province; 11. Loy Razi in Khashrod and Firozi in Delaram districts of Nemroz province. | Drip Irrigation | Not awarded | Under Review of WRI | No |  |  | Helmand, Zabul, Nemroz, Kandahar, Urozgan | Nawzad, Seyure, Delaram, Panjwai, Shah Wali Kot, Terinkot, Khashrod, Daman, Tarnak- Jaldak, Naish | Under Review of WRI | 2027-01-25 | 2027-06-24 |  |  | 5. Drip Irrigation systems
AF2-DIS-07 | Package #7-WBK/AF2 DIS: Demonstration of 9 Drip Irrigation Schemes at 9 district sites of 1. Khwaja bolak in Khan Abad and 2. Shamba Bazar in Dashte Archi 3. Haji Atta Khan & 4. Masjid Dr. Shafiq Mamakhail in Chahar Dara districts of Kunudz province; 5. Tilajat in Rustaq and 6. Chaqul in Baharak districts of Takhar province; 7 Sara-e-Gharbi in Badakhshan province; 8. Khoja Alwan in Dahna-e-Ghori and 9. Qatar Fateh in Dand-e-Ghori district of Baghlan Province | Drip Irrigation | Not awarded | Under Review of WRI | No |  |  | Takhar, Kunduz, Baghlan, Kunudz, Badakhshan | Baharak, Chahar Dara, Dand Ghori, Khan Abad, Dahna-e-Ghori, Kishem, Dashte Archi, Rustaq | Under Review of WRI | 2027-01-25 | 2027-08-03 | Nasratullah, Haji Hamayoon Salimi, Haji Amir Gul, Mohammad Qasim, Ziaurrahman Mohammadi, Haji Nazar Gul, Haji Jamal, Shamsurahman, Fida Mohammad |  | 5. Drip Irrigation systems
AF2-DIS-08 | Package #8-WBK/AF2 DIS: Demonstration of 12 Drip irrigation schemes at 10 district sites of 1. Nasaji in Nahr-e-Shai, 2. Hesarak in Balkh, and 3. Tokhta in Dehdadi districts of Balkh province; 4.Hadbakhshy in Saidabad, 5. Olqani and 6. Adrin in Center, and 7.Lar Badamak in Sandcharak districts of Sar-e-Pul province; 8.Baba Qambar in Khuram Wa Sarbagh, 9.Tangi Asiabad and 10. Hasan Kahil in Aybak districts of Samangan province; 11.Tepa Qeshlaq in Khowja Sabz Posh district of Faryab province; and 12. Tonika in Center of Jawzjan province. | Drip Irrigation | Not awarded | Under Review of WRI | No |  |  | Samangan, Balkh, Sari Pul, Jawzjan, Faryab | Aybak, Mazar-e-Sharif, Charkent, Dehdadi, Sayed Abad, Sheberghan, Hazrat-e-Sultan, Khwaja Sabz Posh, Center | Under Review of WRI | 2026-01-20 | 2026-07-29 |  |  | 5. Drip Irrigation systems
AF2-IS-01 | Package #1-AF2 IS: Rehabilitation of Joy Bazar irrigation scheme located in Obe district of Herat province. | Irrigation Scheme | Awarded | Completed / Handover | No |  |  | Herat | Obeh | Completed / Handover | 2025-09-16 | 2026-09-15 | Afghan Aakam Construction and Road Company C. JV with D-Amini Mashwani Construction Road Juroni and Construction Materials Production Company (AACRC&JV DAMCC) | 050/2025 | 1.Awarded contracts_On&off-farm
AF2-IS-02 | Package # 2-AF2 IS: Rehabilitation of irrigation schemes of 1.Ali Mansoor Canal in Karukh district, 2.Joy Sork and 3.Sar Kari canals in Farsi districts of Herat province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Herat | Karukh, Farsi | Under Construction | 2026-07-22 | 2027-07-21 | Arman Millad Construction Company (AMCC) | 046/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-03 | Package #3-AF2 IS: Rehabilitation of Yazdi irrigation scheme, located in Center Districts of Farah province. | Irrigation Scheme | Not awarded | Under Review of WRI | No |  |  | Farah | Center | Under Review of WRI | 2026-12-15 | 2027-09-14 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-04 | Package #4-AF2 IS: Rehabilitation of Joi Gang irrigation scheme in Bala Murghab districts of Badghis provinec. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Badghis | Bala Murghab | PR to be Raised | 2026-12-31 | 2027-10-27 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-05 | Package #5-AF2 IS: Rehabilitation of Korakha irrigation scheme, located in Dawlatyar District of Ghor province. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Ghor | Dawlatyar | PR to be Raised | 2026-12-25 | 2027-08-12 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-06 | Package #6-AF2 IS: Rehabilitation of Kushtal Canal, Checknawar canal, and Patikhirrki canal irrigation schemes, located in Lalpora ,Spinghar and Khogyani districts of Nangarhar province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Nangarhar | Spinghar, Lalpora, Khogyani | Under Construction | 2025-10-25 | 2026-10-24 | Shirali Khan Barakatzai Construction Company (SBCC) | 054/2025 | 1.Awarded contracts_On&off-farm
AF2-IS-07 | Package #7-AF2 IS: Rehabilitation of Kham Canal and Shandi Toot canal irrigation schemes, located in Dehbala and Sherzad districts of Nangarhar provinces. | Irrigation Scheme | Not awarded | Under Technical Evaluation | No |  |  | Nangarhar | Dehbala, Sherzad | Under Technical Evaluation | 2026-10-30 | 2027-05-28 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-08 | Package #8-AF2 IS: Rehabilitation of Khas Kunar Lower canal and Bahrabad canal irrigation schemes, located in Khas Kunar district of Kunar and Behsood district of Nangarhar provinces. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Nangarhar, Kunar | Behsood, Khas Kunar | Under Construction | 2026-08-20 | 2027-08-19 | Awrish builder construction company (ABCC) | 055/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-09 | Package #9-AF2 IS: Rehabilitation of Akchori canal irrigation scheme, located in Waigal districts of Nuristan provinces. | Irrigation Scheme | Not awarded | ITB Launched | No |  |  | Nuristan | Waigal | ITB Launched | 2026-11-27 | 2027-09-26 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-10 | Package #10-AF2 IS: Rehabilitation of 1.Baraki canal, 2. Darbal canal, 3. Nawikhar canal and 4. Mangali canal irrigation schemes, located in Sayed Abad, Chak and Jaghato districts of Wardak province. | Irrigation Scheme | Awarded | Awarded | Yes |  |  | Wardak | Sayed Abad, Chak, Jaghato | Completed / Handover, Awarded, Under Construction | 2025-11-18 | 2026-11-17 | Zahid Saeed Engineering and Construction Company (ZSCC) | 057/2025 | 1.Awarded contracts_On&off-farm
AF2-IS-11 | Package #11-AF2 IS: Rehabilitation of Musahi Sufla canal irrigation schemes, located in Musahi districts of Kabul province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Kabul | Musahi | Under Construction | 2025-10-27 | 2026-10-26 | Seddiq Amini Construction and Logistic Services (SACC) | 056/2025 | 1.Awarded contracts_On&off-farm
AF2-IS-12 | Package #12-AF2 IS: Rehabilitation of Tapa-e-Ahmad Big canal and Shahre Beland canal irrigation schemes, located in Nijrab and Paryan districts of Kapisa and Panjsher provinces. | Irrigation Scheme | Not awarded | Under Technical Evaluation | No |  |  | Panjshir, Kapisa | Paryan, Nijrab | Under Technical Evaluation | 2026-11-01 | 2027-07-29 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-13 | Package #13-AF2 IS: Rehabilitation of Kamar China canal, Khenkot canal, and Zargara irrigation schemes, located in Sarobi, Chahar Asiab and Paghman districts of Kabul province. | Irrigation Scheme | Not awarded | Under Technical Evaluation | No |  |  | Kabul | Sarobi, Chahar Asiab, Paghman | Under Technical Evaluation | 2026-11-10 | 2027-07-08 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-14 | Package #14-AF2 IS: Rehabilitation of Zard Sang and Topchi Cluster Canal Irrigation scheme, located in Center district of Bamyan province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Bamyan | Center | Under Construction | 2026-01-24 | 2027-01-23 | Nomae Shahr Construction Company (NSCC) | 002/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-15 | Package #15-AF2 IS: Rehabilitation of Pitab joy and Sorkh Kawak Cluster Canal Irrigation scheme, located in Waras districts of Bamyan province. | Irrigation Scheme | Not awarded | Retendered (Re-ITB) | No |  |  | Bamyan | Waras | Retendered (Re-ITB) | 2026-12-15 | 2027-09-21 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-16 | Package #16-AF2 IS: Rehabilitation of Pato (Paye Raqul, Sangchal Takhomak and Kadalak) Cluster canal irrigation scheme in Pato district of Daykundi province | Irrigation Scheme | Awarded | Completed / Handover | No |  |  | Daykundi | Pato | Completed / Handover | 2026-01-21 | 2027-01-20 | Estehkam Baba Construction Company JV Tamadon Bamik Construction Company (EBCC) | 007/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-17 | Package #17-AF2 IS: Rehabilitation of Hezhdi- Nilli, Cluster Canal irrigation schemes, located in Nilli district of Daykundi province. | Irrigation Scheme | Not awarded | Retendered (Re-ITB) | No |  |  | Daykundi | Nilli | Retendered (Re-ITB) | 2026-12-15 | 2027-09-11 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-18 | Package #18-AF2 IS: Rehabilitation of Drang canal irrigation schemes, located in Zurmat district of Paktya province. | Irrigation Scheme | Not awarded | ITB Launched | No |  |  | Paktya | Zurmat | ITB Launched | 2026-11-30 | 2027-10-29 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-19 | Package #19-AF2 IS: Rehabilitation of Khwaja Angor canal and Qalai Wazir canal irrigation schemes located in Kharwar and Pol-i-Alam districts of Logar province. | Irrigation Scheme | Awarded | Under Construction | Yes |  |  | Logar | Kharwar, Pol-i-Alam | Under Construction, Completed / Handover | 2025-12-31 | 2026-12-30 | Unique Wahaj Construction Company (UWCC) | 074/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-20 | Package #20-AF2 IS: Rehabilitation of Welgai irrigation system, located in Matoon district of Khost province. | Irrigation Scheme | Awarded | Completed / Handover | No |  |  | Khost | Matoon | Completed / Handover | 2025-10-12 | 2026-10-11 | Mahmood Raqi Nawin Construction & Road Building Company (MRCC) | 053/2025 | 1.Awarded contracts_On&off-farm
AF2-IS-21 | Package # 21-AF2 IS: Rehabilitation of Markazi Ziruk and Mulakh canal irrigation schemes, located in Ziruk and Yousaf Khil districts of Pakteka province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Pakteka | Ziruk, Yousaf Khil | Under Construction | 2026-06-06 | 2027-06-05 | Farhad Matoonyar Construction Company (FMCC) | 038/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-22 | Package # 22-AF2 IS: Rehabilitation of Gero canal irrigation scheme, located in Center and Qarabagh districts of Ghazni province. | Irrigation Scheme | Not awarded | Under LTO Review | No |  |  | Ghazni | Center | Under LTO Review | 2026-12-28 | 2027-10-24 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-23 | Package #23-AF2 IS: Rehabilitation of Patab canal irrigation schemes, located in Khas Urozgan of Urozgan province. | Irrigation Scheme | Not awarded | Retendered (Re-ITB) | No |  |  | Urozgan | Khas Urozgan | Retendered (Re-ITB) | 2026-12-15 | 2027-09-11 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-24 | Package #24-AF2 IS: Rehabilitation of Shajoy canal irrigation scheme, located in Dayee Chopan districts of Zabul province. | Irrigation Scheme | Not awarded | Under Design | No |  |  | Zabul | Dayee Chopan | Under Design | 2026-12-20 | 2027-09-16 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-25 | Package #25-AF2 IS: Rehabilitation of Urdo Kas canal and Sarkay Lazhey canal irrigation schemes, located in Sha Wali Kot and Boldak districts of Kandahar province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Kandahar | Boldak, Sha Wali Kot | Under Construction | 2026-02-09 | 2026-12-08 | Wasif Construction Company | 012/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-26 | Package #26-AF2 IS: Rehabilitation of Sarwan Qala canal irrigation schemes, located in Sangin district of Kandahar province. | Irrigation Scheme | Awarded | Awarded | No |  |  | Helmand | Sangin | Awarded | 2026-03-03 | 2027-03-02 | New Safi Zada Construction & Road Building Company JV with Elyas Aryoubi Constructin Road building and Logistic Company (NSZ&EACC) | 019/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-27 | Package # 27-AF2 IS: Rehabilitation of Firozi canal irrigation scheme, located in Delaram districts of Nimroz province. | Irrigation Scheme | Not awarded | Under Review of WRI | No |  |  | Nimruz | Delaram | Under Review of WRI | 2026-12-25 | 2027-09-21 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-28 | Package # 28 – AF2 IS: Rehabilitation of Irrigation Schemes of 1. Abil Aroq (Qanjogha), 2. Shaitan Aroq Cluster Canals in Khwaja Ghar District and 3. Kalta Aroq, 4. Pacha Khail, and 5. Sayed Miran (Khar Kar) Cluster Canals in Eshkamish District of Takhar Province | Irrigation Scheme | Awarded | Awarded | Yes |  |  | Takhar | Khwaja Ghar, Eshkamish | Awarded, Under Construction | 2025-12-22 | 2026-12-21 | SHAMAL KARDAN ROAD CONSTRUCTION AND LOGISTIC SERVICES COMPANY LTD (SKRCC) | 067/2025 | 1.Awarded contracts_On&off-farm
AF2-IS-29 | Package #29-AF2 IS: Rehabilitation of Dagh Aruq canal irrigation scheme, located in Chahar Dara district of Kunduz province. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Kunduz | Chahar Dara | PR to be Raised | 2026-11-25 | 2027-09-21 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-30 | Package # 30-AF2 IS: Rehabilitation of Teshkhan canal canals irrigation scheme, located in Ishkashim districts of Badakhshan province. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Badakhshan | Ishkashim | PR to be Raised | 2027-01-12 | 2027-10-09 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-31 | Package #31-AF2 IS: Rehabilitation of 1. Shahidan &Dasht-e Lajam Canal schems in Tala wa barfak district, 2.Sardar Ha canal scheme in Deh Salah district, and 3. Kambilan cluster canal schemes in Fring districts of Baghlan province. | Irrigation Scheme | Awarded | Under Construction | Yes |  |  | Baghlan | Fring, Deh Salah, Tala wa barfak | Completed / Handover, Under Construction | 2026-01-29 | 2026-11-28 | Afghan Eithad construction and Road Building company (AECC) | 009/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-32 | Package #32-AF2 IS: Rehabilitation of Abdul Baqi canal and Mulla Oma canal irrigation schemes, located in Chemtal districts of Balkh province. | Irrigation Scheme | Awarded | Completed / Handover | No |  |  | Balkh | Chemtal | Completed / Handover | 2025-12-31 | 2026-11-29 | Trust Grow Construction and Engineering Company (TGCC) | 075/2025 | 1.Awarded contracts_On&off-farm
AF2-IS-33 | Package #33-AF2 IS: Rehabilitation of Chela Mazar canal and Kushkak canal irrigation schemes, located in Dara-e- Suf-e-Bala and Dara-e-Suf-e-Payeen districts of Samangan province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Samangan | Dara-e- Suf-e-Payeen, Dara-e- Suf-e-Bala | Under Construction | 2026-01-15 | 2026-12-14 | AFGHAN LUCKY CONSTRUCTION COMPANY (ALCC) | 003/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-34 | Package #34-AF2 IS: Rehabilitation of Hashtman canal and Qashqasai canal irrigation schemes, located in Qaisar district of Faryab province. | Irrigation Scheme | Not awarded | ITB Launched | No |  |  | Faryab | Qaisar | ITB Launched | 2026-12-30 | 2027-10-06 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-35 | Package # 35-AF2 IS: Rehabilitation of Bahr-e Ameq canal irrigation scheme, located in Sozma Qala districts of Sar-e-Pul province. | Irrigation Scheme | Awarded | Under Construction | No |  |  | Sar-e- Pul | Sozma Qala | Under Construction | 2026-02-17 | 2027-01-16 | Sakht shamal construction and road building company (SSCC) | 016/2026 | 1.Awarded contracts_On&off-farm
AF2-IS-36 | Package # 36-AF2 IS: Rehabilitation of Joy Shahr canal irrigation scheme, located in Aqcha district of Jawzjan province. | Irrigation Scheme | Not awarded | Under LTO Review | No |  |  | Jawzjan | Aqcha | Under LTO Review | 2026-12-17 | 2027-06-05 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-37 | Package #37-AF2 IS: Rehabilitation of Oshtorkhan/Ahangaran irrigation scheme, located in Firozkoh district of Ghor province. | Irrigation Scheme | Not awarded | Under Design | No |  |  | Ghor | Firozkoh | Under Design | 2026-12-30 | 2027-08-17 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-38 | Package #38-AF2 IS: Rehabilitation of Todanak Payen irrigation scheme, located in Farahrud Districts of Farah province. | Irrigation Scheme | Not awarded | Under Review of WRI | No |  |  | Farah | Farahrud | Under Review of WRI | 2026-12-15 | 2027-09-14 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-39 | Package #39-AF2 IS: Rehabilitation of Ludeenha and Joi Kar irrigation schemes in Bala Murghab districts of Badghis provinec. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Badghis | Bala Murghab | PR to be Raised | 2026-12-30 | 2027-08-27 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-40 | Package #40-AF2 IS: Rehabilitation of Loka Mazar irrigation schemes, located in Dawlatyar District of Ghor province. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Ghor | Dawlatyar | PR to be Raised | 2026-12-31 | 2027-08-28 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-41 | Package #41-AF2 IS: Rehabilitation of Madrasa irrigation schemes, located in Firozkoh district of Ghor province. | Irrigation Scheme | Not awarded | Under Design | No |  |  | Ghor | Firozkoh | Under Design | 2026-12-20 | 2027-08-17 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-42 | Package #42-AF2 IS: Rehabilitation of Zard Nai Charsapan Cluster Canal irrigation schemes, located in Sharrisatan district of Daykundi province. | Irrigation Scheme | Not awarded | Under LTO Review | No |  |  | Daykundi | Shahristan | Under LTO Review | 2026-12-15 | 2027-10-21 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-43 | Package #43-AF2 IS: Rehabilitation of Sar Nary canal irrigation scheme, located in Arghandab districts of Zabul province. | Irrigation Scheme | Not awarded | Under Design | No |  |  | Zabul | Arghandab | Under Design | 2026-12-20 | 2027-09-16 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-44 | Package #44-AF2 IS: Rehabilitation of Boghoz Qum canal irrigation schemes, located in Chahar Dara district of Kunduz province. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Kunduz | Chahar Dara | PR to be Raised | 2026-11-25 | 2027-09-21 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-45 | Package # 45-AF2 IS: Rehabilitation of Khushpak Markazi canals irrigation scheme, located in Ishkashim districts of Badakhshan province. | Irrigation Scheme | Not awarded | PR to be Raised | No |  |  | Badakhshan | Ishkashim | PR to be Raised | 2027-01-13 | 2027-08-11 |  |  | 2.Remain contracts_On&off-farm
AF2-IS-46 | Package # 46-AF2 IS: Rehabilitation of Joy Shahr canal and Khanum Arabia canal irrigation schemes, located in Aqcha and Faizabad districts of Jawzjan province. | Irrigation Scheme | Not awarded | Under LTO Review | No |  |  | Jawzjan | Faizabad | Under LTO Review | 2026-12-18 | 2027-10-14 |  |  | 2.Remain contracts_On&off-farm
AF2-LLL-ALL | EFSP-AF2 LLL supply and delivery (50 units) | Laser Land Leveler (LLL) | Not awarded | Under Awarding | No |  |  | Balklh, Takhar, Herat, Laghman, Sar-E-Pul, Kunduz, Nangarhar, Samangan, Paktya, Parwan, Faryab, Ghor, Badghis, Jawzjan, Kabul, Baghlan, Kunar, Badakhshan, Logar, Midan Wardak, Paktika, Helamand, Farah, Ghazni, Urozgan, Kapisa, Kandahar, Zabul, Khost, Bamyan | Chimtal, Khwaja Ghar, Karukh, Alingar, Sozma Qala, Char Dara, Lalpoora, Dara-e-Suf-e-Payeen, Zurmat, Jabul Saraj, Qaisar, Dawlatyar, Obe, Balamorghab, Aqcha, Qarabagh, Firing, Faizabad, Eshkamish, Khas kunar, Ishkashim, Kharwar, Dara-e-Suf-e-Bala, Hesa Awal Behsood, Yousif Khail, Nahri Siraj, Farah, Ghazni, Mehtherlam, Khas Urozgan, Khogiani, Qala-E-Wazir, Nijrab, Zinda Jan, Deh Sala, Spin Boldak, Pashton Zarghon, Tala Wa Barfak, Khak e Afghan, Shawalikot, Matoon, Bamiyan, Kalakan | Under Awarding | 2026-10-30 | 2027-01-31 |  |  | 6. Supply and delivery of LLL
AF2-WSM-01 | Package #1-AF2 WSM: Construction of Dara Garmak Check dam, located in Qadis districts of Badghis province | Watershed Management | Not awarded | PR to be Raised | No |  |  | Badghis | Qadis | PR to be Raised | 2026-12-05 | 2027-09-01 |  |  | 4.WSM remaining contracts
AF2-WSM-02 | Package #2 -AF2 WSM: Construction of 1. Dareh Shah Toot-1, 2. Dareh ShahToot-2, and 3. Jar Sono check dams in Obe District of Herat Province | Watershed Management | Awarded | Under Construction | No |  |  | Herat | Obe | Under Construction | 2026-02-09 | 2026-12-08 | Shams Afghan Vision Construction and Logistic Services (SAVCC) | 014/2026 | 3.WSM awarded contracts
AF2-WSM-03 | Package #3 -AF2 WSM: Construction of Koklam three Check Dams (# 1, # 2 and # 3 ) in Kushk-e-Kohna District of Herat Province | Watershed Management | Awarded | Under Construction | No |  |  | Herat | Koshk-e-Kohna | Under Construction | 2026-01-21 | 2026-11-20 | Afghan Aakam Construction and Road Company. JV with D- Amini Mashwani Construction Company (AACC) | 006/2026 | 3.WSM awarded contracts
AF2-WSM-04 | Package #4-AF2 WSM: Construction of .Qalai Gerd check dam in Firozkoh dustrict of Ghor province. | Watershed Management | Not awarded | PR to be Raised | No |  |  | Ghor | Firozkoh | PR to be Raised | 2026-12-10 | 2027-10-06 |  |  | 4.WSM remaining contracts
AF2-WSM-05 | Package #5-AF2 WSM/Part-2: Construction of 4 Check dams of 1.Farman Khil and 2.Kharoti in Qarghaee district of Laghman province; 3. Lokhy Solozi and 4. Lala Kali in Chaparhar districts of Nangarhar province. | Watershed Management | Awarded | Awarded | Yes |  |  | Laghman, Nangarhar | Qarghaee, Chaparhar | Under Construction, Awarded | 2026-05-30 | 2026-10-29 | Khaliqi Building & Road Construction Company (KBRCC) | 040/2026 | 3.WSM awarded contracts
AF2-WSM-06 | Package #6-AF2 WSM: Construction of Jarobi Tangi, Chaghari and Adore check dams, located in Shirzad, Rodat, and Khogyani, districts of Nangarhar province. | Watershed Management | Awarded | Completed / Handover | No |  |  | Nangarhar | Sherzad, Rodat, Khogyani | Completed / Handover | 2025-12-23 | 2026-07-22 | Naeemi Safi Construction & Construction Material Company (NSCC) | 065/2026 | 3.WSM awarded contracts
AF2-WSM-07 | Package #7-AF2 WSM: Construction of 3 Check dams of 1.Dargrak, 2. Migano, and 3.Lachagali the Sawkai, Khas Kunar and Narang districts of Kunar province. | Watershed Management | Awarded | Awarded | No |  |  | Kunar | Sawkai, Narang, Khas Kunar | Awarded | 2026-10-11 | 2027-03-10 | Green Bentley construction Company (GBCC) | 064/2026 | 3.WSM awarded contracts
AF2-WSM-08 | Package #8-AF2 WSM: Construction of 1.Ghazgai Check dam in Khake Jabar districts, 2.Toop Dara Check dam and 3.Toot Dara Check dam in Center/ 13th City district Kabul province. | Watershed Management | Awarded | Completed / Handover | No |  |  | Kabul | Center, Khake Jabar | Completed / Handover | 2026-01-20 | 2026-08-19 | ALTIN CONSTRUCTION AND ROAD BUILDING COMPANY (ACC) | 005/2026 | 3.WSM awarded contracts
AF2-WSM-09 | Package #9-AF2 WSM: Construction of 1.Aka Khil Check dam and 2. Sra Qala Check dam in Sayed district, 3.Khar Check dam and 4.Mardala Check dam, located in Jaghatu districts of Wardak province. | Watershed Management | Awarded | Completed / Handover | No |  |  | Maidan Wardak | Sayed Abad, Jaghatu | Completed / Handover | 2026-03-10 | 2026-10-08 | Sayed Abad Construction Company (SACC) | 021/2026 | 3.WSM awarded contracts
AF2-WSM-10 | Package #10-AF2 WSM: Construction of Loy Shenkai Check dams # 1 and # 2 in Tagab district, and Shahr-e-Naw Check dam # 3 located in Nijrab districts of Kapisa province. | Watershed Management | Awarded | Completed / Handover | No |  |  | Kapisa | Tagab, Nijrab | Completed / Handover | 2026-03-09 | 2026-09-08 | Kapisa Kohna Dah Construction Company (KKCC) | 020/2026 | 3.WSM awarded contracts
AF2-WSM-11 | Package #11-AF2 WSM: Construction of 3 Check dams 1.Wolangak in Shikh Ali, 2.Sanzalai, and 3.Sharkai Olia in Koh-e-Safi district of Parwan province. | Watershed Management | Awarded | Awarded | Yes |  |  | Parwan | Koh-e-Safi, Shikh Ali | Under Construction, Awarded | 2026-06-24 | 2026-11-23 | Hemat Ghorzang Construction & Logistic Service Company (HGCC) | 043/2026 | 3.WSM awarded contracts
AF2-WSM-12 | Package #12-AF2 WSM: Construction of 4 Check dams 1. Qoli Ghafoor, 2. Dara-e-Qala-e-Qazi in PD#13 Kabul city, 3.Gul Mohammad and 4.Qala-e-Shah Mahmood in Deh Sabz district of Kabul province. | Watershed Management | Not awarded | PR to be Raised | No |  |  | Kabul | Deh Sabz, PD#13 Kabul | PR to be Raised | 2026-12-15 | 2027-09-11 |  |  | 4.WSM remaining contracts
AF2-WSM-13 | Package #13-AF2 WSM: Construction of 4 Check Dams in 4 district sites of 1.Kata Khana in Yakawlang , 2. Nawora in Panjab, 3.Nahorak in Waras, and 4.Bayani in Sayghan districts of Bamyan province | Watershed Management | Awarded | Under Construction | No |  |  | Bamyan | Yakawalang, Panjab, Waras, Sayghan | Under Construction | 2026-07-22 | 2027-02-21 | Estehkam Baba Construction and Road Construction Company (EBCC) | 051/2026 | 3.WSM awarded contracts
AF2-WSM-14 | Package #14-AF2 WSM: Construction of 1.Shahristan Check dama in Shahristan district, 2.Miramor Check dam in Miramor district, and 3.Khidir Check dams in Khidir districts of Daykundi province. | Watershed Management | Awarded | Completed / Handover | No |  |  | Daykundi | Shahristan, Miramor, Khidir | Completed / Handover | 2026-04-01 | 2026-10-30 | Da Maidan Zawahnono Construction Company (DMZCC) | 025/2026 | 3.WSM awarded contracts
AF2-WSM-15 | Package #15-AF2 WSM: Construction of 3 Check dams of 1. Sangmom, 2. Shilan Korga, and 3.Khulbar in Nili, Ashtarlay, and Sang Takhta districts of Daykundi province. | Watershed Management | Awarded | Awarded | No |  |  | Daykundi | Sang Takht wa Bandar, Nili, Ashtarlay | Awarded | 2026-10-08 | 2027-03-07 | Bahartamadun Construction Company (BCC) | 065/2026 | 3.WSM awarded contracts
AF2-WSM-16 | Package #16-AF2 WSM: Construction of Panami Check dams, located in Mohammad Agha district of Logar province. | Watershed Management | Awarded | Under Construction | No |  |  | Logar | M.Agha | Under Construction | 2026-04-18 | 2026-11-17 | Sayed Shirazi Construction and Road Building Company (SCRC) | 030/2026 | 3.WSM awarded contracts
AF2-WSM-17 | Package #17-AF2 WSM: Construction of Ghoriza Check dams, located in Sayed Karam districts of Paktya province. | Watershed Management | Not awarded | PR to be Raised | No |  |  | Paktya | Sayed Karam | PR to be Raised | 2026-11-20 | 2027-06-28 |  |  | 4.WSM remaining contracts
AF2-WSM-18 | Package #18-AF2 WSM: Construction of Muqarab Check dams, located in Gelan districts of Ghazni province. | Watershed Management | Awarded | Under Construction | No |  |  | Ghazni | Gelan | Under Construction | 2026-07-23 | 2027-01-22 | Hemat safi construction company (HSCC) | 047/2026 | 3.WSM awarded contracts
AF2-WSM-19 | Package #19-AF2 WSM: Construction of two Check dams 1. Wazgarai and 2. Chenargai in Zazai Maidan districts of Khost province. | Watershed Management | Not awarded | ITB Launched | No |  |  | Khost | Zazai Maidan | ITB Launched | 2026-11-30 | 2027-06-28 |  |  | 4.WSM remaining contracts
AF2-WSM-20 | Package #20-AF2 WSM: Construction of Sapari Check dams, located in Sarubi districts of Paktika province. | Watershed Management | Not awarded | PR to be Raised | No |  |  | Paktika | Sarubi | PR to be Raised | 2026-11-25 | 2027-07-03 |  |  | 4.WSM remaining contracts
AF2-WSM-21 | Package #21-AF2 WSM: Construction of 4 Check Dams 1.Choghazey and 2.Sardarkey in Arghistan, 3. Loy Laher in Spin Boldak and 4.Ab Samad Aka in Takhta Pull districts of Kandahar province. | Watershed Management | Awarded | Under Construction | Yes |  |  | Kandahar | Takhta Pul, Arghistan, Spin Boldak | Under Construction, Completed / Handover | 2026-04-28 | 2026-09-27 | Bakhter Pairoz Construction Company (BPCC) | 031/2026 | 3.WSM awarded contracts
AF2-WSM-22 | Package #22-AF2 WSM: Construction of 5 Check dams 1.Kocni Karez , 2.By Khosh , 3. Ghul Khani, 4. Chy Dara in Ghorak district , and 5. Khanjak Mastan Aka in Nesh district of Kandahar province. | Watershed Management | Not awarded | Under Design | No |  |  | Kandahar | Ghorak, Nesh | Under Design | 2026-11-30 | 2027-05-29 |  |  | 4.WSM remaining contracts
AF2-WSM-23 | Package #23-AF2 WSM: Construction of 1,Payazak, 2.Sharak, 3.Khairtot, and 4. Mula Hanifiya Check Dams, located in Shawalikot district of Kandahar province. | Watershed Management | Awarded | Awarded | No |  |  | Kandahar | Shawalikot | Awarded | 2026-08-27 | 2026-02-26 | Afghan Laser Engineering and Construction Company (ALCC) | 057/2026 | 3.WSM awarded contracts
AF2-WSM-24 | Package #24-AF2 WSM: Construction of 5 Check dams 1. Kashata Tangi, 2. Forodi, 3. Valary in Nawzad district, 4.Band Khawanin, and 5.Tykhoghi in Washer district of Helmand province. | Watershed Management | Not awarded | Under Design | No |  |  | Helmand | Washer, Nawzad | Under Design | 2026-12-03 | 2027-06-01 |  |  | 4.WSM remaining contracts
AF2-WSM-25 | Package #25-AF2 WSM: Construction of Qali Gaz, Ghobana, and Nawi Kach Check dams, located in Mizana district of Zabul province. | Watershed Management | Not awarded | PR to be Raised | No |  |  | Zabul | Mizana | PR to be Raised | 2026-11-25 | 2027-06-23 |  |  | 4.WSM remaining contracts
AF2-WSM-26 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | Watershed Management | Awarded | Awarded | Yes |  |  | Badakhshan | Teshkan, Darayim, Arghanj Khwah | Under Construction, Awarded, Completed / Handover | 2026-04-09 | 2026-11-08 | Faiz Qurbani Construction Company (FQCC) | 027/2026 | 3.WSM awarded contracts
AF2-WSM-27 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | Watershed Management | Awarded | Awarded | Yes |  |  | Takhar | Namak Ab, Hazar Sumoch, Khwaja Ghar, Khwaja Bahawuddin, Yangi Qala | Awarded, Completed / Handover, Under Construction | 2026-05-21 | 2026-11-20 | Shafiqullah Wahidi Construction Company (SWCC) | 037/2026 | 3.WSM awarded contracts
AF2-WSM-28 | Package #28-AF2 WSM: Construction of 2 Check dams of 1. Chatqa Sai in Dahna-e-Ghori and 2.Tahiryan in Baghlan Markazi districts of Baghlan province. | Watershed Management | Awarded | Under Construction | No |  |  | Baghlan | Dahna-e-Ghori, Baghlan Markazi | Under Construction | 2026-08-08 | 2026-12-07 | Arman Sharq Construction Company ASCC) | 054/2026 | 3.WSM awarded contracts
AF2-WSM-29 | Package # 29-AF2 WSM: Construction 1. Alburs and 2. Marmul Check dams, located in Marmul and Alburs districts of Balkh province | Watershed Management | Awarded | Under Construction | Yes |  |  | Balkh | Alburz, Marmul | Completed / Handover, Under Construction | 2026-05-12 | 2026-10-11 | Omar Mortaza Construction & Road Building JV Karwan Seraji Construction and Road Building Company (OMCC&KSCC) | 034/2026 | 3.WSM awarded contracts
AF2-WSM-30 | Package #30-AF2 WSM: Construction of 5 Check Damas of A. Majar site # 1 and site # 2; B.Elyasgar site # 3, site 4 and site # 5, located in Aljahad district of Sar-e-Pul province. | Watershed Management | Awarded | Under Construction | No |  |  | Sar-e-Pul | Aljahad | Under Construction | 2026-07-23 | 2026-11-22 | Waheed Wahaj Construction Company (WWCC) | 050/2026 | 3.WSM awarded contracts
AF2-WSM-31 | Package # 31-AF2 WSM: Construction of 1. Khaibar and 2. Chelgazi Check dams, located in Khaibar and Chelgazi districts of Faryab province. | Watershed Management | Awarded | Completed / Handover | No |  |  | Faryab | Chelgazi, Khaibar | Completed / Handover | 2026-05-07 | 2026-09-06 | Malik Hajdar Construction and Road Company (MHCC) | 033/2026 | 3.WSM awarded contracts
AF2-WSM-32 | Package #32-AF2 WSM: Construction of Tai Khunak 4 Check dams of A. Khoja Momin site # 1 and site # 2, B. Sari Shor site # 3 and site #4, located in Aybak district of Samangan province. | Watershed Management | Awarded | Under Construction | No |  |  | Samangan | Aybak | Under Construction | 2026-07-22 | 2026-11-21 | Mudeser Bigmurad Construction Company (MBCC) | 045/2026 | 3.WSM awarded contracts
AF2-WSM-33 | Package #33-AF2 WSM: Construction of 2 Check dams of Ala Taba-1 and Ala Taba-2 in Ablurz district of Balkh province. | Watershed Management | Not awarded | PR to be Raised | No |  |  | Balkh | Alburz | PR to be Raised | 2026-11-25 | 2027-05-24 |  |  | 4.WSM remaining contracts
AF2-WSM-34 | Package #34-AF2 WSM: Construction of two Check dams, 1.Tawqus Sangaw and 2. Khalkoma in Kalbad and Ali Abad district of Kunduz province. | Watershed Management | Not awarded | ITB Launched | No |  |  | Kunduz | Ali Abad, Kalbad | ITB Launched | 2026-10-31 | 2027-04-29 |  |  | 4.WSM remaining contracts

## 10_By_Contractor
Contracts by contractor — one row per company. Count unique Package IDs / contract numbers, not tracker rows.
Example: Zahid Saeed Engineering and Construction Company (ZSCC) is awarded one contract (Package #10-AF2 IS, contract 057/2025) covering four canals in Wardak. On 01_Scheme_Tracker the name appears four times because each canal is a sub-project. Filter this sheet or 03_Package_Summary by Contractor Name to list a company's contracts.
Contractor Name | Awarded contracts | Awarded sub-projects | Total cost (USD) | Package IDs | Contract number(s) | Package / Contract Name | Major intervention | Provinces | Districts
Faiz Qurbani Construction Company (FQCC) | 1 |  |  | AF2-WSM-26 | 027/2026 | Package # 26 – AF2 WSM: Construction of 6 Check Dams in 6 sites of A. Yawol Ha site # 1 and # 2 in Teshkan District, B. Sewak Dara site # 3, Golaki site # 4 in Darayim District, C. Khanaqa site # 5, and Sum Dara site # 6 in Arghanj Khwah District of Badakhshan Province | Watershed Management | Badakhshan | Teshkan, Darayim, Arghanj Khwah
Shafiqullah Wahidi Construction Company (SWCC) | 1 |  |  | AF2-WSM-27 | 037/2026 | Package #27-AF2 WSM: Construction of 5 Check Dams in 5 district sites of 1. Sholish Darra in Namak Ab, 2.Gaji Darra in Hazar Sumoch, 3.Silaba in Khwaja Ghar, 4.Shoor Toghai in Khwaja Bahawudd in and 5.Khalyazi in Yangi Qala districts of Takhar province. | Watershed Management | Takhar | Namak Ab, Hazar Sumoch, Khwaja Ghar, Khwaja Bahawuddin, Yangi Qala
Afghan Laser Engineering and Construction Company (ALCC) | 1 |  |  | AF2-WSM-23 | 057/2026 | Package #23-AF2 WSM: Construction of 1,Payazak, 2.Sharak, 3.Khairtot, and 4. Mula Hanifiya Check Dams, located in Shawalikot district of Kandahar province. | Watershed Management | Kandahar | Shawalikot
Bakhter Pairoz Construction Company (BPCC) | 1 |  |  | AF2-WSM-21 | 031/2026 | Package #21-AF2 WSM: Construction of 4 Check Dams 1.Choghazey and 2.Sardarkey in Arghistan, 3. Loy Laher in Spin Boldak and 4.Ab Samad Aka in Takhta Pull districts of Kandahar province. | Watershed Management | Kandahar | Takhta Pul, Arghistan, Spin Boldak
Estehkam Baba Construction and Road Construction Company (EBCC) | 1 |  |  | AF2-WSM-13 | 051/2026 | Package #13-AF2 WSM: Construction of 4 Check Dams in 4 district sites of 1.Kata Khana in Yakawlang , 2. Nawora in Panjab, 3.Nahorak in Waras, and 4.Bayani in Sayghan districts of Bamyan province | Watershed Management | Bamyan | Yakawalang, Panjab, Waras, Sayghan
Khaliqi Building & Road Construction Company (KBRCC) | 1 |  |  | AF2-WSM-05 | 040/2026 | Package #5-AF2 WSM/Part-2: Construction of 4 Check dams of 1.Farman Khil and 2.Kharoti in Qarghaee district of Laghman province; 3. Lokhy Solozi and 4. Lala Kali in Chaparhar districts of Nangarhar province. | Watershed Management | Laghman, Nangarhar | Qarghaee, Chaparhar
Sayed Abad Construction Company (SACC) | 1 |  |  | AF2-WSM-09 | 021/2026 | Package #9-AF2 WSM: Construction of 1.Aka Khil Check dam and 2. Sra Qala Check dam in Sayed district, 3.Khar Check dam and 4.Mardala Check dam, located in Jaghatu districts of Wardak province. | Watershed Management | Maidan Wardak | Sayed Abad, Jaghatu
Zahid Saeed Engineering and Construction Company (ZSCC) | 1 |  |  | AF2-IS-10 | 057/2025 | Package #10-AF2 IS: Rehabilitation of 1.Baraki canal, 2. Darbal canal, 3. Nawikhar canal and 4. Mangali canal irrigation schemes, located in Sayed Abad, Chak and Jaghato districts of Wardak province. | Irrigation Scheme | Wardak | Sayed Abad, Chak, Jaghato
Afghan Aakam Construction and Road Company. JV with D- Amini Mashwani Construction Company (AACC) | 1 |  |  | AF2-WSM-03 | 006/2026 | Package #3 -AF2 WSM: Construction of Koklam three Check Dams (# 1, # 2 and # 3 ) in Kushk-e-Kohna District of Herat Province | Watershed Management | Herat | Koshk-e-Kohna
Afghan Eithad construction and Road Building company (AECC) | 1 |  |  | AF2-IS-31 | 009/2026 | Package #31-AF2 IS: Rehabilitation of 1. Shahidan &Dasht-e Lajam Canal schems in Tala wa barfak district, 2.Sardar Ha canal scheme in Deh Salah district, and 3. Kambilan cluster canal schemes in Fring districts of Baghlan province. | Irrigation Scheme | Baghlan | Fring, Deh Salah, Tala wa barfak
ALTIN CONSTRUCTION AND ROAD BUILDING COMPANY (ACC) | 1 |  |  | AF2-WSM-08 | 005/2026 | Package #8-AF2 WSM: Construction of 1.Ghazgai Check dam in Khake Jabar districts, 2.Toop Dara Check dam and 3.Toot Dara Check dam in Center/ 13th City district Kabul province. | Watershed Management | Kabul | Center, Khake Jabar
Arman Millad Construction Company (AMCC) | 1 |  |  | AF2-IS-02 | 046/2026 | Package # 2-AF2 IS: Rehabilitation of irrigation schemes of 1.Ali Mansoor Canal in Karukh district, 2.Joy Sork and 3.Sar Kari canals in Farsi districts of Herat province. | Irrigation Scheme | Herat | Karukh, Farsi
Bahartamadun Construction Company (BCC) | 1 |  |  | AF2-WSM-15 | 065/2026 | Package #15-AF2 WSM: Construction of 3 Check dams of 1. Sangmom, 2. Shilan Korga, and 3.Khulbar in Nili, Ashtarlay, and Sang Takhta districts of Daykundi province. | Watershed Management | Daykundi | Sang Takht wa Bandar, Nili, Ashtarlay
Da Maidan Zawahnono Construction Company (DMZCC) | 1 |  |  | AF2-WSM-14 | 025/2026 | Package #14-AF2 WSM: Construction of 1.Shahristan Check dama in Shahristan district, 2.Miramor Check dam in Miramor district, and 3.Khidir Check dams in Khidir districts of Daykundi province. | Watershed Management | Daykundi | Shahristan, Miramor, Khidir
Green Bentley construction Company (GBCC) | 1 |  |  | AF2-WSM-07 | 064/2026 | Package #7-AF2 WSM: Construction of 3 Check dams of 1.Dargrak, 2. Migano, and 3.Lachagali the Sawkai, Khas Kunar and Narang districts of Kunar province. | Watershed Management | Kunar | Sawkai, Narang, Khas Kunar
Hemat Ghorzang Construction & Logistic Service Company (HGCC) | 1 |  |  | AF2-WSM-11 | 043/2026 | Package #11-AF2 WSM: Construction of 3 Check dams 1.Wolangak in Shikh Ali, 2.Sanzalai, and 3.Sharkai Olia in Koh-e-Safi district of Parwan province. | Watershed Management | Parwan | Koh-e-Safi, Shikh Ali
Kapisa Kohna Dah Construction Company (KKCC) | 1 |  |  | AF2-WSM-10 | 020/2026 | Package #10-AF2 WSM: Construction of Loy Shenkai Check dams # 1 and # 2 in Tagab district, and Shahr-e-Naw Check dam # 3 located in Nijrab districts of Kapisa province. | Watershed Management | Kapisa | Tagab, Nijrab
Naeemi Safi Construction & Construction Material Company (NSCC) | 1 |  |  | AF2-WSM-06 | 065/2026 | Package #6-AF2 WSM: Construction of Jarobi Tangi, Chaghari and Adore check dams, located in Shirzad, Rodat, and Khogyani, districts of Nangarhar province. | Watershed Management | Nangarhar | Sherzad, Rodat, Khogyani
Shams Afghan Vision Construction and Logistic Services (SAVCC) | 1 |  |  | AF2-WSM-02 | 014/2026 | Package #2 -AF2 WSM: Construction of 1. Dareh Shah Toot-1, 2. Dareh ShahToot-2, and 3. Jar Sono check dams in Obe District of Herat Province | Watershed Management | Herat | Obe
Shirali Khan Barakatzai Construction Company (SBCC) | 1 |  |  | AF2-IS-06 | 054/2025 | Package #6-AF2 IS: Rehabilitation of Kushtal Canal, Checknawar canal, and Patikhirrki canal irrigation schemes, located in Lalpora ,Spinghar and Khogyani districts of Nangarhar province. | Irrigation Scheme | Nangarhar | Spinghar, Lalpora, Khogyani
AFGHAN LUCKY CONSTRUCTION COMPANY (ALCC) | 1 |  |  | AF2-IS-33 | 003/2026 | Package #33-AF2 IS: Rehabilitation of Chela Mazar canal and Kushkak canal irrigation schemes, located in Dara-e- Suf-e-Bala and Dara-e-Suf-e-Payeen districts of Samangan province. | Irrigation Scheme | Samangan | Dara-e- Suf-e-Payeen, Dara-e- Suf-e-Bala
Arman Sharq Construction Company ASCC) | 1 |  |  | AF2-WSM-28 | 054/2026 | Package #28-AF2 WSM: Construction of 2 Check dams of 1. Chatqa Sai in Dahna-e-Ghori and 2.Tahiryan in Baghlan Markazi districts of Baghlan province. | Watershed Management | Baghlan | Dahna-e-Ghori, Baghlan Markazi
Awrish builder construction company (ABCC) | 1 |  |  | AF2-IS-08 | 055/2026 | Package #8-AF2 IS: Rehabilitation of Khas Kunar Lower canal and Bahrabad canal irrigation schemes, located in Khas Kunar district of Kunar and Behsood district of Nangarhar provinces. | Irrigation Scheme | Nangarhar, Kunar | Behsood, Khas Kunar
Farhad Matoonyar Construction Company (FMCC) | 1 |  |  | AF2-IS-21 | 038/2026 | Package # 21-AF2 IS: Rehabilitation of Markazi Ziruk and Mulakh canal irrigation schemes, located in Ziruk and Yousaf Khil districts of Pakteka province. | Irrigation Scheme | Pakteka | Ziruk, Yousaf Khil
Malik Hajdar Construction and Road Company (MHCC) | 1 |  |  | AF2-WSM-31 | 033/2026 | Package # 31-AF2 WSM: Construction of 1. Khaibar and 2. Chelgazi Check dams, located in Khaibar and Chelgazi districts of Faryab province. | Watershed Management | Faryab | Chelgazi, Khaibar
Mudeser Bigmurad Construction Company (MBCC) | 1 |  |  | AF2-WSM-32 | 045/2026 | Package #32-AF2 WSM: Construction of Tai Khunak 4 Check dams of A. Khoja Momin site # 1 and site # 2, B. Sari Shor site # 3 and site #4, located in Aybak district of Samangan province. | Watershed Management | Samangan | Aybak
Nomae Shahr Construction Company (NSCC) | 1 |  |  | AF2-IS-14 | 002/2026 | Package #14-AF2 IS: Rehabilitation of Zard Sang and Topchi Cluster Canal Irrigation scheme, located in Center district of Bamyan province. | Irrigation Scheme | Bamyan | Center
Omar Mortaza Construction & Road Building JV Karwan Seraji Construction and Road Building Company (OMCC&KSCC) | 1 |  |  | AF2-WSM-29 | 034/2026 | Package # 29-AF2 WSM: Construction 1. Alburs and 2. Marmul Check dams, located in Marmul and Alburs districts of Balkh province | Watershed Management | Balkh | Alburz, Marmul
SHAMAL KARDAN ROAD CONSTRUCTION AND LOGISTIC SERVICES COMPANY LTD (SKRCC) | 1 |  |  | AF2-IS-28 | 067/2025 | Package # 28 – AF2 IS: Rehabilitation of Irrigation Schemes of 1. Abil Aroq (Qanjogha), 2. Shaitan Aroq Cluster Canals in Khwaja Ghar District and 3. Kalta Aroq, 4. Pacha Khail, and 5. Sayed Miran (Khar Kar) Cluster Canals in Eshkamish District of Takhar Province | Irrigation Scheme | Takhar | Khwaja Ghar, Eshkamish
Trust Grow Construction and Engineering Company (TGCC) | 1 |  |  | AF2-IS-32 | 075/2025 | Package #32-AF2 IS: Rehabilitation of Abdul Baqi canal and Mulla Oma canal irrigation schemes, located in Chemtal districts of Balkh province. | Irrigation Scheme | Balkh | Chemtal
Unique Wahaj Construction Company (UWCC) | 1 |  |  | AF2-IS-19 | 074/2026 | Package #19-AF2 IS: Rehabilitation of Khwaja Angor canal and Qalai Wazir canal irrigation schemes located in Kharwar and Pol-i-Alam districts of Logar province. | Irrigation Scheme | Logar | Kharwar, Pol-i-Alam
Waheed Wahaj Construction Company (WWCC) | 1 |  |  | AF2-WSM-30 | 050/2026 | Package #30-AF2 WSM: Construction of 5 Check Damas of A. Majar site # 1 and site # 2; B.Elyasgar site # 3, site 4 and site # 5, located in Aljahad district of Sar-e-Pul province. | Watershed Management | Sar-e-Pul | Aljahad
Wasif Construction Company | 1 |  |  | AF2-IS-25 | 012/2026 | Package #25-AF2 IS: Rehabilitation of Urdo Kas canal and Sarkay Lazhey canal irrigation schemes, located in Sha Wali Kot and Boldak districts of Kandahar province. | Irrigation Scheme | Kandahar | Boldak, Sha Wali Kot
Afghan Aakam Construction and Road Company C. JV with D-Amini Mashwani Construction Road Juroni and Construction Materials Production Company (AACRC&JV DAMCC) | 1 |  |  | AF2-IS-01 | 050/2025 | Package #1-AF2 IS: Rehabilitation of Joy Bazar irrigation scheme located in Obe district of Herat province. | Irrigation Scheme | Herat | Obeh
Estehkam Baba Construction Company JV Tamadon Bamik Construction Company (EBCC) | 1 |  |  | AF2-IS-16 | 007/2026 | Package #16-AF2 IS: Rehabilitation of Pato (Paye Raqul, Sangchal Takhomak and Kadalak) Cluster canal irrigation scheme in Pato district of Daykundi province | Irrigation Scheme | Daykundi | Pato
Hemat safi construction company (HSCC) | 1 |  |  | AF2-WSM-18 | 047/2026 | Package #18-AF2 WSM: Construction of Muqarab Check dams, located in Gelan districts of Ghazni province. | Watershed Management | Ghazni | Gelan
Mahmood Raqi Nawin Construction & Road Building Company (MRCC) | 1 |  |  | AF2-IS-20 | 053/2025 | Package #20-AF2 IS: Rehabilitation of Welgai irrigation system, located in Matoon district of Khost province. | Irrigation Scheme | Khost | Matoon
New Safi Zada Construction & Road Building Company JV with Elyas Aryoubi Constructin Road building and Logistic Company (NSZ&EACC) | 1 |  |  | AF2-IS-26 | 019/2026 | Package #26-AF2 IS: Rehabilitation of Sarwan Qala canal irrigation schemes, located in Sangin district of Kandahar province. | Irrigation Scheme | Helmand | Sangin
Sakht shamal construction and road building company (SSCC) | 1 |  |  | AF2-IS-35 | 016/2026 | Package # 35-AF2 IS: Rehabilitation of Bahr-e Ameq canal irrigation scheme, located in Sozma Qala districts of Sar-e-Pul province. | Irrigation Scheme | Sar-e- Pul | Sozma Qala
Sayed Shirazi Construction and Road Building Company (SCRC) | 1 |  |  | AF2-WSM-16 | 030/2026 | Package #16-AF2 WSM: Construction of Panami Check dams, located in Mohammad Agha district of Logar province. | Watershed Management | Logar | M.Agha
Seddiq Amini Construction and Logistic Services (SACC) | 1 |  |  | AF2-IS-11 | 056/2025 | Package #11-AF2 IS: Rehabilitation of Musahi Sufla canal irrigation schemes, located in Musahi districts of Kabul province. | Irrigation Scheme | Kabul | Musahi

## 11_Package_Status
Package status — unique contracts by step, with the share of each major intervention
Each package is counted once. Read a status row to see how it splits across Irrigation Scheme, Watershed Management, Drip Irrigation, LLL, and Agroforestry (count and share of that status). Completed only when every site of the package is completed. Filter Package status + Major intervention on 03_Package_Summary to list the contracts.
Unique packages |  | Awarded packages |  | Not awarded packages |  | Mixed-site packages |  | Irrigation Scheme | Watershed Management | Drip Irrigation | Laser Land Leveler (LLL) | Agroforestry saplings / seeds
Packages by major intervention — Awarded vs Not awarded (unique contracts)
Major intervention | Packages | Awarded | Not awarded | Share awarded | Share not awarded | Sub-projects (rows)
Irrigation Scheme
Watershed Management
Drip Irrigation
Laser Land Leveler (LLL)
Agroforestry saplings / seeds
Total
Packages by pipeline status — how each step is shared across major interventions
Status | Packages | Share of all packages | Sub-projects (rows) | Awarded packages | Not awarded packages | Irrigation Scheme | Share of this status | Watershed Management | Share of this status | Drip Irrigation | Share of this status | Laser Land Leveler (LLL) | Share of this status | Agroforestry saplings / seeds | Share of this status
Under Design
Under Review of WRI
Under LTO Review
PR to be Raised
ITB Launched
Retendered (Re-ITB)
Under Technical Evaluation
Under Awarding
Awarded
Under Construction
Completed / Handover
Not started
Cancelled
Total
Share of each major intervention across statuses (read down a column)
Status | Irrigation Scheme | Watershed Management | Drip Irrigation | Laser Land Leveler (LLL) | Agroforestry saplings / seeds
How to read: on the Awarded row, Irrigation Scheme / Watershed Management / … counts are unique packages, and Share of this status is that major’s slice of Awarded (they add to 100%). The lower table reads down a major: of all Irrigation Scheme packages, what share is Under Construction vs Awarded. Sub-projects is the old row count — do not use it for package totals. Filter 03_Package_Summary by Package status and Major intervention to list the contracts.

## 04_Date_Rules
Date conditions — what each date means and how schedule health is calculated
All health colours use Excel TODAY(), so they move as the calendar moves. Type the day a step was reached — not a forecast — unless the column says expected / planned.
What you type in a Date: column
Working date = day the step started | In section 4 of 01_Scheme_Tracker, each 'Date: …' cell is the calendar day that step was reached (design started, WRI review started, ITB launched, contract signed, construction started, handover). Do not put the expected future date of a later step in that later column. Leave later dates blank until they happen. Current Status then becomes the latest dated step. If every Date: cell is empty, Current Status uses Reported Status. | Section 4
Awarded Date | This is a formula. It copies Date: Awarded. Type the signature / notice-of-award day in Date: Awarded, not in Awarded Date. | Section 2 copies section 4
Expected award date (Not awarded rows) | Forecast of when the contract should be awarded. This is the date schedule health watches for Not awarded packages. If TODAY() is after this date, the row is Behind — award date passed. If this date is within the next 30 days, the row is At risk — close to off track. | Section 2
Contract / expected end date | For Awarded rows this is the contractual completion date. For Not awarded rows it is the expected completion after award. Planned End Date uses this value when it is filled; otherwise it uses EDATE(Awarded Date, Contract Duration months). | Section 2
Days between steps | Days: A → B = Date of B minus the last previous filled date (a skipped step still measures from the last real date). Days in current status = TODAY() minus the latest filled Date:. This number changes every morning. Total days first → last = last filled Date: minus first filled Date:. Days over target = days in current status minus the target days on 06_Status_Pipeline. A negative day-count means a later step was dated earlier than a previous one — check the dates. | Sections 3 and 5
Schedule health — conditions that use those dates
Cancelled | If Reported Status or Current Status is Cancelled, health is Cancelled (grey). No date test is applied. | Grey
Completed — on track | If Current Status is Completed / Handover, or Actual completion date is filled, or Physical progress ≥ 100, health is Completed — on track (green). The planned end is not used once the work is finished. | Green
Not awarded — Behind — award date passed | Awarded / Not awarded = Not awarded, and Expected award date is filled, and TODAY() > Expected award date. The package should already have been awarded. | Red
Not awarded — At risk — close to off track | Awarded / Not awarded = Not awarded, Expected award date is filled, and that date is today or within the next 30 days. Procurement needs attention now. | Amber
Not awarded — On track | Awarded / Not awarded = Not awarded, Expected award date is filled, and more than 30 days remain until that date. | Green
Not awarded — no expected award date | If Expected award date is blank, the same three tests (behind / at risk / on track) use Planned End Date (or Contract / expected end). If that is also blank, health is No planned date. | Grey / date-based
Awarded — Behind — past end date | Awarded / Not awarded = Awarded, Planned End Date is filled, TODAY() is after that date, and physical progress is blank or below 100. The contract period has expired and the work is not finished. | Red
Awarded — Behind — progress lag | Awarded, both Awarded Date and Planned End Date are filled, progress is below 100, and (elapsed days ÷ contract days × 100) − physical progress > 15. Example: half the contract time has passed (50% elapsed) but progress is 20% → lag of 30 points → Behind. | Red
Awarded — At risk — close to off track | Awarded, Planned End Date is today or within the next 30 days, and progress is blank or below 90. The end date is close and the work is not nearly finished. | Amber
Awarded — On track | Awarded, Planned End Date is more than 30 days away, and there is no progress lag above 15 points (or the work is already complete — see Completed above). | Green
Days vs planned date | Not awarded: Expected award date − TODAY() (or Planned End Date − TODAY() if expected award is blank). Awarded: Planned End Date − TODAY(). Positive = days remaining (green if > 30, amber if 0–30). Negative = days overdue (red). Blank when the row is Completed or Cancelled. | Section 3
How this applies to AF-2 right now
Awarded packages from the master file | Date: Awarded is filled from the signed-date column. Awarded Date copies it. Contract / expected end is the master-file end date. Planned End Date therefore equals that end date. If remarks started with 'Completed in …' or progress is 100, Reported Status is Completed / Handover. Otherwise progress > 0 → Under Construction; progress 0 → Awarded. Phrases such as 'will be completed by …' do not mark the scheme complete. | Master import
Not awarded packages from the master file | Expected award date and expected end come from the remaining-contract sheets. There is usually no Date: Awarded yet, so Current Status follows Reported Status (Under Design, WRI Review, LTO, PR, ITB, Re-ITB, Technical Evaluation, Awarding). Health watches the expected award date against TODAY(). | Master import
Thresholds you can change | Close-to-off-track window = 30 days. Progress-lag trigger = 15 percentage points. Days in current status turns red after 30 days. Edit NEAR_OFFTRACK_DAYS, PROGRESS_LAG_PCT, and STUCK_THRESHOLD_DAYS in tracker_config.py and regenerate. | tracker_config.py

## 05_Example_Filled
EXAMPLE ONLY — two worked schemes so you can see day counts. Do not use for reporting.
1. Scheme identity | [15 empty] | 2. Contract and physical progress | [11 empty] | 3. Live status and schedule health (calculated) | [5 empty] | 4. Status dates — enter the date each step was reached | [13 empty] | 5. Days between steps (calculated)
SN | Package ID | Package / Contract Name | Sub-project in package | Scheme ID | Sub-project / scheme name | Major intervention | Intervention sub-type | Project Name | Region | Province | District | Village | Donor | Awarded / Not awarded | Source sheet | Contractor Name | Contract Number | Contract Cost (USD) | Awarded Date | Expected award date | Contract Duration (months) | Contract / expected end date | Planned End Date | Actual completion date | Physical Works Progress % | Reported Status | Remarks | Current Status (auto) | Days in current status | Total days first → last step | Days over target this step | Schedule health | Days vs planned date | IF('06_Status_Pipeline'!B3="","(spare slot 1)","Date: "&'06_Status_Pipeline'!B3) | IF('06_Status_Pipeline'!B4="","(spare slot 2)","Date: "&'06_Status_Pipeline'!B4) | IF('06_Status_Pipeline'!B5="","(spare slot 3)","Date: "&'06_Status_Pipeline'!B5) | IF('06_Status_Pipeline'!B6="","(spare slot 4)","Date: "&'06_Status_Pipeline'!B6) | IF('06_Status_Pipeline'!B7="","(spare slot 5)","Date: "&'06_Status_Pipeline'!B7) | IF('06_Status_Pipeline'!B8="","(spare slot 6)","Date: "&'06_Status_Pipeline'!B8) | IF('06_Status_Pipeline'!B9="","(spare slot 7)","Date: "&'06_Status_Pipeline'!B9) | IF('06_Status_Pipeline'!B10="","(spare slot 8)","Date: "&'06_Status_Pipeline'!B10) | IF('06_Status_Pipeline'!B11="","(spare slot 9)","Date: "&'06_Status_Pipeline'!B11) | IF('06_Status_Pipeline'!B12="","(spare slot 10)","Date: "&'06_Status_Pipeline'!B12) | IF('06_Status_Pipeline'!B13="","(spare slot 11)","Date: "&'06_Status_Pipeline'!B13) | IF('06_Status_Pipeline'!B14="","(spare slot 12)","Date: "&'06_Status_Pipeline'!B14) | IF('06_Status_Pipeline'!B15="","(spare slot 13)","Date: "&'06_Status_Pipeline'!B15) | IF('06_Status_Pipeline'!B16="","(spare slot 14)","Date: "&'06_Status_Pipeline'!B16) | IF(AND('06_Status_Pipeline'!B3="",'06_Status_Pipeline'!B4=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B3="","(prev)",'06_Status_Pipeline'!B3)&" → "&IF('06_Status_Pipeline'!B4="","(next)",'06_Status_Pipeline'!B4)) | IF(AND('06_Status_Pipeline'!B4="",'06_Status_Pipeline'!B5=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B4="","(prev)",'06_Status_Pipeline'!B4)&" → "&IF('06_Status_Pipeline'!B5="","(next)",'06_Status_Pipeline'!B5)) | IF(AND('06_Status_Pipeline'!B5="",'06_Status_Pipeline'!B6=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B5="","(prev)",'06_Status_Pipeline'!B5)&" → "&IF('06_Status_Pipeline'!B6="","(next)",'06_Status_Pipeline'!B6)) | IF(AND('06_Status_Pipeline'!B6="",'06_Status_Pipeline'!B7=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B6="","(prev)",'06_Status_Pipeline'!B6)&" → "&IF('06_Status_Pipeline'!B7="","(next)",'06_Status_Pipeline'!B7)) | IF(AND('06_Status_Pipeline'!B7="",'06_Status_Pipeline'!B8=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B7="","(prev)",'06_Status_Pipeline'!B7)&" → "&IF('06_Status_Pipeline'!B8="","(next)",'06_Status_Pipeline'!B8)) | IF(AND('06_Status_Pipeline'!B8="",'06_Status_Pipeline'!B9=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B8="","(prev)",'06_Status_Pipeline'!B8)&" → "&IF('06_Status_Pipeline'!B9="","(next)",'06_Status_Pipeline'!B9)) | IF(AND('06_Status_Pipeline'!B9="",'06_Status_Pipeline'!B10=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B9="","(prev)",'06_Status_Pipeline'!B9)&" → "&IF('06_Status_Pipeline'!B10="","(next)",'06_Status_Pipeline'!B10)) | IF(AND('06_Status_Pipeline'!B10="",'06_Status_Pipeline'!B11=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B10="","(prev)",'06_Status_Pipeline'!B10)&" → "&IF('06_Status_Pipeline'!B11="","(next)",'06_Status_Pipeline'!B11)) | IF(AND('06_Status_Pipeline'!B11="",'06_Status_Pipeline'!B12=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B11="","(prev)",'06_Status_Pipeline'!B11)&" → "&IF('06_Status_Pipeline'!B12="","(next)",'06_Status_Pipeline'!B12)) | IF(AND('06_Status_Pipeline'!B12="",'06_Status_Pipeline'!B13=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B12="","(prev)",'06_Status_Pipeline'!B12)&" → "&IF('06_Status_Pipeline'!B13="","(next)",'06_Status_Pipeline'!B13)) | IF(AND('06_Status_Pipeline'!B13="",'06_Status_Pipeline'!B14=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B13="","(prev)",'06_Status_Pipeline'!B13)&" → "&IF('06_Status_Pipeline'!B14="","(next)",'06_Status_Pipeline'!B14)) | IF(AND('06_Status_Pipeline'!B14="",'06_Status_Pipeline'!B15=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B14="","(prev)",'06_Status_Pipeline'!B14)&" → "&IF('06_Status_Pipeline'!B15="","(next)",'06_Status_Pipeline'!B15)) | IF(AND('06_Status_Pipeline'!B15="",'06_Status_Pipeline'!B16=""),"(spare)","Days: "&IF('06_Status_Pipeline'!B15="","(prev)",'06_Status_Pipeline'!B15)&" → "&IF('06_Status_Pipeline'!B16="","(next)",'06_Status_Pipeline'!B16)) | _ProvinceList | _DistrictList
IF(F4="","",ROW()-3) | DEMO-A | DEMO Package A — full pipeline (delete from reports) | 1 of 1 | DEMO-01 | Demo Scheme: completed handover | Watershed Management | Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Badghis | Qadis | Demo Village A | World Bank (WBK/AF-2) | Awarded |  | Demo Contractor Ltd | DEMO-CNT-001 | 120000 | IF(AQ4="","",AQ4) |  | 5 |  | IF(W4<>"",W4,IF(OR(T4="",V4=""),"",EDATE(T4,V4))) |  | 100 | Completed / Handover | EXAMPLE ONLY — shows days between every step. | IF(F4="","",IF(COUNT(AI4:AV4)=0,IF(AA4="","Not started",AA4),SUBSTITUTE(LOOKUP(2,1/(AI4:AV4<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F4="",COUNT(AI4:AV4)=0),"",TODAY()-LOOKUP(2,1/(AI4:AV4<>""),AI4:AV4)) | IF(OR(F4="",COUNT(AI4:AV4)<2),"",LOOKUP(2,1/(AI4:AV4<>""),AI4:AV4)-MIN(AI4:AV4)) | IF(OR(AD4="",AC4="Not started",AC4=""),"",IFERROR(AD4-IF(VLOOKUP(AC4,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC4,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F4="","",IF(OR(AA4="Cancelled",AC4="Cancelled"),"Cancelled",IF(OR(AC4="Completed / Handover",Y4<>"",Z4>=100),"Completed — on track",IF(O4="Not awarded",IF(U4="",IF(X4="","No planned date",IF(TODAY()>X4,"Behind — past planned date",IF(X4-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U4,"Behind — award date passed",IF(U4-TODAY()<=30,"At risk — close to off track","On track"))),IF(X4="","No planned date",IF(AND(TODAY()>X4,OR(Z4="",Z4<100)),"Behind — past end date",IF(AND(T4<>"",X4<>"",Z4<>"",(Z4<100),((TODAY()-T4)/MAX(X4-T4,1)*100)-Z4>15),"Behind — progress lag",IF(AND(X4-TODAY()<=30,X4-TODAY()>=0,OR(Z4="",Z4<90)),"At risk — close to off track","On track")))))))) | IF(OR(F4="",AC4="Completed / Handover",AC4="Cancelled"),"",IF(O4="Not awarded",IF(U4<>"",U4-TODAY(),IF(X4="","",X4-TODAY())),IF(X4="","",X4-TODAY()))) | 2025-01-10 | 2025-02-04 | 2025-02-18 |  | 2025-03-02 |  | 2025-03-24 | 2025-04-08 | 2025-04-22 | 2025-05-10 | 2025-09-30 |  |  |  | IF(OR(F4="",AJ4=""),"",IF(COUNT(AI4:AI4)=0,"",AJ4-LOOKUP(2,1/(AI4:AI4<>""),AI4:AI4))) | IF(OR(F4="",AK4=""),"",IF(COUNT(AI4:AJ4)=0,"",AK4-LOOKUP(2,1/(AI4:AJ4<>""),AI4:AJ4))) | IF(OR(F4="",AL4=""),"",IF(COUNT(AI4:AK4)=0,"",AL4-LOOKUP(2,1/(AI4:AK4<>""),AI4:AK4))) | IF(OR(F4="",AM4=""),"",IF(COUNT(AI4:AL4)=0,"",AM4-LOOKUP(2,1/(AI4:AL4<>""),AI4:AL4))) | IF(OR(F4="",AN4=""),"",IF(COUNT(AI4:AM4)=0,"",AN4-LOOKUP(2,1/(AI4:AM4<>""),AI4:AM4))) | IF(OR(F4="",AO4=""),"",IF(COUNT(AI4:AN4)=0,"",AO4-LOOKUP(2,1/(AI4:AN4<>""),AI4:AN4))) | IF(OR(F4="",AP4=""),"",IF(COUNT(AI4:AO4)=0,"",AP4-LOOKUP(2,1/(AI4:AO4<>""),AI4:AO4))) | IF(OR(F4="",AQ4=""),"",IF(COUNT(AI4:AP4)=0,"",AQ4-LOOKUP(2,1/(AI4:AP4<>""),AI4:AP4))) | IF(OR(F4="",AR4=""),"",IF(COUNT(AI4:AQ4)=0,"",AR4-LOOKUP(2,1/(AI4:AQ4<>""),AI4:AQ4))) | IF(OR(F4="",AS4=""),"",IF(COUNT(AI4:AR4)=0,"",AS4-LOOKUP(2,1/(AI4:AR4<>""),AI4:AR4))) | IF(OR(F4="",AT4=""),"",IF(COUNT(AI4:AS4)=0,"",AT4-LOOKUP(2,1/(AI4:AS4<>""),AI4:AS4))) | IF(OR(F4="",AU4=""),"",IF(COUNT(AI4:AT4)=0,"",AU4-LOOKUP(2,1/(AI4:AT4<>""),AI4:AT4))) | IF(OR(F4="",AV4=""),"",IF(COUNT(AI4:AU4)=0,"",AV4-LOOKUP(2,1/(AI4:AU4<>""),AI4:AU4))) | IF(J4="","All_Provinces",IFERROR(VLOOKUP(J4,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K4="","All_Districts",IFERROR(VLOOKUP(K4,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F5="","",ROW()-3) | DEMO-B | DEMO Package B — mid pipeline (delete from reports) | 1 of 1 | DEMO-02 | Demo Scheme: currently under technical evaluation | Watershed Management | Boulder Check Dam | Emergency Food Security Project (EFSP) – WBK/AF-2 | East / Jalalabad | Kunar | Narang | Demo Village B | World Bank (WBK/AF-2) | Not awarded |  |  |  | 98000 | IF(AQ5="","",AQ5) |  |  |  | IF(W5<>"",W5,IF(OR(T5="",V5=""),"",EDATE(T5,V5))) |  |  | Under Technical Evaluation | EXAMPLE ONLY — later dates are blank; days in current step uses TODAY(). | IF(F5="","",IF(COUNT(AI5:AV5)=0,IF(AA5="","Not started",AA5),SUBSTITUTE(LOOKUP(2,1/(AI5:AV5<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F5="",COUNT(AI5:AV5)=0),"",TODAY()-LOOKUP(2,1/(AI5:AV5<>""),AI5:AV5)) | IF(OR(F5="",COUNT(AI5:AV5)<2),"",LOOKUP(2,1/(AI5:AV5<>""),AI5:AV5)-MIN(AI5:AV5)) | IF(OR(AD5="",AC5="Not started",AC5=""),"",IFERROR(AD5-IF(VLOOKUP(AC5,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC5,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F5="","",IF(OR(AA5="Cancelled",AC5="Cancelled"),"Cancelled",IF(OR(AC5="Completed / Handover",Y5<>"",Z5>=100),"Completed — on track",IF(O5="Not awarded",IF(U5="",IF(X5="","No planned date",IF(TODAY()>X5,"Behind — past planned date",IF(X5-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U5,"Behind — award date passed",IF(U5-TODAY()<=30,"At risk — close to off track","On track"))),IF(X5="","No planned date",IF(AND(TODAY()>X5,OR(Z5="",Z5<100)),"Behind — past end date",IF(AND(T5<>"",X5<>"",Z5<>"",(Z5<100),((TODAY()-T5)/MAX(X5-T5,1)*100)-Z5>15),"Behind — progress lag",IF(AND(X5-TODAY()<=30,X5-TODAY()>=0,OR(Z5="",Z5<90)),"At risk — close to off track","On track")))))))) | IF(OR(F5="",AC5="Completed / Handover",AC5="Cancelled"),"",IF(O5="Not awarded",IF(U5<>"",U5-TODAY(),IF(X5="","",X5-TODAY())),IF(X5="","",X5-TODAY()))) | 2025-06-01 | 2025-06-20 | 2025-07-05 |  | 2025-07-20 |  | 2025-08-15 | [7 empty] | IF(OR(F5="",AJ5=""),"",IF(COUNT(AI5:AI5)=0,"",AJ5-LOOKUP(2,1/(AI5:AI5<>""),AI5:AI5))) | IF(OR(F5="",AK5=""),"",IF(COUNT(AI5:AJ5)=0,"",AK5-LOOKUP(2,1/(AI5:AJ5<>""),AI5:AJ5))) | IF(OR(F5="",AL5=""),"",IF(COUNT(AI5:AK5)=0,"",AL5-LOOKUP(2,1/(AI5:AK5<>""),AI5:AK5))) | IF(OR(F5="",AM5=""),"",IF(COUNT(AI5:AL5)=0,"",AM5-LOOKUP(2,1/(AI5:AL5<>""),AI5:AL5))) | IF(OR(F5="",AN5=""),"",IF(COUNT(AI5:AM5)=0,"",AN5-LOOKUP(2,1/(AI5:AM5<>""),AI5:AM5))) | IF(OR(F5="",AO5=""),"",IF(COUNT(AI5:AN5)=0,"",AO5-LOOKUP(2,1/(AI5:AN5<>""),AI5:AN5))) | IF(OR(F5="",AP5=""),"",IF(COUNT(AI5:AO5)=0,"",AP5-LOOKUP(2,1/(AI5:AO5<>""),AI5:AO5))) | IF(OR(F5="",AQ5=""),"",IF(COUNT(AI5:AP5)=0,"",AQ5-LOOKUP(2,1/(AI5:AP5<>""),AI5:AP5))) | IF(OR(F5="",AR5=""),"",IF(COUNT(AI5:AQ5)=0,"",AR5-LOOKUP(2,1/(AI5:AQ5<>""),AI5:AQ5))) | IF(OR(F5="",AS5=""),"",IF(COUNT(AI5:AR5)=0,"",AS5-LOOKUP(2,1/(AI5:AR5<>""),AI5:AR5))) | IF(OR(F5="",AT5=""),"",IF(COUNT(AI5:AS5)=0,"",AT5-LOOKUP(2,1/(AI5:AS5<>""),AI5:AS5))) | IF(OR(F5="",AU5=""),"",IF(COUNT(AI5:AT5)=0,"",AU5-LOOKUP(2,1/(AI5:AT5<>""),AI5:AT5))) | IF(OR(F5="",AV5=""),"",IF(COUNT(AI5:AU5)=0,"",AV5-LOOKUP(2,1/(AI5:AU5<>""),AI5:AU5))) | IF(J5="","All_Provinces",IFERROR(VLOOKUP(J5,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K5="","All_Districts",IFERROR(VLOOKUP(K5,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F6="","",ROW()-3) | [18 empty] | IF(AQ6="","",AQ6) |  |  |  | IF(W6<>"",W6,IF(OR(T6="",V6=""),"",EDATE(T6,V6))) |  |  |  |  | IF(F6="","",IF(COUNT(AI6:AV6)=0,IF(AA6="","Not started",AA6),SUBSTITUTE(LOOKUP(2,1/(AI6:AV6<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F6="",COUNT(AI6:AV6)=0),"",TODAY()-LOOKUP(2,1/(AI6:AV6<>""),AI6:AV6)) | IF(OR(F6="",COUNT(AI6:AV6)<2),"",LOOKUP(2,1/(AI6:AV6<>""),AI6:AV6)-MIN(AI6:AV6)) | IF(OR(AD6="",AC6="Not started",AC6=""),"",IFERROR(AD6-IF(VLOOKUP(AC6,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC6,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F6="","",IF(OR(AA6="Cancelled",AC6="Cancelled"),"Cancelled",IF(OR(AC6="Completed / Handover",Y6<>"",Z6>=100),"Completed — on track",IF(O6="Not awarded",IF(U6="",IF(X6="","No planned date",IF(TODAY()>X6,"Behind — past planned date",IF(X6-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U6,"Behind — award date passed",IF(U6-TODAY()<=30,"At risk — close to off track","On track"))),IF(X6="","No planned date",IF(AND(TODAY()>X6,OR(Z6="",Z6<100)),"Behind — past end date",IF(AND(T6<>"",X6<>"",Z6<>"",(Z6<100),((TODAY()-T6)/MAX(X6-T6,1)*100)-Z6>15),"Behind — progress lag",IF(AND(X6-TODAY()<=30,X6-TODAY()>=0,OR(Z6="",Z6<90)),"At risk — close to off track","On track")))))))) | IF(OR(F6="",AC6="Completed / Handover",AC6="Cancelled"),"",IF(O6="Not awarded",IF(U6<>"",U6-TODAY(),IF(X6="","",X6-TODAY())),IF(X6="","",X6-TODAY()))) | [14 empty] | IF(OR(F6="",AJ6=""),"",IF(COUNT(AI6:AI6)=0,"",AJ6-LOOKUP(2,1/(AI6:AI6<>""),AI6:AI6))) | IF(OR(F6="",AK6=""),"",IF(COUNT(AI6:AJ6)=0,"",AK6-LOOKUP(2,1/(AI6:AJ6<>""),AI6:AJ6))) | IF(OR(F6="",AL6=""),"",IF(COUNT(AI6:AK6)=0,"",AL6-LOOKUP(2,1/(AI6:AK6<>""),AI6:AK6))) | IF(OR(F6="",AM6=""),"",IF(COUNT(AI6:AL6)=0,"",AM6-LOOKUP(2,1/(AI6:AL6<>""),AI6:AL6))) | IF(OR(F6="",AN6=""),"",IF(COUNT(AI6:AM6)=0,"",AN6-LOOKUP(2,1/(AI6:AM6<>""),AI6:AM6))) | IF(OR(F6="",AO6=""),"",IF(COUNT(AI6:AN6)=0,"",AO6-LOOKUP(2,1/(AI6:AN6<>""),AI6:AN6))) | IF(OR(F6="",AP6=""),"",IF(COUNT(AI6:AO6)=0,"",AP6-LOOKUP(2,1/(AI6:AO6<>""),AI6:AO6))) | IF(OR(F6="",AQ6=""),"",IF(COUNT(AI6:AP6)=0,"",AQ6-LOOKUP(2,1/(AI6:AP6<>""),AI6:AP6))) | IF(OR(F6="",AR6=""),"",IF(COUNT(AI6:AQ6)=0,"",AR6-LOOKUP(2,1/(AI6:AQ6<>""),AI6:AQ6))) | IF(OR(F6="",AS6=""),"",IF(COUNT(AI6:AR6)=0,"",AS6-LOOKUP(2,1/(AI6:AR6<>""),AI6:AR6))) | IF(OR(F6="",AT6=""),"",IF(COUNT(AI6:AS6)=0,"",AT6-LOOKUP(2,1/(AI6:AS6<>""),AI6:AS6))) | IF(OR(F6="",AU6=""),"",IF(COUNT(AI6:AT6)=0,"",AU6-LOOKUP(2,1/(AI6:AT6<>""),AI6:AT6))) | IF(OR(F6="",AV6=""),"",IF(COUNT(AI6:AU6)=0,"",AV6-LOOKUP(2,1/(AI6:AU6<>""),AI6:AU6))) | IF(J6="","All_Provinces",IFERROR(VLOOKUP(J6,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K6="","All_Districts",IFERROR(VLOOKUP(K6,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F7="","",ROW()-3) | [18 empty] | IF(AQ7="","",AQ7) |  |  |  | IF(W7<>"",W7,IF(OR(T7="",V7=""),"",EDATE(T7,V7))) |  |  |  |  | IF(F7="","",IF(COUNT(AI7:AV7)=0,IF(AA7="","Not started",AA7),SUBSTITUTE(LOOKUP(2,1/(AI7:AV7<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F7="",COUNT(AI7:AV7)=0),"",TODAY()-LOOKUP(2,1/(AI7:AV7<>""),AI7:AV7)) | IF(OR(F7="",COUNT(AI7:AV7)<2),"",LOOKUP(2,1/(AI7:AV7<>""),AI7:AV7)-MIN(AI7:AV7)) | IF(OR(AD7="",AC7="Not started",AC7=""),"",IFERROR(AD7-IF(VLOOKUP(AC7,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC7,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F7="","",IF(OR(AA7="Cancelled",AC7="Cancelled"),"Cancelled",IF(OR(AC7="Completed / Handover",Y7<>"",Z7>=100),"Completed — on track",IF(O7="Not awarded",IF(U7="",IF(X7="","No planned date",IF(TODAY()>X7,"Behind — past planned date",IF(X7-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U7,"Behind — award date passed",IF(U7-TODAY()<=30,"At risk — close to off track","On track"))),IF(X7="","No planned date",IF(AND(TODAY()>X7,OR(Z7="",Z7<100)),"Behind — past end date",IF(AND(T7<>"",X7<>"",Z7<>"",(Z7<100),((TODAY()-T7)/MAX(X7-T7,1)*100)-Z7>15),"Behind — progress lag",IF(AND(X7-TODAY()<=30,X7-TODAY()>=0,OR(Z7="",Z7<90)),"At risk — close to off track","On track")))))))) | IF(OR(F7="",AC7="Completed / Handover",AC7="Cancelled"),"",IF(O7="Not awarded",IF(U7<>"",U7-TODAY(),IF(X7="","",X7-TODAY())),IF(X7="","",X7-TODAY()))) | [14 empty] | IF(OR(F7="",AJ7=""),"",IF(COUNT(AI7:AI7)=0,"",AJ7-LOOKUP(2,1/(AI7:AI7<>""),AI7:AI7))) | IF(OR(F7="",AK7=""),"",IF(COUNT(AI7:AJ7)=0,"",AK7-LOOKUP(2,1/(AI7:AJ7<>""),AI7:AJ7))) | IF(OR(F7="",AL7=""),"",IF(COUNT(AI7:AK7)=0,"",AL7-LOOKUP(2,1/(AI7:AK7<>""),AI7:AK7))) | IF(OR(F7="",AM7=""),"",IF(COUNT(AI7:AL7)=0,"",AM7-LOOKUP(2,1/(AI7:AL7<>""),AI7:AL7))) | IF(OR(F7="",AN7=""),"",IF(COUNT(AI7:AM7)=0,"",AN7-LOOKUP(2,1/(AI7:AM7<>""),AI7:AM7))) | IF(OR(F7="",AO7=""),"",IF(COUNT(AI7:AN7)=0,"",AO7-LOOKUP(2,1/(AI7:AN7<>""),AI7:AN7))) | IF(OR(F7="",AP7=""),"",IF(COUNT(AI7:AO7)=0,"",AP7-LOOKUP(2,1/(AI7:AO7<>""),AI7:AO7))) | IF(OR(F7="",AQ7=""),"",IF(COUNT(AI7:AP7)=0,"",AQ7-LOOKUP(2,1/(AI7:AP7<>""),AI7:AP7))) | IF(OR(F7="",AR7=""),"",IF(COUNT(AI7:AQ7)=0,"",AR7-LOOKUP(2,1/(AI7:AQ7<>""),AI7:AQ7))) | IF(OR(F7="",AS7=""),"",IF(COUNT(AI7:AR7)=0,"",AS7-LOOKUP(2,1/(AI7:AR7<>""),AI7:AR7))) | IF(OR(F7="",AT7=""),"",IF(COUNT(AI7:AS7)=0,"",AT7-LOOKUP(2,1/(AI7:AS7<>""),AI7:AS7))) | IF(OR(F7="",AU7=""),"",IF(COUNT(AI7:AT7)=0,"",AU7-LOOKUP(2,1/(AI7:AT7<>""),AI7:AT7))) | IF(OR(F7="",AV7=""),"",IF(COUNT(AI7:AU7)=0,"",AV7-LOOKUP(2,1/(AI7:AU7<>""),AI7:AU7))) | IF(J7="","All_Provinces",IFERROR(VLOOKUP(J7,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K7="","All_Districts",IFERROR(VLOOKUP(K7,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F8="","",ROW()-3) | [18 empty] | IF(AQ8="","",AQ8) |  |  |  | IF(W8<>"",W8,IF(OR(T8="",V8=""),"",EDATE(T8,V8))) |  |  |  |  | IF(F8="","",IF(COUNT(AI8:AV8)=0,IF(AA8="","Not started",AA8),SUBSTITUTE(LOOKUP(2,1/(AI8:AV8<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F8="",COUNT(AI8:AV8)=0),"",TODAY()-LOOKUP(2,1/(AI8:AV8<>""),AI8:AV8)) | IF(OR(F8="",COUNT(AI8:AV8)<2),"",LOOKUP(2,1/(AI8:AV8<>""),AI8:AV8)-MIN(AI8:AV8)) | IF(OR(AD8="",AC8="Not started",AC8=""),"",IFERROR(AD8-IF(VLOOKUP(AC8,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC8,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F8="","",IF(OR(AA8="Cancelled",AC8="Cancelled"),"Cancelled",IF(OR(AC8="Completed / Handover",Y8<>"",Z8>=100),"Completed — on track",IF(O8="Not awarded",IF(U8="",IF(X8="","No planned date",IF(TODAY()>X8,"Behind — past planned date",IF(X8-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U8,"Behind — award date passed",IF(U8-TODAY()<=30,"At risk — close to off track","On track"))),IF(X8="","No planned date",IF(AND(TODAY()>X8,OR(Z8="",Z8<100)),"Behind — past end date",IF(AND(T8<>"",X8<>"",Z8<>"",(Z8<100),((TODAY()-T8)/MAX(X8-T8,1)*100)-Z8>15),"Behind — progress lag",IF(AND(X8-TODAY()<=30,X8-TODAY()>=0,OR(Z8="",Z8<90)),"At risk — close to off track","On track")))))))) | IF(OR(F8="",AC8="Completed / Handover",AC8="Cancelled"),"",IF(O8="Not awarded",IF(U8<>"",U8-TODAY(),IF(X8="","",X8-TODAY())),IF(X8="","",X8-TODAY()))) | [14 empty] | IF(OR(F8="",AJ8=""),"",IF(COUNT(AI8:AI8)=0,"",AJ8-LOOKUP(2,1/(AI8:AI8<>""),AI8:AI8))) | IF(OR(F8="",AK8=""),"",IF(COUNT(AI8:AJ8)=0,"",AK8-LOOKUP(2,1/(AI8:AJ8<>""),AI8:AJ8))) | IF(OR(F8="",AL8=""),"",IF(COUNT(AI8:AK8)=0,"",AL8-LOOKUP(2,1/(AI8:AK8<>""),AI8:AK8))) | IF(OR(F8="",AM8=""),"",IF(COUNT(AI8:AL8)=0,"",AM8-LOOKUP(2,1/(AI8:AL8<>""),AI8:AL8))) | IF(OR(F8="",AN8=""),"",IF(COUNT(AI8:AM8)=0,"",AN8-LOOKUP(2,1/(AI8:AM8<>""),AI8:AM8))) | IF(OR(F8="",AO8=""),"",IF(COUNT(AI8:AN8)=0,"",AO8-LOOKUP(2,1/(AI8:AN8<>""),AI8:AN8))) | IF(OR(F8="",AP8=""),"",IF(COUNT(AI8:AO8)=0,"",AP8-LOOKUP(2,1/(AI8:AO8<>""),AI8:AO8))) | IF(OR(F8="",AQ8=""),"",IF(COUNT(AI8:AP8)=0,"",AQ8-LOOKUP(2,1/(AI8:AP8<>""),AI8:AP8))) | IF(OR(F8="",AR8=""),"",IF(COUNT(AI8:AQ8)=0,"",AR8-LOOKUP(2,1/(AI8:AQ8<>""),AI8:AQ8))) | IF(OR(F8="",AS8=""),"",IF(COUNT(AI8:AR8)=0,"",AS8-LOOKUP(2,1/(AI8:AR8<>""),AI8:AR8))) | IF(OR(F8="",AT8=""),"",IF(COUNT(AI8:AS8)=0,"",AT8-LOOKUP(2,1/(AI8:AS8<>""),AI8:AS8))) | IF(OR(F8="",AU8=""),"",IF(COUNT(AI8:AT8)=0,"",AU8-LOOKUP(2,1/(AI8:AT8<>""),AI8:AT8))) | IF(OR(F8="",AV8=""),"",IF(COUNT(AI8:AU8)=0,"",AV8-LOOKUP(2,1/(AI8:AU8<>""),AI8:AU8))) | IF(J8="","All_Provinces",IFERROR(VLOOKUP(J8,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K8="","All_Districts",IFERROR(VLOOKUP(K8,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F9="","",ROW()-3) | [18 empty] | IF(AQ9="","",AQ9) |  |  |  | IF(W9<>"",W9,IF(OR(T9="",V9=""),"",EDATE(T9,V9))) |  |  |  |  | IF(F9="","",IF(COUNT(AI9:AV9)=0,IF(AA9="","Not started",AA9),SUBSTITUTE(LOOKUP(2,1/(AI9:AV9<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F9="",COUNT(AI9:AV9)=0),"",TODAY()-LOOKUP(2,1/(AI9:AV9<>""),AI9:AV9)) | IF(OR(F9="",COUNT(AI9:AV9)<2),"",LOOKUP(2,1/(AI9:AV9<>""),AI9:AV9)-MIN(AI9:AV9)) | IF(OR(AD9="",AC9="Not started",AC9=""),"",IFERROR(AD9-IF(VLOOKUP(AC9,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC9,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F9="","",IF(OR(AA9="Cancelled",AC9="Cancelled"),"Cancelled",IF(OR(AC9="Completed / Handover",Y9<>"",Z9>=100),"Completed — on track",IF(O9="Not awarded",IF(U9="",IF(X9="","No planned date",IF(TODAY()>X9,"Behind — past planned date",IF(X9-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U9,"Behind — award date passed",IF(U9-TODAY()<=30,"At risk — close to off track","On track"))),IF(X9="","No planned date",IF(AND(TODAY()>X9,OR(Z9="",Z9<100)),"Behind — past end date",IF(AND(T9<>"",X9<>"",Z9<>"",(Z9<100),((TODAY()-T9)/MAX(X9-T9,1)*100)-Z9>15),"Behind — progress lag",IF(AND(X9-TODAY()<=30,X9-TODAY()>=0,OR(Z9="",Z9<90)),"At risk — close to off track","On track")))))))) | IF(OR(F9="",AC9="Completed / Handover",AC9="Cancelled"),"",IF(O9="Not awarded",IF(U9<>"",U9-TODAY(),IF(X9="","",X9-TODAY())),IF(X9="","",X9-TODAY()))) | [14 empty] | IF(OR(F9="",AJ9=""),"",IF(COUNT(AI9:AI9)=0,"",AJ9-LOOKUP(2,1/(AI9:AI9<>""),AI9:AI9))) | IF(OR(F9="",AK9=""),"",IF(COUNT(AI9:AJ9)=0,"",AK9-LOOKUP(2,1/(AI9:AJ9<>""),AI9:AJ9))) | IF(OR(F9="",AL9=""),"",IF(COUNT(AI9:AK9)=0,"",AL9-LOOKUP(2,1/(AI9:AK9<>""),AI9:AK9))) | IF(OR(F9="",AM9=""),"",IF(COUNT(AI9:AL9)=0,"",AM9-LOOKUP(2,1/(AI9:AL9<>""),AI9:AL9))) | IF(OR(F9="",AN9=""),"",IF(COUNT(AI9:AM9)=0,"",AN9-LOOKUP(2,1/(AI9:AM9<>""),AI9:AM9))) | IF(OR(F9="",AO9=""),"",IF(COUNT(AI9:AN9)=0,"",AO9-LOOKUP(2,1/(AI9:AN9<>""),AI9:AN9))) | IF(OR(F9="",AP9=""),"",IF(COUNT(AI9:AO9)=0,"",AP9-LOOKUP(2,1/(AI9:AO9<>""),AI9:AO9))) | IF(OR(F9="",AQ9=""),"",IF(COUNT(AI9:AP9)=0,"",AQ9-LOOKUP(2,1/(AI9:AP9<>""),AI9:AP9))) | IF(OR(F9="",AR9=""),"",IF(COUNT(AI9:AQ9)=0,"",AR9-LOOKUP(2,1/(AI9:AQ9<>""),AI9:AQ9))) | IF(OR(F9="",AS9=""),"",IF(COUNT(AI9:AR9)=0,"",AS9-LOOKUP(2,1/(AI9:AR9<>""),AI9:AR9))) | IF(OR(F9="",AT9=""),"",IF(COUNT(AI9:AS9)=0,"",AT9-LOOKUP(2,1/(AI9:AS9<>""),AI9:AS9))) | IF(OR(F9="",AU9=""),"",IF(COUNT(AI9:AT9)=0,"",AU9-LOOKUP(2,1/(AI9:AT9<>""),AI9:AT9))) | IF(OR(F9="",AV9=""),"",IF(COUNT(AI9:AU9)=0,"",AV9-LOOKUP(2,1/(AI9:AU9<>""),AI9:AU9))) | IF(J9="","All_Provinces",IFERROR(VLOOKUP(J9,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K9="","All_Districts",IFERROR(VLOOKUP(K9,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F10="","",ROW()-3) | [18 empty] | IF(AQ10="","",AQ10) |  |  |  | IF(W10<>"",W10,IF(OR(T10="",V10=""),"",EDATE(T10,V10))) |  |  |  |  | IF(F10="","",IF(COUNT(AI10:AV10)=0,IF(AA10="","Not started",AA10),SUBSTITUTE(LOOKUP(2,1/(AI10:AV10<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F10="",COUNT(AI10:AV10)=0),"",TODAY()-LOOKUP(2,1/(AI10:AV10<>""),AI10:AV10)) | IF(OR(F10="",COUNT(AI10:AV10)<2),"",LOOKUP(2,1/(AI10:AV10<>""),AI10:AV10)-MIN(AI10:AV10)) | IF(OR(AD10="",AC10="Not started",AC10=""),"",IFERROR(AD10-IF(VLOOKUP(AC10,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC10,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F10="","",IF(OR(AA10="Cancelled",AC10="Cancelled"),"Cancelled",IF(OR(AC10="Completed / Handover",Y10<>"",Z10>=100),"Completed — on track",IF(O10="Not awarded",IF(U10="",IF(X10="","No planned date",IF(TODAY()>X10,"Behind — past planned date",IF(X10-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U10,"Behind — award date passed",IF(U10-TODAY()<=30,"At risk — close to off track","On track"))),IF(X10="","No planned date",IF(AND(TODAY()>X10,OR(Z10="",Z10<100)),"Behind — past end date",IF(AND(T10<>"",X10<>"",Z10<>"",(Z10<100),((TODAY()-T10)/MAX(X10-T10,1)*100)-Z10>15),"Behind — progress lag",IF(AND(X10-TODAY()<=30,X10-TODAY()>=0,OR(Z10="",Z10<90)),"At risk — close to off track","On track")))))))) | IF(OR(F10="",AC10="Completed / Handover",AC10="Cancelled"),"",IF(O10="Not awarded",IF(U10<>"",U10-TODAY(),IF(X10="","",X10-TODAY())),IF(X10="","",X10-TODAY()))) | [14 empty] | IF(OR(F10="",AJ10=""),"",IF(COUNT(AI10:AI10)=0,"",AJ10-LOOKUP(2,1/(AI10:AI10<>""),AI10:AI10))) | IF(OR(F10="",AK10=""),"",IF(COUNT(AI10:AJ10)=0,"",AK10-LOOKUP(2,1/(AI10:AJ10<>""),AI10:AJ10))) | IF(OR(F10="",AL10=""),"",IF(COUNT(AI10:AK10)=0,"",AL10-LOOKUP(2,1/(AI10:AK10<>""),AI10:AK10))) | IF(OR(F10="",AM10=""),"",IF(COUNT(AI10:AL10)=0,"",AM10-LOOKUP(2,1/(AI10:AL10<>""),AI10:AL10))) | IF(OR(F10="",AN10=""),"",IF(COUNT(AI10:AM10)=0,"",AN10-LOOKUP(2,1/(AI10:AM10<>""),AI10:AM10))) | IF(OR(F10="",AO10=""),"",IF(COUNT(AI10:AN10)=0,"",AO10-LOOKUP(2,1/(AI10:AN10<>""),AI10:AN10))) | IF(OR(F10="",AP10=""),"",IF(COUNT(AI10:AO10)=0,"",AP10-LOOKUP(2,1/(AI10:AO10<>""),AI10:AO10))) | IF(OR(F10="",AQ10=""),"",IF(COUNT(AI10:AP10)=0,"",AQ10-LOOKUP(2,1/(AI10:AP10<>""),AI10:AP10))) | IF(OR(F10="",AR10=""),"",IF(COUNT(AI10:AQ10)=0,"",AR10-LOOKUP(2,1/(AI10:AQ10<>""),AI10:AQ10))) | IF(OR(F10="",AS10=""),"",IF(COUNT(AI10:AR10)=0,"",AS10-LOOKUP(2,1/(AI10:AR10<>""),AI10:AR10))) | IF(OR(F10="",AT10=""),"",IF(COUNT(AI10:AS10)=0,"",AT10-LOOKUP(2,1/(AI10:AS10<>""),AI10:AS10))) | IF(OR(F10="",AU10=""),"",IF(COUNT(AI10:AT10)=0,"",AU10-LOOKUP(2,1/(AI10:AT10<>""),AI10:AT10))) | IF(OR(F10="",AV10=""),"",IF(COUNT(AI10:AU10)=0,"",AV10-LOOKUP(2,1/(AI10:AU10<>""),AI10:AU10))) | IF(J10="","All_Provinces",IFERROR(VLOOKUP(J10,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K10="","All_Districts",IFERROR(VLOOKUP(K10,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F11="","",ROW()-3) | [18 empty] | IF(AQ11="","",AQ11) |  |  |  | IF(W11<>"",W11,IF(OR(T11="",V11=""),"",EDATE(T11,V11))) |  |  |  |  | IF(F11="","",IF(COUNT(AI11:AV11)=0,IF(AA11="","Not started",AA11),SUBSTITUTE(LOOKUP(2,1/(AI11:AV11<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F11="",COUNT(AI11:AV11)=0),"",TODAY()-LOOKUP(2,1/(AI11:AV11<>""),AI11:AV11)) | IF(OR(F11="",COUNT(AI11:AV11)<2),"",LOOKUP(2,1/(AI11:AV11<>""),AI11:AV11)-MIN(AI11:AV11)) | IF(OR(AD11="",AC11="Not started",AC11=""),"",IFERROR(AD11-IF(VLOOKUP(AC11,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC11,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F11="","",IF(OR(AA11="Cancelled",AC11="Cancelled"),"Cancelled",IF(OR(AC11="Completed / Handover",Y11<>"",Z11>=100),"Completed — on track",IF(O11="Not awarded",IF(U11="",IF(X11="","No planned date",IF(TODAY()>X11,"Behind — past planned date",IF(X11-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U11,"Behind — award date passed",IF(U11-TODAY()<=30,"At risk — close to off track","On track"))),IF(X11="","No planned date",IF(AND(TODAY()>X11,OR(Z11="",Z11<100)),"Behind — past end date",IF(AND(T11<>"",X11<>"",Z11<>"",(Z11<100),((TODAY()-T11)/MAX(X11-T11,1)*100)-Z11>15),"Behind — progress lag",IF(AND(X11-TODAY()<=30,X11-TODAY()>=0,OR(Z11="",Z11<90)),"At risk — close to off track","On track")))))))) | IF(OR(F11="",AC11="Completed / Handover",AC11="Cancelled"),"",IF(O11="Not awarded",IF(U11<>"",U11-TODAY(),IF(X11="","",X11-TODAY())),IF(X11="","",X11-TODAY()))) | [14 empty] | IF(OR(F11="",AJ11=""),"",IF(COUNT(AI11:AI11)=0,"",AJ11-LOOKUP(2,1/(AI11:AI11<>""),AI11:AI11))) | IF(OR(F11="",AK11=""),"",IF(COUNT(AI11:AJ11)=0,"",AK11-LOOKUP(2,1/(AI11:AJ11<>""),AI11:AJ11))) | IF(OR(F11="",AL11=""),"",IF(COUNT(AI11:AK11)=0,"",AL11-LOOKUP(2,1/(AI11:AK11<>""),AI11:AK11))) | IF(OR(F11="",AM11=""),"",IF(COUNT(AI11:AL11)=0,"",AM11-LOOKUP(2,1/(AI11:AL11<>""),AI11:AL11))) | IF(OR(F11="",AN11=""),"",IF(COUNT(AI11:AM11)=0,"",AN11-LOOKUP(2,1/(AI11:AM11<>""),AI11:AM11))) | IF(OR(F11="",AO11=""),"",IF(COUNT(AI11:AN11)=0,"",AO11-LOOKUP(2,1/(AI11:AN11<>""),AI11:AN11))) | IF(OR(F11="",AP11=""),"",IF(COUNT(AI11:AO11)=0,"",AP11-LOOKUP(2,1/(AI11:AO11<>""),AI11:AO11))) | IF(OR(F11="",AQ11=""),"",IF(COUNT(AI11:AP11)=0,"",AQ11-LOOKUP(2,1/(AI11:AP11<>""),AI11:AP11))) | IF(OR(F11="",AR11=""),"",IF(COUNT(AI11:AQ11)=0,"",AR11-LOOKUP(2,1/(AI11:AQ11<>""),AI11:AQ11))) | IF(OR(F11="",AS11=""),"",IF(COUNT(AI11:AR11)=0,"",AS11-LOOKUP(2,1/(AI11:AR11<>""),AI11:AR11))) | IF(OR(F11="",AT11=""),"",IF(COUNT(AI11:AS11)=0,"",AT11-LOOKUP(2,1/(AI11:AS11<>""),AI11:AS11))) | IF(OR(F11="",AU11=""),"",IF(COUNT(AI11:AT11)=0,"",AU11-LOOKUP(2,1/(AI11:AT11<>""),AI11:AT11))) | IF(OR(F11="",AV11=""),"",IF(COUNT(AI11:AU11)=0,"",AV11-LOOKUP(2,1/(AI11:AU11<>""),AI11:AU11))) | IF(J11="","All_Provinces",IFERROR(VLOOKUP(J11,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K11="","All_Districts",IFERROR(VLOOKUP(K11,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F12="","",ROW()-3) | [18 empty] | IF(AQ12="","",AQ12) |  |  |  | IF(W12<>"",W12,IF(OR(T12="",V12=""),"",EDATE(T12,V12))) |  |  |  |  | IF(F12="","",IF(COUNT(AI12:AV12)=0,IF(AA12="","Not started",AA12),SUBSTITUTE(LOOKUP(2,1/(AI12:AV12<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F12="",COUNT(AI12:AV12)=0),"",TODAY()-LOOKUP(2,1/(AI12:AV12<>""),AI12:AV12)) | IF(OR(F12="",COUNT(AI12:AV12)<2),"",LOOKUP(2,1/(AI12:AV12<>""),AI12:AV12)-MIN(AI12:AV12)) | IF(OR(AD12="",AC12="Not started",AC12=""),"",IFERROR(AD12-IF(VLOOKUP(AC12,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC12,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F12="","",IF(OR(AA12="Cancelled",AC12="Cancelled"),"Cancelled",IF(OR(AC12="Completed / Handover",Y12<>"",Z12>=100),"Completed — on track",IF(O12="Not awarded",IF(U12="",IF(X12="","No planned date",IF(TODAY()>X12,"Behind — past planned date",IF(X12-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U12,"Behind — award date passed",IF(U12-TODAY()<=30,"At risk — close to off track","On track"))),IF(X12="","No planned date",IF(AND(TODAY()>X12,OR(Z12="",Z12<100)),"Behind — past end date",IF(AND(T12<>"",X12<>"",Z12<>"",(Z12<100),((TODAY()-T12)/MAX(X12-T12,1)*100)-Z12>15),"Behind — progress lag",IF(AND(X12-TODAY()<=30,X12-TODAY()>=0,OR(Z12="",Z12<90)),"At risk — close to off track","On track")))))))) | IF(OR(F12="",AC12="Completed / Handover",AC12="Cancelled"),"",IF(O12="Not awarded",IF(U12<>"",U12-TODAY(),IF(X12="","",X12-TODAY())),IF(X12="","",X12-TODAY()))) | [14 empty] | IF(OR(F12="",AJ12=""),"",IF(COUNT(AI12:AI12)=0,"",AJ12-LOOKUP(2,1/(AI12:AI12<>""),AI12:AI12))) | IF(OR(F12="",AK12=""),"",IF(COUNT(AI12:AJ12)=0,"",AK12-LOOKUP(2,1/(AI12:AJ12<>""),AI12:AJ12))) | IF(OR(F12="",AL12=""),"",IF(COUNT(AI12:AK12)=0,"",AL12-LOOKUP(2,1/(AI12:AK12<>""),AI12:AK12))) | IF(OR(F12="",AM12=""),"",IF(COUNT(AI12:AL12)=0,"",AM12-LOOKUP(2,1/(AI12:AL12<>""),AI12:AL12))) | IF(OR(F12="",AN12=""),"",IF(COUNT(AI12:AM12)=0,"",AN12-LOOKUP(2,1/(AI12:AM12<>""),AI12:AM12))) | IF(OR(F12="",AO12=""),"",IF(COUNT(AI12:AN12)=0,"",AO12-LOOKUP(2,1/(AI12:AN12<>""),AI12:AN12))) | IF(OR(F12="",AP12=""),"",IF(COUNT(AI12:AO12)=0,"",AP12-LOOKUP(2,1/(AI12:AO12<>""),AI12:AO12))) | IF(OR(F12="",AQ12=""),"",IF(COUNT(AI12:AP12)=0,"",AQ12-LOOKUP(2,1/(AI12:AP12<>""),AI12:AP12))) | IF(OR(F12="",AR12=""),"",IF(COUNT(AI12:AQ12)=0,"",AR12-LOOKUP(2,1/(AI12:AQ12<>""),AI12:AQ12))) | IF(OR(F12="",AS12=""),"",IF(COUNT(AI12:AR12)=0,"",AS12-LOOKUP(2,1/(AI12:AR12<>""),AI12:AR12))) | IF(OR(F12="",AT12=""),"",IF(COUNT(AI12:AS12)=0,"",AT12-LOOKUP(2,1/(AI12:AS12<>""),AI12:AS12))) | IF(OR(F12="",AU12=""),"",IF(COUNT(AI12:AT12)=0,"",AU12-LOOKUP(2,1/(AI12:AT12<>""),AI12:AT12))) | IF(OR(F12="",AV12=""),"",IF(COUNT(AI12:AU12)=0,"",AV12-LOOKUP(2,1/(AI12:AU12<>""),AI12:AU12))) | IF(J12="","All_Provinces",IFERROR(VLOOKUP(J12,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K12="","All_Districts",IFERROR(VLOOKUP(K12,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F13="","",ROW()-3) | [18 empty] | IF(AQ13="","",AQ13) |  |  |  | IF(W13<>"",W13,IF(OR(T13="",V13=""),"",EDATE(T13,V13))) |  |  |  |  | IF(F13="","",IF(COUNT(AI13:AV13)=0,IF(AA13="","Not started",AA13),SUBSTITUTE(LOOKUP(2,1/(AI13:AV13<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F13="",COUNT(AI13:AV13)=0),"",TODAY()-LOOKUP(2,1/(AI13:AV13<>""),AI13:AV13)) | IF(OR(F13="",COUNT(AI13:AV13)<2),"",LOOKUP(2,1/(AI13:AV13<>""),AI13:AV13)-MIN(AI13:AV13)) | IF(OR(AD13="",AC13="Not started",AC13=""),"",IFERROR(AD13-IF(VLOOKUP(AC13,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC13,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F13="","",IF(OR(AA13="Cancelled",AC13="Cancelled"),"Cancelled",IF(OR(AC13="Completed / Handover",Y13<>"",Z13>=100),"Completed — on track",IF(O13="Not awarded",IF(U13="",IF(X13="","No planned date",IF(TODAY()>X13,"Behind — past planned date",IF(X13-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U13,"Behind — award date passed",IF(U13-TODAY()<=30,"At risk — close to off track","On track"))),IF(X13="","No planned date",IF(AND(TODAY()>X13,OR(Z13="",Z13<100)),"Behind — past end date",IF(AND(T13<>"",X13<>"",Z13<>"",(Z13<100),((TODAY()-T13)/MAX(X13-T13,1)*100)-Z13>15),"Behind — progress lag",IF(AND(X13-TODAY()<=30,X13-TODAY()>=0,OR(Z13="",Z13<90)),"At risk — close to off track","On track")))))))) | IF(OR(F13="",AC13="Completed / Handover",AC13="Cancelled"),"",IF(O13="Not awarded",IF(U13<>"",U13-TODAY(),IF(X13="","",X13-TODAY())),IF(X13="","",X13-TODAY()))) | [14 empty] | IF(OR(F13="",AJ13=""),"",IF(COUNT(AI13:AI13)=0,"",AJ13-LOOKUP(2,1/(AI13:AI13<>""),AI13:AI13))) | IF(OR(F13="",AK13=""),"",IF(COUNT(AI13:AJ13)=0,"",AK13-LOOKUP(2,1/(AI13:AJ13<>""),AI13:AJ13))) | IF(OR(F13="",AL13=""),"",IF(COUNT(AI13:AK13)=0,"",AL13-LOOKUP(2,1/(AI13:AK13<>""),AI13:AK13))) | IF(OR(F13="",AM13=""),"",IF(COUNT(AI13:AL13)=0,"",AM13-LOOKUP(2,1/(AI13:AL13<>""),AI13:AL13))) | IF(OR(F13="",AN13=""),"",IF(COUNT(AI13:AM13)=0,"",AN13-LOOKUP(2,1/(AI13:AM13<>""),AI13:AM13))) | IF(OR(F13="",AO13=""),"",IF(COUNT(AI13:AN13)=0,"",AO13-LOOKUP(2,1/(AI13:AN13<>""),AI13:AN13))) | IF(OR(F13="",AP13=""),"",IF(COUNT(AI13:AO13)=0,"",AP13-LOOKUP(2,1/(AI13:AO13<>""),AI13:AO13))) | IF(OR(F13="",AQ13=""),"",IF(COUNT(AI13:AP13)=0,"",AQ13-LOOKUP(2,1/(AI13:AP13<>""),AI13:AP13))) | IF(OR(F13="",AR13=""),"",IF(COUNT(AI13:AQ13)=0,"",AR13-LOOKUP(2,1/(AI13:AQ13<>""),AI13:AQ13))) | IF(OR(F13="",AS13=""),"",IF(COUNT(AI13:AR13)=0,"",AS13-LOOKUP(2,1/(AI13:AR13<>""),AI13:AR13))) | IF(OR(F13="",AT13=""),"",IF(COUNT(AI13:AS13)=0,"",AT13-LOOKUP(2,1/(AI13:AS13<>""),AI13:AS13))) | IF(OR(F13="",AU13=""),"",IF(COUNT(AI13:AT13)=0,"",AU13-LOOKUP(2,1/(AI13:AT13<>""),AI13:AT13))) | IF(OR(F13="",AV13=""),"",IF(COUNT(AI13:AU13)=0,"",AV13-LOOKUP(2,1/(AI13:AU13<>""),AI13:AU13))) | IF(J13="","All_Provinces",IFERROR(VLOOKUP(J13,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K13="","All_Districts",IFERROR(VLOOKUP(K13,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F14="","",ROW()-3) | [18 empty] | IF(AQ14="","",AQ14) |  |  |  | IF(W14<>"",W14,IF(OR(T14="",V14=""),"",EDATE(T14,V14))) |  |  |  |  | IF(F14="","",IF(COUNT(AI14:AV14)=0,IF(AA14="","Not started",AA14),SUBSTITUTE(LOOKUP(2,1/(AI14:AV14<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F14="",COUNT(AI14:AV14)=0),"",TODAY()-LOOKUP(2,1/(AI14:AV14<>""),AI14:AV14)) | IF(OR(F14="",COUNT(AI14:AV14)<2),"",LOOKUP(2,1/(AI14:AV14<>""),AI14:AV14)-MIN(AI14:AV14)) | IF(OR(AD14="",AC14="Not started",AC14=""),"",IFERROR(AD14-IF(VLOOKUP(AC14,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC14,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F14="","",IF(OR(AA14="Cancelled",AC14="Cancelled"),"Cancelled",IF(OR(AC14="Completed / Handover",Y14<>"",Z14>=100),"Completed — on track",IF(O14="Not awarded",IF(U14="",IF(X14="","No planned date",IF(TODAY()>X14,"Behind — past planned date",IF(X14-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U14,"Behind — award date passed",IF(U14-TODAY()<=30,"At risk — close to off track","On track"))),IF(X14="","No planned date",IF(AND(TODAY()>X14,OR(Z14="",Z14<100)),"Behind — past end date",IF(AND(T14<>"",X14<>"",Z14<>"",(Z14<100),((TODAY()-T14)/MAX(X14-T14,1)*100)-Z14>15),"Behind — progress lag",IF(AND(X14-TODAY()<=30,X14-TODAY()>=0,OR(Z14="",Z14<90)),"At risk — close to off track","On track")))))))) | IF(OR(F14="",AC14="Completed / Handover",AC14="Cancelled"),"",IF(O14="Not awarded",IF(U14<>"",U14-TODAY(),IF(X14="","",X14-TODAY())),IF(X14="","",X14-TODAY()))) | [14 empty] | IF(OR(F14="",AJ14=""),"",IF(COUNT(AI14:AI14)=0,"",AJ14-LOOKUP(2,1/(AI14:AI14<>""),AI14:AI14))) | IF(OR(F14="",AK14=""),"",IF(COUNT(AI14:AJ14)=0,"",AK14-LOOKUP(2,1/(AI14:AJ14<>""),AI14:AJ14))) | IF(OR(F14="",AL14=""),"",IF(COUNT(AI14:AK14)=0,"",AL14-LOOKUP(2,1/(AI14:AK14<>""),AI14:AK14))) | IF(OR(F14="",AM14=""),"",IF(COUNT(AI14:AL14)=0,"",AM14-LOOKUP(2,1/(AI14:AL14<>""),AI14:AL14))) | IF(OR(F14="",AN14=""),"",IF(COUNT(AI14:AM14)=0,"",AN14-LOOKUP(2,1/(AI14:AM14<>""),AI14:AM14))) | IF(OR(F14="",AO14=""),"",IF(COUNT(AI14:AN14)=0,"",AO14-LOOKUP(2,1/(AI14:AN14<>""),AI14:AN14))) | IF(OR(F14="",AP14=""),"",IF(COUNT(AI14:AO14)=0,"",AP14-LOOKUP(2,1/(AI14:AO14<>""),AI14:AO14))) | IF(OR(F14="",AQ14=""),"",IF(COUNT(AI14:AP14)=0,"",AQ14-LOOKUP(2,1/(AI14:AP14<>""),AI14:AP14))) | IF(OR(F14="",AR14=""),"",IF(COUNT(AI14:AQ14)=0,"",AR14-LOOKUP(2,1/(AI14:AQ14<>""),AI14:AQ14))) | IF(OR(F14="",AS14=""),"",IF(COUNT(AI14:AR14)=0,"",AS14-LOOKUP(2,1/(AI14:AR14<>""),AI14:AR14))) | IF(OR(F14="",AT14=""),"",IF(COUNT(AI14:AS14)=0,"",AT14-LOOKUP(2,1/(AI14:AS14<>""),AI14:AS14))) | IF(OR(F14="",AU14=""),"",IF(COUNT(AI14:AT14)=0,"",AU14-LOOKUP(2,1/(AI14:AT14<>""),AI14:AT14))) | IF(OR(F14="",AV14=""),"",IF(COUNT(AI14:AU14)=0,"",AV14-LOOKUP(2,1/(AI14:AU14<>""),AI14:AU14))) | IF(J14="","All_Provinces",IFERROR(VLOOKUP(J14,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K14="","All_Districts",IFERROR(VLOOKUP(K14,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F15="","",ROW()-3) | [18 empty] | IF(AQ15="","",AQ15) |  |  |  | IF(W15<>"",W15,IF(OR(T15="",V15=""),"",EDATE(T15,V15))) |  |  |  |  | IF(F15="","",IF(COUNT(AI15:AV15)=0,IF(AA15="","Not started",AA15),SUBSTITUTE(LOOKUP(2,1/(AI15:AV15<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F15="",COUNT(AI15:AV15)=0),"",TODAY()-LOOKUP(2,1/(AI15:AV15<>""),AI15:AV15)) | IF(OR(F15="",COUNT(AI15:AV15)<2),"",LOOKUP(2,1/(AI15:AV15<>""),AI15:AV15)-MIN(AI15:AV15)) | IF(OR(AD15="",AC15="Not started",AC15=""),"",IFERROR(AD15-IF(VLOOKUP(AC15,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC15,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F15="","",IF(OR(AA15="Cancelled",AC15="Cancelled"),"Cancelled",IF(OR(AC15="Completed / Handover",Y15<>"",Z15>=100),"Completed — on track",IF(O15="Not awarded",IF(U15="",IF(X15="","No planned date",IF(TODAY()>X15,"Behind — past planned date",IF(X15-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U15,"Behind — award date passed",IF(U15-TODAY()<=30,"At risk — close to off track","On track"))),IF(X15="","No planned date",IF(AND(TODAY()>X15,OR(Z15="",Z15<100)),"Behind — past end date",IF(AND(T15<>"",X15<>"",Z15<>"",(Z15<100),((TODAY()-T15)/MAX(X15-T15,1)*100)-Z15>15),"Behind — progress lag",IF(AND(X15-TODAY()<=30,X15-TODAY()>=0,OR(Z15="",Z15<90)),"At risk — close to off track","On track")))))))) | IF(OR(F15="",AC15="Completed / Handover",AC15="Cancelled"),"",IF(O15="Not awarded",IF(U15<>"",U15-TODAY(),IF(X15="","",X15-TODAY())),IF(X15="","",X15-TODAY()))) | [14 empty] | IF(OR(F15="",AJ15=""),"",IF(COUNT(AI15:AI15)=0,"",AJ15-LOOKUP(2,1/(AI15:AI15<>""),AI15:AI15))) | IF(OR(F15="",AK15=""),"",IF(COUNT(AI15:AJ15)=0,"",AK15-LOOKUP(2,1/(AI15:AJ15<>""),AI15:AJ15))) | IF(OR(F15="",AL15=""),"",IF(COUNT(AI15:AK15)=0,"",AL15-LOOKUP(2,1/(AI15:AK15<>""),AI15:AK15))) | IF(OR(F15="",AM15=""),"",IF(COUNT(AI15:AL15)=0,"",AM15-LOOKUP(2,1/(AI15:AL15<>""),AI15:AL15))) | IF(OR(F15="",AN15=""),"",IF(COUNT(AI15:AM15)=0,"",AN15-LOOKUP(2,1/(AI15:AM15<>""),AI15:AM15))) | IF(OR(F15="",AO15=""),"",IF(COUNT(AI15:AN15)=0,"",AO15-LOOKUP(2,1/(AI15:AN15<>""),AI15:AN15))) | IF(OR(F15="",AP15=""),"",IF(COUNT(AI15:AO15)=0,"",AP15-LOOKUP(2,1/(AI15:AO15<>""),AI15:AO15))) | IF(OR(F15="",AQ15=""),"",IF(COUNT(AI15:AP15)=0,"",AQ15-LOOKUP(2,1/(AI15:AP15<>""),AI15:AP15))) | IF(OR(F15="",AR15=""),"",IF(COUNT(AI15:AQ15)=0,"",AR15-LOOKUP(2,1/(AI15:AQ15<>""),AI15:AQ15))) | IF(OR(F15="",AS15=""),"",IF(COUNT(AI15:AR15)=0,"",AS15-LOOKUP(2,1/(AI15:AR15<>""),AI15:AR15))) | IF(OR(F15="",AT15=""),"",IF(COUNT(AI15:AS15)=0,"",AT15-LOOKUP(2,1/(AI15:AS15<>""),AI15:AS15))) | IF(OR(F15="",AU15=""),"",IF(COUNT(AI15:AT15)=0,"",AU15-LOOKUP(2,1/(AI15:AT15<>""),AI15:AT15))) | IF(OR(F15="",AV15=""),"",IF(COUNT(AI15:AU15)=0,"",AV15-LOOKUP(2,1/(AI15:AU15<>""),AI15:AU15))) | IF(J15="","All_Provinces",IFERROR(VLOOKUP(J15,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K15="","All_Districts",IFERROR(VLOOKUP(K15,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F16="","",ROW()-3) | [18 empty] | IF(AQ16="","",AQ16) |  |  |  | IF(W16<>"",W16,IF(OR(T16="",V16=""),"",EDATE(T16,V16))) |  |  |  |  | IF(F16="","",IF(COUNT(AI16:AV16)=0,IF(AA16="","Not started",AA16),SUBSTITUTE(LOOKUP(2,1/(AI16:AV16<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F16="",COUNT(AI16:AV16)=0),"",TODAY()-LOOKUP(2,1/(AI16:AV16<>""),AI16:AV16)) | IF(OR(F16="",COUNT(AI16:AV16)<2),"",LOOKUP(2,1/(AI16:AV16<>""),AI16:AV16)-MIN(AI16:AV16)) | IF(OR(AD16="",AC16="Not started",AC16=""),"",IFERROR(AD16-IF(VLOOKUP(AC16,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC16,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F16="","",IF(OR(AA16="Cancelled",AC16="Cancelled"),"Cancelled",IF(OR(AC16="Completed / Handover",Y16<>"",Z16>=100),"Completed — on track",IF(O16="Not awarded",IF(U16="",IF(X16="","No planned date",IF(TODAY()>X16,"Behind — past planned date",IF(X16-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U16,"Behind — award date passed",IF(U16-TODAY()<=30,"At risk — close to off track","On track"))),IF(X16="","No planned date",IF(AND(TODAY()>X16,OR(Z16="",Z16<100)),"Behind — past end date",IF(AND(T16<>"",X16<>"",Z16<>"",(Z16<100),((TODAY()-T16)/MAX(X16-T16,1)*100)-Z16>15),"Behind — progress lag",IF(AND(X16-TODAY()<=30,X16-TODAY()>=0,OR(Z16="",Z16<90)),"At risk — close to off track","On track")))))))) | IF(OR(F16="",AC16="Completed / Handover",AC16="Cancelled"),"",IF(O16="Not awarded",IF(U16<>"",U16-TODAY(),IF(X16="","",X16-TODAY())),IF(X16="","",X16-TODAY()))) | [14 empty] | IF(OR(F16="",AJ16=""),"",IF(COUNT(AI16:AI16)=0,"",AJ16-LOOKUP(2,1/(AI16:AI16<>""),AI16:AI16))) | IF(OR(F16="",AK16=""),"",IF(COUNT(AI16:AJ16)=0,"",AK16-LOOKUP(2,1/(AI16:AJ16<>""),AI16:AJ16))) | IF(OR(F16="",AL16=""),"",IF(COUNT(AI16:AK16)=0,"",AL16-LOOKUP(2,1/(AI16:AK16<>""),AI16:AK16))) | IF(OR(F16="",AM16=""),"",IF(COUNT(AI16:AL16)=0,"",AM16-LOOKUP(2,1/(AI16:AL16<>""),AI16:AL16))) | IF(OR(F16="",AN16=""),"",IF(COUNT(AI16:AM16)=0,"",AN16-LOOKUP(2,1/(AI16:AM16<>""),AI16:AM16))) | IF(OR(F16="",AO16=""),"",IF(COUNT(AI16:AN16)=0,"",AO16-LOOKUP(2,1/(AI16:AN16<>""),AI16:AN16))) | IF(OR(F16="",AP16=""),"",IF(COUNT(AI16:AO16)=0,"",AP16-LOOKUP(2,1/(AI16:AO16<>""),AI16:AO16))) | IF(OR(F16="",AQ16=""),"",IF(COUNT(AI16:AP16)=0,"",AQ16-LOOKUP(2,1/(AI16:AP16<>""),AI16:AP16))) | IF(OR(F16="",AR16=""),"",IF(COUNT(AI16:AQ16)=0,"",AR16-LOOKUP(2,1/(AI16:AQ16<>""),AI16:AQ16))) | IF(OR(F16="",AS16=""),"",IF(COUNT(AI16:AR16)=0,"",AS16-LOOKUP(2,1/(AI16:AR16<>""),AI16:AR16))) | IF(OR(F16="",AT16=""),"",IF(COUNT(AI16:AS16)=0,"",AT16-LOOKUP(2,1/(AI16:AS16<>""),AI16:AS16))) | IF(OR(F16="",AU16=""),"",IF(COUNT(AI16:AT16)=0,"",AU16-LOOKUP(2,1/(AI16:AT16<>""),AI16:AT16))) | IF(OR(F16="",AV16=""),"",IF(COUNT(AI16:AU16)=0,"",AV16-LOOKUP(2,1/(AI16:AU16<>""),AI16:AU16))) | IF(J16="","All_Provinces",IFERROR(VLOOKUP(J16,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K16="","All_Districts",IFERROR(VLOOKUP(K16,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F17="","",ROW()-3) | [18 empty] | IF(AQ17="","",AQ17) |  |  |  | IF(W17<>"",W17,IF(OR(T17="",V17=""),"",EDATE(T17,V17))) |  |  |  |  | IF(F17="","",IF(COUNT(AI17:AV17)=0,IF(AA17="","Not started",AA17),SUBSTITUTE(LOOKUP(2,1/(AI17:AV17<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F17="",COUNT(AI17:AV17)=0),"",TODAY()-LOOKUP(2,1/(AI17:AV17<>""),AI17:AV17)) | IF(OR(F17="",COUNT(AI17:AV17)<2),"",LOOKUP(2,1/(AI17:AV17<>""),AI17:AV17)-MIN(AI17:AV17)) | IF(OR(AD17="",AC17="Not started",AC17=""),"",IFERROR(AD17-IF(VLOOKUP(AC17,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC17,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F17="","",IF(OR(AA17="Cancelled",AC17="Cancelled"),"Cancelled",IF(OR(AC17="Completed / Handover",Y17<>"",Z17>=100),"Completed — on track",IF(O17="Not awarded",IF(U17="",IF(X17="","No planned date",IF(TODAY()>X17,"Behind — past planned date",IF(X17-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U17,"Behind — award date passed",IF(U17-TODAY()<=30,"At risk — close to off track","On track"))),IF(X17="","No planned date",IF(AND(TODAY()>X17,OR(Z17="",Z17<100)),"Behind — past end date",IF(AND(T17<>"",X17<>"",Z17<>"",(Z17<100),((TODAY()-T17)/MAX(X17-T17,1)*100)-Z17>15),"Behind — progress lag",IF(AND(X17-TODAY()<=30,X17-TODAY()>=0,OR(Z17="",Z17<90)),"At risk — close to off track","On track")))))))) | IF(OR(F17="",AC17="Completed / Handover",AC17="Cancelled"),"",IF(O17="Not awarded",IF(U17<>"",U17-TODAY(),IF(X17="","",X17-TODAY())),IF(X17="","",X17-TODAY()))) | [14 empty] | IF(OR(F17="",AJ17=""),"",IF(COUNT(AI17:AI17)=0,"",AJ17-LOOKUP(2,1/(AI17:AI17<>""),AI17:AI17))) | IF(OR(F17="",AK17=""),"",IF(COUNT(AI17:AJ17)=0,"",AK17-LOOKUP(2,1/(AI17:AJ17<>""),AI17:AJ17))) | IF(OR(F17="",AL17=""),"",IF(COUNT(AI17:AK17)=0,"",AL17-LOOKUP(2,1/(AI17:AK17<>""),AI17:AK17))) | IF(OR(F17="",AM17=""),"",IF(COUNT(AI17:AL17)=0,"",AM17-LOOKUP(2,1/(AI17:AL17<>""),AI17:AL17))) | IF(OR(F17="",AN17=""),"",IF(COUNT(AI17:AM17)=0,"",AN17-LOOKUP(2,1/(AI17:AM17<>""),AI17:AM17))) | IF(OR(F17="",AO17=""),"",IF(COUNT(AI17:AN17)=0,"",AO17-LOOKUP(2,1/(AI17:AN17<>""),AI17:AN17))) | IF(OR(F17="",AP17=""),"",IF(COUNT(AI17:AO17)=0,"",AP17-LOOKUP(2,1/(AI17:AO17<>""),AI17:AO17))) | IF(OR(F17="",AQ17=""),"",IF(COUNT(AI17:AP17)=0,"",AQ17-LOOKUP(2,1/(AI17:AP17<>""),AI17:AP17))) | IF(OR(F17="",AR17=""),"",IF(COUNT(AI17:AQ17)=0,"",AR17-LOOKUP(2,1/(AI17:AQ17<>""),AI17:AQ17))) | IF(OR(F17="",AS17=""),"",IF(COUNT(AI17:AR17)=0,"",AS17-LOOKUP(2,1/(AI17:AR17<>""),AI17:AR17))) | IF(OR(F17="",AT17=""),"",IF(COUNT(AI17:AS17)=0,"",AT17-LOOKUP(2,1/(AI17:AS17<>""),AI17:AS17))) | IF(OR(F17="",AU17=""),"",IF(COUNT(AI17:AT17)=0,"",AU17-LOOKUP(2,1/(AI17:AT17<>""),AI17:AT17))) | IF(OR(F17="",AV17=""),"",IF(COUNT(AI17:AU17)=0,"",AV17-LOOKUP(2,1/(AI17:AU17<>""),AI17:AU17))) | IF(J17="","All_Provinces",IFERROR(VLOOKUP(J17,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K17="","All_Districts",IFERROR(VLOOKUP(K17,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F18="","",ROW()-3) | [18 empty] | IF(AQ18="","",AQ18) |  |  |  | IF(W18<>"",W18,IF(OR(T18="",V18=""),"",EDATE(T18,V18))) |  |  |  |  | IF(F18="","",IF(COUNT(AI18:AV18)=0,IF(AA18="","Not started",AA18),SUBSTITUTE(LOOKUP(2,1/(AI18:AV18<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F18="",COUNT(AI18:AV18)=0),"",TODAY()-LOOKUP(2,1/(AI18:AV18<>""),AI18:AV18)) | IF(OR(F18="",COUNT(AI18:AV18)<2),"",LOOKUP(2,1/(AI18:AV18<>""),AI18:AV18)-MIN(AI18:AV18)) | IF(OR(AD18="",AC18="Not started",AC18=""),"",IFERROR(AD18-IF(VLOOKUP(AC18,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC18,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F18="","",IF(OR(AA18="Cancelled",AC18="Cancelled"),"Cancelled",IF(OR(AC18="Completed / Handover",Y18<>"",Z18>=100),"Completed — on track",IF(O18="Not awarded",IF(U18="",IF(X18="","No planned date",IF(TODAY()>X18,"Behind — past planned date",IF(X18-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U18,"Behind — award date passed",IF(U18-TODAY()<=30,"At risk — close to off track","On track"))),IF(X18="","No planned date",IF(AND(TODAY()>X18,OR(Z18="",Z18<100)),"Behind — past end date",IF(AND(T18<>"",X18<>"",Z18<>"",(Z18<100),((TODAY()-T18)/MAX(X18-T18,1)*100)-Z18>15),"Behind — progress lag",IF(AND(X18-TODAY()<=30,X18-TODAY()>=0,OR(Z18="",Z18<90)),"At risk — close to off track","On track")))))))) | IF(OR(F18="",AC18="Completed / Handover",AC18="Cancelled"),"",IF(O18="Not awarded",IF(U18<>"",U18-TODAY(),IF(X18="","",X18-TODAY())),IF(X18="","",X18-TODAY()))) | [14 empty] | IF(OR(F18="",AJ18=""),"",IF(COUNT(AI18:AI18)=0,"",AJ18-LOOKUP(2,1/(AI18:AI18<>""),AI18:AI18))) | IF(OR(F18="",AK18=""),"",IF(COUNT(AI18:AJ18)=0,"",AK18-LOOKUP(2,1/(AI18:AJ18<>""),AI18:AJ18))) | IF(OR(F18="",AL18=""),"",IF(COUNT(AI18:AK18)=0,"",AL18-LOOKUP(2,1/(AI18:AK18<>""),AI18:AK18))) | IF(OR(F18="",AM18=""),"",IF(COUNT(AI18:AL18)=0,"",AM18-LOOKUP(2,1/(AI18:AL18<>""),AI18:AL18))) | IF(OR(F18="",AN18=""),"",IF(COUNT(AI18:AM18)=0,"",AN18-LOOKUP(2,1/(AI18:AM18<>""),AI18:AM18))) | IF(OR(F18="",AO18=""),"",IF(COUNT(AI18:AN18)=0,"",AO18-LOOKUP(2,1/(AI18:AN18<>""),AI18:AN18))) | IF(OR(F18="",AP18=""),"",IF(COUNT(AI18:AO18)=0,"",AP18-LOOKUP(2,1/(AI18:AO18<>""),AI18:AO18))) | IF(OR(F18="",AQ18=""),"",IF(COUNT(AI18:AP18)=0,"",AQ18-LOOKUP(2,1/(AI18:AP18<>""),AI18:AP18))) | IF(OR(F18="",AR18=""),"",IF(COUNT(AI18:AQ18)=0,"",AR18-LOOKUP(2,1/(AI18:AQ18<>""),AI18:AQ18))) | IF(OR(F18="",AS18=""),"",IF(COUNT(AI18:AR18)=0,"",AS18-LOOKUP(2,1/(AI18:AR18<>""),AI18:AR18))) | IF(OR(F18="",AT18=""),"",IF(COUNT(AI18:AS18)=0,"",AT18-LOOKUP(2,1/(AI18:AS18<>""),AI18:AS18))) | IF(OR(F18="",AU18=""),"",IF(COUNT(AI18:AT18)=0,"",AU18-LOOKUP(2,1/(AI18:AT18<>""),AI18:AT18))) | IF(OR(F18="",AV18=""),"",IF(COUNT(AI18:AU18)=0,"",AV18-LOOKUP(2,1/(AI18:AU18<>""),AI18:AU18))) | IF(J18="","All_Provinces",IFERROR(VLOOKUP(J18,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K18="","All_Districts",IFERROR(VLOOKUP(K18,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F19="","",ROW()-3) | [18 empty] | IF(AQ19="","",AQ19) |  |  |  | IF(W19<>"",W19,IF(OR(T19="",V19=""),"",EDATE(T19,V19))) |  |  |  |  | IF(F19="","",IF(COUNT(AI19:AV19)=0,IF(AA19="","Not started",AA19),SUBSTITUTE(LOOKUP(2,1/(AI19:AV19<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F19="",COUNT(AI19:AV19)=0),"",TODAY()-LOOKUP(2,1/(AI19:AV19<>""),AI19:AV19)) | IF(OR(F19="",COUNT(AI19:AV19)<2),"",LOOKUP(2,1/(AI19:AV19<>""),AI19:AV19)-MIN(AI19:AV19)) | IF(OR(AD19="",AC19="Not started",AC19=""),"",IFERROR(AD19-IF(VLOOKUP(AC19,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC19,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F19="","",IF(OR(AA19="Cancelled",AC19="Cancelled"),"Cancelled",IF(OR(AC19="Completed / Handover",Y19<>"",Z19>=100),"Completed — on track",IF(O19="Not awarded",IF(U19="",IF(X19="","No planned date",IF(TODAY()>X19,"Behind — past planned date",IF(X19-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U19,"Behind — award date passed",IF(U19-TODAY()<=30,"At risk — close to off track","On track"))),IF(X19="","No planned date",IF(AND(TODAY()>X19,OR(Z19="",Z19<100)),"Behind — past end date",IF(AND(T19<>"",X19<>"",Z19<>"",(Z19<100),((TODAY()-T19)/MAX(X19-T19,1)*100)-Z19>15),"Behind — progress lag",IF(AND(X19-TODAY()<=30,X19-TODAY()>=0,OR(Z19="",Z19<90)),"At risk — close to off track","On track")))))))) | IF(OR(F19="",AC19="Completed / Handover",AC19="Cancelled"),"",IF(O19="Not awarded",IF(U19<>"",U19-TODAY(),IF(X19="","",X19-TODAY())),IF(X19="","",X19-TODAY()))) | [14 empty] | IF(OR(F19="",AJ19=""),"",IF(COUNT(AI19:AI19)=0,"",AJ19-LOOKUP(2,1/(AI19:AI19<>""),AI19:AI19))) | IF(OR(F19="",AK19=""),"",IF(COUNT(AI19:AJ19)=0,"",AK19-LOOKUP(2,1/(AI19:AJ19<>""),AI19:AJ19))) | IF(OR(F19="",AL19=""),"",IF(COUNT(AI19:AK19)=0,"",AL19-LOOKUP(2,1/(AI19:AK19<>""),AI19:AK19))) | IF(OR(F19="",AM19=""),"",IF(COUNT(AI19:AL19)=0,"",AM19-LOOKUP(2,1/(AI19:AL19<>""),AI19:AL19))) | IF(OR(F19="",AN19=""),"",IF(COUNT(AI19:AM19)=0,"",AN19-LOOKUP(2,1/(AI19:AM19<>""),AI19:AM19))) | IF(OR(F19="",AO19=""),"",IF(COUNT(AI19:AN19)=0,"",AO19-LOOKUP(2,1/(AI19:AN19<>""),AI19:AN19))) | IF(OR(F19="",AP19=""),"",IF(COUNT(AI19:AO19)=0,"",AP19-LOOKUP(2,1/(AI19:AO19<>""),AI19:AO19))) | IF(OR(F19="",AQ19=""),"",IF(COUNT(AI19:AP19)=0,"",AQ19-LOOKUP(2,1/(AI19:AP19<>""),AI19:AP19))) | IF(OR(F19="",AR19=""),"",IF(COUNT(AI19:AQ19)=0,"",AR19-LOOKUP(2,1/(AI19:AQ19<>""),AI19:AQ19))) | IF(OR(F19="",AS19=""),"",IF(COUNT(AI19:AR19)=0,"",AS19-LOOKUP(2,1/(AI19:AR19<>""),AI19:AR19))) | IF(OR(F19="",AT19=""),"",IF(COUNT(AI19:AS19)=0,"",AT19-LOOKUP(2,1/(AI19:AS19<>""),AI19:AS19))) | IF(OR(F19="",AU19=""),"",IF(COUNT(AI19:AT19)=0,"",AU19-LOOKUP(2,1/(AI19:AT19<>""),AI19:AT19))) | IF(OR(F19="",AV19=""),"",IF(COUNT(AI19:AU19)=0,"",AV19-LOOKUP(2,1/(AI19:AU19<>""),AI19:AU19))) | IF(J19="","All_Provinces",IFERROR(VLOOKUP(J19,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K19="","All_Districts",IFERROR(VLOOKUP(K19,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F20="","",ROW()-3) | [18 empty] | IF(AQ20="","",AQ20) |  |  |  | IF(W20<>"",W20,IF(OR(T20="",V20=""),"",EDATE(T20,V20))) |  |  |  |  | IF(F20="","",IF(COUNT(AI20:AV20)=0,IF(AA20="","Not started",AA20),SUBSTITUTE(LOOKUP(2,1/(AI20:AV20<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F20="",COUNT(AI20:AV20)=0),"",TODAY()-LOOKUP(2,1/(AI20:AV20<>""),AI20:AV20)) | IF(OR(F20="",COUNT(AI20:AV20)<2),"",LOOKUP(2,1/(AI20:AV20<>""),AI20:AV20)-MIN(AI20:AV20)) | IF(OR(AD20="",AC20="Not started",AC20=""),"",IFERROR(AD20-IF(VLOOKUP(AC20,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC20,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F20="","",IF(OR(AA20="Cancelled",AC20="Cancelled"),"Cancelled",IF(OR(AC20="Completed / Handover",Y20<>"",Z20>=100),"Completed — on track",IF(O20="Not awarded",IF(U20="",IF(X20="","No planned date",IF(TODAY()>X20,"Behind — past planned date",IF(X20-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U20,"Behind — award date passed",IF(U20-TODAY()<=30,"At risk — close to off track","On track"))),IF(X20="","No planned date",IF(AND(TODAY()>X20,OR(Z20="",Z20<100)),"Behind — past end date",IF(AND(T20<>"",X20<>"",Z20<>"",(Z20<100),((TODAY()-T20)/MAX(X20-T20,1)*100)-Z20>15),"Behind — progress lag",IF(AND(X20-TODAY()<=30,X20-TODAY()>=0,OR(Z20="",Z20<90)),"At risk — close to off track","On track")))))))) | IF(OR(F20="",AC20="Completed / Handover",AC20="Cancelled"),"",IF(O20="Not awarded",IF(U20<>"",U20-TODAY(),IF(X20="","",X20-TODAY())),IF(X20="","",X20-TODAY()))) | [14 empty] | IF(OR(F20="",AJ20=""),"",IF(COUNT(AI20:AI20)=0,"",AJ20-LOOKUP(2,1/(AI20:AI20<>""),AI20:AI20))) | IF(OR(F20="",AK20=""),"",IF(COUNT(AI20:AJ20)=0,"",AK20-LOOKUP(2,1/(AI20:AJ20<>""),AI20:AJ20))) | IF(OR(F20="",AL20=""),"",IF(COUNT(AI20:AK20)=0,"",AL20-LOOKUP(2,1/(AI20:AK20<>""),AI20:AK20))) | IF(OR(F20="",AM20=""),"",IF(COUNT(AI20:AL20)=0,"",AM20-LOOKUP(2,1/(AI20:AL20<>""),AI20:AL20))) | IF(OR(F20="",AN20=""),"",IF(COUNT(AI20:AM20)=0,"",AN20-LOOKUP(2,1/(AI20:AM20<>""),AI20:AM20))) | IF(OR(F20="",AO20=""),"",IF(COUNT(AI20:AN20)=0,"",AO20-LOOKUP(2,1/(AI20:AN20<>""),AI20:AN20))) | IF(OR(F20="",AP20=""),"",IF(COUNT(AI20:AO20)=0,"",AP20-LOOKUP(2,1/(AI20:AO20<>""),AI20:AO20))) | IF(OR(F20="",AQ20=""),"",IF(COUNT(AI20:AP20)=0,"",AQ20-LOOKUP(2,1/(AI20:AP20<>""),AI20:AP20))) | IF(OR(F20="",AR20=""),"",IF(COUNT(AI20:AQ20)=0,"",AR20-LOOKUP(2,1/(AI20:AQ20<>""),AI20:AQ20))) | IF(OR(F20="",AS20=""),"",IF(COUNT(AI20:AR20)=0,"",AS20-LOOKUP(2,1/(AI20:AR20<>""),AI20:AR20))) | IF(OR(F20="",AT20=""),"",IF(COUNT(AI20:AS20)=0,"",AT20-LOOKUP(2,1/(AI20:AS20<>""),AI20:AS20))) | IF(OR(F20="",AU20=""),"",IF(COUNT(AI20:AT20)=0,"",AU20-LOOKUP(2,1/(AI20:AT20<>""),AI20:AT20))) | IF(OR(F20="",AV20=""),"",IF(COUNT(AI20:AU20)=0,"",AV20-LOOKUP(2,1/(AI20:AU20<>""),AI20:AU20))) | IF(J20="","All_Provinces",IFERROR(VLOOKUP(J20,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K20="","All_Districts",IFERROR(VLOOKUP(K20,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F21="","",ROW()-3) | [18 empty] | IF(AQ21="","",AQ21) |  |  |  | IF(W21<>"",W21,IF(OR(T21="",V21=""),"",EDATE(T21,V21))) |  |  |  |  | IF(F21="","",IF(COUNT(AI21:AV21)=0,IF(AA21="","Not started",AA21),SUBSTITUTE(LOOKUP(2,1/(AI21:AV21<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F21="",COUNT(AI21:AV21)=0),"",TODAY()-LOOKUP(2,1/(AI21:AV21<>""),AI21:AV21)) | IF(OR(F21="",COUNT(AI21:AV21)<2),"",LOOKUP(2,1/(AI21:AV21<>""),AI21:AV21)-MIN(AI21:AV21)) | IF(OR(AD21="",AC21="Not started",AC21=""),"",IFERROR(AD21-IF(VLOOKUP(AC21,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC21,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F21="","",IF(OR(AA21="Cancelled",AC21="Cancelled"),"Cancelled",IF(OR(AC21="Completed / Handover",Y21<>"",Z21>=100),"Completed — on track",IF(O21="Not awarded",IF(U21="",IF(X21="","No planned date",IF(TODAY()>X21,"Behind — past planned date",IF(X21-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U21,"Behind — award date passed",IF(U21-TODAY()<=30,"At risk — close to off track","On track"))),IF(X21="","No planned date",IF(AND(TODAY()>X21,OR(Z21="",Z21<100)),"Behind — past end date",IF(AND(T21<>"",X21<>"",Z21<>"",(Z21<100),((TODAY()-T21)/MAX(X21-T21,1)*100)-Z21>15),"Behind — progress lag",IF(AND(X21-TODAY()<=30,X21-TODAY()>=0,OR(Z21="",Z21<90)),"At risk — close to off track","On track")))))))) | IF(OR(F21="",AC21="Completed / Handover",AC21="Cancelled"),"",IF(O21="Not awarded",IF(U21<>"",U21-TODAY(),IF(X21="","",X21-TODAY())),IF(X21="","",X21-TODAY()))) | [14 empty] | IF(OR(F21="",AJ21=""),"",IF(COUNT(AI21:AI21)=0,"",AJ21-LOOKUP(2,1/(AI21:AI21<>""),AI21:AI21))) | IF(OR(F21="",AK21=""),"",IF(COUNT(AI21:AJ21)=0,"",AK21-LOOKUP(2,1/(AI21:AJ21<>""),AI21:AJ21))) | IF(OR(F21="",AL21=""),"",IF(COUNT(AI21:AK21)=0,"",AL21-LOOKUP(2,1/(AI21:AK21<>""),AI21:AK21))) | IF(OR(F21="",AM21=""),"",IF(COUNT(AI21:AL21)=0,"",AM21-LOOKUP(2,1/(AI21:AL21<>""),AI21:AL21))) | IF(OR(F21="",AN21=""),"",IF(COUNT(AI21:AM21)=0,"",AN21-LOOKUP(2,1/(AI21:AM21<>""),AI21:AM21))) | IF(OR(F21="",AO21=""),"",IF(COUNT(AI21:AN21)=0,"",AO21-LOOKUP(2,1/(AI21:AN21<>""),AI21:AN21))) | IF(OR(F21="",AP21=""),"",IF(COUNT(AI21:AO21)=0,"",AP21-LOOKUP(2,1/(AI21:AO21<>""),AI21:AO21))) | IF(OR(F21="",AQ21=""),"",IF(COUNT(AI21:AP21)=0,"",AQ21-LOOKUP(2,1/(AI21:AP21<>""),AI21:AP21))) | IF(OR(F21="",AR21=""),"",IF(COUNT(AI21:AQ21)=0,"",AR21-LOOKUP(2,1/(AI21:AQ21<>""),AI21:AQ21))) | IF(OR(F21="",AS21=""),"",IF(COUNT(AI21:AR21)=0,"",AS21-LOOKUP(2,1/(AI21:AR21<>""),AI21:AR21))) | IF(OR(F21="",AT21=""),"",IF(COUNT(AI21:AS21)=0,"",AT21-LOOKUP(2,1/(AI21:AS21<>""),AI21:AS21))) | IF(OR(F21="",AU21=""),"",IF(COUNT(AI21:AT21)=0,"",AU21-LOOKUP(2,1/(AI21:AT21<>""),AI21:AT21))) | IF(OR(F21="",AV21=""),"",IF(COUNT(AI21:AU21)=0,"",AV21-LOOKUP(2,1/(AI21:AU21<>""),AI21:AU21))) | IF(J21="","All_Provinces",IFERROR(VLOOKUP(J21,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K21="","All_Districts",IFERROR(VLOOKUP(K21,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F22="","",ROW()-3) | [18 empty] | IF(AQ22="","",AQ22) |  |  |  | IF(W22<>"",W22,IF(OR(T22="",V22=""),"",EDATE(T22,V22))) |  |  |  |  | IF(F22="","",IF(COUNT(AI22:AV22)=0,IF(AA22="","Not started",AA22),SUBSTITUTE(LOOKUP(2,1/(AI22:AV22<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F22="",COUNT(AI22:AV22)=0),"",TODAY()-LOOKUP(2,1/(AI22:AV22<>""),AI22:AV22)) | IF(OR(F22="",COUNT(AI22:AV22)<2),"",LOOKUP(2,1/(AI22:AV22<>""),AI22:AV22)-MIN(AI22:AV22)) | IF(OR(AD22="",AC22="Not started",AC22=""),"",IFERROR(AD22-IF(VLOOKUP(AC22,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC22,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F22="","",IF(OR(AA22="Cancelled",AC22="Cancelled"),"Cancelled",IF(OR(AC22="Completed / Handover",Y22<>"",Z22>=100),"Completed — on track",IF(O22="Not awarded",IF(U22="",IF(X22="","No planned date",IF(TODAY()>X22,"Behind — past planned date",IF(X22-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U22,"Behind — award date passed",IF(U22-TODAY()<=30,"At risk — close to off track","On track"))),IF(X22="","No planned date",IF(AND(TODAY()>X22,OR(Z22="",Z22<100)),"Behind — past end date",IF(AND(T22<>"",X22<>"",Z22<>"",(Z22<100),((TODAY()-T22)/MAX(X22-T22,1)*100)-Z22>15),"Behind — progress lag",IF(AND(X22-TODAY()<=30,X22-TODAY()>=0,OR(Z22="",Z22<90)),"At risk — close to off track","On track")))))))) | IF(OR(F22="",AC22="Completed / Handover",AC22="Cancelled"),"",IF(O22="Not awarded",IF(U22<>"",U22-TODAY(),IF(X22="","",X22-TODAY())),IF(X22="","",X22-TODAY()))) | [14 empty] | IF(OR(F22="",AJ22=""),"",IF(COUNT(AI22:AI22)=0,"",AJ22-LOOKUP(2,1/(AI22:AI22<>""),AI22:AI22))) | IF(OR(F22="",AK22=""),"",IF(COUNT(AI22:AJ22)=0,"",AK22-LOOKUP(2,1/(AI22:AJ22<>""),AI22:AJ22))) | IF(OR(F22="",AL22=""),"",IF(COUNT(AI22:AK22)=0,"",AL22-LOOKUP(2,1/(AI22:AK22<>""),AI22:AK22))) | IF(OR(F22="",AM22=""),"",IF(COUNT(AI22:AL22)=0,"",AM22-LOOKUP(2,1/(AI22:AL22<>""),AI22:AL22))) | IF(OR(F22="",AN22=""),"",IF(COUNT(AI22:AM22)=0,"",AN22-LOOKUP(2,1/(AI22:AM22<>""),AI22:AM22))) | IF(OR(F22="",AO22=""),"",IF(COUNT(AI22:AN22)=0,"",AO22-LOOKUP(2,1/(AI22:AN22<>""),AI22:AN22))) | IF(OR(F22="",AP22=""),"",IF(COUNT(AI22:AO22)=0,"",AP22-LOOKUP(2,1/(AI22:AO22<>""),AI22:AO22))) | IF(OR(F22="",AQ22=""),"",IF(COUNT(AI22:AP22)=0,"",AQ22-LOOKUP(2,1/(AI22:AP22<>""),AI22:AP22))) | IF(OR(F22="",AR22=""),"",IF(COUNT(AI22:AQ22)=0,"",AR22-LOOKUP(2,1/(AI22:AQ22<>""),AI22:AQ22))) | IF(OR(F22="",AS22=""),"",IF(COUNT(AI22:AR22)=0,"",AS22-LOOKUP(2,1/(AI22:AR22<>""),AI22:AR22))) | IF(OR(F22="",AT22=""),"",IF(COUNT(AI22:AS22)=0,"",AT22-LOOKUP(2,1/(AI22:AS22<>""),AI22:AS22))) | IF(OR(F22="",AU22=""),"",IF(COUNT(AI22:AT22)=0,"",AU22-LOOKUP(2,1/(AI22:AT22<>""),AI22:AT22))) | IF(OR(F22="",AV22=""),"",IF(COUNT(AI22:AU22)=0,"",AV22-LOOKUP(2,1/(AI22:AU22<>""),AI22:AU22))) | IF(J22="","All_Provinces",IFERROR(VLOOKUP(J22,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K22="","All_Districts",IFERROR(VLOOKUP(K22,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F23="","",ROW()-3) | [18 empty] | IF(AQ23="","",AQ23) |  |  |  | IF(W23<>"",W23,IF(OR(T23="",V23=""),"",EDATE(T23,V23))) |  |  |  |  | IF(F23="","",IF(COUNT(AI23:AV23)=0,IF(AA23="","Not started",AA23),SUBSTITUTE(LOOKUP(2,1/(AI23:AV23<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F23="",COUNT(AI23:AV23)=0),"",TODAY()-LOOKUP(2,1/(AI23:AV23<>""),AI23:AV23)) | IF(OR(F23="",COUNT(AI23:AV23)<2),"",LOOKUP(2,1/(AI23:AV23<>""),AI23:AV23)-MIN(AI23:AV23)) | IF(OR(AD23="",AC23="Not started",AC23=""),"",IFERROR(AD23-IF(VLOOKUP(AC23,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC23,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F23="","",IF(OR(AA23="Cancelled",AC23="Cancelled"),"Cancelled",IF(OR(AC23="Completed / Handover",Y23<>"",Z23>=100),"Completed — on track",IF(O23="Not awarded",IF(U23="",IF(X23="","No planned date",IF(TODAY()>X23,"Behind — past planned date",IF(X23-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U23,"Behind — award date passed",IF(U23-TODAY()<=30,"At risk — close to off track","On track"))),IF(X23="","No planned date",IF(AND(TODAY()>X23,OR(Z23="",Z23<100)),"Behind — past end date",IF(AND(T23<>"",X23<>"",Z23<>"",(Z23<100),((TODAY()-T23)/MAX(X23-T23,1)*100)-Z23>15),"Behind — progress lag",IF(AND(X23-TODAY()<=30,X23-TODAY()>=0,OR(Z23="",Z23<90)),"At risk — close to off track","On track")))))))) | IF(OR(F23="",AC23="Completed / Handover",AC23="Cancelled"),"",IF(O23="Not awarded",IF(U23<>"",U23-TODAY(),IF(X23="","",X23-TODAY())),IF(X23="","",X23-TODAY()))) | [14 empty] | IF(OR(F23="",AJ23=""),"",IF(COUNT(AI23:AI23)=0,"",AJ23-LOOKUP(2,1/(AI23:AI23<>""),AI23:AI23))) | IF(OR(F23="",AK23=""),"",IF(COUNT(AI23:AJ23)=0,"",AK23-LOOKUP(2,1/(AI23:AJ23<>""),AI23:AJ23))) | IF(OR(F23="",AL23=""),"",IF(COUNT(AI23:AK23)=0,"",AL23-LOOKUP(2,1/(AI23:AK23<>""),AI23:AK23))) | IF(OR(F23="",AM23=""),"",IF(COUNT(AI23:AL23)=0,"",AM23-LOOKUP(2,1/(AI23:AL23<>""),AI23:AL23))) | IF(OR(F23="",AN23=""),"",IF(COUNT(AI23:AM23)=0,"",AN23-LOOKUP(2,1/(AI23:AM23<>""),AI23:AM23))) | IF(OR(F23="",AO23=""),"",IF(COUNT(AI23:AN23)=0,"",AO23-LOOKUP(2,1/(AI23:AN23<>""),AI23:AN23))) | IF(OR(F23="",AP23=""),"",IF(COUNT(AI23:AO23)=0,"",AP23-LOOKUP(2,1/(AI23:AO23<>""),AI23:AO23))) | IF(OR(F23="",AQ23=""),"",IF(COUNT(AI23:AP23)=0,"",AQ23-LOOKUP(2,1/(AI23:AP23<>""),AI23:AP23))) | IF(OR(F23="",AR23=""),"",IF(COUNT(AI23:AQ23)=0,"",AR23-LOOKUP(2,1/(AI23:AQ23<>""),AI23:AQ23))) | IF(OR(F23="",AS23=""),"",IF(COUNT(AI23:AR23)=0,"",AS23-LOOKUP(2,1/(AI23:AR23<>""),AI23:AR23))) | IF(OR(F23="",AT23=""),"",IF(COUNT(AI23:AS23)=0,"",AT23-LOOKUP(2,1/(AI23:AS23<>""),AI23:AS23))) | IF(OR(F23="",AU23=""),"",IF(COUNT(AI23:AT23)=0,"",AU23-LOOKUP(2,1/(AI23:AT23<>""),AI23:AT23))) | IF(OR(F23="",AV23=""),"",IF(COUNT(AI23:AU23)=0,"",AV23-LOOKUP(2,1/(AI23:AU23<>""),AI23:AU23))) | IF(J23="","All_Provinces",IFERROR(VLOOKUP(J23,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K23="","All_Districts",IFERROR(VLOOKUP(K23,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F24="","",ROW()-3) | [18 empty] | IF(AQ24="","",AQ24) |  |  |  | IF(W24<>"",W24,IF(OR(T24="",V24=""),"",EDATE(T24,V24))) |  |  |  |  | IF(F24="","",IF(COUNT(AI24:AV24)=0,IF(AA24="","Not started",AA24),SUBSTITUTE(LOOKUP(2,1/(AI24:AV24<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F24="",COUNT(AI24:AV24)=0),"",TODAY()-LOOKUP(2,1/(AI24:AV24<>""),AI24:AV24)) | IF(OR(F24="",COUNT(AI24:AV24)<2),"",LOOKUP(2,1/(AI24:AV24<>""),AI24:AV24)-MIN(AI24:AV24)) | IF(OR(AD24="",AC24="Not started",AC24=""),"",IFERROR(AD24-IF(VLOOKUP(AC24,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC24,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F24="","",IF(OR(AA24="Cancelled",AC24="Cancelled"),"Cancelled",IF(OR(AC24="Completed / Handover",Y24<>"",Z24>=100),"Completed — on track",IF(O24="Not awarded",IF(U24="",IF(X24="","No planned date",IF(TODAY()>X24,"Behind — past planned date",IF(X24-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U24,"Behind — award date passed",IF(U24-TODAY()<=30,"At risk — close to off track","On track"))),IF(X24="","No planned date",IF(AND(TODAY()>X24,OR(Z24="",Z24<100)),"Behind — past end date",IF(AND(T24<>"",X24<>"",Z24<>"",(Z24<100),((TODAY()-T24)/MAX(X24-T24,1)*100)-Z24>15),"Behind — progress lag",IF(AND(X24-TODAY()<=30,X24-TODAY()>=0,OR(Z24="",Z24<90)),"At risk — close to off track","On track")))))))) | IF(OR(F24="",AC24="Completed / Handover",AC24="Cancelled"),"",IF(O24="Not awarded",IF(U24<>"",U24-TODAY(),IF(X24="","",X24-TODAY())),IF(X24="","",X24-TODAY()))) | [14 empty] | IF(OR(F24="",AJ24=""),"",IF(COUNT(AI24:AI24)=0,"",AJ24-LOOKUP(2,1/(AI24:AI24<>""),AI24:AI24))) | IF(OR(F24="",AK24=""),"",IF(COUNT(AI24:AJ24)=0,"",AK24-LOOKUP(2,1/(AI24:AJ24<>""),AI24:AJ24))) | IF(OR(F24="",AL24=""),"",IF(COUNT(AI24:AK24)=0,"",AL24-LOOKUP(2,1/(AI24:AK24<>""),AI24:AK24))) | IF(OR(F24="",AM24=""),"",IF(COUNT(AI24:AL24)=0,"",AM24-LOOKUP(2,1/(AI24:AL24<>""),AI24:AL24))) | IF(OR(F24="",AN24=""),"",IF(COUNT(AI24:AM24)=0,"",AN24-LOOKUP(2,1/(AI24:AM24<>""),AI24:AM24))) | IF(OR(F24="",AO24=""),"",IF(COUNT(AI24:AN24)=0,"",AO24-LOOKUP(2,1/(AI24:AN24<>""),AI24:AN24))) | IF(OR(F24="",AP24=""),"",IF(COUNT(AI24:AO24)=0,"",AP24-LOOKUP(2,1/(AI24:AO24<>""),AI24:AO24))) | IF(OR(F24="",AQ24=""),"",IF(COUNT(AI24:AP24)=0,"",AQ24-LOOKUP(2,1/(AI24:AP24<>""),AI24:AP24))) | IF(OR(F24="",AR24=""),"",IF(COUNT(AI24:AQ24)=0,"",AR24-LOOKUP(2,1/(AI24:AQ24<>""),AI24:AQ24))) | IF(OR(F24="",AS24=""),"",IF(COUNT(AI24:AR24)=0,"",AS24-LOOKUP(2,1/(AI24:AR24<>""),AI24:AR24))) | IF(OR(F24="",AT24=""),"",IF(COUNT(AI24:AS24)=0,"",AT24-LOOKUP(2,1/(AI24:AS24<>""),AI24:AS24))) | IF(OR(F24="",AU24=""),"",IF(COUNT(AI24:AT24)=0,"",AU24-LOOKUP(2,1/(AI24:AT24<>""),AI24:AT24))) | IF(OR(F24="",AV24=""),"",IF(COUNT(AI24:AU24)=0,"",AV24-LOOKUP(2,1/(AI24:AU24<>""),AI24:AU24))) | IF(J24="","All_Provinces",IFERROR(VLOOKUP(J24,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K24="","All_Districts",IFERROR(VLOOKUP(K24,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F25="","",ROW()-3) | [18 empty] | IF(AQ25="","",AQ25) |  |  |  | IF(W25<>"",W25,IF(OR(T25="",V25=""),"",EDATE(T25,V25))) |  |  |  |  | IF(F25="","",IF(COUNT(AI25:AV25)=0,IF(AA25="","Not started",AA25),SUBSTITUTE(LOOKUP(2,1/(AI25:AV25<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F25="",COUNT(AI25:AV25)=0),"",TODAY()-LOOKUP(2,1/(AI25:AV25<>""),AI25:AV25)) | IF(OR(F25="",COUNT(AI25:AV25)<2),"",LOOKUP(2,1/(AI25:AV25<>""),AI25:AV25)-MIN(AI25:AV25)) | IF(OR(AD25="",AC25="Not started",AC25=""),"",IFERROR(AD25-IF(VLOOKUP(AC25,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC25,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F25="","",IF(OR(AA25="Cancelled",AC25="Cancelled"),"Cancelled",IF(OR(AC25="Completed / Handover",Y25<>"",Z25>=100),"Completed — on track",IF(O25="Not awarded",IF(U25="",IF(X25="","No planned date",IF(TODAY()>X25,"Behind — past planned date",IF(X25-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U25,"Behind — award date passed",IF(U25-TODAY()<=30,"At risk — close to off track","On track"))),IF(X25="","No planned date",IF(AND(TODAY()>X25,OR(Z25="",Z25<100)),"Behind — past end date",IF(AND(T25<>"",X25<>"",Z25<>"",(Z25<100),((TODAY()-T25)/MAX(X25-T25,1)*100)-Z25>15),"Behind — progress lag",IF(AND(X25-TODAY()<=30,X25-TODAY()>=0,OR(Z25="",Z25<90)),"At risk — close to off track","On track")))))))) | IF(OR(F25="",AC25="Completed / Handover",AC25="Cancelled"),"",IF(O25="Not awarded",IF(U25<>"",U25-TODAY(),IF(X25="","",X25-TODAY())),IF(X25="","",X25-TODAY()))) | [14 empty] | IF(OR(F25="",AJ25=""),"",IF(COUNT(AI25:AI25)=0,"",AJ25-LOOKUP(2,1/(AI25:AI25<>""),AI25:AI25))) | IF(OR(F25="",AK25=""),"",IF(COUNT(AI25:AJ25)=0,"",AK25-LOOKUP(2,1/(AI25:AJ25<>""),AI25:AJ25))) | IF(OR(F25="",AL25=""),"",IF(COUNT(AI25:AK25)=0,"",AL25-LOOKUP(2,1/(AI25:AK25<>""),AI25:AK25))) | IF(OR(F25="",AM25=""),"",IF(COUNT(AI25:AL25)=0,"",AM25-LOOKUP(2,1/(AI25:AL25<>""),AI25:AL25))) | IF(OR(F25="",AN25=""),"",IF(COUNT(AI25:AM25)=0,"",AN25-LOOKUP(2,1/(AI25:AM25<>""),AI25:AM25))) | IF(OR(F25="",AO25=""),"",IF(COUNT(AI25:AN25)=0,"",AO25-LOOKUP(2,1/(AI25:AN25<>""),AI25:AN25))) | IF(OR(F25="",AP25=""),"",IF(COUNT(AI25:AO25)=0,"",AP25-LOOKUP(2,1/(AI25:AO25<>""),AI25:AO25))) | IF(OR(F25="",AQ25=""),"",IF(COUNT(AI25:AP25)=0,"",AQ25-LOOKUP(2,1/(AI25:AP25<>""),AI25:AP25))) | IF(OR(F25="",AR25=""),"",IF(COUNT(AI25:AQ25)=0,"",AR25-LOOKUP(2,1/(AI25:AQ25<>""),AI25:AQ25))) | IF(OR(F25="",AS25=""),"",IF(COUNT(AI25:AR25)=0,"",AS25-LOOKUP(2,1/(AI25:AR25<>""),AI25:AR25))) | IF(OR(F25="",AT25=""),"",IF(COUNT(AI25:AS25)=0,"",AT25-LOOKUP(2,1/(AI25:AS25<>""),AI25:AS25))) | IF(OR(F25="",AU25=""),"",IF(COUNT(AI25:AT25)=0,"",AU25-LOOKUP(2,1/(AI25:AT25<>""),AI25:AT25))) | IF(OR(F25="",AV25=""),"",IF(COUNT(AI25:AU25)=0,"",AV25-LOOKUP(2,1/(AI25:AU25<>""),AI25:AU25))) | IF(J25="","All_Provinces",IFERROR(VLOOKUP(J25,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K25="","All_Districts",IFERROR(VLOOKUP(K25,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F26="","",ROW()-3) | [18 empty] | IF(AQ26="","",AQ26) |  |  |  | IF(W26<>"",W26,IF(OR(T26="",V26=""),"",EDATE(T26,V26))) |  |  |  |  | IF(F26="","",IF(COUNT(AI26:AV26)=0,IF(AA26="","Not started",AA26),SUBSTITUTE(LOOKUP(2,1/(AI26:AV26<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F26="",COUNT(AI26:AV26)=0),"",TODAY()-LOOKUP(2,1/(AI26:AV26<>""),AI26:AV26)) | IF(OR(F26="",COUNT(AI26:AV26)<2),"",LOOKUP(2,1/(AI26:AV26<>""),AI26:AV26)-MIN(AI26:AV26)) | IF(OR(AD26="",AC26="Not started",AC26=""),"",IFERROR(AD26-IF(VLOOKUP(AC26,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC26,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F26="","",IF(OR(AA26="Cancelled",AC26="Cancelled"),"Cancelled",IF(OR(AC26="Completed / Handover",Y26<>"",Z26>=100),"Completed — on track",IF(O26="Not awarded",IF(U26="",IF(X26="","No planned date",IF(TODAY()>X26,"Behind — past planned date",IF(X26-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U26,"Behind — award date passed",IF(U26-TODAY()<=30,"At risk — close to off track","On track"))),IF(X26="","No planned date",IF(AND(TODAY()>X26,OR(Z26="",Z26<100)),"Behind — past end date",IF(AND(T26<>"",X26<>"",Z26<>"",(Z26<100),((TODAY()-T26)/MAX(X26-T26,1)*100)-Z26>15),"Behind — progress lag",IF(AND(X26-TODAY()<=30,X26-TODAY()>=0,OR(Z26="",Z26<90)),"At risk — close to off track","On track")))))))) | IF(OR(F26="",AC26="Completed / Handover",AC26="Cancelled"),"",IF(O26="Not awarded",IF(U26<>"",U26-TODAY(),IF(X26="","",X26-TODAY())),IF(X26="","",X26-TODAY()))) | [14 empty] | IF(OR(F26="",AJ26=""),"",IF(COUNT(AI26:AI26)=0,"",AJ26-LOOKUP(2,1/(AI26:AI26<>""),AI26:AI26))) | IF(OR(F26="",AK26=""),"",IF(COUNT(AI26:AJ26)=0,"",AK26-LOOKUP(2,1/(AI26:AJ26<>""),AI26:AJ26))) | IF(OR(F26="",AL26=""),"",IF(COUNT(AI26:AK26)=0,"",AL26-LOOKUP(2,1/(AI26:AK26<>""),AI26:AK26))) | IF(OR(F26="",AM26=""),"",IF(COUNT(AI26:AL26)=0,"",AM26-LOOKUP(2,1/(AI26:AL26<>""),AI26:AL26))) | IF(OR(F26="",AN26=""),"",IF(COUNT(AI26:AM26)=0,"",AN26-LOOKUP(2,1/(AI26:AM26<>""),AI26:AM26))) | IF(OR(F26="",AO26=""),"",IF(COUNT(AI26:AN26)=0,"",AO26-LOOKUP(2,1/(AI26:AN26<>""),AI26:AN26))) | IF(OR(F26="",AP26=""),"",IF(COUNT(AI26:AO26)=0,"",AP26-LOOKUP(2,1/(AI26:AO26<>""),AI26:AO26))) | IF(OR(F26="",AQ26=""),"",IF(COUNT(AI26:AP26)=0,"",AQ26-LOOKUP(2,1/(AI26:AP26<>""),AI26:AP26))) | IF(OR(F26="",AR26=""),"",IF(COUNT(AI26:AQ26)=0,"",AR26-LOOKUP(2,1/(AI26:AQ26<>""),AI26:AQ26))) | IF(OR(F26="",AS26=""),"",IF(COUNT(AI26:AR26)=0,"",AS26-LOOKUP(2,1/(AI26:AR26<>""),AI26:AR26))) | IF(OR(F26="",AT26=""),"",IF(COUNT(AI26:AS26)=0,"",AT26-LOOKUP(2,1/(AI26:AS26<>""),AI26:AS26))) | IF(OR(F26="",AU26=""),"",IF(COUNT(AI26:AT26)=0,"",AU26-LOOKUP(2,1/(AI26:AT26<>""),AI26:AT26))) | IF(OR(F26="",AV26=""),"",IF(COUNT(AI26:AU26)=0,"",AV26-LOOKUP(2,1/(AI26:AU26<>""),AI26:AU26))) | IF(J26="","All_Provinces",IFERROR(VLOOKUP(J26,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K26="","All_Districts",IFERROR(VLOOKUP(K26,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F27="","",ROW()-3) | [18 empty] | IF(AQ27="","",AQ27) |  |  |  | IF(W27<>"",W27,IF(OR(T27="",V27=""),"",EDATE(T27,V27))) |  |  |  |  | IF(F27="","",IF(COUNT(AI27:AV27)=0,IF(AA27="","Not started",AA27),SUBSTITUTE(LOOKUP(2,1/(AI27:AV27<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F27="",COUNT(AI27:AV27)=0),"",TODAY()-LOOKUP(2,1/(AI27:AV27<>""),AI27:AV27)) | IF(OR(F27="",COUNT(AI27:AV27)<2),"",LOOKUP(2,1/(AI27:AV27<>""),AI27:AV27)-MIN(AI27:AV27)) | IF(OR(AD27="",AC27="Not started",AC27=""),"",IFERROR(AD27-IF(VLOOKUP(AC27,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC27,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F27="","",IF(OR(AA27="Cancelled",AC27="Cancelled"),"Cancelled",IF(OR(AC27="Completed / Handover",Y27<>"",Z27>=100),"Completed — on track",IF(O27="Not awarded",IF(U27="",IF(X27="","No planned date",IF(TODAY()>X27,"Behind — past planned date",IF(X27-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U27,"Behind — award date passed",IF(U27-TODAY()<=30,"At risk — close to off track","On track"))),IF(X27="","No planned date",IF(AND(TODAY()>X27,OR(Z27="",Z27<100)),"Behind — past end date",IF(AND(T27<>"",X27<>"",Z27<>"",(Z27<100),((TODAY()-T27)/MAX(X27-T27,1)*100)-Z27>15),"Behind — progress lag",IF(AND(X27-TODAY()<=30,X27-TODAY()>=0,OR(Z27="",Z27<90)),"At risk — close to off track","On track")))))))) | IF(OR(F27="",AC27="Completed / Handover",AC27="Cancelled"),"",IF(O27="Not awarded",IF(U27<>"",U27-TODAY(),IF(X27="","",X27-TODAY())),IF(X27="","",X27-TODAY()))) | [14 empty] | IF(OR(F27="",AJ27=""),"",IF(COUNT(AI27:AI27)=0,"",AJ27-LOOKUP(2,1/(AI27:AI27<>""),AI27:AI27))) | IF(OR(F27="",AK27=""),"",IF(COUNT(AI27:AJ27)=0,"",AK27-LOOKUP(2,1/(AI27:AJ27<>""),AI27:AJ27))) | IF(OR(F27="",AL27=""),"",IF(COUNT(AI27:AK27)=0,"",AL27-LOOKUP(2,1/(AI27:AK27<>""),AI27:AK27))) | IF(OR(F27="",AM27=""),"",IF(COUNT(AI27:AL27)=0,"",AM27-LOOKUP(2,1/(AI27:AL27<>""),AI27:AL27))) | IF(OR(F27="",AN27=""),"",IF(COUNT(AI27:AM27)=0,"",AN27-LOOKUP(2,1/(AI27:AM27<>""),AI27:AM27))) | IF(OR(F27="",AO27=""),"",IF(COUNT(AI27:AN27)=0,"",AO27-LOOKUP(2,1/(AI27:AN27<>""),AI27:AN27))) | IF(OR(F27="",AP27=""),"",IF(COUNT(AI27:AO27)=0,"",AP27-LOOKUP(2,1/(AI27:AO27<>""),AI27:AO27))) | IF(OR(F27="",AQ27=""),"",IF(COUNT(AI27:AP27)=0,"",AQ27-LOOKUP(2,1/(AI27:AP27<>""),AI27:AP27))) | IF(OR(F27="",AR27=""),"",IF(COUNT(AI27:AQ27)=0,"",AR27-LOOKUP(2,1/(AI27:AQ27<>""),AI27:AQ27))) | IF(OR(F27="",AS27=""),"",IF(COUNT(AI27:AR27)=0,"",AS27-LOOKUP(2,1/(AI27:AR27<>""),AI27:AR27))) | IF(OR(F27="",AT27=""),"",IF(COUNT(AI27:AS27)=0,"",AT27-LOOKUP(2,1/(AI27:AS27<>""),AI27:AS27))) | IF(OR(F27="",AU27=""),"",IF(COUNT(AI27:AT27)=0,"",AU27-LOOKUP(2,1/(AI27:AT27<>""),AI27:AT27))) | IF(OR(F27="",AV27=""),"",IF(COUNT(AI27:AU27)=0,"",AV27-LOOKUP(2,1/(AI27:AU27<>""),AI27:AU27))) | IF(J27="","All_Provinces",IFERROR(VLOOKUP(J27,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K27="","All_Districts",IFERROR(VLOOKUP(K27,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F28="","",ROW()-3) | [18 empty] | IF(AQ28="","",AQ28) |  |  |  | IF(W28<>"",W28,IF(OR(T28="",V28=""),"",EDATE(T28,V28))) |  |  |  |  | IF(F28="","",IF(COUNT(AI28:AV28)=0,IF(AA28="","Not started",AA28),SUBSTITUTE(LOOKUP(2,1/(AI28:AV28<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F28="",COUNT(AI28:AV28)=0),"",TODAY()-LOOKUP(2,1/(AI28:AV28<>""),AI28:AV28)) | IF(OR(F28="",COUNT(AI28:AV28)<2),"",LOOKUP(2,1/(AI28:AV28<>""),AI28:AV28)-MIN(AI28:AV28)) | IF(OR(AD28="",AC28="Not started",AC28=""),"",IFERROR(AD28-IF(VLOOKUP(AC28,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC28,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F28="","",IF(OR(AA28="Cancelled",AC28="Cancelled"),"Cancelled",IF(OR(AC28="Completed / Handover",Y28<>"",Z28>=100),"Completed — on track",IF(O28="Not awarded",IF(U28="",IF(X28="","No planned date",IF(TODAY()>X28,"Behind — past planned date",IF(X28-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U28,"Behind — award date passed",IF(U28-TODAY()<=30,"At risk — close to off track","On track"))),IF(X28="","No planned date",IF(AND(TODAY()>X28,OR(Z28="",Z28<100)),"Behind — past end date",IF(AND(T28<>"",X28<>"",Z28<>"",(Z28<100),((TODAY()-T28)/MAX(X28-T28,1)*100)-Z28>15),"Behind — progress lag",IF(AND(X28-TODAY()<=30,X28-TODAY()>=0,OR(Z28="",Z28<90)),"At risk — close to off track","On track")))))))) | IF(OR(F28="",AC28="Completed / Handover",AC28="Cancelled"),"",IF(O28="Not awarded",IF(U28<>"",U28-TODAY(),IF(X28="","",X28-TODAY())),IF(X28="","",X28-TODAY()))) | [14 empty] | IF(OR(F28="",AJ28=""),"",IF(COUNT(AI28:AI28)=0,"",AJ28-LOOKUP(2,1/(AI28:AI28<>""),AI28:AI28))) | IF(OR(F28="",AK28=""),"",IF(COUNT(AI28:AJ28)=0,"",AK28-LOOKUP(2,1/(AI28:AJ28<>""),AI28:AJ28))) | IF(OR(F28="",AL28=""),"",IF(COUNT(AI28:AK28)=0,"",AL28-LOOKUP(2,1/(AI28:AK28<>""),AI28:AK28))) | IF(OR(F28="",AM28=""),"",IF(COUNT(AI28:AL28)=0,"",AM28-LOOKUP(2,1/(AI28:AL28<>""),AI28:AL28))) | IF(OR(F28="",AN28=""),"",IF(COUNT(AI28:AM28)=0,"",AN28-LOOKUP(2,1/(AI28:AM28<>""),AI28:AM28))) | IF(OR(F28="",AO28=""),"",IF(COUNT(AI28:AN28)=0,"",AO28-LOOKUP(2,1/(AI28:AN28<>""),AI28:AN28))) | IF(OR(F28="",AP28=""),"",IF(COUNT(AI28:AO28)=0,"",AP28-LOOKUP(2,1/(AI28:AO28<>""),AI28:AO28))) | IF(OR(F28="",AQ28=""),"",IF(COUNT(AI28:AP28)=0,"",AQ28-LOOKUP(2,1/(AI28:AP28<>""),AI28:AP28))) | IF(OR(F28="",AR28=""),"",IF(COUNT(AI28:AQ28)=0,"",AR28-LOOKUP(2,1/(AI28:AQ28<>""),AI28:AQ28))) | IF(OR(F28="",AS28=""),"",IF(COUNT(AI28:AR28)=0,"",AS28-LOOKUP(2,1/(AI28:AR28<>""),AI28:AR28))) | IF(OR(F28="",AT28=""),"",IF(COUNT(AI28:AS28)=0,"",AT28-LOOKUP(2,1/(AI28:AS28<>""),AI28:AS28))) | IF(OR(F28="",AU28=""),"",IF(COUNT(AI28:AT28)=0,"",AU28-LOOKUP(2,1/(AI28:AT28<>""),AI28:AT28))) | IF(OR(F28="",AV28=""),"",IF(COUNT(AI28:AU28)=0,"",AV28-LOOKUP(2,1/(AI28:AU28<>""),AI28:AU28))) | IF(J28="","All_Provinces",IFERROR(VLOOKUP(J28,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K28="","All_Districts",IFERROR(VLOOKUP(K28,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F29="","",ROW()-3) | [18 empty] | IF(AQ29="","",AQ29) |  |  |  | IF(W29<>"",W29,IF(OR(T29="",V29=""),"",EDATE(T29,V29))) |  |  |  |  | IF(F29="","",IF(COUNT(AI29:AV29)=0,IF(AA29="","Not started",AA29),SUBSTITUTE(LOOKUP(2,1/(AI29:AV29<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F29="",COUNT(AI29:AV29)=0),"",TODAY()-LOOKUP(2,1/(AI29:AV29<>""),AI29:AV29)) | IF(OR(F29="",COUNT(AI29:AV29)<2),"",LOOKUP(2,1/(AI29:AV29<>""),AI29:AV29)-MIN(AI29:AV29)) | IF(OR(AD29="",AC29="Not started",AC29=""),"",IFERROR(AD29-IF(VLOOKUP(AC29,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC29,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F29="","",IF(OR(AA29="Cancelled",AC29="Cancelled"),"Cancelled",IF(OR(AC29="Completed / Handover",Y29<>"",Z29>=100),"Completed — on track",IF(O29="Not awarded",IF(U29="",IF(X29="","No planned date",IF(TODAY()>X29,"Behind — past planned date",IF(X29-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U29,"Behind — award date passed",IF(U29-TODAY()<=30,"At risk — close to off track","On track"))),IF(X29="","No planned date",IF(AND(TODAY()>X29,OR(Z29="",Z29<100)),"Behind — past end date",IF(AND(T29<>"",X29<>"",Z29<>"",(Z29<100),((TODAY()-T29)/MAX(X29-T29,1)*100)-Z29>15),"Behind — progress lag",IF(AND(X29-TODAY()<=30,X29-TODAY()>=0,OR(Z29="",Z29<90)),"At risk — close to off track","On track")))))))) | IF(OR(F29="",AC29="Completed / Handover",AC29="Cancelled"),"",IF(O29="Not awarded",IF(U29<>"",U29-TODAY(),IF(X29="","",X29-TODAY())),IF(X29="","",X29-TODAY()))) | [14 empty] | IF(OR(F29="",AJ29=""),"",IF(COUNT(AI29:AI29)=0,"",AJ29-LOOKUP(2,1/(AI29:AI29<>""),AI29:AI29))) | IF(OR(F29="",AK29=""),"",IF(COUNT(AI29:AJ29)=0,"",AK29-LOOKUP(2,1/(AI29:AJ29<>""),AI29:AJ29))) | IF(OR(F29="",AL29=""),"",IF(COUNT(AI29:AK29)=0,"",AL29-LOOKUP(2,1/(AI29:AK29<>""),AI29:AK29))) | IF(OR(F29="",AM29=""),"",IF(COUNT(AI29:AL29)=0,"",AM29-LOOKUP(2,1/(AI29:AL29<>""),AI29:AL29))) | IF(OR(F29="",AN29=""),"",IF(COUNT(AI29:AM29)=0,"",AN29-LOOKUP(2,1/(AI29:AM29<>""),AI29:AM29))) | IF(OR(F29="",AO29=""),"",IF(COUNT(AI29:AN29)=0,"",AO29-LOOKUP(2,1/(AI29:AN29<>""),AI29:AN29))) | IF(OR(F29="",AP29=""),"",IF(COUNT(AI29:AO29)=0,"",AP29-LOOKUP(2,1/(AI29:AO29<>""),AI29:AO29))) | IF(OR(F29="",AQ29=""),"",IF(COUNT(AI29:AP29)=0,"",AQ29-LOOKUP(2,1/(AI29:AP29<>""),AI29:AP29))) | IF(OR(F29="",AR29=""),"",IF(COUNT(AI29:AQ29)=0,"",AR29-LOOKUP(2,1/(AI29:AQ29<>""),AI29:AQ29))) | IF(OR(F29="",AS29=""),"",IF(COUNT(AI29:AR29)=0,"",AS29-LOOKUP(2,1/(AI29:AR29<>""),AI29:AR29))) | IF(OR(F29="",AT29=""),"",IF(COUNT(AI29:AS29)=0,"",AT29-LOOKUP(2,1/(AI29:AS29<>""),AI29:AS29))) | IF(OR(F29="",AU29=""),"",IF(COUNT(AI29:AT29)=0,"",AU29-LOOKUP(2,1/(AI29:AT29<>""),AI29:AT29))) | IF(OR(F29="",AV29=""),"",IF(COUNT(AI29:AU29)=0,"",AV29-LOOKUP(2,1/(AI29:AU29<>""),AI29:AU29))) | IF(J29="","All_Provinces",IFERROR(VLOOKUP(J29,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K29="","All_Districts",IFERROR(VLOOKUP(K29,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F30="","",ROW()-3) | [18 empty] | IF(AQ30="","",AQ30) |  |  |  | IF(W30<>"",W30,IF(OR(T30="",V30=""),"",EDATE(T30,V30))) |  |  |  |  | IF(F30="","",IF(COUNT(AI30:AV30)=0,IF(AA30="","Not started",AA30),SUBSTITUTE(LOOKUP(2,1/(AI30:AV30<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F30="",COUNT(AI30:AV30)=0),"",TODAY()-LOOKUP(2,1/(AI30:AV30<>""),AI30:AV30)) | IF(OR(F30="",COUNT(AI30:AV30)<2),"",LOOKUP(2,1/(AI30:AV30<>""),AI30:AV30)-MIN(AI30:AV30)) | IF(OR(AD30="",AC30="Not started",AC30=""),"",IFERROR(AD30-IF(VLOOKUP(AC30,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC30,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F30="","",IF(OR(AA30="Cancelled",AC30="Cancelled"),"Cancelled",IF(OR(AC30="Completed / Handover",Y30<>"",Z30>=100),"Completed — on track",IF(O30="Not awarded",IF(U30="",IF(X30="","No planned date",IF(TODAY()>X30,"Behind — past planned date",IF(X30-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U30,"Behind — award date passed",IF(U30-TODAY()<=30,"At risk — close to off track","On track"))),IF(X30="","No planned date",IF(AND(TODAY()>X30,OR(Z30="",Z30<100)),"Behind — past end date",IF(AND(T30<>"",X30<>"",Z30<>"",(Z30<100),((TODAY()-T30)/MAX(X30-T30,1)*100)-Z30>15),"Behind — progress lag",IF(AND(X30-TODAY()<=30,X30-TODAY()>=0,OR(Z30="",Z30<90)),"At risk — close to off track","On track")))))))) | IF(OR(F30="",AC30="Completed / Handover",AC30="Cancelled"),"",IF(O30="Not awarded",IF(U30<>"",U30-TODAY(),IF(X30="","",X30-TODAY())),IF(X30="","",X30-TODAY()))) | [14 empty] | IF(OR(F30="",AJ30=""),"",IF(COUNT(AI30:AI30)=0,"",AJ30-LOOKUP(2,1/(AI30:AI30<>""),AI30:AI30))) | IF(OR(F30="",AK30=""),"",IF(COUNT(AI30:AJ30)=0,"",AK30-LOOKUP(2,1/(AI30:AJ30<>""),AI30:AJ30))) | IF(OR(F30="",AL30=""),"",IF(COUNT(AI30:AK30)=0,"",AL30-LOOKUP(2,1/(AI30:AK30<>""),AI30:AK30))) | IF(OR(F30="",AM30=""),"",IF(COUNT(AI30:AL30)=0,"",AM30-LOOKUP(2,1/(AI30:AL30<>""),AI30:AL30))) | IF(OR(F30="",AN30=""),"",IF(COUNT(AI30:AM30)=0,"",AN30-LOOKUP(2,1/(AI30:AM30<>""),AI30:AM30))) | IF(OR(F30="",AO30=""),"",IF(COUNT(AI30:AN30)=0,"",AO30-LOOKUP(2,1/(AI30:AN30<>""),AI30:AN30))) | IF(OR(F30="",AP30=""),"",IF(COUNT(AI30:AO30)=0,"",AP30-LOOKUP(2,1/(AI30:AO30<>""),AI30:AO30))) | IF(OR(F30="",AQ30=""),"",IF(COUNT(AI30:AP30)=0,"",AQ30-LOOKUP(2,1/(AI30:AP30<>""),AI30:AP30))) | IF(OR(F30="",AR30=""),"",IF(COUNT(AI30:AQ30)=0,"",AR30-LOOKUP(2,1/(AI30:AQ30<>""),AI30:AQ30))) | IF(OR(F30="",AS30=""),"",IF(COUNT(AI30:AR30)=0,"",AS30-LOOKUP(2,1/(AI30:AR30<>""),AI30:AR30))) | IF(OR(F30="",AT30=""),"",IF(COUNT(AI30:AS30)=0,"",AT30-LOOKUP(2,1/(AI30:AS30<>""),AI30:AS30))) | IF(OR(F30="",AU30=""),"",IF(COUNT(AI30:AT30)=0,"",AU30-LOOKUP(2,1/(AI30:AT30<>""),AI30:AT30))) | IF(OR(F30="",AV30=""),"",IF(COUNT(AI30:AU30)=0,"",AV30-LOOKUP(2,1/(AI30:AU30<>""),AI30:AU30))) | IF(J30="","All_Provinces",IFERROR(VLOOKUP(J30,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K30="","All_Districts",IFERROR(VLOOKUP(K30,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F31="","",ROW()-3) | [18 empty] | IF(AQ31="","",AQ31) |  |  |  | IF(W31<>"",W31,IF(OR(T31="",V31=""),"",EDATE(T31,V31))) |  |  |  |  | IF(F31="","",IF(COUNT(AI31:AV31)=0,IF(AA31="","Not started",AA31),SUBSTITUTE(LOOKUP(2,1/(AI31:AV31<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F31="",COUNT(AI31:AV31)=0),"",TODAY()-LOOKUP(2,1/(AI31:AV31<>""),AI31:AV31)) | IF(OR(F31="",COUNT(AI31:AV31)<2),"",LOOKUP(2,1/(AI31:AV31<>""),AI31:AV31)-MIN(AI31:AV31)) | IF(OR(AD31="",AC31="Not started",AC31=""),"",IFERROR(AD31-IF(VLOOKUP(AC31,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC31,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F31="","",IF(OR(AA31="Cancelled",AC31="Cancelled"),"Cancelled",IF(OR(AC31="Completed / Handover",Y31<>"",Z31>=100),"Completed — on track",IF(O31="Not awarded",IF(U31="",IF(X31="","No planned date",IF(TODAY()>X31,"Behind — past planned date",IF(X31-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U31,"Behind — award date passed",IF(U31-TODAY()<=30,"At risk — close to off track","On track"))),IF(X31="","No planned date",IF(AND(TODAY()>X31,OR(Z31="",Z31<100)),"Behind — past end date",IF(AND(T31<>"",X31<>"",Z31<>"",(Z31<100),((TODAY()-T31)/MAX(X31-T31,1)*100)-Z31>15),"Behind — progress lag",IF(AND(X31-TODAY()<=30,X31-TODAY()>=0,OR(Z31="",Z31<90)),"At risk — close to off track","On track")))))))) | IF(OR(F31="",AC31="Completed / Handover",AC31="Cancelled"),"",IF(O31="Not awarded",IF(U31<>"",U31-TODAY(),IF(X31="","",X31-TODAY())),IF(X31="","",X31-TODAY()))) | [14 empty] | IF(OR(F31="",AJ31=""),"",IF(COUNT(AI31:AI31)=0,"",AJ31-LOOKUP(2,1/(AI31:AI31<>""),AI31:AI31))) | IF(OR(F31="",AK31=""),"",IF(COUNT(AI31:AJ31)=0,"",AK31-LOOKUP(2,1/(AI31:AJ31<>""),AI31:AJ31))) | IF(OR(F31="",AL31=""),"",IF(COUNT(AI31:AK31)=0,"",AL31-LOOKUP(2,1/(AI31:AK31<>""),AI31:AK31))) | IF(OR(F31="",AM31=""),"",IF(COUNT(AI31:AL31)=0,"",AM31-LOOKUP(2,1/(AI31:AL31<>""),AI31:AL31))) | IF(OR(F31="",AN31=""),"",IF(COUNT(AI31:AM31)=0,"",AN31-LOOKUP(2,1/(AI31:AM31<>""),AI31:AM31))) | IF(OR(F31="",AO31=""),"",IF(COUNT(AI31:AN31)=0,"",AO31-LOOKUP(2,1/(AI31:AN31<>""),AI31:AN31))) | IF(OR(F31="",AP31=""),"",IF(COUNT(AI31:AO31)=0,"",AP31-LOOKUP(2,1/(AI31:AO31<>""),AI31:AO31))) | IF(OR(F31="",AQ31=""),"",IF(COUNT(AI31:AP31)=0,"",AQ31-LOOKUP(2,1/(AI31:AP31<>""),AI31:AP31))) | IF(OR(F31="",AR31=""),"",IF(COUNT(AI31:AQ31)=0,"",AR31-LOOKUP(2,1/(AI31:AQ31<>""),AI31:AQ31))) | IF(OR(F31="",AS31=""),"",IF(COUNT(AI31:AR31)=0,"",AS31-LOOKUP(2,1/(AI31:AR31<>""),AI31:AR31))) | IF(OR(F31="",AT31=""),"",IF(COUNT(AI31:AS31)=0,"",AT31-LOOKUP(2,1/(AI31:AS31<>""),AI31:AS31))) | IF(OR(F31="",AU31=""),"",IF(COUNT(AI31:AT31)=0,"",AU31-LOOKUP(2,1/(AI31:AT31<>""),AI31:AT31))) | IF(OR(F31="",AV31=""),"",IF(COUNT(AI31:AU31)=0,"",AV31-LOOKUP(2,1/(AI31:AU31<>""),AI31:AU31))) | IF(J31="","All_Provinces",IFERROR(VLOOKUP(J31,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K31="","All_Districts",IFERROR(VLOOKUP(K31,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F32="","",ROW()-3) | [18 empty] | IF(AQ32="","",AQ32) |  |  |  | IF(W32<>"",W32,IF(OR(T32="",V32=""),"",EDATE(T32,V32))) |  |  |  |  | IF(F32="","",IF(COUNT(AI32:AV32)=0,IF(AA32="","Not started",AA32),SUBSTITUTE(LOOKUP(2,1/(AI32:AV32<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F32="",COUNT(AI32:AV32)=0),"",TODAY()-LOOKUP(2,1/(AI32:AV32<>""),AI32:AV32)) | IF(OR(F32="",COUNT(AI32:AV32)<2),"",LOOKUP(2,1/(AI32:AV32<>""),AI32:AV32)-MIN(AI32:AV32)) | IF(OR(AD32="",AC32="Not started",AC32=""),"",IFERROR(AD32-IF(VLOOKUP(AC32,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC32,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F32="","",IF(OR(AA32="Cancelled",AC32="Cancelled"),"Cancelled",IF(OR(AC32="Completed / Handover",Y32<>"",Z32>=100),"Completed — on track",IF(O32="Not awarded",IF(U32="",IF(X32="","No planned date",IF(TODAY()>X32,"Behind — past planned date",IF(X32-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U32,"Behind — award date passed",IF(U32-TODAY()<=30,"At risk — close to off track","On track"))),IF(X32="","No planned date",IF(AND(TODAY()>X32,OR(Z32="",Z32<100)),"Behind — past end date",IF(AND(T32<>"",X32<>"",Z32<>"",(Z32<100),((TODAY()-T32)/MAX(X32-T32,1)*100)-Z32>15),"Behind — progress lag",IF(AND(X32-TODAY()<=30,X32-TODAY()>=0,OR(Z32="",Z32<90)),"At risk — close to off track","On track")))))))) | IF(OR(F32="",AC32="Completed / Handover",AC32="Cancelled"),"",IF(O32="Not awarded",IF(U32<>"",U32-TODAY(),IF(X32="","",X32-TODAY())),IF(X32="","",X32-TODAY()))) | [14 empty] | IF(OR(F32="",AJ32=""),"",IF(COUNT(AI32:AI32)=0,"",AJ32-LOOKUP(2,1/(AI32:AI32<>""),AI32:AI32))) | IF(OR(F32="",AK32=""),"",IF(COUNT(AI32:AJ32)=0,"",AK32-LOOKUP(2,1/(AI32:AJ32<>""),AI32:AJ32))) | IF(OR(F32="",AL32=""),"",IF(COUNT(AI32:AK32)=0,"",AL32-LOOKUP(2,1/(AI32:AK32<>""),AI32:AK32))) | IF(OR(F32="",AM32=""),"",IF(COUNT(AI32:AL32)=0,"",AM32-LOOKUP(2,1/(AI32:AL32<>""),AI32:AL32))) | IF(OR(F32="",AN32=""),"",IF(COUNT(AI32:AM32)=0,"",AN32-LOOKUP(2,1/(AI32:AM32<>""),AI32:AM32))) | IF(OR(F32="",AO32=""),"",IF(COUNT(AI32:AN32)=0,"",AO32-LOOKUP(2,1/(AI32:AN32<>""),AI32:AN32))) | IF(OR(F32="",AP32=""),"",IF(COUNT(AI32:AO32)=0,"",AP32-LOOKUP(2,1/(AI32:AO32<>""),AI32:AO32))) | IF(OR(F32="",AQ32=""),"",IF(COUNT(AI32:AP32)=0,"",AQ32-LOOKUP(2,1/(AI32:AP32<>""),AI32:AP32))) | IF(OR(F32="",AR32=""),"",IF(COUNT(AI32:AQ32)=0,"",AR32-LOOKUP(2,1/(AI32:AQ32<>""),AI32:AQ32))) | IF(OR(F32="",AS32=""),"",IF(COUNT(AI32:AR32)=0,"",AS32-LOOKUP(2,1/(AI32:AR32<>""),AI32:AR32))) | IF(OR(F32="",AT32=""),"",IF(COUNT(AI32:AS32)=0,"",AT32-LOOKUP(2,1/(AI32:AS32<>""),AI32:AS32))) | IF(OR(F32="",AU32=""),"",IF(COUNT(AI32:AT32)=0,"",AU32-LOOKUP(2,1/(AI32:AT32<>""),AI32:AT32))) | IF(OR(F32="",AV32=""),"",IF(COUNT(AI32:AU32)=0,"",AV32-LOOKUP(2,1/(AI32:AU32<>""),AI32:AU32))) | IF(J32="","All_Provinces",IFERROR(VLOOKUP(J32,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K32="","All_Districts",IFERROR(VLOOKUP(K32,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F33="","",ROW()-3) | [18 empty] | IF(AQ33="","",AQ33) |  |  |  | IF(W33<>"",W33,IF(OR(T33="",V33=""),"",EDATE(T33,V33))) |  |  |  |  | IF(F33="","",IF(COUNT(AI33:AV33)=0,IF(AA33="","Not started",AA33),SUBSTITUTE(LOOKUP(2,1/(AI33:AV33<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F33="",COUNT(AI33:AV33)=0),"",TODAY()-LOOKUP(2,1/(AI33:AV33<>""),AI33:AV33)) | IF(OR(F33="",COUNT(AI33:AV33)<2),"",LOOKUP(2,1/(AI33:AV33<>""),AI33:AV33)-MIN(AI33:AV33)) | IF(OR(AD33="",AC33="Not started",AC33=""),"",IFERROR(AD33-IF(VLOOKUP(AC33,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC33,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F33="","",IF(OR(AA33="Cancelled",AC33="Cancelled"),"Cancelled",IF(OR(AC33="Completed / Handover",Y33<>"",Z33>=100),"Completed — on track",IF(O33="Not awarded",IF(U33="",IF(X33="","No planned date",IF(TODAY()>X33,"Behind — past planned date",IF(X33-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U33,"Behind — award date passed",IF(U33-TODAY()<=30,"At risk — close to off track","On track"))),IF(X33="","No planned date",IF(AND(TODAY()>X33,OR(Z33="",Z33<100)),"Behind — past end date",IF(AND(T33<>"",X33<>"",Z33<>"",(Z33<100),((TODAY()-T33)/MAX(X33-T33,1)*100)-Z33>15),"Behind — progress lag",IF(AND(X33-TODAY()<=30,X33-TODAY()>=0,OR(Z33="",Z33<90)),"At risk — close to off track","On track")))))))) | IF(OR(F33="",AC33="Completed / Handover",AC33="Cancelled"),"",IF(O33="Not awarded",IF(U33<>"",U33-TODAY(),IF(X33="","",X33-TODAY())),IF(X33="","",X33-TODAY()))) | [14 empty] | IF(OR(F33="",AJ33=""),"",IF(COUNT(AI33:AI33)=0,"",AJ33-LOOKUP(2,1/(AI33:AI33<>""),AI33:AI33))) | IF(OR(F33="",AK33=""),"",IF(COUNT(AI33:AJ33)=0,"",AK33-LOOKUP(2,1/(AI33:AJ33<>""),AI33:AJ33))) | IF(OR(F33="",AL33=""),"",IF(COUNT(AI33:AK33)=0,"",AL33-LOOKUP(2,1/(AI33:AK33<>""),AI33:AK33))) | IF(OR(F33="",AM33=""),"",IF(COUNT(AI33:AL33)=0,"",AM33-LOOKUP(2,1/(AI33:AL33<>""),AI33:AL33))) | IF(OR(F33="",AN33=""),"",IF(COUNT(AI33:AM33)=0,"",AN33-LOOKUP(2,1/(AI33:AM33<>""),AI33:AM33))) | IF(OR(F33="",AO33=""),"",IF(COUNT(AI33:AN33)=0,"",AO33-LOOKUP(2,1/(AI33:AN33<>""),AI33:AN33))) | IF(OR(F33="",AP33=""),"",IF(COUNT(AI33:AO33)=0,"",AP33-LOOKUP(2,1/(AI33:AO33<>""),AI33:AO33))) | IF(OR(F33="",AQ33=""),"",IF(COUNT(AI33:AP33)=0,"",AQ33-LOOKUP(2,1/(AI33:AP33<>""),AI33:AP33))) | IF(OR(F33="",AR33=""),"",IF(COUNT(AI33:AQ33)=0,"",AR33-LOOKUP(2,1/(AI33:AQ33<>""),AI33:AQ33))) | IF(OR(F33="",AS33=""),"",IF(COUNT(AI33:AR33)=0,"",AS33-LOOKUP(2,1/(AI33:AR33<>""),AI33:AR33))) | IF(OR(F33="",AT33=""),"",IF(COUNT(AI33:AS33)=0,"",AT33-LOOKUP(2,1/(AI33:AS33<>""),AI33:AS33))) | IF(OR(F33="",AU33=""),"",IF(COUNT(AI33:AT33)=0,"",AU33-LOOKUP(2,1/(AI33:AT33<>""),AI33:AT33))) | IF(OR(F33="",AV33=""),"",IF(COUNT(AI33:AU33)=0,"",AV33-LOOKUP(2,1/(AI33:AU33<>""),AI33:AU33))) | IF(J33="","All_Provinces",IFERROR(VLOOKUP(J33,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K33="","All_Districts",IFERROR(VLOOKUP(K33,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F34="","",ROW()-3) | [18 empty] | IF(AQ34="","",AQ34) |  |  |  | IF(W34<>"",W34,IF(OR(T34="",V34=""),"",EDATE(T34,V34))) |  |  |  |  | IF(F34="","",IF(COUNT(AI34:AV34)=0,IF(AA34="","Not started",AA34),SUBSTITUTE(LOOKUP(2,1/(AI34:AV34<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F34="",COUNT(AI34:AV34)=0),"",TODAY()-LOOKUP(2,1/(AI34:AV34<>""),AI34:AV34)) | IF(OR(F34="",COUNT(AI34:AV34)<2),"",LOOKUP(2,1/(AI34:AV34<>""),AI34:AV34)-MIN(AI34:AV34)) | IF(OR(AD34="",AC34="Not started",AC34=""),"",IFERROR(AD34-IF(VLOOKUP(AC34,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC34,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F34="","",IF(OR(AA34="Cancelled",AC34="Cancelled"),"Cancelled",IF(OR(AC34="Completed / Handover",Y34<>"",Z34>=100),"Completed — on track",IF(O34="Not awarded",IF(U34="",IF(X34="","No planned date",IF(TODAY()>X34,"Behind — past planned date",IF(X34-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U34,"Behind — award date passed",IF(U34-TODAY()<=30,"At risk — close to off track","On track"))),IF(X34="","No planned date",IF(AND(TODAY()>X34,OR(Z34="",Z34<100)),"Behind — past end date",IF(AND(T34<>"",X34<>"",Z34<>"",(Z34<100),((TODAY()-T34)/MAX(X34-T34,1)*100)-Z34>15),"Behind — progress lag",IF(AND(X34-TODAY()<=30,X34-TODAY()>=0,OR(Z34="",Z34<90)),"At risk — close to off track","On track")))))))) | IF(OR(F34="",AC34="Completed / Handover",AC34="Cancelled"),"",IF(O34="Not awarded",IF(U34<>"",U34-TODAY(),IF(X34="","",X34-TODAY())),IF(X34="","",X34-TODAY()))) | [14 empty] | IF(OR(F34="",AJ34=""),"",IF(COUNT(AI34:AI34)=0,"",AJ34-LOOKUP(2,1/(AI34:AI34<>""),AI34:AI34))) | IF(OR(F34="",AK34=""),"",IF(COUNT(AI34:AJ34)=0,"",AK34-LOOKUP(2,1/(AI34:AJ34<>""),AI34:AJ34))) | IF(OR(F34="",AL34=""),"",IF(COUNT(AI34:AK34)=0,"",AL34-LOOKUP(2,1/(AI34:AK34<>""),AI34:AK34))) | IF(OR(F34="",AM34=""),"",IF(COUNT(AI34:AL34)=0,"",AM34-LOOKUP(2,1/(AI34:AL34<>""),AI34:AL34))) | IF(OR(F34="",AN34=""),"",IF(COUNT(AI34:AM34)=0,"",AN34-LOOKUP(2,1/(AI34:AM34<>""),AI34:AM34))) | IF(OR(F34="",AO34=""),"",IF(COUNT(AI34:AN34)=0,"",AO34-LOOKUP(2,1/(AI34:AN34<>""),AI34:AN34))) | IF(OR(F34="",AP34=""),"",IF(COUNT(AI34:AO34)=0,"",AP34-LOOKUP(2,1/(AI34:AO34<>""),AI34:AO34))) | IF(OR(F34="",AQ34=""),"",IF(COUNT(AI34:AP34)=0,"",AQ34-LOOKUP(2,1/(AI34:AP34<>""),AI34:AP34))) | IF(OR(F34="",AR34=""),"",IF(COUNT(AI34:AQ34)=0,"",AR34-LOOKUP(2,1/(AI34:AQ34<>""),AI34:AQ34))) | IF(OR(F34="",AS34=""),"",IF(COUNT(AI34:AR34)=0,"",AS34-LOOKUP(2,1/(AI34:AR34<>""),AI34:AR34))) | IF(OR(F34="",AT34=""),"",IF(COUNT(AI34:AS34)=0,"",AT34-LOOKUP(2,1/(AI34:AS34<>""),AI34:AS34))) | IF(OR(F34="",AU34=""),"",IF(COUNT(AI34:AT34)=0,"",AU34-LOOKUP(2,1/(AI34:AT34<>""),AI34:AT34))) | IF(OR(F34="",AV34=""),"",IF(COUNT(AI34:AU34)=0,"",AV34-LOOKUP(2,1/(AI34:AU34<>""),AI34:AU34))) | IF(J34="","All_Provinces",IFERROR(VLOOKUP(J34,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K34="","All_Districts",IFERROR(VLOOKUP(K34,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F35="","",ROW()-3) | [18 empty] | IF(AQ35="","",AQ35) |  |  |  | IF(W35<>"",W35,IF(OR(T35="",V35=""),"",EDATE(T35,V35))) |  |  |  |  | IF(F35="","",IF(COUNT(AI35:AV35)=0,IF(AA35="","Not started",AA35),SUBSTITUTE(LOOKUP(2,1/(AI35:AV35<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F35="",COUNT(AI35:AV35)=0),"",TODAY()-LOOKUP(2,1/(AI35:AV35<>""),AI35:AV35)) | IF(OR(F35="",COUNT(AI35:AV35)<2),"",LOOKUP(2,1/(AI35:AV35<>""),AI35:AV35)-MIN(AI35:AV35)) | IF(OR(AD35="",AC35="Not started",AC35=""),"",IFERROR(AD35-IF(VLOOKUP(AC35,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC35,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F35="","",IF(OR(AA35="Cancelled",AC35="Cancelled"),"Cancelled",IF(OR(AC35="Completed / Handover",Y35<>"",Z35>=100),"Completed — on track",IF(O35="Not awarded",IF(U35="",IF(X35="","No planned date",IF(TODAY()>X35,"Behind — past planned date",IF(X35-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U35,"Behind — award date passed",IF(U35-TODAY()<=30,"At risk — close to off track","On track"))),IF(X35="","No planned date",IF(AND(TODAY()>X35,OR(Z35="",Z35<100)),"Behind — past end date",IF(AND(T35<>"",X35<>"",Z35<>"",(Z35<100),((TODAY()-T35)/MAX(X35-T35,1)*100)-Z35>15),"Behind — progress lag",IF(AND(X35-TODAY()<=30,X35-TODAY()>=0,OR(Z35="",Z35<90)),"At risk — close to off track","On track")))))))) | IF(OR(F35="",AC35="Completed / Handover",AC35="Cancelled"),"",IF(O35="Not awarded",IF(U35<>"",U35-TODAY(),IF(X35="","",X35-TODAY())),IF(X35="","",X35-TODAY()))) | [14 empty] | IF(OR(F35="",AJ35=""),"",IF(COUNT(AI35:AI35)=0,"",AJ35-LOOKUP(2,1/(AI35:AI35<>""),AI35:AI35))) | IF(OR(F35="",AK35=""),"",IF(COUNT(AI35:AJ35)=0,"",AK35-LOOKUP(2,1/(AI35:AJ35<>""),AI35:AJ35))) | IF(OR(F35="",AL35=""),"",IF(COUNT(AI35:AK35)=0,"",AL35-LOOKUP(2,1/(AI35:AK35<>""),AI35:AK35))) | IF(OR(F35="",AM35=""),"",IF(COUNT(AI35:AL35)=0,"",AM35-LOOKUP(2,1/(AI35:AL35<>""),AI35:AL35))) | IF(OR(F35="",AN35=""),"",IF(COUNT(AI35:AM35)=0,"",AN35-LOOKUP(2,1/(AI35:AM35<>""),AI35:AM35))) | IF(OR(F35="",AO35=""),"",IF(COUNT(AI35:AN35)=0,"",AO35-LOOKUP(2,1/(AI35:AN35<>""),AI35:AN35))) | IF(OR(F35="",AP35=""),"",IF(COUNT(AI35:AO35)=0,"",AP35-LOOKUP(2,1/(AI35:AO35<>""),AI35:AO35))) | IF(OR(F35="",AQ35=""),"",IF(COUNT(AI35:AP35)=0,"",AQ35-LOOKUP(2,1/(AI35:AP35<>""),AI35:AP35))) | IF(OR(F35="",AR35=""),"",IF(COUNT(AI35:AQ35)=0,"",AR35-LOOKUP(2,1/(AI35:AQ35<>""),AI35:AQ35))) | IF(OR(F35="",AS35=""),"",IF(COUNT(AI35:AR35)=0,"",AS35-LOOKUP(2,1/(AI35:AR35<>""),AI35:AR35))) | IF(OR(F35="",AT35=""),"",IF(COUNT(AI35:AS35)=0,"",AT35-LOOKUP(2,1/(AI35:AS35<>""),AI35:AS35))) | IF(OR(F35="",AU35=""),"",IF(COUNT(AI35:AT35)=0,"",AU35-LOOKUP(2,1/(AI35:AT35<>""),AI35:AT35))) | IF(OR(F35="",AV35=""),"",IF(COUNT(AI35:AU35)=0,"",AV35-LOOKUP(2,1/(AI35:AU35<>""),AI35:AU35))) | IF(J35="","All_Provinces",IFERROR(VLOOKUP(J35,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K35="","All_Districts",IFERROR(VLOOKUP(K35,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F36="","",ROW()-3) | [18 empty] | IF(AQ36="","",AQ36) |  |  |  | IF(W36<>"",W36,IF(OR(T36="",V36=""),"",EDATE(T36,V36))) |  |  |  |  | IF(F36="","",IF(COUNT(AI36:AV36)=0,IF(AA36="","Not started",AA36),SUBSTITUTE(LOOKUP(2,1/(AI36:AV36<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F36="",COUNT(AI36:AV36)=0),"",TODAY()-LOOKUP(2,1/(AI36:AV36<>""),AI36:AV36)) | IF(OR(F36="",COUNT(AI36:AV36)<2),"",LOOKUP(2,1/(AI36:AV36<>""),AI36:AV36)-MIN(AI36:AV36)) | IF(OR(AD36="",AC36="Not started",AC36=""),"",IFERROR(AD36-IF(VLOOKUP(AC36,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC36,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F36="","",IF(OR(AA36="Cancelled",AC36="Cancelled"),"Cancelled",IF(OR(AC36="Completed / Handover",Y36<>"",Z36>=100),"Completed — on track",IF(O36="Not awarded",IF(U36="",IF(X36="","No planned date",IF(TODAY()>X36,"Behind — past planned date",IF(X36-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U36,"Behind — award date passed",IF(U36-TODAY()<=30,"At risk — close to off track","On track"))),IF(X36="","No planned date",IF(AND(TODAY()>X36,OR(Z36="",Z36<100)),"Behind — past end date",IF(AND(T36<>"",X36<>"",Z36<>"",(Z36<100),((TODAY()-T36)/MAX(X36-T36,1)*100)-Z36>15),"Behind — progress lag",IF(AND(X36-TODAY()<=30,X36-TODAY()>=0,OR(Z36="",Z36<90)),"At risk — close to off track","On track")))))))) | IF(OR(F36="",AC36="Completed / Handover",AC36="Cancelled"),"",IF(O36="Not awarded",IF(U36<>"",U36-TODAY(),IF(X36="","",X36-TODAY())),IF(X36="","",X36-TODAY()))) | [14 empty] | IF(OR(F36="",AJ36=""),"",IF(COUNT(AI36:AI36)=0,"",AJ36-LOOKUP(2,1/(AI36:AI36<>""),AI36:AI36))) | IF(OR(F36="",AK36=""),"",IF(COUNT(AI36:AJ36)=0,"",AK36-LOOKUP(2,1/(AI36:AJ36<>""),AI36:AJ36))) | IF(OR(F36="",AL36=""),"",IF(COUNT(AI36:AK36)=0,"",AL36-LOOKUP(2,1/(AI36:AK36<>""),AI36:AK36))) | IF(OR(F36="",AM36=""),"",IF(COUNT(AI36:AL36)=0,"",AM36-LOOKUP(2,1/(AI36:AL36<>""),AI36:AL36))) | IF(OR(F36="",AN36=""),"",IF(COUNT(AI36:AM36)=0,"",AN36-LOOKUP(2,1/(AI36:AM36<>""),AI36:AM36))) | IF(OR(F36="",AO36=""),"",IF(COUNT(AI36:AN36)=0,"",AO36-LOOKUP(2,1/(AI36:AN36<>""),AI36:AN36))) | IF(OR(F36="",AP36=""),"",IF(COUNT(AI36:AO36)=0,"",AP36-LOOKUP(2,1/(AI36:AO36<>""),AI36:AO36))) | IF(OR(F36="",AQ36=""),"",IF(COUNT(AI36:AP36)=0,"",AQ36-LOOKUP(2,1/(AI36:AP36<>""),AI36:AP36))) | IF(OR(F36="",AR36=""),"",IF(COUNT(AI36:AQ36)=0,"",AR36-LOOKUP(2,1/(AI36:AQ36<>""),AI36:AQ36))) | IF(OR(F36="",AS36=""),"",IF(COUNT(AI36:AR36)=0,"",AS36-LOOKUP(2,1/(AI36:AR36<>""),AI36:AR36))) | IF(OR(F36="",AT36=""),"",IF(COUNT(AI36:AS36)=0,"",AT36-LOOKUP(2,1/(AI36:AS36<>""),AI36:AS36))) | IF(OR(F36="",AU36=""),"",IF(COUNT(AI36:AT36)=0,"",AU36-LOOKUP(2,1/(AI36:AT36<>""),AI36:AT36))) | IF(OR(F36="",AV36=""),"",IF(COUNT(AI36:AU36)=0,"",AV36-LOOKUP(2,1/(AI36:AU36<>""),AI36:AU36))) | IF(J36="","All_Provinces",IFERROR(VLOOKUP(J36,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K36="","All_Districts",IFERROR(VLOOKUP(K36,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F37="","",ROW()-3) | [18 empty] | IF(AQ37="","",AQ37) |  |  |  | IF(W37<>"",W37,IF(OR(T37="",V37=""),"",EDATE(T37,V37))) |  |  |  |  | IF(F37="","",IF(COUNT(AI37:AV37)=0,IF(AA37="","Not started",AA37),SUBSTITUTE(LOOKUP(2,1/(AI37:AV37<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F37="",COUNT(AI37:AV37)=0),"",TODAY()-LOOKUP(2,1/(AI37:AV37<>""),AI37:AV37)) | IF(OR(F37="",COUNT(AI37:AV37)<2),"",LOOKUP(2,1/(AI37:AV37<>""),AI37:AV37)-MIN(AI37:AV37)) | IF(OR(AD37="",AC37="Not started",AC37=""),"",IFERROR(AD37-IF(VLOOKUP(AC37,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC37,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F37="","",IF(OR(AA37="Cancelled",AC37="Cancelled"),"Cancelled",IF(OR(AC37="Completed / Handover",Y37<>"",Z37>=100),"Completed — on track",IF(O37="Not awarded",IF(U37="",IF(X37="","No planned date",IF(TODAY()>X37,"Behind — past planned date",IF(X37-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U37,"Behind — award date passed",IF(U37-TODAY()<=30,"At risk — close to off track","On track"))),IF(X37="","No planned date",IF(AND(TODAY()>X37,OR(Z37="",Z37<100)),"Behind — past end date",IF(AND(T37<>"",X37<>"",Z37<>"",(Z37<100),((TODAY()-T37)/MAX(X37-T37,1)*100)-Z37>15),"Behind — progress lag",IF(AND(X37-TODAY()<=30,X37-TODAY()>=0,OR(Z37="",Z37<90)),"At risk — close to off track","On track")))))))) | IF(OR(F37="",AC37="Completed / Handover",AC37="Cancelled"),"",IF(O37="Not awarded",IF(U37<>"",U37-TODAY(),IF(X37="","",X37-TODAY())),IF(X37="","",X37-TODAY()))) | [14 empty] | IF(OR(F37="",AJ37=""),"",IF(COUNT(AI37:AI37)=0,"",AJ37-LOOKUP(2,1/(AI37:AI37<>""),AI37:AI37))) | IF(OR(F37="",AK37=""),"",IF(COUNT(AI37:AJ37)=0,"",AK37-LOOKUP(2,1/(AI37:AJ37<>""),AI37:AJ37))) | IF(OR(F37="",AL37=""),"",IF(COUNT(AI37:AK37)=0,"",AL37-LOOKUP(2,1/(AI37:AK37<>""),AI37:AK37))) | IF(OR(F37="",AM37=""),"",IF(COUNT(AI37:AL37)=0,"",AM37-LOOKUP(2,1/(AI37:AL37<>""),AI37:AL37))) | IF(OR(F37="",AN37=""),"",IF(COUNT(AI37:AM37)=0,"",AN37-LOOKUP(2,1/(AI37:AM37<>""),AI37:AM37))) | IF(OR(F37="",AO37=""),"",IF(COUNT(AI37:AN37)=0,"",AO37-LOOKUP(2,1/(AI37:AN37<>""),AI37:AN37))) | IF(OR(F37="",AP37=""),"",IF(COUNT(AI37:AO37)=0,"",AP37-LOOKUP(2,1/(AI37:AO37<>""),AI37:AO37))) | IF(OR(F37="",AQ37=""),"",IF(COUNT(AI37:AP37)=0,"",AQ37-LOOKUP(2,1/(AI37:AP37<>""),AI37:AP37))) | IF(OR(F37="",AR37=""),"",IF(COUNT(AI37:AQ37)=0,"",AR37-LOOKUP(2,1/(AI37:AQ37<>""),AI37:AQ37))) | IF(OR(F37="",AS37=""),"",IF(COUNT(AI37:AR37)=0,"",AS37-LOOKUP(2,1/(AI37:AR37<>""),AI37:AR37))) | IF(OR(F37="",AT37=""),"",IF(COUNT(AI37:AS37)=0,"",AT37-LOOKUP(2,1/(AI37:AS37<>""),AI37:AS37))) | IF(OR(F37="",AU37=""),"",IF(COUNT(AI37:AT37)=0,"",AU37-LOOKUP(2,1/(AI37:AT37<>""),AI37:AT37))) | IF(OR(F37="",AV37=""),"",IF(COUNT(AI37:AU37)=0,"",AV37-LOOKUP(2,1/(AI37:AU37<>""),AI37:AU37))) | IF(J37="","All_Provinces",IFERROR(VLOOKUP(J37,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K37="","All_Districts",IFERROR(VLOOKUP(K37,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F38="","",ROW()-3) | [18 empty] | IF(AQ38="","",AQ38) |  |  |  | IF(W38<>"",W38,IF(OR(T38="",V38=""),"",EDATE(T38,V38))) |  |  |  |  | IF(F38="","",IF(COUNT(AI38:AV38)=0,IF(AA38="","Not started",AA38),SUBSTITUTE(LOOKUP(2,1/(AI38:AV38<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F38="",COUNT(AI38:AV38)=0),"",TODAY()-LOOKUP(2,1/(AI38:AV38<>""),AI38:AV38)) | IF(OR(F38="",COUNT(AI38:AV38)<2),"",LOOKUP(2,1/(AI38:AV38<>""),AI38:AV38)-MIN(AI38:AV38)) | IF(OR(AD38="",AC38="Not started",AC38=""),"",IFERROR(AD38-IF(VLOOKUP(AC38,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC38,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F38="","",IF(OR(AA38="Cancelled",AC38="Cancelled"),"Cancelled",IF(OR(AC38="Completed / Handover",Y38<>"",Z38>=100),"Completed — on track",IF(O38="Not awarded",IF(U38="",IF(X38="","No planned date",IF(TODAY()>X38,"Behind — past planned date",IF(X38-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U38,"Behind — award date passed",IF(U38-TODAY()<=30,"At risk — close to off track","On track"))),IF(X38="","No planned date",IF(AND(TODAY()>X38,OR(Z38="",Z38<100)),"Behind — past end date",IF(AND(T38<>"",X38<>"",Z38<>"",(Z38<100),((TODAY()-T38)/MAX(X38-T38,1)*100)-Z38>15),"Behind — progress lag",IF(AND(X38-TODAY()<=30,X38-TODAY()>=0,OR(Z38="",Z38<90)),"At risk — close to off track","On track")))))))) | IF(OR(F38="",AC38="Completed / Handover",AC38="Cancelled"),"",IF(O38="Not awarded",IF(U38<>"",U38-TODAY(),IF(X38="","",X38-TODAY())),IF(X38="","",X38-TODAY()))) | [14 empty] | IF(OR(F38="",AJ38=""),"",IF(COUNT(AI38:AI38)=0,"",AJ38-LOOKUP(2,1/(AI38:AI38<>""),AI38:AI38))) | IF(OR(F38="",AK38=""),"",IF(COUNT(AI38:AJ38)=0,"",AK38-LOOKUP(2,1/(AI38:AJ38<>""),AI38:AJ38))) | IF(OR(F38="",AL38=""),"",IF(COUNT(AI38:AK38)=0,"",AL38-LOOKUP(2,1/(AI38:AK38<>""),AI38:AK38))) | IF(OR(F38="",AM38=""),"",IF(COUNT(AI38:AL38)=0,"",AM38-LOOKUP(2,1/(AI38:AL38<>""),AI38:AL38))) | IF(OR(F38="",AN38=""),"",IF(COUNT(AI38:AM38)=0,"",AN38-LOOKUP(2,1/(AI38:AM38<>""),AI38:AM38))) | IF(OR(F38="",AO38=""),"",IF(COUNT(AI38:AN38)=0,"",AO38-LOOKUP(2,1/(AI38:AN38<>""),AI38:AN38))) | IF(OR(F38="",AP38=""),"",IF(COUNT(AI38:AO38)=0,"",AP38-LOOKUP(2,1/(AI38:AO38<>""),AI38:AO38))) | IF(OR(F38="",AQ38=""),"",IF(COUNT(AI38:AP38)=0,"",AQ38-LOOKUP(2,1/(AI38:AP38<>""),AI38:AP38))) | IF(OR(F38="",AR38=""),"",IF(COUNT(AI38:AQ38)=0,"",AR38-LOOKUP(2,1/(AI38:AQ38<>""),AI38:AQ38))) | IF(OR(F38="",AS38=""),"",IF(COUNT(AI38:AR38)=0,"",AS38-LOOKUP(2,1/(AI38:AR38<>""),AI38:AR38))) | IF(OR(F38="",AT38=""),"",IF(COUNT(AI38:AS38)=0,"",AT38-LOOKUP(2,1/(AI38:AS38<>""),AI38:AS38))) | IF(OR(F38="",AU38=""),"",IF(COUNT(AI38:AT38)=0,"",AU38-LOOKUP(2,1/(AI38:AT38<>""),AI38:AT38))) | IF(OR(F38="",AV38=""),"",IF(COUNT(AI38:AU38)=0,"",AV38-LOOKUP(2,1/(AI38:AU38<>""),AI38:AU38))) | IF(J38="","All_Provinces",IFERROR(VLOOKUP(J38,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K38="","All_Districts",IFERROR(VLOOKUP(K38,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F39="","",ROW()-3) | [18 empty] | IF(AQ39="","",AQ39) |  |  |  | IF(W39<>"",W39,IF(OR(T39="",V39=""),"",EDATE(T39,V39))) |  |  |  |  | IF(F39="","",IF(COUNT(AI39:AV39)=0,IF(AA39="","Not started",AA39),SUBSTITUTE(LOOKUP(2,1/(AI39:AV39<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F39="",COUNT(AI39:AV39)=0),"",TODAY()-LOOKUP(2,1/(AI39:AV39<>""),AI39:AV39)) | IF(OR(F39="",COUNT(AI39:AV39)<2),"",LOOKUP(2,1/(AI39:AV39<>""),AI39:AV39)-MIN(AI39:AV39)) | IF(OR(AD39="",AC39="Not started",AC39=""),"",IFERROR(AD39-IF(VLOOKUP(AC39,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC39,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F39="","",IF(OR(AA39="Cancelled",AC39="Cancelled"),"Cancelled",IF(OR(AC39="Completed / Handover",Y39<>"",Z39>=100),"Completed — on track",IF(O39="Not awarded",IF(U39="",IF(X39="","No planned date",IF(TODAY()>X39,"Behind — past planned date",IF(X39-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U39,"Behind — award date passed",IF(U39-TODAY()<=30,"At risk — close to off track","On track"))),IF(X39="","No planned date",IF(AND(TODAY()>X39,OR(Z39="",Z39<100)),"Behind — past end date",IF(AND(T39<>"",X39<>"",Z39<>"",(Z39<100),((TODAY()-T39)/MAX(X39-T39,1)*100)-Z39>15),"Behind — progress lag",IF(AND(X39-TODAY()<=30,X39-TODAY()>=0,OR(Z39="",Z39<90)),"At risk — close to off track","On track")))))))) | IF(OR(F39="",AC39="Completed / Handover",AC39="Cancelled"),"",IF(O39="Not awarded",IF(U39<>"",U39-TODAY(),IF(X39="","",X39-TODAY())),IF(X39="","",X39-TODAY()))) | [14 empty] | IF(OR(F39="",AJ39=""),"",IF(COUNT(AI39:AI39)=0,"",AJ39-LOOKUP(2,1/(AI39:AI39<>""),AI39:AI39))) | IF(OR(F39="",AK39=""),"",IF(COUNT(AI39:AJ39)=0,"",AK39-LOOKUP(2,1/(AI39:AJ39<>""),AI39:AJ39))) | IF(OR(F39="",AL39=""),"",IF(COUNT(AI39:AK39)=0,"",AL39-LOOKUP(2,1/(AI39:AK39<>""),AI39:AK39))) | IF(OR(F39="",AM39=""),"",IF(COUNT(AI39:AL39)=0,"",AM39-LOOKUP(2,1/(AI39:AL39<>""),AI39:AL39))) | IF(OR(F39="",AN39=""),"",IF(COUNT(AI39:AM39)=0,"",AN39-LOOKUP(2,1/(AI39:AM39<>""),AI39:AM39))) | IF(OR(F39="",AO39=""),"",IF(COUNT(AI39:AN39)=0,"",AO39-LOOKUP(2,1/(AI39:AN39<>""),AI39:AN39))) | IF(OR(F39="",AP39=""),"",IF(COUNT(AI39:AO39)=0,"",AP39-LOOKUP(2,1/(AI39:AO39<>""),AI39:AO39))) | IF(OR(F39="",AQ39=""),"",IF(COUNT(AI39:AP39)=0,"",AQ39-LOOKUP(2,1/(AI39:AP39<>""),AI39:AP39))) | IF(OR(F39="",AR39=""),"",IF(COUNT(AI39:AQ39)=0,"",AR39-LOOKUP(2,1/(AI39:AQ39<>""),AI39:AQ39))) | IF(OR(F39="",AS39=""),"",IF(COUNT(AI39:AR39)=0,"",AS39-LOOKUP(2,1/(AI39:AR39<>""),AI39:AR39))) | IF(OR(F39="",AT39=""),"",IF(COUNT(AI39:AS39)=0,"",AT39-LOOKUP(2,1/(AI39:AS39<>""),AI39:AS39))) | IF(OR(F39="",AU39=""),"",IF(COUNT(AI39:AT39)=0,"",AU39-LOOKUP(2,1/(AI39:AT39<>""),AI39:AT39))) | IF(OR(F39="",AV39=""),"",IF(COUNT(AI39:AU39)=0,"",AV39-LOOKUP(2,1/(AI39:AU39<>""),AI39:AU39))) | IF(J39="","All_Provinces",IFERROR(VLOOKUP(J39,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K39="","All_Districts",IFERROR(VLOOKUP(K39,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F40="","",ROW()-3) | [18 empty] | IF(AQ40="","",AQ40) |  |  |  | IF(W40<>"",W40,IF(OR(T40="",V40=""),"",EDATE(T40,V40))) |  |  |  |  | IF(F40="","",IF(COUNT(AI40:AV40)=0,IF(AA40="","Not started",AA40),SUBSTITUTE(LOOKUP(2,1/(AI40:AV40<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F40="",COUNT(AI40:AV40)=0),"",TODAY()-LOOKUP(2,1/(AI40:AV40<>""),AI40:AV40)) | IF(OR(F40="",COUNT(AI40:AV40)<2),"",LOOKUP(2,1/(AI40:AV40<>""),AI40:AV40)-MIN(AI40:AV40)) | IF(OR(AD40="",AC40="Not started",AC40=""),"",IFERROR(AD40-IF(VLOOKUP(AC40,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC40,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F40="","",IF(OR(AA40="Cancelled",AC40="Cancelled"),"Cancelled",IF(OR(AC40="Completed / Handover",Y40<>"",Z40>=100),"Completed — on track",IF(O40="Not awarded",IF(U40="",IF(X40="","No planned date",IF(TODAY()>X40,"Behind — past planned date",IF(X40-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U40,"Behind — award date passed",IF(U40-TODAY()<=30,"At risk — close to off track","On track"))),IF(X40="","No planned date",IF(AND(TODAY()>X40,OR(Z40="",Z40<100)),"Behind — past end date",IF(AND(T40<>"",X40<>"",Z40<>"",(Z40<100),((TODAY()-T40)/MAX(X40-T40,1)*100)-Z40>15),"Behind — progress lag",IF(AND(X40-TODAY()<=30,X40-TODAY()>=0,OR(Z40="",Z40<90)),"At risk — close to off track","On track")))))))) | IF(OR(F40="",AC40="Completed / Handover",AC40="Cancelled"),"",IF(O40="Not awarded",IF(U40<>"",U40-TODAY(),IF(X40="","",X40-TODAY())),IF(X40="","",X40-TODAY()))) | [14 empty] | IF(OR(F40="",AJ40=""),"",IF(COUNT(AI40:AI40)=0,"",AJ40-LOOKUP(2,1/(AI40:AI40<>""),AI40:AI40))) | IF(OR(F40="",AK40=""),"",IF(COUNT(AI40:AJ40)=0,"",AK40-LOOKUP(2,1/(AI40:AJ40<>""),AI40:AJ40))) | IF(OR(F40="",AL40=""),"",IF(COUNT(AI40:AK40)=0,"",AL40-LOOKUP(2,1/(AI40:AK40<>""),AI40:AK40))) | IF(OR(F40="",AM40=""),"",IF(COUNT(AI40:AL40)=0,"",AM40-LOOKUP(2,1/(AI40:AL40<>""),AI40:AL40))) | IF(OR(F40="",AN40=""),"",IF(COUNT(AI40:AM40)=0,"",AN40-LOOKUP(2,1/(AI40:AM40<>""),AI40:AM40))) | IF(OR(F40="",AO40=""),"",IF(COUNT(AI40:AN40)=0,"",AO40-LOOKUP(2,1/(AI40:AN40<>""),AI40:AN40))) | IF(OR(F40="",AP40=""),"",IF(COUNT(AI40:AO40)=0,"",AP40-LOOKUP(2,1/(AI40:AO40<>""),AI40:AO40))) | IF(OR(F40="",AQ40=""),"",IF(COUNT(AI40:AP40)=0,"",AQ40-LOOKUP(2,1/(AI40:AP40<>""),AI40:AP40))) | IF(OR(F40="",AR40=""),"",IF(COUNT(AI40:AQ40)=0,"",AR40-LOOKUP(2,1/(AI40:AQ40<>""),AI40:AQ40))) | IF(OR(F40="",AS40=""),"",IF(COUNT(AI40:AR40)=0,"",AS40-LOOKUP(2,1/(AI40:AR40<>""),AI40:AR40))) | IF(OR(F40="",AT40=""),"",IF(COUNT(AI40:AS40)=0,"",AT40-LOOKUP(2,1/(AI40:AS40<>""),AI40:AS40))) | IF(OR(F40="",AU40=""),"",IF(COUNT(AI40:AT40)=0,"",AU40-LOOKUP(2,1/(AI40:AT40<>""),AI40:AT40))) | IF(OR(F40="",AV40=""),"",IF(COUNT(AI40:AU40)=0,"",AV40-LOOKUP(2,1/(AI40:AU40<>""),AI40:AU40))) | IF(J40="","All_Provinces",IFERROR(VLOOKUP(J40,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K40="","All_Districts",IFERROR(VLOOKUP(K40,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F41="","",ROW()-3) | [18 empty] | IF(AQ41="","",AQ41) |  |  |  | IF(W41<>"",W41,IF(OR(T41="",V41=""),"",EDATE(T41,V41))) |  |  |  |  | IF(F41="","",IF(COUNT(AI41:AV41)=0,IF(AA41="","Not started",AA41),SUBSTITUTE(LOOKUP(2,1/(AI41:AV41<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F41="",COUNT(AI41:AV41)=0),"",TODAY()-LOOKUP(2,1/(AI41:AV41<>""),AI41:AV41)) | IF(OR(F41="",COUNT(AI41:AV41)<2),"",LOOKUP(2,1/(AI41:AV41<>""),AI41:AV41)-MIN(AI41:AV41)) | IF(OR(AD41="",AC41="Not started",AC41=""),"",IFERROR(AD41-IF(VLOOKUP(AC41,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC41,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F41="","",IF(OR(AA41="Cancelled",AC41="Cancelled"),"Cancelled",IF(OR(AC41="Completed / Handover",Y41<>"",Z41>=100),"Completed — on track",IF(O41="Not awarded",IF(U41="",IF(X41="","No planned date",IF(TODAY()>X41,"Behind — past planned date",IF(X41-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U41,"Behind — award date passed",IF(U41-TODAY()<=30,"At risk — close to off track","On track"))),IF(X41="","No planned date",IF(AND(TODAY()>X41,OR(Z41="",Z41<100)),"Behind — past end date",IF(AND(T41<>"",X41<>"",Z41<>"",(Z41<100),((TODAY()-T41)/MAX(X41-T41,1)*100)-Z41>15),"Behind — progress lag",IF(AND(X41-TODAY()<=30,X41-TODAY()>=0,OR(Z41="",Z41<90)),"At risk — close to off track","On track")))))))) | IF(OR(F41="",AC41="Completed / Handover",AC41="Cancelled"),"",IF(O41="Not awarded",IF(U41<>"",U41-TODAY(),IF(X41="","",X41-TODAY())),IF(X41="","",X41-TODAY()))) | [14 empty] | IF(OR(F41="",AJ41=""),"",IF(COUNT(AI41:AI41)=0,"",AJ41-LOOKUP(2,1/(AI41:AI41<>""),AI41:AI41))) | IF(OR(F41="",AK41=""),"",IF(COUNT(AI41:AJ41)=0,"",AK41-LOOKUP(2,1/(AI41:AJ41<>""),AI41:AJ41))) | IF(OR(F41="",AL41=""),"",IF(COUNT(AI41:AK41)=0,"",AL41-LOOKUP(2,1/(AI41:AK41<>""),AI41:AK41))) | IF(OR(F41="",AM41=""),"",IF(COUNT(AI41:AL41)=0,"",AM41-LOOKUP(2,1/(AI41:AL41<>""),AI41:AL41))) | IF(OR(F41="",AN41=""),"",IF(COUNT(AI41:AM41)=0,"",AN41-LOOKUP(2,1/(AI41:AM41<>""),AI41:AM41))) | IF(OR(F41="",AO41=""),"",IF(COUNT(AI41:AN41)=0,"",AO41-LOOKUP(2,1/(AI41:AN41<>""),AI41:AN41))) | IF(OR(F41="",AP41=""),"",IF(COUNT(AI41:AO41)=0,"",AP41-LOOKUP(2,1/(AI41:AO41<>""),AI41:AO41))) | IF(OR(F41="",AQ41=""),"",IF(COUNT(AI41:AP41)=0,"",AQ41-LOOKUP(2,1/(AI41:AP41<>""),AI41:AP41))) | IF(OR(F41="",AR41=""),"",IF(COUNT(AI41:AQ41)=0,"",AR41-LOOKUP(2,1/(AI41:AQ41<>""),AI41:AQ41))) | IF(OR(F41="",AS41=""),"",IF(COUNT(AI41:AR41)=0,"",AS41-LOOKUP(2,1/(AI41:AR41<>""),AI41:AR41))) | IF(OR(F41="",AT41=""),"",IF(COUNT(AI41:AS41)=0,"",AT41-LOOKUP(2,1/(AI41:AS41<>""),AI41:AS41))) | IF(OR(F41="",AU41=""),"",IF(COUNT(AI41:AT41)=0,"",AU41-LOOKUP(2,1/(AI41:AT41<>""),AI41:AT41))) | IF(OR(F41="",AV41=""),"",IF(COUNT(AI41:AU41)=0,"",AV41-LOOKUP(2,1/(AI41:AU41<>""),AI41:AU41))) | IF(J41="","All_Provinces",IFERROR(VLOOKUP(J41,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K41="","All_Districts",IFERROR(VLOOKUP(K41,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F42="","",ROW()-3) | [18 empty] | IF(AQ42="","",AQ42) |  |  |  | IF(W42<>"",W42,IF(OR(T42="",V42=""),"",EDATE(T42,V42))) |  |  |  |  | IF(F42="","",IF(COUNT(AI42:AV42)=0,IF(AA42="","Not started",AA42),SUBSTITUTE(LOOKUP(2,1/(AI42:AV42<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F42="",COUNT(AI42:AV42)=0),"",TODAY()-LOOKUP(2,1/(AI42:AV42<>""),AI42:AV42)) | IF(OR(F42="",COUNT(AI42:AV42)<2),"",LOOKUP(2,1/(AI42:AV42<>""),AI42:AV42)-MIN(AI42:AV42)) | IF(OR(AD42="",AC42="Not started",AC42=""),"",IFERROR(AD42-IF(VLOOKUP(AC42,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC42,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F42="","",IF(OR(AA42="Cancelled",AC42="Cancelled"),"Cancelled",IF(OR(AC42="Completed / Handover",Y42<>"",Z42>=100),"Completed — on track",IF(O42="Not awarded",IF(U42="",IF(X42="","No planned date",IF(TODAY()>X42,"Behind — past planned date",IF(X42-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U42,"Behind — award date passed",IF(U42-TODAY()<=30,"At risk — close to off track","On track"))),IF(X42="","No planned date",IF(AND(TODAY()>X42,OR(Z42="",Z42<100)),"Behind — past end date",IF(AND(T42<>"",X42<>"",Z42<>"",(Z42<100),((TODAY()-T42)/MAX(X42-T42,1)*100)-Z42>15),"Behind — progress lag",IF(AND(X42-TODAY()<=30,X42-TODAY()>=0,OR(Z42="",Z42<90)),"At risk — close to off track","On track")))))))) | IF(OR(F42="",AC42="Completed / Handover",AC42="Cancelled"),"",IF(O42="Not awarded",IF(U42<>"",U42-TODAY(),IF(X42="","",X42-TODAY())),IF(X42="","",X42-TODAY()))) | [14 empty] | IF(OR(F42="",AJ42=""),"",IF(COUNT(AI42:AI42)=0,"",AJ42-LOOKUP(2,1/(AI42:AI42<>""),AI42:AI42))) | IF(OR(F42="",AK42=""),"",IF(COUNT(AI42:AJ42)=0,"",AK42-LOOKUP(2,1/(AI42:AJ42<>""),AI42:AJ42))) | IF(OR(F42="",AL42=""),"",IF(COUNT(AI42:AK42)=0,"",AL42-LOOKUP(2,1/(AI42:AK42<>""),AI42:AK42))) | IF(OR(F42="",AM42=""),"",IF(COUNT(AI42:AL42)=0,"",AM42-LOOKUP(2,1/(AI42:AL42<>""),AI42:AL42))) | IF(OR(F42="",AN42=""),"",IF(COUNT(AI42:AM42)=0,"",AN42-LOOKUP(2,1/(AI42:AM42<>""),AI42:AM42))) | IF(OR(F42="",AO42=""),"",IF(COUNT(AI42:AN42)=0,"",AO42-LOOKUP(2,1/(AI42:AN42<>""),AI42:AN42))) | IF(OR(F42="",AP42=""),"",IF(COUNT(AI42:AO42)=0,"",AP42-LOOKUP(2,1/(AI42:AO42<>""),AI42:AO42))) | IF(OR(F42="",AQ42=""),"",IF(COUNT(AI42:AP42)=0,"",AQ42-LOOKUP(2,1/(AI42:AP42<>""),AI42:AP42))) | IF(OR(F42="",AR42=""),"",IF(COUNT(AI42:AQ42)=0,"",AR42-LOOKUP(2,1/(AI42:AQ42<>""),AI42:AQ42))) | IF(OR(F42="",AS42=""),"",IF(COUNT(AI42:AR42)=0,"",AS42-LOOKUP(2,1/(AI42:AR42<>""),AI42:AR42))) | IF(OR(F42="",AT42=""),"",IF(COUNT(AI42:AS42)=0,"",AT42-LOOKUP(2,1/(AI42:AS42<>""),AI42:AS42))) | IF(OR(F42="",AU42=""),"",IF(COUNT(AI42:AT42)=0,"",AU42-LOOKUP(2,1/(AI42:AT42<>""),AI42:AT42))) | IF(OR(F42="",AV42=""),"",IF(COUNT(AI42:AU42)=0,"",AV42-LOOKUP(2,1/(AI42:AU42<>""),AI42:AU42))) | IF(J42="","All_Provinces",IFERROR(VLOOKUP(J42,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K42="","All_Districts",IFERROR(VLOOKUP(K42,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F43="","",ROW()-3) | [18 empty] | IF(AQ43="","",AQ43) |  |  |  | IF(W43<>"",W43,IF(OR(T43="",V43=""),"",EDATE(T43,V43))) |  |  |  |  | IF(F43="","",IF(COUNT(AI43:AV43)=0,IF(AA43="","Not started",AA43),SUBSTITUTE(LOOKUP(2,1/(AI43:AV43<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F43="",COUNT(AI43:AV43)=0),"",TODAY()-LOOKUP(2,1/(AI43:AV43<>""),AI43:AV43)) | IF(OR(F43="",COUNT(AI43:AV43)<2),"",LOOKUP(2,1/(AI43:AV43<>""),AI43:AV43)-MIN(AI43:AV43)) | IF(OR(AD43="",AC43="Not started",AC43=""),"",IFERROR(AD43-IF(VLOOKUP(AC43,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC43,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F43="","",IF(OR(AA43="Cancelled",AC43="Cancelled"),"Cancelled",IF(OR(AC43="Completed / Handover",Y43<>"",Z43>=100),"Completed — on track",IF(O43="Not awarded",IF(U43="",IF(X43="","No planned date",IF(TODAY()>X43,"Behind — past planned date",IF(X43-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U43,"Behind — award date passed",IF(U43-TODAY()<=30,"At risk — close to off track","On track"))),IF(X43="","No planned date",IF(AND(TODAY()>X43,OR(Z43="",Z43<100)),"Behind — past end date",IF(AND(T43<>"",X43<>"",Z43<>"",(Z43<100),((TODAY()-T43)/MAX(X43-T43,1)*100)-Z43>15),"Behind — progress lag",IF(AND(X43-TODAY()<=30,X43-TODAY()>=0,OR(Z43="",Z43<90)),"At risk — close to off track","On track")))))))) | IF(OR(F43="",AC43="Completed / Handover",AC43="Cancelled"),"",IF(O43="Not awarded",IF(U43<>"",U43-TODAY(),IF(X43="","",X43-TODAY())),IF(X43="","",X43-TODAY()))) | [14 empty] | IF(OR(F43="",AJ43=""),"",IF(COUNT(AI43:AI43)=0,"",AJ43-LOOKUP(2,1/(AI43:AI43<>""),AI43:AI43))) | IF(OR(F43="",AK43=""),"",IF(COUNT(AI43:AJ43)=0,"",AK43-LOOKUP(2,1/(AI43:AJ43<>""),AI43:AJ43))) | IF(OR(F43="",AL43=""),"",IF(COUNT(AI43:AK43)=0,"",AL43-LOOKUP(2,1/(AI43:AK43<>""),AI43:AK43))) | IF(OR(F43="",AM43=""),"",IF(COUNT(AI43:AL43)=0,"",AM43-LOOKUP(2,1/(AI43:AL43<>""),AI43:AL43))) | IF(OR(F43="",AN43=""),"",IF(COUNT(AI43:AM43)=0,"",AN43-LOOKUP(2,1/(AI43:AM43<>""),AI43:AM43))) | IF(OR(F43="",AO43=""),"",IF(COUNT(AI43:AN43)=0,"",AO43-LOOKUP(2,1/(AI43:AN43<>""),AI43:AN43))) | IF(OR(F43="",AP43=""),"",IF(COUNT(AI43:AO43)=0,"",AP43-LOOKUP(2,1/(AI43:AO43<>""),AI43:AO43))) | IF(OR(F43="",AQ43=""),"",IF(COUNT(AI43:AP43)=0,"",AQ43-LOOKUP(2,1/(AI43:AP43<>""),AI43:AP43))) | IF(OR(F43="",AR43=""),"",IF(COUNT(AI43:AQ43)=0,"",AR43-LOOKUP(2,1/(AI43:AQ43<>""),AI43:AQ43))) | IF(OR(F43="",AS43=""),"",IF(COUNT(AI43:AR43)=0,"",AS43-LOOKUP(2,1/(AI43:AR43<>""),AI43:AR43))) | IF(OR(F43="",AT43=""),"",IF(COUNT(AI43:AS43)=0,"",AT43-LOOKUP(2,1/(AI43:AS43<>""),AI43:AS43))) | IF(OR(F43="",AU43=""),"",IF(COUNT(AI43:AT43)=0,"",AU43-LOOKUP(2,1/(AI43:AT43<>""),AI43:AT43))) | IF(OR(F43="",AV43=""),"",IF(COUNT(AI43:AU43)=0,"",AV43-LOOKUP(2,1/(AI43:AU43<>""),AI43:AU43))) | IF(J43="","All_Provinces",IFERROR(VLOOKUP(J43,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K43="","All_Districts",IFERROR(VLOOKUP(K43,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F44="","",ROW()-3) | [18 empty] | IF(AQ44="","",AQ44) |  |  |  | IF(W44<>"",W44,IF(OR(T44="",V44=""),"",EDATE(T44,V44))) |  |  |  |  | IF(F44="","",IF(COUNT(AI44:AV44)=0,IF(AA44="","Not started",AA44),SUBSTITUTE(LOOKUP(2,1/(AI44:AV44<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F44="",COUNT(AI44:AV44)=0),"",TODAY()-LOOKUP(2,1/(AI44:AV44<>""),AI44:AV44)) | IF(OR(F44="",COUNT(AI44:AV44)<2),"",LOOKUP(2,1/(AI44:AV44<>""),AI44:AV44)-MIN(AI44:AV44)) | IF(OR(AD44="",AC44="Not started",AC44=""),"",IFERROR(AD44-IF(VLOOKUP(AC44,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC44,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F44="","",IF(OR(AA44="Cancelled",AC44="Cancelled"),"Cancelled",IF(OR(AC44="Completed / Handover",Y44<>"",Z44>=100),"Completed — on track",IF(O44="Not awarded",IF(U44="",IF(X44="","No planned date",IF(TODAY()>X44,"Behind — past planned date",IF(X44-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U44,"Behind — award date passed",IF(U44-TODAY()<=30,"At risk — close to off track","On track"))),IF(X44="","No planned date",IF(AND(TODAY()>X44,OR(Z44="",Z44<100)),"Behind — past end date",IF(AND(T44<>"",X44<>"",Z44<>"",(Z44<100),((TODAY()-T44)/MAX(X44-T44,1)*100)-Z44>15),"Behind — progress lag",IF(AND(X44-TODAY()<=30,X44-TODAY()>=0,OR(Z44="",Z44<90)),"At risk — close to off track","On track")))))))) | IF(OR(F44="",AC44="Completed / Handover",AC44="Cancelled"),"",IF(O44="Not awarded",IF(U44<>"",U44-TODAY(),IF(X44="","",X44-TODAY())),IF(X44="","",X44-TODAY()))) | [14 empty] | IF(OR(F44="",AJ44=""),"",IF(COUNT(AI44:AI44)=0,"",AJ44-LOOKUP(2,1/(AI44:AI44<>""),AI44:AI44))) | IF(OR(F44="",AK44=""),"",IF(COUNT(AI44:AJ44)=0,"",AK44-LOOKUP(2,1/(AI44:AJ44<>""),AI44:AJ44))) | IF(OR(F44="",AL44=""),"",IF(COUNT(AI44:AK44)=0,"",AL44-LOOKUP(2,1/(AI44:AK44<>""),AI44:AK44))) | IF(OR(F44="",AM44=""),"",IF(COUNT(AI44:AL44)=0,"",AM44-LOOKUP(2,1/(AI44:AL44<>""),AI44:AL44))) | IF(OR(F44="",AN44=""),"",IF(COUNT(AI44:AM44)=0,"",AN44-LOOKUP(2,1/(AI44:AM44<>""),AI44:AM44))) | IF(OR(F44="",AO44=""),"",IF(COUNT(AI44:AN44)=0,"",AO44-LOOKUP(2,1/(AI44:AN44<>""),AI44:AN44))) | IF(OR(F44="",AP44=""),"",IF(COUNT(AI44:AO44)=0,"",AP44-LOOKUP(2,1/(AI44:AO44<>""),AI44:AO44))) | IF(OR(F44="",AQ44=""),"",IF(COUNT(AI44:AP44)=0,"",AQ44-LOOKUP(2,1/(AI44:AP44<>""),AI44:AP44))) | IF(OR(F44="",AR44=""),"",IF(COUNT(AI44:AQ44)=0,"",AR44-LOOKUP(2,1/(AI44:AQ44<>""),AI44:AQ44))) | IF(OR(F44="",AS44=""),"",IF(COUNT(AI44:AR44)=0,"",AS44-LOOKUP(2,1/(AI44:AR44<>""),AI44:AR44))) | IF(OR(F44="",AT44=""),"",IF(COUNT(AI44:AS44)=0,"",AT44-LOOKUP(2,1/(AI44:AS44<>""),AI44:AS44))) | IF(OR(F44="",AU44=""),"",IF(COUNT(AI44:AT44)=0,"",AU44-LOOKUP(2,1/(AI44:AT44<>""),AI44:AT44))) | IF(OR(F44="",AV44=""),"",IF(COUNT(AI44:AU44)=0,"",AV44-LOOKUP(2,1/(AI44:AU44<>""),AI44:AU44))) | IF(J44="","All_Provinces",IFERROR(VLOOKUP(J44,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K44="","All_Districts",IFERROR(VLOOKUP(K44,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F45="","",ROW()-3) | [18 empty] | IF(AQ45="","",AQ45) |  |  |  | IF(W45<>"",W45,IF(OR(T45="",V45=""),"",EDATE(T45,V45))) |  |  |  |  | IF(F45="","",IF(COUNT(AI45:AV45)=0,IF(AA45="","Not started",AA45),SUBSTITUTE(LOOKUP(2,1/(AI45:AV45<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F45="",COUNT(AI45:AV45)=0),"",TODAY()-LOOKUP(2,1/(AI45:AV45<>""),AI45:AV45)) | IF(OR(F45="",COUNT(AI45:AV45)<2),"",LOOKUP(2,1/(AI45:AV45<>""),AI45:AV45)-MIN(AI45:AV45)) | IF(OR(AD45="",AC45="Not started",AC45=""),"",IFERROR(AD45-IF(VLOOKUP(AC45,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC45,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F45="","",IF(OR(AA45="Cancelled",AC45="Cancelled"),"Cancelled",IF(OR(AC45="Completed / Handover",Y45<>"",Z45>=100),"Completed — on track",IF(O45="Not awarded",IF(U45="",IF(X45="","No planned date",IF(TODAY()>X45,"Behind — past planned date",IF(X45-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U45,"Behind — award date passed",IF(U45-TODAY()<=30,"At risk — close to off track","On track"))),IF(X45="","No planned date",IF(AND(TODAY()>X45,OR(Z45="",Z45<100)),"Behind — past end date",IF(AND(T45<>"",X45<>"",Z45<>"",(Z45<100),((TODAY()-T45)/MAX(X45-T45,1)*100)-Z45>15),"Behind — progress lag",IF(AND(X45-TODAY()<=30,X45-TODAY()>=0,OR(Z45="",Z45<90)),"At risk — close to off track","On track")))))))) | IF(OR(F45="",AC45="Completed / Handover",AC45="Cancelled"),"",IF(O45="Not awarded",IF(U45<>"",U45-TODAY(),IF(X45="","",X45-TODAY())),IF(X45="","",X45-TODAY()))) | [14 empty] | IF(OR(F45="",AJ45=""),"",IF(COUNT(AI45:AI45)=0,"",AJ45-LOOKUP(2,1/(AI45:AI45<>""),AI45:AI45))) | IF(OR(F45="",AK45=""),"",IF(COUNT(AI45:AJ45)=0,"",AK45-LOOKUP(2,1/(AI45:AJ45<>""),AI45:AJ45))) | IF(OR(F45="",AL45=""),"",IF(COUNT(AI45:AK45)=0,"",AL45-LOOKUP(2,1/(AI45:AK45<>""),AI45:AK45))) | IF(OR(F45="",AM45=""),"",IF(COUNT(AI45:AL45)=0,"",AM45-LOOKUP(2,1/(AI45:AL45<>""),AI45:AL45))) | IF(OR(F45="",AN45=""),"",IF(COUNT(AI45:AM45)=0,"",AN45-LOOKUP(2,1/(AI45:AM45<>""),AI45:AM45))) | IF(OR(F45="",AO45=""),"",IF(COUNT(AI45:AN45)=0,"",AO45-LOOKUP(2,1/(AI45:AN45<>""),AI45:AN45))) | IF(OR(F45="",AP45=""),"",IF(COUNT(AI45:AO45)=0,"",AP45-LOOKUP(2,1/(AI45:AO45<>""),AI45:AO45))) | IF(OR(F45="",AQ45=""),"",IF(COUNT(AI45:AP45)=0,"",AQ45-LOOKUP(2,1/(AI45:AP45<>""),AI45:AP45))) | IF(OR(F45="",AR45=""),"",IF(COUNT(AI45:AQ45)=0,"",AR45-LOOKUP(2,1/(AI45:AQ45<>""),AI45:AQ45))) | IF(OR(F45="",AS45=""),"",IF(COUNT(AI45:AR45)=0,"",AS45-LOOKUP(2,1/(AI45:AR45<>""),AI45:AR45))) | IF(OR(F45="",AT45=""),"",IF(COUNT(AI45:AS45)=0,"",AT45-LOOKUP(2,1/(AI45:AS45<>""),AI45:AS45))) | IF(OR(F45="",AU45=""),"",IF(COUNT(AI45:AT45)=0,"",AU45-LOOKUP(2,1/(AI45:AT45<>""),AI45:AT45))) | IF(OR(F45="",AV45=""),"",IF(COUNT(AI45:AU45)=0,"",AV45-LOOKUP(2,1/(AI45:AU45<>""),AI45:AU45))) | IF(J45="","All_Provinces",IFERROR(VLOOKUP(J45,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K45="","All_Districts",IFERROR(VLOOKUP(K45,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F46="","",ROW()-3) | [18 empty] | IF(AQ46="","",AQ46) |  |  |  | IF(W46<>"",W46,IF(OR(T46="",V46=""),"",EDATE(T46,V46))) |  |  |  |  | IF(F46="","",IF(COUNT(AI46:AV46)=0,IF(AA46="","Not started",AA46),SUBSTITUTE(LOOKUP(2,1/(AI46:AV46<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F46="",COUNT(AI46:AV46)=0),"",TODAY()-LOOKUP(2,1/(AI46:AV46<>""),AI46:AV46)) | IF(OR(F46="",COUNT(AI46:AV46)<2),"",LOOKUP(2,1/(AI46:AV46<>""),AI46:AV46)-MIN(AI46:AV46)) | IF(OR(AD46="",AC46="Not started",AC46=""),"",IFERROR(AD46-IF(VLOOKUP(AC46,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC46,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F46="","",IF(OR(AA46="Cancelled",AC46="Cancelled"),"Cancelled",IF(OR(AC46="Completed / Handover",Y46<>"",Z46>=100),"Completed — on track",IF(O46="Not awarded",IF(U46="",IF(X46="","No planned date",IF(TODAY()>X46,"Behind — past planned date",IF(X46-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U46,"Behind — award date passed",IF(U46-TODAY()<=30,"At risk — close to off track","On track"))),IF(X46="","No planned date",IF(AND(TODAY()>X46,OR(Z46="",Z46<100)),"Behind — past end date",IF(AND(T46<>"",X46<>"",Z46<>"",(Z46<100),((TODAY()-T46)/MAX(X46-T46,1)*100)-Z46>15),"Behind — progress lag",IF(AND(X46-TODAY()<=30,X46-TODAY()>=0,OR(Z46="",Z46<90)),"At risk — close to off track","On track")))))))) | IF(OR(F46="",AC46="Completed / Handover",AC46="Cancelled"),"",IF(O46="Not awarded",IF(U46<>"",U46-TODAY(),IF(X46="","",X46-TODAY())),IF(X46="","",X46-TODAY()))) | [14 empty] | IF(OR(F46="",AJ46=""),"",IF(COUNT(AI46:AI46)=0,"",AJ46-LOOKUP(2,1/(AI46:AI46<>""),AI46:AI46))) | IF(OR(F46="",AK46=""),"",IF(COUNT(AI46:AJ46)=0,"",AK46-LOOKUP(2,1/(AI46:AJ46<>""),AI46:AJ46))) | IF(OR(F46="",AL46=""),"",IF(COUNT(AI46:AK46)=0,"",AL46-LOOKUP(2,1/(AI46:AK46<>""),AI46:AK46))) | IF(OR(F46="",AM46=""),"",IF(COUNT(AI46:AL46)=0,"",AM46-LOOKUP(2,1/(AI46:AL46<>""),AI46:AL46))) | IF(OR(F46="",AN46=""),"",IF(COUNT(AI46:AM46)=0,"",AN46-LOOKUP(2,1/(AI46:AM46<>""),AI46:AM46))) | IF(OR(F46="",AO46=""),"",IF(COUNT(AI46:AN46)=0,"",AO46-LOOKUP(2,1/(AI46:AN46<>""),AI46:AN46))) | IF(OR(F46="",AP46=""),"",IF(COUNT(AI46:AO46)=0,"",AP46-LOOKUP(2,1/(AI46:AO46<>""),AI46:AO46))) | IF(OR(F46="",AQ46=""),"",IF(COUNT(AI46:AP46)=0,"",AQ46-LOOKUP(2,1/(AI46:AP46<>""),AI46:AP46))) | IF(OR(F46="",AR46=""),"",IF(COUNT(AI46:AQ46)=0,"",AR46-LOOKUP(2,1/(AI46:AQ46<>""),AI46:AQ46))) | IF(OR(F46="",AS46=""),"",IF(COUNT(AI46:AR46)=0,"",AS46-LOOKUP(2,1/(AI46:AR46<>""),AI46:AR46))) | IF(OR(F46="",AT46=""),"",IF(COUNT(AI46:AS46)=0,"",AT46-LOOKUP(2,1/(AI46:AS46<>""),AI46:AS46))) | IF(OR(F46="",AU46=""),"",IF(COUNT(AI46:AT46)=0,"",AU46-LOOKUP(2,1/(AI46:AT46<>""),AI46:AT46))) | IF(OR(F46="",AV46=""),"",IF(COUNT(AI46:AU46)=0,"",AV46-LOOKUP(2,1/(AI46:AU46<>""),AI46:AU46))) | IF(J46="","All_Provinces",IFERROR(VLOOKUP(J46,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K46="","All_Districts",IFERROR(VLOOKUP(K46,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F47="","",ROW()-3) | [18 empty] | IF(AQ47="","",AQ47) |  |  |  | IF(W47<>"",W47,IF(OR(T47="",V47=""),"",EDATE(T47,V47))) |  |  |  |  | IF(F47="","",IF(COUNT(AI47:AV47)=0,IF(AA47="","Not started",AA47),SUBSTITUTE(LOOKUP(2,1/(AI47:AV47<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F47="",COUNT(AI47:AV47)=0),"",TODAY()-LOOKUP(2,1/(AI47:AV47<>""),AI47:AV47)) | IF(OR(F47="",COUNT(AI47:AV47)<2),"",LOOKUP(2,1/(AI47:AV47<>""),AI47:AV47)-MIN(AI47:AV47)) | IF(OR(AD47="",AC47="Not started",AC47=""),"",IFERROR(AD47-IF(VLOOKUP(AC47,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC47,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F47="","",IF(OR(AA47="Cancelled",AC47="Cancelled"),"Cancelled",IF(OR(AC47="Completed / Handover",Y47<>"",Z47>=100),"Completed — on track",IF(O47="Not awarded",IF(U47="",IF(X47="","No planned date",IF(TODAY()>X47,"Behind — past planned date",IF(X47-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U47,"Behind — award date passed",IF(U47-TODAY()<=30,"At risk — close to off track","On track"))),IF(X47="","No planned date",IF(AND(TODAY()>X47,OR(Z47="",Z47<100)),"Behind — past end date",IF(AND(T47<>"",X47<>"",Z47<>"",(Z47<100),((TODAY()-T47)/MAX(X47-T47,1)*100)-Z47>15),"Behind — progress lag",IF(AND(X47-TODAY()<=30,X47-TODAY()>=0,OR(Z47="",Z47<90)),"At risk — close to off track","On track")))))))) | IF(OR(F47="",AC47="Completed / Handover",AC47="Cancelled"),"",IF(O47="Not awarded",IF(U47<>"",U47-TODAY(),IF(X47="","",X47-TODAY())),IF(X47="","",X47-TODAY()))) | [14 empty] | IF(OR(F47="",AJ47=""),"",IF(COUNT(AI47:AI47)=0,"",AJ47-LOOKUP(2,1/(AI47:AI47<>""),AI47:AI47))) | IF(OR(F47="",AK47=""),"",IF(COUNT(AI47:AJ47)=0,"",AK47-LOOKUP(2,1/(AI47:AJ47<>""),AI47:AJ47))) | IF(OR(F47="",AL47=""),"",IF(COUNT(AI47:AK47)=0,"",AL47-LOOKUP(2,1/(AI47:AK47<>""),AI47:AK47))) | IF(OR(F47="",AM47=""),"",IF(COUNT(AI47:AL47)=0,"",AM47-LOOKUP(2,1/(AI47:AL47<>""),AI47:AL47))) | IF(OR(F47="",AN47=""),"",IF(COUNT(AI47:AM47)=0,"",AN47-LOOKUP(2,1/(AI47:AM47<>""),AI47:AM47))) | IF(OR(F47="",AO47=""),"",IF(COUNT(AI47:AN47)=0,"",AO47-LOOKUP(2,1/(AI47:AN47<>""),AI47:AN47))) | IF(OR(F47="",AP47=""),"",IF(COUNT(AI47:AO47)=0,"",AP47-LOOKUP(2,1/(AI47:AO47<>""),AI47:AO47))) | IF(OR(F47="",AQ47=""),"",IF(COUNT(AI47:AP47)=0,"",AQ47-LOOKUP(2,1/(AI47:AP47<>""),AI47:AP47))) | IF(OR(F47="",AR47=""),"",IF(COUNT(AI47:AQ47)=0,"",AR47-LOOKUP(2,1/(AI47:AQ47<>""),AI47:AQ47))) | IF(OR(F47="",AS47=""),"",IF(COUNT(AI47:AR47)=0,"",AS47-LOOKUP(2,1/(AI47:AR47<>""),AI47:AR47))) | IF(OR(F47="",AT47=""),"",IF(COUNT(AI47:AS47)=0,"",AT47-LOOKUP(2,1/(AI47:AS47<>""),AI47:AS47))) | IF(OR(F47="",AU47=""),"",IF(COUNT(AI47:AT47)=0,"",AU47-LOOKUP(2,1/(AI47:AT47<>""),AI47:AT47))) | IF(OR(F47="",AV47=""),"",IF(COUNT(AI47:AU47)=0,"",AV47-LOOKUP(2,1/(AI47:AU47<>""),AI47:AU47))) | IF(J47="","All_Provinces",IFERROR(VLOOKUP(J47,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K47="","All_Districts",IFERROR(VLOOKUP(K47,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F48="","",ROW()-3) | [18 empty] | IF(AQ48="","",AQ48) |  |  |  | IF(W48<>"",W48,IF(OR(T48="",V48=""),"",EDATE(T48,V48))) |  |  |  |  | IF(F48="","",IF(COUNT(AI48:AV48)=0,IF(AA48="","Not started",AA48),SUBSTITUTE(LOOKUP(2,1/(AI48:AV48<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F48="",COUNT(AI48:AV48)=0),"",TODAY()-LOOKUP(2,1/(AI48:AV48<>""),AI48:AV48)) | IF(OR(F48="",COUNT(AI48:AV48)<2),"",LOOKUP(2,1/(AI48:AV48<>""),AI48:AV48)-MIN(AI48:AV48)) | IF(OR(AD48="",AC48="Not started",AC48=""),"",IFERROR(AD48-IF(VLOOKUP(AC48,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC48,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F48="","",IF(OR(AA48="Cancelled",AC48="Cancelled"),"Cancelled",IF(OR(AC48="Completed / Handover",Y48<>"",Z48>=100),"Completed — on track",IF(O48="Not awarded",IF(U48="",IF(X48="","No planned date",IF(TODAY()>X48,"Behind — past planned date",IF(X48-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U48,"Behind — award date passed",IF(U48-TODAY()<=30,"At risk — close to off track","On track"))),IF(X48="","No planned date",IF(AND(TODAY()>X48,OR(Z48="",Z48<100)),"Behind — past end date",IF(AND(T48<>"",X48<>"",Z48<>"",(Z48<100),((TODAY()-T48)/MAX(X48-T48,1)*100)-Z48>15),"Behind — progress lag",IF(AND(X48-TODAY()<=30,X48-TODAY()>=0,OR(Z48="",Z48<90)),"At risk — close to off track","On track")))))))) | IF(OR(F48="",AC48="Completed / Handover",AC48="Cancelled"),"",IF(O48="Not awarded",IF(U48<>"",U48-TODAY(),IF(X48="","",X48-TODAY())),IF(X48="","",X48-TODAY()))) | [14 empty] | IF(OR(F48="",AJ48=""),"",IF(COUNT(AI48:AI48)=0,"",AJ48-LOOKUP(2,1/(AI48:AI48<>""),AI48:AI48))) | IF(OR(F48="",AK48=""),"",IF(COUNT(AI48:AJ48)=0,"",AK48-LOOKUP(2,1/(AI48:AJ48<>""),AI48:AJ48))) | IF(OR(F48="",AL48=""),"",IF(COUNT(AI48:AK48)=0,"",AL48-LOOKUP(2,1/(AI48:AK48<>""),AI48:AK48))) | IF(OR(F48="",AM48=""),"",IF(COUNT(AI48:AL48)=0,"",AM48-LOOKUP(2,1/(AI48:AL48<>""),AI48:AL48))) | IF(OR(F48="",AN48=""),"",IF(COUNT(AI48:AM48)=0,"",AN48-LOOKUP(2,1/(AI48:AM48<>""),AI48:AM48))) | IF(OR(F48="",AO48=""),"",IF(COUNT(AI48:AN48)=0,"",AO48-LOOKUP(2,1/(AI48:AN48<>""),AI48:AN48))) | IF(OR(F48="",AP48=""),"",IF(COUNT(AI48:AO48)=0,"",AP48-LOOKUP(2,1/(AI48:AO48<>""),AI48:AO48))) | IF(OR(F48="",AQ48=""),"",IF(COUNT(AI48:AP48)=0,"",AQ48-LOOKUP(2,1/(AI48:AP48<>""),AI48:AP48))) | IF(OR(F48="",AR48=""),"",IF(COUNT(AI48:AQ48)=0,"",AR48-LOOKUP(2,1/(AI48:AQ48<>""),AI48:AQ48))) | IF(OR(F48="",AS48=""),"",IF(COUNT(AI48:AR48)=0,"",AS48-LOOKUP(2,1/(AI48:AR48<>""),AI48:AR48))) | IF(OR(F48="",AT48=""),"",IF(COUNT(AI48:AS48)=0,"",AT48-LOOKUP(2,1/(AI48:AS48<>""),AI48:AS48))) | IF(OR(F48="",AU48=""),"",IF(COUNT(AI48:AT48)=0,"",AU48-LOOKUP(2,1/(AI48:AT48<>""),AI48:AT48))) | IF(OR(F48="",AV48=""),"",IF(COUNT(AI48:AU48)=0,"",AV48-LOOKUP(2,1/(AI48:AU48<>""),AI48:AU48))) | IF(J48="","All_Provinces",IFERROR(VLOOKUP(J48,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K48="","All_Districts",IFERROR(VLOOKUP(K48,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F49="","",ROW()-3) | [18 empty] | IF(AQ49="","",AQ49) |  |  |  | IF(W49<>"",W49,IF(OR(T49="",V49=""),"",EDATE(T49,V49))) |  |  |  |  | IF(F49="","",IF(COUNT(AI49:AV49)=0,IF(AA49="","Not started",AA49),SUBSTITUTE(LOOKUP(2,1/(AI49:AV49<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F49="",COUNT(AI49:AV49)=0),"",TODAY()-LOOKUP(2,1/(AI49:AV49<>""),AI49:AV49)) | IF(OR(F49="",COUNT(AI49:AV49)<2),"",LOOKUP(2,1/(AI49:AV49<>""),AI49:AV49)-MIN(AI49:AV49)) | IF(OR(AD49="",AC49="Not started",AC49=""),"",IFERROR(AD49-IF(VLOOKUP(AC49,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC49,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F49="","",IF(OR(AA49="Cancelled",AC49="Cancelled"),"Cancelled",IF(OR(AC49="Completed / Handover",Y49<>"",Z49>=100),"Completed — on track",IF(O49="Not awarded",IF(U49="",IF(X49="","No planned date",IF(TODAY()>X49,"Behind — past planned date",IF(X49-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U49,"Behind — award date passed",IF(U49-TODAY()<=30,"At risk — close to off track","On track"))),IF(X49="","No planned date",IF(AND(TODAY()>X49,OR(Z49="",Z49<100)),"Behind — past end date",IF(AND(T49<>"",X49<>"",Z49<>"",(Z49<100),((TODAY()-T49)/MAX(X49-T49,1)*100)-Z49>15),"Behind — progress lag",IF(AND(X49-TODAY()<=30,X49-TODAY()>=0,OR(Z49="",Z49<90)),"At risk — close to off track","On track")))))))) | IF(OR(F49="",AC49="Completed / Handover",AC49="Cancelled"),"",IF(O49="Not awarded",IF(U49<>"",U49-TODAY(),IF(X49="","",X49-TODAY())),IF(X49="","",X49-TODAY()))) | [14 empty] | IF(OR(F49="",AJ49=""),"",IF(COUNT(AI49:AI49)=0,"",AJ49-LOOKUP(2,1/(AI49:AI49<>""),AI49:AI49))) | IF(OR(F49="",AK49=""),"",IF(COUNT(AI49:AJ49)=0,"",AK49-LOOKUP(2,1/(AI49:AJ49<>""),AI49:AJ49))) | IF(OR(F49="",AL49=""),"",IF(COUNT(AI49:AK49)=0,"",AL49-LOOKUP(2,1/(AI49:AK49<>""),AI49:AK49))) | IF(OR(F49="",AM49=""),"",IF(COUNT(AI49:AL49)=0,"",AM49-LOOKUP(2,1/(AI49:AL49<>""),AI49:AL49))) | IF(OR(F49="",AN49=""),"",IF(COUNT(AI49:AM49)=0,"",AN49-LOOKUP(2,1/(AI49:AM49<>""),AI49:AM49))) | IF(OR(F49="",AO49=""),"",IF(COUNT(AI49:AN49)=0,"",AO49-LOOKUP(2,1/(AI49:AN49<>""),AI49:AN49))) | IF(OR(F49="",AP49=""),"",IF(COUNT(AI49:AO49)=0,"",AP49-LOOKUP(2,1/(AI49:AO49<>""),AI49:AO49))) | IF(OR(F49="",AQ49=""),"",IF(COUNT(AI49:AP49)=0,"",AQ49-LOOKUP(2,1/(AI49:AP49<>""),AI49:AP49))) | IF(OR(F49="",AR49=""),"",IF(COUNT(AI49:AQ49)=0,"",AR49-LOOKUP(2,1/(AI49:AQ49<>""),AI49:AQ49))) | IF(OR(F49="",AS49=""),"",IF(COUNT(AI49:AR49)=0,"",AS49-LOOKUP(2,1/(AI49:AR49<>""),AI49:AR49))) | IF(OR(F49="",AT49=""),"",IF(COUNT(AI49:AS49)=0,"",AT49-LOOKUP(2,1/(AI49:AS49<>""),AI49:AS49))) | IF(OR(F49="",AU49=""),"",IF(COUNT(AI49:AT49)=0,"",AU49-LOOKUP(2,1/(AI49:AT49<>""),AI49:AT49))) | IF(OR(F49="",AV49=""),"",IF(COUNT(AI49:AU49)=0,"",AV49-LOOKUP(2,1/(AI49:AU49<>""),AI49:AU49))) | IF(J49="","All_Provinces",IFERROR(VLOOKUP(J49,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K49="","All_Districts",IFERROR(VLOOKUP(K49,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F50="","",ROW()-3) | [18 empty] | IF(AQ50="","",AQ50) |  |  |  | IF(W50<>"",W50,IF(OR(T50="",V50=""),"",EDATE(T50,V50))) |  |  |  |  | IF(F50="","",IF(COUNT(AI50:AV50)=0,IF(AA50="","Not started",AA50),SUBSTITUTE(LOOKUP(2,1/(AI50:AV50<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F50="",COUNT(AI50:AV50)=0),"",TODAY()-LOOKUP(2,1/(AI50:AV50<>""),AI50:AV50)) | IF(OR(F50="",COUNT(AI50:AV50)<2),"",LOOKUP(2,1/(AI50:AV50<>""),AI50:AV50)-MIN(AI50:AV50)) | IF(OR(AD50="",AC50="Not started",AC50=""),"",IFERROR(AD50-IF(VLOOKUP(AC50,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC50,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F50="","",IF(OR(AA50="Cancelled",AC50="Cancelled"),"Cancelled",IF(OR(AC50="Completed / Handover",Y50<>"",Z50>=100),"Completed — on track",IF(O50="Not awarded",IF(U50="",IF(X50="","No planned date",IF(TODAY()>X50,"Behind — past planned date",IF(X50-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U50,"Behind — award date passed",IF(U50-TODAY()<=30,"At risk — close to off track","On track"))),IF(X50="","No planned date",IF(AND(TODAY()>X50,OR(Z50="",Z50<100)),"Behind — past end date",IF(AND(T50<>"",X50<>"",Z50<>"",(Z50<100),((TODAY()-T50)/MAX(X50-T50,1)*100)-Z50>15),"Behind — progress lag",IF(AND(X50-TODAY()<=30,X50-TODAY()>=0,OR(Z50="",Z50<90)),"At risk — close to off track","On track")))))))) | IF(OR(F50="",AC50="Completed / Handover",AC50="Cancelled"),"",IF(O50="Not awarded",IF(U50<>"",U50-TODAY(),IF(X50="","",X50-TODAY())),IF(X50="","",X50-TODAY()))) | [14 empty] | IF(OR(F50="",AJ50=""),"",IF(COUNT(AI50:AI50)=0,"",AJ50-LOOKUP(2,1/(AI50:AI50<>""),AI50:AI50))) | IF(OR(F50="",AK50=""),"",IF(COUNT(AI50:AJ50)=0,"",AK50-LOOKUP(2,1/(AI50:AJ50<>""),AI50:AJ50))) | IF(OR(F50="",AL50=""),"",IF(COUNT(AI50:AK50)=0,"",AL50-LOOKUP(2,1/(AI50:AK50<>""),AI50:AK50))) | IF(OR(F50="",AM50=""),"",IF(COUNT(AI50:AL50)=0,"",AM50-LOOKUP(2,1/(AI50:AL50<>""),AI50:AL50))) | IF(OR(F50="",AN50=""),"",IF(COUNT(AI50:AM50)=0,"",AN50-LOOKUP(2,1/(AI50:AM50<>""),AI50:AM50))) | IF(OR(F50="",AO50=""),"",IF(COUNT(AI50:AN50)=0,"",AO50-LOOKUP(2,1/(AI50:AN50<>""),AI50:AN50))) | IF(OR(F50="",AP50=""),"",IF(COUNT(AI50:AO50)=0,"",AP50-LOOKUP(2,1/(AI50:AO50<>""),AI50:AO50))) | IF(OR(F50="",AQ50=""),"",IF(COUNT(AI50:AP50)=0,"",AQ50-LOOKUP(2,1/(AI50:AP50<>""),AI50:AP50))) | IF(OR(F50="",AR50=""),"",IF(COUNT(AI50:AQ50)=0,"",AR50-LOOKUP(2,1/(AI50:AQ50<>""),AI50:AQ50))) | IF(OR(F50="",AS50=""),"",IF(COUNT(AI50:AR50)=0,"",AS50-LOOKUP(2,1/(AI50:AR50<>""),AI50:AR50))) | IF(OR(F50="",AT50=""),"",IF(COUNT(AI50:AS50)=0,"",AT50-LOOKUP(2,1/(AI50:AS50<>""),AI50:AS50))) | IF(OR(F50="",AU50=""),"",IF(COUNT(AI50:AT50)=0,"",AU50-LOOKUP(2,1/(AI50:AT50<>""),AI50:AT50))) | IF(OR(F50="",AV50=""),"",IF(COUNT(AI50:AU50)=0,"",AV50-LOOKUP(2,1/(AI50:AU50<>""),AI50:AU50))) | IF(J50="","All_Provinces",IFERROR(VLOOKUP(J50,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K50="","All_Districts",IFERROR(VLOOKUP(K50,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F51="","",ROW()-3) | [18 empty] | IF(AQ51="","",AQ51) |  |  |  | IF(W51<>"",W51,IF(OR(T51="",V51=""),"",EDATE(T51,V51))) |  |  |  |  | IF(F51="","",IF(COUNT(AI51:AV51)=0,IF(AA51="","Not started",AA51),SUBSTITUTE(LOOKUP(2,1/(AI51:AV51<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F51="",COUNT(AI51:AV51)=0),"",TODAY()-LOOKUP(2,1/(AI51:AV51<>""),AI51:AV51)) | IF(OR(F51="",COUNT(AI51:AV51)<2),"",LOOKUP(2,1/(AI51:AV51<>""),AI51:AV51)-MIN(AI51:AV51)) | IF(OR(AD51="",AC51="Not started",AC51=""),"",IFERROR(AD51-IF(VLOOKUP(AC51,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC51,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F51="","",IF(OR(AA51="Cancelled",AC51="Cancelled"),"Cancelled",IF(OR(AC51="Completed / Handover",Y51<>"",Z51>=100),"Completed — on track",IF(O51="Not awarded",IF(U51="",IF(X51="","No planned date",IF(TODAY()>X51,"Behind — past planned date",IF(X51-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U51,"Behind — award date passed",IF(U51-TODAY()<=30,"At risk — close to off track","On track"))),IF(X51="","No planned date",IF(AND(TODAY()>X51,OR(Z51="",Z51<100)),"Behind — past end date",IF(AND(T51<>"",X51<>"",Z51<>"",(Z51<100),((TODAY()-T51)/MAX(X51-T51,1)*100)-Z51>15),"Behind — progress lag",IF(AND(X51-TODAY()<=30,X51-TODAY()>=0,OR(Z51="",Z51<90)),"At risk — close to off track","On track")))))))) | IF(OR(F51="",AC51="Completed / Handover",AC51="Cancelled"),"",IF(O51="Not awarded",IF(U51<>"",U51-TODAY(),IF(X51="","",X51-TODAY())),IF(X51="","",X51-TODAY()))) | [14 empty] | IF(OR(F51="",AJ51=""),"",IF(COUNT(AI51:AI51)=0,"",AJ51-LOOKUP(2,1/(AI51:AI51<>""),AI51:AI51))) | IF(OR(F51="",AK51=""),"",IF(COUNT(AI51:AJ51)=0,"",AK51-LOOKUP(2,1/(AI51:AJ51<>""),AI51:AJ51))) | IF(OR(F51="",AL51=""),"",IF(COUNT(AI51:AK51)=0,"",AL51-LOOKUP(2,1/(AI51:AK51<>""),AI51:AK51))) | IF(OR(F51="",AM51=""),"",IF(COUNT(AI51:AL51)=0,"",AM51-LOOKUP(2,1/(AI51:AL51<>""),AI51:AL51))) | IF(OR(F51="",AN51=""),"",IF(COUNT(AI51:AM51)=0,"",AN51-LOOKUP(2,1/(AI51:AM51<>""),AI51:AM51))) | IF(OR(F51="",AO51=""),"",IF(COUNT(AI51:AN51)=0,"",AO51-LOOKUP(2,1/(AI51:AN51<>""),AI51:AN51))) | IF(OR(F51="",AP51=""),"",IF(COUNT(AI51:AO51)=0,"",AP51-LOOKUP(2,1/(AI51:AO51<>""),AI51:AO51))) | IF(OR(F51="",AQ51=""),"",IF(COUNT(AI51:AP51)=0,"",AQ51-LOOKUP(2,1/(AI51:AP51<>""),AI51:AP51))) | IF(OR(F51="",AR51=""),"",IF(COUNT(AI51:AQ51)=0,"",AR51-LOOKUP(2,1/(AI51:AQ51<>""),AI51:AQ51))) | IF(OR(F51="",AS51=""),"",IF(COUNT(AI51:AR51)=0,"",AS51-LOOKUP(2,1/(AI51:AR51<>""),AI51:AR51))) | IF(OR(F51="",AT51=""),"",IF(COUNT(AI51:AS51)=0,"",AT51-LOOKUP(2,1/(AI51:AS51<>""),AI51:AS51))) | IF(OR(F51="",AU51=""),"",IF(COUNT(AI51:AT51)=0,"",AU51-LOOKUP(2,1/(AI51:AT51<>""),AI51:AT51))) | IF(OR(F51="",AV51=""),"",IF(COUNT(AI51:AU51)=0,"",AV51-LOOKUP(2,1/(AI51:AU51<>""),AI51:AU51))) | IF(J51="","All_Provinces",IFERROR(VLOOKUP(J51,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K51="","All_Districts",IFERROR(VLOOKUP(K51,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F52="","",ROW()-3) | [18 empty] | IF(AQ52="","",AQ52) |  |  |  | IF(W52<>"",W52,IF(OR(T52="",V52=""),"",EDATE(T52,V52))) |  |  |  |  | IF(F52="","",IF(COUNT(AI52:AV52)=0,IF(AA52="","Not started",AA52),SUBSTITUTE(LOOKUP(2,1/(AI52:AV52<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F52="",COUNT(AI52:AV52)=0),"",TODAY()-LOOKUP(2,1/(AI52:AV52<>""),AI52:AV52)) | IF(OR(F52="",COUNT(AI52:AV52)<2),"",LOOKUP(2,1/(AI52:AV52<>""),AI52:AV52)-MIN(AI52:AV52)) | IF(OR(AD52="",AC52="Not started",AC52=""),"",IFERROR(AD52-IF(VLOOKUP(AC52,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC52,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F52="","",IF(OR(AA52="Cancelled",AC52="Cancelled"),"Cancelled",IF(OR(AC52="Completed / Handover",Y52<>"",Z52>=100),"Completed — on track",IF(O52="Not awarded",IF(U52="",IF(X52="","No planned date",IF(TODAY()>X52,"Behind — past planned date",IF(X52-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U52,"Behind — award date passed",IF(U52-TODAY()<=30,"At risk — close to off track","On track"))),IF(X52="","No planned date",IF(AND(TODAY()>X52,OR(Z52="",Z52<100)),"Behind — past end date",IF(AND(T52<>"",X52<>"",Z52<>"",(Z52<100),((TODAY()-T52)/MAX(X52-T52,1)*100)-Z52>15),"Behind — progress lag",IF(AND(X52-TODAY()<=30,X52-TODAY()>=0,OR(Z52="",Z52<90)),"At risk — close to off track","On track")))))))) | IF(OR(F52="",AC52="Completed / Handover",AC52="Cancelled"),"",IF(O52="Not awarded",IF(U52<>"",U52-TODAY(),IF(X52="","",X52-TODAY())),IF(X52="","",X52-TODAY()))) | [14 empty] | IF(OR(F52="",AJ52=""),"",IF(COUNT(AI52:AI52)=0,"",AJ52-LOOKUP(2,1/(AI52:AI52<>""),AI52:AI52))) | IF(OR(F52="",AK52=""),"",IF(COUNT(AI52:AJ52)=0,"",AK52-LOOKUP(2,1/(AI52:AJ52<>""),AI52:AJ52))) | IF(OR(F52="",AL52=""),"",IF(COUNT(AI52:AK52)=0,"",AL52-LOOKUP(2,1/(AI52:AK52<>""),AI52:AK52))) | IF(OR(F52="",AM52=""),"",IF(COUNT(AI52:AL52)=0,"",AM52-LOOKUP(2,1/(AI52:AL52<>""),AI52:AL52))) | IF(OR(F52="",AN52=""),"",IF(COUNT(AI52:AM52)=0,"",AN52-LOOKUP(2,1/(AI52:AM52<>""),AI52:AM52))) | IF(OR(F52="",AO52=""),"",IF(COUNT(AI52:AN52)=0,"",AO52-LOOKUP(2,1/(AI52:AN52<>""),AI52:AN52))) | IF(OR(F52="",AP52=""),"",IF(COUNT(AI52:AO52)=0,"",AP52-LOOKUP(2,1/(AI52:AO52<>""),AI52:AO52))) | IF(OR(F52="",AQ52=""),"",IF(COUNT(AI52:AP52)=0,"",AQ52-LOOKUP(2,1/(AI52:AP52<>""),AI52:AP52))) | IF(OR(F52="",AR52=""),"",IF(COUNT(AI52:AQ52)=0,"",AR52-LOOKUP(2,1/(AI52:AQ52<>""),AI52:AQ52))) | IF(OR(F52="",AS52=""),"",IF(COUNT(AI52:AR52)=0,"",AS52-LOOKUP(2,1/(AI52:AR52<>""),AI52:AR52))) | IF(OR(F52="",AT52=""),"",IF(COUNT(AI52:AS52)=0,"",AT52-LOOKUP(2,1/(AI52:AS52<>""),AI52:AS52))) | IF(OR(F52="",AU52=""),"",IF(COUNT(AI52:AT52)=0,"",AU52-LOOKUP(2,1/(AI52:AT52<>""),AI52:AT52))) | IF(OR(F52="",AV52=""),"",IF(COUNT(AI52:AU52)=0,"",AV52-LOOKUP(2,1/(AI52:AU52<>""),AI52:AU52))) | IF(J52="","All_Provinces",IFERROR(VLOOKUP(J52,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K52="","All_Districts",IFERROR(VLOOKUP(K52,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F53="","",ROW()-3) | [18 empty] | IF(AQ53="","",AQ53) |  |  |  | IF(W53<>"",W53,IF(OR(T53="",V53=""),"",EDATE(T53,V53))) |  |  |  |  | IF(F53="","",IF(COUNT(AI53:AV53)=0,IF(AA53="","Not started",AA53),SUBSTITUTE(LOOKUP(2,1/(AI53:AV53<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F53="",COUNT(AI53:AV53)=0),"",TODAY()-LOOKUP(2,1/(AI53:AV53<>""),AI53:AV53)) | IF(OR(F53="",COUNT(AI53:AV53)<2),"",LOOKUP(2,1/(AI53:AV53<>""),AI53:AV53)-MIN(AI53:AV53)) | IF(OR(AD53="",AC53="Not started",AC53=""),"",IFERROR(AD53-IF(VLOOKUP(AC53,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC53,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F53="","",IF(OR(AA53="Cancelled",AC53="Cancelled"),"Cancelled",IF(OR(AC53="Completed / Handover",Y53<>"",Z53>=100),"Completed — on track",IF(O53="Not awarded",IF(U53="",IF(X53="","No planned date",IF(TODAY()>X53,"Behind — past planned date",IF(X53-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U53,"Behind — award date passed",IF(U53-TODAY()<=30,"At risk — close to off track","On track"))),IF(X53="","No planned date",IF(AND(TODAY()>X53,OR(Z53="",Z53<100)),"Behind — past end date",IF(AND(T53<>"",X53<>"",Z53<>"",(Z53<100),((TODAY()-T53)/MAX(X53-T53,1)*100)-Z53>15),"Behind — progress lag",IF(AND(X53-TODAY()<=30,X53-TODAY()>=0,OR(Z53="",Z53<90)),"At risk — close to off track","On track")))))))) | IF(OR(F53="",AC53="Completed / Handover",AC53="Cancelled"),"",IF(O53="Not awarded",IF(U53<>"",U53-TODAY(),IF(X53="","",X53-TODAY())),IF(X53="","",X53-TODAY()))) | [14 empty] | IF(OR(F53="",AJ53=""),"",IF(COUNT(AI53:AI53)=0,"",AJ53-LOOKUP(2,1/(AI53:AI53<>""),AI53:AI53))) | IF(OR(F53="",AK53=""),"",IF(COUNT(AI53:AJ53)=0,"",AK53-LOOKUP(2,1/(AI53:AJ53<>""),AI53:AJ53))) | IF(OR(F53="",AL53=""),"",IF(COUNT(AI53:AK53)=0,"",AL53-LOOKUP(2,1/(AI53:AK53<>""),AI53:AK53))) | IF(OR(F53="",AM53=""),"",IF(COUNT(AI53:AL53)=0,"",AM53-LOOKUP(2,1/(AI53:AL53<>""),AI53:AL53))) | IF(OR(F53="",AN53=""),"",IF(COUNT(AI53:AM53)=0,"",AN53-LOOKUP(2,1/(AI53:AM53<>""),AI53:AM53))) | IF(OR(F53="",AO53=""),"",IF(COUNT(AI53:AN53)=0,"",AO53-LOOKUP(2,1/(AI53:AN53<>""),AI53:AN53))) | IF(OR(F53="",AP53=""),"",IF(COUNT(AI53:AO53)=0,"",AP53-LOOKUP(2,1/(AI53:AO53<>""),AI53:AO53))) | IF(OR(F53="",AQ53=""),"",IF(COUNT(AI53:AP53)=0,"",AQ53-LOOKUP(2,1/(AI53:AP53<>""),AI53:AP53))) | IF(OR(F53="",AR53=""),"",IF(COUNT(AI53:AQ53)=0,"",AR53-LOOKUP(2,1/(AI53:AQ53<>""),AI53:AQ53))) | IF(OR(F53="",AS53=""),"",IF(COUNT(AI53:AR53)=0,"",AS53-LOOKUP(2,1/(AI53:AR53<>""),AI53:AR53))) | IF(OR(F53="",AT53=""),"",IF(COUNT(AI53:AS53)=0,"",AT53-LOOKUP(2,1/(AI53:AS53<>""),AI53:AS53))) | IF(OR(F53="",AU53=""),"",IF(COUNT(AI53:AT53)=0,"",AU53-LOOKUP(2,1/(AI53:AT53<>""),AI53:AT53))) | IF(OR(F53="",AV53=""),"",IF(COUNT(AI53:AU53)=0,"",AV53-LOOKUP(2,1/(AI53:AU53<>""),AI53:AU53))) | IF(J53="","All_Provinces",IFERROR(VLOOKUP(J53,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K53="","All_Districts",IFERROR(VLOOKUP(K53,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F54="","",ROW()-3) | [18 empty] | IF(AQ54="","",AQ54) |  |  |  | IF(W54<>"",W54,IF(OR(T54="",V54=""),"",EDATE(T54,V54))) |  |  |  |  | IF(F54="","",IF(COUNT(AI54:AV54)=0,IF(AA54="","Not started",AA54),SUBSTITUTE(LOOKUP(2,1/(AI54:AV54<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F54="",COUNT(AI54:AV54)=0),"",TODAY()-LOOKUP(2,1/(AI54:AV54<>""),AI54:AV54)) | IF(OR(F54="",COUNT(AI54:AV54)<2),"",LOOKUP(2,1/(AI54:AV54<>""),AI54:AV54)-MIN(AI54:AV54)) | IF(OR(AD54="",AC54="Not started",AC54=""),"",IFERROR(AD54-IF(VLOOKUP(AC54,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC54,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F54="","",IF(OR(AA54="Cancelled",AC54="Cancelled"),"Cancelled",IF(OR(AC54="Completed / Handover",Y54<>"",Z54>=100),"Completed — on track",IF(O54="Not awarded",IF(U54="",IF(X54="","No planned date",IF(TODAY()>X54,"Behind — past planned date",IF(X54-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U54,"Behind — award date passed",IF(U54-TODAY()<=30,"At risk — close to off track","On track"))),IF(X54="","No planned date",IF(AND(TODAY()>X54,OR(Z54="",Z54<100)),"Behind — past end date",IF(AND(T54<>"",X54<>"",Z54<>"",(Z54<100),((TODAY()-T54)/MAX(X54-T54,1)*100)-Z54>15),"Behind — progress lag",IF(AND(X54-TODAY()<=30,X54-TODAY()>=0,OR(Z54="",Z54<90)),"At risk — close to off track","On track")))))))) | IF(OR(F54="",AC54="Completed / Handover",AC54="Cancelled"),"",IF(O54="Not awarded",IF(U54<>"",U54-TODAY(),IF(X54="","",X54-TODAY())),IF(X54="","",X54-TODAY()))) | [14 empty] | IF(OR(F54="",AJ54=""),"",IF(COUNT(AI54:AI54)=0,"",AJ54-LOOKUP(2,1/(AI54:AI54<>""),AI54:AI54))) | IF(OR(F54="",AK54=""),"",IF(COUNT(AI54:AJ54)=0,"",AK54-LOOKUP(2,1/(AI54:AJ54<>""),AI54:AJ54))) | IF(OR(F54="",AL54=""),"",IF(COUNT(AI54:AK54)=0,"",AL54-LOOKUP(2,1/(AI54:AK54<>""),AI54:AK54))) | IF(OR(F54="",AM54=""),"",IF(COUNT(AI54:AL54)=0,"",AM54-LOOKUP(2,1/(AI54:AL54<>""),AI54:AL54))) | IF(OR(F54="",AN54=""),"",IF(COUNT(AI54:AM54)=0,"",AN54-LOOKUP(2,1/(AI54:AM54<>""),AI54:AM54))) | IF(OR(F54="",AO54=""),"",IF(COUNT(AI54:AN54)=0,"",AO54-LOOKUP(2,1/(AI54:AN54<>""),AI54:AN54))) | IF(OR(F54="",AP54=""),"",IF(COUNT(AI54:AO54)=0,"",AP54-LOOKUP(2,1/(AI54:AO54<>""),AI54:AO54))) | IF(OR(F54="",AQ54=""),"",IF(COUNT(AI54:AP54)=0,"",AQ54-LOOKUP(2,1/(AI54:AP54<>""),AI54:AP54))) | IF(OR(F54="",AR54=""),"",IF(COUNT(AI54:AQ54)=0,"",AR54-LOOKUP(2,1/(AI54:AQ54<>""),AI54:AQ54))) | IF(OR(F54="",AS54=""),"",IF(COUNT(AI54:AR54)=0,"",AS54-LOOKUP(2,1/(AI54:AR54<>""),AI54:AR54))) | IF(OR(F54="",AT54=""),"",IF(COUNT(AI54:AS54)=0,"",AT54-LOOKUP(2,1/(AI54:AS54<>""),AI54:AS54))) | IF(OR(F54="",AU54=""),"",IF(COUNT(AI54:AT54)=0,"",AU54-LOOKUP(2,1/(AI54:AT54<>""),AI54:AT54))) | IF(OR(F54="",AV54=""),"",IF(COUNT(AI54:AU54)=0,"",AV54-LOOKUP(2,1/(AI54:AU54<>""),AI54:AU54))) | IF(J54="","All_Provinces",IFERROR(VLOOKUP(J54,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K54="","All_Districts",IFERROR(VLOOKUP(K54,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F55="","",ROW()-3) | [18 empty] | IF(AQ55="","",AQ55) |  |  |  | IF(W55<>"",W55,IF(OR(T55="",V55=""),"",EDATE(T55,V55))) |  |  |  |  | IF(F55="","",IF(COUNT(AI55:AV55)=0,IF(AA55="","Not started",AA55),SUBSTITUTE(LOOKUP(2,1/(AI55:AV55<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F55="",COUNT(AI55:AV55)=0),"",TODAY()-LOOKUP(2,1/(AI55:AV55<>""),AI55:AV55)) | IF(OR(F55="",COUNT(AI55:AV55)<2),"",LOOKUP(2,1/(AI55:AV55<>""),AI55:AV55)-MIN(AI55:AV55)) | IF(OR(AD55="",AC55="Not started",AC55=""),"",IFERROR(AD55-IF(VLOOKUP(AC55,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC55,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F55="","",IF(OR(AA55="Cancelled",AC55="Cancelled"),"Cancelled",IF(OR(AC55="Completed / Handover",Y55<>"",Z55>=100),"Completed — on track",IF(O55="Not awarded",IF(U55="",IF(X55="","No planned date",IF(TODAY()>X55,"Behind — past planned date",IF(X55-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U55,"Behind — award date passed",IF(U55-TODAY()<=30,"At risk — close to off track","On track"))),IF(X55="","No planned date",IF(AND(TODAY()>X55,OR(Z55="",Z55<100)),"Behind — past end date",IF(AND(T55<>"",X55<>"",Z55<>"",(Z55<100),((TODAY()-T55)/MAX(X55-T55,1)*100)-Z55>15),"Behind — progress lag",IF(AND(X55-TODAY()<=30,X55-TODAY()>=0,OR(Z55="",Z55<90)),"At risk — close to off track","On track")))))))) | IF(OR(F55="",AC55="Completed / Handover",AC55="Cancelled"),"",IF(O55="Not awarded",IF(U55<>"",U55-TODAY(),IF(X55="","",X55-TODAY())),IF(X55="","",X55-TODAY()))) | [14 empty] | IF(OR(F55="",AJ55=""),"",IF(COUNT(AI55:AI55)=0,"",AJ55-LOOKUP(2,1/(AI55:AI55<>""),AI55:AI55))) | IF(OR(F55="",AK55=""),"",IF(COUNT(AI55:AJ55)=0,"",AK55-LOOKUP(2,1/(AI55:AJ55<>""),AI55:AJ55))) | IF(OR(F55="",AL55=""),"",IF(COUNT(AI55:AK55)=0,"",AL55-LOOKUP(2,1/(AI55:AK55<>""),AI55:AK55))) | IF(OR(F55="",AM55=""),"",IF(COUNT(AI55:AL55)=0,"",AM55-LOOKUP(2,1/(AI55:AL55<>""),AI55:AL55))) | IF(OR(F55="",AN55=""),"",IF(COUNT(AI55:AM55)=0,"",AN55-LOOKUP(2,1/(AI55:AM55<>""),AI55:AM55))) | IF(OR(F55="",AO55=""),"",IF(COUNT(AI55:AN55)=0,"",AO55-LOOKUP(2,1/(AI55:AN55<>""),AI55:AN55))) | IF(OR(F55="",AP55=""),"",IF(COUNT(AI55:AO55)=0,"",AP55-LOOKUP(2,1/(AI55:AO55<>""),AI55:AO55))) | IF(OR(F55="",AQ55=""),"",IF(COUNT(AI55:AP55)=0,"",AQ55-LOOKUP(2,1/(AI55:AP55<>""),AI55:AP55))) | IF(OR(F55="",AR55=""),"",IF(COUNT(AI55:AQ55)=0,"",AR55-LOOKUP(2,1/(AI55:AQ55<>""),AI55:AQ55))) | IF(OR(F55="",AS55=""),"",IF(COUNT(AI55:AR55)=0,"",AS55-LOOKUP(2,1/(AI55:AR55<>""),AI55:AR55))) | IF(OR(F55="",AT55=""),"",IF(COUNT(AI55:AS55)=0,"",AT55-LOOKUP(2,1/(AI55:AS55<>""),AI55:AS55))) | IF(OR(F55="",AU55=""),"",IF(COUNT(AI55:AT55)=0,"",AU55-LOOKUP(2,1/(AI55:AT55<>""),AI55:AT55))) | IF(OR(F55="",AV55=""),"",IF(COUNT(AI55:AU55)=0,"",AV55-LOOKUP(2,1/(AI55:AU55<>""),AI55:AU55))) | IF(J55="","All_Provinces",IFERROR(VLOOKUP(J55,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K55="","All_Districts",IFERROR(VLOOKUP(K55,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F56="","",ROW()-3) | [18 empty] | IF(AQ56="","",AQ56) |  |  |  | IF(W56<>"",W56,IF(OR(T56="",V56=""),"",EDATE(T56,V56))) |  |  |  |  | IF(F56="","",IF(COUNT(AI56:AV56)=0,IF(AA56="","Not started",AA56),SUBSTITUTE(LOOKUP(2,1/(AI56:AV56<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F56="",COUNT(AI56:AV56)=0),"",TODAY()-LOOKUP(2,1/(AI56:AV56<>""),AI56:AV56)) | IF(OR(F56="",COUNT(AI56:AV56)<2),"",LOOKUP(2,1/(AI56:AV56<>""),AI56:AV56)-MIN(AI56:AV56)) | IF(OR(AD56="",AC56="Not started",AC56=""),"",IFERROR(AD56-IF(VLOOKUP(AC56,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC56,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F56="","",IF(OR(AA56="Cancelled",AC56="Cancelled"),"Cancelled",IF(OR(AC56="Completed / Handover",Y56<>"",Z56>=100),"Completed — on track",IF(O56="Not awarded",IF(U56="",IF(X56="","No planned date",IF(TODAY()>X56,"Behind — past planned date",IF(X56-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U56,"Behind — award date passed",IF(U56-TODAY()<=30,"At risk — close to off track","On track"))),IF(X56="","No planned date",IF(AND(TODAY()>X56,OR(Z56="",Z56<100)),"Behind — past end date",IF(AND(T56<>"",X56<>"",Z56<>"",(Z56<100),((TODAY()-T56)/MAX(X56-T56,1)*100)-Z56>15),"Behind — progress lag",IF(AND(X56-TODAY()<=30,X56-TODAY()>=0,OR(Z56="",Z56<90)),"At risk — close to off track","On track")))))))) | IF(OR(F56="",AC56="Completed / Handover",AC56="Cancelled"),"",IF(O56="Not awarded",IF(U56<>"",U56-TODAY(),IF(X56="","",X56-TODAY())),IF(X56="","",X56-TODAY()))) | [14 empty] | IF(OR(F56="",AJ56=""),"",IF(COUNT(AI56:AI56)=0,"",AJ56-LOOKUP(2,1/(AI56:AI56<>""),AI56:AI56))) | IF(OR(F56="",AK56=""),"",IF(COUNT(AI56:AJ56)=0,"",AK56-LOOKUP(2,1/(AI56:AJ56<>""),AI56:AJ56))) | IF(OR(F56="",AL56=""),"",IF(COUNT(AI56:AK56)=0,"",AL56-LOOKUP(2,1/(AI56:AK56<>""),AI56:AK56))) | IF(OR(F56="",AM56=""),"",IF(COUNT(AI56:AL56)=0,"",AM56-LOOKUP(2,1/(AI56:AL56<>""),AI56:AL56))) | IF(OR(F56="",AN56=""),"",IF(COUNT(AI56:AM56)=0,"",AN56-LOOKUP(2,1/(AI56:AM56<>""),AI56:AM56))) | IF(OR(F56="",AO56=""),"",IF(COUNT(AI56:AN56)=0,"",AO56-LOOKUP(2,1/(AI56:AN56<>""),AI56:AN56))) | IF(OR(F56="",AP56=""),"",IF(COUNT(AI56:AO56)=0,"",AP56-LOOKUP(2,1/(AI56:AO56<>""),AI56:AO56))) | IF(OR(F56="",AQ56=""),"",IF(COUNT(AI56:AP56)=0,"",AQ56-LOOKUP(2,1/(AI56:AP56<>""),AI56:AP56))) | IF(OR(F56="",AR56=""),"",IF(COUNT(AI56:AQ56)=0,"",AR56-LOOKUP(2,1/(AI56:AQ56<>""),AI56:AQ56))) | IF(OR(F56="",AS56=""),"",IF(COUNT(AI56:AR56)=0,"",AS56-LOOKUP(2,1/(AI56:AR56<>""),AI56:AR56))) | IF(OR(F56="",AT56=""),"",IF(COUNT(AI56:AS56)=0,"",AT56-LOOKUP(2,1/(AI56:AS56<>""),AI56:AS56))) | IF(OR(F56="",AU56=""),"",IF(COUNT(AI56:AT56)=0,"",AU56-LOOKUP(2,1/(AI56:AT56<>""),AI56:AT56))) | IF(OR(F56="",AV56=""),"",IF(COUNT(AI56:AU56)=0,"",AV56-LOOKUP(2,1/(AI56:AU56<>""),AI56:AU56))) | IF(J56="","All_Provinces",IFERROR(VLOOKUP(J56,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K56="","All_Districts",IFERROR(VLOOKUP(K56,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F57="","",ROW()-3) | [18 empty] | IF(AQ57="","",AQ57) |  |  |  | IF(W57<>"",W57,IF(OR(T57="",V57=""),"",EDATE(T57,V57))) |  |  |  |  | IF(F57="","",IF(COUNT(AI57:AV57)=0,IF(AA57="","Not started",AA57),SUBSTITUTE(LOOKUP(2,1/(AI57:AV57<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F57="",COUNT(AI57:AV57)=0),"",TODAY()-LOOKUP(2,1/(AI57:AV57<>""),AI57:AV57)) | IF(OR(F57="",COUNT(AI57:AV57)<2),"",LOOKUP(2,1/(AI57:AV57<>""),AI57:AV57)-MIN(AI57:AV57)) | IF(OR(AD57="",AC57="Not started",AC57=""),"",IFERROR(AD57-IF(VLOOKUP(AC57,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC57,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F57="","",IF(OR(AA57="Cancelled",AC57="Cancelled"),"Cancelled",IF(OR(AC57="Completed / Handover",Y57<>"",Z57>=100),"Completed — on track",IF(O57="Not awarded",IF(U57="",IF(X57="","No planned date",IF(TODAY()>X57,"Behind — past planned date",IF(X57-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U57,"Behind — award date passed",IF(U57-TODAY()<=30,"At risk — close to off track","On track"))),IF(X57="","No planned date",IF(AND(TODAY()>X57,OR(Z57="",Z57<100)),"Behind — past end date",IF(AND(T57<>"",X57<>"",Z57<>"",(Z57<100),((TODAY()-T57)/MAX(X57-T57,1)*100)-Z57>15),"Behind — progress lag",IF(AND(X57-TODAY()<=30,X57-TODAY()>=0,OR(Z57="",Z57<90)),"At risk — close to off track","On track")))))))) | IF(OR(F57="",AC57="Completed / Handover",AC57="Cancelled"),"",IF(O57="Not awarded",IF(U57<>"",U57-TODAY(),IF(X57="","",X57-TODAY())),IF(X57="","",X57-TODAY()))) | [14 empty] | IF(OR(F57="",AJ57=""),"",IF(COUNT(AI57:AI57)=0,"",AJ57-LOOKUP(2,1/(AI57:AI57<>""),AI57:AI57))) | IF(OR(F57="",AK57=""),"",IF(COUNT(AI57:AJ57)=0,"",AK57-LOOKUP(2,1/(AI57:AJ57<>""),AI57:AJ57))) | IF(OR(F57="",AL57=""),"",IF(COUNT(AI57:AK57)=0,"",AL57-LOOKUP(2,1/(AI57:AK57<>""),AI57:AK57))) | IF(OR(F57="",AM57=""),"",IF(COUNT(AI57:AL57)=0,"",AM57-LOOKUP(2,1/(AI57:AL57<>""),AI57:AL57))) | IF(OR(F57="",AN57=""),"",IF(COUNT(AI57:AM57)=0,"",AN57-LOOKUP(2,1/(AI57:AM57<>""),AI57:AM57))) | IF(OR(F57="",AO57=""),"",IF(COUNT(AI57:AN57)=0,"",AO57-LOOKUP(2,1/(AI57:AN57<>""),AI57:AN57))) | IF(OR(F57="",AP57=""),"",IF(COUNT(AI57:AO57)=0,"",AP57-LOOKUP(2,1/(AI57:AO57<>""),AI57:AO57))) | IF(OR(F57="",AQ57=""),"",IF(COUNT(AI57:AP57)=0,"",AQ57-LOOKUP(2,1/(AI57:AP57<>""),AI57:AP57))) | IF(OR(F57="",AR57=""),"",IF(COUNT(AI57:AQ57)=0,"",AR57-LOOKUP(2,1/(AI57:AQ57<>""),AI57:AQ57))) | IF(OR(F57="",AS57=""),"",IF(COUNT(AI57:AR57)=0,"",AS57-LOOKUP(2,1/(AI57:AR57<>""),AI57:AR57))) | IF(OR(F57="",AT57=""),"",IF(COUNT(AI57:AS57)=0,"",AT57-LOOKUP(2,1/(AI57:AS57<>""),AI57:AS57))) | IF(OR(F57="",AU57=""),"",IF(COUNT(AI57:AT57)=0,"",AU57-LOOKUP(2,1/(AI57:AT57<>""),AI57:AT57))) | IF(OR(F57="",AV57=""),"",IF(COUNT(AI57:AU57)=0,"",AV57-LOOKUP(2,1/(AI57:AU57<>""),AI57:AU57))) | IF(J57="","All_Provinces",IFERROR(VLOOKUP(J57,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K57="","All_Districts",IFERROR(VLOOKUP(K57,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F58="","",ROW()-3) | [18 empty] | IF(AQ58="","",AQ58) |  |  |  | IF(W58<>"",W58,IF(OR(T58="",V58=""),"",EDATE(T58,V58))) |  |  |  |  | IF(F58="","",IF(COUNT(AI58:AV58)=0,IF(AA58="","Not started",AA58),SUBSTITUTE(LOOKUP(2,1/(AI58:AV58<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F58="",COUNT(AI58:AV58)=0),"",TODAY()-LOOKUP(2,1/(AI58:AV58<>""),AI58:AV58)) | IF(OR(F58="",COUNT(AI58:AV58)<2),"",LOOKUP(2,1/(AI58:AV58<>""),AI58:AV58)-MIN(AI58:AV58)) | IF(OR(AD58="",AC58="Not started",AC58=""),"",IFERROR(AD58-IF(VLOOKUP(AC58,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC58,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F58="","",IF(OR(AA58="Cancelled",AC58="Cancelled"),"Cancelled",IF(OR(AC58="Completed / Handover",Y58<>"",Z58>=100),"Completed — on track",IF(O58="Not awarded",IF(U58="",IF(X58="","No planned date",IF(TODAY()>X58,"Behind — past planned date",IF(X58-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U58,"Behind — award date passed",IF(U58-TODAY()<=30,"At risk — close to off track","On track"))),IF(X58="","No planned date",IF(AND(TODAY()>X58,OR(Z58="",Z58<100)),"Behind — past end date",IF(AND(T58<>"",X58<>"",Z58<>"",(Z58<100),((TODAY()-T58)/MAX(X58-T58,1)*100)-Z58>15),"Behind — progress lag",IF(AND(X58-TODAY()<=30,X58-TODAY()>=0,OR(Z58="",Z58<90)),"At risk — close to off track","On track")))))))) | IF(OR(F58="",AC58="Completed / Handover",AC58="Cancelled"),"",IF(O58="Not awarded",IF(U58<>"",U58-TODAY(),IF(X58="","",X58-TODAY())),IF(X58="","",X58-TODAY()))) | [14 empty] | IF(OR(F58="",AJ58=""),"",IF(COUNT(AI58:AI58)=0,"",AJ58-LOOKUP(2,1/(AI58:AI58<>""),AI58:AI58))) | IF(OR(F58="",AK58=""),"",IF(COUNT(AI58:AJ58)=0,"",AK58-LOOKUP(2,1/(AI58:AJ58<>""),AI58:AJ58))) | IF(OR(F58="",AL58=""),"",IF(COUNT(AI58:AK58)=0,"",AL58-LOOKUP(2,1/(AI58:AK58<>""),AI58:AK58))) | IF(OR(F58="",AM58=""),"",IF(COUNT(AI58:AL58)=0,"",AM58-LOOKUP(2,1/(AI58:AL58<>""),AI58:AL58))) | IF(OR(F58="",AN58=""),"",IF(COUNT(AI58:AM58)=0,"",AN58-LOOKUP(2,1/(AI58:AM58<>""),AI58:AM58))) | IF(OR(F58="",AO58=""),"",IF(COUNT(AI58:AN58)=0,"",AO58-LOOKUP(2,1/(AI58:AN58<>""),AI58:AN58))) | IF(OR(F58="",AP58=""),"",IF(COUNT(AI58:AO58)=0,"",AP58-LOOKUP(2,1/(AI58:AO58<>""),AI58:AO58))) | IF(OR(F58="",AQ58=""),"",IF(COUNT(AI58:AP58)=0,"",AQ58-LOOKUP(2,1/(AI58:AP58<>""),AI58:AP58))) | IF(OR(F58="",AR58=""),"",IF(COUNT(AI58:AQ58)=0,"",AR58-LOOKUP(2,1/(AI58:AQ58<>""),AI58:AQ58))) | IF(OR(F58="",AS58=""),"",IF(COUNT(AI58:AR58)=0,"",AS58-LOOKUP(2,1/(AI58:AR58<>""),AI58:AR58))) | IF(OR(F58="",AT58=""),"",IF(COUNT(AI58:AS58)=0,"",AT58-LOOKUP(2,1/(AI58:AS58<>""),AI58:AS58))) | IF(OR(F58="",AU58=""),"",IF(COUNT(AI58:AT58)=0,"",AU58-LOOKUP(2,1/(AI58:AT58<>""),AI58:AT58))) | IF(OR(F58="",AV58=""),"",IF(COUNT(AI58:AU58)=0,"",AV58-LOOKUP(2,1/(AI58:AU58<>""),AI58:AU58))) | IF(J58="","All_Provinces",IFERROR(VLOOKUP(J58,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K58="","All_Districts",IFERROR(VLOOKUP(K58,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F59="","",ROW()-3) | [18 empty] | IF(AQ59="","",AQ59) |  |  |  | IF(W59<>"",W59,IF(OR(T59="",V59=""),"",EDATE(T59,V59))) |  |  |  |  | IF(F59="","",IF(COUNT(AI59:AV59)=0,IF(AA59="","Not started",AA59),SUBSTITUTE(LOOKUP(2,1/(AI59:AV59<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F59="",COUNT(AI59:AV59)=0),"",TODAY()-LOOKUP(2,1/(AI59:AV59<>""),AI59:AV59)) | IF(OR(F59="",COUNT(AI59:AV59)<2),"",LOOKUP(2,1/(AI59:AV59<>""),AI59:AV59)-MIN(AI59:AV59)) | IF(OR(AD59="",AC59="Not started",AC59=""),"",IFERROR(AD59-IF(VLOOKUP(AC59,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC59,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F59="","",IF(OR(AA59="Cancelled",AC59="Cancelled"),"Cancelled",IF(OR(AC59="Completed / Handover",Y59<>"",Z59>=100),"Completed — on track",IF(O59="Not awarded",IF(U59="",IF(X59="","No planned date",IF(TODAY()>X59,"Behind — past planned date",IF(X59-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U59,"Behind — award date passed",IF(U59-TODAY()<=30,"At risk — close to off track","On track"))),IF(X59="","No planned date",IF(AND(TODAY()>X59,OR(Z59="",Z59<100)),"Behind — past end date",IF(AND(T59<>"",X59<>"",Z59<>"",(Z59<100),((TODAY()-T59)/MAX(X59-T59,1)*100)-Z59>15),"Behind — progress lag",IF(AND(X59-TODAY()<=30,X59-TODAY()>=0,OR(Z59="",Z59<90)),"At risk — close to off track","On track")))))))) | IF(OR(F59="",AC59="Completed / Handover",AC59="Cancelled"),"",IF(O59="Not awarded",IF(U59<>"",U59-TODAY(),IF(X59="","",X59-TODAY())),IF(X59="","",X59-TODAY()))) | [14 empty] | IF(OR(F59="",AJ59=""),"",IF(COUNT(AI59:AI59)=0,"",AJ59-LOOKUP(2,1/(AI59:AI59<>""),AI59:AI59))) | IF(OR(F59="",AK59=""),"",IF(COUNT(AI59:AJ59)=0,"",AK59-LOOKUP(2,1/(AI59:AJ59<>""),AI59:AJ59))) | IF(OR(F59="",AL59=""),"",IF(COUNT(AI59:AK59)=0,"",AL59-LOOKUP(2,1/(AI59:AK59<>""),AI59:AK59))) | IF(OR(F59="",AM59=""),"",IF(COUNT(AI59:AL59)=0,"",AM59-LOOKUP(2,1/(AI59:AL59<>""),AI59:AL59))) | IF(OR(F59="",AN59=""),"",IF(COUNT(AI59:AM59)=0,"",AN59-LOOKUP(2,1/(AI59:AM59<>""),AI59:AM59))) | IF(OR(F59="",AO59=""),"",IF(COUNT(AI59:AN59)=0,"",AO59-LOOKUP(2,1/(AI59:AN59<>""),AI59:AN59))) | IF(OR(F59="",AP59=""),"",IF(COUNT(AI59:AO59)=0,"",AP59-LOOKUP(2,1/(AI59:AO59<>""),AI59:AO59))) | IF(OR(F59="",AQ59=""),"",IF(COUNT(AI59:AP59)=0,"",AQ59-LOOKUP(2,1/(AI59:AP59<>""),AI59:AP59))) | IF(OR(F59="",AR59=""),"",IF(COUNT(AI59:AQ59)=0,"",AR59-LOOKUP(2,1/(AI59:AQ59<>""),AI59:AQ59))) | IF(OR(F59="",AS59=""),"",IF(COUNT(AI59:AR59)=0,"",AS59-LOOKUP(2,1/(AI59:AR59<>""),AI59:AR59))) | IF(OR(F59="",AT59=""),"",IF(COUNT(AI59:AS59)=0,"",AT59-LOOKUP(2,1/(AI59:AS59<>""),AI59:AS59))) | IF(OR(F59="",AU59=""),"",IF(COUNT(AI59:AT59)=0,"",AU59-LOOKUP(2,1/(AI59:AT59<>""),AI59:AT59))) | IF(OR(F59="",AV59=""),"",IF(COUNT(AI59:AU59)=0,"",AV59-LOOKUP(2,1/(AI59:AU59<>""),AI59:AU59))) | IF(J59="","All_Provinces",IFERROR(VLOOKUP(J59,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K59="","All_Districts",IFERROR(VLOOKUP(K59,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F60="","",ROW()-3) | [18 empty] | IF(AQ60="","",AQ60) |  |  |  | IF(W60<>"",W60,IF(OR(T60="",V60=""),"",EDATE(T60,V60))) |  |  |  |  | IF(F60="","",IF(COUNT(AI60:AV60)=0,IF(AA60="","Not started",AA60),SUBSTITUTE(LOOKUP(2,1/(AI60:AV60<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F60="",COUNT(AI60:AV60)=0),"",TODAY()-LOOKUP(2,1/(AI60:AV60<>""),AI60:AV60)) | IF(OR(F60="",COUNT(AI60:AV60)<2),"",LOOKUP(2,1/(AI60:AV60<>""),AI60:AV60)-MIN(AI60:AV60)) | IF(OR(AD60="",AC60="Not started",AC60=""),"",IFERROR(AD60-IF(VLOOKUP(AC60,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC60,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F60="","",IF(OR(AA60="Cancelled",AC60="Cancelled"),"Cancelled",IF(OR(AC60="Completed / Handover",Y60<>"",Z60>=100),"Completed — on track",IF(O60="Not awarded",IF(U60="",IF(X60="","No planned date",IF(TODAY()>X60,"Behind — past planned date",IF(X60-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U60,"Behind — award date passed",IF(U60-TODAY()<=30,"At risk — close to off track","On track"))),IF(X60="","No planned date",IF(AND(TODAY()>X60,OR(Z60="",Z60<100)),"Behind — past end date",IF(AND(T60<>"",X60<>"",Z60<>"",(Z60<100),((TODAY()-T60)/MAX(X60-T60,1)*100)-Z60>15),"Behind — progress lag",IF(AND(X60-TODAY()<=30,X60-TODAY()>=0,OR(Z60="",Z60<90)),"At risk — close to off track","On track")))))))) | IF(OR(F60="",AC60="Completed / Handover",AC60="Cancelled"),"",IF(O60="Not awarded",IF(U60<>"",U60-TODAY(),IF(X60="","",X60-TODAY())),IF(X60="","",X60-TODAY()))) | [14 empty] | IF(OR(F60="",AJ60=""),"",IF(COUNT(AI60:AI60)=0,"",AJ60-LOOKUP(2,1/(AI60:AI60<>""),AI60:AI60))) | IF(OR(F60="",AK60=""),"",IF(COUNT(AI60:AJ60)=0,"",AK60-LOOKUP(2,1/(AI60:AJ60<>""),AI60:AJ60))) | IF(OR(F60="",AL60=""),"",IF(COUNT(AI60:AK60)=0,"",AL60-LOOKUP(2,1/(AI60:AK60<>""),AI60:AK60))) | IF(OR(F60="",AM60=""),"",IF(COUNT(AI60:AL60)=0,"",AM60-LOOKUP(2,1/(AI60:AL60<>""),AI60:AL60))) | IF(OR(F60="",AN60=""),"",IF(COUNT(AI60:AM60)=0,"",AN60-LOOKUP(2,1/(AI60:AM60<>""),AI60:AM60))) | IF(OR(F60="",AO60=""),"",IF(COUNT(AI60:AN60)=0,"",AO60-LOOKUP(2,1/(AI60:AN60<>""),AI60:AN60))) | IF(OR(F60="",AP60=""),"",IF(COUNT(AI60:AO60)=0,"",AP60-LOOKUP(2,1/(AI60:AO60<>""),AI60:AO60))) | IF(OR(F60="",AQ60=""),"",IF(COUNT(AI60:AP60)=0,"",AQ60-LOOKUP(2,1/(AI60:AP60<>""),AI60:AP60))) | IF(OR(F60="",AR60=""),"",IF(COUNT(AI60:AQ60)=0,"",AR60-LOOKUP(2,1/(AI60:AQ60<>""),AI60:AQ60))) | IF(OR(F60="",AS60=""),"",IF(COUNT(AI60:AR60)=0,"",AS60-LOOKUP(2,1/(AI60:AR60<>""),AI60:AR60))) | IF(OR(F60="",AT60=""),"",IF(COUNT(AI60:AS60)=0,"",AT60-LOOKUP(2,1/(AI60:AS60<>""),AI60:AS60))) | IF(OR(F60="",AU60=""),"",IF(COUNT(AI60:AT60)=0,"",AU60-LOOKUP(2,1/(AI60:AT60<>""),AI60:AT60))) | IF(OR(F60="",AV60=""),"",IF(COUNT(AI60:AU60)=0,"",AV60-LOOKUP(2,1/(AI60:AU60<>""),AI60:AU60))) | IF(J60="","All_Provinces",IFERROR(VLOOKUP(J60,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K60="","All_Districts",IFERROR(VLOOKUP(K60,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F61="","",ROW()-3) | [18 empty] | IF(AQ61="","",AQ61) |  |  |  | IF(W61<>"",W61,IF(OR(T61="",V61=""),"",EDATE(T61,V61))) |  |  |  |  | IF(F61="","",IF(COUNT(AI61:AV61)=0,IF(AA61="","Not started",AA61),SUBSTITUTE(LOOKUP(2,1/(AI61:AV61<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F61="",COUNT(AI61:AV61)=0),"",TODAY()-LOOKUP(2,1/(AI61:AV61<>""),AI61:AV61)) | IF(OR(F61="",COUNT(AI61:AV61)<2),"",LOOKUP(2,1/(AI61:AV61<>""),AI61:AV61)-MIN(AI61:AV61)) | IF(OR(AD61="",AC61="Not started",AC61=""),"",IFERROR(AD61-IF(VLOOKUP(AC61,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC61,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F61="","",IF(OR(AA61="Cancelled",AC61="Cancelled"),"Cancelled",IF(OR(AC61="Completed / Handover",Y61<>"",Z61>=100),"Completed — on track",IF(O61="Not awarded",IF(U61="",IF(X61="","No planned date",IF(TODAY()>X61,"Behind — past planned date",IF(X61-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U61,"Behind — award date passed",IF(U61-TODAY()<=30,"At risk — close to off track","On track"))),IF(X61="","No planned date",IF(AND(TODAY()>X61,OR(Z61="",Z61<100)),"Behind — past end date",IF(AND(T61<>"",X61<>"",Z61<>"",(Z61<100),((TODAY()-T61)/MAX(X61-T61,1)*100)-Z61>15),"Behind — progress lag",IF(AND(X61-TODAY()<=30,X61-TODAY()>=0,OR(Z61="",Z61<90)),"At risk — close to off track","On track")))))))) | IF(OR(F61="",AC61="Completed / Handover",AC61="Cancelled"),"",IF(O61="Not awarded",IF(U61<>"",U61-TODAY(),IF(X61="","",X61-TODAY())),IF(X61="","",X61-TODAY()))) | [14 empty] | IF(OR(F61="",AJ61=""),"",IF(COUNT(AI61:AI61)=0,"",AJ61-LOOKUP(2,1/(AI61:AI61<>""),AI61:AI61))) | IF(OR(F61="",AK61=""),"",IF(COUNT(AI61:AJ61)=0,"",AK61-LOOKUP(2,1/(AI61:AJ61<>""),AI61:AJ61))) | IF(OR(F61="",AL61=""),"",IF(COUNT(AI61:AK61)=0,"",AL61-LOOKUP(2,1/(AI61:AK61<>""),AI61:AK61))) | IF(OR(F61="",AM61=""),"",IF(COUNT(AI61:AL61)=0,"",AM61-LOOKUP(2,1/(AI61:AL61<>""),AI61:AL61))) | IF(OR(F61="",AN61=""),"",IF(COUNT(AI61:AM61)=0,"",AN61-LOOKUP(2,1/(AI61:AM61<>""),AI61:AM61))) | IF(OR(F61="",AO61=""),"",IF(COUNT(AI61:AN61)=0,"",AO61-LOOKUP(2,1/(AI61:AN61<>""),AI61:AN61))) | IF(OR(F61="",AP61=""),"",IF(COUNT(AI61:AO61)=0,"",AP61-LOOKUP(2,1/(AI61:AO61<>""),AI61:AO61))) | IF(OR(F61="",AQ61=""),"",IF(COUNT(AI61:AP61)=0,"",AQ61-LOOKUP(2,1/(AI61:AP61<>""),AI61:AP61))) | IF(OR(F61="",AR61=""),"",IF(COUNT(AI61:AQ61)=0,"",AR61-LOOKUP(2,1/(AI61:AQ61<>""),AI61:AQ61))) | IF(OR(F61="",AS61=""),"",IF(COUNT(AI61:AR61)=0,"",AS61-LOOKUP(2,1/(AI61:AR61<>""),AI61:AR61))) | IF(OR(F61="",AT61=""),"",IF(COUNT(AI61:AS61)=0,"",AT61-LOOKUP(2,1/(AI61:AS61<>""),AI61:AS61))) | IF(OR(F61="",AU61=""),"",IF(COUNT(AI61:AT61)=0,"",AU61-LOOKUP(2,1/(AI61:AT61<>""),AI61:AT61))) | IF(OR(F61="",AV61=""),"",IF(COUNT(AI61:AU61)=0,"",AV61-LOOKUP(2,1/(AI61:AU61<>""),AI61:AU61))) | IF(J61="","All_Provinces",IFERROR(VLOOKUP(J61,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K61="","All_Districts",IFERROR(VLOOKUP(K61,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F62="","",ROW()-3) | [18 empty] | IF(AQ62="","",AQ62) |  |  |  | IF(W62<>"",W62,IF(OR(T62="",V62=""),"",EDATE(T62,V62))) |  |  |  |  | IF(F62="","",IF(COUNT(AI62:AV62)=0,IF(AA62="","Not started",AA62),SUBSTITUTE(LOOKUP(2,1/(AI62:AV62<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F62="",COUNT(AI62:AV62)=0),"",TODAY()-LOOKUP(2,1/(AI62:AV62<>""),AI62:AV62)) | IF(OR(F62="",COUNT(AI62:AV62)<2),"",LOOKUP(2,1/(AI62:AV62<>""),AI62:AV62)-MIN(AI62:AV62)) | IF(OR(AD62="",AC62="Not started",AC62=""),"",IFERROR(AD62-IF(VLOOKUP(AC62,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC62,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F62="","",IF(OR(AA62="Cancelled",AC62="Cancelled"),"Cancelled",IF(OR(AC62="Completed / Handover",Y62<>"",Z62>=100),"Completed — on track",IF(O62="Not awarded",IF(U62="",IF(X62="","No planned date",IF(TODAY()>X62,"Behind — past planned date",IF(X62-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U62,"Behind — award date passed",IF(U62-TODAY()<=30,"At risk — close to off track","On track"))),IF(X62="","No planned date",IF(AND(TODAY()>X62,OR(Z62="",Z62<100)),"Behind — past end date",IF(AND(T62<>"",X62<>"",Z62<>"",(Z62<100),((TODAY()-T62)/MAX(X62-T62,1)*100)-Z62>15),"Behind — progress lag",IF(AND(X62-TODAY()<=30,X62-TODAY()>=0,OR(Z62="",Z62<90)),"At risk — close to off track","On track")))))))) | IF(OR(F62="",AC62="Completed / Handover",AC62="Cancelled"),"",IF(O62="Not awarded",IF(U62<>"",U62-TODAY(),IF(X62="","",X62-TODAY())),IF(X62="","",X62-TODAY()))) | [14 empty] | IF(OR(F62="",AJ62=""),"",IF(COUNT(AI62:AI62)=0,"",AJ62-LOOKUP(2,1/(AI62:AI62<>""),AI62:AI62))) | IF(OR(F62="",AK62=""),"",IF(COUNT(AI62:AJ62)=0,"",AK62-LOOKUP(2,1/(AI62:AJ62<>""),AI62:AJ62))) | IF(OR(F62="",AL62=""),"",IF(COUNT(AI62:AK62)=0,"",AL62-LOOKUP(2,1/(AI62:AK62<>""),AI62:AK62))) | IF(OR(F62="",AM62=""),"",IF(COUNT(AI62:AL62)=0,"",AM62-LOOKUP(2,1/(AI62:AL62<>""),AI62:AL62))) | IF(OR(F62="",AN62=""),"",IF(COUNT(AI62:AM62)=0,"",AN62-LOOKUP(2,1/(AI62:AM62<>""),AI62:AM62))) | IF(OR(F62="",AO62=""),"",IF(COUNT(AI62:AN62)=0,"",AO62-LOOKUP(2,1/(AI62:AN62<>""),AI62:AN62))) | IF(OR(F62="",AP62=""),"",IF(COUNT(AI62:AO62)=0,"",AP62-LOOKUP(2,1/(AI62:AO62<>""),AI62:AO62))) | IF(OR(F62="",AQ62=""),"",IF(COUNT(AI62:AP62)=0,"",AQ62-LOOKUP(2,1/(AI62:AP62<>""),AI62:AP62))) | IF(OR(F62="",AR62=""),"",IF(COUNT(AI62:AQ62)=0,"",AR62-LOOKUP(2,1/(AI62:AQ62<>""),AI62:AQ62))) | IF(OR(F62="",AS62=""),"",IF(COUNT(AI62:AR62)=0,"",AS62-LOOKUP(2,1/(AI62:AR62<>""),AI62:AR62))) | IF(OR(F62="",AT62=""),"",IF(COUNT(AI62:AS62)=0,"",AT62-LOOKUP(2,1/(AI62:AS62<>""),AI62:AS62))) | IF(OR(F62="",AU62=""),"",IF(COUNT(AI62:AT62)=0,"",AU62-LOOKUP(2,1/(AI62:AT62<>""),AI62:AT62))) | IF(OR(F62="",AV62=""),"",IF(COUNT(AI62:AU62)=0,"",AV62-LOOKUP(2,1/(AI62:AU62<>""),AI62:AU62))) | IF(J62="","All_Provinces",IFERROR(VLOOKUP(J62,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K62="","All_Districts",IFERROR(VLOOKUP(K62,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F63="","",ROW()-3) | [18 empty] | IF(AQ63="","",AQ63) |  |  |  | IF(W63<>"",W63,IF(OR(T63="",V63=""),"",EDATE(T63,V63))) |  |  |  |  | IF(F63="","",IF(COUNT(AI63:AV63)=0,IF(AA63="","Not started",AA63),SUBSTITUTE(LOOKUP(2,1/(AI63:AV63<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F63="",COUNT(AI63:AV63)=0),"",TODAY()-LOOKUP(2,1/(AI63:AV63<>""),AI63:AV63)) | IF(OR(F63="",COUNT(AI63:AV63)<2),"",LOOKUP(2,1/(AI63:AV63<>""),AI63:AV63)-MIN(AI63:AV63)) | IF(OR(AD63="",AC63="Not started",AC63=""),"",IFERROR(AD63-IF(VLOOKUP(AC63,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC63,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F63="","",IF(OR(AA63="Cancelled",AC63="Cancelled"),"Cancelled",IF(OR(AC63="Completed / Handover",Y63<>"",Z63>=100),"Completed — on track",IF(O63="Not awarded",IF(U63="",IF(X63="","No planned date",IF(TODAY()>X63,"Behind — past planned date",IF(X63-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U63,"Behind — award date passed",IF(U63-TODAY()<=30,"At risk — close to off track","On track"))),IF(X63="","No planned date",IF(AND(TODAY()>X63,OR(Z63="",Z63<100)),"Behind — past end date",IF(AND(T63<>"",X63<>"",Z63<>"",(Z63<100),((TODAY()-T63)/MAX(X63-T63,1)*100)-Z63>15),"Behind — progress lag",IF(AND(X63-TODAY()<=30,X63-TODAY()>=0,OR(Z63="",Z63<90)),"At risk — close to off track","On track")))))))) | IF(OR(F63="",AC63="Completed / Handover",AC63="Cancelled"),"",IF(O63="Not awarded",IF(U63<>"",U63-TODAY(),IF(X63="","",X63-TODAY())),IF(X63="","",X63-TODAY()))) | [14 empty] | IF(OR(F63="",AJ63=""),"",IF(COUNT(AI63:AI63)=0,"",AJ63-LOOKUP(2,1/(AI63:AI63<>""),AI63:AI63))) | IF(OR(F63="",AK63=""),"",IF(COUNT(AI63:AJ63)=0,"",AK63-LOOKUP(2,1/(AI63:AJ63<>""),AI63:AJ63))) | IF(OR(F63="",AL63=""),"",IF(COUNT(AI63:AK63)=0,"",AL63-LOOKUP(2,1/(AI63:AK63<>""),AI63:AK63))) | IF(OR(F63="",AM63=""),"",IF(COUNT(AI63:AL63)=0,"",AM63-LOOKUP(2,1/(AI63:AL63<>""),AI63:AL63))) | IF(OR(F63="",AN63=""),"",IF(COUNT(AI63:AM63)=0,"",AN63-LOOKUP(2,1/(AI63:AM63<>""),AI63:AM63))) | IF(OR(F63="",AO63=""),"",IF(COUNT(AI63:AN63)=0,"",AO63-LOOKUP(2,1/(AI63:AN63<>""),AI63:AN63))) | IF(OR(F63="",AP63=""),"",IF(COUNT(AI63:AO63)=0,"",AP63-LOOKUP(2,1/(AI63:AO63<>""),AI63:AO63))) | IF(OR(F63="",AQ63=""),"",IF(COUNT(AI63:AP63)=0,"",AQ63-LOOKUP(2,1/(AI63:AP63<>""),AI63:AP63))) | IF(OR(F63="",AR63=""),"",IF(COUNT(AI63:AQ63)=0,"",AR63-LOOKUP(2,1/(AI63:AQ63<>""),AI63:AQ63))) | IF(OR(F63="",AS63=""),"",IF(COUNT(AI63:AR63)=0,"",AS63-LOOKUP(2,1/(AI63:AR63<>""),AI63:AR63))) | IF(OR(F63="",AT63=""),"",IF(COUNT(AI63:AS63)=0,"",AT63-LOOKUP(2,1/(AI63:AS63<>""),AI63:AS63))) | IF(OR(F63="",AU63=""),"",IF(COUNT(AI63:AT63)=0,"",AU63-LOOKUP(2,1/(AI63:AT63<>""),AI63:AT63))) | IF(OR(F63="",AV63=""),"",IF(COUNT(AI63:AU63)=0,"",AV63-LOOKUP(2,1/(AI63:AU63<>""),AI63:AU63))) | IF(J63="","All_Provinces",IFERROR(VLOOKUP(J63,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K63="","All_Districts",IFERROR(VLOOKUP(K63,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F64="","",ROW()-3) | [18 empty] | IF(AQ64="","",AQ64) |  |  |  | IF(W64<>"",W64,IF(OR(T64="",V64=""),"",EDATE(T64,V64))) |  |  |  |  | IF(F64="","",IF(COUNT(AI64:AV64)=0,IF(AA64="","Not started",AA64),SUBSTITUTE(LOOKUP(2,1/(AI64:AV64<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F64="",COUNT(AI64:AV64)=0),"",TODAY()-LOOKUP(2,1/(AI64:AV64<>""),AI64:AV64)) | IF(OR(F64="",COUNT(AI64:AV64)<2),"",LOOKUP(2,1/(AI64:AV64<>""),AI64:AV64)-MIN(AI64:AV64)) | IF(OR(AD64="",AC64="Not started",AC64=""),"",IFERROR(AD64-IF(VLOOKUP(AC64,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC64,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F64="","",IF(OR(AA64="Cancelled",AC64="Cancelled"),"Cancelled",IF(OR(AC64="Completed / Handover",Y64<>"",Z64>=100),"Completed — on track",IF(O64="Not awarded",IF(U64="",IF(X64="","No planned date",IF(TODAY()>X64,"Behind — past planned date",IF(X64-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U64,"Behind — award date passed",IF(U64-TODAY()<=30,"At risk — close to off track","On track"))),IF(X64="","No planned date",IF(AND(TODAY()>X64,OR(Z64="",Z64<100)),"Behind — past end date",IF(AND(T64<>"",X64<>"",Z64<>"",(Z64<100),((TODAY()-T64)/MAX(X64-T64,1)*100)-Z64>15),"Behind — progress lag",IF(AND(X64-TODAY()<=30,X64-TODAY()>=0,OR(Z64="",Z64<90)),"At risk — close to off track","On track")))))))) | IF(OR(F64="",AC64="Completed / Handover",AC64="Cancelled"),"",IF(O64="Not awarded",IF(U64<>"",U64-TODAY(),IF(X64="","",X64-TODAY())),IF(X64="","",X64-TODAY()))) | [14 empty] | IF(OR(F64="",AJ64=""),"",IF(COUNT(AI64:AI64)=0,"",AJ64-LOOKUP(2,1/(AI64:AI64<>""),AI64:AI64))) | IF(OR(F64="",AK64=""),"",IF(COUNT(AI64:AJ64)=0,"",AK64-LOOKUP(2,1/(AI64:AJ64<>""),AI64:AJ64))) | IF(OR(F64="",AL64=""),"",IF(COUNT(AI64:AK64)=0,"",AL64-LOOKUP(2,1/(AI64:AK64<>""),AI64:AK64))) | IF(OR(F64="",AM64=""),"",IF(COUNT(AI64:AL64)=0,"",AM64-LOOKUP(2,1/(AI64:AL64<>""),AI64:AL64))) | IF(OR(F64="",AN64=""),"",IF(COUNT(AI64:AM64)=0,"",AN64-LOOKUP(2,1/(AI64:AM64<>""),AI64:AM64))) | IF(OR(F64="",AO64=""),"",IF(COUNT(AI64:AN64)=0,"",AO64-LOOKUP(2,1/(AI64:AN64<>""),AI64:AN64))) | IF(OR(F64="",AP64=""),"",IF(COUNT(AI64:AO64)=0,"",AP64-LOOKUP(2,1/(AI64:AO64<>""),AI64:AO64))) | IF(OR(F64="",AQ64=""),"",IF(COUNT(AI64:AP64)=0,"",AQ64-LOOKUP(2,1/(AI64:AP64<>""),AI64:AP64))) | IF(OR(F64="",AR64=""),"",IF(COUNT(AI64:AQ64)=0,"",AR64-LOOKUP(2,1/(AI64:AQ64<>""),AI64:AQ64))) | IF(OR(F64="",AS64=""),"",IF(COUNT(AI64:AR64)=0,"",AS64-LOOKUP(2,1/(AI64:AR64<>""),AI64:AR64))) | IF(OR(F64="",AT64=""),"",IF(COUNT(AI64:AS64)=0,"",AT64-LOOKUP(2,1/(AI64:AS64<>""),AI64:AS64))) | IF(OR(F64="",AU64=""),"",IF(COUNT(AI64:AT64)=0,"",AU64-LOOKUP(2,1/(AI64:AT64<>""),AI64:AT64))) | IF(OR(F64="",AV64=""),"",IF(COUNT(AI64:AU64)=0,"",AV64-LOOKUP(2,1/(AI64:AU64<>""),AI64:AU64))) | IF(J64="","All_Provinces",IFERROR(VLOOKUP(J64,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K64="","All_Districts",IFERROR(VLOOKUP(K64,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F65="","",ROW()-3) | [18 empty] | IF(AQ65="","",AQ65) |  |  |  | IF(W65<>"",W65,IF(OR(T65="",V65=""),"",EDATE(T65,V65))) |  |  |  |  | IF(F65="","",IF(COUNT(AI65:AV65)=0,IF(AA65="","Not started",AA65),SUBSTITUTE(LOOKUP(2,1/(AI65:AV65<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F65="",COUNT(AI65:AV65)=0),"",TODAY()-LOOKUP(2,1/(AI65:AV65<>""),AI65:AV65)) | IF(OR(F65="",COUNT(AI65:AV65)<2),"",LOOKUP(2,1/(AI65:AV65<>""),AI65:AV65)-MIN(AI65:AV65)) | IF(OR(AD65="",AC65="Not started",AC65=""),"",IFERROR(AD65-IF(VLOOKUP(AC65,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC65,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F65="","",IF(OR(AA65="Cancelled",AC65="Cancelled"),"Cancelled",IF(OR(AC65="Completed / Handover",Y65<>"",Z65>=100),"Completed — on track",IF(O65="Not awarded",IF(U65="",IF(X65="","No planned date",IF(TODAY()>X65,"Behind — past planned date",IF(X65-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U65,"Behind — award date passed",IF(U65-TODAY()<=30,"At risk — close to off track","On track"))),IF(X65="","No planned date",IF(AND(TODAY()>X65,OR(Z65="",Z65<100)),"Behind — past end date",IF(AND(T65<>"",X65<>"",Z65<>"",(Z65<100),((TODAY()-T65)/MAX(X65-T65,1)*100)-Z65>15),"Behind — progress lag",IF(AND(X65-TODAY()<=30,X65-TODAY()>=0,OR(Z65="",Z65<90)),"At risk — close to off track","On track")))))))) | IF(OR(F65="",AC65="Completed / Handover",AC65="Cancelled"),"",IF(O65="Not awarded",IF(U65<>"",U65-TODAY(),IF(X65="","",X65-TODAY())),IF(X65="","",X65-TODAY()))) | [14 empty] | IF(OR(F65="",AJ65=""),"",IF(COUNT(AI65:AI65)=0,"",AJ65-LOOKUP(2,1/(AI65:AI65<>""),AI65:AI65))) | IF(OR(F65="",AK65=""),"",IF(COUNT(AI65:AJ65)=0,"",AK65-LOOKUP(2,1/(AI65:AJ65<>""),AI65:AJ65))) | IF(OR(F65="",AL65=""),"",IF(COUNT(AI65:AK65)=0,"",AL65-LOOKUP(2,1/(AI65:AK65<>""),AI65:AK65))) | IF(OR(F65="",AM65=""),"",IF(COUNT(AI65:AL65)=0,"",AM65-LOOKUP(2,1/(AI65:AL65<>""),AI65:AL65))) | IF(OR(F65="",AN65=""),"",IF(COUNT(AI65:AM65)=0,"",AN65-LOOKUP(2,1/(AI65:AM65<>""),AI65:AM65))) | IF(OR(F65="",AO65=""),"",IF(COUNT(AI65:AN65)=0,"",AO65-LOOKUP(2,1/(AI65:AN65<>""),AI65:AN65))) | IF(OR(F65="",AP65=""),"",IF(COUNT(AI65:AO65)=0,"",AP65-LOOKUP(2,1/(AI65:AO65<>""),AI65:AO65))) | IF(OR(F65="",AQ65=""),"",IF(COUNT(AI65:AP65)=0,"",AQ65-LOOKUP(2,1/(AI65:AP65<>""),AI65:AP65))) | IF(OR(F65="",AR65=""),"",IF(COUNT(AI65:AQ65)=0,"",AR65-LOOKUP(2,1/(AI65:AQ65<>""),AI65:AQ65))) | IF(OR(F65="",AS65=""),"",IF(COUNT(AI65:AR65)=0,"",AS65-LOOKUP(2,1/(AI65:AR65<>""),AI65:AR65))) | IF(OR(F65="",AT65=""),"",IF(COUNT(AI65:AS65)=0,"",AT65-LOOKUP(2,1/(AI65:AS65<>""),AI65:AS65))) | IF(OR(F65="",AU65=""),"",IF(COUNT(AI65:AT65)=0,"",AU65-LOOKUP(2,1/(AI65:AT65<>""),AI65:AT65))) | IF(OR(F65="",AV65=""),"",IF(COUNT(AI65:AU65)=0,"",AV65-LOOKUP(2,1/(AI65:AU65<>""),AI65:AU65))) | IF(J65="","All_Provinces",IFERROR(VLOOKUP(J65,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K65="","All_Districts",IFERROR(VLOOKUP(K65,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F66="","",ROW()-3) | [18 empty] | IF(AQ66="","",AQ66) |  |  |  | IF(W66<>"",W66,IF(OR(T66="",V66=""),"",EDATE(T66,V66))) |  |  |  |  | IF(F66="","",IF(COUNT(AI66:AV66)=0,IF(AA66="","Not started",AA66),SUBSTITUTE(LOOKUP(2,1/(AI66:AV66<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F66="",COUNT(AI66:AV66)=0),"",TODAY()-LOOKUP(2,1/(AI66:AV66<>""),AI66:AV66)) | IF(OR(F66="",COUNT(AI66:AV66)<2),"",LOOKUP(2,1/(AI66:AV66<>""),AI66:AV66)-MIN(AI66:AV66)) | IF(OR(AD66="",AC66="Not started",AC66=""),"",IFERROR(AD66-IF(VLOOKUP(AC66,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC66,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F66="","",IF(OR(AA66="Cancelled",AC66="Cancelled"),"Cancelled",IF(OR(AC66="Completed / Handover",Y66<>"",Z66>=100),"Completed — on track",IF(O66="Not awarded",IF(U66="",IF(X66="","No planned date",IF(TODAY()>X66,"Behind — past planned date",IF(X66-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U66,"Behind — award date passed",IF(U66-TODAY()<=30,"At risk — close to off track","On track"))),IF(X66="","No planned date",IF(AND(TODAY()>X66,OR(Z66="",Z66<100)),"Behind — past end date",IF(AND(T66<>"",X66<>"",Z66<>"",(Z66<100),((TODAY()-T66)/MAX(X66-T66,1)*100)-Z66>15),"Behind — progress lag",IF(AND(X66-TODAY()<=30,X66-TODAY()>=0,OR(Z66="",Z66<90)),"At risk — close to off track","On track")))))))) | IF(OR(F66="",AC66="Completed / Handover",AC66="Cancelled"),"",IF(O66="Not awarded",IF(U66<>"",U66-TODAY(),IF(X66="","",X66-TODAY())),IF(X66="","",X66-TODAY()))) | [14 empty] | IF(OR(F66="",AJ66=""),"",IF(COUNT(AI66:AI66)=0,"",AJ66-LOOKUP(2,1/(AI66:AI66<>""),AI66:AI66))) | IF(OR(F66="",AK66=""),"",IF(COUNT(AI66:AJ66)=0,"",AK66-LOOKUP(2,1/(AI66:AJ66<>""),AI66:AJ66))) | IF(OR(F66="",AL66=""),"",IF(COUNT(AI66:AK66)=0,"",AL66-LOOKUP(2,1/(AI66:AK66<>""),AI66:AK66))) | IF(OR(F66="",AM66=""),"",IF(COUNT(AI66:AL66)=0,"",AM66-LOOKUP(2,1/(AI66:AL66<>""),AI66:AL66))) | IF(OR(F66="",AN66=""),"",IF(COUNT(AI66:AM66)=0,"",AN66-LOOKUP(2,1/(AI66:AM66<>""),AI66:AM66))) | IF(OR(F66="",AO66=""),"",IF(COUNT(AI66:AN66)=0,"",AO66-LOOKUP(2,1/(AI66:AN66<>""),AI66:AN66))) | IF(OR(F66="",AP66=""),"",IF(COUNT(AI66:AO66)=0,"",AP66-LOOKUP(2,1/(AI66:AO66<>""),AI66:AO66))) | IF(OR(F66="",AQ66=""),"",IF(COUNT(AI66:AP66)=0,"",AQ66-LOOKUP(2,1/(AI66:AP66<>""),AI66:AP66))) | IF(OR(F66="",AR66=""),"",IF(COUNT(AI66:AQ66)=0,"",AR66-LOOKUP(2,1/(AI66:AQ66<>""),AI66:AQ66))) | IF(OR(F66="",AS66=""),"",IF(COUNT(AI66:AR66)=0,"",AS66-LOOKUP(2,1/(AI66:AR66<>""),AI66:AR66))) | IF(OR(F66="",AT66=""),"",IF(COUNT(AI66:AS66)=0,"",AT66-LOOKUP(2,1/(AI66:AS66<>""),AI66:AS66))) | IF(OR(F66="",AU66=""),"",IF(COUNT(AI66:AT66)=0,"",AU66-LOOKUP(2,1/(AI66:AT66<>""),AI66:AT66))) | IF(OR(F66="",AV66=""),"",IF(COUNT(AI66:AU66)=0,"",AV66-LOOKUP(2,1/(AI66:AU66<>""),AI66:AU66))) | IF(J66="","All_Provinces",IFERROR(VLOOKUP(J66,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K66="","All_Districts",IFERROR(VLOOKUP(K66,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F67="","",ROW()-3) | [18 empty] | IF(AQ67="","",AQ67) |  |  |  | IF(W67<>"",W67,IF(OR(T67="",V67=""),"",EDATE(T67,V67))) |  |  |  |  | IF(F67="","",IF(COUNT(AI67:AV67)=0,IF(AA67="","Not started",AA67),SUBSTITUTE(LOOKUP(2,1/(AI67:AV67<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F67="",COUNT(AI67:AV67)=0),"",TODAY()-LOOKUP(2,1/(AI67:AV67<>""),AI67:AV67)) | IF(OR(F67="",COUNT(AI67:AV67)<2),"",LOOKUP(2,1/(AI67:AV67<>""),AI67:AV67)-MIN(AI67:AV67)) | IF(OR(AD67="",AC67="Not started",AC67=""),"",IFERROR(AD67-IF(VLOOKUP(AC67,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC67,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F67="","",IF(OR(AA67="Cancelled",AC67="Cancelled"),"Cancelled",IF(OR(AC67="Completed / Handover",Y67<>"",Z67>=100),"Completed — on track",IF(O67="Not awarded",IF(U67="",IF(X67="","No planned date",IF(TODAY()>X67,"Behind — past planned date",IF(X67-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U67,"Behind — award date passed",IF(U67-TODAY()<=30,"At risk — close to off track","On track"))),IF(X67="","No planned date",IF(AND(TODAY()>X67,OR(Z67="",Z67<100)),"Behind — past end date",IF(AND(T67<>"",X67<>"",Z67<>"",(Z67<100),((TODAY()-T67)/MAX(X67-T67,1)*100)-Z67>15),"Behind — progress lag",IF(AND(X67-TODAY()<=30,X67-TODAY()>=0,OR(Z67="",Z67<90)),"At risk — close to off track","On track")))))))) | IF(OR(F67="",AC67="Completed / Handover",AC67="Cancelled"),"",IF(O67="Not awarded",IF(U67<>"",U67-TODAY(),IF(X67="","",X67-TODAY())),IF(X67="","",X67-TODAY()))) | [14 empty] | IF(OR(F67="",AJ67=""),"",IF(COUNT(AI67:AI67)=0,"",AJ67-LOOKUP(2,1/(AI67:AI67<>""),AI67:AI67))) | IF(OR(F67="",AK67=""),"",IF(COUNT(AI67:AJ67)=0,"",AK67-LOOKUP(2,1/(AI67:AJ67<>""),AI67:AJ67))) | IF(OR(F67="",AL67=""),"",IF(COUNT(AI67:AK67)=0,"",AL67-LOOKUP(2,1/(AI67:AK67<>""),AI67:AK67))) | IF(OR(F67="",AM67=""),"",IF(COUNT(AI67:AL67)=0,"",AM67-LOOKUP(2,1/(AI67:AL67<>""),AI67:AL67))) | IF(OR(F67="",AN67=""),"",IF(COUNT(AI67:AM67)=0,"",AN67-LOOKUP(2,1/(AI67:AM67<>""),AI67:AM67))) | IF(OR(F67="",AO67=""),"",IF(COUNT(AI67:AN67)=0,"",AO67-LOOKUP(2,1/(AI67:AN67<>""),AI67:AN67))) | IF(OR(F67="",AP67=""),"",IF(COUNT(AI67:AO67)=0,"",AP67-LOOKUP(2,1/(AI67:AO67<>""),AI67:AO67))) | IF(OR(F67="",AQ67=""),"",IF(COUNT(AI67:AP67)=0,"",AQ67-LOOKUP(2,1/(AI67:AP67<>""),AI67:AP67))) | IF(OR(F67="",AR67=""),"",IF(COUNT(AI67:AQ67)=0,"",AR67-LOOKUP(2,1/(AI67:AQ67<>""),AI67:AQ67))) | IF(OR(F67="",AS67=""),"",IF(COUNT(AI67:AR67)=0,"",AS67-LOOKUP(2,1/(AI67:AR67<>""),AI67:AR67))) | IF(OR(F67="",AT67=""),"",IF(COUNT(AI67:AS67)=0,"",AT67-LOOKUP(2,1/(AI67:AS67<>""),AI67:AS67))) | IF(OR(F67="",AU67=""),"",IF(COUNT(AI67:AT67)=0,"",AU67-LOOKUP(2,1/(AI67:AT67<>""),AI67:AT67))) | IF(OR(F67="",AV67=""),"",IF(COUNT(AI67:AU67)=0,"",AV67-LOOKUP(2,1/(AI67:AU67<>""),AI67:AU67))) | IF(J67="","All_Provinces",IFERROR(VLOOKUP(J67,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K67="","All_Districts",IFERROR(VLOOKUP(K67,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F68="","",ROW()-3) | [18 empty] | IF(AQ68="","",AQ68) |  |  |  | IF(W68<>"",W68,IF(OR(T68="",V68=""),"",EDATE(T68,V68))) |  |  |  |  | IF(F68="","",IF(COUNT(AI68:AV68)=0,IF(AA68="","Not started",AA68),SUBSTITUTE(LOOKUP(2,1/(AI68:AV68<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F68="",COUNT(AI68:AV68)=0),"",TODAY()-LOOKUP(2,1/(AI68:AV68<>""),AI68:AV68)) | IF(OR(F68="",COUNT(AI68:AV68)<2),"",LOOKUP(2,1/(AI68:AV68<>""),AI68:AV68)-MIN(AI68:AV68)) | IF(OR(AD68="",AC68="Not started",AC68=""),"",IFERROR(AD68-IF(VLOOKUP(AC68,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC68,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F68="","",IF(OR(AA68="Cancelled",AC68="Cancelled"),"Cancelled",IF(OR(AC68="Completed / Handover",Y68<>"",Z68>=100),"Completed — on track",IF(O68="Not awarded",IF(U68="",IF(X68="","No planned date",IF(TODAY()>X68,"Behind — past planned date",IF(X68-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U68,"Behind — award date passed",IF(U68-TODAY()<=30,"At risk — close to off track","On track"))),IF(X68="","No planned date",IF(AND(TODAY()>X68,OR(Z68="",Z68<100)),"Behind — past end date",IF(AND(T68<>"",X68<>"",Z68<>"",(Z68<100),((TODAY()-T68)/MAX(X68-T68,1)*100)-Z68>15),"Behind — progress lag",IF(AND(X68-TODAY()<=30,X68-TODAY()>=0,OR(Z68="",Z68<90)),"At risk — close to off track","On track")))))))) | IF(OR(F68="",AC68="Completed / Handover",AC68="Cancelled"),"",IF(O68="Not awarded",IF(U68<>"",U68-TODAY(),IF(X68="","",X68-TODAY())),IF(X68="","",X68-TODAY()))) | [14 empty] | IF(OR(F68="",AJ68=""),"",IF(COUNT(AI68:AI68)=0,"",AJ68-LOOKUP(2,1/(AI68:AI68<>""),AI68:AI68))) | IF(OR(F68="",AK68=""),"",IF(COUNT(AI68:AJ68)=0,"",AK68-LOOKUP(2,1/(AI68:AJ68<>""),AI68:AJ68))) | IF(OR(F68="",AL68=""),"",IF(COUNT(AI68:AK68)=0,"",AL68-LOOKUP(2,1/(AI68:AK68<>""),AI68:AK68))) | IF(OR(F68="",AM68=""),"",IF(COUNT(AI68:AL68)=0,"",AM68-LOOKUP(2,1/(AI68:AL68<>""),AI68:AL68))) | IF(OR(F68="",AN68=""),"",IF(COUNT(AI68:AM68)=0,"",AN68-LOOKUP(2,1/(AI68:AM68<>""),AI68:AM68))) | IF(OR(F68="",AO68=""),"",IF(COUNT(AI68:AN68)=0,"",AO68-LOOKUP(2,1/(AI68:AN68<>""),AI68:AN68))) | IF(OR(F68="",AP68=""),"",IF(COUNT(AI68:AO68)=0,"",AP68-LOOKUP(2,1/(AI68:AO68<>""),AI68:AO68))) | IF(OR(F68="",AQ68=""),"",IF(COUNT(AI68:AP68)=0,"",AQ68-LOOKUP(2,1/(AI68:AP68<>""),AI68:AP68))) | IF(OR(F68="",AR68=""),"",IF(COUNT(AI68:AQ68)=0,"",AR68-LOOKUP(2,1/(AI68:AQ68<>""),AI68:AQ68))) | IF(OR(F68="",AS68=""),"",IF(COUNT(AI68:AR68)=0,"",AS68-LOOKUP(2,1/(AI68:AR68<>""),AI68:AR68))) | IF(OR(F68="",AT68=""),"",IF(COUNT(AI68:AS68)=0,"",AT68-LOOKUP(2,1/(AI68:AS68<>""),AI68:AS68))) | IF(OR(F68="",AU68=""),"",IF(COUNT(AI68:AT68)=0,"",AU68-LOOKUP(2,1/(AI68:AT68<>""),AI68:AT68))) | IF(OR(F68="",AV68=""),"",IF(COUNT(AI68:AU68)=0,"",AV68-LOOKUP(2,1/(AI68:AU68<>""),AI68:AU68))) | IF(J68="","All_Provinces",IFERROR(VLOOKUP(J68,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K68="","All_Districts",IFERROR(VLOOKUP(K68,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F69="","",ROW()-3) | [18 empty] | IF(AQ69="","",AQ69) |  |  |  | IF(W69<>"",W69,IF(OR(T69="",V69=""),"",EDATE(T69,V69))) |  |  |  |  | IF(F69="","",IF(COUNT(AI69:AV69)=0,IF(AA69="","Not started",AA69),SUBSTITUTE(LOOKUP(2,1/(AI69:AV69<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F69="",COUNT(AI69:AV69)=0),"",TODAY()-LOOKUP(2,1/(AI69:AV69<>""),AI69:AV69)) | IF(OR(F69="",COUNT(AI69:AV69)<2),"",LOOKUP(2,1/(AI69:AV69<>""),AI69:AV69)-MIN(AI69:AV69)) | IF(OR(AD69="",AC69="Not started",AC69=""),"",IFERROR(AD69-IF(VLOOKUP(AC69,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC69,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F69="","",IF(OR(AA69="Cancelled",AC69="Cancelled"),"Cancelled",IF(OR(AC69="Completed / Handover",Y69<>"",Z69>=100),"Completed — on track",IF(O69="Not awarded",IF(U69="",IF(X69="","No planned date",IF(TODAY()>X69,"Behind — past planned date",IF(X69-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U69,"Behind — award date passed",IF(U69-TODAY()<=30,"At risk — close to off track","On track"))),IF(X69="","No planned date",IF(AND(TODAY()>X69,OR(Z69="",Z69<100)),"Behind — past end date",IF(AND(T69<>"",X69<>"",Z69<>"",(Z69<100),((TODAY()-T69)/MAX(X69-T69,1)*100)-Z69>15),"Behind — progress lag",IF(AND(X69-TODAY()<=30,X69-TODAY()>=0,OR(Z69="",Z69<90)),"At risk — close to off track","On track")))))))) | IF(OR(F69="",AC69="Completed / Handover",AC69="Cancelled"),"",IF(O69="Not awarded",IF(U69<>"",U69-TODAY(),IF(X69="","",X69-TODAY())),IF(X69="","",X69-TODAY()))) | [14 empty] | IF(OR(F69="",AJ69=""),"",IF(COUNT(AI69:AI69)=0,"",AJ69-LOOKUP(2,1/(AI69:AI69<>""),AI69:AI69))) | IF(OR(F69="",AK69=""),"",IF(COUNT(AI69:AJ69)=0,"",AK69-LOOKUP(2,1/(AI69:AJ69<>""),AI69:AJ69))) | IF(OR(F69="",AL69=""),"",IF(COUNT(AI69:AK69)=0,"",AL69-LOOKUP(2,1/(AI69:AK69<>""),AI69:AK69))) | IF(OR(F69="",AM69=""),"",IF(COUNT(AI69:AL69)=0,"",AM69-LOOKUP(2,1/(AI69:AL69<>""),AI69:AL69))) | IF(OR(F69="",AN69=""),"",IF(COUNT(AI69:AM69)=0,"",AN69-LOOKUP(2,1/(AI69:AM69<>""),AI69:AM69))) | IF(OR(F69="",AO69=""),"",IF(COUNT(AI69:AN69)=0,"",AO69-LOOKUP(2,1/(AI69:AN69<>""),AI69:AN69))) | IF(OR(F69="",AP69=""),"",IF(COUNT(AI69:AO69)=0,"",AP69-LOOKUP(2,1/(AI69:AO69<>""),AI69:AO69))) | IF(OR(F69="",AQ69=""),"",IF(COUNT(AI69:AP69)=0,"",AQ69-LOOKUP(2,1/(AI69:AP69<>""),AI69:AP69))) | IF(OR(F69="",AR69=""),"",IF(COUNT(AI69:AQ69)=0,"",AR69-LOOKUP(2,1/(AI69:AQ69<>""),AI69:AQ69))) | IF(OR(F69="",AS69=""),"",IF(COUNT(AI69:AR69)=0,"",AS69-LOOKUP(2,1/(AI69:AR69<>""),AI69:AR69))) | IF(OR(F69="",AT69=""),"",IF(COUNT(AI69:AS69)=0,"",AT69-LOOKUP(2,1/(AI69:AS69<>""),AI69:AS69))) | IF(OR(F69="",AU69=""),"",IF(COUNT(AI69:AT69)=0,"",AU69-LOOKUP(2,1/(AI69:AT69<>""),AI69:AT69))) | IF(OR(F69="",AV69=""),"",IF(COUNT(AI69:AU69)=0,"",AV69-LOOKUP(2,1/(AI69:AU69<>""),AI69:AU69))) | IF(J69="","All_Provinces",IFERROR(VLOOKUP(J69,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K69="","All_Districts",IFERROR(VLOOKUP(K69,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F70="","",ROW()-3) | [18 empty] | IF(AQ70="","",AQ70) |  |  |  | IF(W70<>"",W70,IF(OR(T70="",V70=""),"",EDATE(T70,V70))) |  |  |  |  | IF(F70="","",IF(COUNT(AI70:AV70)=0,IF(AA70="","Not started",AA70),SUBSTITUTE(LOOKUP(2,1/(AI70:AV70<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F70="",COUNT(AI70:AV70)=0),"",TODAY()-LOOKUP(2,1/(AI70:AV70<>""),AI70:AV70)) | IF(OR(F70="",COUNT(AI70:AV70)<2),"",LOOKUP(2,1/(AI70:AV70<>""),AI70:AV70)-MIN(AI70:AV70)) | IF(OR(AD70="",AC70="Not started",AC70=""),"",IFERROR(AD70-IF(VLOOKUP(AC70,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC70,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F70="","",IF(OR(AA70="Cancelled",AC70="Cancelled"),"Cancelled",IF(OR(AC70="Completed / Handover",Y70<>"",Z70>=100),"Completed — on track",IF(O70="Not awarded",IF(U70="",IF(X70="","No planned date",IF(TODAY()>X70,"Behind — past planned date",IF(X70-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U70,"Behind — award date passed",IF(U70-TODAY()<=30,"At risk — close to off track","On track"))),IF(X70="","No planned date",IF(AND(TODAY()>X70,OR(Z70="",Z70<100)),"Behind — past end date",IF(AND(T70<>"",X70<>"",Z70<>"",(Z70<100),((TODAY()-T70)/MAX(X70-T70,1)*100)-Z70>15),"Behind — progress lag",IF(AND(X70-TODAY()<=30,X70-TODAY()>=0,OR(Z70="",Z70<90)),"At risk — close to off track","On track")))))))) | IF(OR(F70="",AC70="Completed / Handover",AC70="Cancelled"),"",IF(O70="Not awarded",IF(U70<>"",U70-TODAY(),IF(X70="","",X70-TODAY())),IF(X70="","",X70-TODAY()))) | [14 empty] | IF(OR(F70="",AJ70=""),"",IF(COUNT(AI70:AI70)=0,"",AJ70-LOOKUP(2,1/(AI70:AI70<>""),AI70:AI70))) | IF(OR(F70="",AK70=""),"",IF(COUNT(AI70:AJ70)=0,"",AK70-LOOKUP(2,1/(AI70:AJ70<>""),AI70:AJ70))) | IF(OR(F70="",AL70=""),"",IF(COUNT(AI70:AK70)=0,"",AL70-LOOKUP(2,1/(AI70:AK70<>""),AI70:AK70))) | IF(OR(F70="",AM70=""),"",IF(COUNT(AI70:AL70)=0,"",AM70-LOOKUP(2,1/(AI70:AL70<>""),AI70:AL70))) | IF(OR(F70="",AN70=""),"",IF(COUNT(AI70:AM70)=0,"",AN70-LOOKUP(2,1/(AI70:AM70<>""),AI70:AM70))) | IF(OR(F70="",AO70=""),"",IF(COUNT(AI70:AN70)=0,"",AO70-LOOKUP(2,1/(AI70:AN70<>""),AI70:AN70))) | IF(OR(F70="",AP70=""),"",IF(COUNT(AI70:AO70)=0,"",AP70-LOOKUP(2,1/(AI70:AO70<>""),AI70:AO70))) | IF(OR(F70="",AQ70=""),"",IF(COUNT(AI70:AP70)=0,"",AQ70-LOOKUP(2,1/(AI70:AP70<>""),AI70:AP70))) | IF(OR(F70="",AR70=""),"",IF(COUNT(AI70:AQ70)=0,"",AR70-LOOKUP(2,1/(AI70:AQ70<>""),AI70:AQ70))) | IF(OR(F70="",AS70=""),"",IF(COUNT(AI70:AR70)=0,"",AS70-LOOKUP(2,1/(AI70:AR70<>""),AI70:AR70))) | IF(OR(F70="",AT70=""),"",IF(COUNT(AI70:AS70)=0,"",AT70-LOOKUP(2,1/(AI70:AS70<>""),AI70:AS70))) | IF(OR(F70="",AU70=""),"",IF(COUNT(AI70:AT70)=0,"",AU70-LOOKUP(2,1/(AI70:AT70<>""),AI70:AT70))) | IF(OR(F70="",AV70=""),"",IF(COUNT(AI70:AU70)=0,"",AV70-LOOKUP(2,1/(AI70:AU70<>""),AI70:AU70))) | IF(J70="","All_Provinces",IFERROR(VLOOKUP(J70,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K70="","All_Districts",IFERROR(VLOOKUP(K70,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F71="","",ROW()-3) | [18 empty] | IF(AQ71="","",AQ71) |  |  |  | IF(W71<>"",W71,IF(OR(T71="",V71=""),"",EDATE(T71,V71))) |  |  |  |  | IF(F71="","",IF(COUNT(AI71:AV71)=0,IF(AA71="","Not started",AA71),SUBSTITUTE(LOOKUP(2,1/(AI71:AV71<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F71="",COUNT(AI71:AV71)=0),"",TODAY()-LOOKUP(2,1/(AI71:AV71<>""),AI71:AV71)) | IF(OR(F71="",COUNT(AI71:AV71)<2),"",LOOKUP(2,1/(AI71:AV71<>""),AI71:AV71)-MIN(AI71:AV71)) | IF(OR(AD71="",AC71="Not started",AC71=""),"",IFERROR(AD71-IF(VLOOKUP(AC71,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC71,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F71="","",IF(OR(AA71="Cancelled",AC71="Cancelled"),"Cancelled",IF(OR(AC71="Completed / Handover",Y71<>"",Z71>=100),"Completed — on track",IF(O71="Not awarded",IF(U71="",IF(X71="","No planned date",IF(TODAY()>X71,"Behind — past planned date",IF(X71-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U71,"Behind — award date passed",IF(U71-TODAY()<=30,"At risk — close to off track","On track"))),IF(X71="","No planned date",IF(AND(TODAY()>X71,OR(Z71="",Z71<100)),"Behind — past end date",IF(AND(T71<>"",X71<>"",Z71<>"",(Z71<100),((TODAY()-T71)/MAX(X71-T71,1)*100)-Z71>15),"Behind — progress lag",IF(AND(X71-TODAY()<=30,X71-TODAY()>=0,OR(Z71="",Z71<90)),"At risk — close to off track","On track")))))))) | IF(OR(F71="",AC71="Completed / Handover",AC71="Cancelled"),"",IF(O71="Not awarded",IF(U71<>"",U71-TODAY(),IF(X71="","",X71-TODAY())),IF(X71="","",X71-TODAY()))) | [14 empty] | IF(OR(F71="",AJ71=""),"",IF(COUNT(AI71:AI71)=0,"",AJ71-LOOKUP(2,1/(AI71:AI71<>""),AI71:AI71))) | IF(OR(F71="",AK71=""),"",IF(COUNT(AI71:AJ71)=0,"",AK71-LOOKUP(2,1/(AI71:AJ71<>""),AI71:AJ71))) | IF(OR(F71="",AL71=""),"",IF(COUNT(AI71:AK71)=0,"",AL71-LOOKUP(2,1/(AI71:AK71<>""),AI71:AK71))) | IF(OR(F71="",AM71=""),"",IF(COUNT(AI71:AL71)=0,"",AM71-LOOKUP(2,1/(AI71:AL71<>""),AI71:AL71))) | IF(OR(F71="",AN71=""),"",IF(COUNT(AI71:AM71)=0,"",AN71-LOOKUP(2,1/(AI71:AM71<>""),AI71:AM71))) | IF(OR(F71="",AO71=""),"",IF(COUNT(AI71:AN71)=0,"",AO71-LOOKUP(2,1/(AI71:AN71<>""),AI71:AN71))) | IF(OR(F71="",AP71=""),"",IF(COUNT(AI71:AO71)=0,"",AP71-LOOKUP(2,1/(AI71:AO71<>""),AI71:AO71))) | IF(OR(F71="",AQ71=""),"",IF(COUNT(AI71:AP71)=0,"",AQ71-LOOKUP(2,1/(AI71:AP71<>""),AI71:AP71))) | IF(OR(F71="",AR71=""),"",IF(COUNT(AI71:AQ71)=0,"",AR71-LOOKUP(2,1/(AI71:AQ71<>""),AI71:AQ71))) | IF(OR(F71="",AS71=""),"",IF(COUNT(AI71:AR71)=0,"",AS71-LOOKUP(2,1/(AI71:AR71<>""),AI71:AR71))) | IF(OR(F71="",AT71=""),"",IF(COUNT(AI71:AS71)=0,"",AT71-LOOKUP(2,1/(AI71:AS71<>""),AI71:AS71))) | IF(OR(F71="",AU71=""),"",IF(COUNT(AI71:AT71)=0,"",AU71-LOOKUP(2,1/(AI71:AT71<>""),AI71:AT71))) | IF(OR(F71="",AV71=""),"",IF(COUNT(AI71:AU71)=0,"",AV71-LOOKUP(2,1/(AI71:AU71<>""),AI71:AU71))) | IF(J71="","All_Provinces",IFERROR(VLOOKUP(J71,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K71="","All_Districts",IFERROR(VLOOKUP(K71,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F72="","",ROW()-3) | [18 empty] | IF(AQ72="","",AQ72) |  |  |  | IF(W72<>"",W72,IF(OR(T72="",V72=""),"",EDATE(T72,V72))) |  |  |  |  | IF(F72="","",IF(COUNT(AI72:AV72)=0,IF(AA72="","Not started",AA72),SUBSTITUTE(LOOKUP(2,1/(AI72:AV72<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F72="",COUNT(AI72:AV72)=0),"",TODAY()-LOOKUP(2,1/(AI72:AV72<>""),AI72:AV72)) | IF(OR(F72="",COUNT(AI72:AV72)<2),"",LOOKUP(2,1/(AI72:AV72<>""),AI72:AV72)-MIN(AI72:AV72)) | IF(OR(AD72="",AC72="Not started",AC72=""),"",IFERROR(AD72-IF(VLOOKUP(AC72,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC72,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F72="","",IF(OR(AA72="Cancelled",AC72="Cancelled"),"Cancelled",IF(OR(AC72="Completed / Handover",Y72<>"",Z72>=100),"Completed — on track",IF(O72="Not awarded",IF(U72="",IF(X72="","No planned date",IF(TODAY()>X72,"Behind — past planned date",IF(X72-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U72,"Behind — award date passed",IF(U72-TODAY()<=30,"At risk — close to off track","On track"))),IF(X72="","No planned date",IF(AND(TODAY()>X72,OR(Z72="",Z72<100)),"Behind — past end date",IF(AND(T72<>"",X72<>"",Z72<>"",(Z72<100),((TODAY()-T72)/MAX(X72-T72,1)*100)-Z72>15),"Behind — progress lag",IF(AND(X72-TODAY()<=30,X72-TODAY()>=0,OR(Z72="",Z72<90)),"At risk — close to off track","On track")))))))) | IF(OR(F72="",AC72="Completed / Handover",AC72="Cancelled"),"",IF(O72="Not awarded",IF(U72<>"",U72-TODAY(),IF(X72="","",X72-TODAY())),IF(X72="","",X72-TODAY()))) | [14 empty] | IF(OR(F72="",AJ72=""),"",IF(COUNT(AI72:AI72)=0,"",AJ72-LOOKUP(2,1/(AI72:AI72<>""),AI72:AI72))) | IF(OR(F72="",AK72=""),"",IF(COUNT(AI72:AJ72)=0,"",AK72-LOOKUP(2,1/(AI72:AJ72<>""),AI72:AJ72))) | IF(OR(F72="",AL72=""),"",IF(COUNT(AI72:AK72)=0,"",AL72-LOOKUP(2,1/(AI72:AK72<>""),AI72:AK72))) | IF(OR(F72="",AM72=""),"",IF(COUNT(AI72:AL72)=0,"",AM72-LOOKUP(2,1/(AI72:AL72<>""),AI72:AL72))) | IF(OR(F72="",AN72=""),"",IF(COUNT(AI72:AM72)=0,"",AN72-LOOKUP(2,1/(AI72:AM72<>""),AI72:AM72))) | IF(OR(F72="",AO72=""),"",IF(COUNT(AI72:AN72)=0,"",AO72-LOOKUP(2,1/(AI72:AN72<>""),AI72:AN72))) | IF(OR(F72="",AP72=""),"",IF(COUNT(AI72:AO72)=0,"",AP72-LOOKUP(2,1/(AI72:AO72<>""),AI72:AO72))) | IF(OR(F72="",AQ72=""),"",IF(COUNT(AI72:AP72)=0,"",AQ72-LOOKUP(2,1/(AI72:AP72<>""),AI72:AP72))) | IF(OR(F72="",AR72=""),"",IF(COUNT(AI72:AQ72)=0,"",AR72-LOOKUP(2,1/(AI72:AQ72<>""),AI72:AQ72))) | IF(OR(F72="",AS72=""),"",IF(COUNT(AI72:AR72)=0,"",AS72-LOOKUP(2,1/(AI72:AR72<>""),AI72:AR72))) | IF(OR(F72="",AT72=""),"",IF(COUNT(AI72:AS72)=0,"",AT72-LOOKUP(2,1/(AI72:AS72<>""),AI72:AS72))) | IF(OR(F72="",AU72=""),"",IF(COUNT(AI72:AT72)=0,"",AU72-LOOKUP(2,1/(AI72:AT72<>""),AI72:AT72))) | IF(OR(F72="",AV72=""),"",IF(COUNT(AI72:AU72)=0,"",AV72-LOOKUP(2,1/(AI72:AU72<>""),AI72:AU72))) | IF(J72="","All_Provinces",IFERROR(VLOOKUP(J72,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K72="","All_Districts",IFERROR(VLOOKUP(K72,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F73="","",ROW()-3) | [18 empty] | IF(AQ73="","",AQ73) |  |  |  | IF(W73<>"",W73,IF(OR(T73="",V73=""),"",EDATE(T73,V73))) |  |  |  |  | IF(F73="","",IF(COUNT(AI73:AV73)=0,IF(AA73="","Not started",AA73),SUBSTITUTE(LOOKUP(2,1/(AI73:AV73<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F73="",COUNT(AI73:AV73)=0),"",TODAY()-LOOKUP(2,1/(AI73:AV73<>""),AI73:AV73)) | IF(OR(F73="",COUNT(AI73:AV73)<2),"",LOOKUP(2,1/(AI73:AV73<>""),AI73:AV73)-MIN(AI73:AV73)) | IF(OR(AD73="",AC73="Not started",AC73=""),"",IFERROR(AD73-IF(VLOOKUP(AC73,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC73,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F73="","",IF(OR(AA73="Cancelled",AC73="Cancelled"),"Cancelled",IF(OR(AC73="Completed / Handover",Y73<>"",Z73>=100),"Completed — on track",IF(O73="Not awarded",IF(U73="",IF(X73="","No planned date",IF(TODAY()>X73,"Behind — past planned date",IF(X73-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U73,"Behind — award date passed",IF(U73-TODAY()<=30,"At risk — close to off track","On track"))),IF(X73="","No planned date",IF(AND(TODAY()>X73,OR(Z73="",Z73<100)),"Behind — past end date",IF(AND(T73<>"",X73<>"",Z73<>"",(Z73<100),((TODAY()-T73)/MAX(X73-T73,1)*100)-Z73>15),"Behind — progress lag",IF(AND(X73-TODAY()<=30,X73-TODAY()>=0,OR(Z73="",Z73<90)),"At risk — close to off track","On track")))))))) | IF(OR(F73="",AC73="Completed / Handover",AC73="Cancelled"),"",IF(O73="Not awarded",IF(U73<>"",U73-TODAY(),IF(X73="","",X73-TODAY())),IF(X73="","",X73-TODAY()))) | [14 empty] | IF(OR(F73="",AJ73=""),"",IF(COUNT(AI73:AI73)=0,"",AJ73-LOOKUP(2,1/(AI73:AI73<>""),AI73:AI73))) | IF(OR(F73="",AK73=""),"",IF(COUNT(AI73:AJ73)=0,"",AK73-LOOKUP(2,1/(AI73:AJ73<>""),AI73:AJ73))) | IF(OR(F73="",AL73=""),"",IF(COUNT(AI73:AK73)=0,"",AL73-LOOKUP(2,1/(AI73:AK73<>""),AI73:AK73))) | IF(OR(F73="",AM73=""),"",IF(COUNT(AI73:AL73)=0,"",AM73-LOOKUP(2,1/(AI73:AL73<>""),AI73:AL73))) | IF(OR(F73="",AN73=""),"",IF(COUNT(AI73:AM73)=0,"",AN73-LOOKUP(2,1/(AI73:AM73<>""),AI73:AM73))) | IF(OR(F73="",AO73=""),"",IF(COUNT(AI73:AN73)=0,"",AO73-LOOKUP(2,1/(AI73:AN73<>""),AI73:AN73))) | IF(OR(F73="",AP73=""),"",IF(COUNT(AI73:AO73)=0,"",AP73-LOOKUP(2,1/(AI73:AO73<>""),AI73:AO73))) | IF(OR(F73="",AQ73=""),"",IF(COUNT(AI73:AP73)=0,"",AQ73-LOOKUP(2,1/(AI73:AP73<>""),AI73:AP73))) | IF(OR(F73="",AR73=""),"",IF(COUNT(AI73:AQ73)=0,"",AR73-LOOKUP(2,1/(AI73:AQ73<>""),AI73:AQ73))) | IF(OR(F73="",AS73=""),"",IF(COUNT(AI73:AR73)=0,"",AS73-LOOKUP(2,1/(AI73:AR73<>""),AI73:AR73))) | IF(OR(F73="",AT73=""),"",IF(COUNT(AI73:AS73)=0,"",AT73-LOOKUP(2,1/(AI73:AS73<>""),AI73:AS73))) | IF(OR(F73="",AU73=""),"",IF(COUNT(AI73:AT73)=0,"",AU73-LOOKUP(2,1/(AI73:AT73<>""),AI73:AT73))) | IF(OR(F73="",AV73=""),"",IF(COUNT(AI73:AU73)=0,"",AV73-LOOKUP(2,1/(AI73:AU73<>""),AI73:AU73))) | IF(J73="","All_Provinces",IFERROR(VLOOKUP(J73,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K73="","All_Districts",IFERROR(VLOOKUP(K73,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F74="","",ROW()-3) | [18 empty] | IF(AQ74="","",AQ74) |  |  |  | IF(W74<>"",W74,IF(OR(T74="",V74=""),"",EDATE(T74,V74))) |  |  |  |  | IF(F74="","",IF(COUNT(AI74:AV74)=0,IF(AA74="","Not started",AA74),SUBSTITUTE(LOOKUP(2,1/(AI74:AV74<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F74="",COUNT(AI74:AV74)=0),"",TODAY()-LOOKUP(2,1/(AI74:AV74<>""),AI74:AV74)) | IF(OR(F74="",COUNT(AI74:AV74)<2),"",LOOKUP(2,1/(AI74:AV74<>""),AI74:AV74)-MIN(AI74:AV74)) | IF(OR(AD74="",AC74="Not started",AC74=""),"",IFERROR(AD74-IF(VLOOKUP(AC74,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC74,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F74="","",IF(OR(AA74="Cancelled",AC74="Cancelled"),"Cancelled",IF(OR(AC74="Completed / Handover",Y74<>"",Z74>=100),"Completed — on track",IF(O74="Not awarded",IF(U74="",IF(X74="","No planned date",IF(TODAY()>X74,"Behind — past planned date",IF(X74-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U74,"Behind — award date passed",IF(U74-TODAY()<=30,"At risk — close to off track","On track"))),IF(X74="","No planned date",IF(AND(TODAY()>X74,OR(Z74="",Z74<100)),"Behind — past end date",IF(AND(T74<>"",X74<>"",Z74<>"",(Z74<100),((TODAY()-T74)/MAX(X74-T74,1)*100)-Z74>15),"Behind — progress lag",IF(AND(X74-TODAY()<=30,X74-TODAY()>=0,OR(Z74="",Z74<90)),"At risk — close to off track","On track")))))))) | IF(OR(F74="",AC74="Completed / Handover",AC74="Cancelled"),"",IF(O74="Not awarded",IF(U74<>"",U74-TODAY(),IF(X74="","",X74-TODAY())),IF(X74="","",X74-TODAY()))) | [14 empty] | IF(OR(F74="",AJ74=""),"",IF(COUNT(AI74:AI74)=0,"",AJ74-LOOKUP(2,1/(AI74:AI74<>""),AI74:AI74))) | IF(OR(F74="",AK74=""),"",IF(COUNT(AI74:AJ74)=0,"",AK74-LOOKUP(2,1/(AI74:AJ74<>""),AI74:AJ74))) | IF(OR(F74="",AL74=""),"",IF(COUNT(AI74:AK74)=0,"",AL74-LOOKUP(2,1/(AI74:AK74<>""),AI74:AK74))) | IF(OR(F74="",AM74=""),"",IF(COUNT(AI74:AL74)=0,"",AM74-LOOKUP(2,1/(AI74:AL74<>""),AI74:AL74))) | IF(OR(F74="",AN74=""),"",IF(COUNT(AI74:AM74)=0,"",AN74-LOOKUP(2,1/(AI74:AM74<>""),AI74:AM74))) | IF(OR(F74="",AO74=""),"",IF(COUNT(AI74:AN74)=0,"",AO74-LOOKUP(2,1/(AI74:AN74<>""),AI74:AN74))) | IF(OR(F74="",AP74=""),"",IF(COUNT(AI74:AO74)=0,"",AP74-LOOKUP(2,1/(AI74:AO74<>""),AI74:AO74))) | IF(OR(F74="",AQ74=""),"",IF(COUNT(AI74:AP74)=0,"",AQ74-LOOKUP(2,1/(AI74:AP74<>""),AI74:AP74))) | IF(OR(F74="",AR74=""),"",IF(COUNT(AI74:AQ74)=0,"",AR74-LOOKUP(2,1/(AI74:AQ74<>""),AI74:AQ74))) | IF(OR(F74="",AS74=""),"",IF(COUNT(AI74:AR74)=0,"",AS74-LOOKUP(2,1/(AI74:AR74<>""),AI74:AR74))) | IF(OR(F74="",AT74=""),"",IF(COUNT(AI74:AS74)=0,"",AT74-LOOKUP(2,1/(AI74:AS74<>""),AI74:AS74))) | IF(OR(F74="",AU74=""),"",IF(COUNT(AI74:AT74)=0,"",AU74-LOOKUP(2,1/(AI74:AT74<>""),AI74:AT74))) | IF(OR(F74="",AV74=""),"",IF(COUNT(AI74:AU74)=0,"",AV74-LOOKUP(2,1/(AI74:AU74<>""),AI74:AU74))) | IF(J74="","All_Provinces",IFERROR(VLOOKUP(J74,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K74="","All_Districts",IFERROR(VLOOKUP(K74,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F75="","",ROW()-3) | [18 empty] | IF(AQ75="","",AQ75) |  |  |  | IF(W75<>"",W75,IF(OR(T75="",V75=""),"",EDATE(T75,V75))) |  |  |  |  | IF(F75="","",IF(COUNT(AI75:AV75)=0,IF(AA75="","Not started",AA75),SUBSTITUTE(LOOKUP(2,1/(AI75:AV75<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F75="",COUNT(AI75:AV75)=0),"",TODAY()-LOOKUP(2,1/(AI75:AV75<>""),AI75:AV75)) | IF(OR(F75="",COUNT(AI75:AV75)<2),"",LOOKUP(2,1/(AI75:AV75<>""),AI75:AV75)-MIN(AI75:AV75)) | IF(OR(AD75="",AC75="Not started",AC75=""),"",IFERROR(AD75-IF(VLOOKUP(AC75,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC75,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F75="","",IF(OR(AA75="Cancelled",AC75="Cancelled"),"Cancelled",IF(OR(AC75="Completed / Handover",Y75<>"",Z75>=100),"Completed — on track",IF(O75="Not awarded",IF(U75="",IF(X75="","No planned date",IF(TODAY()>X75,"Behind — past planned date",IF(X75-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U75,"Behind — award date passed",IF(U75-TODAY()<=30,"At risk — close to off track","On track"))),IF(X75="","No planned date",IF(AND(TODAY()>X75,OR(Z75="",Z75<100)),"Behind — past end date",IF(AND(T75<>"",X75<>"",Z75<>"",(Z75<100),((TODAY()-T75)/MAX(X75-T75,1)*100)-Z75>15),"Behind — progress lag",IF(AND(X75-TODAY()<=30,X75-TODAY()>=0,OR(Z75="",Z75<90)),"At risk — close to off track","On track")))))))) | IF(OR(F75="",AC75="Completed / Handover",AC75="Cancelled"),"",IF(O75="Not awarded",IF(U75<>"",U75-TODAY(),IF(X75="","",X75-TODAY())),IF(X75="","",X75-TODAY()))) | [14 empty] | IF(OR(F75="",AJ75=""),"",IF(COUNT(AI75:AI75)=0,"",AJ75-LOOKUP(2,1/(AI75:AI75<>""),AI75:AI75))) | IF(OR(F75="",AK75=""),"",IF(COUNT(AI75:AJ75)=0,"",AK75-LOOKUP(2,1/(AI75:AJ75<>""),AI75:AJ75))) | IF(OR(F75="",AL75=""),"",IF(COUNT(AI75:AK75)=0,"",AL75-LOOKUP(2,1/(AI75:AK75<>""),AI75:AK75))) | IF(OR(F75="",AM75=""),"",IF(COUNT(AI75:AL75)=0,"",AM75-LOOKUP(2,1/(AI75:AL75<>""),AI75:AL75))) | IF(OR(F75="",AN75=""),"",IF(COUNT(AI75:AM75)=0,"",AN75-LOOKUP(2,1/(AI75:AM75<>""),AI75:AM75))) | IF(OR(F75="",AO75=""),"",IF(COUNT(AI75:AN75)=0,"",AO75-LOOKUP(2,1/(AI75:AN75<>""),AI75:AN75))) | IF(OR(F75="",AP75=""),"",IF(COUNT(AI75:AO75)=0,"",AP75-LOOKUP(2,1/(AI75:AO75<>""),AI75:AO75))) | IF(OR(F75="",AQ75=""),"",IF(COUNT(AI75:AP75)=0,"",AQ75-LOOKUP(2,1/(AI75:AP75<>""),AI75:AP75))) | IF(OR(F75="",AR75=""),"",IF(COUNT(AI75:AQ75)=0,"",AR75-LOOKUP(2,1/(AI75:AQ75<>""),AI75:AQ75))) | IF(OR(F75="",AS75=""),"",IF(COUNT(AI75:AR75)=0,"",AS75-LOOKUP(2,1/(AI75:AR75<>""),AI75:AR75))) | IF(OR(F75="",AT75=""),"",IF(COUNT(AI75:AS75)=0,"",AT75-LOOKUP(2,1/(AI75:AS75<>""),AI75:AS75))) | IF(OR(F75="",AU75=""),"",IF(COUNT(AI75:AT75)=0,"",AU75-LOOKUP(2,1/(AI75:AT75<>""),AI75:AT75))) | IF(OR(F75="",AV75=""),"",IF(COUNT(AI75:AU75)=0,"",AV75-LOOKUP(2,1/(AI75:AU75<>""),AI75:AU75))) | IF(J75="","All_Provinces",IFERROR(VLOOKUP(J75,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K75="","All_Districts",IFERROR(VLOOKUP(K75,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F76="","",ROW()-3) | [18 empty] | IF(AQ76="","",AQ76) |  |  |  | IF(W76<>"",W76,IF(OR(T76="",V76=""),"",EDATE(T76,V76))) |  |  |  |  | IF(F76="","",IF(COUNT(AI76:AV76)=0,IF(AA76="","Not started",AA76),SUBSTITUTE(LOOKUP(2,1/(AI76:AV76<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F76="",COUNT(AI76:AV76)=0),"",TODAY()-LOOKUP(2,1/(AI76:AV76<>""),AI76:AV76)) | IF(OR(F76="",COUNT(AI76:AV76)<2),"",LOOKUP(2,1/(AI76:AV76<>""),AI76:AV76)-MIN(AI76:AV76)) | IF(OR(AD76="",AC76="Not started",AC76=""),"",IFERROR(AD76-IF(VLOOKUP(AC76,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC76,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F76="","",IF(OR(AA76="Cancelled",AC76="Cancelled"),"Cancelled",IF(OR(AC76="Completed / Handover",Y76<>"",Z76>=100),"Completed — on track",IF(O76="Not awarded",IF(U76="",IF(X76="","No planned date",IF(TODAY()>X76,"Behind — past planned date",IF(X76-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U76,"Behind — award date passed",IF(U76-TODAY()<=30,"At risk — close to off track","On track"))),IF(X76="","No planned date",IF(AND(TODAY()>X76,OR(Z76="",Z76<100)),"Behind — past end date",IF(AND(T76<>"",X76<>"",Z76<>"",(Z76<100),((TODAY()-T76)/MAX(X76-T76,1)*100)-Z76>15),"Behind — progress lag",IF(AND(X76-TODAY()<=30,X76-TODAY()>=0,OR(Z76="",Z76<90)),"At risk — close to off track","On track")))))))) | IF(OR(F76="",AC76="Completed / Handover",AC76="Cancelled"),"",IF(O76="Not awarded",IF(U76<>"",U76-TODAY(),IF(X76="","",X76-TODAY())),IF(X76="","",X76-TODAY()))) | [14 empty] | IF(OR(F76="",AJ76=""),"",IF(COUNT(AI76:AI76)=0,"",AJ76-LOOKUP(2,1/(AI76:AI76<>""),AI76:AI76))) | IF(OR(F76="",AK76=""),"",IF(COUNT(AI76:AJ76)=0,"",AK76-LOOKUP(2,1/(AI76:AJ76<>""),AI76:AJ76))) | IF(OR(F76="",AL76=""),"",IF(COUNT(AI76:AK76)=0,"",AL76-LOOKUP(2,1/(AI76:AK76<>""),AI76:AK76))) | IF(OR(F76="",AM76=""),"",IF(COUNT(AI76:AL76)=0,"",AM76-LOOKUP(2,1/(AI76:AL76<>""),AI76:AL76))) | IF(OR(F76="",AN76=""),"",IF(COUNT(AI76:AM76)=0,"",AN76-LOOKUP(2,1/(AI76:AM76<>""),AI76:AM76))) | IF(OR(F76="",AO76=""),"",IF(COUNT(AI76:AN76)=0,"",AO76-LOOKUP(2,1/(AI76:AN76<>""),AI76:AN76))) | IF(OR(F76="",AP76=""),"",IF(COUNT(AI76:AO76)=0,"",AP76-LOOKUP(2,1/(AI76:AO76<>""),AI76:AO76))) | IF(OR(F76="",AQ76=""),"",IF(COUNT(AI76:AP76)=0,"",AQ76-LOOKUP(2,1/(AI76:AP76<>""),AI76:AP76))) | IF(OR(F76="",AR76=""),"",IF(COUNT(AI76:AQ76)=0,"",AR76-LOOKUP(2,1/(AI76:AQ76<>""),AI76:AQ76))) | IF(OR(F76="",AS76=""),"",IF(COUNT(AI76:AR76)=0,"",AS76-LOOKUP(2,1/(AI76:AR76<>""),AI76:AR76))) | IF(OR(F76="",AT76=""),"",IF(COUNT(AI76:AS76)=0,"",AT76-LOOKUP(2,1/(AI76:AS76<>""),AI76:AS76))) | IF(OR(F76="",AU76=""),"",IF(COUNT(AI76:AT76)=0,"",AU76-LOOKUP(2,1/(AI76:AT76<>""),AI76:AT76))) | IF(OR(F76="",AV76=""),"",IF(COUNT(AI76:AU76)=0,"",AV76-LOOKUP(2,1/(AI76:AU76<>""),AI76:AU76))) | IF(J76="","All_Provinces",IFERROR(VLOOKUP(J76,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K76="","All_Districts",IFERROR(VLOOKUP(K76,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F77="","",ROW()-3) | [18 empty] | IF(AQ77="","",AQ77) |  |  |  | IF(W77<>"",W77,IF(OR(T77="",V77=""),"",EDATE(T77,V77))) |  |  |  |  | IF(F77="","",IF(COUNT(AI77:AV77)=0,IF(AA77="","Not started",AA77),SUBSTITUTE(LOOKUP(2,1/(AI77:AV77<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F77="",COUNT(AI77:AV77)=0),"",TODAY()-LOOKUP(2,1/(AI77:AV77<>""),AI77:AV77)) | IF(OR(F77="",COUNT(AI77:AV77)<2),"",LOOKUP(2,1/(AI77:AV77<>""),AI77:AV77)-MIN(AI77:AV77)) | IF(OR(AD77="",AC77="Not started",AC77=""),"",IFERROR(AD77-IF(VLOOKUP(AC77,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC77,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F77="","",IF(OR(AA77="Cancelled",AC77="Cancelled"),"Cancelled",IF(OR(AC77="Completed / Handover",Y77<>"",Z77>=100),"Completed — on track",IF(O77="Not awarded",IF(U77="",IF(X77="","No planned date",IF(TODAY()>X77,"Behind — past planned date",IF(X77-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U77,"Behind — award date passed",IF(U77-TODAY()<=30,"At risk — close to off track","On track"))),IF(X77="","No planned date",IF(AND(TODAY()>X77,OR(Z77="",Z77<100)),"Behind — past end date",IF(AND(T77<>"",X77<>"",Z77<>"",(Z77<100),((TODAY()-T77)/MAX(X77-T77,1)*100)-Z77>15),"Behind — progress lag",IF(AND(X77-TODAY()<=30,X77-TODAY()>=0,OR(Z77="",Z77<90)),"At risk — close to off track","On track")))))))) | IF(OR(F77="",AC77="Completed / Handover",AC77="Cancelled"),"",IF(O77="Not awarded",IF(U77<>"",U77-TODAY(),IF(X77="","",X77-TODAY())),IF(X77="","",X77-TODAY()))) | [14 empty] | IF(OR(F77="",AJ77=""),"",IF(COUNT(AI77:AI77)=0,"",AJ77-LOOKUP(2,1/(AI77:AI77<>""),AI77:AI77))) | IF(OR(F77="",AK77=""),"",IF(COUNT(AI77:AJ77)=0,"",AK77-LOOKUP(2,1/(AI77:AJ77<>""),AI77:AJ77))) | IF(OR(F77="",AL77=""),"",IF(COUNT(AI77:AK77)=0,"",AL77-LOOKUP(2,1/(AI77:AK77<>""),AI77:AK77))) | IF(OR(F77="",AM77=""),"",IF(COUNT(AI77:AL77)=0,"",AM77-LOOKUP(2,1/(AI77:AL77<>""),AI77:AL77))) | IF(OR(F77="",AN77=""),"",IF(COUNT(AI77:AM77)=0,"",AN77-LOOKUP(2,1/(AI77:AM77<>""),AI77:AM77))) | IF(OR(F77="",AO77=""),"",IF(COUNT(AI77:AN77)=0,"",AO77-LOOKUP(2,1/(AI77:AN77<>""),AI77:AN77))) | IF(OR(F77="",AP77=""),"",IF(COUNT(AI77:AO77)=0,"",AP77-LOOKUP(2,1/(AI77:AO77<>""),AI77:AO77))) | IF(OR(F77="",AQ77=""),"",IF(COUNT(AI77:AP77)=0,"",AQ77-LOOKUP(2,1/(AI77:AP77<>""),AI77:AP77))) | IF(OR(F77="",AR77=""),"",IF(COUNT(AI77:AQ77)=0,"",AR77-LOOKUP(2,1/(AI77:AQ77<>""),AI77:AQ77))) | IF(OR(F77="",AS77=""),"",IF(COUNT(AI77:AR77)=0,"",AS77-LOOKUP(2,1/(AI77:AR77<>""),AI77:AR77))) | IF(OR(F77="",AT77=""),"",IF(COUNT(AI77:AS77)=0,"",AT77-LOOKUP(2,1/(AI77:AS77<>""),AI77:AS77))) | IF(OR(F77="",AU77=""),"",IF(COUNT(AI77:AT77)=0,"",AU77-LOOKUP(2,1/(AI77:AT77<>""),AI77:AT77))) | IF(OR(F77="",AV77=""),"",IF(COUNT(AI77:AU77)=0,"",AV77-LOOKUP(2,1/(AI77:AU77<>""),AI77:AU77))) | IF(J77="","All_Provinces",IFERROR(VLOOKUP(J77,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K77="","All_Districts",IFERROR(VLOOKUP(K77,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F78="","",ROW()-3) | [18 empty] | IF(AQ78="","",AQ78) |  |  |  | IF(W78<>"",W78,IF(OR(T78="",V78=""),"",EDATE(T78,V78))) |  |  |  |  | IF(F78="","",IF(COUNT(AI78:AV78)=0,IF(AA78="","Not started",AA78),SUBSTITUTE(LOOKUP(2,1/(AI78:AV78<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F78="",COUNT(AI78:AV78)=0),"",TODAY()-LOOKUP(2,1/(AI78:AV78<>""),AI78:AV78)) | IF(OR(F78="",COUNT(AI78:AV78)<2),"",LOOKUP(2,1/(AI78:AV78<>""),AI78:AV78)-MIN(AI78:AV78)) | IF(OR(AD78="",AC78="Not started",AC78=""),"",IFERROR(AD78-IF(VLOOKUP(AC78,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC78,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F78="","",IF(OR(AA78="Cancelled",AC78="Cancelled"),"Cancelled",IF(OR(AC78="Completed / Handover",Y78<>"",Z78>=100),"Completed — on track",IF(O78="Not awarded",IF(U78="",IF(X78="","No planned date",IF(TODAY()>X78,"Behind — past planned date",IF(X78-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U78,"Behind — award date passed",IF(U78-TODAY()<=30,"At risk — close to off track","On track"))),IF(X78="","No planned date",IF(AND(TODAY()>X78,OR(Z78="",Z78<100)),"Behind — past end date",IF(AND(T78<>"",X78<>"",Z78<>"",(Z78<100),((TODAY()-T78)/MAX(X78-T78,1)*100)-Z78>15),"Behind — progress lag",IF(AND(X78-TODAY()<=30,X78-TODAY()>=0,OR(Z78="",Z78<90)),"At risk — close to off track","On track")))))))) | IF(OR(F78="",AC78="Completed / Handover",AC78="Cancelled"),"",IF(O78="Not awarded",IF(U78<>"",U78-TODAY(),IF(X78="","",X78-TODAY())),IF(X78="","",X78-TODAY()))) | [14 empty] | IF(OR(F78="",AJ78=""),"",IF(COUNT(AI78:AI78)=0,"",AJ78-LOOKUP(2,1/(AI78:AI78<>""),AI78:AI78))) | IF(OR(F78="",AK78=""),"",IF(COUNT(AI78:AJ78)=0,"",AK78-LOOKUP(2,1/(AI78:AJ78<>""),AI78:AJ78))) | IF(OR(F78="",AL78=""),"",IF(COUNT(AI78:AK78)=0,"",AL78-LOOKUP(2,1/(AI78:AK78<>""),AI78:AK78))) | IF(OR(F78="",AM78=""),"",IF(COUNT(AI78:AL78)=0,"",AM78-LOOKUP(2,1/(AI78:AL78<>""),AI78:AL78))) | IF(OR(F78="",AN78=""),"",IF(COUNT(AI78:AM78)=0,"",AN78-LOOKUP(2,1/(AI78:AM78<>""),AI78:AM78))) | IF(OR(F78="",AO78=""),"",IF(COUNT(AI78:AN78)=0,"",AO78-LOOKUP(2,1/(AI78:AN78<>""),AI78:AN78))) | IF(OR(F78="",AP78=""),"",IF(COUNT(AI78:AO78)=0,"",AP78-LOOKUP(2,1/(AI78:AO78<>""),AI78:AO78))) | IF(OR(F78="",AQ78=""),"",IF(COUNT(AI78:AP78)=0,"",AQ78-LOOKUP(2,1/(AI78:AP78<>""),AI78:AP78))) | IF(OR(F78="",AR78=""),"",IF(COUNT(AI78:AQ78)=0,"",AR78-LOOKUP(2,1/(AI78:AQ78<>""),AI78:AQ78))) | IF(OR(F78="",AS78=""),"",IF(COUNT(AI78:AR78)=0,"",AS78-LOOKUP(2,1/(AI78:AR78<>""),AI78:AR78))) | IF(OR(F78="",AT78=""),"",IF(COUNT(AI78:AS78)=0,"",AT78-LOOKUP(2,1/(AI78:AS78<>""),AI78:AS78))) | IF(OR(F78="",AU78=""),"",IF(COUNT(AI78:AT78)=0,"",AU78-LOOKUP(2,1/(AI78:AT78<>""),AI78:AT78))) | IF(OR(F78="",AV78=""),"",IF(COUNT(AI78:AU78)=0,"",AV78-LOOKUP(2,1/(AI78:AU78<>""),AI78:AU78))) | IF(J78="","All_Provinces",IFERROR(VLOOKUP(J78,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K78="","All_Districts",IFERROR(VLOOKUP(K78,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F79="","",ROW()-3) | [18 empty] | IF(AQ79="","",AQ79) |  |  |  | IF(W79<>"",W79,IF(OR(T79="",V79=""),"",EDATE(T79,V79))) |  |  |  |  | IF(F79="","",IF(COUNT(AI79:AV79)=0,IF(AA79="","Not started",AA79),SUBSTITUTE(LOOKUP(2,1/(AI79:AV79<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F79="",COUNT(AI79:AV79)=0),"",TODAY()-LOOKUP(2,1/(AI79:AV79<>""),AI79:AV79)) | IF(OR(F79="",COUNT(AI79:AV79)<2),"",LOOKUP(2,1/(AI79:AV79<>""),AI79:AV79)-MIN(AI79:AV79)) | IF(OR(AD79="",AC79="Not started",AC79=""),"",IFERROR(AD79-IF(VLOOKUP(AC79,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC79,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F79="","",IF(OR(AA79="Cancelled",AC79="Cancelled"),"Cancelled",IF(OR(AC79="Completed / Handover",Y79<>"",Z79>=100),"Completed — on track",IF(O79="Not awarded",IF(U79="",IF(X79="","No planned date",IF(TODAY()>X79,"Behind — past planned date",IF(X79-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U79,"Behind — award date passed",IF(U79-TODAY()<=30,"At risk — close to off track","On track"))),IF(X79="","No planned date",IF(AND(TODAY()>X79,OR(Z79="",Z79<100)),"Behind — past end date",IF(AND(T79<>"",X79<>"",Z79<>"",(Z79<100),((TODAY()-T79)/MAX(X79-T79,1)*100)-Z79>15),"Behind — progress lag",IF(AND(X79-TODAY()<=30,X79-TODAY()>=0,OR(Z79="",Z79<90)),"At risk — close to off track","On track")))))))) | IF(OR(F79="",AC79="Completed / Handover",AC79="Cancelled"),"",IF(O79="Not awarded",IF(U79<>"",U79-TODAY(),IF(X79="","",X79-TODAY())),IF(X79="","",X79-TODAY()))) | [14 empty] | IF(OR(F79="",AJ79=""),"",IF(COUNT(AI79:AI79)=0,"",AJ79-LOOKUP(2,1/(AI79:AI79<>""),AI79:AI79))) | IF(OR(F79="",AK79=""),"",IF(COUNT(AI79:AJ79)=0,"",AK79-LOOKUP(2,1/(AI79:AJ79<>""),AI79:AJ79))) | IF(OR(F79="",AL79=""),"",IF(COUNT(AI79:AK79)=0,"",AL79-LOOKUP(2,1/(AI79:AK79<>""),AI79:AK79))) | IF(OR(F79="",AM79=""),"",IF(COUNT(AI79:AL79)=0,"",AM79-LOOKUP(2,1/(AI79:AL79<>""),AI79:AL79))) | IF(OR(F79="",AN79=""),"",IF(COUNT(AI79:AM79)=0,"",AN79-LOOKUP(2,1/(AI79:AM79<>""),AI79:AM79))) | IF(OR(F79="",AO79=""),"",IF(COUNT(AI79:AN79)=0,"",AO79-LOOKUP(2,1/(AI79:AN79<>""),AI79:AN79))) | IF(OR(F79="",AP79=""),"",IF(COUNT(AI79:AO79)=0,"",AP79-LOOKUP(2,1/(AI79:AO79<>""),AI79:AO79))) | IF(OR(F79="",AQ79=""),"",IF(COUNT(AI79:AP79)=0,"",AQ79-LOOKUP(2,1/(AI79:AP79<>""),AI79:AP79))) | IF(OR(F79="",AR79=""),"",IF(COUNT(AI79:AQ79)=0,"",AR79-LOOKUP(2,1/(AI79:AQ79<>""),AI79:AQ79))) | IF(OR(F79="",AS79=""),"",IF(COUNT(AI79:AR79)=0,"",AS79-LOOKUP(2,1/(AI79:AR79<>""),AI79:AR79))) | IF(OR(F79="",AT79=""),"",IF(COUNT(AI79:AS79)=0,"",AT79-LOOKUP(2,1/(AI79:AS79<>""),AI79:AS79))) | IF(OR(F79="",AU79=""),"",IF(COUNT(AI79:AT79)=0,"",AU79-LOOKUP(2,1/(AI79:AT79<>""),AI79:AT79))) | IF(OR(F79="",AV79=""),"",IF(COUNT(AI79:AU79)=0,"",AV79-LOOKUP(2,1/(AI79:AU79<>""),AI79:AU79))) | IF(J79="","All_Provinces",IFERROR(VLOOKUP(J79,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K79="","All_Districts",IFERROR(VLOOKUP(K79,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F80="","",ROW()-3) | [18 empty] | IF(AQ80="","",AQ80) |  |  |  | IF(W80<>"",W80,IF(OR(T80="",V80=""),"",EDATE(T80,V80))) |  |  |  |  | IF(F80="","",IF(COUNT(AI80:AV80)=0,IF(AA80="","Not started",AA80),SUBSTITUTE(LOOKUP(2,1/(AI80:AV80<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F80="",COUNT(AI80:AV80)=0),"",TODAY()-LOOKUP(2,1/(AI80:AV80<>""),AI80:AV80)) | IF(OR(F80="",COUNT(AI80:AV80)<2),"",LOOKUP(2,1/(AI80:AV80<>""),AI80:AV80)-MIN(AI80:AV80)) | IF(OR(AD80="",AC80="Not started",AC80=""),"",IFERROR(AD80-IF(VLOOKUP(AC80,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC80,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F80="","",IF(OR(AA80="Cancelled",AC80="Cancelled"),"Cancelled",IF(OR(AC80="Completed / Handover",Y80<>"",Z80>=100),"Completed — on track",IF(O80="Not awarded",IF(U80="",IF(X80="","No planned date",IF(TODAY()>X80,"Behind — past planned date",IF(X80-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U80,"Behind — award date passed",IF(U80-TODAY()<=30,"At risk — close to off track","On track"))),IF(X80="","No planned date",IF(AND(TODAY()>X80,OR(Z80="",Z80<100)),"Behind — past end date",IF(AND(T80<>"",X80<>"",Z80<>"",(Z80<100),((TODAY()-T80)/MAX(X80-T80,1)*100)-Z80>15),"Behind — progress lag",IF(AND(X80-TODAY()<=30,X80-TODAY()>=0,OR(Z80="",Z80<90)),"At risk — close to off track","On track")))))))) | IF(OR(F80="",AC80="Completed / Handover",AC80="Cancelled"),"",IF(O80="Not awarded",IF(U80<>"",U80-TODAY(),IF(X80="","",X80-TODAY())),IF(X80="","",X80-TODAY()))) | [14 empty] | IF(OR(F80="",AJ80=""),"",IF(COUNT(AI80:AI80)=0,"",AJ80-LOOKUP(2,1/(AI80:AI80<>""),AI80:AI80))) | IF(OR(F80="",AK80=""),"",IF(COUNT(AI80:AJ80)=0,"",AK80-LOOKUP(2,1/(AI80:AJ80<>""),AI80:AJ80))) | IF(OR(F80="",AL80=""),"",IF(COUNT(AI80:AK80)=0,"",AL80-LOOKUP(2,1/(AI80:AK80<>""),AI80:AK80))) | IF(OR(F80="",AM80=""),"",IF(COUNT(AI80:AL80)=0,"",AM80-LOOKUP(2,1/(AI80:AL80<>""),AI80:AL80))) | IF(OR(F80="",AN80=""),"",IF(COUNT(AI80:AM80)=0,"",AN80-LOOKUP(2,1/(AI80:AM80<>""),AI80:AM80))) | IF(OR(F80="",AO80=""),"",IF(COUNT(AI80:AN80)=0,"",AO80-LOOKUP(2,1/(AI80:AN80<>""),AI80:AN80))) | IF(OR(F80="",AP80=""),"",IF(COUNT(AI80:AO80)=0,"",AP80-LOOKUP(2,1/(AI80:AO80<>""),AI80:AO80))) | IF(OR(F80="",AQ80=""),"",IF(COUNT(AI80:AP80)=0,"",AQ80-LOOKUP(2,1/(AI80:AP80<>""),AI80:AP80))) | IF(OR(F80="",AR80=""),"",IF(COUNT(AI80:AQ80)=0,"",AR80-LOOKUP(2,1/(AI80:AQ80<>""),AI80:AQ80))) | IF(OR(F80="",AS80=""),"",IF(COUNT(AI80:AR80)=0,"",AS80-LOOKUP(2,1/(AI80:AR80<>""),AI80:AR80))) | IF(OR(F80="",AT80=""),"",IF(COUNT(AI80:AS80)=0,"",AT80-LOOKUP(2,1/(AI80:AS80<>""),AI80:AS80))) | IF(OR(F80="",AU80=""),"",IF(COUNT(AI80:AT80)=0,"",AU80-LOOKUP(2,1/(AI80:AT80<>""),AI80:AT80))) | IF(OR(F80="",AV80=""),"",IF(COUNT(AI80:AU80)=0,"",AV80-LOOKUP(2,1/(AI80:AU80<>""),AI80:AU80))) | IF(J80="","All_Provinces",IFERROR(VLOOKUP(J80,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K80="","All_Districts",IFERROR(VLOOKUP(K80,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F81="","",ROW()-3) | [18 empty] | IF(AQ81="","",AQ81) |  |  |  | IF(W81<>"",W81,IF(OR(T81="",V81=""),"",EDATE(T81,V81))) |  |  |  |  | IF(F81="","",IF(COUNT(AI81:AV81)=0,IF(AA81="","Not started",AA81),SUBSTITUTE(LOOKUP(2,1/(AI81:AV81<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F81="",COUNT(AI81:AV81)=0),"",TODAY()-LOOKUP(2,1/(AI81:AV81<>""),AI81:AV81)) | IF(OR(F81="",COUNT(AI81:AV81)<2),"",LOOKUP(2,1/(AI81:AV81<>""),AI81:AV81)-MIN(AI81:AV81)) | IF(OR(AD81="",AC81="Not started",AC81=""),"",IFERROR(AD81-IF(VLOOKUP(AC81,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC81,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F81="","",IF(OR(AA81="Cancelled",AC81="Cancelled"),"Cancelled",IF(OR(AC81="Completed / Handover",Y81<>"",Z81>=100),"Completed — on track",IF(O81="Not awarded",IF(U81="",IF(X81="","No planned date",IF(TODAY()>X81,"Behind — past planned date",IF(X81-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U81,"Behind — award date passed",IF(U81-TODAY()<=30,"At risk — close to off track","On track"))),IF(X81="","No planned date",IF(AND(TODAY()>X81,OR(Z81="",Z81<100)),"Behind — past end date",IF(AND(T81<>"",X81<>"",Z81<>"",(Z81<100),((TODAY()-T81)/MAX(X81-T81,1)*100)-Z81>15),"Behind — progress lag",IF(AND(X81-TODAY()<=30,X81-TODAY()>=0,OR(Z81="",Z81<90)),"At risk — close to off track","On track")))))))) | IF(OR(F81="",AC81="Completed / Handover",AC81="Cancelled"),"",IF(O81="Not awarded",IF(U81<>"",U81-TODAY(),IF(X81="","",X81-TODAY())),IF(X81="","",X81-TODAY()))) | [14 empty] | IF(OR(F81="",AJ81=""),"",IF(COUNT(AI81:AI81)=0,"",AJ81-LOOKUP(2,1/(AI81:AI81<>""),AI81:AI81))) | IF(OR(F81="",AK81=""),"",IF(COUNT(AI81:AJ81)=0,"",AK81-LOOKUP(2,1/(AI81:AJ81<>""),AI81:AJ81))) | IF(OR(F81="",AL81=""),"",IF(COUNT(AI81:AK81)=0,"",AL81-LOOKUP(2,1/(AI81:AK81<>""),AI81:AK81))) | IF(OR(F81="",AM81=""),"",IF(COUNT(AI81:AL81)=0,"",AM81-LOOKUP(2,1/(AI81:AL81<>""),AI81:AL81))) | IF(OR(F81="",AN81=""),"",IF(COUNT(AI81:AM81)=0,"",AN81-LOOKUP(2,1/(AI81:AM81<>""),AI81:AM81))) | IF(OR(F81="",AO81=""),"",IF(COUNT(AI81:AN81)=0,"",AO81-LOOKUP(2,1/(AI81:AN81<>""),AI81:AN81))) | IF(OR(F81="",AP81=""),"",IF(COUNT(AI81:AO81)=0,"",AP81-LOOKUP(2,1/(AI81:AO81<>""),AI81:AO81))) | IF(OR(F81="",AQ81=""),"",IF(COUNT(AI81:AP81)=0,"",AQ81-LOOKUP(2,1/(AI81:AP81<>""),AI81:AP81))) | IF(OR(F81="",AR81=""),"",IF(COUNT(AI81:AQ81)=0,"",AR81-LOOKUP(2,1/(AI81:AQ81<>""),AI81:AQ81))) | IF(OR(F81="",AS81=""),"",IF(COUNT(AI81:AR81)=0,"",AS81-LOOKUP(2,1/(AI81:AR81<>""),AI81:AR81))) | IF(OR(F81="",AT81=""),"",IF(COUNT(AI81:AS81)=0,"",AT81-LOOKUP(2,1/(AI81:AS81<>""),AI81:AS81))) | IF(OR(F81="",AU81=""),"",IF(COUNT(AI81:AT81)=0,"",AU81-LOOKUP(2,1/(AI81:AT81<>""),AI81:AT81))) | IF(OR(F81="",AV81=""),"",IF(COUNT(AI81:AU81)=0,"",AV81-LOOKUP(2,1/(AI81:AU81<>""),AI81:AU81))) | IF(J81="","All_Provinces",IFERROR(VLOOKUP(J81,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K81="","All_Districts",IFERROR(VLOOKUP(K81,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F82="","",ROW()-3) | [18 empty] | IF(AQ82="","",AQ82) |  |  |  | IF(W82<>"",W82,IF(OR(T82="",V82=""),"",EDATE(T82,V82))) |  |  |  |  | IF(F82="","",IF(COUNT(AI82:AV82)=0,IF(AA82="","Not started",AA82),SUBSTITUTE(LOOKUP(2,1/(AI82:AV82<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F82="",COUNT(AI82:AV82)=0),"",TODAY()-LOOKUP(2,1/(AI82:AV82<>""),AI82:AV82)) | IF(OR(F82="",COUNT(AI82:AV82)<2),"",LOOKUP(2,1/(AI82:AV82<>""),AI82:AV82)-MIN(AI82:AV82)) | IF(OR(AD82="",AC82="Not started",AC82=""),"",IFERROR(AD82-IF(VLOOKUP(AC82,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC82,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F82="","",IF(OR(AA82="Cancelled",AC82="Cancelled"),"Cancelled",IF(OR(AC82="Completed / Handover",Y82<>"",Z82>=100),"Completed — on track",IF(O82="Not awarded",IF(U82="",IF(X82="","No planned date",IF(TODAY()>X82,"Behind — past planned date",IF(X82-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U82,"Behind — award date passed",IF(U82-TODAY()<=30,"At risk — close to off track","On track"))),IF(X82="","No planned date",IF(AND(TODAY()>X82,OR(Z82="",Z82<100)),"Behind — past end date",IF(AND(T82<>"",X82<>"",Z82<>"",(Z82<100),((TODAY()-T82)/MAX(X82-T82,1)*100)-Z82>15),"Behind — progress lag",IF(AND(X82-TODAY()<=30,X82-TODAY()>=0,OR(Z82="",Z82<90)),"At risk — close to off track","On track")))))))) | IF(OR(F82="",AC82="Completed / Handover",AC82="Cancelled"),"",IF(O82="Not awarded",IF(U82<>"",U82-TODAY(),IF(X82="","",X82-TODAY())),IF(X82="","",X82-TODAY()))) | [14 empty] | IF(OR(F82="",AJ82=""),"",IF(COUNT(AI82:AI82)=0,"",AJ82-LOOKUP(2,1/(AI82:AI82<>""),AI82:AI82))) | IF(OR(F82="",AK82=""),"",IF(COUNT(AI82:AJ82)=0,"",AK82-LOOKUP(2,1/(AI82:AJ82<>""),AI82:AJ82))) | IF(OR(F82="",AL82=""),"",IF(COUNT(AI82:AK82)=0,"",AL82-LOOKUP(2,1/(AI82:AK82<>""),AI82:AK82))) | IF(OR(F82="",AM82=""),"",IF(COUNT(AI82:AL82)=0,"",AM82-LOOKUP(2,1/(AI82:AL82<>""),AI82:AL82))) | IF(OR(F82="",AN82=""),"",IF(COUNT(AI82:AM82)=0,"",AN82-LOOKUP(2,1/(AI82:AM82<>""),AI82:AM82))) | IF(OR(F82="",AO82=""),"",IF(COUNT(AI82:AN82)=0,"",AO82-LOOKUP(2,1/(AI82:AN82<>""),AI82:AN82))) | IF(OR(F82="",AP82=""),"",IF(COUNT(AI82:AO82)=0,"",AP82-LOOKUP(2,1/(AI82:AO82<>""),AI82:AO82))) | IF(OR(F82="",AQ82=""),"",IF(COUNT(AI82:AP82)=0,"",AQ82-LOOKUP(2,1/(AI82:AP82<>""),AI82:AP82))) | IF(OR(F82="",AR82=""),"",IF(COUNT(AI82:AQ82)=0,"",AR82-LOOKUP(2,1/(AI82:AQ82<>""),AI82:AQ82))) | IF(OR(F82="",AS82=""),"",IF(COUNT(AI82:AR82)=0,"",AS82-LOOKUP(2,1/(AI82:AR82<>""),AI82:AR82))) | IF(OR(F82="",AT82=""),"",IF(COUNT(AI82:AS82)=0,"",AT82-LOOKUP(2,1/(AI82:AS82<>""),AI82:AS82))) | IF(OR(F82="",AU82=""),"",IF(COUNT(AI82:AT82)=0,"",AU82-LOOKUP(2,1/(AI82:AT82<>""),AI82:AT82))) | IF(OR(F82="",AV82=""),"",IF(COUNT(AI82:AU82)=0,"",AV82-LOOKUP(2,1/(AI82:AU82<>""),AI82:AU82))) | IF(J82="","All_Provinces",IFERROR(VLOOKUP(J82,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K82="","All_Districts",IFERROR(VLOOKUP(K82,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F83="","",ROW()-3) | [18 empty] | IF(AQ83="","",AQ83) |  |  |  | IF(W83<>"",W83,IF(OR(T83="",V83=""),"",EDATE(T83,V83))) |  |  |  |  | IF(F83="","",IF(COUNT(AI83:AV83)=0,IF(AA83="","Not started",AA83),SUBSTITUTE(LOOKUP(2,1/(AI83:AV83<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F83="",COUNT(AI83:AV83)=0),"",TODAY()-LOOKUP(2,1/(AI83:AV83<>""),AI83:AV83)) | IF(OR(F83="",COUNT(AI83:AV83)<2),"",LOOKUP(2,1/(AI83:AV83<>""),AI83:AV83)-MIN(AI83:AV83)) | IF(OR(AD83="",AC83="Not started",AC83=""),"",IFERROR(AD83-IF(VLOOKUP(AC83,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC83,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F83="","",IF(OR(AA83="Cancelled",AC83="Cancelled"),"Cancelled",IF(OR(AC83="Completed / Handover",Y83<>"",Z83>=100),"Completed — on track",IF(O83="Not awarded",IF(U83="",IF(X83="","No planned date",IF(TODAY()>X83,"Behind — past planned date",IF(X83-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U83,"Behind — award date passed",IF(U83-TODAY()<=30,"At risk — close to off track","On track"))),IF(X83="","No planned date",IF(AND(TODAY()>X83,OR(Z83="",Z83<100)),"Behind — past end date",IF(AND(T83<>"",X83<>"",Z83<>"",(Z83<100),((TODAY()-T83)/MAX(X83-T83,1)*100)-Z83>15),"Behind — progress lag",IF(AND(X83-TODAY()<=30,X83-TODAY()>=0,OR(Z83="",Z83<90)),"At risk — close to off track","On track")))))))) | IF(OR(F83="",AC83="Completed / Handover",AC83="Cancelled"),"",IF(O83="Not awarded",IF(U83<>"",U83-TODAY(),IF(X83="","",X83-TODAY())),IF(X83="","",X83-TODAY()))) | [14 empty] | IF(OR(F83="",AJ83=""),"",IF(COUNT(AI83:AI83)=0,"",AJ83-LOOKUP(2,1/(AI83:AI83<>""),AI83:AI83))) | IF(OR(F83="",AK83=""),"",IF(COUNT(AI83:AJ83)=0,"",AK83-LOOKUP(2,1/(AI83:AJ83<>""),AI83:AJ83))) | IF(OR(F83="",AL83=""),"",IF(COUNT(AI83:AK83)=0,"",AL83-LOOKUP(2,1/(AI83:AK83<>""),AI83:AK83))) | IF(OR(F83="",AM83=""),"",IF(COUNT(AI83:AL83)=0,"",AM83-LOOKUP(2,1/(AI83:AL83<>""),AI83:AL83))) | IF(OR(F83="",AN83=""),"",IF(COUNT(AI83:AM83)=0,"",AN83-LOOKUP(2,1/(AI83:AM83<>""),AI83:AM83))) | IF(OR(F83="",AO83=""),"",IF(COUNT(AI83:AN83)=0,"",AO83-LOOKUP(2,1/(AI83:AN83<>""),AI83:AN83))) | IF(OR(F83="",AP83=""),"",IF(COUNT(AI83:AO83)=0,"",AP83-LOOKUP(2,1/(AI83:AO83<>""),AI83:AO83))) | IF(OR(F83="",AQ83=""),"",IF(COUNT(AI83:AP83)=0,"",AQ83-LOOKUP(2,1/(AI83:AP83<>""),AI83:AP83))) | IF(OR(F83="",AR83=""),"",IF(COUNT(AI83:AQ83)=0,"",AR83-LOOKUP(2,1/(AI83:AQ83<>""),AI83:AQ83))) | IF(OR(F83="",AS83=""),"",IF(COUNT(AI83:AR83)=0,"",AS83-LOOKUP(2,1/(AI83:AR83<>""),AI83:AR83))) | IF(OR(F83="",AT83=""),"",IF(COUNT(AI83:AS83)=0,"",AT83-LOOKUP(2,1/(AI83:AS83<>""),AI83:AS83))) | IF(OR(F83="",AU83=""),"",IF(COUNT(AI83:AT83)=0,"",AU83-LOOKUP(2,1/(AI83:AT83<>""),AI83:AT83))) | IF(OR(F83="",AV83=""),"",IF(COUNT(AI83:AU83)=0,"",AV83-LOOKUP(2,1/(AI83:AU83<>""),AI83:AU83))) | IF(J83="","All_Provinces",IFERROR(VLOOKUP(J83,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K83="","All_Districts",IFERROR(VLOOKUP(K83,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F84="","",ROW()-3) | [18 empty] | IF(AQ84="","",AQ84) |  |  |  | IF(W84<>"",W84,IF(OR(T84="",V84=""),"",EDATE(T84,V84))) |  |  |  |  | IF(F84="","",IF(COUNT(AI84:AV84)=0,IF(AA84="","Not started",AA84),SUBSTITUTE(LOOKUP(2,1/(AI84:AV84<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F84="",COUNT(AI84:AV84)=0),"",TODAY()-LOOKUP(2,1/(AI84:AV84<>""),AI84:AV84)) | IF(OR(F84="",COUNT(AI84:AV84)<2),"",LOOKUP(2,1/(AI84:AV84<>""),AI84:AV84)-MIN(AI84:AV84)) | IF(OR(AD84="",AC84="Not started",AC84=""),"",IFERROR(AD84-IF(VLOOKUP(AC84,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC84,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F84="","",IF(OR(AA84="Cancelled",AC84="Cancelled"),"Cancelled",IF(OR(AC84="Completed / Handover",Y84<>"",Z84>=100),"Completed — on track",IF(O84="Not awarded",IF(U84="",IF(X84="","No planned date",IF(TODAY()>X84,"Behind — past planned date",IF(X84-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U84,"Behind — award date passed",IF(U84-TODAY()<=30,"At risk — close to off track","On track"))),IF(X84="","No planned date",IF(AND(TODAY()>X84,OR(Z84="",Z84<100)),"Behind — past end date",IF(AND(T84<>"",X84<>"",Z84<>"",(Z84<100),((TODAY()-T84)/MAX(X84-T84,1)*100)-Z84>15),"Behind — progress lag",IF(AND(X84-TODAY()<=30,X84-TODAY()>=0,OR(Z84="",Z84<90)),"At risk — close to off track","On track")))))))) | IF(OR(F84="",AC84="Completed / Handover",AC84="Cancelled"),"",IF(O84="Not awarded",IF(U84<>"",U84-TODAY(),IF(X84="","",X84-TODAY())),IF(X84="","",X84-TODAY()))) | [14 empty] | IF(OR(F84="",AJ84=""),"",IF(COUNT(AI84:AI84)=0,"",AJ84-LOOKUP(2,1/(AI84:AI84<>""),AI84:AI84))) | IF(OR(F84="",AK84=""),"",IF(COUNT(AI84:AJ84)=0,"",AK84-LOOKUP(2,1/(AI84:AJ84<>""),AI84:AJ84))) | IF(OR(F84="",AL84=""),"",IF(COUNT(AI84:AK84)=0,"",AL84-LOOKUP(2,1/(AI84:AK84<>""),AI84:AK84))) | IF(OR(F84="",AM84=""),"",IF(COUNT(AI84:AL84)=0,"",AM84-LOOKUP(2,1/(AI84:AL84<>""),AI84:AL84))) | IF(OR(F84="",AN84=""),"",IF(COUNT(AI84:AM84)=0,"",AN84-LOOKUP(2,1/(AI84:AM84<>""),AI84:AM84))) | IF(OR(F84="",AO84=""),"",IF(COUNT(AI84:AN84)=0,"",AO84-LOOKUP(2,1/(AI84:AN84<>""),AI84:AN84))) | IF(OR(F84="",AP84=""),"",IF(COUNT(AI84:AO84)=0,"",AP84-LOOKUP(2,1/(AI84:AO84<>""),AI84:AO84))) | IF(OR(F84="",AQ84=""),"",IF(COUNT(AI84:AP84)=0,"",AQ84-LOOKUP(2,1/(AI84:AP84<>""),AI84:AP84))) | IF(OR(F84="",AR84=""),"",IF(COUNT(AI84:AQ84)=0,"",AR84-LOOKUP(2,1/(AI84:AQ84<>""),AI84:AQ84))) | IF(OR(F84="",AS84=""),"",IF(COUNT(AI84:AR84)=0,"",AS84-LOOKUP(2,1/(AI84:AR84<>""),AI84:AR84))) | IF(OR(F84="",AT84=""),"",IF(COUNT(AI84:AS84)=0,"",AT84-LOOKUP(2,1/(AI84:AS84<>""),AI84:AS84))) | IF(OR(F84="",AU84=""),"",IF(COUNT(AI84:AT84)=0,"",AU84-LOOKUP(2,1/(AI84:AT84<>""),AI84:AT84))) | IF(OR(F84="",AV84=""),"",IF(COUNT(AI84:AU84)=0,"",AV84-LOOKUP(2,1/(AI84:AU84<>""),AI84:AU84))) | IF(J84="","All_Provinces",IFERROR(VLOOKUP(J84,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K84="","All_Districts",IFERROR(VLOOKUP(K84,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F85="","",ROW()-3) | [18 empty] | IF(AQ85="","",AQ85) |  |  |  | IF(W85<>"",W85,IF(OR(T85="",V85=""),"",EDATE(T85,V85))) |  |  |  |  | IF(F85="","",IF(COUNT(AI85:AV85)=0,IF(AA85="","Not started",AA85),SUBSTITUTE(LOOKUP(2,1/(AI85:AV85<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F85="",COUNT(AI85:AV85)=0),"",TODAY()-LOOKUP(2,1/(AI85:AV85<>""),AI85:AV85)) | IF(OR(F85="",COUNT(AI85:AV85)<2),"",LOOKUP(2,1/(AI85:AV85<>""),AI85:AV85)-MIN(AI85:AV85)) | IF(OR(AD85="",AC85="Not started",AC85=""),"",IFERROR(AD85-IF(VLOOKUP(AC85,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC85,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F85="","",IF(OR(AA85="Cancelled",AC85="Cancelled"),"Cancelled",IF(OR(AC85="Completed / Handover",Y85<>"",Z85>=100),"Completed — on track",IF(O85="Not awarded",IF(U85="",IF(X85="","No planned date",IF(TODAY()>X85,"Behind — past planned date",IF(X85-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U85,"Behind — award date passed",IF(U85-TODAY()<=30,"At risk — close to off track","On track"))),IF(X85="","No planned date",IF(AND(TODAY()>X85,OR(Z85="",Z85<100)),"Behind — past end date",IF(AND(T85<>"",X85<>"",Z85<>"",(Z85<100),((TODAY()-T85)/MAX(X85-T85,1)*100)-Z85>15),"Behind — progress lag",IF(AND(X85-TODAY()<=30,X85-TODAY()>=0,OR(Z85="",Z85<90)),"At risk — close to off track","On track")))))))) | IF(OR(F85="",AC85="Completed / Handover",AC85="Cancelled"),"",IF(O85="Not awarded",IF(U85<>"",U85-TODAY(),IF(X85="","",X85-TODAY())),IF(X85="","",X85-TODAY()))) | [14 empty] | IF(OR(F85="",AJ85=""),"",IF(COUNT(AI85:AI85)=0,"",AJ85-LOOKUP(2,1/(AI85:AI85<>""),AI85:AI85))) | IF(OR(F85="",AK85=""),"",IF(COUNT(AI85:AJ85)=0,"",AK85-LOOKUP(2,1/(AI85:AJ85<>""),AI85:AJ85))) | IF(OR(F85="",AL85=""),"",IF(COUNT(AI85:AK85)=0,"",AL85-LOOKUP(2,1/(AI85:AK85<>""),AI85:AK85))) | IF(OR(F85="",AM85=""),"",IF(COUNT(AI85:AL85)=0,"",AM85-LOOKUP(2,1/(AI85:AL85<>""),AI85:AL85))) | IF(OR(F85="",AN85=""),"",IF(COUNT(AI85:AM85)=0,"",AN85-LOOKUP(2,1/(AI85:AM85<>""),AI85:AM85))) | IF(OR(F85="",AO85=""),"",IF(COUNT(AI85:AN85)=0,"",AO85-LOOKUP(2,1/(AI85:AN85<>""),AI85:AN85))) | IF(OR(F85="",AP85=""),"",IF(COUNT(AI85:AO85)=0,"",AP85-LOOKUP(2,1/(AI85:AO85<>""),AI85:AO85))) | IF(OR(F85="",AQ85=""),"",IF(COUNT(AI85:AP85)=0,"",AQ85-LOOKUP(2,1/(AI85:AP85<>""),AI85:AP85))) | IF(OR(F85="",AR85=""),"",IF(COUNT(AI85:AQ85)=0,"",AR85-LOOKUP(2,1/(AI85:AQ85<>""),AI85:AQ85))) | IF(OR(F85="",AS85=""),"",IF(COUNT(AI85:AR85)=0,"",AS85-LOOKUP(2,1/(AI85:AR85<>""),AI85:AR85))) | IF(OR(F85="",AT85=""),"",IF(COUNT(AI85:AS85)=0,"",AT85-LOOKUP(2,1/(AI85:AS85<>""),AI85:AS85))) | IF(OR(F85="",AU85=""),"",IF(COUNT(AI85:AT85)=0,"",AU85-LOOKUP(2,1/(AI85:AT85<>""),AI85:AT85))) | IF(OR(F85="",AV85=""),"",IF(COUNT(AI85:AU85)=0,"",AV85-LOOKUP(2,1/(AI85:AU85<>""),AI85:AU85))) | IF(J85="","All_Provinces",IFERROR(VLOOKUP(J85,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K85="","All_Districts",IFERROR(VLOOKUP(K85,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F86="","",ROW()-3) | [18 empty] | IF(AQ86="","",AQ86) |  |  |  | IF(W86<>"",W86,IF(OR(T86="",V86=""),"",EDATE(T86,V86))) |  |  |  |  | IF(F86="","",IF(COUNT(AI86:AV86)=0,IF(AA86="","Not started",AA86),SUBSTITUTE(LOOKUP(2,1/(AI86:AV86<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F86="",COUNT(AI86:AV86)=0),"",TODAY()-LOOKUP(2,1/(AI86:AV86<>""),AI86:AV86)) | IF(OR(F86="",COUNT(AI86:AV86)<2),"",LOOKUP(2,1/(AI86:AV86<>""),AI86:AV86)-MIN(AI86:AV86)) | IF(OR(AD86="",AC86="Not started",AC86=""),"",IFERROR(AD86-IF(VLOOKUP(AC86,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC86,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F86="","",IF(OR(AA86="Cancelled",AC86="Cancelled"),"Cancelled",IF(OR(AC86="Completed / Handover",Y86<>"",Z86>=100),"Completed — on track",IF(O86="Not awarded",IF(U86="",IF(X86="","No planned date",IF(TODAY()>X86,"Behind — past planned date",IF(X86-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U86,"Behind — award date passed",IF(U86-TODAY()<=30,"At risk — close to off track","On track"))),IF(X86="","No planned date",IF(AND(TODAY()>X86,OR(Z86="",Z86<100)),"Behind — past end date",IF(AND(T86<>"",X86<>"",Z86<>"",(Z86<100),((TODAY()-T86)/MAX(X86-T86,1)*100)-Z86>15),"Behind — progress lag",IF(AND(X86-TODAY()<=30,X86-TODAY()>=0,OR(Z86="",Z86<90)),"At risk — close to off track","On track")))))))) | IF(OR(F86="",AC86="Completed / Handover",AC86="Cancelled"),"",IF(O86="Not awarded",IF(U86<>"",U86-TODAY(),IF(X86="","",X86-TODAY())),IF(X86="","",X86-TODAY()))) | [14 empty] | IF(OR(F86="",AJ86=""),"",IF(COUNT(AI86:AI86)=0,"",AJ86-LOOKUP(2,1/(AI86:AI86<>""),AI86:AI86))) | IF(OR(F86="",AK86=""),"",IF(COUNT(AI86:AJ86)=0,"",AK86-LOOKUP(2,1/(AI86:AJ86<>""),AI86:AJ86))) | IF(OR(F86="",AL86=""),"",IF(COUNT(AI86:AK86)=0,"",AL86-LOOKUP(2,1/(AI86:AK86<>""),AI86:AK86))) | IF(OR(F86="",AM86=""),"",IF(COUNT(AI86:AL86)=0,"",AM86-LOOKUP(2,1/(AI86:AL86<>""),AI86:AL86))) | IF(OR(F86="",AN86=""),"",IF(COUNT(AI86:AM86)=0,"",AN86-LOOKUP(2,1/(AI86:AM86<>""),AI86:AM86))) | IF(OR(F86="",AO86=""),"",IF(COUNT(AI86:AN86)=0,"",AO86-LOOKUP(2,1/(AI86:AN86<>""),AI86:AN86))) | IF(OR(F86="",AP86=""),"",IF(COUNT(AI86:AO86)=0,"",AP86-LOOKUP(2,1/(AI86:AO86<>""),AI86:AO86))) | IF(OR(F86="",AQ86=""),"",IF(COUNT(AI86:AP86)=0,"",AQ86-LOOKUP(2,1/(AI86:AP86<>""),AI86:AP86))) | IF(OR(F86="",AR86=""),"",IF(COUNT(AI86:AQ86)=0,"",AR86-LOOKUP(2,1/(AI86:AQ86<>""),AI86:AQ86))) | IF(OR(F86="",AS86=""),"",IF(COUNT(AI86:AR86)=0,"",AS86-LOOKUP(2,1/(AI86:AR86<>""),AI86:AR86))) | IF(OR(F86="",AT86=""),"",IF(COUNT(AI86:AS86)=0,"",AT86-LOOKUP(2,1/(AI86:AS86<>""),AI86:AS86))) | IF(OR(F86="",AU86=""),"",IF(COUNT(AI86:AT86)=0,"",AU86-LOOKUP(2,1/(AI86:AT86<>""),AI86:AT86))) | IF(OR(F86="",AV86=""),"",IF(COUNT(AI86:AU86)=0,"",AV86-LOOKUP(2,1/(AI86:AU86<>""),AI86:AU86))) | IF(J86="","All_Provinces",IFERROR(VLOOKUP(J86,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K86="","All_Districts",IFERROR(VLOOKUP(K86,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F87="","",ROW()-3) | [18 empty] | IF(AQ87="","",AQ87) |  |  |  | IF(W87<>"",W87,IF(OR(T87="",V87=""),"",EDATE(T87,V87))) |  |  |  |  | IF(F87="","",IF(COUNT(AI87:AV87)=0,IF(AA87="","Not started",AA87),SUBSTITUTE(LOOKUP(2,1/(AI87:AV87<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F87="",COUNT(AI87:AV87)=0),"",TODAY()-LOOKUP(2,1/(AI87:AV87<>""),AI87:AV87)) | IF(OR(F87="",COUNT(AI87:AV87)<2),"",LOOKUP(2,1/(AI87:AV87<>""),AI87:AV87)-MIN(AI87:AV87)) | IF(OR(AD87="",AC87="Not started",AC87=""),"",IFERROR(AD87-IF(VLOOKUP(AC87,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC87,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F87="","",IF(OR(AA87="Cancelled",AC87="Cancelled"),"Cancelled",IF(OR(AC87="Completed / Handover",Y87<>"",Z87>=100),"Completed — on track",IF(O87="Not awarded",IF(U87="",IF(X87="","No planned date",IF(TODAY()>X87,"Behind — past planned date",IF(X87-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U87,"Behind — award date passed",IF(U87-TODAY()<=30,"At risk — close to off track","On track"))),IF(X87="","No planned date",IF(AND(TODAY()>X87,OR(Z87="",Z87<100)),"Behind — past end date",IF(AND(T87<>"",X87<>"",Z87<>"",(Z87<100),((TODAY()-T87)/MAX(X87-T87,1)*100)-Z87>15),"Behind — progress lag",IF(AND(X87-TODAY()<=30,X87-TODAY()>=0,OR(Z87="",Z87<90)),"At risk — close to off track","On track")))))))) | IF(OR(F87="",AC87="Completed / Handover",AC87="Cancelled"),"",IF(O87="Not awarded",IF(U87<>"",U87-TODAY(),IF(X87="","",X87-TODAY())),IF(X87="","",X87-TODAY()))) | [14 empty] | IF(OR(F87="",AJ87=""),"",IF(COUNT(AI87:AI87)=0,"",AJ87-LOOKUP(2,1/(AI87:AI87<>""),AI87:AI87))) | IF(OR(F87="",AK87=""),"",IF(COUNT(AI87:AJ87)=0,"",AK87-LOOKUP(2,1/(AI87:AJ87<>""),AI87:AJ87))) | IF(OR(F87="",AL87=""),"",IF(COUNT(AI87:AK87)=0,"",AL87-LOOKUP(2,1/(AI87:AK87<>""),AI87:AK87))) | IF(OR(F87="",AM87=""),"",IF(COUNT(AI87:AL87)=0,"",AM87-LOOKUP(2,1/(AI87:AL87<>""),AI87:AL87))) | IF(OR(F87="",AN87=""),"",IF(COUNT(AI87:AM87)=0,"",AN87-LOOKUP(2,1/(AI87:AM87<>""),AI87:AM87))) | IF(OR(F87="",AO87=""),"",IF(COUNT(AI87:AN87)=0,"",AO87-LOOKUP(2,1/(AI87:AN87<>""),AI87:AN87))) | IF(OR(F87="",AP87=""),"",IF(COUNT(AI87:AO87)=0,"",AP87-LOOKUP(2,1/(AI87:AO87<>""),AI87:AO87))) | IF(OR(F87="",AQ87=""),"",IF(COUNT(AI87:AP87)=0,"",AQ87-LOOKUP(2,1/(AI87:AP87<>""),AI87:AP87))) | IF(OR(F87="",AR87=""),"",IF(COUNT(AI87:AQ87)=0,"",AR87-LOOKUP(2,1/(AI87:AQ87<>""),AI87:AQ87))) | IF(OR(F87="",AS87=""),"",IF(COUNT(AI87:AR87)=0,"",AS87-LOOKUP(2,1/(AI87:AR87<>""),AI87:AR87))) | IF(OR(F87="",AT87=""),"",IF(COUNT(AI87:AS87)=0,"",AT87-LOOKUP(2,1/(AI87:AS87<>""),AI87:AS87))) | IF(OR(F87="",AU87=""),"",IF(COUNT(AI87:AT87)=0,"",AU87-LOOKUP(2,1/(AI87:AT87<>""),AI87:AT87))) | IF(OR(F87="",AV87=""),"",IF(COUNT(AI87:AU87)=0,"",AV87-LOOKUP(2,1/(AI87:AU87<>""),AI87:AU87))) | IF(J87="","All_Provinces",IFERROR(VLOOKUP(J87,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K87="","All_Districts",IFERROR(VLOOKUP(K87,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F88="","",ROW()-3) | [18 empty] | IF(AQ88="","",AQ88) |  |  |  | IF(W88<>"",W88,IF(OR(T88="",V88=""),"",EDATE(T88,V88))) |  |  |  |  | IF(F88="","",IF(COUNT(AI88:AV88)=0,IF(AA88="","Not started",AA88),SUBSTITUTE(LOOKUP(2,1/(AI88:AV88<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F88="",COUNT(AI88:AV88)=0),"",TODAY()-LOOKUP(2,1/(AI88:AV88<>""),AI88:AV88)) | IF(OR(F88="",COUNT(AI88:AV88)<2),"",LOOKUP(2,1/(AI88:AV88<>""),AI88:AV88)-MIN(AI88:AV88)) | IF(OR(AD88="",AC88="Not started",AC88=""),"",IFERROR(AD88-IF(VLOOKUP(AC88,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC88,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F88="","",IF(OR(AA88="Cancelled",AC88="Cancelled"),"Cancelled",IF(OR(AC88="Completed / Handover",Y88<>"",Z88>=100),"Completed — on track",IF(O88="Not awarded",IF(U88="",IF(X88="","No planned date",IF(TODAY()>X88,"Behind — past planned date",IF(X88-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U88,"Behind — award date passed",IF(U88-TODAY()<=30,"At risk — close to off track","On track"))),IF(X88="","No planned date",IF(AND(TODAY()>X88,OR(Z88="",Z88<100)),"Behind — past end date",IF(AND(T88<>"",X88<>"",Z88<>"",(Z88<100),((TODAY()-T88)/MAX(X88-T88,1)*100)-Z88>15),"Behind — progress lag",IF(AND(X88-TODAY()<=30,X88-TODAY()>=0,OR(Z88="",Z88<90)),"At risk — close to off track","On track")))))))) | IF(OR(F88="",AC88="Completed / Handover",AC88="Cancelled"),"",IF(O88="Not awarded",IF(U88<>"",U88-TODAY(),IF(X88="","",X88-TODAY())),IF(X88="","",X88-TODAY()))) | [14 empty] | IF(OR(F88="",AJ88=""),"",IF(COUNT(AI88:AI88)=0,"",AJ88-LOOKUP(2,1/(AI88:AI88<>""),AI88:AI88))) | IF(OR(F88="",AK88=""),"",IF(COUNT(AI88:AJ88)=0,"",AK88-LOOKUP(2,1/(AI88:AJ88<>""),AI88:AJ88))) | IF(OR(F88="",AL88=""),"",IF(COUNT(AI88:AK88)=0,"",AL88-LOOKUP(2,1/(AI88:AK88<>""),AI88:AK88))) | IF(OR(F88="",AM88=""),"",IF(COUNT(AI88:AL88)=0,"",AM88-LOOKUP(2,1/(AI88:AL88<>""),AI88:AL88))) | IF(OR(F88="",AN88=""),"",IF(COUNT(AI88:AM88)=0,"",AN88-LOOKUP(2,1/(AI88:AM88<>""),AI88:AM88))) | IF(OR(F88="",AO88=""),"",IF(COUNT(AI88:AN88)=0,"",AO88-LOOKUP(2,1/(AI88:AN88<>""),AI88:AN88))) | IF(OR(F88="",AP88=""),"",IF(COUNT(AI88:AO88)=0,"",AP88-LOOKUP(2,1/(AI88:AO88<>""),AI88:AO88))) | IF(OR(F88="",AQ88=""),"",IF(COUNT(AI88:AP88)=0,"",AQ88-LOOKUP(2,1/(AI88:AP88<>""),AI88:AP88))) | IF(OR(F88="",AR88=""),"",IF(COUNT(AI88:AQ88)=0,"",AR88-LOOKUP(2,1/(AI88:AQ88<>""),AI88:AQ88))) | IF(OR(F88="",AS88=""),"",IF(COUNT(AI88:AR88)=0,"",AS88-LOOKUP(2,1/(AI88:AR88<>""),AI88:AR88))) | IF(OR(F88="",AT88=""),"",IF(COUNT(AI88:AS88)=0,"",AT88-LOOKUP(2,1/(AI88:AS88<>""),AI88:AS88))) | IF(OR(F88="",AU88=""),"",IF(COUNT(AI88:AT88)=0,"",AU88-LOOKUP(2,1/(AI88:AT88<>""),AI88:AT88))) | IF(OR(F88="",AV88=""),"",IF(COUNT(AI88:AU88)=0,"",AV88-LOOKUP(2,1/(AI88:AU88<>""),AI88:AU88))) | IF(J88="","All_Provinces",IFERROR(VLOOKUP(J88,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K88="","All_Districts",IFERROR(VLOOKUP(K88,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F89="","",ROW()-3) | [18 empty] | IF(AQ89="","",AQ89) |  |  |  | IF(W89<>"",W89,IF(OR(T89="",V89=""),"",EDATE(T89,V89))) |  |  |  |  | IF(F89="","",IF(COUNT(AI89:AV89)=0,IF(AA89="","Not started",AA89),SUBSTITUTE(LOOKUP(2,1/(AI89:AV89<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F89="",COUNT(AI89:AV89)=0),"",TODAY()-LOOKUP(2,1/(AI89:AV89<>""),AI89:AV89)) | IF(OR(F89="",COUNT(AI89:AV89)<2),"",LOOKUP(2,1/(AI89:AV89<>""),AI89:AV89)-MIN(AI89:AV89)) | IF(OR(AD89="",AC89="Not started",AC89=""),"",IFERROR(AD89-IF(VLOOKUP(AC89,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC89,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F89="","",IF(OR(AA89="Cancelled",AC89="Cancelled"),"Cancelled",IF(OR(AC89="Completed / Handover",Y89<>"",Z89>=100),"Completed — on track",IF(O89="Not awarded",IF(U89="",IF(X89="","No planned date",IF(TODAY()>X89,"Behind — past planned date",IF(X89-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U89,"Behind — award date passed",IF(U89-TODAY()<=30,"At risk — close to off track","On track"))),IF(X89="","No planned date",IF(AND(TODAY()>X89,OR(Z89="",Z89<100)),"Behind — past end date",IF(AND(T89<>"",X89<>"",Z89<>"",(Z89<100),((TODAY()-T89)/MAX(X89-T89,1)*100)-Z89>15),"Behind — progress lag",IF(AND(X89-TODAY()<=30,X89-TODAY()>=0,OR(Z89="",Z89<90)),"At risk — close to off track","On track")))))))) | IF(OR(F89="",AC89="Completed / Handover",AC89="Cancelled"),"",IF(O89="Not awarded",IF(U89<>"",U89-TODAY(),IF(X89="","",X89-TODAY())),IF(X89="","",X89-TODAY()))) | [14 empty] | IF(OR(F89="",AJ89=""),"",IF(COUNT(AI89:AI89)=0,"",AJ89-LOOKUP(2,1/(AI89:AI89<>""),AI89:AI89))) | IF(OR(F89="",AK89=""),"",IF(COUNT(AI89:AJ89)=0,"",AK89-LOOKUP(2,1/(AI89:AJ89<>""),AI89:AJ89))) | IF(OR(F89="",AL89=""),"",IF(COUNT(AI89:AK89)=0,"",AL89-LOOKUP(2,1/(AI89:AK89<>""),AI89:AK89))) | IF(OR(F89="",AM89=""),"",IF(COUNT(AI89:AL89)=0,"",AM89-LOOKUP(2,1/(AI89:AL89<>""),AI89:AL89))) | IF(OR(F89="",AN89=""),"",IF(COUNT(AI89:AM89)=0,"",AN89-LOOKUP(2,1/(AI89:AM89<>""),AI89:AM89))) | IF(OR(F89="",AO89=""),"",IF(COUNT(AI89:AN89)=0,"",AO89-LOOKUP(2,1/(AI89:AN89<>""),AI89:AN89))) | IF(OR(F89="",AP89=""),"",IF(COUNT(AI89:AO89)=0,"",AP89-LOOKUP(2,1/(AI89:AO89<>""),AI89:AO89))) | IF(OR(F89="",AQ89=""),"",IF(COUNT(AI89:AP89)=0,"",AQ89-LOOKUP(2,1/(AI89:AP89<>""),AI89:AP89))) | IF(OR(F89="",AR89=""),"",IF(COUNT(AI89:AQ89)=0,"",AR89-LOOKUP(2,1/(AI89:AQ89<>""),AI89:AQ89))) | IF(OR(F89="",AS89=""),"",IF(COUNT(AI89:AR89)=0,"",AS89-LOOKUP(2,1/(AI89:AR89<>""),AI89:AR89))) | IF(OR(F89="",AT89=""),"",IF(COUNT(AI89:AS89)=0,"",AT89-LOOKUP(2,1/(AI89:AS89<>""),AI89:AS89))) | IF(OR(F89="",AU89=""),"",IF(COUNT(AI89:AT89)=0,"",AU89-LOOKUP(2,1/(AI89:AT89<>""),AI89:AT89))) | IF(OR(F89="",AV89=""),"",IF(COUNT(AI89:AU89)=0,"",AV89-LOOKUP(2,1/(AI89:AU89<>""),AI89:AU89))) | IF(J89="","All_Provinces",IFERROR(VLOOKUP(J89,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K89="","All_Districts",IFERROR(VLOOKUP(K89,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F90="","",ROW()-3) | [18 empty] | IF(AQ90="","",AQ90) |  |  |  | IF(W90<>"",W90,IF(OR(T90="",V90=""),"",EDATE(T90,V90))) |  |  |  |  | IF(F90="","",IF(COUNT(AI90:AV90)=0,IF(AA90="","Not started",AA90),SUBSTITUTE(LOOKUP(2,1/(AI90:AV90<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F90="",COUNT(AI90:AV90)=0),"",TODAY()-LOOKUP(2,1/(AI90:AV90<>""),AI90:AV90)) | IF(OR(F90="",COUNT(AI90:AV90)<2),"",LOOKUP(2,1/(AI90:AV90<>""),AI90:AV90)-MIN(AI90:AV90)) | IF(OR(AD90="",AC90="Not started",AC90=""),"",IFERROR(AD90-IF(VLOOKUP(AC90,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC90,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F90="","",IF(OR(AA90="Cancelled",AC90="Cancelled"),"Cancelled",IF(OR(AC90="Completed / Handover",Y90<>"",Z90>=100),"Completed — on track",IF(O90="Not awarded",IF(U90="",IF(X90="","No planned date",IF(TODAY()>X90,"Behind — past planned date",IF(X90-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U90,"Behind — award date passed",IF(U90-TODAY()<=30,"At risk — close to off track","On track"))),IF(X90="","No planned date",IF(AND(TODAY()>X90,OR(Z90="",Z90<100)),"Behind — past end date",IF(AND(T90<>"",X90<>"",Z90<>"",(Z90<100),((TODAY()-T90)/MAX(X90-T90,1)*100)-Z90>15),"Behind — progress lag",IF(AND(X90-TODAY()<=30,X90-TODAY()>=0,OR(Z90="",Z90<90)),"At risk — close to off track","On track")))))))) | IF(OR(F90="",AC90="Completed / Handover",AC90="Cancelled"),"",IF(O90="Not awarded",IF(U90<>"",U90-TODAY(),IF(X90="","",X90-TODAY())),IF(X90="","",X90-TODAY()))) | [14 empty] | IF(OR(F90="",AJ90=""),"",IF(COUNT(AI90:AI90)=0,"",AJ90-LOOKUP(2,1/(AI90:AI90<>""),AI90:AI90))) | IF(OR(F90="",AK90=""),"",IF(COUNT(AI90:AJ90)=0,"",AK90-LOOKUP(2,1/(AI90:AJ90<>""),AI90:AJ90))) | IF(OR(F90="",AL90=""),"",IF(COUNT(AI90:AK90)=0,"",AL90-LOOKUP(2,1/(AI90:AK90<>""),AI90:AK90))) | IF(OR(F90="",AM90=""),"",IF(COUNT(AI90:AL90)=0,"",AM90-LOOKUP(2,1/(AI90:AL90<>""),AI90:AL90))) | IF(OR(F90="",AN90=""),"",IF(COUNT(AI90:AM90)=0,"",AN90-LOOKUP(2,1/(AI90:AM90<>""),AI90:AM90))) | IF(OR(F90="",AO90=""),"",IF(COUNT(AI90:AN90)=0,"",AO90-LOOKUP(2,1/(AI90:AN90<>""),AI90:AN90))) | IF(OR(F90="",AP90=""),"",IF(COUNT(AI90:AO90)=0,"",AP90-LOOKUP(2,1/(AI90:AO90<>""),AI90:AO90))) | IF(OR(F90="",AQ90=""),"",IF(COUNT(AI90:AP90)=0,"",AQ90-LOOKUP(2,1/(AI90:AP90<>""),AI90:AP90))) | IF(OR(F90="",AR90=""),"",IF(COUNT(AI90:AQ90)=0,"",AR90-LOOKUP(2,1/(AI90:AQ90<>""),AI90:AQ90))) | IF(OR(F90="",AS90=""),"",IF(COUNT(AI90:AR90)=0,"",AS90-LOOKUP(2,1/(AI90:AR90<>""),AI90:AR90))) | IF(OR(F90="",AT90=""),"",IF(COUNT(AI90:AS90)=0,"",AT90-LOOKUP(2,1/(AI90:AS90<>""),AI90:AS90))) | IF(OR(F90="",AU90=""),"",IF(COUNT(AI90:AT90)=0,"",AU90-LOOKUP(2,1/(AI90:AT90<>""),AI90:AT90))) | IF(OR(F90="",AV90=""),"",IF(COUNT(AI90:AU90)=0,"",AV90-LOOKUP(2,1/(AI90:AU90<>""),AI90:AU90))) | IF(J90="","All_Provinces",IFERROR(VLOOKUP(J90,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K90="","All_Districts",IFERROR(VLOOKUP(K90,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F91="","",ROW()-3) | [18 empty] | IF(AQ91="","",AQ91) |  |  |  | IF(W91<>"",W91,IF(OR(T91="",V91=""),"",EDATE(T91,V91))) |  |  |  |  | IF(F91="","",IF(COUNT(AI91:AV91)=0,IF(AA91="","Not started",AA91),SUBSTITUTE(LOOKUP(2,1/(AI91:AV91<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F91="",COUNT(AI91:AV91)=0),"",TODAY()-LOOKUP(2,1/(AI91:AV91<>""),AI91:AV91)) | IF(OR(F91="",COUNT(AI91:AV91)<2),"",LOOKUP(2,1/(AI91:AV91<>""),AI91:AV91)-MIN(AI91:AV91)) | IF(OR(AD91="",AC91="Not started",AC91=""),"",IFERROR(AD91-IF(VLOOKUP(AC91,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC91,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F91="","",IF(OR(AA91="Cancelled",AC91="Cancelled"),"Cancelled",IF(OR(AC91="Completed / Handover",Y91<>"",Z91>=100),"Completed — on track",IF(O91="Not awarded",IF(U91="",IF(X91="","No planned date",IF(TODAY()>X91,"Behind — past planned date",IF(X91-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U91,"Behind — award date passed",IF(U91-TODAY()<=30,"At risk — close to off track","On track"))),IF(X91="","No planned date",IF(AND(TODAY()>X91,OR(Z91="",Z91<100)),"Behind — past end date",IF(AND(T91<>"",X91<>"",Z91<>"",(Z91<100),((TODAY()-T91)/MAX(X91-T91,1)*100)-Z91>15),"Behind — progress lag",IF(AND(X91-TODAY()<=30,X91-TODAY()>=0,OR(Z91="",Z91<90)),"At risk — close to off track","On track")))))))) | IF(OR(F91="",AC91="Completed / Handover",AC91="Cancelled"),"",IF(O91="Not awarded",IF(U91<>"",U91-TODAY(),IF(X91="","",X91-TODAY())),IF(X91="","",X91-TODAY()))) | [14 empty] | IF(OR(F91="",AJ91=""),"",IF(COUNT(AI91:AI91)=0,"",AJ91-LOOKUP(2,1/(AI91:AI91<>""),AI91:AI91))) | IF(OR(F91="",AK91=""),"",IF(COUNT(AI91:AJ91)=0,"",AK91-LOOKUP(2,1/(AI91:AJ91<>""),AI91:AJ91))) | IF(OR(F91="",AL91=""),"",IF(COUNT(AI91:AK91)=0,"",AL91-LOOKUP(2,1/(AI91:AK91<>""),AI91:AK91))) | IF(OR(F91="",AM91=""),"",IF(COUNT(AI91:AL91)=0,"",AM91-LOOKUP(2,1/(AI91:AL91<>""),AI91:AL91))) | IF(OR(F91="",AN91=""),"",IF(COUNT(AI91:AM91)=0,"",AN91-LOOKUP(2,1/(AI91:AM91<>""),AI91:AM91))) | IF(OR(F91="",AO91=""),"",IF(COUNT(AI91:AN91)=0,"",AO91-LOOKUP(2,1/(AI91:AN91<>""),AI91:AN91))) | IF(OR(F91="",AP91=""),"",IF(COUNT(AI91:AO91)=0,"",AP91-LOOKUP(2,1/(AI91:AO91<>""),AI91:AO91))) | IF(OR(F91="",AQ91=""),"",IF(COUNT(AI91:AP91)=0,"",AQ91-LOOKUP(2,1/(AI91:AP91<>""),AI91:AP91))) | IF(OR(F91="",AR91=""),"",IF(COUNT(AI91:AQ91)=0,"",AR91-LOOKUP(2,1/(AI91:AQ91<>""),AI91:AQ91))) | IF(OR(F91="",AS91=""),"",IF(COUNT(AI91:AR91)=0,"",AS91-LOOKUP(2,1/(AI91:AR91<>""),AI91:AR91))) | IF(OR(F91="",AT91=""),"",IF(COUNT(AI91:AS91)=0,"",AT91-LOOKUP(2,1/(AI91:AS91<>""),AI91:AS91))) | IF(OR(F91="",AU91=""),"",IF(COUNT(AI91:AT91)=0,"",AU91-LOOKUP(2,1/(AI91:AT91<>""),AI91:AT91))) | IF(OR(F91="",AV91=""),"",IF(COUNT(AI91:AU91)=0,"",AV91-LOOKUP(2,1/(AI91:AU91<>""),AI91:AU91))) | IF(J91="","All_Provinces",IFERROR(VLOOKUP(J91,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K91="","All_Districts",IFERROR(VLOOKUP(K91,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F92="","",ROW()-3) | [18 empty] | IF(AQ92="","",AQ92) |  |  |  | IF(W92<>"",W92,IF(OR(T92="",V92=""),"",EDATE(T92,V92))) |  |  |  |  | IF(F92="","",IF(COUNT(AI92:AV92)=0,IF(AA92="","Not started",AA92),SUBSTITUTE(LOOKUP(2,1/(AI92:AV92<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F92="",COUNT(AI92:AV92)=0),"",TODAY()-LOOKUP(2,1/(AI92:AV92<>""),AI92:AV92)) | IF(OR(F92="",COUNT(AI92:AV92)<2),"",LOOKUP(2,1/(AI92:AV92<>""),AI92:AV92)-MIN(AI92:AV92)) | IF(OR(AD92="",AC92="Not started",AC92=""),"",IFERROR(AD92-IF(VLOOKUP(AC92,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC92,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F92="","",IF(OR(AA92="Cancelled",AC92="Cancelled"),"Cancelled",IF(OR(AC92="Completed / Handover",Y92<>"",Z92>=100),"Completed — on track",IF(O92="Not awarded",IF(U92="",IF(X92="","No planned date",IF(TODAY()>X92,"Behind — past planned date",IF(X92-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U92,"Behind — award date passed",IF(U92-TODAY()<=30,"At risk — close to off track","On track"))),IF(X92="","No planned date",IF(AND(TODAY()>X92,OR(Z92="",Z92<100)),"Behind — past end date",IF(AND(T92<>"",X92<>"",Z92<>"",(Z92<100),((TODAY()-T92)/MAX(X92-T92,1)*100)-Z92>15),"Behind — progress lag",IF(AND(X92-TODAY()<=30,X92-TODAY()>=0,OR(Z92="",Z92<90)),"At risk — close to off track","On track")))))))) | IF(OR(F92="",AC92="Completed / Handover",AC92="Cancelled"),"",IF(O92="Not awarded",IF(U92<>"",U92-TODAY(),IF(X92="","",X92-TODAY())),IF(X92="","",X92-TODAY()))) | [14 empty] | IF(OR(F92="",AJ92=""),"",IF(COUNT(AI92:AI92)=0,"",AJ92-LOOKUP(2,1/(AI92:AI92<>""),AI92:AI92))) | IF(OR(F92="",AK92=""),"",IF(COUNT(AI92:AJ92)=0,"",AK92-LOOKUP(2,1/(AI92:AJ92<>""),AI92:AJ92))) | IF(OR(F92="",AL92=""),"",IF(COUNT(AI92:AK92)=0,"",AL92-LOOKUP(2,1/(AI92:AK92<>""),AI92:AK92))) | IF(OR(F92="",AM92=""),"",IF(COUNT(AI92:AL92)=0,"",AM92-LOOKUP(2,1/(AI92:AL92<>""),AI92:AL92))) | IF(OR(F92="",AN92=""),"",IF(COUNT(AI92:AM92)=0,"",AN92-LOOKUP(2,1/(AI92:AM92<>""),AI92:AM92))) | IF(OR(F92="",AO92=""),"",IF(COUNT(AI92:AN92)=0,"",AO92-LOOKUP(2,1/(AI92:AN92<>""),AI92:AN92))) | IF(OR(F92="",AP92=""),"",IF(COUNT(AI92:AO92)=0,"",AP92-LOOKUP(2,1/(AI92:AO92<>""),AI92:AO92))) | IF(OR(F92="",AQ92=""),"",IF(COUNT(AI92:AP92)=0,"",AQ92-LOOKUP(2,1/(AI92:AP92<>""),AI92:AP92))) | IF(OR(F92="",AR92=""),"",IF(COUNT(AI92:AQ92)=0,"",AR92-LOOKUP(2,1/(AI92:AQ92<>""),AI92:AQ92))) | IF(OR(F92="",AS92=""),"",IF(COUNT(AI92:AR92)=0,"",AS92-LOOKUP(2,1/(AI92:AR92<>""),AI92:AR92))) | IF(OR(F92="",AT92=""),"",IF(COUNT(AI92:AS92)=0,"",AT92-LOOKUP(2,1/(AI92:AS92<>""),AI92:AS92))) | IF(OR(F92="",AU92=""),"",IF(COUNT(AI92:AT92)=0,"",AU92-LOOKUP(2,1/(AI92:AT92<>""),AI92:AT92))) | IF(OR(F92="",AV92=""),"",IF(COUNT(AI92:AU92)=0,"",AV92-LOOKUP(2,1/(AI92:AU92<>""),AI92:AU92))) | IF(J92="","All_Provinces",IFERROR(VLOOKUP(J92,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K92="","All_Districts",IFERROR(VLOOKUP(K92,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F93="","",ROW()-3) | [18 empty] | IF(AQ93="","",AQ93) |  |  |  | IF(W93<>"",W93,IF(OR(T93="",V93=""),"",EDATE(T93,V93))) |  |  |  |  | IF(F93="","",IF(COUNT(AI93:AV93)=0,IF(AA93="","Not started",AA93),SUBSTITUTE(LOOKUP(2,1/(AI93:AV93<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F93="",COUNT(AI93:AV93)=0),"",TODAY()-LOOKUP(2,1/(AI93:AV93<>""),AI93:AV93)) | IF(OR(F93="",COUNT(AI93:AV93)<2),"",LOOKUP(2,1/(AI93:AV93<>""),AI93:AV93)-MIN(AI93:AV93)) | IF(OR(AD93="",AC93="Not started",AC93=""),"",IFERROR(AD93-IF(VLOOKUP(AC93,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC93,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F93="","",IF(OR(AA93="Cancelled",AC93="Cancelled"),"Cancelled",IF(OR(AC93="Completed / Handover",Y93<>"",Z93>=100),"Completed — on track",IF(O93="Not awarded",IF(U93="",IF(X93="","No planned date",IF(TODAY()>X93,"Behind — past planned date",IF(X93-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U93,"Behind — award date passed",IF(U93-TODAY()<=30,"At risk — close to off track","On track"))),IF(X93="","No planned date",IF(AND(TODAY()>X93,OR(Z93="",Z93<100)),"Behind — past end date",IF(AND(T93<>"",X93<>"",Z93<>"",(Z93<100),((TODAY()-T93)/MAX(X93-T93,1)*100)-Z93>15),"Behind — progress lag",IF(AND(X93-TODAY()<=30,X93-TODAY()>=0,OR(Z93="",Z93<90)),"At risk — close to off track","On track")))))))) | IF(OR(F93="",AC93="Completed / Handover",AC93="Cancelled"),"",IF(O93="Not awarded",IF(U93<>"",U93-TODAY(),IF(X93="","",X93-TODAY())),IF(X93="","",X93-TODAY()))) | [14 empty] | IF(OR(F93="",AJ93=""),"",IF(COUNT(AI93:AI93)=0,"",AJ93-LOOKUP(2,1/(AI93:AI93<>""),AI93:AI93))) | IF(OR(F93="",AK93=""),"",IF(COUNT(AI93:AJ93)=0,"",AK93-LOOKUP(2,1/(AI93:AJ93<>""),AI93:AJ93))) | IF(OR(F93="",AL93=""),"",IF(COUNT(AI93:AK93)=0,"",AL93-LOOKUP(2,1/(AI93:AK93<>""),AI93:AK93))) | IF(OR(F93="",AM93=""),"",IF(COUNT(AI93:AL93)=0,"",AM93-LOOKUP(2,1/(AI93:AL93<>""),AI93:AL93))) | IF(OR(F93="",AN93=""),"",IF(COUNT(AI93:AM93)=0,"",AN93-LOOKUP(2,1/(AI93:AM93<>""),AI93:AM93))) | IF(OR(F93="",AO93=""),"",IF(COUNT(AI93:AN93)=0,"",AO93-LOOKUP(2,1/(AI93:AN93<>""),AI93:AN93))) | IF(OR(F93="",AP93=""),"",IF(COUNT(AI93:AO93)=0,"",AP93-LOOKUP(2,1/(AI93:AO93<>""),AI93:AO93))) | IF(OR(F93="",AQ93=""),"",IF(COUNT(AI93:AP93)=0,"",AQ93-LOOKUP(2,1/(AI93:AP93<>""),AI93:AP93))) | IF(OR(F93="",AR93=""),"",IF(COUNT(AI93:AQ93)=0,"",AR93-LOOKUP(2,1/(AI93:AQ93<>""),AI93:AQ93))) | IF(OR(F93="",AS93=""),"",IF(COUNT(AI93:AR93)=0,"",AS93-LOOKUP(2,1/(AI93:AR93<>""),AI93:AR93))) | IF(OR(F93="",AT93=""),"",IF(COUNT(AI93:AS93)=0,"",AT93-LOOKUP(2,1/(AI93:AS93<>""),AI93:AS93))) | IF(OR(F93="",AU93=""),"",IF(COUNT(AI93:AT93)=0,"",AU93-LOOKUP(2,1/(AI93:AT93<>""),AI93:AT93))) | IF(OR(F93="",AV93=""),"",IF(COUNT(AI93:AU93)=0,"",AV93-LOOKUP(2,1/(AI93:AU93<>""),AI93:AU93))) | IF(J93="","All_Provinces",IFERROR(VLOOKUP(J93,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K93="","All_Districts",IFERROR(VLOOKUP(K93,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F94="","",ROW()-3) | [18 empty] | IF(AQ94="","",AQ94) |  |  |  | IF(W94<>"",W94,IF(OR(T94="",V94=""),"",EDATE(T94,V94))) |  |  |  |  | IF(F94="","",IF(COUNT(AI94:AV94)=0,IF(AA94="","Not started",AA94),SUBSTITUTE(LOOKUP(2,1/(AI94:AV94<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F94="",COUNT(AI94:AV94)=0),"",TODAY()-LOOKUP(2,1/(AI94:AV94<>""),AI94:AV94)) | IF(OR(F94="",COUNT(AI94:AV94)<2),"",LOOKUP(2,1/(AI94:AV94<>""),AI94:AV94)-MIN(AI94:AV94)) | IF(OR(AD94="",AC94="Not started",AC94=""),"",IFERROR(AD94-IF(VLOOKUP(AC94,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC94,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F94="","",IF(OR(AA94="Cancelled",AC94="Cancelled"),"Cancelled",IF(OR(AC94="Completed / Handover",Y94<>"",Z94>=100),"Completed — on track",IF(O94="Not awarded",IF(U94="",IF(X94="","No planned date",IF(TODAY()>X94,"Behind — past planned date",IF(X94-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U94,"Behind — award date passed",IF(U94-TODAY()<=30,"At risk — close to off track","On track"))),IF(X94="","No planned date",IF(AND(TODAY()>X94,OR(Z94="",Z94<100)),"Behind — past end date",IF(AND(T94<>"",X94<>"",Z94<>"",(Z94<100),((TODAY()-T94)/MAX(X94-T94,1)*100)-Z94>15),"Behind — progress lag",IF(AND(X94-TODAY()<=30,X94-TODAY()>=0,OR(Z94="",Z94<90)),"At risk — close to off track","On track")))))))) | IF(OR(F94="",AC94="Completed / Handover",AC94="Cancelled"),"",IF(O94="Not awarded",IF(U94<>"",U94-TODAY(),IF(X94="","",X94-TODAY())),IF(X94="","",X94-TODAY()))) | [14 empty] | IF(OR(F94="",AJ94=""),"",IF(COUNT(AI94:AI94)=0,"",AJ94-LOOKUP(2,1/(AI94:AI94<>""),AI94:AI94))) | IF(OR(F94="",AK94=""),"",IF(COUNT(AI94:AJ94)=0,"",AK94-LOOKUP(2,1/(AI94:AJ94<>""),AI94:AJ94))) | IF(OR(F94="",AL94=""),"",IF(COUNT(AI94:AK94)=0,"",AL94-LOOKUP(2,1/(AI94:AK94<>""),AI94:AK94))) | IF(OR(F94="",AM94=""),"",IF(COUNT(AI94:AL94)=0,"",AM94-LOOKUP(2,1/(AI94:AL94<>""),AI94:AL94))) | IF(OR(F94="",AN94=""),"",IF(COUNT(AI94:AM94)=0,"",AN94-LOOKUP(2,1/(AI94:AM94<>""),AI94:AM94))) | IF(OR(F94="",AO94=""),"",IF(COUNT(AI94:AN94)=0,"",AO94-LOOKUP(2,1/(AI94:AN94<>""),AI94:AN94))) | IF(OR(F94="",AP94=""),"",IF(COUNT(AI94:AO94)=0,"",AP94-LOOKUP(2,1/(AI94:AO94<>""),AI94:AO94))) | IF(OR(F94="",AQ94=""),"",IF(COUNT(AI94:AP94)=0,"",AQ94-LOOKUP(2,1/(AI94:AP94<>""),AI94:AP94))) | IF(OR(F94="",AR94=""),"",IF(COUNT(AI94:AQ94)=0,"",AR94-LOOKUP(2,1/(AI94:AQ94<>""),AI94:AQ94))) | IF(OR(F94="",AS94=""),"",IF(COUNT(AI94:AR94)=0,"",AS94-LOOKUP(2,1/(AI94:AR94<>""),AI94:AR94))) | IF(OR(F94="",AT94=""),"",IF(COUNT(AI94:AS94)=0,"",AT94-LOOKUP(2,1/(AI94:AS94<>""),AI94:AS94))) | IF(OR(F94="",AU94=""),"",IF(COUNT(AI94:AT94)=0,"",AU94-LOOKUP(2,1/(AI94:AT94<>""),AI94:AT94))) | IF(OR(F94="",AV94=""),"",IF(COUNT(AI94:AU94)=0,"",AV94-LOOKUP(2,1/(AI94:AU94<>""),AI94:AU94))) | IF(J94="","All_Provinces",IFERROR(VLOOKUP(J94,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K94="","All_Districts",IFERROR(VLOOKUP(K94,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F95="","",ROW()-3) | [18 empty] | IF(AQ95="","",AQ95) |  |  |  | IF(W95<>"",W95,IF(OR(T95="",V95=""),"",EDATE(T95,V95))) |  |  |  |  | IF(F95="","",IF(COUNT(AI95:AV95)=0,IF(AA95="","Not started",AA95),SUBSTITUTE(LOOKUP(2,1/(AI95:AV95<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F95="",COUNT(AI95:AV95)=0),"",TODAY()-LOOKUP(2,1/(AI95:AV95<>""),AI95:AV95)) | IF(OR(F95="",COUNT(AI95:AV95)<2),"",LOOKUP(2,1/(AI95:AV95<>""),AI95:AV95)-MIN(AI95:AV95)) | IF(OR(AD95="",AC95="Not started",AC95=""),"",IFERROR(AD95-IF(VLOOKUP(AC95,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC95,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F95="","",IF(OR(AA95="Cancelled",AC95="Cancelled"),"Cancelled",IF(OR(AC95="Completed / Handover",Y95<>"",Z95>=100),"Completed — on track",IF(O95="Not awarded",IF(U95="",IF(X95="","No planned date",IF(TODAY()>X95,"Behind — past planned date",IF(X95-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U95,"Behind — award date passed",IF(U95-TODAY()<=30,"At risk — close to off track","On track"))),IF(X95="","No planned date",IF(AND(TODAY()>X95,OR(Z95="",Z95<100)),"Behind — past end date",IF(AND(T95<>"",X95<>"",Z95<>"",(Z95<100),((TODAY()-T95)/MAX(X95-T95,1)*100)-Z95>15),"Behind — progress lag",IF(AND(X95-TODAY()<=30,X95-TODAY()>=0,OR(Z95="",Z95<90)),"At risk — close to off track","On track")))))))) | IF(OR(F95="",AC95="Completed / Handover",AC95="Cancelled"),"",IF(O95="Not awarded",IF(U95<>"",U95-TODAY(),IF(X95="","",X95-TODAY())),IF(X95="","",X95-TODAY()))) | [14 empty] | IF(OR(F95="",AJ95=""),"",IF(COUNT(AI95:AI95)=0,"",AJ95-LOOKUP(2,1/(AI95:AI95<>""),AI95:AI95))) | IF(OR(F95="",AK95=""),"",IF(COUNT(AI95:AJ95)=0,"",AK95-LOOKUP(2,1/(AI95:AJ95<>""),AI95:AJ95))) | IF(OR(F95="",AL95=""),"",IF(COUNT(AI95:AK95)=0,"",AL95-LOOKUP(2,1/(AI95:AK95<>""),AI95:AK95))) | IF(OR(F95="",AM95=""),"",IF(COUNT(AI95:AL95)=0,"",AM95-LOOKUP(2,1/(AI95:AL95<>""),AI95:AL95))) | IF(OR(F95="",AN95=""),"",IF(COUNT(AI95:AM95)=0,"",AN95-LOOKUP(2,1/(AI95:AM95<>""),AI95:AM95))) | IF(OR(F95="",AO95=""),"",IF(COUNT(AI95:AN95)=0,"",AO95-LOOKUP(2,1/(AI95:AN95<>""),AI95:AN95))) | IF(OR(F95="",AP95=""),"",IF(COUNT(AI95:AO95)=0,"",AP95-LOOKUP(2,1/(AI95:AO95<>""),AI95:AO95))) | IF(OR(F95="",AQ95=""),"",IF(COUNT(AI95:AP95)=0,"",AQ95-LOOKUP(2,1/(AI95:AP95<>""),AI95:AP95))) | IF(OR(F95="",AR95=""),"",IF(COUNT(AI95:AQ95)=0,"",AR95-LOOKUP(2,1/(AI95:AQ95<>""),AI95:AQ95))) | IF(OR(F95="",AS95=""),"",IF(COUNT(AI95:AR95)=0,"",AS95-LOOKUP(2,1/(AI95:AR95<>""),AI95:AR95))) | IF(OR(F95="",AT95=""),"",IF(COUNT(AI95:AS95)=0,"",AT95-LOOKUP(2,1/(AI95:AS95<>""),AI95:AS95))) | IF(OR(F95="",AU95=""),"",IF(COUNT(AI95:AT95)=0,"",AU95-LOOKUP(2,1/(AI95:AT95<>""),AI95:AT95))) | IF(OR(F95="",AV95=""),"",IF(COUNT(AI95:AU95)=0,"",AV95-LOOKUP(2,1/(AI95:AU95<>""),AI95:AU95))) | IF(J95="","All_Provinces",IFERROR(VLOOKUP(J95,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K95="","All_Districts",IFERROR(VLOOKUP(K95,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F96="","",ROW()-3) | [18 empty] | IF(AQ96="","",AQ96) |  |  |  | IF(W96<>"",W96,IF(OR(T96="",V96=""),"",EDATE(T96,V96))) |  |  |  |  | IF(F96="","",IF(COUNT(AI96:AV96)=0,IF(AA96="","Not started",AA96),SUBSTITUTE(LOOKUP(2,1/(AI96:AV96<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F96="",COUNT(AI96:AV96)=0),"",TODAY()-LOOKUP(2,1/(AI96:AV96<>""),AI96:AV96)) | IF(OR(F96="",COUNT(AI96:AV96)<2),"",LOOKUP(2,1/(AI96:AV96<>""),AI96:AV96)-MIN(AI96:AV96)) | IF(OR(AD96="",AC96="Not started",AC96=""),"",IFERROR(AD96-IF(VLOOKUP(AC96,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC96,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F96="","",IF(OR(AA96="Cancelled",AC96="Cancelled"),"Cancelled",IF(OR(AC96="Completed / Handover",Y96<>"",Z96>=100),"Completed — on track",IF(O96="Not awarded",IF(U96="",IF(X96="","No planned date",IF(TODAY()>X96,"Behind — past planned date",IF(X96-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U96,"Behind — award date passed",IF(U96-TODAY()<=30,"At risk — close to off track","On track"))),IF(X96="","No planned date",IF(AND(TODAY()>X96,OR(Z96="",Z96<100)),"Behind — past end date",IF(AND(T96<>"",X96<>"",Z96<>"",(Z96<100),((TODAY()-T96)/MAX(X96-T96,1)*100)-Z96>15),"Behind — progress lag",IF(AND(X96-TODAY()<=30,X96-TODAY()>=0,OR(Z96="",Z96<90)),"At risk — close to off track","On track")))))))) | IF(OR(F96="",AC96="Completed / Handover",AC96="Cancelled"),"",IF(O96="Not awarded",IF(U96<>"",U96-TODAY(),IF(X96="","",X96-TODAY())),IF(X96="","",X96-TODAY()))) | [14 empty] | IF(OR(F96="",AJ96=""),"",IF(COUNT(AI96:AI96)=0,"",AJ96-LOOKUP(2,1/(AI96:AI96<>""),AI96:AI96))) | IF(OR(F96="",AK96=""),"",IF(COUNT(AI96:AJ96)=0,"",AK96-LOOKUP(2,1/(AI96:AJ96<>""),AI96:AJ96))) | IF(OR(F96="",AL96=""),"",IF(COUNT(AI96:AK96)=0,"",AL96-LOOKUP(2,1/(AI96:AK96<>""),AI96:AK96))) | IF(OR(F96="",AM96=""),"",IF(COUNT(AI96:AL96)=0,"",AM96-LOOKUP(2,1/(AI96:AL96<>""),AI96:AL96))) | IF(OR(F96="",AN96=""),"",IF(COUNT(AI96:AM96)=0,"",AN96-LOOKUP(2,1/(AI96:AM96<>""),AI96:AM96))) | IF(OR(F96="",AO96=""),"",IF(COUNT(AI96:AN96)=0,"",AO96-LOOKUP(2,1/(AI96:AN96<>""),AI96:AN96))) | IF(OR(F96="",AP96=""),"",IF(COUNT(AI96:AO96)=0,"",AP96-LOOKUP(2,1/(AI96:AO96<>""),AI96:AO96))) | IF(OR(F96="",AQ96=""),"",IF(COUNT(AI96:AP96)=0,"",AQ96-LOOKUP(2,1/(AI96:AP96<>""),AI96:AP96))) | IF(OR(F96="",AR96=""),"",IF(COUNT(AI96:AQ96)=0,"",AR96-LOOKUP(2,1/(AI96:AQ96<>""),AI96:AQ96))) | IF(OR(F96="",AS96=""),"",IF(COUNT(AI96:AR96)=0,"",AS96-LOOKUP(2,1/(AI96:AR96<>""),AI96:AR96))) | IF(OR(F96="",AT96=""),"",IF(COUNT(AI96:AS96)=0,"",AT96-LOOKUP(2,1/(AI96:AS96<>""),AI96:AS96))) | IF(OR(F96="",AU96=""),"",IF(COUNT(AI96:AT96)=0,"",AU96-LOOKUP(2,1/(AI96:AT96<>""),AI96:AT96))) | IF(OR(F96="",AV96=""),"",IF(COUNT(AI96:AU96)=0,"",AV96-LOOKUP(2,1/(AI96:AU96<>""),AI96:AU96))) | IF(J96="","All_Provinces",IFERROR(VLOOKUP(J96,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K96="","All_Districts",IFERROR(VLOOKUP(K96,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F97="","",ROW()-3) | [18 empty] | IF(AQ97="","",AQ97) |  |  |  | IF(W97<>"",W97,IF(OR(T97="",V97=""),"",EDATE(T97,V97))) |  |  |  |  | IF(F97="","",IF(COUNT(AI97:AV97)=0,IF(AA97="","Not started",AA97),SUBSTITUTE(LOOKUP(2,1/(AI97:AV97<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F97="",COUNT(AI97:AV97)=0),"",TODAY()-LOOKUP(2,1/(AI97:AV97<>""),AI97:AV97)) | IF(OR(F97="",COUNT(AI97:AV97)<2),"",LOOKUP(2,1/(AI97:AV97<>""),AI97:AV97)-MIN(AI97:AV97)) | IF(OR(AD97="",AC97="Not started",AC97=""),"",IFERROR(AD97-IF(VLOOKUP(AC97,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC97,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F97="","",IF(OR(AA97="Cancelled",AC97="Cancelled"),"Cancelled",IF(OR(AC97="Completed / Handover",Y97<>"",Z97>=100),"Completed — on track",IF(O97="Not awarded",IF(U97="",IF(X97="","No planned date",IF(TODAY()>X97,"Behind — past planned date",IF(X97-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U97,"Behind — award date passed",IF(U97-TODAY()<=30,"At risk — close to off track","On track"))),IF(X97="","No planned date",IF(AND(TODAY()>X97,OR(Z97="",Z97<100)),"Behind — past end date",IF(AND(T97<>"",X97<>"",Z97<>"",(Z97<100),((TODAY()-T97)/MAX(X97-T97,1)*100)-Z97>15),"Behind — progress lag",IF(AND(X97-TODAY()<=30,X97-TODAY()>=0,OR(Z97="",Z97<90)),"At risk — close to off track","On track")))))))) | IF(OR(F97="",AC97="Completed / Handover",AC97="Cancelled"),"",IF(O97="Not awarded",IF(U97<>"",U97-TODAY(),IF(X97="","",X97-TODAY())),IF(X97="","",X97-TODAY()))) | [14 empty] | IF(OR(F97="",AJ97=""),"",IF(COUNT(AI97:AI97)=0,"",AJ97-LOOKUP(2,1/(AI97:AI97<>""),AI97:AI97))) | IF(OR(F97="",AK97=""),"",IF(COUNT(AI97:AJ97)=0,"",AK97-LOOKUP(2,1/(AI97:AJ97<>""),AI97:AJ97))) | IF(OR(F97="",AL97=""),"",IF(COUNT(AI97:AK97)=0,"",AL97-LOOKUP(2,1/(AI97:AK97<>""),AI97:AK97))) | IF(OR(F97="",AM97=""),"",IF(COUNT(AI97:AL97)=0,"",AM97-LOOKUP(2,1/(AI97:AL97<>""),AI97:AL97))) | IF(OR(F97="",AN97=""),"",IF(COUNT(AI97:AM97)=0,"",AN97-LOOKUP(2,1/(AI97:AM97<>""),AI97:AM97))) | IF(OR(F97="",AO97=""),"",IF(COUNT(AI97:AN97)=0,"",AO97-LOOKUP(2,1/(AI97:AN97<>""),AI97:AN97))) | IF(OR(F97="",AP97=""),"",IF(COUNT(AI97:AO97)=0,"",AP97-LOOKUP(2,1/(AI97:AO97<>""),AI97:AO97))) | IF(OR(F97="",AQ97=""),"",IF(COUNT(AI97:AP97)=0,"",AQ97-LOOKUP(2,1/(AI97:AP97<>""),AI97:AP97))) | IF(OR(F97="",AR97=""),"",IF(COUNT(AI97:AQ97)=0,"",AR97-LOOKUP(2,1/(AI97:AQ97<>""),AI97:AQ97))) | IF(OR(F97="",AS97=""),"",IF(COUNT(AI97:AR97)=0,"",AS97-LOOKUP(2,1/(AI97:AR97<>""),AI97:AR97))) | IF(OR(F97="",AT97=""),"",IF(COUNT(AI97:AS97)=0,"",AT97-LOOKUP(2,1/(AI97:AS97<>""),AI97:AS97))) | IF(OR(F97="",AU97=""),"",IF(COUNT(AI97:AT97)=0,"",AU97-LOOKUP(2,1/(AI97:AT97<>""),AI97:AT97))) | IF(OR(F97="",AV97=""),"",IF(COUNT(AI97:AU97)=0,"",AV97-LOOKUP(2,1/(AI97:AU97<>""),AI97:AU97))) | IF(J97="","All_Provinces",IFERROR(VLOOKUP(J97,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K97="","All_Districts",IFERROR(VLOOKUP(K97,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F98="","",ROW()-3) | [18 empty] | IF(AQ98="","",AQ98) |  |  |  | IF(W98<>"",W98,IF(OR(T98="",V98=""),"",EDATE(T98,V98))) |  |  |  |  | IF(F98="","",IF(COUNT(AI98:AV98)=0,IF(AA98="","Not started",AA98),SUBSTITUTE(LOOKUP(2,1/(AI98:AV98<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F98="",COUNT(AI98:AV98)=0),"",TODAY()-LOOKUP(2,1/(AI98:AV98<>""),AI98:AV98)) | IF(OR(F98="",COUNT(AI98:AV98)<2),"",LOOKUP(2,1/(AI98:AV98<>""),AI98:AV98)-MIN(AI98:AV98)) | IF(OR(AD98="",AC98="Not started",AC98=""),"",IFERROR(AD98-IF(VLOOKUP(AC98,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC98,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F98="","",IF(OR(AA98="Cancelled",AC98="Cancelled"),"Cancelled",IF(OR(AC98="Completed / Handover",Y98<>"",Z98>=100),"Completed — on track",IF(O98="Not awarded",IF(U98="",IF(X98="","No planned date",IF(TODAY()>X98,"Behind — past planned date",IF(X98-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U98,"Behind — award date passed",IF(U98-TODAY()<=30,"At risk — close to off track","On track"))),IF(X98="","No planned date",IF(AND(TODAY()>X98,OR(Z98="",Z98<100)),"Behind — past end date",IF(AND(T98<>"",X98<>"",Z98<>"",(Z98<100),((TODAY()-T98)/MAX(X98-T98,1)*100)-Z98>15),"Behind — progress lag",IF(AND(X98-TODAY()<=30,X98-TODAY()>=0,OR(Z98="",Z98<90)),"At risk — close to off track","On track")))))))) | IF(OR(F98="",AC98="Completed / Handover",AC98="Cancelled"),"",IF(O98="Not awarded",IF(U98<>"",U98-TODAY(),IF(X98="","",X98-TODAY())),IF(X98="","",X98-TODAY()))) | [14 empty] | IF(OR(F98="",AJ98=""),"",IF(COUNT(AI98:AI98)=0,"",AJ98-LOOKUP(2,1/(AI98:AI98<>""),AI98:AI98))) | IF(OR(F98="",AK98=""),"",IF(COUNT(AI98:AJ98)=0,"",AK98-LOOKUP(2,1/(AI98:AJ98<>""),AI98:AJ98))) | IF(OR(F98="",AL98=""),"",IF(COUNT(AI98:AK98)=0,"",AL98-LOOKUP(2,1/(AI98:AK98<>""),AI98:AK98))) | IF(OR(F98="",AM98=""),"",IF(COUNT(AI98:AL98)=0,"",AM98-LOOKUP(2,1/(AI98:AL98<>""),AI98:AL98))) | IF(OR(F98="",AN98=""),"",IF(COUNT(AI98:AM98)=0,"",AN98-LOOKUP(2,1/(AI98:AM98<>""),AI98:AM98))) | IF(OR(F98="",AO98=""),"",IF(COUNT(AI98:AN98)=0,"",AO98-LOOKUP(2,1/(AI98:AN98<>""),AI98:AN98))) | IF(OR(F98="",AP98=""),"",IF(COUNT(AI98:AO98)=0,"",AP98-LOOKUP(2,1/(AI98:AO98<>""),AI98:AO98))) | IF(OR(F98="",AQ98=""),"",IF(COUNT(AI98:AP98)=0,"",AQ98-LOOKUP(2,1/(AI98:AP98<>""),AI98:AP98))) | IF(OR(F98="",AR98=""),"",IF(COUNT(AI98:AQ98)=0,"",AR98-LOOKUP(2,1/(AI98:AQ98<>""),AI98:AQ98))) | IF(OR(F98="",AS98=""),"",IF(COUNT(AI98:AR98)=0,"",AS98-LOOKUP(2,1/(AI98:AR98<>""),AI98:AR98))) | IF(OR(F98="",AT98=""),"",IF(COUNT(AI98:AS98)=0,"",AT98-LOOKUP(2,1/(AI98:AS98<>""),AI98:AS98))) | IF(OR(F98="",AU98=""),"",IF(COUNT(AI98:AT98)=0,"",AU98-LOOKUP(2,1/(AI98:AT98<>""),AI98:AT98))) | IF(OR(F98="",AV98=""),"",IF(COUNT(AI98:AU98)=0,"",AV98-LOOKUP(2,1/(AI98:AU98<>""),AI98:AU98))) | IF(J98="","All_Provinces",IFERROR(VLOOKUP(J98,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K98="","All_Districts",IFERROR(VLOOKUP(K98,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F99="","",ROW()-3) | [18 empty] | IF(AQ99="","",AQ99) |  |  |  | IF(W99<>"",W99,IF(OR(T99="",V99=""),"",EDATE(T99,V99))) |  |  |  |  | IF(F99="","",IF(COUNT(AI99:AV99)=0,IF(AA99="","Not started",AA99),SUBSTITUTE(LOOKUP(2,1/(AI99:AV99<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F99="",COUNT(AI99:AV99)=0),"",TODAY()-LOOKUP(2,1/(AI99:AV99<>""),AI99:AV99)) | IF(OR(F99="",COUNT(AI99:AV99)<2),"",LOOKUP(2,1/(AI99:AV99<>""),AI99:AV99)-MIN(AI99:AV99)) | IF(OR(AD99="",AC99="Not started",AC99=""),"",IFERROR(AD99-IF(VLOOKUP(AC99,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC99,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F99="","",IF(OR(AA99="Cancelled",AC99="Cancelled"),"Cancelled",IF(OR(AC99="Completed / Handover",Y99<>"",Z99>=100),"Completed — on track",IF(O99="Not awarded",IF(U99="",IF(X99="","No planned date",IF(TODAY()>X99,"Behind — past planned date",IF(X99-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U99,"Behind — award date passed",IF(U99-TODAY()<=30,"At risk — close to off track","On track"))),IF(X99="","No planned date",IF(AND(TODAY()>X99,OR(Z99="",Z99<100)),"Behind — past end date",IF(AND(T99<>"",X99<>"",Z99<>"",(Z99<100),((TODAY()-T99)/MAX(X99-T99,1)*100)-Z99>15),"Behind — progress lag",IF(AND(X99-TODAY()<=30,X99-TODAY()>=0,OR(Z99="",Z99<90)),"At risk — close to off track","On track")))))))) | IF(OR(F99="",AC99="Completed / Handover",AC99="Cancelled"),"",IF(O99="Not awarded",IF(U99<>"",U99-TODAY(),IF(X99="","",X99-TODAY())),IF(X99="","",X99-TODAY()))) | [14 empty] | IF(OR(F99="",AJ99=""),"",IF(COUNT(AI99:AI99)=0,"",AJ99-LOOKUP(2,1/(AI99:AI99<>""),AI99:AI99))) | IF(OR(F99="",AK99=""),"",IF(COUNT(AI99:AJ99)=0,"",AK99-LOOKUP(2,1/(AI99:AJ99<>""),AI99:AJ99))) | IF(OR(F99="",AL99=""),"",IF(COUNT(AI99:AK99)=0,"",AL99-LOOKUP(2,1/(AI99:AK99<>""),AI99:AK99))) | IF(OR(F99="",AM99=""),"",IF(COUNT(AI99:AL99)=0,"",AM99-LOOKUP(2,1/(AI99:AL99<>""),AI99:AL99))) | IF(OR(F99="",AN99=""),"",IF(COUNT(AI99:AM99)=0,"",AN99-LOOKUP(2,1/(AI99:AM99<>""),AI99:AM99))) | IF(OR(F99="",AO99=""),"",IF(COUNT(AI99:AN99)=0,"",AO99-LOOKUP(2,1/(AI99:AN99<>""),AI99:AN99))) | IF(OR(F99="",AP99=""),"",IF(COUNT(AI99:AO99)=0,"",AP99-LOOKUP(2,1/(AI99:AO99<>""),AI99:AO99))) | IF(OR(F99="",AQ99=""),"",IF(COUNT(AI99:AP99)=0,"",AQ99-LOOKUP(2,1/(AI99:AP99<>""),AI99:AP99))) | IF(OR(F99="",AR99=""),"",IF(COUNT(AI99:AQ99)=0,"",AR99-LOOKUP(2,1/(AI99:AQ99<>""),AI99:AQ99))) | IF(OR(F99="",AS99=""),"",IF(COUNT(AI99:AR99)=0,"",AS99-LOOKUP(2,1/(AI99:AR99<>""),AI99:AR99))) | IF(OR(F99="",AT99=""),"",IF(COUNT(AI99:AS99)=0,"",AT99-LOOKUP(2,1/(AI99:AS99<>""),AI99:AS99))) | IF(OR(F99="",AU99=""),"",IF(COUNT(AI99:AT99)=0,"",AU99-LOOKUP(2,1/(AI99:AT99<>""),AI99:AT99))) | IF(OR(F99="",AV99=""),"",IF(COUNT(AI99:AU99)=0,"",AV99-LOOKUP(2,1/(AI99:AU99<>""),AI99:AU99))) | IF(J99="","All_Provinces",IFERROR(VLOOKUP(J99,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K99="","All_Districts",IFERROR(VLOOKUP(K99,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F100="","",ROW()-3) | [18 empty] | IF(AQ100="","",AQ100) |  |  |  | IF(W100<>"",W100,IF(OR(T100="",V100=""),"",EDATE(T100,V100))) |  |  |  |  | IF(F100="","",IF(COUNT(AI100:AV100)=0,IF(AA100="","Not started",AA100),SUBSTITUTE(LOOKUP(2,1/(AI100:AV100<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F100="",COUNT(AI100:AV100)=0),"",TODAY()-LOOKUP(2,1/(AI100:AV100<>""),AI100:AV100)) | IF(OR(F100="",COUNT(AI100:AV100)<2),"",LOOKUP(2,1/(AI100:AV100<>""),AI100:AV100)-MIN(AI100:AV100)) | IF(OR(AD100="",AC100="Not started",AC100=""),"",IFERROR(AD100-IF(VLOOKUP(AC100,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC100,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F100="","",IF(OR(AA100="Cancelled",AC100="Cancelled"),"Cancelled",IF(OR(AC100="Completed / Handover",Y100<>"",Z100>=100),"Completed — on track",IF(O100="Not awarded",IF(U100="",IF(X100="","No planned date",IF(TODAY()>X100,"Behind — past planned date",IF(X100-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U100,"Behind — award date passed",IF(U100-TODAY()<=30,"At risk — close to off track","On track"))),IF(X100="","No planned date",IF(AND(TODAY()>X100,OR(Z100="",Z100<100)),"Behind — past end date",IF(AND(T100<>"",X100<>"",Z100<>"",(Z100<100),((TODAY()-T100)/MAX(X100-T100,1)*100)-Z100>15),"Behind — progress lag",IF(AND(X100-TODAY()<=30,X100-TODAY()>=0,OR(Z100="",Z100<90)),"At risk — close to off track","On track")))))))) | IF(OR(F100="",AC100="Completed / Handover",AC100="Cancelled"),"",IF(O100="Not awarded",IF(U100<>"",U100-TODAY(),IF(X100="","",X100-TODAY())),IF(X100="","",X100-TODAY()))) | [14 empty] | IF(OR(F100="",AJ100=""),"",IF(COUNT(AI100:AI100)=0,"",AJ100-LOOKUP(2,1/(AI100:AI100<>""),AI100:AI100))) | IF(OR(F100="",AK100=""),"",IF(COUNT(AI100:AJ100)=0,"",AK100-LOOKUP(2,1/(AI100:AJ100<>""),AI100:AJ100))) | IF(OR(F100="",AL100=""),"",IF(COUNT(AI100:AK100)=0,"",AL100-LOOKUP(2,1/(AI100:AK100<>""),AI100:AK100))) | IF(OR(F100="",AM100=""),"",IF(COUNT(AI100:AL100)=0,"",AM100-LOOKUP(2,1/(AI100:AL100<>""),AI100:AL100))) | IF(OR(F100="",AN100=""),"",IF(COUNT(AI100:AM100)=0,"",AN100-LOOKUP(2,1/(AI100:AM100<>""),AI100:AM100))) | IF(OR(F100="",AO100=""),"",IF(COUNT(AI100:AN100)=0,"",AO100-LOOKUP(2,1/(AI100:AN100<>""),AI100:AN100))) | IF(OR(F100="",AP100=""),"",IF(COUNT(AI100:AO100)=0,"",AP100-LOOKUP(2,1/(AI100:AO100<>""),AI100:AO100))) | IF(OR(F100="",AQ100=""),"",IF(COUNT(AI100:AP100)=0,"",AQ100-LOOKUP(2,1/(AI100:AP100<>""),AI100:AP100))) | IF(OR(F100="",AR100=""),"",IF(COUNT(AI100:AQ100)=0,"",AR100-LOOKUP(2,1/(AI100:AQ100<>""),AI100:AQ100))) | IF(OR(F100="",AS100=""),"",IF(COUNT(AI100:AR100)=0,"",AS100-LOOKUP(2,1/(AI100:AR100<>""),AI100:AR100))) | IF(OR(F100="",AT100=""),"",IF(COUNT(AI100:AS100)=0,"",AT100-LOOKUP(2,1/(AI100:AS100<>""),AI100:AS100))) | IF(OR(F100="",AU100=""),"",IF(COUNT(AI100:AT100)=0,"",AU100-LOOKUP(2,1/(AI100:AT100<>""),AI100:AT100))) | IF(OR(F100="",AV100=""),"",IF(COUNT(AI100:AU100)=0,"",AV100-LOOKUP(2,1/(AI100:AU100<>""),AI100:AU100))) | IF(J100="","All_Provinces",IFERROR(VLOOKUP(J100,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K100="","All_Districts",IFERROR(VLOOKUP(K100,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F101="","",ROW()-3) | [18 empty] | IF(AQ101="","",AQ101) |  |  |  | IF(W101<>"",W101,IF(OR(T101="",V101=""),"",EDATE(T101,V101))) |  |  |  |  | IF(F101="","",IF(COUNT(AI101:AV101)=0,IF(AA101="","Not started",AA101),SUBSTITUTE(LOOKUP(2,1/(AI101:AV101<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F101="",COUNT(AI101:AV101)=0),"",TODAY()-LOOKUP(2,1/(AI101:AV101<>""),AI101:AV101)) | IF(OR(F101="",COUNT(AI101:AV101)<2),"",LOOKUP(2,1/(AI101:AV101<>""),AI101:AV101)-MIN(AI101:AV101)) | IF(OR(AD101="",AC101="Not started",AC101=""),"",IFERROR(AD101-IF(VLOOKUP(AC101,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC101,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F101="","",IF(OR(AA101="Cancelled",AC101="Cancelled"),"Cancelled",IF(OR(AC101="Completed / Handover",Y101<>"",Z101>=100),"Completed — on track",IF(O101="Not awarded",IF(U101="",IF(X101="","No planned date",IF(TODAY()>X101,"Behind — past planned date",IF(X101-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U101,"Behind — award date passed",IF(U101-TODAY()<=30,"At risk — close to off track","On track"))),IF(X101="","No planned date",IF(AND(TODAY()>X101,OR(Z101="",Z101<100)),"Behind — past end date",IF(AND(T101<>"",X101<>"",Z101<>"",(Z101<100),((TODAY()-T101)/MAX(X101-T101,1)*100)-Z101>15),"Behind — progress lag",IF(AND(X101-TODAY()<=30,X101-TODAY()>=0,OR(Z101="",Z101<90)),"At risk — close to off track","On track")))))))) | IF(OR(F101="",AC101="Completed / Handover",AC101="Cancelled"),"",IF(O101="Not awarded",IF(U101<>"",U101-TODAY(),IF(X101="","",X101-TODAY())),IF(X101="","",X101-TODAY()))) | [14 empty] | IF(OR(F101="",AJ101=""),"",IF(COUNT(AI101:AI101)=0,"",AJ101-LOOKUP(2,1/(AI101:AI101<>""),AI101:AI101))) | IF(OR(F101="",AK101=""),"",IF(COUNT(AI101:AJ101)=0,"",AK101-LOOKUP(2,1/(AI101:AJ101<>""),AI101:AJ101))) | IF(OR(F101="",AL101=""),"",IF(COUNT(AI101:AK101)=0,"",AL101-LOOKUP(2,1/(AI101:AK101<>""),AI101:AK101))) | IF(OR(F101="",AM101=""),"",IF(COUNT(AI101:AL101)=0,"",AM101-LOOKUP(2,1/(AI101:AL101<>""),AI101:AL101))) | IF(OR(F101="",AN101=""),"",IF(COUNT(AI101:AM101)=0,"",AN101-LOOKUP(2,1/(AI101:AM101<>""),AI101:AM101))) | IF(OR(F101="",AO101=""),"",IF(COUNT(AI101:AN101)=0,"",AO101-LOOKUP(2,1/(AI101:AN101<>""),AI101:AN101))) | IF(OR(F101="",AP101=""),"",IF(COUNT(AI101:AO101)=0,"",AP101-LOOKUP(2,1/(AI101:AO101<>""),AI101:AO101))) | IF(OR(F101="",AQ101=""),"",IF(COUNT(AI101:AP101)=0,"",AQ101-LOOKUP(2,1/(AI101:AP101<>""),AI101:AP101))) | IF(OR(F101="",AR101=""),"",IF(COUNT(AI101:AQ101)=0,"",AR101-LOOKUP(2,1/(AI101:AQ101<>""),AI101:AQ101))) | IF(OR(F101="",AS101=""),"",IF(COUNT(AI101:AR101)=0,"",AS101-LOOKUP(2,1/(AI101:AR101<>""),AI101:AR101))) | IF(OR(F101="",AT101=""),"",IF(COUNT(AI101:AS101)=0,"",AT101-LOOKUP(2,1/(AI101:AS101<>""),AI101:AS101))) | IF(OR(F101="",AU101=""),"",IF(COUNT(AI101:AT101)=0,"",AU101-LOOKUP(2,1/(AI101:AT101<>""),AI101:AT101))) | IF(OR(F101="",AV101=""),"",IF(COUNT(AI101:AU101)=0,"",AV101-LOOKUP(2,1/(AI101:AU101<>""),AI101:AU101))) | IF(J101="","All_Provinces",IFERROR(VLOOKUP(J101,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K101="","All_Districts",IFERROR(VLOOKUP(K101,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F102="","",ROW()-3) | [18 empty] | IF(AQ102="","",AQ102) |  |  |  | IF(W102<>"",W102,IF(OR(T102="",V102=""),"",EDATE(T102,V102))) |  |  |  |  | IF(F102="","",IF(COUNT(AI102:AV102)=0,IF(AA102="","Not started",AA102),SUBSTITUTE(LOOKUP(2,1/(AI102:AV102<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F102="",COUNT(AI102:AV102)=0),"",TODAY()-LOOKUP(2,1/(AI102:AV102<>""),AI102:AV102)) | IF(OR(F102="",COUNT(AI102:AV102)<2),"",LOOKUP(2,1/(AI102:AV102<>""),AI102:AV102)-MIN(AI102:AV102)) | IF(OR(AD102="",AC102="Not started",AC102=""),"",IFERROR(AD102-IF(VLOOKUP(AC102,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC102,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F102="","",IF(OR(AA102="Cancelled",AC102="Cancelled"),"Cancelled",IF(OR(AC102="Completed / Handover",Y102<>"",Z102>=100),"Completed — on track",IF(O102="Not awarded",IF(U102="",IF(X102="","No planned date",IF(TODAY()>X102,"Behind — past planned date",IF(X102-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U102,"Behind — award date passed",IF(U102-TODAY()<=30,"At risk — close to off track","On track"))),IF(X102="","No planned date",IF(AND(TODAY()>X102,OR(Z102="",Z102<100)),"Behind — past end date",IF(AND(T102<>"",X102<>"",Z102<>"",(Z102<100),((TODAY()-T102)/MAX(X102-T102,1)*100)-Z102>15),"Behind — progress lag",IF(AND(X102-TODAY()<=30,X102-TODAY()>=0,OR(Z102="",Z102<90)),"At risk — close to off track","On track")))))))) | IF(OR(F102="",AC102="Completed / Handover",AC102="Cancelled"),"",IF(O102="Not awarded",IF(U102<>"",U102-TODAY(),IF(X102="","",X102-TODAY())),IF(X102="","",X102-TODAY()))) | [14 empty] | IF(OR(F102="",AJ102=""),"",IF(COUNT(AI102:AI102)=0,"",AJ102-LOOKUP(2,1/(AI102:AI102<>""),AI102:AI102))) | IF(OR(F102="",AK102=""),"",IF(COUNT(AI102:AJ102)=0,"",AK102-LOOKUP(2,1/(AI102:AJ102<>""),AI102:AJ102))) | IF(OR(F102="",AL102=""),"",IF(COUNT(AI102:AK102)=0,"",AL102-LOOKUP(2,1/(AI102:AK102<>""),AI102:AK102))) | IF(OR(F102="",AM102=""),"",IF(COUNT(AI102:AL102)=0,"",AM102-LOOKUP(2,1/(AI102:AL102<>""),AI102:AL102))) | IF(OR(F102="",AN102=""),"",IF(COUNT(AI102:AM102)=0,"",AN102-LOOKUP(2,1/(AI102:AM102<>""),AI102:AM102))) | IF(OR(F102="",AO102=""),"",IF(COUNT(AI102:AN102)=0,"",AO102-LOOKUP(2,1/(AI102:AN102<>""),AI102:AN102))) | IF(OR(F102="",AP102=""),"",IF(COUNT(AI102:AO102)=0,"",AP102-LOOKUP(2,1/(AI102:AO102<>""),AI102:AO102))) | IF(OR(F102="",AQ102=""),"",IF(COUNT(AI102:AP102)=0,"",AQ102-LOOKUP(2,1/(AI102:AP102<>""),AI102:AP102))) | IF(OR(F102="",AR102=""),"",IF(COUNT(AI102:AQ102)=0,"",AR102-LOOKUP(2,1/(AI102:AQ102<>""),AI102:AQ102))) | IF(OR(F102="",AS102=""),"",IF(COUNT(AI102:AR102)=0,"",AS102-LOOKUP(2,1/(AI102:AR102<>""),AI102:AR102))) | IF(OR(F102="",AT102=""),"",IF(COUNT(AI102:AS102)=0,"",AT102-LOOKUP(2,1/(AI102:AS102<>""),AI102:AS102))) | IF(OR(F102="",AU102=""),"",IF(COUNT(AI102:AT102)=0,"",AU102-LOOKUP(2,1/(AI102:AT102<>""),AI102:AT102))) | IF(OR(F102="",AV102=""),"",IF(COUNT(AI102:AU102)=0,"",AV102-LOOKUP(2,1/(AI102:AU102<>""),AI102:AU102))) | IF(J102="","All_Provinces",IFERROR(VLOOKUP(J102,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K102="","All_Districts",IFERROR(VLOOKUP(K102,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F103="","",ROW()-3) | [18 empty] | IF(AQ103="","",AQ103) |  |  |  | IF(W103<>"",W103,IF(OR(T103="",V103=""),"",EDATE(T103,V103))) |  |  |  |  | IF(F103="","",IF(COUNT(AI103:AV103)=0,IF(AA103="","Not started",AA103),SUBSTITUTE(LOOKUP(2,1/(AI103:AV103<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F103="",COUNT(AI103:AV103)=0),"",TODAY()-LOOKUP(2,1/(AI103:AV103<>""),AI103:AV103)) | IF(OR(F103="",COUNT(AI103:AV103)<2),"",LOOKUP(2,1/(AI103:AV103<>""),AI103:AV103)-MIN(AI103:AV103)) | IF(OR(AD103="",AC103="Not started",AC103=""),"",IFERROR(AD103-IF(VLOOKUP(AC103,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC103,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F103="","",IF(OR(AA103="Cancelled",AC103="Cancelled"),"Cancelled",IF(OR(AC103="Completed / Handover",Y103<>"",Z103>=100),"Completed — on track",IF(O103="Not awarded",IF(U103="",IF(X103="","No planned date",IF(TODAY()>X103,"Behind — past planned date",IF(X103-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U103,"Behind — award date passed",IF(U103-TODAY()<=30,"At risk — close to off track","On track"))),IF(X103="","No planned date",IF(AND(TODAY()>X103,OR(Z103="",Z103<100)),"Behind — past end date",IF(AND(T103<>"",X103<>"",Z103<>"",(Z103<100),((TODAY()-T103)/MAX(X103-T103,1)*100)-Z103>15),"Behind — progress lag",IF(AND(X103-TODAY()<=30,X103-TODAY()>=0,OR(Z103="",Z103<90)),"At risk — close to off track","On track")))))))) | IF(OR(F103="",AC103="Completed / Handover",AC103="Cancelled"),"",IF(O103="Not awarded",IF(U103<>"",U103-TODAY(),IF(X103="","",X103-TODAY())),IF(X103="","",X103-TODAY()))) | [14 empty] | IF(OR(F103="",AJ103=""),"",IF(COUNT(AI103:AI103)=0,"",AJ103-LOOKUP(2,1/(AI103:AI103<>""),AI103:AI103))) | IF(OR(F103="",AK103=""),"",IF(COUNT(AI103:AJ103)=0,"",AK103-LOOKUP(2,1/(AI103:AJ103<>""),AI103:AJ103))) | IF(OR(F103="",AL103=""),"",IF(COUNT(AI103:AK103)=0,"",AL103-LOOKUP(2,1/(AI103:AK103<>""),AI103:AK103))) | IF(OR(F103="",AM103=""),"",IF(COUNT(AI103:AL103)=0,"",AM103-LOOKUP(2,1/(AI103:AL103<>""),AI103:AL103))) | IF(OR(F103="",AN103=""),"",IF(COUNT(AI103:AM103)=0,"",AN103-LOOKUP(2,1/(AI103:AM103<>""),AI103:AM103))) | IF(OR(F103="",AO103=""),"",IF(COUNT(AI103:AN103)=0,"",AO103-LOOKUP(2,1/(AI103:AN103<>""),AI103:AN103))) | IF(OR(F103="",AP103=""),"",IF(COUNT(AI103:AO103)=0,"",AP103-LOOKUP(2,1/(AI103:AO103<>""),AI103:AO103))) | IF(OR(F103="",AQ103=""),"",IF(COUNT(AI103:AP103)=0,"",AQ103-LOOKUP(2,1/(AI103:AP103<>""),AI103:AP103))) | IF(OR(F103="",AR103=""),"",IF(COUNT(AI103:AQ103)=0,"",AR103-LOOKUP(2,1/(AI103:AQ103<>""),AI103:AQ103))) | IF(OR(F103="",AS103=""),"",IF(COUNT(AI103:AR103)=0,"",AS103-LOOKUP(2,1/(AI103:AR103<>""),AI103:AR103))) | IF(OR(F103="",AT103=""),"",IF(COUNT(AI103:AS103)=0,"",AT103-LOOKUP(2,1/(AI103:AS103<>""),AI103:AS103))) | IF(OR(F103="",AU103=""),"",IF(COUNT(AI103:AT103)=0,"",AU103-LOOKUP(2,1/(AI103:AT103<>""),AI103:AT103))) | IF(OR(F103="",AV103=""),"",IF(COUNT(AI103:AU103)=0,"",AV103-LOOKUP(2,1/(AI103:AU103<>""),AI103:AU103))) | IF(J103="","All_Provinces",IFERROR(VLOOKUP(J103,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K103="","All_Districts",IFERROR(VLOOKUP(K103,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F104="","",ROW()-3) | [18 empty] | IF(AQ104="","",AQ104) |  |  |  | IF(W104<>"",W104,IF(OR(T104="",V104=""),"",EDATE(T104,V104))) |  |  |  |  | IF(F104="","",IF(COUNT(AI104:AV104)=0,IF(AA104="","Not started",AA104),SUBSTITUTE(LOOKUP(2,1/(AI104:AV104<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F104="",COUNT(AI104:AV104)=0),"",TODAY()-LOOKUP(2,1/(AI104:AV104<>""),AI104:AV104)) | IF(OR(F104="",COUNT(AI104:AV104)<2),"",LOOKUP(2,1/(AI104:AV104<>""),AI104:AV104)-MIN(AI104:AV104)) | IF(OR(AD104="",AC104="Not started",AC104=""),"",IFERROR(AD104-IF(VLOOKUP(AC104,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC104,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F104="","",IF(OR(AA104="Cancelled",AC104="Cancelled"),"Cancelled",IF(OR(AC104="Completed / Handover",Y104<>"",Z104>=100),"Completed — on track",IF(O104="Not awarded",IF(U104="",IF(X104="","No planned date",IF(TODAY()>X104,"Behind — past planned date",IF(X104-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U104,"Behind — award date passed",IF(U104-TODAY()<=30,"At risk — close to off track","On track"))),IF(X104="","No planned date",IF(AND(TODAY()>X104,OR(Z104="",Z104<100)),"Behind — past end date",IF(AND(T104<>"",X104<>"",Z104<>"",(Z104<100),((TODAY()-T104)/MAX(X104-T104,1)*100)-Z104>15),"Behind — progress lag",IF(AND(X104-TODAY()<=30,X104-TODAY()>=0,OR(Z104="",Z104<90)),"At risk — close to off track","On track")))))))) | IF(OR(F104="",AC104="Completed / Handover",AC104="Cancelled"),"",IF(O104="Not awarded",IF(U104<>"",U104-TODAY(),IF(X104="","",X104-TODAY())),IF(X104="","",X104-TODAY()))) | [14 empty] | IF(OR(F104="",AJ104=""),"",IF(COUNT(AI104:AI104)=0,"",AJ104-LOOKUP(2,1/(AI104:AI104<>""),AI104:AI104))) | IF(OR(F104="",AK104=""),"",IF(COUNT(AI104:AJ104)=0,"",AK104-LOOKUP(2,1/(AI104:AJ104<>""),AI104:AJ104))) | IF(OR(F104="",AL104=""),"",IF(COUNT(AI104:AK104)=0,"",AL104-LOOKUP(2,1/(AI104:AK104<>""),AI104:AK104))) | IF(OR(F104="",AM104=""),"",IF(COUNT(AI104:AL104)=0,"",AM104-LOOKUP(2,1/(AI104:AL104<>""),AI104:AL104))) | IF(OR(F104="",AN104=""),"",IF(COUNT(AI104:AM104)=0,"",AN104-LOOKUP(2,1/(AI104:AM104<>""),AI104:AM104))) | IF(OR(F104="",AO104=""),"",IF(COUNT(AI104:AN104)=0,"",AO104-LOOKUP(2,1/(AI104:AN104<>""),AI104:AN104))) | IF(OR(F104="",AP104=""),"",IF(COUNT(AI104:AO104)=0,"",AP104-LOOKUP(2,1/(AI104:AO104<>""),AI104:AO104))) | IF(OR(F104="",AQ104=""),"",IF(COUNT(AI104:AP104)=0,"",AQ104-LOOKUP(2,1/(AI104:AP104<>""),AI104:AP104))) | IF(OR(F104="",AR104=""),"",IF(COUNT(AI104:AQ104)=0,"",AR104-LOOKUP(2,1/(AI104:AQ104<>""),AI104:AQ104))) | IF(OR(F104="",AS104=""),"",IF(COUNT(AI104:AR104)=0,"",AS104-LOOKUP(2,1/(AI104:AR104<>""),AI104:AR104))) | IF(OR(F104="",AT104=""),"",IF(COUNT(AI104:AS104)=0,"",AT104-LOOKUP(2,1/(AI104:AS104<>""),AI104:AS104))) | IF(OR(F104="",AU104=""),"",IF(COUNT(AI104:AT104)=0,"",AU104-LOOKUP(2,1/(AI104:AT104<>""),AI104:AT104))) | IF(OR(F104="",AV104=""),"",IF(COUNT(AI104:AU104)=0,"",AV104-LOOKUP(2,1/(AI104:AU104<>""),AI104:AU104))) | IF(J104="","All_Provinces",IFERROR(VLOOKUP(J104,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K104="","All_Districts",IFERROR(VLOOKUP(K104,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F105="","",ROW()-3) | [18 empty] | IF(AQ105="","",AQ105) |  |  |  | IF(W105<>"",W105,IF(OR(T105="",V105=""),"",EDATE(T105,V105))) |  |  |  |  | IF(F105="","",IF(COUNT(AI105:AV105)=0,IF(AA105="","Not started",AA105),SUBSTITUTE(LOOKUP(2,1/(AI105:AV105<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F105="",COUNT(AI105:AV105)=0),"",TODAY()-LOOKUP(2,1/(AI105:AV105<>""),AI105:AV105)) | IF(OR(F105="",COUNT(AI105:AV105)<2),"",LOOKUP(2,1/(AI105:AV105<>""),AI105:AV105)-MIN(AI105:AV105)) | IF(OR(AD105="",AC105="Not started",AC105=""),"",IFERROR(AD105-IF(VLOOKUP(AC105,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC105,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F105="","",IF(OR(AA105="Cancelled",AC105="Cancelled"),"Cancelled",IF(OR(AC105="Completed / Handover",Y105<>"",Z105>=100),"Completed — on track",IF(O105="Not awarded",IF(U105="",IF(X105="","No planned date",IF(TODAY()>X105,"Behind — past planned date",IF(X105-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U105,"Behind — award date passed",IF(U105-TODAY()<=30,"At risk — close to off track","On track"))),IF(X105="","No planned date",IF(AND(TODAY()>X105,OR(Z105="",Z105<100)),"Behind — past end date",IF(AND(T105<>"",X105<>"",Z105<>"",(Z105<100),((TODAY()-T105)/MAX(X105-T105,1)*100)-Z105>15),"Behind — progress lag",IF(AND(X105-TODAY()<=30,X105-TODAY()>=0,OR(Z105="",Z105<90)),"At risk — close to off track","On track")))))))) | IF(OR(F105="",AC105="Completed / Handover",AC105="Cancelled"),"",IF(O105="Not awarded",IF(U105<>"",U105-TODAY(),IF(X105="","",X105-TODAY())),IF(X105="","",X105-TODAY()))) | [14 empty] | IF(OR(F105="",AJ105=""),"",IF(COUNT(AI105:AI105)=0,"",AJ105-LOOKUP(2,1/(AI105:AI105<>""),AI105:AI105))) | IF(OR(F105="",AK105=""),"",IF(COUNT(AI105:AJ105)=0,"",AK105-LOOKUP(2,1/(AI105:AJ105<>""),AI105:AJ105))) | IF(OR(F105="",AL105=""),"",IF(COUNT(AI105:AK105)=0,"",AL105-LOOKUP(2,1/(AI105:AK105<>""),AI105:AK105))) | IF(OR(F105="",AM105=""),"",IF(COUNT(AI105:AL105)=0,"",AM105-LOOKUP(2,1/(AI105:AL105<>""),AI105:AL105))) | IF(OR(F105="",AN105=""),"",IF(COUNT(AI105:AM105)=0,"",AN105-LOOKUP(2,1/(AI105:AM105<>""),AI105:AM105))) | IF(OR(F105="",AO105=""),"",IF(COUNT(AI105:AN105)=0,"",AO105-LOOKUP(2,1/(AI105:AN105<>""),AI105:AN105))) | IF(OR(F105="",AP105=""),"",IF(COUNT(AI105:AO105)=0,"",AP105-LOOKUP(2,1/(AI105:AO105<>""),AI105:AO105))) | IF(OR(F105="",AQ105=""),"",IF(COUNT(AI105:AP105)=0,"",AQ105-LOOKUP(2,1/(AI105:AP105<>""),AI105:AP105))) | IF(OR(F105="",AR105=""),"",IF(COUNT(AI105:AQ105)=0,"",AR105-LOOKUP(2,1/(AI105:AQ105<>""),AI105:AQ105))) | IF(OR(F105="",AS105=""),"",IF(COUNT(AI105:AR105)=0,"",AS105-LOOKUP(2,1/(AI105:AR105<>""),AI105:AR105))) | IF(OR(F105="",AT105=""),"",IF(COUNT(AI105:AS105)=0,"",AT105-LOOKUP(2,1/(AI105:AS105<>""),AI105:AS105))) | IF(OR(F105="",AU105=""),"",IF(COUNT(AI105:AT105)=0,"",AU105-LOOKUP(2,1/(AI105:AT105<>""),AI105:AT105))) | IF(OR(F105="",AV105=""),"",IF(COUNT(AI105:AU105)=0,"",AV105-LOOKUP(2,1/(AI105:AU105<>""),AI105:AU105))) | IF(J105="","All_Provinces",IFERROR(VLOOKUP(J105,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K105="","All_Districts",IFERROR(VLOOKUP(K105,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F106="","",ROW()-3) | [18 empty] | IF(AQ106="","",AQ106) |  |  |  | IF(W106<>"",W106,IF(OR(T106="",V106=""),"",EDATE(T106,V106))) |  |  |  |  | IF(F106="","",IF(COUNT(AI106:AV106)=0,IF(AA106="","Not started",AA106),SUBSTITUTE(LOOKUP(2,1/(AI106:AV106<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F106="",COUNT(AI106:AV106)=0),"",TODAY()-LOOKUP(2,1/(AI106:AV106<>""),AI106:AV106)) | IF(OR(F106="",COUNT(AI106:AV106)<2),"",LOOKUP(2,1/(AI106:AV106<>""),AI106:AV106)-MIN(AI106:AV106)) | IF(OR(AD106="",AC106="Not started",AC106=""),"",IFERROR(AD106-IF(VLOOKUP(AC106,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC106,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F106="","",IF(OR(AA106="Cancelled",AC106="Cancelled"),"Cancelled",IF(OR(AC106="Completed / Handover",Y106<>"",Z106>=100),"Completed — on track",IF(O106="Not awarded",IF(U106="",IF(X106="","No planned date",IF(TODAY()>X106,"Behind — past planned date",IF(X106-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U106,"Behind — award date passed",IF(U106-TODAY()<=30,"At risk — close to off track","On track"))),IF(X106="","No planned date",IF(AND(TODAY()>X106,OR(Z106="",Z106<100)),"Behind — past end date",IF(AND(T106<>"",X106<>"",Z106<>"",(Z106<100),((TODAY()-T106)/MAX(X106-T106,1)*100)-Z106>15),"Behind — progress lag",IF(AND(X106-TODAY()<=30,X106-TODAY()>=0,OR(Z106="",Z106<90)),"At risk — close to off track","On track")))))))) | IF(OR(F106="",AC106="Completed / Handover",AC106="Cancelled"),"",IF(O106="Not awarded",IF(U106<>"",U106-TODAY(),IF(X106="","",X106-TODAY())),IF(X106="","",X106-TODAY()))) | [14 empty] | IF(OR(F106="",AJ106=""),"",IF(COUNT(AI106:AI106)=0,"",AJ106-LOOKUP(2,1/(AI106:AI106<>""),AI106:AI106))) | IF(OR(F106="",AK106=""),"",IF(COUNT(AI106:AJ106)=0,"",AK106-LOOKUP(2,1/(AI106:AJ106<>""),AI106:AJ106))) | IF(OR(F106="",AL106=""),"",IF(COUNT(AI106:AK106)=0,"",AL106-LOOKUP(2,1/(AI106:AK106<>""),AI106:AK106))) | IF(OR(F106="",AM106=""),"",IF(COUNT(AI106:AL106)=0,"",AM106-LOOKUP(2,1/(AI106:AL106<>""),AI106:AL106))) | IF(OR(F106="",AN106=""),"",IF(COUNT(AI106:AM106)=0,"",AN106-LOOKUP(2,1/(AI106:AM106<>""),AI106:AM106))) | IF(OR(F106="",AO106=""),"",IF(COUNT(AI106:AN106)=0,"",AO106-LOOKUP(2,1/(AI106:AN106<>""),AI106:AN106))) | IF(OR(F106="",AP106=""),"",IF(COUNT(AI106:AO106)=0,"",AP106-LOOKUP(2,1/(AI106:AO106<>""),AI106:AO106))) | IF(OR(F106="",AQ106=""),"",IF(COUNT(AI106:AP106)=0,"",AQ106-LOOKUP(2,1/(AI106:AP106<>""),AI106:AP106))) | IF(OR(F106="",AR106=""),"",IF(COUNT(AI106:AQ106)=0,"",AR106-LOOKUP(2,1/(AI106:AQ106<>""),AI106:AQ106))) | IF(OR(F106="",AS106=""),"",IF(COUNT(AI106:AR106)=0,"",AS106-LOOKUP(2,1/(AI106:AR106<>""),AI106:AR106))) | IF(OR(F106="",AT106=""),"",IF(COUNT(AI106:AS106)=0,"",AT106-LOOKUP(2,1/(AI106:AS106<>""),AI106:AS106))) | IF(OR(F106="",AU106=""),"",IF(COUNT(AI106:AT106)=0,"",AU106-LOOKUP(2,1/(AI106:AT106<>""),AI106:AT106))) | IF(OR(F106="",AV106=""),"",IF(COUNT(AI106:AU106)=0,"",AV106-LOOKUP(2,1/(AI106:AU106<>""),AI106:AU106))) | IF(J106="","All_Provinces",IFERROR(VLOOKUP(J106,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K106="","All_Districts",IFERROR(VLOOKUP(K106,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F107="","",ROW()-3) | [18 empty] | IF(AQ107="","",AQ107) |  |  |  | IF(W107<>"",W107,IF(OR(T107="",V107=""),"",EDATE(T107,V107))) |  |  |  |  | IF(F107="","",IF(COUNT(AI107:AV107)=0,IF(AA107="","Not started",AA107),SUBSTITUTE(LOOKUP(2,1/(AI107:AV107<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F107="",COUNT(AI107:AV107)=0),"",TODAY()-LOOKUP(2,1/(AI107:AV107<>""),AI107:AV107)) | IF(OR(F107="",COUNT(AI107:AV107)<2),"",LOOKUP(2,1/(AI107:AV107<>""),AI107:AV107)-MIN(AI107:AV107)) | IF(OR(AD107="",AC107="Not started",AC107=""),"",IFERROR(AD107-IF(VLOOKUP(AC107,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC107,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F107="","",IF(OR(AA107="Cancelled",AC107="Cancelled"),"Cancelled",IF(OR(AC107="Completed / Handover",Y107<>"",Z107>=100),"Completed — on track",IF(O107="Not awarded",IF(U107="",IF(X107="","No planned date",IF(TODAY()>X107,"Behind — past planned date",IF(X107-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U107,"Behind — award date passed",IF(U107-TODAY()<=30,"At risk — close to off track","On track"))),IF(X107="","No planned date",IF(AND(TODAY()>X107,OR(Z107="",Z107<100)),"Behind — past end date",IF(AND(T107<>"",X107<>"",Z107<>"",(Z107<100),((TODAY()-T107)/MAX(X107-T107,1)*100)-Z107>15),"Behind — progress lag",IF(AND(X107-TODAY()<=30,X107-TODAY()>=0,OR(Z107="",Z107<90)),"At risk — close to off track","On track")))))))) | IF(OR(F107="",AC107="Completed / Handover",AC107="Cancelled"),"",IF(O107="Not awarded",IF(U107<>"",U107-TODAY(),IF(X107="","",X107-TODAY())),IF(X107="","",X107-TODAY()))) | [14 empty] | IF(OR(F107="",AJ107=""),"",IF(COUNT(AI107:AI107)=0,"",AJ107-LOOKUP(2,1/(AI107:AI107<>""),AI107:AI107))) | IF(OR(F107="",AK107=""),"",IF(COUNT(AI107:AJ107)=0,"",AK107-LOOKUP(2,1/(AI107:AJ107<>""),AI107:AJ107))) | IF(OR(F107="",AL107=""),"",IF(COUNT(AI107:AK107)=0,"",AL107-LOOKUP(2,1/(AI107:AK107<>""),AI107:AK107))) | IF(OR(F107="",AM107=""),"",IF(COUNT(AI107:AL107)=0,"",AM107-LOOKUP(2,1/(AI107:AL107<>""),AI107:AL107))) | IF(OR(F107="",AN107=""),"",IF(COUNT(AI107:AM107)=0,"",AN107-LOOKUP(2,1/(AI107:AM107<>""),AI107:AM107))) | IF(OR(F107="",AO107=""),"",IF(COUNT(AI107:AN107)=0,"",AO107-LOOKUP(2,1/(AI107:AN107<>""),AI107:AN107))) | IF(OR(F107="",AP107=""),"",IF(COUNT(AI107:AO107)=0,"",AP107-LOOKUP(2,1/(AI107:AO107<>""),AI107:AO107))) | IF(OR(F107="",AQ107=""),"",IF(COUNT(AI107:AP107)=0,"",AQ107-LOOKUP(2,1/(AI107:AP107<>""),AI107:AP107))) | IF(OR(F107="",AR107=""),"",IF(COUNT(AI107:AQ107)=0,"",AR107-LOOKUP(2,1/(AI107:AQ107<>""),AI107:AQ107))) | IF(OR(F107="",AS107=""),"",IF(COUNT(AI107:AR107)=0,"",AS107-LOOKUP(2,1/(AI107:AR107<>""),AI107:AR107))) | IF(OR(F107="",AT107=""),"",IF(COUNT(AI107:AS107)=0,"",AT107-LOOKUP(2,1/(AI107:AS107<>""),AI107:AS107))) | IF(OR(F107="",AU107=""),"",IF(COUNT(AI107:AT107)=0,"",AU107-LOOKUP(2,1/(AI107:AT107<>""),AI107:AT107))) | IF(OR(F107="",AV107=""),"",IF(COUNT(AI107:AU107)=0,"",AV107-LOOKUP(2,1/(AI107:AU107<>""),AI107:AU107))) | IF(J107="","All_Provinces",IFERROR(VLOOKUP(J107,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K107="","All_Districts",IFERROR(VLOOKUP(K107,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F108="","",ROW()-3) | [18 empty] | IF(AQ108="","",AQ108) |  |  |  | IF(W108<>"",W108,IF(OR(T108="",V108=""),"",EDATE(T108,V108))) |  |  |  |  | IF(F108="","",IF(COUNT(AI108:AV108)=0,IF(AA108="","Not started",AA108),SUBSTITUTE(LOOKUP(2,1/(AI108:AV108<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F108="",COUNT(AI108:AV108)=0),"",TODAY()-LOOKUP(2,1/(AI108:AV108<>""),AI108:AV108)) | IF(OR(F108="",COUNT(AI108:AV108)<2),"",LOOKUP(2,1/(AI108:AV108<>""),AI108:AV108)-MIN(AI108:AV108)) | IF(OR(AD108="",AC108="Not started",AC108=""),"",IFERROR(AD108-IF(VLOOKUP(AC108,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC108,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F108="","",IF(OR(AA108="Cancelled",AC108="Cancelled"),"Cancelled",IF(OR(AC108="Completed / Handover",Y108<>"",Z108>=100),"Completed — on track",IF(O108="Not awarded",IF(U108="",IF(X108="","No planned date",IF(TODAY()>X108,"Behind — past planned date",IF(X108-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U108,"Behind — award date passed",IF(U108-TODAY()<=30,"At risk — close to off track","On track"))),IF(X108="","No planned date",IF(AND(TODAY()>X108,OR(Z108="",Z108<100)),"Behind — past end date",IF(AND(T108<>"",X108<>"",Z108<>"",(Z108<100),((TODAY()-T108)/MAX(X108-T108,1)*100)-Z108>15),"Behind — progress lag",IF(AND(X108-TODAY()<=30,X108-TODAY()>=0,OR(Z108="",Z108<90)),"At risk — close to off track","On track")))))))) | IF(OR(F108="",AC108="Completed / Handover",AC108="Cancelled"),"",IF(O108="Not awarded",IF(U108<>"",U108-TODAY(),IF(X108="","",X108-TODAY())),IF(X108="","",X108-TODAY()))) | [14 empty] | IF(OR(F108="",AJ108=""),"",IF(COUNT(AI108:AI108)=0,"",AJ108-LOOKUP(2,1/(AI108:AI108<>""),AI108:AI108))) | IF(OR(F108="",AK108=""),"",IF(COUNT(AI108:AJ108)=0,"",AK108-LOOKUP(2,1/(AI108:AJ108<>""),AI108:AJ108))) | IF(OR(F108="",AL108=""),"",IF(COUNT(AI108:AK108)=0,"",AL108-LOOKUP(2,1/(AI108:AK108<>""),AI108:AK108))) | IF(OR(F108="",AM108=""),"",IF(COUNT(AI108:AL108)=0,"",AM108-LOOKUP(2,1/(AI108:AL108<>""),AI108:AL108))) | IF(OR(F108="",AN108=""),"",IF(COUNT(AI108:AM108)=0,"",AN108-LOOKUP(2,1/(AI108:AM108<>""),AI108:AM108))) | IF(OR(F108="",AO108=""),"",IF(COUNT(AI108:AN108)=0,"",AO108-LOOKUP(2,1/(AI108:AN108<>""),AI108:AN108))) | IF(OR(F108="",AP108=""),"",IF(COUNT(AI108:AO108)=0,"",AP108-LOOKUP(2,1/(AI108:AO108<>""),AI108:AO108))) | IF(OR(F108="",AQ108=""),"",IF(COUNT(AI108:AP108)=0,"",AQ108-LOOKUP(2,1/(AI108:AP108<>""),AI108:AP108))) | IF(OR(F108="",AR108=""),"",IF(COUNT(AI108:AQ108)=0,"",AR108-LOOKUP(2,1/(AI108:AQ108<>""),AI108:AQ108))) | IF(OR(F108="",AS108=""),"",IF(COUNT(AI108:AR108)=0,"",AS108-LOOKUP(2,1/(AI108:AR108<>""),AI108:AR108))) | IF(OR(F108="",AT108=""),"",IF(COUNT(AI108:AS108)=0,"",AT108-LOOKUP(2,1/(AI108:AS108<>""),AI108:AS108))) | IF(OR(F108="",AU108=""),"",IF(COUNT(AI108:AT108)=0,"",AU108-LOOKUP(2,1/(AI108:AT108<>""),AI108:AT108))) | IF(OR(F108="",AV108=""),"",IF(COUNT(AI108:AU108)=0,"",AV108-LOOKUP(2,1/(AI108:AU108<>""),AI108:AU108))) | IF(J108="","All_Provinces",IFERROR(VLOOKUP(J108,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K108="","All_Districts",IFERROR(VLOOKUP(K108,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F109="","",ROW()-3) | [18 empty] | IF(AQ109="","",AQ109) |  |  |  | IF(W109<>"",W109,IF(OR(T109="",V109=""),"",EDATE(T109,V109))) |  |  |  |  | IF(F109="","",IF(COUNT(AI109:AV109)=0,IF(AA109="","Not started",AA109),SUBSTITUTE(LOOKUP(2,1/(AI109:AV109<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F109="",COUNT(AI109:AV109)=0),"",TODAY()-LOOKUP(2,1/(AI109:AV109<>""),AI109:AV109)) | IF(OR(F109="",COUNT(AI109:AV109)<2),"",LOOKUP(2,1/(AI109:AV109<>""),AI109:AV109)-MIN(AI109:AV109)) | IF(OR(AD109="",AC109="Not started",AC109=""),"",IFERROR(AD109-IF(VLOOKUP(AC109,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC109,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F109="","",IF(OR(AA109="Cancelled",AC109="Cancelled"),"Cancelled",IF(OR(AC109="Completed / Handover",Y109<>"",Z109>=100),"Completed — on track",IF(O109="Not awarded",IF(U109="",IF(X109="","No planned date",IF(TODAY()>X109,"Behind — past planned date",IF(X109-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U109,"Behind — award date passed",IF(U109-TODAY()<=30,"At risk — close to off track","On track"))),IF(X109="","No planned date",IF(AND(TODAY()>X109,OR(Z109="",Z109<100)),"Behind — past end date",IF(AND(T109<>"",X109<>"",Z109<>"",(Z109<100),((TODAY()-T109)/MAX(X109-T109,1)*100)-Z109>15),"Behind — progress lag",IF(AND(X109-TODAY()<=30,X109-TODAY()>=0,OR(Z109="",Z109<90)),"At risk — close to off track","On track")))))))) | IF(OR(F109="",AC109="Completed / Handover",AC109="Cancelled"),"",IF(O109="Not awarded",IF(U109<>"",U109-TODAY(),IF(X109="","",X109-TODAY())),IF(X109="","",X109-TODAY()))) | [14 empty] | IF(OR(F109="",AJ109=""),"",IF(COUNT(AI109:AI109)=0,"",AJ109-LOOKUP(2,1/(AI109:AI109<>""),AI109:AI109))) | IF(OR(F109="",AK109=""),"",IF(COUNT(AI109:AJ109)=0,"",AK109-LOOKUP(2,1/(AI109:AJ109<>""),AI109:AJ109))) | IF(OR(F109="",AL109=""),"",IF(COUNT(AI109:AK109)=0,"",AL109-LOOKUP(2,1/(AI109:AK109<>""),AI109:AK109))) | IF(OR(F109="",AM109=""),"",IF(COUNT(AI109:AL109)=0,"",AM109-LOOKUP(2,1/(AI109:AL109<>""),AI109:AL109))) | IF(OR(F109="",AN109=""),"",IF(COUNT(AI109:AM109)=0,"",AN109-LOOKUP(2,1/(AI109:AM109<>""),AI109:AM109))) | IF(OR(F109="",AO109=""),"",IF(COUNT(AI109:AN109)=0,"",AO109-LOOKUP(2,1/(AI109:AN109<>""),AI109:AN109))) | IF(OR(F109="",AP109=""),"",IF(COUNT(AI109:AO109)=0,"",AP109-LOOKUP(2,1/(AI109:AO109<>""),AI109:AO109))) | IF(OR(F109="",AQ109=""),"",IF(COUNT(AI109:AP109)=0,"",AQ109-LOOKUP(2,1/(AI109:AP109<>""),AI109:AP109))) | IF(OR(F109="",AR109=""),"",IF(COUNT(AI109:AQ109)=0,"",AR109-LOOKUP(2,1/(AI109:AQ109<>""),AI109:AQ109))) | IF(OR(F109="",AS109=""),"",IF(COUNT(AI109:AR109)=0,"",AS109-LOOKUP(2,1/(AI109:AR109<>""),AI109:AR109))) | IF(OR(F109="",AT109=""),"",IF(COUNT(AI109:AS109)=0,"",AT109-LOOKUP(2,1/(AI109:AS109<>""),AI109:AS109))) | IF(OR(F109="",AU109=""),"",IF(COUNT(AI109:AT109)=0,"",AU109-LOOKUP(2,1/(AI109:AT109<>""),AI109:AT109))) | IF(OR(F109="",AV109=""),"",IF(COUNT(AI109:AU109)=0,"",AV109-LOOKUP(2,1/(AI109:AU109<>""),AI109:AU109))) | IF(J109="","All_Provinces",IFERROR(VLOOKUP(J109,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K109="","All_Districts",IFERROR(VLOOKUP(K109,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F110="","",ROW()-3) | [18 empty] | IF(AQ110="","",AQ110) |  |  |  | IF(W110<>"",W110,IF(OR(T110="",V110=""),"",EDATE(T110,V110))) |  |  |  |  | IF(F110="","",IF(COUNT(AI110:AV110)=0,IF(AA110="","Not started",AA110),SUBSTITUTE(LOOKUP(2,1/(AI110:AV110<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F110="",COUNT(AI110:AV110)=0),"",TODAY()-LOOKUP(2,1/(AI110:AV110<>""),AI110:AV110)) | IF(OR(F110="",COUNT(AI110:AV110)<2),"",LOOKUP(2,1/(AI110:AV110<>""),AI110:AV110)-MIN(AI110:AV110)) | IF(OR(AD110="",AC110="Not started",AC110=""),"",IFERROR(AD110-IF(VLOOKUP(AC110,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC110,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F110="","",IF(OR(AA110="Cancelled",AC110="Cancelled"),"Cancelled",IF(OR(AC110="Completed / Handover",Y110<>"",Z110>=100),"Completed — on track",IF(O110="Not awarded",IF(U110="",IF(X110="","No planned date",IF(TODAY()>X110,"Behind — past planned date",IF(X110-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U110,"Behind — award date passed",IF(U110-TODAY()<=30,"At risk — close to off track","On track"))),IF(X110="","No planned date",IF(AND(TODAY()>X110,OR(Z110="",Z110<100)),"Behind — past end date",IF(AND(T110<>"",X110<>"",Z110<>"",(Z110<100),((TODAY()-T110)/MAX(X110-T110,1)*100)-Z110>15),"Behind — progress lag",IF(AND(X110-TODAY()<=30,X110-TODAY()>=0,OR(Z110="",Z110<90)),"At risk — close to off track","On track")))))))) | IF(OR(F110="",AC110="Completed / Handover",AC110="Cancelled"),"",IF(O110="Not awarded",IF(U110<>"",U110-TODAY(),IF(X110="","",X110-TODAY())),IF(X110="","",X110-TODAY()))) | [14 empty] | IF(OR(F110="",AJ110=""),"",IF(COUNT(AI110:AI110)=0,"",AJ110-LOOKUP(2,1/(AI110:AI110<>""),AI110:AI110))) | IF(OR(F110="",AK110=""),"",IF(COUNT(AI110:AJ110)=0,"",AK110-LOOKUP(2,1/(AI110:AJ110<>""),AI110:AJ110))) | IF(OR(F110="",AL110=""),"",IF(COUNT(AI110:AK110)=0,"",AL110-LOOKUP(2,1/(AI110:AK110<>""),AI110:AK110))) | IF(OR(F110="",AM110=""),"",IF(COUNT(AI110:AL110)=0,"",AM110-LOOKUP(2,1/(AI110:AL110<>""),AI110:AL110))) | IF(OR(F110="",AN110=""),"",IF(COUNT(AI110:AM110)=0,"",AN110-LOOKUP(2,1/(AI110:AM110<>""),AI110:AM110))) | IF(OR(F110="",AO110=""),"",IF(COUNT(AI110:AN110)=0,"",AO110-LOOKUP(2,1/(AI110:AN110<>""),AI110:AN110))) | IF(OR(F110="",AP110=""),"",IF(COUNT(AI110:AO110)=0,"",AP110-LOOKUP(2,1/(AI110:AO110<>""),AI110:AO110))) | IF(OR(F110="",AQ110=""),"",IF(COUNT(AI110:AP110)=0,"",AQ110-LOOKUP(2,1/(AI110:AP110<>""),AI110:AP110))) | IF(OR(F110="",AR110=""),"",IF(COUNT(AI110:AQ110)=0,"",AR110-LOOKUP(2,1/(AI110:AQ110<>""),AI110:AQ110))) | IF(OR(F110="",AS110=""),"",IF(COUNT(AI110:AR110)=0,"",AS110-LOOKUP(2,1/(AI110:AR110<>""),AI110:AR110))) | IF(OR(F110="",AT110=""),"",IF(COUNT(AI110:AS110)=0,"",AT110-LOOKUP(2,1/(AI110:AS110<>""),AI110:AS110))) | IF(OR(F110="",AU110=""),"",IF(COUNT(AI110:AT110)=0,"",AU110-LOOKUP(2,1/(AI110:AT110<>""),AI110:AT110))) | IF(OR(F110="",AV110=""),"",IF(COUNT(AI110:AU110)=0,"",AV110-LOOKUP(2,1/(AI110:AU110<>""),AI110:AU110))) | IF(J110="","All_Provinces",IFERROR(VLOOKUP(J110,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K110="","All_Districts",IFERROR(VLOOKUP(K110,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F111="","",ROW()-3) | [18 empty] | IF(AQ111="","",AQ111) |  |  |  | IF(W111<>"",W111,IF(OR(T111="",V111=""),"",EDATE(T111,V111))) |  |  |  |  | IF(F111="","",IF(COUNT(AI111:AV111)=0,IF(AA111="","Not started",AA111),SUBSTITUTE(LOOKUP(2,1/(AI111:AV111<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F111="",COUNT(AI111:AV111)=0),"",TODAY()-LOOKUP(2,1/(AI111:AV111<>""),AI111:AV111)) | IF(OR(F111="",COUNT(AI111:AV111)<2),"",LOOKUP(2,1/(AI111:AV111<>""),AI111:AV111)-MIN(AI111:AV111)) | IF(OR(AD111="",AC111="Not started",AC111=""),"",IFERROR(AD111-IF(VLOOKUP(AC111,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC111,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F111="","",IF(OR(AA111="Cancelled",AC111="Cancelled"),"Cancelled",IF(OR(AC111="Completed / Handover",Y111<>"",Z111>=100),"Completed — on track",IF(O111="Not awarded",IF(U111="",IF(X111="","No planned date",IF(TODAY()>X111,"Behind — past planned date",IF(X111-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U111,"Behind — award date passed",IF(U111-TODAY()<=30,"At risk — close to off track","On track"))),IF(X111="","No planned date",IF(AND(TODAY()>X111,OR(Z111="",Z111<100)),"Behind — past end date",IF(AND(T111<>"",X111<>"",Z111<>"",(Z111<100),((TODAY()-T111)/MAX(X111-T111,1)*100)-Z111>15),"Behind — progress lag",IF(AND(X111-TODAY()<=30,X111-TODAY()>=0,OR(Z111="",Z111<90)),"At risk — close to off track","On track")))))))) | IF(OR(F111="",AC111="Completed / Handover",AC111="Cancelled"),"",IF(O111="Not awarded",IF(U111<>"",U111-TODAY(),IF(X111="","",X111-TODAY())),IF(X111="","",X111-TODAY()))) | [14 empty] | IF(OR(F111="",AJ111=""),"",IF(COUNT(AI111:AI111)=0,"",AJ111-LOOKUP(2,1/(AI111:AI111<>""),AI111:AI111))) | IF(OR(F111="",AK111=""),"",IF(COUNT(AI111:AJ111)=0,"",AK111-LOOKUP(2,1/(AI111:AJ111<>""),AI111:AJ111))) | IF(OR(F111="",AL111=""),"",IF(COUNT(AI111:AK111)=0,"",AL111-LOOKUP(2,1/(AI111:AK111<>""),AI111:AK111))) | IF(OR(F111="",AM111=""),"",IF(COUNT(AI111:AL111)=0,"",AM111-LOOKUP(2,1/(AI111:AL111<>""),AI111:AL111))) | IF(OR(F111="",AN111=""),"",IF(COUNT(AI111:AM111)=0,"",AN111-LOOKUP(2,1/(AI111:AM111<>""),AI111:AM111))) | IF(OR(F111="",AO111=""),"",IF(COUNT(AI111:AN111)=0,"",AO111-LOOKUP(2,1/(AI111:AN111<>""),AI111:AN111))) | IF(OR(F111="",AP111=""),"",IF(COUNT(AI111:AO111)=0,"",AP111-LOOKUP(2,1/(AI111:AO111<>""),AI111:AO111))) | IF(OR(F111="",AQ111=""),"",IF(COUNT(AI111:AP111)=0,"",AQ111-LOOKUP(2,1/(AI111:AP111<>""),AI111:AP111))) | IF(OR(F111="",AR111=""),"",IF(COUNT(AI111:AQ111)=0,"",AR111-LOOKUP(2,1/(AI111:AQ111<>""),AI111:AQ111))) | IF(OR(F111="",AS111=""),"",IF(COUNT(AI111:AR111)=0,"",AS111-LOOKUP(2,1/(AI111:AR111<>""),AI111:AR111))) | IF(OR(F111="",AT111=""),"",IF(COUNT(AI111:AS111)=0,"",AT111-LOOKUP(2,1/(AI111:AS111<>""),AI111:AS111))) | IF(OR(F111="",AU111=""),"",IF(COUNT(AI111:AT111)=0,"",AU111-LOOKUP(2,1/(AI111:AT111<>""),AI111:AT111))) | IF(OR(F111="",AV111=""),"",IF(COUNT(AI111:AU111)=0,"",AV111-LOOKUP(2,1/(AI111:AU111<>""),AI111:AU111))) | IF(J111="","All_Provinces",IFERROR(VLOOKUP(J111,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K111="","All_Districts",IFERROR(VLOOKUP(K111,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F112="","",ROW()-3) | [18 empty] | IF(AQ112="","",AQ112) |  |  |  | IF(W112<>"",W112,IF(OR(T112="",V112=""),"",EDATE(T112,V112))) |  |  |  |  | IF(F112="","",IF(COUNT(AI112:AV112)=0,IF(AA112="","Not started",AA112),SUBSTITUTE(LOOKUP(2,1/(AI112:AV112<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F112="",COUNT(AI112:AV112)=0),"",TODAY()-LOOKUP(2,1/(AI112:AV112<>""),AI112:AV112)) | IF(OR(F112="",COUNT(AI112:AV112)<2),"",LOOKUP(2,1/(AI112:AV112<>""),AI112:AV112)-MIN(AI112:AV112)) | IF(OR(AD112="",AC112="Not started",AC112=""),"",IFERROR(AD112-IF(VLOOKUP(AC112,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC112,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F112="","",IF(OR(AA112="Cancelled",AC112="Cancelled"),"Cancelled",IF(OR(AC112="Completed / Handover",Y112<>"",Z112>=100),"Completed — on track",IF(O112="Not awarded",IF(U112="",IF(X112="","No planned date",IF(TODAY()>X112,"Behind — past planned date",IF(X112-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U112,"Behind — award date passed",IF(U112-TODAY()<=30,"At risk — close to off track","On track"))),IF(X112="","No planned date",IF(AND(TODAY()>X112,OR(Z112="",Z112<100)),"Behind — past end date",IF(AND(T112<>"",X112<>"",Z112<>"",(Z112<100),((TODAY()-T112)/MAX(X112-T112,1)*100)-Z112>15),"Behind — progress lag",IF(AND(X112-TODAY()<=30,X112-TODAY()>=0,OR(Z112="",Z112<90)),"At risk — close to off track","On track")))))))) | IF(OR(F112="",AC112="Completed / Handover",AC112="Cancelled"),"",IF(O112="Not awarded",IF(U112<>"",U112-TODAY(),IF(X112="","",X112-TODAY())),IF(X112="","",X112-TODAY()))) | [14 empty] | IF(OR(F112="",AJ112=""),"",IF(COUNT(AI112:AI112)=0,"",AJ112-LOOKUP(2,1/(AI112:AI112<>""),AI112:AI112))) | IF(OR(F112="",AK112=""),"",IF(COUNT(AI112:AJ112)=0,"",AK112-LOOKUP(2,1/(AI112:AJ112<>""),AI112:AJ112))) | IF(OR(F112="",AL112=""),"",IF(COUNT(AI112:AK112)=0,"",AL112-LOOKUP(2,1/(AI112:AK112<>""),AI112:AK112))) | IF(OR(F112="",AM112=""),"",IF(COUNT(AI112:AL112)=0,"",AM112-LOOKUP(2,1/(AI112:AL112<>""),AI112:AL112))) | IF(OR(F112="",AN112=""),"",IF(COUNT(AI112:AM112)=0,"",AN112-LOOKUP(2,1/(AI112:AM112<>""),AI112:AM112))) | IF(OR(F112="",AO112=""),"",IF(COUNT(AI112:AN112)=0,"",AO112-LOOKUP(2,1/(AI112:AN112<>""),AI112:AN112))) | IF(OR(F112="",AP112=""),"",IF(COUNT(AI112:AO112)=0,"",AP112-LOOKUP(2,1/(AI112:AO112<>""),AI112:AO112))) | IF(OR(F112="",AQ112=""),"",IF(COUNT(AI112:AP112)=0,"",AQ112-LOOKUP(2,1/(AI112:AP112<>""),AI112:AP112))) | IF(OR(F112="",AR112=""),"",IF(COUNT(AI112:AQ112)=0,"",AR112-LOOKUP(2,1/(AI112:AQ112<>""),AI112:AQ112))) | IF(OR(F112="",AS112=""),"",IF(COUNT(AI112:AR112)=0,"",AS112-LOOKUP(2,1/(AI112:AR112<>""),AI112:AR112))) | IF(OR(F112="",AT112=""),"",IF(COUNT(AI112:AS112)=0,"",AT112-LOOKUP(2,1/(AI112:AS112<>""),AI112:AS112))) | IF(OR(F112="",AU112=""),"",IF(COUNT(AI112:AT112)=0,"",AU112-LOOKUP(2,1/(AI112:AT112<>""),AI112:AT112))) | IF(OR(F112="",AV112=""),"",IF(COUNT(AI112:AU112)=0,"",AV112-LOOKUP(2,1/(AI112:AU112<>""),AI112:AU112))) | IF(J112="","All_Provinces",IFERROR(VLOOKUP(J112,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K112="","All_Districts",IFERROR(VLOOKUP(K112,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F113="","",ROW()-3) | [18 empty] | IF(AQ113="","",AQ113) |  |  |  | IF(W113<>"",W113,IF(OR(T113="",V113=""),"",EDATE(T113,V113))) |  |  |  |  | IF(F113="","",IF(COUNT(AI113:AV113)=0,IF(AA113="","Not started",AA113),SUBSTITUTE(LOOKUP(2,1/(AI113:AV113<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F113="",COUNT(AI113:AV113)=0),"",TODAY()-LOOKUP(2,1/(AI113:AV113<>""),AI113:AV113)) | IF(OR(F113="",COUNT(AI113:AV113)<2),"",LOOKUP(2,1/(AI113:AV113<>""),AI113:AV113)-MIN(AI113:AV113)) | IF(OR(AD113="",AC113="Not started",AC113=""),"",IFERROR(AD113-IF(VLOOKUP(AC113,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC113,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F113="","",IF(OR(AA113="Cancelled",AC113="Cancelled"),"Cancelled",IF(OR(AC113="Completed / Handover",Y113<>"",Z113>=100),"Completed — on track",IF(O113="Not awarded",IF(U113="",IF(X113="","No planned date",IF(TODAY()>X113,"Behind — past planned date",IF(X113-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U113,"Behind — award date passed",IF(U113-TODAY()<=30,"At risk — close to off track","On track"))),IF(X113="","No planned date",IF(AND(TODAY()>X113,OR(Z113="",Z113<100)),"Behind — past end date",IF(AND(T113<>"",X113<>"",Z113<>"",(Z113<100),((TODAY()-T113)/MAX(X113-T113,1)*100)-Z113>15),"Behind — progress lag",IF(AND(X113-TODAY()<=30,X113-TODAY()>=0,OR(Z113="",Z113<90)),"At risk — close to off track","On track")))))))) | IF(OR(F113="",AC113="Completed / Handover",AC113="Cancelled"),"",IF(O113="Not awarded",IF(U113<>"",U113-TODAY(),IF(X113="","",X113-TODAY())),IF(X113="","",X113-TODAY()))) | [14 empty] | IF(OR(F113="",AJ113=""),"",IF(COUNT(AI113:AI113)=0,"",AJ113-LOOKUP(2,1/(AI113:AI113<>""),AI113:AI113))) | IF(OR(F113="",AK113=""),"",IF(COUNT(AI113:AJ113)=0,"",AK113-LOOKUP(2,1/(AI113:AJ113<>""),AI113:AJ113))) | IF(OR(F113="",AL113=""),"",IF(COUNT(AI113:AK113)=0,"",AL113-LOOKUP(2,1/(AI113:AK113<>""),AI113:AK113))) | IF(OR(F113="",AM113=""),"",IF(COUNT(AI113:AL113)=0,"",AM113-LOOKUP(2,1/(AI113:AL113<>""),AI113:AL113))) | IF(OR(F113="",AN113=""),"",IF(COUNT(AI113:AM113)=0,"",AN113-LOOKUP(2,1/(AI113:AM113<>""),AI113:AM113))) | IF(OR(F113="",AO113=""),"",IF(COUNT(AI113:AN113)=0,"",AO113-LOOKUP(2,1/(AI113:AN113<>""),AI113:AN113))) | IF(OR(F113="",AP113=""),"",IF(COUNT(AI113:AO113)=0,"",AP113-LOOKUP(2,1/(AI113:AO113<>""),AI113:AO113))) | IF(OR(F113="",AQ113=""),"",IF(COUNT(AI113:AP113)=0,"",AQ113-LOOKUP(2,1/(AI113:AP113<>""),AI113:AP113))) | IF(OR(F113="",AR113=""),"",IF(COUNT(AI113:AQ113)=0,"",AR113-LOOKUP(2,1/(AI113:AQ113<>""),AI113:AQ113))) | IF(OR(F113="",AS113=""),"",IF(COUNT(AI113:AR113)=0,"",AS113-LOOKUP(2,1/(AI113:AR113<>""),AI113:AR113))) | IF(OR(F113="",AT113=""),"",IF(COUNT(AI113:AS113)=0,"",AT113-LOOKUP(2,1/(AI113:AS113<>""),AI113:AS113))) | IF(OR(F113="",AU113=""),"",IF(COUNT(AI113:AT113)=0,"",AU113-LOOKUP(2,1/(AI113:AT113<>""),AI113:AT113))) | IF(OR(F113="",AV113=""),"",IF(COUNT(AI113:AU113)=0,"",AV113-LOOKUP(2,1/(AI113:AU113<>""),AI113:AU113))) | IF(J113="","All_Provinces",IFERROR(VLOOKUP(J113,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K113="","All_Districts",IFERROR(VLOOKUP(K113,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F114="","",ROW()-3) | [18 empty] | IF(AQ114="","",AQ114) |  |  |  | IF(W114<>"",W114,IF(OR(T114="",V114=""),"",EDATE(T114,V114))) |  |  |  |  | IF(F114="","",IF(COUNT(AI114:AV114)=0,IF(AA114="","Not started",AA114),SUBSTITUTE(LOOKUP(2,1/(AI114:AV114<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F114="",COUNT(AI114:AV114)=0),"",TODAY()-LOOKUP(2,1/(AI114:AV114<>""),AI114:AV114)) | IF(OR(F114="",COUNT(AI114:AV114)<2),"",LOOKUP(2,1/(AI114:AV114<>""),AI114:AV114)-MIN(AI114:AV114)) | IF(OR(AD114="",AC114="Not started",AC114=""),"",IFERROR(AD114-IF(VLOOKUP(AC114,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC114,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F114="","",IF(OR(AA114="Cancelled",AC114="Cancelled"),"Cancelled",IF(OR(AC114="Completed / Handover",Y114<>"",Z114>=100),"Completed — on track",IF(O114="Not awarded",IF(U114="",IF(X114="","No planned date",IF(TODAY()>X114,"Behind — past planned date",IF(X114-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U114,"Behind — award date passed",IF(U114-TODAY()<=30,"At risk — close to off track","On track"))),IF(X114="","No planned date",IF(AND(TODAY()>X114,OR(Z114="",Z114<100)),"Behind — past end date",IF(AND(T114<>"",X114<>"",Z114<>"",(Z114<100),((TODAY()-T114)/MAX(X114-T114,1)*100)-Z114>15),"Behind — progress lag",IF(AND(X114-TODAY()<=30,X114-TODAY()>=0,OR(Z114="",Z114<90)),"At risk — close to off track","On track")))))))) | IF(OR(F114="",AC114="Completed / Handover",AC114="Cancelled"),"",IF(O114="Not awarded",IF(U114<>"",U114-TODAY(),IF(X114="","",X114-TODAY())),IF(X114="","",X114-TODAY()))) | [14 empty] | IF(OR(F114="",AJ114=""),"",IF(COUNT(AI114:AI114)=0,"",AJ114-LOOKUP(2,1/(AI114:AI114<>""),AI114:AI114))) | IF(OR(F114="",AK114=""),"",IF(COUNT(AI114:AJ114)=0,"",AK114-LOOKUP(2,1/(AI114:AJ114<>""),AI114:AJ114))) | IF(OR(F114="",AL114=""),"",IF(COUNT(AI114:AK114)=0,"",AL114-LOOKUP(2,1/(AI114:AK114<>""),AI114:AK114))) | IF(OR(F114="",AM114=""),"",IF(COUNT(AI114:AL114)=0,"",AM114-LOOKUP(2,1/(AI114:AL114<>""),AI114:AL114))) | IF(OR(F114="",AN114=""),"",IF(COUNT(AI114:AM114)=0,"",AN114-LOOKUP(2,1/(AI114:AM114<>""),AI114:AM114))) | IF(OR(F114="",AO114=""),"",IF(COUNT(AI114:AN114)=0,"",AO114-LOOKUP(2,1/(AI114:AN114<>""),AI114:AN114))) | IF(OR(F114="",AP114=""),"",IF(COUNT(AI114:AO114)=0,"",AP114-LOOKUP(2,1/(AI114:AO114<>""),AI114:AO114))) | IF(OR(F114="",AQ114=""),"",IF(COUNT(AI114:AP114)=0,"",AQ114-LOOKUP(2,1/(AI114:AP114<>""),AI114:AP114))) | IF(OR(F114="",AR114=""),"",IF(COUNT(AI114:AQ114)=0,"",AR114-LOOKUP(2,1/(AI114:AQ114<>""),AI114:AQ114))) | IF(OR(F114="",AS114=""),"",IF(COUNT(AI114:AR114)=0,"",AS114-LOOKUP(2,1/(AI114:AR114<>""),AI114:AR114))) | IF(OR(F114="",AT114=""),"",IF(COUNT(AI114:AS114)=0,"",AT114-LOOKUP(2,1/(AI114:AS114<>""),AI114:AS114))) | IF(OR(F114="",AU114=""),"",IF(COUNT(AI114:AT114)=0,"",AU114-LOOKUP(2,1/(AI114:AT114<>""),AI114:AT114))) | IF(OR(F114="",AV114=""),"",IF(COUNT(AI114:AU114)=0,"",AV114-LOOKUP(2,1/(AI114:AU114<>""),AI114:AU114))) | IF(J114="","All_Provinces",IFERROR(VLOOKUP(J114,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K114="","All_Districts",IFERROR(VLOOKUP(K114,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F115="","",ROW()-3) | [18 empty] | IF(AQ115="","",AQ115) |  |  |  | IF(W115<>"",W115,IF(OR(T115="",V115=""),"",EDATE(T115,V115))) |  |  |  |  | IF(F115="","",IF(COUNT(AI115:AV115)=0,IF(AA115="","Not started",AA115),SUBSTITUTE(LOOKUP(2,1/(AI115:AV115<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F115="",COUNT(AI115:AV115)=0),"",TODAY()-LOOKUP(2,1/(AI115:AV115<>""),AI115:AV115)) | IF(OR(F115="",COUNT(AI115:AV115)<2),"",LOOKUP(2,1/(AI115:AV115<>""),AI115:AV115)-MIN(AI115:AV115)) | IF(OR(AD115="",AC115="Not started",AC115=""),"",IFERROR(AD115-IF(VLOOKUP(AC115,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC115,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F115="","",IF(OR(AA115="Cancelled",AC115="Cancelled"),"Cancelled",IF(OR(AC115="Completed / Handover",Y115<>"",Z115>=100),"Completed — on track",IF(O115="Not awarded",IF(U115="",IF(X115="","No planned date",IF(TODAY()>X115,"Behind — past planned date",IF(X115-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U115,"Behind — award date passed",IF(U115-TODAY()<=30,"At risk — close to off track","On track"))),IF(X115="","No planned date",IF(AND(TODAY()>X115,OR(Z115="",Z115<100)),"Behind — past end date",IF(AND(T115<>"",X115<>"",Z115<>"",(Z115<100),((TODAY()-T115)/MAX(X115-T115,1)*100)-Z115>15),"Behind — progress lag",IF(AND(X115-TODAY()<=30,X115-TODAY()>=0,OR(Z115="",Z115<90)),"At risk — close to off track","On track")))))))) | IF(OR(F115="",AC115="Completed / Handover",AC115="Cancelled"),"",IF(O115="Not awarded",IF(U115<>"",U115-TODAY(),IF(X115="","",X115-TODAY())),IF(X115="","",X115-TODAY()))) | [14 empty] | IF(OR(F115="",AJ115=""),"",IF(COUNT(AI115:AI115)=0,"",AJ115-LOOKUP(2,1/(AI115:AI115<>""),AI115:AI115))) | IF(OR(F115="",AK115=""),"",IF(COUNT(AI115:AJ115)=0,"",AK115-LOOKUP(2,1/(AI115:AJ115<>""),AI115:AJ115))) | IF(OR(F115="",AL115=""),"",IF(COUNT(AI115:AK115)=0,"",AL115-LOOKUP(2,1/(AI115:AK115<>""),AI115:AK115))) | IF(OR(F115="",AM115=""),"",IF(COUNT(AI115:AL115)=0,"",AM115-LOOKUP(2,1/(AI115:AL115<>""),AI115:AL115))) | IF(OR(F115="",AN115=""),"",IF(COUNT(AI115:AM115)=0,"",AN115-LOOKUP(2,1/(AI115:AM115<>""),AI115:AM115))) | IF(OR(F115="",AO115=""),"",IF(COUNT(AI115:AN115)=0,"",AO115-LOOKUP(2,1/(AI115:AN115<>""),AI115:AN115))) | IF(OR(F115="",AP115=""),"",IF(COUNT(AI115:AO115)=0,"",AP115-LOOKUP(2,1/(AI115:AO115<>""),AI115:AO115))) | IF(OR(F115="",AQ115=""),"",IF(COUNT(AI115:AP115)=0,"",AQ115-LOOKUP(2,1/(AI115:AP115<>""),AI115:AP115))) | IF(OR(F115="",AR115=""),"",IF(COUNT(AI115:AQ115)=0,"",AR115-LOOKUP(2,1/(AI115:AQ115<>""),AI115:AQ115))) | IF(OR(F115="",AS115=""),"",IF(COUNT(AI115:AR115)=0,"",AS115-LOOKUP(2,1/(AI115:AR115<>""),AI115:AR115))) | IF(OR(F115="",AT115=""),"",IF(COUNT(AI115:AS115)=0,"",AT115-LOOKUP(2,1/(AI115:AS115<>""),AI115:AS115))) | IF(OR(F115="",AU115=""),"",IF(COUNT(AI115:AT115)=0,"",AU115-LOOKUP(2,1/(AI115:AT115<>""),AI115:AT115))) | IF(OR(F115="",AV115=""),"",IF(COUNT(AI115:AU115)=0,"",AV115-LOOKUP(2,1/(AI115:AU115<>""),AI115:AU115))) | IF(J115="","All_Provinces",IFERROR(VLOOKUP(J115,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K115="","All_Districts",IFERROR(VLOOKUP(K115,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F116="","",ROW()-3) | [18 empty] | IF(AQ116="","",AQ116) |  |  |  | IF(W116<>"",W116,IF(OR(T116="",V116=""),"",EDATE(T116,V116))) |  |  |  |  | IF(F116="","",IF(COUNT(AI116:AV116)=0,IF(AA116="","Not started",AA116),SUBSTITUTE(LOOKUP(2,1/(AI116:AV116<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F116="",COUNT(AI116:AV116)=0),"",TODAY()-LOOKUP(2,1/(AI116:AV116<>""),AI116:AV116)) | IF(OR(F116="",COUNT(AI116:AV116)<2),"",LOOKUP(2,1/(AI116:AV116<>""),AI116:AV116)-MIN(AI116:AV116)) | IF(OR(AD116="",AC116="Not started",AC116=""),"",IFERROR(AD116-IF(VLOOKUP(AC116,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC116,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F116="","",IF(OR(AA116="Cancelled",AC116="Cancelled"),"Cancelled",IF(OR(AC116="Completed / Handover",Y116<>"",Z116>=100),"Completed — on track",IF(O116="Not awarded",IF(U116="",IF(X116="","No planned date",IF(TODAY()>X116,"Behind — past planned date",IF(X116-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U116,"Behind — award date passed",IF(U116-TODAY()<=30,"At risk — close to off track","On track"))),IF(X116="","No planned date",IF(AND(TODAY()>X116,OR(Z116="",Z116<100)),"Behind — past end date",IF(AND(T116<>"",X116<>"",Z116<>"",(Z116<100),((TODAY()-T116)/MAX(X116-T116,1)*100)-Z116>15),"Behind — progress lag",IF(AND(X116-TODAY()<=30,X116-TODAY()>=0,OR(Z116="",Z116<90)),"At risk — close to off track","On track")))))))) | IF(OR(F116="",AC116="Completed / Handover",AC116="Cancelled"),"",IF(O116="Not awarded",IF(U116<>"",U116-TODAY(),IF(X116="","",X116-TODAY())),IF(X116="","",X116-TODAY()))) | [14 empty] | IF(OR(F116="",AJ116=""),"",IF(COUNT(AI116:AI116)=0,"",AJ116-LOOKUP(2,1/(AI116:AI116<>""),AI116:AI116))) | IF(OR(F116="",AK116=""),"",IF(COUNT(AI116:AJ116)=0,"",AK116-LOOKUP(2,1/(AI116:AJ116<>""),AI116:AJ116))) | IF(OR(F116="",AL116=""),"",IF(COUNT(AI116:AK116)=0,"",AL116-LOOKUP(2,1/(AI116:AK116<>""),AI116:AK116))) | IF(OR(F116="",AM116=""),"",IF(COUNT(AI116:AL116)=0,"",AM116-LOOKUP(2,1/(AI116:AL116<>""),AI116:AL116))) | IF(OR(F116="",AN116=""),"",IF(COUNT(AI116:AM116)=0,"",AN116-LOOKUP(2,1/(AI116:AM116<>""),AI116:AM116))) | IF(OR(F116="",AO116=""),"",IF(COUNT(AI116:AN116)=0,"",AO116-LOOKUP(2,1/(AI116:AN116<>""),AI116:AN116))) | IF(OR(F116="",AP116=""),"",IF(COUNT(AI116:AO116)=0,"",AP116-LOOKUP(2,1/(AI116:AO116<>""),AI116:AO116))) | IF(OR(F116="",AQ116=""),"",IF(COUNT(AI116:AP116)=0,"",AQ116-LOOKUP(2,1/(AI116:AP116<>""),AI116:AP116))) | IF(OR(F116="",AR116=""),"",IF(COUNT(AI116:AQ116)=0,"",AR116-LOOKUP(2,1/(AI116:AQ116<>""),AI116:AQ116))) | IF(OR(F116="",AS116=""),"",IF(COUNT(AI116:AR116)=0,"",AS116-LOOKUP(2,1/(AI116:AR116<>""),AI116:AR116))) | IF(OR(F116="",AT116=""),"",IF(COUNT(AI116:AS116)=0,"",AT116-LOOKUP(2,1/(AI116:AS116<>""),AI116:AS116))) | IF(OR(F116="",AU116=""),"",IF(COUNT(AI116:AT116)=0,"",AU116-LOOKUP(2,1/(AI116:AT116<>""),AI116:AT116))) | IF(OR(F116="",AV116=""),"",IF(COUNT(AI116:AU116)=0,"",AV116-LOOKUP(2,1/(AI116:AU116<>""),AI116:AU116))) | IF(J116="","All_Provinces",IFERROR(VLOOKUP(J116,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K116="","All_Districts",IFERROR(VLOOKUP(K116,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F117="","",ROW()-3) | [18 empty] | IF(AQ117="","",AQ117) |  |  |  | IF(W117<>"",W117,IF(OR(T117="",V117=""),"",EDATE(T117,V117))) |  |  |  |  | IF(F117="","",IF(COUNT(AI117:AV117)=0,IF(AA117="","Not started",AA117),SUBSTITUTE(LOOKUP(2,1/(AI117:AV117<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F117="",COUNT(AI117:AV117)=0),"",TODAY()-LOOKUP(2,1/(AI117:AV117<>""),AI117:AV117)) | IF(OR(F117="",COUNT(AI117:AV117)<2),"",LOOKUP(2,1/(AI117:AV117<>""),AI117:AV117)-MIN(AI117:AV117)) | IF(OR(AD117="",AC117="Not started",AC117=""),"",IFERROR(AD117-IF(VLOOKUP(AC117,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC117,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F117="","",IF(OR(AA117="Cancelled",AC117="Cancelled"),"Cancelled",IF(OR(AC117="Completed / Handover",Y117<>"",Z117>=100),"Completed — on track",IF(O117="Not awarded",IF(U117="",IF(X117="","No planned date",IF(TODAY()>X117,"Behind — past planned date",IF(X117-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U117,"Behind — award date passed",IF(U117-TODAY()<=30,"At risk — close to off track","On track"))),IF(X117="","No planned date",IF(AND(TODAY()>X117,OR(Z117="",Z117<100)),"Behind — past end date",IF(AND(T117<>"",X117<>"",Z117<>"",(Z117<100),((TODAY()-T117)/MAX(X117-T117,1)*100)-Z117>15),"Behind — progress lag",IF(AND(X117-TODAY()<=30,X117-TODAY()>=0,OR(Z117="",Z117<90)),"At risk — close to off track","On track")))))))) | IF(OR(F117="",AC117="Completed / Handover",AC117="Cancelled"),"",IF(O117="Not awarded",IF(U117<>"",U117-TODAY(),IF(X117="","",X117-TODAY())),IF(X117="","",X117-TODAY()))) | [14 empty] | IF(OR(F117="",AJ117=""),"",IF(COUNT(AI117:AI117)=0,"",AJ117-LOOKUP(2,1/(AI117:AI117<>""),AI117:AI117))) | IF(OR(F117="",AK117=""),"",IF(COUNT(AI117:AJ117)=0,"",AK117-LOOKUP(2,1/(AI117:AJ117<>""),AI117:AJ117))) | IF(OR(F117="",AL117=""),"",IF(COUNT(AI117:AK117)=0,"",AL117-LOOKUP(2,1/(AI117:AK117<>""),AI117:AK117))) | IF(OR(F117="",AM117=""),"",IF(COUNT(AI117:AL117)=0,"",AM117-LOOKUP(2,1/(AI117:AL117<>""),AI117:AL117))) | IF(OR(F117="",AN117=""),"",IF(COUNT(AI117:AM117)=0,"",AN117-LOOKUP(2,1/(AI117:AM117<>""),AI117:AM117))) | IF(OR(F117="",AO117=""),"",IF(COUNT(AI117:AN117)=0,"",AO117-LOOKUP(2,1/(AI117:AN117<>""),AI117:AN117))) | IF(OR(F117="",AP117=""),"",IF(COUNT(AI117:AO117)=0,"",AP117-LOOKUP(2,1/(AI117:AO117<>""),AI117:AO117))) | IF(OR(F117="",AQ117=""),"",IF(COUNT(AI117:AP117)=0,"",AQ117-LOOKUP(2,1/(AI117:AP117<>""),AI117:AP117))) | IF(OR(F117="",AR117=""),"",IF(COUNT(AI117:AQ117)=0,"",AR117-LOOKUP(2,1/(AI117:AQ117<>""),AI117:AQ117))) | IF(OR(F117="",AS117=""),"",IF(COUNT(AI117:AR117)=0,"",AS117-LOOKUP(2,1/(AI117:AR117<>""),AI117:AR117))) | IF(OR(F117="",AT117=""),"",IF(COUNT(AI117:AS117)=0,"",AT117-LOOKUP(2,1/(AI117:AS117<>""),AI117:AS117))) | IF(OR(F117="",AU117=""),"",IF(COUNT(AI117:AT117)=0,"",AU117-LOOKUP(2,1/(AI117:AT117<>""),AI117:AT117))) | IF(OR(F117="",AV117=""),"",IF(COUNT(AI117:AU117)=0,"",AV117-LOOKUP(2,1/(AI117:AU117<>""),AI117:AU117))) | IF(J117="","All_Provinces",IFERROR(VLOOKUP(J117,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K117="","All_Districts",IFERROR(VLOOKUP(K117,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F118="","",ROW()-3) | [18 empty] | IF(AQ118="","",AQ118) |  |  |  | IF(W118<>"",W118,IF(OR(T118="",V118=""),"",EDATE(T118,V118))) |  |  |  |  | IF(F118="","",IF(COUNT(AI118:AV118)=0,IF(AA118="","Not started",AA118),SUBSTITUTE(LOOKUP(2,1/(AI118:AV118<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F118="",COUNT(AI118:AV118)=0),"",TODAY()-LOOKUP(2,1/(AI118:AV118<>""),AI118:AV118)) | IF(OR(F118="",COUNT(AI118:AV118)<2),"",LOOKUP(2,1/(AI118:AV118<>""),AI118:AV118)-MIN(AI118:AV118)) | IF(OR(AD118="",AC118="Not started",AC118=""),"",IFERROR(AD118-IF(VLOOKUP(AC118,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC118,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F118="","",IF(OR(AA118="Cancelled",AC118="Cancelled"),"Cancelled",IF(OR(AC118="Completed / Handover",Y118<>"",Z118>=100),"Completed — on track",IF(O118="Not awarded",IF(U118="",IF(X118="","No planned date",IF(TODAY()>X118,"Behind — past planned date",IF(X118-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U118,"Behind — award date passed",IF(U118-TODAY()<=30,"At risk — close to off track","On track"))),IF(X118="","No planned date",IF(AND(TODAY()>X118,OR(Z118="",Z118<100)),"Behind — past end date",IF(AND(T118<>"",X118<>"",Z118<>"",(Z118<100),((TODAY()-T118)/MAX(X118-T118,1)*100)-Z118>15),"Behind — progress lag",IF(AND(X118-TODAY()<=30,X118-TODAY()>=0,OR(Z118="",Z118<90)),"At risk — close to off track","On track")))))))) | IF(OR(F118="",AC118="Completed / Handover",AC118="Cancelled"),"",IF(O118="Not awarded",IF(U118<>"",U118-TODAY(),IF(X118="","",X118-TODAY())),IF(X118="","",X118-TODAY()))) | [14 empty] | IF(OR(F118="",AJ118=""),"",IF(COUNT(AI118:AI118)=0,"",AJ118-LOOKUP(2,1/(AI118:AI118<>""),AI118:AI118))) | IF(OR(F118="",AK118=""),"",IF(COUNT(AI118:AJ118)=0,"",AK118-LOOKUP(2,1/(AI118:AJ118<>""),AI118:AJ118))) | IF(OR(F118="",AL118=""),"",IF(COUNT(AI118:AK118)=0,"",AL118-LOOKUP(2,1/(AI118:AK118<>""),AI118:AK118))) | IF(OR(F118="",AM118=""),"",IF(COUNT(AI118:AL118)=0,"",AM118-LOOKUP(2,1/(AI118:AL118<>""),AI118:AL118))) | IF(OR(F118="",AN118=""),"",IF(COUNT(AI118:AM118)=0,"",AN118-LOOKUP(2,1/(AI118:AM118<>""),AI118:AM118))) | IF(OR(F118="",AO118=""),"",IF(COUNT(AI118:AN118)=0,"",AO118-LOOKUP(2,1/(AI118:AN118<>""),AI118:AN118))) | IF(OR(F118="",AP118=""),"",IF(COUNT(AI118:AO118)=0,"",AP118-LOOKUP(2,1/(AI118:AO118<>""),AI118:AO118))) | IF(OR(F118="",AQ118=""),"",IF(COUNT(AI118:AP118)=0,"",AQ118-LOOKUP(2,1/(AI118:AP118<>""),AI118:AP118))) | IF(OR(F118="",AR118=""),"",IF(COUNT(AI118:AQ118)=0,"",AR118-LOOKUP(2,1/(AI118:AQ118<>""),AI118:AQ118))) | IF(OR(F118="",AS118=""),"",IF(COUNT(AI118:AR118)=0,"",AS118-LOOKUP(2,1/(AI118:AR118<>""),AI118:AR118))) | IF(OR(F118="",AT118=""),"",IF(COUNT(AI118:AS118)=0,"",AT118-LOOKUP(2,1/(AI118:AS118<>""),AI118:AS118))) | IF(OR(F118="",AU118=""),"",IF(COUNT(AI118:AT118)=0,"",AU118-LOOKUP(2,1/(AI118:AT118<>""),AI118:AT118))) | IF(OR(F118="",AV118=""),"",IF(COUNT(AI118:AU118)=0,"",AV118-LOOKUP(2,1/(AI118:AU118<>""),AI118:AU118))) | IF(J118="","All_Provinces",IFERROR(VLOOKUP(J118,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K118="","All_Districts",IFERROR(VLOOKUP(K118,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F119="","",ROW()-3) | [18 empty] | IF(AQ119="","",AQ119) |  |  |  | IF(W119<>"",W119,IF(OR(T119="",V119=""),"",EDATE(T119,V119))) |  |  |  |  | IF(F119="","",IF(COUNT(AI119:AV119)=0,IF(AA119="","Not started",AA119),SUBSTITUTE(LOOKUP(2,1/(AI119:AV119<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F119="",COUNT(AI119:AV119)=0),"",TODAY()-LOOKUP(2,1/(AI119:AV119<>""),AI119:AV119)) | IF(OR(F119="",COUNT(AI119:AV119)<2),"",LOOKUP(2,1/(AI119:AV119<>""),AI119:AV119)-MIN(AI119:AV119)) | IF(OR(AD119="",AC119="Not started",AC119=""),"",IFERROR(AD119-IF(VLOOKUP(AC119,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC119,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F119="","",IF(OR(AA119="Cancelled",AC119="Cancelled"),"Cancelled",IF(OR(AC119="Completed / Handover",Y119<>"",Z119>=100),"Completed — on track",IF(O119="Not awarded",IF(U119="",IF(X119="","No planned date",IF(TODAY()>X119,"Behind — past planned date",IF(X119-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U119,"Behind — award date passed",IF(U119-TODAY()<=30,"At risk — close to off track","On track"))),IF(X119="","No planned date",IF(AND(TODAY()>X119,OR(Z119="",Z119<100)),"Behind — past end date",IF(AND(T119<>"",X119<>"",Z119<>"",(Z119<100),((TODAY()-T119)/MAX(X119-T119,1)*100)-Z119>15),"Behind — progress lag",IF(AND(X119-TODAY()<=30,X119-TODAY()>=0,OR(Z119="",Z119<90)),"At risk — close to off track","On track")))))))) | IF(OR(F119="",AC119="Completed / Handover",AC119="Cancelled"),"",IF(O119="Not awarded",IF(U119<>"",U119-TODAY(),IF(X119="","",X119-TODAY())),IF(X119="","",X119-TODAY()))) | [14 empty] | IF(OR(F119="",AJ119=""),"",IF(COUNT(AI119:AI119)=0,"",AJ119-LOOKUP(2,1/(AI119:AI119<>""),AI119:AI119))) | IF(OR(F119="",AK119=""),"",IF(COUNT(AI119:AJ119)=0,"",AK119-LOOKUP(2,1/(AI119:AJ119<>""),AI119:AJ119))) | IF(OR(F119="",AL119=""),"",IF(COUNT(AI119:AK119)=0,"",AL119-LOOKUP(2,1/(AI119:AK119<>""),AI119:AK119))) | IF(OR(F119="",AM119=""),"",IF(COUNT(AI119:AL119)=0,"",AM119-LOOKUP(2,1/(AI119:AL119<>""),AI119:AL119))) | IF(OR(F119="",AN119=""),"",IF(COUNT(AI119:AM119)=0,"",AN119-LOOKUP(2,1/(AI119:AM119<>""),AI119:AM119))) | IF(OR(F119="",AO119=""),"",IF(COUNT(AI119:AN119)=0,"",AO119-LOOKUP(2,1/(AI119:AN119<>""),AI119:AN119))) | IF(OR(F119="",AP119=""),"",IF(COUNT(AI119:AO119)=0,"",AP119-LOOKUP(2,1/(AI119:AO119<>""),AI119:AO119))) | IF(OR(F119="",AQ119=""),"",IF(COUNT(AI119:AP119)=0,"",AQ119-LOOKUP(2,1/(AI119:AP119<>""),AI119:AP119))) | IF(OR(F119="",AR119=""),"",IF(COUNT(AI119:AQ119)=0,"",AR119-LOOKUP(2,1/(AI119:AQ119<>""),AI119:AQ119))) | IF(OR(F119="",AS119=""),"",IF(COUNT(AI119:AR119)=0,"",AS119-LOOKUP(2,1/(AI119:AR119<>""),AI119:AR119))) | IF(OR(F119="",AT119=""),"",IF(COUNT(AI119:AS119)=0,"",AT119-LOOKUP(2,1/(AI119:AS119<>""),AI119:AS119))) | IF(OR(F119="",AU119=""),"",IF(COUNT(AI119:AT119)=0,"",AU119-LOOKUP(2,1/(AI119:AT119<>""),AI119:AT119))) | IF(OR(F119="",AV119=""),"",IF(COUNT(AI119:AU119)=0,"",AV119-LOOKUP(2,1/(AI119:AU119<>""),AI119:AU119))) | IF(J119="","All_Provinces",IFERROR(VLOOKUP(J119,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K119="","All_Districts",IFERROR(VLOOKUP(K119,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F120="","",ROW()-3) | [18 empty] | IF(AQ120="","",AQ120) |  |  |  | IF(W120<>"",W120,IF(OR(T120="",V120=""),"",EDATE(T120,V120))) |  |  |  |  | IF(F120="","",IF(COUNT(AI120:AV120)=0,IF(AA120="","Not started",AA120),SUBSTITUTE(LOOKUP(2,1/(AI120:AV120<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F120="",COUNT(AI120:AV120)=0),"",TODAY()-LOOKUP(2,1/(AI120:AV120<>""),AI120:AV120)) | IF(OR(F120="",COUNT(AI120:AV120)<2),"",LOOKUP(2,1/(AI120:AV120<>""),AI120:AV120)-MIN(AI120:AV120)) | IF(OR(AD120="",AC120="Not started",AC120=""),"",IFERROR(AD120-IF(VLOOKUP(AC120,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC120,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F120="","",IF(OR(AA120="Cancelled",AC120="Cancelled"),"Cancelled",IF(OR(AC120="Completed / Handover",Y120<>"",Z120>=100),"Completed — on track",IF(O120="Not awarded",IF(U120="",IF(X120="","No planned date",IF(TODAY()>X120,"Behind — past planned date",IF(X120-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U120,"Behind — award date passed",IF(U120-TODAY()<=30,"At risk — close to off track","On track"))),IF(X120="","No planned date",IF(AND(TODAY()>X120,OR(Z120="",Z120<100)),"Behind — past end date",IF(AND(T120<>"",X120<>"",Z120<>"",(Z120<100),((TODAY()-T120)/MAX(X120-T120,1)*100)-Z120>15),"Behind — progress lag",IF(AND(X120-TODAY()<=30,X120-TODAY()>=0,OR(Z120="",Z120<90)),"At risk — close to off track","On track")))))))) | IF(OR(F120="",AC120="Completed / Handover",AC120="Cancelled"),"",IF(O120="Not awarded",IF(U120<>"",U120-TODAY(),IF(X120="","",X120-TODAY())),IF(X120="","",X120-TODAY()))) | [14 empty] | IF(OR(F120="",AJ120=""),"",IF(COUNT(AI120:AI120)=0,"",AJ120-LOOKUP(2,1/(AI120:AI120<>""),AI120:AI120))) | IF(OR(F120="",AK120=""),"",IF(COUNT(AI120:AJ120)=0,"",AK120-LOOKUP(2,1/(AI120:AJ120<>""),AI120:AJ120))) | IF(OR(F120="",AL120=""),"",IF(COUNT(AI120:AK120)=0,"",AL120-LOOKUP(2,1/(AI120:AK120<>""),AI120:AK120))) | IF(OR(F120="",AM120=""),"",IF(COUNT(AI120:AL120)=0,"",AM120-LOOKUP(2,1/(AI120:AL120<>""),AI120:AL120))) | IF(OR(F120="",AN120=""),"",IF(COUNT(AI120:AM120)=0,"",AN120-LOOKUP(2,1/(AI120:AM120<>""),AI120:AM120))) | IF(OR(F120="",AO120=""),"",IF(COUNT(AI120:AN120)=0,"",AO120-LOOKUP(2,1/(AI120:AN120<>""),AI120:AN120))) | IF(OR(F120="",AP120=""),"",IF(COUNT(AI120:AO120)=0,"",AP120-LOOKUP(2,1/(AI120:AO120<>""),AI120:AO120))) | IF(OR(F120="",AQ120=""),"",IF(COUNT(AI120:AP120)=0,"",AQ120-LOOKUP(2,1/(AI120:AP120<>""),AI120:AP120))) | IF(OR(F120="",AR120=""),"",IF(COUNT(AI120:AQ120)=0,"",AR120-LOOKUP(2,1/(AI120:AQ120<>""),AI120:AQ120))) | IF(OR(F120="",AS120=""),"",IF(COUNT(AI120:AR120)=0,"",AS120-LOOKUP(2,1/(AI120:AR120<>""),AI120:AR120))) | IF(OR(F120="",AT120=""),"",IF(COUNT(AI120:AS120)=0,"",AT120-LOOKUP(2,1/(AI120:AS120<>""),AI120:AS120))) | IF(OR(F120="",AU120=""),"",IF(COUNT(AI120:AT120)=0,"",AU120-LOOKUP(2,1/(AI120:AT120<>""),AI120:AT120))) | IF(OR(F120="",AV120=""),"",IF(COUNT(AI120:AU120)=0,"",AV120-LOOKUP(2,1/(AI120:AU120<>""),AI120:AU120))) | IF(J120="","All_Provinces",IFERROR(VLOOKUP(J120,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K120="","All_Districts",IFERROR(VLOOKUP(K120,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F121="","",ROW()-3) | [18 empty] | IF(AQ121="","",AQ121) |  |  |  | IF(W121<>"",W121,IF(OR(T121="",V121=""),"",EDATE(T121,V121))) |  |  |  |  | IF(F121="","",IF(COUNT(AI121:AV121)=0,IF(AA121="","Not started",AA121),SUBSTITUTE(LOOKUP(2,1/(AI121:AV121<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F121="",COUNT(AI121:AV121)=0),"",TODAY()-LOOKUP(2,1/(AI121:AV121<>""),AI121:AV121)) | IF(OR(F121="",COUNT(AI121:AV121)<2),"",LOOKUP(2,1/(AI121:AV121<>""),AI121:AV121)-MIN(AI121:AV121)) | IF(OR(AD121="",AC121="Not started",AC121=""),"",IFERROR(AD121-IF(VLOOKUP(AC121,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC121,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F121="","",IF(OR(AA121="Cancelled",AC121="Cancelled"),"Cancelled",IF(OR(AC121="Completed / Handover",Y121<>"",Z121>=100),"Completed — on track",IF(O121="Not awarded",IF(U121="",IF(X121="","No planned date",IF(TODAY()>X121,"Behind — past planned date",IF(X121-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U121,"Behind — award date passed",IF(U121-TODAY()<=30,"At risk — close to off track","On track"))),IF(X121="","No planned date",IF(AND(TODAY()>X121,OR(Z121="",Z121<100)),"Behind — past end date",IF(AND(T121<>"",X121<>"",Z121<>"",(Z121<100),((TODAY()-T121)/MAX(X121-T121,1)*100)-Z121>15),"Behind — progress lag",IF(AND(X121-TODAY()<=30,X121-TODAY()>=0,OR(Z121="",Z121<90)),"At risk — close to off track","On track")))))))) | IF(OR(F121="",AC121="Completed / Handover",AC121="Cancelled"),"",IF(O121="Not awarded",IF(U121<>"",U121-TODAY(),IF(X121="","",X121-TODAY())),IF(X121="","",X121-TODAY()))) | [14 empty] | IF(OR(F121="",AJ121=""),"",IF(COUNT(AI121:AI121)=0,"",AJ121-LOOKUP(2,1/(AI121:AI121<>""),AI121:AI121))) | IF(OR(F121="",AK121=""),"",IF(COUNT(AI121:AJ121)=0,"",AK121-LOOKUP(2,1/(AI121:AJ121<>""),AI121:AJ121))) | IF(OR(F121="",AL121=""),"",IF(COUNT(AI121:AK121)=0,"",AL121-LOOKUP(2,1/(AI121:AK121<>""),AI121:AK121))) | IF(OR(F121="",AM121=""),"",IF(COUNT(AI121:AL121)=0,"",AM121-LOOKUP(2,1/(AI121:AL121<>""),AI121:AL121))) | IF(OR(F121="",AN121=""),"",IF(COUNT(AI121:AM121)=0,"",AN121-LOOKUP(2,1/(AI121:AM121<>""),AI121:AM121))) | IF(OR(F121="",AO121=""),"",IF(COUNT(AI121:AN121)=0,"",AO121-LOOKUP(2,1/(AI121:AN121<>""),AI121:AN121))) | IF(OR(F121="",AP121=""),"",IF(COUNT(AI121:AO121)=0,"",AP121-LOOKUP(2,1/(AI121:AO121<>""),AI121:AO121))) | IF(OR(F121="",AQ121=""),"",IF(COUNT(AI121:AP121)=0,"",AQ121-LOOKUP(2,1/(AI121:AP121<>""),AI121:AP121))) | IF(OR(F121="",AR121=""),"",IF(COUNT(AI121:AQ121)=0,"",AR121-LOOKUP(2,1/(AI121:AQ121<>""),AI121:AQ121))) | IF(OR(F121="",AS121=""),"",IF(COUNT(AI121:AR121)=0,"",AS121-LOOKUP(2,1/(AI121:AR121<>""),AI121:AR121))) | IF(OR(F121="",AT121=""),"",IF(COUNT(AI121:AS121)=0,"",AT121-LOOKUP(2,1/(AI121:AS121<>""),AI121:AS121))) | IF(OR(F121="",AU121=""),"",IF(COUNT(AI121:AT121)=0,"",AU121-LOOKUP(2,1/(AI121:AT121<>""),AI121:AT121))) | IF(OR(F121="",AV121=""),"",IF(COUNT(AI121:AU121)=0,"",AV121-LOOKUP(2,1/(AI121:AU121<>""),AI121:AU121))) | IF(J121="","All_Provinces",IFERROR(VLOOKUP(J121,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K121="","All_Districts",IFERROR(VLOOKUP(K121,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F122="","",ROW()-3) | [18 empty] | IF(AQ122="","",AQ122) |  |  |  | IF(W122<>"",W122,IF(OR(T122="",V122=""),"",EDATE(T122,V122))) |  |  |  |  | IF(F122="","",IF(COUNT(AI122:AV122)=0,IF(AA122="","Not started",AA122),SUBSTITUTE(LOOKUP(2,1/(AI122:AV122<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F122="",COUNT(AI122:AV122)=0),"",TODAY()-LOOKUP(2,1/(AI122:AV122<>""),AI122:AV122)) | IF(OR(F122="",COUNT(AI122:AV122)<2),"",LOOKUP(2,1/(AI122:AV122<>""),AI122:AV122)-MIN(AI122:AV122)) | IF(OR(AD122="",AC122="Not started",AC122=""),"",IFERROR(AD122-IF(VLOOKUP(AC122,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC122,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F122="","",IF(OR(AA122="Cancelled",AC122="Cancelled"),"Cancelled",IF(OR(AC122="Completed / Handover",Y122<>"",Z122>=100),"Completed — on track",IF(O122="Not awarded",IF(U122="",IF(X122="","No planned date",IF(TODAY()>X122,"Behind — past planned date",IF(X122-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U122,"Behind — award date passed",IF(U122-TODAY()<=30,"At risk — close to off track","On track"))),IF(X122="","No planned date",IF(AND(TODAY()>X122,OR(Z122="",Z122<100)),"Behind — past end date",IF(AND(T122<>"",X122<>"",Z122<>"",(Z122<100),((TODAY()-T122)/MAX(X122-T122,1)*100)-Z122>15),"Behind — progress lag",IF(AND(X122-TODAY()<=30,X122-TODAY()>=0,OR(Z122="",Z122<90)),"At risk — close to off track","On track")))))))) | IF(OR(F122="",AC122="Completed / Handover",AC122="Cancelled"),"",IF(O122="Not awarded",IF(U122<>"",U122-TODAY(),IF(X122="","",X122-TODAY())),IF(X122="","",X122-TODAY()))) | [14 empty] | IF(OR(F122="",AJ122=""),"",IF(COUNT(AI122:AI122)=0,"",AJ122-LOOKUP(2,1/(AI122:AI122<>""),AI122:AI122))) | IF(OR(F122="",AK122=""),"",IF(COUNT(AI122:AJ122)=0,"",AK122-LOOKUP(2,1/(AI122:AJ122<>""),AI122:AJ122))) | IF(OR(F122="",AL122=""),"",IF(COUNT(AI122:AK122)=0,"",AL122-LOOKUP(2,1/(AI122:AK122<>""),AI122:AK122))) | IF(OR(F122="",AM122=""),"",IF(COUNT(AI122:AL122)=0,"",AM122-LOOKUP(2,1/(AI122:AL122<>""),AI122:AL122))) | IF(OR(F122="",AN122=""),"",IF(COUNT(AI122:AM122)=0,"",AN122-LOOKUP(2,1/(AI122:AM122<>""),AI122:AM122))) | IF(OR(F122="",AO122=""),"",IF(COUNT(AI122:AN122)=0,"",AO122-LOOKUP(2,1/(AI122:AN122<>""),AI122:AN122))) | IF(OR(F122="",AP122=""),"",IF(COUNT(AI122:AO122)=0,"",AP122-LOOKUP(2,1/(AI122:AO122<>""),AI122:AO122))) | IF(OR(F122="",AQ122=""),"",IF(COUNT(AI122:AP122)=0,"",AQ122-LOOKUP(2,1/(AI122:AP122<>""),AI122:AP122))) | IF(OR(F122="",AR122=""),"",IF(COUNT(AI122:AQ122)=0,"",AR122-LOOKUP(2,1/(AI122:AQ122<>""),AI122:AQ122))) | IF(OR(F122="",AS122=""),"",IF(COUNT(AI122:AR122)=0,"",AS122-LOOKUP(2,1/(AI122:AR122<>""),AI122:AR122))) | IF(OR(F122="",AT122=""),"",IF(COUNT(AI122:AS122)=0,"",AT122-LOOKUP(2,1/(AI122:AS122<>""),AI122:AS122))) | IF(OR(F122="",AU122=""),"",IF(COUNT(AI122:AT122)=0,"",AU122-LOOKUP(2,1/(AI122:AT122<>""),AI122:AT122))) | IF(OR(F122="",AV122=""),"",IF(COUNT(AI122:AU122)=0,"",AV122-LOOKUP(2,1/(AI122:AU122<>""),AI122:AU122))) | IF(J122="","All_Provinces",IFERROR(VLOOKUP(J122,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K122="","All_Districts",IFERROR(VLOOKUP(K122,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F123="","",ROW()-3) | [18 empty] | IF(AQ123="","",AQ123) |  |  |  | IF(W123<>"",W123,IF(OR(T123="",V123=""),"",EDATE(T123,V123))) |  |  |  |  | IF(F123="","",IF(COUNT(AI123:AV123)=0,IF(AA123="","Not started",AA123),SUBSTITUTE(LOOKUP(2,1/(AI123:AV123<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F123="",COUNT(AI123:AV123)=0),"",TODAY()-LOOKUP(2,1/(AI123:AV123<>""),AI123:AV123)) | IF(OR(F123="",COUNT(AI123:AV123)<2),"",LOOKUP(2,1/(AI123:AV123<>""),AI123:AV123)-MIN(AI123:AV123)) | IF(OR(AD123="",AC123="Not started",AC123=""),"",IFERROR(AD123-IF(VLOOKUP(AC123,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC123,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F123="","",IF(OR(AA123="Cancelled",AC123="Cancelled"),"Cancelled",IF(OR(AC123="Completed / Handover",Y123<>"",Z123>=100),"Completed — on track",IF(O123="Not awarded",IF(U123="",IF(X123="","No planned date",IF(TODAY()>X123,"Behind — past planned date",IF(X123-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U123,"Behind — award date passed",IF(U123-TODAY()<=30,"At risk — close to off track","On track"))),IF(X123="","No planned date",IF(AND(TODAY()>X123,OR(Z123="",Z123<100)),"Behind — past end date",IF(AND(T123<>"",X123<>"",Z123<>"",(Z123<100),((TODAY()-T123)/MAX(X123-T123,1)*100)-Z123>15),"Behind — progress lag",IF(AND(X123-TODAY()<=30,X123-TODAY()>=0,OR(Z123="",Z123<90)),"At risk — close to off track","On track")))))))) | IF(OR(F123="",AC123="Completed / Handover",AC123="Cancelled"),"",IF(O123="Not awarded",IF(U123<>"",U123-TODAY(),IF(X123="","",X123-TODAY())),IF(X123="","",X123-TODAY()))) | [14 empty] | IF(OR(F123="",AJ123=""),"",IF(COUNT(AI123:AI123)=0,"",AJ123-LOOKUP(2,1/(AI123:AI123<>""),AI123:AI123))) | IF(OR(F123="",AK123=""),"",IF(COUNT(AI123:AJ123)=0,"",AK123-LOOKUP(2,1/(AI123:AJ123<>""),AI123:AJ123))) | IF(OR(F123="",AL123=""),"",IF(COUNT(AI123:AK123)=0,"",AL123-LOOKUP(2,1/(AI123:AK123<>""),AI123:AK123))) | IF(OR(F123="",AM123=""),"",IF(COUNT(AI123:AL123)=0,"",AM123-LOOKUP(2,1/(AI123:AL123<>""),AI123:AL123))) | IF(OR(F123="",AN123=""),"",IF(COUNT(AI123:AM123)=0,"",AN123-LOOKUP(2,1/(AI123:AM123<>""),AI123:AM123))) | IF(OR(F123="",AO123=""),"",IF(COUNT(AI123:AN123)=0,"",AO123-LOOKUP(2,1/(AI123:AN123<>""),AI123:AN123))) | IF(OR(F123="",AP123=""),"",IF(COUNT(AI123:AO123)=0,"",AP123-LOOKUP(2,1/(AI123:AO123<>""),AI123:AO123))) | IF(OR(F123="",AQ123=""),"",IF(COUNT(AI123:AP123)=0,"",AQ123-LOOKUP(2,1/(AI123:AP123<>""),AI123:AP123))) | IF(OR(F123="",AR123=""),"",IF(COUNT(AI123:AQ123)=0,"",AR123-LOOKUP(2,1/(AI123:AQ123<>""),AI123:AQ123))) | IF(OR(F123="",AS123=""),"",IF(COUNT(AI123:AR123)=0,"",AS123-LOOKUP(2,1/(AI123:AR123<>""),AI123:AR123))) | IF(OR(F123="",AT123=""),"",IF(COUNT(AI123:AS123)=0,"",AT123-LOOKUP(2,1/(AI123:AS123<>""),AI123:AS123))) | IF(OR(F123="",AU123=""),"",IF(COUNT(AI123:AT123)=0,"",AU123-LOOKUP(2,1/(AI123:AT123<>""),AI123:AT123))) | IF(OR(F123="",AV123=""),"",IF(COUNT(AI123:AU123)=0,"",AV123-LOOKUP(2,1/(AI123:AU123<>""),AI123:AU123))) | IF(J123="","All_Provinces",IFERROR(VLOOKUP(J123,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K123="","All_Districts",IFERROR(VLOOKUP(K123,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F124="","",ROW()-3) | [18 empty] | IF(AQ124="","",AQ124) |  |  |  | IF(W124<>"",W124,IF(OR(T124="",V124=""),"",EDATE(T124,V124))) |  |  |  |  | IF(F124="","",IF(COUNT(AI124:AV124)=0,IF(AA124="","Not started",AA124),SUBSTITUTE(LOOKUP(2,1/(AI124:AV124<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F124="",COUNT(AI124:AV124)=0),"",TODAY()-LOOKUP(2,1/(AI124:AV124<>""),AI124:AV124)) | IF(OR(F124="",COUNT(AI124:AV124)<2),"",LOOKUP(2,1/(AI124:AV124<>""),AI124:AV124)-MIN(AI124:AV124)) | IF(OR(AD124="",AC124="Not started",AC124=""),"",IFERROR(AD124-IF(VLOOKUP(AC124,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC124,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F124="","",IF(OR(AA124="Cancelled",AC124="Cancelled"),"Cancelled",IF(OR(AC124="Completed / Handover",Y124<>"",Z124>=100),"Completed — on track",IF(O124="Not awarded",IF(U124="",IF(X124="","No planned date",IF(TODAY()>X124,"Behind — past planned date",IF(X124-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U124,"Behind — award date passed",IF(U124-TODAY()<=30,"At risk — close to off track","On track"))),IF(X124="","No planned date",IF(AND(TODAY()>X124,OR(Z124="",Z124<100)),"Behind — past end date",IF(AND(T124<>"",X124<>"",Z124<>"",(Z124<100),((TODAY()-T124)/MAX(X124-T124,1)*100)-Z124>15),"Behind — progress lag",IF(AND(X124-TODAY()<=30,X124-TODAY()>=0,OR(Z124="",Z124<90)),"At risk — close to off track","On track")))))))) | IF(OR(F124="",AC124="Completed / Handover",AC124="Cancelled"),"",IF(O124="Not awarded",IF(U124<>"",U124-TODAY(),IF(X124="","",X124-TODAY())),IF(X124="","",X124-TODAY()))) | [14 empty] | IF(OR(F124="",AJ124=""),"",IF(COUNT(AI124:AI124)=0,"",AJ124-LOOKUP(2,1/(AI124:AI124<>""),AI124:AI124))) | IF(OR(F124="",AK124=""),"",IF(COUNT(AI124:AJ124)=0,"",AK124-LOOKUP(2,1/(AI124:AJ124<>""),AI124:AJ124))) | IF(OR(F124="",AL124=""),"",IF(COUNT(AI124:AK124)=0,"",AL124-LOOKUP(2,1/(AI124:AK124<>""),AI124:AK124))) | IF(OR(F124="",AM124=""),"",IF(COUNT(AI124:AL124)=0,"",AM124-LOOKUP(2,1/(AI124:AL124<>""),AI124:AL124))) | IF(OR(F124="",AN124=""),"",IF(COUNT(AI124:AM124)=0,"",AN124-LOOKUP(2,1/(AI124:AM124<>""),AI124:AM124))) | IF(OR(F124="",AO124=""),"",IF(COUNT(AI124:AN124)=0,"",AO124-LOOKUP(2,1/(AI124:AN124<>""),AI124:AN124))) | IF(OR(F124="",AP124=""),"",IF(COUNT(AI124:AO124)=0,"",AP124-LOOKUP(2,1/(AI124:AO124<>""),AI124:AO124))) | IF(OR(F124="",AQ124=""),"",IF(COUNT(AI124:AP124)=0,"",AQ124-LOOKUP(2,1/(AI124:AP124<>""),AI124:AP124))) | IF(OR(F124="",AR124=""),"",IF(COUNT(AI124:AQ124)=0,"",AR124-LOOKUP(2,1/(AI124:AQ124<>""),AI124:AQ124))) | IF(OR(F124="",AS124=""),"",IF(COUNT(AI124:AR124)=0,"",AS124-LOOKUP(2,1/(AI124:AR124<>""),AI124:AR124))) | IF(OR(F124="",AT124=""),"",IF(COUNT(AI124:AS124)=0,"",AT124-LOOKUP(2,1/(AI124:AS124<>""),AI124:AS124))) | IF(OR(F124="",AU124=""),"",IF(COUNT(AI124:AT124)=0,"",AU124-LOOKUP(2,1/(AI124:AT124<>""),AI124:AT124))) | IF(OR(F124="",AV124=""),"",IF(COUNT(AI124:AU124)=0,"",AV124-LOOKUP(2,1/(AI124:AU124<>""),AI124:AU124))) | IF(J124="","All_Provinces",IFERROR(VLOOKUP(J124,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K124="","All_Districts",IFERROR(VLOOKUP(K124,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F125="","",ROW()-3) | [18 empty] | IF(AQ125="","",AQ125) |  |  |  | IF(W125<>"",W125,IF(OR(T125="",V125=""),"",EDATE(T125,V125))) |  |  |  |  | IF(F125="","",IF(COUNT(AI125:AV125)=0,IF(AA125="","Not started",AA125),SUBSTITUTE(LOOKUP(2,1/(AI125:AV125<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F125="",COUNT(AI125:AV125)=0),"",TODAY()-LOOKUP(2,1/(AI125:AV125<>""),AI125:AV125)) | IF(OR(F125="",COUNT(AI125:AV125)<2),"",LOOKUP(2,1/(AI125:AV125<>""),AI125:AV125)-MIN(AI125:AV125)) | IF(OR(AD125="",AC125="Not started",AC125=""),"",IFERROR(AD125-IF(VLOOKUP(AC125,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC125,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F125="","",IF(OR(AA125="Cancelled",AC125="Cancelled"),"Cancelled",IF(OR(AC125="Completed / Handover",Y125<>"",Z125>=100),"Completed — on track",IF(O125="Not awarded",IF(U125="",IF(X125="","No planned date",IF(TODAY()>X125,"Behind — past planned date",IF(X125-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U125,"Behind — award date passed",IF(U125-TODAY()<=30,"At risk — close to off track","On track"))),IF(X125="","No planned date",IF(AND(TODAY()>X125,OR(Z125="",Z125<100)),"Behind — past end date",IF(AND(T125<>"",X125<>"",Z125<>"",(Z125<100),((TODAY()-T125)/MAX(X125-T125,1)*100)-Z125>15),"Behind — progress lag",IF(AND(X125-TODAY()<=30,X125-TODAY()>=0,OR(Z125="",Z125<90)),"At risk — close to off track","On track")))))))) | IF(OR(F125="",AC125="Completed / Handover",AC125="Cancelled"),"",IF(O125="Not awarded",IF(U125<>"",U125-TODAY(),IF(X125="","",X125-TODAY())),IF(X125="","",X125-TODAY()))) | [14 empty] | IF(OR(F125="",AJ125=""),"",IF(COUNT(AI125:AI125)=0,"",AJ125-LOOKUP(2,1/(AI125:AI125<>""),AI125:AI125))) | IF(OR(F125="",AK125=""),"",IF(COUNT(AI125:AJ125)=0,"",AK125-LOOKUP(2,1/(AI125:AJ125<>""),AI125:AJ125))) | IF(OR(F125="",AL125=""),"",IF(COUNT(AI125:AK125)=0,"",AL125-LOOKUP(2,1/(AI125:AK125<>""),AI125:AK125))) | IF(OR(F125="",AM125=""),"",IF(COUNT(AI125:AL125)=0,"",AM125-LOOKUP(2,1/(AI125:AL125<>""),AI125:AL125))) | IF(OR(F125="",AN125=""),"",IF(COUNT(AI125:AM125)=0,"",AN125-LOOKUP(2,1/(AI125:AM125<>""),AI125:AM125))) | IF(OR(F125="",AO125=""),"",IF(COUNT(AI125:AN125)=0,"",AO125-LOOKUP(2,1/(AI125:AN125<>""),AI125:AN125))) | IF(OR(F125="",AP125=""),"",IF(COUNT(AI125:AO125)=0,"",AP125-LOOKUP(2,1/(AI125:AO125<>""),AI125:AO125))) | IF(OR(F125="",AQ125=""),"",IF(COUNT(AI125:AP125)=0,"",AQ125-LOOKUP(2,1/(AI125:AP125<>""),AI125:AP125))) | IF(OR(F125="",AR125=""),"",IF(COUNT(AI125:AQ125)=0,"",AR125-LOOKUP(2,1/(AI125:AQ125<>""),AI125:AQ125))) | IF(OR(F125="",AS125=""),"",IF(COUNT(AI125:AR125)=0,"",AS125-LOOKUP(2,1/(AI125:AR125<>""),AI125:AR125))) | IF(OR(F125="",AT125=""),"",IF(COUNT(AI125:AS125)=0,"",AT125-LOOKUP(2,1/(AI125:AS125<>""),AI125:AS125))) | IF(OR(F125="",AU125=""),"",IF(COUNT(AI125:AT125)=0,"",AU125-LOOKUP(2,1/(AI125:AT125<>""),AI125:AT125))) | IF(OR(F125="",AV125=""),"",IF(COUNT(AI125:AU125)=0,"",AV125-LOOKUP(2,1/(AI125:AU125<>""),AI125:AU125))) | IF(J125="","All_Provinces",IFERROR(VLOOKUP(J125,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K125="","All_Districts",IFERROR(VLOOKUP(K125,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F126="","",ROW()-3) | [18 empty] | IF(AQ126="","",AQ126) |  |  |  | IF(W126<>"",W126,IF(OR(T126="",V126=""),"",EDATE(T126,V126))) |  |  |  |  | IF(F126="","",IF(COUNT(AI126:AV126)=0,IF(AA126="","Not started",AA126),SUBSTITUTE(LOOKUP(2,1/(AI126:AV126<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F126="",COUNT(AI126:AV126)=0),"",TODAY()-LOOKUP(2,1/(AI126:AV126<>""),AI126:AV126)) | IF(OR(F126="",COUNT(AI126:AV126)<2),"",LOOKUP(2,1/(AI126:AV126<>""),AI126:AV126)-MIN(AI126:AV126)) | IF(OR(AD126="",AC126="Not started",AC126=""),"",IFERROR(AD126-IF(VLOOKUP(AC126,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC126,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F126="","",IF(OR(AA126="Cancelled",AC126="Cancelled"),"Cancelled",IF(OR(AC126="Completed / Handover",Y126<>"",Z126>=100),"Completed — on track",IF(O126="Not awarded",IF(U126="",IF(X126="","No planned date",IF(TODAY()>X126,"Behind — past planned date",IF(X126-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U126,"Behind — award date passed",IF(U126-TODAY()<=30,"At risk — close to off track","On track"))),IF(X126="","No planned date",IF(AND(TODAY()>X126,OR(Z126="",Z126<100)),"Behind — past end date",IF(AND(T126<>"",X126<>"",Z126<>"",(Z126<100),((TODAY()-T126)/MAX(X126-T126,1)*100)-Z126>15),"Behind — progress lag",IF(AND(X126-TODAY()<=30,X126-TODAY()>=0,OR(Z126="",Z126<90)),"At risk — close to off track","On track")))))))) | IF(OR(F126="",AC126="Completed / Handover",AC126="Cancelled"),"",IF(O126="Not awarded",IF(U126<>"",U126-TODAY(),IF(X126="","",X126-TODAY())),IF(X126="","",X126-TODAY()))) | [14 empty] | IF(OR(F126="",AJ126=""),"",IF(COUNT(AI126:AI126)=0,"",AJ126-LOOKUP(2,1/(AI126:AI126<>""),AI126:AI126))) | IF(OR(F126="",AK126=""),"",IF(COUNT(AI126:AJ126)=0,"",AK126-LOOKUP(2,1/(AI126:AJ126<>""),AI126:AJ126))) | IF(OR(F126="",AL126=""),"",IF(COUNT(AI126:AK126)=0,"",AL126-LOOKUP(2,1/(AI126:AK126<>""),AI126:AK126))) | IF(OR(F126="",AM126=""),"",IF(COUNT(AI126:AL126)=0,"",AM126-LOOKUP(2,1/(AI126:AL126<>""),AI126:AL126))) | IF(OR(F126="",AN126=""),"",IF(COUNT(AI126:AM126)=0,"",AN126-LOOKUP(2,1/(AI126:AM126<>""),AI126:AM126))) | IF(OR(F126="",AO126=""),"",IF(COUNT(AI126:AN126)=0,"",AO126-LOOKUP(2,1/(AI126:AN126<>""),AI126:AN126))) | IF(OR(F126="",AP126=""),"",IF(COUNT(AI126:AO126)=0,"",AP126-LOOKUP(2,1/(AI126:AO126<>""),AI126:AO126))) | IF(OR(F126="",AQ126=""),"",IF(COUNT(AI126:AP126)=0,"",AQ126-LOOKUP(2,1/(AI126:AP126<>""),AI126:AP126))) | IF(OR(F126="",AR126=""),"",IF(COUNT(AI126:AQ126)=0,"",AR126-LOOKUP(2,1/(AI126:AQ126<>""),AI126:AQ126))) | IF(OR(F126="",AS126=""),"",IF(COUNT(AI126:AR126)=0,"",AS126-LOOKUP(2,1/(AI126:AR126<>""),AI126:AR126))) | IF(OR(F126="",AT126=""),"",IF(COUNT(AI126:AS126)=0,"",AT126-LOOKUP(2,1/(AI126:AS126<>""),AI126:AS126))) | IF(OR(F126="",AU126=""),"",IF(COUNT(AI126:AT126)=0,"",AU126-LOOKUP(2,1/(AI126:AT126<>""),AI126:AT126))) | IF(OR(F126="",AV126=""),"",IF(COUNT(AI126:AU126)=0,"",AV126-LOOKUP(2,1/(AI126:AU126<>""),AI126:AU126))) | IF(J126="","All_Provinces",IFERROR(VLOOKUP(J126,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K126="","All_Districts",IFERROR(VLOOKUP(K126,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F127="","",ROW()-3) | [18 empty] | IF(AQ127="","",AQ127) |  |  |  | IF(W127<>"",W127,IF(OR(T127="",V127=""),"",EDATE(T127,V127))) |  |  |  |  | IF(F127="","",IF(COUNT(AI127:AV127)=0,IF(AA127="","Not started",AA127),SUBSTITUTE(LOOKUP(2,1/(AI127:AV127<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F127="",COUNT(AI127:AV127)=0),"",TODAY()-LOOKUP(2,1/(AI127:AV127<>""),AI127:AV127)) | IF(OR(F127="",COUNT(AI127:AV127)<2),"",LOOKUP(2,1/(AI127:AV127<>""),AI127:AV127)-MIN(AI127:AV127)) | IF(OR(AD127="",AC127="Not started",AC127=""),"",IFERROR(AD127-IF(VLOOKUP(AC127,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC127,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F127="","",IF(OR(AA127="Cancelled",AC127="Cancelled"),"Cancelled",IF(OR(AC127="Completed / Handover",Y127<>"",Z127>=100),"Completed — on track",IF(O127="Not awarded",IF(U127="",IF(X127="","No planned date",IF(TODAY()>X127,"Behind — past planned date",IF(X127-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U127,"Behind — award date passed",IF(U127-TODAY()<=30,"At risk — close to off track","On track"))),IF(X127="","No planned date",IF(AND(TODAY()>X127,OR(Z127="",Z127<100)),"Behind — past end date",IF(AND(T127<>"",X127<>"",Z127<>"",(Z127<100),((TODAY()-T127)/MAX(X127-T127,1)*100)-Z127>15),"Behind — progress lag",IF(AND(X127-TODAY()<=30,X127-TODAY()>=0,OR(Z127="",Z127<90)),"At risk — close to off track","On track")))))))) | IF(OR(F127="",AC127="Completed / Handover",AC127="Cancelled"),"",IF(O127="Not awarded",IF(U127<>"",U127-TODAY(),IF(X127="","",X127-TODAY())),IF(X127="","",X127-TODAY()))) | [14 empty] | IF(OR(F127="",AJ127=""),"",IF(COUNT(AI127:AI127)=0,"",AJ127-LOOKUP(2,1/(AI127:AI127<>""),AI127:AI127))) | IF(OR(F127="",AK127=""),"",IF(COUNT(AI127:AJ127)=0,"",AK127-LOOKUP(2,1/(AI127:AJ127<>""),AI127:AJ127))) | IF(OR(F127="",AL127=""),"",IF(COUNT(AI127:AK127)=0,"",AL127-LOOKUP(2,1/(AI127:AK127<>""),AI127:AK127))) | IF(OR(F127="",AM127=""),"",IF(COUNT(AI127:AL127)=0,"",AM127-LOOKUP(2,1/(AI127:AL127<>""),AI127:AL127))) | IF(OR(F127="",AN127=""),"",IF(COUNT(AI127:AM127)=0,"",AN127-LOOKUP(2,1/(AI127:AM127<>""),AI127:AM127))) | IF(OR(F127="",AO127=""),"",IF(COUNT(AI127:AN127)=0,"",AO127-LOOKUP(2,1/(AI127:AN127<>""),AI127:AN127))) | IF(OR(F127="",AP127=""),"",IF(COUNT(AI127:AO127)=0,"",AP127-LOOKUP(2,1/(AI127:AO127<>""),AI127:AO127))) | IF(OR(F127="",AQ127=""),"",IF(COUNT(AI127:AP127)=0,"",AQ127-LOOKUP(2,1/(AI127:AP127<>""),AI127:AP127))) | IF(OR(F127="",AR127=""),"",IF(COUNT(AI127:AQ127)=0,"",AR127-LOOKUP(2,1/(AI127:AQ127<>""),AI127:AQ127))) | IF(OR(F127="",AS127=""),"",IF(COUNT(AI127:AR127)=0,"",AS127-LOOKUP(2,1/(AI127:AR127<>""),AI127:AR127))) | IF(OR(F127="",AT127=""),"",IF(COUNT(AI127:AS127)=0,"",AT127-LOOKUP(2,1/(AI127:AS127<>""),AI127:AS127))) | IF(OR(F127="",AU127=""),"",IF(COUNT(AI127:AT127)=0,"",AU127-LOOKUP(2,1/(AI127:AT127<>""),AI127:AT127))) | IF(OR(F127="",AV127=""),"",IF(COUNT(AI127:AU127)=0,"",AV127-LOOKUP(2,1/(AI127:AU127<>""),AI127:AU127))) | IF(J127="","All_Provinces",IFERROR(VLOOKUP(J127,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K127="","All_Districts",IFERROR(VLOOKUP(K127,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F128="","",ROW()-3) | [18 empty] | IF(AQ128="","",AQ128) |  |  |  | IF(W128<>"",W128,IF(OR(T128="",V128=""),"",EDATE(T128,V128))) |  |  |  |  | IF(F128="","",IF(COUNT(AI128:AV128)=0,IF(AA128="","Not started",AA128),SUBSTITUTE(LOOKUP(2,1/(AI128:AV128<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F128="",COUNT(AI128:AV128)=0),"",TODAY()-LOOKUP(2,1/(AI128:AV128<>""),AI128:AV128)) | IF(OR(F128="",COUNT(AI128:AV128)<2),"",LOOKUP(2,1/(AI128:AV128<>""),AI128:AV128)-MIN(AI128:AV128)) | IF(OR(AD128="",AC128="Not started",AC128=""),"",IFERROR(AD128-IF(VLOOKUP(AC128,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC128,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F128="","",IF(OR(AA128="Cancelled",AC128="Cancelled"),"Cancelled",IF(OR(AC128="Completed / Handover",Y128<>"",Z128>=100),"Completed — on track",IF(O128="Not awarded",IF(U128="",IF(X128="","No planned date",IF(TODAY()>X128,"Behind — past planned date",IF(X128-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U128,"Behind — award date passed",IF(U128-TODAY()<=30,"At risk — close to off track","On track"))),IF(X128="","No planned date",IF(AND(TODAY()>X128,OR(Z128="",Z128<100)),"Behind — past end date",IF(AND(T128<>"",X128<>"",Z128<>"",(Z128<100),((TODAY()-T128)/MAX(X128-T128,1)*100)-Z128>15),"Behind — progress lag",IF(AND(X128-TODAY()<=30,X128-TODAY()>=0,OR(Z128="",Z128<90)),"At risk — close to off track","On track")))))))) | IF(OR(F128="",AC128="Completed / Handover",AC128="Cancelled"),"",IF(O128="Not awarded",IF(U128<>"",U128-TODAY(),IF(X128="","",X128-TODAY())),IF(X128="","",X128-TODAY()))) | [14 empty] | IF(OR(F128="",AJ128=""),"",IF(COUNT(AI128:AI128)=0,"",AJ128-LOOKUP(2,1/(AI128:AI128<>""),AI128:AI128))) | IF(OR(F128="",AK128=""),"",IF(COUNT(AI128:AJ128)=0,"",AK128-LOOKUP(2,1/(AI128:AJ128<>""),AI128:AJ128))) | IF(OR(F128="",AL128=""),"",IF(COUNT(AI128:AK128)=0,"",AL128-LOOKUP(2,1/(AI128:AK128<>""),AI128:AK128))) | IF(OR(F128="",AM128=""),"",IF(COUNT(AI128:AL128)=0,"",AM128-LOOKUP(2,1/(AI128:AL128<>""),AI128:AL128))) | IF(OR(F128="",AN128=""),"",IF(COUNT(AI128:AM128)=0,"",AN128-LOOKUP(2,1/(AI128:AM128<>""),AI128:AM128))) | IF(OR(F128="",AO128=""),"",IF(COUNT(AI128:AN128)=0,"",AO128-LOOKUP(2,1/(AI128:AN128<>""),AI128:AN128))) | IF(OR(F128="",AP128=""),"",IF(COUNT(AI128:AO128)=0,"",AP128-LOOKUP(2,1/(AI128:AO128<>""),AI128:AO128))) | IF(OR(F128="",AQ128=""),"",IF(COUNT(AI128:AP128)=0,"",AQ128-LOOKUP(2,1/(AI128:AP128<>""),AI128:AP128))) | IF(OR(F128="",AR128=""),"",IF(COUNT(AI128:AQ128)=0,"",AR128-LOOKUP(2,1/(AI128:AQ128<>""),AI128:AQ128))) | IF(OR(F128="",AS128=""),"",IF(COUNT(AI128:AR128)=0,"",AS128-LOOKUP(2,1/(AI128:AR128<>""),AI128:AR128))) | IF(OR(F128="",AT128=""),"",IF(COUNT(AI128:AS128)=0,"",AT128-LOOKUP(2,1/(AI128:AS128<>""),AI128:AS128))) | IF(OR(F128="",AU128=""),"",IF(COUNT(AI128:AT128)=0,"",AU128-LOOKUP(2,1/(AI128:AT128<>""),AI128:AT128))) | IF(OR(F128="",AV128=""),"",IF(COUNT(AI128:AU128)=0,"",AV128-LOOKUP(2,1/(AI128:AU128<>""),AI128:AU128))) | IF(J128="","All_Provinces",IFERROR(VLOOKUP(J128,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K128="","All_Districts",IFERROR(VLOOKUP(K128,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F129="","",ROW()-3) | [18 empty] | IF(AQ129="","",AQ129) |  |  |  | IF(W129<>"",W129,IF(OR(T129="",V129=""),"",EDATE(T129,V129))) |  |  |  |  | IF(F129="","",IF(COUNT(AI129:AV129)=0,IF(AA129="","Not started",AA129),SUBSTITUTE(LOOKUP(2,1/(AI129:AV129<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F129="",COUNT(AI129:AV129)=0),"",TODAY()-LOOKUP(2,1/(AI129:AV129<>""),AI129:AV129)) | IF(OR(F129="",COUNT(AI129:AV129)<2),"",LOOKUP(2,1/(AI129:AV129<>""),AI129:AV129)-MIN(AI129:AV129)) | IF(OR(AD129="",AC129="Not started",AC129=""),"",IFERROR(AD129-IF(VLOOKUP(AC129,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC129,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F129="","",IF(OR(AA129="Cancelled",AC129="Cancelled"),"Cancelled",IF(OR(AC129="Completed / Handover",Y129<>"",Z129>=100),"Completed — on track",IF(O129="Not awarded",IF(U129="",IF(X129="","No planned date",IF(TODAY()>X129,"Behind — past planned date",IF(X129-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U129,"Behind — award date passed",IF(U129-TODAY()<=30,"At risk — close to off track","On track"))),IF(X129="","No planned date",IF(AND(TODAY()>X129,OR(Z129="",Z129<100)),"Behind — past end date",IF(AND(T129<>"",X129<>"",Z129<>"",(Z129<100),((TODAY()-T129)/MAX(X129-T129,1)*100)-Z129>15),"Behind — progress lag",IF(AND(X129-TODAY()<=30,X129-TODAY()>=0,OR(Z129="",Z129<90)),"At risk — close to off track","On track")))))))) | IF(OR(F129="",AC129="Completed / Handover",AC129="Cancelled"),"",IF(O129="Not awarded",IF(U129<>"",U129-TODAY(),IF(X129="","",X129-TODAY())),IF(X129="","",X129-TODAY()))) | [14 empty] | IF(OR(F129="",AJ129=""),"",IF(COUNT(AI129:AI129)=0,"",AJ129-LOOKUP(2,1/(AI129:AI129<>""),AI129:AI129))) | IF(OR(F129="",AK129=""),"",IF(COUNT(AI129:AJ129)=0,"",AK129-LOOKUP(2,1/(AI129:AJ129<>""),AI129:AJ129))) | IF(OR(F129="",AL129=""),"",IF(COUNT(AI129:AK129)=0,"",AL129-LOOKUP(2,1/(AI129:AK129<>""),AI129:AK129))) | IF(OR(F129="",AM129=""),"",IF(COUNT(AI129:AL129)=0,"",AM129-LOOKUP(2,1/(AI129:AL129<>""),AI129:AL129))) | IF(OR(F129="",AN129=""),"",IF(COUNT(AI129:AM129)=0,"",AN129-LOOKUP(2,1/(AI129:AM129<>""),AI129:AM129))) | IF(OR(F129="",AO129=""),"",IF(COUNT(AI129:AN129)=0,"",AO129-LOOKUP(2,1/(AI129:AN129<>""),AI129:AN129))) | IF(OR(F129="",AP129=""),"",IF(COUNT(AI129:AO129)=0,"",AP129-LOOKUP(2,1/(AI129:AO129<>""),AI129:AO129))) | IF(OR(F129="",AQ129=""),"",IF(COUNT(AI129:AP129)=0,"",AQ129-LOOKUP(2,1/(AI129:AP129<>""),AI129:AP129))) | IF(OR(F129="",AR129=""),"",IF(COUNT(AI129:AQ129)=0,"",AR129-LOOKUP(2,1/(AI129:AQ129<>""),AI129:AQ129))) | IF(OR(F129="",AS129=""),"",IF(COUNT(AI129:AR129)=0,"",AS129-LOOKUP(2,1/(AI129:AR129<>""),AI129:AR129))) | IF(OR(F129="",AT129=""),"",IF(COUNT(AI129:AS129)=0,"",AT129-LOOKUP(2,1/(AI129:AS129<>""),AI129:AS129))) | IF(OR(F129="",AU129=""),"",IF(COUNT(AI129:AT129)=0,"",AU129-LOOKUP(2,1/(AI129:AT129<>""),AI129:AT129))) | IF(OR(F129="",AV129=""),"",IF(COUNT(AI129:AU129)=0,"",AV129-LOOKUP(2,1/(AI129:AU129<>""),AI129:AU129))) | IF(J129="","All_Provinces",IFERROR(VLOOKUP(J129,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K129="","All_Districts",IFERROR(VLOOKUP(K129,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F130="","",ROW()-3) | [18 empty] | IF(AQ130="","",AQ130) |  |  |  | IF(W130<>"",W130,IF(OR(T130="",V130=""),"",EDATE(T130,V130))) |  |  |  |  | IF(F130="","",IF(COUNT(AI130:AV130)=0,IF(AA130="","Not started",AA130),SUBSTITUTE(LOOKUP(2,1/(AI130:AV130<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F130="",COUNT(AI130:AV130)=0),"",TODAY()-LOOKUP(2,1/(AI130:AV130<>""),AI130:AV130)) | IF(OR(F130="",COUNT(AI130:AV130)<2),"",LOOKUP(2,1/(AI130:AV130<>""),AI130:AV130)-MIN(AI130:AV130)) | IF(OR(AD130="",AC130="Not started",AC130=""),"",IFERROR(AD130-IF(VLOOKUP(AC130,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC130,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F130="","",IF(OR(AA130="Cancelled",AC130="Cancelled"),"Cancelled",IF(OR(AC130="Completed / Handover",Y130<>"",Z130>=100),"Completed — on track",IF(O130="Not awarded",IF(U130="",IF(X130="","No planned date",IF(TODAY()>X130,"Behind — past planned date",IF(X130-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U130,"Behind — award date passed",IF(U130-TODAY()<=30,"At risk — close to off track","On track"))),IF(X130="","No planned date",IF(AND(TODAY()>X130,OR(Z130="",Z130<100)),"Behind — past end date",IF(AND(T130<>"",X130<>"",Z130<>"",(Z130<100),((TODAY()-T130)/MAX(X130-T130,1)*100)-Z130>15),"Behind — progress lag",IF(AND(X130-TODAY()<=30,X130-TODAY()>=0,OR(Z130="",Z130<90)),"At risk — close to off track","On track")))))))) | IF(OR(F130="",AC130="Completed / Handover",AC130="Cancelled"),"",IF(O130="Not awarded",IF(U130<>"",U130-TODAY(),IF(X130="","",X130-TODAY())),IF(X130="","",X130-TODAY()))) | [14 empty] | IF(OR(F130="",AJ130=""),"",IF(COUNT(AI130:AI130)=0,"",AJ130-LOOKUP(2,1/(AI130:AI130<>""),AI130:AI130))) | IF(OR(F130="",AK130=""),"",IF(COUNT(AI130:AJ130)=0,"",AK130-LOOKUP(2,1/(AI130:AJ130<>""),AI130:AJ130))) | IF(OR(F130="",AL130=""),"",IF(COUNT(AI130:AK130)=0,"",AL130-LOOKUP(2,1/(AI130:AK130<>""),AI130:AK130))) | IF(OR(F130="",AM130=""),"",IF(COUNT(AI130:AL130)=0,"",AM130-LOOKUP(2,1/(AI130:AL130<>""),AI130:AL130))) | IF(OR(F130="",AN130=""),"",IF(COUNT(AI130:AM130)=0,"",AN130-LOOKUP(2,1/(AI130:AM130<>""),AI130:AM130))) | IF(OR(F130="",AO130=""),"",IF(COUNT(AI130:AN130)=0,"",AO130-LOOKUP(2,1/(AI130:AN130<>""),AI130:AN130))) | IF(OR(F130="",AP130=""),"",IF(COUNT(AI130:AO130)=0,"",AP130-LOOKUP(2,1/(AI130:AO130<>""),AI130:AO130))) | IF(OR(F130="",AQ130=""),"",IF(COUNT(AI130:AP130)=0,"",AQ130-LOOKUP(2,1/(AI130:AP130<>""),AI130:AP130))) | IF(OR(F130="",AR130=""),"",IF(COUNT(AI130:AQ130)=0,"",AR130-LOOKUP(2,1/(AI130:AQ130<>""),AI130:AQ130))) | IF(OR(F130="",AS130=""),"",IF(COUNT(AI130:AR130)=0,"",AS130-LOOKUP(2,1/(AI130:AR130<>""),AI130:AR130))) | IF(OR(F130="",AT130=""),"",IF(COUNT(AI130:AS130)=0,"",AT130-LOOKUP(2,1/(AI130:AS130<>""),AI130:AS130))) | IF(OR(F130="",AU130=""),"",IF(COUNT(AI130:AT130)=0,"",AU130-LOOKUP(2,1/(AI130:AT130<>""),AI130:AT130))) | IF(OR(F130="",AV130=""),"",IF(COUNT(AI130:AU130)=0,"",AV130-LOOKUP(2,1/(AI130:AU130<>""),AI130:AU130))) | IF(J130="","All_Provinces",IFERROR(VLOOKUP(J130,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K130="","All_Districts",IFERROR(VLOOKUP(K130,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F131="","",ROW()-3) | [18 empty] | IF(AQ131="","",AQ131) |  |  |  | IF(W131<>"",W131,IF(OR(T131="",V131=""),"",EDATE(T131,V131))) |  |  |  |  | IF(F131="","",IF(COUNT(AI131:AV131)=0,IF(AA131="","Not started",AA131),SUBSTITUTE(LOOKUP(2,1/(AI131:AV131<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F131="",COUNT(AI131:AV131)=0),"",TODAY()-LOOKUP(2,1/(AI131:AV131<>""),AI131:AV131)) | IF(OR(F131="",COUNT(AI131:AV131)<2),"",LOOKUP(2,1/(AI131:AV131<>""),AI131:AV131)-MIN(AI131:AV131)) | IF(OR(AD131="",AC131="Not started",AC131=""),"",IFERROR(AD131-IF(VLOOKUP(AC131,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC131,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F131="","",IF(OR(AA131="Cancelled",AC131="Cancelled"),"Cancelled",IF(OR(AC131="Completed / Handover",Y131<>"",Z131>=100),"Completed — on track",IF(O131="Not awarded",IF(U131="",IF(X131="","No planned date",IF(TODAY()>X131,"Behind — past planned date",IF(X131-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U131,"Behind — award date passed",IF(U131-TODAY()<=30,"At risk — close to off track","On track"))),IF(X131="","No planned date",IF(AND(TODAY()>X131,OR(Z131="",Z131<100)),"Behind — past end date",IF(AND(T131<>"",X131<>"",Z131<>"",(Z131<100),((TODAY()-T131)/MAX(X131-T131,1)*100)-Z131>15),"Behind — progress lag",IF(AND(X131-TODAY()<=30,X131-TODAY()>=0,OR(Z131="",Z131<90)),"At risk — close to off track","On track")))))))) | IF(OR(F131="",AC131="Completed / Handover",AC131="Cancelled"),"",IF(O131="Not awarded",IF(U131<>"",U131-TODAY(),IF(X131="","",X131-TODAY())),IF(X131="","",X131-TODAY()))) | [14 empty] | IF(OR(F131="",AJ131=""),"",IF(COUNT(AI131:AI131)=0,"",AJ131-LOOKUP(2,1/(AI131:AI131<>""),AI131:AI131))) | IF(OR(F131="",AK131=""),"",IF(COUNT(AI131:AJ131)=0,"",AK131-LOOKUP(2,1/(AI131:AJ131<>""),AI131:AJ131))) | IF(OR(F131="",AL131=""),"",IF(COUNT(AI131:AK131)=0,"",AL131-LOOKUP(2,1/(AI131:AK131<>""),AI131:AK131))) | IF(OR(F131="",AM131=""),"",IF(COUNT(AI131:AL131)=0,"",AM131-LOOKUP(2,1/(AI131:AL131<>""),AI131:AL131))) | IF(OR(F131="",AN131=""),"",IF(COUNT(AI131:AM131)=0,"",AN131-LOOKUP(2,1/(AI131:AM131<>""),AI131:AM131))) | IF(OR(F131="",AO131=""),"",IF(COUNT(AI131:AN131)=0,"",AO131-LOOKUP(2,1/(AI131:AN131<>""),AI131:AN131))) | IF(OR(F131="",AP131=""),"",IF(COUNT(AI131:AO131)=0,"",AP131-LOOKUP(2,1/(AI131:AO131<>""),AI131:AO131))) | IF(OR(F131="",AQ131=""),"",IF(COUNT(AI131:AP131)=0,"",AQ131-LOOKUP(2,1/(AI131:AP131<>""),AI131:AP131))) | IF(OR(F131="",AR131=""),"",IF(COUNT(AI131:AQ131)=0,"",AR131-LOOKUP(2,1/(AI131:AQ131<>""),AI131:AQ131))) | IF(OR(F131="",AS131=""),"",IF(COUNT(AI131:AR131)=0,"",AS131-LOOKUP(2,1/(AI131:AR131<>""),AI131:AR131))) | IF(OR(F131="",AT131=""),"",IF(COUNT(AI131:AS131)=0,"",AT131-LOOKUP(2,1/(AI131:AS131<>""),AI131:AS131))) | IF(OR(F131="",AU131=""),"",IF(COUNT(AI131:AT131)=0,"",AU131-LOOKUP(2,1/(AI131:AT131<>""),AI131:AT131))) | IF(OR(F131="",AV131=""),"",IF(COUNT(AI131:AU131)=0,"",AV131-LOOKUP(2,1/(AI131:AU131<>""),AI131:AU131))) | IF(J131="","All_Provinces",IFERROR(VLOOKUP(J131,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K131="","All_Districts",IFERROR(VLOOKUP(K131,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F132="","",ROW()-3) | [18 empty] | IF(AQ132="","",AQ132) |  |  |  | IF(W132<>"",W132,IF(OR(T132="",V132=""),"",EDATE(T132,V132))) |  |  |  |  | IF(F132="","",IF(COUNT(AI132:AV132)=0,IF(AA132="","Not started",AA132),SUBSTITUTE(LOOKUP(2,1/(AI132:AV132<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F132="",COUNT(AI132:AV132)=0),"",TODAY()-LOOKUP(2,1/(AI132:AV132<>""),AI132:AV132)) | IF(OR(F132="",COUNT(AI132:AV132)<2),"",LOOKUP(2,1/(AI132:AV132<>""),AI132:AV132)-MIN(AI132:AV132)) | IF(OR(AD132="",AC132="Not started",AC132=""),"",IFERROR(AD132-IF(VLOOKUP(AC132,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC132,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F132="","",IF(OR(AA132="Cancelled",AC132="Cancelled"),"Cancelled",IF(OR(AC132="Completed / Handover",Y132<>"",Z132>=100),"Completed — on track",IF(O132="Not awarded",IF(U132="",IF(X132="","No planned date",IF(TODAY()>X132,"Behind — past planned date",IF(X132-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U132,"Behind — award date passed",IF(U132-TODAY()<=30,"At risk — close to off track","On track"))),IF(X132="","No planned date",IF(AND(TODAY()>X132,OR(Z132="",Z132<100)),"Behind — past end date",IF(AND(T132<>"",X132<>"",Z132<>"",(Z132<100),((TODAY()-T132)/MAX(X132-T132,1)*100)-Z132>15),"Behind — progress lag",IF(AND(X132-TODAY()<=30,X132-TODAY()>=0,OR(Z132="",Z132<90)),"At risk — close to off track","On track")))))))) | IF(OR(F132="",AC132="Completed / Handover",AC132="Cancelled"),"",IF(O132="Not awarded",IF(U132<>"",U132-TODAY(),IF(X132="","",X132-TODAY())),IF(X132="","",X132-TODAY()))) | [14 empty] | IF(OR(F132="",AJ132=""),"",IF(COUNT(AI132:AI132)=0,"",AJ132-LOOKUP(2,1/(AI132:AI132<>""),AI132:AI132))) | IF(OR(F132="",AK132=""),"",IF(COUNT(AI132:AJ132)=0,"",AK132-LOOKUP(2,1/(AI132:AJ132<>""),AI132:AJ132))) | IF(OR(F132="",AL132=""),"",IF(COUNT(AI132:AK132)=0,"",AL132-LOOKUP(2,1/(AI132:AK132<>""),AI132:AK132))) | IF(OR(F132="",AM132=""),"",IF(COUNT(AI132:AL132)=0,"",AM132-LOOKUP(2,1/(AI132:AL132<>""),AI132:AL132))) | IF(OR(F132="",AN132=""),"",IF(COUNT(AI132:AM132)=0,"",AN132-LOOKUP(2,1/(AI132:AM132<>""),AI132:AM132))) | IF(OR(F132="",AO132=""),"",IF(COUNT(AI132:AN132)=0,"",AO132-LOOKUP(2,1/(AI132:AN132<>""),AI132:AN132))) | IF(OR(F132="",AP132=""),"",IF(COUNT(AI132:AO132)=0,"",AP132-LOOKUP(2,1/(AI132:AO132<>""),AI132:AO132))) | IF(OR(F132="",AQ132=""),"",IF(COUNT(AI132:AP132)=0,"",AQ132-LOOKUP(2,1/(AI132:AP132<>""),AI132:AP132))) | IF(OR(F132="",AR132=""),"",IF(COUNT(AI132:AQ132)=0,"",AR132-LOOKUP(2,1/(AI132:AQ132<>""),AI132:AQ132))) | IF(OR(F132="",AS132=""),"",IF(COUNT(AI132:AR132)=0,"",AS132-LOOKUP(2,1/(AI132:AR132<>""),AI132:AR132))) | IF(OR(F132="",AT132=""),"",IF(COUNT(AI132:AS132)=0,"",AT132-LOOKUP(2,1/(AI132:AS132<>""),AI132:AS132))) | IF(OR(F132="",AU132=""),"",IF(COUNT(AI132:AT132)=0,"",AU132-LOOKUP(2,1/(AI132:AT132<>""),AI132:AT132))) | IF(OR(F132="",AV132=""),"",IF(COUNT(AI132:AU132)=0,"",AV132-LOOKUP(2,1/(AI132:AU132<>""),AI132:AU132))) | IF(J132="","All_Provinces",IFERROR(VLOOKUP(J132,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K132="","All_Districts",IFERROR(VLOOKUP(K132,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F133="","",ROW()-3) | [18 empty] | IF(AQ133="","",AQ133) |  |  |  | IF(W133<>"",W133,IF(OR(T133="",V133=""),"",EDATE(T133,V133))) |  |  |  |  | IF(F133="","",IF(COUNT(AI133:AV133)=0,IF(AA133="","Not started",AA133),SUBSTITUTE(LOOKUP(2,1/(AI133:AV133<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F133="",COUNT(AI133:AV133)=0),"",TODAY()-LOOKUP(2,1/(AI133:AV133<>""),AI133:AV133)) | IF(OR(F133="",COUNT(AI133:AV133)<2),"",LOOKUP(2,1/(AI133:AV133<>""),AI133:AV133)-MIN(AI133:AV133)) | IF(OR(AD133="",AC133="Not started",AC133=""),"",IFERROR(AD133-IF(VLOOKUP(AC133,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC133,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F133="","",IF(OR(AA133="Cancelled",AC133="Cancelled"),"Cancelled",IF(OR(AC133="Completed / Handover",Y133<>"",Z133>=100),"Completed — on track",IF(O133="Not awarded",IF(U133="",IF(X133="","No planned date",IF(TODAY()>X133,"Behind — past planned date",IF(X133-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U133,"Behind — award date passed",IF(U133-TODAY()<=30,"At risk — close to off track","On track"))),IF(X133="","No planned date",IF(AND(TODAY()>X133,OR(Z133="",Z133<100)),"Behind — past end date",IF(AND(T133<>"",X133<>"",Z133<>"",(Z133<100),((TODAY()-T133)/MAX(X133-T133,1)*100)-Z133>15),"Behind — progress lag",IF(AND(X133-TODAY()<=30,X133-TODAY()>=0,OR(Z133="",Z133<90)),"At risk — close to off track","On track")))))))) | IF(OR(F133="",AC133="Completed / Handover",AC133="Cancelled"),"",IF(O133="Not awarded",IF(U133<>"",U133-TODAY(),IF(X133="","",X133-TODAY())),IF(X133="","",X133-TODAY()))) | [14 empty] | IF(OR(F133="",AJ133=""),"",IF(COUNT(AI133:AI133)=0,"",AJ133-LOOKUP(2,1/(AI133:AI133<>""),AI133:AI133))) | IF(OR(F133="",AK133=""),"",IF(COUNT(AI133:AJ133)=0,"",AK133-LOOKUP(2,1/(AI133:AJ133<>""),AI133:AJ133))) | IF(OR(F133="",AL133=""),"",IF(COUNT(AI133:AK133)=0,"",AL133-LOOKUP(2,1/(AI133:AK133<>""),AI133:AK133))) | IF(OR(F133="",AM133=""),"",IF(COUNT(AI133:AL133)=0,"",AM133-LOOKUP(2,1/(AI133:AL133<>""),AI133:AL133))) | IF(OR(F133="",AN133=""),"",IF(COUNT(AI133:AM133)=0,"",AN133-LOOKUP(2,1/(AI133:AM133<>""),AI133:AM133))) | IF(OR(F133="",AO133=""),"",IF(COUNT(AI133:AN133)=0,"",AO133-LOOKUP(2,1/(AI133:AN133<>""),AI133:AN133))) | IF(OR(F133="",AP133=""),"",IF(COUNT(AI133:AO133)=0,"",AP133-LOOKUP(2,1/(AI133:AO133<>""),AI133:AO133))) | IF(OR(F133="",AQ133=""),"",IF(COUNT(AI133:AP133)=0,"",AQ133-LOOKUP(2,1/(AI133:AP133<>""),AI133:AP133))) | IF(OR(F133="",AR133=""),"",IF(COUNT(AI133:AQ133)=0,"",AR133-LOOKUP(2,1/(AI133:AQ133<>""),AI133:AQ133))) | IF(OR(F133="",AS133=""),"",IF(COUNT(AI133:AR133)=0,"",AS133-LOOKUP(2,1/(AI133:AR133<>""),AI133:AR133))) | IF(OR(F133="",AT133=""),"",IF(COUNT(AI133:AS133)=0,"",AT133-LOOKUP(2,1/(AI133:AS133<>""),AI133:AS133))) | IF(OR(F133="",AU133=""),"",IF(COUNT(AI133:AT133)=0,"",AU133-LOOKUP(2,1/(AI133:AT133<>""),AI133:AT133))) | IF(OR(F133="",AV133=""),"",IF(COUNT(AI133:AU133)=0,"",AV133-LOOKUP(2,1/(AI133:AU133<>""),AI133:AU133))) | IF(J133="","All_Provinces",IFERROR(VLOOKUP(J133,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K133="","All_Districts",IFERROR(VLOOKUP(K133,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F134="","",ROW()-3) | [18 empty] | IF(AQ134="","",AQ134) |  |  |  | IF(W134<>"",W134,IF(OR(T134="",V134=""),"",EDATE(T134,V134))) |  |  |  |  | IF(F134="","",IF(COUNT(AI134:AV134)=0,IF(AA134="","Not started",AA134),SUBSTITUTE(LOOKUP(2,1/(AI134:AV134<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F134="",COUNT(AI134:AV134)=0),"",TODAY()-LOOKUP(2,1/(AI134:AV134<>""),AI134:AV134)) | IF(OR(F134="",COUNT(AI134:AV134)<2),"",LOOKUP(2,1/(AI134:AV134<>""),AI134:AV134)-MIN(AI134:AV134)) | IF(OR(AD134="",AC134="Not started",AC134=""),"",IFERROR(AD134-IF(VLOOKUP(AC134,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC134,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F134="","",IF(OR(AA134="Cancelled",AC134="Cancelled"),"Cancelled",IF(OR(AC134="Completed / Handover",Y134<>"",Z134>=100),"Completed — on track",IF(O134="Not awarded",IF(U134="",IF(X134="","No planned date",IF(TODAY()>X134,"Behind — past planned date",IF(X134-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U134,"Behind — award date passed",IF(U134-TODAY()<=30,"At risk — close to off track","On track"))),IF(X134="","No planned date",IF(AND(TODAY()>X134,OR(Z134="",Z134<100)),"Behind — past end date",IF(AND(T134<>"",X134<>"",Z134<>"",(Z134<100),((TODAY()-T134)/MAX(X134-T134,1)*100)-Z134>15),"Behind — progress lag",IF(AND(X134-TODAY()<=30,X134-TODAY()>=0,OR(Z134="",Z134<90)),"At risk — close to off track","On track")))))))) | IF(OR(F134="",AC134="Completed / Handover",AC134="Cancelled"),"",IF(O134="Not awarded",IF(U134<>"",U134-TODAY(),IF(X134="","",X134-TODAY())),IF(X134="","",X134-TODAY()))) | [14 empty] | IF(OR(F134="",AJ134=""),"",IF(COUNT(AI134:AI134)=0,"",AJ134-LOOKUP(2,1/(AI134:AI134<>""),AI134:AI134))) | IF(OR(F134="",AK134=""),"",IF(COUNT(AI134:AJ134)=0,"",AK134-LOOKUP(2,1/(AI134:AJ134<>""),AI134:AJ134))) | IF(OR(F134="",AL134=""),"",IF(COUNT(AI134:AK134)=0,"",AL134-LOOKUP(2,1/(AI134:AK134<>""),AI134:AK134))) | IF(OR(F134="",AM134=""),"",IF(COUNT(AI134:AL134)=0,"",AM134-LOOKUP(2,1/(AI134:AL134<>""),AI134:AL134))) | IF(OR(F134="",AN134=""),"",IF(COUNT(AI134:AM134)=0,"",AN134-LOOKUP(2,1/(AI134:AM134<>""),AI134:AM134))) | IF(OR(F134="",AO134=""),"",IF(COUNT(AI134:AN134)=0,"",AO134-LOOKUP(2,1/(AI134:AN134<>""),AI134:AN134))) | IF(OR(F134="",AP134=""),"",IF(COUNT(AI134:AO134)=0,"",AP134-LOOKUP(2,1/(AI134:AO134<>""),AI134:AO134))) | IF(OR(F134="",AQ134=""),"",IF(COUNT(AI134:AP134)=0,"",AQ134-LOOKUP(2,1/(AI134:AP134<>""),AI134:AP134))) | IF(OR(F134="",AR134=""),"",IF(COUNT(AI134:AQ134)=0,"",AR134-LOOKUP(2,1/(AI134:AQ134<>""),AI134:AQ134))) | IF(OR(F134="",AS134=""),"",IF(COUNT(AI134:AR134)=0,"",AS134-LOOKUP(2,1/(AI134:AR134<>""),AI134:AR134))) | IF(OR(F134="",AT134=""),"",IF(COUNT(AI134:AS134)=0,"",AT134-LOOKUP(2,1/(AI134:AS134<>""),AI134:AS134))) | IF(OR(F134="",AU134=""),"",IF(COUNT(AI134:AT134)=0,"",AU134-LOOKUP(2,1/(AI134:AT134<>""),AI134:AT134))) | IF(OR(F134="",AV134=""),"",IF(COUNT(AI134:AU134)=0,"",AV134-LOOKUP(2,1/(AI134:AU134<>""),AI134:AU134))) | IF(J134="","All_Provinces",IFERROR(VLOOKUP(J134,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K134="","All_Districts",IFERROR(VLOOKUP(K134,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F135="","",ROW()-3) | [18 empty] | IF(AQ135="","",AQ135) |  |  |  | IF(W135<>"",W135,IF(OR(T135="",V135=""),"",EDATE(T135,V135))) |  |  |  |  | IF(F135="","",IF(COUNT(AI135:AV135)=0,IF(AA135="","Not started",AA135),SUBSTITUTE(LOOKUP(2,1/(AI135:AV135<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F135="",COUNT(AI135:AV135)=0),"",TODAY()-LOOKUP(2,1/(AI135:AV135<>""),AI135:AV135)) | IF(OR(F135="",COUNT(AI135:AV135)<2),"",LOOKUP(2,1/(AI135:AV135<>""),AI135:AV135)-MIN(AI135:AV135)) | IF(OR(AD135="",AC135="Not started",AC135=""),"",IFERROR(AD135-IF(VLOOKUP(AC135,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC135,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F135="","",IF(OR(AA135="Cancelled",AC135="Cancelled"),"Cancelled",IF(OR(AC135="Completed / Handover",Y135<>"",Z135>=100),"Completed — on track",IF(O135="Not awarded",IF(U135="",IF(X135="","No planned date",IF(TODAY()>X135,"Behind — past planned date",IF(X135-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U135,"Behind — award date passed",IF(U135-TODAY()<=30,"At risk — close to off track","On track"))),IF(X135="","No planned date",IF(AND(TODAY()>X135,OR(Z135="",Z135<100)),"Behind — past end date",IF(AND(T135<>"",X135<>"",Z135<>"",(Z135<100),((TODAY()-T135)/MAX(X135-T135,1)*100)-Z135>15),"Behind — progress lag",IF(AND(X135-TODAY()<=30,X135-TODAY()>=0,OR(Z135="",Z135<90)),"At risk — close to off track","On track")))))))) | IF(OR(F135="",AC135="Completed / Handover",AC135="Cancelled"),"",IF(O135="Not awarded",IF(U135<>"",U135-TODAY(),IF(X135="","",X135-TODAY())),IF(X135="","",X135-TODAY()))) | [14 empty] | IF(OR(F135="",AJ135=""),"",IF(COUNT(AI135:AI135)=0,"",AJ135-LOOKUP(2,1/(AI135:AI135<>""),AI135:AI135))) | IF(OR(F135="",AK135=""),"",IF(COUNT(AI135:AJ135)=0,"",AK135-LOOKUP(2,1/(AI135:AJ135<>""),AI135:AJ135))) | IF(OR(F135="",AL135=""),"",IF(COUNT(AI135:AK135)=0,"",AL135-LOOKUP(2,1/(AI135:AK135<>""),AI135:AK135))) | IF(OR(F135="",AM135=""),"",IF(COUNT(AI135:AL135)=0,"",AM135-LOOKUP(2,1/(AI135:AL135<>""),AI135:AL135))) | IF(OR(F135="",AN135=""),"",IF(COUNT(AI135:AM135)=0,"",AN135-LOOKUP(2,1/(AI135:AM135<>""),AI135:AM135))) | IF(OR(F135="",AO135=""),"",IF(COUNT(AI135:AN135)=0,"",AO135-LOOKUP(2,1/(AI135:AN135<>""),AI135:AN135))) | IF(OR(F135="",AP135=""),"",IF(COUNT(AI135:AO135)=0,"",AP135-LOOKUP(2,1/(AI135:AO135<>""),AI135:AO135))) | IF(OR(F135="",AQ135=""),"",IF(COUNT(AI135:AP135)=0,"",AQ135-LOOKUP(2,1/(AI135:AP135<>""),AI135:AP135))) | IF(OR(F135="",AR135=""),"",IF(COUNT(AI135:AQ135)=0,"",AR135-LOOKUP(2,1/(AI135:AQ135<>""),AI135:AQ135))) | IF(OR(F135="",AS135=""),"",IF(COUNT(AI135:AR135)=0,"",AS135-LOOKUP(2,1/(AI135:AR135<>""),AI135:AR135))) | IF(OR(F135="",AT135=""),"",IF(COUNT(AI135:AS135)=0,"",AT135-LOOKUP(2,1/(AI135:AS135<>""),AI135:AS135))) | IF(OR(F135="",AU135=""),"",IF(COUNT(AI135:AT135)=0,"",AU135-LOOKUP(2,1/(AI135:AT135<>""),AI135:AT135))) | IF(OR(F135="",AV135=""),"",IF(COUNT(AI135:AU135)=0,"",AV135-LOOKUP(2,1/(AI135:AU135<>""),AI135:AU135))) | IF(J135="","All_Provinces",IFERROR(VLOOKUP(J135,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K135="","All_Districts",IFERROR(VLOOKUP(K135,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F136="","",ROW()-3) | [18 empty] | IF(AQ136="","",AQ136) |  |  |  | IF(W136<>"",W136,IF(OR(T136="",V136=""),"",EDATE(T136,V136))) |  |  |  |  | IF(F136="","",IF(COUNT(AI136:AV136)=0,IF(AA136="","Not started",AA136),SUBSTITUTE(LOOKUP(2,1/(AI136:AV136<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F136="",COUNT(AI136:AV136)=0),"",TODAY()-LOOKUP(2,1/(AI136:AV136<>""),AI136:AV136)) | IF(OR(F136="",COUNT(AI136:AV136)<2),"",LOOKUP(2,1/(AI136:AV136<>""),AI136:AV136)-MIN(AI136:AV136)) | IF(OR(AD136="",AC136="Not started",AC136=""),"",IFERROR(AD136-IF(VLOOKUP(AC136,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC136,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F136="","",IF(OR(AA136="Cancelled",AC136="Cancelled"),"Cancelled",IF(OR(AC136="Completed / Handover",Y136<>"",Z136>=100),"Completed — on track",IF(O136="Not awarded",IF(U136="",IF(X136="","No planned date",IF(TODAY()>X136,"Behind — past planned date",IF(X136-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U136,"Behind — award date passed",IF(U136-TODAY()<=30,"At risk — close to off track","On track"))),IF(X136="","No planned date",IF(AND(TODAY()>X136,OR(Z136="",Z136<100)),"Behind — past end date",IF(AND(T136<>"",X136<>"",Z136<>"",(Z136<100),((TODAY()-T136)/MAX(X136-T136,1)*100)-Z136>15),"Behind — progress lag",IF(AND(X136-TODAY()<=30,X136-TODAY()>=0,OR(Z136="",Z136<90)),"At risk — close to off track","On track")))))))) | IF(OR(F136="",AC136="Completed / Handover",AC136="Cancelled"),"",IF(O136="Not awarded",IF(U136<>"",U136-TODAY(),IF(X136="","",X136-TODAY())),IF(X136="","",X136-TODAY()))) | [14 empty] | IF(OR(F136="",AJ136=""),"",IF(COUNT(AI136:AI136)=0,"",AJ136-LOOKUP(2,1/(AI136:AI136<>""),AI136:AI136))) | IF(OR(F136="",AK136=""),"",IF(COUNT(AI136:AJ136)=0,"",AK136-LOOKUP(2,1/(AI136:AJ136<>""),AI136:AJ136))) | IF(OR(F136="",AL136=""),"",IF(COUNT(AI136:AK136)=0,"",AL136-LOOKUP(2,1/(AI136:AK136<>""),AI136:AK136))) | IF(OR(F136="",AM136=""),"",IF(COUNT(AI136:AL136)=0,"",AM136-LOOKUP(2,1/(AI136:AL136<>""),AI136:AL136))) | IF(OR(F136="",AN136=""),"",IF(COUNT(AI136:AM136)=0,"",AN136-LOOKUP(2,1/(AI136:AM136<>""),AI136:AM136))) | IF(OR(F136="",AO136=""),"",IF(COUNT(AI136:AN136)=0,"",AO136-LOOKUP(2,1/(AI136:AN136<>""),AI136:AN136))) | IF(OR(F136="",AP136=""),"",IF(COUNT(AI136:AO136)=0,"",AP136-LOOKUP(2,1/(AI136:AO136<>""),AI136:AO136))) | IF(OR(F136="",AQ136=""),"",IF(COUNT(AI136:AP136)=0,"",AQ136-LOOKUP(2,1/(AI136:AP136<>""),AI136:AP136))) | IF(OR(F136="",AR136=""),"",IF(COUNT(AI136:AQ136)=0,"",AR136-LOOKUP(2,1/(AI136:AQ136<>""),AI136:AQ136))) | IF(OR(F136="",AS136=""),"",IF(COUNT(AI136:AR136)=0,"",AS136-LOOKUP(2,1/(AI136:AR136<>""),AI136:AR136))) | IF(OR(F136="",AT136=""),"",IF(COUNT(AI136:AS136)=0,"",AT136-LOOKUP(2,1/(AI136:AS136<>""),AI136:AS136))) | IF(OR(F136="",AU136=""),"",IF(COUNT(AI136:AT136)=0,"",AU136-LOOKUP(2,1/(AI136:AT136<>""),AI136:AT136))) | IF(OR(F136="",AV136=""),"",IF(COUNT(AI136:AU136)=0,"",AV136-LOOKUP(2,1/(AI136:AU136<>""),AI136:AU136))) | IF(J136="","All_Provinces",IFERROR(VLOOKUP(J136,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K136="","All_Districts",IFERROR(VLOOKUP(K136,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F137="","",ROW()-3) | [18 empty] | IF(AQ137="","",AQ137) |  |  |  | IF(W137<>"",W137,IF(OR(T137="",V137=""),"",EDATE(T137,V137))) |  |  |  |  | IF(F137="","",IF(COUNT(AI137:AV137)=0,IF(AA137="","Not started",AA137),SUBSTITUTE(LOOKUP(2,1/(AI137:AV137<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F137="",COUNT(AI137:AV137)=0),"",TODAY()-LOOKUP(2,1/(AI137:AV137<>""),AI137:AV137)) | IF(OR(F137="",COUNT(AI137:AV137)<2),"",LOOKUP(2,1/(AI137:AV137<>""),AI137:AV137)-MIN(AI137:AV137)) | IF(OR(AD137="",AC137="Not started",AC137=""),"",IFERROR(AD137-IF(VLOOKUP(AC137,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC137,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F137="","",IF(OR(AA137="Cancelled",AC137="Cancelled"),"Cancelled",IF(OR(AC137="Completed / Handover",Y137<>"",Z137>=100),"Completed — on track",IF(O137="Not awarded",IF(U137="",IF(X137="","No planned date",IF(TODAY()>X137,"Behind — past planned date",IF(X137-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U137,"Behind — award date passed",IF(U137-TODAY()<=30,"At risk — close to off track","On track"))),IF(X137="","No planned date",IF(AND(TODAY()>X137,OR(Z137="",Z137<100)),"Behind — past end date",IF(AND(T137<>"",X137<>"",Z137<>"",(Z137<100),((TODAY()-T137)/MAX(X137-T137,1)*100)-Z137>15),"Behind — progress lag",IF(AND(X137-TODAY()<=30,X137-TODAY()>=0,OR(Z137="",Z137<90)),"At risk — close to off track","On track")))))))) | IF(OR(F137="",AC137="Completed / Handover",AC137="Cancelled"),"",IF(O137="Not awarded",IF(U137<>"",U137-TODAY(),IF(X137="","",X137-TODAY())),IF(X137="","",X137-TODAY()))) | [14 empty] | IF(OR(F137="",AJ137=""),"",IF(COUNT(AI137:AI137)=0,"",AJ137-LOOKUP(2,1/(AI137:AI137<>""),AI137:AI137))) | IF(OR(F137="",AK137=""),"",IF(COUNT(AI137:AJ137)=0,"",AK137-LOOKUP(2,1/(AI137:AJ137<>""),AI137:AJ137))) | IF(OR(F137="",AL137=""),"",IF(COUNT(AI137:AK137)=0,"",AL137-LOOKUP(2,1/(AI137:AK137<>""),AI137:AK137))) | IF(OR(F137="",AM137=""),"",IF(COUNT(AI137:AL137)=0,"",AM137-LOOKUP(2,1/(AI137:AL137<>""),AI137:AL137))) | IF(OR(F137="",AN137=""),"",IF(COUNT(AI137:AM137)=0,"",AN137-LOOKUP(2,1/(AI137:AM137<>""),AI137:AM137))) | IF(OR(F137="",AO137=""),"",IF(COUNT(AI137:AN137)=0,"",AO137-LOOKUP(2,1/(AI137:AN137<>""),AI137:AN137))) | IF(OR(F137="",AP137=""),"",IF(COUNT(AI137:AO137)=0,"",AP137-LOOKUP(2,1/(AI137:AO137<>""),AI137:AO137))) | IF(OR(F137="",AQ137=""),"",IF(COUNT(AI137:AP137)=0,"",AQ137-LOOKUP(2,1/(AI137:AP137<>""),AI137:AP137))) | IF(OR(F137="",AR137=""),"",IF(COUNT(AI137:AQ137)=0,"",AR137-LOOKUP(2,1/(AI137:AQ137<>""),AI137:AQ137))) | IF(OR(F137="",AS137=""),"",IF(COUNT(AI137:AR137)=0,"",AS137-LOOKUP(2,1/(AI137:AR137<>""),AI137:AR137))) | IF(OR(F137="",AT137=""),"",IF(COUNT(AI137:AS137)=0,"",AT137-LOOKUP(2,1/(AI137:AS137<>""),AI137:AS137))) | IF(OR(F137="",AU137=""),"",IF(COUNT(AI137:AT137)=0,"",AU137-LOOKUP(2,1/(AI137:AT137<>""),AI137:AT137))) | IF(OR(F137="",AV137=""),"",IF(COUNT(AI137:AU137)=0,"",AV137-LOOKUP(2,1/(AI137:AU137<>""),AI137:AU137))) | IF(J137="","All_Provinces",IFERROR(VLOOKUP(J137,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K137="","All_Districts",IFERROR(VLOOKUP(K137,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F138="","",ROW()-3) | [18 empty] | IF(AQ138="","",AQ138) |  |  |  | IF(W138<>"",W138,IF(OR(T138="",V138=""),"",EDATE(T138,V138))) |  |  |  |  | IF(F138="","",IF(COUNT(AI138:AV138)=0,IF(AA138="","Not started",AA138),SUBSTITUTE(LOOKUP(2,1/(AI138:AV138<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F138="",COUNT(AI138:AV138)=0),"",TODAY()-LOOKUP(2,1/(AI138:AV138<>""),AI138:AV138)) | IF(OR(F138="",COUNT(AI138:AV138)<2),"",LOOKUP(2,1/(AI138:AV138<>""),AI138:AV138)-MIN(AI138:AV138)) | IF(OR(AD138="",AC138="Not started",AC138=""),"",IFERROR(AD138-IF(VLOOKUP(AC138,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC138,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F138="","",IF(OR(AA138="Cancelled",AC138="Cancelled"),"Cancelled",IF(OR(AC138="Completed / Handover",Y138<>"",Z138>=100),"Completed — on track",IF(O138="Not awarded",IF(U138="",IF(X138="","No planned date",IF(TODAY()>X138,"Behind — past planned date",IF(X138-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U138,"Behind — award date passed",IF(U138-TODAY()<=30,"At risk — close to off track","On track"))),IF(X138="","No planned date",IF(AND(TODAY()>X138,OR(Z138="",Z138<100)),"Behind — past end date",IF(AND(T138<>"",X138<>"",Z138<>"",(Z138<100),((TODAY()-T138)/MAX(X138-T138,1)*100)-Z138>15),"Behind — progress lag",IF(AND(X138-TODAY()<=30,X138-TODAY()>=0,OR(Z138="",Z138<90)),"At risk — close to off track","On track")))))))) | IF(OR(F138="",AC138="Completed / Handover",AC138="Cancelled"),"",IF(O138="Not awarded",IF(U138<>"",U138-TODAY(),IF(X138="","",X138-TODAY())),IF(X138="","",X138-TODAY()))) | [14 empty] | IF(OR(F138="",AJ138=""),"",IF(COUNT(AI138:AI138)=0,"",AJ138-LOOKUP(2,1/(AI138:AI138<>""),AI138:AI138))) | IF(OR(F138="",AK138=""),"",IF(COUNT(AI138:AJ138)=0,"",AK138-LOOKUP(2,1/(AI138:AJ138<>""),AI138:AJ138))) | IF(OR(F138="",AL138=""),"",IF(COUNT(AI138:AK138)=0,"",AL138-LOOKUP(2,1/(AI138:AK138<>""),AI138:AK138))) | IF(OR(F138="",AM138=""),"",IF(COUNT(AI138:AL138)=0,"",AM138-LOOKUP(2,1/(AI138:AL138<>""),AI138:AL138))) | IF(OR(F138="",AN138=""),"",IF(COUNT(AI138:AM138)=0,"",AN138-LOOKUP(2,1/(AI138:AM138<>""),AI138:AM138))) | IF(OR(F138="",AO138=""),"",IF(COUNT(AI138:AN138)=0,"",AO138-LOOKUP(2,1/(AI138:AN138<>""),AI138:AN138))) | IF(OR(F138="",AP138=""),"",IF(COUNT(AI138:AO138)=0,"",AP138-LOOKUP(2,1/(AI138:AO138<>""),AI138:AO138))) | IF(OR(F138="",AQ138=""),"",IF(COUNT(AI138:AP138)=0,"",AQ138-LOOKUP(2,1/(AI138:AP138<>""),AI138:AP138))) | IF(OR(F138="",AR138=""),"",IF(COUNT(AI138:AQ138)=0,"",AR138-LOOKUP(2,1/(AI138:AQ138<>""),AI138:AQ138))) | IF(OR(F138="",AS138=""),"",IF(COUNT(AI138:AR138)=0,"",AS138-LOOKUP(2,1/(AI138:AR138<>""),AI138:AR138))) | IF(OR(F138="",AT138=""),"",IF(COUNT(AI138:AS138)=0,"",AT138-LOOKUP(2,1/(AI138:AS138<>""),AI138:AS138))) | IF(OR(F138="",AU138=""),"",IF(COUNT(AI138:AT138)=0,"",AU138-LOOKUP(2,1/(AI138:AT138<>""),AI138:AT138))) | IF(OR(F138="",AV138=""),"",IF(COUNT(AI138:AU138)=0,"",AV138-LOOKUP(2,1/(AI138:AU138<>""),AI138:AU138))) | IF(J138="","All_Provinces",IFERROR(VLOOKUP(J138,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K138="","All_Districts",IFERROR(VLOOKUP(K138,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F139="","",ROW()-3) | [18 empty] | IF(AQ139="","",AQ139) |  |  |  | IF(W139<>"",W139,IF(OR(T139="",V139=""),"",EDATE(T139,V139))) |  |  |  |  | IF(F139="","",IF(COUNT(AI139:AV139)=0,IF(AA139="","Not started",AA139),SUBSTITUTE(LOOKUP(2,1/(AI139:AV139<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F139="",COUNT(AI139:AV139)=0),"",TODAY()-LOOKUP(2,1/(AI139:AV139<>""),AI139:AV139)) | IF(OR(F139="",COUNT(AI139:AV139)<2),"",LOOKUP(2,1/(AI139:AV139<>""),AI139:AV139)-MIN(AI139:AV139)) | IF(OR(AD139="",AC139="Not started",AC139=""),"",IFERROR(AD139-IF(VLOOKUP(AC139,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC139,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F139="","",IF(OR(AA139="Cancelled",AC139="Cancelled"),"Cancelled",IF(OR(AC139="Completed / Handover",Y139<>"",Z139>=100),"Completed — on track",IF(O139="Not awarded",IF(U139="",IF(X139="","No planned date",IF(TODAY()>X139,"Behind — past planned date",IF(X139-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U139,"Behind — award date passed",IF(U139-TODAY()<=30,"At risk — close to off track","On track"))),IF(X139="","No planned date",IF(AND(TODAY()>X139,OR(Z139="",Z139<100)),"Behind — past end date",IF(AND(T139<>"",X139<>"",Z139<>"",(Z139<100),((TODAY()-T139)/MAX(X139-T139,1)*100)-Z139>15),"Behind — progress lag",IF(AND(X139-TODAY()<=30,X139-TODAY()>=0,OR(Z139="",Z139<90)),"At risk — close to off track","On track")))))))) | IF(OR(F139="",AC139="Completed / Handover",AC139="Cancelled"),"",IF(O139="Not awarded",IF(U139<>"",U139-TODAY(),IF(X139="","",X139-TODAY())),IF(X139="","",X139-TODAY()))) | [14 empty] | IF(OR(F139="",AJ139=""),"",IF(COUNT(AI139:AI139)=0,"",AJ139-LOOKUP(2,1/(AI139:AI139<>""),AI139:AI139))) | IF(OR(F139="",AK139=""),"",IF(COUNT(AI139:AJ139)=0,"",AK139-LOOKUP(2,1/(AI139:AJ139<>""),AI139:AJ139))) | IF(OR(F139="",AL139=""),"",IF(COUNT(AI139:AK139)=0,"",AL139-LOOKUP(2,1/(AI139:AK139<>""),AI139:AK139))) | IF(OR(F139="",AM139=""),"",IF(COUNT(AI139:AL139)=0,"",AM139-LOOKUP(2,1/(AI139:AL139<>""),AI139:AL139))) | IF(OR(F139="",AN139=""),"",IF(COUNT(AI139:AM139)=0,"",AN139-LOOKUP(2,1/(AI139:AM139<>""),AI139:AM139))) | IF(OR(F139="",AO139=""),"",IF(COUNT(AI139:AN139)=0,"",AO139-LOOKUP(2,1/(AI139:AN139<>""),AI139:AN139))) | IF(OR(F139="",AP139=""),"",IF(COUNT(AI139:AO139)=0,"",AP139-LOOKUP(2,1/(AI139:AO139<>""),AI139:AO139))) | IF(OR(F139="",AQ139=""),"",IF(COUNT(AI139:AP139)=0,"",AQ139-LOOKUP(2,1/(AI139:AP139<>""),AI139:AP139))) | IF(OR(F139="",AR139=""),"",IF(COUNT(AI139:AQ139)=0,"",AR139-LOOKUP(2,1/(AI139:AQ139<>""),AI139:AQ139))) | IF(OR(F139="",AS139=""),"",IF(COUNT(AI139:AR139)=0,"",AS139-LOOKUP(2,1/(AI139:AR139<>""),AI139:AR139))) | IF(OR(F139="",AT139=""),"",IF(COUNT(AI139:AS139)=0,"",AT139-LOOKUP(2,1/(AI139:AS139<>""),AI139:AS139))) | IF(OR(F139="",AU139=""),"",IF(COUNT(AI139:AT139)=0,"",AU139-LOOKUP(2,1/(AI139:AT139<>""),AI139:AT139))) | IF(OR(F139="",AV139=""),"",IF(COUNT(AI139:AU139)=0,"",AV139-LOOKUP(2,1/(AI139:AU139<>""),AI139:AU139))) | IF(J139="","All_Provinces",IFERROR(VLOOKUP(J139,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K139="","All_Districts",IFERROR(VLOOKUP(K139,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F140="","",ROW()-3) | [18 empty] | IF(AQ140="","",AQ140) |  |  |  | IF(W140<>"",W140,IF(OR(T140="",V140=""),"",EDATE(T140,V140))) |  |  |  |  | IF(F140="","",IF(COUNT(AI140:AV140)=0,IF(AA140="","Not started",AA140),SUBSTITUTE(LOOKUP(2,1/(AI140:AV140<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F140="",COUNT(AI140:AV140)=0),"",TODAY()-LOOKUP(2,1/(AI140:AV140<>""),AI140:AV140)) | IF(OR(F140="",COUNT(AI140:AV140)<2),"",LOOKUP(2,1/(AI140:AV140<>""),AI140:AV140)-MIN(AI140:AV140)) | IF(OR(AD140="",AC140="Not started",AC140=""),"",IFERROR(AD140-IF(VLOOKUP(AC140,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC140,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F140="","",IF(OR(AA140="Cancelled",AC140="Cancelled"),"Cancelled",IF(OR(AC140="Completed / Handover",Y140<>"",Z140>=100),"Completed — on track",IF(O140="Not awarded",IF(U140="",IF(X140="","No planned date",IF(TODAY()>X140,"Behind — past planned date",IF(X140-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U140,"Behind — award date passed",IF(U140-TODAY()<=30,"At risk — close to off track","On track"))),IF(X140="","No planned date",IF(AND(TODAY()>X140,OR(Z140="",Z140<100)),"Behind — past end date",IF(AND(T140<>"",X140<>"",Z140<>"",(Z140<100),((TODAY()-T140)/MAX(X140-T140,1)*100)-Z140>15),"Behind — progress lag",IF(AND(X140-TODAY()<=30,X140-TODAY()>=0,OR(Z140="",Z140<90)),"At risk — close to off track","On track")))))))) | IF(OR(F140="",AC140="Completed / Handover",AC140="Cancelled"),"",IF(O140="Not awarded",IF(U140<>"",U140-TODAY(),IF(X140="","",X140-TODAY())),IF(X140="","",X140-TODAY()))) | [14 empty] | IF(OR(F140="",AJ140=""),"",IF(COUNT(AI140:AI140)=0,"",AJ140-LOOKUP(2,1/(AI140:AI140<>""),AI140:AI140))) | IF(OR(F140="",AK140=""),"",IF(COUNT(AI140:AJ140)=0,"",AK140-LOOKUP(2,1/(AI140:AJ140<>""),AI140:AJ140))) | IF(OR(F140="",AL140=""),"",IF(COUNT(AI140:AK140)=0,"",AL140-LOOKUP(2,1/(AI140:AK140<>""),AI140:AK140))) | IF(OR(F140="",AM140=""),"",IF(COUNT(AI140:AL140)=0,"",AM140-LOOKUP(2,1/(AI140:AL140<>""),AI140:AL140))) | IF(OR(F140="",AN140=""),"",IF(COUNT(AI140:AM140)=0,"",AN140-LOOKUP(2,1/(AI140:AM140<>""),AI140:AM140))) | IF(OR(F140="",AO140=""),"",IF(COUNT(AI140:AN140)=0,"",AO140-LOOKUP(2,1/(AI140:AN140<>""),AI140:AN140))) | IF(OR(F140="",AP140=""),"",IF(COUNT(AI140:AO140)=0,"",AP140-LOOKUP(2,1/(AI140:AO140<>""),AI140:AO140))) | IF(OR(F140="",AQ140=""),"",IF(COUNT(AI140:AP140)=0,"",AQ140-LOOKUP(2,1/(AI140:AP140<>""),AI140:AP140))) | IF(OR(F140="",AR140=""),"",IF(COUNT(AI140:AQ140)=0,"",AR140-LOOKUP(2,1/(AI140:AQ140<>""),AI140:AQ140))) | IF(OR(F140="",AS140=""),"",IF(COUNT(AI140:AR140)=0,"",AS140-LOOKUP(2,1/(AI140:AR140<>""),AI140:AR140))) | IF(OR(F140="",AT140=""),"",IF(COUNT(AI140:AS140)=0,"",AT140-LOOKUP(2,1/(AI140:AS140<>""),AI140:AS140))) | IF(OR(F140="",AU140=""),"",IF(COUNT(AI140:AT140)=0,"",AU140-LOOKUP(2,1/(AI140:AT140<>""),AI140:AT140))) | IF(OR(F140="",AV140=""),"",IF(COUNT(AI140:AU140)=0,"",AV140-LOOKUP(2,1/(AI140:AU140<>""),AI140:AU140))) | IF(J140="","All_Provinces",IFERROR(VLOOKUP(J140,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K140="","All_Districts",IFERROR(VLOOKUP(K140,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F141="","",ROW()-3) | [18 empty] | IF(AQ141="","",AQ141) |  |  |  | IF(W141<>"",W141,IF(OR(T141="",V141=""),"",EDATE(T141,V141))) |  |  |  |  | IF(F141="","",IF(COUNT(AI141:AV141)=0,IF(AA141="","Not started",AA141),SUBSTITUTE(LOOKUP(2,1/(AI141:AV141<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F141="",COUNT(AI141:AV141)=0),"",TODAY()-LOOKUP(2,1/(AI141:AV141<>""),AI141:AV141)) | IF(OR(F141="",COUNT(AI141:AV141)<2),"",LOOKUP(2,1/(AI141:AV141<>""),AI141:AV141)-MIN(AI141:AV141)) | IF(OR(AD141="",AC141="Not started",AC141=""),"",IFERROR(AD141-IF(VLOOKUP(AC141,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC141,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F141="","",IF(OR(AA141="Cancelled",AC141="Cancelled"),"Cancelled",IF(OR(AC141="Completed / Handover",Y141<>"",Z141>=100),"Completed — on track",IF(O141="Not awarded",IF(U141="",IF(X141="","No planned date",IF(TODAY()>X141,"Behind — past planned date",IF(X141-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U141,"Behind — award date passed",IF(U141-TODAY()<=30,"At risk — close to off track","On track"))),IF(X141="","No planned date",IF(AND(TODAY()>X141,OR(Z141="",Z141<100)),"Behind — past end date",IF(AND(T141<>"",X141<>"",Z141<>"",(Z141<100),((TODAY()-T141)/MAX(X141-T141,1)*100)-Z141>15),"Behind — progress lag",IF(AND(X141-TODAY()<=30,X141-TODAY()>=0,OR(Z141="",Z141<90)),"At risk — close to off track","On track")))))))) | IF(OR(F141="",AC141="Completed / Handover",AC141="Cancelled"),"",IF(O141="Not awarded",IF(U141<>"",U141-TODAY(),IF(X141="","",X141-TODAY())),IF(X141="","",X141-TODAY()))) | [14 empty] | IF(OR(F141="",AJ141=""),"",IF(COUNT(AI141:AI141)=0,"",AJ141-LOOKUP(2,1/(AI141:AI141<>""),AI141:AI141))) | IF(OR(F141="",AK141=""),"",IF(COUNT(AI141:AJ141)=0,"",AK141-LOOKUP(2,1/(AI141:AJ141<>""),AI141:AJ141))) | IF(OR(F141="",AL141=""),"",IF(COUNT(AI141:AK141)=0,"",AL141-LOOKUP(2,1/(AI141:AK141<>""),AI141:AK141))) | IF(OR(F141="",AM141=""),"",IF(COUNT(AI141:AL141)=0,"",AM141-LOOKUP(2,1/(AI141:AL141<>""),AI141:AL141))) | IF(OR(F141="",AN141=""),"",IF(COUNT(AI141:AM141)=0,"",AN141-LOOKUP(2,1/(AI141:AM141<>""),AI141:AM141))) | IF(OR(F141="",AO141=""),"",IF(COUNT(AI141:AN141)=0,"",AO141-LOOKUP(2,1/(AI141:AN141<>""),AI141:AN141))) | IF(OR(F141="",AP141=""),"",IF(COUNT(AI141:AO141)=0,"",AP141-LOOKUP(2,1/(AI141:AO141<>""),AI141:AO141))) | IF(OR(F141="",AQ141=""),"",IF(COUNT(AI141:AP141)=0,"",AQ141-LOOKUP(2,1/(AI141:AP141<>""),AI141:AP141))) | IF(OR(F141="",AR141=""),"",IF(COUNT(AI141:AQ141)=0,"",AR141-LOOKUP(2,1/(AI141:AQ141<>""),AI141:AQ141))) | IF(OR(F141="",AS141=""),"",IF(COUNT(AI141:AR141)=0,"",AS141-LOOKUP(2,1/(AI141:AR141<>""),AI141:AR141))) | IF(OR(F141="",AT141=""),"",IF(COUNT(AI141:AS141)=0,"",AT141-LOOKUP(2,1/(AI141:AS141<>""),AI141:AS141))) | IF(OR(F141="",AU141=""),"",IF(COUNT(AI141:AT141)=0,"",AU141-LOOKUP(2,1/(AI141:AT141<>""),AI141:AT141))) | IF(OR(F141="",AV141=""),"",IF(COUNT(AI141:AU141)=0,"",AV141-LOOKUP(2,1/(AI141:AU141<>""),AI141:AU141))) | IF(J141="","All_Provinces",IFERROR(VLOOKUP(J141,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K141="","All_Districts",IFERROR(VLOOKUP(K141,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F142="","",ROW()-3) | [18 empty] | IF(AQ142="","",AQ142) |  |  |  | IF(W142<>"",W142,IF(OR(T142="",V142=""),"",EDATE(T142,V142))) |  |  |  |  | IF(F142="","",IF(COUNT(AI142:AV142)=0,IF(AA142="","Not started",AA142),SUBSTITUTE(LOOKUP(2,1/(AI142:AV142<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F142="",COUNT(AI142:AV142)=0),"",TODAY()-LOOKUP(2,1/(AI142:AV142<>""),AI142:AV142)) | IF(OR(F142="",COUNT(AI142:AV142)<2),"",LOOKUP(2,1/(AI142:AV142<>""),AI142:AV142)-MIN(AI142:AV142)) | IF(OR(AD142="",AC142="Not started",AC142=""),"",IFERROR(AD142-IF(VLOOKUP(AC142,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC142,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F142="","",IF(OR(AA142="Cancelled",AC142="Cancelled"),"Cancelled",IF(OR(AC142="Completed / Handover",Y142<>"",Z142>=100),"Completed — on track",IF(O142="Not awarded",IF(U142="",IF(X142="","No planned date",IF(TODAY()>X142,"Behind — past planned date",IF(X142-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U142,"Behind — award date passed",IF(U142-TODAY()<=30,"At risk — close to off track","On track"))),IF(X142="","No planned date",IF(AND(TODAY()>X142,OR(Z142="",Z142<100)),"Behind — past end date",IF(AND(T142<>"",X142<>"",Z142<>"",(Z142<100),((TODAY()-T142)/MAX(X142-T142,1)*100)-Z142>15),"Behind — progress lag",IF(AND(X142-TODAY()<=30,X142-TODAY()>=0,OR(Z142="",Z142<90)),"At risk — close to off track","On track")))))))) | IF(OR(F142="",AC142="Completed / Handover",AC142="Cancelled"),"",IF(O142="Not awarded",IF(U142<>"",U142-TODAY(),IF(X142="","",X142-TODAY())),IF(X142="","",X142-TODAY()))) | [14 empty] | IF(OR(F142="",AJ142=""),"",IF(COUNT(AI142:AI142)=0,"",AJ142-LOOKUP(2,1/(AI142:AI142<>""),AI142:AI142))) | IF(OR(F142="",AK142=""),"",IF(COUNT(AI142:AJ142)=0,"",AK142-LOOKUP(2,1/(AI142:AJ142<>""),AI142:AJ142))) | IF(OR(F142="",AL142=""),"",IF(COUNT(AI142:AK142)=0,"",AL142-LOOKUP(2,1/(AI142:AK142<>""),AI142:AK142))) | IF(OR(F142="",AM142=""),"",IF(COUNT(AI142:AL142)=0,"",AM142-LOOKUP(2,1/(AI142:AL142<>""),AI142:AL142))) | IF(OR(F142="",AN142=""),"",IF(COUNT(AI142:AM142)=0,"",AN142-LOOKUP(2,1/(AI142:AM142<>""),AI142:AM142))) | IF(OR(F142="",AO142=""),"",IF(COUNT(AI142:AN142)=0,"",AO142-LOOKUP(2,1/(AI142:AN142<>""),AI142:AN142))) | IF(OR(F142="",AP142=""),"",IF(COUNT(AI142:AO142)=0,"",AP142-LOOKUP(2,1/(AI142:AO142<>""),AI142:AO142))) | IF(OR(F142="",AQ142=""),"",IF(COUNT(AI142:AP142)=0,"",AQ142-LOOKUP(2,1/(AI142:AP142<>""),AI142:AP142))) | IF(OR(F142="",AR142=""),"",IF(COUNT(AI142:AQ142)=0,"",AR142-LOOKUP(2,1/(AI142:AQ142<>""),AI142:AQ142))) | IF(OR(F142="",AS142=""),"",IF(COUNT(AI142:AR142)=0,"",AS142-LOOKUP(2,1/(AI142:AR142<>""),AI142:AR142))) | IF(OR(F142="",AT142=""),"",IF(COUNT(AI142:AS142)=0,"",AT142-LOOKUP(2,1/(AI142:AS142<>""),AI142:AS142))) | IF(OR(F142="",AU142=""),"",IF(COUNT(AI142:AT142)=0,"",AU142-LOOKUP(2,1/(AI142:AT142<>""),AI142:AT142))) | IF(OR(F142="",AV142=""),"",IF(COUNT(AI142:AU142)=0,"",AV142-LOOKUP(2,1/(AI142:AU142<>""),AI142:AU142))) | IF(J142="","All_Provinces",IFERROR(VLOOKUP(J142,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K142="","All_Districts",IFERROR(VLOOKUP(K142,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F143="","",ROW()-3) | [18 empty] | IF(AQ143="","",AQ143) |  |  |  | IF(W143<>"",W143,IF(OR(T143="",V143=""),"",EDATE(T143,V143))) |  |  |  |  | IF(F143="","",IF(COUNT(AI143:AV143)=0,IF(AA143="","Not started",AA143),SUBSTITUTE(LOOKUP(2,1/(AI143:AV143<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F143="",COUNT(AI143:AV143)=0),"",TODAY()-LOOKUP(2,1/(AI143:AV143<>""),AI143:AV143)) | IF(OR(F143="",COUNT(AI143:AV143)<2),"",LOOKUP(2,1/(AI143:AV143<>""),AI143:AV143)-MIN(AI143:AV143)) | IF(OR(AD143="",AC143="Not started",AC143=""),"",IFERROR(AD143-IF(VLOOKUP(AC143,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC143,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F143="","",IF(OR(AA143="Cancelled",AC143="Cancelled"),"Cancelled",IF(OR(AC143="Completed / Handover",Y143<>"",Z143>=100),"Completed — on track",IF(O143="Not awarded",IF(U143="",IF(X143="","No planned date",IF(TODAY()>X143,"Behind — past planned date",IF(X143-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U143,"Behind — award date passed",IF(U143-TODAY()<=30,"At risk — close to off track","On track"))),IF(X143="","No planned date",IF(AND(TODAY()>X143,OR(Z143="",Z143<100)),"Behind — past end date",IF(AND(T143<>"",X143<>"",Z143<>"",(Z143<100),((TODAY()-T143)/MAX(X143-T143,1)*100)-Z143>15),"Behind — progress lag",IF(AND(X143-TODAY()<=30,X143-TODAY()>=0,OR(Z143="",Z143<90)),"At risk — close to off track","On track")))))))) | IF(OR(F143="",AC143="Completed / Handover",AC143="Cancelled"),"",IF(O143="Not awarded",IF(U143<>"",U143-TODAY(),IF(X143="","",X143-TODAY())),IF(X143="","",X143-TODAY()))) | [14 empty] | IF(OR(F143="",AJ143=""),"",IF(COUNT(AI143:AI143)=0,"",AJ143-LOOKUP(2,1/(AI143:AI143<>""),AI143:AI143))) | IF(OR(F143="",AK143=""),"",IF(COUNT(AI143:AJ143)=0,"",AK143-LOOKUP(2,1/(AI143:AJ143<>""),AI143:AJ143))) | IF(OR(F143="",AL143=""),"",IF(COUNT(AI143:AK143)=0,"",AL143-LOOKUP(2,1/(AI143:AK143<>""),AI143:AK143))) | IF(OR(F143="",AM143=""),"",IF(COUNT(AI143:AL143)=0,"",AM143-LOOKUP(2,1/(AI143:AL143<>""),AI143:AL143))) | IF(OR(F143="",AN143=""),"",IF(COUNT(AI143:AM143)=0,"",AN143-LOOKUP(2,1/(AI143:AM143<>""),AI143:AM143))) | IF(OR(F143="",AO143=""),"",IF(COUNT(AI143:AN143)=0,"",AO143-LOOKUP(2,1/(AI143:AN143<>""),AI143:AN143))) | IF(OR(F143="",AP143=""),"",IF(COUNT(AI143:AO143)=0,"",AP143-LOOKUP(2,1/(AI143:AO143<>""),AI143:AO143))) | IF(OR(F143="",AQ143=""),"",IF(COUNT(AI143:AP143)=0,"",AQ143-LOOKUP(2,1/(AI143:AP143<>""),AI143:AP143))) | IF(OR(F143="",AR143=""),"",IF(COUNT(AI143:AQ143)=0,"",AR143-LOOKUP(2,1/(AI143:AQ143<>""),AI143:AQ143))) | IF(OR(F143="",AS143=""),"",IF(COUNT(AI143:AR143)=0,"",AS143-LOOKUP(2,1/(AI143:AR143<>""),AI143:AR143))) | IF(OR(F143="",AT143=""),"",IF(COUNT(AI143:AS143)=0,"",AT143-LOOKUP(2,1/(AI143:AS143<>""),AI143:AS143))) | IF(OR(F143="",AU143=""),"",IF(COUNT(AI143:AT143)=0,"",AU143-LOOKUP(2,1/(AI143:AT143<>""),AI143:AT143))) | IF(OR(F143="",AV143=""),"",IF(COUNT(AI143:AU143)=0,"",AV143-LOOKUP(2,1/(AI143:AU143<>""),AI143:AU143))) | IF(J143="","All_Provinces",IFERROR(VLOOKUP(J143,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K143="","All_Districts",IFERROR(VLOOKUP(K143,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F144="","",ROW()-3) | [18 empty] | IF(AQ144="","",AQ144) |  |  |  | IF(W144<>"",W144,IF(OR(T144="",V144=""),"",EDATE(T144,V144))) |  |  |  |  | IF(F144="","",IF(COUNT(AI144:AV144)=0,IF(AA144="","Not started",AA144),SUBSTITUTE(LOOKUP(2,1/(AI144:AV144<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F144="",COUNT(AI144:AV144)=0),"",TODAY()-LOOKUP(2,1/(AI144:AV144<>""),AI144:AV144)) | IF(OR(F144="",COUNT(AI144:AV144)<2),"",LOOKUP(2,1/(AI144:AV144<>""),AI144:AV144)-MIN(AI144:AV144)) | IF(OR(AD144="",AC144="Not started",AC144=""),"",IFERROR(AD144-IF(VLOOKUP(AC144,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC144,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F144="","",IF(OR(AA144="Cancelled",AC144="Cancelled"),"Cancelled",IF(OR(AC144="Completed / Handover",Y144<>"",Z144>=100),"Completed — on track",IF(O144="Not awarded",IF(U144="",IF(X144="","No planned date",IF(TODAY()>X144,"Behind — past planned date",IF(X144-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U144,"Behind — award date passed",IF(U144-TODAY()<=30,"At risk — close to off track","On track"))),IF(X144="","No planned date",IF(AND(TODAY()>X144,OR(Z144="",Z144<100)),"Behind — past end date",IF(AND(T144<>"",X144<>"",Z144<>"",(Z144<100),((TODAY()-T144)/MAX(X144-T144,1)*100)-Z144>15),"Behind — progress lag",IF(AND(X144-TODAY()<=30,X144-TODAY()>=0,OR(Z144="",Z144<90)),"At risk — close to off track","On track")))))))) | IF(OR(F144="",AC144="Completed / Handover",AC144="Cancelled"),"",IF(O144="Not awarded",IF(U144<>"",U144-TODAY(),IF(X144="","",X144-TODAY())),IF(X144="","",X144-TODAY()))) | [14 empty] | IF(OR(F144="",AJ144=""),"",IF(COUNT(AI144:AI144)=0,"",AJ144-LOOKUP(2,1/(AI144:AI144<>""),AI144:AI144))) | IF(OR(F144="",AK144=""),"",IF(COUNT(AI144:AJ144)=0,"",AK144-LOOKUP(2,1/(AI144:AJ144<>""),AI144:AJ144))) | IF(OR(F144="",AL144=""),"",IF(COUNT(AI144:AK144)=0,"",AL144-LOOKUP(2,1/(AI144:AK144<>""),AI144:AK144))) | IF(OR(F144="",AM144=""),"",IF(COUNT(AI144:AL144)=0,"",AM144-LOOKUP(2,1/(AI144:AL144<>""),AI144:AL144))) | IF(OR(F144="",AN144=""),"",IF(COUNT(AI144:AM144)=0,"",AN144-LOOKUP(2,1/(AI144:AM144<>""),AI144:AM144))) | IF(OR(F144="",AO144=""),"",IF(COUNT(AI144:AN144)=0,"",AO144-LOOKUP(2,1/(AI144:AN144<>""),AI144:AN144))) | IF(OR(F144="",AP144=""),"",IF(COUNT(AI144:AO144)=0,"",AP144-LOOKUP(2,1/(AI144:AO144<>""),AI144:AO144))) | IF(OR(F144="",AQ144=""),"",IF(COUNT(AI144:AP144)=0,"",AQ144-LOOKUP(2,1/(AI144:AP144<>""),AI144:AP144))) | IF(OR(F144="",AR144=""),"",IF(COUNT(AI144:AQ144)=0,"",AR144-LOOKUP(2,1/(AI144:AQ144<>""),AI144:AQ144))) | IF(OR(F144="",AS144=""),"",IF(COUNT(AI144:AR144)=0,"",AS144-LOOKUP(2,1/(AI144:AR144<>""),AI144:AR144))) | IF(OR(F144="",AT144=""),"",IF(COUNT(AI144:AS144)=0,"",AT144-LOOKUP(2,1/(AI144:AS144<>""),AI144:AS144))) | IF(OR(F144="",AU144=""),"",IF(COUNT(AI144:AT144)=0,"",AU144-LOOKUP(2,1/(AI144:AT144<>""),AI144:AT144))) | IF(OR(F144="",AV144=""),"",IF(COUNT(AI144:AU144)=0,"",AV144-LOOKUP(2,1/(AI144:AU144<>""),AI144:AU144))) | IF(J144="","All_Provinces",IFERROR(VLOOKUP(J144,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K144="","All_Districts",IFERROR(VLOOKUP(K144,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F145="","",ROW()-3) | [18 empty] | IF(AQ145="","",AQ145) |  |  |  | IF(W145<>"",W145,IF(OR(T145="",V145=""),"",EDATE(T145,V145))) |  |  |  |  | IF(F145="","",IF(COUNT(AI145:AV145)=0,IF(AA145="","Not started",AA145),SUBSTITUTE(LOOKUP(2,1/(AI145:AV145<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F145="",COUNT(AI145:AV145)=0),"",TODAY()-LOOKUP(2,1/(AI145:AV145<>""),AI145:AV145)) | IF(OR(F145="",COUNT(AI145:AV145)<2),"",LOOKUP(2,1/(AI145:AV145<>""),AI145:AV145)-MIN(AI145:AV145)) | IF(OR(AD145="",AC145="Not started",AC145=""),"",IFERROR(AD145-IF(VLOOKUP(AC145,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC145,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F145="","",IF(OR(AA145="Cancelled",AC145="Cancelled"),"Cancelled",IF(OR(AC145="Completed / Handover",Y145<>"",Z145>=100),"Completed — on track",IF(O145="Not awarded",IF(U145="",IF(X145="","No planned date",IF(TODAY()>X145,"Behind — past planned date",IF(X145-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U145,"Behind — award date passed",IF(U145-TODAY()<=30,"At risk — close to off track","On track"))),IF(X145="","No planned date",IF(AND(TODAY()>X145,OR(Z145="",Z145<100)),"Behind — past end date",IF(AND(T145<>"",X145<>"",Z145<>"",(Z145<100),((TODAY()-T145)/MAX(X145-T145,1)*100)-Z145>15),"Behind — progress lag",IF(AND(X145-TODAY()<=30,X145-TODAY()>=0,OR(Z145="",Z145<90)),"At risk — close to off track","On track")))))))) | IF(OR(F145="",AC145="Completed / Handover",AC145="Cancelled"),"",IF(O145="Not awarded",IF(U145<>"",U145-TODAY(),IF(X145="","",X145-TODAY())),IF(X145="","",X145-TODAY()))) | [14 empty] | IF(OR(F145="",AJ145=""),"",IF(COUNT(AI145:AI145)=0,"",AJ145-LOOKUP(2,1/(AI145:AI145<>""),AI145:AI145))) | IF(OR(F145="",AK145=""),"",IF(COUNT(AI145:AJ145)=0,"",AK145-LOOKUP(2,1/(AI145:AJ145<>""),AI145:AJ145))) | IF(OR(F145="",AL145=""),"",IF(COUNT(AI145:AK145)=0,"",AL145-LOOKUP(2,1/(AI145:AK145<>""),AI145:AK145))) | IF(OR(F145="",AM145=""),"",IF(COUNT(AI145:AL145)=0,"",AM145-LOOKUP(2,1/(AI145:AL145<>""),AI145:AL145))) | IF(OR(F145="",AN145=""),"",IF(COUNT(AI145:AM145)=0,"",AN145-LOOKUP(2,1/(AI145:AM145<>""),AI145:AM145))) | IF(OR(F145="",AO145=""),"",IF(COUNT(AI145:AN145)=0,"",AO145-LOOKUP(2,1/(AI145:AN145<>""),AI145:AN145))) | IF(OR(F145="",AP145=""),"",IF(COUNT(AI145:AO145)=0,"",AP145-LOOKUP(2,1/(AI145:AO145<>""),AI145:AO145))) | IF(OR(F145="",AQ145=""),"",IF(COUNT(AI145:AP145)=0,"",AQ145-LOOKUP(2,1/(AI145:AP145<>""),AI145:AP145))) | IF(OR(F145="",AR145=""),"",IF(COUNT(AI145:AQ145)=0,"",AR145-LOOKUP(2,1/(AI145:AQ145<>""),AI145:AQ145))) | IF(OR(F145="",AS145=""),"",IF(COUNT(AI145:AR145)=0,"",AS145-LOOKUP(2,1/(AI145:AR145<>""),AI145:AR145))) | IF(OR(F145="",AT145=""),"",IF(COUNT(AI145:AS145)=0,"",AT145-LOOKUP(2,1/(AI145:AS145<>""),AI145:AS145))) | IF(OR(F145="",AU145=""),"",IF(COUNT(AI145:AT145)=0,"",AU145-LOOKUP(2,1/(AI145:AT145<>""),AI145:AT145))) | IF(OR(F145="",AV145=""),"",IF(COUNT(AI145:AU145)=0,"",AV145-LOOKUP(2,1/(AI145:AU145<>""),AI145:AU145))) | IF(J145="","All_Provinces",IFERROR(VLOOKUP(J145,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K145="","All_Districts",IFERROR(VLOOKUP(K145,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F146="","",ROW()-3) | [18 empty] | IF(AQ146="","",AQ146) |  |  |  | IF(W146<>"",W146,IF(OR(T146="",V146=""),"",EDATE(T146,V146))) |  |  |  |  | IF(F146="","",IF(COUNT(AI146:AV146)=0,IF(AA146="","Not started",AA146),SUBSTITUTE(LOOKUP(2,1/(AI146:AV146<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F146="",COUNT(AI146:AV146)=0),"",TODAY()-LOOKUP(2,1/(AI146:AV146<>""),AI146:AV146)) | IF(OR(F146="",COUNT(AI146:AV146)<2),"",LOOKUP(2,1/(AI146:AV146<>""),AI146:AV146)-MIN(AI146:AV146)) | IF(OR(AD146="",AC146="Not started",AC146=""),"",IFERROR(AD146-IF(VLOOKUP(AC146,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC146,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F146="","",IF(OR(AA146="Cancelled",AC146="Cancelled"),"Cancelled",IF(OR(AC146="Completed / Handover",Y146<>"",Z146>=100),"Completed — on track",IF(O146="Not awarded",IF(U146="",IF(X146="","No planned date",IF(TODAY()>X146,"Behind — past planned date",IF(X146-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U146,"Behind — award date passed",IF(U146-TODAY()<=30,"At risk — close to off track","On track"))),IF(X146="","No planned date",IF(AND(TODAY()>X146,OR(Z146="",Z146<100)),"Behind — past end date",IF(AND(T146<>"",X146<>"",Z146<>"",(Z146<100),((TODAY()-T146)/MAX(X146-T146,1)*100)-Z146>15),"Behind — progress lag",IF(AND(X146-TODAY()<=30,X146-TODAY()>=0,OR(Z146="",Z146<90)),"At risk — close to off track","On track")))))))) | IF(OR(F146="",AC146="Completed / Handover",AC146="Cancelled"),"",IF(O146="Not awarded",IF(U146<>"",U146-TODAY(),IF(X146="","",X146-TODAY())),IF(X146="","",X146-TODAY()))) | [14 empty] | IF(OR(F146="",AJ146=""),"",IF(COUNT(AI146:AI146)=0,"",AJ146-LOOKUP(2,1/(AI146:AI146<>""),AI146:AI146))) | IF(OR(F146="",AK146=""),"",IF(COUNT(AI146:AJ146)=0,"",AK146-LOOKUP(2,1/(AI146:AJ146<>""),AI146:AJ146))) | IF(OR(F146="",AL146=""),"",IF(COUNT(AI146:AK146)=0,"",AL146-LOOKUP(2,1/(AI146:AK146<>""),AI146:AK146))) | IF(OR(F146="",AM146=""),"",IF(COUNT(AI146:AL146)=0,"",AM146-LOOKUP(2,1/(AI146:AL146<>""),AI146:AL146))) | IF(OR(F146="",AN146=""),"",IF(COUNT(AI146:AM146)=0,"",AN146-LOOKUP(2,1/(AI146:AM146<>""),AI146:AM146))) | IF(OR(F146="",AO146=""),"",IF(COUNT(AI146:AN146)=0,"",AO146-LOOKUP(2,1/(AI146:AN146<>""),AI146:AN146))) | IF(OR(F146="",AP146=""),"",IF(COUNT(AI146:AO146)=0,"",AP146-LOOKUP(2,1/(AI146:AO146<>""),AI146:AO146))) | IF(OR(F146="",AQ146=""),"",IF(COUNT(AI146:AP146)=0,"",AQ146-LOOKUP(2,1/(AI146:AP146<>""),AI146:AP146))) | IF(OR(F146="",AR146=""),"",IF(COUNT(AI146:AQ146)=0,"",AR146-LOOKUP(2,1/(AI146:AQ146<>""),AI146:AQ146))) | IF(OR(F146="",AS146=""),"",IF(COUNT(AI146:AR146)=0,"",AS146-LOOKUP(2,1/(AI146:AR146<>""),AI146:AR146))) | IF(OR(F146="",AT146=""),"",IF(COUNT(AI146:AS146)=0,"",AT146-LOOKUP(2,1/(AI146:AS146<>""),AI146:AS146))) | IF(OR(F146="",AU146=""),"",IF(COUNT(AI146:AT146)=0,"",AU146-LOOKUP(2,1/(AI146:AT146<>""),AI146:AT146))) | IF(OR(F146="",AV146=""),"",IF(COUNT(AI146:AU146)=0,"",AV146-LOOKUP(2,1/(AI146:AU146<>""),AI146:AU146))) | IF(J146="","All_Provinces",IFERROR(VLOOKUP(J146,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K146="","All_Districts",IFERROR(VLOOKUP(K146,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F147="","",ROW()-3) | [18 empty] | IF(AQ147="","",AQ147) |  |  |  | IF(W147<>"",W147,IF(OR(T147="",V147=""),"",EDATE(T147,V147))) |  |  |  |  | IF(F147="","",IF(COUNT(AI147:AV147)=0,IF(AA147="","Not started",AA147),SUBSTITUTE(LOOKUP(2,1/(AI147:AV147<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F147="",COUNT(AI147:AV147)=0),"",TODAY()-LOOKUP(2,1/(AI147:AV147<>""),AI147:AV147)) | IF(OR(F147="",COUNT(AI147:AV147)<2),"",LOOKUP(2,1/(AI147:AV147<>""),AI147:AV147)-MIN(AI147:AV147)) | IF(OR(AD147="",AC147="Not started",AC147=""),"",IFERROR(AD147-IF(VLOOKUP(AC147,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC147,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F147="","",IF(OR(AA147="Cancelled",AC147="Cancelled"),"Cancelled",IF(OR(AC147="Completed / Handover",Y147<>"",Z147>=100),"Completed — on track",IF(O147="Not awarded",IF(U147="",IF(X147="","No planned date",IF(TODAY()>X147,"Behind — past planned date",IF(X147-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U147,"Behind — award date passed",IF(U147-TODAY()<=30,"At risk — close to off track","On track"))),IF(X147="","No planned date",IF(AND(TODAY()>X147,OR(Z147="",Z147<100)),"Behind — past end date",IF(AND(T147<>"",X147<>"",Z147<>"",(Z147<100),((TODAY()-T147)/MAX(X147-T147,1)*100)-Z147>15),"Behind — progress lag",IF(AND(X147-TODAY()<=30,X147-TODAY()>=0,OR(Z147="",Z147<90)),"At risk — close to off track","On track")))))))) | IF(OR(F147="",AC147="Completed / Handover",AC147="Cancelled"),"",IF(O147="Not awarded",IF(U147<>"",U147-TODAY(),IF(X147="","",X147-TODAY())),IF(X147="","",X147-TODAY()))) | [14 empty] | IF(OR(F147="",AJ147=""),"",IF(COUNT(AI147:AI147)=0,"",AJ147-LOOKUP(2,1/(AI147:AI147<>""),AI147:AI147))) | IF(OR(F147="",AK147=""),"",IF(COUNT(AI147:AJ147)=0,"",AK147-LOOKUP(2,1/(AI147:AJ147<>""),AI147:AJ147))) | IF(OR(F147="",AL147=""),"",IF(COUNT(AI147:AK147)=0,"",AL147-LOOKUP(2,1/(AI147:AK147<>""),AI147:AK147))) | IF(OR(F147="",AM147=""),"",IF(COUNT(AI147:AL147)=0,"",AM147-LOOKUP(2,1/(AI147:AL147<>""),AI147:AL147))) | IF(OR(F147="",AN147=""),"",IF(COUNT(AI147:AM147)=0,"",AN147-LOOKUP(2,1/(AI147:AM147<>""),AI147:AM147))) | IF(OR(F147="",AO147=""),"",IF(COUNT(AI147:AN147)=0,"",AO147-LOOKUP(2,1/(AI147:AN147<>""),AI147:AN147))) | IF(OR(F147="",AP147=""),"",IF(COUNT(AI147:AO147)=0,"",AP147-LOOKUP(2,1/(AI147:AO147<>""),AI147:AO147))) | IF(OR(F147="",AQ147=""),"",IF(COUNT(AI147:AP147)=0,"",AQ147-LOOKUP(2,1/(AI147:AP147<>""),AI147:AP147))) | IF(OR(F147="",AR147=""),"",IF(COUNT(AI147:AQ147)=0,"",AR147-LOOKUP(2,1/(AI147:AQ147<>""),AI147:AQ147))) | IF(OR(F147="",AS147=""),"",IF(COUNT(AI147:AR147)=0,"",AS147-LOOKUP(2,1/(AI147:AR147<>""),AI147:AR147))) | IF(OR(F147="",AT147=""),"",IF(COUNT(AI147:AS147)=0,"",AT147-LOOKUP(2,1/(AI147:AS147<>""),AI147:AS147))) | IF(OR(F147="",AU147=""),"",IF(COUNT(AI147:AT147)=0,"",AU147-LOOKUP(2,1/(AI147:AT147<>""),AI147:AT147))) | IF(OR(F147="",AV147=""),"",IF(COUNT(AI147:AU147)=0,"",AV147-LOOKUP(2,1/(AI147:AU147<>""),AI147:AU147))) | IF(J147="","All_Provinces",IFERROR(VLOOKUP(J147,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K147="","All_Districts",IFERROR(VLOOKUP(K147,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F148="","",ROW()-3) | [18 empty] | IF(AQ148="","",AQ148) |  |  |  | IF(W148<>"",W148,IF(OR(T148="",V148=""),"",EDATE(T148,V148))) |  |  |  |  | IF(F148="","",IF(COUNT(AI148:AV148)=0,IF(AA148="","Not started",AA148),SUBSTITUTE(LOOKUP(2,1/(AI148:AV148<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F148="",COUNT(AI148:AV148)=0),"",TODAY()-LOOKUP(2,1/(AI148:AV148<>""),AI148:AV148)) | IF(OR(F148="",COUNT(AI148:AV148)<2),"",LOOKUP(2,1/(AI148:AV148<>""),AI148:AV148)-MIN(AI148:AV148)) | IF(OR(AD148="",AC148="Not started",AC148=""),"",IFERROR(AD148-IF(VLOOKUP(AC148,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC148,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F148="","",IF(OR(AA148="Cancelled",AC148="Cancelled"),"Cancelled",IF(OR(AC148="Completed / Handover",Y148<>"",Z148>=100),"Completed — on track",IF(O148="Not awarded",IF(U148="",IF(X148="","No planned date",IF(TODAY()>X148,"Behind — past planned date",IF(X148-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U148,"Behind — award date passed",IF(U148-TODAY()<=30,"At risk — close to off track","On track"))),IF(X148="","No planned date",IF(AND(TODAY()>X148,OR(Z148="",Z148<100)),"Behind — past end date",IF(AND(T148<>"",X148<>"",Z148<>"",(Z148<100),((TODAY()-T148)/MAX(X148-T148,1)*100)-Z148>15),"Behind — progress lag",IF(AND(X148-TODAY()<=30,X148-TODAY()>=0,OR(Z148="",Z148<90)),"At risk — close to off track","On track")))))))) | IF(OR(F148="",AC148="Completed / Handover",AC148="Cancelled"),"",IF(O148="Not awarded",IF(U148<>"",U148-TODAY(),IF(X148="","",X148-TODAY())),IF(X148="","",X148-TODAY()))) | [14 empty] | IF(OR(F148="",AJ148=""),"",IF(COUNT(AI148:AI148)=0,"",AJ148-LOOKUP(2,1/(AI148:AI148<>""),AI148:AI148))) | IF(OR(F148="",AK148=""),"",IF(COUNT(AI148:AJ148)=0,"",AK148-LOOKUP(2,1/(AI148:AJ148<>""),AI148:AJ148))) | IF(OR(F148="",AL148=""),"",IF(COUNT(AI148:AK148)=0,"",AL148-LOOKUP(2,1/(AI148:AK148<>""),AI148:AK148))) | IF(OR(F148="",AM148=""),"",IF(COUNT(AI148:AL148)=0,"",AM148-LOOKUP(2,1/(AI148:AL148<>""),AI148:AL148))) | IF(OR(F148="",AN148=""),"",IF(COUNT(AI148:AM148)=0,"",AN148-LOOKUP(2,1/(AI148:AM148<>""),AI148:AM148))) | IF(OR(F148="",AO148=""),"",IF(COUNT(AI148:AN148)=0,"",AO148-LOOKUP(2,1/(AI148:AN148<>""),AI148:AN148))) | IF(OR(F148="",AP148=""),"",IF(COUNT(AI148:AO148)=0,"",AP148-LOOKUP(2,1/(AI148:AO148<>""),AI148:AO148))) | IF(OR(F148="",AQ148=""),"",IF(COUNT(AI148:AP148)=0,"",AQ148-LOOKUP(2,1/(AI148:AP148<>""),AI148:AP148))) | IF(OR(F148="",AR148=""),"",IF(COUNT(AI148:AQ148)=0,"",AR148-LOOKUP(2,1/(AI148:AQ148<>""),AI148:AQ148))) | IF(OR(F148="",AS148=""),"",IF(COUNT(AI148:AR148)=0,"",AS148-LOOKUP(2,1/(AI148:AR148<>""),AI148:AR148))) | IF(OR(F148="",AT148=""),"",IF(COUNT(AI148:AS148)=0,"",AT148-LOOKUP(2,1/(AI148:AS148<>""),AI148:AS148))) | IF(OR(F148="",AU148=""),"",IF(COUNT(AI148:AT148)=0,"",AU148-LOOKUP(2,1/(AI148:AT148<>""),AI148:AT148))) | IF(OR(F148="",AV148=""),"",IF(COUNT(AI148:AU148)=0,"",AV148-LOOKUP(2,1/(AI148:AU148<>""),AI148:AU148))) | IF(J148="","All_Provinces",IFERROR(VLOOKUP(J148,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K148="","All_Districts",IFERROR(VLOOKUP(K148,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F149="","",ROW()-3) | [18 empty] | IF(AQ149="","",AQ149) |  |  |  | IF(W149<>"",W149,IF(OR(T149="",V149=""),"",EDATE(T149,V149))) |  |  |  |  | IF(F149="","",IF(COUNT(AI149:AV149)=0,IF(AA149="","Not started",AA149),SUBSTITUTE(LOOKUP(2,1/(AI149:AV149<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F149="",COUNT(AI149:AV149)=0),"",TODAY()-LOOKUP(2,1/(AI149:AV149<>""),AI149:AV149)) | IF(OR(F149="",COUNT(AI149:AV149)<2),"",LOOKUP(2,1/(AI149:AV149<>""),AI149:AV149)-MIN(AI149:AV149)) | IF(OR(AD149="",AC149="Not started",AC149=""),"",IFERROR(AD149-IF(VLOOKUP(AC149,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC149,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F149="","",IF(OR(AA149="Cancelled",AC149="Cancelled"),"Cancelled",IF(OR(AC149="Completed / Handover",Y149<>"",Z149>=100),"Completed — on track",IF(O149="Not awarded",IF(U149="",IF(X149="","No planned date",IF(TODAY()>X149,"Behind — past planned date",IF(X149-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U149,"Behind — award date passed",IF(U149-TODAY()<=30,"At risk — close to off track","On track"))),IF(X149="","No planned date",IF(AND(TODAY()>X149,OR(Z149="",Z149<100)),"Behind — past end date",IF(AND(T149<>"",X149<>"",Z149<>"",(Z149<100),((TODAY()-T149)/MAX(X149-T149,1)*100)-Z149>15),"Behind — progress lag",IF(AND(X149-TODAY()<=30,X149-TODAY()>=0,OR(Z149="",Z149<90)),"At risk — close to off track","On track")))))))) | IF(OR(F149="",AC149="Completed / Handover",AC149="Cancelled"),"",IF(O149="Not awarded",IF(U149<>"",U149-TODAY(),IF(X149="","",X149-TODAY())),IF(X149="","",X149-TODAY()))) | [14 empty] | IF(OR(F149="",AJ149=""),"",IF(COUNT(AI149:AI149)=0,"",AJ149-LOOKUP(2,1/(AI149:AI149<>""),AI149:AI149))) | IF(OR(F149="",AK149=""),"",IF(COUNT(AI149:AJ149)=0,"",AK149-LOOKUP(2,1/(AI149:AJ149<>""),AI149:AJ149))) | IF(OR(F149="",AL149=""),"",IF(COUNT(AI149:AK149)=0,"",AL149-LOOKUP(2,1/(AI149:AK149<>""),AI149:AK149))) | IF(OR(F149="",AM149=""),"",IF(COUNT(AI149:AL149)=0,"",AM149-LOOKUP(2,1/(AI149:AL149<>""),AI149:AL149))) | IF(OR(F149="",AN149=""),"",IF(COUNT(AI149:AM149)=0,"",AN149-LOOKUP(2,1/(AI149:AM149<>""),AI149:AM149))) | IF(OR(F149="",AO149=""),"",IF(COUNT(AI149:AN149)=0,"",AO149-LOOKUP(2,1/(AI149:AN149<>""),AI149:AN149))) | IF(OR(F149="",AP149=""),"",IF(COUNT(AI149:AO149)=0,"",AP149-LOOKUP(2,1/(AI149:AO149<>""),AI149:AO149))) | IF(OR(F149="",AQ149=""),"",IF(COUNT(AI149:AP149)=0,"",AQ149-LOOKUP(2,1/(AI149:AP149<>""),AI149:AP149))) | IF(OR(F149="",AR149=""),"",IF(COUNT(AI149:AQ149)=0,"",AR149-LOOKUP(2,1/(AI149:AQ149<>""),AI149:AQ149))) | IF(OR(F149="",AS149=""),"",IF(COUNT(AI149:AR149)=0,"",AS149-LOOKUP(2,1/(AI149:AR149<>""),AI149:AR149))) | IF(OR(F149="",AT149=""),"",IF(COUNT(AI149:AS149)=0,"",AT149-LOOKUP(2,1/(AI149:AS149<>""),AI149:AS149))) | IF(OR(F149="",AU149=""),"",IF(COUNT(AI149:AT149)=0,"",AU149-LOOKUP(2,1/(AI149:AT149<>""),AI149:AT149))) | IF(OR(F149="",AV149=""),"",IF(COUNT(AI149:AU149)=0,"",AV149-LOOKUP(2,1/(AI149:AU149<>""),AI149:AU149))) | IF(J149="","All_Provinces",IFERROR(VLOOKUP(J149,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K149="","All_Districts",IFERROR(VLOOKUP(K149,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F150="","",ROW()-3) | [18 empty] | IF(AQ150="","",AQ150) |  |  |  | IF(W150<>"",W150,IF(OR(T150="",V150=""),"",EDATE(T150,V150))) |  |  |  |  | IF(F150="","",IF(COUNT(AI150:AV150)=0,IF(AA150="","Not started",AA150),SUBSTITUTE(LOOKUP(2,1/(AI150:AV150<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F150="",COUNT(AI150:AV150)=0),"",TODAY()-LOOKUP(2,1/(AI150:AV150<>""),AI150:AV150)) | IF(OR(F150="",COUNT(AI150:AV150)<2),"",LOOKUP(2,1/(AI150:AV150<>""),AI150:AV150)-MIN(AI150:AV150)) | IF(OR(AD150="",AC150="Not started",AC150=""),"",IFERROR(AD150-IF(VLOOKUP(AC150,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC150,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F150="","",IF(OR(AA150="Cancelled",AC150="Cancelled"),"Cancelled",IF(OR(AC150="Completed / Handover",Y150<>"",Z150>=100),"Completed — on track",IF(O150="Not awarded",IF(U150="",IF(X150="","No planned date",IF(TODAY()>X150,"Behind — past planned date",IF(X150-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U150,"Behind — award date passed",IF(U150-TODAY()<=30,"At risk — close to off track","On track"))),IF(X150="","No planned date",IF(AND(TODAY()>X150,OR(Z150="",Z150<100)),"Behind — past end date",IF(AND(T150<>"",X150<>"",Z150<>"",(Z150<100),((TODAY()-T150)/MAX(X150-T150,1)*100)-Z150>15),"Behind — progress lag",IF(AND(X150-TODAY()<=30,X150-TODAY()>=0,OR(Z150="",Z150<90)),"At risk — close to off track","On track")))))))) | IF(OR(F150="",AC150="Completed / Handover",AC150="Cancelled"),"",IF(O150="Not awarded",IF(U150<>"",U150-TODAY(),IF(X150="","",X150-TODAY())),IF(X150="","",X150-TODAY()))) | [14 empty] | IF(OR(F150="",AJ150=""),"",IF(COUNT(AI150:AI150)=0,"",AJ150-LOOKUP(2,1/(AI150:AI150<>""),AI150:AI150))) | IF(OR(F150="",AK150=""),"",IF(COUNT(AI150:AJ150)=0,"",AK150-LOOKUP(2,1/(AI150:AJ150<>""),AI150:AJ150))) | IF(OR(F150="",AL150=""),"",IF(COUNT(AI150:AK150)=0,"",AL150-LOOKUP(2,1/(AI150:AK150<>""),AI150:AK150))) | IF(OR(F150="",AM150=""),"",IF(COUNT(AI150:AL150)=0,"",AM150-LOOKUP(2,1/(AI150:AL150<>""),AI150:AL150))) | IF(OR(F150="",AN150=""),"",IF(COUNT(AI150:AM150)=0,"",AN150-LOOKUP(2,1/(AI150:AM150<>""),AI150:AM150))) | IF(OR(F150="",AO150=""),"",IF(COUNT(AI150:AN150)=0,"",AO150-LOOKUP(2,1/(AI150:AN150<>""),AI150:AN150))) | IF(OR(F150="",AP150=""),"",IF(COUNT(AI150:AO150)=0,"",AP150-LOOKUP(2,1/(AI150:AO150<>""),AI150:AO150))) | IF(OR(F150="",AQ150=""),"",IF(COUNT(AI150:AP150)=0,"",AQ150-LOOKUP(2,1/(AI150:AP150<>""),AI150:AP150))) | IF(OR(F150="",AR150=""),"",IF(COUNT(AI150:AQ150)=0,"",AR150-LOOKUP(2,1/(AI150:AQ150<>""),AI150:AQ150))) | IF(OR(F150="",AS150=""),"",IF(COUNT(AI150:AR150)=0,"",AS150-LOOKUP(2,1/(AI150:AR150<>""),AI150:AR150))) | IF(OR(F150="",AT150=""),"",IF(COUNT(AI150:AS150)=0,"",AT150-LOOKUP(2,1/(AI150:AS150<>""),AI150:AS150))) | IF(OR(F150="",AU150=""),"",IF(COUNT(AI150:AT150)=0,"",AU150-LOOKUP(2,1/(AI150:AT150<>""),AI150:AT150))) | IF(OR(F150="",AV150=""),"",IF(COUNT(AI150:AU150)=0,"",AV150-LOOKUP(2,1/(AI150:AU150<>""),AI150:AU150))) | IF(J150="","All_Provinces",IFERROR(VLOOKUP(J150,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K150="","All_Districts",IFERROR(VLOOKUP(K150,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F151="","",ROW()-3) | [18 empty] | IF(AQ151="","",AQ151) |  |  |  | IF(W151<>"",W151,IF(OR(T151="",V151=""),"",EDATE(T151,V151))) |  |  |  |  | IF(F151="","",IF(COUNT(AI151:AV151)=0,IF(AA151="","Not started",AA151),SUBSTITUTE(LOOKUP(2,1/(AI151:AV151<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F151="",COUNT(AI151:AV151)=0),"",TODAY()-LOOKUP(2,1/(AI151:AV151<>""),AI151:AV151)) | IF(OR(F151="",COUNT(AI151:AV151)<2),"",LOOKUP(2,1/(AI151:AV151<>""),AI151:AV151)-MIN(AI151:AV151)) | IF(OR(AD151="",AC151="Not started",AC151=""),"",IFERROR(AD151-IF(VLOOKUP(AC151,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC151,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F151="","",IF(OR(AA151="Cancelled",AC151="Cancelled"),"Cancelled",IF(OR(AC151="Completed / Handover",Y151<>"",Z151>=100),"Completed — on track",IF(O151="Not awarded",IF(U151="",IF(X151="","No planned date",IF(TODAY()>X151,"Behind — past planned date",IF(X151-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U151,"Behind — award date passed",IF(U151-TODAY()<=30,"At risk — close to off track","On track"))),IF(X151="","No planned date",IF(AND(TODAY()>X151,OR(Z151="",Z151<100)),"Behind — past end date",IF(AND(T151<>"",X151<>"",Z151<>"",(Z151<100),((TODAY()-T151)/MAX(X151-T151,1)*100)-Z151>15),"Behind — progress lag",IF(AND(X151-TODAY()<=30,X151-TODAY()>=0,OR(Z151="",Z151<90)),"At risk — close to off track","On track")))))))) | IF(OR(F151="",AC151="Completed / Handover",AC151="Cancelled"),"",IF(O151="Not awarded",IF(U151<>"",U151-TODAY(),IF(X151="","",X151-TODAY())),IF(X151="","",X151-TODAY()))) | [14 empty] | IF(OR(F151="",AJ151=""),"",IF(COUNT(AI151:AI151)=0,"",AJ151-LOOKUP(2,1/(AI151:AI151<>""),AI151:AI151))) | IF(OR(F151="",AK151=""),"",IF(COUNT(AI151:AJ151)=0,"",AK151-LOOKUP(2,1/(AI151:AJ151<>""),AI151:AJ151))) | IF(OR(F151="",AL151=""),"",IF(COUNT(AI151:AK151)=0,"",AL151-LOOKUP(2,1/(AI151:AK151<>""),AI151:AK151))) | IF(OR(F151="",AM151=""),"",IF(COUNT(AI151:AL151)=0,"",AM151-LOOKUP(2,1/(AI151:AL151<>""),AI151:AL151))) | IF(OR(F151="",AN151=""),"",IF(COUNT(AI151:AM151)=0,"",AN151-LOOKUP(2,1/(AI151:AM151<>""),AI151:AM151))) | IF(OR(F151="",AO151=""),"",IF(COUNT(AI151:AN151)=0,"",AO151-LOOKUP(2,1/(AI151:AN151<>""),AI151:AN151))) | IF(OR(F151="",AP151=""),"",IF(COUNT(AI151:AO151)=0,"",AP151-LOOKUP(2,1/(AI151:AO151<>""),AI151:AO151))) | IF(OR(F151="",AQ151=""),"",IF(COUNT(AI151:AP151)=0,"",AQ151-LOOKUP(2,1/(AI151:AP151<>""),AI151:AP151))) | IF(OR(F151="",AR151=""),"",IF(COUNT(AI151:AQ151)=0,"",AR151-LOOKUP(2,1/(AI151:AQ151<>""),AI151:AQ151))) | IF(OR(F151="",AS151=""),"",IF(COUNT(AI151:AR151)=0,"",AS151-LOOKUP(2,1/(AI151:AR151<>""),AI151:AR151))) | IF(OR(F151="",AT151=""),"",IF(COUNT(AI151:AS151)=0,"",AT151-LOOKUP(2,1/(AI151:AS151<>""),AI151:AS151))) | IF(OR(F151="",AU151=""),"",IF(COUNT(AI151:AT151)=0,"",AU151-LOOKUP(2,1/(AI151:AT151<>""),AI151:AT151))) | IF(OR(F151="",AV151=""),"",IF(COUNT(AI151:AU151)=0,"",AV151-LOOKUP(2,1/(AI151:AU151<>""),AI151:AU151))) | IF(J151="","All_Provinces",IFERROR(VLOOKUP(J151,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K151="","All_Districts",IFERROR(VLOOKUP(K151,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F152="","",ROW()-3) | [18 empty] | IF(AQ152="","",AQ152) |  |  |  | IF(W152<>"",W152,IF(OR(T152="",V152=""),"",EDATE(T152,V152))) |  |  |  |  | IF(F152="","",IF(COUNT(AI152:AV152)=0,IF(AA152="","Not started",AA152),SUBSTITUTE(LOOKUP(2,1/(AI152:AV152<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F152="",COUNT(AI152:AV152)=0),"",TODAY()-LOOKUP(2,1/(AI152:AV152<>""),AI152:AV152)) | IF(OR(F152="",COUNT(AI152:AV152)<2),"",LOOKUP(2,1/(AI152:AV152<>""),AI152:AV152)-MIN(AI152:AV152)) | IF(OR(AD152="",AC152="Not started",AC152=""),"",IFERROR(AD152-IF(VLOOKUP(AC152,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC152,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F152="","",IF(OR(AA152="Cancelled",AC152="Cancelled"),"Cancelled",IF(OR(AC152="Completed / Handover",Y152<>"",Z152>=100),"Completed — on track",IF(O152="Not awarded",IF(U152="",IF(X152="","No planned date",IF(TODAY()>X152,"Behind — past planned date",IF(X152-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U152,"Behind — award date passed",IF(U152-TODAY()<=30,"At risk — close to off track","On track"))),IF(X152="","No planned date",IF(AND(TODAY()>X152,OR(Z152="",Z152<100)),"Behind — past end date",IF(AND(T152<>"",X152<>"",Z152<>"",(Z152<100),((TODAY()-T152)/MAX(X152-T152,1)*100)-Z152>15),"Behind — progress lag",IF(AND(X152-TODAY()<=30,X152-TODAY()>=0,OR(Z152="",Z152<90)),"At risk — close to off track","On track")))))))) | IF(OR(F152="",AC152="Completed / Handover",AC152="Cancelled"),"",IF(O152="Not awarded",IF(U152<>"",U152-TODAY(),IF(X152="","",X152-TODAY())),IF(X152="","",X152-TODAY()))) | [14 empty] | IF(OR(F152="",AJ152=""),"",IF(COUNT(AI152:AI152)=0,"",AJ152-LOOKUP(2,1/(AI152:AI152<>""),AI152:AI152))) | IF(OR(F152="",AK152=""),"",IF(COUNT(AI152:AJ152)=0,"",AK152-LOOKUP(2,1/(AI152:AJ152<>""),AI152:AJ152))) | IF(OR(F152="",AL152=""),"",IF(COUNT(AI152:AK152)=0,"",AL152-LOOKUP(2,1/(AI152:AK152<>""),AI152:AK152))) | IF(OR(F152="",AM152=""),"",IF(COUNT(AI152:AL152)=0,"",AM152-LOOKUP(2,1/(AI152:AL152<>""),AI152:AL152))) | IF(OR(F152="",AN152=""),"",IF(COUNT(AI152:AM152)=0,"",AN152-LOOKUP(2,1/(AI152:AM152<>""),AI152:AM152))) | IF(OR(F152="",AO152=""),"",IF(COUNT(AI152:AN152)=0,"",AO152-LOOKUP(2,1/(AI152:AN152<>""),AI152:AN152))) | IF(OR(F152="",AP152=""),"",IF(COUNT(AI152:AO152)=0,"",AP152-LOOKUP(2,1/(AI152:AO152<>""),AI152:AO152))) | IF(OR(F152="",AQ152=""),"",IF(COUNT(AI152:AP152)=0,"",AQ152-LOOKUP(2,1/(AI152:AP152<>""),AI152:AP152))) | IF(OR(F152="",AR152=""),"",IF(COUNT(AI152:AQ152)=0,"",AR152-LOOKUP(2,1/(AI152:AQ152<>""),AI152:AQ152))) | IF(OR(F152="",AS152=""),"",IF(COUNT(AI152:AR152)=0,"",AS152-LOOKUP(2,1/(AI152:AR152<>""),AI152:AR152))) | IF(OR(F152="",AT152=""),"",IF(COUNT(AI152:AS152)=0,"",AT152-LOOKUP(2,1/(AI152:AS152<>""),AI152:AS152))) | IF(OR(F152="",AU152=""),"",IF(COUNT(AI152:AT152)=0,"",AU152-LOOKUP(2,1/(AI152:AT152<>""),AI152:AT152))) | IF(OR(F152="",AV152=""),"",IF(COUNT(AI152:AU152)=0,"",AV152-LOOKUP(2,1/(AI152:AU152<>""),AI152:AU152))) | IF(J152="","All_Provinces",IFERROR(VLOOKUP(J152,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K152="","All_Districts",IFERROR(VLOOKUP(K152,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F153="","",ROW()-3) | [18 empty] | IF(AQ153="","",AQ153) |  |  |  | IF(W153<>"",W153,IF(OR(T153="",V153=""),"",EDATE(T153,V153))) |  |  |  |  | IF(F153="","",IF(COUNT(AI153:AV153)=0,IF(AA153="","Not started",AA153),SUBSTITUTE(LOOKUP(2,1/(AI153:AV153<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F153="",COUNT(AI153:AV153)=0),"",TODAY()-LOOKUP(2,1/(AI153:AV153<>""),AI153:AV153)) | IF(OR(F153="",COUNT(AI153:AV153)<2),"",LOOKUP(2,1/(AI153:AV153<>""),AI153:AV153)-MIN(AI153:AV153)) | IF(OR(AD153="",AC153="Not started",AC153=""),"",IFERROR(AD153-IF(VLOOKUP(AC153,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC153,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F153="","",IF(OR(AA153="Cancelled",AC153="Cancelled"),"Cancelled",IF(OR(AC153="Completed / Handover",Y153<>"",Z153>=100),"Completed — on track",IF(O153="Not awarded",IF(U153="",IF(X153="","No planned date",IF(TODAY()>X153,"Behind — past planned date",IF(X153-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U153,"Behind — award date passed",IF(U153-TODAY()<=30,"At risk — close to off track","On track"))),IF(X153="","No planned date",IF(AND(TODAY()>X153,OR(Z153="",Z153<100)),"Behind — past end date",IF(AND(T153<>"",X153<>"",Z153<>"",(Z153<100),((TODAY()-T153)/MAX(X153-T153,1)*100)-Z153>15),"Behind — progress lag",IF(AND(X153-TODAY()<=30,X153-TODAY()>=0,OR(Z153="",Z153<90)),"At risk — close to off track","On track")))))))) | IF(OR(F153="",AC153="Completed / Handover",AC153="Cancelled"),"",IF(O153="Not awarded",IF(U153<>"",U153-TODAY(),IF(X153="","",X153-TODAY())),IF(X153="","",X153-TODAY()))) | [14 empty] | IF(OR(F153="",AJ153=""),"",IF(COUNT(AI153:AI153)=0,"",AJ153-LOOKUP(2,1/(AI153:AI153<>""),AI153:AI153))) | IF(OR(F153="",AK153=""),"",IF(COUNT(AI153:AJ153)=0,"",AK153-LOOKUP(2,1/(AI153:AJ153<>""),AI153:AJ153))) | IF(OR(F153="",AL153=""),"",IF(COUNT(AI153:AK153)=0,"",AL153-LOOKUP(2,1/(AI153:AK153<>""),AI153:AK153))) | IF(OR(F153="",AM153=""),"",IF(COUNT(AI153:AL153)=0,"",AM153-LOOKUP(2,1/(AI153:AL153<>""),AI153:AL153))) | IF(OR(F153="",AN153=""),"",IF(COUNT(AI153:AM153)=0,"",AN153-LOOKUP(2,1/(AI153:AM153<>""),AI153:AM153))) | IF(OR(F153="",AO153=""),"",IF(COUNT(AI153:AN153)=0,"",AO153-LOOKUP(2,1/(AI153:AN153<>""),AI153:AN153))) | IF(OR(F153="",AP153=""),"",IF(COUNT(AI153:AO153)=0,"",AP153-LOOKUP(2,1/(AI153:AO153<>""),AI153:AO153))) | IF(OR(F153="",AQ153=""),"",IF(COUNT(AI153:AP153)=0,"",AQ153-LOOKUP(2,1/(AI153:AP153<>""),AI153:AP153))) | IF(OR(F153="",AR153=""),"",IF(COUNT(AI153:AQ153)=0,"",AR153-LOOKUP(2,1/(AI153:AQ153<>""),AI153:AQ153))) | IF(OR(F153="",AS153=""),"",IF(COUNT(AI153:AR153)=0,"",AS153-LOOKUP(2,1/(AI153:AR153<>""),AI153:AR153))) | IF(OR(F153="",AT153=""),"",IF(COUNT(AI153:AS153)=0,"",AT153-LOOKUP(2,1/(AI153:AS153<>""),AI153:AS153))) | IF(OR(F153="",AU153=""),"",IF(COUNT(AI153:AT153)=0,"",AU153-LOOKUP(2,1/(AI153:AT153<>""),AI153:AT153))) | IF(OR(F153="",AV153=""),"",IF(COUNT(AI153:AU153)=0,"",AV153-LOOKUP(2,1/(AI153:AU153<>""),AI153:AU153))) | IF(J153="","All_Provinces",IFERROR(VLOOKUP(J153,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K153="","All_Districts",IFERROR(VLOOKUP(K153,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F154="","",ROW()-3) | [18 empty] | IF(AQ154="","",AQ154) |  |  |  | IF(W154<>"",W154,IF(OR(T154="",V154=""),"",EDATE(T154,V154))) |  |  |  |  | IF(F154="","",IF(COUNT(AI154:AV154)=0,IF(AA154="","Not started",AA154),SUBSTITUTE(LOOKUP(2,1/(AI154:AV154<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F154="",COUNT(AI154:AV154)=0),"",TODAY()-LOOKUP(2,1/(AI154:AV154<>""),AI154:AV154)) | IF(OR(F154="",COUNT(AI154:AV154)<2),"",LOOKUP(2,1/(AI154:AV154<>""),AI154:AV154)-MIN(AI154:AV154)) | IF(OR(AD154="",AC154="Not started",AC154=""),"",IFERROR(AD154-IF(VLOOKUP(AC154,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC154,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F154="","",IF(OR(AA154="Cancelled",AC154="Cancelled"),"Cancelled",IF(OR(AC154="Completed / Handover",Y154<>"",Z154>=100),"Completed — on track",IF(O154="Not awarded",IF(U154="",IF(X154="","No planned date",IF(TODAY()>X154,"Behind — past planned date",IF(X154-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U154,"Behind — award date passed",IF(U154-TODAY()<=30,"At risk — close to off track","On track"))),IF(X154="","No planned date",IF(AND(TODAY()>X154,OR(Z154="",Z154<100)),"Behind — past end date",IF(AND(T154<>"",X154<>"",Z154<>"",(Z154<100),((TODAY()-T154)/MAX(X154-T154,1)*100)-Z154>15),"Behind — progress lag",IF(AND(X154-TODAY()<=30,X154-TODAY()>=0,OR(Z154="",Z154<90)),"At risk — close to off track","On track")))))))) | IF(OR(F154="",AC154="Completed / Handover",AC154="Cancelled"),"",IF(O154="Not awarded",IF(U154<>"",U154-TODAY(),IF(X154="","",X154-TODAY())),IF(X154="","",X154-TODAY()))) | [14 empty] | IF(OR(F154="",AJ154=""),"",IF(COUNT(AI154:AI154)=0,"",AJ154-LOOKUP(2,1/(AI154:AI154<>""),AI154:AI154))) | IF(OR(F154="",AK154=""),"",IF(COUNT(AI154:AJ154)=0,"",AK154-LOOKUP(2,1/(AI154:AJ154<>""),AI154:AJ154))) | IF(OR(F154="",AL154=""),"",IF(COUNT(AI154:AK154)=0,"",AL154-LOOKUP(2,1/(AI154:AK154<>""),AI154:AK154))) | IF(OR(F154="",AM154=""),"",IF(COUNT(AI154:AL154)=0,"",AM154-LOOKUP(2,1/(AI154:AL154<>""),AI154:AL154))) | IF(OR(F154="",AN154=""),"",IF(COUNT(AI154:AM154)=0,"",AN154-LOOKUP(2,1/(AI154:AM154<>""),AI154:AM154))) | IF(OR(F154="",AO154=""),"",IF(COUNT(AI154:AN154)=0,"",AO154-LOOKUP(2,1/(AI154:AN154<>""),AI154:AN154))) | IF(OR(F154="",AP154=""),"",IF(COUNT(AI154:AO154)=0,"",AP154-LOOKUP(2,1/(AI154:AO154<>""),AI154:AO154))) | IF(OR(F154="",AQ154=""),"",IF(COUNT(AI154:AP154)=0,"",AQ154-LOOKUP(2,1/(AI154:AP154<>""),AI154:AP154))) | IF(OR(F154="",AR154=""),"",IF(COUNT(AI154:AQ154)=0,"",AR154-LOOKUP(2,1/(AI154:AQ154<>""),AI154:AQ154))) | IF(OR(F154="",AS154=""),"",IF(COUNT(AI154:AR154)=0,"",AS154-LOOKUP(2,1/(AI154:AR154<>""),AI154:AR154))) | IF(OR(F154="",AT154=""),"",IF(COUNT(AI154:AS154)=0,"",AT154-LOOKUP(2,1/(AI154:AS154<>""),AI154:AS154))) | IF(OR(F154="",AU154=""),"",IF(COUNT(AI154:AT154)=0,"",AU154-LOOKUP(2,1/(AI154:AT154<>""),AI154:AT154))) | IF(OR(F154="",AV154=""),"",IF(COUNT(AI154:AU154)=0,"",AV154-LOOKUP(2,1/(AI154:AU154<>""),AI154:AU154))) | IF(J154="","All_Provinces",IFERROR(VLOOKUP(J154,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K154="","All_Districts",IFERROR(VLOOKUP(K154,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F155="","",ROW()-3) | [18 empty] | IF(AQ155="","",AQ155) |  |  |  | IF(W155<>"",W155,IF(OR(T155="",V155=""),"",EDATE(T155,V155))) |  |  |  |  | IF(F155="","",IF(COUNT(AI155:AV155)=0,IF(AA155="","Not started",AA155),SUBSTITUTE(LOOKUP(2,1/(AI155:AV155<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F155="",COUNT(AI155:AV155)=0),"",TODAY()-LOOKUP(2,1/(AI155:AV155<>""),AI155:AV155)) | IF(OR(F155="",COUNT(AI155:AV155)<2),"",LOOKUP(2,1/(AI155:AV155<>""),AI155:AV155)-MIN(AI155:AV155)) | IF(OR(AD155="",AC155="Not started",AC155=""),"",IFERROR(AD155-IF(VLOOKUP(AC155,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC155,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F155="","",IF(OR(AA155="Cancelled",AC155="Cancelled"),"Cancelled",IF(OR(AC155="Completed / Handover",Y155<>"",Z155>=100),"Completed — on track",IF(O155="Not awarded",IF(U155="",IF(X155="","No planned date",IF(TODAY()>X155,"Behind — past planned date",IF(X155-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U155,"Behind — award date passed",IF(U155-TODAY()<=30,"At risk — close to off track","On track"))),IF(X155="","No planned date",IF(AND(TODAY()>X155,OR(Z155="",Z155<100)),"Behind — past end date",IF(AND(T155<>"",X155<>"",Z155<>"",(Z155<100),((TODAY()-T155)/MAX(X155-T155,1)*100)-Z155>15),"Behind — progress lag",IF(AND(X155-TODAY()<=30,X155-TODAY()>=0,OR(Z155="",Z155<90)),"At risk — close to off track","On track")))))))) | IF(OR(F155="",AC155="Completed / Handover",AC155="Cancelled"),"",IF(O155="Not awarded",IF(U155<>"",U155-TODAY(),IF(X155="","",X155-TODAY())),IF(X155="","",X155-TODAY()))) | [14 empty] | IF(OR(F155="",AJ155=""),"",IF(COUNT(AI155:AI155)=0,"",AJ155-LOOKUP(2,1/(AI155:AI155<>""),AI155:AI155))) | IF(OR(F155="",AK155=""),"",IF(COUNT(AI155:AJ155)=0,"",AK155-LOOKUP(2,1/(AI155:AJ155<>""),AI155:AJ155))) | IF(OR(F155="",AL155=""),"",IF(COUNT(AI155:AK155)=0,"",AL155-LOOKUP(2,1/(AI155:AK155<>""),AI155:AK155))) | IF(OR(F155="",AM155=""),"",IF(COUNT(AI155:AL155)=0,"",AM155-LOOKUP(2,1/(AI155:AL155<>""),AI155:AL155))) | IF(OR(F155="",AN155=""),"",IF(COUNT(AI155:AM155)=0,"",AN155-LOOKUP(2,1/(AI155:AM155<>""),AI155:AM155))) | IF(OR(F155="",AO155=""),"",IF(COUNT(AI155:AN155)=0,"",AO155-LOOKUP(2,1/(AI155:AN155<>""),AI155:AN155))) | IF(OR(F155="",AP155=""),"",IF(COUNT(AI155:AO155)=0,"",AP155-LOOKUP(2,1/(AI155:AO155<>""),AI155:AO155))) | IF(OR(F155="",AQ155=""),"",IF(COUNT(AI155:AP155)=0,"",AQ155-LOOKUP(2,1/(AI155:AP155<>""),AI155:AP155))) | IF(OR(F155="",AR155=""),"",IF(COUNT(AI155:AQ155)=0,"",AR155-LOOKUP(2,1/(AI155:AQ155<>""),AI155:AQ155))) | IF(OR(F155="",AS155=""),"",IF(COUNT(AI155:AR155)=0,"",AS155-LOOKUP(2,1/(AI155:AR155<>""),AI155:AR155))) | IF(OR(F155="",AT155=""),"",IF(COUNT(AI155:AS155)=0,"",AT155-LOOKUP(2,1/(AI155:AS155<>""),AI155:AS155))) | IF(OR(F155="",AU155=""),"",IF(COUNT(AI155:AT155)=0,"",AU155-LOOKUP(2,1/(AI155:AT155<>""),AI155:AT155))) | IF(OR(F155="",AV155=""),"",IF(COUNT(AI155:AU155)=0,"",AV155-LOOKUP(2,1/(AI155:AU155<>""),AI155:AU155))) | IF(J155="","All_Provinces",IFERROR(VLOOKUP(J155,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K155="","All_Districts",IFERROR(VLOOKUP(K155,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F156="","",ROW()-3) | [18 empty] | IF(AQ156="","",AQ156) |  |  |  | IF(W156<>"",W156,IF(OR(T156="",V156=""),"",EDATE(T156,V156))) |  |  |  |  | IF(F156="","",IF(COUNT(AI156:AV156)=0,IF(AA156="","Not started",AA156),SUBSTITUTE(LOOKUP(2,1/(AI156:AV156<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F156="",COUNT(AI156:AV156)=0),"",TODAY()-LOOKUP(2,1/(AI156:AV156<>""),AI156:AV156)) | IF(OR(F156="",COUNT(AI156:AV156)<2),"",LOOKUP(2,1/(AI156:AV156<>""),AI156:AV156)-MIN(AI156:AV156)) | IF(OR(AD156="",AC156="Not started",AC156=""),"",IFERROR(AD156-IF(VLOOKUP(AC156,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC156,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F156="","",IF(OR(AA156="Cancelled",AC156="Cancelled"),"Cancelled",IF(OR(AC156="Completed / Handover",Y156<>"",Z156>=100),"Completed — on track",IF(O156="Not awarded",IF(U156="",IF(X156="","No planned date",IF(TODAY()>X156,"Behind — past planned date",IF(X156-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U156,"Behind — award date passed",IF(U156-TODAY()<=30,"At risk — close to off track","On track"))),IF(X156="","No planned date",IF(AND(TODAY()>X156,OR(Z156="",Z156<100)),"Behind — past end date",IF(AND(T156<>"",X156<>"",Z156<>"",(Z156<100),((TODAY()-T156)/MAX(X156-T156,1)*100)-Z156>15),"Behind — progress lag",IF(AND(X156-TODAY()<=30,X156-TODAY()>=0,OR(Z156="",Z156<90)),"At risk — close to off track","On track")))))))) | IF(OR(F156="",AC156="Completed / Handover",AC156="Cancelled"),"",IF(O156="Not awarded",IF(U156<>"",U156-TODAY(),IF(X156="","",X156-TODAY())),IF(X156="","",X156-TODAY()))) | [14 empty] | IF(OR(F156="",AJ156=""),"",IF(COUNT(AI156:AI156)=0,"",AJ156-LOOKUP(2,1/(AI156:AI156<>""),AI156:AI156))) | IF(OR(F156="",AK156=""),"",IF(COUNT(AI156:AJ156)=0,"",AK156-LOOKUP(2,1/(AI156:AJ156<>""),AI156:AJ156))) | IF(OR(F156="",AL156=""),"",IF(COUNT(AI156:AK156)=0,"",AL156-LOOKUP(2,1/(AI156:AK156<>""),AI156:AK156))) | IF(OR(F156="",AM156=""),"",IF(COUNT(AI156:AL156)=0,"",AM156-LOOKUP(2,1/(AI156:AL156<>""),AI156:AL156))) | IF(OR(F156="",AN156=""),"",IF(COUNT(AI156:AM156)=0,"",AN156-LOOKUP(2,1/(AI156:AM156<>""),AI156:AM156))) | IF(OR(F156="",AO156=""),"",IF(COUNT(AI156:AN156)=0,"",AO156-LOOKUP(2,1/(AI156:AN156<>""),AI156:AN156))) | IF(OR(F156="",AP156=""),"",IF(COUNT(AI156:AO156)=0,"",AP156-LOOKUP(2,1/(AI156:AO156<>""),AI156:AO156))) | IF(OR(F156="",AQ156=""),"",IF(COUNT(AI156:AP156)=0,"",AQ156-LOOKUP(2,1/(AI156:AP156<>""),AI156:AP156))) | IF(OR(F156="",AR156=""),"",IF(COUNT(AI156:AQ156)=0,"",AR156-LOOKUP(2,1/(AI156:AQ156<>""),AI156:AQ156))) | IF(OR(F156="",AS156=""),"",IF(COUNT(AI156:AR156)=0,"",AS156-LOOKUP(2,1/(AI156:AR156<>""),AI156:AR156))) | IF(OR(F156="",AT156=""),"",IF(COUNT(AI156:AS156)=0,"",AT156-LOOKUP(2,1/(AI156:AS156<>""),AI156:AS156))) | IF(OR(F156="",AU156=""),"",IF(COUNT(AI156:AT156)=0,"",AU156-LOOKUP(2,1/(AI156:AT156<>""),AI156:AT156))) | IF(OR(F156="",AV156=""),"",IF(COUNT(AI156:AU156)=0,"",AV156-LOOKUP(2,1/(AI156:AU156<>""),AI156:AU156))) | IF(J156="","All_Provinces",IFERROR(VLOOKUP(J156,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K156="","All_Districts",IFERROR(VLOOKUP(K156,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F157="","",ROW()-3) | [18 empty] | IF(AQ157="","",AQ157) |  |  |  | IF(W157<>"",W157,IF(OR(T157="",V157=""),"",EDATE(T157,V157))) |  |  |  |  | IF(F157="","",IF(COUNT(AI157:AV157)=0,IF(AA157="","Not started",AA157),SUBSTITUTE(LOOKUP(2,1/(AI157:AV157<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F157="",COUNT(AI157:AV157)=0),"",TODAY()-LOOKUP(2,1/(AI157:AV157<>""),AI157:AV157)) | IF(OR(F157="",COUNT(AI157:AV157)<2),"",LOOKUP(2,1/(AI157:AV157<>""),AI157:AV157)-MIN(AI157:AV157)) | IF(OR(AD157="",AC157="Not started",AC157=""),"",IFERROR(AD157-IF(VLOOKUP(AC157,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC157,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F157="","",IF(OR(AA157="Cancelled",AC157="Cancelled"),"Cancelled",IF(OR(AC157="Completed / Handover",Y157<>"",Z157>=100),"Completed — on track",IF(O157="Not awarded",IF(U157="",IF(X157="","No planned date",IF(TODAY()>X157,"Behind — past planned date",IF(X157-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U157,"Behind — award date passed",IF(U157-TODAY()<=30,"At risk — close to off track","On track"))),IF(X157="","No planned date",IF(AND(TODAY()>X157,OR(Z157="",Z157<100)),"Behind — past end date",IF(AND(T157<>"",X157<>"",Z157<>"",(Z157<100),((TODAY()-T157)/MAX(X157-T157,1)*100)-Z157>15),"Behind — progress lag",IF(AND(X157-TODAY()<=30,X157-TODAY()>=0,OR(Z157="",Z157<90)),"At risk — close to off track","On track")))))))) | IF(OR(F157="",AC157="Completed / Handover",AC157="Cancelled"),"",IF(O157="Not awarded",IF(U157<>"",U157-TODAY(),IF(X157="","",X157-TODAY())),IF(X157="","",X157-TODAY()))) | [14 empty] | IF(OR(F157="",AJ157=""),"",IF(COUNT(AI157:AI157)=0,"",AJ157-LOOKUP(2,1/(AI157:AI157<>""),AI157:AI157))) | IF(OR(F157="",AK157=""),"",IF(COUNT(AI157:AJ157)=0,"",AK157-LOOKUP(2,1/(AI157:AJ157<>""),AI157:AJ157))) | IF(OR(F157="",AL157=""),"",IF(COUNT(AI157:AK157)=0,"",AL157-LOOKUP(2,1/(AI157:AK157<>""),AI157:AK157))) | IF(OR(F157="",AM157=""),"",IF(COUNT(AI157:AL157)=0,"",AM157-LOOKUP(2,1/(AI157:AL157<>""),AI157:AL157))) | IF(OR(F157="",AN157=""),"",IF(COUNT(AI157:AM157)=0,"",AN157-LOOKUP(2,1/(AI157:AM157<>""),AI157:AM157))) | IF(OR(F157="",AO157=""),"",IF(COUNT(AI157:AN157)=0,"",AO157-LOOKUP(2,1/(AI157:AN157<>""),AI157:AN157))) | IF(OR(F157="",AP157=""),"",IF(COUNT(AI157:AO157)=0,"",AP157-LOOKUP(2,1/(AI157:AO157<>""),AI157:AO157))) | IF(OR(F157="",AQ157=""),"",IF(COUNT(AI157:AP157)=0,"",AQ157-LOOKUP(2,1/(AI157:AP157<>""),AI157:AP157))) | IF(OR(F157="",AR157=""),"",IF(COUNT(AI157:AQ157)=0,"",AR157-LOOKUP(2,1/(AI157:AQ157<>""),AI157:AQ157))) | IF(OR(F157="",AS157=""),"",IF(COUNT(AI157:AR157)=0,"",AS157-LOOKUP(2,1/(AI157:AR157<>""),AI157:AR157))) | IF(OR(F157="",AT157=""),"",IF(COUNT(AI157:AS157)=0,"",AT157-LOOKUP(2,1/(AI157:AS157<>""),AI157:AS157))) | IF(OR(F157="",AU157=""),"",IF(COUNT(AI157:AT157)=0,"",AU157-LOOKUP(2,1/(AI157:AT157<>""),AI157:AT157))) | IF(OR(F157="",AV157=""),"",IF(COUNT(AI157:AU157)=0,"",AV157-LOOKUP(2,1/(AI157:AU157<>""),AI157:AU157))) | IF(J157="","All_Provinces",IFERROR(VLOOKUP(J157,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K157="","All_Districts",IFERROR(VLOOKUP(K157,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F158="","",ROW()-3) | [18 empty] | IF(AQ158="","",AQ158) |  |  |  | IF(W158<>"",W158,IF(OR(T158="",V158=""),"",EDATE(T158,V158))) |  |  |  |  | IF(F158="","",IF(COUNT(AI158:AV158)=0,IF(AA158="","Not started",AA158),SUBSTITUTE(LOOKUP(2,1/(AI158:AV158<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F158="",COUNT(AI158:AV158)=0),"",TODAY()-LOOKUP(2,1/(AI158:AV158<>""),AI158:AV158)) | IF(OR(F158="",COUNT(AI158:AV158)<2),"",LOOKUP(2,1/(AI158:AV158<>""),AI158:AV158)-MIN(AI158:AV158)) | IF(OR(AD158="",AC158="Not started",AC158=""),"",IFERROR(AD158-IF(VLOOKUP(AC158,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC158,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F158="","",IF(OR(AA158="Cancelled",AC158="Cancelled"),"Cancelled",IF(OR(AC158="Completed / Handover",Y158<>"",Z158>=100),"Completed — on track",IF(O158="Not awarded",IF(U158="",IF(X158="","No planned date",IF(TODAY()>X158,"Behind — past planned date",IF(X158-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U158,"Behind — award date passed",IF(U158-TODAY()<=30,"At risk — close to off track","On track"))),IF(X158="","No planned date",IF(AND(TODAY()>X158,OR(Z158="",Z158<100)),"Behind — past end date",IF(AND(T158<>"",X158<>"",Z158<>"",(Z158<100),((TODAY()-T158)/MAX(X158-T158,1)*100)-Z158>15),"Behind — progress lag",IF(AND(X158-TODAY()<=30,X158-TODAY()>=0,OR(Z158="",Z158<90)),"At risk — close to off track","On track")))))))) | IF(OR(F158="",AC158="Completed / Handover",AC158="Cancelled"),"",IF(O158="Not awarded",IF(U158<>"",U158-TODAY(),IF(X158="","",X158-TODAY())),IF(X158="","",X158-TODAY()))) | [14 empty] | IF(OR(F158="",AJ158=""),"",IF(COUNT(AI158:AI158)=0,"",AJ158-LOOKUP(2,1/(AI158:AI158<>""),AI158:AI158))) | IF(OR(F158="",AK158=""),"",IF(COUNT(AI158:AJ158)=0,"",AK158-LOOKUP(2,1/(AI158:AJ158<>""),AI158:AJ158))) | IF(OR(F158="",AL158=""),"",IF(COUNT(AI158:AK158)=0,"",AL158-LOOKUP(2,1/(AI158:AK158<>""),AI158:AK158))) | IF(OR(F158="",AM158=""),"",IF(COUNT(AI158:AL158)=0,"",AM158-LOOKUP(2,1/(AI158:AL158<>""),AI158:AL158))) | IF(OR(F158="",AN158=""),"",IF(COUNT(AI158:AM158)=0,"",AN158-LOOKUP(2,1/(AI158:AM158<>""),AI158:AM158))) | IF(OR(F158="",AO158=""),"",IF(COUNT(AI158:AN158)=0,"",AO158-LOOKUP(2,1/(AI158:AN158<>""),AI158:AN158))) | IF(OR(F158="",AP158=""),"",IF(COUNT(AI158:AO158)=0,"",AP158-LOOKUP(2,1/(AI158:AO158<>""),AI158:AO158))) | IF(OR(F158="",AQ158=""),"",IF(COUNT(AI158:AP158)=0,"",AQ158-LOOKUP(2,1/(AI158:AP158<>""),AI158:AP158))) | IF(OR(F158="",AR158=""),"",IF(COUNT(AI158:AQ158)=0,"",AR158-LOOKUP(2,1/(AI158:AQ158<>""),AI158:AQ158))) | IF(OR(F158="",AS158=""),"",IF(COUNT(AI158:AR158)=0,"",AS158-LOOKUP(2,1/(AI158:AR158<>""),AI158:AR158))) | IF(OR(F158="",AT158=""),"",IF(COUNT(AI158:AS158)=0,"",AT158-LOOKUP(2,1/(AI158:AS158<>""),AI158:AS158))) | IF(OR(F158="",AU158=""),"",IF(COUNT(AI158:AT158)=0,"",AU158-LOOKUP(2,1/(AI158:AT158<>""),AI158:AT158))) | IF(OR(F158="",AV158=""),"",IF(COUNT(AI158:AU158)=0,"",AV158-LOOKUP(2,1/(AI158:AU158<>""),AI158:AU158))) | IF(J158="","All_Provinces",IFERROR(VLOOKUP(J158,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K158="","All_Districts",IFERROR(VLOOKUP(K158,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F159="","",ROW()-3) | [18 empty] | IF(AQ159="","",AQ159) |  |  |  | IF(W159<>"",W159,IF(OR(T159="",V159=""),"",EDATE(T159,V159))) |  |  |  |  | IF(F159="","",IF(COUNT(AI159:AV159)=0,IF(AA159="","Not started",AA159),SUBSTITUTE(LOOKUP(2,1/(AI159:AV159<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F159="",COUNT(AI159:AV159)=0),"",TODAY()-LOOKUP(2,1/(AI159:AV159<>""),AI159:AV159)) | IF(OR(F159="",COUNT(AI159:AV159)<2),"",LOOKUP(2,1/(AI159:AV159<>""),AI159:AV159)-MIN(AI159:AV159)) | IF(OR(AD159="",AC159="Not started",AC159=""),"",IFERROR(AD159-IF(VLOOKUP(AC159,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC159,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F159="","",IF(OR(AA159="Cancelled",AC159="Cancelled"),"Cancelled",IF(OR(AC159="Completed / Handover",Y159<>"",Z159>=100),"Completed — on track",IF(O159="Not awarded",IF(U159="",IF(X159="","No planned date",IF(TODAY()>X159,"Behind — past planned date",IF(X159-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U159,"Behind — award date passed",IF(U159-TODAY()<=30,"At risk — close to off track","On track"))),IF(X159="","No planned date",IF(AND(TODAY()>X159,OR(Z159="",Z159<100)),"Behind — past end date",IF(AND(T159<>"",X159<>"",Z159<>"",(Z159<100),((TODAY()-T159)/MAX(X159-T159,1)*100)-Z159>15),"Behind — progress lag",IF(AND(X159-TODAY()<=30,X159-TODAY()>=0,OR(Z159="",Z159<90)),"At risk — close to off track","On track")))))))) | IF(OR(F159="",AC159="Completed / Handover",AC159="Cancelled"),"",IF(O159="Not awarded",IF(U159<>"",U159-TODAY(),IF(X159="","",X159-TODAY())),IF(X159="","",X159-TODAY()))) | [14 empty] | IF(OR(F159="",AJ159=""),"",IF(COUNT(AI159:AI159)=0,"",AJ159-LOOKUP(2,1/(AI159:AI159<>""),AI159:AI159))) | IF(OR(F159="",AK159=""),"",IF(COUNT(AI159:AJ159)=0,"",AK159-LOOKUP(2,1/(AI159:AJ159<>""),AI159:AJ159))) | IF(OR(F159="",AL159=""),"",IF(COUNT(AI159:AK159)=0,"",AL159-LOOKUP(2,1/(AI159:AK159<>""),AI159:AK159))) | IF(OR(F159="",AM159=""),"",IF(COUNT(AI159:AL159)=0,"",AM159-LOOKUP(2,1/(AI159:AL159<>""),AI159:AL159))) | IF(OR(F159="",AN159=""),"",IF(COUNT(AI159:AM159)=0,"",AN159-LOOKUP(2,1/(AI159:AM159<>""),AI159:AM159))) | IF(OR(F159="",AO159=""),"",IF(COUNT(AI159:AN159)=0,"",AO159-LOOKUP(2,1/(AI159:AN159<>""),AI159:AN159))) | IF(OR(F159="",AP159=""),"",IF(COUNT(AI159:AO159)=0,"",AP159-LOOKUP(2,1/(AI159:AO159<>""),AI159:AO159))) | IF(OR(F159="",AQ159=""),"",IF(COUNT(AI159:AP159)=0,"",AQ159-LOOKUP(2,1/(AI159:AP159<>""),AI159:AP159))) | IF(OR(F159="",AR159=""),"",IF(COUNT(AI159:AQ159)=0,"",AR159-LOOKUP(2,1/(AI159:AQ159<>""),AI159:AQ159))) | IF(OR(F159="",AS159=""),"",IF(COUNT(AI159:AR159)=0,"",AS159-LOOKUP(2,1/(AI159:AR159<>""),AI159:AR159))) | IF(OR(F159="",AT159=""),"",IF(COUNT(AI159:AS159)=0,"",AT159-LOOKUP(2,1/(AI159:AS159<>""),AI159:AS159))) | IF(OR(F159="",AU159=""),"",IF(COUNT(AI159:AT159)=0,"",AU159-LOOKUP(2,1/(AI159:AT159<>""),AI159:AT159))) | IF(OR(F159="",AV159=""),"",IF(COUNT(AI159:AU159)=0,"",AV159-LOOKUP(2,1/(AI159:AU159<>""),AI159:AU159))) | IF(J159="","All_Provinces",IFERROR(VLOOKUP(J159,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K159="","All_Districts",IFERROR(VLOOKUP(K159,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F160="","",ROW()-3) | [18 empty] | IF(AQ160="","",AQ160) |  |  |  | IF(W160<>"",W160,IF(OR(T160="",V160=""),"",EDATE(T160,V160))) |  |  |  |  | IF(F160="","",IF(COUNT(AI160:AV160)=0,IF(AA160="","Not started",AA160),SUBSTITUTE(LOOKUP(2,1/(AI160:AV160<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F160="",COUNT(AI160:AV160)=0),"",TODAY()-LOOKUP(2,1/(AI160:AV160<>""),AI160:AV160)) | IF(OR(F160="",COUNT(AI160:AV160)<2),"",LOOKUP(2,1/(AI160:AV160<>""),AI160:AV160)-MIN(AI160:AV160)) | IF(OR(AD160="",AC160="Not started",AC160=""),"",IFERROR(AD160-IF(VLOOKUP(AC160,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC160,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F160="","",IF(OR(AA160="Cancelled",AC160="Cancelled"),"Cancelled",IF(OR(AC160="Completed / Handover",Y160<>"",Z160>=100),"Completed — on track",IF(O160="Not awarded",IF(U160="",IF(X160="","No planned date",IF(TODAY()>X160,"Behind — past planned date",IF(X160-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U160,"Behind — award date passed",IF(U160-TODAY()<=30,"At risk — close to off track","On track"))),IF(X160="","No planned date",IF(AND(TODAY()>X160,OR(Z160="",Z160<100)),"Behind — past end date",IF(AND(T160<>"",X160<>"",Z160<>"",(Z160<100),((TODAY()-T160)/MAX(X160-T160,1)*100)-Z160>15),"Behind — progress lag",IF(AND(X160-TODAY()<=30,X160-TODAY()>=0,OR(Z160="",Z160<90)),"At risk — close to off track","On track")))))))) | IF(OR(F160="",AC160="Completed / Handover",AC160="Cancelled"),"",IF(O160="Not awarded",IF(U160<>"",U160-TODAY(),IF(X160="","",X160-TODAY())),IF(X160="","",X160-TODAY()))) | [14 empty] | IF(OR(F160="",AJ160=""),"",IF(COUNT(AI160:AI160)=0,"",AJ160-LOOKUP(2,1/(AI160:AI160<>""),AI160:AI160))) | IF(OR(F160="",AK160=""),"",IF(COUNT(AI160:AJ160)=0,"",AK160-LOOKUP(2,1/(AI160:AJ160<>""),AI160:AJ160))) | IF(OR(F160="",AL160=""),"",IF(COUNT(AI160:AK160)=0,"",AL160-LOOKUP(2,1/(AI160:AK160<>""),AI160:AK160))) | IF(OR(F160="",AM160=""),"",IF(COUNT(AI160:AL160)=0,"",AM160-LOOKUP(2,1/(AI160:AL160<>""),AI160:AL160))) | IF(OR(F160="",AN160=""),"",IF(COUNT(AI160:AM160)=0,"",AN160-LOOKUP(2,1/(AI160:AM160<>""),AI160:AM160))) | IF(OR(F160="",AO160=""),"",IF(COUNT(AI160:AN160)=0,"",AO160-LOOKUP(2,1/(AI160:AN160<>""),AI160:AN160))) | IF(OR(F160="",AP160=""),"",IF(COUNT(AI160:AO160)=0,"",AP160-LOOKUP(2,1/(AI160:AO160<>""),AI160:AO160))) | IF(OR(F160="",AQ160=""),"",IF(COUNT(AI160:AP160)=0,"",AQ160-LOOKUP(2,1/(AI160:AP160<>""),AI160:AP160))) | IF(OR(F160="",AR160=""),"",IF(COUNT(AI160:AQ160)=0,"",AR160-LOOKUP(2,1/(AI160:AQ160<>""),AI160:AQ160))) | IF(OR(F160="",AS160=""),"",IF(COUNT(AI160:AR160)=0,"",AS160-LOOKUP(2,1/(AI160:AR160<>""),AI160:AR160))) | IF(OR(F160="",AT160=""),"",IF(COUNT(AI160:AS160)=0,"",AT160-LOOKUP(2,1/(AI160:AS160<>""),AI160:AS160))) | IF(OR(F160="",AU160=""),"",IF(COUNT(AI160:AT160)=0,"",AU160-LOOKUP(2,1/(AI160:AT160<>""),AI160:AT160))) | IF(OR(F160="",AV160=""),"",IF(COUNT(AI160:AU160)=0,"",AV160-LOOKUP(2,1/(AI160:AU160<>""),AI160:AU160))) | IF(J160="","All_Provinces",IFERROR(VLOOKUP(J160,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K160="","All_Districts",IFERROR(VLOOKUP(K160,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F161="","",ROW()-3) | [18 empty] | IF(AQ161="","",AQ161) |  |  |  | IF(W161<>"",W161,IF(OR(T161="",V161=""),"",EDATE(T161,V161))) |  |  |  |  | IF(F161="","",IF(COUNT(AI161:AV161)=0,IF(AA161="","Not started",AA161),SUBSTITUTE(LOOKUP(2,1/(AI161:AV161<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F161="",COUNT(AI161:AV161)=0),"",TODAY()-LOOKUP(2,1/(AI161:AV161<>""),AI161:AV161)) | IF(OR(F161="",COUNT(AI161:AV161)<2),"",LOOKUP(2,1/(AI161:AV161<>""),AI161:AV161)-MIN(AI161:AV161)) | IF(OR(AD161="",AC161="Not started",AC161=""),"",IFERROR(AD161-IF(VLOOKUP(AC161,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC161,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F161="","",IF(OR(AA161="Cancelled",AC161="Cancelled"),"Cancelled",IF(OR(AC161="Completed / Handover",Y161<>"",Z161>=100),"Completed — on track",IF(O161="Not awarded",IF(U161="",IF(X161="","No planned date",IF(TODAY()>X161,"Behind — past planned date",IF(X161-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U161,"Behind — award date passed",IF(U161-TODAY()<=30,"At risk — close to off track","On track"))),IF(X161="","No planned date",IF(AND(TODAY()>X161,OR(Z161="",Z161<100)),"Behind — past end date",IF(AND(T161<>"",X161<>"",Z161<>"",(Z161<100),((TODAY()-T161)/MAX(X161-T161,1)*100)-Z161>15),"Behind — progress lag",IF(AND(X161-TODAY()<=30,X161-TODAY()>=0,OR(Z161="",Z161<90)),"At risk — close to off track","On track")))))))) | IF(OR(F161="",AC161="Completed / Handover",AC161="Cancelled"),"",IF(O161="Not awarded",IF(U161<>"",U161-TODAY(),IF(X161="","",X161-TODAY())),IF(X161="","",X161-TODAY()))) | [14 empty] | IF(OR(F161="",AJ161=""),"",IF(COUNT(AI161:AI161)=0,"",AJ161-LOOKUP(2,1/(AI161:AI161<>""),AI161:AI161))) | IF(OR(F161="",AK161=""),"",IF(COUNT(AI161:AJ161)=0,"",AK161-LOOKUP(2,1/(AI161:AJ161<>""),AI161:AJ161))) | IF(OR(F161="",AL161=""),"",IF(COUNT(AI161:AK161)=0,"",AL161-LOOKUP(2,1/(AI161:AK161<>""),AI161:AK161))) | IF(OR(F161="",AM161=""),"",IF(COUNT(AI161:AL161)=0,"",AM161-LOOKUP(2,1/(AI161:AL161<>""),AI161:AL161))) | IF(OR(F161="",AN161=""),"",IF(COUNT(AI161:AM161)=0,"",AN161-LOOKUP(2,1/(AI161:AM161<>""),AI161:AM161))) | IF(OR(F161="",AO161=""),"",IF(COUNT(AI161:AN161)=0,"",AO161-LOOKUP(2,1/(AI161:AN161<>""),AI161:AN161))) | IF(OR(F161="",AP161=""),"",IF(COUNT(AI161:AO161)=0,"",AP161-LOOKUP(2,1/(AI161:AO161<>""),AI161:AO161))) | IF(OR(F161="",AQ161=""),"",IF(COUNT(AI161:AP161)=0,"",AQ161-LOOKUP(2,1/(AI161:AP161<>""),AI161:AP161))) | IF(OR(F161="",AR161=""),"",IF(COUNT(AI161:AQ161)=0,"",AR161-LOOKUP(2,1/(AI161:AQ161<>""),AI161:AQ161))) | IF(OR(F161="",AS161=""),"",IF(COUNT(AI161:AR161)=0,"",AS161-LOOKUP(2,1/(AI161:AR161<>""),AI161:AR161))) | IF(OR(F161="",AT161=""),"",IF(COUNT(AI161:AS161)=0,"",AT161-LOOKUP(2,1/(AI161:AS161<>""),AI161:AS161))) | IF(OR(F161="",AU161=""),"",IF(COUNT(AI161:AT161)=0,"",AU161-LOOKUP(2,1/(AI161:AT161<>""),AI161:AT161))) | IF(OR(F161="",AV161=""),"",IF(COUNT(AI161:AU161)=0,"",AV161-LOOKUP(2,1/(AI161:AU161<>""),AI161:AU161))) | IF(J161="","All_Provinces",IFERROR(VLOOKUP(J161,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K161="","All_Districts",IFERROR(VLOOKUP(K161,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F162="","",ROW()-3) | [18 empty] | IF(AQ162="","",AQ162) |  |  |  | IF(W162<>"",W162,IF(OR(T162="",V162=""),"",EDATE(T162,V162))) |  |  |  |  | IF(F162="","",IF(COUNT(AI162:AV162)=0,IF(AA162="","Not started",AA162),SUBSTITUTE(LOOKUP(2,1/(AI162:AV162<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F162="",COUNT(AI162:AV162)=0),"",TODAY()-LOOKUP(2,1/(AI162:AV162<>""),AI162:AV162)) | IF(OR(F162="",COUNT(AI162:AV162)<2),"",LOOKUP(2,1/(AI162:AV162<>""),AI162:AV162)-MIN(AI162:AV162)) | IF(OR(AD162="",AC162="Not started",AC162=""),"",IFERROR(AD162-IF(VLOOKUP(AC162,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC162,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F162="","",IF(OR(AA162="Cancelled",AC162="Cancelled"),"Cancelled",IF(OR(AC162="Completed / Handover",Y162<>"",Z162>=100),"Completed — on track",IF(O162="Not awarded",IF(U162="",IF(X162="","No planned date",IF(TODAY()>X162,"Behind — past planned date",IF(X162-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U162,"Behind — award date passed",IF(U162-TODAY()<=30,"At risk — close to off track","On track"))),IF(X162="","No planned date",IF(AND(TODAY()>X162,OR(Z162="",Z162<100)),"Behind — past end date",IF(AND(T162<>"",X162<>"",Z162<>"",(Z162<100),((TODAY()-T162)/MAX(X162-T162,1)*100)-Z162>15),"Behind — progress lag",IF(AND(X162-TODAY()<=30,X162-TODAY()>=0,OR(Z162="",Z162<90)),"At risk — close to off track","On track")))))))) | IF(OR(F162="",AC162="Completed / Handover",AC162="Cancelled"),"",IF(O162="Not awarded",IF(U162<>"",U162-TODAY(),IF(X162="","",X162-TODAY())),IF(X162="","",X162-TODAY()))) | [14 empty] | IF(OR(F162="",AJ162=""),"",IF(COUNT(AI162:AI162)=0,"",AJ162-LOOKUP(2,1/(AI162:AI162<>""),AI162:AI162))) | IF(OR(F162="",AK162=""),"",IF(COUNT(AI162:AJ162)=0,"",AK162-LOOKUP(2,1/(AI162:AJ162<>""),AI162:AJ162))) | IF(OR(F162="",AL162=""),"",IF(COUNT(AI162:AK162)=0,"",AL162-LOOKUP(2,1/(AI162:AK162<>""),AI162:AK162))) | IF(OR(F162="",AM162=""),"",IF(COUNT(AI162:AL162)=0,"",AM162-LOOKUP(2,1/(AI162:AL162<>""),AI162:AL162))) | IF(OR(F162="",AN162=""),"",IF(COUNT(AI162:AM162)=0,"",AN162-LOOKUP(2,1/(AI162:AM162<>""),AI162:AM162))) | IF(OR(F162="",AO162=""),"",IF(COUNT(AI162:AN162)=0,"",AO162-LOOKUP(2,1/(AI162:AN162<>""),AI162:AN162))) | IF(OR(F162="",AP162=""),"",IF(COUNT(AI162:AO162)=0,"",AP162-LOOKUP(2,1/(AI162:AO162<>""),AI162:AO162))) | IF(OR(F162="",AQ162=""),"",IF(COUNT(AI162:AP162)=0,"",AQ162-LOOKUP(2,1/(AI162:AP162<>""),AI162:AP162))) | IF(OR(F162="",AR162=""),"",IF(COUNT(AI162:AQ162)=0,"",AR162-LOOKUP(2,1/(AI162:AQ162<>""),AI162:AQ162))) | IF(OR(F162="",AS162=""),"",IF(COUNT(AI162:AR162)=0,"",AS162-LOOKUP(2,1/(AI162:AR162<>""),AI162:AR162))) | IF(OR(F162="",AT162=""),"",IF(COUNT(AI162:AS162)=0,"",AT162-LOOKUP(2,1/(AI162:AS162<>""),AI162:AS162))) | IF(OR(F162="",AU162=""),"",IF(COUNT(AI162:AT162)=0,"",AU162-LOOKUP(2,1/(AI162:AT162<>""),AI162:AT162))) | IF(OR(F162="",AV162=""),"",IF(COUNT(AI162:AU162)=0,"",AV162-LOOKUP(2,1/(AI162:AU162<>""),AI162:AU162))) | IF(J162="","All_Provinces",IFERROR(VLOOKUP(J162,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K162="","All_Districts",IFERROR(VLOOKUP(K162,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F163="","",ROW()-3) | [18 empty] | IF(AQ163="","",AQ163) |  |  |  | IF(W163<>"",W163,IF(OR(T163="",V163=""),"",EDATE(T163,V163))) |  |  |  |  | IF(F163="","",IF(COUNT(AI163:AV163)=0,IF(AA163="","Not started",AA163),SUBSTITUTE(LOOKUP(2,1/(AI163:AV163<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F163="",COUNT(AI163:AV163)=0),"",TODAY()-LOOKUP(2,1/(AI163:AV163<>""),AI163:AV163)) | IF(OR(F163="",COUNT(AI163:AV163)<2),"",LOOKUP(2,1/(AI163:AV163<>""),AI163:AV163)-MIN(AI163:AV163)) | IF(OR(AD163="",AC163="Not started",AC163=""),"",IFERROR(AD163-IF(VLOOKUP(AC163,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC163,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F163="","",IF(OR(AA163="Cancelled",AC163="Cancelled"),"Cancelled",IF(OR(AC163="Completed / Handover",Y163<>"",Z163>=100),"Completed — on track",IF(O163="Not awarded",IF(U163="",IF(X163="","No planned date",IF(TODAY()>X163,"Behind — past planned date",IF(X163-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U163,"Behind — award date passed",IF(U163-TODAY()<=30,"At risk — close to off track","On track"))),IF(X163="","No planned date",IF(AND(TODAY()>X163,OR(Z163="",Z163<100)),"Behind — past end date",IF(AND(T163<>"",X163<>"",Z163<>"",(Z163<100),((TODAY()-T163)/MAX(X163-T163,1)*100)-Z163>15),"Behind — progress lag",IF(AND(X163-TODAY()<=30,X163-TODAY()>=0,OR(Z163="",Z163<90)),"At risk — close to off track","On track")))))))) | IF(OR(F163="",AC163="Completed / Handover",AC163="Cancelled"),"",IF(O163="Not awarded",IF(U163<>"",U163-TODAY(),IF(X163="","",X163-TODAY())),IF(X163="","",X163-TODAY()))) | [14 empty] | IF(OR(F163="",AJ163=""),"",IF(COUNT(AI163:AI163)=0,"",AJ163-LOOKUP(2,1/(AI163:AI163<>""),AI163:AI163))) | IF(OR(F163="",AK163=""),"",IF(COUNT(AI163:AJ163)=0,"",AK163-LOOKUP(2,1/(AI163:AJ163<>""),AI163:AJ163))) | IF(OR(F163="",AL163=""),"",IF(COUNT(AI163:AK163)=0,"",AL163-LOOKUP(2,1/(AI163:AK163<>""),AI163:AK163))) | IF(OR(F163="",AM163=""),"",IF(COUNT(AI163:AL163)=0,"",AM163-LOOKUP(2,1/(AI163:AL163<>""),AI163:AL163))) | IF(OR(F163="",AN163=""),"",IF(COUNT(AI163:AM163)=0,"",AN163-LOOKUP(2,1/(AI163:AM163<>""),AI163:AM163))) | IF(OR(F163="",AO163=""),"",IF(COUNT(AI163:AN163)=0,"",AO163-LOOKUP(2,1/(AI163:AN163<>""),AI163:AN163))) | IF(OR(F163="",AP163=""),"",IF(COUNT(AI163:AO163)=0,"",AP163-LOOKUP(2,1/(AI163:AO163<>""),AI163:AO163))) | IF(OR(F163="",AQ163=""),"",IF(COUNT(AI163:AP163)=0,"",AQ163-LOOKUP(2,1/(AI163:AP163<>""),AI163:AP163))) | IF(OR(F163="",AR163=""),"",IF(COUNT(AI163:AQ163)=0,"",AR163-LOOKUP(2,1/(AI163:AQ163<>""),AI163:AQ163))) | IF(OR(F163="",AS163=""),"",IF(COUNT(AI163:AR163)=0,"",AS163-LOOKUP(2,1/(AI163:AR163<>""),AI163:AR163))) | IF(OR(F163="",AT163=""),"",IF(COUNT(AI163:AS163)=0,"",AT163-LOOKUP(2,1/(AI163:AS163<>""),AI163:AS163))) | IF(OR(F163="",AU163=""),"",IF(COUNT(AI163:AT163)=0,"",AU163-LOOKUP(2,1/(AI163:AT163<>""),AI163:AT163))) | IF(OR(F163="",AV163=""),"",IF(COUNT(AI163:AU163)=0,"",AV163-LOOKUP(2,1/(AI163:AU163<>""),AI163:AU163))) | IF(J163="","All_Provinces",IFERROR(VLOOKUP(J163,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K163="","All_Districts",IFERROR(VLOOKUP(K163,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F164="","",ROW()-3) | [18 empty] | IF(AQ164="","",AQ164) |  |  |  | IF(W164<>"",W164,IF(OR(T164="",V164=""),"",EDATE(T164,V164))) |  |  |  |  | IF(F164="","",IF(COUNT(AI164:AV164)=0,IF(AA164="","Not started",AA164),SUBSTITUTE(LOOKUP(2,1/(AI164:AV164<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F164="",COUNT(AI164:AV164)=0),"",TODAY()-LOOKUP(2,1/(AI164:AV164<>""),AI164:AV164)) | IF(OR(F164="",COUNT(AI164:AV164)<2),"",LOOKUP(2,1/(AI164:AV164<>""),AI164:AV164)-MIN(AI164:AV164)) | IF(OR(AD164="",AC164="Not started",AC164=""),"",IFERROR(AD164-IF(VLOOKUP(AC164,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC164,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F164="","",IF(OR(AA164="Cancelled",AC164="Cancelled"),"Cancelled",IF(OR(AC164="Completed / Handover",Y164<>"",Z164>=100),"Completed — on track",IF(O164="Not awarded",IF(U164="",IF(X164="","No planned date",IF(TODAY()>X164,"Behind — past planned date",IF(X164-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U164,"Behind — award date passed",IF(U164-TODAY()<=30,"At risk — close to off track","On track"))),IF(X164="","No planned date",IF(AND(TODAY()>X164,OR(Z164="",Z164<100)),"Behind — past end date",IF(AND(T164<>"",X164<>"",Z164<>"",(Z164<100),((TODAY()-T164)/MAX(X164-T164,1)*100)-Z164>15),"Behind — progress lag",IF(AND(X164-TODAY()<=30,X164-TODAY()>=0,OR(Z164="",Z164<90)),"At risk — close to off track","On track")))))))) | IF(OR(F164="",AC164="Completed / Handover",AC164="Cancelled"),"",IF(O164="Not awarded",IF(U164<>"",U164-TODAY(),IF(X164="","",X164-TODAY())),IF(X164="","",X164-TODAY()))) | [14 empty] | IF(OR(F164="",AJ164=""),"",IF(COUNT(AI164:AI164)=0,"",AJ164-LOOKUP(2,1/(AI164:AI164<>""),AI164:AI164))) | IF(OR(F164="",AK164=""),"",IF(COUNT(AI164:AJ164)=0,"",AK164-LOOKUP(2,1/(AI164:AJ164<>""),AI164:AJ164))) | IF(OR(F164="",AL164=""),"",IF(COUNT(AI164:AK164)=0,"",AL164-LOOKUP(2,1/(AI164:AK164<>""),AI164:AK164))) | IF(OR(F164="",AM164=""),"",IF(COUNT(AI164:AL164)=0,"",AM164-LOOKUP(2,1/(AI164:AL164<>""),AI164:AL164))) | IF(OR(F164="",AN164=""),"",IF(COUNT(AI164:AM164)=0,"",AN164-LOOKUP(2,1/(AI164:AM164<>""),AI164:AM164))) | IF(OR(F164="",AO164=""),"",IF(COUNT(AI164:AN164)=0,"",AO164-LOOKUP(2,1/(AI164:AN164<>""),AI164:AN164))) | IF(OR(F164="",AP164=""),"",IF(COUNT(AI164:AO164)=0,"",AP164-LOOKUP(2,1/(AI164:AO164<>""),AI164:AO164))) | IF(OR(F164="",AQ164=""),"",IF(COUNT(AI164:AP164)=0,"",AQ164-LOOKUP(2,1/(AI164:AP164<>""),AI164:AP164))) | IF(OR(F164="",AR164=""),"",IF(COUNT(AI164:AQ164)=0,"",AR164-LOOKUP(2,1/(AI164:AQ164<>""),AI164:AQ164))) | IF(OR(F164="",AS164=""),"",IF(COUNT(AI164:AR164)=0,"",AS164-LOOKUP(2,1/(AI164:AR164<>""),AI164:AR164))) | IF(OR(F164="",AT164=""),"",IF(COUNT(AI164:AS164)=0,"",AT164-LOOKUP(2,1/(AI164:AS164<>""),AI164:AS164))) | IF(OR(F164="",AU164=""),"",IF(COUNT(AI164:AT164)=0,"",AU164-LOOKUP(2,1/(AI164:AT164<>""),AI164:AT164))) | IF(OR(F164="",AV164=""),"",IF(COUNT(AI164:AU164)=0,"",AV164-LOOKUP(2,1/(AI164:AU164<>""),AI164:AU164))) | IF(J164="","All_Provinces",IFERROR(VLOOKUP(J164,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K164="","All_Districts",IFERROR(VLOOKUP(K164,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F165="","",ROW()-3) | [18 empty] | IF(AQ165="","",AQ165) |  |  |  | IF(W165<>"",W165,IF(OR(T165="",V165=""),"",EDATE(T165,V165))) |  |  |  |  | IF(F165="","",IF(COUNT(AI165:AV165)=0,IF(AA165="","Not started",AA165),SUBSTITUTE(LOOKUP(2,1/(AI165:AV165<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F165="",COUNT(AI165:AV165)=0),"",TODAY()-LOOKUP(2,1/(AI165:AV165<>""),AI165:AV165)) | IF(OR(F165="",COUNT(AI165:AV165)<2),"",LOOKUP(2,1/(AI165:AV165<>""),AI165:AV165)-MIN(AI165:AV165)) | IF(OR(AD165="",AC165="Not started",AC165=""),"",IFERROR(AD165-IF(VLOOKUP(AC165,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC165,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F165="","",IF(OR(AA165="Cancelled",AC165="Cancelled"),"Cancelled",IF(OR(AC165="Completed / Handover",Y165<>"",Z165>=100),"Completed — on track",IF(O165="Not awarded",IF(U165="",IF(X165="","No planned date",IF(TODAY()>X165,"Behind — past planned date",IF(X165-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U165,"Behind — award date passed",IF(U165-TODAY()<=30,"At risk — close to off track","On track"))),IF(X165="","No planned date",IF(AND(TODAY()>X165,OR(Z165="",Z165<100)),"Behind — past end date",IF(AND(T165<>"",X165<>"",Z165<>"",(Z165<100),((TODAY()-T165)/MAX(X165-T165,1)*100)-Z165>15),"Behind — progress lag",IF(AND(X165-TODAY()<=30,X165-TODAY()>=0,OR(Z165="",Z165<90)),"At risk — close to off track","On track")))))))) | IF(OR(F165="",AC165="Completed / Handover",AC165="Cancelled"),"",IF(O165="Not awarded",IF(U165<>"",U165-TODAY(),IF(X165="","",X165-TODAY())),IF(X165="","",X165-TODAY()))) | [14 empty] | IF(OR(F165="",AJ165=""),"",IF(COUNT(AI165:AI165)=0,"",AJ165-LOOKUP(2,1/(AI165:AI165<>""),AI165:AI165))) | IF(OR(F165="",AK165=""),"",IF(COUNT(AI165:AJ165)=0,"",AK165-LOOKUP(2,1/(AI165:AJ165<>""),AI165:AJ165))) | IF(OR(F165="",AL165=""),"",IF(COUNT(AI165:AK165)=0,"",AL165-LOOKUP(2,1/(AI165:AK165<>""),AI165:AK165))) | IF(OR(F165="",AM165=""),"",IF(COUNT(AI165:AL165)=0,"",AM165-LOOKUP(2,1/(AI165:AL165<>""),AI165:AL165))) | IF(OR(F165="",AN165=""),"",IF(COUNT(AI165:AM165)=0,"",AN165-LOOKUP(2,1/(AI165:AM165<>""),AI165:AM165))) | IF(OR(F165="",AO165=""),"",IF(COUNT(AI165:AN165)=0,"",AO165-LOOKUP(2,1/(AI165:AN165<>""),AI165:AN165))) | IF(OR(F165="",AP165=""),"",IF(COUNT(AI165:AO165)=0,"",AP165-LOOKUP(2,1/(AI165:AO165<>""),AI165:AO165))) | IF(OR(F165="",AQ165=""),"",IF(COUNT(AI165:AP165)=0,"",AQ165-LOOKUP(2,1/(AI165:AP165<>""),AI165:AP165))) | IF(OR(F165="",AR165=""),"",IF(COUNT(AI165:AQ165)=0,"",AR165-LOOKUP(2,1/(AI165:AQ165<>""),AI165:AQ165))) | IF(OR(F165="",AS165=""),"",IF(COUNT(AI165:AR165)=0,"",AS165-LOOKUP(2,1/(AI165:AR165<>""),AI165:AR165))) | IF(OR(F165="",AT165=""),"",IF(COUNT(AI165:AS165)=0,"",AT165-LOOKUP(2,1/(AI165:AS165<>""),AI165:AS165))) | IF(OR(F165="",AU165=""),"",IF(COUNT(AI165:AT165)=0,"",AU165-LOOKUP(2,1/(AI165:AT165<>""),AI165:AT165))) | IF(OR(F165="",AV165=""),"",IF(COUNT(AI165:AU165)=0,"",AV165-LOOKUP(2,1/(AI165:AU165<>""),AI165:AU165))) | IF(J165="","All_Provinces",IFERROR(VLOOKUP(J165,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K165="","All_Districts",IFERROR(VLOOKUP(K165,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F166="","",ROW()-3) | [18 empty] | IF(AQ166="","",AQ166) |  |  |  | IF(W166<>"",W166,IF(OR(T166="",V166=""),"",EDATE(T166,V166))) |  |  |  |  | IF(F166="","",IF(COUNT(AI166:AV166)=0,IF(AA166="","Not started",AA166),SUBSTITUTE(LOOKUP(2,1/(AI166:AV166<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F166="",COUNT(AI166:AV166)=0),"",TODAY()-LOOKUP(2,1/(AI166:AV166<>""),AI166:AV166)) | IF(OR(F166="",COUNT(AI166:AV166)<2),"",LOOKUP(2,1/(AI166:AV166<>""),AI166:AV166)-MIN(AI166:AV166)) | IF(OR(AD166="",AC166="Not started",AC166=""),"",IFERROR(AD166-IF(VLOOKUP(AC166,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC166,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F166="","",IF(OR(AA166="Cancelled",AC166="Cancelled"),"Cancelled",IF(OR(AC166="Completed / Handover",Y166<>"",Z166>=100),"Completed — on track",IF(O166="Not awarded",IF(U166="",IF(X166="","No planned date",IF(TODAY()>X166,"Behind — past planned date",IF(X166-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U166,"Behind — award date passed",IF(U166-TODAY()<=30,"At risk — close to off track","On track"))),IF(X166="","No planned date",IF(AND(TODAY()>X166,OR(Z166="",Z166<100)),"Behind — past end date",IF(AND(T166<>"",X166<>"",Z166<>"",(Z166<100),((TODAY()-T166)/MAX(X166-T166,1)*100)-Z166>15),"Behind — progress lag",IF(AND(X166-TODAY()<=30,X166-TODAY()>=0,OR(Z166="",Z166<90)),"At risk — close to off track","On track")))))))) | IF(OR(F166="",AC166="Completed / Handover",AC166="Cancelled"),"",IF(O166="Not awarded",IF(U166<>"",U166-TODAY(),IF(X166="","",X166-TODAY())),IF(X166="","",X166-TODAY()))) | [14 empty] | IF(OR(F166="",AJ166=""),"",IF(COUNT(AI166:AI166)=0,"",AJ166-LOOKUP(2,1/(AI166:AI166<>""),AI166:AI166))) | IF(OR(F166="",AK166=""),"",IF(COUNT(AI166:AJ166)=0,"",AK166-LOOKUP(2,1/(AI166:AJ166<>""),AI166:AJ166))) | IF(OR(F166="",AL166=""),"",IF(COUNT(AI166:AK166)=0,"",AL166-LOOKUP(2,1/(AI166:AK166<>""),AI166:AK166))) | IF(OR(F166="",AM166=""),"",IF(COUNT(AI166:AL166)=0,"",AM166-LOOKUP(2,1/(AI166:AL166<>""),AI166:AL166))) | IF(OR(F166="",AN166=""),"",IF(COUNT(AI166:AM166)=0,"",AN166-LOOKUP(2,1/(AI166:AM166<>""),AI166:AM166))) | IF(OR(F166="",AO166=""),"",IF(COUNT(AI166:AN166)=0,"",AO166-LOOKUP(2,1/(AI166:AN166<>""),AI166:AN166))) | IF(OR(F166="",AP166=""),"",IF(COUNT(AI166:AO166)=0,"",AP166-LOOKUP(2,1/(AI166:AO166<>""),AI166:AO166))) | IF(OR(F166="",AQ166=""),"",IF(COUNT(AI166:AP166)=0,"",AQ166-LOOKUP(2,1/(AI166:AP166<>""),AI166:AP166))) | IF(OR(F166="",AR166=""),"",IF(COUNT(AI166:AQ166)=0,"",AR166-LOOKUP(2,1/(AI166:AQ166<>""),AI166:AQ166))) | IF(OR(F166="",AS166=""),"",IF(COUNT(AI166:AR166)=0,"",AS166-LOOKUP(2,1/(AI166:AR166<>""),AI166:AR166))) | IF(OR(F166="",AT166=""),"",IF(COUNT(AI166:AS166)=0,"",AT166-LOOKUP(2,1/(AI166:AS166<>""),AI166:AS166))) | IF(OR(F166="",AU166=""),"",IF(COUNT(AI166:AT166)=0,"",AU166-LOOKUP(2,1/(AI166:AT166<>""),AI166:AT166))) | IF(OR(F166="",AV166=""),"",IF(COUNT(AI166:AU166)=0,"",AV166-LOOKUP(2,1/(AI166:AU166<>""),AI166:AU166))) | IF(J166="","All_Provinces",IFERROR(VLOOKUP(J166,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K166="","All_Districts",IFERROR(VLOOKUP(K166,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F167="","",ROW()-3) | [18 empty] | IF(AQ167="","",AQ167) |  |  |  | IF(W167<>"",W167,IF(OR(T167="",V167=""),"",EDATE(T167,V167))) |  |  |  |  | IF(F167="","",IF(COUNT(AI167:AV167)=0,IF(AA167="","Not started",AA167),SUBSTITUTE(LOOKUP(2,1/(AI167:AV167<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F167="",COUNT(AI167:AV167)=0),"",TODAY()-LOOKUP(2,1/(AI167:AV167<>""),AI167:AV167)) | IF(OR(F167="",COUNT(AI167:AV167)<2),"",LOOKUP(2,1/(AI167:AV167<>""),AI167:AV167)-MIN(AI167:AV167)) | IF(OR(AD167="",AC167="Not started",AC167=""),"",IFERROR(AD167-IF(VLOOKUP(AC167,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC167,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F167="","",IF(OR(AA167="Cancelled",AC167="Cancelled"),"Cancelled",IF(OR(AC167="Completed / Handover",Y167<>"",Z167>=100),"Completed — on track",IF(O167="Not awarded",IF(U167="",IF(X167="","No planned date",IF(TODAY()>X167,"Behind — past planned date",IF(X167-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U167,"Behind — award date passed",IF(U167-TODAY()<=30,"At risk — close to off track","On track"))),IF(X167="","No planned date",IF(AND(TODAY()>X167,OR(Z167="",Z167<100)),"Behind — past end date",IF(AND(T167<>"",X167<>"",Z167<>"",(Z167<100),((TODAY()-T167)/MAX(X167-T167,1)*100)-Z167>15),"Behind — progress lag",IF(AND(X167-TODAY()<=30,X167-TODAY()>=0,OR(Z167="",Z167<90)),"At risk — close to off track","On track")))))))) | IF(OR(F167="",AC167="Completed / Handover",AC167="Cancelled"),"",IF(O167="Not awarded",IF(U167<>"",U167-TODAY(),IF(X167="","",X167-TODAY())),IF(X167="","",X167-TODAY()))) | [14 empty] | IF(OR(F167="",AJ167=""),"",IF(COUNT(AI167:AI167)=0,"",AJ167-LOOKUP(2,1/(AI167:AI167<>""),AI167:AI167))) | IF(OR(F167="",AK167=""),"",IF(COUNT(AI167:AJ167)=0,"",AK167-LOOKUP(2,1/(AI167:AJ167<>""),AI167:AJ167))) | IF(OR(F167="",AL167=""),"",IF(COUNT(AI167:AK167)=0,"",AL167-LOOKUP(2,1/(AI167:AK167<>""),AI167:AK167))) | IF(OR(F167="",AM167=""),"",IF(COUNT(AI167:AL167)=0,"",AM167-LOOKUP(2,1/(AI167:AL167<>""),AI167:AL167))) | IF(OR(F167="",AN167=""),"",IF(COUNT(AI167:AM167)=0,"",AN167-LOOKUP(2,1/(AI167:AM167<>""),AI167:AM167))) | IF(OR(F167="",AO167=""),"",IF(COUNT(AI167:AN167)=0,"",AO167-LOOKUP(2,1/(AI167:AN167<>""),AI167:AN167))) | IF(OR(F167="",AP167=""),"",IF(COUNT(AI167:AO167)=0,"",AP167-LOOKUP(2,1/(AI167:AO167<>""),AI167:AO167))) | IF(OR(F167="",AQ167=""),"",IF(COUNT(AI167:AP167)=0,"",AQ167-LOOKUP(2,1/(AI167:AP167<>""),AI167:AP167))) | IF(OR(F167="",AR167=""),"",IF(COUNT(AI167:AQ167)=0,"",AR167-LOOKUP(2,1/(AI167:AQ167<>""),AI167:AQ167))) | IF(OR(F167="",AS167=""),"",IF(COUNT(AI167:AR167)=0,"",AS167-LOOKUP(2,1/(AI167:AR167<>""),AI167:AR167))) | IF(OR(F167="",AT167=""),"",IF(COUNT(AI167:AS167)=0,"",AT167-LOOKUP(2,1/(AI167:AS167<>""),AI167:AS167))) | IF(OR(F167="",AU167=""),"",IF(COUNT(AI167:AT167)=0,"",AU167-LOOKUP(2,1/(AI167:AT167<>""),AI167:AT167))) | IF(OR(F167="",AV167=""),"",IF(COUNT(AI167:AU167)=0,"",AV167-LOOKUP(2,1/(AI167:AU167<>""),AI167:AU167))) | IF(J167="","All_Provinces",IFERROR(VLOOKUP(J167,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K167="","All_Districts",IFERROR(VLOOKUP(K167,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F168="","",ROW()-3) | [18 empty] | IF(AQ168="","",AQ168) |  |  |  | IF(W168<>"",W168,IF(OR(T168="",V168=""),"",EDATE(T168,V168))) |  |  |  |  | IF(F168="","",IF(COUNT(AI168:AV168)=0,IF(AA168="","Not started",AA168),SUBSTITUTE(LOOKUP(2,1/(AI168:AV168<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F168="",COUNT(AI168:AV168)=0),"",TODAY()-LOOKUP(2,1/(AI168:AV168<>""),AI168:AV168)) | IF(OR(F168="",COUNT(AI168:AV168)<2),"",LOOKUP(2,1/(AI168:AV168<>""),AI168:AV168)-MIN(AI168:AV168)) | IF(OR(AD168="",AC168="Not started",AC168=""),"",IFERROR(AD168-IF(VLOOKUP(AC168,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC168,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F168="","",IF(OR(AA168="Cancelled",AC168="Cancelled"),"Cancelled",IF(OR(AC168="Completed / Handover",Y168<>"",Z168>=100),"Completed — on track",IF(O168="Not awarded",IF(U168="",IF(X168="","No planned date",IF(TODAY()>X168,"Behind — past planned date",IF(X168-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U168,"Behind — award date passed",IF(U168-TODAY()<=30,"At risk — close to off track","On track"))),IF(X168="","No planned date",IF(AND(TODAY()>X168,OR(Z168="",Z168<100)),"Behind — past end date",IF(AND(T168<>"",X168<>"",Z168<>"",(Z168<100),((TODAY()-T168)/MAX(X168-T168,1)*100)-Z168>15),"Behind — progress lag",IF(AND(X168-TODAY()<=30,X168-TODAY()>=0,OR(Z168="",Z168<90)),"At risk — close to off track","On track")))))))) | IF(OR(F168="",AC168="Completed / Handover",AC168="Cancelled"),"",IF(O168="Not awarded",IF(U168<>"",U168-TODAY(),IF(X168="","",X168-TODAY())),IF(X168="","",X168-TODAY()))) | [14 empty] | IF(OR(F168="",AJ168=""),"",IF(COUNT(AI168:AI168)=0,"",AJ168-LOOKUP(2,1/(AI168:AI168<>""),AI168:AI168))) | IF(OR(F168="",AK168=""),"",IF(COUNT(AI168:AJ168)=0,"",AK168-LOOKUP(2,1/(AI168:AJ168<>""),AI168:AJ168))) | IF(OR(F168="",AL168=""),"",IF(COUNT(AI168:AK168)=0,"",AL168-LOOKUP(2,1/(AI168:AK168<>""),AI168:AK168))) | IF(OR(F168="",AM168=""),"",IF(COUNT(AI168:AL168)=0,"",AM168-LOOKUP(2,1/(AI168:AL168<>""),AI168:AL168))) | IF(OR(F168="",AN168=""),"",IF(COUNT(AI168:AM168)=0,"",AN168-LOOKUP(2,1/(AI168:AM168<>""),AI168:AM168))) | IF(OR(F168="",AO168=""),"",IF(COUNT(AI168:AN168)=0,"",AO168-LOOKUP(2,1/(AI168:AN168<>""),AI168:AN168))) | IF(OR(F168="",AP168=""),"",IF(COUNT(AI168:AO168)=0,"",AP168-LOOKUP(2,1/(AI168:AO168<>""),AI168:AO168))) | IF(OR(F168="",AQ168=""),"",IF(COUNT(AI168:AP168)=0,"",AQ168-LOOKUP(2,1/(AI168:AP168<>""),AI168:AP168))) | IF(OR(F168="",AR168=""),"",IF(COUNT(AI168:AQ168)=0,"",AR168-LOOKUP(2,1/(AI168:AQ168<>""),AI168:AQ168))) | IF(OR(F168="",AS168=""),"",IF(COUNT(AI168:AR168)=0,"",AS168-LOOKUP(2,1/(AI168:AR168<>""),AI168:AR168))) | IF(OR(F168="",AT168=""),"",IF(COUNT(AI168:AS168)=0,"",AT168-LOOKUP(2,1/(AI168:AS168<>""),AI168:AS168))) | IF(OR(F168="",AU168=""),"",IF(COUNT(AI168:AT168)=0,"",AU168-LOOKUP(2,1/(AI168:AT168<>""),AI168:AT168))) | IF(OR(F168="",AV168=""),"",IF(COUNT(AI168:AU168)=0,"",AV168-LOOKUP(2,1/(AI168:AU168<>""),AI168:AU168))) | IF(J168="","All_Provinces",IFERROR(VLOOKUP(J168,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K168="","All_Districts",IFERROR(VLOOKUP(K168,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F169="","",ROW()-3) | [18 empty] | IF(AQ169="","",AQ169) |  |  |  | IF(W169<>"",W169,IF(OR(T169="",V169=""),"",EDATE(T169,V169))) |  |  |  |  | IF(F169="","",IF(COUNT(AI169:AV169)=0,IF(AA169="","Not started",AA169),SUBSTITUTE(LOOKUP(2,1/(AI169:AV169<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F169="",COUNT(AI169:AV169)=0),"",TODAY()-LOOKUP(2,1/(AI169:AV169<>""),AI169:AV169)) | IF(OR(F169="",COUNT(AI169:AV169)<2),"",LOOKUP(2,1/(AI169:AV169<>""),AI169:AV169)-MIN(AI169:AV169)) | IF(OR(AD169="",AC169="Not started",AC169=""),"",IFERROR(AD169-IF(VLOOKUP(AC169,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC169,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F169="","",IF(OR(AA169="Cancelled",AC169="Cancelled"),"Cancelled",IF(OR(AC169="Completed / Handover",Y169<>"",Z169>=100),"Completed — on track",IF(O169="Not awarded",IF(U169="",IF(X169="","No planned date",IF(TODAY()>X169,"Behind — past planned date",IF(X169-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U169,"Behind — award date passed",IF(U169-TODAY()<=30,"At risk — close to off track","On track"))),IF(X169="","No planned date",IF(AND(TODAY()>X169,OR(Z169="",Z169<100)),"Behind — past end date",IF(AND(T169<>"",X169<>"",Z169<>"",(Z169<100),((TODAY()-T169)/MAX(X169-T169,1)*100)-Z169>15),"Behind — progress lag",IF(AND(X169-TODAY()<=30,X169-TODAY()>=0,OR(Z169="",Z169<90)),"At risk — close to off track","On track")))))))) | IF(OR(F169="",AC169="Completed / Handover",AC169="Cancelled"),"",IF(O169="Not awarded",IF(U169<>"",U169-TODAY(),IF(X169="","",X169-TODAY())),IF(X169="","",X169-TODAY()))) | [14 empty] | IF(OR(F169="",AJ169=""),"",IF(COUNT(AI169:AI169)=0,"",AJ169-LOOKUP(2,1/(AI169:AI169<>""),AI169:AI169))) | IF(OR(F169="",AK169=""),"",IF(COUNT(AI169:AJ169)=0,"",AK169-LOOKUP(2,1/(AI169:AJ169<>""),AI169:AJ169))) | IF(OR(F169="",AL169=""),"",IF(COUNT(AI169:AK169)=0,"",AL169-LOOKUP(2,1/(AI169:AK169<>""),AI169:AK169))) | IF(OR(F169="",AM169=""),"",IF(COUNT(AI169:AL169)=0,"",AM169-LOOKUP(2,1/(AI169:AL169<>""),AI169:AL169))) | IF(OR(F169="",AN169=""),"",IF(COUNT(AI169:AM169)=0,"",AN169-LOOKUP(2,1/(AI169:AM169<>""),AI169:AM169))) | IF(OR(F169="",AO169=""),"",IF(COUNT(AI169:AN169)=0,"",AO169-LOOKUP(2,1/(AI169:AN169<>""),AI169:AN169))) | IF(OR(F169="",AP169=""),"",IF(COUNT(AI169:AO169)=0,"",AP169-LOOKUP(2,1/(AI169:AO169<>""),AI169:AO169))) | IF(OR(F169="",AQ169=""),"",IF(COUNT(AI169:AP169)=0,"",AQ169-LOOKUP(2,1/(AI169:AP169<>""),AI169:AP169))) | IF(OR(F169="",AR169=""),"",IF(COUNT(AI169:AQ169)=0,"",AR169-LOOKUP(2,1/(AI169:AQ169<>""),AI169:AQ169))) | IF(OR(F169="",AS169=""),"",IF(COUNT(AI169:AR169)=0,"",AS169-LOOKUP(2,1/(AI169:AR169<>""),AI169:AR169))) | IF(OR(F169="",AT169=""),"",IF(COUNT(AI169:AS169)=0,"",AT169-LOOKUP(2,1/(AI169:AS169<>""),AI169:AS169))) | IF(OR(F169="",AU169=""),"",IF(COUNT(AI169:AT169)=0,"",AU169-LOOKUP(2,1/(AI169:AT169<>""),AI169:AT169))) | IF(OR(F169="",AV169=""),"",IF(COUNT(AI169:AU169)=0,"",AV169-LOOKUP(2,1/(AI169:AU169<>""),AI169:AU169))) | IF(J169="","All_Provinces",IFERROR(VLOOKUP(J169,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K169="","All_Districts",IFERROR(VLOOKUP(K169,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F170="","",ROW()-3) | [18 empty] | IF(AQ170="","",AQ170) |  |  |  | IF(W170<>"",W170,IF(OR(T170="",V170=""),"",EDATE(T170,V170))) |  |  |  |  | IF(F170="","",IF(COUNT(AI170:AV170)=0,IF(AA170="","Not started",AA170),SUBSTITUTE(LOOKUP(2,1/(AI170:AV170<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F170="",COUNT(AI170:AV170)=0),"",TODAY()-LOOKUP(2,1/(AI170:AV170<>""),AI170:AV170)) | IF(OR(F170="",COUNT(AI170:AV170)<2),"",LOOKUP(2,1/(AI170:AV170<>""),AI170:AV170)-MIN(AI170:AV170)) | IF(OR(AD170="",AC170="Not started",AC170=""),"",IFERROR(AD170-IF(VLOOKUP(AC170,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC170,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F170="","",IF(OR(AA170="Cancelled",AC170="Cancelled"),"Cancelled",IF(OR(AC170="Completed / Handover",Y170<>"",Z170>=100),"Completed — on track",IF(O170="Not awarded",IF(U170="",IF(X170="","No planned date",IF(TODAY()>X170,"Behind — past planned date",IF(X170-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U170,"Behind — award date passed",IF(U170-TODAY()<=30,"At risk — close to off track","On track"))),IF(X170="","No planned date",IF(AND(TODAY()>X170,OR(Z170="",Z170<100)),"Behind — past end date",IF(AND(T170<>"",X170<>"",Z170<>"",(Z170<100),((TODAY()-T170)/MAX(X170-T170,1)*100)-Z170>15),"Behind — progress lag",IF(AND(X170-TODAY()<=30,X170-TODAY()>=0,OR(Z170="",Z170<90)),"At risk — close to off track","On track")))))))) | IF(OR(F170="",AC170="Completed / Handover",AC170="Cancelled"),"",IF(O170="Not awarded",IF(U170<>"",U170-TODAY(),IF(X170="","",X170-TODAY())),IF(X170="","",X170-TODAY()))) | [14 empty] | IF(OR(F170="",AJ170=""),"",IF(COUNT(AI170:AI170)=0,"",AJ170-LOOKUP(2,1/(AI170:AI170<>""),AI170:AI170))) | IF(OR(F170="",AK170=""),"",IF(COUNT(AI170:AJ170)=0,"",AK170-LOOKUP(2,1/(AI170:AJ170<>""),AI170:AJ170))) | IF(OR(F170="",AL170=""),"",IF(COUNT(AI170:AK170)=0,"",AL170-LOOKUP(2,1/(AI170:AK170<>""),AI170:AK170))) | IF(OR(F170="",AM170=""),"",IF(COUNT(AI170:AL170)=0,"",AM170-LOOKUP(2,1/(AI170:AL170<>""),AI170:AL170))) | IF(OR(F170="",AN170=""),"",IF(COUNT(AI170:AM170)=0,"",AN170-LOOKUP(2,1/(AI170:AM170<>""),AI170:AM170))) | IF(OR(F170="",AO170=""),"",IF(COUNT(AI170:AN170)=0,"",AO170-LOOKUP(2,1/(AI170:AN170<>""),AI170:AN170))) | IF(OR(F170="",AP170=""),"",IF(COUNT(AI170:AO170)=0,"",AP170-LOOKUP(2,1/(AI170:AO170<>""),AI170:AO170))) | IF(OR(F170="",AQ170=""),"",IF(COUNT(AI170:AP170)=0,"",AQ170-LOOKUP(2,1/(AI170:AP170<>""),AI170:AP170))) | IF(OR(F170="",AR170=""),"",IF(COUNT(AI170:AQ170)=0,"",AR170-LOOKUP(2,1/(AI170:AQ170<>""),AI170:AQ170))) | IF(OR(F170="",AS170=""),"",IF(COUNT(AI170:AR170)=0,"",AS170-LOOKUP(2,1/(AI170:AR170<>""),AI170:AR170))) | IF(OR(F170="",AT170=""),"",IF(COUNT(AI170:AS170)=0,"",AT170-LOOKUP(2,1/(AI170:AS170<>""),AI170:AS170))) | IF(OR(F170="",AU170=""),"",IF(COUNT(AI170:AT170)=0,"",AU170-LOOKUP(2,1/(AI170:AT170<>""),AI170:AT170))) | IF(OR(F170="",AV170=""),"",IF(COUNT(AI170:AU170)=0,"",AV170-LOOKUP(2,1/(AI170:AU170<>""),AI170:AU170))) | IF(J170="","All_Provinces",IFERROR(VLOOKUP(J170,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K170="","All_Districts",IFERROR(VLOOKUP(K170,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F171="","",ROW()-3) | [18 empty] | IF(AQ171="","",AQ171) |  |  |  | IF(W171<>"",W171,IF(OR(T171="",V171=""),"",EDATE(T171,V171))) |  |  |  |  | IF(F171="","",IF(COUNT(AI171:AV171)=0,IF(AA171="","Not started",AA171),SUBSTITUTE(LOOKUP(2,1/(AI171:AV171<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F171="",COUNT(AI171:AV171)=0),"",TODAY()-LOOKUP(2,1/(AI171:AV171<>""),AI171:AV171)) | IF(OR(F171="",COUNT(AI171:AV171)<2),"",LOOKUP(2,1/(AI171:AV171<>""),AI171:AV171)-MIN(AI171:AV171)) | IF(OR(AD171="",AC171="Not started",AC171=""),"",IFERROR(AD171-IF(VLOOKUP(AC171,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC171,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F171="","",IF(OR(AA171="Cancelled",AC171="Cancelled"),"Cancelled",IF(OR(AC171="Completed / Handover",Y171<>"",Z171>=100),"Completed — on track",IF(O171="Not awarded",IF(U171="",IF(X171="","No planned date",IF(TODAY()>X171,"Behind — past planned date",IF(X171-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U171,"Behind — award date passed",IF(U171-TODAY()<=30,"At risk — close to off track","On track"))),IF(X171="","No planned date",IF(AND(TODAY()>X171,OR(Z171="",Z171<100)),"Behind — past end date",IF(AND(T171<>"",X171<>"",Z171<>"",(Z171<100),((TODAY()-T171)/MAX(X171-T171,1)*100)-Z171>15),"Behind — progress lag",IF(AND(X171-TODAY()<=30,X171-TODAY()>=0,OR(Z171="",Z171<90)),"At risk — close to off track","On track")))))))) | IF(OR(F171="",AC171="Completed / Handover",AC171="Cancelled"),"",IF(O171="Not awarded",IF(U171<>"",U171-TODAY(),IF(X171="","",X171-TODAY())),IF(X171="","",X171-TODAY()))) | [14 empty] | IF(OR(F171="",AJ171=""),"",IF(COUNT(AI171:AI171)=0,"",AJ171-LOOKUP(2,1/(AI171:AI171<>""),AI171:AI171))) | IF(OR(F171="",AK171=""),"",IF(COUNT(AI171:AJ171)=0,"",AK171-LOOKUP(2,1/(AI171:AJ171<>""),AI171:AJ171))) | IF(OR(F171="",AL171=""),"",IF(COUNT(AI171:AK171)=0,"",AL171-LOOKUP(2,1/(AI171:AK171<>""),AI171:AK171))) | IF(OR(F171="",AM171=""),"",IF(COUNT(AI171:AL171)=0,"",AM171-LOOKUP(2,1/(AI171:AL171<>""),AI171:AL171))) | IF(OR(F171="",AN171=""),"",IF(COUNT(AI171:AM171)=0,"",AN171-LOOKUP(2,1/(AI171:AM171<>""),AI171:AM171))) | IF(OR(F171="",AO171=""),"",IF(COUNT(AI171:AN171)=0,"",AO171-LOOKUP(2,1/(AI171:AN171<>""),AI171:AN171))) | IF(OR(F171="",AP171=""),"",IF(COUNT(AI171:AO171)=0,"",AP171-LOOKUP(2,1/(AI171:AO171<>""),AI171:AO171))) | IF(OR(F171="",AQ171=""),"",IF(COUNT(AI171:AP171)=0,"",AQ171-LOOKUP(2,1/(AI171:AP171<>""),AI171:AP171))) | IF(OR(F171="",AR171=""),"",IF(COUNT(AI171:AQ171)=0,"",AR171-LOOKUP(2,1/(AI171:AQ171<>""),AI171:AQ171))) | IF(OR(F171="",AS171=""),"",IF(COUNT(AI171:AR171)=0,"",AS171-LOOKUP(2,1/(AI171:AR171<>""),AI171:AR171))) | IF(OR(F171="",AT171=""),"",IF(COUNT(AI171:AS171)=0,"",AT171-LOOKUP(2,1/(AI171:AS171<>""),AI171:AS171))) | IF(OR(F171="",AU171=""),"",IF(COUNT(AI171:AT171)=0,"",AU171-LOOKUP(2,1/(AI171:AT171<>""),AI171:AT171))) | IF(OR(F171="",AV171=""),"",IF(COUNT(AI171:AU171)=0,"",AV171-LOOKUP(2,1/(AI171:AU171<>""),AI171:AU171))) | IF(J171="","All_Provinces",IFERROR(VLOOKUP(J171,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K171="","All_Districts",IFERROR(VLOOKUP(K171,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F172="","",ROW()-3) | [18 empty] | IF(AQ172="","",AQ172) |  |  |  | IF(W172<>"",W172,IF(OR(T172="",V172=""),"",EDATE(T172,V172))) |  |  |  |  | IF(F172="","",IF(COUNT(AI172:AV172)=0,IF(AA172="","Not started",AA172),SUBSTITUTE(LOOKUP(2,1/(AI172:AV172<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F172="",COUNT(AI172:AV172)=0),"",TODAY()-LOOKUP(2,1/(AI172:AV172<>""),AI172:AV172)) | IF(OR(F172="",COUNT(AI172:AV172)<2),"",LOOKUP(2,1/(AI172:AV172<>""),AI172:AV172)-MIN(AI172:AV172)) | IF(OR(AD172="",AC172="Not started",AC172=""),"",IFERROR(AD172-IF(VLOOKUP(AC172,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC172,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F172="","",IF(OR(AA172="Cancelled",AC172="Cancelled"),"Cancelled",IF(OR(AC172="Completed / Handover",Y172<>"",Z172>=100),"Completed — on track",IF(O172="Not awarded",IF(U172="",IF(X172="","No planned date",IF(TODAY()>X172,"Behind — past planned date",IF(X172-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U172,"Behind — award date passed",IF(U172-TODAY()<=30,"At risk — close to off track","On track"))),IF(X172="","No planned date",IF(AND(TODAY()>X172,OR(Z172="",Z172<100)),"Behind — past end date",IF(AND(T172<>"",X172<>"",Z172<>"",(Z172<100),((TODAY()-T172)/MAX(X172-T172,1)*100)-Z172>15),"Behind — progress lag",IF(AND(X172-TODAY()<=30,X172-TODAY()>=0,OR(Z172="",Z172<90)),"At risk — close to off track","On track")))))))) | IF(OR(F172="",AC172="Completed / Handover",AC172="Cancelled"),"",IF(O172="Not awarded",IF(U172<>"",U172-TODAY(),IF(X172="","",X172-TODAY())),IF(X172="","",X172-TODAY()))) | [14 empty] | IF(OR(F172="",AJ172=""),"",IF(COUNT(AI172:AI172)=0,"",AJ172-LOOKUP(2,1/(AI172:AI172<>""),AI172:AI172))) | IF(OR(F172="",AK172=""),"",IF(COUNT(AI172:AJ172)=0,"",AK172-LOOKUP(2,1/(AI172:AJ172<>""),AI172:AJ172))) | IF(OR(F172="",AL172=""),"",IF(COUNT(AI172:AK172)=0,"",AL172-LOOKUP(2,1/(AI172:AK172<>""),AI172:AK172))) | IF(OR(F172="",AM172=""),"",IF(COUNT(AI172:AL172)=0,"",AM172-LOOKUP(2,1/(AI172:AL172<>""),AI172:AL172))) | IF(OR(F172="",AN172=""),"",IF(COUNT(AI172:AM172)=0,"",AN172-LOOKUP(2,1/(AI172:AM172<>""),AI172:AM172))) | IF(OR(F172="",AO172=""),"",IF(COUNT(AI172:AN172)=0,"",AO172-LOOKUP(2,1/(AI172:AN172<>""),AI172:AN172))) | IF(OR(F172="",AP172=""),"",IF(COUNT(AI172:AO172)=0,"",AP172-LOOKUP(2,1/(AI172:AO172<>""),AI172:AO172))) | IF(OR(F172="",AQ172=""),"",IF(COUNT(AI172:AP172)=0,"",AQ172-LOOKUP(2,1/(AI172:AP172<>""),AI172:AP172))) | IF(OR(F172="",AR172=""),"",IF(COUNT(AI172:AQ172)=0,"",AR172-LOOKUP(2,1/(AI172:AQ172<>""),AI172:AQ172))) | IF(OR(F172="",AS172=""),"",IF(COUNT(AI172:AR172)=0,"",AS172-LOOKUP(2,1/(AI172:AR172<>""),AI172:AR172))) | IF(OR(F172="",AT172=""),"",IF(COUNT(AI172:AS172)=0,"",AT172-LOOKUP(2,1/(AI172:AS172<>""),AI172:AS172))) | IF(OR(F172="",AU172=""),"",IF(COUNT(AI172:AT172)=0,"",AU172-LOOKUP(2,1/(AI172:AT172<>""),AI172:AT172))) | IF(OR(F172="",AV172=""),"",IF(COUNT(AI172:AU172)=0,"",AV172-LOOKUP(2,1/(AI172:AU172<>""),AI172:AU172))) | IF(J172="","All_Provinces",IFERROR(VLOOKUP(J172,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K172="","All_Districts",IFERROR(VLOOKUP(K172,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F173="","",ROW()-3) | [18 empty] | IF(AQ173="","",AQ173) |  |  |  | IF(W173<>"",W173,IF(OR(T173="",V173=""),"",EDATE(T173,V173))) |  |  |  |  | IF(F173="","",IF(COUNT(AI173:AV173)=0,IF(AA173="","Not started",AA173),SUBSTITUTE(LOOKUP(2,1/(AI173:AV173<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F173="",COUNT(AI173:AV173)=0),"",TODAY()-LOOKUP(2,1/(AI173:AV173<>""),AI173:AV173)) | IF(OR(F173="",COUNT(AI173:AV173)<2),"",LOOKUP(2,1/(AI173:AV173<>""),AI173:AV173)-MIN(AI173:AV173)) | IF(OR(AD173="",AC173="Not started",AC173=""),"",IFERROR(AD173-IF(VLOOKUP(AC173,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC173,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F173="","",IF(OR(AA173="Cancelled",AC173="Cancelled"),"Cancelled",IF(OR(AC173="Completed / Handover",Y173<>"",Z173>=100),"Completed — on track",IF(O173="Not awarded",IF(U173="",IF(X173="","No planned date",IF(TODAY()>X173,"Behind — past planned date",IF(X173-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U173,"Behind — award date passed",IF(U173-TODAY()<=30,"At risk — close to off track","On track"))),IF(X173="","No planned date",IF(AND(TODAY()>X173,OR(Z173="",Z173<100)),"Behind — past end date",IF(AND(T173<>"",X173<>"",Z173<>"",(Z173<100),((TODAY()-T173)/MAX(X173-T173,1)*100)-Z173>15),"Behind — progress lag",IF(AND(X173-TODAY()<=30,X173-TODAY()>=0,OR(Z173="",Z173<90)),"At risk — close to off track","On track")))))))) | IF(OR(F173="",AC173="Completed / Handover",AC173="Cancelled"),"",IF(O173="Not awarded",IF(U173<>"",U173-TODAY(),IF(X173="","",X173-TODAY())),IF(X173="","",X173-TODAY()))) | [14 empty] | IF(OR(F173="",AJ173=""),"",IF(COUNT(AI173:AI173)=0,"",AJ173-LOOKUP(2,1/(AI173:AI173<>""),AI173:AI173))) | IF(OR(F173="",AK173=""),"",IF(COUNT(AI173:AJ173)=0,"",AK173-LOOKUP(2,1/(AI173:AJ173<>""),AI173:AJ173))) | IF(OR(F173="",AL173=""),"",IF(COUNT(AI173:AK173)=0,"",AL173-LOOKUP(2,1/(AI173:AK173<>""),AI173:AK173))) | IF(OR(F173="",AM173=""),"",IF(COUNT(AI173:AL173)=0,"",AM173-LOOKUP(2,1/(AI173:AL173<>""),AI173:AL173))) | IF(OR(F173="",AN173=""),"",IF(COUNT(AI173:AM173)=0,"",AN173-LOOKUP(2,1/(AI173:AM173<>""),AI173:AM173))) | IF(OR(F173="",AO173=""),"",IF(COUNT(AI173:AN173)=0,"",AO173-LOOKUP(2,1/(AI173:AN173<>""),AI173:AN173))) | IF(OR(F173="",AP173=""),"",IF(COUNT(AI173:AO173)=0,"",AP173-LOOKUP(2,1/(AI173:AO173<>""),AI173:AO173))) | IF(OR(F173="",AQ173=""),"",IF(COUNT(AI173:AP173)=0,"",AQ173-LOOKUP(2,1/(AI173:AP173<>""),AI173:AP173))) | IF(OR(F173="",AR173=""),"",IF(COUNT(AI173:AQ173)=0,"",AR173-LOOKUP(2,1/(AI173:AQ173<>""),AI173:AQ173))) | IF(OR(F173="",AS173=""),"",IF(COUNT(AI173:AR173)=0,"",AS173-LOOKUP(2,1/(AI173:AR173<>""),AI173:AR173))) | IF(OR(F173="",AT173=""),"",IF(COUNT(AI173:AS173)=0,"",AT173-LOOKUP(2,1/(AI173:AS173<>""),AI173:AS173))) | IF(OR(F173="",AU173=""),"",IF(COUNT(AI173:AT173)=0,"",AU173-LOOKUP(2,1/(AI173:AT173<>""),AI173:AT173))) | IF(OR(F173="",AV173=""),"",IF(COUNT(AI173:AU173)=0,"",AV173-LOOKUP(2,1/(AI173:AU173<>""),AI173:AU173))) | IF(J173="","All_Provinces",IFERROR(VLOOKUP(J173,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K173="","All_Districts",IFERROR(VLOOKUP(K173,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F174="","",ROW()-3) | [18 empty] | IF(AQ174="","",AQ174) |  |  |  | IF(W174<>"",W174,IF(OR(T174="",V174=""),"",EDATE(T174,V174))) |  |  |  |  | IF(F174="","",IF(COUNT(AI174:AV174)=0,IF(AA174="","Not started",AA174),SUBSTITUTE(LOOKUP(2,1/(AI174:AV174<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F174="",COUNT(AI174:AV174)=0),"",TODAY()-LOOKUP(2,1/(AI174:AV174<>""),AI174:AV174)) | IF(OR(F174="",COUNT(AI174:AV174)<2),"",LOOKUP(2,1/(AI174:AV174<>""),AI174:AV174)-MIN(AI174:AV174)) | IF(OR(AD174="",AC174="Not started",AC174=""),"",IFERROR(AD174-IF(VLOOKUP(AC174,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC174,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F174="","",IF(OR(AA174="Cancelled",AC174="Cancelled"),"Cancelled",IF(OR(AC174="Completed / Handover",Y174<>"",Z174>=100),"Completed — on track",IF(O174="Not awarded",IF(U174="",IF(X174="","No planned date",IF(TODAY()>X174,"Behind — past planned date",IF(X174-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U174,"Behind — award date passed",IF(U174-TODAY()<=30,"At risk — close to off track","On track"))),IF(X174="","No planned date",IF(AND(TODAY()>X174,OR(Z174="",Z174<100)),"Behind — past end date",IF(AND(T174<>"",X174<>"",Z174<>"",(Z174<100),((TODAY()-T174)/MAX(X174-T174,1)*100)-Z174>15),"Behind — progress lag",IF(AND(X174-TODAY()<=30,X174-TODAY()>=0,OR(Z174="",Z174<90)),"At risk — close to off track","On track")))))))) | IF(OR(F174="",AC174="Completed / Handover",AC174="Cancelled"),"",IF(O174="Not awarded",IF(U174<>"",U174-TODAY(),IF(X174="","",X174-TODAY())),IF(X174="","",X174-TODAY()))) | [14 empty] | IF(OR(F174="",AJ174=""),"",IF(COUNT(AI174:AI174)=0,"",AJ174-LOOKUP(2,1/(AI174:AI174<>""),AI174:AI174))) | IF(OR(F174="",AK174=""),"",IF(COUNT(AI174:AJ174)=0,"",AK174-LOOKUP(2,1/(AI174:AJ174<>""),AI174:AJ174))) | IF(OR(F174="",AL174=""),"",IF(COUNT(AI174:AK174)=0,"",AL174-LOOKUP(2,1/(AI174:AK174<>""),AI174:AK174))) | IF(OR(F174="",AM174=""),"",IF(COUNT(AI174:AL174)=0,"",AM174-LOOKUP(2,1/(AI174:AL174<>""),AI174:AL174))) | IF(OR(F174="",AN174=""),"",IF(COUNT(AI174:AM174)=0,"",AN174-LOOKUP(2,1/(AI174:AM174<>""),AI174:AM174))) | IF(OR(F174="",AO174=""),"",IF(COUNT(AI174:AN174)=0,"",AO174-LOOKUP(2,1/(AI174:AN174<>""),AI174:AN174))) | IF(OR(F174="",AP174=""),"",IF(COUNT(AI174:AO174)=0,"",AP174-LOOKUP(2,1/(AI174:AO174<>""),AI174:AO174))) | IF(OR(F174="",AQ174=""),"",IF(COUNT(AI174:AP174)=0,"",AQ174-LOOKUP(2,1/(AI174:AP174<>""),AI174:AP174))) | IF(OR(F174="",AR174=""),"",IF(COUNT(AI174:AQ174)=0,"",AR174-LOOKUP(2,1/(AI174:AQ174<>""),AI174:AQ174))) | IF(OR(F174="",AS174=""),"",IF(COUNT(AI174:AR174)=0,"",AS174-LOOKUP(2,1/(AI174:AR174<>""),AI174:AR174))) | IF(OR(F174="",AT174=""),"",IF(COUNT(AI174:AS174)=0,"",AT174-LOOKUP(2,1/(AI174:AS174<>""),AI174:AS174))) | IF(OR(F174="",AU174=""),"",IF(COUNT(AI174:AT174)=0,"",AU174-LOOKUP(2,1/(AI174:AT174<>""),AI174:AT174))) | IF(OR(F174="",AV174=""),"",IF(COUNT(AI174:AU174)=0,"",AV174-LOOKUP(2,1/(AI174:AU174<>""),AI174:AU174))) | IF(J174="","All_Provinces",IFERROR(VLOOKUP(J174,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K174="","All_Districts",IFERROR(VLOOKUP(K174,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F175="","",ROW()-3) | [18 empty] | IF(AQ175="","",AQ175) |  |  |  | IF(W175<>"",W175,IF(OR(T175="",V175=""),"",EDATE(T175,V175))) |  |  |  |  | IF(F175="","",IF(COUNT(AI175:AV175)=0,IF(AA175="","Not started",AA175),SUBSTITUTE(LOOKUP(2,1/(AI175:AV175<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F175="",COUNT(AI175:AV175)=0),"",TODAY()-LOOKUP(2,1/(AI175:AV175<>""),AI175:AV175)) | IF(OR(F175="",COUNT(AI175:AV175)<2),"",LOOKUP(2,1/(AI175:AV175<>""),AI175:AV175)-MIN(AI175:AV175)) | IF(OR(AD175="",AC175="Not started",AC175=""),"",IFERROR(AD175-IF(VLOOKUP(AC175,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC175,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F175="","",IF(OR(AA175="Cancelled",AC175="Cancelled"),"Cancelled",IF(OR(AC175="Completed / Handover",Y175<>"",Z175>=100),"Completed — on track",IF(O175="Not awarded",IF(U175="",IF(X175="","No planned date",IF(TODAY()>X175,"Behind — past planned date",IF(X175-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U175,"Behind — award date passed",IF(U175-TODAY()<=30,"At risk — close to off track","On track"))),IF(X175="","No planned date",IF(AND(TODAY()>X175,OR(Z175="",Z175<100)),"Behind — past end date",IF(AND(T175<>"",X175<>"",Z175<>"",(Z175<100),((TODAY()-T175)/MAX(X175-T175,1)*100)-Z175>15),"Behind — progress lag",IF(AND(X175-TODAY()<=30,X175-TODAY()>=0,OR(Z175="",Z175<90)),"At risk — close to off track","On track")))))))) | IF(OR(F175="",AC175="Completed / Handover",AC175="Cancelled"),"",IF(O175="Not awarded",IF(U175<>"",U175-TODAY(),IF(X175="","",X175-TODAY())),IF(X175="","",X175-TODAY()))) | [14 empty] | IF(OR(F175="",AJ175=""),"",IF(COUNT(AI175:AI175)=0,"",AJ175-LOOKUP(2,1/(AI175:AI175<>""),AI175:AI175))) | IF(OR(F175="",AK175=""),"",IF(COUNT(AI175:AJ175)=0,"",AK175-LOOKUP(2,1/(AI175:AJ175<>""),AI175:AJ175))) | IF(OR(F175="",AL175=""),"",IF(COUNT(AI175:AK175)=0,"",AL175-LOOKUP(2,1/(AI175:AK175<>""),AI175:AK175))) | IF(OR(F175="",AM175=""),"",IF(COUNT(AI175:AL175)=0,"",AM175-LOOKUP(2,1/(AI175:AL175<>""),AI175:AL175))) | IF(OR(F175="",AN175=""),"",IF(COUNT(AI175:AM175)=0,"",AN175-LOOKUP(2,1/(AI175:AM175<>""),AI175:AM175))) | IF(OR(F175="",AO175=""),"",IF(COUNT(AI175:AN175)=0,"",AO175-LOOKUP(2,1/(AI175:AN175<>""),AI175:AN175))) | IF(OR(F175="",AP175=""),"",IF(COUNT(AI175:AO175)=0,"",AP175-LOOKUP(2,1/(AI175:AO175<>""),AI175:AO175))) | IF(OR(F175="",AQ175=""),"",IF(COUNT(AI175:AP175)=0,"",AQ175-LOOKUP(2,1/(AI175:AP175<>""),AI175:AP175))) | IF(OR(F175="",AR175=""),"",IF(COUNT(AI175:AQ175)=0,"",AR175-LOOKUP(2,1/(AI175:AQ175<>""),AI175:AQ175))) | IF(OR(F175="",AS175=""),"",IF(COUNT(AI175:AR175)=0,"",AS175-LOOKUP(2,1/(AI175:AR175<>""),AI175:AR175))) | IF(OR(F175="",AT175=""),"",IF(COUNT(AI175:AS175)=0,"",AT175-LOOKUP(2,1/(AI175:AS175<>""),AI175:AS175))) | IF(OR(F175="",AU175=""),"",IF(COUNT(AI175:AT175)=0,"",AU175-LOOKUP(2,1/(AI175:AT175<>""),AI175:AT175))) | IF(OR(F175="",AV175=""),"",IF(COUNT(AI175:AU175)=0,"",AV175-LOOKUP(2,1/(AI175:AU175<>""),AI175:AU175))) | IF(J175="","All_Provinces",IFERROR(VLOOKUP(J175,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K175="","All_Districts",IFERROR(VLOOKUP(K175,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F176="","",ROW()-3) | [18 empty] | IF(AQ176="","",AQ176) |  |  |  | IF(W176<>"",W176,IF(OR(T176="",V176=""),"",EDATE(T176,V176))) |  |  |  |  | IF(F176="","",IF(COUNT(AI176:AV176)=0,IF(AA176="","Not started",AA176),SUBSTITUTE(LOOKUP(2,1/(AI176:AV176<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F176="",COUNT(AI176:AV176)=0),"",TODAY()-LOOKUP(2,1/(AI176:AV176<>""),AI176:AV176)) | IF(OR(F176="",COUNT(AI176:AV176)<2),"",LOOKUP(2,1/(AI176:AV176<>""),AI176:AV176)-MIN(AI176:AV176)) | IF(OR(AD176="",AC176="Not started",AC176=""),"",IFERROR(AD176-IF(VLOOKUP(AC176,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC176,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F176="","",IF(OR(AA176="Cancelled",AC176="Cancelled"),"Cancelled",IF(OR(AC176="Completed / Handover",Y176<>"",Z176>=100),"Completed — on track",IF(O176="Not awarded",IF(U176="",IF(X176="","No planned date",IF(TODAY()>X176,"Behind — past planned date",IF(X176-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U176,"Behind — award date passed",IF(U176-TODAY()<=30,"At risk — close to off track","On track"))),IF(X176="","No planned date",IF(AND(TODAY()>X176,OR(Z176="",Z176<100)),"Behind — past end date",IF(AND(T176<>"",X176<>"",Z176<>"",(Z176<100),((TODAY()-T176)/MAX(X176-T176,1)*100)-Z176>15),"Behind — progress lag",IF(AND(X176-TODAY()<=30,X176-TODAY()>=0,OR(Z176="",Z176<90)),"At risk — close to off track","On track")))))))) | IF(OR(F176="",AC176="Completed / Handover",AC176="Cancelled"),"",IF(O176="Not awarded",IF(U176<>"",U176-TODAY(),IF(X176="","",X176-TODAY())),IF(X176="","",X176-TODAY()))) | [14 empty] | IF(OR(F176="",AJ176=""),"",IF(COUNT(AI176:AI176)=0,"",AJ176-LOOKUP(2,1/(AI176:AI176<>""),AI176:AI176))) | IF(OR(F176="",AK176=""),"",IF(COUNT(AI176:AJ176)=0,"",AK176-LOOKUP(2,1/(AI176:AJ176<>""),AI176:AJ176))) | IF(OR(F176="",AL176=""),"",IF(COUNT(AI176:AK176)=0,"",AL176-LOOKUP(2,1/(AI176:AK176<>""),AI176:AK176))) | IF(OR(F176="",AM176=""),"",IF(COUNT(AI176:AL176)=0,"",AM176-LOOKUP(2,1/(AI176:AL176<>""),AI176:AL176))) | IF(OR(F176="",AN176=""),"",IF(COUNT(AI176:AM176)=0,"",AN176-LOOKUP(2,1/(AI176:AM176<>""),AI176:AM176))) | IF(OR(F176="",AO176=""),"",IF(COUNT(AI176:AN176)=0,"",AO176-LOOKUP(2,1/(AI176:AN176<>""),AI176:AN176))) | IF(OR(F176="",AP176=""),"",IF(COUNT(AI176:AO176)=0,"",AP176-LOOKUP(2,1/(AI176:AO176<>""),AI176:AO176))) | IF(OR(F176="",AQ176=""),"",IF(COUNT(AI176:AP176)=0,"",AQ176-LOOKUP(2,1/(AI176:AP176<>""),AI176:AP176))) | IF(OR(F176="",AR176=""),"",IF(COUNT(AI176:AQ176)=0,"",AR176-LOOKUP(2,1/(AI176:AQ176<>""),AI176:AQ176))) | IF(OR(F176="",AS176=""),"",IF(COUNT(AI176:AR176)=0,"",AS176-LOOKUP(2,1/(AI176:AR176<>""),AI176:AR176))) | IF(OR(F176="",AT176=""),"",IF(COUNT(AI176:AS176)=0,"",AT176-LOOKUP(2,1/(AI176:AS176<>""),AI176:AS176))) | IF(OR(F176="",AU176=""),"",IF(COUNT(AI176:AT176)=0,"",AU176-LOOKUP(2,1/(AI176:AT176<>""),AI176:AT176))) | IF(OR(F176="",AV176=""),"",IF(COUNT(AI176:AU176)=0,"",AV176-LOOKUP(2,1/(AI176:AU176<>""),AI176:AU176))) | IF(J176="","All_Provinces",IFERROR(VLOOKUP(J176,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K176="","All_Districts",IFERROR(VLOOKUP(K176,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F177="","",ROW()-3) | [18 empty] | IF(AQ177="","",AQ177) |  |  |  | IF(W177<>"",W177,IF(OR(T177="",V177=""),"",EDATE(T177,V177))) |  |  |  |  | IF(F177="","",IF(COUNT(AI177:AV177)=0,IF(AA177="","Not started",AA177),SUBSTITUTE(LOOKUP(2,1/(AI177:AV177<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F177="",COUNT(AI177:AV177)=0),"",TODAY()-LOOKUP(2,1/(AI177:AV177<>""),AI177:AV177)) | IF(OR(F177="",COUNT(AI177:AV177)<2),"",LOOKUP(2,1/(AI177:AV177<>""),AI177:AV177)-MIN(AI177:AV177)) | IF(OR(AD177="",AC177="Not started",AC177=""),"",IFERROR(AD177-IF(VLOOKUP(AC177,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC177,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F177="","",IF(OR(AA177="Cancelled",AC177="Cancelled"),"Cancelled",IF(OR(AC177="Completed / Handover",Y177<>"",Z177>=100),"Completed — on track",IF(O177="Not awarded",IF(U177="",IF(X177="","No planned date",IF(TODAY()>X177,"Behind — past planned date",IF(X177-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U177,"Behind — award date passed",IF(U177-TODAY()<=30,"At risk — close to off track","On track"))),IF(X177="","No planned date",IF(AND(TODAY()>X177,OR(Z177="",Z177<100)),"Behind — past end date",IF(AND(T177<>"",X177<>"",Z177<>"",(Z177<100),((TODAY()-T177)/MAX(X177-T177,1)*100)-Z177>15),"Behind — progress lag",IF(AND(X177-TODAY()<=30,X177-TODAY()>=0,OR(Z177="",Z177<90)),"At risk — close to off track","On track")))))))) | IF(OR(F177="",AC177="Completed / Handover",AC177="Cancelled"),"",IF(O177="Not awarded",IF(U177<>"",U177-TODAY(),IF(X177="","",X177-TODAY())),IF(X177="","",X177-TODAY()))) | [14 empty] | IF(OR(F177="",AJ177=""),"",IF(COUNT(AI177:AI177)=0,"",AJ177-LOOKUP(2,1/(AI177:AI177<>""),AI177:AI177))) | IF(OR(F177="",AK177=""),"",IF(COUNT(AI177:AJ177)=0,"",AK177-LOOKUP(2,1/(AI177:AJ177<>""),AI177:AJ177))) | IF(OR(F177="",AL177=""),"",IF(COUNT(AI177:AK177)=0,"",AL177-LOOKUP(2,1/(AI177:AK177<>""),AI177:AK177))) | IF(OR(F177="",AM177=""),"",IF(COUNT(AI177:AL177)=0,"",AM177-LOOKUP(2,1/(AI177:AL177<>""),AI177:AL177))) | IF(OR(F177="",AN177=""),"",IF(COUNT(AI177:AM177)=0,"",AN177-LOOKUP(2,1/(AI177:AM177<>""),AI177:AM177))) | IF(OR(F177="",AO177=""),"",IF(COUNT(AI177:AN177)=0,"",AO177-LOOKUP(2,1/(AI177:AN177<>""),AI177:AN177))) | IF(OR(F177="",AP177=""),"",IF(COUNT(AI177:AO177)=0,"",AP177-LOOKUP(2,1/(AI177:AO177<>""),AI177:AO177))) | IF(OR(F177="",AQ177=""),"",IF(COUNT(AI177:AP177)=0,"",AQ177-LOOKUP(2,1/(AI177:AP177<>""),AI177:AP177))) | IF(OR(F177="",AR177=""),"",IF(COUNT(AI177:AQ177)=0,"",AR177-LOOKUP(2,1/(AI177:AQ177<>""),AI177:AQ177))) | IF(OR(F177="",AS177=""),"",IF(COUNT(AI177:AR177)=0,"",AS177-LOOKUP(2,1/(AI177:AR177<>""),AI177:AR177))) | IF(OR(F177="",AT177=""),"",IF(COUNT(AI177:AS177)=0,"",AT177-LOOKUP(2,1/(AI177:AS177<>""),AI177:AS177))) | IF(OR(F177="",AU177=""),"",IF(COUNT(AI177:AT177)=0,"",AU177-LOOKUP(2,1/(AI177:AT177<>""),AI177:AT177))) | IF(OR(F177="",AV177=""),"",IF(COUNT(AI177:AU177)=0,"",AV177-LOOKUP(2,1/(AI177:AU177<>""),AI177:AU177))) | IF(J177="","All_Provinces",IFERROR(VLOOKUP(J177,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K177="","All_Districts",IFERROR(VLOOKUP(K177,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F178="","",ROW()-3) | [18 empty] | IF(AQ178="","",AQ178) |  |  |  | IF(W178<>"",W178,IF(OR(T178="",V178=""),"",EDATE(T178,V178))) |  |  |  |  | IF(F178="","",IF(COUNT(AI178:AV178)=0,IF(AA178="","Not started",AA178),SUBSTITUTE(LOOKUP(2,1/(AI178:AV178<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F178="",COUNT(AI178:AV178)=0),"",TODAY()-LOOKUP(2,1/(AI178:AV178<>""),AI178:AV178)) | IF(OR(F178="",COUNT(AI178:AV178)<2),"",LOOKUP(2,1/(AI178:AV178<>""),AI178:AV178)-MIN(AI178:AV178)) | IF(OR(AD178="",AC178="Not started",AC178=""),"",IFERROR(AD178-IF(VLOOKUP(AC178,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC178,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F178="","",IF(OR(AA178="Cancelled",AC178="Cancelled"),"Cancelled",IF(OR(AC178="Completed / Handover",Y178<>"",Z178>=100),"Completed — on track",IF(O178="Not awarded",IF(U178="",IF(X178="","No planned date",IF(TODAY()>X178,"Behind — past planned date",IF(X178-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U178,"Behind — award date passed",IF(U178-TODAY()<=30,"At risk — close to off track","On track"))),IF(X178="","No planned date",IF(AND(TODAY()>X178,OR(Z178="",Z178<100)),"Behind — past end date",IF(AND(T178<>"",X178<>"",Z178<>"",(Z178<100),((TODAY()-T178)/MAX(X178-T178,1)*100)-Z178>15),"Behind — progress lag",IF(AND(X178-TODAY()<=30,X178-TODAY()>=0,OR(Z178="",Z178<90)),"At risk — close to off track","On track")))))))) | IF(OR(F178="",AC178="Completed / Handover",AC178="Cancelled"),"",IF(O178="Not awarded",IF(U178<>"",U178-TODAY(),IF(X178="","",X178-TODAY())),IF(X178="","",X178-TODAY()))) | [14 empty] | IF(OR(F178="",AJ178=""),"",IF(COUNT(AI178:AI178)=0,"",AJ178-LOOKUP(2,1/(AI178:AI178<>""),AI178:AI178))) | IF(OR(F178="",AK178=""),"",IF(COUNT(AI178:AJ178)=0,"",AK178-LOOKUP(2,1/(AI178:AJ178<>""),AI178:AJ178))) | IF(OR(F178="",AL178=""),"",IF(COUNT(AI178:AK178)=0,"",AL178-LOOKUP(2,1/(AI178:AK178<>""),AI178:AK178))) | IF(OR(F178="",AM178=""),"",IF(COUNT(AI178:AL178)=0,"",AM178-LOOKUP(2,1/(AI178:AL178<>""),AI178:AL178))) | IF(OR(F178="",AN178=""),"",IF(COUNT(AI178:AM178)=0,"",AN178-LOOKUP(2,1/(AI178:AM178<>""),AI178:AM178))) | IF(OR(F178="",AO178=""),"",IF(COUNT(AI178:AN178)=0,"",AO178-LOOKUP(2,1/(AI178:AN178<>""),AI178:AN178))) | IF(OR(F178="",AP178=""),"",IF(COUNT(AI178:AO178)=0,"",AP178-LOOKUP(2,1/(AI178:AO178<>""),AI178:AO178))) | IF(OR(F178="",AQ178=""),"",IF(COUNT(AI178:AP178)=0,"",AQ178-LOOKUP(2,1/(AI178:AP178<>""),AI178:AP178))) | IF(OR(F178="",AR178=""),"",IF(COUNT(AI178:AQ178)=0,"",AR178-LOOKUP(2,1/(AI178:AQ178<>""),AI178:AQ178))) | IF(OR(F178="",AS178=""),"",IF(COUNT(AI178:AR178)=0,"",AS178-LOOKUP(2,1/(AI178:AR178<>""),AI178:AR178))) | IF(OR(F178="",AT178=""),"",IF(COUNT(AI178:AS178)=0,"",AT178-LOOKUP(2,1/(AI178:AS178<>""),AI178:AS178))) | IF(OR(F178="",AU178=""),"",IF(COUNT(AI178:AT178)=0,"",AU178-LOOKUP(2,1/(AI178:AT178<>""),AI178:AT178))) | IF(OR(F178="",AV178=""),"",IF(COUNT(AI178:AU178)=0,"",AV178-LOOKUP(2,1/(AI178:AU178<>""),AI178:AU178))) | IF(J178="","All_Provinces",IFERROR(VLOOKUP(J178,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K178="","All_Districts",IFERROR(VLOOKUP(K178,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F179="","",ROW()-3) | [18 empty] | IF(AQ179="","",AQ179) |  |  |  | IF(W179<>"",W179,IF(OR(T179="",V179=""),"",EDATE(T179,V179))) |  |  |  |  | IF(F179="","",IF(COUNT(AI179:AV179)=0,IF(AA179="","Not started",AA179),SUBSTITUTE(LOOKUP(2,1/(AI179:AV179<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F179="",COUNT(AI179:AV179)=0),"",TODAY()-LOOKUP(2,1/(AI179:AV179<>""),AI179:AV179)) | IF(OR(F179="",COUNT(AI179:AV179)<2),"",LOOKUP(2,1/(AI179:AV179<>""),AI179:AV179)-MIN(AI179:AV179)) | IF(OR(AD179="",AC179="Not started",AC179=""),"",IFERROR(AD179-IF(VLOOKUP(AC179,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC179,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F179="","",IF(OR(AA179="Cancelled",AC179="Cancelled"),"Cancelled",IF(OR(AC179="Completed / Handover",Y179<>"",Z179>=100),"Completed — on track",IF(O179="Not awarded",IF(U179="",IF(X179="","No planned date",IF(TODAY()>X179,"Behind — past planned date",IF(X179-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U179,"Behind — award date passed",IF(U179-TODAY()<=30,"At risk — close to off track","On track"))),IF(X179="","No planned date",IF(AND(TODAY()>X179,OR(Z179="",Z179<100)),"Behind — past end date",IF(AND(T179<>"",X179<>"",Z179<>"",(Z179<100),((TODAY()-T179)/MAX(X179-T179,1)*100)-Z179>15),"Behind — progress lag",IF(AND(X179-TODAY()<=30,X179-TODAY()>=0,OR(Z179="",Z179<90)),"At risk — close to off track","On track")))))))) | IF(OR(F179="",AC179="Completed / Handover",AC179="Cancelled"),"",IF(O179="Not awarded",IF(U179<>"",U179-TODAY(),IF(X179="","",X179-TODAY())),IF(X179="","",X179-TODAY()))) | [14 empty] | IF(OR(F179="",AJ179=""),"",IF(COUNT(AI179:AI179)=0,"",AJ179-LOOKUP(2,1/(AI179:AI179<>""),AI179:AI179))) | IF(OR(F179="",AK179=""),"",IF(COUNT(AI179:AJ179)=0,"",AK179-LOOKUP(2,1/(AI179:AJ179<>""),AI179:AJ179))) | IF(OR(F179="",AL179=""),"",IF(COUNT(AI179:AK179)=0,"",AL179-LOOKUP(2,1/(AI179:AK179<>""),AI179:AK179))) | IF(OR(F179="",AM179=""),"",IF(COUNT(AI179:AL179)=0,"",AM179-LOOKUP(2,1/(AI179:AL179<>""),AI179:AL179))) | IF(OR(F179="",AN179=""),"",IF(COUNT(AI179:AM179)=0,"",AN179-LOOKUP(2,1/(AI179:AM179<>""),AI179:AM179))) | IF(OR(F179="",AO179=""),"",IF(COUNT(AI179:AN179)=0,"",AO179-LOOKUP(2,1/(AI179:AN179<>""),AI179:AN179))) | IF(OR(F179="",AP179=""),"",IF(COUNT(AI179:AO179)=0,"",AP179-LOOKUP(2,1/(AI179:AO179<>""),AI179:AO179))) | IF(OR(F179="",AQ179=""),"",IF(COUNT(AI179:AP179)=0,"",AQ179-LOOKUP(2,1/(AI179:AP179<>""),AI179:AP179))) | IF(OR(F179="",AR179=""),"",IF(COUNT(AI179:AQ179)=0,"",AR179-LOOKUP(2,1/(AI179:AQ179<>""),AI179:AQ179))) | IF(OR(F179="",AS179=""),"",IF(COUNT(AI179:AR179)=0,"",AS179-LOOKUP(2,1/(AI179:AR179<>""),AI179:AR179))) | IF(OR(F179="",AT179=""),"",IF(COUNT(AI179:AS179)=0,"",AT179-LOOKUP(2,1/(AI179:AS179<>""),AI179:AS179))) | IF(OR(F179="",AU179=""),"",IF(COUNT(AI179:AT179)=0,"",AU179-LOOKUP(2,1/(AI179:AT179<>""),AI179:AT179))) | IF(OR(F179="",AV179=""),"",IF(COUNT(AI179:AU179)=0,"",AV179-LOOKUP(2,1/(AI179:AU179<>""),AI179:AU179))) | IF(J179="","All_Provinces",IFERROR(VLOOKUP(J179,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K179="","All_Districts",IFERROR(VLOOKUP(K179,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F180="","",ROW()-3) | [18 empty] | IF(AQ180="","",AQ180) |  |  |  | IF(W180<>"",W180,IF(OR(T180="",V180=""),"",EDATE(T180,V180))) |  |  |  |  | IF(F180="","",IF(COUNT(AI180:AV180)=0,IF(AA180="","Not started",AA180),SUBSTITUTE(LOOKUP(2,1/(AI180:AV180<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F180="",COUNT(AI180:AV180)=0),"",TODAY()-LOOKUP(2,1/(AI180:AV180<>""),AI180:AV180)) | IF(OR(F180="",COUNT(AI180:AV180)<2),"",LOOKUP(2,1/(AI180:AV180<>""),AI180:AV180)-MIN(AI180:AV180)) | IF(OR(AD180="",AC180="Not started",AC180=""),"",IFERROR(AD180-IF(VLOOKUP(AC180,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC180,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F180="","",IF(OR(AA180="Cancelled",AC180="Cancelled"),"Cancelled",IF(OR(AC180="Completed / Handover",Y180<>"",Z180>=100),"Completed — on track",IF(O180="Not awarded",IF(U180="",IF(X180="","No planned date",IF(TODAY()>X180,"Behind — past planned date",IF(X180-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U180,"Behind — award date passed",IF(U180-TODAY()<=30,"At risk — close to off track","On track"))),IF(X180="","No planned date",IF(AND(TODAY()>X180,OR(Z180="",Z180<100)),"Behind — past end date",IF(AND(T180<>"",X180<>"",Z180<>"",(Z180<100),((TODAY()-T180)/MAX(X180-T180,1)*100)-Z180>15),"Behind — progress lag",IF(AND(X180-TODAY()<=30,X180-TODAY()>=0,OR(Z180="",Z180<90)),"At risk — close to off track","On track")))))))) | IF(OR(F180="",AC180="Completed / Handover",AC180="Cancelled"),"",IF(O180="Not awarded",IF(U180<>"",U180-TODAY(),IF(X180="","",X180-TODAY())),IF(X180="","",X180-TODAY()))) | [14 empty] | IF(OR(F180="",AJ180=""),"",IF(COUNT(AI180:AI180)=0,"",AJ180-LOOKUP(2,1/(AI180:AI180<>""),AI180:AI180))) | IF(OR(F180="",AK180=""),"",IF(COUNT(AI180:AJ180)=0,"",AK180-LOOKUP(2,1/(AI180:AJ180<>""),AI180:AJ180))) | IF(OR(F180="",AL180=""),"",IF(COUNT(AI180:AK180)=0,"",AL180-LOOKUP(2,1/(AI180:AK180<>""),AI180:AK180))) | IF(OR(F180="",AM180=""),"",IF(COUNT(AI180:AL180)=0,"",AM180-LOOKUP(2,1/(AI180:AL180<>""),AI180:AL180))) | IF(OR(F180="",AN180=""),"",IF(COUNT(AI180:AM180)=0,"",AN180-LOOKUP(2,1/(AI180:AM180<>""),AI180:AM180))) | IF(OR(F180="",AO180=""),"",IF(COUNT(AI180:AN180)=0,"",AO180-LOOKUP(2,1/(AI180:AN180<>""),AI180:AN180))) | IF(OR(F180="",AP180=""),"",IF(COUNT(AI180:AO180)=0,"",AP180-LOOKUP(2,1/(AI180:AO180<>""),AI180:AO180))) | IF(OR(F180="",AQ180=""),"",IF(COUNT(AI180:AP180)=0,"",AQ180-LOOKUP(2,1/(AI180:AP180<>""),AI180:AP180))) | IF(OR(F180="",AR180=""),"",IF(COUNT(AI180:AQ180)=0,"",AR180-LOOKUP(2,1/(AI180:AQ180<>""),AI180:AQ180))) | IF(OR(F180="",AS180=""),"",IF(COUNT(AI180:AR180)=0,"",AS180-LOOKUP(2,1/(AI180:AR180<>""),AI180:AR180))) | IF(OR(F180="",AT180=""),"",IF(COUNT(AI180:AS180)=0,"",AT180-LOOKUP(2,1/(AI180:AS180<>""),AI180:AS180))) | IF(OR(F180="",AU180=""),"",IF(COUNT(AI180:AT180)=0,"",AU180-LOOKUP(2,1/(AI180:AT180<>""),AI180:AT180))) | IF(OR(F180="",AV180=""),"",IF(COUNT(AI180:AU180)=0,"",AV180-LOOKUP(2,1/(AI180:AU180<>""),AI180:AU180))) | IF(J180="","All_Provinces",IFERROR(VLOOKUP(J180,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K180="","All_Districts",IFERROR(VLOOKUP(K180,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F181="","",ROW()-3) | [18 empty] | IF(AQ181="","",AQ181) |  |  |  | IF(W181<>"",W181,IF(OR(T181="",V181=""),"",EDATE(T181,V181))) |  |  |  |  | IF(F181="","",IF(COUNT(AI181:AV181)=0,IF(AA181="","Not started",AA181),SUBSTITUTE(LOOKUP(2,1/(AI181:AV181<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F181="",COUNT(AI181:AV181)=0),"",TODAY()-LOOKUP(2,1/(AI181:AV181<>""),AI181:AV181)) | IF(OR(F181="",COUNT(AI181:AV181)<2),"",LOOKUP(2,1/(AI181:AV181<>""),AI181:AV181)-MIN(AI181:AV181)) | IF(OR(AD181="",AC181="Not started",AC181=""),"",IFERROR(AD181-IF(VLOOKUP(AC181,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC181,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F181="","",IF(OR(AA181="Cancelled",AC181="Cancelled"),"Cancelled",IF(OR(AC181="Completed / Handover",Y181<>"",Z181>=100),"Completed — on track",IF(O181="Not awarded",IF(U181="",IF(X181="","No planned date",IF(TODAY()>X181,"Behind — past planned date",IF(X181-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U181,"Behind — award date passed",IF(U181-TODAY()<=30,"At risk — close to off track","On track"))),IF(X181="","No planned date",IF(AND(TODAY()>X181,OR(Z181="",Z181<100)),"Behind — past end date",IF(AND(T181<>"",X181<>"",Z181<>"",(Z181<100),((TODAY()-T181)/MAX(X181-T181,1)*100)-Z181>15),"Behind — progress lag",IF(AND(X181-TODAY()<=30,X181-TODAY()>=0,OR(Z181="",Z181<90)),"At risk — close to off track","On track")))))))) | IF(OR(F181="",AC181="Completed / Handover",AC181="Cancelled"),"",IF(O181="Not awarded",IF(U181<>"",U181-TODAY(),IF(X181="","",X181-TODAY())),IF(X181="","",X181-TODAY()))) | [14 empty] | IF(OR(F181="",AJ181=""),"",IF(COUNT(AI181:AI181)=0,"",AJ181-LOOKUP(2,1/(AI181:AI181<>""),AI181:AI181))) | IF(OR(F181="",AK181=""),"",IF(COUNT(AI181:AJ181)=0,"",AK181-LOOKUP(2,1/(AI181:AJ181<>""),AI181:AJ181))) | IF(OR(F181="",AL181=""),"",IF(COUNT(AI181:AK181)=0,"",AL181-LOOKUP(2,1/(AI181:AK181<>""),AI181:AK181))) | IF(OR(F181="",AM181=""),"",IF(COUNT(AI181:AL181)=0,"",AM181-LOOKUP(2,1/(AI181:AL181<>""),AI181:AL181))) | IF(OR(F181="",AN181=""),"",IF(COUNT(AI181:AM181)=0,"",AN181-LOOKUP(2,1/(AI181:AM181<>""),AI181:AM181))) | IF(OR(F181="",AO181=""),"",IF(COUNT(AI181:AN181)=0,"",AO181-LOOKUP(2,1/(AI181:AN181<>""),AI181:AN181))) | IF(OR(F181="",AP181=""),"",IF(COUNT(AI181:AO181)=0,"",AP181-LOOKUP(2,1/(AI181:AO181<>""),AI181:AO181))) | IF(OR(F181="",AQ181=""),"",IF(COUNT(AI181:AP181)=0,"",AQ181-LOOKUP(2,1/(AI181:AP181<>""),AI181:AP181))) | IF(OR(F181="",AR181=""),"",IF(COUNT(AI181:AQ181)=0,"",AR181-LOOKUP(2,1/(AI181:AQ181<>""),AI181:AQ181))) | IF(OR(F181="",AS181=""),"",IF(COUNT(AI181:AR181)=0,"",AS181-LOOKUP(2,1/(AI181:AR181<>""),AI181:AR181))) | IF(OR(F181="",AT181=""),"",IF(COUNT(AI181:AS181)=0,"",AT181-LOOKUP(2,1/(AI181:AS181<>""),AI181:AS181))) | IF(OR(F181="",AU181=""),"",IF(COUNT(AI181:AT181)=0,"",AU181-LOOKUP(2,1/(AI181:AT181<>""),AI181:AT181))) | IF(OR(F181="",AV181=""),"",IF(COUNT(AI181:AU181)=0,"",AV181-LOOKUP(2,1/(AI181:AU181<>""),AI181:AU181))) | IF(J181="","All_Provinces",IFERROR(VLOOKUP(J181,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K181="","All_Districts",IFERROR(VLOOKUP(K181,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F182="","",ROW()-3) | [18 empty] | IF(AQ182="","",AQ182) |  |  |  | IF(W182<>"",W182,IF(OR(T182="",V182=""),"",EDATE(T182,V182))) |  |  |  |  | IF(F182="","",IF(COUNT(AI182:AV182)=0,IF(AA182="","Not started",AA182),SUBSTITUTE(LOOKUP(2,1/(AI182:AV182<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F182="",COUNT(AI182:AV182)=0),"",TODAY()-LOOKUP(2,1/(AI182:AV182<>""),AI182:AV182)) | IF(OR(F182="",COUNT(AI182:AV182)<2),"",LOOKUP(2,1/(AI182:AV182<>""),AI182:AV182)-MIN(AI182:AV182)) | IF(OR(AD182="",AC182="Not started",AC182=""),"",IFERROR(AD182-IF(VLOOKUP(AC182,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC182,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F182="","",IF(OR(AA182="Cancelled",AC182="Cancelled"),"Cancelled",IF(OR(AC182="Completed / Handover",Y182<>"",Z182>=100),"Completed — on track",IF(O182="Not awarded",IF(U182="",IF(X182="","No planned date",IF(TODAY()>X182,"Behind — past planned date",IF(X182-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U182,"Behind — award date passed",IF(U182-TODAY()<=30,"At risk — close to off track","On track"))),IF(X182="","No planned date",IF(AND(TODAY()>X182,OR(Z182="",Z182<100)),"Behind — past end date",IF(AND(T182<>"",X182<>"",Z182<>"",(Z182<100),((TODAY()-T182)/MAX(X182-T182,1)*100)-Z182>15),"Behind — progress lag",IF(AND(X182-TODAY()<=30,X182-TODAY()>=0,OR(Z182="",Z182<90)),"At risk — close to off track","On track")))))))) | IF(OR(F182="",AC182="Completed / Handover",AC182="Cancelled"),"",IF(O182="Not awarded",IF(U182<>"",U182-TODAY(),IF(X182="","",X182-TODAY())),IF(X182="","",X182-TODAY()))) | [14 empty] | IF(OR(F182="",AJ182=""),"",IF(COUNT(AI182:AI182)=0,"",AJ182-LOOKUP(2,1/(AI182:AI182<>""),AI182:AI182))) | IF(OR(F182="",AK182=""),"",IF(COUNT(AI182:AJ182)=0,"",AK182-LOOKUP(2,1/(AI182:AJ182<>""),AI182:AJ182))) | IF(OR(F182="",AL182=""),"",IF(COUNT(AI182:AK182)=0,"",AL182-LOOKUP(2,1/(AI182:AK182<>""),AI182:AK182))) | IF(OR(F182="",AM182=""),"",IF(COUNT(AI182:AL182)=0,"",AM182-LOOKUP(2,1/(AI182:AL182<>""),AI182:AL182))) | IF(OR(F182="",AN182=""),"",IF(COUNT(AI182:AM182)=0,"",AN182-LOOKUP(2,1/(AI182:AM182<>""),AI182:AM182))) | IF(OR(F182="",AO182=""),"",IF(COUNT(AI182:AN182)=0,"",AO182-LOOKUP(2,1/(AI182:AN182<>""),AI182:AN182))) | IF(OR(F182="",AP182=""),"",IF(COUNT(AI182:AO182)=0,"",AP182-LOOKUP(2,1/(AI182:AO182<>""),AI182:AO182))) | IF(OR(F182="",AQ182=""),"",IF(COUNT(AI182:AP182)=0,"",AQ182-LOOKUP(2,1/(AI182:AP182<>""),AI182:AP182))) | IF(OR(F182="",AR182=""),"",IF(COUNT(AI182:AQ182)=0,"",AR182-LOOKUP(2,1/(AI182:AQ182<>""),AI182:AQ182))) | IF(OR(F182="",AS182=""),"",IF(COUNT(AI182:AR182)=0,"",AS182-LOOKUP(2,1/(AI182:AR182<>""),AI182:AR182))) | IF(OR(F182="",AT182=""),"",IF(COUNT(AI182:AS182)=0,"",AT182-LOOKUP(2,1/(AI182:AS182<>""),AI182:AS182))) | IF(OR(F182="",AU182=""),"",IF(COUNT(AI182:AT182)=0,"",AU182-LOOKUP(2,1/(AI182:AT182<>""),AI182:AT182))) | IF(OR(F182="",AV182=""),"",IF(COUNT(AI182:AU182)=0,"",AV182-LOOKUP(2,1/(AI182:AU182<>""),AI182:AU182))) | IF(J182="","All_Provinces",IFERROR(VLOOKUP(J182,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K182="","All_Districts",IFERROR(VLOOKUP(K182,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F183="","",ROW()-3) | [18 empty] | IF(AQ183="","",AQ183) |  |  |  | IF(W183<>"",W183,IF(OR(T183="",V183=""),"",EDATE(T183,V183))) |  |  |  |  | IF(F183="","",IF(COUNT(AI183:AV183)=0,IF(AA183="","Not started",AA183),SUBSTITUTE(LOOKUP(2,1/(AI183:AV183<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F183="",COUNT(AI183:AV183)=0),"",TODAY()-LOOKUP(2,1/(AI183:AV183<>""),AI183:AV183)) | IF(OR(F183="",COUNT(AI183:AV183)<2),"",LOOKUP(2,1/(AI183:AV183<>""),AI183:AV183)-MIN(AI183:AV183)) | IF(OR(AD183="",AC183="Not started",AC183=""),"",IFERROR(AD183-IF(VLOOKUP(AC183,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC183,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F183="","",IF(OR(AA183="Cancelled",AC183="Cancelled"),"Cancelled",IF(OR(AC183="Completed / Handover",Y183<>"",Z183>=100),"Completed — on track",IF(O183="Not awarded",IF(U183="",IF(X183="","No planned date",IF(TODAY()>X183,"Behind — past planned date",IF(X183-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U183,"Behind — award date passed",IF(U183-TODAY()<=30,"At risk — close to off track","On track"))),IF(X183="","No planned date",IF(AND(TODAY()>X183,OR(Z183="",Z183<100)),"Behind — past end date",IF(AND(T183<>"",X183<>"",Z183<>"",(Z183<100),((TODAY()-T183)/MAX(X183-T183,1)*100)-Z183>15),"Behind — progress lag",IF(AND(X183-TODAY()<=30,X183-TODAY()>=0,OR(Z183="",Z183<90)),"At risk — close to off track","On track")))))))) | IF(OR(F183="",AC183="Completed / Handover",AC183="Cancelled"),"",IF(O183="Not awarded",IF(U183<>"",U183-TODAY(),IF(X183="","",X183-TODAY())),IF(X183="","",X183-TODAY()))) | [14 empty] | IF(OR(F183="",AJ183=""),"",IF(COUNT(AI183:AI183)=0,"",AJ183-LOOKUP(2,1/(AI183:AI183<>""),AI183:AI183))) | IF(OR(F183="",AK183=""),"",IF(COUNT(AI183:AJ183)=0,"",AK183-LOOKUP(2,1/(AI183:AJ183<>""),AI183:AJ183))) | IF(OR(F183="",AL183=""),"",IF(COUNT(AI183:AK183)=0,"",AL183-LOOKUP(2,1/(AI183:AK183<>""),AI183:AK183))) | IF(OR(F183="",AM183=""),"",IF(COUNT(AI183:AL183)=0,"",AM183-LOOKUP(2,1/(AI183:AL183<>""),AI183:AL183))) | IF(OR(F183="",AN183=""),"",IF(COUNT(AI183:AM183)=0,"",AN183-LOOKUP(2,1/(AI183:AM183<>""),AI183:AM183))) | IF(OR(F183="",AO183=""),"",IF(COUNT(AI183:AN183)=0,"",AO183-LOOKUP(2,1/(AI183:AN183<>""),AI183:AN183))) | IF(OR(F183="",AP183=""),"",IF(COUNT(AI183:AO183)=0,"",AP183-LOOKUP(2,1/(AI183:AO183<>""),AI183:AO183))) | IF(OR(F183="",AQ183=""),"",IF(COUNT(AI183:AP183)=0,"",AQ183-LOOKUP(2,1/(AI183:AP183<>""),AI183:AP183))) | IF(OR(F183="",AR183=""),"",IF(COUNT(AI183:AQ183)=0,"",AR183-LOOKUP(2,1/(AI183:AQ183<>""),AI183:AQ183))) | IF(OR(F183="",AS183=""),"",IF(COUNT(AI183:AR183)=0,"",AS183-LOOKUP(2,1/(AI183:AR183<>""),AI183:AR183))) | IF(OR(F183="",AT183=""),"",IF(COUNT(AI183:AS183)=0,"",AT183-LOOKUP(2,1/(AI183:AS183<>""),AI183:AS183))) | IF(OR(F183="",AU183=""),"",IF(COUNT(AI183:AT183)=0,"",AU183-LOOKUP(2,1/(AI183:AT183<>""),AI183:AT183))) | IF(OR(F183="",AV183=""),"",IF(COUNT(AI183:AU183)=0,"",AV183-LOOKUP(2,1/(AI183:AU183<>""),AI183:AU183))) | IF(J183="","All_Provinces",IFERROR(VLOOKUP(J183,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K183="","All_Districts",IFERROR(VLOOKUP(K183,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F184="","",ROW()-3) | [18 empty] | IF(AQ184="","",AQ184) |  |  |  | IF(W184<>"",W184,IF(OR(T184="",V184=""),"",EDATE(T184,V184))) |  |  |  |  | IF(F184="","",IF(COUNT(AI184:AV184)=0,IF(AA184="","Not started",AA184),SUBSTITUTE(LOOKUP(2,1/(AI184:AV184<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F184="",COUNT(AI184:AV184)=0),"",TODAY()-LOOKUP(2,1/(AI184:AV184<>""),AI184:AV184)) | IF(OR(F184="",COUNT(AI184:AV184)<2),"",LOOKUP(2,1/(AI184:AV184<>""),AI184:AV184)-MIN(AI184:AV184)) | IF(OR(AD184="",AC184="Not started",AC184=""),"",IFERROR(AD184-IF(VLOOKUP(AC184,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC184,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F184="","",IF(OR(AA184="Cancelled",AC184="Cancelled"),"Cancelled",IF(OR(AC184="Completed / Handover",Y184<>"",Z184>=100),"Completed — on track",IF(O184="Not awarded",IF(U184="",IF(X184="","No planned date",IF(TODAY()>X184,"Behind — past planned date",IF(X184-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U184,"Behind — award date passed",IF(U184-TODAY()<=30,"At risk — close to off track","On track"))),IF(X184="","No planned date",IF(AND(TODAY()>X184,OR(Z184="",Z184<100)),"Behind — past end date",IF(AND(T184<>"",X184<>"",Z184<>"",(Z184<100),((TODAY()-T184)/MAX(X184-T184,1)*100)-Z184>15),"Behind — progress lag",IF(AND(X184-TODAY()<=30,X184-TODAY()>=0,OR(Z184="",Z184<90)),"At risk — close to off track","On track")))))))) | IF(OR(F184="",AC184="Completed / Handover",AC184="Cancelled"),"",IF(O184="Not awarded",IF(U184<>"",U184-TODAY(),IF(X184="","",X184-TODAY())),IF(X184="","",X184-TODAY()))) | [14 empty] | IF(OR(F184="",AJ184=""),"",IF(COUNT(AI184:AI184)=0,"",AJ184-LOOKUP(2,1/(AI184:AI184<>""),AI184:AI184))) | IF(OR(F184="",AK184=""),"",IF(COUNT(AI184:AJ184)=0,"",AK184-LOOKUP(2,1/(AI184:AJ184<>""),AI184:AJ184))) | IF(OR(F184="",AL184=""),"",IF(COUNT(AI184:AK184)=0,"",AL184-LOOKUP(2,1/(AI184:AK184<>""),AI184:AK184))) | IF(OR(F184="",AM184=""),"",IF(COUNT(AI184:AL184)=0,"",AM184-LOOKUP(2,1/(AI184:AL184<>""),AI184:AL184))) | IF(OR(F184="",AN184=""),"",IF(COUNT(AI184:AM184)=0,"",AN184-LOOKUP(2,1/(AI184:AM184<>""),AI184:AM184))) | IF(OR(F184="",AO184=""),"",IF(COUNT(AI184:AN184)=0,"",AO184-LOOKUP(2,1/(AI184:AN184<>""),AI184:AN184))) | IF(OR(F184="",AP184=""),"",IF(COUNT(AI184:AO184)=0,"",AP184-LOOKUP(2,1/(AI184:AO184<>""),AI184:AO184))) | IF(OR(F184="",AQ184=""),"",IF(COUNT(AI184:AP184)=0,"",AQ184-LOOKUP(2,1/(AI184:AP184<>""),AI184:AP184))) | IF(OR(F184="",AR184=""),"",IF(COUNT(AI184:AQ184)=0,"",AR184-LOOKUP(2,1/(AI184:AQ184<>""),AI184:AQ184))) | IF(OR(F184="",AS184=""),"",IF(COUNT(AI184:AR184)=0,"",AS184-LOOKUP(2,1/(AI184:AR184<>""),AI184:AR184))) | IF(OR(F184="",AT184=""),"",IF(COUNT(AI184:AS184)=0,"",AT184-LOOKUP(2,1/(AI184:AS184<>""),AI184:AS184))) | IF(OR(F184="",AU184=""),"",IF(COUNT(AI184:AT184)=0,"",AU184-LOOKUP(2,1/(AI184:AT184<>""),AI184:AT184))) | IF(OR(F184="",AV184=""),"",IF(COUNT(AI184:AU184)=0,"",AV184-LOOKUP(2,1/(AI184:AU184<>""),AI184:AU184))) | IF(J184="","All_Provinces",IFERROR(VLOOKUP(J184,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K184="","All_Districts",IFERROR(VLOOKUP(K184,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F185="","",ROW()-3) | [18 empty] | IF(AQ185="","",AQ185) |  |  |  | IF(W185<>"",W185,IF(OR(T185="",V185=""),"",EDATE(T185,V185))) |  |  |  |  | IF(F185="","",IF(COUNT(AI185:AV185)=0,IF(AA185="","Not started",AA185),SUBSTITUTE(LOOKUP(2,1/(AI185:AV185<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F185="",COUNT(AI185:AV185)=0),"",TODAY()-LOOKUP(2,1/(AI185:AV185<>""),AI185:AV185)) | IF(OR(F185="",COUNT(AI185:AV185)<2),"",LOOKUP(2,1/(AI185:AV185<>""),AI185:AV185)-MIN(AI185:AV185)) | IF(OR(AD185="",AC185="Not started",AC185=""),"",IFERROR(AD185-IF(VLOOKUP(AC185,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC185,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F185="","",IF(OR(AA185="Cancelled",AC185="Cancelled"),"Cancelled",IF(OR(AC185="Completed / Handover",Y185<>"",Z185>=100),"Completed — on track",IF(O185="Not awarded",IF(U185="",IF(X185="","No planned date",IF(TODAY()>X185,"Behind — past planned date",IF(X185-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U185,"Behind — award date passed",IF(U185-TODAY()<=30,"At risk — close to off track","On track"))),IF(X185="","No planned date",IF(AND(TODAY()>X185,OR(Z185="",Z185<100)),"Behind — past end date",IF(AND(T185<>"",X185<>"",Z185<>"",(Z185<100),((TODAY()-T185)/MAX(X185-T185,1)*100)-Z185>15),"Behind — progress lag",IF(AND(X185-TODAY()<=30,X185-TODAY()>=0,OR(Z185="",Z185<90)),"At risk — close to off track","On track")))))))) | IF(OR(F185="",AC185="Completed / Handover",AC185="Cancelled"),"",IF(O185="Not awarded",IF(U185<>"",U185-TODAY(),IF(X185="","",X185-TODAY())),IF(X185="","",X185-TODAY()))) | [14 empty] | IF(OR(F185="",AJ185=""),"",IF(COUNT(AI185:AI185)=0,"",AJ185-LOOKUP(2,1/(AI185:AI185<>""),AI185:AI185))) | IF(OR(F185="",AK185=""),"",IF(COUNT(AI185:AJ185)=0,"",AK185-LOOKUP(2,1/(AI185:AJ185<>""),AI185:AJ185))) | IF(OR(F185="",AL185=""),"",IF(COUNT(AI185:AK185)=0,"",AL185-LOOKUP(2,1/(AI185:AK185<>""),AI185:AK185))) | IF(OR(F185="",AM185=""),"",IF(COUNT(AI185:AL185)=0,"",AM185-LOOKUP(2,1/(AI185:AL185<>""),AI185:AL185))) | IF(OR(F185="",AN185=""),"",IF(COUNT(AI185:AM185)=0,"",AN185-LOOKUP(2,1/(AI185:AM185<>""),AI185:AM185))) | IF(OR(F185="",AO185=""),"",IF(COUNT(AI185:AN185)=0,"",AO185-LOOKUP(2,1/(AI185:AN185<>""),AI185:AN185))) | IF(OR(F185="",AP185=""),"",IF(COUNT(AI185:AO185)=0,"",AP185-LOOKUP(2,1/(AI185:AO185<>""),AI185:AO185))) | IF(OR(F185="",AQ185=""),"",IF(COUNT(AI185:AP185)=0,"",AQ185-LOOKUP(2,1/(AI185:AP185<>""),AI185:AP185))) | IF(OR(F185="",AR185=""),"",IF(COUNT(AI185:AQ185)=0,"",AR185-LOOKUP(2,1/(AI185:AQ185<>""),AI185:AQ185))) | IF(OR(F185="",AS185=""),"",IF(COUNT(AI185:AR185)=0,"",AS185-LOOKUP(2,1/(AI185:AR185<>""),AI185:AR185))) | IF(OR(F185="",AT185=""),"",IF(COUNT(AI185:AS185)=0,"",AT185-LOOKUP(2,1/(AI185:AS185<>""),AI185:AS185))) | IF(OR(F185="",AU185=""),"",IF(COUNT(AI185:AT185)=0,"",AU185-LOOKUP(2,1/(AI185:AT185<>""),AI185:AT185))) | IF(OR(F185="",AV185=""),"",IF(COUNT(AI185:AU185)=0,"",AV185-LOOKUP(2,1/(AI185:AU185<>""),AI185:AU185))) | IF(J185="","All_Provinces",IFERROR(VLOOKUP(J185,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K185="","All_Districts",IFERROR(VLOOKUP(K185,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F186="","",ROW()-3) | [18 empty] | IF(AQ186="","",AQ186) |  |  |  | IF(W186<>"",W186,IF(OR(T186="",V186=""),"",EDATE(T186,V186))) |  |  |  |  | IF(F186="","",IF(COUNT(AI186:AV186)=0,IF(AA186="","Not started",AA186),SUBSTITUTE(LOOKUP(2,1/(AI186:AV186<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F186="",COUNT(AI186:AV186)=0),"",TODAY()-LOOKUP(2,1/(AI186:AV186<>""),AI186:AV186)) | IF(OR(F186="",COUNT(AI186:AV186)<2),"",LOOKUP(2,1/(AI186:AV186<>""),AI186:AV186)-MIN(AI186:AV186)) | IF(OR(AD186="",AC186="Not started",AC186=""),"",IFERROR(AD186-IF(VLOOKUP(AC186,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC186,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F186="","",IF(OR(AA186="Cancelled",AC186="Cancelled"),"Cancelled",IF(OR(AC186="Completed / Handover",Y186<>"",Z186>=100),"Completed — on track",IF(O186="Not awarded",IF(U186="",IF(X186="","No planned date",IF(TODAY()>X186,"Behind — past planned date",IF(X186-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U186,"Behind — award date passed",IF(U186-TODAY()<=30,"At risk — close to off track","On track"))),IF(X186="","No planned date",IF(AND(TODAY()>X186,OR(Z186="",Z186<100)),"Behind — past end date",IF(AND(T186<>"",X186<>"",Z186<>"",(Z186<100),((TODAY()-T186)/MAX(X186-T186,1)*100)-Z186>15),"Behind — progress lag",IF(AND(X186-TODAY()<=30,X186-TODAY()>=0,OR(Z186="",Z186<90)),"At risk — close to off track","On track")))))))) | IF(OR(F186="",AC186="Completed / Handover",AC186="Cancelled"),"",IF(O186="Not awarded",IF(U186<>"",U186-TODAY(),IF(X186="","",X186-TODAY())),IF(X186="","",X186-TODAY()))) | [14 empty] | IF(OR(F186="",AJ186=""),"",IF(COUNT(AI186:AI186)=0,"",AJ186-LOOKUP(2,1/(AI186:AI186<>""),AI186:AI186))) | IF(OR(F186="",AK186=""),"",IF(COUNT(AI186:AJ186)=0,"",AK186-LOOKUP(2,1/(AI186:AJ186<>""),AI186:AJ186))) | IF(OR(F186="",AL186=""),"",IF(COUNT(AI186:AK186)=0,"",AL186-LOOKUP(2,1/(AI186:AK186<>""),AI186:AK186))) | IF(OR(F186="",AM186=""),"",IF(COUNT(AI186:AL186)=0,"",AM186-LOOKUP(2,1/(AI186:AL186<>""),AI186:AL186))) | IF(OR(F186="",AN186=""),"",IF(COUNT(AI186:AM186)=0,"",AN186-LOOKUP(2,1/(AI186:AM186<>""),AI186:AM186))) | IF(OR(F186="",AO186=""),"",IF(COUNT(AI186:AN186)=0,"",AO186-LOOKUP(2,1/(AI186:AN186<>""),AI186:AN186))) | IF(OR(F186="",AP186=""),"",IF(COUNT(AI186:AO186)=0,"",AP186-LOOKUP(2,1/(AI186:AO186<>""),AI186:AO186))) | IF(OR(F186="",AQ186=""),"",IF(COUNT(AI186:AP186)=0,"",AQ186-LOOKUP(2,1/(AI186:AP186<>""),AI186:AP186))) | IF(OR(F186="",AR186=""),"",IF(COUNT(AI186:AQ186)=0,"",AR186-LOOKUP(2,1/(AI186:AQ186<>""),AI186:AQ186))) | IF(OR(F186="",AS186=""),"",IF(COUNT(AI186:AR186)=0,"",AS186-LOOKUP(2,1/(AI186:AR186<>""),AI186:AR186))) | IF(OR(F186="",AT186=""),"",IF(COUNT(AI186:AS186)=0,"",AT186-LOOKUP(2,1/(AI186:AS186<>""),AI186:AS186))) | IF(OR(F186="",AU186=""),"",IF(COUNT(AI186:AT186)=0,"",AU186-LOOKUP(2,1/(AI186:AT186<>""),AI186:AT186))) | IF(OR(F186="",AV186=""),"",IF(COUNT(AI186:AU186)=0,"",AV186-LOOKUP(2,1/(AI186:AU186<>""),AI186:AU186))) | IF(J186="","All_Provinces",IFERROR(VLOOKUP(J186,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K186="","All_Districts",IFERROR(VLOOKUP(K186,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F187="","",ROW()-3) | [18 empty] | IF(AQ187="","",AQ187) |  |  |  | IF(W187<>"",W187,IF(OR(T187="",V187=""),"",EDATE(T187,V187))) |  |  |  |  | IF(F187="","",IF(COUNT(AI187:AV187)=0,IF(AA187="","Not started",AA187),SUBSTITUTE(LOOKUP(2,1/(AI187:AV187<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F187="",COUNT(AI187:AV187)=0),"",TODAY()-LOOKUP(2,1/(AI187:AV187<>""),AI187:AV187)) | IF(OR(F187="",COUNT(AI187:AV187)<2),"",LOOKUP(2,1/(AI187:AV187<>""),AI187:AV187)-MIN(AI187:AV187)) | IF(OR(AD187="",AC187="Not started",AC187=""),"",IFERROR(AD187-IF(VLOOKUP(AC187,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC187,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F187="","",IF(OR(AA187="Cancelled",AC187="Cancelled"),"Cancelled",IF(OR(AC187="Completed / Handover",Y187<>"",Z187>=100),"Completed — on track",IF(O187="Not awarded",IF(U187="",IF(X187="","No planned date",IF(TODAY()>X187,"Behind — past planned date",IF(X187-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U187,"Behind — award date passed",IF(U187-TODAY()<=30,"At risk — close to off track","On track"))),IF(X187="","No planned date",IF(AND(TODAY()>X187,OR(Z187="",Z187<100)),"Behind — past end date",IF(AND(T187<>"",X187<>"",Z187<>"",(Z187<100),((TODAY()-T187)/MAX(X187-T187,1)*100)-Z187>15),"Behind — progress lag",IF(AND(X187-TODAY()<=30,X187-TODAY()>=0,OR(Z187="",Z187<90)),"At risk — close to off track","On track")))))))) | IF(OR(F187="",AC187="Completed / Handover",AC187="Cancelled"),"",IF(O187="Not awarded",IF(U187<>"",U187-TODAY(),IF(X187="","",X187-TODAY())),IF(X187="","",X187-TODAY()))) | [14 empty] | IF(OR(F187="",AJ187=""),"",IF(COUNT(AI187:AI187)=0,"",AJ187-LOOKUP(2,1/(AI187:AI187<>""),AI187:AI187))) | IF(OR(F187="",AK187=""),"",IF(COUNT(AI187:AJ187)=0,"",AK187-LOOKUP(2,1/(AI187:AJ187<>""),AI187:AJ187))) | IF(OR(F187="",AL187=""),"",IF(COUNT(AI187:AK187)=0,"",AL187-LOOKUP(2,1/(AI187:AK187<>""),AI187:AK187))) | IF(OR(F187="",AM187=""),"",IF(COUNT(AI187:AL187)=0,"",AM187-LOOKUP(2,1/(AI187:AL187<>""),AI187:AL187))) | IF(OR(F187="",AN187=""),"",IF(COUNT(AI187:AM187)=0,"",AN187-LOOKUP(2,1/(AI187:AM187<>""),AI187:AM187))) | IF(OR(F187="",AO187=""),"",IF(COUNT(AI187:AN187)=0,"",AO187-LOOKUP(2,1/(AI187:AN187<>""),AI187:AN187))) | IF(OR(F187="",AP187=""),"",IF(COUNT(AI187:AO187)=0,"",AP187-LOOKUP(2,1/(AI187:AO187<>""),AI187:AO187))) | IF(OR(F187="",AQ187=""),"",IF(COUNT(AI187:AP187)=0,"",AQ187-LOOKUP(2,1/(AI187:AP187<>""),AI187:AP187))) | IF(OR(F187="",AR187=""),"",IF(COUNT(AI187:AQ187)=0,"",AR187-LOOKUP(2,1/(AI187:AQ187<>""),AI187:AQ187))) | IF(OR(F187="",AS187=""),"",IF(COUNT(AI187:AR187)=0,"",AS187-LOOKUP(2,1/(AI187:AR187<>""),AI187:AR187))) | IF(OR(F187="",AT187=""),"",IF(COUNT(AI187:AS187)=0,"",AT187-LOOKUP(2,1/(AI187:AS187<>""),AI187:AS187))) | IF(OR(F187="",AU187=""),"",IF(COUNT(AI187:AT187)=0,"",AU187-LOOKUP(2,1/(AI187:AT187<>""),AI187:AT187))) | IF(OR(F187="",AV187=""),"",IF(COUNT(AI187:AU187)=0,"",AV187-LOOKUP(2,1/(AI187:AU187<>""),AI187:AU187))) | IF(J187="","All_Provinces",IFERROR(VLOOKUP(J187,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K187="","All_Districts",IFERROR(VLOOKUP(K187,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F188="","",ROW()-3) | [18 empty] | IF(AQ188="","",AQ188) |  |  |  | IF(W188<>"",W188,IF(OR(T188="",V188=""),"",EDATE(T188,V188))) |  |  |  |  | IF(F188="","",IF(COUNT(AI188:AV188)=0,IF(AA188="","Not started",AA188),SUBSTITUTE(LOOKUP(2,1/(AI188:AV188<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F188="",COUNT(AI188:AV188)=0),"",TODAY()-LOOKUP(2,1/(AI188:AV188<>""),AI188:AV188)) | IF(OR(F188="",COUNT(AI188:AV188)<2),"",LOOKUP(2,1/(AI188:AV188<>""),AI188:AV188)-MIN(AI188:AV188)) | IF(OR(AD188="",AC188="Not started",AC188=""),"",IFERROR(AD188-IF(VLOOKUP(AC188,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC188,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F188="","",IF(OR(AA188="Cancelled",AC188="Cancelled"),"Cancelled",IF(OR(AC188="Completed / Handover",Y188<>"",Z188>=100),"Completed — on track",IF(O188="Not awarded",IF(U188="",IF(X188="","No planned date",IF(TODAY()>X188,"Behind — past planned date",IF(X188-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U188,"Behind — award date passed",IF(U188-TODAY()<=30,"At risk — close to off track","On track"))),IF(X188="","No planned date",IF(AND(TODAY()>X188,OR(Z188="",Z188<100)),"Behind — past end date",IF(AND(T188<>"",X188<>"",Z188<>"",(Z188<100),((TODAY()-T188)/MAX(X188-T188,1)*100)-Z188>15),"Behind — progress lag",IF(AND(X188-TODAY()<=30,X188-TODAY()>=0,OR(Z188="",Z188<90)),"At risk — close to off track","On track")))))))) | IF(OR(F188="",AC188="Completed / Handover",AC188="Cancelled"),"",IF(O188="Not awarded",IF(U188<>"",U188-TODAY(),IF(X188="","",X188-TODAY())),IF(X188="","",X188-TODAY()))) | [14 empty] | IF(OR(F188="",AJ188=""),"",IF(COUNT(AI188:AI188)=0,"",AJ188-LOOKUP(2,1/(AI188:AI188<>""),AI188:AI188))) | IF(OR(F188="",AK188=""),"",IF(COUNT(AI188:AJ188)=0,"",AK188-LOOKUP(2,1/(AI188:AJ188<>""),AI188:AJ188))) | IF(OR(F188="",AL188=""),"",IF(COUNT(AI188:AK188)=0,"",AL188-LOOKUP(2,1/(AI188:AK188<>""),AI188:AK188))) | IF(OR(F188="",AM188=""),"",IF(COUNT(AI188:AL188)=0,"",AM188-LOOKUP(2,1/(AI188:AL188<>""),AI188:AL188))) | IF(OR(F188="",AN188=""),"",IF(COUNT(AI188:AM188)=0,"",AN188-LOOKUP(2,1/(AI188:AM188<>""),AI188:AM188))) | IF(OR(F188="",AO188=""),"",IF(COUNT(AI188:AN188)=0,"",AO188-LOOKUP(2,1/(AI188:AN188<>""),AI188:AN188))) | IF(OR(F188="",AP188=""),"",IF(COUNT(AI188:AO188)=0,"",AP188-LOOKUP(2,1/(AI188:AO188<>""),AI188:AO188))) | IF(OR(F188="",AQ188=""),"",IF(COUNT(AI188:AP188)=0,"",AQ188-LOOKUP(2,1/(AI188:AP188<>""),AI188:AP188))) | IF(OR(F188="",AR188=""),"",IF(COUNT(AI188:AQ188)=0,"",AR188-LOOKUP(2,1/(AI188:AQ188<>""),AI188:AQ188))) | IF(OR(F188="",AS188=""),"",IF(COUNT(AI188:AR188)=0,"",AS188-LOOKUP(2,1/(AI188:AR188<>""),AI188:AR188))) | IF(OR(F188="",AT188=""),"",IF(COUNT(AI188:AS188)=0,"",AT188-LOOKUP(2,1/(AI188:AS188<>""),AI188:AS188))) | IF(OR(F188="",AU188=""),"",IF(COUNT(AI188:AT188)=0,"",AU188-LOOKUP(2,1/(AI188:AT188<>""),AI188:AT188))) | IF(OR(F188="",AV188=""),"",IF(COUNT(AI188:AU188)=0,"",AV188-LOOKUP(2,1/(AI188:AU188<>""),AI188:AU188))) | IF(J188="","All_Provinces",IFERROR(VLOOKUP(J188,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K188="","All_Districts",IFERROR(VLOOKUP(K188,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F189="","",ROW()-3) | [18 empty] | IF(AQ189="","",AQ189) |  |  |  | IF(W189<>"",W189,IF(OR(T189="",V189=""),"",EDATE(T189,V189))) |  |  |  |  | IF(F189="","",IF(COUNT(AI189:AV189)=0,IF(AA189="","Not started",AA189),SUBSTITUTE(LOOKUP(2,1/(AI189:AV189<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F189="",COUNT(AI189:AV189)=0),"",TODAY()-LOOKUP(2,1/(AI189:AV189<>""),AI189:AV189)) | IF(OR(F189="",COUNT(AI189:AV189)<2),"",LOOKUP(2,1/(AI189:AV189<>""),AI189:AV189)-MIN(AI189:AV189)) | IF(OR(AD189="",AC189="Not started",AC189=""),"",IFERROR(AD189-IF(VLOOKUP(AC189,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC189,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F189="","",IF(OR(AA189="Cancelled",AC189="Cancelled"),"Cancelled",IF(OR(AC189="Completed / Handover",Y189<>"",Z189>=100),"Completed — on track",IF(O189="Not awarded",IF(U189="",IF(X189="","No planned date",IF(TODAY()>X189,"Behind — past planned date",IF(X189-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U189,"Behind — award date passed",IF(U189-TODAY()<=30,"At risk — close to off track","On track"))),IF(X189="","No planned date",IF(AND(TODAY()>X189,OR(Z189="",Z189<100)),"Behind — past end date",IF(AND(T189<>"",X189<>"",Z189<>"",(Z189<100),((TODAY()-T189)/MAX(X189-T189,1)*100)-Z189>15),"Behind — progress lag",IF(AND(X189-TODAY()<=30,X189-TODAY()>=0,OR(Z189="",Z189<90)),"At risk — close to off track","On track")))))))) | IF(OR(F189="",AC189="Completed / Handover",AC189="Cancelled"),"",IF(O189="Not awarded",IF(U189<>"",U189-TODAY(),IF(X189="","",X189-TODAY())),IF(X189="","",X189-TODAY()))) | [14 empty] | IF(OR(F189="",AJ189=""),"",IF(COUNT(AI189:AI189)=0,"",AJ189-LOOKUP(2,1/(AI189:AI189<>""),AI189:AI189))) | IF(OR(F189="",AK189=""),"",IF(COUNT(AI189:AJ189)=0,"",AK189-LOOKUP(2,1/(AI189:AJ189<>""),AI189:AJ189))) | IF(OR(F189="",AL189=""),"",IF(COUNT(AI189:AK189)=0,"",AL189-LOOKUP(2,1/(AI189:AK189<>""),AI189:AK189))) | IF(OR(F189="",AM189=""),"",IF(COUNT(AI189:AL189)=0,"",AM189-LOOKUP(2,1/(AI189:AL189<>""),AI189:AL189))) | IF(OR(F189="",AN189=""),"",IF(COUNT(AI189:AM189)=0,"",AN189-LOOKUP(2,1/(AI189:AM189<>""),AI189:AM189))) | IF(OR(F189="",AO189=""),"",IF(COUNT(AI189:AN189)=0,"",AO189-LOOKUP(2,1/(AI189:AN189<>""),AI189:AN189))) | IF(OR(F189="",AP189=""),"",IF(COUNT(AI189:AO189)=0,"",AP189-LOOKUP(2,1/(AI189:AO189<>""),AI189:AO189))) | IF(OR(F189="",AQ189=""),"",IF(COUNT(AI189:AP189)=0,"",AQ189-LOOKUP(2,1/(AI189:AP189<>""),AI189:AP189))) | IF(OR(F189="",AR189=""),"",IF(COUNT(AI189:AQ189)=0,"",AR189-LOOKUP(2,1/(AI189:AQ189<>""),AI189:AQ189))) | IF(OR(F189="",AS189=""),"",IF(COUNT(AI189:AR189)=0,"",AS189-LOOKUP(2,1/(AI189:AR189<>""),AI189:AR189))) | IF(OR(F189="",AT189=""),"",IF(COUNT(AI189:AS189)=0,"",AT189-LOOKUP(2,1/(AI189:AS189<>""),AI189:AS189))) | IF(OR(F189="",AU189=""),"",IF(COUNT(AI189:AT189)=0,"",AU189-LOOKUP(2,1/(AI189:AT189<>""),AI189:AT189))) | IF(OR(F189="",AV189=""),"",IF(COUNT(AI189:AU189)=0,"",AV189-LOOKUP(2,1/(AI189:AU189<>""),AI189:AU189))) | IF(J189="","All_Provinces",IFERROR(VLOOKUP(J189,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K189="","All_Districts",IFERROR(VLOOKUP(K189,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F190="","",ROW()-3) | [18 empty] | IF(AQ190="","",AQ190) |  |  |  | IF(W190<>"",W190,IF(OR(T190="",V190=""),"",EDATE(T190,V190))) |  |  |  |  | IF(F190="","",IF(COUNT(AI190:AV190)=0,IF(AA190="","Not started",AA190),SUBSTITUTE(LOOKUP(2,1/(AI190:AV190<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F190="",COUNT(AI190:AV190)=0),"",TODAY()-LOOKUP(2,1/(AI190:AV190<>""),AI190:AV190)) | IF(OR(F190="",COUNT(AI190:AV190)<2),"",LOOKUP(2,1/(AI190:AV190<>""),AI190:AV190)-MIN(AI190:AV190)) | IF(OR(AD190="",AC190="Not started",AC190=""),"",IFERROR(AD190-IF(VLOOKUP(AC190,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC190,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F190="","",IF(OR(AA190="Cancelled",AC190="Cancelled"),"Cancelled",IF(OR(AC190="Completed / Handover",Y190<>"",Z190>=100),"Completed — on track",IF(O190="Not awarded",IF(U190="",IF(X190="","No planned date",IF(TODAY()>X190,"Behind — past planned date",IF(X190-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U190,"Behind — award date passed",IF(U190-TODAY()<=30,"At risk — close to off track","On track"))),IF(X190="","No planned date",IF(AND(TODAY()>X190,OR(Z190="",Z190<100)),"Behind — past end date",IF(AND(T190<>"",X190<>"",Z190<>"",(Z190<100),((TODAY()-T190)/MAX(X190-T190,1)*100)-Z190>15),"Behind — progress lag",IF(AND(X190-TODAY()<=30,X190-TODAY()>=0,OR(Z190="",Z190<90)),"At risk — close to off track","On track")))))))) | IF(OR(F190="",AC190="Completed / Handover",AC190="Cancelled"),"",IF(O190="Not awarded",IF(U190<>"",U190-TODAY(),IF(X190="","",X190-TODAY())),IF(X190="","",X190-TODAY()))) | [14 empty] | IF(OR(F190="",AJ190=""),"",IF(COUNT(AI190:AI190)=0,"",AJ190-LOOKUP(2,1/(AI190:AI190<>""),AI190:AI190))) | IF(OR(F190="",AK190=""),"",IF(COUNT(AI190:AJ190)=0,"",AK190-LOOKUP(2,1/(AI190:AJ190<>""),AI190:AJ190))) | IF(OR(F190="",AL190=""),"",IF(COUNT(AI190:AK190)=0,"",AL190-LOOKUP(2,1/(AI190:AK190<>""),AI190:AK190))) | IF(OR(F190="",AM190=""),"",IF(COUNT(AI190:AL190)=0,"",AM190-LOOKUP(2,1/(AI190:AL190<>""),AI190:AL190))) | IF(OR(F190="",AN190=""),"",IF(COUNT(AI190:AM190)=0,"",AN190-LOOKUP(2,1/(AI190:AM190<>""),AI190:AM190))) | IF(OR(F190="",AO190=""),"",IF(COUNT(AI190:AN190)=0,"",AO190-LOOKUP(2,1/(AI190:AN190<>""),AI190:AN190))) | IF(OR(F190="",AP190=""),"",IF(COUNT(AI190:AO190)=0,"",AP190-LOOKUP(2,1/(AI190:AO190<>""),AI190:AO190))) | IF(OR(F190="",AQ190=""),"",IF(COUNT(AI190:AP190)=0,"",AQ190-LOOKUP(2,1/(AI190:AP190<>""),AI190:AP190))) | IF(OR(F190="",AR190=""),"",IF(COUNT(AI190:AQ190)=0,"",AR190-LOOKUP(2,1/(AI190:AQ190<>""),AI190:AQ190))) | IF(OR(F190="",AS190=""),"",IF(COUNT(AI190:AR190)=0,"",AS190-LOOKUP(2,1/(AI190:AR190<>""),AI190:AR190))) | IF(OR(F190="",AT190=""),"",IF(COUNT(AI190:AS190)=0,"",AT190-LOOKUP(2,1/(AI190:AS190<>""),AI190:AS190))) | IF(OR(F190="",AU190=""),"",IF(COUNT(AI190:AT190)=0,"",AU190-LOOKUP(2,1/(AI190:AT190<>""),AI190:AT190))) | IF(OR(F190="",AV190=""),"",IF(COUNT(AI190:AU190)=0,"",AV190-LOOKUP(2,1/(AI190:AU190<>""),AI190:AU190))) | IF(J190="","All_Provinces",IFERROR(VLOOKUP(J190,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K190="","All_Districts",IFERROR(VLOOKUP(K190,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F191="","",ROW()-3) | [18 empty] | IF(AQ191="","",AQ191) |  |  |  | IF(W191<>"",W191,IF(OR(T191="",V191=""),"",EDATE(T191,V191))) |  |  |  |  | IF(F191="","",IF(COUNT(AI191:AV191)=0,IF(AA191="","Not started",AA191),SUBSTITUTE(LOOKUP(2,1/(AI191:AV191<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F191="",COUNT(AI191:AV191)=0),"",TODAY()-LOOKUP(2,1/(AI191:AV191<>""),AI191:AV191)) | IF(OR(F191="",COUNT(AI191:AV191)<2),"",LOOKUP(2,1/(AI191:AV191<>""),AI191:AV191)-MIN(AI191:AV191)) | IF(OR(AD191="",AC191="Not started",AC191=""),"",IFERROR(AD191-IF(VLOOKUP(AC191,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC191,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F191="","",IF(OR(AA191="Cancelled",AC191="Cancelled"),"Cancelled",IF(OR(AC191="Completed / Handover",Y191<>"",Z191>=100),"Completed — on track",IF(O191="Not awarded",IF(U191="",IF(X191="","No planned date",IF(TODAY()>X191,"Behind — past planned date",IF(X191-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U191,"Behind — award date passed",IF(U191-TODAY()<=30,"At risk — close to off track","On track"))),IF(X191="","No planned date",IF(AND(TODAY()>X191,OR(Z191="",Z191<100)),"Behind — past end date",IF(AND(T191<>"",X191<>"",Z191<>"",(Z191<100),((TODAY()-T191)/MAX(X191-T191,1)*100)-Z191>15),"Behind — progress lag",IF(AND(X191-TODAY()<=30,X191-TODAY()>=0,OR(Z191="",Z191<90)),"At risk — close to off track","On track")))))))) | IF(OR(F191="",AC191="Completed / Handover",AC191="Cancelled"),"",IF(O191="Not awarded",IF(U191<>"",U191-TODAY(),IF(X191="","",X191-TODAY())),IF(X191="","",X191-TODAY()))) | [14 empty] | IF(OR(F191="",AJ191=""),"",IF(COUNT(AI191:AI191)=0,"",AJ191-LOOKUP(2,1/(AI191:AI191<>""),AI191:AI191))) | IF(OR(F191="",AK191=""),"",IF(COUNT(AI191:AJ191)=0,"",AK191-LOOKUP(2,1/(AI191:AJ191<>""),AI191:AJ191))) | IF(OR(F191="",AL191=""),"",IF(COUNT(AI191:AK191)=0,"",AL191-LOOKUP(2,1/(AI191:AK191<>""),AI191:AK191))) | IF(OR(F191="",AM191=""),"",IF(COUNT(AI191:AL191)=0,"",AM191-LOOKUP(2,1/(AI191:AL191<>""),AI191:AL191))) | IF(OR(F191="",AN191=""),"",IF(COUNT(AI191:AM191)=0,"",AN191-LOOKUP(2,1/(AI191:AM191<>""),AI191:AM191))) | IF(OR(F191="",AO191=""),"",IF(COUNT(AI191:AN191)=0,"",AO191-LOOKUP(2,1/(AI191:AN191<>""),AI191:AN191))) | IF(OR(F191="",AP191=""),"",IF(COUNT(AI191:AO191)=0,"",AP191-LOOKUP(2,1/(AI191:AO191<>""),AI191:AO191))) | IF(OR(F191="",AQ191=""),"",IF(COUNT(AI191:AP191)=0,"",AQ191-LOOKUP(2,1/(AI191:AP191<>""),AI191:AP191))) | IF(OR(F191="",AR191=""),"",IF(COUNT(AI191:AQ191)=0,"",AR191-LOOKUP(2,1/(AI191:AQ191<>""),AI191:AQ191))) | IF(OR(F191="",AS191=""),"",IF(COUNT(AI191:AR191)=0,"",AS191-LOOKUP(2,1/(AI191:AR191<>""),AI191:AR191))) | IF(OR(F191="",AT191=""),"",IF(COUNT(AI191:AS191)=0,"",AT191-LOOKUP(2,1/(AI191:AS191<>""),AI191:AS191))) | IF(OR(F191="",AU191=""),"",IF(COUNT(AI191:AT191)=0,"",AU191-LOOKUP(2,1/(AI191:AT191<>""),AI191:AT191))) | IF(OR(F191="",AV191=""),"",IF(COUNT(AI191:AU191)=0,"",AV191-LOOKUP(2,1/(AI191:AU191<>""),AI191:AU191))) | IF(J191="","All_Provinces",IFERROR(VLOOKUP(J191,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K191="","All_Districts",IFERROR(VLOOKUP(K191,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F192="","",ROW()-3) | [18 empty] | IF(AQ192="","",AQ192) |  |  |  | IF(W192<>"",W192,IF(OR(T192="",V192=""),"",EDATE(T192,V192))) |  |  |  |  | IF(F192="","",IF(COUNT(AI192:AV192)=0,IF(AA192="","Not started",AA192),SUBSTITUTE(LOOKUP(2,1/(AI192:AV192<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F192="",COUNT(AI192:AV192)=0),"",TODAY()-LOOKUP(2,1/(AI192:AV192<>""),AI192:AV192)) | IF(OR(F192="",COUNT(AI192:AV192)<2),"",LOOKUP(2,1/(AI192:AV192<>""),AI192:AV192)-MIN(AI192:AV192)) | IF(OR(AD192="",AC192="Not started",AC192=""),"",IFERROR(AD192-IF(VLOOKUP(AC192,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC192,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F192="","",IF(OR(AA192="Cancelled",AC192="Cancelled"),"Cancelled",IF(OR(AC192="Completed / Handover",Y192<>"",Z192>=100),"Completed — on track",IF(O192="Not awarded",IF(U192="",IF(X192="","No planned date",IF(TODAY()>X192,"Behind — past planned date",IF(X192-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U192,"Behind — award date passed",IF(U192-TODAY()<=30,"At risk — close to off track","On track"))),IF(X192="","No planned date",IF(AND(TODAY()>X192,OR(Z192="",Z192<100)),"Behind — past end date",IF(AND(T192<>"",X192<>"",Z192<>"",(Z192<100),((TODAY()-T192)/MAX(X192-T192,1)*100)-Z192>15),"Behind — progress lag",IF(AND(X192-TODAY()<=30,X192-TODAY()>=0,OR(Z192="",Z192<90)),"At risk — close to off track","On track")))))))) | IF(OR(F192="",AC192="Completed / Handover",AC192="Cancelled"),"",IF(O192="Not awarded",IF(U192<>"",U192-TODAY(),IF(X192="","",X192-TODAY())),IF(X192="","",X192-TODAY()))) | [14 empty] | IF(OR(F192="",AJ192=""),"",IF(COUNT(AI192:AI192)=0,"",AJ192-LOOKUP(2,1/(AI192:AI192<>""),AI192:AI192))) | IF(OR(F192="",AK192=""),"",IF(COUNT(AI192:AJ192)=0,"",AK192-LOOKUP(2,1/(AI192:AJ192<>""),AI192:AJ192))) | IF(OR(F192="",AL192=""),"",IF(COUNT(AI192:AK192)=0,"",AL192-LOOKUP(2,1/(AI192:AK192<>""),AI192:AK192))) | IF(OR(F192="",AM192=""),"",IF(COUNT(AI192:AL192)=0,"",AM192-LOOKUP(2,1/(AI192:AL192<>""),AI192:AL192))) | IF(OR(F192="",AN192=""),"",IF(COUNT(AI192:AM192)=0,"",AN192-LOOKUP(2,1/(AI192:AM192<>""),AI192:AM192))) | IF(OR(F192="",AO192=""),"",IF(COUNT(AI192:AN192)=0,"",AO192-LOOKUP(2,1/(AI192:AN192<>""),AI192:AN192))) | IF(OR(F192="",AP192=""),"",IF(COUNT(AI192:AO192)=0,"",AP192-LOOKUP(2,1/(AI192:AO192<>""),AI192:AO192))) | IF(OR(F192="",AQ192=""),"",IF(COUNT(AI192:AP192)=0,"",AQ192-LOOKUP(2,1/(AI192:AP192<>""),AI192:AP192))) | IF(OR(F192="",AR192=""),"",IF(COUNT(AI192:AQ192)=0,"",AR192-LOOKUP(2,1/(AI192:AQ192<>""),AI192:AQ192))) | IF(OR(F192="",AS192=""),"",IF(COUNT(AI192:AR192)=0,"",AS192-LOOKUP(2,1/(AI192:AR192<>""),AI192:AR192))) | IF(OR(F192="",AT192=""),"",IF(COUNT(AI192:AS192)=0,"",AT192-LOOKUP(2,1/(AI192:AS192<>""),AI192:AS192))) | IF(OR(F192="",AU192=""),"",IF(COUNT(AI192:AT192)=0,"",AU192-LOOKUP(2,1/(AI192:AT192<>""),AI192:AT192))) | IF(OR(F192="",AV192=""),"",IF(COUNT(AI192:AU192)=0,"",AV192-LOOKUP(2,1/(AI192:AU192<>""),AI192:AU192))) | IF(J192="","All_Provinces",IFERROR(VLOOKUP(J192,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K192="","All_Districts",IFERROR(VLOOKUP(K192,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F193="","",ROW()-3) | [18 empty] | IF(AQ193="","",AQ193) |  |  |  | IF(W193<>"",W193,IF(OR(T193="",V193=""),"",EDATE(T193,V193))) |  |  |  |  | IF(F193="","",IF(COUNT(AI193:AV193)=0,IF(AA193="","Not started",AA193),SUBSTITUTE(LOOKUP(2,1/(AI193:AV193<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F193="",COUNT(AI193:AV193)=0),"",TODAY()-LOOKUP(2,1/(AI193:AV193<>""),AI193:AV193)) | IF(OR(F193="",COUNT(AI193:AV193)<2),"",LOOKUP(2,1/(AI193:AV193<>""),AI193:AV193)-MIN(AI193:AV193)) | IF(OR(AD193="",AC193="Not started",AC193=""),"",IFERROR(AD193-IF(VLOOKUP(AC193,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC193,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F193="","",IF(OR(AA193="Cancelled",AC193="Cancelled"),"Cancelled",IF(OR(AC193="Completed / Handover",Y193<>"",Z193>=100),"Completed — on track",IF(O193="Not awarded",IF(U193="",IF(X193="","No planned date",IF(TODAY()>X193,"Behind — past planned date",IF(X193-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U193,"Behind — award date passed",IF(U193-TODAY()<=30,"At risk — close to off track","On track"))),IF(X193="","No planned date",IF(AND(TODAY()>X193,OR(Z193="",Z193<100)),"Behind — past end date",IF(AND(T193<>"",X193<>"",Z193<>"",(Z193<100),((TODAY()-T193)/MAX(X193-T193,1)*100)-Z193>15),"Behind — progress lag",IF(AND(X193-TODAY()<=30,X193-TODAY()>=0,OR(Z193="",Z193<90)),"At risk — close to off track","On track")))))))) | IF(OR(F193="",AC193="Completed / Handover",AC193="Cancelled"),"",IF(O193="Not awarded",IF(U193<>"",U193-TODAY(),IF(X193="","",X193-TODAY())),IF(X193="","",X193-TODAY()))) | [14 empty] | IF(OR(F193="",AJ193=""),"",IF(COUNT(AI193:AI193)=0,"",AJ193-LOOKUP(2,1/(AI193:AI193<>""),AI193:AI193))) | IF(OR(F193="",AK193=""),"",IF(COUNT(AI193:AJ193)=0,"",AK193-LOOKUP(2,1/(AI193:AJ193<>""),AI193:AJ193))) | IF(OR(F193="",AL193=""),"",IF(COUNT(AI193:AK193)=0,"",AL193-LOOKUP(2,1/(AI193:AK193<>""),AI193:AK193))) | IF(OR(F193="",AM193=""),"",IF(COUNT(AI193:AL193)=0,"",AM193-LOOKUP(2,1/(AI193:AL193<>""),AI193:AL193))) | IF(OR(F193="",AN193=""),"",IF(COUNT(AI193:AM193)=0,"",AN193-LOOKUP(2,1/(AI193:AM193<>""),AI193:AM193))) | IF(OR(F193="",AO193=""),"",IF(COUNT(AI193:AN193)=0,"",AO193-LOOKUP(2,1/(AI193:AN193<>""),AI193:AN193))) | IF(OR(F193="",AP193=""),"",IF(COUNT(AI193:AO193)=0,"",AP193-LOOKUP(2,1/(AI193:AO193<>""),AI193:AO193))) | IF(OR(F193="",AQ193=""),"",IF(COUNT(AI193:AP193)=0,"",AQ193-LOOKUP(2,1/(AI193:AP193<>""),AI193:AP193))) | IF(OR(F193="",AR193=""),"",IF(COUNT(AI193:AQ193)=0,"",AR193-LOOKUP(2,1/(AI193:AQ193<>""),AI193:AQ193))) | IF(OR(F193="",AS193=""),"",IF(COUNT(AI193:AR193)=0,"",AS193-LOOKUP(2,1/(AI193:AR193<>""),AI193:AR193))) | IF(OR(F193="",AT193=""),"",IF(COUNT(AI193:AS193)=0,"",AT193-LOOKUP(2,1/(AI193:AS193<>""),AI193:AS193))) | IF(OR(F193="",AU193=""),"",IF(COUNT(AI193:AT193)=0,"",AU193-LOOKUP(2,1/(AI193:AT193<>""),AI193:AT193))) | IF(OR(F193="",AV193=""),"",IF(COUNT(AI193:AU193)=0,"",AV193-LOOKUP(2,1/(AI193:AU193<>""),AI193:AU193))) | IF(J193="","All_Provinces",IFERROR(VLOOKUP(J193,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K193="","All_Districts",IFERROR(VLOOKUP(K193,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F194="","",ROW()-3) | [18 empty] | IF(AQ194="","",AQ194) |  |  |  | IF(W194<>"",W194,IF(OR(T194="",V194=""),"",EDATE(T194,V194))) |  |  |  |  | IF(F194="","",IF(COUNT(AI194:AV194)=0,IF(AA194="","Not started",AA194),SUBSTITUTE(LOOKUP(2,1/(AI194:AV194<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F194="",COUNT(AI194:AV194)=0),"",TODAY()-LOOKUP(2,1/(AI194:AV194<>""),AI194:AV194)) | IF(OR(F194="",COUNT(AI194:AV194)<2),"",LOOKUP(2,1/(AI194:AV194<>""),AI194:AV194)-MIN(AI194:AV194)) | IF(OR(AD194="",AC194="Not started",AC194=""),"",IFERROR(AD194-IF(VLOOKUP(AC194,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC194,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F194="","",IF(OR(AA194="Cancelled",AC194="Cancelled"),"Cancelled",IF(OR(AC194="Completed / Handover",Y194<>"",Z194>=100),"Completed — on track",IF(O194="Not awarded",IF(U194="",IF(X194="","No planned date",IF(TODAY()>X194,"Behind — past planned date",IF(X194-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U194,"Behind — award date passed",IF(U194-TODAY()<=30,"At risk — close to off track","On track"))),IF(X194="","No planned date",IF(AND(TODAY()>X194,OR(Z194="",Z194<100)),"Behind — past end date",IF(AND(T194<>"",X194<>"",Z194<>"",(Z194<100),((TODAY()-T194)/MAX(X194-T194,1)*100)-Z194>15),"Behind — progress lag",IF(AND(X194-TODAY()<=30,X194-TODAY()>=0,OR(Z194="",Z194<90)),"At risk — close to off track","On track")))))))) | IF(OR(F194="",AC194="Completed / Handover",AC194="Cancelled"),"",IF(O194="Not awarded",IF(U194<>"",U194-TODAY(),IF(X194="","",X194-TODAY())),IF(X194="","",X194-TODAY()))) | [14 empty] | IF(OR(F194="",AJ194=""),"",IF(COUNT(AI194:AI194)=0,"",AJ194-LOOKUP(2,1/(AI194:AI194<>""),AI194:AI194))) | IF(OR(F194="",AK194=""),"",IF(COUNT(AI194:AJ194)=0,"",AK194-LOOKUP(2,1/(AI194:AJ194<>""),AI194:AJ194))) | IF(OR(F194="",AL194=""),"",IF(COUNT(AI194:AK194)=0,"",AL194-LOOKUP(2,1/(AI194:AK194<>""),AI194:AK194))) | IF(OR(F194="",AM194=""),"",IF(COUNT(AI194:AL194)=0,"",AM194-LOOKUP(2,1/(AI194:AL194<>""),AI194:AL194))) | IF(OR(F194="",AN194=""),"",IF(COUNT(AI194:AM194)=0,"",AN194-LOOKUP(2,1/(AI194:AM194<>""),AI194:AM194))) | IF(OR(F194="",AO194=""),"",IF(COUNT(AI194:AN194)=0,"",AO194-LOOKUP(2,1/(AI194:AN194<>""),AI194:AN194))) | IF(OR(F194="",AP194=""),"",IF(COUNT(AI194:AO194)=0,"",AP194-LOOKUP(2,1/(AI194:AO194<>""),AI194:AO194))) | IF(OR(F194="",AQ194=""),"",IF(COUNT(AI194:AP194)=0,"",AQ194-LOOKUP(2,1/(AI194:AP194<>""),AI194:AP194))) | IF(OR(F194="",AR194=""),"",IF(COUNT(AI194:AQ194)=0,"",AR194-LOOKUP(2,1/(AI194:AQ194<>""),AI194:AQ194))) | IF(OR(F194="",AS194=""),"",IF(COUNT(AI194:AR194)=0,"",AS194-LOOKUP(2,1/(AI194:AR194<>""),AI194:AR194))) | IF(OR(F194="",AT194=""),"",IF(COUNT(AI194:AS194)=0,"",AT194-LOOKUP(2,1/(AI194:AS194<>""),AI194:AS194))) | IF(OR(F194="",AU194=""),"",IF(COUNT(AI194:AT194)=0,"",AU194-LOOKUP(2,1/(AI194:AT194<>""),AI194:AT194))) | IF(OR(F194="",AV194=""),"",IF(COUNT(AI194:AU194)=0,"",AV194-LOOKUP(2,1/(AI194:AU194<>""),AI194:AU194))) | IF(J194="","All_Provinces",IFERROR(VLOOKUP(J194,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K194="","All_Districts",IFERROR(VLOOKUP(K194,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F195="","",ROW()-3) | [18 empty] | IF(AQ195="","",AQ195) |  |  |  | IF(W195<>"",W195,IF(OR(T195="",V195=""),"",EDATE(T195,V195))) |  |  |  |  | IF(F195="","",IF(COUNT(AI195:AV195)=0,IF(AA195="","Not started",AA195),SUBSTITUTE(LOOKUP(2,1/(AI195:AV195<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F195="",COUNT(AI195:AV195)=0),"",TODAY()-LOOKUP(2,1/(AI195:AV195<>""),AI195:AV195)) | IF(OR(F195="",COUNT(AI195:AV195)<2),"",LOOKUP(2,1/(AI195:AV195<>""),AI195:AV195)-MIN(AI195:AV195)) | IF(OR(AD195="",AC195="Not started",AC195=""),"",IFERROR(AD195-IF(VLOOKUP(AC195,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC195,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F195="","",IF(OR(AA195="Cancelled",AC195="Cancelled"),"Cancelled",IF(OR(AC195="Completed / Handover",Y195<>"",Z195>=100),"Completed — on track",IF(O195="Not awarded",IF(U195="",IF(X195="","No planned date",IF(TODAY()>X195,"Behind — past planned date",IF(X195-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U195,"Behind — award date passed",IF(U195-TODAY()<=30,"At risk — close to off track","On track"))),IF(X195="","No planned date",IF(AND(TODAY()>X195,OR(Z195="",Z195<100)),"Behind — past end date",IF(AND(T195<>"",X195<>"",Z195<>"",(Z195<100),((TODAY()-T195)/MAX(X195-T195,1)*100)-Z195>15),"Behind — progress lag",IF(AND(X195-TODAY()<=30,X195-TODAY()>=0,OR(Z195="",Z195<90)),"At risk — close to off track","On track")))))))) | IF(OR(F195="",AC195="Completed / Handover",AC195="Cancelled"),"",IF(O195="Not awarded",IF(U195<>"",U195-TODAY(),IF(X195="","",X195-TODAY())),IF(X195="","",X195-TODAY()))) | [14 empty] | IF(OR(F195="",AJ195=""),"",IF(COUNT(AI195:AI195)=0,"",AJ195-LOOKUP(2,1/(AI195:AI195<>""),AI195:AI195))) | IF(OR(F195="",AK195=""),"",IF(COUNT(AI195:AJ195)=0,"",AK195-LOOKUP(2,1/(AI195:AJ195<>""),AI195:AJ195))) | IF(OR(F195="",AL195=""),"",IF(COUNT(AI195:AK195)=0,"",AL195-LOOKUP(2,1/(AI195:AK195<>""),AI195:AK195))) | IF(OR(F195="",AM195=""),"",IF(COUNT(AI195:AL195)=0,"",AM195-LOOKUP(2,1/(AI195:AL195<>""),AI195:AL195))) | IF(OR(F195="",AN195=""),"",IF(COUNT(AI195:AM195)=0,"",AN195-LOOKUP(2,1/(AI195:AM195<>""),AI195:AM195))) | IF(OR(F195="",AO195=""),"",IF(COUNT(AI195:AN195)=0,"",AO195-LOOKUP(2,1/(AI195:AN195<>""),AI195:AN195))) | IF(OR(F195="",AP195=""),"",IF(COUNT(AI195:AO195)=0,"",AP195-LOOKUP(2,1/(AI195:AO195<>""),AI195:AO195))) | IF(OR(F195="",AQ195=""),"",IF(COUNT(AI195:AP195)=0,"",AQ195-LOOKUP(2,1/(AI195:AP195<>""),AI195:AP195))) | IF(OR(F195="",AR195=""),"",IF(COUNT(AI195:AQ195)=0,"",AR195-LOOKUP(2,1/(AI195:AQ195<>""),AI195:AQ195))) | IF(OR(F195="",AS195=""),"",IF(COUNT(AI195:AR195)=0,"",AS195-LOOKUP(2,1/(AI195:AR195<>""),AI195:AR195))) | IF(OR(F195="",AT195=""),"",IF(COUNT(AI195:AS195)=0,"",AT195-LOOKUP(2,1/(AI195:AS195<>""),AI195:AS195))) | IF(OR(F195="",AU195=""),"",IF(COUNT(AI195:AT195)=0,"",AU195-LOOKUP(2,1/(AI195:AT195<>""),AI195:AT195))) | IF(OR(F195="",AV195=""),"",IF(COUNT(AI195:AU195)=0,"",AV195-LOOKUP(2,1/(AI195:AU195<>""),AI195:AU195))) | IF(J195="","All_Provinces",IFERROR(VLOOKUP(J195,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K195="","All_Districts",IFERROR(VLOOKUP(K195,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F196="","",ROW()-3) | [18 empty] | IF(AQ196="","",AQ196) |  |  |  | IF(W196<>"",W196,IF(OR(T196="",V196=""),"",EDATE(T196,V196))) |  |  |  |  | IF(F196="","",IF(COUNT(AI196:AV196)=0,IF(AA196="","Not started",AA196),SUBSTITUTE(LOOKUP(2,1/(AI196:AV196<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F196="",COUNT(AI196:AV196)=0),"",TODAY()-LOOKUP(2,1/(AI196:AV196<>""),AI196:AV196)) | IF(OR(F196="",COUNT(AI196:AV196)<2),"",LOOKUP(2,1/(AI196:AV196<>""),AI196:AV196)-MIN(AI196:AV196)) | IF(OR(AD196="",AC196="Not started",AC196=""),"",IFERROR(AD196-IF(VLOOKUP(AC196,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC196,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F196="","",IF(OR(AA196="Cancelled",AC196="Cancelled"),"Cancelled",IF(OR(AC196="Completed / Handover",Y196<>"",Z196>=100),"Completed — on track",IF(O196="Not awarded",IF(U196="",IF(X196="","No planned date",IF(TODAY()>X196,"Behind — past planned date",IF(X196-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U196,"Behind — award date passed",IF(U196-TODAY()<=30,"At risk — close to off track","On track"))),IF(X196="","No planned date",IF(AND(TODAY()>X196,OR(Z196="",Z196<100)),"Behind — past end date",IF(AND(T196<>"",X196<>"",Z196<>"",(Z196<100),((TODAY()-T196)/MAX(X196-T196,1)*100)-Z196>15),"Behind — progress lag",IF(AND(X196-TODAY()<=30,X196-TODAY()>=0,OR(Z196="",Z196<90)),"At risk — close to off track","On track")))))))) | IF(OR(F196="",AC196="Completed / Handover",AC196="Cancelled"),"",IF(O196="Not awarded",IF(U196<>"",U196-TODAY(),IF(X196="","",X196-TODAY())),IF(X196="","",X196-TODAY()))) | [14 empty] | IF(OR(F196="",AJ196=""),"",IF(COUNT(AI196:AI196)=0,"",AJ196-LOOKUP(2,1/(AI196:AI196<>""),AI196:AI196))) | IF(OR(F196="",AK196=""),"",IF(COUNT(AI196:AJ196)=0,"",AK196-LOOKUP(2,1/(AI196:AJ196<>""),AI196:AJ196))) | IF(OR(F196="",AL196=""),"",IF(COUNT(AI196:AK196)=0,"",AL196-LOOKUP(2,1/(AI196:AK196<>""),AI196:AK196))) | IF(OR(F196="",AM196=""),"",IF(COUNT(AI196:AL196)=0,"",AM196-LOOKUP(2,1/(AI196:AL196<>""),AI196:AL196))) | IF(OR(F196="",AN196=""),"",IF(COUNT(AI196:AM196)=0,"",AN196-LOOKUP(2,1/(AI196:AM196<>""),AI196:AM196))) | IF(OR(F196="",AO196=""),"",IF(COUNT(AI196:AN196)=0,"",AO196-LOOKUP(2,1/(AI196:AN196<>""),AI196:AN196))) | IF(OR(F196="",AP196=""),"",IF(COUNT(AI196:AO196)=0,"",AP196-LOOKUP(2,1/(AI196:AO196<>""),AI196:AO196))) | IF(OR(F196="",AQ196=""),"",IF(COUNT(AI196:AP196)=0,"",AQ196-LOOKUP(2,1/(AI196:AP196<>""),AI196:AP196))) | IF(OR(F196="",AR196=""),"",IF(COUNT(AI196:AQ196)=0,"",AR196-LOOKUP(2,1/(AI196:AQ196<>""),AI196:AQ196))) | IF(OR(F196="",AS196=""),"",IF(COUNT(AI196:AR196)=0,"",AS196-LOOKUP(2,1/(AI196:AR196<>""),AI196:AR196))) | IF(OR(F196="",AT196=""),"",IF(COUNT(AI196:AS196)=0,"",AT196-LOOKUP(2,1/(AI196:AS196<>""),AI196:AS196))) | IF(OR(F196="",AU196=""),"",IF(COUNT(AI196:AT196)=0,"",AU196-LOOKUP(2,1/(AI196:AT196<>""),AI196:AT196))) | IF(OR(F196="",AV196=""),"",IF(COUNT(AI196:AU196)=0,"",AV196-LOOKUP(2,1/(AI196:AU196<>""),AI196:AU196))) | IF(J196="","All_Provinces",IFERROR(VLOOKUP(J196,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K196="","All_Districts",IFERROR(VLOOKUP(K196,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F197="","",ROW()-3) | [18 empty] | IF(AQ197="","",AQ197) |  |  |  | IF(W197<>"",W197,IF(OR(T197="",V197=""),"",EDATE(T197,V197))) |  |  |  |  | IF(F197="","",IF(COUNT(AI197:AV197)=0,IF(AA197="","Not started",AA197),SUBSTITUTE(LOOKUP(2,1/(AI197:AV197<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F197="",COUNT(AI197:AV197)=0),"",TODAY()-LOOKUP(2,1/(AI197:AV197<>""),AI197:AV197)) | IF(OR(F197="",COUNT(AI197:AV197)<2),"",LOOKUP(2,1/(AI197:AV197<>""),AI197:AV197)-MIN(AI197:AV197)) | IF(OR(AD197="",AC197="Not started",AC197=""),"",IFERROR(AD197-IF(VLOOKUP(AC197,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC197,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F197="","",IF(OR(AA197="Cancelled",AC197="Cancelled"),"Cancelled",IF(OR(AC197="Completed / Handover",Y197<>"",Z197>=100),"Completed — on track",IF(O197="Not awarded",IF(U197="",IF(X197="","No planned date",IF(TODAY()>X197,"Behind — past planned date",IF(X197-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U197,"Behind — award date passed",IF(U197-TODAY()<=30,"At risk — close to off track","On track"))),IF(X197="","No planned date",IF(AND(TODAY()>X197,OR(Z197="",Z197<100)),"Behind — past end date",IF(AND(T197<>"",X197<>"",Z197<>"",(Z197<100),((TODAY()-T197)/MAX(X197-T197,1)*100)-Z197>15),"Behind — progress lag",IF(AND(X197-TODAY()<=30,X197-TODAY()>=0,OR(Z197="",Z197<90)),"At risk — close to off track","On track")))))))) | IF(OR(F197="",AC197="Completed / Handover",AC197="Cancelled"),"",IF(O197="Not awarded",IF(U197<>"",U197-TODAY(),IF(X197="","",X197-TODAY())),IF(X197="","",X197-TODAY()))) | [14 empty] | IF(OR(F197="",AJ197=""),"",IF(COUNT(AI197:AI197)=0,"",AJ197-LOOKUP(2,1/(AI197:AI197<>""),AI197:AI197))) | IF(OR(F197="",AK197=""),"",IF(COUNT(AI197:AJ197)=0,"",AK197-LOOKUP(2,1/(AI197:AJ197<>""),AI197:AJ197))) | IF(OR(F197="",AL197=""),"",IF(COUNT(AI197:AK197)=0,"",AL197-LOOKUP(2,1/(AI197:AK197<>""),AI197:AK197))) | IF(OR(F197="",AM197=""),"",IF(COUNT(AI197:AL197)=0,"",AM197-LOOKUP(2,1/(AI197:AL197<>""),AI197:AL197))) | IF(OR(F197="",AN197=""),"",IF(COUNT(AI197:AM197)=0,"",AN197-LOOKUP(2,1/(AI197:AM197<>""),AI197:AM197))) | IF(OR(F197="",AO197=""),"",IF(COUNT(AI197:AN197)=0,"",AO197-LOOKUP(2,1/(AI197:AN197<>""),AI197:AN197))) | IF(OR(F197="",AP197=""),"",IF(COUNT(AI197:AO197)=0,"",AP197-LOOKUP(2,1/(AI197:AO197<>""),AI197:AO197))) | IF(OR(F197="",AQ197=""),"",IF(COUNT(AI197:AP197)=0,"",AQ197-LOOKUP(2,1/(AI197:AP197<>""),AI197:AP197))) | IF(OR(F197="",AR197=""),"",IF(COUNT(AI197:AQ197)=0,"",AR197-LOOKUP(2,1/(AI197:AQ197<>""),AI197:AQ197))) | IF(OR(F197="",AS197=""),"",IF(COUNT(AI197:AR197)=0,"",AS197-LOOKUP(2,1/(AI197:AR197<>""),AI197:AR197))) | IF(OR(F197="",AT197=""),"",IF(COUNT(AI197:AS197)=0,"",AT197-LOOKUP(2,1/(AI197:AS197<>""),AI197:AS197))) | IF(OR(F197="",AU197=""),"",IF(COUNT(AI197:AT197)=0,"",AU197-LOOKUP(2,1/(AI197:AT197<>""),AI197:AT197))) | IF(OR(F197="",AV197=""),"",IF(COUNT(AI197:AU197)=0,"",AV197-LOOKUP(2,1/(AI197:AU197<>""),AI197:AU197))) | IF(J197="","All_Provinces",IFERROR(VLOOKUP(J197,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K197="","All_Districts",IFERROR(VLOOKUP(K197,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F198="","",ROW()-3) | [18 empty] | IF(AQ198="","",AQ198) |  |  |  | IF(W198<>"",W198,IF(OR(T198="",V198=""),"",EDATE(T198,V198))) |  |  |  |  | IF(F198="","",IF(COUNT(AI198:AV198)=0,IF(AA198="","Not started",AA198),SUBSTITUTE(LOOKUP(2,1/(AI198:AV198<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F198="",COUNT(AI198:AV198)=0),"",TODAY()-LOOKUP(2,1/(AI198:AV198<>""),AI198:AV198)) | IF(OR(F198="",COUNT(AI198:AV198)<2),"",LOOKUP(2,1/(AI198:AV198<>""),AI198:AV198)-MIN(AI198:AV198)) | IF(OR(AD198="",AC198="Not started",AC198=""),"",IFERROR(AD198-IF(VLOOKUP(AC198,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC198,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F198="","",IF(OR(AA198="Cancelled",AC198="Cancelled"),"Cancelled",IF(OR(AC198="Completed / Handover",Y198<>"",Z198>=100),"Completed — on track",IF(O198="Not awarded",IF(U198="",IF(X198="","No planned date",IF(TODAY()>X198,"Behind — past planned date",IF(X198-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U198,"Behind — award date passed",IF(U198-TODAY()<=30,"At risk — close to off track","On track"))),IF(X198="","No planned date",IF(AND(TODAY()>X198,OR(Z198="",Z198<100)),"Behind — past end date",IF(AND(T198<>"",X198<>"",Z198<>"",(Z198<100),((TODAY()-T198)/MAX(X198-T198,1)*100)-Z198>15),"Behind — progress lag",IF(AND(X198-TODAY()<=30,X198-TODAY()>=0,OR(Z198="",Z198<90)),"At risk — close to off track","On track")))))))) | IF(OR(F198="",AC198="Completed / Handover",AC198="Cancelled"),"",IF(O198="Not awarded",IF(U198<>"",U198-TODAY(),IF(X198="","",X198-TODAY())),IF(X198="","",X198-TODAY()))) | [14 empty] | IF(OR(F198="",AJ198=""),"",IF(COUNT(AI198:AI198)=0,"",AJ198-LOOKUP(2,1/(AI198:AI198<>""),AI198:AI198))) | IF(OR(F198="",AK198=""),"",IF(COUNT(AI198:AJ198)=0,"",AK198-LOOKUP(2,1/(AI198:AJ198<>""),AI198:AJ198))) | IF(OR(F198="",AL198=""),"",IF(COUNT(AI198:AK198)=0,"",AL198-LOOKUP(2,1/(AI198:AK198<>""),AI198:AK198))) | IF(OR(F198="",AM198=""),"",IF(COUNT(AI198:AL198)=0,"",AM198-LOOKUP(2,1/(AI198:AL198<>""),AI198:AL198))) | IF(OR(F198="",AN198=""),"",IF(COUNT(AI198:AM198)=0,"",AN198-LOOKUP(2,1/(AI198:AM198<>""),AI198:AM198))) | IF(OR(F198="",AO198=""),"",IF(COUNT(AI198:AN198)=0,"",AO198-LOOKUP(2,1/(AI198:AN198<>""),AI198:AN198))) | IF(OR(F198="",AP198=""),"",IF(COUNT(AI198:AO198)=0,"",AP198-LOOKUP(2,1/(AI198:AO198<>""),AI198:AO198))) | IF(OR(F198="",AQ198=""),"",IF(COUNT(AI198:AP198)=0,"",AQ198-LOOKUP(2,1/(AI198:AP198<>""),AI198:AP198))) | IF(OR(F198="",AR198=""),"",IF(COUNT(AI198:AQ198)=0,"",AR198-LOOKUP(2,1/(AI198:AQ198<>""),AI198:AQ198))) | IF(OR(F198="",AS198=""),"",IF(COUNT(AI198:AR198)=0,"",AS198-LOOKUP(2,1/(AI198:AR198<>""),AI198:AR198))) | IF(OR(F198="",AT198=""),"",IF(COUNT(AI198:AS198)=0,"",AT198-LOOKUP(2,1/(AI198:AS198<>""),AI198:AS198))) | IF(OR(F198="",AU198=""),"",IF(COUNT(AI198:AT198)=0,"",AU198-LOOKUP(2,1/(AI198:AT198<>""),AI198:AT198))) | IF(OR(F198="",AV198=""),"",IF(COUNT(AI198:AU198)=0,"",AV198-LOOKUP(2,1/(AI198:AU198<>""),AI198:AU198))) | IF(J198="","All_Provinces",IFERROR(VLOOKUP(J198,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K198="","All_Districts",IFERROR(VLOOKUP(K198,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F199="","",ROW()-3) | [18 empty] | IF(AQ199="","",AQ199) |  |  |  | IF(W199<>"",W199,IF(OR(T199="",V199=""),"",EDATE(T199,V199))) |  |  |  |  | IF(F199="","",IF(COUNT(AI199:AV199)=0,IF(AA199="","Not started",AA199),SUBSTITUTE(LOOKUP(2,1/(AI199:AV199<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F199="",COUNT(AI199:AV199)=0),"",TODAY()-LOOKUP(2,1/(AI199:AV199<>""),AI199:AV199)) | IF(OR(F199="",COUNT(AI199:AV199)<2),"",LOOKUP(2,1/(AI199:AV199<>""),AI199:AV199)-MIN(AI199:AV199)) | IF(OR(AD199="",AC199="Not started",AC199=""),"",IFERROR(AD199-IF(VLOOKUP(AC199,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC199,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F199="","",IF(OR(AA199="Cancelled",AC199="Cancelled"),"Cancelled",IF(OR(AC199="Completed / Handover",Y199<>"",Z199>=100),"Completed — on track",IF(O199="Not awarded",IF(U199="",IF(X199="","No planned date",IF(TODAY()>X199,"Behind — past planned date",IF(X199-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U199,"Behind — award date passed",IF(U199-TODAY()<=30,"At risk — close to off track","On track"))),IF(X199="","No planned date",IF(AND(TODAY()>X199,OR(Z199="",Z199<100)),"Behind — past end date",IF(AND(T199<>"",X199<>"",Z199<>"",(Z199<100),((TODAY()-T199)/MAX(X199-T199,1)*100)-Z199>15),"Behind — progress lag",IF(AND(X199-TODAY()<=30,X199-TODAY()>=0,OR(Z199="",Z199<90)),"At risk — close to off track","On track")))))))) | IF(OR(F199="",AC199="Completed / Handover",AC199="Cancelled"),"",IF(O199="Not awarded",IF(U199<>"",U199-TODAY(),IF(X199="","",X199-TODAY())),IF(X199="","",X199-TODAY()))) | [14 empty] | IF(OR(F199="",AJ199=""),"",IF(COUNT(AI199:AI199)=0,"",AJ199-LOOKUP(2,1/(AI199:AI199<>""),AI199:AI199))) | IF(OR(F199="",AK199=""),"",IF(COUNT(AI199:AJ199)=0,"",AK199-LOOKUP(2,1/(AI199:AJ199<>""),AI199:AJ199))) | IF(OR(F199="",AL199=""),"",IF(COUNT(AI199:AK199)=0,"",AL199-LOOKUP(2,1/(AI199:AK199<>""),AI199:AK199))) | IF(OR(F199="",AM199=""),"",IF(COUNT(AI199:AL199)=0,"",AM199-LOOKUP(2,1/(AI199:AL199<>""),AI199:AL199))) | IF(OR(F199="",AN199=""),"",IF(COUNT(AI199:AM199)=0,"",AN199-LOOKUP(2,1/(AI199:AM199<>""),AI199:AM199))) | IF(OR(F199="",AO199=""),"",IF(COUNT(AI199:AN199)=0,"",AO199-LOOKUP(2,1/(AI199:AN199<>""),AI199:AN199))) | IF(OR(F199="",AP199=""),"",IF(COUNT(AI199:AO199)=0,"",AP199-LOOKUP(2,1/(AI199:AO199<>""),AI199:AO199))) | IF(OR(F199="",AQ199=""),"",IF(COUNT(AI199:AP199)=0,"",AQ199-LOOKUP(2,1/(AI199:AP199<>""),AI199:AP199))) | IF(OR(F199="",AR199=""),"",IF(COUNT(AI199:AQ199)=0,"",AR199-LOOKUP(2,1/(AI199:AQ199<>""),AI199:AQ199))) | IF(OR(F199="",AS199=""),"",IF(COUNT(AI199:AR199)=0,"",AS199-LOOKUP(2,1/(AI199:AR199<>""),AI199:AR199))) | IF(OR(F199="",AT199=""),"",IF(COUNT(AI199:AS199)=0,"",AT199-LOOKUP(2,1/(AI199:AS199<>""),AI199:AS199))) | IF(OR(F199="",AU199=""),"",IF(COUNT(AI199:AT199)=0,"",AU199-LOOKUP(2,1/(AI199:AT199<>""),AI199:AT199))) | IF(OR(F199="",AV199=""),"",IF(COUNT(AI199:AU199)=0,"",AV199-LOOKUP(2,1/(AI199:AU199<>""),AI199:AU199))) | IF(J199="","All_Provinces",IFERROR(VLOOKUP(J199,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K199="","All_Districts",IFERROR(VLOOKUP(K199,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F200="","",ROW()-3) | [18 empty] | IF(AQ200="","",AQ200) |  |  |  | IF(W200<>"",W200,IF(OR(T200="",V200=""),"",EDATE(T200,V200))) |  |  |  |  | IF(F200="","",IF(COUNT(AI200:AV200)=0,IF(AA200="","Not started",AA200),SUBSTITUTE(LOOKUP(2,1/(AI200:AV200<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F200="",COUNT(AI200:AV200)=0),"",TODAY()-LOOKUP(2,1/(AI200:AV200<>""),AI200:AV200)) | IF(OR(F200="",COUNT(AI200:AV200)<2),"",LOOKUP(2,1/(AI200:AV200<>""),AI200:AV200)-MIN(AI200:AV200)) | IF(OR(AD200="",AC200="Not started",AC200=""),"",IFERROR(AD200-IF(VLOOKUP(AC200,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC200,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F200="","",IF(OR(AA200="Cancelled",AC200="Cancelled"),"Cancelled",IF(OR(AC200="Completed / Handover",Y200<>"",Z200>=100),"Completed — on track",IF(O200="Not awarded",IF(U200="",IF(X200="","No planned date",IF(TODAY()>X200,"Behind — past planned date",IF(X200-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U200,"Behind — award date passed",IF(U200-TODAY()<=30,"At risk — close to off track","On track"))),IF(X200="","No planned date",IF(AND(TODAY()>X200,OR(Z200="",Z200<100)),"Behind — past end date",IF(AND(T200<>"",X200<>"",Z200<>"",(Z200<100),((TODAY()-T200)/MAX(X200-T200,1)*100)-Z200>15),"Behind — progress lag",IF(AND(X200-TODAY()<=30,X200-TODAY()>=0,OR(Z200="",Z200<90)),"At risk — close to off track","On track")))))))) | IF(OR(F200="",AC200="Completed / Handover",AC200="Cancelled"),"",IF(O200="Not awarded",IF(U200<>"",U200-TODAY(),IF(X200="","",X200-TODAY())),IF(X200="","",X200-TODAY()))) | [14 empty] | IF(OR(F200="",AJ200=""),"",IF(COUNT(AI200:AI200)=0,"",AJ200-LOOKUP(2,1/(AI200:AI200<>""),AI200:AI200))) | IF(OR(F200="",AK200=""),"",IF(COUNT(AI200:AJ200)=0,"",AK200-LOOKUP(2,1/(AI200:AJ200<>""),AI200:AJ200))) | IF(OR(F200="",AL200=""),"",IF(COUNT(AI200:AK200)=0,"",AL200-LOOKUP(2,1/(AI200:AK200<>""),AI200:AK200))) | IF(OR(F200="",AM200=""),"",IF(COUNT(AI200:AL200)=0,"",AM200-LOOKUP(2,1/(AI200:AL200<>""),AI200:AL200))) | IF(OR(F200="",AN200=""),"",IF(COUNT(AI200:AM200)=0,"",AN200-LOOKUP(2,1/(AI200:AM200<>""),AI200:AM200))) | IF(OR(F200="",AO200=""),"",IF(COUNT(AI200:AN200)=0,"",AO200-LOOKUP(2,1/(AI200:AN200<>""),AI200:AN200))) | IF(OR(F200="",AP200=""),"",IF(COUNT(AI200:AO200)=0,"",AP200-LOOKUP(2,1/(AI200:AO200<>""),AI200:AO200))) | IF(OR(F200="",AQ200=""),"",IF(COUNT(AI200:AP200)=0,"",AQ200-LOOKUP(2,1/(AI200:AP200<>""),AI200:AP200))) | IF(OR(F200="",AR200=""),"",IF(COUNT(AI200:AQ200)=0,"",AR200-LOOKUP(2,1/(AI200:AQ200<>""),AI200:AQ200))) | IF(OR(F200="",AS200=""),"",IF(COUNT(AI200:AR200)=0,"",AS200-LOOKUP(2,1/(AI200:AR200<>""),AI200:AR200))) | IF(OR(F200="",AT200=""),"",IF(COUNT(AI200:AS200)=0,"",AT200-LOOKUP(2,1/(AI200:AS200<>""),AI200:AS200))) | IF(OR(F200="",AU200=""),"",IF(COUNT(AI200:AT200)=0,"",AU200-LOOKUP(2,1/(AI200:AT200<>""),AI200:AT200))) | IF(OR(F200="",AV200=""),"",IF(COUNT(AI200:AU200)=0,"",AV200-LOOKUP(2,1/(AI200:AU200<>""),AI200:AU200))) | IF(J200="","All_Provinces",IFERROR(VLOOKUP(J200,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K200="","All_Districts",IFERROR(VLOOKUP(K200,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F201="","",ROW()-3) | [18 empty] | IF(AQ201="","",AQ201) |  |  |  | IF(W201<>"",W201,IF(OR(T201="",V201=""),"",EDATE(T201,V201))) |  |  |  |  | IF(F201="","",IF(COUNT(AI201:AV201)=0,IF(AA201="","Not started",AA201),SUBSTITUTE(LOOKUP(2,1/(AI201:AV201<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F201="",COUNT(AI201:AV201)=0),"",TODAY()-LOOKUP(2,1/(AI201:AV201<>""),AI201:AV201)) | IF(OR(F201="",COUNT(AI201:AV201)<2),"",LOOKUP(2,1/(AI201:AV201<>""),AI201:AV201)-MIN(AI201:AV201)) | IF(OR(AD201="",AC201="Not started",AC201=""),"",IFERROR(AD201-IF(VLOOKUP(AC201,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC201,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F201="","",IF(OR(AA201="Cancelled",AC201="Cancelled"),"Cancelled",IF(OR(AC201="Completed / Handover",Y201<>"",Z201>=100),"Completed — on track",IF(O201="Not awarded",IF(U201="",IF(X201="","No planned date",IF(TODAY()>X201,"Behind — past planned date",IF(X201-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U201,"Behind — award date passed",IF(U201-TODAY()<=30,"At risk — close to off track","On track"))),IF(X201="","No planned date",IF(AND(TODAY()>X201,OR(Z201="",Z201<100)),"Behind — past end date",IF(AND(T201<>"",X201<>"",Z201<>"",(Z201<100),((TODAY()-T201)/MAX(X201-T201,1)*100)-Z201>15),"Behind — progress lag",IF(AND(X201-TODAY()<=30,X201-TODAY()>=0,OR(Z201="",Z201<90)),"At risk — close to off track","On track")))))))) | IF(OR(F201="",AC201="Completed / Handover",AC201="Cancelled"),"",IF(O201="Not awarded",IF(U201<>"",U201-TODAY(),IF(X201="","",X201-TODAY())),IF(X201="","",X201-TODAY()))) | [14 empty] | IF(OR(F201="",AJ201=""),"",IF(COUNT(AI201:AI201)=0,"",AJ201-LOOKUP(2,1/(AI201:AI201<>""),AI201:AI201))) | IF(OR(F201="",AK201=""),"",IF(COUNT(AI201:AJ201)=0,"",AK201-LOOKUP(2,1/(AI201:AJ201<>""),AI201:AJ201))) | IF(OR(F201="",AL201=""),"",IF(COUNT(AI201:AK201)=0,"",AL201-LOOKUP(2,1/(AI201:AK201<>""),AI201:AK201))) | IF(OR(F201="",AM201=""),"",IF(COUNT(AI201:AL201)=0,"",AM201-LOOKUP(2,1/(AI201:AL201<>""),AI201:AL201))) | IF(OR(F201="",AN201=""),"",IF(COUNT(AI201:AM201)=0,"",AN201-LOOKUP(2,1/(AI201:AM201<>""),AI201:AM201))) | IF(OR(F201="",AO201=""),"",IF(COUNT(AI201:AN201)=0,"",AO201-LOOKUP(2,1/(AI201:AN201<>""),AI201:AN201))) | IF(OR(F201="",AP201=""),"",IF(COUNT(AI201:AO201)=0,"",AP201-LOOKUP(2,1/(AI201:AO201<>""),AI201:AO201))) | IF(OR(F201="",AQ201=""),"",IF(COUNT(AI201:AP201)=0,"",AQ201-LOOKUP(2,1/(AI201:AP201<>""),AI201:AP201))) | IF(OR(F201="",AR201=""),"",IF(COUNT(AI201:AQ201)=0,"",AR201-LOOKUP(2,1/(AI201:AQ201<>""),AI201:AQ201))) | IF(OR(F201="",AS201=""),"",IF(COUNT(AI201:AR201)=0,"",AS201-LOOKUP(2,1/(AI201:AR201<>""),AI201:AR201))) | IF(OR(F201="",AT201=""),"",IF(COUNT(AI201:AS201)=0,"",AT201-LOOKUP(2,1/(AI201:AS201<>""),AI201:AS201))) | IF(OR(F201="",AU201=""),"",IF(COUNT(AI201:AT201)=0,"",AU201-LOOKUP(2,1/(AI201:AT201<>""),AI201:AT201))) | IF(OR(F201="",AV201=""),"",IF(COUNT(AI201:AU201)=0,"",AV201-LOOKUP(2,1/(AI201:AU201<>""),AI201:AU201))) | IF(J201="","All_Provinces",IFERROR(VLOOKUP(J201,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K201="","All_Districts",IFERROR(VLOOKUP(K201,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F202="","",ROW()-3) | [18 empty] | IF(AQ202="","",AQ202) |  |  |  | IF(W202<>"",W202,IF(OR(T202="",V202=""),"",EDATE(T202,V202))) |  |  |  |  | IF(F202="","",IF(COUNT(AI202:AV202)=0,IF(AA202="","Not started",AA202),SUBSTITUTE(LOOKUP(2,1/(AI202:AV202<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F202="",COUNT(AI202:AV202)=0),"",TODAY()-LOOKUP(2,1/(AI202:AV202<>""),AI202:AV202)) | IF(OR(F202="",COUNT(AI202:AV202)<2),"",LOOKUP(2,1/(AI202:AV202<>""),AI202:AV202)-MIN(AI202:AV202)) | IF(OR(AD202="",AC202="Not started",AC202=""),"",IFERROR(AD202-IF(VLOOKUP(AC202,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC202,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F202="","",IF(OR(AA202="Cancelled",AC202="Cancelled"),"Cancelled",IF(OR(AC202="Completed / Handover",Y202<>"",Z202>=100),"Completed — on track",IF(O202="Not awarded",IF(U202="",IF(X202="","No planned date",IF(TODAY()>X202,"Behind — past planned date",IF(X202-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U202,"Behind — award date passed",IF(U202-TODAY()<=30,"At risk — close to off track","On track"))),IF(X202="","No planned date",IF(AND(TODAY()>X202,OR(Z202="",Z202<100)),"Behind — past end date",IF(AND(T202<>"",X202<>"",Z202<>"",(Z202<100),((TODAY()-T202)/MAX(X202-T202,1)*100)-Z202>15),"Behind — progress lag",IF(AND(X202-TODAY()<=30,X202-TODAY()>=0,OR(Z202="",Z202<90)),"At risk — close to off track","On track")))))))) | IF(OR(F202="",AC202="Completed / Handover",AC202="Cancelled"),"",IF(O202="Not awarded",IF(U202<>"",U202-TODAY(),IF(X202="","",X202-TODAY())),IF(X202="","",X202-TODAY()))) | [14 empty] | IF(OR(F202="",AJ202=""),"",IF(COUNT(AI202:AI202)=0,"",AJ202-LOOKUP(2,1/(AI202:AI202<>""),AI202:AI202))) | IF(OR(F202="",AK202=""),"",IF(COUNT(AI202:AJ202)=0,"",AK202-LOOKUP(2,1/(AI202:AJ202<>""),AI202:AJ202))) | IF(OR(F202="",AL202=""),"",IF(COUNT(AI202:AK202)=0,"",AL202-LOOKUP(2,1/(AI202:AK202<>""),AI202:AK202))) | IF(OR(F202="",AM202=""),"",IF(COUNT(AI202:AL202)=0,"",AM202-LOOKUP(2,1/(AI202:AL202<>""),AI202:AL202))) | IF(OR(F202="",AN202=""),"",IF(COUNT(AI202:AM202)=0,"",AN202-LOOKUP(2,1/(AI202:AM202<>""),AI202:AM202))) | IF(OR(F202="",AO202=""),"",IF(COUNT(AI202:AN202)=0,"",AO202-LOOKUP(2,1/(AI202:AN202<>""),AI202:AN202))) | IF(OR(F202="",AP202=""),"",IF(COUNT(AI202:AO202)=0,"",AP202-LOOKUP(2,1/(AI202:AO202<>""),AI202:AO202))) | IF(OR(F202="",AQ202=""),"",IF(COUNT(AI202:AP202)=0,"",AQ202-LOOKUP(2,1/(AI202:AP202<>""),AI202:AP202))) | IF(OR(F202="",AR202=""),"",IF(COUNT(AI202:AQ202)=0,"",AR202-LOOKUP(2,1/(AI202:AQ202<>""),AI202:AQ202))) | IF(OR(F202="",AS202=""),"",IF(COUNT(AI202:AR202)=0,"",AS202-LOOKUP(2,1/(AI202:AR202<>""),AI202:AR202))) | IF(OR(F202="",AT202=""),"",IF(COUNT(AI202:AS202)=0,"",AT202-LOOKUP(2,1/(AI202:AS202<>""),AI202:AS202))) | IF(OR(F202="",AU202=""),"",IF(COUNT(AI202:AT202)=0,"",AU202-LOOKUP(2,1/(AI202:AT202<>""),AI202:AT202))) | IF(OR(F202="",AV202=""),"",IF(COUNT(AI202:AU202)=0,"",AV202-LOOKUP(2,1/(AI202:AU202<>""),AI202:AU202))) | IF(J202="","All_Provinces",IFERROR(VLOOKUP(J202,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K202="","All_Districts",IFERROR(VLOOKUP(K202,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F203="","",ROW()-3) | [18 empty] | IF(AQ203="","",AQ203) |  |  |  | IF(W203<>"",W203,IF(OR(T203="",V203=""),"",EDATE(T203,V203))) |  |  |  |  | IF(F203="","",IF(COUNT(AI203:AV203)=0,IF(AA203="","Not started",AA203),SUBSTITUTE(LOOKUP(2,1/(AI203:AV203<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F203="",COUNT(AI203:AV203)=0),"",TODAY()-LOOKUP(2,1/(AI203:AV203<>""),AI203:AV203)) | IF(OR(F203="",COUNT(AI203:AV203)<2),"",LOOKUP(2,1/(AI203:AV203<>""),AI203:AV203)-MIN(AI203:AV203)) | IF(OR(AD203="",AC203="Not started",AC203=""),"",IFERROR(AD203-IF(VLOOKUP(AC203,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC203,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F203="","",IF(OR(AA203="Cancelled",AC203="Cancelled"),"Cancelled",IF(OR(AC203="Completed / Handover",Y203<>"",Z203>=100),"Completed — on track",IF(O203="Not awarded",IF(U203="",IF(X203="","No planned date",IF(TODAY()>X203,"Behind — past planned date",IF(X203-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U203,"Behind — award date passed",IF(U203-TODAY()<=30,"At risk — close to off track","On track"))),IF(X203="","No planned date",IF(AND(TODAY()>X203,OR(Z203="",Z203<100)),"Behind — past end date",IF(AND(T203<>"",X203<>"",Z203<>"",(Z203<100),((TODAY()-T203)/MAX(X203-T203,1)*100)-Z203>15),"Behind — progress lag",IF(AND(X203-TODAY()<=30,X203-TODAY()>=0,OR(Z203="",Z203<90)),"At risk — close to off track","On track")))))))) | IF(OR(F203="",AC203="Completed / Handover",AC203="Cancelled"),"",IF(O203="Not awarded",IF(U203<>"",U203-TODAY(),IF(X203="","",X203-TODAY())),IF(X203="","",X203-TODAY()))) | [14 empty] | IF(OR(F203="",AJ203=""),"",IF(COUNT(AI203:AI203)=0,"",AJ203-LOOKUP(2,1/(AI203:AI203<>""),AI203:AI203))) | IF(OR(F203="",AK203=""),"",IF(COUNT(AI203:AJ203)=0,"",AK203-LOOKUP(2,1/(AI203:AJ203<>""),AI203:AJ203))) | IF(OR(F203="",AL203=""),"",IF(COUNT(AI203:AK203)=0,"",AL203-LOOKUP(2,1/(AI203:AK203<>""),AI203:AK203))) | IF(OR(F203="",AM203=""),"",IF(COUNT(AI203:AL203)=0,"",AM203-LOOKUP(2,1/(AI203:AL203<>""),AI203:AL203))) | IF(OR(F203="",AN203=""),"",IF(COUNT(AI203:AM203)=0,"",AN203-LOOKUP(2,1/(AI203:AM203<>""),AI203:AM203))) | IF(OR(F203="",AO203=""),"",IF(COUNT(AI203:AN203)=0,"",AO203-LOOKUP(2,1/(AI203:AN203<>""),AI203:AN203))) | IF(OR(F203="",AP203=""),"",IF(COUNT(AI203:AO203)=0,"",AP203-LOOKUP(2,1/(AI203:AO203<>""),AI203:AO203))) | IF(OR(F203="",AQ203=""),"",IF(COUNT(AI203:AP203)=0,"",AQ203-LOOKUP(2,1/(AI203:AP203<>""),AI203:AP203))) | IF(OR(F203="",AR203=""),"",IF(COUNT(AI203:AQ203)=0,"",AR203-LOOKUP(2,1/(AI203:AQ203<>""),AI203:AQ203))) | IF(OR(F203="",AS203=""),"",IF(COUNT(AI203:AR203)=0,"",AS203-LOOKUP(2,1/(AI203:AR203<>""),AI203:AR203))) | IF(OR(F203="",AT203=""),"",IF(COUNT(AI203:AS203)=0,"",AT203-LOOKUP(2,1/(AI203:AS203<>""),AI203:AS203))) | IF(OR(F203="",AU203=""),"",IF(COUNT(AI203:AT203)=0,"",AU203-LOOKUP(2,1/(AI203:AT203<>""),AI203:AT203))) | IF(OR(F203="",AV203=""),"",IF(COUNT(AI203:AU203)=0,"",AV203-LOOKUP(2,1/(AI203:AU203<>""),AI203:AU203))) | IF(J203="","All_Provinces",IFERROR(VLOOKUP(J203,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K203="","All_Districts",IFERROR(VLOOKUP(K203,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F204="","",ROW()-3) | [18 empty] | IF(AQ204="","",AQ204) |  |  |  | IF(W204<>"",W204,IF(OR(T204="",V204=""),"",EDATE(T204,V204))) |  |  |  |  | IF(F204="","",IF(COUNT(AI204:AV204)=0,IF(AA204="","Not started",AA204),SUBSTITUTE(LOOKUP(2,1/(AI204:AV204<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F204="",COUNT(AI204:AV204)=0),"",TODAY()-LOOKUP(2,1/(AI204:AV204<>""),AI204:AV204)) | IF(OR(F204="",COUNT(AI204:AV204)<2),"",LOOKUP(2,1/(AI204:AV204<>""),AI204:AV204)-MIN(AI204:AV204)) | IF(OR(AD204="",AC204="Not started",AC204=""),"",IFERROR(AD204-IF(VLOOKUP(AC204,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC204,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F204="","",IF(OR(AA204="Cancelled",AC204="Cancelled"),"Cancelled",IF(OR(AC204="Completed / Handover",Y204<>"",Z204>=100),"Completed — on track",IF(O204="Not awarded",IF(U204="",IF(X204="","No planned date",IF(TODAY()>X204,"Behind — past planned date",IF(X204-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U204,"Behind — award date passed",IF(U204-TODAY()<=30,"At risk — close to off track","On track"))),IF(X204="","No planned date",IF(AND(TODAY()>X204,OR(Z204="",Z204<100)),"Behind — past end date",IF(AND(T204<>"",X204<>"",Z204<>"",(Z204<100),((TODAY()-T204)/MAX(X204-T204,1)*100)-Z204>15),"Behind — progress lag",IF(AND(X204-TODAY()<=30,X204-TODAY()>=0,OR(Z204="",Z204<90)),"At risk — close to off track","On track")))))))) | IF(OR(F204="",AC204="Completed / Handover",AC204="Cancelled"),"",IF(O204="Not awarded",IF(U204<>"",U204-TODAY(),IF(X204="","",X204-TODAY())),IF(X204="","",X204-TODAY()))) | [14 empty] | IF(OR(F204="",AJ204=""),"",IF(COUNT(AI204:AI204)=0,"",AJ204-LOOKUP(2,1/(AI204:AI204<>""),AI204:AI204))) | IF(OR(F204="",AK204=""),"",IF(COUNT(AI204:AJ204)=0,"",AK204-LOOKUP(2,1/(AI204:AJ204<>""),AI204:AJ204))) | IF(OR(F204="",AL204=""),"",IF(COUNT(AI204:AK204)=0,"",AL204-LOOKUP(2,1/(AI204:AK204<>""),AI204:AK204))) | IF(OR(F204="",AM204=""),"",IF(COUNT(AI204:AL204)=0,"",AM204-LOOKUP(2,1/(AI204:AL204<>""),AI204:AL204))) | IF(OR(F204="",AN204=""),"",IF(COUNT(AI204:AM204)=0,"",AN204-LOOKUP(2,1/(AI204:AM204<>""),AI204:AM204))) | IF(OR(F204="",AO204=""),"",IF(COUNT(AI204:AN204)=0,"",AO204-LOOKUP(2,1/(AI204:AN204<>""),AI204:AN204))) | IF(OR(F204="",AP204=""),"",IF(COUNT(AI204:AO204)=0,"",AP204-LOOKUP(2,1/(AI204:AO204<>""),AI204:AO204))) | IF(OR(F204="",AQ204=""),"",IF(COUNT(AI204:AP204)=0,"",AQ204-LOOKUP(2,1/(AI204:AP204<>""),AI204:AP204))) | IF(OR(F204="",AR204=""),"",IF(COUNT(AI204:AQ204)=0,"",AR204-LOOKUP(2,1/(AI204:AQ204<>""),AI204:AQ204))) | IF(OR(F204="",AS204=""),"",IF(COUNT(AI204:AR204)=0,"",AS204-LOOKUP(2,1/(AI204:AR204<>""),AI204:AR204))) | IF(OR(F204="",AT204=""),"",IF(COUNT(AI204:AS204)=0,"",AT204-LOOKUP(2,1/(AI204:AS204<>""),AI204:AS204))) | IF(OR(F204="",AU204=""),"",IF(COUNT(AI204:AT204)=0,"",AU204-LOOKUP(2,1/(AI204:AT204<>""),AI204:AT204))) | IF(OR(F204="",AV204=""),"",IF(COUNT(AI204:AU204)=0,"",AV204-LOOKUP(2,1/(AI204:AU204<>""),AI204:AU204))) | IF(J204="","All_Provinces",IFERROR(VLOOKUP(J204,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K204="","All_Districts",IFERROR(VLOOKUP(K204,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F205="","",ROW()-3) | [18 empty] | IF(AQ205="","",AQ205) |  |  |  | IF(W205<>"",W205,IF(OR(T205="",V205=""),"",EDATE(T205,V205))) |  |  |  |  | IF(F205="","",IF(COUNT(AI205:AV205)=0,IF(AA205="","Not started",AA205),SUBSTITUTE(LOOKUP(2,1/(AI205:AV205<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F205="",COUNT(AI205:AV205)=0),"",TODAY()-LOOKUP(2,1/(AI205:AV205<>""),AI205:AV205)) | IF(OR(F205="",COUNT(AI205:AV205)<2),"",LOOKUP(2,1/(AI205:AV205<>""),AI205:AV205)-MIN(AI205:AV205)) | IF(OR(AD205="",AC205="Not started",AC205=""),"",IFERROR(AD205-IF(VLOOKUP(AC205,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC205,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F205="","",IF(OR(AA205="Cancelled",AC205="Cancelled"),"Cancelled",IF(OR(AC205="Completed / Handover",Y205<>"",Z205>=100),"Completed — on track",IF(O205="Not awarded",IF(U205="",IF(X205="","No planned date",IF(TODAY()>X205,"Behind — past planned date",IF(X205-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U205,"Behind — award date passed",IF(U205-TODAY()<=30,"At risk — close to off track","On track"))),IF(X205="","No planned date",IF(AND(TODAY()>X205,OR(Z205="",Z205<100)),"Behind — past end date",IF(AND(T205<>"",X205<>"",Z205<>"",(Z205<100),((TODAY()-T205)/MAX(X205-T205,1)*100)-Z205>15),"Behind — progress lag",IF(AND(X205-TODAY()<=30,X205-TODAY()>=0,OR(Z205="",Z205<90)),"At risk — close to off track","On track")))))))) | IF(OR(F205="",AC205="Completed / Handover",AC205="Cancelled"),"",IF(O205="Not awarded",IF(U205<>"",U205-TODAY(),IF(X205="","",X205-TODAY())),IF(X205="","",X205-TODAY()))) | [14 empty] | IF(OR(F205="",AJ205=""),"",IF(COUNT(AI205:AI205)=0,"",AJ205-LOOKUP(2,1/(AI205:AI205<>""),AI205:AI205))) | IF(OR(F205="",AK205=""),"",IF(COUNT(AI205:AJ205)=0,"",AK205-LOOKUP(2,1/(AI205:AJ205<>""),AI205:AJ205))) | IF(OR(F205="",AL205=""),"",IF(COUNT(AI205:AK205)=0,"",AL205-LOOKUP(2,1/(AI205:AK205<>""),AI205:AK205))) | IF(OR(F205="",AM205=""),"",IF(COUNT(AI205:AL205)=0,"",AM205-LOOKUP(2,1/(AI205:AL205<>""),AI205:AL205))) | IF(OR(F205="",AN205=""),"",IF(COUNT(AI205:AM205)=0,"",AN205-LOOKUP(2,1/(AI205:AM205<>""),AI205:AM205))) | IF(OR(F205="",AO205=""),"",IF(COUNT(AI205:AN205)=0,"",AO205-LOOKUP(2,1/(AI205:AN205<>""),AI205:AN205))) | IF(OR(F205="",AP205=""),"",IF(COUNT(AI205:AO205)=0,"",AP205-LOOKUP(2,1/(AI205:AO205<>""),AI205:AO205))) | IF(OR(F205="",AQ205=""),"",IF(COUNT(AI205:AP205)=0,"",AQ205-LOOKUP(2,1/(AI205:AP205<>""),AI205:AP205))) | IF(OR(F205="",AR205=""),"",IF(COUNT(AI205:AQ205)=0,"",AR205-LOOKUP(2,1/(AI205:AQ205<>""),AI205:AQ205))) | IF(OR(F205="",AS205=""),"",IF(COUNT(AI205:AR205)=0,"",AS205-LOOKUP(2,1/(AI205:AR205<>""),AI205:AR205))) | IF(OR(F205="",AT205=""),"",IF(COUNT(AI205:AS205)=0,"",AT205-LOOKUP(2,1/(AI205:AS205<>""),AI205:AS205))) | IF(OR(F205="",AU205=""),"",IF(COUNT(AI205:AT205)=0,"",AU205-LOOKUP(2,1/(AI205:AT205<>""),AI205:AT205))) | IF(OR(F205="",AV205=""),"",IF(COUNT(AI205:AU205)=0,"",AV205-LOOKUP(2,1/(AI205:AU205<>""),AI205:AU205))) | IF(J205="","All_Provinces",IFERROR(VLOOKUP(J205,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K205="","All_Districts",IFERROR(VLOOKUP(K205,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F206="","",ROW()-3) | [18 empty] | IF(AQ206="","",AQ206) |  |  |  | IF(W206<>"",W206,IF(OR(T206="",V206=""),"",EDATE(T206,V206))) |  |  |  |  | IF(F206="","",IF(COUNT(AI206:AV206)=0,IF(AA206="","Not started",AA206),SUBSTITUTE(LOOKUP(2,1/(AI206:AV206<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F206="",COUNT(AI206:AV206)=0),"",TODAY()-LOOKUP(2,1/(AI206:AV206<>""),AI206:AV206)) | IF(OR(F206="",COUNT(AI206:AV206)<2),"",LOOKUP(2,1/(AI206:AV206<>""),AI206:AV206)-MIN(AI206:AV206)) | IF(OR(AD206="",AC206="Not started",AC206=""),"",IFERROR(AD206-IF(VLOOKUP(AC206,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC206,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F206="","",IF(OR(AA206="Cancelled",AC206="Cancelled"),"Cancelled",IF(OR(AC206="Completed / Handover",Y206<>"",Z206>=100),"Completed — on track",IF(O206="Not awarded",IF(U206="",IF(X206="","No planned date",IF(TODAY()>X206,"Behind — past planned date",IF(X206-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U206,"Behind — award date passed",IF(U206-TODAY()<=30,"At risk — close to off track","On track"))),IF(X206="","No planned date",IF(AND(TODAY()>X206,OR(Z206="",Z206<100)),"Behind — past end date",IF(AND(T206<>"",X206<>"",Z206<>"",(Z206<100),((TODAY()-T206)/MAX(X206-T206,1)*100)-Z206>15),"Behind — progress lag",IF(AND(X206-TODAY()<=30,X206-TODAY()>=0,OR(Z206="",Z206<90)),"At risk — close to off track","On track")))))))) | IF(OR(F206="",AC206="Completed / Handover",AC206="Cancelled"),"",IF(O206="Not awarded",IF(U206<>"",U206-TODAY(),IF(X206="","",X206-TODAY())),IF(X206="","",X206-TODAY()))) | [14 empty] | IF(OR(F206="",AJ206=""),"",IF(COUNT(AI206:AI206)=0,"",AJ206-LOOKUP(2,1/(AI206:AI206<>""),AI206:AI206))) | IF(OR(F206="",AK206=""),"",IF(COUNT(AI206:AJ206)=0,"",AK206-LOOKUP(2,1/(AI206:AJ206<>""),AI206:AJ206))) | IF(OR(F206="",AL206=""),"",IF(COUNT(AI206:AK206)=0,"",AL206-LOOKUP(2,1/(AI206:AK206<>""),AI206:AK206))) | IF(OR(F206="",AM206=""),"",IF(COUNT(AI206:AL206)=0,"",AM206-LOOKUP(2,1/(AI206:AL206<>""),AI206:AL206))) | IF(OR(F206="",AN206=""),"",IF(COUNT(AI206:AM206)=0,"",AN206-LOOKUP(2,1/(AI206:AM206<>""),AI206:AM206))) | IF(OR(F206="",AO206=""),"",IF(COUNT(AI206:AN206)=0,"",AO206-LOOKUP(2,1/(AI206:AN206<>""),AI206:AN206))) | IF(OR(F206="",AP206=""),"",IF(COUNT(AI206:AO206)=0,"",AP206-LOOKUP(2,1/(AI206:AO206<>""),AI206:AO206))) | IF(OR(F206="",AQ206=""),"",IF(COUNT(AI206:AP206)=0,"",AQ206-LOOKUP(2,1/(AI206:AP206<>""),AI206:AP206))) | IF(OR(F206="",AR206=""),"",IF(COUNT(AI206:AQ206)=0,"",AR206-LOOKUP(2,1/(AI206:AQ206<>""),AI206:AQ206))) | IF(OR(F206="",AS206=""),"",IF(COUNT(AI206:AR206)=0,"",AS206-LOOKUP(2,1/(AI206:AR206<>""),AI206:AR206))) | IF(OR(F206="",AT206=""),"",IF(COUNT(AI206:AS206)=0,"",AT206-LOOKUP(2,1/(AI206:AS206<>""),AI206:AS206))) | IF(OR(F206="",AU206=""),"",IF(COUNT(AI206:AT206)=0,"",AU206-LOOKUP(2,1/(AI206:AT206<>""),AI206:AT206))) | IF(OR(F206="",AV206=""),"",IF(COUNT(AI206:AU206)=0,"",AV206-LOOKUP(2,1/(AI206:AU206<>""),AI206:AU206))) | IF(J206="","All_Provinces",IFERROR(VLOOKUP(J206,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K206="","All_Districts",IFERROR(VLOOKUP(K206,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F207="","",ROW()-3) | [18 empty] | IF(AQ207="","",AQ207) |  |  |  | IF(W207<>"",W207,IF(OR(T207="",V207=""),"",EDATE(T207,V207))) |  |  |  |  | IF(F207="","",IF(COUNT(AI207:AV207)=0,IF(AA207="","Not started",AA207),SUBSTITUTE(LOOKUP(2,1/(AI207:AV207<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F207="",COUNT(AI207:AV207)=0),"",TODAY()-LOOKUP(2,1/(AI207:AV207<>""),AI207:AV207)) | IF(OR(F207="",COUNT(AI207:AV207)<2),"",LOOKUP(2,1/(AI207:AV207<>""),AI207:AV207)-MIN(AI207:AV207)) | IF(OR(AD207="",AC207="Not started",AC207=""),"",IFERROR(AD207-IF(VLOOKUP(AC207,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC207,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F207="","",IF(OR(AA207="Cancelled",AC207="Cancelled"),"Cancelled",IF(OR(AC207="Completed / Handover",Y207<>"",Z207>=100),"Completed — on track",IF(O207="Not awarded",IF(U207="",IF(X207="","No planned date",IF(TODAY()>X207,"Behind — past planned date",IF(X207-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U207,"Behind — award date passed",IF(U207-TODAY()<=30,"At risk — close to off track","On track"))),IF(X207="","No planned date",IF(AND(TODAY()>X207,OR(Z207="",Z207<100)),"Behind — past end date",IF(AND(T207<>"",X207<>"",Z207<>"",(Z207<100),((TODAY()-T207)/MAX(X207-T207,1)*100)-Z207>15),"Behind — progress lag",IF(AND(X207-TODAY()<=30,X207-TODAY()>=0,OR(Z207="",Z207<90)),"At risk — close to off track","On track")))))))) | IF(OR(F207="",AC207="Completed / Handover",AC207="Cancelled"),"",IF(O207="Not awarded",IF(U207<>"",U207-TODAY(),IF(X207="","",X207-TODAY())),IF(X207="","",X207-TODAY()))) | [14 empty] | IF(OR(F207="",AJ207=""),"",IF(COUNT(AI207:AI207)=0,"",AJ207-LOOKUP(2,1/(AI207:AI207<>""),AI207:AI207))) | IF(OR(F207="",AK207=""),"",IF(COUNT(AI207:AJ207)=0,"",AK207-LOOKUP(2,1/(AI207:AJ207<>""),AI207:AJ207))) | IF(OR(F207="",AL207=""),"",IF(COUNT(AI207:AK207)=0,"",AL207-LOOKUP(2,1/(AI207:AK207<>""),AI207:AK207))) | IF(OR(F207="",AM207=""),"",IF(COUNT(AI207:AL207)=0,"",AM207-LOOKUP(2,1/(AI207:AL207<>""),AI207:AL207))) | IF(OR(F207="",AN207=""),"",IF(COUNT(AI207:AM207)=0,"",AN207-LOOKUP(2,1/(AI207:AM207<>""),AI207:AM207))) | IF(OR(F207="",AO207=""),"",IF(COUNT(AI207:AN207)=0,"",AO207-LOOKUP(2,1/(AI207:AN207<>""),AI207:AN207))) | IF(OR(F207="",AP207=""),"",IF(COUNT(AI207:AO207)=0,"",AP207-LOOKUP(2,1/(AI207:AO207<>""),AI207:AO207))) | IF(OR(F207="",AQ207=""),"",IF(COUNT(AI207:AP207)=0,"",AQ207-LOOKUP(2,1/(AI207:AP207<>""),AI207:AP207))) | IF(OR(F207="",AR207=""),"",IF(COUNT(AI207:AQ207)=0,"",AR207-LOOKUP(2,1/(AI207:AQ207<>""),AI207:AQ207))) | IF(OR(F207="",AS207=""),"",IF(COUNT(AI207:AR207)=0,"",AS207-LOOKUP(2,1/(AI207:AR207<>""),AI207:AR207))) | IF(OR(F207="",AT207=""),"",IF(COUNT(AI207:AS207)=0,"",AT207-LOOKUP(2,1/(AI207:AS207<>""),AI207:AS207))) | IF(OR(F207="",AU207=""),"",IF(COUNT(AI207:AT207)=0,"",AU207-LOOKUP(2,1/(AI207:AT207<>""),AI207:AT207))) | IF(OR(F207="",AV207=""),"",IF(COUNT(AI207:AU207)=0,"",AV207-LOOKUP(2,1/(AI207:AU207<>""),AI207:AU207))) | IF(J207="","All_Provinces",IFERROR(VLOOKUP(J207,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K207="","All_Districts",IFERROR(VLOOKUP(K207,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F208="","",ROW()-3) | [18 empty] | IF(AQ208="","",AQ208) |  |  |  | IF(W208<>"",W208,IF(OR(T208="",V208=""),"",EDATE(T208,V208))) |  |  |  |  | IF(F208="","",IF(COUNT(AI208:AV208)=0,IF(AA208="","Not started",AA208),SUBSTITUTE(LOOKUP(2,1/(AI208:AV208<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F208="",COUNT(AI208:AV208)=0),"",TODAY()-LOOKUP(2,1/(AI208:AV208<>""),AI208:AV208)) | IF(OR(F208="",COUNT(AI208:AV208)<2),"",LOOKUP(2,1/(AI208:AV208<>""),AI208:AV208)-MIN(AI208:AV208)) | IF(OR(AD208="",AC208="Not started",AC208=""),"",IFERROR(AD208-IF(VLOOKUP(AC208,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC208,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F208="","",IF(OR(AA208="Cancelled",AC208="Cancelled"),"Cancelled",IF(OR(AC208="Completed / Handover",Y208<>"",Z208>=100),"Completed — on track",IF(O208="Not awarded",IF(U208="",IF(X208="","No planned date",IF(TODAY()>X208,"Behind — past planned date",IF(X208-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U208,"Behind — award date passed",IF(U208-TODAY()<=30,"At risk — close to off track","On track"))),IF(X208="","No planned date",IF(AND(TODAY()>X208,OR(Z208="",Z208<100)),"Behind — past end date",IF(AND(T208<>"",X208<>"",Z208<>"",(Z208<100),((TODAY()-T208)/MAX(X208-T208,1)*100)-Z208>15),"Behind — progress lag",IF(AND(X208-TODAY()<=30,X208-TODAY()>=0,OR(Z208="",Z208<90)),"At risk — close to off track","On track")))))))) | IF(OR(F208="",AC208="Completed / Handover",AC208="Cancelled"),"",IF(O208="Not awarded",IF(U208<>"",U208-TODAY(),IF(X208="","",X208-TODAY())),IF(X208="","",X208-TODAY()))) | [14 empty] | IF(OR(F208="",AJ208=""),"",IF(COUNT(AI208:AI208)=0,"",AJ208-LOOKUP(2,1/(AI208:AI208<>""),AI208:AI208))) | IF(OR(F208="",AK208=""),"",IF(COUNT(AI208:AJ208)=0,"",AK208-LOOKUP(2,1/(AI208:AJ208<>""),AI208:AJ208))) | IF(OR(F208="",AL208=""),"",IF(COUNT(AI208:AK208)=0,"",AL208-LOOKUP(2,1/(AI208:AK208<>""),AI208:AK208))) | IF(OR(F208="",AM208=""),"",IF(COUNT(AI208:AL208)=0,"",AM208-LOOKUP(2,1/(AI208:AL208<>""),AI208:AL208))) | IF(OR(F208="",AN208=""),"",IF(COUNT(AI208:AM208)=0,"",AN208-LOOKUP(2,1/(AI208:AM208<>""),AI208:AM208))) | IF(OR(F208="",AO208=""),"",IF(COUNT(AI208:AN208)=0,"",AO208-LOOKUP(2,1/(AI208:AN208<>""),AI208:AN208))) | IF(OR(F208="",AP208=""),"",IF(COUNT(AI208:AO208)=0,"",AP208-LOOKUP(2,1/(AI208:AO208<>""),AI208:AO208))) | IF(OR(F208="",AQ208=""),"",IF(COUNT(AI208:AP208)=0,"",AQ208-LOOKUP(2,1/(AI208:AP208<>""),AI208:AP208))) | IF(OR(F208="",AR208=""),"",IF(COUNT(AI208:AQ208)=0,"",AR208-LOOKUP(2,1/(AI208:AQ208<>""),AI208:AQ208))) | IF(OR(F208="",AS208=""),"",IF(COUNT(AI208:AR208)=0,"",AS208-LOOKUP(2,1/(AI208:AR208<>""),AI208:AR208))) | IF(OR(F208="",AT208=""),"",IF(COUNT(AI208:AS208)=0,"",AT208-LOOKUP(2,1/(AI208:AS208<>""),AI208:AS208))) | IF(OR(F208="",AU208=""),"",IF(COUNT(AI208:AT208)=0,"",AU208-LOOKUP(2,1/(AI208:AT208<>""),AI208:AT208))) | IF(OR(F208="",AV208=""),"",IF(COUNT(AI208:AU208)=0,"",AV208-LOOKUP(2,1/(AI208:AU208<>""),AI208:AU208))) | IF(J208="","All_Provinces",IFERROR(VLOOKUP(J208,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K208="","All_Districts",IFERROR(VLOOKUP(K208,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F209="","",ROW()-3) | [18 empty] | IF(AQ209="","",AQ209) |  |  |  | IF(W209<>"",W209,IF(OR(T209="",V209=""),"",EDATE(T209,V209))) |  |  |  |  | IF(F209="","",IF(COUNT(AI209:AV209)=0,IF(AA209="","Not started",AA209),SUBSTITUTE(LOOKUP(2,1/(AI209:AV209<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F209="",COUNT(AI209:AV209)=0),"",TODAY()-LOOKUP(2,1/(AI209:AV209<>""),AI209:AV209)) | IF(OR(F209="",COUNT(AI209:AV209)<2),"",LOOKUP(2,1/(AI209:AV209<>""),AI209:AV209)-MIN(AI209:AV209)) | IF(OR(AD209="",AC209="Not started",AC209=""),"",IFERROR(AD209-IF(VLOOKUP(AC209,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC209,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F209="","",IF(OR(AA209="Cancelled",AC209="Cancelled"),"Cancelled",IF(OR(AC209="Completed / Handover",Y209<>"",Z209>=100),"Completed — on track",IF(O209="Not awarded",IF(U209="",IF(X209="","No planned date",IF(TODAY()>X209,"Behind — past planned date",IF(X209-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U209,"Behind — award date passed",IF(U209-TODAY()<=30,"At risk — close to off track","On track"))),IF(X209="","No planned date",IF(AND(TODAY()>X209,OR(Z209="",Z209<100)),"Behind — past end date",IF(AND(T209<>"",X209<>"",Z209<>"",(Z209<100),((TODAY()-T209)/MAX(X209-T209,1)*100)-Z209>15),"Behind — progress lag",IF(AND(X209-TODAY()<=30,X209-TODAY()>=0,OR(Z209="",Z209<90)),"At risk — close to off track","On track")))))))) | IF(OR(F209="",AC209="Completed / Handover",AC209="Cancelled"),"",IF(O209="Not awarded",IF(U209<>"",U209-TODAY(),IF(X209="","",X209-TODAY())),IF(X209="","",X209-TODAY()))) | [14 empty] | IF(OR(F209="",AJ209=""),"",IF(COUNT(AI209:AI209)=0,"",AJ209-LOOKUP(2,1/(AI209:AI209<>""),AI209:AI209))) | IF(OR(F209="",AK209=""),"",IF(COUNT(AI209:AJ209)=0,"",AK209-LOOKUP(2,1/(AI209:AJ209<>""),AI209:AJ209))) | IF(OR(F209="",AL209=""),"",IF(COUNT(AI209:AK209)=0,"",AL209-LOOKUP(2,1/(AI209:AK209<>""),AI209:AK209))) | IF(OR(F209="",AM209=""),"",IF(COUNT(AI209:AL209)=0,"",AM209-LOOKUP(2,1/(AI209:AL209<>""),AI209:AL209))) | IF(OR(F209="",AN209=""),"",IF(COUNT(AI209:AM209)=0,"",AN209-LOOKUP(2,1/(AI209:AM209<>""),AI209:AM209))) | IF(OR(F209="",AO209=""),"",IF(COUNT(AI209:AN209)=0,"",AO209-LOOKUP(2,1/(AI209:AN209<>""),AI209:AN209))) | IF(OR(F209="",AP209=""),"",IF(COUNT(AI209:AO209)=0,"",AP209-LOOKUP(2,1/(AI209:AO209<>""),AI209:AO209))) | IF(OR(F209="",AQ209=""),"",IF(COUNT(AI209:AP209)=0,"",AQ209-LOOKUP(2,1/(AI209:AP209<>""),AI209:AP209))) | IF(OR(F209="",AR209=""),"",IF(COUNT(AI209:AQ209)=0,"",AR209-LOOKUP(2,1/(AI209:AQ209<>""),AI209:AQ209))) | IF(OR(F209="",AS209=""),"",IF(COUNT(AI209:AR209)=0,"",AS209-LOOKUP(2,1/(AI209:AR209<>""),AI209:AR209))) | IF(OR(F209="",AT209=""),"",IF(COUNT(AI209:AS209)=0,"",AT209-LOOKUP(2,1/(AI209:AS209<>""),AI209:AS209))) | IF(OR(F209="",AU209=""),"",IF(COUNT(AI209:AT209)=0,"",AU209-LOOKUP(2,1/(AI209:AT209<>""),AI209:AT209))) | IF(OR(F209="",AV209=""),"",IF(COUNT(AI209:AU209)=0,"",AV209-LOOKUP(2,1/(AI209:AU209<>""),AI209:AU209))) | IF(J209="","All_Provinces",IFERROR(VLOOKUP(J209,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K209="","All_Districts",IFERROR(VLOOKUP(K209,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F210="","",ROW()-3) | [18 empty] | IF(AQ210="","",AQ210) |  |  |  | IF(W210<>"",W210,IF(OR(T210="",V210=""),"",EDATE(T210,V210))) |  |  |  |  | IF(F210="","",IF(COUNT(AI210:AV210)=0,IF(AA210="","Not started",AA210),SUBSTITUTE(LOOKUP(2,1/(AI210:AV210<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F210="",COUNT(AI210:AV210)=0),"",TODAY()-LOOKUP(2,1/(AI210:AV210<>""),AI210:AV210)) | IF(OR(F210="",COUNT(AI210:AV210)<2),"",LOOKUP(2,1/(AI210:AV210<>""),AI210:AV210)-MIN(AI210:AV210)) | IF(OR(AD210="",AC210="Not started",AC210=""),"",IFERROR(AD210-IF(VLOOKUP(AC210,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC210,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F210="","",IF(OR(AA210="Cancelled",AC210="Cancelled"),"Cancelled",IF(OR(AC210="Completed / Handover",Y210<>"",Z210>=100),"Completed — on track",IF(O210="Not awarded",IF(U210="",IF(X210="","No planned date",IF(TODAY()>X210,"Behind — past planned date",IF(X210-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U210,"Behind — award date passed",IF(U210-TODAY()<=30,"At risk — close to off track","On track"))),IF(X210="","No planned date",IF(AND(TODAY()>X210,OR(Z210="",Z210<100)),"Behind — past end date",IF(AND(T210<>"",X210<>"",Z210<>"",(Z210<100),((TODAY()-T210)/MAX(X210-T210,1)*100)-Z210>15),"Behind — progress lag",IF(AND(X210-TODAY()<=30,X210-TODAY()>=0,OR(Z210="",Z210<90)),"At risk — close to off track","On track")))))))) | IF(OR(F210="",AC210="Completed / Handover",AC210="Cancelled"),"",IF(O210="Not awarded",IF(U210<>"",U210-TODAY(),IF(X210="","",X210-TODAY())),IF(X210="","",X210-TODAY()))) | [14 empty] | IF(OR(F210="",AJ210=""),"",IF(COUNT(AI210:AI210)=0,"",AJ210-LOOKUP(2,1/(AI210:AI210<>""),AI210:AI210))) | IF(OR(F210="",AK210=""),"",IF(COUNT(AI210:AJ210)=0,"",AK210-LOOKUP(2,1/(AI210:AJ210<>""),AI210:AJ210))) | IF(OR(F210="",AL210=""),"",IF(COUNT(AI210:AK210)=0,"",AL210-LOOKUP(2,1/(AI210:AK210<>""),AI210:AK210))) | IF(OR(F210="",AM210=""),"",IF(COUNT(AI210:AL210)=0,"",AM210-LOOKUP(2,1/(AI210:AL210<>""),AI210:AL210))) | IF(OR(F210="",AN210=""),"",IF(COUNT(AI210:AM210)=0,"",AN210-LOOKUP(2,1/(AI210:AM210<>""),AI210:AM210))) | IF(OR(F210="",AO210=""),"",IF(COUNT(AI210:AN210)=0,"",AO210-LOOKUP(2,1/(AI210:AN210<>""),AI210:AN210))) | IF(OR(F210="",AP210=""),"",IF(COUNT(AI210:AO210)=0,"",AP210-LOOKUP(2,1/(AI210:AO210<>""),AI210:AO210))) | IF(OR(F210="",AQ210=""),"",IF(COUNT(AI210:AP210)=0,"",AQ210-LOOKUP(2,1/(AI210:AP210<>""),AI210:AP210))) | IF(OR(F210="",AR210=""),"",IF(COUNT(AI210:AQ210)=0,"",AR210-LOOKUP(2,1/(AI210:AQ210<>""),AI210:AQ210))) | IF(OR(F210="",AS210=""),"",IF(COUNT(AI210:AR210)=0,"",AS210-LOOKUP(2,1/(AI210:AR210<>""),AI210:AR210))) | IF(OR(F210="",AT210=""),"",IF(COUNT(AI210:AS210)=0,"",AT210-LOOKUP(2,1/(AI210:AS210<>""),AI210:AS210))) | IF(OR(F210="",AU210=""),"",IF(COUNT(AI210:AT210)=0,"",AU210-LOOKUP(2,1/(AI210:AT210<>""),AI210:AT210))) | IF(OR(F210="",AV210=""),"",IF(COUNT(AI210:AU210)=0,"",AV210-LOOKUP(2,1/(AI210:AU210<>""),AI210:AU210))) | IF(J210="","All_Provinces",IFERROR(VLOOKUP(J210,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K210="","All_Districts",IFERROR(VLOOKUP(K210,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F211="","",ROW()-3) | [18 empty] | IF(AQ211="","",AQ211) |  |  |  | IF(W211<>"",W211,IF(OR(T211="",V211=""),"",EDATE(T211,V211))) |  |  |  |  | IF(F211="","",IF(COUNT(AI211:AV211)=0,IF(AA211="","Not started",AA211),SUBSTITUTE(LOOKUP(2,1/(AI211:AV211<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F211="",COUNT(AI211:AV211)=0),"",TODAY()-LOOKUP(2,1/(AI211:AV211<>""),AI211:AV211)) | IF(OR(F211="",COUNT(AI211:AV211)<2),"",LOOKUP(2,1/(AI211:AV211<>""),AI211:AV211)-MIN(AI211:AV211)) | IF(OR(AD211="",AC211="Not started",AC211=""),"",IFERROR(AD211-IF(VLOOKUP(AC211,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC211,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F211="","",IF(OR(AA211="Cancelled",AC211="Cancelled"),"Cancelled",IF(OR(AC211="Completed / Handover",Y211<>"",Z211>=100),"Completed — on track",IF(O211="Not awarded",IF(U211="",IF(X211="","No planned date",IF(TODAY()>X211,"Behind — past planned date",IF(X211-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U211,"Behind — award date passed",IF(U211-TODAY()<=30,"At risk — close to off track","On track"))),IF(X211="","No planned date",IF(AND(TODAY()>X211,OR(Z211="",Z211<100)),"Behind — past end date",IF(AND(T211<>"",X211<>"",Z211<>"",(Z211<100),((TODAY()-T211)/MAX(X211-T211,1)*100)-Z211>15),"Behind — progress lag",IF(AND(X211-TODAY()<=30,X211-TODAY()>=0,OR(Z211="",Z211<90)),"At risk — close to off track","On track")))))))) | IF(OR(F211="",AC211="Completed / Handover",AC211="Cancelled"),"",IF(O211="Not awarded",IF(U211<>"",U211-TODAY(),IF(X211="","",X211-TODAY())),IF(X211="","",X211-TODAY()))) | [14 empty] | IF(OR(F211="",AJ211=""),"",IF(COUNT(AI211:AI211)=0,"",AJ211-LOOKUP(2,1/(AI211:AI211<>""),AI211:AI211))) | IF(OR(F211="",AK211=""),"",IF(COUNT(AI211:AJ211)=0,"",AK211-LOOKUP(2,1/(AI211:AJ211<>""),AI211:AJ211))) | IF(OR(F211="",AL211=""),"",IF(COUNT(AI211:AK211)=0,"",AL211-LOOKUP(2,1/(AI211:AK211<>""),AI211:AK211))) | IF(OR(F211="",AM211=""),"",IF(COUNT(AI211:AL211)=0,"",AM211-LOOKUP(2,1/(AI211:AL211<>""),AI211:AL211))) | IF(OR(F211="",AN211=""),"",IF(COUNT(AI211:AM211)=0,"",AN211-LOOKUP(2,1/(AI211:AM211<>""),AI211:AM211))) | IF(OR(F211="",AO211=""),"",IF(COUNT(AI211:AN211)=0,"",AO211-LOOKUP(2,1/(AI211:AN211<>""),AI211:AN211))) | IF(OR(F211="",AP211=""),"",IF(COUNT(AI211:AO211)=0,"",AP211-LOOKUP(2,1/(AI211:AO211<>""),AI211:AO211))) | IF(OR(F211="",AQ211=""),"",IF(COUNT(AI211:AP211)=0,"",AQ211-LOOKUP(2,1/(AI211:AP211<>""),AI211:AP211))) | IF(OR(F211="",AR211=""),"",IF(COUNT(AI211:AQ211)=0,"",AR211-LOOKUP(2,1/(AI211:AQ211<>""),AI211:AQ211))) | IF(OR(F211="",AS211=""),"",IF(COUNT(AI211:AR211)=0,"",AS211-LOOKUP(2,1/(AI211:AR211<>""),AI211:AR211))) | IF(OR(F211="",AT211=""),"",IF(COUNT(AI211:AS211)=0,"",AT211-LOOKUP(2,1/(AI211:AS211<>""),AI211:AS211))) | IF(OR(F211="",AU211=""),"",IF(COUNT(AI211:AT211)=0,"",AU211-LOOKUP(2,1/(AI211:AT211<>""),AI211:AT211))) | IF(OR(F211="",AV211=""),"",IF(COUNT(AI211:AU211)=0,"",AV211-LOOKUP(2,1/(AI211:AU211<>""),AI211:AU211))) | IF(J211="","All_Provinces",IFERROR(VLOOKUP(J211,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K211="","All_Districts",IFERROR(VLOOKUP(K211,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F212="","",ROW()-3) | [18 empty] | IF(AQ212="","",AQ212) |  |  |  | IF(W212<>"",W212,IF(OR(T212="",V212=""),"",EDATE(T212,V212))) |  |  |  |  | IF(F212="","",IF(COUNT(AI212:AV212)=0,IF(AA212="","Not started",AA212),SUBSTITUTE(LOOKUP(2,1/(AI212:AV212<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F212="",COUNT(AI212:AV212)=0),"",TODAY()-LOOKUP(2,1/(AI212:AV212<>""),AI212:AV212)) | IF(OR(F212="",COUNT(AI212:AV212)<2),"",LOOKUP(2,1/(AI212:AV212<>""),AI212:AV212)-MIN(AI212:AV212)) | IF(OR(AD212="",AC212="Not started",AC212=""),"",IFERROR(AD212-IF(VLOOKUP(AC212,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC212,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F212="","",IF(OR(AA212="Cancelled",AC212="Cancelled"),"Cancelled",IF(OR(AC212="Completed / Handover",Y212<>"",Z212>=100),"Completed — on track",IF(O212="Not awarded",IF(U212="",IF(X212="","No planned date",IF(TODAY()>X212,"Behind — past planned date",IF(X212-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U212,"Behind — award date passed",IF(U212-TODAY()<=30,"At risk — close to off track","On track"))),IF(X212="","No planned date",IF(AND(TODAY()>X212,OR(Z212="",Z212<100)),"Behind — past end date",IF(AND(T212<>"",X212<>"",Z212<>"",(Z212<100),((TODAY()-T212)/MAX(X212-T212,1)*100)-Z212>15),"Behind — progress lag",IF(AND(X212-TODAY()<=30,X212-TODAY()>=0,OR(Z212="",Z212<90)),"At risk — close to off track","On track")))))))) | IF(OR(F212="",AC212="Completed / Handover",AC212="Cancelled"),"",IF(O212="Not awarded",IF(U212<>"",U212-TODAY(),IF(X212="","",X212-TODAY())),IF(X212="","",X212-TODAY()))) | [14 empty] | IF(OR(F212="",AJ212=""),"",IF(COUNT(AI212:AI212)=0,"",AJ212-LOOKUP(2,1/(AI212:AI212<>""),AI212:AI212))) | IF(OR(F212="",AK212=""),"",IF(COUNT(AI212:AJ212)=0,"",AK212-LOOKUP(2,1/(AI212:AJ212<>""),AI212:AJ212))) | IF(OR(F212="",AL212=""),"",IF(COUNT(AI212:AK212)=0,"",AL212-LOOKUP(2,1/(AI212:AK212<>""),AI212:AK212))) | IF(OR(F212="",AM212=""),"",IF(COUNT(AI212:AL212)=0,"",AM212-LOOKUP(2,1/(AI212:AL212<>""),AI212:AL212))) | IF(OR(F212="",AN212=""),"",IF(COUNT(AI212:AM212)=0,"",AN212-LOOKUP(2,1/(AI212:AM212<>""),AI212:AM212))) | IF(OR(F212="",AO212=""),"",IF(COUNT(AI212:AN212)=0,"",AO212-LOOKUP(2,1/(AI212:AN212<>""),AI212:AN212))) | IF(OR(F212="",AP212=""),"",IF(COUNT(AI212:AO212)=0,"",AP212-LOOKUP(2,1/(AI212:AO212<>""),AI212:AO212))) | IF(OR(F212="",AQ212=""),"",IF(COUNT(AI212:AP212)=0,"",AQ212-LOOKUP(2,1/(AI212:AP212<>""),AI212:AP212))) | IF(OR(F212="",AR212=""),"",IF(COUNT(AI212:AQ212)=0,"",AR212-LOOKUP(2,1/(AI212:AQ212<>""),AI212:AQ212))) | IF(OR(F212="",AS212=""),"",IF(COUNT(AI212:AR212)=0,"",AS212-LOOKUP(2,1/(AI212:AR212<>""),AI212:AR212))) | IF(OR(F212="",AT212=""),"",IF(COUNT(AI212:AS212)=0,"",AT212-LOOKUP(2,1/(AI212:AS212<>""),AI212:AS212))) | IF(OR(F212="",AU212=""),"",IF(COUNT(AI212:AT212)=0,"",AU212-LOOKUP(2,1/(AI212:AT212<>""),AI212:AT212))) | IF(OR(F212="",AV212=""),"",IF(COUNT(AI212:AU212)=0,"",AV212-LOOKUP(2,1/(AI212:AU212<>""),AI212:AU212))) | IF(J212="","All_Provinces",IFERROR(VLOOKUP(J212,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K212="","All_Districts",IFERROR(VLOOKUP(K212,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F213="","",ROW()-3) | [18 empty] | IF(AQ213="","",AQ213) |  |  |  | IF(W213<>"",W213,IF(OR(T213="",V213=""),"",EDATE(T213,V213))) |  |  |  |  | IF(F213="","",IF(COUNT(AI213:AV213)=0,IF(AA213="","Not started",AA213),SUBSTITUTE(LOOKUP(2,1/(AI213:AV213<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F213="",COUNT(AI213:AV213)=0),"",TODAY()-LOOKUP(2,1/(AI213:AV213<>""),AI213:AV213)) | IF(OR(F213="",COUNT(AI213:AV213)<2),"",LOOKUP(2,1/(AI213:AV213<>""),AI213:AV213)-MIN(AI213:AV213)) | IF(OR(AD213="",AC213="Not started",AC213=""),"",IFERROR(AD213-IF(VLOOKUP(AC213,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC213,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F213="","",IF(OR(AA213="Cancelled",AC213="Cancelled"),"Cancelled",IF(OR(AC213="Completed / Handover",Y213<>"",Z213>=100),"Completed — on track",IF(O213="Not awarded",IF(U213="",IF(X213="","No planned date",IF(TODAY()>X213,"Behind — past planned date",IF(X213-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U213,"Behind — award date passed",IF(U213-TODAY()<=30,"At risk — close to off track","On track"))),IF(X213="","No planned date",IF(AND(TODAY()>X213,OR(Z213="",Z213<100)),"Behind — past end date",IF(AND(T213<>"",X213<>"",Z213<>"",(Z213<100),((TODAY()-T213)/MAX(X213-T213,1)*100)-Z213>15),"Behind — progress lag",IF(AND(X213-TODAY()<=30,X213-TODAY()>=0,OR(Z213="",Z213<90)),"At risk — close to off track","On track")))))))) | IF(OR(F213="",AC213="Completed / Handover",AC213="Cancelled"),"",IF(O213="Not awarded",IF(U213<>"",U213-TODAY(),IF(X213="","",X213-TODAY())),IF(X213="","",X213-TODAY()))) | [14 empty] | IF(OR(F213="",AJ213=""),"",IF(COUNT(AI213:AI213)=0,"",AJ213-LOOKUP(2,1/(AI213:AI213<>""),AI213:AI213))) | IF(OR(F213="",AK213=""),"",IF(COUNT(AI213:AJ213)=0,"",AK213-LOOKUP(2,1/(AI213:AJ213<>""),AI213:AJ213))) | IF(OR(F213="",AL213=""),"",IF(COUNT(AI213:AK213)=0,"",AL213-LOOKUP(2,1/(AI213:AK213<>""),AI213:AK213))) | IF(OR(F213="",AM213=""),"",IF(COUNT(AI213:AL213)=0,"",AM213-LOOKUP(2,1/(AI213:AL213<>""),AI213:AL213))) | IF(OR(F213="",AN213=""),"",IF(COUNT(AI213:AM213)=0,"",AN213-LOOKUP(2,1/(AI213:AM213<>""),AI213:AM213))) | IF(OR(F213="",AO213=""),"",IF(COUNT(AI213:AN213)=0,"",AO213-LOOKUP(2,1/(AI213:AN213<>""),AI213:AN213))) | IF(OR(F213="",AP213=""),"",IF(COUNT(AI213:AO213)=0,"",AP213-LOOKUP(2,1/(AI213:AO213<>""),AI213:AO213))) | IF(OR(F213="",AQ213=""),"",IF(COUNT(AI213:AP213)=0,"",AQ213-LOOKUP(2,1/(AI213:AP213<>""),AI213:AP213))) | IF(OR(F213="",AR213=""),"",IF(COUNT(AI213:AQ213)=0,"",AR213-LOOKUP(2,1/(AI213:AQ213<>""),AI213:AQ213))) | IF(OR(F213="",AS213=""),"",IF(COUNT(AI213:AR213)=0,"",AS213-LOOKUP(2,1/(AI213:AR213<>""),AI213:AR213))) | IF(OR(F213="",AT213=""),"",IF(COUNT(AI213:AS213)=0,"",AT213-LOOKUP(2,1/(AI213:AS213<>""),AI213:AS213))) | IF(OR(F213="",AU213=""),"",IF(COUNT(AI213:AT213)=0,"",AU213-LOOKUP(2,1/(AI213:AT213<>""),AI213:AT213))) | IF(OR(F213="",AV213=""),"",IF(COUNT(AI213:AU213)=0,"",AV213-LOOKUP(2,1/(AI213:AU213<>""),AI213:AU213))) | IF(J213="","All_Provinces",IFERROR(VLOOKUP(J213,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K213="","All_Districts",IFERROR(VLOOKUP(K213,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F214="","",ROW()-3) | [18 empty] | IF(AQ214="","",AQ214) |  |  |  | IF(W214<>"",W214,IF(OR(T214="",V214=""),"",EDATE(T214,V214))) |  |  |  |  | IF(F214="","",IF(COUNT(AI214:AV214)=0,IF(AA214="","Not started",AA214),SUBSTITUTE(LOOKUP(2,1/(AI214:AV214<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F214="",COUNT(AI214:AV214)=0),"",TODAY()-LOOKUP(2,1/(AI214:AV214<>""),AI214:AV214)) | IF(OR(F214="",COUNT(AI214:AV214)<2),"",LOOKUP(2,1/(AI214:AV214<>""),AI214:AV214)-MIN(AI214:AV214)) | IF(OR(AD214="",AC214="Not started",AC214=""),"",IFERROR(AD214-IF(VLOOKUP(AC214,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC214,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F214="","",IF(OR(AA214="Cancelled",AC214="Cancelled"),"Cancelled",IF(OR(AC214="Completed / Handover",Y214<>"",Z214>=100),"Completed — on track",IF(O214="Not awarded",IF(U214="",IF(X214="","No planned date",IF(TODAY()>X214,"Behind — past planned date",IF(X214-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U214,"Behind — award date passed",IF(U214-TODAY()<=30,"At risk — close to off track","On track"))),IF(X214="","No planned date",IF(AND(TODAY()>X214,OR(Z214="",Z214<100)),"Behind — past end date",IF(AND(T214<>"",X214<>"",Z214<>"",(Z214<100),((TODAY()-T214)/MAX(X214-T214,1)*100)-Z214>15),"Behind — progress lag",IF(AND(X214-TODAY()<=30,X214-TODAY()>=0,OR(Z214="",Z214<90)),"At risk — close to off track","On track")))))))) | IF(OR(F214="",AC214="Completed / Handover",AC214="Cancelled"),"",IF(O214="Not awarded",IF(U214<>"",U214-TODAY(),IF(X214="","",X214-TODAY())),IF(X214="","",X214-TODAY()))) | [14 empty] | IF(OR(F214="",AJ214=""),"",IF(COUNT(AI214:AI214)=0,"",AJ214-LOOKUP(2,1/(AI214:AI214<>""),AI214:AI214))) | IF(OR(F214="",AK214=""),"",IF(COUNT(AI214:AJ214)=0,"",AK214-LOOKUP(2,1/(AI214:AJ214<>""),AI214:AJ214))) | IF(OR(F214="",AL214=""),"",IF(COUNT(AI214:AK214)=0,"",AL214-LOOKUP(2,1/(AI214:AK214<>""),AI214:AK214))) | IF(OR(F214="",AM214=""),"",IF(COUNT(AI214:AL214)=0,"",AM214-LOOKUP(2,1/(AI214:AL214<>""),AI214:AL214))) | IF(OR(F214="",AN214=""),"",IF(COUNT(AI214:AM214)=0,"",AN214-LOOKUP(2,1/(AI214:AM214<>""),AI214:AM214))) | IF(OR(F214="",AO214=""),"",IF(COUNT(AI214:AN214)=0,"",AO214-LOOKUP(2,1/(AI214:AN214<>""),AI214:AN214))) | IF(OR(F214="",AP214=""),"",IF(COUNT(AI214:AO214)=0,"",AP214-LOOKUP(2,1/(AI214:AO214<>""),AI214:AO214))) | IF(OR(F214="",AQ214=""),"",IF(COUNT(AI214:AP214)=0,"",AQ214-LOOKUP(2,1/(AI214:AP214<>""),AI214:AP214))) | IF(OR(F214="",AR214=""),"",IF(COUNT(AI214:AQ214)=0,"",AR214-LOOKUP(2,1/(AI214:AQ214<>""),AI214:AQ214))) | IF(OR(F214="",AS214=""),"",IF(COUNT(AI214:AR214)=0,"",AS214-LOOKUP(2,1/(AI214:AR214<>""),AI214:AR214))) | IF(OR(F214="",AT214=""),"",IF(COUNT(AI214:AS214)=0,"",AT214-LOOKUP(2,1/(AI214:AS214<>""),AI214:AS214))) | IF(OR(F214="",AU214=""),"",IF(COUNT(AI214:AT214)=0,"",AU214-LOOKUP(2,1/(AI214:AT214<>""),AI214:AT214))) | IF(OR(F214="",AV214=""),"",IF(COUNT(AI214:AU214)=0,"",AV214-LOOKUP(2,1/(AI214:AU214<>""),AI214:AU214))) | IF(J214="","All_Provinces",IFERROR(VLOOKUP(J214,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K214="","All_Districts",IFERROR(VLOOKUP(K214,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F215="","",ROW()-3) | [18 empty] | IF(AQ215="","",AQ215) |  |  |  | IF(W215<>"",W215,IF(OR(T215="",V215=""),"",EDATE(T215,V215))) |  |  |  |  | IF(F215="","",IF(COUNT(AI215:AV215)=0,IF(AA215="","Not started",AA215),SUBSTITUTE(LOOKUP(2,1/(AI215:AV215<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F215="",COUNT(AI215:AV215)=0),"",TODAY()-LOOKUP(2,1/(AI215:AV215<>""),AI215:AV215)) | IF(OR(F215="",COUNT(AI215:AV215)<2),"",LOOKUP(2,1/(AI215:AV215<>""),AI215:AV215)-MIN(AI215:AV215)) | IF(OR(AD215="",AC215="Not started",AC215=""),"",IFERROR(AD215-IF(VLOOKUP(AC215,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC215,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F215="","",IF(OR(AA215="Cancelled",AC215="Cancelled"),"Cancelled",IF(OR(AC215="Completed / Handover",Y215<>"",Z215>=100),"Completed — on track",IF(O215="Not awarded",IF(U215="",IF(X215="","No planned date",IF(TODAY()>X215,"Behind — past planned date",IF(X215-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U215,"Behind — award date passed",IF(U215-TODAY()<=30,"At risk — close to off track","On track"))),IF(X215="","No planned date",IF(AND(TODAY()>X215,OR(Z215="",Z215<100)),"Behind — past end date",IF(AND(T215<>"",X215<>"",Z215<>"",(Z215<100),((TODAY()-T215)/MAX(X215-T215,1)*100)-Z215>15),"Behind — progress lag",IF(AND(X215-TODAY()<=30,X215-TODAY()>=0,OR(Z215="",Z215<90)),"At risk — close to off track","On track")))))))) | IF(OR(F215="",AC215="Completed / Handover",AC215="Cancelled"),"",IF(O215="Not awarded",IF(U215<>"",U215-TODAY(),IF(X215="","",X215-TODAY())),IF(X215="","",X215-TODAY()))) | [14 empty] | IF(OR(F215="",AJ215=""),"",IF(COUNT(AI215:AI215)=0,"",AJ215-LOOKUP(2,1/(AI215:AI215<>""),AI215:AI215))) | IF(OR(F215="",AK215=""),"",IF(COUNT(AI215:AJ215)=0,"",AK215-LOOKUP(2,1/(AI215:AJ215<>""),AI215:AJ215))) | IF(OR(F215="",AL215=""),"",IF(COUNT(AI215:AK215)=0,"",AL215-LOOKUP(2,1/(AI215:AK215<>""),AI215:AK215))) | IF(OR(F215="",AM215=""),"",IF(COUNT(AI215:AL215)=0,"",AM215-LOOKUP(2,1/(AI215:AL215<>""),AI215:AL215))) | IF(OR(F215="",AN215=""),"",IF(COUNT(AI215:AM215)=0,"",AN215-LOOKUP(2,1/(AI215:AM215<>""),AI215:AM215))) | IF(OR(F215="",AO215=""),"",IF(COUNT(AI215:AN215)=0,"",AO215-LOOKUP(2,1/(AI215:AN215<>""),AI215:AN215))) | IF(OR(F215="",AP215=""),"",IF(COUNT(AI215:AO215)=0,"",AP215-LOOKUP(2,1/(AI215:AO215<>""),AI215:AO215))) | IF(OR(F215="",AQ215=""),"",IF(COUNT(AI215:AP215)=0,"",AQ215-LOOKUP(2,1/(AI215:AP215<>""),AI215:AP215))) | IF(OR(F215="",AR215=""),"",IF(COUNT(AI215:AQ215)=0,"",AR215-LOOKUP(2,1/(AI215:AQ215<>""),AI215:AQ215))) | IF(OR(F215="",AS215=""),"",IF(COUNT(AI215:AR215)=0,"",AS215-LOOKUP(2,1/(AI215:AR215<>""),AI215:AR215))) | IF(OR(F215="",AT215=""),"",IF(COUNT(AI215:AS215)=0,"",AT215-LOOKUP(2,1/(AI215:AS215<>""),AI215:AS215))) | IF(OR(F215="",AU215=""),"",IF(COUNT(AI215:AT215)=0,"",AU215-LOOKUP(2,1/(AI215:AT215<>""),AI215:AT215))) | IF(OR(F215="",AV215=""),"",IF(COUNT(AI215:AU215)=0,"",AV215-LOOKUP(2,1/(AI215:AU215<>""),AI215:AU215))) | IF(J215="","All_Provinces",IFERROR(VLOOKUP(J215,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K215="","All_Districts",IFERROR(VLOOKUP(K215,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F216="","",ROW()-3) | [18 empty] | IF(AQ216="","",AQ216) |  |  |  | IF(W216<>"",W216,IF(OR(T216="",V216=""),"",EDATE(T216,V216))) |  |  |  |  | IF(F216="","",IF(COUNT(AI216:AV216)=0,IF(AA216="","Not started",AA216),SUBSTITUTE(LOOKUP(2,1/(AI216:AV216<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F216="",COUNT(AI216:AV216)=0),"",TODAY()-LOOKUP(2,1/(AI216:AV216<>""),AI216:AV216)) | IF(OR(F216="",COUNT(AI216:AV216)<2),"",LOOKUP(2,1/(AI216:AV216<>""),AI216:AV216)-MIN(AI216:AV216)) | IF(OR(AD216="",AC216="Not started",AC216=""),"",IFERROR(AD216-IF(VLOOKUP(AC216,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC216,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F216="","",IF(OR(AA216="Cancelled",AC216="Cancelled"),"Cancelled",IF(OR(AC216="Completed / Handover",Y216<>"",Z216>=100),"Completed — on track",IF(O216="Not awarded",IF(U216="",IF(X216="","No planned date",IF(TODAY()>X216,"Behind — past planned date",IF(X216-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U216,"Behind — award date passed",IF(U216-TODAY()<=30,"At risk — close to off track","On track"))),IF(X216="","No planned date",IF(AND(TODAY()>X216,OR(Z216="",Z216<100)),"Behind — past end date",IF(AND(T216<>"",X216<>"",Z216<>"",(Z216<100),((TODAY()-T216)/MAX(X216-T216,1)*100)-Z216>15),"Behind — progress lag",IF(AND(X216-TODAY()<=30,X216-TODAY()>=0,OR(Z216="",Z216<90)),"At risk — close to off track","On track")))))))) | IF(OR(F216="",AC216="Completed / Handover",AC216="Cancelled"),"",IF(O216="Not awarded",IF(U216<>"",U216-TODAY(),IF(X216="","",X216-TODAY())),IF(X216="","",X216-TODAY()))) | [14 empty] | IF(OR(F216="",AJ216=""),"",IF(COUNT(AI216:AI216)=0,"",AJ216-LOOKUP(2,1/(AI216:AI216<>""),AI216:AI216))) | IF(OR(F216="",AK216=""),"",IF(COUNT(AI216:AJ216)=0,"",AK216-LOOKUP(2,1/(AI216:AJ216<>""),AI216:AJ216))) | IF(OR(F216="",AL216=""),"",IF(COUNT(AI216:AK216)=0,"",AL216-LOOKUP(2,1/(AI216:AK216<>""),AI216:AK216))) | IF(OR(F216="",AM216=""),"",IF(COUNT(AI216:AL216)=0,"",AM216-LOOKUP(2,1/(AI216:AL216<>""),AI216:AL216))) | IF(OR(F216="",AN216=""),"",IF(COUNT(AI216:AM216)=0,"",AN216-LOOKUP(2,1/(AI216:AM216<>""),AI216:AM216))) | IF(OR(F216="",AO216=""),"",IF(COUNT(AI216:AN216)=0,"",AO216-LOOKUP(2,1/(AI216:AN216<>""),AI216:AN216))) | IF(OR(F216="",AP216=""),"",IF(COUNT(AI216:AO216)=0,"",AP216-LOOKUP(2,1/(AI216:AO216<>""),AI216:AO216))) | IF(OR(F216="",AQ216=""),"",IF(COUNT(AI216:AP216)=0,"",AQ216-LOOKUP(2,1/(AI216:AP216<>""),AI216:AP216))) | IF(OR(F216="",AR216=""),"",IF(COUNT(AI216:AQ216)=0,"",AR216-LOOKUP(2,1/(AI216:AQ216<>""),AI216:AQ216))) | IF(OR(F216="",AS216=""),"",IF(COUNT(AI216:AR216)=0,"",AS216-LOOKUP(2,1/(AI216:AR216<>""),AI216:AR216))) | IF(OR(F216="",AT216=""),"",IF(COUNT(AI216:AS216)=0,"",AT216-LOOKUP(2,1/(AI216:AS216<>""),AI216:AS216))) | IF(OR(F216="",AU216=""),"",IF(COUNT(AI216:AT216)=0,"",AU216-LOOKUP(2,1/(AI216:AT216<>""),AI216:AT216))) | IF(OR(F216="",AV216=""),"",IF(COUNT(AI216:AU216)=0,"",AV216-LOOKUP(2,1/(AI216:AU216<>""),AI216:AU216))) | IF(J216="","All_Provinces",IFERROR(VLOOKUP(J216,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K216="","All_Districts",IFERROR(VLOOKUP(K216,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F217="","",ROW()-3) | [18 empty] | IF(AQ217="","",AQ217) |  |  |  | IF(W217<>"",W217,IF(OR(T217="",V217=""),"",EDATE(T217,V217))) |  |  |  |  | IF(F217="","",IF(COUNT(AI217:AV217)=0,IF(AA217="","Not started",AA217),SUBSTITUTE(LOOKUP(2,1/(AI217:AV217<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F217="",COUNT(AI217:AV217)=0),"",TODAY()-LOOKUP(2,1/(AI217:AV217<>""),AI217:AV217)) | IF(OR(F217="",COUNT(AI217:AV217)<2),"",LOOKUP(2,1/(AI217:AV217<>""),AI217:AV217)-MIN(AI217:AV217)) | IF(OR(AD217="",AC217="Not started",AC217=""),"",IFERROR(AD217-IF(VLOOKUP(AC217,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC217,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F217="","",IF(OR(AA217="Cancelled",AC217="Cancelled"),"Cancelled",IF(OR(AC217="Completed / Handover",Y217<>"",Z217>=100),"Completed — on track",IF(O217="Not awarded",IF(U217="",IF(X217="","No planned date",IF(TODAY()>X217,"Behind — past planned date",IF(X217-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U217,"Behind — award date passed",IF(U217-TODAY()<=30,"At risk — close to off track","On track"))),IF(X217="","No planned date",IF(AND(TODAY()>X217,OR(Z217="",Z217<100)),"Behind — past end date",IF(AND(T217<>"",X217<>"",Z217<>"",(Z217<100),((TODAY()-T217)/MAX(X217-T217,1)*100)-Z217>15),"Behind — progress lag",IF(AND(X217-TODAY()<=30,X217-TODAY()>=0,OR(Z217="",Z217<90)),"At risk — close to off track","On track")))))))) | IF(OR(F217="",AC217="Completed / Handover",AC217="Cancelled"),"",IF(O217="Not awarded",IF(U217<>"",U217-TODAY(),IF(X217="","",X217-TODAY())),IF(X217="","",X217-TODAY()))) | [14 empty] | IF(OR(F217="",AJ217=""),"",IF(COUNT(AI217:AI217)=0,"",AJ217-LOOKUP(2,1/(AI217:AI217<>""),AI217:AI217))) | IF(OR(F217="",AK217=""),"",IF(COUNT(AI217:AJ217)=0,"",AK217-LOOKUP(2,1/(AI217:AJ217<>""),AI217:AJ217))) | IF(OR(F217="",AL217=""),"",IF(COUNT(AI217:AK217)=0,"",AL217-LOOKUP(2,1/(AI217:AK217<>""),AI217:AK217))) | IF(OR(F217="",AM217=""),"",IF(COUNT(AI217:AL217)=0,"",AM217-LOOKUP(2,1/(AI217:AL217<>""),AI217:AL217))) | IF(OR(F217="",AN217=""),"",IF(COUNT(AI217:AM217)=0,"",AN217-LOOKUP(2,1/(AI217:AM217<>""),AI217:AM217))) | IF(OR(F217="",AO217=""),"",IF(COUNT(AI217:AN217)=0,"",AO217-LOOKUP(2,1/(AI217:AN217<>""),AI217:AN217))) | IF(OR(F217="",AP217=""),"",IF(COUNT(AI217:AO217)=0,"",AP217-LOOKUP(2,1/(AI217:AO217<>""),AI217:AO217))) | IF(OR(F217="",AQ217=""),"",IF(COUNT(AI217:AP217)=0,"",AQ217-LOOKUP(2,1/(AI217:AP217<>""),AI217:AP217))) | IF(OR(F217="",AR217=""),"",IF(COUNT(AI217:AQ217)=0,"",AR217-LOOKUP(2,1/(AI217:AQ217<>""),AI217:AQ217))) | IF(OR(F217="",AS217=""),"",IF(COUNT(AI217:AR217)=0,"",AS217-LOOKUP(2,1/(AI217:AR217<>""),AI217:AR217))) | IF(OR(F217="",AT217=""),"",IF(COUNT(AI217:AS217)=0,"",AT217-LOOKUP(2,1/(AI217:AS217<>""),AI217:AS217))) | IF(OR(F217="",AU217=""),"",IF(COUNT(AI217:AT217)=0,"",AU217-LOOKUP(2,1/(AI217:AT217<>""),AI217:AT217))) | IF(OR(F217="",AV217=""),"",IF(COUNT(AI217:AU217)=0,"",AV217-LOOKUP(2,1/(AI217:AU217<>""),AI217:AU217))) | IF(J217="","All_Provinces",IFERROR(VLOOKUP(J217,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K217="","All_Districts",IFERROR(VLOOKUP(K217,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F218="","",ROW()-3) | [18 empty] | IF(AQ218="","",AQ218) |  |  |  | IF(W218<>"",W218,IF(OR(T218="",V218=""),"",EDATE(T218,V218))) |  |  |  |  | IF(F218="","",IF(COUNT(AI218:AV218)=0,IF(AA218="","Not started",AA218),SUBSTITUTE(LOOKUP(2,1/(AI218:AV218<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F218="",COUNT(AI218:AV218)=0),"",TODAY()-LOOKUP(2,1/(AI218:AV218<>""),AI218:AV218)) | IF(OR(F218="",COUNT(AI218:AV218)<2),"",LOOKUP(2,1/(AI218:AV218<>""),AI218:AV218)-MIN(AI218:AV218)) | IF(OR(AD218="",AC218="Not started",AC218=""),"",IFERROR(AD218-IF(VLOOKUP(AC218,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC218,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F218="","",IF(OR(AA218="Cancelled",AC218="Cancelled"),"Cancelled",IF(OR(AC218="Completed / Handover",Y218<>"",Z218>=100),"Completed — on track",IF(O218="Not awarded",IF(U218="",IF(X218="","No planned date",IF(TODAY()>X218,"Behind — past planned date",IF(X218-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U218,"Behind — award date passed",IF(U218-TODAY()<=30,"At risk — close to off track","On track"))),IF(X218="","No planned date",IF(AND(TODAY()>X218,OR(Z218="",Z218<100)),"Behind — past end date",IF(AND(T218<>"",X218<>"",Z218<>"",(Z218<100),((TODAY()-T218)/MAX(X218-T218,1)*100)-Z218>15),"Behind — progress lag",IF(AND(X218-TODAY()<=30,X218-TODAY()>=0,OR(Z218="",Z218<90)),"At risk — close to off track","On track")))))))) | IF(OR(F218="",AC218="Completed / Handover",AC218="Cancelled"),"",IF(O218="Not awarded",IF(U218<>"",U218-TODAY(),IF(X218="","",X218-TODAY())),IF(X218="","",X218-TODAY()))) | [14 empty] | IF(OR(F218="",AJ218=""),"",IF(COUNT(AI218:AI218)=0,"",AJ218-LOOKUP(2,1/(AI218:AI218<>""),AI218:AI218))) | IF(OR(F218="",AK218=""),"",IF(COUNT(AI218:AJ218)=0,"",AK218-LOOKUP(2,1/(AI218:AJ218<>""),AI218:AJ218))) | IF(OR(F218="",AL218=""),"",IF(COUNT(AI218:AK218)=0,"",AL218-LOOKUP(2,1/(AI218:AK218<>""),AI218:AK218))) | IF(OR(F218="",AM218=""),"",IF(COUNT(AI218:AL218)=0,"",AM218-LOOKUP(2,1/(AI218:AL218<>""),AI218:AL218))) | IF(OR(F218="",AN218=""),"",IF(COUNT(AI218:AM218)=0,"",AN218-LOOKUP(2,1/(AI218:AM218<>""),AI218:AM218))) | IF(OR(F218="",AO218=""),"",IF(COUNT(AI218:AN218)=0,"",AO218-LOOKUP(2,1/(AI218:AN218<>""),AI218:AN218))) | IF(OR(F218="",AP218=""),"",IF(COUNT(AI218:AO218)=0,"",AP218-LOOKUP(2,1/(AI218:AO218<>""),AI218:AO218))) | IF(OR(F218="",AQ218=""),"",IF(COUNT(AI218:AP218)=0,"",AQ218-LOOKUP(2,1/(AI218:AP218<>""),AI218:AP218))) | IF(OR(F218="",AR218=""),"",IF(COUNT(AI218:AQ218)=0,"",AR218-LOOKUP(2,1/(AI218:AQ218<>""),AI218:AQ218))) | IF(OR(F218="",AS218=""),"",IF(COUNT(AI218:AR218)=0,"",AS218-LOOKUP(2,1/(AI218:AR218<>""),AI218:AR218))) | IF(OR(F218="",AT218=""),"",IF(COUNT(AI218:AS218)=0,"",AT218-LOOKUP(2,1/(AI218:AS218<>""),AI218:AS218))) | IF(OR(F218="",AU218=""),"",IF(COUNT(AI218:AT218)=0,"",AU218-LOOKUP(2,1/(AI218:AT218<>""),AI218:AT218))) | IF(OR(F218="",AV218=""),"",IF(COUNT(AI218:AU218)=0,"",AV218-LOOKUP(2,1/(AI218:AU218<>""),AI218:AU218))) | IF(J218="","All_Provinces",IFERROR(VLOOKUP(J218,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K218="","All_Districts",IFERROR(VLOOKUP(K218,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F219="","",ROW()-3) | [18 empty] | IF(AQ219="","",AQ219) |  |  |  | IF(W219<>"",W219,IF(OR(T219="",V219=""),"",EDATE(T219,V219))) |  |  |  |  | IF(F219="","",IF(COUNT(AI219:AV219)=0,IF(AA219="","Not started",AA219),SUBSTITUTE(LOOKUP(2,1/(AI219:AV219<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F219="",COUNT(AI219:AV219)=0),"",TODAY()-LOOKUP(2,1/(AI219:AV219<>""),AI219:AV219)) | IF(OR(F219="",COUNT(AI219:AV219)<2),"",LOOKUP(2,1/(AI219:AV219<>""),AI219:AV219)-MIN(AI219:AV219)) | IF(OR(AD219="",AC219="Not started",AC219=""),"",IFERROR(AD219-IF(VLOOKUP(AC219,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC219,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F219="","",IF(OR(AA219="Cancelled",AC219="Cancelled"),"Cancelled",IF(OR(AC219="Completed / Handover",Y219<>"",Z219>=100),"Completed — on track",IF(O219="Not awarded",IF(U219="",IF(X219="","No planned date",IF(TODAY()>X219,"Behind — past planned date",IF(X219-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U219,"Behind — award date passed",IF(U219-TODAY()<=30,"At risk — close to off track","On track"))),IF(X219="","No planned date",IF(AND(TODAY()>X219,OR(Z219="",Z219<100)),"Behind — past end date",IF(AND(T219<>"",X219<>"",Z219<>"",(Z219<100),((TODAY()-T219)/MAX(X219-T219,1)*100)-Z219>15),"Behind — progress lag",IF(AND(X219-TODAY()<=30,X219-TODAY()>=0,OR(Z219="",Z219<90)),"At risk — close to off track","On track")))))))) | IF(OR(F219="",AC219="Completed / Handover",AC219="Cancelled"),"",IF(O219="Not awarded",IF(U219<>"",U219-TODAY(),IF(X219="","",X219-TODAY())),IF(X219="","",X219-TODAY()))) | [14 empty] | IF(OR(F219="",AJ219=""),"",IF(COUNT(AI219:AI219)=0,"",AJ219-LOOKUP(2,1/(AI219:AI219<>""),AI219:AI219))) | IF(OR(F219="",AK219=""),"",IF(COUNT(AI219:AJ219)=0,"",AK219-LOOKUP(2,1/(AI219:AJ219<>""),AI219:AJ219))) | IF(OR(F219="",AL219=""),"",IF(COUNT(AI219:AK219)=0,"",AL219-LOOKUP(2,1/(AI219:AK219<>""),AI219:AK219))) | IF(OR(F219="",AM219=""),"",IF(COUNT(AI219:AL219)=0,"",AM219-LOOKUP(2,1/(AI219:AL219<>""),AI219:AL219))) | IF(OR(F219="",AN219=""),"",IF(COUNT(AI219:AM219)=0,"",AN219-LOOKUP(2,1/(AI219:AM219<>""),AI219:AM219))) | IF(OR(F219="",AO219=""),"",IF(COUNT(AI219:AN219)=0,"",AO219-LOOKUP(2,1/(AI219:AN219<>""),AI219:AN219))) | IF(OR(F219="",AP219=""),"",IF(COUNT(AI219:AO219)=0,"",AP219-LOOKUP(2,1/(AI219:AO219<>""),AI219:AO219))) | IF(OR(F219="",AQ219=""),"",IF(COUNT(AI219:AP219)=0,"",AQ219-LOOKUP(2,1/(AI219:AP219<>""),AI219:AP219))) | IF(OR(F219="",AR219=""),"",IF(COUNT(AI219:AQ219)=0,"",AR219-LOOKUP(2,1/(AI219:AQ219<>""),AI219:AQ219))) | IF(OR(F219="",AS219=""),"",IF(COUNT(AI219:AR219)=0,"",AS219-LOOKUP(2,1/(AI219:AR219<>""),AI219:AR219))) | IF(OR(F219="",AT219=""),"",IF(COUNT(AI219:AS219)=0,"",AT219-LOOKUP(2,1/(AI219:AS219<>""),AI219:AS219))) | IF(OR(F219="",AU219=""),"",IF(COUNT(AI219:AT219)=0,"",AU219-LOOKUP(2,1/(AI219:AT219<>""),AI219:AT219))) | IF(OR(F219="",AV219=""),"",IF(COUNT(AI219:AU219)=0,"",AV219-LOOKUP(2,1/(AI219:AU219<>""),AI219:AU219))) | IF(J219="","All_Provinces",IFERROR(VLOOKUP(J219,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K219="","All_Districts",IFERROR(VLOOKUP(K219,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F220="","",ROW()-3) | [18 empty] | IF(AQ220="","",AQ220) |  |  |  | IF(W220<>"",W220,IF(OR(T220="",V220=""),"",EDATE(T220,V220))) |  |  |  |  | IF(F220="","",IF(COUNT(AI220:AV220)=0,IF(AA220="","Not started",AA220),SUBSTITUTE(LOOKUP(2,1/(AI220:AV220<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F220="",COUNT(AI220:AV220)=0),"",TODAY()-LOOKUP(2,1/(AI220:AV220<>""),AI220:AV220)) | IF(OR(F220="",COUNT(AI220:AV220)<2),"",LOOKUP(2,1/(AI220:AV220<>""),AI220:AV220)-MIN(AI220:AV220)) | IF(OR(AD220="",AC220="Not started",AC220=""),"",IFERROR(AD220-IF(VLOOKUP(AC220,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC220,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F220="","",IF(OR(AA220="Cancelled",AC220="Cancelled"),"Cancelled",IF(OR(AC220="Completed / Handover",Y220<>"",Z220>=100),"Completed — on track",IF(O220="Not awarded",IF(U220="",IF(X220="","No planned date",IF(TODAY()>X220,"Behind — past planned date",IF(X220-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U220,"Behind — award date passed",IF(U220-TODAY()<=30,"At risk — close to off track","On track"))),IF(X220="","No planned date",IF(AND(TODAY()>X220,OR(Z220="",Z220<100)),"Behind — past end date",IF(AND(T220<>"",X220<>"",Z220<>"",(Z220<100),((TODAY()-T220)/MAX(X220-T220,1)*100)-Z220>15),"Behind — progress lag",IF(AND(X220-TODAY()<=30,X220-TODAY()>=0,OR(Z220="",Z220<90)),"At risk — close to off track","On track")))))))) | IF(OR(F220="",AC220="Completed / Handover",AC220="Cancelled"),"",IF(O220="Not awarded",IF(U220<>"",U220-TODAY(),IF(X220="","",X220-TODAY())),IF(X220="","",X220-TODAY()))) | [14 empty] | IF(OR(F220="",AJ220=""),"",IF(COUNT(AI220:AI220)=0,"",AJ220-LOOKUP(2,1/(AI220:AI220<>""),AI220:AI220))) | IF(OR(F220="",AK220=""),"",IF(COUNT(AI220:AJ220)=0,"",AK220-LOOKUP(2,1/(AI220:AJ220<>""),AI220:AJ220))) | IF(OR(F220="",AL220=""),"",IF(COUNT(AI220:AK220)=0,"",AL220-LOOKUP(2,1/(AI220:AK220<>""),AI220:AK220))) | IF(OR(F220="",AM220=""),"",IF(COUNT(AI220:AL220)=0,"",AM220-LOOKUP(2,1/(AI220:AL220<>""),AI220:AL220))) | IF(OR(F220="",AN220=""),"",IF(COUNT(AI220:AM220)=0,"",AN220-LOOKUP(2,1/(AI220:AM220<>""),AI220:AM220))) | IF(OR(F220="",AO220=""),"",IF(COUNT(AI220:AN220)=0,"",AO220-LOOKUP(2,1/(AI220:AN220<>""),AI220:AN220))) | IF(OR(F220="",AP220=""),"",IF(COUNT(AI220:AO220)=0,"",AP220-LOOKUP(2,1/(AI220:AO220<>""),AI220:AO220))) | IF(OR(F220="",AQ220=""),"",IF(COUNT(AI220:AP220)=0,"",AQ220-LOOKUP(2,1/(AI220:AP220<>""),AI220:AP220))) | IF(OR(F220="",AR220=""),"",IF(COUNT(AI220:AQ220)=0,"",AR220-LOOKUP(2,1/(AI220:AQ220<>""),AI220:AQ220))) | IF(OR(F220="",AS220=""),"",IF(COUNT(AI220:AR220)=0,"",AS220-LOOKUP(2,1/(AI220:AR220<>""),AI220:AR220))) | IF(OR(F220="",AT220=""),"",IF(COUNT(AI220:AS220)=0,"",AT220-LOOKUP(2,1/(AI220:AS220<>""),AI220:AS220))) | IF(OR(F220="",AU220=""),"",IF(COUNT(AI220:AT220)=0,"",AU220-LOOKUP(2,1/(AI220:AT220<>""),AI220:AT220))) | IF(OR(F220="",AV220=""),"",IF(COUNT(AI220:AU220)=0,"",AV220-LOOKUP(2,1/(AI220:AU220<>""),AI220:AU220))) | IF(J220="","All_Provinces",IFERROR(VLOOKUP(J220,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K220="","All_Districts",IFERROR(VLOOKUP(K220,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F221="","",ROW()-3) | [18 empty] | IF(AQ221="","",AQ221) |  |  |  | IF(W221<>"",W221,IF(OR(T221="",V221=""),"",EDATE(T221,V221))) |  |  |  |  | IF(F221="","",IF(COUNT(AI221:AV221)=0,IF(AA221="","Not started",AA221),SUBSTITUTE(LOOKUP(2,1/(AI221:AV221<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F221="",COUNT(AI221:AV221)=0),"",TODAY()-LOOKUP(2,1/(AI221:AV221<>""),AI221:AV221)) | IF(OR(F221="",COUNT(AI221:AV221)<2),"",LOOKUP(2,1/(AI221:AV221<>""),AI221:AV221)-MIN(AI221:AV221)) | IF(OR(AD221="",AC221="Not started",AC221=""),"",IFERROR(AD221-IF(VLOOKUP(AC221,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC221,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F221="","",IF(OR(AA221="Cancelled",AC221="Cancelled"),"Cancelled",IF(OR(AC221="Completed / Handover",Y221<>"",Z221>=100),"Completed — on track",IF(O221="Not awarded",IF(U221="",IF(X221="","No planned date",IF(TODAY()>X221,"Behind — past planned date",IF(X221-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U221,"Behind — award date passed",IF(U221-TODAY()<=30,"At risk — close to off track","On track"))),IF(X221="","No planned date",IF(AND(TODAY()>X221,OR(Z221="",Z221<100)),"Behind — past end date",IF(AND(T221<>"",X221<>"",Z221<>"",(Z221<100),((TODAY()-T221)/MAX(X221-T221,1)*100)-Z221>15),"Behind — progress lag",IF(AND(X221-TODAY()<=30,X221-TODAY()>=0,OR(Z221="",Z221<90)),"At risk — close to off track","On track")))))))) | IF(OR(F221="",AC221="Completed / Handover",AC221="Cancelled"),"",IF(O221="Not awarded",IF(U221<>"",U221-TODAY(),IF(X221="","",X221-TODAY())),IF(X221="","",X221-TODAY()))) | [14 empty] | IF(OR(F221="",AJ221=""),"",IF(COUNT(AI221:AI221)=0,"",AJ221-LOOKUP(2,1/(AI221:AI221<>""),AI221:AI221))) | IF(OR(F221="",AK221=""),"",IF(COUNT(AI221:AJ221)=0,"",AK221-LOOKUP(2,1/(AI221:AJ221<>""),AI221:AJ221))) | IF(OR(F221="",AL221=""),"",IF(COUNT(AI221:AK221)=0,"",AL221-LOOKUP(2,1/(AI221:AK221<>""),AI221:AK221))) | IF(OR(F221="",AM221=""),"",IF(COUNT(AI221:AL221)=0,"",AM221-LOOKUP(2,1/(AI221:AL221<>""),AI221:AL221))) | IF(OR(F221="",AN221=""),"",IF(COUNT(AI221:AM221)=0,"",AN221-LOOKUP(2,1/(AI221:AM221<>""),AI221:AM221))) | IF(OR(F221="",AO221=""),"",IF(COUNT(AI221:AN221)=0,"",AO221-LOOKUP(2,1/(AI221:AN221<>""),AI221:AN221))) | IF(OR(F221="",AP221=""),"",IF(COUNT(AI221:AO221)=0,"",AP221-LOOKUP(2,1/(AI221:AO221<>""),AI221:AO221))) | IF(OR(F221="",AQ221=""),"",IF(COUNT(AI221:AP221)=0,"",AQ221-LOOKUP(2,1/(AI221:AP221<>""),AI221:AP221))) | IF(OR(F221="",AR221=""),"",IF(COUNT(AI221:AQ221)=0,"",AR221-LOOKUP(2,1/(AI221:AQ221<>""),AI221:AQ221))) | IF(OR(F221="",AS221=""),"",IF(COUNT(AI221:AR221)=0,"",AS221-LOOKUP(2,1/(AI221:AR221<>""),AI221:AR221))) | IF(OR(F221="",AT221=""),"",IF(COUNT(AI221:AS221)=0,"",AT221-LOOKUP(2,1/(AI221:AS221<>""),AI221:AS221))) | IF(OR(F221="",AU221=""),"",IF(COUNT(AI221:AT221)=0,"",AU221-LOOKUP(2,1/(AI221:AT221<>""),AI221:AT221))) | IF(OR(F221="",AV221=""),"",IF(COUNT(AI221:AU221)=0,"",AV221-LOOKUP(2,1/(AI221:AU221<>""),AI221:AU221))) | IF(J221="","All_Provinces",IFERROR(VLOOKUP(J221,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K221="","All_Districts",IFERROR(VLOOKUP(K221,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F222="","",ROW()-3) | [18 empty] | IF(AQ222="","",AQ222) |  |  |  | IF(W222<>"",W222,IF(OR(T222="",V222=""),"",EDATE(T222,V222))) |  |  |  |  | IF(F222="","",IF(COUNT(AI222:AV222)=0,IF(AA222="","Not started",AA222),SUBSTITUTE(LOOKUP(2,1/(AI222:AV222<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F222="",COUNT(AI222:AV222)=0),"",TODAY()-LOOKUP(2,1/(AI222:AV222<>""),AI222:AV222)) | IF(OR(F222="",COUNT(AI222:AV222)<2),"",LOOKUP(2,1/(AI222:AV222<>""),AI222:AV222)-MIN(AI222:AV222)) | IF(OR(AD222="",AC222="Not started",AC222=""),"",IFERROR(AD222-IF(VLOOKUP(AC222,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC222,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F222="","",IF(OR(AA222="Cancelled",AC222="Cancelled"),"Cancelled",IF(OR(AC222="Completed / Handover",Y222<>"",Z222>=100),"Completed — on track",IF(O222="Not awarded",IF(U222="",IF(X222="","No planned date",IF(TODAY()>X222,"Behind — past planned date",IF(X222-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U222,"Behind — award date passed",IF(U222-TODAY()<=30,"At risk — close to off track","On track"))),IF(X222="","No planned date",IF(AND(TODAY()>X222,OR(Z222="",Z222<100)),"Behind — past end date",IF(AND(T222<>"",X222<>"",Z222<>"",(Z222<100),((TODAY()-T222)/MAX(X222-T222,1)*100)-Z222>15),"Behind — progress lag",IF(AND(X222-TODAY()<=30,X222-TODAY()>=0,OR(Z222="",Z222<90)),"At risk — close to off track","On track")))))))) | IF(OR(F222="",AC222="Completed / Handover",AC222="Cancelled"),"",IF(O222="Not awarded",IF(U222<>"",U222-TODAY(),IF(X222="","",X222-TODAY())),IF(X222="","",X222-TODAY()))) | [14 empty] | IF(OR(F222="",AJ222=""),"",IF(COUNT(AI222:AI222)=0,"",AJ222-LOOKUP(2,1/(AI222:AI222<>""),AI222:AI222))) | IF(OR(F222="",AK222=""),"",IF(COUNT(AI222:AJ222)=0,"",AK222-LOOKUP(2,1/(AI222:AJ222<>""),AI222:AJ222))) | IF(OR(F222="",AL222=""),"",IF(COUNT(AI222:AK222)=0,"",AL222-LOOKUP(2,1/(AI222:AK222<>""),AI222:AK222))) | IF(OR(F222="",AM222=""),"",IF(COUNT(AI222:AL222)=0,"",AM222-LOOKUP(2,1/(AI222:AL222<>""),AI222:AL222))) | IF(OR(F222="",AN222=""),"",IF(COUNT(AI222:AM222)=0,"",AN222-LOOKUP(2,1/(AI222:AM222<>""),AI222:AM222))) | IF(OR(F222="",AO222=""),"",IF(COUNT(AI222:AN222)=0,"",AO222-LOOKUP(2,1/(AI222:AN222<>""),AI222:AN222))) | IF(OR(F222="",AP222=""),"",IF(COUNT(AI222:AO222)=0,"",AP222-LOOKUP(2,1/(AI222:AO222<>""),AI222:AO222))) | IF(OR(F222="",AQ222=""),"",IF(COUNT(AI222:AP222)=0,"",AQ222-LOOKUP(2,1/(AI222:AP222<>""),AI222:AP222))) | IF(OR(F222="",AR222=""),"",IF(COUNT(AI222:AQ222)=0,"",AR222-LOOKUP(2,1/(AI222:AQ222<>""),AI222:AQ222))) | IF(OR(F222="",AS222=""),"",IF(COUNT(AI222:AR222)=0,"",AS222-LOOKUP(2,1/(AI222:AR222<>""),AI222:AR222))) | IF(OR(F222="",AT222=""),"",IF(COUNT(AI222:AS222)=0,"",AT222-LOOKUP(2,1/(AI222:AS222<>""),AI222:AS222))) | IF(OR(F222="",AU222=""),"",IF(COUNT(AI222:AT222)=0,"",AU222-LOOKUP(2,1/(AI222:AT222<>""),AI222:AT222))) | IF(OR(F222="",AV222=""),"",IF(COUNT(AI222:AU222)=0,"",AV222-LOOKUP(2,1/(AI222:AU222<>""),AI222:AU222))) | IF(J222="","All_Provinces",IFERROR(VLOOKUP(J222,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K222="","All_Districts",IFERROR(VLOOKUP(K222,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F223="","",ROW()-3) | [18 empty] | IF(AQ223="","",AQ223) |  |  |  | IF(W223<>"",W223,IF(OR(T223="",V223=""),"",EDATE(T223,V223))) |  |  |  |  | IF(F223="","",IF(COUNT(AI223:AV223)=0,IF(AA223="","Not started",AA223),SUBSTITUTE(LOOKUP(2,1/(AI223:AV223<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F223="",COUNT(AI223:AV223)=0),"",TODAY()-LOOKUP(2,1/(AI223:AV223<>""),AI223:AV223)) | IF(OR(F223="",COUNT(AI223:AV223)<2),"",LOOKUP(2,1/(AI223:AV223<>""),AI223:AV223)-MIN(AI223:AV223)) | IF(OR(AD223="",AC223="Not started",AC223=""),"",IFERROR(AD223-IF(VLOOKUP(AC223,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC223,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F223="","",IF(OR(AA223="Cancelled",AC223="Cancelled"),"Cancelled",IF(OR(AC223="Completed / Handover",Y223<>"",Z223>=100),"Completed — on track",IF(O223="Not awarded",IF(U223="",IF(X223="","No planned date",IF(TODAY()>X223,"Behind — past planned date",IF(X223-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U223,"Behind — award date passed",IF(U223-TODAY()<=30,"At risk — close to off track","On track"))),IF(X223="","No planned date",IF(AND(TODAY()>X223,OR(Z223="",Z223<100)),"Behind — past end date",IF(AND(T223<>"",X223<>"",Z223<>"",(Z223<100),((TODAY()-T223)/MAX(X223-T223,1)*100)-Z223>15),"Behind — progress lag",IF(AND(X223-TODAY()<=30,X223-TODAY()>=0,OR(Z223="",Z223<90)),"At risk — close to off track","On track")))))))) | IF(OR(F223="",AC223="Completed / Handover",AC223="Cancelled"),"",IF(O223="Not awarded",IF(U223<>"",U223-TODAY(),IF(X223="","",X223-TODAY())),IF(X223="","",X223-TODAY()))) | [14 empty] | IF(OR(F223="",AJ223=""),"",IF(COUNT(AI223:AI223)=0,"",AJ223-LOOKUP(2,1/(AI223:AI223<>""),AI223:AI223))) | IF(OR(F223="",AK223=""),"",IF(COUNT(AI223:AJ223)=0,"",AK223-LOOKUP(2,1/(AI223:AJ223<>""),AI223:AJ223))) | IF(OR(F223="",AL223=""),"",IF(COUNT(AI223:AK223)=0,"",AL223-LOOKUP(2,1/(AI223:AK223<>""),AI223:AK223))) | IF(OR(F223="",AM223=""),"",IF(COUNT(AI223:AL223)=0,"",AM223-LOOKUP(2,1/(AI223:AL223<>""),AI223:AL223))) | IF(OR(F223="",AN223=""),"",IF(COUNT(AI223:AM223)=0,"",AN223-LOOKUP(2,1/(AI223:AM223<>""),AI223:AM223))) | IF(OR(F223="",AO223=""),"",IF(COUNT(AI223:AN223)=0,"",AO223-LOOKUP(2,1/(AI223:AN223<>""),AI223:AN223))) | IF(OR(F223="",AP223=""),"",IF(COUNT(AI223:AO223)=0,"",AP223-LOOKUP(2,1/(AI223:AO223<>""),AI223:AO223))) | IF(OR(F223="",AQ223=""),"",IF(COUNT(AI223:AP223)=0,"",AQ223-LOOKUP(2,1/(AI223:AP223<>""),AI223:AP223))) | IF(OR(F223="",AR223=""),"",IF(COUNT(AI223:AQ223)=0,"",AR223-LOOKUP(2,1/(AI223:AQ223<>""),AI223:AQ223))) | IF(OR(F223="",AS223=""),"",IF(COUNT(AI223:AR223)=0,"",AS223-LOOKUP(2,1/(AI223:AR223<>""),AI223:AR223))) | IF(OR(F223="",AT223=""),"",IF(COUNT(AI223:AS223)=0,"",AT223-LOOKUP(2,1/(AI223:AS223<>""),AI223:AS223))) | IF(OR(F223="",AU223=""),"",IF(COUNT(AI223:AT223)=0,"",AU223-LOOKUP(2,1/(AI223:AT223<>""),AI223:AT223))) | IF(OR(F223="",AV223=""),"",IF(COUNT(AI223:AU223)=0,"",AV223-LOOKUP(2,1/(AI223:AU223<>""),AI223:AU223))) | IF(J223="","All_Provinces",IFERROR(VLOOKUP(J223,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K223="","All_Districts",IFERROR(VLOOKUP(K223,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F224="","",ROW()-3) | [18 empty] | IF(AQ224="","",AQ224) |  |  |  | IF(W224<>"",W224,IF(OR(T224="",V224=""),"",EDATE(T224,V224))) |  |  |  |  | IF(F224="","",IF(COUNT(AI224:AV224)=0,IF(AA224="","Not started",AA224),SUBSTITUTE(LOOKUP(2,1/(AI224:AV224<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F224="",COUNT(AI224:AV224)=0),"",TODAY()-LOOKUP(2,1/(AI224:AV224<>""),AI224:AV224)) | IF(OR(F224="",COUNT(AI224:AV224)<2),"",LOOKUP(2,1/(AI224:AV224<>""),AI224:AV224)-MIN(AI224:AV224)) | IF(OR(AD224="",AC224="Not started",AC224=""),"",IFERROR(AD224-IF(VLOOKUP(AC224,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC224,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F224="","",IF(OR(AA224="Cancelled",AC224="Cancelled"),"Cancelled",IF(OR(AC224="Completed / Handover",Y224<>"",Z224>=100),"Completed — on track",IF(O224="Not awarded",IF(U224="",IF(X224="","No planned date",IF(TODAY()>X224,"Behind — past planned date",IF(X224-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U224,"Behind — award date passed",IF(U224-TODAY()<=30,"At risk — close to off track","On track"))),IF(X224="","No planned date",IF(AND(TODAY()>X224,OR(Z224="",Z224<100)),"Behind — past end date",IF(AND(T224<>"",X224<>"",Z224<>"",(Z224<100),((TODAY()-T224)/MAX(X224-T224,1)*100)-Z224>15),"Behind — progress lag",IF(AND(X224-TODAY()<=30,X224-TODAY()>=0,OR(Z224="",Z224<90)),"At risk — close to off track","On track")))))))) | IF(OR(F224="",AC224="Completed / Handover",AC224="Cancelled"),"",IF(O224="Not awarded",IF(U224<>"",U224-TODAY(),IF(X224="","",X224-TODAY())),IF(X224="","",X224-TODAY()))) | [14 empty] | IF(OR(F224="",AJ224=""),"",IF(COUNT(AI224:AI224)=0,"",AJ224-LOOKUP(2,1/(AI224:AI224<>""),AI224:AI224))) | IF(OR(F224="",AK224=""),"",IF(COUNT(AI224:AJ224)=0,"",AK224-LOOKUP(2,1/(AI224:AJ224<>""),AI224:AJ224))) | IF(OR(F224="",AL224=""),"",IF(COUNT(AI224:AK224)=0,"",AL224-LOOKUP(2,1/(AI224:AK224<>""),AI224:AK224))) | IF(OR(F224="",AM224=""),"",IF(COUNT(AI224:AL224)=0,"",AM224-LOOKUP(2,1/(AI224:AL224<>""),AI224:AL224))) | IF(OR(F224="",AN224=""),"",IF(COUNT(AI224:AM224)=0,"",AN224-LOOKUP(2,1/(AI224:AM224<>""),AI224:AM224))) | IF(OR(F224="",AO224=""),"",IF(COUNT(AI224:AN224)=0,"",AO224-LOOKUP(2,1/(AI224:AN224<>""),AI224:AN224))) | IF(OR(F224="",AP224=""),"",IF(COUNT(AI224:AO224)=0,"",AP224-LOOKUP(2,1/(AI224:AO224<>""),AI224:AO224))) | IF(OR(F224="",AQ224=""),"",IF(COUNT(AI224:AP224)=0,"",AQ224-LOOKUP(2,1/(AI224:AP224<>""),AI224:AP224))) | IF(OR(F224="",AR224=""),"",IF(COUNT(AI224:AQ224)=0,"",AR224-LOOKUP(2,1/(AI224:AQ224<>""),AI224:AQ224))) | IF(OR(F224="",AS224=""),"",IF(COUNT(AI224:AR224)=0,"",AS224-LOOKUP(2,1/(AI224:AR224<>""),AI224:AR224))) | IF(OR(F224="",AT224=""),"",IF(COUNT(AI224:AS224)=0,"",AT224-LOOKUP(2,1/(AI224:AS224<>""),AI224:AS224))) | IF(OR(F224="",AU224=""),"",IF(COUNT(AI224:AT224)=0,"",AU224-LOOKUP(2,1/(AI224:AT224<>""),AI224:AT224))) | IF(OR(F224="",AV224=""),"",IF(COUNT(AI224:AU224)=0,"",AV224-LOOKUP(2,1/(AI224:AU224<>""),AI224:AU224))) | IF(J224="","All_Provinces",IFERROR(VLOOKUP(J224,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K224="","All_Districts",IFERROR(VLOOKUP(K224,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F225="","",ROW()-3) | [18 empty] | IF(AQ225="","",AQ225) |  |  |  | IF(W225<>"",W225,IF(OR(T225="",V225=""),"",EDATE(T225,V225))) |  |  |  |  | IF(F225="","",IF(COUNT(AI225:AV225)=0,IF(AA225="","Not started",AA225),SUBSTITUTE(LOOKUP(2,1/(AI225:AV225<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F225="",COUNT(AI225:AV225)=0),"",TODAY()-LOOKUP(2,1/(AI225:AV225<>""),AI225:AV225)) | IF(OR(F225="",COUNT(AI225:AV225)<2),"",LOOKUP(2,1/(AI225:AV225<>""),AI225:AV225)-MIN(AI225:AV225)) | IF(OR(AD225="",AC225="Not started",AC225=""),"",IFERROR(AD225-IF(VLOOKUP(AC225,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC225,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F225="","",IF(OR(AA225="Cancelled",AC225="Cancelled"),"Cancelled",IF(OR(AC225="Completed / Handover",Y225<>"",Z225>=100),"Completed — on track",IF(O225="Not awarded",IF(U225="",IF(X225="","No planned date",IF(TODAY()>X225,"Behind — past planned date",IF(X225-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U225,"Behind — award date passed",IF(U225-TODAY()<=30,"At risk — close to off track","On track"))),IF(X225="","No planned date",IF(AND(TODAY()>X225,OR(Z225="",Z225<100)),"Behind — past end date",IF(AND(T225<>"",X225<>"",Z225<>"",(Z225<100),((TODAY()-T225)/MAX(X225-T225,1)*100)-Z225>15),"Behind — progress lag",IF(AND(X225-TODAY()<=30,X225-TODAY()>=0,OR(Z225="",Z225<90)),"At risk — close to off track","On track")))))))) | IF(OR(F225="",AC225="Completed / Handover",AC225="Cancelled"),"",IF(O225="Not awarded",IF(U225<>"",U225-TODAY(),IF(X225="","",X225-TODAY())),IF(X225="","",X225-TODAY()))) | [14 empty] | IF(OR(F225="",AJ225=""),"",IF(COUNT(AI225:AI225)=0,"",AJ225-LOOKUP(2,1/(AI225:AI225<>""),AI225:AI225))) | IF(OR(F225="",AK225=""),"",IF(COUNT(AI225:AJ225)=0,"",AK225-LOOKUP(2,1/(AI225:AJ225<>""),AI225:AJ225))) | IF(OR(F225="",AL225=""),"",IF(COUNT(AI225:AK225)=0,"",AL225-LOOKUP(2,1/(AI225:AK225<>""),AI225:AK225))) | IF(OR(F225="",AM225=""),"",IF(COUNT(AI225:AL225)=0,"",AM225-LOOKUP(2,1/(AI225:AL225<>""),AI225:AL225))) | IF(OR(F225="",AN225=""),"",IF(COUNT(AI225:AM225)=0,"",AN225-LOOKUP(2,1/(AI225:AM225<>""),AI225:AM225))) | IF(OR(F225="",AO225=""),"",IF(COUNT(AI225:AN225)=0,"",AO225-LOOKUP(2,1/(AI225:AN225<>""),AI225:AN225))) | IF(OR(F225="",AP225=""),"",IF(COUNT(AI225:AO225)=0,"",AP225-LOOKUP(2,1/(AI225:AO225<>""),AI225:AO225))) | IF(OR(F225="",AQ225=""),"",IF(COUNT(AI225:AP225)=0,"",AQ225-LOOKUP(2,1/(AI225:AP225<>""),AI225:AP225))) | IF(OR(F225="",AR225=""),"",IF(COUNT(AI225:AQ225)=0,"",AR225-LOOKUP(2,1/(AI225:AQ225<>""),AI225:AQ225))) | IF(OR(F225="",AS225=""),"",IF(COUNT(AI225:AR225)=0,"",AS225-LOOKUP(2,1/(AI225:AR225<>""),AI225:AR225))) | IF(OR(F225="",AT225=""),"",IF(COUNT(AI225:AS225)=0,"",AT225-LOOKUP(2,1/(AI225:AS225<>""),AI225:AS225))) | IF(OR(F225="",AU225=""),"",IF(COUNT(AI225:AT225)=0,"",AU225-LOOKUP(2,1/(AI225:AT225<>""),AI225:AT225))) | IF(OR(F225="",AV225=""),"",IF(COUNT(AI225:AU225)=0,"",AV225-LOOKUP(2,1/(AI225:AU225<>""),AI225:AU225))) | IF(J225="","All_Provinces",IFERROR(VLOOKUP(J225,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K225="","All_Districts",IFERROR(VLOOKUP(K225,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F226="","",ROW()-3) | [18 empty] | IF(AQ226="","",AQ226) |  |  |  | IF(W226<>"",W226,IF(OR(T226="",V226=""),"",EDATE(T226,V226))) |  |  |  |  | IF(F226="","",IF(COUNT(AI226:AV226)=0,IF(AA226="","Not started",AA226),SUBSTITUTE(LOOKUP(2,1/(AI226:AV226<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F226="",COUNT(AI226:AV226)=0),"",TODAY()-LOOKUP(2,1/(AI226:AV226<>""),AI226:AV226)) | IF(OR(F226="",COUNT(AI226:AV226)<2),"",LOOKUP(2,1/(AI226:AV226<>""),AI226:AV226)-MIN(AI226:AV226)) | IF(OR(AD226="",AC226="Not started",AC226=""),"",IFERROR(AD226-IF(VLOOKUP(AC226,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC226,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F226="","",IF(OR(AA226="Cancelled",AC226="Cancelled"),"Cancelled",IF(OR(AC226="Completed / Handover",Y226<>"",Z226>=100),"Completed — on track",IF(O226="Not awarded",IF(U226="",IF(X226="","No planned date",IF(TODAY()>X226,"Behind — past planned date",IF(X226-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U226,"Behind — award date passed",IF(U226-TODAY()<=30,"At risk — close to off track","On track"))),IF(X226="","No planned date",IF(AND(TODAY()>X226,OR(Z226="",Z226<100)),"Behind — past end date",IF(AND(T226<>"",X226<>"",Z226<>"",(Z226<100),((TODAY()-T226)/MAX(X226-T226,1)*100)-Z226>15),"Behind — progress lag",IF(AND(X226-TODAY()<=30,X226-TODAY()>=0,OR(Z226="",Z226<90)),"At risk — close to off track","On track")))))))) | IF(OR(F226="",AC226="Completed / Handover",AC226="Cancelled"),"",IF(O226="Not awarded",IF(U226<>"",U226-TODAY(),IF(X226="","",X226-TODAY())),IF(X226="","",X226-TODAY()))) | [14 empty] | IF(OR(F226="",AJ226=""),"",IF(COUNT(AI226:AI226)=0,"",AJ226-LOOKUP(2,1/(AI226:AI226<>""),AI226:AI226))) | IF(OR(F226="",AK226=""),"",IF(COUNT(AI226:AJ226)=0,"",AK226-LOOKUP(2,1/(AI226:AJ226<>""),AI226:AJ226))) | IF(OR(F226="",AL226=""),"",IF(COUNT(AI226:AK226)=0,"",AL226-LOOKUP(2,1/(AI226:AK226<>""),AI226:AK226))) | IF(OR(F226="",AM226=""),"",IF(COUNT(AI226:AL226)=0,"",AM226-LOOKUP(2,1/(AI226:AL226<>""),AI226:AL226))) | IF(OR(F226="",AN226=""),"",IF(COUNT(AI226:AM226)=0,"",AN226-LOOKUP(2,1/(AI226:AM226<>""),AI226:AM226))) | IF(OR(F226="",AO226=""),"",IF(COUNT(AI226:AN226)=0,"",AO226-LOOKUP(2,1/(AI226:AN226<>""),AI226:AN226))) | IF(OR(F226="",AP226=""),"",IF(COUNT(AI226:AO226)=0,"",AP226-LOOKUP(2,1/(AI226:AO226<>""),AI226:AO226))) | IF(OR(F226="",AQ226=""),"",IF(COUNT(AI226:AP226)=0,"",AQ226-LOOKUP(2,1/(AI226:AP226<>""),AI226:AP226))) | IF(OR(F226="",AR226=""),"",IF(COUNT(AI226:AQ226)=0,"",AR226-LOOKUP(2,1/(AI226:AQ226<>""),AI226:AQ226))) | IF(OR(F226="",AS226=""),"",IF(COUNT(AI226:AR226)=0,"",AS226-LOOKUP(2,1/(AI226:AR226<>""),AI226:AR226))) | IF(OR(F226="",AT226=""),"",IF(COUNT(AI226:AS226)=0,"",AT226-LOOKUP(2,1/(AI226:AS226<>""),AI226:AS226))) | IF(OR(F226="",AU226=""),"",IF(COUNT(AI226:AT226)=0,"",AU226-LOOKUP(2,1/(AI226:AT226<>""),AI226:AT226))) | IF(OR(F226="",AV226=""),"",IF(COUNT(AI226:AU226)=0,"",AV226-LOOKUP(2,1/(AI226:AU226<>""),AI226:AU226))) | IF(J226="","All_Provinces",IFERROR(VLOOKUP(J226,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K226="","All_Districts",IFERROR(VLOOKUP(K226,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F227="","",ROW()-3) | [18 empty] | IF(AQ227="","",AQ227) |  |  |  | IF(W227<>"",W227,IF(OR(T227="",V227=""),"",EDATE(T227,V227))) |  |  |  |  | IF(F227="","",IF(COUNT(AI227:AV227)=0,IF(AA227="","Not started",AA227),SUBSTITUTE(LOOKUP(2,1/(AI227:AV227<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F227="",COUNT(AI227:AV227)=0),"",TODAY()-LOOKUP(2,1/(AI227:AV227<>""),AI227:AV227)) | IF(OR(F227="",COUNT(AI227:AV227)<2),"",LOOKUP(2,1/(AI227:AV227<>""),AI227:AV227)-MIN(AI227:AV227)) | IF(OR(AD227="",AC227="Not started",AC227=""),"",IFERROR(AD227-IF(VLOOKUP(AC227,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC227,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F227="","",IF(OR(AA227="Cancelled",AC227="Cancelled"),"Cancelled",IF(OR(AC227="Completed / Handover",Y227<>"",Z227>=100),"Completed — on track",IF(O227="Not awarded",IF(U227="",IF(X227="","No planned date",IF(TODAY()>X227,"Behind — past planned date",IF(X227-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U227,"Behind — award date passed",IF(U227-TODAY()<=30,"At risk — close to off track","On track"))),IF(X227="","No planned date",IF(AND(TODAY()>X227,OR(Z227="",Z227<100)),"Behind — past end date",IF(AND(T227<>"",X227<>"",Z227<>"",(Z227<100),((TODAY()-T227)/MAX(X227-T227,1)*100)-Z227>15),"Behind — progress lag",IF(AND(X227-TODAY()<=30,X227-TODAY()>=0,OR(Z227="",Z227<90)),"At risk — close to off track","On track")))))))) | IF(OR(F227="",AC227="Completed / Handover",AC227="Cancelled"),"",IF(O227="Not awarded",IF(U227<>"",U227-TODAY(),IF(X227="","",X227-TODAY())),IF(X227="","",X227-TODAY()))) | [14 empty] | IF(OR(F227="",AJ227=""),"",IF(COUNT(AI227:AI227)=0,"",AJ227-LOOKUP(2,1/(AI227:AI227<>""),AI227:AI227))) | IF(OR(F227="",AK227=""),"",IF(COUNT(AI227:AJ227)=0,"",AK227-LOOKUP(2,1/(AI227:AJ227<>""),AI227:AJ227))) | IF(OR(F227="",AL227=""),"",IF(COUNT(AI227:AK227)=0,"",AL227-LOOKUP(2,1/(AI227:AK227<>""),AI227:AK227))) | IF(OR(F227="",AM227=""),"",IF(COUNT(AI227:AL227)=0,"",AM227-LOOKUP(2,1/(AI227:AL227<>""),AI227:AL227))) | IF(OR(F227="",AN227=""),"",IF(COUNT(AI227:AM227)=0,"",AN227-LOOKUP(2,1/(AI227:AM227<>""),AI227:AM227))) | IF(OR(F227="",AO227=""),"",IF(COUNT(AI227:AN227)=0,"",AO227-LOOKUP(2,1/(AI227:AN227<>""),AI227:AN227))) | IF(OR(F227="",AP227=""),"",IF(COUNT(AI227:AO227)=0,"",AP227-LOOKUP(2,1/(AI227:AO227<>""),AI227:AO227))) | IF(OR(F227="",AQ227=""),"",IF(COUNT(AI227:AP227)=0,"",AQ227-LOOKUP(2,1/(AI227:AP227<>""),AI227:AP227))) | IF(OR(F227="",AR227=""),"",IF(COUNT(AI227:AQ227)=0,"",AR227-LOOKUP(2,1/(AI227:AQ227<>""),AI227:AQ227))) | IF(OR(F227="",AS227=""),"",IF(COUNT(AI227:AR227)=0,"",AS227-LOOKUP(2,1/(AI227:AR227<>""),AI227:AR227))) | IF(OR(F227="",AT227=""),"",IF(COUNT(AI227:AS227)=0,"",AT227-LOOKUP(2,1/(AI227:AS227<>""),AI227:AS227))) | IF(OR(F227="",AU227=""),"",IF(COUNT(AI227:AT227)=0,"",AU227-LOOKUP(2,1/(AI227:AT227<>""),AI227:AT227))) | IF(OR(F227="",AV227=""),"",IF(COUNT(AI227:AU227)=0,"",AV227-LOOKUP(2,1/(AI227:AU227<>""),AI227:AU227))) | IF(J227="","All_Provinces",IFERROR(VLOOKUP(J227,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K227="","All_Districts",IFERROR(VLOOKUP(K227,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F228="","",ROW()-3) | [18 empty] | IF(AQ228="","",AQ228) |  |  |  | IF(W228<>"",W228,IF(OR(T228="",V228=""),"",EDATE(T228,V228))) |  |  |  |  | IF(F228="","",IF(COUNT(AI228:AV228)=0,IF(AA228="","Not started",AA228),SUBSTITUTE(LOOKUP(2,1/(AI228:AV228<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F228="",COUNT(AI228:AV228)=0),"",TODAY()-LOOKUP(2,1/(AI228:AV228<>""),AI228:AV228)) | IF(OR(F228="",COUNT(AI228:AV228)<2),"",LOOKUP(2,1/(AI228:AV228<>""),AI228:AV228)-MIN(AI228:AV228)) | IF(OR(AD228="",AC228="Not started",AC228=""),"",IFERROR(AD228-IF(VLOOKUP(AC228,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC228,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F228="","",IF(OR(AA228="Cancelled",AC228="Cancelled"),"Cancelled",IF(OR(AC228="Completed / Handover",Y228<>"",Z228>=100),"Completed — on track",IF(O228="Not awarded",IF(U228="",IF(X228="","No planned date",IF(TODAY()>X228,"Behind — past planned date",IF(X228-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U228,"Behind — award date passed",IF(U228-TODAY()<=30,"At risk — close to off track","On track"))),IF(X228="","No planned date",IF(AND(TODAY()>X228,OR(Z228="",Z228<100)),"Behind — past end date",IF(AND(T228<>"",X228<>"",Z228<>"",(Z228<100),((TODAY()-T228)/MAX(X228-T228,1)*100)-Z228>15),"Behind — progress lag",IF(AND(X228-TODAY()<=30,X228-TODAY()>=0,OR(Z228="",Z228<90)),"At risk — close to off track","On track")))))))) | IF(OR(F228="",AC228="Completed / Handover",AC228="Cancelled"),"",IF(O228="Not awarded",IF(U228<>"",U228-TODAY(),IF(X228="","",X228-TODAY())),IF(X228="","",X228-TODAY()))) | [14 empty] | IF(OR(F228="",AJ228=""),"",IF(COUNT(AI228:AI228)=0,"",AJ228-LOOKUP(2,1/(AI228:AI228<>""),AI228:AI228))) | IF(OR(F228="",AK228=""),"",IF(COUNT(AI228:AJ228)=0,"",AK228-LOOKUP(2,1/(AI228:AJ228<>""),AI228:AJ228))) | IF(OR(F228="",AL228=""),"",IF(COUNT(AI228:AK228)=0,"",AL228-LOOKUP(2,1/(AI228:AK228<>""),AI228:AK228))) | IF(OR(F228="",AM228=""),"",IF(COUNT(AI228:AL228)=0,"",AM228-LOOKUP(2,1/(AI228:AL228<>""),AI228:AL228))) | IF(OR(F228="",AN228=""),"",IF(COUNT(AI228:AM228)=0,"",AN228-LOOKUP(2,1/(AI228:AM228<>""),AI228:AM228))) | IF(OR(F228="",AO228=""),"",IF(COUNT(AI228:AN228)=0,"",AO228-LOOKUP(2,1/(AI228:AN228<>""),AI228:AN228))) | IF(OR(F228="",AP228=""),"",IF(COUNT(AI228:AO228)=0,"",AP228-LOOKUP(2,1/(AI228:AO228<>""),AI228:AO228))) | IF(OR(F228="",AQ228=""),"",IF(COUNT(AI228:AP228)=0,"",AQ228-LOOKUP(2,1/(AI228:AP228<>""),AI228:AP228))) | IF(OR(F228="",AR228=""),"",IF(COUNT(AI228:AQ228)=0,"",AR228-LOOKUP(2,1/(AI228:AQ228<>""),AI228:AQ228))) | IF(OR(F228="",AS228=""),"",IF(COUNT(AI228:AR228)=0,"",AS228-LOOKUP(2,1/(AI228:AR228<>""),AI228:AR228))) | IF(OR(F228="",AT228=""),"",IF(COUNT(AI228:AS228)=0,"",AT228-LOOKUP(2,1/(AI228:AS228<>""),AI228:AS228))) | IF(OR(F228="",AU228=""),"",IF(COUNT(AI228:AT228)=0,"",AU228-LOOKUP(2,1/(AI228:AT228<>""),AI228:AT228))) | IF(OR(F228="",AV228=""),"",IF(COUNT(AI228:AU228)=0,"",AV228-LOOKUP(2,1/(AI228:AU228<>""),AI228:AU228))) | IF(J228="","All_Provinces",IFERROR(VLOOKUP(J228,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K228="","All_Districts",IFERROR(VLOOKUP(K228,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F229="","",ROW()-3) | [18 empty] | IF(AQ229="","",AQ229) |  |  |  | IF(W229<>"",W229,IF(OR(T229="",V229=""),"",EDATE(T229,V229))) |  |  |  |  | IF(F229="","",IF(COUNT(AI229:AV229)=0,IF(AA229="","Not started",AA229),SUBSTITUTE(LOOKUP(2,1/(AI229:AV229<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F229="",COUNT(AI229:AV229)=0),"",TODAY()-LOOKUP(2,1/(AI229:AV229<>""),AI229:AV229)) | IF(OR(F229="",COUNT(AI229:AV229)<2),"",LOOKUP(2,1/(AI229:AV229<>""),AI229:AV229)-MIN(AI229:AV229)) | IF(OR(AD229="",AC229="Not started",AC229=""),"",IFERROR(AD229-IF(VLOOKUP(AC229,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC229,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F229="","",IF(OR(AA229="Cancelled",AC229="Cancelled"),"Cancelled",IF(OR(AC229="Completed / Handover",Y229<>"",Z229>=100),"Completed — on track",IF(O229="Not awarded",IF(U229="",IF(X229="","No planned date",IF(TODAY()>X229,"Behind — past planned date",IF(X229-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U229,"Behind — award date passed",IF(U229-TODAY()<=30,"At risk — close to off track","On track"))),IF(X229="","No planned date",IF(AND(TODAY()>X229,OR(Z229="",Z229<100)),"Behind — past end date",IF(AND(T229<>"",X229<>"",Z229<>"",(Z229<100),((TODAY()-T229)/MAX(X229-T229,1)*100)-Z229>15),"Behind — progress lag",IF(AND(X229-TODAY()<=30,X229-TODAY()>=0,OR(Z229="",Z229<90)),"At risk — close to off track","On track")))))))) | IF(OR(F229="",AC229="Completed / Handover",AC229="Cancelled"),"",IF(O229="Not awarded",IF(U229<>"",U229-TODAY(),IF(X229="","",X229-TODAY())),IF(X229="","",X229-TODAY()))) | [14 empty] | IF(OR(F229="",AJ229=""),"",IF(COUNT(AI229:AI229)=0,"",AJ229-LOOKUP(2,1/(AI229:AI229<>""),AI229:AI229))) | IF(OR(F229="",AK229=""),"",IF(COUNT(AI229:AJ229)=0,"",AK229-LOOKUP(2,1/(AI229:AJ229<>""),AI229:AJ229))) | IF(OR(F229="",AL229=""),"",IF(COUNT(AI229:AK229)=0,"",AL229-LOOKUP(2,1/(AI229:AK229<>""),AI229:AK229))) | IF(OR(F229="",AM229=""),"",IF(COUNT(AI229:AL229)=0,"",AM229-LOOKUP(2,1/(AI229:AL229<>""),AI229:AL229))) | IF(OR(F229="",AN229=""),"",IF(COUNT(AI229:AM229)=0,"",AN229-LOOKUP(2,1/(AI229:AM229<>""),AI229:AM229))) | IF(OR(F229="",AO229=""),"",IF(COUNT(AI229:AN229)=0,"",AO229-LOOKUP(2,1/(AI229:AN229<>""),AI229:AN229))) | IF(OR(F229="",AP229=""),"",IF(COUNT(AI229:AO229)=0,"",AP229-LOOKUP(2,1/(AI229:AO229<>""),AI229:AO229))) | IF(OR(F229="",AQ229=""),"",IF(COUNT(AI229:AP229)=0,"",AQ229-LOOKUP(2,1/(AI229:AP229<>""),AI229:AP229))) | IF(OR(F229="",AR229=""),"",IF(COUNT(AI229:AQ229)=0,"",AR229-LOOKUP(2,1/(AI229:AQ229<>""),AI229:AQ229))) | IF(OR(F229="",AS229=""),"",IF(COUNT(AI229:AR229)=0,"",AS229-LOOKUP(2,1/(AI229:AR229<>""),AI229:AR229))) | IF(OR(F229="",AT229=""),"",IF(COUNT(AI229:AS229)=0,"",AT229-LOOKUP(2,1/(AI229:AS229<>""),AI229:AS229))) | IF(OR(F229="",AU229=""),"",IF(COUNT(AI229:AT229)=0,"",AU229-LOOKUP(2,1/(AI229:AT229<>""),AI229:AT229))) | IF(OR(F229="",AV229=""),"",IF(COUNT(AI229:AU229)=0,"",AV229-LOOKUP(2,1/(AI229:AU229<>""),AI229:AU229))) | IF(J229="","All_Provinces",IFERROR(VLOOKUP(J229,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K229="","All_Districts",IFERROR(VLOOKUP(K229,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F230="","",ROW()-3) | [18 empty] | IF(AQ230="","",AQ230) |  |  |  | IF(W230<>"",W230,IF(OR(T230="",V230=""),"",EDATE(T230,V230))) |  |  |  |  | IF(F230="","",IF(COUNT(AI230:AV230)=0,IF(AA230="","Not started",AA230),SUBSTITUTE(LOOKUP(2,1/(AI230:AV230<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F230="",COUNT(AI230:AV230)=0),"",TODAY()-LOOKUP(2,1/(AI230:AV230<>""),AI230:AV230)) | IF(OR(F230="",COUNT(AI230:AV230)<2),"",LOOKUP(2,1/(AI230:AV230<>""),AI230:AV230)-MIN(AI230:AV230)) | IF(OR(AD230="",AC230="Not started",AC230=""),"",IFERROR(AD230-IF(VLOOKUP(AC230,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC230,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F230="","",IF(OR(AA230="Cancelled",AC230="Cancelled"),"Cancelled",IF(OR(AC230="Completed / Handover",Y230<>"",Z230>=100),"Completed — on track",IF(O230="Not awarded",IF(U230="",IF(X230="","No planned date",IF(TODAY()>X230,"Behind — past planned date",IF(X230-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U230,"Behind — award date passed",IF(U230-TODAY()<=30,"At risk — close to off track","On track"))),IF(X230="","No planned date",IF(AND(TODAY()>X230,OR(Z230="",Z230<100)),"Behind — past end date",IF(AND(T230<>"",X230<>"",Z230<>"",(Z230<100),((TODAY()-T230)/MAX(X230-T230,1)*100)-Z230>15),"Behind — progress lag",IF(AND(X230-TODAY()<=30,X230-TODAY()>=0,OR(Z230="",Z230<90)),"At risk — close to off track","On track")))))))) | IF(OR(F230="",AC230="Completed / Handover",AC230="Cancelled"),"",IF(O230="Not awarded",IF(U230<>"",U230-TODAY(),IF(X230="","",X230-TODAY())),IF(X230="","",X230-TODAY()))) | [14 empty] | IF(OR(F230="",AJ230=""),"",IF(COUNT(AI230:AI230)=0,"",AJ230-LOOKUP(2,1/(AI230:AI230<>""),AI230:AI230))) | IF(OR(F230="",AK230=""),"",IF(COUNT(AI230:AJ230)=0,"",AK230-LOOKUP(2,1/(AI230:AJ230<>""),AI230:AJ230))) | IF(OR(F230="",AL230=""),"",IF(COUNT(AI230:AK230)=0,"",AL230-LOOKUP(2,1/(AI230:AK230<>""),AI230:AK230))) | IF(OR(F230="",AM230=""),"",IF(COUNT(AI230:AL230)=0,"",AM230-LOOKUP(2,1/(AI230:AL230<>""),AI230:AL230))) | IF(OR(F230="",AN230=""),"",IF(COUNT(AI230:AM230)=0,"",AN230-LOOKUP(2,1/(AI230:AM230<>""),AI230:AM230))) | IF(OR(F230="",AO230=""),"",IF(COUNT(AI230:AN230)=0,"",AO230-LOOKUP(2,1/(AI230:AN230<>""),AI230:AN230))) | IF(OR(F230="",AP230=""),"",IF(COUNT(AI230:AO230)=0,"",AP230-LOOKUP(2,1/(AI230:AO230<>""),AI230:AO230))) | IF(OR(F230="",AQ230=""),"",IF(COUNT(AI230:AP230)=0,"",AQ230-LOOKUP(2,1/(AI230:AP230<>""),AI230:AP230))) | IF(OR(F230="",AR230=""),"",IF(COUNT(AI230:AQ230)=0,"",AR230-LOOKUP(2,1/(AI230:AQ230<>""),AI230:AQ230))) | IF(OR(F230="",AS230=""),"",IF(COUNT(AI230:AR230)=0,"",AS230-LOOKUP(2,1/(AI230:AR230<>""),AI230:AR230))) | IF(OR(F230="",AT230=""),"",IF(COUNT(AI230:AS230)=0,"",AT230-LOOKUP(2,1/(AI230:AS230<>""),AI230:AS230))) | IF(OR(F230="",AU230=""),"",IF(COUNT(AI230:AT230)=0,"",AU230-LOOKUP(2,1/(AI230:AT230<>""),AI230:AT230))) | IF(OR(F230="",AV230=""),"",IF(COUNT(AI230:AU230)=0,"",AV230-LOOKUP(2,1/(AI230:AU230<>""),AI230:AU230))) | IF(J230="","All_Provinces",IFERROR(VLOOKUP(J230,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K230="","All_Districts",IFERROR(VLOOKUP(K230,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F231="","",ROW()-3) | [18 empty] | IF(AQ231="","",AQ231) |  |  |  | IF(W231<>"",W231,IF(OR(T231="",V231=""),"",EDATE(T231,V231))) |  |  |  |  | IF(F231="","",IF(COUNT(AI231:AV231)=0,IF(AA231="","Not started",AA231),SUBSTITUTE(LOOKUP(2,1/(AI231:AV231<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F231="",COUNT(AI231:AV231)=0),"",TODAY()-LOOKUP(2,1/(AI231:AV231<>""),AI231:AV231)) | IF(OR(F231="",COUNT(AI231:AV231)<2),"",LOOKUP(2,1/(AI231:AV231<>""),AI231:AV231)-MIN(AI231:AV231)) | IF(OR(AD231="",AC231="Not started",AC231=""),"",IFERROR(AD231-IF(VLOOKUP(AC231,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC231,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F231="","",IF(OR(AA231="Cancelled",AC231="Cancelled"),"Cancelled",IF(OR(AC231="Completed / Handover",Y231<>"",Z231>=100),"Completed — on track",IF(O231="Not awarded",IF(U231="",IF(X231="","No planned date",IF(TODAY()>X231,"Behind — past planned date",IF(X231-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U231,"Behind — award date passed",IF(U231-TODAY()<=30,"At risk — close to off track","On track"))),IF(X231="","No planned date",IF(AND(TODAY()>X231,OR(Z231="",Z231<100)),"Behind — past end date",IF(AND(T231<>"",X231<>"",Z231<>"",(Z231<100),((TODAY()-T231)/MAX(X231-T231,1)*100)-Z231>15),"Behind — progress lag",IF(AND(X231-TODAY()<=30,X231-TODAY()>=0,OR(Z231="",Z231<90)),"At risk — close to off track","On track")))))))) | IF(OR(F231="",AC231="Completed / Handover",AC231="Cancelled"),"",IF(O231="Not awarded",IF(U231<>"",U231-TODAY(),IF(X231="","",X231-TODAY())),IF(X231="","",X231-TODAY()))) | [14 empty] | IF(OR(F231="",AJ231=""),"",IF(COUNT(AI231:AI231)=0,"",AJ231-LOOKUP(2,1/(AI231:AI231<>""),AI231:AI231))) | IF(OR(F231="",AK231=""),"",IF(COUNT(AI231:AJ231)=0,"",AK231-LOOKUP(2,1/(AI231:AJ231<>""),AI231:AJ231))) | IF(OR(F231="",AL231=""),"",IF(COUNT(AI231:AK231)=0,"",AL231-LOOKUP(2,1/(AI231:AK231<>""),AI231:AK231))) | IF(OR(F231="",AM231=""),"",IF(COUNT(AI231:AL231)=0,"",AM231-LOOKUP(2,1/(AI231:AL231<>""),AI231:AL231))) | IF(OR(F231="",AN231=""),"",IF(COUNT(AI231:AM231)=0,"",AN231-LOOKUP(2,1/(AI231:AM231<>""),AI231:AM231))) | IF(OR(F231="",AO231=""),"",IF(COUNT(AI231:AN231)=0,"",AO231-LOOKUP(2,1/(AI231:AN231<>""),AI231:AN231))) | IF(OR(F231="",AP231=""),"",IF(COUNT(AI231:AO231)=0,"",AP231-LOOKUP(2,1/(AI231:AO231<>""),AI231:AO231))) | IF(OR(F231="",AQ231=""),"",IF(COUNT(AI231:AP231)=0,"",AQ231-LOOKUP(2,1/(AI231:AP231<>""),AI231:AP231))) | IF(OR(F231="",AR231=""),"",IF(COUNT(AI231:AQ231)=0,"",AR231-LOOKUP(2,1/(AI231:AQ231<>""),AI231:AQ231))) | IF(OR(F231="",AS231=""),"",IF(COUNT(AI231:AR231)=0,"",AS231-LOOKUP(2,1/(AI231:AR231<>""),AI231:AR231))) | IF(OR(F231="",AT231=""),"",IF(COUNT(AI231:AS231)=0,"",AT231-LOOKUP(2,1/(AI231:AS231<>""),AI231:AS231))) | IF(OR(F231="",AU231=""),"",IF(COUNT(AI231:AT231)=0,"",AU231-LOOKUP(2,1/(AI231:AT231<>""),AI231:AT231))) | IF(OR(F231="",AV231=""),"",IF(COUNT(AI231:AU231)=0,"",AV231-LOOKUP(2,1/(AI231:AU231<>""),AI231:AU231))) | IF(J231="","All_Provinces",IFERROR(VLOOKUP(J231,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K231="","All_Districts",IFERROR(VLOOKUP(K231,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F232="","",ROW()-3) | [18 empty] | IF(AQ232="","",AQ232) |  |  |  | IF(W232<>"",W232,IF(OR(T232="",V232=""),"",EDATE(T232,V232))) |  |  |  |  | IF(F232="","",IF(COUNT(AI232:AV232)=0,IF(AA232="","Not started",AA232),SUBSTITUTE(LOOKUP(2,1/(AI232:AV232<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F232="",COUNT(AI232:AV232)=0),"",TODAY()-LOOKUP(2,1/(AI232:AV232<>""),AI232:AV232)) | IF(OR(F232="",COUNT(AI232:AV232)<2),"",LOOKUP(2,1/(AI232:AV232<>""),AI232:AV232)-MIN(AI232:AV232)) | IF(OR(AD232="",AC232="Not started",AC232=""),"",IFERROR(AD232-IF(VLOOKUP(AC232,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC232,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F232="","",IF(OR(AA232="Cancelled",AC232="Cancelled"),"Cancelled",IF(OR(AC232="Completed / Handover",Y232<>"",Z232>=100),"Completed — on track",IF(O232="Not awarded",IF(U232="",IF(X232="","No planned date",IF(TODAY()>X232,"Behind — past planned date",IF(X232-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U232,"Behind — award date passed",IF(U232-TODAY()<=30,"At risk — close to off track","On track"))),IF(X232="","No planned date",IF(AND(TODAY()>X232,OR(Z232="",Z232<100)),"Behind — past end date",IF(AND(T232<>"",X232<>"",Z232<>"",(Z232<100),((TODAY()-T232)/MAX(X232-T232,1)*100)-Z232>15),"Behind — progress lag",IF(AND(X232-TODAY()<=30,X232-TODAY()>=0,OR(Z232="",Z232<90)),"At risk — close to off track","On track")))))))) | IF(OR(F232="",AC232="Completed / Handover",AC232="Cancelled"),"",IF(O232="Not awarded",IF(U232<>"",U232-TODAY(),IF(X232="","",X232-TODAY())),IF(X232="","",X232-TODAY()))) | [14 empty] | IF(OR(F232="",AJ232=""),"",IF(COUNT(AI232:AI232)=0,"",AJ232-LOOKUP(2,1/(AI232:AI232<>""),AI232:AI232))) | IF(OR(F232="",AK232=""),"",IF(COUNT(AI232:AJ232)=0,"",AK232-LOOKUP(2,1/(AI232:AJ232<>""),AI232:AJ232))) | IF(OR(F232="",AL232=""),"",IF(COUNT(AI232:AK232)=0,"",AL232-LOOKUP(2,1/(AI232:AK232<>""),AI232:AK232))) | IF(OR(F232="",AM232=""),"",IF(COUNT(AI232:AL232)=0,"",AM232-LOOKUP(2,1/(AI232:AL232<>""),AI232:AL232))) | IF(OR(F232="",AN232=""),"",IF(COUNT(AI232:AM232)=0,"",AN232-LOOKUP(2,1/(AI232:AM232<>""),AI232:AM232))) | IF(OR(F232="",AO232=""),"",IF(COUNT(AI232:AN232)=0,"",AO232-LOOKUP(2,1/(AI232:AN232<>""),AI232:AN232))) | IF(OR(F232="",AP232=""),"",IF(COUNT(AI232:AO232)=0,"",AP232-LOOKUP(2,1/(AI232:AO232<>""),AI232:AO232))) | IF(OR(F232="",AQ232=""),"",IF(COUNT(AI232:AP232)=0,"",AQ232-LOOKUP(2,1/(AI232:AP232<>""),AI232:AP232))) | IF(OR(F232="",AR232=""),"",IF(COUNT(AI232:AQ232)=0,"",AR232-LOOKUP(2,1/(AI232:AQ232<>""),AI232:AQ232))) | IF(OR(F232="",AS232=""),"",IF(COUNT(AI232:AR232)=0,"",AS232-LOOKUP(2,1/(AI232:AR232<>""),AI232:AR232))) | IF(OR(F232="",AT232=""),"",IF(COUNT(AI232:AS232)=0,"",AT232-LOOKUP(2,1/(AI232:AS232<>""),AI232:AS232))) | IF(OR(F232="",AU232=""),"",IF(COUNT(AI232:AT232)=0,"",AU232-LOOKUP(2,1/(AI232:AT232<>""),AI232:AT232))) | IF(OR(F232="",AV232=""),"",IF(COUNT(AI232:AU232)=0,"",AV232-LOOKUP(2,1/(AI232:AU232<>""),AI232:AU232))) | IF(J232="","All_Provinces",IFERROR(VLOOKUP(J232,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K232="","All_Districts",IFERROR(VLOOKUP(K232,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F233="","",ROW()-3) | [18 empty] | IF(AQ233="","",AQ233) |  |  |  | IF(W233<>"",W233,IF(OR(T233="",V233=""),"",EDATE(T233,V233))) |  |  |  |  | IF(F233="","",IF(COUNT(AI233:AV233)=0,IF(AA233="","Not started",AA233),SUBSTITUTE(LOOKUP(2,1/(AI233:AV233<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F233="",COUNT(AI233:AV233)=0),"",TODAY()-LOOKUP(2,1/(AI233:AV233<>""),AI233:AV233)) | IF(OR(F233="",COUNT(AI233:AV233)<2),"",LOOKUP(2,1/(AI233:AV233<>""),AI233:AV233)-MIN(AI233:AV233)) | IF(OR(AD233="",AC233="Not started",AC233=""),"",IFERROR(AD233-IF(VLOOKUP(AC233,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC233,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F233="","",IF(OR(AA233="Cancelled",AC233="Cancelled"),"Cancelled",IF(OR(AC233="Completed / Handover",Y233<>"",Z233>=100),"Completed — on track",IF(O233="Not awarded",IF(U233="",IF(X233="","No planned date",IF(TODAY()>X233,"Behind — past planned date",IF(X233-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U233,"Behind — award date passed",IF(U233-TODAY()<=30,"At risk — close to off track","On track"))),IF(X233="","No planned date",IF(AND(TODAY()>X233,OR(Z233="",Z233<100)),"Behind — past end date",IF(AND(T233<>"",X233<>"",Z233<>"",(Z233<100),((TODAY()-T233)/MAX(X233-T233,1)*100)-Z233>15),"Behind — progress lag",IF(AND(X233-TODAY()<=30,X233-TODAY()>=0,OR(Z233="",Z233<90)),"At risk — close to off track","On track")))))))) | IF(OR(F233="",AC233="Completed / Handover",AC233="Cancelled"),"",IF(O233="Not awarded",IF(U233<>"",U233-TODAY(),IF(X233="","",X233-TODAY())),IF(X233="","",X233-TODAY()))) | [14 empty] | IF(OR(F233="",AJ233=""),"",IF(COUNT(AI233:AI233)=0,"",AJ233-LOOKUP(2,1/(AI233:AI233<>""),AI233:AI233))) | IF(OR(F233="",AK233=""),"",IF(COUNT(AI233:AJ233)=0,"",AK233-LOOKUP(2,1/(AI233:AJ233<>""),AI233:AJ233))) | IF(OR(F233="",AL233=""),"",IF(COUNT(AI233:AK233)=0,"",AL233-LOOKUP(2,1/(AI233:AK233<>""),AI233:AK233))) | IF(OR(F233="",AM233=""),"",IF(COUNT(AI233:AL233)=0,"",AM233-LOOKUP(2,1/(AI233:AL233<>""),AI233:AL233))) | IF(OR(F233="",AN233=""),"",IF(COUNT(AI233:AM233)=0,"",AN233-LOOKUP(2,1/(AI233:AM233<>""),AI233:AM233))) | IF(OR(F233="",AO233=""),"",IF(COUNT(AI233:AN233)=0,"",AO233-LOOKUP(2,1/(AI233:AN233<>""),AI233:AN233))) | IF(OR(F233="",AP233=""),"",IF(COUNT(AI233:AO233)=0,"",AP233-LOOKUP(2,1/(AI233:AO233<>""),AI233:AO233))) | IF(OR(F233="",AQ233=""),"",IF(COUNT(AI233:AP233)=0,"",AQ233-LOOKUP(2,1/(AI233:AP233<>""),AI233:AP233))) | IF(OR(F233="",AR233=""),"",IF(COUNT(AI233:AQ233)=0,"",AR233-LOOKUP(2,1/(AI233:AQ233<>""),AI233:AQ233))) | IF(OR(F233="",AS233=""),"",IF(COUNT(AI233:AR233)=0,"",AS233-LOOKUP(2,1/(AI233:AR233<>""),AI233:AR233))) | IF(OR(F233="",AT233=""),"",IF(COUNT(AI233:AS233)=0,"",AT233-LOOKUP(2,1/(AI233:AS233<>""),AI233:AS233))) | IF(OR(F233="",AU233=""),"",IF(COUNT(AI233:AT233)=0,"",AU233-LOOKUP(2,1/(AI233:AT233<>""),AI233:AT233))) | IF(OR(F233="",AV233=""),"",IF(COUNT(AI233:AU233)=0,"",AV233-LOOKUP(2,1/(AI233:AU233<>""),AI233:AU233))) | IF(J233="","All_Provinces",IFERROR(VLOOKUP(J233,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K233="","All_Districts",IFERROR(VLOOKUP(K233,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F234="","",ROW()-3) | [18 empty] | IF(AQ234="","",AQ234) |  |  |  | IF(W234<>"",W234,IF(OR(T234="",V234=""),"",EDATE(T234,V234))) |  |  |  |  | IF(F234="","",IF(COUNT(AI234:AV234)=0,IF(AA234="","Not started",AA234),SUBSTITUTE(LOOKUP(2,1/(AI234:AV234<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F234="",COUNT(AI234:AV234)=0),"",TODAY()-LOOKUP(2,1/(AI234:AV234<>""),AI234:AV234)) | IF(OR(F234="",COUNT(AI234:AV234)<2),"",LOOKUP(2,1/(AI234:AV234<>""),AI234:AV234)-MIN(AI234:AV234)) | IF(OR(AD234="",AC234="Not started",AC234=""),"",IFERROR(AD234-IF(VLOOKUP(AC234,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC234,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F234="","",IF(OR(AA234="Cancelled",AC234="Cancelled"),"Cancelled",IF(OR(AC234="Completed / Handover",Y234<>"",Z234>=100),"Completed — on track",IF(O234="Not awarded",IF(U234="",IF(X234="","No planned date",IF(TODAY()>X234,"Behind — past planned date",IF(X234-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U234,"Behind — award date passed",IF(U234-TODAY()<=30,"At risk — close to off track","On track"))),IF(X234="","No planned date",IF(AND(TODAY()>X234,OR(Z234="",Z234<100)),"Behind — past end date",IF(AND(T234<>"",X234<>"",Z234<>"",(Z234<100),((TODAY()-T234)/MAX(X234-T234,1)*100)-Z234>15),"Behind — progress lag",IF(AND(X234-TODAY()<=30,X234-TODAY()>=0,OR(Z234="",Z234<90)),"At risk — close to off track","On track")))))))) | IF(OR(F234="",AC234="Completed / Handover",AC234="Cancelled"),"",IF(O234="Not awarded",IF(U234<>"",U234-TODAY(),IF(X234="","",X234-TODAY())),IF(X234="","",X234-TODAY()))) | [14 empty] | IF(OR(F234="",AJ234=""),"",IF(COUNT(AI234:AI234)=0,"",AJ234-LOOKUP(2,1/(AI234:AI234<>""),AI234:AI234))) | IF(OR(F234="",AK234=""),"",IF(COUNT(AI234:AJ234)=0,"",AK234-LOOKUP(2,1/(AI234:AJ234<>""),AI234:AJ234))) | IF(OR(F234="",AL234=""),"",IF(COUNT(AI234:AK234)=0,"",AL234-LOOKUP(2,1/(AI234:AK234<>""),AI234:AK234))) | IF(OR(F234="",AM234=""),"",IF(COUNT(AI234:AL234)=0,"",AM234-LOOKUP(2,1/(AI234:AL234<>""),AI234:AL234))) | IF(OR(F234="",AN234=""),"",IF(COUNT(AI234:AM234)=0,"",AN234-LOOKUP(2,1/(AI234:AM234<>""),AI234:AM234))) | IF(OR(F234="",AO234=""),"",IF(COUNT(AI234:AN234)=0,"",AO234-LOOKUP(2,1/(AI234:AN234<>""),AI234:AN234))) | IF(OR(F234="",AP234=""),"",IF(COUNT(AI234:AO234)=0,"",AP234-LOOKUP(2,1/(AI234:AO234<>""),AI234:AO234))) | IF(OR(F234="",AQ234=""),"",IF(COUNT(AI234:AP234)=0,"",AQ234-LOOKUP(2,1/(AI234:AP234<>""),AI234:AP234))) | IF(OR(F234="",AR234=""),"",IF(COUNT(AI234:AQ234)=0,"",AR234-LOOKUP(2,1/(AI234:AQ234<>""),AI234:AQ234))) | IF(OR(F234="",AS234=""),"",IF(COUNT(AI234:AR234)=0,"",AS234-LOOKUP(2,1/(AI234:AR234<>""),AI234:AR234))) | IF(OR(F234="",AT234=""),"",IF(COUNT(AI234:AS234)=0,"",AT234-LOOKUP(2,1/(AI234:AS234<>""),AI234:AS234))) | IF(OR(F234="",AU234=""),"",IF(COUNT(AI234:AT234)=0,"",AU234-LOOKUP(2,1/(AI234:AT234<>""),AI234:AT234))) | IF(OR(F234="",AV234=""),"",IF(COUNT(AI234:AU234)=0,"",AV234-LOOKUP(2,1/(AI234:AU234<>""),AI234:AU234))) | IF(J234="","All_Provinces",IFERROR(VLOOKUP(J234,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K234="","All_Districts",IFERROR(VLOOKUP(K234,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F235="","",ROW()-3) | [18 empty] | IF(AQ235="","",AQ235) |  |  |  | IF(W235<>"",W235,IF(OR(T235="",V235=""),"",EDATE(T235,V235))) |  |  |  |  | IF(F235="","",IF(COUNT(AI235:AV235)=0,IF(AA235="","Not started",AA235),SUBSTITUTE(LOOKUP(2,1/(AI235:AV235<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F235="",COUNT(AI235:AV235)=0),"",TODAY()-LOOKUP(2,1/(AI235:AV235<>""),AI235:AV235)) | IF(OR(F235="",COUNT(AI235:AV235)<2),"",LOOKUP(2,1/(AI235:AV235<>""),AI235:AV235)-MIN(AI235:AV235)) | IF(OR(AD235="",AC235="Not started",AC235=""),"",IFERROR(AD235-IF(VLOOKUP(AC235,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC235,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F235="","",IF(OR(AA235="Cancelled",AC235="Cancelled"),"Cancelled",IF(OR(AC235="Completed / Handover",Y235<>"",Z235>=100),"Completed — on track",IF(O235="Not awarded",IF(U235="",IF(X235="","No planned date",IF(TODAY()>X235,"Behind — past planned date",IF(X235-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U235,"Behind — award date passed",IF(U235-TODAY()<=30,"At risk — close to off track","On track"))),IF(X235="","No planned date",IF(AND(TODAY()>X235,OR(Z235="",Z235<100)),"Behind — past end date",IF(AND(T235<>"",X235<>"",Z235<>"",(Z235<100),((TODAY()-T235)/MAX(X235-T235,1)*100)-Z235>15),"Behind — progress lag",IF(AND(X235-TODAY()<=30,X235-TODAY()>=0,OR(Z235="",Z235<90)),"At risk — close to off track","On track")))))))) | IF(OR(F235="",AC235="Completed / Handover",AC235="Cancelled"),"",IF(O235="Not awarded",IF(U235<>"",U235-TODAY(),IF(X235="","",X235-TODAY())),IF(X235="","",X235-TODAY()))) | [14 empty] | IF(OR(F235="",AJ235=""),"",IF(COUNT(AI235:AI235)=0,"",AJ235-LOOKUP(2,1/(AI235:AI235<>""),AI235:AI235))) | IF(OR(F235="",AK235=""),"",IF(COUNT(AI235:AJ235)=0,"",AK235-LOOKUP(2,1/(AI235:AJ235<>""),AI235:AJ235))) | IF(OR(F235="",AL235=""),"",IF(COUNT(AI235:AK235)=0,"",AL235-LOOKUP(2,1/(AI235:AK235<>""),AI235:AK235))) | IF(OR(F235="",AM235=""),"",IF(COUNT(AI235:AL235)=0,"",AM235-LOOKUP(2,1/(AI235:AL235<>""),AI235:AL235))) | IF(OR(F235="",AN235=""),"",IF(COUNT(AI235:AM235)=0,"",AN235-LOOKUP(2,1/(AI235:AM235<>""),AI235:AM235))) | IF(OR(F235="",AO235=""),"",IF(COUNT(AI235:AN235)=0,"",AO235-LOOKUP(2,1/(AI235:AN235<>""),AI235:AN235))) | IF(OR(F235="",AP235=""),"",IF(COUNT(AI235:AO235)=0,"",AP235-LOOKUP(2,1/(AI235:AO235<>""),AI235:AO235))) | IF(OR(F235="",AQ235=""),"",IF(COUNT(AI235:AP235)=0,"",AQ235-LOOKUP(2,1/(AI235:AP235<>""),AI235:AP235))) | IF(OR(F235="",AR235=""),"",IF(COUNT(AI235:AQ235)=0,"",AR235-LOOKUP(2,1/(AI235:AQ235<>""),AI235:AQ235))) | IF(OR(F235="",AS235=""),"",IF(COUNT(AI235:AR235)=0,"",AS235-LOOKUP(2,1/(AI235:AR235<>""),AI235:AR235))) | IF(OR(F235="",AT235=""),"",IF(COUNT(AI235:AS235)=0,"",AT235-LOOKUP(2,1/(AI235:AS235<>""),AI235:AS235))) | IF(OR(F235="",AU235=""),"",IF(COUNT(AI235:AT235)=0,"",AU235-LOOKUP(2,1/(AI235:AT235<>""),AI235:AT235))) | IF(OR(F235="",AV235=""),"",IF(COUNT(AI235:AU235)=0,"",AV235-LOOKUP(2,1/(AI235:AU235<>""),AI235:AU235))) | IF(J235="","All_Provinces",IFERROR(VLOOKUP(J235,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K235="","All_Districts",IFERROR(VLOOKUP(K235,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F236="","",ROW()-3) | [18 empty] | IF(AQ236="","",AQ236) |  |  |  | IF(W236<>"",W236,IF(OR(T236="",V236=""),"",EDATE(T236,V236))) |  |  |  |  | IF(F236="","",IF(COUNT(AI236:AV236)=0,IF(AA236="","Not started",AA236),SUBSTITUTE(LOOKUP(2,1/(AI236:AV236<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F236="",COUNT(AI236:AV236)=0),"",TODAY()-LOOKUP(2,1/(AI236:AV236<>""),AI236:AV236)) | IF(OR(F236="",COUNT(AI236:AV236)<2),"",LOOKUP(2,1/(AI236:AV236<>""),AI236:AV236)-MIN(AI236:AV236)) | IF(OR(AD236="",AC236="Not started",AC236=""),"",IFERROR(AD236-IF(VLOOKUP(AC236,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC236,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F236="","",IF(OR(AA236="Cancelled",AC236="Cancelled"),"Cancelled",IF(OR(AC236="Completed / Handover",Y236<>"",Z236>=100),"Completed — on track",IF(O236="Not awarded",IF(U236="",IF(X236="","No planned date",IF(TODAY()>X236,"Behind — past planned date",IF(X236-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U236,"Behind — award date passed",IF(U236-TODAY()<=30,"At risk — close to off track","On track"))),IF(X236="","No planned date",IF(AND(TODAY()>X236,OR(Z236="",Z236<100)),"Behind — past end date",IF(AND(T236<>"",X236<>"",Z236<>"",(Z236<100),((TODAY()-T236)/MAX(X236-T236,1)*100)-Z236>15),"Behind — progress lag",IF(AND(X236-TODAY()<=30,X236-TODAY()>=0,OR(Z236="",Z236<90)),"At risk — close to off track","On track")))))))) | IF(OR(F236="",AC236="Completed / Handover",AC236="Cancelled"),"",IF(O236="Not awarded",IF(U236<>"",U236-TODAY(),IF(X236="","",X236-TODAY())),IF(X236="","",X236-TODAY()))) | [14 empty] | IF(OR(F236="",AJ236=""),"",IF(COUNT(AI236:AI236)=0,"",AJ236-LOOKUP(2,1/(AI236:AI236<>""),AI236:AI236))) | IF(OR(F236="",AK236=""),"",IF(COUNT(AI236:AJ236)=0,"",AK236-LOOKUP(2,1/(AI236:AJ236<>""),AI236:AJ236))) | IF(OR(F236="",AL236=""),"",IF(COUNT(AI236:AK236)=0,"",AL236-LOOKUP(2,1/(AI236:AK236<>""),AI236:AK236))) | IF(OR(F236="",AM236=""),"",IF(COUNT(AI236:AL236)=0,"",AM236-LOOKUP(2,1/(AI236:AL236<>""),AI236:AL236))) | IF(OR(F236="",AN236=""),"",IF(COUNT(AI236:AM236)=0,"",AN236-LOOKUP(2,1/(AI236:AM236<>""),AI236:AM236))) | IF(OR(F236="",AO236=""),"",IF(COUNT(AI236:AN236)=0,"",AO236-LOOKUP(2,1/(AI236:AN236<>""),AI236:AN236))) | IF(OR(F236="",AP236=""),"",IF(COUNT(AI236:AO236)=0,"",AP236-LOOKUP(2,1/(AI236:AO236<>""),AI236:AO236))) | IF(OR(F236="",AQ236=""),"",IF(COUNT(AI236:AP236)=0,"",AQ236-LOOKUP(2,1/(AI236:AP236<>""),AI236:AP236))) | IF(OR(F236="",AR236=""),"",IF(COUNT(AI236:AQ236)=0,"",AR236-LOOKUP(2,1/(AI236:AQ236<>""),AI236:AQ236))) | IF(OR(F236="",AS236=""),"",IF(COUNT(AI236:AR236)=0,"",AS236-LOOKUP(2,1/(AI236:AR236<>""),AI236:AR236))) | IF(OR(F236="",AT236=""),"",IF(COUNT(AI236:AS236)=0,"",AT236-LOOKUP(2,1/(AI236:AS236<>""),AI236:AS236))) | IF(OR(F236="",AU236=""),"",IF(COUNT(AI236:AT236)=0,"",AU236-LOOKUP(2,1/(AI236:AT236<>""),AI236:AT236))) | IF(OR(F236="",AV236=""),"",IF(COUNT(AI236:AU236)=0,"",AV236-LOOKUP(2,1/(AI236:AU236<>""),AI236:AU236))) | IF(J236="","All_Provinces",IFERROR(VLOOKUP(J236,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K236="","All_Districts",IFERROR(VLOOKUP(K236,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F237="","",ROW()-3) | [18 empty] | IF(AQ237="","",AQ237) |  |  |  | IF(W237<>"",W237,IF(OR(T237="",V237=""),"",EDATE(T237,V237))) |  |  |  |  | IF(F237="","",IF(COUNT(AI237:AV237)=0,IF(AA237="","Not started",AA237),SUBSTITUTE(LOOKUP(2,1/(AI237:AV237<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F237="",COUNT(AI237:AV237)=0),"",TODAY()-LOOKUP(2,1/(AI237:AV237<>""),AI237:AV237)) | IF(OR(F237="",COUNT(AI237:AV237)<2),"",LOOKUP(2,1/(AI237:AV237<>""),AI237:AV237)-MIN(AI237:AV237)) | IF(OR(AD237="",AC237="Not started",AC237=""),"",IFERROR(AD237-IF(VLOOKUP(AC237,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC237,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F237="","",IF(OR(AA237="Cancelled",AC237="Cancelled"),"Cancelled",IF(OR(AC237="Completed / Handover",Y237<>"",Z237>=100),"Completed — on track",IF(O237="Not awarded",IF(U237="",IF(X237="","No planned date",IF(TODAY()>X237,"Behind — past planned date",IF(X237-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U237,"Behind — award date passed",IF(U237-TODAY()<=30,"At risk — close to off track","On track"))),IF(X237="","No planned date",IF(AND(TODAY()>X237,OR(Z237="",Z237<100)),"Behind — past end date",IF(AND(T237<>"",X237<>"",Z237<>"",(Z237<100),((TODAY()-T237)/MAX(X237-T237,1)*100)-Z237>15),"Behind — progress lag",IF(AND(X237-TODAY()<=30,X237-TODAY()>=0,OR(Z237="",Z237<90)),"At risk — close to off track","On track")))))))) | IF(OR(F237="",AC237="Completed / Handover",AC237="Cancelled"),"",IF(O237="Not awarded",IF(U237<>"",U237-TODAY(),IF(X237="","",X237-TODAY())),IF(X237="","",X237-TODAY()))) | [14 empty] | IF(OR(F237="",AJ237=""),"",IF(COUNT(AI237:AI237)=0,"",AJ237-LOOKUP(2,1/(AI237:AI237<>""),AI237:AI237))) | IF(OR(F237="",AK237=""),"",IF(COUNT(AI237:AJ237)=0,"",AK237-LOOKUP(2,1/(AI237:AJ237<>""),AI237:AJ237))) | IF(OR(F237="",AL237=""),"",IF(COUNT(AI237:AK237)=0,"",AL237-LOOKUP(2,1/(AI237:AK237<>""),AI237:AK237))) | IF(OR(F237="",AM237=""),"",IF(COUNT(AI237:AL237)=0,"",AM237-LOOKUP(2,1/(AI237:AL237<>""),AI237:AL237))) | IF(OR(F237="",AN237=""),"",IF(COUNT(AI237:AM237)=0,"",AN237-LOOKUP(2,1/(AI237:AM237<>""),AI237:AM237))) | IF(OR(F237="",AO237=""),"",IF(COUNT(AI237:AN237)=0,"",AO237-LOOKUP(2,1/(AI237:AN237<>""),AI237:AN237))) | IF(OR(F237="",AP237=""),"",IF(COUNT(AI237:AO237)=0,"",AP237-LOOKUP(2,1/(AI237:AO237<>""),AI237:AO237))) | IF(OR(F237="",AQ237=""),"",IF(COUNT(AI237:AP237)=0,"",AQ237-LOOKUP(2,1/(AI237:AP237<>""),AI237:AP237))) | IF(OR(F237="",AR237=""),"",IF(COUNT(AI237:AQ237)=0,"",AR237-LOOKUP(2,1/(AI237:AQ237<>""),AI237:AQ237))) | IF(OR(F237="",AS237=""),"",IF(COUNT(AI237:AR237)=0,"",AS237-LOOKUP(2,1/(AI237:AR237<>""),AI237:AR237))) | IF(OR(F237="",AT237=""),"",IF(COUNT(AI237:AS237)=0,"",AT237-LOOKUP(2,1/(AI237:AS237<>""),AI237:AS237))) | IF(OR(F237="",AU237=""),"",IF(COUNT(AI237:AT237)=0,"",AU237-LOOKUP(2,1/(AI237:AT237<>""),AI237:AT237))) | IF(OR(F237="",AV237=""),"",IF(COUNT(AI237:AU237)=0,"",AV237-LOOKUP(2,1/(AI237:AU237<>""),AI237:AU237))) | IF(J237="","All_Provinces",IFERROR(VLOOKUP(J237,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K237="","All_Districts",IFERROR(VLOOKUP(K237,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F238="","",ROW()-3) | [18 empty] | IF(AQ238="","",AQ238) |  |  |  | IF(W238<>"",W238,IF(OR(T238="",V238=""),"",EDATE(T238,V238))) |  |  |  |  | IF(F238="","",IF(COUNT(AI238:AV238)=0,IF(AA238="","Not started",AA238),SUBSTITUTE(LOOKUP(2,1/(AI238:AV238<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F238="",COUNT(AI238:AV238)=0),"",TODAY()-LOOKUP(2,1/(AI238:AV238<>""),AI238:AV238)) | IF(OR(F238="",COUNT(AI238:AV238)<2),"",LOOKUP(2,1/(AI238:AV238<>""),AI238:AV238)-MIN(AI238:AV238)) | IF(OR(AD238="",AC238="Not started",AC238=""),"",IFERROR(AD238-IF(VLOOKUP(AC238,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC238,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F238="","",IF(OR(AA238="Cancelled",AC238="Cancelled"),"Cancelled",IF(OR(AC238="Completed / Handover",Y238<>"",Z238>=100),"Completed — on track",IF(O238="Not awarded",IF(U238="",IF(X238="","No planned date",IF(TODAY()>X238,"Behind — past planned date",IF(X238-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U238,"Behind — award date passed",IF(U238-TODAY()<=30,"At risk — close to off track","On track"))),IF(X238="","No planned date",IF(AND(TODAY()>X238,OR(Z238="",Z238<100)),"Behind — past end date",IF(AND(T238<>"",X238<>"",Z238<>"",(Z238<100),((TODAY()-T238)/MAX(X238-T238,1)*100)-Z238>15),"Behind — progress lag",IF(AND(X238-TODAY()<=30,X238-TODAY()>=0,OR(Z238="",Z238<90)),"At risk — close to off track","On track")))))))) | IF(OR(F238="",AC238="Completed / Handover",AC238="Cancelled"),"",IF(O238="Not awarded",IF(U238<>"",U238-TODAY(),IF(X238="","",X238-TODAY())),IF(X238="","",X238-TODAY()))) | [14 empty] | IF(OR(F238="",AJ238=""),"",IF(COUNT(AI238:AI238)=0,"",AJ238-LOOKUP(2,1/(AI238:AI238<>""),AI238:AI238))) | IF(OR(F238="",AK238=""),"",IF(COUNT(AI238:AJ238)=0,"",AK238-LOOKUP(2,1/(AI238:AJ238<>""),AI238:AJ238))) | IF(OR(F238="",AL238=""),"",IF(COUNT(AI238:AK238)=0,"",AL238-LOOKUP(2,1/(AI238:AK238<>""),AI238:AK238))) | IF(OR(F238="",AM238=""),"",IF(COUNT(AI238:AL238)=0,"",AM238-LOOKUP(2,1/(AI238:AL238<>""),AI238:AL238))) | IF(OR(F238="",AN238=""),"",IF(COUNT(AI238:AM238)=0,"",AN238-LOOKUP(2,1/(AI238:AM238<>""),AI238:AM238))) | IF(OR(F238="",AO238=""),"",IF(COUNT(AI238:AN238)=0,"",AO238-LOOKUP(2,1/(AI238:AN238<>""),AI238:AN238))) | IF(OR(F238="",AP238=""),"",IF(COUNT(AI238:AO238)=0,"",AP238-LOOKUP(2,1/(AI238:AO238<>""),AI238:AO238))) | IF(OR(F238="",AQ238=""),"",IF(COUNT(AI238:AP238)=0,"",AQ238-LOOKUP(2,1/(AI238:AP238<>""),AI238:AP238))) | IF(OR(F238="",AR238=""),"",IF(COUNT(AI238:AQ238)=0,"",AR238-LOOKUP(2,1/(AI238:AQ238<>""),AI238:AQ238))) | IF(OR(F238="",AS238=""),"",IF(COUNT(AI238:AR238)=0,"",AS238-LOOKUP(2,1/(AI238:AR238<>""),AI238:AR238))) | IF(OR(F238="",AT238=""),"",IF(COUNT(AI238:AS238)=0,"",AT238-LOOKUP(2,1/(AI238:AS238<>""),AI238:AS238))) | IF(OR(F238="",AU238=""),"",IF(COUNT(AI238:AT238)=0,"",AU238-LOOKUP(2,1/(AI238:AT238<>""),AI238:AT238))) | IF(OR(F238="",AV238=""),"",IF(COUNT(AI238:AU238)=0,"",AV238-LOOKUP(2,1/(AI238:AU238<>""),AI238:AU238))) | IF(J238="","All_Provinces",IFERROR(VLOOKUP(J238,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K238="","All_Districts",IFERROR(VLOOKUP(K238,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F239="","",ROW()-3) | [18 empty] | IF(AQ239="","",AQ239) |  |  |  | IF(W239<>"",W239,IF(OR(T239="",V239=""),"",EDATE(T239,V239))) |  |  |  |  | IF(F239="","",IF(COUNT(AI239:AV239)=0,IF(AA239="","Not started",AA239),SUBSTITUTE(LOOKUP(2,1/(AI239:AV239<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F239="",COUNT(AI239:AV239)=0),"",TODAY()-LOOKUP(2,1/(AI239:AV239<>""),AI239:AV239)) | IF(OR(F239="",COUNT(AI239:AV239)<2),"",LOOKUP(2,1/(AI239:AV239<>""),AI239:AV239)-MIN(AI239:AV239)) | IF(OR(AD239="",AC239="Not started",AC239=""),"",IFERROR(AD239-IF(VLOOKUP(AC239,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC239,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F239="","",IF(OR(AA239="Cancelled",AC239="Cancelled"),"Cancelled",IF(OR(AC239="Completed / Handover",Y239<>"",Z239>=100),"Completed — on track",IF(O239="Not awarded",IF(U239="",IF(X239="","No planned date",IF(TODAY()>X239,"Behind — past planned date",IF(X239-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U239,"Behind — award date passed",IF(U239-TODAY()<=30,"At risk — close to off track","On track"))),IF(X239="","No planned date",IF(AND(TODAY()>X239,OR(Z239="",Z239<100)),"Behind — past end date",IF(AND(T239<>"",X239<>"",Z239<>"",(Z239<100),((TODAY()-T239)/MAX(X239-T239,1)*100)-Z239>15),"Behind — progress lag",IF(AND(X239-TODAY()<=30,X239-TODAY()>=0,OR(Z239="",Z239<90)),"At risk — close to off track","On track")))))))) | IF(OR(F239="",AC239="Completed / Handover",AC239="Cancelled"),"",IF(O239="Not awarded",IF(U239<>"",U239-TODAY(),IF(X239="","",X239-TODAY())),IF(X239="","",X239-TODAY()))) | [14 empty] | IF(OR(F239="",AJ239=""),"",IF(COUNT(AI239:AI239)=0,"",AJ239-LOOKUP(2,1/(AI239:AI239<>""),AI239:AI239))) | IF(OR(F239="",AK239=""),"",IF(COUNT(AI239:AJ239)=0,"",AK239-LOOKUP(2,1/(AI239:AJ239<>""),AI239:AJ239))) | IF(OR(F239="",AL239=""),"",IF(COUNT(AI239:AK239)=0,"",AL239-LOOKUP(2,1/(AI239:AK239<>""),AI239:AK239))) | IF(OR(F239="",AM239=""),"",IF(COUNT(AI239:AL239)=0,"",AM239-LOOKUP(2,1/(AI239:AL239<>""),AI239:AL239))) | IF(OR(F239="",AN239=""),"",IF(COUNT(AI239:AM239)=0,"",AN239-LOOKUP(2,1/(AI239:AM239<>""),AI239:AM239))) | IF(OR(F239="",AO239=""),"",IF(COUNT(AI239:AN239)=0,"",AO239-LOOKUP(2,1/(AI239:AN239<>""),AI239:AN239))) | IF(OR(F239="",AP239=""),"",IF(COUNT(AI239:AO239)=0,"",AP239-LOOKUP(2,1/(AI239:AO239<>""),AI239:AO239))) | IF(OR(F239="",AQ239=""),"",IF(COUNT(AI239:AP239)=0,"",AQ239-LOOKUP(2,1/(AI239:AP239<>""),AI239:AP239))) | IF(OR(F239="",AR239=""),"",IF(COUNT(AI239:AQ239)=0,"",AR239-LOOKUP(2,1/(AI239:AQ239<>""),AI239:AQ239))) | IF(OR(F239="",AS239=""),"",IF(COUNT(AI239:AR239)=0,"",AS239-LOOKUP(2,1/(AI239:AR239<>""),AI239:AR239))) | IF(OR(F239="",AT239=""),"",IF(COUNT(AI239:AS239)=0,"",AT239-LOOKUP(2,1/(AI239:AS239<>""),AI239:AS239))) | IF(OR(F239="",AU239=""),"",IF(COUNT(AI239:AT239)=0,"",AU239-LOOKUP(2,1/(AI239:AT239<>""),AI239:AT239))) | IF(OR(F239="",AV239=""),"",IF(COUNT(AI239:AU239)=0,"",AV239-LOOKUP(2,1/(AI239:AU239<>""),AI239:AU239))) | IF(J239="","All_Provinces",IFERROR(VLOOKUP(J239,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K239="","All_Districts",IFERROR(VLOOKUP(K239,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F240="","",ROW()-3) | [18 empty] | IF(AQ240="","",AQ240) |  |  |  | IF(W240<>"",W240,IF(OR(T240="",V240=""),"",EDATE(T240,V240))) |  |  |  |  | IF(F240="","",IF(COUNT(AI240:AV240)=0,IF(AA240="","Not started",AA240),SUBSTITUTE(LOOKUP(2,1/(AI240:AV240<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F240="",COUNT(AI240:AV240)=0),"",TODAY()-LOOKUP(2,1/(AI240:AV240<>""),AI240:AV240)) | IF(OR(F240="",COUNT(AI240:AV240)<2),"",LOOKUP(2,1/(AI240:AV240<>""),AI240:AV240)-MIN(AI240:AV240)) | IF(OR(AD240="",AC240="Not started",AC240=""),"",IFERROR(AD240-IF(VLOOKUP(AC240,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC240,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F240="","",IF(OR(AA240="Cancelled",AC240="Cancelled"),"Cancelled",IF(OR(AC240="Completed / Handover",Y240<>"",Z240>=100),"Completed — on track",IF(O240="Not awarded",IF(U240="",IF(X240="","No planned date",IF(TODAY()>X240,"Behind — past planned date",IF(X240-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U240,"Behind — award date passed",IF(U240-TODAY()<=30,"At risk — close to off track","On track"))),IF(X240="","No planned date",IF(AND(TODAY()>X240,OR(Z240="",Z240<100)),"Behind — past end date",IF(AND(T240<>"",X240<>"",Z240<>"",(Z240<100),((TODAY()-T240)/MAX(X240-T240,1)*100)-Z240>15),"Behind — progress lag",IF(AND(X240-TODAY()<=30,X240-TODAY()>=0,OR(Z240="",Z240<90)),"At risk — close to off track","On track")))))))) | IF(OR(F240="",AC240="Completed / Handover",AC240="Cancelled"),"",IF(O240="Not awarded",IF(U240<>"",U240-TODAY(),IF(X240="","",X240-TODAY())),IF(X240="","",X240-TODAY()))) | [14 empty] | IF(OR(F240="",AJ240=""),"",IF(COUNT(AI240:AI240)=0,"",AJ240-LOOKUP(2,1/(AI240:AI240<>""),AI240:AI240))) | IF(OR(F240="",AK240=""),"",IF(COUNT(AI240:AJ240)=0,"",AK240-LOOKUP(2,1/(AI240:AJ240<>""),AI240:AJ240))) | IF(OR(F240="",AL240=""),"",IF(COUNT(AI240:AK240)=0,"",AL240-LOOKUP(2,1/(AI240:AK240<>""),AI240:AK240))) | IF(OR(F240="",AM240=""),"",IF(COUNT(AI240:AL240)=0,"",AM240-LOOKUP(2,1/(AI240:AL240<>""),AI240:AL240))) | IF(OR(F240="",AN240=""),"",IF(COUNT(AI240:AM240)=0,"",AN240-LOOKUP(2,1/(AI240:AM240<>""),AI240:AM240))) | IF(OR(F240="",AO240=""),"",IF(COUNT(AI240:AN240)=0,"",AO240-LOOKUP(2,1/(AI240:AN240<>""),AI240:AN240))) | IF(OR(F240="",AP240=""),"",IF(COUNT(AI240:AO240)=0,"",AP240-LOOKUP(2,1/(AI240:AO240<>""),AI240:AO240))) | IF(OR(F240="",AQ240=""),"",IF(COUNT(AI240:AP240)=0,"",AQ240-LOOKUP(2,1/(AI240:AP240<>""),AI240:AP240))) | IF(OR(F240="",AR240=""),"",IF(COUNT(AI240:AQ240)=0,"",AR240-LOOKUP(2,1/(AI240:AQ240<>""),AI240:AQ240))) | IF(OR(F240="",AS240=""),"",IF(COUNT(AI240:AR240)=0,"",AS240-LOOKUP(2,1/(AI240:AR240<>""),AI240:AR240))) | IF(OR(F240="",AT240=""),"",IF(COUNT(AI240:AS240)=0,"",AT240-LOOKUP(2,1/(AI240:AS240<>""),AI240:AS240))) | IF(OR(F240="",AU240=""),"",IF(COUNT(AI240:AT240)=0,"",AU240-LOOKUP(2,1/(AI240:AT240<>""),AI240:AT240))) | IF(OR(F240="",AV240=""),"",IF(COUNT(AI240:AU240)=0,"",AV240-LOOKUP(2,1/(AI240:AU240<>""),AI240:AU240))) | IF(J240="","All_Provinces",IFERROR(VLOOKUP(J240,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K240="","All_Districts",IFERROR(VLOOKUP(K240,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F241="","",ROW()-3) | [18 empty] | IF(AQ241="","",AQ241) |  |  |  | IF(W241<>"",W241,IF(OR(T241="",V241=""),"",EDATE(T241,V241))) |  |  |  |  | IF(F241="","",IF(COUNT(AI241:AV241)=0,IF(AA241="","Not started",AA241),SUBSTITUTE(LOOKUP(2,1/(AI241:AV241<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F241="",COUNT(AI241:AV241)=0),"",TODAY()-LOOKUP(2,1/(AI241:AV241<>""),AI241:AV241)) | IF(OR(F241="",COUNT(AI241:AV241)<2),"",LOOKUP(2,1/(AI241:AV241<>""),AI241:AV241)-MIN(AI241:AV241)) | IF(OR(AD241="",AC241="Not started",AC241=""),"",IFERROR(AD241-IF(VLOOKUP(AC241,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC241,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F241="","",IF(OR(AA241="Cancelled",AC241="Cancelled"),"Cancelled",IF(OR(AC241="Completed / Handover",Y241<>"",Z241>=100),"Completed — on track",IF(O241="Not awarded",IF(U241="",IF(X241="","No planned date",IF(TODAY()>X241,"Behind — past planned date",IF(X241-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U241,"Behind — award date passed",IF(U241-TODAY()<=30,"At risk — close to off track","On track"))),IF(X241="","No planned date",IF(AND(TODAY()>X241,OR(Z241="",Z241<100)),"Behind — past end date",IF(AND(T241<>"",X241<>"",Z241<>"",(Z241<100),((TODAY()-T241)/MAX(X241-T241,1)*100)-Z241>15),"Behind — progress lag",IF(AND(X241-TODAY()<=30,X241-TODAY()>=0,OR(Z241="",Z241<90)),"At risk — close to off track","On track")))))))) | IF(OR(F241="",AC241="Completed / Handover",AC241="Cancelled"),"",IF(O241="Not awarded",IF(U241<>"",U241-TODAY(),IF(X241="","",X241-TODAY())),IF(X241="","",X241-TODAY()))) | [14 empty] | IF(OR(F241="",AJ241=""),"",IF(COUNT(AI241:AI241)=0,"",AJ241-LOOKUP(2,1/(AI241:AI241<>""),AI241:AI241))) | IF(OR(F241="",AK241=""),"",IF(COUNT(AI241:AJ241)=0,"",AK241-LOOKUP(2,1/(AI241:AJ241<>""),AI241:AJ241))) | IF(OR(F241="",AL241=""),"",IF(COUNT(AI241:AK241)=0,"",AL241-LOOKUP(2,1/(AI241:AK241<>""),AI241:AK241))) | IF(OR(F241="",AM241=""),"",IF(COUNT(AI241:AL241)=0,"",AM241-LOOKUP(2,1/(AI241:AL241<>""),AI241:AL241))) | IF(OR(F241="",AN241=""),"",IF(COUNT(AI241:AM241)=0,"",AN241-LOOKUP(2,1/(AI241:AM241<>""),AI241:AM241))) | IF(OR(F241="",AO241=""),"",IF(COUNT(AI241:AN241)=0,"",AO241-LOOKUP(2,1/(AI241:AN241<>""),AI241:AN241))) | IF(OR(F241="",AP241=""),"",IF(COUNT(AI241:AO241)=0,"",AP241-LOOKUP(2,1/(AI241:AO241<>""),AI241:AO241))) | IF(OR(F241="",AQ241=""),"",IF(COUNT(AI241:AP241)=0,"",AQ241-LOOKUP(2,1/(AI241:AP241<>""),AI241:AP241))) | IF(OR(F241="",AR241=""),"",IF(COUNT(AI241:AQ241)=0,"",AR241-LOOKUP(2,1/(AI241:AQ241<>""),AI241:AQ241))) | IF(OR(F241="",AS241=""),"",IF(COUNT(AI241:AR241)=0,"",AS241-LOOKUP(2,1/(AI241:AR241<>""),AI241:AR241))) | IF(OR(F241="",AT241=""),"",IF(COUNT(AI241:AS241)=0,"",AT241-LOOKUP(2,1/(AI241:AS241<>""),AI241:AS241))) | IF(OR(F241="",AU241=""),"",IF(COUNT(AI241:AT241)=0,"",AU241-LOOKUP(2,1/(AI241:AT241<>""),AI241:AT241))) | IF(OR(F241="",AV241=""),"",IF(COUNT(AI241:AU241)=0,"",AV241-LOOKUP(2,1/(AI241:AU241<>""),AI241:AU241))) | IF(J241="","All_Provinces",IFERROR(VLOOKUP(J241,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K241="","All_Districts",IFERROR(VLOOKUP(K241,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F242="","",ROW()-3) | [18 empty] | IF(AQ242="","",AQ242) |  |  |  | IF(W242<>"",W242,IF(OR(T242="",V242=""),"",EDATE(T242,V242))) |  |  |  |  | IF(F242="","",IF(COUNT(AI242:AV242)=0,IF(AA242="","Not started",AA242),SUBSTITUTE(LOOKUP(2,1/(AI242:AV242<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F242="",COUNT(AI242:AV242)=0),"",TODAY()-LOOKUP(2,1/(AI242:AV242<>""),AI242:AV242)) | IF(OR(F242="",COUNT(AI242:AV242)<2),"",LOOKUP(2,1/(AI242:AV242<>""),AI242:AV242)-MIN(AI242:AV242)) | IF(OR(AD242="",AC242="Not started",AC242=""),"",IFERROR(AD242-IF(VLOOKUP(AC242,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC242,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F242="","",IF(OR(AA242="Cancelled",AC242="Cancelled"),"Cancelled",IF(OR(AC242="Completed / Handover",Y242<>"",Z242>=100),"Completed — on track",IF(O242="Not awarded",IF(U242="",IF(X242="","No planned date",IF(TODAY()>X242,"Behind — past planned date",IF(X242-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U242,"Behind — award date passed",IF(U242-TODAY()<=30,"At risk — close to off track","On track"))),IF(X242="","No planned date",IF(AND(TODAY()>X242,OR(Z242="",Z242<100)),"Behind — past end date",IF(AND(T242<>"",X242<>"",Z242<>"",(Z242<100),((TODAY()-T242)/MAX(X242-T242,1)*100)-Z242>15),"Behind — progress lag",IF(AND(X242-TODAY()<=30,X242-TODAY()>=0,OR(Z242="",Z242<90)),"At risk — close to off track","On track")))))))) | IF(OR(F242="",AC242="Completed / Handover",AC242="Cancelled"),"",IF(O242="Not awarded",IF(U242<>"",U242-TODAY(),IF(X242="","",X242-TODAY())),IF(X242="","",X242-TODAY()))) | [14 empty] | IF(OR(F242="",AJ242=""),"",IF(COUNT(AI242:AI242)=0,"",AJ242-LOOKUP(2,1/(AI242:AI242<>""),AI242:AI242))) | IF(OR(F242="",AK242=""),"",IF(COUNT(AI242:AJ242)=0,"",AK242-LOOKUP(2,1/(AI242:AJ242<>""),AI242:AJ242))) | IF(OR(F242="",AL242=""),"",IF(COUNT(AI242:AK242)=0,"",AL242-LOOKUP(2,1/(AI242:AK242<>""),AI242:AK242))) | IF(OR(F242="",AM242=""),"",IF(COUNT(AI242:AL242)=0,"",AM242-LOOKUP(2,1/(AI242:AL242<>""),AI242:AL242))) | IF(OR(F242="",AN242=""),"",IF(COUNT(AI242:AM242)=0,"",AN242-LOOKUP(2,1/(AI242:AM242<>""),AI242:AM242))) | IF(OR(F242="",AO242=""),"",IF(COUNT(AI242:AN242)=0,"",AO242-LOOKUP(2,1/(AI242:AN242<>""),AI242:AN242))) | IF(OR(F242="",AP242=""),"",IF(COUNT(AI242:AO242)=0,"",AP242-LOOKUP(2,1/(AI242:AO242<>""),AI242:AO242))) | IF(OR(F242="",AQ242=""),"",IF(COUNT(AI242:AP242)=0,"",AQ242-LOOKUP(2,1/(AI242:AP242<>""),AI242:AP242))) | IF(OR(F242="",AR242=""),"",IF(COUNT(AI242:AQ242)=0,"",AR242-LOOKUP(2,1/(AI242:AQ242<>""),AI242:AQ242))) | IF(OR(F242="",AS242=""),"",IF(COUNT(AI242:AR242)=0,"",AS242-LOOKUP(2,1/(AI242:AR242<>""),AI242:AR242))) | IF(OR(F242="",AT242=""),"",IF(COUNT(AI242:AS242)=0,"",AT242-LOOKUP(2,1/(AI242:AS242<>""),AI242:AS242))) | IF(OR(F242="",AU242=""),"",IF(COUNT(AI242:AT242)=0,"",AU242-LOOKUP(2,1/(AI242:AT242<>""),AI242:AT242))) | IF(OR(F242="",AV242=""),"",IF(COUNT(AI242:AU242)=0,"",AV242-LOOKUP(2,1/(AI242:AU242<>""),AI242:AU242))) | IF(J242="","All_Provinces",IFERROR(VLOOKUP(J242,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K242="","All_Districts",IFERROR(VLOOKUP(K242,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F243="","",ROW()-3) | [18 empty] | IF(AQ243="","",AQ243) |  |  |  | IF(W243<>"",W243,IF(OR(T243="",V243=""),"",EDATE(T243,V243))) |  |  |  |  | IF(F243="","",IF(COUNT(AI243:AV243)=0,IF(AA243="","Not started",AA243),SUBSTITUTE(LOOKUP(2,1/(AI243:AV243<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F243="",COUNT(AI243:AV243)=0),"",TODAY()-LOOKUP(2,1/(AI243:AV243<>""),AI243:AV243)) | IF(OR(F243="",COUNT(AI243:AV243)<2),"",LOOKUP(2,1/(AI243:AV243<>""),AI243:AV243)-MIN(AI243:AV243)) | IF(OR(AD243="",AC243="Not started",AC243=""),"",IFERROR(AD243-IF(VLOOKUP(AC243,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC243,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F243="","",IF(OR(AA243="Cancelled",AC243="Cancelled"),"Cancelled",IF(OR(AC243="Completed / Handover",Y243<>"",Z243>=100),"Completed — on track",IF(O243="Not awarded",IF(U243="",IF(X243="","No planned date",IF(TODAY()>X243,"Behind — past planned date",IF(X243-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U243,"Behind — award date passed",IF(U243-TODAY()<=30,"At risk — close to off track","On track"))),IF(X243="","No planned date",IF(AND(TODAY()>X243,OR(Z243="",Z243<100)),"Behind — past end date",IF(AND(T243<>"",X243<>"",Z243<>"",(Z243<100),((TODAY()-T243)/MAX(X243-T243,1)*100)-Z243>15),"Behind — progress lag",IF(AND(X243-TODAY()<=30,X243-TODAY()>=0,OR(Z243="",Z243<90)),"At risk — close to off track","On track")))))))) | IF(OR(F243="",AC243="Completed / Handover",AC243="Cancelled"),"",IF(O243="Not awarded",IF(U243<>"",U243-TODAY(),IF(X243="","",X243-TODAY())),IF(X243="","",X243-TODAY()))) | [14 empty] | IF(OR(F243="",AJ243=""),"",IF(COUNT(AI243:AI243)=0,"",AJ243-LOOKUP(2,1/(AI243:AI243<>""),AI243:AI243))) | IF(OR(F243="",AK243=""),"",IF(COUNT(AI243:AJ243)=0,"",AK243-LOOKUP(2,1/(AI243:AJ243<>""),AI243:AJ243))) | IF(OR(F243="",AL243=""),"",IF(COUNT(AI243:AK243)=0,"",AL243-LOOKUP(2,1/(AI243:AK243<>""),AI243:AK243))) | IF(OR(F243="",AM243=""),"",IF(COUNT(AI243:AL243)=0,"",AM243-LOOKUP(2,1/(AI243:AL243<>""),AI243:AL243))) | IF(OR(F243="",AN243=""),"",IF(COUNT(AI243:AM243)=0,"",AN243-LOOKUP(2,1/(AI243:AM243<>""),AI243:AM243))) | IF(OR(F243="",AO243=""),"",IF(COUNT(AI243:AN243)=0,"",AO243-LOOKUP(2,1/(AI243:AN243<>""),AI243:AN243))) | IF(OR(F243="",AP243=""),"",IF(COUNT(AI243:AO243)=0,"",AP243-LOOKUP(2,1/(AI243:AO243<>""),AI243:AO243))) | IF(OR(F243="",AQ243=""),"",IF(COUNT(AI243:AP243)=0,"",AQ243-LOOKUP(2,1/(AI243:AP243<>""),AI243:AP243))) | IF(OR(F243="",AR243=""),"",IF(COUNT(AI243:AQ243)=0,"",AR243-LOOKUP(2,1/(AI243:AQ243<>""),AI243:AQ243))) | IF(OR(F243="",AS243=""),"",IF(COUNT(AI243:AR243)=0,"",AS243-LOOKUP(2,1/(AI243:AR243<>""),AI243:AR243))) | IF(OR(F243="",AT243=""),"",IF(COUNT(AI243:AS243)=0,"",AT243-LOOKUP(2,1/(AI243:AS243<>""),AI243:AS243))) | IF(OR(F243="",AU243=""),"",IF(COUNT(AI243:AT243)=0,"",AU243-LOOKUP(2,1/(AI243:AT243<>""),AI243:AT243))) | IF(OR(F243="",AV243=""),"",IF(COUNT(AI243:AU243)=0,"",AV243-LOOKUP(2,1/(AI243:AU243<>""),AI243:AU243))) | IF(J243="","All_Provinces",IFERROR(VLOOKUP(J243,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K243="","All_Districts",IFERROR(VLOOKUP(K243,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F244="","",ROW()-3) | [18 empty] | IF(AQ244="","",AQ244) |  |  |  | IF(W244<>"",W244,IF(OR(T244="",V244=""),"",EDATE(T244,V244))) |  |  |  |  | IF(F244="","",IF(COUNT(AI244:AV244)=0,IF(AA244="","Not started",AA244),SUBSTITUTE(LOOKUP(2,1/(AI244:AV244<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F244="",COUNT(AI244:AV244)=0),"",TODAY()-LOOKUP(2,1/(AI244:AV244<>""),AI244:AV244)) | IF(OR(F244="",COUNT(AI244:AV244)<2),"",LOOKUP(2,1/(AI244:AV244<>""),AI244:AV244)-MIN(AI244:AV244)) | IF(OR(AD244="",AC244="Not started",AC244=""),"",IFERROR(AD244-IF(VLOOKUP(AC244,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC244,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F244="","",IF(OR(AA244="Cancelled",AC244="Cancelled"),"Cancelled",IF(OR(AC244="Completed / Handover",Y244<>"",Z244>=100),"Completed — on track",IF(O244="Not awarded",IF(U244="",IF(X244="","No planned date",IF(TODAY()>X244,"Behind — past planned date",IF(X244-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U244,"Behind — award date passed",IF(U244-TODAY()<=30,"At risk — close to off track","On track"))),IF(X244="","No planned date",IF(AND(TODAY()>X244,OR(Z244="",Z244<100)),"Behind — past end date",IF(AND(T244<>"",X244<>"",Z244<>"",(Z244<100),((TODAY()-T244)/MAX(X244-T244,1)*100)-Z244>15),"Behind — progress lag",IF(AND(X244-TODAY()<=30,X244-TODAY()>=0,OR(Z244="",Z244<90)),"At risk — close to off track","On track")))))))) | IF(OR(F244="",AC244="Completed / Handover",AC244="Cancelled"),"",IF(O244="Not awarded",IF(U244<>"",U244-TODAY(),IF(X244="","",X244-TODAY())),IF(X244="","",X244-TODAY()))) | [14 empty] | IF(OR(F244="",AJ244=""),"",IF(COUNT(AI244:AI244)=0,"",AJ244-LOOKUP(2,1/(AI244:AI244<>""),AI244:AI244))) | IF(OR(F244="",AK244=""),"",IF(COUNT(AI244:AJ244)=0,"",AK244-LOOKUP(2,1/(AI244:AJ244<>""),AI244:AJ244))) | IF(OR(F244="",AL244=""),"",IF(COUNT(AI244:AK244)=0,"",AL244-LOOKUP(2,1/(AI244:AK244<>""),AI244:AK244))) | IF(OR(F244="",AM244=""),"",IF(COUNT(AI244:AL244)=0,"",AM244-LOOKUP(2,1/(AI244:AL244<>""),AI244:AL244))) | IF(OR(F244="",AN244=""),"",IF(COUNT(AI244:AM244)=0,"",AN244-LOOKUP(2,1/(AI244:AM244<>""),AI244:AM244))) | IF(OR(F244="",AO244=""),"",IF(COUNT(AI244:AN244)=0,"",AO244-LOOKUP(2,1/(AI244:AN244<>""),AI244:AN244))) | IF(OR(F244="",AP244=""),"",IF(COUNT(AI244:AO244)=0,"",AP244-LOOKUP(2,1/(AI244:AO244<>""),AI244:AO244))) | IF(OR(F244="",AQ244=""),"",IF(COUNT(AI244:AP244)=0,"",AQ244-LOOKUP(2,1/(AI244:AP244<>""),AI244:AP244))) | IF(OR(F244="",AR244=""),"",IF(COUNT(AI244:AQ244)=0,"",AR244-LOOKUP(2,1/(AI244:AQ244<>""),AI244:AQ244))) | IF(OR(F244="",AS244=""),"",IF(COUNT(AI244:AR244)=0,"",AS244-LOOKUP(2,1/(AI244:AR244<>""),AI244:AR244))) | IF(OR(F244="",AT244=""),"",IF(COUNT(AI244:AS244)=0,"",AT244-LOOKUP(2,1/(AI244:AS244<>""),AI244:AS244))) | IF(OR(F244="",AU244=""),"",IF(COUNT(AI244:AT244)=0,"",AU244-LOOKUP(2,1/(AI244:AT244<>""),AI244:AT244))) | IF(OR(F244="",AV244=""),"",IF(COUNT(AI244:AU244)=0,"",AV244-LOOKUP(2,1/(AI244:AU244<>""),AI244:AU244))) | IF(J244="","All_Provinces",IFERROR(VLOOKUP(J244,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K244="","All_Districts",IFERROR(VLOOKUP(K244,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F245="","",ROW()-3) | [18 empty] | IF(AQ245="","",AQ245) |  |  |  | IF(W245<>"",W245,IF(OR(T245="",V245=""),"",EDATE(T245,V245))) |  |  |  |  | IF(F245="","",IF(COUNT(AI245:AV245)=0,IF(AA245="","Not started",AA245),SUBSTITUTE(LOOKUP(2,1/(AI245:AV245<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F245="",COUNT(AI245:AV245)=0),"",TODAY()-LOOKUP(2,1/(AI245:AV245<>""),AI245:AV245)) | IF(OR(F245="",COUNT(AI245:AV245)<2),"",LOOKUP(2,1/(AI245:AV245<>""),AI245:AV245)-MIN(AI245:AV245)) | IF(OR(AD245="",AC245="Not started",AC245=""),"",IFERROR(AD245-IF(VLOOKUP(AC245,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC245,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F245="","",IF(OR(AA245="Cancelled",AC245="Cancelled"),"Cancelled",IF(OR(AC245="Completed / Handover",Y245<>"",Z245>=100),"Completed — on track",IF(O245="Not awarded",IF(U245="",IF(X245="","No planned date",IF(TODAY()>X245,"Behind — past planned date",IF(X245-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U245,"Behind — award date passed",IF(U245-TODAY()<=30,"At risk — close to off track","On track"))),IF(X245="","No planned date",IF(AND(TODAY()>X245,OR(Z245="",Z245<100)),"Behind — past end date",IF(AND(T245<>"",X245<>"",Z245<>"",(Z245<100),((TODAY()-T245)/MAX(X245-T245,1)*100)-Z245>15),"Behind — progress lag",IF(AND(X245-TODAY()<=30,X245-TODAY()>=0,OR(Z245="",Z245<90)),"At risk — close to off track","On track")))))))) | IF(OR(F245="",AC245="Completed / Handover",AC245="Cancelled"),"",IF(O245="Not awarded",IF(U245<>"",U245-TODAY(),IF(X245="","",X245-TODAY())),IF(X245="","",X245-TODAY()))) | [14 empty] | IF(OR(F245="",AJ245=""),"",IF(COUNT(AI245:AI245)=0,"",AJ245-LOOKUP(2,1/(AI245:AI245<>""),AI245:AI245))) | IF(OR(F245="",AK245=""),"",IF(COUNT(AI245:AJ245)=0,"",AK245-LOOKUP(2,1/(AI245:AJ245<>""),AI245:AJ245))) | IF(OR(F245="",AL245=""),"",IF(COUNT(AI245:AK245)=0,"",AL245-LOOKUP(2,1/(AI245:AK245<>""),AI245:AK245))) | IF(OR(F245="",AM245=""),"",IF(COUNT(AI245:AL245)=0,"",AM245-LOOKUP(2,1/(AI245:AL245<>""),AI245:AL245))) | IF(OR(F245="",AN245=""),"",IF(COUNT(AI245:AM245)=0,"",AN245-LOOKUP(2,1/(AI245:AM245<>""),AI245:AM245))) | IF(OR(F245="",AO245=""),"",IF(COUNT(AI245:AN245)=0,"",AO245-LOOKUP(2,1/(AI245:AN245<>""),AI245:AN245))) | IF(OR(F245="",AP245=""),"",IF(COUNT(AI245:AO245)=0,"",AP245-LOOKUP(2,1/(AI245:AO245<>""),AI245:AO245))) | IF(OR(F245="",AQ245=""),"",IF(COUNT(AI245:AP245)=0,"",AQ245-LOOKUP(2,1/(AI245:AP245<>""),AI245:AP245))) | IF(OR(F245="",AR245=""),"",IF(COUNT(AI245:AQ245)=0,"",AR245-LOOKUP(2,1/(AI245:AQ245<>""),AI245:AQ245))) | IF(OR(F245="",AS245=""),"",IF(COUNT(AI245:AR245)=0,"",AS245-LOOKUP(2,1/(AI245:AR245<>""),AI245:AR245))) | IF(OR(F245="",AT245=""),"",IF(COUNT(AI245:AS245)=0,"",AT245-LOOKUP(2,1/(AI245:AS245<>""),AI245:AS245))) | IF(OR(F245="",AU245=""),"",IF(COUNT(AI245:AT245)=0,"",AU245-LOOKUP(2,1/(AI245:AT245<>""),AI245:AT245))) | IF(OR(F245="",AV245=""),"",IF(COUNT(AI245:AU245)=0,"",AV245-LOOKUP(2,1/(AI245:AU245<>""),AI245:AU245))) | IF(J245="","All_Provinces",IFERROR(VLOOKUP(J245,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K245="","All_Districts",IFERROR(VLOOKUP(K245,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F246="","",ROW()-3) | [18 empty] | IF(AQ246="","",AQ246) |  |  |  | IF(W246<>"",W246,IF(OR(T246="",V246=""),"",EDATE(T246,V246))) |  |  |  |  | IF(F246="","",IF(COUNT(AI246:AV246)=0,IF(AA246="","Not started",AA246),SUBSTITUTE(LOOKUP(2,1/(AI246:AV246<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F246="",COUNT(AI246:AV246)=0),"",TODAY()-LOOKUP(2,1/(AI246:AV246<>""),AI246:AV246)) | IF(OR(F246="",COUNT(AI246:AV246)<2),"",LOOKUP(2,1/(AI246:AV246<>""),AI246:AV246)-MIN(AI246:AV246)) | IF(OR(AD246="",AC246="Not started",AC246=""),"",IFERROR(AD246-IF(VLOOKUP(AC246,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC246,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F246="","",IF(OR(AA246="Cancelled",AC246="Cancelled"),"Cancelled",IF(OR(AC246="Completed / Handover",Y246<>"",Z246>=100),"Completed — on track",IF(O246="Not awarded",IF(U246="",IF(X246="","No planned date",IF(TODAY()>X246,"Behind — past planned date",IF(X246-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U246,"Behind — award date passed",IF(U246-TODAY()<=30,"At risk — close to off track","On track"))),IF(X246="","No planned date",IF(AND(TODAY()>X246,OR(Z246="",Z246<100)),"Behind — past end date",IF(AND(T246<>"",X246<>"",Z246<>"",(Z246<100),((TODAY()-T246)/MAX(X246-T246,1)*100)-Z246>15),"Behind — progress lag",IF(AND(X246-TODAY()<=30,X246-TODAY()>=0,OR(Z246="",Z246<90)),"At risk — close to off track","On track")))))))) | IF(OR(F246="",AC246="Completed / Handover",AC246="Cancelled"),"",IF(O246="Not awarded",IF(U246<>"",U246-TODAY(),IF(X246="","",X246-TODAY())),IF(X246="","",X246-TODAY()))) | [14 empty] | IF(OR(F246="",AJ246=""),"",IF(COUNT(AI246:AI246)=0,"",AJ246-LOOKUP(2,1/(AI246:AI246<>""),AI246:AI246))) | IF(OR(F246="",AK246=""),"",IF(COUNT(AI246:AJ246)=0,"",AK246-LOOKUP(2,1/(AI246:AJ246<>""),AI246:AJ246))) | IF(OR(F246="",AL246=""),"",IF(COUNT(AI246:AK246)=0,"",AL246-LOOKUP(2,1/(AI246:AK246<>""),AI246:AK246))) | IF(OR(F246="",AM246=""),"",IF(COUNT(AI246:AL246)=0,"",AM246-LOOKUP(2,1/(AI246:AL246<>""),AI246:AL246))) | IF(OR(F246="",AN246=""),"",IF(COUNT(AI246:AM246)=0,"",AN246-LOOKUP(2,1/(AI246:AM246<>""),AI246:AM246))) | IF(OR(F246="",AO246=""),"",IF(COUNT(AI246:AN246)=0,"",AO246-LOOKUP(2,1/(AI246:AN246<>""),AI246:AN246))) | IF(OR(F246="",AP246=""),"",IF(COUNT(AI246:AO246)=0,"",AP246-LOOKUP(2,1/(AI246:AO246<>""),AI246:AO246))) | IF(OR(F246="",AQ246=""),"",IF(COUNT(AI246:AP246)=0,"",AQ246-LOOKUP(2,1/(AI246:AP246<>""),AI246:AP246))) | IF(OR(F246="",AR246=""),"",IF(COUNT(AI246:AQ246)=0,"",AR246-LOOKUP(2,1/(AI246:AQ246<>""),AI246:AQ246))) | IF(OR(F246="",AS246=""),"",IF(COUNT(AI246:AR246)=0,"",AS246-LOOKUP(2,1/(AI246:AR246<>""),AI246:AR246))) | IF(OR(F246="",AT246=""),"",IF(COUNT(AI246:AS246)=0,"",AT246-LOOKUP(2,1/(AI246:AS246<>""),AI246:AS246))) | IF(OR(F246="",AU246=""),"",IF(COUNT(AI246:AT246)=0,"",AU246-LOOKUP(2,1/(AI246:AT246<>""),AI246:AT246))) | IF(OR(F246="",AV246=""),"",IF(COUNT(AI246:AU246)=0,"",AV246-LOOKUP(2,1/(AI246:AU246<>""),AI246:AU246))) | IF(J246="","All_Provinces",IFERROR(VLOOKUP(J246,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K246="","All_Districts",IFERROR(VLOOKUP(K246,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F247="","",ROW()-3) | [18 empty] | IF(AQ247="","",AQ247) |  |  |  | IF(W247<>"",W247,IF(OR(T247="",V247=""),"",EDATE(T247,V247))) |  |  |  |  | IF(F247="","",IF(COUNT(AI247:AV247)=0,IF(AA247="","Not started",AA247),SUBSTITUTE(LOOKUP(2,1/(AI247:AV247<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F247="",COUNT(AI247:AV247)=0),"",TODAY()-LOOKUP(2,1/(AI247:AV247<>""),AI247:AV247)) | IF(OR(F247="",COUNT(AI247:AV247)<2),"",LOOKUP(2,1/(AI247:AV247<>""),AI247:AV247)-MIN(AI247:AV247)) | IF(OR(AD247="",AC247="Not started",AC247=""),"",IFERROR(AD247-IF(VLOOKUP(AC247,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC247,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F247="","",IF(OR(AA247="Cancelled",AC247="Cancelled"),"Cancelled",IF(OR(AC247="Completed / Handover",Y247<>"",Z247>=100),"Completed — on track",IF(O247="Not awarded",IF(U247="",IF(X247="","No planned date",IF(TODAY()>X247,"Behind — past planned date",IF(X247-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U247,"Behind — award date passed",IF(U247-TODAY()<=30,"At risk — close to off track","On track"))),IF(X247="","No planned date",IF(AND(TODAY()>X247,OR(Z247="",Z247<100)),"Behind — past end date",IF(AND(T247<>"",X247<>"",Z247<>"",(Z247<100),((TODAY()-T247)/MAX(X247-T247,1)*100)-Z247>15),"Behind — progress lag",IF(AND(X247-TODAY()<=30,X247-TODAY()>=0,OR(Z247="",Z247<90)),"At risk — close to off track","On track")))))))) | IF(OR(F247="",AC247="Completed / Handover",AC247="Cancelled"),"",IF(O247="Not awarded",IF(U247<>"",U247-TODAY(),IF(X247="","",X247-TODAY())),IF(X247="","",X247-TODAY()))) | [14 empty] | IF(OR(F247="",AJ247=""),"",IF(COUNT(AI247:AI247)=0,"",AJ247-LOOKUP(2,1/(AI247:AI247<>""),AI247:AI247))) | IF(OR(F247="",AK247=""),"",IF(COUNT(AI247:AJ247)=0,"",AK247-LOOKUP(2,1/(AI247:AJ247<>""),AI247:AJ247))) | IF(OR(F247="",AL247=""),"",IF(COUNT(AI247:AK247)=0,"",AL247-LOOKUP(2,1/(AI247:AK247<>""),AI247:AK247))) | IF(OR(F247="",AM247=""),"",IF(COUNT(AI247:AL247)=0,"",AM247-LOOKUP(2,1/(AI247:AL247<>""),AI247:AL247))) | IF(OR(F247="",AN247=""),"",IF(COUNT(AI247:AM247)=0,"",AN247-LOOKUP(2,1/(AI247:AM247<>""),AI247:AM247))) | IF(OR(F247="",AO247=""),"",IF(COUNT(AI247:AN247)=0,"",AO247-LOOKUP(2,1/(AI247:AN247<>""),AI247:AN247))) | IF(OR(F247="",AP247=""),"",IF(COUNT(AI247:AO247)=0,"",AP247-LOOKUP(2,1/(AI247:AO247<>""),AI247:AO247))) | IF(OR(F247="",AQ247=""),"",IF(COUNT(AI247:AP247)=0,"",AQ247-LOOKUP(2,1/(AI247:AP247<>""),AI247:AP247))) | IF(OR(F247="",AR247=""),"",IF(COUNT(AI247:AQ247)=0,"",AR247-LOOKUP(2,1/(AI247:AQ247<>""),AI247:AQ247))) | IF(OR(F247="",AS247=""),"",IF(COUNT(AI247:AR247)=0,"",AS247-LOOKUP(2,1/(AI247:AR247<>""),AI247:AR247))) | IF(OR(F247="",AT247=""),"",IF(COUNT(AI247:AS247)=0,"",AT247-LOOKUP(2,1/(AI247:AS247<>""),AI247:AS247))) | IF(OR(F247="",AU247=""),"",IF(COUNT(AI247:AT247)=0,"",AU247-LOOKUP(2,1/(AI247:AT247<>""),AI247:AT247))) | IF(OR(F247="",AV247=""),"",IF(COUNT(AI247:AU247)=0,"",AV247-LOOKUP(2,1/(AI247:AU247<>""),AI247:AU247))) | IF(J247="","All_Provinces",IFERROR(VLOOKUP(J247,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K247="","All_Districts",IFERROR(VLOOKUP(K247,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F248="","",ROW()-3) | [18 empty] | IF(AQ248="","",AQ248) |  |  |  | IF(W248<>"",W248,IF(OR(T248="",V248=""),"",EDATE(T248,V248))) |  |  |  |  | IF(F248="","",IF(COUNT(AI248:AV248)=0,IF(AA248="","Not started",AA248),SUBSTITUTE(LOOKUP(2,1/(AI248:AV248<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F248="",COUNT(AI248:AV248)=0),"",TODAY()-LOOKUP(2,1/(AI248:AV248<>""),AI248:AV248)) | IF(OR(F248="",COUNT(AI248:AV248)<2),"",LOOKUP(2,1/(AI248:AV248<>""),AI248:AV248)-MIN(AI248:AV248)) | IF(OR(AD248="",AC248="Not started",AC248=""),"",IFERROR(AD248-IF(VLOOKUP(AC248,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC248,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F248="","",IF(OR(AA248="Cancelled",AC248="Cancelled"),"Cancelled",IF(OR(AC248="Completed / Handover",Y248<>"",Z248>=100),"Completed — on track",IF(O248="Not awarded",IF(U248="",IF(X248="","No planned date",IF(TODAY()>X248,"Behind — past planned date",IF(X248-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U248,"Behind — award date passed",IF(U248-TODAY()<=30,"At risk — close to off track","On track"))),IF(X248="","No planned date",IF(AND(TODAY()>X248,OR(Z248="",Z248<100)),"Behind — past end date",IF(AND(T248<>"",X248<>"",Z248<>"",(Z248<100),((TODAY()-T248)/MAX(X248-T248,1)*100)-Z248>15),"Behind — progress lag",IF(AND(X248-TODAY()<=30,X248-TODAY()>=0,OR(Z248="",Z248<90)),"At risk — close to off track","On track")))))))) | IF(OR(F248="",AC248="Completed / Handover",AC248="Cancelled"),"",IF(O248="Not awarded",IF(U248<>"",U248-TODAY(),IF(X248="","",X248-TODAY())),IF(X248="","",X248-TODAY()))) | [14 empty] | IF(OR(F248="",AJ248=""),"",IF(COUNT(AI248:AI248)=0,"",AJ248-LOOKUP(2,1/(AI248:AI248<>""),AI248:AI248))) | IF(OR(F248="",AK248=""),"",IF(COUNT(AI248:AJ248)=0,"",AK248-LOOKUP(2,1/(AI248:AJ248<>""),AI248:AJ248))) | IF(OR(F248="",AL248=""),"",IF(COUNT(AI248:AK248)=0,"",AL248-LOOKUP(2,1/(AI248:AK248<>""),AI248:AK248))) | IF(OR(F248="",AM248=""),"",IF(COUNT(AI248:AL248)=0,"",AM248-LOOKUP(2,1/(AI248:AL248<>""),AI248:AL248))) | IF(OR(F248="",AN248=""),"",IF(COUNT(AI248:AM248)=0,"",AN248-LOOKUP(2,1/(AI248:AM248<>""),AI248:AM248))) | IF(OR(F248="",AO248=""),"",IF(COUNT(AI248:AN248)=0,"",AO248-LOOKUP(2,1/(AI248:AN248<>""),AI248:AN248))) | IF(OR(F248="",AP248=""),"",IF(COUNT(AI248:AO248)=0,"",AP248-LOOKUP(2,1/(AI248:AO248<>""),AI248:AO248))) | IF(OR(F248="",AQ248=""),"",IF(COUNT(AI248:AP248)=0,"",AQ248-LOOKUP(2,1/(AI248:AP248<>""),AI248:AP248))) | IF(OR(F248="",AR248=""),"",IF(COUNT(AI248:AQ248)=0,"",AR248-LOOKUP(2,1/(AI248:AQ248<>""),AI248:AQ248))) | IF(OR(F248="",AS248=""),"",IF(COUNT(AI248:AR248)=0,"",AS248-LOOKUP(2,1/(AI248:AR248<>""),AI248:AR248))) | IF(OR(F248="",AT248=""),"",IF(COUNT(AI248:AS248)=0,"",AT248-LOOKUP(2,1/(AI248:AS248<>""),AI248:AS248))) | IF(OR(F248="",AU248=""),"",IF(COUNT(AI248:AT248)=0,"",AU248-LOOKUP(2,1/(AI248:AT248<>""),AI248:AT248))) | IF(OR(F248="",AV248=""),"",IF(COUNT(AI248:AU248)=0,"",AV248-LOOKUP(2,1/(AI248:AU248<>""),AI248:AU248))) | IF(J248="","All_Provinces",IFERROR(VLOOKUP(J248,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K248="","All_Districts",IFERROR(VLOOKUP(K248,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F249="","",ROW()-3) | [18 empty] | IF(AQ249="","",AQ249) |  |  |  | IF(W249<>"",W249,IF(OR(T249="",V249=""),"",EDATE(T249,V249))) |  |  |  |  | IF(F249="","",IF(COUNT(AI249:AV249)=0,IF(AA249="","Not started",AA249),SUBSTITUTE(LOOKUP(2,1/(AI249:AV249<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F249="",COUNT(AI249:AV249)=0),"",TODAY()-LOOKUP(2,1/(AI249:AV249<>""),AI249:AV249)) | IF(OR(F249="",COUNT(AI249:AV249)<2),"",LOOKUP(2,1/(AI249:AV249<>""),AI249:AV249)-MIN(AI249:AV249)) | IF(OR(AD249="",AC249="Not started",AC249=""),"",IFERROR(AD249-IF(VLOOKUP(AC249,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC249,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F249="","",IF(OR(AA249="Cancelled",AC249="Cancelled"),"Cancelled",IF(OR(AC249="Completed / Handover",Y249<>"",Z249>=100),"Completed — on track",IF(O249="Not awarded",IF(U249="",IF(X249="","No planned date",IF(TODAY()>X249,"Behind — past planned date",IF(X249-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U249,"Behind — award date passed",IF(U249-TODAY()<=30,"At risk — close to off track","On track"))),IF(X249="","No planned date",IF(AND(TODAY()>X249,OR(Z249="",Z249<100)),"Behind — past end date",IF(AND(T249<>"",X249<>"",Z249<>"",(Z249<100),((TODAY()-T249)/MAX(X249-T249,1)*100)-Z249>15),"Behind — progress lag",IF(AND(X249-TODAY()<=30,X249-TODAY()>=0,OR(Z249="",Z249<90)),"At risk — close to off track","On track")))))))) | IF(OR(F249="",AC249="Completed / Handover",AC249="Cancelled"),"",IF(O249="Not awarded",IF(U249<>"",U249-TODAY(),IF(X249="","",X249-TODAY())),IF(X249="","",X249-TODAY()))) | [14 empty] | IF(OR(F249="",AJ249=""),"",IF(COUNT(AI249:AI249)=0,"",AJ249-LOOKUP(2,1/(AI249:AI249<>""),AI249:AI249))) | IF(OR(F249="",AK249=""),"",IF(COUNT(AI249:AJ249)=0,"",AK249-LOOKUP(2,1/(AI249:AJ249<>""),AI249:AJ249))) | IF(OR(F249="",AL249=""),"",IF(COUNT(AI249:AK249)=0,"",AL249-LOOKUP(2,1/(AI249:AK249<>""),AI249:AK249))) | IF(OR(F249="",AM249=""),"",IF(COUNT(AI249:AL249)=0,"",AM249-LOOKUP(2,1/(AI249:AL249<>""),AI249:AL249))) | IF(OR(F249="",AN249=""),"",IF(COUNT(AI249:AM249)=0,"",AN249-LOOKUP(2,1/(AI249:AM249<>""),AI249:AM249))) | IF(OR(F249="",AO249=""),"",IF(COUNT(AI249:AN249)=0,"",AO249-LOOKUP(2,1/(AI249:AN249<>""),AI249:AN249))) | IF(OR(F249="",AP249=""),"",IF(COUNT(AI249:AO249)=0,"",AP249-LOOKUP(2,1/(AI249:AO249<>""),AI249:AO249))) | IF(OR(F249="",AQ249=""),"",IF(COUNT(AI249:AP249)=0,"",AQ249-LOOKUP(2,1/(AI249:AP249<>""),AI249:AP249))) | IF(OR(F249="",AR249=""),"",IF(COUNT(AI249:AQ249)=0,"",AR249-LOOKUP(2,1/(AI249:AQ249<>""),AI249:AQ249))) | IF(OR(F249="",AS249=""),"",IF(COUNT(AI249:AR249)=0,"",AS249-LOOKUP(2,1/(AI249:AR249<>""),AI249:AR249))) | IF(OR(F249="",AT249=""),"",IF(COUNT(AI249:AS249)=0,"",AT249-LOOKUP(2,1/(AI249:AS249<>""),AI249:AS249))) | IF(OR(F249="",AU249=""),"",IF(COUNT(AI249:AT249)=0,"",AU249-LOOKUP(2,1/(AI249:AT249<>""),AI249:AT249))) | IF(OR(F249="",AV249=""),"",IF(COUNT(AI249:AU249)=0,"",AV249-LOOKUP(2,1/(AI249:AU249<>""),AI249:AU249))) | IF(J249="","All_Provinces",IFERROR(VLOOKUP(J249,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K249="","All_Districts",IFERROR(VLOOKUP(K249,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F250="","",ROW()-3) | [18 empty] | IF(AQ250="","",AQ250) |  |  |  | IF(W250<>"",W250,IF(OR(T250="",V250=""),"",EDATE(T250,V250))) |  |  |  |  | IF(F250="","",IF(COUNT(AI250:AV250)=0,IF(AA250="","Not started",AA250),SUBSTITUTE(LOOKUP(2,1/(AI250:AV250<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F250="",COUNT(AI250:AV250)=0),"",TODAY()-LOOKUP(2,1/(AI250:AV250<>""),AI250:AV250)) | IF(OR(F250="",COUNT(AI250:AV250)<2),"",LOOKUP(2,1/(AI250:AV250<>""),AI250:AV250)-MIN(AI250:AV250)) | IF(OR(AD250="",AC250="Not started",AC250=""),"",IFERROR(AD250-IF(VLOOKUP(AC250,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC250,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F250="","",IF(OR(AA250="Cancelled",AC250="Cancelled"),"Cancelled",IF(OR(AC250="Completed / Handover",Y250<>"",Z250>=100),"Completed — on track",IF(O250="Not awarded",IF(U250="",IF(X250="","No planned date",IF(TODAY()>X250,"Behind — past planned date",IF(X250-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U250,"Behind — award date passed",IF(U250-TODAY()<=30,"At risk — close to off track","On track"))),IF(X250="","No planned date",IF(AND(TODAY()>X250,OR(Z250="",Z250<100)),"Behind — past end date",IF(AND(T250<>"",X250<>"",Z250<>"",(Z250<100),((TODAY()-T250)/MAX(X250-T250,1)*100)-Z250>15),"Behind — progress lag",IF(AND(X250-TODAY()<=30,X250-TODAY()>=0,OR(Z250="",Z250<90)),"At risk — close to off track","On track")))))))) | IF(OR(F250="",AC250="Completed / Handover",AC250="Cancelled"),"",IF(O250="Not awarded",IF(U250<>"",U250-TODAY(),IF(X250="","",X250-TODAY())),IF(X250="","",X250-TODAY()))) | [14 empty] | IF(OR(F250="",AJ250=""),"",IF(COUNT(AI250:AI250)=0,"",AJ250-LOOKUP(2,1/(AI250:AI250<>""),AI250:AI250))) | IF(OR(F250="",AK250=""),"",IF(COUNT(AI250:AJ250)=0,"",AK250-LOOKUP(2,1/(AI250:AJ250<>""),AI250:AJ250))) | IF(OR(F250="",AL250=""),"",IF(COUNT(AI250:AK250)=0,"",AL250-LOOKUP(2,1/(AI250:AK250<>""),AI250:AK250))) | IF(OR(F250="",AM250=""),"",IF(COUNT(AI250:AL250)=0,"",AM250-LOOKUP(2,1/(AI250:AL250<>""),AI250:AL250))) | IF(OR(F250="",AN250=""),"",IF(COUNT(AI250:AM250)=0,"",AN250-LOOKUP(2,1/(AI250:AM250<>""),AI250:AM250))) | IF(OR(F250="",AO250=""),"",IF(COUNT(AI250:AN250)=0,"",AO250-LOOKUP(2,1/(AI250:AN250<>""),AI250:AN250))) | IF(OR(F250="",AP250=""),"",IF(COUNT(AI250:AO250)=0,"",AP250-LOOKUP(2,1/(AI250:AO250<>""),AI250:AO250))) | IF(OR(F250="",AQ250=""),"",IF(COUNT(AI250:AP250)=0,"",AQ250-LOOKUP(2,1/(AI250:AP250<>""),AI250:AP250))) | IF(OR(F250="",AR250=""),"",IF(COUNT(AI250:AQ250)=0,"",AR250-LOOKUP(2,1/(AI250:AQ250<>""),AI250:AQ250))) | IF(OR(F250="",AS250=""),"",IF(COUNT(AI250:AR250)=0,"",AS250-LOOKUP(2,1/(AI250:AR250<>""),AI250:AR250))) | IF(OR(F250="",AT250=""),"",IF(COUNT(AI250:AS250)=0,"",AT250-LOOKUP(2,1/(AI250:AS250<>""),AI250:AS250))) | IF(OR(F250="",AU250=""),"",IF(COUNT(AI250:AT250)=0,"",AU250-LOOKUP(2,1/(AI250:AT250<>""),AI250:AT250))) | IF(OR(F250="",AV250=""),"",IF(COUNT(AI250:AU250)=0,"",AV250-LOOKUP(2,1/(AI250:AU250<>""),AI250:AU250))) | IF(J250="","All_Provinces",IFERROR(VLOOKUP(J250,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K250="","All_Districts",IFERROR(VLOOKUP(K250,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F251="","",ROW()-3) | [18 empty] | IF(AQ251="","",AQ251) |  |  |  | IF(W251<>"",W251,IF(OR(T251="",V251=""),"",EDATE(T251,V251))) |  |  |  |  | IF(F251="","",IF(COUNT(AI251:AV251)=0,IF(AA251="","Not started",AA251),SUBSTITUTE(LOOKUP(2,1/(AI251:AV251<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F251="",COUNT(AI251:AV251)=0),"",TODAY()-LOOKUP(2,1/(AI251:AV251<>""),AI251:AV251)) | IF(OR(F251="",COUNT(AI251:AV251)<2),"",LOOKUP(2,1/(AI251:AV251<>""),AI251:AV251)-MIN(AI251:AV251)) | IF(OR(AD251="",AC251="Not started",AC251=""),"",IFERROR(AD251-IF(VLOOKUP(AC251,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC251,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F251="","",IF(OR(AA251="Cancelled",AC251="Cancelled"),"Cancelled",IF(OR(AC251="Completed / Handover",Y251<>"",Z251>=100),"Completed — on track",IF(O251="Not awarded",IF(U251="",IF(X251="","No planned date",IF(TODAY()>X251,"Behind — past planned date",IF(X251-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U251,"Behind — award date passed",IF(U251-TODAY()<=30,"At risk — close to off track","On track"))),IF(X251="","No planned date",IF(AND(TODAY()>X251,OR(Z251="",Z251<100)),"Behind — past end date",IF(AND(T251<>"",X251<>"",Z251<>"",(Z251<100),((TODAY()-T251)/MAX(X251-T251,1)*100)-Z251>15),"Behind — progress lag",IF(AND(X251-TODAY()<=30,X251-TODAY()>=0,OR(Z251="",Z251<90)),"At risk — close to off track","On track")))))))) | IF(OR(F251="",AC251="Completed / Handover",AC251="Cancelled"),"",IF(O251="Not awarded",IF(U251<>"",U251-TODAY(),IF(X251="","",X251-TODAY())),IF(X251="","",X251-TODAY()))) | [14 empty] | IF(OR(F251="",AJ251=""),"",IF(COUNT(AI251:AI251)=0,"",AJ251-LOOKUP(2,1/(AI251:AI251<>""),AI251:AI251))) | IF(OR(F251="",AK251=""),"",IF(COUNT(AI251:AJ251)=0,"",AK251-LOOKUP(2,1/(AI251:AJ251<>""),AI251:AJ251))) | IF(OR(F251="",AL251=""),"",IF(COUNT(AI251:AK251)=0,"",AL251-LOOKUP(2,1/(AI251:AK251<>""),AI251:AK251))) | IF(OR(F251="",AM251=""),"",IF(COUNT(AI251:AL251)=0,"",AM251-LOOKUP(2,1/(AI251:AL251<>""),AI251:AL251))) | IF(OR(F251="",AN251=""),"",IF(COUNT(AI251:AM251)=0,"",AN251-LOOKUP(2,1/(AI251:AM251<>""),AI251:AM251))) | IF(OR(F251="",AO251=""),"",IF(COUNT(AI251:AN251)=0,"",AO251-LOOKUP(2,1/(AI251:AN251<>""),AI251:AN251))) | IF(OR(F251="",AP251=""),"",IF(COUNT(AI251:AO251)=0,"",AP251-LOOKUP(2,1/(AI251:AO251<>""),AI251:AO251))) | IF(OR(F251="",AQ251=""),"",IF(COUNT(AI251:AP251)=0,"",AQ251-LOOKUP(2,1/(AI251:AP251<>""),AI251:AP251))) | IF(OR(F251="",AR251=""),"",IF(COUNT(AI251:AQ251)=0,"",AR251-LOOKUP(2,1/(AI251:AQ251<>""),AI251:AQ251))) | IF(OR(F251="",AS251=""),"",IF(COUNT(AI251:AR251)=0,"",AS251-LOOKUP(2,1/(AI251:AR251<>""),AI251:AR251))) | IF(OR(F251="",AT251=""),"",IF(COUNT(AI251:AS251)=0,"",AT251-LOOKUP(2,1/(AI251:AS251<>""),AI251:AS251))) | IF(OR(F251="",AU251=""),"",IF(COUNT(AI251:AT251)=0,"",AU251-LOOKUP(2,1/(AI251:AT251<>""),AI251:AT251))) | IF(OR(F251="",AV251=""),"",IF(COUNT(AI251:AU251)=0,"",AV251-LOOKUP(2,1/(AI251:AU251<>""),AI251:AU251))) | IF(J251="","All_Provinces",IFERROR(VLOOKUP(J251,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K251="","All_Districts",IFERROR(VLOOKUP(K251,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F252="","",ROW()-3) | [18 empty] | IF(AQ252="","",AQ252) |  |  |  | IF(W252<>"",W252,IF(OR(T252="",V252=""),"",EDATE(T252,V252))) |  |  |  |  | IF(F252="","",IF(COUNT(AI252:AV252)=0,IF(AA252="","Not started",AA252),SUBSTITUTE(LOOKUP(2,1/(AI252:AV252<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F252="",COUNT(AI252:AV252)=0),"",TODAY()-LOOKUP(2,1/(AI252:AV252<>""),AI252:AV252)) | IF(OR(F252="",COUNT(AI252:AV252)<2),"",LOOKUP(2,1/(AI252:AV252<>""),AI252:AV252)-MIN(AI252:AV252)) | IF(OR(AD252="",AC252="Not started",AC252=""),"",IFERROR(AD252-IF(VLOOKUP(AC252,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC252,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F252="","",IF(OR(AA252="Cancelled",AC252="Cancelled"),"Cancelled",IF(OR(AC252="Completed / Handover",Y252<>"",Z252>=100),"Completed — on track",IF(O252="Not awarded",IF(U252="",IF(X252="","No planned date",IF(TODAY()>X252,"Behind — past planned date",IF(X252-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U252,"Behind — award date passed",IF(U252-TODAY()<=30,"At risk — close to off track","On track"))),IF(X252="","No planned date",IF(AND(TODAY()>X252,OR(Z252="",Z252<100)),"Behind — past end date",IF(AND(T252<>"",X252<>"",Z252<>"",(Z252<100),((TODAY()-T252)/MAX(X252-T252,1)*100)-Z252>15),"Behind — progress lag",IF(AND(X252-TODAY()<=30,X252-TODAY()>=0,OR(Z252="",Z252<90)),"At risk — close to off track","On track")))))))) | IF(OR(F252="",AC252="Completed / Handover",AC252="Cancelled"),"",IF(O252="Not awarded",IF(U252<>"",U252-TODAY(),IF(X252="","",X252-TODAY())),IF(X252="","",X252-TODAY()))) | [14 empty] | IF(OR(F252="",AJ252=""),"",IF(COUNT(AI252:AI252)=0,"",AJ252-LOOKUP(2,1/(AI252:AI252<>""),AI252:AI252))) | IF(OR(F252="",AK252=""),"",IF(COUNT(AI252:AJ252)=0,"",AK252-LOOKUP(2,1/(AI252:AJ252<>""),AI252:AJ252))) | IF(OR(F252="",AL252=""),"",IF(COUNT(AI252:AK252)=0,"",AL252-LOOKUP(2,1/(AI252:AK252<>""),AI252:AK252))) | IF(OR(F252="",AM252=""),"",IF(COUNT(AI252:AL252)=0,"",AM252-LOOKUP(2,1/(AI252:AL252<>""),AI252:AL252))) | IF(OR(F252="",AN252=""),"",IF(COUNT(AI252:AM252)=0,"",AN252-LOOKUP(2,1/(AI252:AM252<>""),AI252:AM252))) | IF(OR(F252="",AO252=""),"",IF(COUNT(AI252:AN252)=0,"",AO252-LOOKUP(2,1/(AI252:AN252<>""),AI252:AN252))) | IF(OR(F252="",AP252=""),"",IF(COUNT(AI252:AO252)=0,"",AP252-LOOKUP(2,1/(AI252:AO252<>""),AI252:AO252))) | IF(OR(F252="",AQ252=""),"",IF(COUNT(AI252:AP252)=0,"",AQ252-LOOKUP(2,1/(AI252:AP252<>""),AI252:AP252))) | IF(OR(F252="",AR252=""),"",IF(COUNT(AI252:AQ252)=0,"",AR252-LOOKUP(2,1/(AI252:AQ252<>""),AI252:AQ252))) | IF(OR(F252="",AS252=""),"",IF(COUNT(AI252:AR252)=0,"",AS252-LOOKUP(2,1/(AI252:AR252<>""),AI252:AR252))) | IF(OR(F252="",AT252=""),"",IF(COUNT(AI252:AS252)=0,"",AT252-LOOKUP(2,1/(AI252:AS252<>""),AI252:AS252))) | IF(OR(F252="",AU252=""),"",IF(COUNT(AI252:AT252)=0,"",AU252-LOOKUP(2,1/(AI252:AT252<>""),AI252:AT252))) | IF(OR(F252="",AV252=""),"",IF(COUNT(AI252:AU252)=0,"",AV252-LOOKUP(2,1/(AI252:AU252<>""),AI252:AU252))) | IF(J252="","All_Provinces",IFERROR(VLOOKUP(J252,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K252="","All_Districts",IFERROR(VLOOKUP(K252,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F253="","",ROW()-3) | [18 empty] | IF(AQ253="","",AQ253) |  |  |  | IF(W253<>"",W253,IF(OR(T253="",V253=""),"",EDATE(T253,V253))) |  |  |  |  | IF(F253="","",IF(COUNT(AI253:AV253)=0,IF(AA253="","Not started",AA253),SUBSTITUTE(LOOKUP(2,1/(AI253:AV253<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F253="",COUNT(AI253:AV253)=0),"",TODAY()-LOOKUP(2,1/(AI253:AV253<>""),AI253:AV253)) | IF(OR(F253="",COUNT(AI253:AV253)<2),"",LOOKUP(2,1/(AI253:AV253<>""),AI253:AV253)-MIN(AI253:AV253)) | IF(OR(AD253="",AC253="Not started",AC253=""),"",IFERROR(AD253-IF(VLOOKUP(AC253,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC253,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F253="","",IF(OR(AA253="Cancelled",AC253="Cancelled"),"Cancelled",IF(OR(AC253="Completed / Handover",Y253<>"",Z253>=100),"Completed — on track",IF(O253="Not awarded",IF(U253="",IF(X253="","No planned date",IF(TODAY()>X253,"Behind — past planned date",IF(X253-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U253,"Behind — award date passed",IF(U253-TODAY()<=30,"At risk — close to off track","On track"))),IF(X253="","No planned date",IF(AND(TODAY()>X253,OR(Z253="",Z253<100)),"Behind — past end date",IF(AND(T253<>"",X253<>"",Z253<>"",(Z253<100),((TODAY()-T253)/MAX(X253-T253,1)*100)-Z253>15),"Behind — progress lag",IF(AND(X253-TODAY()<=30,X253-TODAY()>=0,OR(Z253="",Z253<90)),"At risk — close to off track","On track")))))))) | IF(OR(F253="",AC253="Completed / Handover",AC253="Cancelled"),"",IF(O253="Not awarded",IF(U253<>"",U253-TODAY(),IF(X253="","",X253-TODAY())),IF(X253="","",X253-TODAY()))) | [14 empty] | IF(OR(F253="",AJ253=""),"",IF(COUNT(AI253:AI253)=0,"",AJ253-LOOKUP(2,1/(AI253:AI253<>""),AI253:AI253))) | IF(OR(F253="",AK253=""),"",IF(COUNT(AI253:AJ253)=0,"",AK253-LOOKUP(2,1/(AI253:AJ253<>""),AI253:AJ253))) | IF(OR(F253="",AL253=""),"",IF(COUNT(AI253:AK253)=0,"",AL253-LOOKUP(2,1/(AI253:AK253<>""),AI253:AK253))) | IF(OR(F253="",AM253=""),"",IF(COUNT(AI253:AL253)=0,"",AM253-LOOKUP(2,1/(AI253:AL253<>""),AI253:AL253))) | IF(OR(F253="",AN253=""),"",IF(COUNT(AI253:AM253)=0,"",AN253-LOOKUP(2,1/(AI253:AM253<>""),AI253:AM253))) | IF(OR(F253="",AO253=""),"",IF(COUNT(AI253:AN253)=0,"",AO253-LOOKUP(2,1/(AI253:AN253<>""),AI253:AN253))) | IF(OR(F253="",AP253=""),"",IF(COUNT(AI253:AO253)=0,"",AP253-LOOKUP(2,1/(AI253:AO253<>""),AI253:AO253))) | IF(OR(F253="",AQ253=""),"",IF(COUNT(AI253:AP253)=0,"",AQ253-LOOKUP(2,1/(AI253:AP253<>""),AI253:AP253))) | IF(OR(F253="",AR253=""),"",IF(COUNT(AI253:AQ253)=0,"",AR253-LOOKUP(2,1/(AI253:AQ253<>""),AI253:AQ253))) | IF(OR(F253="",AS253=""),"",IF(COUNT(AI253:AR253)=0,"",AS253-LOOKUP(2,1/(AI253:AR253<>""),AI253:AR253))) | IF(OR(F253="",AT253=""),"",IF(COUNT(AI253:AS253)=0,"",AT253-LOOKUP(2,1/(AI253:AS253<>""),AI253:AS253))) | IF(OR(F253="",AU253=""),"",IF(COUNT(AI253:AT253)=0,"",AU253-LOOKUP(2,1/(AI253:AT253<>""),AI253:AT253))) | IF(OR(F253="",AV253=""),"",IF(COUNT(AI253:AU253)=0,"",AV253-LOOKUP(2,1/(AI253:AU253<>""),AI253:AU253))) | IF(J253="","All_Provinces",IFERROR(VLOOKUP(J253,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K253="","All_Districts",IFERROR(VLOOKUP(K253,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F254="","",ROW()-3) | [18 empty] | IF(AQ254="","",AQ254) |  |  |  | IF(W254<>"",W254,IF(OR(T254="",V254=""),"",EDATE(T254,V254))) |  |  |  |  | IF(F254="","",IF(COUNT(AI254:AV254)=0,IF(AA254="","Not started",AA254),SUBSTITUTE(LOOKUP(2,1/(AI254:AV254<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F254="",COUNT(AI254:AV254)=0),"",TODAY()-LOOKUP(2,1/(AI254:AV254<>""),AI254:AV254)) | IF(OR(F254="",COUNT(AI254:AV254)<2),"",LOOKUP(2,1/(AI254:AV254<>""),AI254:AV254)-MIN(AI254:AV254)) | IF(OR(AD254="",AC254="Not started",AC254=""),"",IFERROR(AD254-IF(VLOOKUP(AC254,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC254,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F254="","",IF(OR(AA254="Cancelled",AC254="Cancelled"),"Cancelled",IF(OR(AC254="Completed / Handover",Y254<>"",Z254>=100),"Completed — on track",IF(O254="Not awarded",IF(U254="",IF(X254="","No planned date",IF(TODAY()>X254,"Behind — past planned date",IF(X254-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U254,"Behind — award date passed",IF(U254-TODAY()<=30,"At risk — close to off track","On track"))),IF(X254="","No planned date",IF(AND(TODAY()>X254,OR(Z254="",Z254<100)),"Behind — past end date",IF(AND(T254<>"",X254<>"",Z254<>"",(Z254<100),((TODAY()-T254)/MAX(X254-T254,1)*100)-Z254>15),"Behind — progress lag",IF(AND(X254-TODAY()<=30,X254-TODAY()>=0,OR(Z254="",Z254<90)),"At risk — close to off track","On track")))))))) | IF(OR(F254="",AC254="Completed / Handover",AC254="Cancelled"),"",IF(O254="Not awarded",IF(U254<>"",U254-TODAY(),IF(X254="","",X254-TODAY())),IF(X254="","",X254-TODAY()))) | [14 empty] | IF(OR(F254="",AJ254=""),"",IF(COUNT(AI254:AI254)=0,"",AJ254-LOOKUP(2,1/(AI254:AI254<>""),AI254:AI254))) | IF(OR(F254="",AK254=""),"",IF(COUNT(AI254:AJ254)=0,"",AK254-LOOKUP(2,1/(AI254:AJ254<>""),AI254:AJ254))) | IF(OR(F254="",AL254=""),"",IF(COUNT(AI254:AK254)=0,"",AL254-LOOKUP(2,1/(AI254:AK254<>""),AI254:AK254))) | IF(OR(F254="",AM254=""),"",IF(COUNT(AI254:AL254)=0,"",AM254-LOOKUP(2,1/(AI254:AL254<>""),AI254:AL254))) | IF(OR(F254="",AN254=""),"",IF(COUNT(AI254:AM254)=0,"",AN254-LOOKUP(2,1/(AI254:AM254<>""),AI254:AM254))) | IF(OR(F254="",AO254=""),"",IF(COUNT(AI254:AN254)=0,"",AO254-LOOKUP(2,1/(AI254:AN254<>""),AI254:AN254))) | IF(OR(F254="",AP254=""),"",IF(COUNT(AI254:AO254)=0,"",AP254-LOOKUP(2,1/(AI254:AO254<>""),AI254:AO254))) | IF(OR(F254="",AQ254=""),"",IF(COUNT(AI254:AP254)=0,"",AQ254-LOOKUP(2,1/(AI254:AP254<>""),AI254:AP254))) | IF(OR(F254="",AR254=""),"",IF(COUNT(AI254:AQ254)=0,"",AR254-LOOKUP(2,1/(AI254:AQ254<>""),AI254:AQ254))) | IF(OR(F254="",AS254=""),"",IF(COUNT(AI254:AR254)=0,"",AS254-LOOKUP(2,1/(AI254:AR254<>""),AI254:AR254))) | IF(OR(F254="",AT254=""),"",IF(COUNT(AI254:AS254)=0,"",AT254-LOOKUP(2,1/(AI254:AS254<>""),AI254:AS254))) | IF(OR(F254="",AU254=""),"",IF(COUNT(AI254:AT254)=0,"",AU254-LOOKUP(2,1/(AI254:AT254<>""),AI254:AT254))) | IF(OR(F254="",AV254=""),"",IF(COUNT(AI254:AU254)=0,"",AV254-LOOKUP(2,1/(AI254:AU254<>""),AI254:AU254))) | IF(J254="","All_Provinces",IFERROR(VLOOKUP(J254,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K254="","All_Districts",IFERROR(VLOOKUP(K254,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F255="","",ROW()-3) | [18 empty] | IF(AQ255="","",AQ255) |  |  |  | IF(W255<>"",W255,IF(OR(T255="",V255=""),"",EDATE(T255,V255))) |  |  |  |  | IF(F255="","",IF(COUNT(AI255:AV255)=0,IF(AA255="","Not started",AA255),SUBSTITUTE(LOOKUP(2,1/(AI255:AV255<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F255="",COUNT(AI255:AV255)=0),"",TODAY()-LOOKUP(2,1/(AI255:AV255<>""),AI255:AV255)) | IF(OR(F255="",COUNT(AI255:AV255)<2),"",LOOKUP(2,1/(AI255:AV255<>""),AI255:AV255)-MIN(AI255:AV255)) | IF(OR(AD255="",AC255="Not started",AC255=""),"",IFERROR(AD255-IF(VLOOKUP(AC255,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC255,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F255="","",IF(OR(AA255="Cancelled",AC255="Cancelled"),"Cancelled",IF(OR(AC255="Completed / Handover",Y255<>"",Z255>=100),"Completed — on track",IF(O255="Not awarded",IF(U255="",IF(X255="","No planned date",IF(TODAY()>X255,"Behind — past planned date",IF(X255-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U255,"Behind — award date passed",IF(U255-TODAY()<=30,"At risk — close to off track","On track"))),IF(X255="","No planned date",IF(AND(TODAY()>X255,OR(Z255="",Z255<100)),"Behind — past end date",IF(AND(T255<>"",X255<>"",Z255<>"",(Z255<100),((TODAY()-T255)/MAX(X255-T255,1)*100)-Z255>15),"Behind — progress lag",IF(AND(X255-TODAY()<=30,X255-TODAY()>=0,OR(Z255="",Z255<90)),"At risk — close to off track","On track")))))))) | IF(OR(F255="",AC255="Completed / Handover",AC255="Cancelled"),"",IF(O255="Not awarded",IF(U255<>"",U255-TODAY(),IF(X255="","",X255-TODAY())),IF(X255="","",X255-TODAY()))) | [14 empty] | IF(OR(F255="",AJ255=""),"",IF(COUNT(AI255:AI255)=0,"",AJ255-LOOKUP(2,1/(AI255:AI255<>""),AI255:AI255))) | IF(OR(F255="",AK255=""),"",IF(COUNT(AI255:AJ255)=0,"",AK255-LOOKUP(2,1/(AI255:AJ255<>""),AI255:AJ255))) | IF(OR(F255="",AL255=""),"",IF(COUNT(AI255:AK255)=0,"",AL255-LOOKUP(2,1/(AI255:AK255<>""),AI255:AK255))) | IF(OR(F255="",AM255=""),"",IF(COUNT(AI255:AL255)=0,"",AM255-LOOKUP(2,1/(AI255:AL255<>""),AI255:AL255))) | IF(OR(F255="",AN255=""),"",IF(COUNT(AI255:AM255)=0,"",AN255-LOOKUP(2,1/(AI255:AM255<>""),AI255:AM255))) | IF(OR(F255="",AO255=""),"",IF(COUNT(AI255:AN255)=0,"",AO255-LOOKUP(2,1/(AI255:AN255<>""),AI255:AN255))) | IF(OR(F255="",AP255=""),"",IF(COUNT(AI255:AO255)=0,"",AP255-LOOKUP(2,1/(AI255:AO255<>""),AI255:AO255))) | IF(OR(F255="",AQ255=""),"",IF(COUNT(AI255:AP255)=0,"",AQ255-LOOKUP(2,1/(AI255:AP255<>""),AI255:AP255))) | IF(OR(F255="",AR255=""),"",IF(COUNT(AI255:AQ255)=0,"",AR255-LOOKUP(2,1/(AI255:AQ255<>""),AI255:AQ255))) | IF(OR(F255="",AS255=""),"",IF(COUNT(AI255:AR255)=0,"",AS255-LOOKUP(2,1/(AI255:AR255<>""),AI255:AR255))) | IF(OR(F255="",AT255=""),"",IF(COUNT(AI255:AS255)=0,"",AT255-LOOKUP(2,1/(AI255:AS255<>""),AI255:AS255))) | IF(OR(F255="",AU255=""),"",IF(COUNT(AI255:AT255)=0,"",AU255-LOOKUP(2,1/(AI255:AT255<>""),AI255:AT255))) | IF(OR(F255="",AV255=""),"",IF(COUNT(AI255:AU255)=0,"",AV255-LOOKUP(2,1/(AI255:AU255<>""),AI255:AU255))) | IF(J255="","All_Provinces",IFERROR(VLOOKUP(J255,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K255="","All_Districts",IFERROR(VLOOKUP(K255,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F256="","",ROW()-3) | [18 empty] | IF(AQ256="","",AQ256) |  |  |  | IF(W256<>"",W256,IF(OR(T256="",V256=""),"",EDATE(T256,V256))) |  |  |  |  | IF(F256="","",IF(COUNT(AI256:AV256)=0,IF(AA256="","Not started",AA256),SUBSTITUTE(LOOKUP(2,1/(AI256:AV256<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F256="",COUNT(AI256:AV256)=0),"",TODAY()-LOOKUP(2,1/(AI256:AV256<>""),AI256:AV256)) | IF(OR(F256="",COUNT(AI256:AV256)<2),"",LOOKUP(2,1/(AI256:AV256<>""),AI256:AV256)-MIN(AI256:AV256)) | IF(OR(AD256="",AC256="Not started",AC256=""),"",IFERROR(AD256-IF(VLOOKUP(AC256,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC256,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F256="","",IF(OR(AA256="Cancelled",AC256="Cancelled"),"Cancelled",IF(OR(AC256="Completed / Handover",Y256<>"",Z256>=100),"Completed — on track",IF(O256="Not awarded",IF(U256="",IF(X256="","No planned date",IF(TODAY()>X256,"Behind — past planned date",IF(X256-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U256,"Behind — award date passed",IF(U256-TODAY()<=30,"At risk — close to off track","On track"))),IF(X256="","No planned date",IF(AND(TODAY()>X256,OR(Z256="",Z256<100)),"Behind — past end date",IF(AND(T256<>"",X256<>"",Z256<>"",(Z256<100),((TODAY()-T256)/MAX(X256-T256,1)*100)-Z256>15),"Behind — progress lag",IF(AND(X256-TODAY()<=30,X256-TODAY()>=0,OR(Z256="",Z256<90)),"At risk — close to off track","On track")))))))) | IF(OR(F256="",AC256="Completed / Handover",AC256="Cancelled"),"",IF(O256="Not awarded",IF(U256<>"",U256-TODAY(),IF(X256="","",X256-TODAY())),IF(X256="","",X256-TODAY()))) | [14 empty] | IF(OR(F256="",AJ256=""),"",IF(COUNT(AI256:AI256)=0,"",AJ256-LOOKUP(2,1/(AI256:AI256<>""),AI256:AI256))) | IF(OR(F256="",AK256=""),"",IF(COUNT(AI256:AJ256)=0,"",AK256-LOOKUP(2,1/(AI256:AJ256<>""),AI256:AJ256))) | IF(OR(F256="",AL256=""),"",IF(COUNT(AI256:AK256)=0,"",AL256-LOOKUP(2,1/(AI256:AK256<>""),AI256:AK256))) | IF(OR(F256="",AM256=""),"",IF(COUNT(AI256:AL256)=0,"",AM256-LOOKUP(2,1/(AI256:AL256<>""),AI256:AL256))) | IF(OR(F256="",AN256=""),"",IF(COUNT(AI256:AM256)=0,"",AN256-LOOKUP(2,1/(AI256:AM256<>""),AI256:AM256))) | IF(OR(F256="",AO256=""),"",IF(COUNT(AI256:AN256)=0,"",AO256-LOOKUP(2,1/(AI256:AN256<>""),AI256:AN256))) | IF(OR(F256="",AP256=""),"",IF(COUNT(AI256:AO256)=0,"",AP256-LOOKUP(2,1/(AI256:AO256<>""),AI256:AO256))) | IF(OR(F256="",AQ256=""),"",IF(COUNT(AI256:AP256)=0,"",AQ256-LOOKUP(2,1/(AI256:AP256<>""),AI256:AP256))) | IF(OR(F256="",AR256=""),"",IF(COUNT(AI256:AQ256)=0,"",AR256-LOOKUP(2,1/(AI256:AQ256<>""),AI256:AQ256))) | IF(OR(F256="",AS256=""),"",IF(COUNT(AI256:AR256)=0,"",AS256-LOOKUP(2,1/(AI256:AR256<>""),AI256:AR256))) | IF(OR(F256="",AT256=""),"",IF(COUNT(AI256:AS256)=0,"",AT256-LOOKUP(2,1/(AI256:AS256<>""),AI256:AS256))) | IF(OR(F256="",AU256=""),"",IF(COUNT(AI256:AT256)=0,"",AU256-LOOKUP(2,1/(AI256:AT256<>""),AI256:AT256))) | IF(OR(F256="",AV256=""),"",IF(COUNT(AI256:AU256)=0,"",AV256-LOOKUP(2,1/(AI256:AU256<>""),AI256:AU256))) | IF(J256="","All_Provinces",IFERROR(VLOOKUP(J256,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K256="","All_Districts",IFERROR(VLOOKUP(K256,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F257="","",ROW()-3) | [18 empty] | IF(AQ257="","",AQ257) |  |  |  | IF(W257<>"",W257,IF(OR(T257="",V257=""),"",EDATE(T257,V257))) |  |  |  |  | IF(F257="","",IF(COUNT(AI257:AV257)=0,IF(AA257="","Not started",AA257),SUBSTITUTE(LOOKUP(2,1/(AI257:AV257<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F257="",COUNT(AI257:AV257)=0),"",TODAY()-LOOKUP(2,1/(AI257:AV257<>""),AI257:AV257)) | IF(OR(F257="",COUNT(AI257:AV257)<2),"",LOOKUP(2,1/(AI257:AV257<>""),AI257:AV257)-MIN(AI257:AV257)) | IF(OR(AD257="",AC257="Not started",AC257=""),"",IFERROR(AD257-IF(VLOOKUP(AC257,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC257,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F257="","",IF(OR(AA257="Cancelled",AC257="Cancelled"),"Cancelled",IF(OR(AC257="Completed / Handover",Y257<>"",Z257>=100),"Completed — on track",IF(O257="Not awarded",IF(U257="",IF(X257="","No planned date",IF(TODAY()>X257,"Behind — past planned date",IF(X257-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U257,"Behind — award date passed",IF(U257-TODAY()<=30,"At risk — close to off track","On track"))),IF(X257="","No planned date",IF(AND(TODAY()>X257,OR(Z257="",Z257<100)),"Behind — past end date",IF(AND(T257<>"",X257<>"",Z257<>"",(Z257<100),((TODAY()-T257)/MAX(X257-T257,1)*100)-Z257>15),"Behind — progress lag",IF(AND(X257-TODAY()<=30,X257-TODAY()>=0,OR(Z257="",Z257<90)),"At risk — close to off track","On track")))))))) | IF(OR(F257="",AC257="Completed / Handover",AC257="Cancelled"),"",IF(O257="Not awarded",IF(U257<>"",U257-TODAY(),IF(X257="","",X257-TODAY())),IF(X257="","",X257-TODAY()))) | [14 empty] | IF(OR(F257="",AJ257=""),"",IF(COUNT(AI257:AI257)=0,"",AJ257-LOOKUP(2,1/(AI257:AI257<>""),AI257:AI257))) | IF(OR(F257="",AK257=""),"",IF(COUNT(AI257:AJ257)=0,"",AK257-LOOKUP(2,1/(AI257:AJ257<>""),AI257:AJ257))) | IF(OR(F257="",AL257=""),"",IF(COUNT(AI257:AK257)=0,"",AL257-LOOKUP(2,1/(AI257:AK257<>""),AI257:AK257))) | IF(OR(F257="",AM257=""),"",IF(COUNT(AI257:AL257)=0,"",AM257-LOOKUP(2,1/(AI257:AL257<>""),AI257:AL257))) | IF(OR(F257="",AN257=""),"",IF(COUNT(AI257:AM257)=0,"",AN257-LOOKUP(2,1/(AI257:AM257<>""),AI257:AM257))) | IF(OR(F257="",AO257=""),"",IF(COUNT(AI257:AN257)=0,"",AO257-LOOKUP(2,1/(AI257:AN257<>""),AI257:AN257))) | IF(OR(F257="",AP257=""),"",IF(COUNT(AI257:AO257)=0,"",AP257-LOOKUP(2,1/(AI257:AO257<>""),AI257:AO257))) | IF(OR(F257="",AQ257=""),"",IF(COUNT(AI257:AP257)=0,"",AQ257-LOOKUP(2,1/(AI257:AP257<>""),AI257:AP257))) | IF(OR(F257="",AR257=""),"",IF(COUNT(AI257:AQ257)=0,"",AR257-LOOKUP(2,1/(AI257:AQ257<>""),AI257:AQ257))) | IF(OR(F257="",AS257=""),"",IF(COUNT(AI257:AR257)=0,"",AS257-LOOKUP(2,1/(AI257:AR257<>""),AI257:AR257))) | IF(OR(F257="",AT257=""),"",IF(COUNT(AI257:AS257)=0,"",AT257-LOOKUP(2,1/(AI257:AS257<>""),AI257:AS257))) | IF(OR(F257="",AU257=""),"",IF(COUNT(AI257:AT257)=0,"",AU257-LOOKUP(2,1/(AI257:AT257<>""),AI257:AT257))) | IF(OR(F257="",AV257=""),"",IF(COUNT(AI257:AU257)=0,"",AV257-LOOKUP(2,1/(AI257:AU257<>""),AI257:AU257))) | IF(J257="","All_Provinces",IFERROR(VLOOKUP(J257,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K257="","All_Districts",IFERROR(VLOOKUP(K257,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F258="","",ROW()-3) | [18 empty] | IF(AQ258="","",AQ258) |  |  |  | IF(W258<>"",W258,IF(OR(T258="",V258=""),"",EDATE(T258,V258))) |  |  |  |  | IF(F258="","",IF(COUNT(AI258:AV258)=0,IF(AA258="","Not started",AA258),SUBSTITUTE(LOOKUP(2,1/(AI258:AV258<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F258="",COUNT(AI258:AV258)=0),"",TODAY()-LOOKUP(2,1/(AI258:AV258<>""),AI258:AV258)) | IF(OR(F258="",COUNT(AI258:AV258)<2),"",LOOKUP(2,1/(AI258:AV258<>""),AI258:AV258)-MIN(AI258:AV258)) | IF(OR(AD258="",AC258="Not started",AC258=""),"",IFERROR(AD258-IF(VLOOKUP(AC258,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC258,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F258="","",IF(OR(AA258="Cancelled",AC258="Cancelled"),"Cancelled",IF(OR(AC258="Completed / Handover",Y258<>"",Z258>=100),"Completed — on track",IF(O258="Not awarded",IF(U258="",IF(X258="","No planned date",IF(TODAY()>X258,"Behind — past planned date",IF(X258-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U258,"Behind — award date passed",IF(U258-TODAY()<=30,"At risk — close to off track","On track"))),IF(X258="","No planned date",IF(AND(TODAY()>X258,OR(Z258="",Z258<100)),"Behind — past end date",IF(AND(T258<>"",X258<>"",Z258<>"",(Z258<100),((TODAY()-T258)/MAX(X258-T258,1)*100)-Z258>15),"Behind — progress lag",IF(AND(X258-TODAY()<=30,X258-TODAY()>=0,OR(Z258="",Z258<90)),"At risk — close to off track","On track")))))))) | IF(OR(F258="",AC258="Completed / Handover",AC258="Cancelled"),"",IF(O258="Not awarded",IF(U258<>"",U258-TODAY(),IF(X258="","",X258-TODAY())),IF(X258="","",X258-TODAY()))) | [14 empty] | IF(OR(F258="",AJ258=""),"",IF(COUNT(AI258:AI258)=0,"",AJ258-LOOKUP(2,1/(AI258:AI258<>""),AI258:AI258))) | IF(OR(F258="",AK258=""),"",IF(COUNT(AI258:AJ258)=0,"",AK258-LOOKUP(2,1/(AI258:AJ258<>""),AI258:AJ258))) | IF(OR(F258="",AL258=""),"",IF(COUNT(AI258:AK258)=0,"",AL258-LOOKUP(2,1/(AI258:AK258<>""),AI258:AK258))) | IF(OR(F258="",AM258=""),"",IF(COUNT(AI258:AL258)=0,"",AM258-LOOKUP(2,1/(AI258:AL258<>""),AI258:AL258))) | IF(OR(F258="",AN258=""),"",IF(COUNT(AI258:AM258)=0,"",AN258-LOOKUP(2,1/(AI258:AM258<>""),AI258:AM258))) | IF(OR(F258="",AO258=""),"",IF(COUNT(AI258:AN258)=0,"",AO258-LOOKUP(2,1/(AI258:AN258<>""),AI258:AN258))) | IF(OR(F258="",AP258=""),"",IF(COUNT(AI258:AO258)=0,"",AP258-LOOKUP(2,1/(AI258:AO258<>""),AI258:AO258))) | IF(OR(F258="",AQ258=""),"",IF(COUNT(AI258:AP258)=0,"",AQ258-LOOKUP(2,1/(AI258:AP258<>""),AI258:AP258))) | IF(OR(F258="",AR258=""),"",IF(COUNT(AI258:AQ258)=0,"",AR258-LOOKUP(2,1/(AI258:AQ258<>""),AI258:AQ258))) | IF(OR(F258="",AS258=""),"",IF(COUNT(AI258:AR258)=0,"",AS258-LOOKUP(2,1/(AI258:AR258<>""),AI258:AR258))) | IF(OR(F258="",AT258=""),"",IF(COUNT(AI258:AS258)=0,"",AT258-LOOKUP(2,1/(AI258:AS258<>""),AI258:AS258))) | IF(OR(F258="",AU258=""),"",IF(COUNT(AI258:AT258)=0,"",AU258-LOOKUP(2,1/(AI258:AT258<>""),AI258:AT258))) | IF(OR(F258="",AV258=""),"",IF(COUNT(AI258:AU258)=0,"",AV258-LOOKUP(2,1/(AI258:AU258<>""),AI258:AU258))) | IF(J258="","All_Provinces",IFERROR(VLOOKUP(J258,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K258="","All_Districts",IFERROR(VLOOKUP(K258,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F259="","",ROW()-3) | [18 empty] | IF(AQ259="","",AQ259) |  |  |  | IF(W259<>"",W259,IF(OR(T259="",V259=""),"",EDATE(T259,V259))) |  |  |  |  | IF(F259="","",IF(COUNT(AI259:AV259)=0,IF(AA259="","Not started",AA259),SUBSTITUTE(LOOKUP(2,1/(AI259:AV259<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F259="",COUNT(AI259:AV259)=0),"",TODAY()-LOOKUP(2,1/(AI259:AV259<>""),AI259:AV259)) | IF(OR(F259="",COUNT(AI259:AV259)<2),"",LOOKUP(2,1/(AI259:AV259<>""),AI259:AV259)-MIN(AI259:AV259)) | IF(OR(AD259="",AC259="Not started",AC259=""),"",IFERROR(AD259-IF(VLOOKUP(AC259,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC259,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F259="","",IF(OR(AA259="Cancelled",AC259="Cancelled"),"Cancelled",IF(OR(AC259="Completed / Handover",Y259<>"",Z259>=100),"Completed — on track",IF(O259="Not awarded",IF(U259="",IF(X259="","No planned date",IF(TODAY()>X259,"Behind — past planned date",IF(X259-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U259,"Behind — award date passed",IF(U259-TODAY()<=30,"At risk — close to off track","On track"))),IF(X259="","No planned date",IF(AND(TODAY()>X259,OR(Z259="",Z259<100)),"Behind — past end date",IF(AND(T259<>"",X259<>"",Z259<>"",(Z259<100),((TODAY()-T259)/MAX(X259-T259,1)*100)-Z259>15),"Behind — progress lag",IF(AND(X259-TODAY()<=30,X259-TODAY()>=0,OR(Z259="",Z259<90)),"At risk — close to off track","On track")))))))) | IF(OR(F259="",AC259="Completed / Handover",AC259="Cancelled"),"",IF(O259="Not awarded",IF(U259<>"",U259-TODAY(),IF(X259="","",X259-TODAY())),IF(X259="","",X259-TODAY()))) | [14 empty] | IF(OR(F259="",AJ259=""),"",IF(COUNT(AI259:AI259)=0,"",AJ259-LOOKUP(2,1/(AI259:AI259<>""),AI259:AI259))) | IF(OR(F259="",AK259=""),"",IF(COUNT(AI259:AJ259)=0,"",AK259-LOOKUP(2,1/(AI259:AJ259<>""),AI259:AJ259))) | IF(OR(F259="",AL259=""),"",IF(COUNT(AI259:AK259)=0,"",AL259-LOOKUP(2,1/(AI259:AK259<>""),AI259:AK259))) | IF(OR(F259="",AM259=""),"",IF(COUNT(AI259:AL259)=0,"",AM259-LOOKUP(2,1/(AI259:AL259<>""),AI259:AL259))) | IF(OR(F259="",AN259=""),"",IF(COUNT(AI259:AM259)=0,"",AN259-LOOKUP(2,1/(AI259:AM259<>""),AI259:AM259))) | IF(OR(F259="",AO259=""),"",IF(COUNT(AI259:AN259)=0,"",AO259-LOOKUP(2,1/(AI259:AN259<>""),AI259:AN259))) | IF(OR(F259="",AP259=""),"",IF(COUNT(AI259:AO259)=0,"",AP259-LOOKUP(2,1/(AI259:AO259<>""),AI259:AO259))) | IF(OR(F259="",AQ259=""),"",IF(COUNT(AI259:AP259)=0,"",AQ259-LOOKUP(2,1/(AI259:AP259<>""),AI259:AP259))) | IF(OR(F259="",AR259=""),"",IF(COUNT(AI259:AQ259)=0,"",AR259-LOOKUP(2,1/(AI259:AQ259<>""),AI259:AQ259))) | IF(OR(F259="",AS259=""),"",IF(COUNT(AI259:AR259)=0,"",AS259-LOOKUP(2,1/(AI259:AR259<>""),AI259:AR259))) | IF(OR(F259="",AT259=""),"",IF(COUNT(AI259:AS259)=0,"",AT259-LOOKUP(2,1/(AI259:AS259<>""),AI259:AS259))) | IF(OR(F259="",AU259=""),"",IF(COUNT(AI259:AT259)=0,"",AU259-LOOKUP(2,1/(AI259:AT259<>""),AI259:AT259))) | IF(OR(F259="",AV259=""),"",IF(COUNT(AI259:AU259)=0,"",AV259-LOOKUP(2,1/(AI259:AU259<>""),AI259:AU259))) | IF(J259="","All_Provinces",IFERROR(VLOOKUP(J259,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K259="","All_Districts",IFERROR(VLOOKUP(K259,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F260="","",ROW()-3) | [18 empty] | IF(AQ260="","",AQ260) |  |  |  | IF(W260<>"",W260,IF(OR(T260="",V260=""),"",EDATE(T260,V260))) |  |  |  |  | IF(F260="","",IF(COUNT(AI260:AV260)=0,IF(AA260="","Not started",AA260),SUBSTITUTE(LOOKUP(2,1/(AI260:AV260<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F260="",COUNT(AI260:AV260)=0),"",TODAY()-LOOKUP(2,1/(AI260:AV260<>""),AI260:AV260)) | IF(OR(F260="",COUNT(AI260:AV260)<2),"",LOOKUP(2,1/(AI260:AV260<>""),AI260:AV260)-MIN(AI260:AV260)) | IF(OR(AD260="",AC260="Not started",AC260=""),"",IFERROR(AD260-IF(VLOOKUP(AC260,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC260,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F260="","",IF(OR(AA260="Cancelled",AC260="Cancelled"),"Cancelled",IF(OR(AC260="Completed / Handover",Y260<>"",Z260>=100),"Completed — on track",IF(O260="Not awarded",IF(U260="",IF(X260="","No planned date",IF(TODAY()>X260,"Behind — past planned date",IF(X260-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U260,"Behind — award date passed",IF(U260-TODAY()<=30,"At risk — close to off track","On track"))),IF(X260="","No planned date",IF(AND(TODAY()>X260,OR(Z260="",Z260<100)),"Behind — past end date",IF(AND(T260<>"",X260<>"",Z260<>"",(Z260<100),((TODAY()-T260)/MAX(X260-T260,1)*100)-Z260>15),"Behind — progress lag",IF(AND(X260-TODAY()<=30,X260-TODAY()>=0,OR(Z260="",Z260<90)),"At risk — close to off track","On track")))))))) | IF(OR(F260="",AC260="Completed / Handover",AC260="Cancelled"),"",IF(O260="Not awarded",IF(U260<>"",U260-TODAY(),IF(X260="","",X260-TODAY())),IF(X260="","",X260-TODAY()))) | [14 empty] | IF(OR(F260="",AJ260=""),"",IF(COUNT(AI260:AI260)=0,"",AJ260-LOOKUP(2,1/(AI260:AI260<>""),AI260:AI260))) | IF(OR(F260="",AK260=""),"",IF(COUNT(AI260:AJ260)=0,"",AK260-LOOKUP(2,1/(AI260:AJ260<>""),AI260:AJ260))) | IF(OR(F260="",AL260=""),"",IF(COUNT(AI260:AK260)=0,"",AL260-LOOKUP(2,1/(AI260:AK260<>""),AI260:AK260))) | IF(OR(F260="",AM260=""),"",IF(COUNT(AI260:AL260)=0,"",AM260-LOOKUP(2,1/(AI260:AL260<>""),AI260:AL260))) | IF(OR(F260="",AN260=""),"",IF(COUNT(AI260:AM260)=0,"",AN260-LOOKUP(2,1/(AI260:AM260<>""),AI260:AM260))) | IF(OR(F260="",AO260=""),"",IF(COUNT(AI260:AN260)=0,"",AO260-LOOKUP(2,1/(AI260:AN260<>""),AI260:AN260))) | IF(OR(F260="",AP260=""),"",IF(COUNT(AI260:AO260)=0,"",AP260-LOOKUP(2,1/(AI260:AO260<>""),AI260:AO260))) | IF(OR(F260="",AQ260=""),"",IF(COUNT(AI260:AP260)=0,"",AQ260-LOOKUP(2,1/(AI260:AP260<>""),AI260:AP260))) | IF(OR(F260="",AR260=""),"",IF(COUNT(AI260:AQ260)=0,"",AR260-LOOKUP(2,1/(AI260:AQ260<>""),AI260:AQ260))) | IF(OR(F260="",AS260=""),"",IF(COUNT(AI260:AR260)=0,"",AS260-LOOKUP(2,1/(AI260:AR260<>""),AI260:AR260))) | IF(OR(F260="",AT260=""),"",IF(COUNT(AI260:AS260)=0,"",AT260-LOOKUP(2,1/(AI260:AS260<>""),AI260:AS260))) | IF(OR(F260="",AU260=""),"",IF(COUNT(AI260:AT260)=0,"",AU260-LOOKUP(2,1/(AI260:AT260<>""),AI260:AT260))) | IF(OR(F260="",AV260=""),"",IF(COUNT(AI260:AU260)=0,"",AV260-LOOKUP(2,1/(AI260:AU260<>""),AI260:AU260))) | IF(J260="","All_Provinces",IFERROR(VLOOKUP(J260,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K260="","All_Districts",IFERROR(VLOOKUP(K260,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F261="","",ROW()-3) | [18 empty] | IF(AQ261="","",AQ261) |  |  |  | IF(W261<>"",W261,IF(OR(T261="",V261=""),"",EDATE(T261,V261))) |  |  |  |  | IF(F261="","",IF(COUNT(AI261:AV261)=0,IF(AA261="","Not started",AA261),SUBSTITUTE(LOOKUP(2,1/(AI261:AV261<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F261="",COUNT(AI261:AV261)=0),"",TODAY()-LOOKUP(2,1/(AI261:AV261<>""),AI261:AV261)) | IF(OR(F261="",COUNT(AI261:AV261)<2),"",LOOKUP(2,1/(AI261:AV261<>""),AI261:AV261)-MIN(AI261:AV261)) | IF(OR(AD261="",AC261="Not started",AC261=""),"",IFERROR(AD261-IF(VLOOKUP(AC261,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC261,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F261="","",IF(OR(AA261="Cancelled",AC261="Cancelled"),"Cancelled",IF(OR(AC261="Completed / Handover",Y261<>"",Z261>=100),"Completed — on track",IF(O261="Not awarded",IF(U261="",IF(X261="","No planned date",IF(TODAY()>X261,"Behind — past planned date",IF(X261-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U261,"Behind — award date passed",IF(U261-TODAY()<=30,"At risk — close to off track","On track"))),IF(X261="","No planned date",IF(AND(TODAY()>X261,OR(Z261="",Z261<100)),"Behind — past end date",IF(AND(T261<>"",X261<>"",Z261<>"",(Z261<100),((TODAY()-T261)/MAX(X261-T261,1)*100)-Z261>15),"Behind — progress lag",IF(AND(X261-TODAY()<=30,X261-TODAY()>=0,OR(Z261="",Z261<90)),"At risk — close to off track","On track")))))))) | IF(OR(F261="",AC261="Completed / Handover",AC261="Cancelled"),"",IF(O261="Not awarded",IF(U261<>"",U261-TODAY(),IF(X261="","",X261-TODAY())),IF(X261="","",X261-TODAY()))) | [14 empty] | IF(OR(F261="",AJ261=""),"",IF(COUNT(AI261:AI261)=0,"",AJ261-LOOKUP(2,1/(AI261:AI261<>""),AI261:AI261))) | IF(OR(F261="",AK261=""),"",IF(COUNT(AI261:AJ261)=0,"",AK261-LOOKUP(2,1/(AI261:AJ261<>""),AI261:AJ261))) | IF(OR(F261="",AL261=""),"",IF(COUNT(AI261:AK261)=0,"",AL261-LOOKUP(2,1/(AI261:AK261<>""),AI261:AK261))) | IF(OR(F261="",AM261=""),"",IF(COUNT(AI261:AL261)=0,"",AM261-LOOKUP(2,1/(AI261:AL261<>""),AI261:AL261))) | IF(OR(F261="",AN261=""),"",IF(COUNT(AI261:AM261)=0,"",AN261-LOOKUP(2,1/(AI261:AM261<>""),AI261:AM261))) | IF(OR(F261="",AO261=""),"",IF(COUNT(AI261:AN261)=0,"",AO261-LOOKUP(2,1/(AI261:AN261<>""),AI261:AN261))) | IF(OR(F261="",AP261=""),"",IF(COUNT(AI261:AO261)=0,"",AP261-LOOKUP(2,1/(AI261:AO261<>""),AI261:AO261))) | IF(OR(F261="",AQ261=""),"",IF(COUNT(AI261:AP261)=0,"",AQ261-LOOKUP(2,1/(AI261:AP261<>""),AI261:AP261))) | IF(OR(F261="",AR261=""),"",IF(COUNT(AI261:AQ261)=0,"",AR261-LOOKUP(2,1/(AI261:AQ261<>""),AI261:AQ261))) | IF(OR(F261="",AS261=""),"",IF(COUNT(AI261:AR261)=0,"",AS261-LOOKUP(2,1/(AI261:AR261<>""),AI261:AR261))) | IF(OR(F261="",AT261=""),"",IF(COUNT(AI261:AS261)=0,"",AT261-LOOKUP(2,1/(AI261:AS261<>""),AI261:AS261))) | IF(OR(F261="",AU261=""),"",IF(COUNT(AI261:AT261)=0,"",AU261-LOOKUP(2,1/(AI261:AT261<>""),AI261:AT261))) | IF(OR(F261="",AV261=""),"",IF(COUNT(AI261:AU261)=0,"",AV261-LOOKUP(2,1/(AI261:AU261<>""),AI261:AU261))) | IF(J261="","All_Provinces",IFERROR(VLOOKUP(J261,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K261="","All_Districts",IFERROR(VLOOKUP(K261,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F262="","",ROW()-3) | [18 empty] | IF(AQ262="","",AQ262) |  |  |  | IF(W262<>"",W262,IF(OR(T262="",V262=""),"",EDATE(T262,V262))) |  |  |  |  | IF(F262="","",IF(COUNT(AI262:AV262)=0,IF(AA262="","Not started",AA262),SUBSTITUTE(LOOKUP(2,1/(AI262:AV262<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F262="",COUNT(AI262:AV262)=0),"",TODAY()-LOOKUP(2,1/(AI262:AV262<>""),AI262:AV262)) | IF(OR(F262="",COUNT(AI262:AV262)<2),"",LOOKUP(2,1/(AI262:AV262<>""),AI262:AV262)-MIN(AI262:AV262)) | IF(OR(AD262="",AC262="Not started",AC262=""),"",IFERROR(AD262-IF(VLOOKUP(AC262,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC262,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F262="","",IF(OR(AA262="Cancelled",AC262="Cancelled"),"Cancelled",IF(OR(AC262="Completed / Handover",Y262<>"",Z262>=100),"Completed — on track",IF(O262="Not awarded",IF(U262="",IF(X262="","No planned date",IF(TODAY()>X262,"Behind — past planned date",IF(X262-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U262,"Behind — award date passed",IF(U262-TODAY()<=30,"At risk — close to off track","On track"))),IF(X262="","No planned date",IF(AND(TODAY()>X262,OR(Z262="",Z262<100)),"Behind — past end date",IF(AND(T262<>"",X262<>"",Z262<>"",(Z262<100),((TODAY()-T262)/MAX(X262-T262,1)*100)-Z262>15),"Behind — progress lag",IF(AND(X262-TODAY()<=30,X262-TODAY()>=0,OR(Z262="",Z262<90)),"At risk — close to off track","On track")))))))) | IF(OR(F262="",AC262="Completed / Handover",AC262="Cancelled"),"",IF(O262="Not awarded",IF(U262<>"",U262-TODAY(),IF(X262="","",X262-TODAY())),IF(X262="","",X262-TODAY()))) | [14 empty] | IF(OR(F262="",AJ262=""),"",IF(COUNT(AI262:AI262)=0,"",AJ262-LOOKUP(2,1/(AI262:AI262<>""),AI262:AI262))) | IF(OR(F262="",AK262=""),"",IF(COUNT(AI262:AJ262)=0,"",AK262-LOOKUP(2,1/(AI262:AJ262<>""),AI262:AJ262))) | IF(OR(F262="",AL262=""),"",IF(COUNT(AI262:AK262)=0,"",AL262-LOOKUP(2,1/(AI262:AK262<>""),AI262:AK262))) | IF(OR(F262="",AM262=""),"",IF(COUNT(AI262:AL262)=0,"",AM262-LOOKUP(2,1/(AI262:AL262<>""),AI262:AL262))) | IF(OR(F262="",AN262=""),"",IF(COUNT(AI262:AM262)=0,"",AN262-LOOKUP(2,1/(AI262:AM262<>""),AI262:AM262))) | IF(OR(F262="",AO262=""),"",IF(COUNT(AI262:AN262)=0,"",AO262-LOOKUP(2,1/(AI262:AN262<>""),AI262:AN262))) | IF(OR(F262="",AP262=""),"",IF(COUNT(AI262:AO262)=0,"",AP262-LOOKUP(2,1/(AI262:AO262<>""),AI262:AO262))) | IF(OR(F262="",AQ262=""),"",IF(COUNT(AI262:AP262)=0,"",AQ262-LOOKUP(2,1/(AI262:AP262<>""),AI262:AP262))) | IF(OR(F262="",AR262=""),"",IF(COUNT(AI262:AQ262)=0,"",AR262-LOOKUP(2,1/(AI262:AQ262<>""),AI262:AQ262))) | IF(OR(F262="",AS262=""),"",IF(COUNT(AI262:AR262)=0,"",AS262-LOOKUP(2,1/(AI262:AR262<>""),AI262:AR262))) | IF(OR(F262="",AT262=""),"",IF(COUNT(AI262:AS262)=0,"",AT262-LOOKUP(2,1/(AI262:AS262<>""),AI262:AS262))) | IF(OR(F262="",AU262=""),"",IF(COUNT(AI262:AT262)=0,"",AU262-LOOKUP(2,1/(AI262:AT262<>""),AI262:AT262))) | IF(OR(F262="",AV262=""),"",IF(COUNT(AI262:AU262)=0,"",AV262-LOOKUP(2,1/(AI262:AU262<>""),AI262:AU262))) | IF(J262="","All_Provinces",IFERROR(VLOOKUP(J262,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K262="","All_Districts",IFERROR(VLOOKUP(K262,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F263="","",ROW()-3) | [18 empty] | IF(AQ263="","",AQ263) |  |  |  | IF(W263<>"",W263,IF(OR(T263="",V263=""),"",EDATE(T263,V263))) |  |  |  |  | IF(F263="","",IF(COUNT(AI263:AV263)=0,IF(AA263="","Not started",AA263),SUBSTITUTE(LOOKUP(2,1/(AI263:AV263<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F263="",COUNT(AI263:AV263)=0),"",TODAY()-LOOKUP(2,1/(AI263:AV263<>""),AI263:AV263)) | IF(OR(F263="",COUNT(AI263:AV263)<2),"",LOOKUP(2,1/(AI263:AV263<>""),AI263:AV263)-MIN(AI263:AV263)) | IF(OR(AD263="",AC263="Not started",AC263=""),"",IFERROR(AD263-IF(VLOOKUP(AC263,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC263,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F263="","",IF(OR(AA263="Cancelled",AC263="Cancelled"),"Cancelled",IF(OR(AC263="Completed / Handover",Y263<>"",Z263>=100),"Completed — on track",IF(O263="Not awarded",IF(U263="",IF(X263="","No planned date",IF(TODAY()>X263,"Behind — past planned date",IF(X263-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U263,"Behind — award date passed",IF(U263-TODAY()<=30,"At risk — close to off track","On track"))),IF(X263="","No planned date",IF(AND(TODAY()>X263,OR(Z263="",Z263<100)),"Behind — past end date",IF(AND(T263<>"",X263<>"",Z263<>"",(Z263<100),((TODAY()-T263)/MAX(X263-T263,1)*100)-Z263>15),"Behind — progress lag",IF(AND(X263-TODAY()<=30,X263-TODAY()>=0,OR(Z263="",Z263<90)),"At risk — close to off track","On track")))))))) | IF(OR(F263="",AC263="Completed / Handover",AC263="Cancelled"),"",IF(O263="Not awarded",IF(U263<>"",U263-TODAY(),IF(X263="","",X263-TODAY())),IF(X263="","",X263-TODAY()))) | [14 empty] | IF(OR(F263="",AJ263=""),"",IF(COUNT(AI263:AI263)=0,"",AJ263-LOOKUP(2,1/(AI263:AI263<>""),AI263:AI263))) | IF(OR(F263="",AK263=""),"",IF(COUNT(AI263:AJ263)=0,"",AK263-LOOKUP(2,1/(AI263:AJ263<>""),AI263:AJ263))) | IF(OR(F263="",AL263=""),"",IF(COUNT(AI263:AK263)=0,"",AL263-LOOKUP(2,1/(AI263:AK263<>""),AI263:AK263))) | IF(OR(F263="",AM263=""),"",IF(COUNT(AI263:AL263)=0,"",AM263-LOOKUP(2,1/(AI263:AL263<>""),AI263:AL263))) | IF(OR(F263="",AN263=""),"",IF(COUNT(AI263:AM263)=0,"",AN263-LOOKUP(2,1/(AI263:AM263<>""),AI263:AM263))) | IF(OR(F263="",AO263=""),"",IF(COUNT(AI263:AN263)=0,"",AO263-LOOKUP(2,1/(AI263:AN263<>""),AI263:AN263))) | IF(OR(F263="",AP263=""),"",IF(COUNT(AI263:AO263)=0,"",AP263-LOOKUP(2,1/(AI263:AO263<>""),AI263:AO263))) | IF(OR(F263="",AQ263=""),"",IF(COUNT(AI263:AP263)=0,"",AQ263-LOOKUP(2,1/(AI263:AP263<>""),AI263:AP263))) | IF(OR(F263="",AR263=""),"",IF(COUNT(AI263:AQ263)=0,"",AR263-LOOKUP(2,1/(AI263:AQ263<>""),AI263:AQ263))) | IF(OR(F263="",AS263=""),"",IF(COUNT(AI263:AR263)=0,"",AS263-LOOKUP(2,1/(AI263:AR263<>""),AI263:AR263))) | IF(OR(F263="",AT263=""),"",IF(COUNT(AI263:AS263)=0,"",AT263-LOOKUP(2,1/(AI263:AS263<>""),AI263:AS263))) | IF(OR(F263="",AU263=""),"",IF(COUNT(AI263:AT263)=0,"",AU263-LOOKUP(2,1/(AI263:AT263<>""),AI263:AT263))) | IF(OR(F263="",AV263=""),"",IF(COUNT(AI263:AU263)=0,"",AV263-LOOKUP(2,1/(AI263:AU263<>""),AI263:AU263))) | IF(J263="","All_Provinces",IFERROR(VLOOKUP(J263,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K263="","All_Districts",IFERROR(VLOOKUP(K263,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F264="","",ROW()-3) | [18 empty] | IF(AQ264="","",AQ264) |  |  |  | IF(W264<>"",W264,IF(OR(T264="",V264=""),"",EDATE(T264,V264))) |  |  |  |  | IF(F264="","",IF(COUNT(AI264:AV264)=0,IF(AA264="","Not started",AA264),SUBSTITUTE(LOOKUP(2,1/(AI264:AV264<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F264="",COUNT(AI264:AV264)=0),"",TODAY()-LOOKUP(2,1/(AI264:AV264<>""),AI264:AV264)) | IF(OR(F264="",COUNT(AI264:AV264)<2),"",LOOKUP(2,1/(AI264:AV264<>""),AI264:AV264)-MIN(AI264:AV264)) | IF(OR(AD264="",AC264="Not started",AC264=""),"",IFERROR(AD264-IF(VLOOKUP(AC264,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC264,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F264="","",IF(OR(AA264="Cancelled",AC264="Cancelled"),"Cancelled",IF(OR(AC264="Completed / Handover",Y264<>"",Z264>=100),"Completed — on track",IF(O264="Not awarded",IF(U264="",IF(X264="","No planned date",IF(TODAY()>X264,"Behind — past planned date",IF(X264-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U264,"Behind — award date passed",IF(U264-TODAY()<=30,"At risk — close to off track","On track"))),IF(X264="","No planned date",IF(AND(TODAY()>X264,OR(Z264="",Z264<100)),"Behind — past end date",IF(AND(T264<>"",X264<>"",Z264<>"",(Z264<100),((TODAY()-T264)/MAX(X264-T264,1)*100)-Z264>15),"Behind — progress lag",IF(AND(X264-TODAY()<=30,X264-TODAY()>=0,OR(Z264="",Z264<90)),"At risk — close to off track","On track")))))))) | IF(OR(F264="",AC264="Completed / Handover",AC264="Cancelled"),"",IF(O264="Not awarded",IF(U264<>"",U264-TODAY(),IF(X264="","",X264-TODAY())),IF(X264="","",X264-TODAY()))) | [14 empty] | IF(OR(F264="",AJ264=""),"",IF(COUNT(AI264:AI264)=0,"",AJ264-LOOKUP(2,1/(AI264:AI264<>""),AI264:AI264))) | IF(OR(F264="",AK264=""),"",IF(COUNT(AI264:AJ264)=0,"",AK264-LOOKUP(2,1/(AI264:AJ264<>""),AI264:AJ264))) | IF(OR(F264="",AL264=""),"",IF(COUNT(AI264:AK264)=0,"",AL264-LOOKUP(2,1/(AI264:AK264<>""),AI264:AK264))) | IF(OR(F264="",AM264=""),"",IF(COUNT(AI264:AL264)=0,"",AM264-LOOKUP(2,1/(AI264:AL264<>""),AI264:AL264))) | IF(OR(F264="",AN264=""),"",IF(COUNT(AI264:AM264)=0,"",AN264-LOOKUP(2,1/(AI264:AM264<>""),AI264:AM264))) | IF(OR(F264="",AO264=""),"",IF(COUNT(AI264:AN264)=0,"",AO264-LOOKUP(2,1/(AI264:AN264<>""),AI264:AN264))) | IF(OR(F264="",AP264=""),"",IF(COUNT(AI264:AO264)=0,"",AP264-LOOKUP(2,1/(AI264:AO264<>""),AI264:AO264))) | IF(OR(F264="",AQ264=""),"",IF(COUNT(AI264:AP264)=0,"",AQ264-LOOKUP(2,1/(AI264:AP264<>""),AI264:AP264))) | IF(OR(F264="",AR264=""),"",IF(COUNT(AI264:AQ264)=0,"",AR264-LOOKUP(2,1/(AI264:AQ264<>""),AI264:AQ264))) | IF(OR(F264="",AS264=""),"",IF(COUNT(AI264:AR264)=0,"",AS264-LOOKUP(2,1/(AI264:AR264<>""),AI264:AR264))) | IF(OR(F264="",AT264=""),"",IF(COUNT(AI264:AS264)=0,"",AT264-LOOKUP(2,1/(AI264:AS264<>""),AI264:AS264))) | IF(OR(F264="",AU264=""),"",IF(COUNT(AI264:AT264)=0,"",AU264-LOOKUP(2,1/(AI264:AT264<>""),AI264:AT264))) | IF(OR(F264="",AV264=""),"",IF(COUNT(AI264:AU264)=0,"",AV264-LOOKUP(2,1/(AI264:AU264<>""),AI264:AU264))) | IF(J264="","All_Provinces",IFERROR(VLOOKUP(J264,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K264="","All_Districts",IFERROR(VLOOKUP(K264,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F265="","",ROW()-3) | [18 empty] | IF(AQ265="","",AQ265) |  |  |  | IF(W265<>"",W265,IF(OR(T265="",V265=""),"",EDATE(T265,V265))) |  |  |  |  | IF(F265="","",IF(COUNT(AI265:AV265)=0,IF(AA265="","Not started",AA265),SUBSTITUTE(LOOKUP(2,1/(AI265:AV265<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F265="",COUNT(AI265:AV265)=0),"",TODAY()-LOOKUP(2,1/(AI265:AV265<>""),AI265:AV265)) | IF(OR(F265="",COUNT(AI265:AV265)<2),"",LOOKUP(2,1/(AI265:AV265<>""),AI265:AV265)-MIN(AI265:AV265)) | IF(OR(AD265="",AC265="Not started",AC265=""),"",IFERROR(AD265-IF(VLOOKUP(AC265,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC265,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F265="","",IF(OR(AA265="Cancelled",AC265="Cancelled"),"Cancelled",IF(OR(AC265="Completed / Handover",Y265<>"",Z265>=100),"Completed — on track",IF(O265="Not awarded",IF(U265="",IF(X265="","No planned date",IF(TODAY()>X265,"Behind — past planned date",IF(X265-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U265,"Behind — award date passed",IF(U265-TODAY()<=30,"At risk — close to off track","On track"))),IF(X265="","No planned date",IF(AND(TODAY()>X265,OR(Z265="",Z265<100)),"Behind — past end date",IF(AND(T265<>"",X265<>"",Z265<>"",(Z265<100),((TODAY()-T265)/MAX(X265-T265,1)*100)-Z265>15),"Behind — progress lag",IF(AND(X265-TODAY()<=30,X265-TODAY()>=0,OR(Z265="",Z265<90)),"At risk — close to off track","On track")))))))) | IF(OR(F265="",AC265="Completed / Handover",AC265="Cancelled"),"",IF(O265="Not awarded",IF(U265<>"",U265-TODAY(),IF(X265="","",X265-TODAY())),IF(X265="","",X265-TODAY()))) | [14 empty] | IF(OR(F265="",AJ265=""),"",IF(COUNT(AI265:AI265)=0,"",AJ265-LOOKUP(2,1/(AI265:AI265<>""),AI265:AI265))) | IF(OR(F265="",AK265=""),"",IF(COUNT(AI265:AJ265)=0,"",AK265-LOOKUP(2,1/(AI265:AJ265<>""),AI265:AJ265))) | IF(OR(F265="",AL265=""),"",IF(COUNT(AI265:AK265)=0,"",AL265-LOOKUP(2,1/(AI265:AK265<>""),AI265:AK265))) | IF(OR(F265="",AM265=""),"",IF(COUNT(AI265:AL265)=0,"",AM265-LOOKUP(2,1/(AI265:AL265<>""),AI265:AL265))) | IF(OR(F265="",AN265=""),"",IF(COUNT(AI265:AM265)=0,"",AN265-LOOKUP(2,1/(AI265:AM265<>""),AI265:AM265))) | IF(OR(F265="",AO265=""),"",IF(COUNT(AI265:AN265)=0,"",AO265-LOOKUP(2,1/(AI265:AN265<>""),AI265:AN265))) | IF(OR(F265="",AP265=""),"",IF(COUNT(AI265:AO265)=0,"",AP265-LOOKUP(2,1/(AI265:AO265<>""),AI265:AO265))) | IF(OR(F265="",AQ265=""),"",IF(COUNT(AI265:AP265)=0,"",AQ265-LOOKUP(2,1/(AI265:AP265<>""),AI265:AP265))) | IF(OR(F265="",AR265=""),"",IF(COUNT(AI265:AQ265)=0,"",AR265-LOOKUP(2,1/(AI265:AQ265<>""),AI265:AQ265))) | IF(OR(F265="",AS265=""),"",IF(COUNT(AI265:AR265)=0,"",AS265-LOOKUP(2,1/(AI265:AR265<>""),AI265:AR265))) | IF(OR(F265="",AT265=""),"",IF(COUNT(AI265:AS265)=0,"",AT265-LOOKUP(2,1/(AI265:AS265<>""),AI265:AS265))) | IF(OR(F265="",AU265=""),"",IF(COUNT(AI265:AT265)=0,"",AU265-LOOKUP(2,1/(AI265:AT265<>""),AI265:AT265))) | IF(OR(F265="",AV265=""),"",IF(COUNT(AI265:AU265)=0,"",AV265-LOOKUP(2,1/(AI265:AU265<>""),AI265:AU265))) | IF(J265="","All_Provinces",IFERROR(VLOOKUP(J265,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K265="","All_Districts",IFERROR(VLOOKUP(K265,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F266="","",ROW()-3) | [18 empty] | IF(AQ266="","",AQ266) |  |  |  | IF(W266<>"",W266,IF(OR(T266="",V266=""),"",EDATE(T266,V266))) |  |  |  |  | IF(F266="","",IF(COUNT(AI266:AV266)=0,IF(AA266="","Not started",AA266),SUBSTITUTE(LOOKUP(2,1/(AI266:AV266<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F266="",COUNT(AI266:AV266)=0),"",TODAY()-LOOKUP(2,1/(AI266:AV266<>""),AI266:AV266)) | IF(OR(F266="",COUNT(AI266:AV266)<2),"",LOOKUP(2,1/(AI266:AV266<>""),AI266:AV266)-MIN(AI266:AV266)) | IF(OR(AD266="",AC266="Not started",AC266=""),"",IFERROR(AD266-IF(VLOOKUP(AC266,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC266,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F266="","",IF(OR(AA266="Cancelled",AC266="Cancelled"),"Cancelled",IF(OR(AC266="Completed / Handover",Y266<>"",Z266>=100),"Completed — on track",IF(O266="Not awarded",IF(U266="",IF(X266="","No planned date",IF(TODAY()>X266,"Behind — past planned date",IF(X266-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U266,"Behind — award date passed",IF(U266-TODAY()<=30,"At risk — close to off track","On track"))),IF(X266="","No planned date",IF(AND(TODAY()>X266,OR(Z266="",Z266<100)),"Behind — past end date",IF(AND(T266<>"",X266<>"",Z266<>"",(Z266<100),((TODAY()-T266)/MAX(X266-T266,1)*100)-Z266>15),"Behind — progress lag",IF(AND(X266-TODAY()<=30,X266-TODAY()>=0,OR(Z266="",Z266<90)),"At risk — close to off track","On track")))))))) | IF(OR(F266="",AC266="Completed / Handover",AC266="Cancelled"),"",IF(O266="Not awarded",IF(U266<>"",U266-TODAY(),IF(X266="","",X266-TODAY())),IF(X266="","",X266-TODAY()))) | [14 empty] | IF(OR(F266="",AJ266=""),"",IF(COUNT(AI266:AI266)=0,"",AJ266-LOOKUP(2,1/(AI266:AI266<>""),AI266:AI266))) | IF(OR(F266="",AK266=""),"",IF(COUNT(AI266:AJ266)=0,"",AK266-LOOKUP(2,1/(AI266:AJ266<>""),AI266:AJ266))) | IF(OR(F266="",AL266=""),"",IF(COUNT(AI266:AK266)=0,"",AL266-LOOKUP(2,1/(AI266:AK266<>""),AI266:AK266))) | IF(OR(F266="",AM266=""),"",IF(COUNT(AI266:AL266)=0,"",AM266-LOOKUP(2,1/(AI266:AL266<>""),AI266:AL266))) | IF(OR(F266="",AN266=""),"",IF(COUNT(AI266:AM266)=0,"",AN266-LOOKUP(2,1/(AI266:AM266<>""),AI266:AM266))) | IF(OR(F266="",AO266=""),"",IF(COUNT(AI266:AN266)=0,"",AO266-LOOKUP(2,1/(AI266:AN266<>""),AI266:AN266))) | IF(OR(F266="",AP266=""),"",IF(COUNT(AI266:AO266)=0,"",AP266-LOOKUP(2,1/(AI266:AO266<>""),AI266:AO266))) | IF(OR(F266="",AQ266=""),"",IF(COUNT(AI266:AP266)=0,"",AQ266-LOOKUP(2,1/(AI266:AP266<>""),AI266:AP266))) | IF(OR(F266="",AR266=""),"",IF(COUNT(AI266:AQ266)=0,"",AR266-LOOKUP(2,1/(AI266:AQ266<>""),AI266:AQ266))) | IF(OR(F266="",AS266=""),"",IF(COUNT(AI266:AR266)=0,"",AS266-LOOKUP(2,1/(AI266:AR266<>""),AI266:AR266))) | IF(OR(F266="",AT266=""),"",IF(COUNT(AI266:AS266)=0,"",AT266-LOOKUP(2,1/(AI266:AS266<>""),AI266:AS266))) | IF(OR(F266="",AU266=""),"",IF(COUNT(AI266:AT266)=0,"",AU266-LOOKUP(2,1/(AI266:AT266<>""),AI266:AT266))) | IF(OR(F266="",AV266=""),"",IF(COUNT(AI266:AU266)=0,"",AV266-LOOKUP(2,1/(AI266:AU266<>""),AI266:AU266))) | IF(J266="","All_Provinces",IFERROR(VLOOKUP(J266,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K266="","All_Districts",IFERROR(VLOOKUP(K266,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F267="","",ROW()-3) | [18 empty] | IF(AQ267="","",AQ267) |  |  |  | IF(W267<>"",W267,IF(OR(T267="",V267=""),"",EDATE(T267,V267))) |  |  |  |  | IF(F267="","",IF(COUNT(AI267:AV267)=0,IF(AA267="","Not started",AA267),SUBSTITUTE(LOOKUP(2,1/(AI267:AV267<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F267="",COUNT(AI267:AV267)=0),"",TODAY()-LOOKUP(2,1/(AI267:AV267<>""),AI267:AV267)) | IF(OR(F267="",COUNT(AI267:AV267)<2),"",LOOKUP(2,1/(AI267:AV267<>""),AI267:AV267)-MIN(AI267:AV267)) | IF(OR(AD267="",AC267="Not started",AC267=""),"",IFERROR(AD267-IF(VLOOKUP(AC267,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC267,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F267="","",IF(OR(AA267="Cancelled",AC267="Cancelled"),"Cancelled",IF(OR(AC267="Completed / Handover",Y267<>"",Z267>=100),"Completed — on track",IF(O267="Not awarded",IF(U267="",IF(X267="","No planned date",IF(TODAY()>X267,"Behind — past planned date",IF(X267-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U267,"Behind — award date passed",IF(U267-TODAY()<=30,"At risk — close to off track","On track"))),IF(X267="","No planned date",IF(AND(TODAY()>X267,OR(Z267="",Z267<100)),"Behind — past end date",IF(AND(T267<>"",X267<>"",Z267<>"",(Z267<100),((TODAY()-T267)/MAX(X267-T267,1)*100)-Z267>15),"Behind — progress lag",IF(AND(X267-TODAY()<=30,X267-TODAY()>=0,OR(Z267="",Z267<90)),"At risk — close to off track","On track")))))))) | IF(OR(F267="",AC267="Completed / Handover",AC267="Cancelled"),"",IF(O267="Not awarded",IF(U267<>"",U267-TODAY(),IF(X267="","",X267-TODAY())),IF(X267="","",X267-TODAY()))) | [14 empty] | IF(OR(F267="",AJ267=""),"",IF(COUNT(AI267:AI267)=0,"",AJ267-LOOKUP(2,1/(AI267:AI267<>""),AI267:AI267))) | IF(OR(F267="",AK267=""),"",IF(COUNT(AI267:AJ267)=0,"",AK267-LOOKUP(2,1/(AI267:AJ267<>""),AI267:AJ267))) | IF(OR(F267="",AL267=""),"",IF(COUNT(AI267:AK267)=0,"",AL267-LOOKUP(2,1/(AI267:AK267<>""),AI267:AK267))) | IF(OR(F267="",AM267=""),"",IF(COUNT(AI267:AL267)=0,"",AM267-LOOKUP(2,1/(AI267:AL267<>""),AI267:AL267))) | IF(OR(F267="",AN267=""),"",IF(COUNT(AI267:AM267)=0,"",AN267-LOOKUP(2,1/(AI267:AM267<>""),AI267:AM267))) | IF(OR(F267="",AO267=""),"",IF(COUNT(AI267:AN267)=0,"",AO267-LOOKUP(2,1/(AI267:AN267<>""),AI267:AN267))) | IF(OR(F267="",AP267=""),"",IF(COUNT(AI267:AO267)=0,"",AP267-LOOKUP(2,1/(AI267:AO267<>""),AI267:AO267))) | IF(OR(F267="",AQ267=""),"",IF(COUNT(AI267:AP267)=0,"",AQ267-LOOKUP(2,1/(AI267:AP267<>""),AI267:AP267))) | IF(OR(F267="",AR267=""),"",IF(COUNT(AI267:AQ267)=0,"",AR267-LOOKUP(2,1/(AI267:AQ267<>""),AI267:AQ267))) | IF(OR(F267="",AS267=""),"",IF(COUNT(AI267:AR267)=0,"",AS267-LOOKUP(2,1/(AI267:AR267<>""),AI267:AR267))) | IF(OR(F267="",AT267=""),"",IF(COUNT(AI267:AS267)=0,"",AT267-LOOKUP(2,1/(AI267:AS267<>""),AI267:AS267))) | IF(OR(F267="",AU267=""),"",IF(COUNT(AI267:AT267)=0,"",AU267-LOOKUP(2,1/(AI267:AT267<>""),AI267:AT267))) | IF(OR(F267="",AV267=""),"",IF(COUNT(AI267:AU267)=0,"",AV267-LOOKUP(2,1/(AI267:AU267<>""),AI267:AU267))) | IF(J267="","All_Provinces",IFERROR(VLOOKUP(J267,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K267="","All_Districts",IFERROR(VLOOKUP(K267,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F268="","",ROW()-3) | [18 empty] | IF(AQ268="","",AQ268) |  |  |  | IF(W268<>"",W268,IF(OR(T268="",V268=""),"",EDATE(T268,V268))) |  |  |  |  | IF(F268="","",IF(COUNT(AI268:AV268)=0,IF(AA268="","Not started",AA268),SUBSTITUTE(LOOKUP(2,1/(AI268:AV268<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F268="",COUNT(AI268:AV268)=0),"",TODAY()-LOOKUP(2,1/(AI268:AV268<>""),AI268:AV268)) | IF(OR(F268="",COUNT(AI268:AV268)<2),"",LOOKUP(2,1/(AI268:AV268<>""),AI268:AV268)-MIN(AI268:AV268)) | IF(OR(AD268="",AC268="Not started",AC268=""),"",IFERROR(AD268-IF(VLOOKUP(AC268,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC268,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F268="","",IF(OR(AA268="Cancelled",AC268="Cancelled"),"Cancelled",IF(OR(AC268="Completed / Handover",Y268<>"",Z268>=100),"Completed — on track",IF(O268="Not awarded",IF(U268="",IF(X268="","No planned date",IF(TODAY()>X268,"Behind — past planned date",IF(X268-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U268,"Behind — award date passed",IF(U268-TODAY()<=30,"At risk — close to off track","On track"))),IF(X268="","No planned date",IF(AND(TODAY()>X268,OR(Z268="",Z268<100)),"Behind — past end date",IF(AND(T268<>"",X268<>"",Z268<>"",(Z268<100),((TODAY()-T268)/MAX(X268-T268,1)*100)-Z268>15),"Behind — progress lag",IF(AND(X268-TODAY()<=30,X268-TODAY()>=0,OR(Z268="",Z268<90)),"At risk — close to off track","On track")))))))) | IF(OR(F268="",AC268="Completed / Handover",AC268="Cancelled"),"",IF(O268="Not awarded",IF(U268<>"",U268-TODAY(),IF(X268="","",X268-TODAY())),IF(X268="","",X268-TODAY()))) | [14 empty] | IF(OR(F268="",AJ268=""),"",IF(COUNT(AI268:AI268)=0,"",AJ268-LOOKUP(2,1/(AI268:AI268<>""),AI268:AI268))) | IF(OR(F268="",AK268=""),"",IF(COUNT(AI268:AJ268)=0,"",AK268-LOOKUP(2,1/(AI268:AJ268<>""),AI268:AJ268))) | IF(OR(F268="",AL268=""),"",IF(COUNT(AI268:AK268)=0,"",AL268-LOOKUP(2,1/(AI268:AK268<>""),AI268:AK268))) | IF(OR(F268="",AM268=""),"",IF(COUNT(AI268:AL268)=0,"",AM268-LOOKUP(2,1/(AI268:AL268<>""),AI268:AL268))) | IF(OR(F268="",AN268=""),"",IF(COUNT(AI268:AM268)=0,"",AN268-LOOKUP(2,1/(AI268:AM268<>""),AI268:AM268))) | IF(OR(F268="",AO268=""),"",IF(COUNT(AI268:AN268)=0,"",AO268-LOOKUP(2,1/(AI268:AN268<>""),AI268:AN268))) | IF(OR(F268="",AP268=""),"",IF(COUNT(AI268:AO268)=0,"",AP268-LOOKUP(2,1/(AI268:AO268<>""),AI268:AO268))) | IF(OR(F268="",AQ268=""),"",IF(COUNT(AI268:AP268)=0,"",AQ268-LOOKUP(2,1/(AI268:AP268<>""),AI268:AP268))) | IF(OR(F268="",AR268=""),"",IF(COUNT(AI268:AQ268)=0,"",AR268-LOOKUP(2,1/(AI268:AQ268<>""),AI268:AQ268))) | IF(OR(F268="",AS268=""),"",IF(COUNT(AI268:AR268)=0,"",AS268-LOOKUP(2,1/(AI268:AR268<>""),AI268:AR268))) | IF(OR(F268="",AT268=""),"",IF(COUNT(AI268:AS268)=0,"",AT268-LOOKUP(2,1/(AI268:AS268<>""),AI268:AS268))) | IF(OR(F268="",AU268=""),"",IF(COUNT(AI268:AT268)=0,"",AU268-LOOKUP(2,1/(AI268:AT268<>""),AI268:AT268))) | IF(OR(F268="",AV268=""),"",IF(COUNT(AI268:AU268)=0,"",AV268-LOOKUP(2,1/(AI268:AU268<>""),AI268:AU268))) | IF(J268="","All_Provinces",IFERROR(VLOOKUP(J268,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K268="","All_Districts",IFERROR(VLOOKUP(K268,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F269="","",ROW()-3) | [18 empty] | IF(AQ269="","",AQ269) |  |  |  | IF(W269<>"",W269,IF(OR(T269="",V269=""),"",EDATE(T269,V269))) |  |  |  |  | IF(F269="","",IF(COUNT(AI269:AV269)=0,IF(AA269="","Not started",AA269),SUBSTITUTE(LOOKUP(2,1/(AI269:AV269<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F269="",COUNT(AI269:AV269)=0),"",TODAY()-LOOKUP(2,1/(AI269:AV269<>""),AI269:AV269)) | IF(OR(F269="",COUNT(AI269:AV269)<2),"",LOOKUP(2,1/(AI269:AV269<>""),AI269:AV269)-MIN(AI269:AV269)) | IF(OR(AD269="",AC269="Not started",AC269=""),"",IFERROR(AD269-IF(VLOOKUP(AC269,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC269,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F269="","",IF(OR(AA269="Cancelled",AC269="Cancelled"),"Cancelled",IF(OR(AC269="Completed / Handover",Y269<>"",Z269>=100),"Completed — on track",IF(O269="Not awarded",IF(U269="",IF(X269="","No planned date",IF(TODAY()>X269,"Behind — past planned date",IF(X269-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U269,"Behind — award date passed",IF(U269-TODAY()<=30,"At risk — close to off track","On track"))),IF(X269="","No planned date",IF(AND(TODAY()>X269,OR(Z269="",Z269<100)),"Behind — past end date",IF(AND(T269<>"",X269<>"",Z269<>"",(Z269<100),((TODAY()-T269)/MAX(X269-T269,1)*100)-Z269>15),"Behind — progress lag",IF(AND(X269-TODAY()<=30,X269-TODAY()>=0,OR(Z269="",Z269<90)),"At risk — close to off track","On track")))))))) | IF(OR(F269="",AC269="Completed / Handover",AC269="Cancelled"),"",IF(O269="Not awarded",IF(U269<>"",U269-TODAY(),IF(X269="","",X269-TODAY())),IF(X269="","",X269-TODAY()))) | [14 empty] | IF(OR(F269="",AJ269=""),"",IF(COUNT(AI269:AI269)=0,"",AJ269-LOOKUP(2,1/(AI269:AI269<>""),AI269:AI269))) | IF(OR(F269="",AK269=""),"",IF(COUNT(AI269:AJ269)=0,"",AK269-LOOKUP(2,1/(AI269:AJ269<>""),AI269:AJ269))) | IF(OR(F269="",AL269=""),"",IF(COUNT(AI269:AK269)=0,"",AL269-LOOKUP(2,1/(AI269:AK269<>""),AI269:AK269))) | IF(OR(F269="",AM269=""),"",IF(COUNT(AI269:AL269)=0,"",AM269-LOOKUP(2,1/(AI269:AL269<>""),AI269:AL269))) | IF(OR(F269="",AN269=""),"",IF(COUNT(AI269:AM269)=0,"",AN269-LOOKUP(2,1/(AI269:AM269<>""),AI269:AM269))) | IF(OR(F269="",AO269=""),"",IF(COUNT(AI269:AN269)=0,"",AO269-LOOKUP(2,1/(AI269:AN269<>""),AI269:AN269))) | IF(OR(F269="",AP269=""),"",IF(COUNT(AI269:AO269)=0,"",AP269-LOOKUP(2,1/(AI269:AO269<>""),AI269:AO269))) | IF(OR(F269="",AQ269=""),"",IF(COUNT(AI269:AP269)=0,"",AQ269-LOOKUP(2,1/(AI269:AP269<>""),AI269:AP269))) | IF(OR(F269="",AR269=""),"",IF(COUNT(AI269:AQ269)=0,"",AR269-LOOKUP(2,1/(AI269:AQ269<>""),AI269:AQ269))) | IF(OR(F269="",AS269=""),"",IF(COUNT(AI269:AR269)=0,"",AS269-LOOKUP(2,1/(AI269:AR269<>""),AI269:AR269))) | IF(OR(F269="",AT269=""),"",IF(COUNT(AI269:AS269)=0,"",AT269-LOOKUP(2,1/(AI269:AS269<>""),AI269:AS269))) | IF(OR(F269="",AU269=""),"",IF(COUNT(AI269:AT269)=0,"",AU269-LOOKUP(2,1/(AI269:AT269<>""),AI269:AT269))) | IF(OR(F269="",AV269=""),"",IF(COUNT(AI269:AU269)=0,"",AV269-LOOKUP(2,1/(AI269:AU269<>""),AI269:AU269))) | IF(J269="","All_Provinces",IFERROR(VLOOKUP(J269,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K269="","All_Districts",IFERROR(VLOOKUP(K269,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F270="","",ROW()-3) | [18 empty] | IF(AQ270="","",AQ270) |  |  |  | IF(W270<>"",W270,IF(OR(T270="",V270=""),"",EDATE(T270,V270))) |  |  |  |  | IF(F270="","",IF(COUNT(AI270:AV270)=0,IF(AA270="","Not started",AA270),SUBSTITUTE(LOOKUP(2,1/(AI270:AV270<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F270="",COUNT(AI270:AV270)=0),"",TODAY()-LOOKUP(2,1/(AI270:AV270<>""),AI270:AV270)) | IF(OR(F270="",COUNT(AI270:AV270)<2),"",LOOKUP(2,1/(AI270:AV270<>""),AI270:AV270)-MIN(AI270:AV270)) | IF(OR(AD270="",AC270="Not started",AC270=""),"",IFERROR(AD270-IF(VLOOKUP(AC270,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC270,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F270="","",IF(OR(AA270="Cancelled",AC270="Cancelled"),"Cancelled",IF(OR(AC270="Completed / Handover",Y270<>"",Z270>=100),"Completed — on track",IF(O270="Not awarded",IF(U270="",IF(X270="","No planned date",IF(TODAY()>X270,"Behind — past planned date",IF(X270-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U270,"Behind — award date passed",IF(U270-TODAY()<=30,"At risk — close to off track","On track"))),IF(X270="","No planned date",IF(AND(TODAY()>X270,OR(Z270="",Z270<100)),"Behind — past end date",IF(AND(T270<>"",X270<>"",Z270<>"",(Z270<100),((TODAY()-T270)/MAX(X270-T270,1)*100)-Z270>15),"Behind — progress lag",IF(AND(X270-TODAY()<=30,X270-TODAY()>=0,OR(Z270="",Z270<90)),"At risk — close to off track","On track")))))))) | IF(OR(F270="",AC270="Completed / Handover",AC270="Cancelled"),"",IF(O270="Not awarded",IF(U270<>"",U270-TODAY(),IF(X270="","",X270-TODAY())),IF(X270="","",X270-TODAY()))) | [14 empty] | IF(OR(F270="",AJ270=""),"",IF(COUNT(AI270:AI270)=0,"",AJ270-LOOKUP(2,1/(AI270:AI270<>""),AI270:AI270))) | IF(OR(F270="",AK270=""),"",IF(COUNT(AI270:AJ270)=0,"",AK270-LOOKUP(2,1/(AI270:AJ270<>""),AI270:AJ270))) | IF(OR(F270="",AL270=""),"",IF(COUNT(AI270:AK270)=0,"",AL270-LOOKUP(2,1/(AI270:AK270<>""),AI270:AK270))) | IF(OR(F270="",AM270=""),"",IF(COUNT(AI270:AL270)=0,"",AM270-LOOKUP(2,1/(AI270:AL270<>""),AI270:AL270))) | IF(OR(F270="",AN270=""),"",IF(COUNT(AI270:AM270)=0,"",AN270-LOOKUP(2,1/(AI270:AM270<>""),AI270:AM270))) | IF(OR(F270="",AO270=""),"",IF(COUNT(AI270:AN270)=0,"",AO270-LOOKUP(2,1/(AI270:AN270<>""),AI270:AN270))) | IF(OR(F270="",AP270=""),"",IF(COUNT(AI270:AO270)=0,"",AP270-LOOKUP(2,1/(AI270:AO270<>""),AI270:AO270))) | IF(OR(F270="",AQ270=""),"",IF(COUNT(AI270:AP270)=0,"",AQ270-LOOKUP(2,1/(AI270:AP270<>""),AI270:AP270))) | IF(OR(F270="",AR270=""),"",IF(COUNT(AI270:AQ270)=0,"",AR270-LOOKUP(2,1/(AI270:AQ270<>""),AI270:AQ270))) | IF(OR(F270="",AS270=""),"",IF(COUNT(AI270:AR270)=0,"",AS270-LOOKUP(2,1/(AI270:AR270<>""),AI270:AR270))) | IF(OR(F270="",AT270=""),"",IF(COUNT(AI270:AS270)=0,"",AT270-LOOKUP(2,1/(AI270:AS270<>""),AI270:AS270))) | IF(OR(F270="",AU270=""),"",IF(COUNT(AI270:AT270)=0,"",AU270-LOOKUP(2,1/(AI270:AT270<>""),AI270:AT270))) | IF(OR(F270="",AV270=""),"",IF(COUNT(AI270:AU270)=0,"",AV270-LOOKUP(2,1/(AI270:AU270<>""),AI270:AU270))) | IF(J270="","All_Provinces",IFERROR(VLOOKUP(J270,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K270="","All_Districts",IFERROR(VLOOKUP(K270,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F271="","",ROW()-3) | [18 empty] | IF(AQ271="","",AQ271) |  |  |  | IF(W271<>"",W271,IF(OR(T271="",V271=""),"",EDATE(T271,V271))) |  |  |  |  | IF(F271="","",IF(COUNT(AI271:AV271)=0,IF(AA271="","Not started",AA271),SUBSTITUTE(LOOKUP(2,1/(AI271:AV271<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F271="",COUNT(AI271:AV271)=0),"",TODAY()-LOOKUP(2,1/(AI271:AV271<>""),AI271:AV271)) | IF(OR(F271="",COUNT(AI271:AV271)<2),"",LOOKUP(2,1/(AI271:AV271<>""),AI271:AV271)-MIN(AI271:AV271)) | IF(OR(AD271="",AC271="Not started",AC271=""),"",IFERROR(AD271-IF(VLOOKUP(AC271,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC271,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F271="","",IF(OR(AA271="Cancelled",AC271="Cancelled"),"Cancelled",IF(OR(AC271="Completed / Handover",Y271<>"",Z271>=100),"Completed — on track",IF(O271="Not awarded",IF(U271="",IF(X271="","No planned date",IF(TODAY()>X271,"Behind — past planned date",IF(X271-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U271,"Behind — award date passed",IF(U271-TODAY()<=30,"At risk — close to off track","On track"))),IF(X271="","No planned date",IF(AND(TODAY()>X271,OR(Z271="",Z271<100)),"Behind — past end date",IF(AND(T271<>"",X271<>"",Z271<>"",(Z271<100),((TODAY()-T271)/MAX(X271-T271,1)*100)-Z271>15),"Behind — progress lag",IF(AND(X271-TODAY()<=30,X271-TODAY()>=0,OR(Z271="",Z271<90)),"At risk — close to off track","On track")))))))) | IF(OR(F271="",AC271="Completed / Handover",AC271="Cancelled"),"",IF(O271="Not awarded",IF(U271<>"",U271-TODAY(),IF(X271="","",X271-TODAY())),IF(X271="","",X271-TODAY()))) | [14 empty] | IF(OR(F271="",AJ271=""),"",IF(COUNT(AI271:AI271)=0,"",AJ271-LOOKUP(2,1/(AI271:AI271<>""),AI271:AI271))) | IF(OR(F271="",AK271=""),"",IF(COUNT(AI271:AJ271)=0,"",AK271-LOOKUP(2,1/(AI271:AJ271<>""),AI271:AJ271))) | IF(OR(F271="",AL271=""),"",IF(COUNT(AI271:AK271)=0,"",AL271-LOOKUP(2,1/(AI271:AK271<>""),AI271:AK271))) | IF(OR(F271="",AM271=""),"",IF(COUNT(AI271:AL271)=0,"",AM271-LOOKUP(2,1/(AI271:AL271<>""),AI271:AL271))) | IF(OR(F271="",AN271=""),"",IF(COUNT(AI271:AM271)=0,"",AN271-LOOKUP(2,1/(AI271:AM271<>""),AI271:AM271))) | IF(OR(F271="",AO271=""),"",IF(COUNT(AI271:AN271)=0,"",AO271-LOOKUP(2,1/(AI271:AN271<>""),AI271:AN271))) | IF(OR(F271="",AP271=""),"",IF(COUNT(AI271:AO271)=0,"",AP271-LOOKUP(2,1/(AI271:AO271<>""),AI271:AO271))) | IF(OR(F271="",AQ271=""),"",IF(COUNT(AI271:AP271)=0,"",AQ271-LOOKUP(2,1/(AI271:AP271<>""),AI271:AP271))) | IF(OR(F271="",AR271=""),"",IF(COUNT(AI271:AQ271)=0,"",AR271-LOOKUP(2,1/(AI271:AQ271<>""),AI271:AQ271))) | IF(OR(F271="",AS271=""),"",IF(COUNT(AI271:AR271)=0,"",AS271-LOOKUP(2,1/(AI271:AR271<>""),AI271:AR271))) | IF(OR(F271="",AT271=""),"",IF(COUNT(AI271:AS271)=0,"",AT271-LOOKUP(2,1/(AI271:AS271<>""),AI271:AS271))) | IF(OR(F271="",AU271=""),"",IF(COUNT(AI271:AT271)=0,"",AU271-LOOKUP(2,1/(AI271:AT271<>""),AI271:AT271))) | IF(OR(F271="",AV271=""),"",IF(COUNT(AI271:AU271)=0,"",AV271-LOOKUP(2,1/(AI271:AU271<>""),AI271:AU271))) | IF(J271="","All_Provinces",IFERROR(VLOOKUP(J271,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K271="","All_Districts",IFERROR(VLOOKUP(K271,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F272="","",ROW()-3) | [18 empty] | IF(AQ272="","",AQ272) |  |  |  | IF(W272<>"",W272,IF(OR(T272="",V272=""),"",EDATE(T272,V272))) |  |  |  |  | IF(F272="","",IF(COUNT(AI272:AV272)=0,IF(AA272="","Not started",AA272),SUBSTITUTE(LOOKUP(2,1/(AI272:AV272<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F272="",COUNT(AI272:AV272)=0),"",TODAY()-LOOKUP(2,1/(AI272:AV272<>""),AI272:AV272)) | IF(OR(F272="",COUNT(AI272:AV272)<2),"",LOOKUP(2,1/(AI272:AV272<>""),AI272:AV272)-MIN(AI272:AV272)) | IF(OR(AD272="",AC272="Not started",AC272=""),"",IFERROR(AD272-IF(VLOOKUP(AC272,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC272,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F272="","",IF(OR(AA272="Cancelled",AC272="Cancelled"),"Cancelled",IF(OR(AC272="Completed / Handover",Y272<>"",Z272>=100),"Completed — on track",IF(O272="Not awarded",IF(U272="",IF(X272="","No planned date",IF(TODAY()>X272,"Behind — past planned date",IF(X272-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U272,"Behind — award date passed",IF(U272-TODAY()<=30,"At risk — close to off track","On track"))),IF(X272="","No planned date",IF(AND(TODAY()>X272,OR(Z272="",Z272<100)),"Behind — past end date",IF(AND(T272<>"",X272<>"",Z272<>"",(Z272<100),((TODAY()-T272)/MAX(X272-T272,1)*100)-Z272>15),"Behind — progress lag",IF(AND(X272-TODAY()<=30,X272-TODAY()>=0,OR(Z272="",Z272<90)),"At risk — close to off track","On track")))))))) | IF(OR(F272="",AC272="Completed / Handover",AC272="Cancelled"),"",IF(O272="Not awarded",IF(U272<>"",U272-TODAY(),IF(X272="","",X272-TODAY())),IF(X272="","",X272-TODAY()))) | [14 empty] | IF(OR(F272="",AJ272=""),"",IF(COUNT(AI272:AI272)=0,"",AJ272-LOOKUP(2,1/(AI272:AI272<>""),AI272:AI272))) | IF(OR(F272="",AK272=""),"",IF(COUNT(AI272:AJ272)=0,"",AK272-LOOKUP(2,1/(AI272:AJ272<>""),AI272:AJ272))) | IF(OR(F272="",AL272=""),"",IF(COUNT(AI272:AK272)=0,"",AL272-LOOKUP(2,1/(AI272:AK272<>""),AI272:AK272))) | IF(OR(F272="",AM272=""),"",IF(COUNT(AI272:AL272)=0,"",AM272-LOOKUP(2,1/(AI272:AL272<>""),AI272:AL272))) | IF(OR(F272="",AN272=""),"",IF(COUNT(AI272:AM272)=0,"",AN272-LOOKUP(2,1/(AI272:AM272<>""),AI272:AM272))) | IF(OR(F272="",AO272=""),"",IF(COUNT(AI272:AN272)=0,"",AO272-LOOKUP(2,1/(AI272:AN272<>""),AI272:AN272))) | IF(OR(F272="",AP272=""),"",IF(COUNT(AI272:AO272)=0,"",AP272-LOOKUP(2,1/(AI272:AO272<>""),AI272:AO272))) | IF(OR(F272="",AQ272=""),"",IF(COUNT(AI272:AP272)=0,"",AQ272-LOOKUP(2,1/(AI272:AP272<>""),AI272:AP272))) | IF(OR(F272="",AR272=""),"",IF(COUNT(AI272:AQ272)=0,"",AR272-LOOKUP(2,1/(AI272:AQ272<>""),AI272:AQ272))) | IF(OR(F272="",AS272=""),"",IF(COUNT(AI272:AR272)=0,"",AS272-LOOKUP(2,1/(AI272:AR272<>""),AI272:AR272))) | IF(OR(F272="",AT272=""),"",IF(COUNT(AI272:AS272)=0,"",AT272-LOOKUP(2,1/(AI272:AS272<>""),AI272:AS272))) | IF(OR(F272="",AU272=""),"",IF(COUNT(AI272:AT272)=0,"",AU272-LOOKUP(2,1/(AI272:AT272<>""),AI272:AT272))) | IF(OR(F272="",AV272=""),"",IF(COUNT(AI272:AU272)=0,"",AV272-LOOKUP(2,1/(AI272:AU272<>""),AI272:AU272))) | IF(J272="","All_Provinces",IFERROR(VLOOKUP(J272,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K272="","All_Districts",IFERROR(VLOOKUP(K272,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F273="","",ROW()-3) | [18 empty] | IF(AQ273="","",AQ273) |  |  |  | IF(W273<>"",W273,IF(OR(T273="",V273=""),"",EDATE(T273,V273))) |  |  |  |  | IF(F273="","",IF(COUNT(AI273:AV273)=0,IF(AA273="","Not started",AA273),SUBSTITUTE(LOOKUP(2,1/(AI273:AV273<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F273="",COUNT(AI273:AV273)=0),"",TODAY()-LOOKUP(2,1/(AI273:AV273<>""),AI273:AV273)) | IF(OR(F273="",COUNT(AI273:AV273)<2),"",LOOKUP(2,1/(AI273:AV273<>""),AI273:AV273)-MIN(AI273:AV273)) | IF(OR(AD273="",AC273="Not started",AC273=""),"",IFERROR(AD273-IF(VLOOKUP(AC273,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC273,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F273="","",IF(OR(AA273="Cancelled",AC273="Cancelled"),"Cancelled",IF(OR(AC273="Completed / Handover",Y273<>"",Z273>=100),"Completed — on track",IF(O273="Not awarded",IF(U273="",IF(X273="","No planned date",IF(TODAY()>X273,"Behind — past planned date",IF(X273-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U273,"Behind — award date passed",IF(U273-TODAY()<=30,"At risk — close to off track","On track"))),IF(X273="","No planned date",IF(AND(TODAY()>X273,OR(Z273="",Z273<100)),"Behind — past end date",IF(AND(T273<>"",X273<>"",Z273<>"",(Z273<100),((TODAY()-T273)/MAX(X273-T273,1)*100)-Z273>15),"Behind — progress lag",IF(AND(X273-TODAY()<=30,X273-TODAY()>=0,OR(Z273="",Z273<90)),"At risk — close to off track","On track")))))))) | IF(OR(F273="",AC273="Completed / Handover",AC273="Cancelled"),"",IF(O273="Not awarded",IF(U273<>"",U273-TODAY(),IF(X273="","",X273-TODAY())),IF(X273="","",X273-TODAY()))) | [14 empty] | IF(OR(F273="",AJ273=""),"",IF(COUNT(AI273:AI273)=0,"",AJ273-LOOKUP(2,1/(AI273:AI273<>""),AI273:AI273))) | IF(OR(F273="",AK273=""),"",IF(COUNT(AI273:AJ273)=0,"",AK273-LOOKUP(2,1/(AI273:AJ273<>""),AI273:AJ273))) | IF(OR(F273="",AL273=""),"",IF(COUNT(AI273:AK273)=0,"",AL273-LOOKUP(2,1/(AI273:AK273<>""),AI273:AK273))) | IF(OR(F273="",AM273=""),"",IF(COUNT(AI273:AL273)=0,"",AM273-LOOKUP(2,1/(AI273:AL273<>""),AI273:AL273))) | IF(OR(F273="",AN273=""),"",IF(COUNT(AI273:AM273)=0,"",AN273-LOOKUP(2,1/(AI273:AM273<>""),AI273:AM273))) | IF(OR(F273="",AO273=""),"",IF(COUNT(AI273:AN273)=0,"",AO273-LOOKUP(2,1/(AI273:AN273<>""),AI273:AN273))) | IF(OR(F273="",AP273=""),"",IF(COUNT(AI273:AO273)=0,"",AP273-LOOKUP(2,1/(AI273:AO273<>""),AI273:AO273))) | IF(OR(F273="",AQ273=""),"",IF(COUNT(AI273:AP273)=0,"",AQ273-LOOKUP(2,1/(AI273:AP273<>""),AI273:AP273))) | IF(OR(F273="",AR273=""),"",IF(COUNT(AI273:AQ273)=0,"",AR273-LOOKUP(2,1/(AI273:AQ273<>""),AI273:AQ273))) | IF(OR(F273="",AS273=""),"",IF(COUNT(AI273:AR273)=0,"",AS273-LOOKUP(2,1/(AI273:AR273<>""),AI273:AR273))) | IF(OR(F273="",AT273=""),"",IF(COUNT(AI273:AS273)=0,"",AT273-LOOKUP(2,1/(AI273:AS273<>""),AI273:AS273))) | IF(OR(F273="",AU273=""),"",IF(COUNT(AI273:AT273)=0,"",AU273-LOOKUP(2,1/(AI273:AT273<>""),AI273:AT273))) | IF(OR(F273="",AV273=""),"",IF(COUNT(AI273:AU273)=0,"",AV273-LOOKUP(2,1/(AI273:AU273<>""),AI273:AU273))) | IF(J273="","All_Provinces",IFERROR(VLOOKUP(J273,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K273="","All_Districts",IFERROR(VLOOKUP(K273,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F274="","",ROW()-3) | [18 empty] | IF(AQ274="","",AQ274) |  |  |  | IF(W274<>"",W274,IF(OR(T274="",V274=""),"",EDATE(T274,V274))) |  |  |  |  | IF(F274="","",IF(COUNT(AI274:AV274)=0,IF(AA274="","Not started",AA274),SUBSTITUTE(LOOKUP(2,1/(AI274:AV274<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F274="",COUNT(AI274:AV274)=0),"",TODAY()-LOOKUP(2,1/(AI274:AV274<>""),AI274:AV274)) | IF(OR(F274="",COUNT(AI274:AV274)<2),"",LOOKUP(2,1/(AI274:AV274<>""),AI274:AV274)-MIN(AI274:AV274)) | IF(OR(AD274="",AC274="Not started",AC274=""),"",IFERROR(AD274-IF(VLOOKUP(AC274,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC274,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F274="","",IF(OR(AA274="Cancelled",AC274="Cancelled"),"Cancelled",IF(OR(AC274="Completed / Handover",Y274<>"",Z274>=100),"Completed — on track",IF(O274="Not awarded",IF(U274="",IF(X274="","No planned date",IF(TODAY()>X274,"Behind — past planned date",IF(X274-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U274,"Behind — award date passed",IF(U274-TODAY()<=30,"At risk — close to off track","On track"))),IF(X274="","No planned date",IF(AND(TODAY()>X274,OR(Z274="",Z274<100)),"Behind — past end date",IF(AND(T274<>"",X274<>"",Z274<>"",(Z274<100),((TODAY()-T274)/MAX(X274-T274,1)*100)-Z274>15),"Behind — progress lag",IF(AND(X274-TODAY()<=30,X274-TODAY()>=0,OR(Z274="",Z274<90)),"At risk — close to off track","On track")))))))) | IF(OR(F274="",AC274="Completed / Handover",AC274="Cancelled"),"",IF(O274="Not awarded",IF(U274<>"",U274-TODAY(),IF(X274="","",X274-TODAY())),IF(X274="","",X274-TODAY()))) | [14 empty] | IF(OR(F274="",AJ274=""),"",IF(COUNT(AI274:AI274)=0,"",AJ274-LOOKUP(2,1/(AI274:AI274<>""),AI274:AI274))) | IF(OR(F274="",AK274=""),"",IF(COUNT(AI274:AJ274)=0,"",AK274-LOOKUP(2,1/(AI274:AJ274<>""),AI274:AJ274))) | IF(OR(F274="",AL274=""),"",IF(COUNT(AI274:AK274)=0,"",AL274-LOOKUP(2,1/(AI274:AK274<>""),AI274:AK274))) | IF(OR(F274="",AM274=""),"",IF(COUNT(AI274:AL274)=0,"",AM274-LOOKUP(2,1/(AI274:AL274<>""),AI274:AL274))) | IF(OR(F274="",AN274=""),"",IF(COUNT(AI274:AM274)=0,"",AN274-LOOKUP(2,1/(AI274:AM274<>""),AI274:AM274))) | IF(OR(F274="",AO274=""),"",IF(COUNT(AI274:AN274)=0,"",AO274-LOOKUP(2,1/(AI274:AN274<>""),AI274:AN274))) | IF(OR(F274="",AP274=""),"",IF(COUNT(AI274:AO274)=0,"",AP274-LOOKUP(2,1/(AI274:AO274<>""),AI274:AO274))) | IF(OR(F274="",AQ274=""),"",IF(COUNT(AI274:AP274)=0,"",AQ274-LOOKUP(2,1/(AI274:AP274<>""),AI274:AP274))) | IF(OR(F274="",AR274=""),"",IF(COUNT(AI274:AQ274)=0,"",AR274-LOOKUP(2,1/(AI274:AQ274<>""),AI274:AQ274))) | IF(OR(F274="",AS274=""),"",IF(COUNT(AI274:AR274)=0,"",AS274-LOOKUP(2,1/(AI274:AR274<>""),AI274:AR274))) | IF(OR(F274="",AT274=""),"",IF(COUNT(AI274:AS274)=0,"",AT274-LOOKUP(2,1/(AI274:AS274<>""),AI274:AS274))) | IF(OR(F274="",AU274=""),"",IF(COUNT(AI274:AT274)=0,"",AU274-LOOKUP(2,1/(AI274:AT274<>""),AI274:AT274))) | IF(OR(F274="",AV274=""),"",IF(COUNT(AI274:AU274)=0,"",AV274-LOOKUP(2,1/(AI274:AU274<>""),AI274:AU274))) | IF(J274="","All_Provinces",IFERROR(VLOOKUP(J274,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K274="","All_Districts",IFERROR(VLOOKUP(K274,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F275="","",ROW()-3) | [18 empty] | IF(AQ275="","",AQ275) |  |  |  | IF(W275<>"",W275,IF(OR(T275="",V275=""),"",EDATE(T275,V275))) |  |  |  |  | IF(F275="","",IF(COUNT(AI275:AV275)=0,IF(AA275="","Not started",AA275),SUBSTITUTE(LOOKUP(2,1/(AI275:AV275<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F275="",COUNT(AI275:AV275)=0),"",TODAY()-LOOKUP(2,1/(AI275:AV275<>""),AI275:AV275)) | IF(OR(F275="",COUNT(AI275:AV275)<2),"",LOOKUP(2,1/(AI275:AV275<>""),AI275:AV275)-MIN(AI275:AV275)) | IF(OR(AD275="",AC275="Not started",AC275=""),"",IFERROR(AD275-IF(VLOOKUP(AC275,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC275,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F275="","",IF(OR(AA275="Cancelled",AC275="Cancelled"),"Cancelled",IF(OR(AC275="Completed / Handover",Y275<>"",Z275>=100),"Completed — on track",IF(O275="Not awarded",IF(U275="",IF(X275="","No planned date",IF(TODAY()>X275,"Behind — past planned date",IF(X275-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U275,"Behind — award date passed",IF(U275-TODAY()<=30,"At risk — close to off track","On track"))),IF(X275="","No planned date",IF(AND(TODAY()>X275,OR(Z275="",Z275<100)),"Behind — past end date",IF(AND(T275<>"",X275<>"",Z275<>"",(Z275<100),((TODAY()-T275)/MAX(X275-T275,1)*100)-Z275>15),"Behind — progress lag",IF(AND(X275-TODAY()<=30,X275-TODAY()>=0,OR(Z275="",Z275<90)),"At risk — close to off track","On track")))))))) | IF(OR(F275="",AC275="Completed / Handover",AC275="Cancelled"),"",IF(O275="Not awarded",IF(U275<>"",U275-TODAY(),IF(X275="","",X275-TODAY())),IF(X275="","",X275-TODAY()))) | [14 empty] | IF(OR(F275="",AJ275=""),"",IF(COUNT(AI275:AI275)=0,"",AJ275-LOOKUP(2,1/(AI275:AI275<>""),AI275:AI275))) | IF(OR(F275="",AK275=""),"",IF(COUNT(AI275:AJ275)=0,"",AK275-LOOKUP(2,1/(AI275:AJ275<>""),AI275:AJ275))) | IF(OR(F275="",AL275=""),"",IF(COUNT(AI275:AK275)=0,"",AL275-LOOKUP(2,1/(AI275:AK275<>""),AI275:AK275))) | IF(OR(F275="",AM275=""),"",IF(COUNT(AI275:AL275)=0,"",AM275-LOOKUP(2,1/(AI275:AL275<>""),AI275:AL275))) | IF(OR(F275="",AN275=""),"",IF(COUNT(AI275:AM275)=0,"",AN275-LOOKUP(2,1/(AI275:AM275<>""),AI275:AM275))) | IF(OR(F275="",AO275=""),"",IF(COUNT(AI275:AN275)=0,"",AO275-LOOKUP(2,1/(AI275:AN275<>""),AI275:AN275))) | IF(OR(F275="",AP275=""),"",IF(COUNT(AI275:AO275)=0,"",AP275-LOOKUP(2,1/(AI275:AO275<>""),AI275:AO275))) | IF(OR(F275="",AQ275=""),"",IF(COUNT(AI275:AP275)=0,"",AQ275-LOOKUP(2,1/(AI275:AP275<>""),AI275:AP275))) | IF(OR(F275="",AR275=""),"",IF(COUNT(AI275:AQ275)=0,"",AR275-LOOKUP(2,1/(AI275:AQ275<>""),AI275:AQ275))) | IF(OR(F275="",AS275=""),"",IF(COUNT(AI275:AR275)=0,"",AS275-LOOKUP(2,1/(AI275:AR275<>""),AI275:AR275))) | IF(OR(F275="",AT275=""),"",IF(COUNT(AI275:AS275)=0,"",AT275-LOOKUP(2,1/(AI275:AS275<>""),AI275:AS275))) | IF(OR(F275="",AU275=""),"",IF(COUNT(AI275:AT275)=0,"",AU275-LOOKUP(2,1/(AI275:AT275<>""),AI275:AT275))) | IF(OR(F275="",AV275=""),"",IF(COUNT(AI275:AU275)=0,"",AV275-LOOKUP(2,1/(AI275:AU275<>""),AI275:AU275))) | IF(J275="","All_Provinces",IFERROR(VLOOKUP(J275,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K275="","All_Districts",IFERROR(VLOOKUP(K275,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F276="","",ROW()-3) | [18 empty] | IF(AQ276="","",AQ276) |  |  |  | IF(W276<>"",W276,IF(OR(T276="",V276=""),"",EDATE(T276,V276))) |  |  |  |  | IF(F276="","",IF(COUNT(AI276:AV276)=0,IF(AA276="","Not started",AA276),SUBSTITUTE(LOOKUP(2,1/(AI276:AV276<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F276="",COUNT(AI276:AV276)=0),"",TODAY()-LOOKUP(2,1/(AI276:AV276<>""),AI276:AV276)) | IF(OR(F276="",COUNT(AI276:AV276)<2),"",LOOKUP(2,1/(AI276:AV276<>""),AI276:AV276)-MIN(AI276:AV276)) | IF(OR(AD276="",AC276="Not started",AC276=""),"",IFERROR(AD276-IF(VLOOKUP(AC276,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC276,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F276="","",IF(OR(AA276="Cancelled",AC276="Cancelled"),"Cancelled",IF(OR(AC276="Completed / Handover",Y276<>"",Z276>=100),"Completed — on track",IF(O276="Not awarded",IF(U276="",IF(X276="","No planned date",IF(TODAY()>X276,"Behind — past planned date",IF(X276-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U276,"Behind — award date passed",IF(U276-TODAY()<=30,"At risk — close to off track","On track"))),IF(X276="","No planned date",IF(AND(TODAY()>X276,OR(Z276="",Z276<100)),"Behind — past end date",IF(AND(T276<>"",X276<>"",Z276<>"",(Z276<100),((TODAY()-T276)/MAX(X276-T276,1)*100)-Z276>15),"Behind — progress lag",IF(AND(X276-TODAY()<=30,X276-TODAY()>=0,OR(Z276="",Z276<90)),"At risk — close to off track","On track")))))))) | IF(OR(F276="",AC276="Completed / Handover",AC276="Cancelled"),"",IF(O276="Not awarded",IF(U276<>"",U276-TODAY(),IF(X276="","",X276-TODAY())),IF(X276="","",X276-TODAY()))) | [14 empty] | IF(OR(F276="",AJ276=""),"",IF(COUNT(AI276:AI276)=0,"",AJ276-LOOKUP(2,1/(AI276:AI276<>""),AI276:AI276))) | IF(OR(F276="",AK276=""),"",IF(COUNT(AI276:AJ276)=0,"",AK276-LOOKUP(2,1/(AI276:AJ276<>""),AI276:AJ276))) | IF(OR(F276="",AL276=""),"",IF(COUNT(AI276:AK276)=0,"",AL276-LOOKUP(2,1/(AI276:AK276<>""),AI276:AK276))) | IF(OR(F276="",AM276=""),"",IF(COUNT(AI276:AL276)=0,"",AM276-LOOKUP(2,1/(AI276:AL276<>""),AI276:AL276))) | IF(OR(F276="",AN276=""),"",IF(COUNT(AI276:AM276)=0,"",AN276-LOOKUP(2,1/(AI276:AM276<>""),AI276:AM276))) | IF(OR(F276="",AO276=""),"",IF(COUNT(AI276:AN276)=0,"",AO276-LOOKUP(2,1/(AI276:AN276<>""),AI276:AN276))) | IF(OR(F276="",AP276=""),"",IF(COUNT(AI276:AO276)=0,"",AP276-LOOKUP(2,1/(AI276:AO276<>""),AI276:AO276))) | IF(OR(F276="",AQ276=""),"",IF(COUNT(AI276:AP276)=0,"",AQ276-LOOKUP(2,1/(AI276:AP276<>""),AI276:AP276))) | IF(OR(F276="",AR276=""),"",IF(COUNT(AI276:AQ276)=0,"",AR276-LOOKUP(2,1/(AI276:AQ276<>""),AI276:AQ276))) | IF(OR(F276="",AS276=""),"",IF(COUNT(AI276:AR276)=0,"",AS276-LOOKUP(2,1/(AI276:AR276<>""),AI276:AR276))) | IF(OR(F276="",AT276=""),"",IF(COUNT(AI276:AS276)=0,"",AT276-LOOKUP(2,1/(AI276:AS276<>""),AI276:AS276))) | IF(OR(F276="",AU276=""),"",IF(COUNT(AI276:AT276)=0,"",AU276-LOOKUP(2,1/(AI276:AT276<>""),AI276:AT276))) | IF(OR(F276="",AV276=""),"",IF(COUNT(AI276:AU276)=0,"",AV276-LOOKUP(2,1/(AI276:AU276<>""),AI276:AU276))) | IF(J276="","All_Provinces",IFERROR(VLOOKUP(J276,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K276="","All_Districts",IFERROR(VLOOKUP(K276,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F277="","",ROW()-3) | [18 empty] | IF(AQ277="","",AQ277) |  |  |  | IF(W277<>"",W277,IF(OR(T277="",V277=""),"",EDATE(T277,V277))) |  |  |  |  | IF(F277="","",IF(COUNT(AI277:AV277)=0,IF(AA277="","Not started",AA277),SUBSTITUTE(LOOKUP(2,1/(AI277:AV277<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F277="",COUNT(AI277:AV277)=0),"",TODAY()-LOOKUP(2,1/(AI277:AV277<>""),AI277:AV277)) | IF(OR(F277="",COUNT(AI277:AV277)<2),"",LOOKUP(2,1/(AI277:AV277<>""),AI277:AV277)-MIN(AI277:AV277)) | IF(OR(AD277="",AC277="Not started",AC277=""),"",IFERROR(AD277-IF(VLOOKUP(AC277,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC277,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F277="","",IF(OR(AA277="Cancelled",AC277="Cancelled"),"Cancelled",IF(OR(AC277="Completed / Handover",Y277<>"",Z277>=100),"Completed — on track",IF(O277="Not awarded",IF(U277="",IF(X277="","No planned date",IF(TODAY()>X277,"Behind — past planned date",IF(X277-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U277,"Behind — award date passed",IF(U277-TODAY()<=30,"At risk — close to off track","On track"))),IF(X277="","No planned date",IF(AND(TODAY()>X277,OR(Z277="",Z277<100)),"Behind — past end date",IF(AND(T277<>"",X277<>"",Z277<>"",(Z277<100),((TODAY()-T277)/MAX(X277-T277,1)*100)-Z277>15),"Behind — progress lag",IF(AND(X277-TODAY()<=30,X277-TODAY()>=0,OR(Z277="",Z277<90)),"At risk — close to off track","On track")))))))) | IF(OR(F277="",AC277="Completed / Handover",AC277="Cancelled"),"",IF(O277="Not awarded",IF(U277<>"",U277-TODAY(),IF(X277="","",X277-TODAY())),IF(X277="","",X277-TODAY()))) | [14 empty] | IF(OR(F277="",AJ277=""),"",IF(COUNT(AI277:AI277)=0,"",AJ277-LOOKUP(2,1/(AI277:AI277<>""),AI277:AI277))) | IF(OR(F277="",AK277=""),"",IF(COUNT(AI277:AJ277)=0,"",AK277-LOOKUP(2,1/(AI277:AJ277<>""),AI277:AJ277))) | IF(OR(F277="",AL277=""),"",IF(COUNT(AI277:AK277)=0,"",AL277-LOOKUP(2,1/(AI277:AK277<>""),AI277:AK277))) | IF(OR(F277="",AM277=""),"",IF(COUNT(AI277:AL277)=0,"",AM277-LOOKUP(2,1/(AI277:AL277<>""),AI277:AL277))) | IF(OR(F277="",AN277=""),"",IF(COUNT(AI277:AM277)=0,"",AN277-LOOKUP(2,1/(AI277:AM277<>""),AI277:AM277))) | IF(OR(F277="",AO277=""),"",IF(COUNT(AI277:AN277)=0,"",AO277-LOOKUP(2,1/(AI277:AN277<>""),AI277:AN277))) | IF(OR(F277="",AP277=""),"",IF(COUNT(AI277:AO277)=0,"",AP277-LOOKUP(2,1/(AI277:AO277<>""),AI277:AO277))) | IF(OR(F277="",AQ277=""),"",IF(COUNT(AI277:AP277)=0,"",AQ277-LOOKUP(2,1/(AI277:AP277<>""),AI277:AP277))) | IF(OR(F277="",AR277=""),"",IF(COUNT(AI277:AQ277)=0,"",AR277-LOOKUP(2,1/(AI277:AQ277<>""),AI277:AQ277))) | IF(OR(F277="",AS277=""),"",IF(COUNT(AI277:AR277)=0,"",AS277-LOOKUP(2,1/(AI277:AR277<>""),AI277:AR277))) | IF(OR(F277="",AT277=""),"",IF(COUNT(AI277:AS277)=0,"",AT277-LOOKUP(2,1/(AI277:AS277<>""),AI277:AS277))) | IF(OR(F277="",AU277=""),"",IF(COUNT(AI277:AT277)=0,"",AU277-LOOKUP(2,1/(AI277:AT277<>""),AI277:AT277))) | IF(OR(F277="",AV277=""),"",IF(COUNT(AI277:AU277)=0,"",AV277-LOOKUP(2,1/(AI277:AU277<>""),AI277:AU277))) | IF(J277="","All_Provinces",IFERROR(VLOOKUP(J277,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K277="","All_Districts",IFERROR(VLOOKUP(K277,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F278="","",ROW()-3) | [18 empty] | IF(AQ278="","",AQ278) |  |  |  | IF(W278<>"",W278,IF(OR(T278="",V278=""),"",EDATE(T278,V278))) |  |  |  |  | IF(F278="","",IF(COUNT(AI278:AV278)=0,IF(AA278="","Not started",AA278),SUBSTITUTE(LOOKUP(2,1/(AI278:AV278<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F278="",COUNT(AI278:AV278)=0),"",TODAY()-LOOKUP(2,1/(AI278:AV278<>""),AI278:AV278)) | IF(OR(F278="",COUNT(AI278:AV278)<2),"",LOOKUP(2,1/(AI278:AV278<>""),AI278:AV278)-MIN(AI278:AV278)) | IF(OR(AD278="",AC278="Not started",AC278=""),"",IFERROR(AD278-IF(VLOOKUP(AC278,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC278,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F278="","",IF(OR(AA278="Cancelled",AC278="Cancelled"),"Cancelled",IF(OR(AC278="Completed / Handover",Y278<>"",Z278>=100),"Completed — on track",IF(O278="Not awarded",IF(U278="",IF(X278="","No planned date",IF(TODAY()>X278,"Behind — past planned date",IF(X278-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U278,"Behind — award date passed",IF(U278-TODAY()<=30,"At risk — close to off track","On track"))),IF(X278="","No planned date",IF(AND(TODAY()>X278,OR(Z278="",Z278<100)),"Behind — past end date",IF(AND(T278<>"",X278<>"",Z278<>"",(Z278<100),((TODAY()-T278)/MAX(X278-T278,1)*100)-Z278>15),"Behind — progress lag",IF(AND(X278-TODAY()<=30,X278-TODAY()>=0,OR(Z278="",Z278<90)),"At risk — close to off track","On track")))))))) | IF(OR(F278="",AC278="Completed / Handover",AC278="Cancelled"),"",IF(O278="Not awarded",IF(U278<>"",U278-TODAY(),IF(X278="","",X278-TODAY())),IF(X278="","",X278-TODAY()))) | [14 empty] | IF(OR(F278="",AJ278=""),"",IF(COUNT(AI278:AI278)=0,"",AJ278-LOOKUP(2,1/(AI278:AI278<>""),AI278:AI278))) | IF(OR(F278="",AK278=""),"",IF(COUNT(AI278:AJ278)=0,"",AK278-LOOKUP(2,1/(AI278:AJ278<>""),AI278:AJ278))) | IF(OR(F278="",AL278=""),"",IF(COUNT(AI278:AK278)=0,"",AL278-LOOKUP(2,1/(AI278:AK278<>""),AI278:AK278))) | IF(OR(F278="",AM278=""),"",IF(COUNT(AI278:AL278)=0,"",AM278-LOOKUP(2,1/(AI278:AL278<>""),AI278:AL278))) | IF(OR(F278="",AN278=""),"",IF(COUNT(AI278:AM278)=0,"",AN278-LOOKUP(2,1/(AI278:AM278<>""),AI278:AM278))) | IF(OR(F278="",AO278=""),"",IF(COUNT(AI278:AN278)=0,"",AO278-LOOKUP(2,1/(AI278:AN278<>""),AI278:AN278))) | IF(OR(F278="",AP278=""),"",IF(COUNT(AI278:AO278)=0,"",AP278-LOOKUP(2,1/(AI278:AO278<>""),AI278:AO278))) | IF(OR(F278="",AQ278=""),"",IF(COUNT(AI278:AP278)=0,"",AQ278-LOOKUP(2,1/(AI278:AP278<>""),AI278:AP278))) | IF(OR(F278="",AR278=""),"",IF(COUNT(AI278:AQ278)=0,"",AR278-LOOKUP(2,1/(AI278:AQ278<>""),AI278:AQ278))) | IF(OR(F278="",AS278=""),"",IF(COUNT(AI278:AR278)=0,"",AS278-LOOKUP(2,1/(AI278:AR278<>""),AI278:AR278))) | IF(OR(F278="",AT278=""),"",IF(COUNT(AI278:AS278)=0,"",AT278-LOOKUP(2,1/(AI278:AS278<>""),AI278:AS278))) | IF(OR(F278="",AU278=""),"",IF(COUNT(AI278:AT278)=0,"",AU278-LOOKUP(2,1/(AI278:AT278<>""),AI278:AT278))) | IF(OR(F278="",AV278=""),"",IF(COUNT(AI278:AU278)=0,"",AV278-LOOKUP(2,1/(AI278:AU278<>""),AI278:AU278))) | IF(J278="","All_Provinces",IFERROR(VLOOKUP(J278,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K278="","All_Districts",IFERROR(VLOOKUP(K278,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F279="","",ROW()-3) | [18 empty] | IF(AQ279="","",AQ279) |  |  |  | IF(W279<>"",W279,IF(OR(T279="",V279=""),"",EDATE(T279,V279))) |  |  |  |  | IF(F279="","",IF(COUNT(AI279:AV279)=0,IF(AA279="","Not started",AA279),SUBSTITUTE(LOOKUP(2,1/(AI279:AV279<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F279="",COUNT(AI279:AV279)=0),"",TODAY()-LOOKUP(2,1/(AI279:AV279<>""),AI279:AV279)) | IF(OR(F279="",COUNT(AI279:AV279)<2),"",LOOKUP(2,1/(AI279:AV279<>""),AI279:AV279)-MIN(AI279:AV279)) | IF(OR(AD279="",AC279="Not started",AC279=""),"",IFERROR(AD279-IF(VLOOKUP(AC279,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC279,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F279="","",IF(OR(AA279="Cancelled",AC279="Cancelled"),"Cancelled",IF(OR(AC279="Completed / Handover",Y279<>"",Z279>=100),"Completed — on track",IF(O279="Not awarded",IF(U279="",IF(X279="","No planned date",IF(TODAY()>X279,"Behind — past planned date",IF(X279-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U279,"Behind — award date passed",IF(U279-TODAY()<=30,"At risk — close to off track","On track"))),IF(X279="","No planned date",IF(AND(TODAY()>X279,OR(Z279="",Z279<100)),"Behind — past end date",IF(AND(T279<>"",X279<>"",Z279<>"",(Z279<100),((TODAY()-T279)/MAX(X279-T279,1)*100)-Z279>15),"Behind — progress lag",IF(AND(X279-TODAY()<=30,X279-TODAY()>=0,OR(Z279="",Z279<90)),"At risk — close to off track","On track")))))))) | IF(OR(F279="",AC279="Completed / Handover",AC279="Cancelled"),"",IF(O279="Not awarded",IF(U279<>"",U279-TODAY(),IF(X279="","",X279-TODAY())),IF(X279="","",X279-TODAY()))) | [14 empty] | IF(OR(F279="",AJ279=""),"",IF(COUNT(AI279:AI279)=0,"",AJ279-LOOKUP(2,1/(AI279:AI279<>""),AI279:AI279))) | IF(OR(F279="",AK279=""),"",IF(COUNT(AI279:AJ279)=0,"",AK279-LOOKUP(2,1/(AI279:AJ279<>""),AI279:AJ279))) | IF(OR(F279="",AL279=""),"",IF(COUNT(AI279:AK279)=0,"",AL279-LOOKUP(2,1/(AI279:AK279<>""),AI279:AK279))) | IF(OR(F279="",AM279=""),"",IF(COUNT(AI279:AL279)=0,"",AM279-LOOKUP(2,1/(AI279:AL279<>""),AI279:AL279))) | IF(OR(F279="",AN279=""),"",IF(COUNT(AI279:AM279)=0,"",AN279-LOOKUP(2,1/(AI279:AM279<>""),AI279:AM279))) | IF(OR(F279="",AO279=""),"",IF(COUNT(AI279:AN279)=0,"",AO279-LOOKUP(2,1/(AI279:AN279<>""),AI279:AN279))) | IF(OR(F279="",AP279=""),"",IF(COUNT(AI279:AO279)=0,"",AP279-LOOKUP(2,1/(AI279:AO279<>""),AI279:AO279))) | IF(OR(F279="",AQ279=""),"",IF(COUNT(AI279:AP279)=0,"",AQ279-LOOKUP(2,1/(AI279:AP279<>""),AI279:AP279))) | IF(OR(F279="",AR279=""),"",IF(COUNT(AI279:AQ279)=0,"",AR279-LOOKUP(2,1/(AI279:AQ279<>""),AI279:AQ279))) | IF(OR(F279="",AS279=""),"",IF(COUNT(AI279:AR279)=0,"",AS279-LOOKUP(2,1/(AI279:AR279<>""),AI279:AR279))) | IF(OR(F279="",AT279=""),"",IF(COUNT(AI279:AS279)=0,"",AT279-LOOKUP(2,1/(AI279:AS279<>""),AI279:AS279))) | IF(OR(F279="",AU279=""),"",IF(COUNT(AI279:AT279)=0,"",AU279-LOOKUP(2,1/(AI279:AT279<>""),AI279:AT279))) | IF(OR(F279="",AV279=""),"",IF(COUNT(AI279:AU279)=0,"",AV279-LOOKUP(2,1/(AI279:AU279<>""),AI279:AU279))) | IF(J279="","All_Provinces",IFERROR(VLOOKUP(J279,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K279="","All_Districts",IFERROR(VLOOKUP(K279,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F280="","",ROW()-3) | [18 empty] | IF(AQ280="","",AQ280) |  |  |  | IF(W280<>"",W280,IF(OR(T280="",V280=""),"",EDATE(T280,V280))) |  |  |  |  | IF(F280="","",IF(COUNT(AI280:AV280)=0,IF(AA280="","Not started",AA280),SUBSTITUTE(LOOKUP(2,1/(AI280:AV280<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F280="",COUNT(AI280:AV280)=0),"",TODAY()-LOOKUP(2,1/(AI280:AV280<>""),AI280:AV280)) | IF(OR(F280="",COUNT(AI280:AV280)<2),"",LOOKUP(2,1/(AI280:AV280<>""),AI280:AV280)-MIN(AI280:AV280)) | IF(OR(AD280="",AC280="Not started",AC280=""),"",IFERROR(AD280-IF(VLOOKUP(AC280,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC280,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F280="","",IF(OR(AA280="Cancelled",AC280="Cancelled"),"Cancelled",IF(OR(AC280="Completed / Handover",Y280<>"",Z280>=100),"Completed — on track",IF(O280="Not awarded",IF(U280="",IF(X280="","No planned date",IF(TODAY()>X280,"Behind — past planned date",IF(X280-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U280,"Behind — award date passed",IF(U280-TODAY()<=30,"At risk — close to off track","On track"))),IF(X280="","No planned date",IF(AND(TODAY()>X280,OR(Z280="",Z280<100)),"Behind — past end date",IF(AND(T280<>"",X280<>"",Z280<>"",(Z280<100),((TODAY()-T280)/MAX(X280-T280,1)*100)-Z280>15),"Behind — progress lag",IF(AND(X280-TODAY()<=30,X280-TODAY()>=0,OR(Z280="",Z280<90)),"At risk — close to off track","On track")))))))) | IF(OR(F280="",AC280="Completed / Handover",AC280="Cancelled"),"",IF(O280="Not awarded",IF(U280<>"",U280-TODAY(),IF(X280="","",X280-TODAY())),IF(X280="","",X280-TODAY()))) | [14 empty] | IF(OR(F280="",AJ280=""),"",IF(COUNT(AI280:AI280)=0,"",AJ280-LOOKUP(2,1/(AI280:AI280<>""),AI280:AI280))) | IF(OR(F280="",AK280=""),"",IF(COUNT(AI280:AJ280)=0,"",AK280-LOOKUP(2,1/(AI280:AJ280<>""),AI280:AJ280))) | IF(OR(F280="",AL280=""),"",IF(COUNT(AI280:AK280)=0,"",AL280-LOOKUP(2,1/(AI280:AK280<>""),AI280:AK280))) | IF(OR(F280="",AM280=""),"",IF(COUNT(AI280:AL280)=0,"",AM280-LOOKUP(2,1/(AI280:AL280<>""),AI280:AL280))) | IF(OR(F280="",AN280=""),"",IF(COUNT(AI280:AM280)=0,"",AN280-LOOKUP(2,1/(AI280:AM280<>""),AI280:AM280))) | IF(OR(F280="",AO280=""),"",IF(COUNT(AI280:AN280)=0,"",AO280-LOOKUP(2,1/(AI280:AN280<>""),AI280:AN280))) | IF(OR(F280="",AP280=""),"",IF(COUNT(AI280:AO280)=0,"",AP280-LOOKUP(2,1/(AI280:AO280<>""),AI280:AO280))) | IF(OR(F280="",AQ280=""),"",IF(COUNT(AI280:AP280)=0,"",AQ280-LOOKUP(2,1/(AI280:AP280<>""),AI280:AP280))) | IF(OR(F280="",AR280=""),"",IF(COUNT(AI280:AQ280)=0,"",AR280-LOOKUP(2,1/(AI280:AQ280<>""),AI280:AQ280))) | IF(OR(F280="",AS280=""),"",IF(COUNT(AI280:AR280)=0,"",AS280-LOOKUP(2,1/(AI280:AR280<>""),AI280:AR280))) | IF(OR(F280="",AT280=""),"",IF(COUNT(AI280:AS280)=0,"",AT280-LOOKUP(2,1/(AI280:AS280<>""),AI280:AS280))) | IF(OR(F280="",AU280=""),"",IF(COUNT(AI280:AT280)=0,"",AU280-LOOKUP(2,1/(AI280:AT280<>""),AI280:AT280))) | IF(OR(F280="",AV280=""),"",IF(COUNT(AI280:AU280)=0,"",AV280-LOOKUP(2,1/(AI280:AU280<>""),AI280:AU280))) | IF(J280="","All_Provinces",IFERROR(VLOOKUP(J280,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K280="","All_Districts",IFERROR(VLOOKUP(K280,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F281="","",ROW()-3) | [18 empty] | IF(AQ281="","",AQ281) |  |  |  | IF(W281<>"",W281,IF(OR(T281="",V281=""),"",EDATE(T281,V281))) |  |  |  |  | IF(F281="","",IF(COUNT(AI281:AV281)=0,IF(AA281="","Not started",AA281),SUBSTITUTE(LOOKUP(2,1/(AI281:AV281<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F281="",COUNT(AI281:AV281)=0),"",TODAY()-LOOKUP(2,1/(AI281:AV281<>""),AI281:AV281)) | IF(OR(F281="",COUNT(AI281:AV281)<2),"",LOOKUP(2,1/(AI281:AV281<>""),AI281:AV281)-MIN(AI281:AV281)) | IF(OR(AD281="",AC281="Not started",AC281=""),"",IFERROR(AD281-IF(VLOOKUP(AC281,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC281,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F281="","",IF(OR(AA281="Cancelled",AC281="Cancelled"),"Cancelled",IF(OR(AC281="Completed / Handover",Y281<>"",Z281>=100),"Completed — on track",IF(O281="Not awarded",IF(U281="",IF(X281="","No planned date",IF(TODAY()>X281,"Behind — past planned date",IF(X281-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U281,"Behind — award date passed",IF(U281-TODAY()<=30,"At risk — close to off track","On track"))),IF(X281="","No planned date",IF(AND(TODAY()>X281,OR(Z281="",Z281<100)),"Behind — past end date",IF(AND(T281<>"",X281<>"",Z281<>"",(Z281<100),((TODAY()-T281)/MAX(X281-T281,1)*100)-Z281>15),"Behind — progress lag",IF(AND(X281-TODAY()<=30,X281-TODAY()>=0,OR(Z281="",Z281<90)),"At risk — close to off track","On track")))))))) | IF(OR(F281="",AC281="Completed / Handover",AC281="Cancelled"),"",IF(O281="Not awarded",IF(U281<>"",U281-TODAY(),IF(X281="","",X281-TODAY())),IF(X281="","",X281-TODAY()))) | [14 empty] | IF(OR(F281="",AJ281=""),"",IF(COUNT(AI281:AI281)=0,"",AJ281-LOOKUP(2,1/(AI281:AI281<>""),AI281:AI281))) | IF(OR(F281="",AK281=""),"",IF(COUNT(AI281:AJ281)=0,"",AK281-LOOKUP(2,1/(AI281:AJ281<>""),AI281:AJ281))) | IF(OR(F281="",AL281=""),"",IF(COUNT(AI281:AK281)=0,"",AL281-LOOKUP(2,1/(AI281:AK281<>""),AI281:AK281))) | IF(OR(F281="",AM281=""),"",IF(COUNT(AI281:AL281)=0,"",AM281-LOOKUP(2,1/(AI281:AL281<>""),AI281:AL281))) | IF(OR(F281="",AN281=""),"",IF(COUNT(AI281:AM281)=0,"",AN281-LOOKUP(2,1/(AI281:AM281<>""),AI281:AM281))) | IF(OR(F281="",AO281=""),"",IF(COUNT(AI281:AN281)=0,"",AO281-LOOKUP(2,1/(AI281:AN281<>""),AI281:AN281))) | IF(OR(F281="",AP281=""),"",IF(COUNT(AI281:AO281)=0,"",AP281-LOOKUP(2,1/(AI281:AO281<>""),AI281:AO281))) | IF(OR(F281="",AQ281=""),"",IF(COUNT(AI281:AP281)=0,"",AQ281-LOOKUP(2,1/(AI281:AP281<>""),AI281:AP281))) | IF(OR(F281="",AR281=""),"",IF(COUNT(AI281:AQ281)=0,"",AR281-LOOKUP(2,1/(AI281:AQ281<>""),AI281:AQ281))) | IF(OR(F281="",AS281=""),"",IF(COUNT(AI281:AR281)=0,"",AS281-LOOKUP(2,1/(AI281:AR281<>""),AI281:AR281))) | IF(OR(F281="",AT281=""),"",IF(COUNT(AI281:AS281)=0,"",AT281-LOOKUP(2,1/(AI281:AS281<>""),AI281:AS281))) | IF(OR(F281="",AU281=""),"",IF(COUNT(AI281:AT281)=0,"",AU281-LOOKUP(2,1/(AI281:AT281<>""),AI281:AT281))) | IF(OR(F281="",AV281=""),"",IF(COUNT(AI281:AU281)=0,"",AV281-LOOKUP(2,1/(AI281:AU281<>""),AI281:AU281))) | IF(J281="","All_Provinces",IFERROR(VLOOKUP(J281,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K281="","All_Districts",IFERROR(VLOOKUP(K281,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F282="","",ROW()-3) | [18 empty] | IF(AQ282="","",AQ282) |  |  |  | IF(W282<>"",W282,IF(OR(T282="",V282=""),"",EDATE(T282,V282))) |  |  |  |  | IF(F282="","",IF(COUNT(AI282:AV282)=0,IF(AA282="","Not started",AA282),SUBSTITUTE(LOOKUP(2,1/(AI282:AV282<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F282="",COUNT(AI282:AV282)=0),"",TODAY()-LOOKUP(2,1/(AI282:AV282<>""),AI282:AV282)) | IF(OR(F282="",COUNT(AI282:AV282)<2),"",LOOKUP(2,1/(AI282:AV282<>""),AI282:AV282)-MIN(AI282:AV282)) | IF(OR(AD282="",AC282="Not started",AC282=""),"",IFERROR(AD282-IF(VLOOKUP(AC282,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC282,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F282="","",IF(OR(AA282="Cancelled",AC282="Cancelled"),"Cancelled",IF(OR(AC282="Completed / Handover",Y282<>"",Z282>=100),"Completed — on track",IF(O282="Not awarded",IF(U282="",IF(X282="","No planned date",IF(TODAY()>X282,"Behind — past planned date",IF(X282-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U282,"Behind — award date passed",IF(U282-TODAY()<=30,"At risk — close to off track","On track"))),IF(X282="","No planned date",IF(AND(TODAY()>X282,OR(Z282="",Z282<100)),"Behind — past end date",IF(AND(T282<>"",X282<>"",Z282<>"",(Z282<100),((TODAY()-T282)/MAX(X282-T282,1)*100)-Z282>15),"Behind — progress lag",IF(AND(X282-TODAY()<=30,X282-TODAY()>=0,OR(Z282="",Z282<90)),"At risk — close to off track","On track")))))))) | IF(OR(F282="",AC282="Completed / Handover",AC282="Cancelled"),"",IF(O282="Not awarded",IF(U282<>"",U282-TODAY(),IF(X282="","",X282-TODAY())),IF(X282="","",X282-TODAY()))) | [14 empty] | IF(OR(F282="",AJ282=""),"",IF(COUNT(AI282:AI282)=0,"",AJ282-LOOKUP(2,1/(AI282:AI282<>""),AI282:AI282))) | IF(OR(F282="",AK282=""),"",IF(COUNT(AI282:AJ282)=0,"",AK282-LOOKUP(2,1/(AI282:AJ282<>""),AI282:AJ282))) | IF(OR(F282="",AL282=""),"",IF(COUNT(AI282:AK282)=0,"",AL282-LOOKUP(2,1/(AI282:AK282<>""),AI282:AK282))) | IF(OR(F282="",AM282=""),"",IF(COUNT(AI282:AL282)=0,"",AM282-LOOKUP(2,1/(AI282:AL282<>""),AI282:AL282))) | IF(OR(F282="",AN282=""),"",IF(COUNT(AI282:AM282)=0,"",AN282-LOOKUP(2,1/(AI282:AM282<>""),AI282:AM282))) | IF(OR(F282="",AO282=""),"",IF(COUNT(AI282:AN282)=0,"",AO282-LOOKUP(2,1/(AI282:AN282<>""),AI282:AN282))) | IF(OR(F282="",AP282=""),"",IF(COUNT(AI282:AO282)=0,"",AP282-LOOKUP(2,1/(AI282:AO282<>""),AI282:AO282))) | IF(OR(F282="",AQ282=""),"",IF(COUNT(AI282:AP282)=0,"",AQ282-LOOKUP(2,1/(AI282:AP282<>""),AI282:AP282))) | IF(OR(F282="",AR282=""),"",IF(COUNT(AI282:AQ282)=0,"",AR282-LOOKUP(2,1/(AI282:AQ282<>""),AI282:AQ282))) | IF(OR(F282="",AS282=""),"",IF(COUNT(AI282:AR282)=0,"",AS282-LOOKUP(2,1/(AI282:AR282<>""),AI282:AR282))) | IF(OR(F282="",AT282=""),"",IF(COUNT(AI282:AS282)=0,"",AT282-LOOKUP(2,1/(AI282:AS282<>""),AI282:AS282))) | IF(OR(F282="",AU282=""),"",IF(COUNT(AI282:AT282)=0,"",AU282-LOOKUP(2,1/(AI282:AT282<>""),AI282:AT282))) | IF(OR(F282="",AV282=""),"",IF(COUNT(AI282:AU282)=0,"",AV282-LOOKUP(2,1/(AI282:AU282<>""),AI282:AU282))) | IF(J282="","All_Provinces",IFERROR(VLOOKUP(J282,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K282="","All_Districts",IFERROR(VLOOKUP(K282,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F283="","",ROW()-3) | [18 empty] | IF(AQ283="","",AQ283) |  |  |  | IF(W283<>"",W283,IF(OR(T283="",V283=""),"",EDATE(T283,V283))) |  |  |  |  | IF(F283="","",IF(COUNT(AI283:AV283)=0,IF(AA283="","Not started",AA283),SUBSTITUTE(LOOKUP(2,1/(AI283:AV283<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F283="",COUNT(AI283:AV283)=0),"",TODAY()-LOOKUP(2,1/(AI283:AV283<>""),AI283:AV283)) | IF(OR(F283="",COUNT(AI283:AV283)<2),"",LOOKUP(2,1/(AI283:AV283<>""),AI283:AV283)-MIN(AI283:AV283)) | IF(OR(AD283="",AC283="Not started",AC283=""),"",IFERROR(AD283-IF(VLOOKUP(AC283,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC283,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F283="","",IF(OR(AA283="Cancelled",AC283="Cancelled"),"Cancelled",IF(OR(AC283="Completed / Handover",Y283<>"",Z283>=100),"Completed — on track",IF(O283="Not awarded",IF(U283="",IF(X283="","No planned date",IF(TODAY()>X283,"Behind — past planned date",IF(X283-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U283,"Behind — award date passed",IF(U283-TODAY()<=30,"At risk — close to off track","On track"))),IF(X283="","No planned date",IF(AND(TODAY()>X283,OR(Z283="",Z283<100)),"Behind — past end date",IF(AND(T283<>"",X283<>"",Z283<>"",(Z283<100),((TODAY()-T283)/MAX(X283-T283,1)*100)-Z283>15),"Behind — progress lag",IF(AND(X283-TODAY()<=30,X283-TODAY()>=0,OR(Z283="",Z283<90)),"At risk — close to off track","On track")))))))) | IF(OR(F283="",AC283="Completed / Handover",AC283="Cancelled"),"",IF(O283="Not awarded",IF(U283<>"",U283-TODAY(),IF(X283="","",X283-TODAY())),IF(X283="","",X283-TODAY()))) | [14 empty] | IF(OR(F283="",AJ283=""),"",IF(COUNT(AI283:AI283)=0,"",AJ283-LOOKUP(2,1/(AI283:AI283<>""),AI283:AI283))) | IF(OR(F283="",AK283=""),"",IF(COUNT(AI283:AJ283)=0,"",AK283-LOOKUP(2,1/(AI283:AJ283<>""),AI283:AJ283))) | IF(OR(F283="",AL283=""),"",IF(COUNT(AI283:AK283)=0,"",AL283-LOOKUP(2,1/(AI283:AK283<>""),AI283:AK283))) | IF(OR(F283="",AM283=""),"",IF(COUNT(AI283:AL283)=0,"",AM283-LOOKUP(2,1/(AI283:AL283<>""),AI283:AL283))) | IF(OR(F283="",AN283=""),"",IF(COUNT(AI283:AM283)=0,"",AN283-LOOKUP(2,1/(AI283:AM283<>""),AI283:AM283))) | IF(OR(F283="",AO283=""),"",IF(COUNT(AI283:AN283)=0,"",AO283-LOOKUP(2,1/(AI283:AN283<>""),AI283:AN283))) | IF(OR(F283="",AP283=""),"",IF(COUNT(AI283:AO283)=0,"",AP283-LOOKUP(2,1/(AI283:AO283<>""),AI283:AO283))) | IF(OR(F283="",AQ283=""),"",IF(COUNT(AI283:AP283)=0,"",AQ283-LOOKUP(2,1/(AI283:AP283<>""),AI283:AP283))) | IF(OR(F283="",AR283=""),"",IF(COUNT(AI283:AQ283)=0,"",AR283-LOOKUP(2,1/(AI283:AQ283<>""),AI283:AQ283))) | IF(OR(F283="",AS283=""),"",IF(COUNT(AI283:AR283)=0,"",AS283-LOOKUP(2,1/(AI283:AR283<>""),AI283:AR283))) | IF(OR(F283="",AT283=""),"",IF(COUNT(AI283:AS283)=0,"",AT283-LOOKUP(2,1/(AI283:AS283<>""),AI283:AS283))) | IF(OR(F283="",AU283=""),"",IF(COUNT(AI283:AT283)=0,"",AU283-LOOKUP(2,1/(AI283:AT283<>""),AI283:AT283))) | IF(OR(F283="",AV283=""),"",IF(COUNT(AI283:AU283)=0,"",AV283-LOOKUP(2,1/(AI283:AU283<>""),AI283:AU283))) | IF(J283="","All_Provinces",IFERROR(VLOOKUP(J283,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K283="","All_Districts",IFERROR(VLOOKUP(K283,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F284="","",ROW()-3) | [18 empty] | IF(AQ284="","",AQ284) |  |  |  | IF(W284<>"",W284,IF(OR(T284="",V284=""),"",EDATE(T284,V284))) |  |  |  |  | IF(F284="","",IF(COUNT(AI284:AV284)=0,IF(AA284="","Not started",AA284),SUBSTITUTE(LOOKUP(2,1/(AI284:AV284<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F284="",COUNT(AI284:AV284)=0),"",TODAY()-LOOKUP(2,1/(AI284:AV284<>""),AI284:AV284)) | IF(OR(F284="",COUNT(AI284:AV284)<2),"",LOOKUP(2,1/(AI284:AV284<>""),AI284:AV284)-MIN(AI284:AV284)) | IF(OR(AD284="",AC284="Not started",AC284=""),"",IFERROR(AD284-IF(VLOOKUP(AC284,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC284,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F284="","",IF(OR(AA284="Cancelled",AC284="Cancelled"),"Cancelled",IF(OR(AC284="Completed / Handover",Y284<>"",Z284>=100),"Completed — on track",IF(O284="Not awarded",IF(U284="",IF(X284="","No planned date",IF(TODAY()>X284,"Behind — past planned date",IF(X284-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U284,"Behind — award date passed",IF(U284-TODAY()<=30,"At risk — close to off track","On track"))),IF(X284="","No planned date",IF(AND(TODAY()>X284,OR(Z284="",Z284<100)),"Behind — past end date",IF(AND(T284<>"",X284<>"",Z284<>"",(Z284<100),((TODAY()-T284)/MAX(X284-T284,1)*100)-Z284>15),"Behind — progress lag",IF(AND(X284-TODAY()<=30,X284-TODAY()>=0,OR(Z284="",Z284<90)),"At risk — close to off track","On track")))))))) | IF(OR(F284="",AC284="Completed / Handover",AC284="Cancelled"),"",IF(O284="Not awarded",IF(U284<>"",U284-TODAY(),IF(X284="","",X284-TODAY())),IF(X284="","",X284-TODAY()))) | [14 empty] | IF(OR(F284="",AJ284=""),"",IF(COUNT(AI284:AI284)=0,"",AJ284-LOOKUP(2,1/(AI284:AI284<>""),AI284:AI284))) | IF(OR(F284="",AK284=""),"",IF(COUNT(AI284:AJ284)=0,"",AK284-LOOKUP(2,1/(AI284:AJ284<>""),AI284:AJ284))) | IF(OR(F284="",AL284=""),"",IF(COUNT(AI284:AK284)=0,"",AL284-LOOKUP(2,1/(AI284:AK284<>""),AI284:AK284))) | IF(OR(F284="",AM284=""),"",IF(COUNT(AI284:AL284)=0,"",AM284-LOOKUP(2,1/(AI284:AL284<>""),AI284:AL284))) | IF(OR(F284="",AN284=""),"",IF(COUNT(AI284:AM284)=0,"",AN284-LOOKUP(2,1/(AI284:AM284<>""),AI284:AM284))) | IF(OR(F284="",AO284=""),"",IF(COUNT(AI284:AN284)=0,"",AO284-LOOKUP(2,1/(AI284:AN284<>""),AI284:AN284))) | IF(OR(F284="",AP284=""),"",IF(COUNT(AI284:AO284)=0,"",AP284-LOOKUP(2,1/(AI284:AO284<>""),AI284:AO284))) | IF(OR(F284="",AQ284=""),"",IF(COUNT(AI284:AP284)=0,"",AQ284-LOOKUP(2,1/(AI284:AP284<>""),AI284:AP284))) | IF(OR(F284="",AR284=""),"",IF(COUNT(AI284:AQ284)=0,"",AR284-LOOKUP(2,1/(AI284:AQ284<>""),AI284:AQ284))) | IF(OR(F284="",AS284=""),"",IF(COUNT(AI284:AR284)=0,"",AS284-LOOKUP(2,1/(AI284:AR284<>""),AI284:AR284))) | IF(OR(F284="",AT284=""),"",IF(COUNT(AI284:AS284)=0,"",AT284-LOOKUP(2,1/(AI284:AS284<>""),AI284:AS284))) | IF(OR(F284="",AU284=""),"",IF(COUNT(AI284:AT284)=0,"",AU284-LOOKUP(2,1/(AI284:AT284<>""),AI284:AT284))) | IF(OR(F284="",AV284=""),"",IF(COUNT(AI284:AU284)=0,"",AV284-LOOKUP(2,1/(AI284:AU284<>""),AI284:AU284))) | IF(J284="","All_Provinces",IFERROR(VLOOKUP(J284,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K284="","All_Districts",IFERROR(VLOOKUP(K284,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F285="","",ROW()-3) | [18 empty] | IF(AQ285="","",AQ285) |  |  |  | IF(W285<>"",W285,IF(OR(T285="",V285=""),"",EDATE(T285,V285))) |  |  |  |  | IF(F285="","",IF(COUNT(AI285:AV285)=0,IF(AA285="","Not started",AA285),SUBSTITUTE(LOOKUP(2,1/(AI285:AV285<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F285="",COUNT(AI285:AV285)=0),"",TODAY()-LOOKUP(2,1/(AI285:AV285<>""),AI285:AV285)) | IF(OR(F285="",COUNT(AI285:AV285)<2),"",LOOKUP(2,1/(AI285:AV285<>""),AI285:AV285)-MIN(AI285:AV285)) | IF(OR(AD285="",AC285="Not started",AC285=""),"",IFERROR(AD285-IF(VLOOKUP(AC285,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC285,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F285="","",IF(OR(AA285="Cancelled",AC285="Cancelled"),"Cancelled",IF(OR(AC285="Completed / Handover",Y285<>"",Z285>=100),"Completed — on track",IF(O285="Not awarded",IF(U285="",IF(X285="","No planned date",IF(TODAY()>X285,"Behind — past planned date",IF(X285-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U285,"Behind — award date passed",IF(U285-TODAY()<=30,"At risk — close to off track","On track"))),IF(X285="","No planned date",IF(AND(TODAY()>X285,OR(Z285="",Z285<100)),"Behind — past end date",IF(AND(T285<>"",X285<>"",Z285<>"",(Z285<100),((TODAY()-T285)/MAX(X285-T285,1)*100)-Z285>15),"Behind — progress lag",IF(AND(X285-TODAY()<=30,X285-TODAY()>=0,OR(Z285="",Z285<90)),"At risk — close to off track","On track")))))))) | IF(OR(F285="",AC285="Completed / Handover",AC285="Cancelled"),"",IF(O285="Not awarded",IF(U285<>"",U285-TODAY(),IF(X285="","",X285-TODAY())),IF(X285="","",X285-TODAY()))) | [14 empty] | IF(OR(F285="",AJ285=""),"",IF(COUNT(AI285:AI285)=0,"",AJ285-LOOKUP(2,1/(AI285:AI285<>""),AI285:AI285))) | IF(OR(F285="",AK285=""),"",IF(COUNT(AI285:AJ285)=0,"",AK285-LOOKUP(2,1/(AI285:AJ285<>""),AI285:AJ285))) | IF(OR(F285="",AL285=""),"",IF(COUNT(AI285:AK285)=0,"",AL285-LOOKUP(2,1/(AI285:AK285<>""),AI285:AK285))) | IF(OR(F285="",AM285=""),"",IF(COUNT(AI285:AL285)=0,"",AM285-LOOKUP(2,1/(AI285:AL285<>""),AI285:AL285))) | IF(OR(F285="",AN285=""),"",IF(COUNT(AI285:AM285)=0,"",AN285-LOOKUP(2,1/(AI285:AM285<>""),AI285:AM285))) | IF(OR(F285="",AO285=""),"",IF(COUNT(AI285:AN285)=0,"",AO285-LOOKUP(2,1/(AI285:AN285<>""),AI285:AN285))) | IF(OR(F285="",AP285=""),"",IF(COUNT(AI285:AO285)=0,"",AP285-LOOKUP(2,1/(AI285:AO285<>""),AI285:AO285))) | IF(OR(F285="",AQ285=""),"",IF(COUNT(AI285:AP285)=0,"",AQ285-LOOKUP(2,1/(AI285:AP285<>""),AI285:AP285))) | IF(OR(F285="",AR285=""),"",IF(COUNT(AI285:AQ285)=0,"",AR285-LOOKUP(2,1/(AI285:AQ285<>""),AI285:AQ285))) | IF(OR(F285="",AS285=""),"",IF(COUNT(AI285:AR285)=0,"",AS285-LOOKUP(2,1/(AI285:AR285<>""),AI285:AR285))) | IF(OR(F285="",AT285=""),"",IF(COUNT(AI285:AS285)=0,"",AT285-LOOKUP(2,1/(AI285:AS285<>""),AI285:AS285))) | IF(OR(F285="",AU285=""),"",IF(COUNT(AI285:AT285)=0,"",AU285-LOOKUP(2,1/(AI285:AT285<>""),AI285:AT285))) | IF(OR(F285="",AV285=""),"",IF(COUNT(AI285:AU285)=0,"",AV285-LOOKUP(2,1/(AI285:AU285<>""),AI285:AU285))) | IF(J285="","All_Provinces",IFERROR(VLOOKUP(J285,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K285="","All_Districts",IFERROR(VLOOKUP(K285,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F286="","",ROW()-3) | [18 empty] | IF(AQ286="","",AQ286) |  |  |  | IF(W286<>"",W286,IF(OR(T286="",V286=""),"",EDATE(T286,V286))) |  |  |  |  | IF(F286="","",IF(COUNT(AI286:AV286)=0,IF(AA286="","Not started",AA286),SUBSTITUTE(LOOKUP(2,1/(AI286:AV286<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F286="",COUNT(AI286:AV286)=0),"",TODAY()-LOOKUP(2,1/(AI286:AV286<>""),AI286:AV286)) | IF(OR(F286="",COUNT(AI286:AV286)<2),"",LOOKUP(2,1/(AI286:AV286<>""),AI286:AV286)-MIN(AI286:AV286)) | IF(OR(AD286="",AC286="Not started",AC286=""),"",IFERROR(AD286-IF(VLOOKUP(AC286,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC286,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F286="","",IF(OR(AA286="Cancelled",AC286="Cancelled"),"Cancelled",IF(OR(AC286="Completed / Handover",Y286<>"",Z286>=100),"Completed — on track",IF(O286="Not awarded",IF(U286="",IF(X286="","No planned date",IF(TODAY()>X286,"Behind — past planned date",IF(X286-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U286,"Behind — award date passed",IF(U286-TODAY()<=30,"At risk — close to off track","On track"))),IF(X286="","No planned date",IF(AND(TODAY()>X286,OR(Z286="",Z286<100)),"Behind — past end date",IF(AND(T286<>"",X286<>"",Z286<>"",(Z286<100),((TODAY()-T286)/MAX(X286-T286,1)*100)-Z286>15),"Behind — progress lag",IF(AND(X286-TODAY()<=30,X286-TODAY()>=0,OR(Z286="",Z286<90)),"At risk — close to off track","On track")))))))) | IF(OR(F286="",AC286="Completed / Handover",AC286="Cancelled"),"",IF(O286="Not awarded",IF(U286<>"",U286-TODAY(),IF(X286="","",X286-TODAY())),IF(X286="","",X286-TODAY()))) | [14 empty] | IF(OR(F286="",AJ286=""),"",IF(COUNT(AI286:AI286)=0,"",AJ286-LOOKUP(2,1/(AI286:AI286<>""),AI286:AI286))) | IF(OR(F286="",AK286=""),"",IF(COUNT(AI286:AJ286)=0,"",AK286-LOOKUP(2,1/(AI286:AJ286<>""),AI286:AJ286))) | IF(OR(F286="",AL286=""),"",IF(COUNT(AI286:AK286)=0,"",AL286-LOOKUP(2,1/(AI286:AK286<>""),AI286:AK286))) | IF(OR(F286="",AM286=""),"",IF(COUNT(AI286:AL286)=0,"",AM286-LOOKUP(2,1/(AI286:AL286<>""),AI286:AL286))) | IF(OR(F286="",AN286=""),"",IF(COUNT(AI286:AM286)=0,"",AN286-LOOKUP(2,1/(AI286:AM286<>""),AI286:AM286))) | IF(OR(F286="",AO286=""),"",IF(COUNT(AI286:AN286)=0,"",AO286-LOOKUP(2,1/(AI286:AN286<>""),AI286:AN286))) | IF(OR(F286="",AP286=""),"",IF(COUNT(AI286:AO286)=0,"",AP286-LOOKUP(2,1/(AI286:AO286<>""),AI286:AO286))) | IF(OR(F286="",AQ286=""),"",IF(COUNT(AI286:AP286)=0,"",AQ286-LOOKUP(2,1/(AI286:AP286<>""),AI286:AP286))) | IF(OR(F286="",AR286=""),"",IF(COUNT(AI286:AQ286)=0,"",AR286-LOOKUP(2,1/(AI286:AQ286<>""),AI286:AQ286))) | IF(OR(F286="",AS286=""),"",IF(COUNT(AI286:AR286)=0,"",AS286-LOOKUP(2,1/(AI286:AR286<>""),AI286:AR286))) | IF(OR(F286="",AT286=""),"",IF(COUNT(AI286:AS286)=0,"",AT286-LOOKUP(2,1/(AI286:AS286<>""),AI286:AS286))) | IF(OR(F286="",AU286=""),"",IF(COUNT(AI286:AT286)=0,"",AU286-LOOKUP(2,1/(AI286:AT286<>""),AI286:AT286))) | IF(OR(F286="",AV286=""),"",IF(COUNT(AI286:AU286)=0,"",AV286-LOOKUP(2,1/(AI286:AU286<>""),AI286:AU286))) | IF(J286="","All_Provinces",IFERROR(VLOOKUP(J286,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K286="","All_Districts",IFERROR(VLOOKUP(K286,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F287="","",ROW()-3) | [18 empty] | IF(AQ287="","",AQ287) |  |  |  | IF(W287<>"",W287,IF(OR(T287="",V287=""),"",EDATE(T287,V287))) |  |  |  |  | IF(F287="","",IF(COUNT(AI287:AV287)=0,IF(AA287="","Not started",AA287),SUBSTITUTE(LOOKUP(2,1/(AI287:AV287<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F287="",COUNT(AI287:AV287)=0),"",TODAY()-LOOKUP(2,1/(AI287:AV287<>""),AI287:AV287)) | IF(OR(F287="",COUNT(AI287:AV287)<2),"",LOOKUP(2,1/(AI287:AV287<>""),AI287:AV287)-MIN(AI287:AV287)) | IF(OR(AD287="",AC287="Not started",AC287=""),"",IFERROR(AD287-IF(VLOOKUP(AC287,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC287,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F287="","",IF(OR(AA287="Cancelled",AC287="Cancelled"),"Cancelled",IF(OR(AC287="Completed / Handover",Y287<>"",Z287>=100),"Completed — on track",IF(O287="Not awarded",IF(U287="",IF(X287="","No planned date",IF(TODAY()>X287,"Behind — past planned date",IF(X287-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U287,"Behind — award date passed",IF(U287-TODAY()<=30,"At risk — close to off track","On track"))),IF(X287="","No planned date",IF(AND(TODAY()>X287,OR(Z287="",Z287<100)),"Behind — past end date",IF(AND(T287<>"",X287<>"",Z287<>"",(Z287<100),((TODAY()-T287)/MAX(X287-T287,1)*100)-Z287>15),"Behind — progress lag",IF(AND(X287-TODAY()<=30,X287-TODAY()>=0,OR(Z287="",Z287<90)),"At risk — close to off track","On track")))))))) | IF(OR(F287="",AC287="Completed / Handover",AC287="Cancelled"),"",IF(O287="Not awarded",IF(U287<>"",U287-TODAY(),IF(X287="","",X287-TODAY())),IF(X287="","",X287-TODAY()))) | [14 empty] | IF(OR(F287="",AJ287=""),"",IF(COUNT(AI287:AI287)=0,"",AJ287-LOOKUP(2,1/(AI287:AI287<>""),AI287:AI287))) | IF(OR(F287="",AK287=""),"",IF(COUNT(AI287:AJ287)=0,"",AK287-LOOKUP(2,1/(AI287:AJ287<>""),AI287:AJ287))) | IF(OR(F287="",AL287=""),"",IF(COUNT(AI287:AK287)=0,"",AL287-LOOKUP(2,1/(AI287:AK287<>""),AI287:AK287))) | IF(OR(F287="",AM287=""),"",IF(COUNT(AI287:AL287)=0,"",AM287-LOOKUP(2,1/(AI287:AL287<>""),AI287:AL287))) | IF(OR(F287="",AN287=""),"",IF(COUNT(AI287:AM287)=0,"",AN287-LOOKUP(2,1/(AI287:AM287<>""),AI287:AM287))) | IF(OR(F287="",AO287=""),"",IF(COUNT(AI287:AN287)=0,"",AO287-LOOKUP(2,1/(AI287:AN287<>""),AI287:AN287))) | IF(OR(F287="",AP287=""),"",IF(COUNT(AI287:AO287)=0,"",AP287-LOOKUP(2,1/(AI287:AO287<>""),AI287:AO287))) | IF(OR(F287="",AQ287=""),"",IF(COUNT(AI287:AP287)=0,"",AQ287-LOOKUP(2,1/(AI287:AP287<>""),AI287:AP287))) | IF(OR(F287="",AR287=""),"",IF(COUNT(AI287:AQ287)=0,"",AR287-LOOKUP(2,1/(AI287:AQ287<>""),AI287:AQ287))) | IF(OR(F287="",AS287=""),"",IF(COUNT(AI287:AR287)=0,"",AS287-LOOKUP(2,1/(AI287:AR287<>""),AI287:AR287))) | IF(OR(F287="",AT287=""),"",IF(COUNT(AI287:AS287)=0,"",AT287-LOOKUP(2,1/(AI287:AS287<>""),AI287:AS287))) | IF(OR(F287="",AU287=""),"",IF(COUNT(AI287:AT287)=0,"",AU287-LOOKUP(2,1/(AI287:AT287<>""),AI287:AT287))) | IF(OR(F287="",AV287=""),"",IF(COUNT(AI287:AU287)=0,"",AV287-LOOKUP(2,1/(AI287:AU287<>""),AI287:AU287))) | IF(J287="","All_Provinces",IFERROR(VLOOKUP(J287,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K287="","All_Districts",IFERROR(VLOOKUP(K287,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F288="","",ROW()-3) | [18 empty] | IF(AQ288="","",AQ288) |  |  |  | IF(W288<>"",W288,IF(OR(T288="",V288=""),"",EDATE(T288,V288))) |  |  |  |  | IF(F288="","",IF(COUNT(AI288:AV288)=0,IF(AA288="","Not started",AA288),SUBSTITUTE(LOOKUP(2,1/(AI288:AV288<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F288="",COUNT(AI288:AV288)=0),"",TODAY()-LOOKUP(2,1/(AI288:AV288<>""),AI288:AV288)) | IF(OR(F288="",COUNT(AI288:AV288)<2),"",LOOKUP(2,1/(AI288:AV288<>""),AI288:AV288)-MIN(AI288:AV288)) | IF(OR(AD288="",AC288="Not started",AC288=""),"",IFERROR(AD288-IF(VLOOKUP(AC288,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC288,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F288="","",IF(OR(AA288="Cancelled",AC288="Cancelled"),"Cancelled",IF(OR(AC288="Completed / Handover",Y288<>"",Z288>=100),"Completed — on track",IF(O288="Not awarded",IF(U288="",IF(X288="","No planned date",IF(TODAY()>X288,"Behind — past planned date",IF(X288-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U288,"Behind — award date passed",IF(U288-TODAY()<=30,"At risk — close to off track","On track"))),IF(X288="","No planned date",IF(AND(TODAY()>X288,OR(Z288="",Z288<100)),"Behind — past end date",IF(AND(T288<>"",X288<>"",Z288<>"",(Z288<100),((TODAY()-T288)/MAX(X288-T288,1)*100)-Z288>15),"Behind — progress lag",IF(AND(X288-TODAY()<=30,X288-TODAY()>=0,OR(Z288="",Z288<90)),"At risk — close to off track","On track")))))))) | IF(OR(F288="",AC288="Completed / Handover",AC288="Cancelled"),"",IF(O288="Not awarded",IF(U288<>"",U288-TODAY(),IF(X288="","",X288-TODAY())),IF(X288="","",X288-TODAY()))) | [14 empty] | IF(OR(F288="",AJ288=""),"",IF(COUNT(AI288:AI288)=0,"",AJ288-LOOKUP(2,1/(AI288:AI288<>""),AI288:AI288))) | IF(OR(F288="",AK288=""),"",IF(COUNT(AI288:AJ288)=0,"",AK288-LOOKUP(2,1/(AI288:AJ288<>""),AI288:AJ288))) | IF(OR(F288="",AL288=""),"",IF(COUNT(AI288:AK288)=0,"",AL288-LOOKUP(2,1/(AI288:AK288<>""),AI288:AK288))) | IF(OR(F288="",AM288=""),"",IF(COUNT(AI288:AL288)=0,"",AM288-LOOKUP(2,1/(AI288:AL288<>""),AI288:AL288))) | IF(OR(F288="",AN288=""),"",IF(COUNT(AI288:AM288)=0,"",AN288-LOOKUP(2,1/(AI288:AM288<>""),AI288:AM288))) | IF(OR(F288="",AO288=""),"",IF(COUNT(AI288:AN288)=0,"",AO288-LOOKUP(2,1/(AI288:AN288<>""),AI288:AN288))) | IF(OR(F288="",AP288=""),"",IF(COUNT(AI288:AO288)=0,"",AP288-LOOKUP(2,1/(AI288:AO288<>""),AI288:AO288))) | IF(OR(F288="",AQ288=""),"",IF(COUNT(AI288:AP288)=0,"",AQ288-LOOKUP(2,1/(AI288:AP288<>""),AI288:AP288))) | IF(OR(F288="",AR288=""),"",IF(COUNT(AI288:AQ288)=0,"",AR288-LOOKUP(2,1/(AI288:AQ288<>""),AI288:AQ288))) | IF(OR(F288="",AS288=""),"",IF(COUNT(AI288:AR288)=0,"",AS288-LOOKUP(2,1/(AI288:AR288<>""),AI288:AR288))) | IF(OR(F288="",AT288=""),"",IF(COUNT(AI288:AS288)=0,"",AT288-LOOKUP(2,1/(AI288:AS288<>""),AI288:AS288))) | IF(OR(F288="",AU288=""),"",IF(COUNT(AI288:AT288)=0,"",AU288-LOOKUP(2,1/(AI288:AT288<>""),AI288:AT288))) | IF(OR(F288="",AV288=""),"",IF(COUNT(AI288:AU288)=0,"",AV288-LOOKUP(2,1/(AI288:AU288<>""),AI288:AU288))) | IF(J288="","All_Provinces",IFERROR(VLOOKUP(J288,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K288="","All_Districts",IFERROR(VLOOKUP(K288,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F289="","",ROW()-3) | [18 empty] | IF(AQ289="","",AQ289) |  |  |  | IF(W289<>"",W289,IF(OR(T289="",V289=""),"",EDATE(T289,V289))) |  |  |  |  | IF(F289="","",IF(COUNT(AI289:AV289)=0,IF(AA289="","Not started",AA289),SUBSTITUTE(LOOKUP(2,1/(AI289:AV289<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F289="",COUNT(AI289:AV289)=0),"",TODAY()-LOOKUP(2,1/(AI289:AV289<>""),AI289:AV289)) | IF(OR(F289="",COUNT(AI289:AV289)<2),"",LOOKUP(2,1/(AI289:AV289<>""),AI289:AV289)-MIN(AI289:AV289)) | IF(OR(AD289="",AC289="Not started",AC289=""),"",IFERROR(AD289-IF(VLOOKUP(AC289,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC289,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F289="","",IF(OR(AA289="Cancelled",AC289="Cancelled"),"Cancelled",IF(OR(AC289="Completed / Handover",Y289<>"",Z289>=100),"Completed — on track",IF(O289="Not awarded",IF(U289="",IF(X289="","No planned date",IF(TODAY()>X289,"Behind — past planned date",IF(X289-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U289,"Behind — award date passed",IF(U289-TODAY()<=30,"At risk — close to off track","On track"))),IF(X289="","No planned date",IF(AND(TODAY()>X289,OR(Z289="",Z289<100)),"Behind — past end date",IF(AND(T289<>"",X289<>"",Z289<>"",(Z289<100),((TODAY()-T289)/MAX(X289-T289,1)*100)-Z289>15),"Behind — progress lag",IF(AND(X289-TODAY()<=30,X289-TODAY()>=0,OR(Z289="",Z289<90)),"At risk — close to off track","On track")))))))) | IF(OR(F289="",AC289="Completed / Handover",AC289="Cancelled"),"",IF(O289="Not awarded",IF(U289<>"",U289-TODAY(),IF(X289="","",X289-TODAY())),IF(X289="","",X289-TODAY()))) | [14 empty] | IF(OR(F289="",AJ289=""),"",IF(COUNT(AI289:AI289)=0,"",AJ289-LOOKUP(2,1/(AI289:AI289<>""),AI289:AI289))) | IF(OR(F289="",AK289=""),"",IF(COUNT(AI289:AJ289)=0,"",AK289-LOOKUP(2,1/(AI289:AJ289<>""),AI289:AJ289))) | IF(OR(F289="",AL289=""),"",IF(COUNT(AI289:AK289)=0,"",AL289-LOOKUP(2,1/(AI289:AK289<>""),AI289:AK289))) | IF(OR(F289="",AM289=""),"",IF(COUNT(AI289:AL289)=0,"",AM289-LOOKUP(2,1/(AI289:AL289<>""),AI289:AL289))) | IF(OR(F289="",AN289=""),"",IF(COUNT(AI289:AM289)=0,"",AN289-LOOKUP(2,1/(AI289:AM289<>""),AI289:AM289))) | IF(OR(F289="",AO289=""),"",IF(COUNT(AI289:AN289)=0,"",AO289-LOOKUP(2,1/(AI289:AN289<>""),AI289:AN289))) | IF(OR(F289="",AP289=""),"",IF(COUNT(AI289:AO289)=0,"",AP289-LOOKUP(2,1/(AI289:AO289<>""),AI289:AO289))) | IF(OR(F289="",AQ289=""),"",IF(COUNT(AI289:AP289)=0,"",AQ289-LOOKUP(2,1/(AI289:AP289<>""),AI289:AP289))) | IF(OR(F289="",AR289=""),"",IF(COUNT(AI289:AQ289)=0,"",AR289-LOOKUP(2,1/(AI289:AQ289<>""),AI289:AQ289))) | IF(OR(F289="",AS289=""),"",IF(COUNT(AI289:AR289)=0,"",AS289-LOOKUP(2,1/(AI289:AR289<>""),AI289:AR289))) | IF(OR(F289="",AT289=""),"",IF(COUNT(AI289:AS289)=0,"",AT289-LOOKUP(2,1/(AI289:AS289<>""),AI289:AS289))) | IF(OR(F289="",AU289=""),"",IF(COUNT(AI289:AT289)=0,"",AU289-LOOKUP(2,1/(AI289:AT289<>""),AI289:AT289))) | IF(OR(F289="",AV289=""),"",IF(COUNT(AI289:AU289)=0,"",AV289-LOOKUP(2,1/(AI289:AU289<>""),AI289:AU289))) | IF(J289="","All_Provinces",IFERROR(VLOOKUP(J289,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K289="","All_Districts",IFERROR(VLOOKUP(K289,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F290="","",ROW()-3) | [18 empty] | IF(AQ290="","",AQ290) |  |  |  | IF(W290<>"",W290,IF(OR(T290="",V290=""),"",EDATE(T290,V290))) |  |  |  |  | IF(F290="","",IF(COUNT(AI290:AV290)=0,IF(AA290="","Not started",AA290),SUBSTITUTE(LOOKUP(2,1/(AI290:AV290<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F290="",COUNT(AI290:AV290)=0),"",TODAY()-LOOKUP(2,1/(AI290:AV290<>""),AI290:AV290)) | IF(OR(F290="",COUNT(AI290:AV290)<2),"",LOOKUP(2,1/(AI290:AV290<>""),AI290:AV290)-MIN(AI290:AV290)) | IF(OR(AD290="",AC290="Not started",AC290=""),"",IFERROR(AD290-IF(VLOOKUP(AC290,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC290,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F290="","",IF(OR(AA290="Cancelled",AC290="Cancelled"),"Cancelled",IF(OR(AC290="Completed / Handover",Y290<>"",Z290>=100),"Completed — on track",IF(O290="Not awarded",IF(U290="",IF(X290="","No planned date",IF(TODAY()>X290,"Behind — past planned date",IF(X290-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U290,"Behind — award date passed",IF(U290-TODAY()<=30,"At risk — close to off track","On track"))),IF(X290="","No planned date",IF(AND(TODAY()>X290,OR(Z290="",Z290<100)),"Behind — past end date",IF(AND(T290<>"",X290<>"",Z290<>"",(Z290<100),((TODAY()-T290)/MAX(X290-T290,1)*100)-Z290>15),"Behind — progress lag",IF(AND(X290-TODAY()<=30,X290-TODAY()>=0,OR(Z290="",Z290<90)),"At risk — close to off track","On track")))))))) | IF(OR(F290="",AC290="Completed / Handover",AC290="Cancelled"),"",IF(O290="Not awarded",IF(U290<>"",U290-TODAY(),IF(X290="","",X290-TODAY())),IF(X290="","",X290-TODAY()))) | [14 empty] | IF(OR(F290="",AJ290=""),"",IF(COUNT(AI290:AI290)=0,"",AJ290-LOOKUP(2,1/(AI290:AI290<>""),AI290:AI290))) | IF(OR(F290="",AK290=""),"",IF(COUNT(AI290:AJ290)=0,"",AK290-LOOKUP(2,1/(AI290:AJ290<>""),AI290:AJ290))) | IF(OR(F290="",AL290=""),"",IF(COUNT(AI290:AK290)=0,"",AL290-LOOKUP(2,1/(AI290:AK290<>""),AI290:AK290))) | IF(OR(F290="",AM290=""),"",IF(COUNT(AI290:AL290)=0,"",AM290-LOOKUP(2,1/(AI290:AL290<>""),AI290:AL290))) | IF(OR(F290="",AN290=""),"",IF(COUNT(AI290:AM290)=0,"",AN290-LOOKUP(2,1/(AI290:AM290<>""),AI290:AM290))) | IF(OR(F290="",AO290=""),"",IF(COUNT(AI290:AN290)=0,"",AO290-LOOKUP(2,1/(AI290:AN290<>""),AI290:AN290))) | IF(OR(F290="",AP290=""),"",IF(COUNT(AI290:AO290)=0,"",AP290-LOOKUP(2,1/(AI290:AO290<>""),AI290:AO290))) | IF(OR(F290="",AQ290=""),"",IF(COUNT(AI290:AP290)=0,"",AQ290-LOOKUP(2,1/(AI290:AP290<>""),AI290:AP290))) | IF(OR(F290="",AR290=""),"",IF(COUNT(AI290:AQ290)=0,"",AR290-LOOKUP(2,1/(AI290:AQ290<>""),AI290:AQ290))) | IF(OR(F290="",AS290=""),"",IF(COUNT(AI290:AR290)=0,"",AS290-LOOKUP(2,1/(AI290:AR290<>""),AI290:AR290))) | IF(OR(F290="",AT290=""),"",IF(COUNT(AI290:AS290)=0,"",AT290-LOOKUP(2,1/(AI290:AS290<>""),AI290:AS290))) | IF(OR(F290="",AU290=""),"",IF(COUNT(AI290:AT290)=0,"",AU290-LOOKUP(2,1/(AI290:AT290<>""),AI290:AT290))) | IF(OR(F290="",AV290=""),"",IF(COUNT(AI290:AU290)=0,"",AV290-LOOKUP(2,1/(AI290:AU290<>""),AI290:AU290))) | IF(J290="","All_Provinces",IFERROR(VLOOKUP(J290,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K290="","All_Districts",IFERROR(VLOOKUP(K290,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F291="","",ROW()-3) | [18 empty] | IF(AQ291="","",AQ291) |  |  |  | IF(W291<>"",W291,IF(OR(T291="",V291=""),"",EDATE(T291,V291))) |  |  |  |  | IF(F291="","",IF(COUNT(AI291:AV291)=0,IF(AA291="","Not started",AA291),SUBSTITUTE(LOOKUP(2,1/(AI291:AV291<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F291="",COUNT(AI291:AV291)=0),"",TODAY()-LOOKUP(2,1/(AI291:AV291<>""),AI291:AV291)) | IF(OR(F291="",COUNT(AI291:AV291)<2),"",LOOKUP(2,1/(AI291:AV291<>""),AI291:AV291)-MIN(AI291:AV291)) | IF(OR(AD291="",AC291="Not started",AC291=""),"",IFERROR(AD291-IF(VLOOKUP(AC291,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC291,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F291="","",IF(OR(AA291="Cancelled",AC291="Cancelled"),"Cancelled",IF(OR(AC291="Completed / Handover",Y291<>"",Z291>=100),"Completed — on track",IF(O291="Not awarded",IF(U291="",IF(X291="","No planned date",IF(TODAY()>X291,"Behind — past planned date",IF(X291-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U291,"Behind — award date passed",IF(U291-TODAY()<=30,"At risk — close to off track","On track"))),IF(X291="","No planned date",IF(AND(TODAY()>X291,OR(Z291="",Z291<100)),"Behind — past end date",IF(AND(T291<>"",X291<>"",Z291<>"",(Z291<100),((TODAY()-T291)/MAX(X291-T291,1)*100)-Z291>15),"Behind — progress lag",IF(AND(X291-TODAY()<=30,X291-TODAY()>=0,OR(Z291="",Z291<90)),"At risk — close to off track","On track")))))))) | IF(OR(F291="",AC291="Completed / Handover",AC291="Cancelled"),"",IF(O291="Not awarded",IF(U291<>"",U291-TODAY(),IF(X291="","",X291-TODAY())),IF(X291="","",X291-TODAY()))) | [14 empty] | IF(OR(F291="",AJ291=""),"",IF(COUNT(AI291:AI291)=0,"",AJ291-LOOKUP(2,1/(AI291:AI291<>""),AI291:AI291))) | IF(OR(F291="",AK291=""),"",IF(COUNT(AI291:AJ291)=0,"",AK291-LOOKUP(2,1/(AI291:AJ291<>""),AI291:AJ291))) | IF(OR(F291="",AL291=""),"",IF(COUNT(AI291:AK291)=0,"",AL291-LOOKUP(2,1/(AI291:AK291<>""),AI291:AK291))) | IF(OR(F291="",AM291=""),"",IF(COUNT(AI291:AL291)=0,"",AM291-LOOKUP(2,1/(AI291:AL291<>""),AI291:AL291))) | IF(OR(F291="",AN291=""),"",IF(COUNT(AI291:AM291)=0,"",AN291-LOOKUP(2,1/(AI291:AM291<>""),AI291:AM291))) | IF(OR(F291="",AO291=""),"",IF(COUNT(AI291:AN291)=0,"",AO291-LOOKUP(2,1/(AI291:AN291<>""),AI291:AN291))) | IF(OR(F291="",AP291=""),"",IF(COUNT(AI291:AO291)=0,"",AP291-LOOKUP(2,1/(AI291:AO291<>""),AI291:AO291))) | IF(OR(F291="",AQ291=""),"",IF(COUNT(AI291:AP291)=0,"",AQ291-LOOKUP(2,1/(AI291:AP291<>""),AI291:AP291))) | IF(OR(F291="",AR291=""),"",IF(COUNT(AI291:AQ291)=0,"",AR291-LOOKUP(2,1/(AI291:AQ291<>""),AI291:AQ291))) | IF(OR(F291="",AS291=""),"",IF(COUNT(AI291:AR291)=0,"",AS291-LOOKUP(2,1/(AI291:AR291<>""),AI291:AR291))) | IF(OR(F291="",AT291=""),"",IF(COUNT(AI291:AS291)=0,"",AT291-LOOKUP(2,1/(AI291:AS291<>""),AI291:AS291))) | IF(OR(F291="",AU291=""),"",IF(COUNT(AI291:AT291)=0,"",AU291-LOOKUP(2,1/(AI291:AT291<>""),AI291:AT291))) | IF(OR(F291="",AV291=""),"",IF(COUNT(AI291:AU291)=0,"",AV291-LOOKUP(2,1/(AI291:AU291<>""),AI291:AU291))) | IF(J291="","All_Provinces",IFERROR(VLOOKUP(J291,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K291="","All_Districts",IFERROR(VLOOKUP(K291,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F292="","",ROW()-3) | [18 empty] | IF(AQ292="","",AQ292) |  |  |  | IF(W292<>"",W292,IF(OR(T292="",V292=""),"",EDATE(T292,V292))) |  |  |  |  | IF(F292="","",IF(COUNT(AI292:AV292)=0,IF(AA292="","Not started",AA292),SUBSTITUTE(LOOKUP(2,1/(AI292:AV292<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F292="",COUNT(AI292:AV292)=0),"",TODAY()-LOOKUP(2,1/(AI292:AV292<>""),AI292:AV292)) | IF(OR(F292="",COUNT(AI292:AV292)<2),"",LOOKUP(2,1/(AI292:AV292<>""),AI292:AV292)-MIN(AI292:AV292)) | IF(OR(AD292="",AC292="Not started",AC292=""),"",IFERROR(AD292-IF(VLOOKUP(AC292,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC292,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F292="","",IF(OR(AA292="Cancelled",AC292="Cancelled"),"Cancelled",IF(OR(AC292="Completed / Handover",Y292<>"",Z292>=100),"Completed — on track",IF(O292="Not awarded",IF(U292="",IF(X292="","No planned date",IF(TODAY()>X292,"Behind — past planned date",IF(X292-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U292,"Behind — award date passed",IF(U292-TODAY()<=30,"At risk — close to off track","On track"))),IF(X292="","No planned date",IF(AND(TODAY()>X292,OR(Z292="",Z292<100)),"Behind — past end date",IF(AND(T292<>"",X292<>"",Z292<>"",(Z292<100),((TODAY()-T292)/MAX(X292-T292,1)*100)-Z292>15),"Behind — progress lag",IF(AND(X292-TODAY()<=30,X292-TODAY()>=0,OR(Z292="",Z292<90)),"At risk — close to off track","On track")))))))) | IF(OR(F292="",AC292="Completed / Handover",AC292="Cancelled"),"",IF(O292="Not awarded",IF(U292<>"",U292-TODAY(),IF(X292="","",X292-TODAY())),IF(X292="","",X292-TODAY()))) | [14 empty] | IF(OR(F292="",AJ292=""),"",IF(COUNT(AI292:AI292)=0,"",AJ292-LOOKUP(2,1/(AI292:AI292<>""),AI292:AI292))) | IF(OR(F292="",AK292=""),"",IF(COUNT(AI292:AJ292)=0,"",AK292-LOOKUP(2,1/(AI292:AJ292<>""),AI292:AJ292))) | IF(OR(F292="",AL292=""),"",IF(COUNT(AI292:AK292)=0,"",AL292-LOOKUP(2,1/(AI292:AK292<>""),AI292:AK292))) | IF(OR(F292="",AM292=""),"",IF(COUNT(AI292:AL292)=0,"",AM292-LOOKUP(2,1/(AI292:AL292<>""),AI292:AL292))) | IF(OR(F292="",AN292=""),"",IF(COUNT(AI292:AM292)=0,"",AN292-LOOKUP(2,1/(AI292:AM292<>""),AI292:AM292))) | IF(OR(F292="",AO292=""),"",IF(COUNT(AI292:AN292)=0,"",AO292-LOOKUP(2,1/(AI292:AN292<>""),AI292:AN292))) | IF(OR(F292="",AP292=""),"",IF(COUNT(AI292:AO292)=0,"",AP292-LOOKUP(2,1/(AI292:AO292<>""),AI292:AO292))) | IF(OR(F292="",AQ292=""),"",IF(COUNT(AI292:AP292)=0,"",AQ292-LOOKUP(2,1/(AI292:AP292<>""),AI292:AP292))) | IF(OR(F292="",AR292=""),"",IF(COUNT(AI292:AQ292)=0,"",AR292-LOOKUP(2,1/(AI292:AQ292<>""),AI292:AQ292))) | IF(OR(F292="",AS292=""),"",IF(COUNT(AI292:AR292)=0,"",AS292-LOOKUP(2,1/(AI292:AR292<>""),AI292:AR292))) | IF(OR(F292="",AT292=""),"",IF(COUNT(AI292:AS292)=0,"",AT292-LOOKUP(2,1/(AI292:AS292<>""),AI292:AS292))) | IF(OR(F292="",AU292=""),"",IF(COUNT(AI292:AT292)=0,"",AU292-LOOKUP(2,1/(AI292:AT292<>""),AI292:AT292))) | IF(OR(F292="",AV292=""),"",IF(COUNT(AI292:AU292)=0,"",AV292-LOOKUP(2,1/(AI292:AU292<>""),AI292:AU292))) | IF(J292="","All_Provinces",IFERROR(VLOOKUP(J292,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K292="","All_Districts",IFERROR(VLOOKUP(K292,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F293="","",ROW()-3) | [18 empty] | IF(AQ293="","",AQ293) |  |  |  | IF(W293<>"",W293,IF(OR(T293="",V293=""),"",EDATE(T293,V293))) |  |  |  |  | IF(F293="","",IF(COUNT(AI293:AV293)=0,IF(AA293="","Not started",AA293),SUBSTITUTE(LOOKUP(2,1/(AI293:AV293<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F293="",COUNT(AI293:AV293)=0),"",TODAY()-LOOKUP(2,1/(AI293:AV293<>""),AI293:AV293)) | IF(OR(F293="",COUNT(AI293:AV293)<2),"",LOOKUP(2,1/(AI293:AV293<>""),AI293:AV293)-MIN(AI293:AV293)) | IF(OR(AD293="",AC293="Not started",AC293=""),"",IFERROR(AD293-IF(VLOOKUP(AC293,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC293,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F293="","",IF(OR(AA293="Cancelled",AC293="Cancelled"),"Cancelled",IF(OR(AC293="Completed / Handover",Y293<>"",Z293>=100),"Completed — on track",IF(O293="Not awarded",IF(U293="",IF(X293="","No planned date",IF(TODAY()>X293,"Behind — past planned date",IF(X293-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U293,"Behind — award date passed",IF(U293-TODAY()<=30,"At risk — close to off track","On track"))),IF(X293="","No planned date",IF(AND(TODAY()>X293,OR(Z293="",Z293<100)),"Behind — past end date",IF(AND(T293<>"",X293<>"",Z293<>"",(Z293<100),((TODAY()-T293)/MAX(X293-T293,1)*100)-Z293>15),"Behind — progress lag",IF(AND(X293-TODAY()<=30,X293-TODAY()>=0,OR(Z293="",Z293<90)),"At risk — close to off track","On track")))))))) | IF(OR(F293="",AC293="Completed / Handover",AC293="Cancelled"),"",IF(O293="Not awarded",IF(U293<>"",U293-TODAY(),IF(X293="","",X293-TODAY())),IF(X293="","",X293-TODAY()))) | [14 empty] | IF(OR(F293="",AJ293=""),"",IF(COUNT(AI293:AI293)=0,"",AJ293-LOOKUP(2,1/(AI293:AI293<>""),AI293:AI293))) | IF(OR(F293="",AK293=""),"",IF(COUNT(AI293:AJ293)=0,"",AK293-LOOKUP(2,1/(AI293:AJ293<>""),AI293:AJ293))) | IF(OR(F293="",AL293=""),"",IF(COUNT(AI293:AK293)=0,"",AL293-LOOKUP(2,1/(AI293:AK293<>""),AI293:AK293))) | IF(OR(F293="",AM293=""),"",IF(COUNT(AI293:AL293)=0,"",AM293-LOOKUP(2,1/(AI293:AL293<>""),AI293:AL293))) | IF(OR(F293="",AN293=""),"",IF(COUNT(AI293:AM293)=0,"",AN293-LOOKUP(2,1/(AI293:AM293<>""),AI293:AM293))) | IF(OR(F293="",AO293=""),"",IF(COUNT(AI293:AN293)=0,"",AO293-LOOKUP(2,1/(AI293:AN293<>""),AI293:AN293))) | IF(OR(F293="",AP293=""),"",IF(COUNT(AI293:AO293)=0,"",AP293-LOOKUP(2,1/(AI293:AO293<>""),AI293:AO293))) | IF(OR(F293="",AQ293=""),"",IF(COUNT(AI293:AP293)=0,"",AQ293-LOOKUP(2,1/(AI293:AP293<>""),AI293:AP293))) | IF(OR(F293="",AR293=""),"",IF(COUNT(AI293:AQ293)=0,"",AR293-LOOKUP(2,1/(AI293:AQ293<>""),AI293:AQ293))) | IF(OR(F293="",AS293=""),"",IF(COUNT(AI293:AR293)=0,"",AS293-LOOKUP(2,1/(AI293:AR293<>""),AI293:AR293))) | IF(OR(F293="",AT293=""),"",IF(COUNT(AI293:AS293)=0,"",AT293-LOOKUP(2,1/(AI293:AS293<>""),AI293:AS293))) | IF(OR(F293="",AU293=""),"",IF(COUNT(AI293:AT293)=0,"",AU293-LOOKUP(2,1/(AI293:AT293<>""),AI293:AT293))) | IF(OR(F293="",AV293=""),"",IF(COUNT(AI293:AU293)=0,"",AV293-LOOKUP(2,1/(AI293:AU293<>""),AI293:AU293))) | IF(J293="","All_Provinces",IFERROR(VLOOKUP(J293,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K293="","All_Districts",IFERROR(VLOOKUP(K293,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F294="","",ROW()-3) | [18 empty] | IF(AQ294="","",AQ294) |  |  |  | IF(W294<>"",W294,IF(OR(T294="",V294=""),"",EDATE(T294,V294))) |  |  |  |  | IF(F294="","",IF(COUNT(AI294:AV294)=0,IF(AA294="","Not started",AA294),SUBSTITUTE(LOOKUP(2,1/(AI294:AV294<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F294="",COUNT(AI294:AV294)=0),"",TODAY()-LOOKUP(2,1/(AI294:AV294<>""),AI294:AV294)) | IF(OR(F294="",COUNT(AI294:AV294)<2),"",LOOKUP(2,1/(AI294:AV294<>""),AI294:AV294)-MIN(AI294:AV294)) | IF(OR(AD294="",AC294="Not started",AC294=""),"",IFERROR(AD294-IF(VLOOKUP(AC294,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC294,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F294="","",IF(OR(AA294="Cancelled",AC294="Cancelled"),"Cancelled",IF(OR(AC294="Completed / Handover",Y294<>"",Z294>=100),"Completed — on track",IF(O294="Not awarded",IF(U294="",IF(X294="","No planned date",IF(TODAY()>X294,"Behind — past planned date",IF(X294-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U294,"Behind — award date passed",IF(U294-TODAY()<=30,"At risk — close to off track","On track"))),IF(X294="","No planned date",IF(AND(TODAY()>X294,OR(Z294="",Z294<100)),"Behind — past end date",IF(AND(T294<>"",X294<>"",Z294<>"",(Z294<100),((TODAY()-T294)/MAX(X294-T294,1)*100)-Z294>15),"Behind — progress lag",IF(AND(X294-TODAY()<=30,X294-TODAY()>=0,OR(Z294="",Z294<90)),"At risk — close to off track","On track")))))))) | IF(OR(F294="",AC294="Completed / Handover",AC294="Cancelled"),"",IF(O294="Not awarded",IF(U294<>"",U294-TODAY(),IF(X294="","",X294-TODAY())),IF(X294="","",X294-TODAY()))) | [14 empty] | IF(OR(F294="",AJ294=""),"",IF(COUNT(AI294:AI294)=0,"",AJ294-LOOKUP(2,1/(AI294:AI294<>""),AI294:AI294))) | IF(OR(F294="",AK294=""),"",IF(COUNT(AI294:AJ294)=0,"",AK294-LOOKUP(2,1/(AI294:AJ294<>""),AI294:AJ294))) | IF(OR(F294="",AL294=""),"",IF(COUNT(AI294:AK294)=0,"",AL294-LOOKUP(2,1/(AI294:AK294<>""),AI294:AK294))) | IF(OR(F294="",AM294=""),"",IF(COUNT(AI294:AL294)=0,"",AM294-LOOKUP(2,1/(AI294:AL294<>""),AI294:AL294))) | IF(OR(F294="",AN294=""),"",IF(COUNT(AI294:AM294)=0,"",AN294-LOOKUP(2,1/(AI294:AM294<>""),AI294:AM294))) | IF(OR(F294="",AO294=""),"",IF(COUNT(AI294:AN294)=0,"",AO294-LOOKUP(2,1/(AI294:AN294<>""),AI294:AN294))) | IF(OR(F294="",AP294=""),"",IF(COUNT(AI294:AO294)=0,"",AP294-LOOKUP(2,1/(AI294:AO294<>""),AI294:AO294))) | IF(OR(F294="",AQ294=""),"",IF(COUNT(AI294:AP294)=0,"",AQ294-LOOKUP(2,1/(AI294:AP294<>""),AI294:AP294))) | IF(OR(F294="",AR294=""),"",IF(COUNT(AI294:AQ294)=0,"",AR294-LOOKUP(2,1/(AI294:AQ294<>""),AI294:AQ294))) | IF(OR(F294="",AS294=""),"",IF(COUNT(AI294:AR294)=0,"",AS294-LOOKUP(2,1/(AI294:AR294<>""),AI294:AR294))) | IF(OR(F294="",AT294=""),"",IF(COUNT(AI294:AS294)=0,"",AT294-LOOKUP(2,1/(AI294:AS294<>""),AI294:AS294))) | IF(OR(F294="",AU294=""),"",IF(COUNT(AI294:AT294)=0,"",AU294-LOOKUP(2,1/(AI294:AT294<>""),AI294:AT294))) | IF(OR(F294="",AV294=""),"",IF(COUNT(AI294:AU294)=0,"",AV294-LOOKUP(2,1/(AI294:AU294<>""),AI294:AU294))) | IF(J294="","All_Provinces",IFERROR(VLOOKUP(J294,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K294="","All_Districts",IFERROR(VLOOKUP(K294,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F295="","",ROW()-3) | [18 empty] | IF(AQ295="","",AQ295) |  |  |  | IF(W295<>"",W295,IF(OR(T295="",V295=""),"",EDATE(T295,V295))) |  |  |  |  | IF(F295="","",IF(COUNT(AI295:AV295)=0,IF(AA295="","Not started",AA295),SUBSTITUTE(LOOKUP(2,1/(AI295:AV295<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F295="",COUNT(AI295:AV295)=0),"",TODAY()-LOOKUP(2,1/(AI295:AV295<>""),AI295:AV295)) | IF(OR(F295="",COUNT(AI295:AV295)<2),"",LOOKUP(2,1/(AI295:AV295<>""),AI295:AV295)-MIN(AI295:AV295)) | IF(OR(AD295="",AC295="Not started",AC295=""),"",IFERROR(AD295-IF(VLOOKUP(AC295,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC295,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F295="","",IF(OR(AA295="Cancelled",AC295="Cancelled"),"Cancelled",IF(OR(AC295="Completed / Handover",Y295<>"",Z295>=100),"Completed — on track",IF(O295="Not awarded",IF(U295="",IF(X295="","No planned date",IF(TODAY()>X295,"Behind — past planned date",IF(X295-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U295,"Behind — award date passed",IF(U295-TODAY()<=30,"At risk — close to off track","On track"))),IF(X295="","No planned date",IF(AND(TODAY()>X295,OR(Z295="",Z295<100)),"Behind — past end date",IF(AND(T295<>"",X295<>"",Z295<>"",(Z295<100),((TODAY()-T295)/MAX(X295-T295,1)*100)-Z295>15),"Behind — progress lag",IF(AND(X295-TODAY()<=30,X295-TODAY()>=0,OR(Z295="",Z295<90)),"At risk — close to off track","On track")))))))) | IF(OR(F295="",AC295="Completed / Handover",AC295="Cancelled"),"",IF(O295="Not awarded",IF(U295<>"",U295-TODAY(),IF(X295="","",X295-TODAY())),IF(X295="","",X295-TODAY()))) | [14 empty] | IF(OR(F295="",AJ295=""),"",IF(COUNT(AI295:AI295)=0,"",AJ295-LOOKUP(2,1/(AI295:AI295<>""),AI295:AI295))) | IF(OR(F295="",AK295=""),"",IF(COUNT(AI295:AJ295)=0,"",AK295-LOOKUP(2,1/(AI295:AJ295<>""),AI295:AJ295))) | IF(OR(F295="",AL295=""),"",IF(COUNT(AI295:AK295)=0,"",AL295-LOOKUP(2,1/(AI295:AK295<>""),AI295:AK295))) | IF(OR(F295="",AM295=""),"",IF(COUNT(AI295:AL295)=0,"",AM295-LOOKUP(2,1/(AI295:AL295<>""),AI295:AL295))) | IF(OR(F295="",AN295=""),"",IF(COUNT(AI295:AM295)=0,"",AN295-LOOKUP(2,1/(AI295:AM295<>""),AI295:AM295))) | IF(OR(F295="",AO295=""),"",IF(COUNT(AI295:AN295)=0,"",AO295-LOOKUP(2,1/(AI295:AN295<>""),AI295:AN295))) | IF(OR(F295="",AP295=""),"",IF(COUNT(AI295:AO295)=0,"",AP295-LOOKUP(2,1/(AI295:AO295<>""),AI295:AO295))) | IF(OR(F295="",AQ295=""),"",IF(COUNT(AI295:AP295)=0,"",AQ295-LOOKUP(2,1/(AI295:AP295<>""),AI295:AP295))) | IF(OR(F295="",AR295=""),"",IF(COUNT(AI295:AQ295)=0,"",AR295-LOOKUP(2,1/(AI295:AQ295<>""),AI295:AQ295))) | IF(OR(F295="",AS295=""),"",IF(COUNT(AI295:AR295)=0,"",AS295-LOOKUP(2,1/(AI295:AR295<>""),AI295:AR295))) | IF(OR(F295="",AT295=""),"",IF(COUNT(AI295:AS295)=0,"",AT295-LOOKUP(2,1/(AI295:AS295<>""),AI295:AS295))) | IF(OR(F295="",AU295=""),"",IF(COUNT(AI295:AT295)=0,"",AU295-LOOKUP(2,1/(AI295:AT295<>""),AI295:AT295))) | IF(OR(F295="",AV295=""),"",IF(COUNT(AI295:AU295)=0,"",AV295-LOOKUP(2,1/(AI295:AU295<>""),AI295:AU295))) | IF(J295="","All_Provinces",IFERROR(VLOOKUP(J295,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K295="","All_Districts",IFERROR(VLOOKUP(K295,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F296="","",ROW()-3) | [18 empty] | IF(AQ296="","",AQ296) |  |  |  | IF(W296<>"",W296,IF(OR(T296="",V296=""),"",EDATE(T296,V296))) |  |  |  |  | IF(F296="","",IF(COUNT(AI296:AV296)=0,IF(AA296="","Not started",AA296),SUBSTITUTE(LOOKUP(2,1/(AI296:AV296<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F296="",COUNT(AI296:AV296)=0),"",TODAY()-LOOKUP(2,1/(AI296:AV296<>""),AI296:AV296)) | IF(OR(F296="",COUNT(AI296:AV296)<2),"",LOOKUP(2,1/(AI296:AV296<>""),AI296:AV296)-MIN(AI296:AV296)) | IF(OR(AD296="",AC296="Not started",AC296=""),"",IFERROR(AD296-IF(VLOOKUP(AC296,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC296,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F296="","",IF(OR(AA296="Cancelled",AC296="Cancelled"),"Cancelled",IF(OR(AC296="Completed / Handover",Y296<>"",Z296>=100),"Completed — on track",IF(O296="Not awarded",IF(U296="",IF(X296="","No planned date",IF(TODAY()>X296,"Behind — past planned date",IF(X296-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U296,"Behind — award date passed",IF(U296-TODAY()<=30,"At risk — close to off track","On track"))),IF(X296="","No planned date",IF(AND(TODAY()>X296,OR(Z296="",Z296<100)),"Behind — past end date",IF(AND(T296<>"",X296<>"",Z296<>"",(Z296<100),((TODAY()-T296)/MAX(X296-T296,1)*100)-Z296>15),"Behind — progress lag",IF(AND(X296-TODAY()<=30,X296-TODAY()>=0,OR(Z296="",Z296<90)),"At risk — close to off track","On track")))))))) | IF(OR(F296="",AC296="Completed / Handover",AC296="Cancelled"),"",IF(O296="Not awarded",IF(U296<>"",U296-TODAY(),IF(X296="","",X296-TODAY())),IF(X296="","",X296-TODAY()))) | [14 empty] | IF(OR(F296="",AJ296=""),"",IF(COUNT(AI296:AI296)=0,"",AJ296-LOOKUP(2,1/(AI296:AI296<>""),AI296:AI296))) | IF(OR(F296="",AK296=""),"",IF(COUNT(AI296:AJ296)=0,"",AK296-LOOKUP(2,1/(AI296:AJ296<>""),AI296:AJ296))) | IF(OR(F296="",AL296=""),"",IF(COUNT(AI296:AK296)=0,"",AL296-LOOKUP(2,1/(AI296:AK296<>""),AI296:AK296))) | IF(OR(F296="",AM296=""),"",IF(COUNT(AI296:AL296)=0,"",AM296-LOOKUP(2,1/(AI296:AL296<>""),AI296:AL296))) | IF(OR(F296="",AN296=""),"",IF(COUNT(AI296:AM296)=0,"",AN296-LOOKUP(2,1/(AI296:AM296<>""),AI296:AM296))) | IF(OR(F296="",AO296=""),"",IF(COUNT(AI296:AN296)=0,"",AO296-LOOKUP(2,1/(AI296:AN296<>""),AI296:AN296))) | IF(OR(F296="",AP296=""),"",IF(COUNT(AI296:AO296)=0,"",AP296-LOOKUP(2,1/(AI296:AO296<>""),AI296:AO296))) | IF(OR(F296="",AQ296=""),"",IF(COUNT(AI296:AP296)=0,"",AQ296-LOOKUP(2,1/(AI296:AP296<>""),AI296:AP296))) | IF(OR(F296="",AR296=""),"",IF(COUNT(AI296:AQ296)=0,"",AR296-LOOKUP(2,1/(AI296:AQ296<>""),AI296:AQ296))) | IF(OR(F296="",AS296=""),"",IF(COUNT(AI296:AR296)=0,"",AS296-LOOKUP(2,1/(AI296:AR296<>""),AI296:AR296))) | IF(OR(F296="",AT296=""),"",IF(COUNT(AI296:AS296)=0,"",AT296-LOOKUP(2,1/(AI296:AS296<>""),AI296:AS296))) | IF(OR(F296="",AU296=""),"",IF(COUNT(AI296:AT296)=0,"",AU296-LOOKUP(2,1/(AI296:AT296<>""),AI296:AT296))) | IF(OR(F296="",AV296=""),"",IF(COUNT(AI296:AU296)=0,"",AV296-LOOKUP(2,1/(AI296:AU296<>""),AI296:AU296))) | IF(J296="","All_Provinces",IFERROR(VLOOKUP(J296,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K296="","All_Districts",IFERROR(VLOOKUP(K296,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F297="","",ROW()-3) | [18 empty] | IF(AQ297="","",AQ297) |  |  |  | IF(W297<>"",W297,IF(OR(T297="",V297=""),"",EDATE(T297,V297))) |  |  |  |  | IF(F297="","",IF(COUNT(AI297:AV297)=0,IF(AA297="","Not started",AA297),SUBSTITUTE(LOOKUP(2,1/(AI297:AV297<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F297="",COUNT(AI297:AV297)=0),"",TODAY()-LOOKUP(2,1/(AI297:AV297<>""),AI297:AV297)) | IF(OR(F297="",COUNT(AI297:AV297)<2),"",LOOKUP(2,1/(AI297:AV297<>""),AI297:AV297)-MIN(AI297:AV297)) | IF(OR(AD297="",AC297="Not started",AC297=""),"",IFERROR(AD297-IF(VLOOKUP(AC297,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC297,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F297="","",IF(OR(AA297="Cancelled",AC297="Cancelled"),"Cancelled",IF(OR(AC297="Completed / Handover",Y297<>"",Z297>=100),"Completed — on track",IF(O297="Not awarded",IF(U297="",IF(X297="","No planned date",IF(TODAY()>X297,"Behind — past planned date",IF(X297-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U297,"Behind — award date passed",IF(U297-TODAY()<=30,"At risk — close to off track","On track"))),IF(X297="","No planned date",IF(AND(TODAY()>X297,OR(Z297="",Z297<100)),"Behind — past end date",IF(AND(T297<>"",X297<>"",Z297<>"",(Z297<100),((TODAY()-T297)/MAX(X297-T297,1)*100)-Z297>15),"Behind — progress lag",IF(AND(X297-TODAY()<=30,X297-TODAY()>=0,OR(Z297="",Z297<90)),"At risk — close to off track","On track")))))))) | IF(OR(F297="",AC297="Completed / Handover",AC297="Cancelled"),"",IF(O297="Not awarded",IF(U297<>"",U297-TODAY(),IF(X297="","",X297-TODAY())),IF(X297="","",X297-TODAY()))) | [14 empty] | IF(OR(F297="",AJ297=""),"",IF(COUNT(AI297:AI297)=0,"",AJ297-LOOKUP(2,1/(AI297:AI297<>""),AI297:AI297))) | IF(OR(F297="",AK297=""),"",IF(COUNT(AI297:AJ297)=0,"",AK297-LOOKUP(2,1/(AI297:AJ297<>""),AI297:AJ297))) | IF(OR(F297="",AL297=""),"",IF(COUNT(AI297:AK297)=0,"",AL297-LOOKUP(2,1/(AI297:AK297<>""),AI297:AK297))) | IF(OR(F297="",AM297=""),"",IF(COUNT(AI297:AL297)=0,"",AM297-LOOKUP(2,1/(AI297:AL297<>""),AI297:AL297))) | IF(OR(F297="",AN297=""),"",IF(COUNT(AI297:AM297)=0,"",AN297-LOOKUP(2,1/(AI297:AM297<>""),AI297:AM297))) | IF(OR(F297="",AO297=""),"",IF(COUNT(AI297:AN297)=0,"",AO297-LOOKUP(2,1/(AI297:AN297<>""),AI297:AN297))) | IF(OR(F297="",AP297=""),"",IF(COUNT(AI297:AO297)=0,"",AP297-LOOKUP(2,1/(AI297:AO297<>""),AI297:AO297))) | IF(OR(F297="",AQ297=""),"",IF(COUNT(AI297:AP297)=0,"",AQ297-LOOKUP(2,1/(AI297:AP297<>""),AI297:AP297))) | IF(OR(F297="",AR297=""),"",IF(COUNT(AI297:AQ297)=0,"",AR297-LOOKUP(2,1/(AI297:AQ297<>""),AI297:AQ297))) | IF(OR(F297="",AS297=""),"",IF(COUNT(AI297:AR297)=0,"",AS297-LOOKUP(2,1/(AI297:AR297<>""),AI297:AR297))) | IF(OR(F297="",AT297=""),"",IF(COUNT(AI297:AS297)=0,"",AT297-LOOKUP(2,1/(AI297:AS297<>""),AI297:AS297))) | IF(OR(F297="",AU297=""),"",IF(COUNT(AI297:AT297)=0,"",AU297-LOOKUP(2,1/(AI297:AT297<>""),AI297:AT297))) | IF(OR(F297="",AV297=""),"",IF(COUNT(AI297:AU297)=0,"",AV297-LOOKUP(2,1/(AI297:AU297<>""),AI297:AU297))) | IF(J297="","All_Provinces",IFERROR(VLOOKUP(J297,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K297="","All_Districts",IFERROR(VLOOKUP(K297,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F298="","",ROW()-3) | [18 empty] | IF(AQ298="","",AQ298) |  |  |  | IF(W298<>"",W298,IF(OR(T298="",V298=""),"",EDATE(T298,V298))) |  |  |  |  | IF(F298="","",IF(COUNT(AI298:AV298)=0,IF(AA298="","Not started",AA298),SUBSTITUTE(LOOKUP(2,1/(AI298:AV298<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F298="",COUNT(AI298:AV298)=0),"",TODAY()-LOOKUP(2,1/(AI298:AV298<>""),AI298:AV298)) | IF(OR(F298="",COUNT(AI298:AV298)<2),"",LOOKUP(2,1/(AI298:AV298<>""),AI298:AV298)-MIN(AI298:AV298)) | IF(OR(AD298="",AC298="Not started",AC298=""),"",IFERROR(AD298-IF(VLOOKUP(AC298,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC298,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F298="","",IF(OR(AA298="Cancelled",AC298="Cancelled"),"Cancelled",IF(OR(AC298="Completed / Handover",Y298<>"",Z298>=100),"Completed — on track",IF(O298="Not awarded",IF(U298="",IF(X298="","No planned date",IF(TODAY()>X298,"Behind — past planned date",IF(X298-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U298,"Behind — award date passed",IF(U298-TODAY()<=30,"At risk — close to off track","On track"))),IF(X298="","No planned date",IF(AND(TODAY()>X298,OR(Z298="",Z298<100)),"Behind — past end date",IF(AND(T298<>"",X298<>"",Z298<>"",(Z298<100),((TODAY()-T298)/MAX(X298-T298,1)*100)-Z298>15),"Behind — progress lag",IF(AND(X298-TODAY()<=30,X298-TODAY()>=0,OR(Z298="",Z298<90)),"At risk — close to off track","On track")))))))) | IF(OR(F298="",AC298="Completed / Handover",AC298="Cancelled"),"",IF(O298="Not awarded",IF(U298<>"",U298-TODAY(),IF(X298="","",X298-TODAY())),IF(X298="","",X298-TODAY()))) | [14 empty] | IF(OR(F298="",AJ298=""),"",IF(COUNT(AI298:AI298)=0,"",AJ298-LOOKUP(2,1/(AI298:AI298<>""),AI298:AI298))) | IF(OR(F298="",AK298=""),"",IF(COUNT(AI298:AJ298)=0,"",AK298-LOOKUP(2,1/(AI298:AJ298<>""),AI298:AJ298))) | IF(OR(F298="",AL298=""),"",IF(COUNT(AI298:AK298)=0,"",AL298-LOOKUP(2,1/(AI298:AK298<>""),AI298:AK298))) | IF(OR(F298="",AM298=""),"",IF(COUNT(AI298:AL298)=0,"",AM298-LOOKUP(2,1/(AI298:AL298<>""),AI298:AL298))) | IF(OR(F298="",AN298=""),"",IF(COUNT(AI298:AM298)=0,"",AN298-LOOKUP(2,1/(AI298:AM298<>""),AI298:AM298))) | IF(OR(F298="",AO298=""),"",IF(COUNT(AI298:AN298)=0,"",AO298-LOOKUP(2,1/(AI298:AN298<>""),AI298:AN298))) | IF(OR(F298="",AP298=""),"",IF(COUNT(AI298:AO298)=0,"",AP298-LOOKUP(2,1/(AI298:AO298<>""),AI298:AO298))) | IF(OR(F298="",AQ298=""),"",IF(COUNT(AI298:AP298)=0,"",AQ298-LOOKUP(2,1/(AI298:AP298<>""),AI298:AP298))) | IF(OR(F298="",AR298=""),"",IF(COUNT(AI298:AQ298)=0,"",AR298-LOOKUP(2,1/(AI298:AQ298<>""),AI298:AQ298))) | IF(OR(F298="",AS298=""),"",IF(COUNT(AI298:AR298)=0,"",AS298-LOOKUP(2,1/(AI298:AR298<>""),AI298:AR298))) | IF(OR(F298="",AT298=""),"",IF(COUNT(AI298:AS298)=0,"",AT298-LOOKUP(2,1/(AI298:AS298<>""),AI298:AS298))) | IF(OR(F298="",AU298=""),"",IF(COUNT(AI298:AT298)=0,"",AU298-LOOKUP(2,1/(AI298:AT298<>""),AI298:AT298))) | IF(OR(F298="",AV298=""),"",IF(COUNT(AI298:AU298)=0,"",AV298-LOOKUP(2,1/(AI298:AU298<>""),AI298:AU298))) | IF(J298="","All_Provinces",IFERROR(VLOOKUP(J298,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K298="","All_Districts",IFERROR(VLOOKUP(K298,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F299="","",ROW()-3) | [18 empty] | IF(AQ299="","",AQ299) |  |  |  | IF(W299<>"",W299,IF(OR(T299="",V299=""),"",EDATE(T299,V299))) |  |  |  |  | IF(F299="","",IF(COUNT(AI299:AV299)=0,IF(AA299="","Not started",AA299),SUBSTITUTE(LOOKUP(2,1/(AI299:AV299<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F299="",COUNT(AI299:AV299)=0),"",TODAY()-LOOKUP(2,1/(AI299:AV299<>""),AI299:AV299)) | IF(OR(F299="",COUNT(AI299:AV299)<2),"",LOOKUP(2,1/(AI299:AV299<>""),AI299:AV299)-MIN(AI299:AV299)) | IF(OR(AD299="",AC299="Not started",AC299=""),"",IFERROR(AD299-IF(VLOOKUP(AC299,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC299,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F299="","",IF(OR(AA299="Cancelled",AC299="Cancelled"),"Cancelled",IF(OR(AC299="Completed / Handover",Y299<>"",Z299>=100),"Completed — on track",IF(O299="Not awarded",IF(U299="",IF(X299="","No planned date",IF(TODAY()>X299,"Behind — past planned date",IF(X299-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U299,"Behind — award date passed",IF(U299-TODAY()<=30,"At risk — close to off track","On track"))),IF(X299="","No planned date",IF(AND(TODAY()>X299,OR(Z299="",Z299<100)),"Behind — past end date",IF(AND(T299<>"",X299<>"",Z299<>"",(Z299<100),((TODAY()-T299)/MAX(X299-T299,1)*100)-Z299>15),"Behind — progress lag",IF(AND(X299-TODAY()<=30,X299-TODAY()>=0,OR(Z299="",Z299<90)),"At risk — close to off track","On track")))))))) | IF(OR(F299="",AC299="Completed / Handover",AC299="Cancelled"),"",IF(O299="Not awarded",IF(U299<>"",U299-TODAY(),IF(X299="","",X299-TODAY())),IF(X299="","",X299-TODAY()))) | [14 empty] | IF(OR(F299="",AJ299=""),"",IF(COUNT(AI299:AI299)=0,"",AJ299-LOOKUP(2,1/(AI299:AI299<>""),AI299:AI299))) | IF(OR(F299="",AK299=""),"",IF(COUNT(AI299:AJ299)=0,"",AK299-LOOKUP(2,1/(AI299:AJ299<>""),AI299:AJ299))) | IF(OR(F299="",AL299=""),"",IF(COUNT(AI299:AK299)=0,"",AL299-LOOKUP(2,1/(AI299:AK299<>""),AI299:AK299))) | IF(OR(F299="",AM299=""),"",IF(COUNT(AI299:AL299)=0,"",AM299-LOOKUP(2,1/(AI299:AL299<>""),AI299:AL299))) | IF(OR(F299="",AN299=""),"",IF(COUNT(AI299:AM299)=0,"",AN299-LOOKUP(2,1/(AI299:AM299<>""),AI299:AM299))) | IF(OR(F299="",AO299=""),"",IF(COUNT(AI299:AN299)=0,"",AO299-LOOKUP(2,1/(AI299:AN299<>""),AI299:AN299))) | IF(OR(F299="",AP299=""),"",IF(COUNT(AI299:AO299)=0,"",AP299-LOOKUP(2,1/(AI299:AO299<>""),AI299:AO299))) | IF(OR(F299="",AQ299=""),"",IF(COUNT(AI299:AP299)=0,"",AQ299-LOOKUP(2,1/(AI299:AP299<>""),AI299:AP299))) | IF(OR(F299="",AR299=""),"",IF(COUNT(AI299:AQ299)=0,"",AR299-LOOKUP(2,1/(AI299:AQ299<>""),AI299:AQ299))) | IF(OR(F299="",AS299=""),"",IF(COUNT(AI299:AR299)=0,"",AS299-LOOKUP(2,1/(AI299:AR299<>""),AI299:AR299))) | IF(OR(F299="",AT299=""),"",IF(COUNT(AI299:AS299)=0,"",AT299-LOOKUP(2,1/(AI299:AS299<>""),AI299:AS299))) | IF(OR(F299="",AU299=""),"",IF(COUNT(AI299:AT299)=0,"",AU299-LOOKUP(2,1/(AI299:AT299<>""),AI299:AT299))) | IF(OR(F299="",AV299=""),"",IF(COUNT(AI299:AU299)=0,"",AV299-LOOKUP(2,1/(AI299:AU299<>""),AI299:AU299))) | IF(J299="","All_Provinces",IFERROR(VLOOKUP(J299,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K299="","All_Districts",IFERROR(VLOOKUP(K299,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F300="","",ROW()-3) | [18 empty] | IF(AQ300="","",AQ300) |  |  |  | IF(W300<>"",W300,IF(OR(T300="",V300=""),"",EDATE(T300,V300))) |  |  |  |  | IF(F300="","",IF(COUNT(AI300:AV300)=0,IF(AA300="","Not started",AA300),SUBSTITUTE(LOOKUP(2,1/(AI300:AV300<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F300="",COUNT(AI300:AV300)=0),"",TODAY()-LOOKUP(2,1/(AI300:AV300<>""),AI300:AV300)) | IF(OR(F300="",COUNT(AI300:AV300)<2),"",LOOKUP(2,1/(AI300:AV300<>""),AI300:AV300)-MIN(AI300:AV300)) | IF(OR(AD300="",AC300="Not started",AC300=""),"",IFERROR(AD300-IF(VLOOKUP(AC300,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC300,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F300="","",IF(OR(AA300="Cancelled",AC300="Cancelled"),"Cancelled",IF(OR(AC300="Completed / Handover",Y300<>"",Z300>=100),"Completed — on track",IF(O300="Not awarded",IF(U300="",IF(X300="","No planned date",IF(TODAY()>X300,"Behind — past planned date",IF(X300-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U300,"Behind — award date passed",IF(U300-TODAY()<=30,"At risk — close to off track","On track"))),IF(X300="","No planned date",IF(AND(TODAY()>X300,OR(Z300="",Z300<100)),"Behind — past end date",IF(AND(T300<>"",X300<>"",Z300<>"",(Z300<100),((TODAY()-T300)/MAX(X300-T300,1)*100)-Z300>15),"Behind — progress lag",IF(AND(X300-TODAY()<=30,X300-TODAY()>=0,OR(Z300="",Z300<90)),"At risk — close to off track","On track")))))))) | IF(OR(F300="",AC300="Completed / Handover",AC300="Cancelled"),"",IF(O300="Not awarded",IF(U300<>"",U300-TODAY(),IF(X300="","",X300-TODAY())),IF(X300="","",X300-TODAY()))) | [14 empty] | IF(OR(F300="",AJ300=""),"",IF(COUNT(AI300:AI300)=0,"",AJ300-LOOKUP(2,1/(AI300:AI300<>""),AI300:AI300))) | IF(OR(F300="",AK300=""),"",IF(COUNT(AI300:AJ300)=0,"",AK300-LOOKUP(2,1/(AI300:AJ300<>""),AI300:AJ300))) | IF(OR(F300="",AL300=""),"",IF(COUNT(AI300:AK300)=0,"",AL300-LOOKUP(2,1/(AI300:AK300<>""),AI300:AK300))) | IF(OR(F300="",AM300=""),"",IF(COUNT(AI300:AL300)=0,"",AM300-LOOKUP(2,1/(AI300:AL300<>""),AI300:AL300))) | IF(OR(F300="",AN300=""),"",IF(COUNT(AI300:AM300)=0,"",AN300-LOOKUP(2,1/(AI300:AM300<>""),AI300:AM300))) | IF(OR(F300="",AO300=""),"",IF(COUNT(AI300:AN300)=0,"",AO300-LOOKUP(2,1/(AI300:AN300<>""),AI300:AN300))) | IF(OR(F300="",AP300=""),"",IF(COUNT(AI300:AO300)=0,"",AP300-LOOKUP(2,1/(AI300:AO300<>""),AI300:AO300))) | IF(OR(F300="",AQ300=""),"",IF(COUNT(AI300:AP300)=0,"",AQ300-LOOKUP(2,1/(AI300:AP300<>""),AI300:AP300))) | IF(OR(F300="",AR300=""),"",IF(COUNT(AI300:AQ300)=0,"",AR300-LOOKUP(2,1/(AI300:AQ300<>""),AI300:AQ300))) | IF(OR(F300="",AS300=""),"",IF(COUNT(AI300:AR300)=0,"",AS300-LOOKUP(2,1/(AI300:AR300<>""),AI300:AR300))) | IF(OR(F300="",AT300=""),"",IF(COUNT(AI300:AS300)=0,"",AT300-LOOKUP(2,1/(AI300:AS300<>""),AI300:AS300))) | IF(OR(F300="",AU300=""),"",IF(COUNT(AI300:AT300)=0,"",AU300-LOOKUP(2,1/(AI300:AT300<>""),AI300:AT300))) | IF(OR(F300="",AV300=""),"",IF(COUNT(AI300:AU300)=0,"",AV300-LOOKUP(2,1/(AI300:AU300<>""),AI300:AU300))) | IF(J300="","All_Provinces",IFERROR(VLOOKUP(J300,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K300="","All_Districts",IFERROR(VLOOKUP(K300,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F301="","",ROW()-3) | [18 empty] | IF(AQ301="","",AQ301) |  |  |  | IF(W301<>"",W301,IF(OR(T301="",V301=""),"",EDATE(T301,V301))) |  |  |  |  | IF(F301="","",IF(COUNT(AI301:AV301)=0,IF(AA301="","Not started",AA301),SUBSTITUTE(LOOKUP(2,1/(AI301:AV301<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F301="",COUNT(AI301:AV301)=0),"",TODAY()-LOOKUP(2,1/(AI301:AV301<>""),AI301:AV301)) | IF(OR(F301="",COUNT(AI301:AV301)<2),"",LOOKUP(2,1/(AI301:AV301<>""),AI301:AV301)-MIN(AI301:AV301)) | IF(OR(AD301="",AC301="Not started",AC301=""),"",IFERROR(AD301-IF(VLOOKUP(AC301,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC301,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F301="","",IF(OR(AA301="Cancelled",AC301="Cancelled"),"Cancelled",IF(OR(AC301="Completed / Handover",Y301<>"",Z301>=100),"Completed — on track",IF(O301="Not awarded",IF(U301="",IF(X301="","No planned date",IF(TODAY()>X301,"Behind — past planned date",IF(X301-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U301,"Behind — award date passed",IF(U301-TODAY()<=30,"At risk — close to off track","On track"))),IF(X301="","No planned date",IF(AND(TODAY()>X301,OR(Z301="",Z301<100)),"Behind — past end date",IF(AND(T301<>"",X301<>"",Z301<>"",(Z301<100),((TODAY()-T301)/MAX(X301-T301,1)*100)-Z301>15),"Behind — progress lag",IF(AND(X301-TODAY()<=30,X301-TODAY()>=0,OR(Z301="",Z301<90)),"At risk — close to off track","On track")))))))) | IF(OR(F301="",AC301="Completed / Handover",AC301="Cancelled"),"",IF(O301="Not awarded",IF(U301<>"",U301-TODAY(),IF(X301="","",X301-TODAY())),IF(X301="","",X301-TODAY()))) | [14 empty] | IF(OR(F301="",AJ301=""),"",IF(COUNT(AI301:AI301)=0,"",AJ301-LOOKUP(2,1/(AI301:AI301<>""),AI301:AI301))) | IF(OR(F301="",AK301=""),"",IF(COUNT(AI301:AJ301)=0,"",AK301-LOOKUP(2,1/(AI301:AJ301<>""),AI301:AJ301))) | IF(OR(F301="",AL301=""),"",IF(COUNT(AI301:AK301)=0,"",AL301-LOOKUP(2,1/(AI301:AK301<>""),AI301:AK301))) | IF(OR(F301="",AM301=""),"",IF(COUNT(AI301:AL301)=0,"",AM301-LOOKUP(2,1/(AI301:AL301<>""),AI301:AL301))) | IF(OR(F301="",AN301=""),"",IF(COUNT(AI301:AM301)=0,"",AN301-LOOKUP(2,1/(AI301:AM301<>""),AI301:AM301))) | IF(OR(F301="",AO301=""),"",IF(COUNT(AI301:AN301)=0,"",AO301-LOOKUP(2,1/(AI301:AN301<>""),AI301:AN301))) | IF(OR(F301="",AP301=""),"",IF(COUNT(AI301:AO301)=0,"",AP301-LOOKUP(2,1/(AI301:AO301<>""),AI301:AO301))) | IF(OR(F301="",AQ301=""),"",IF(COUNT(AI301:AP301)=0,"",AQ301-LOOKUP(2,1/(AI301:AP301<>""),AI301:AP301))) | IF(OR(F301="",AR301=""),"",IF(COUNT(AI301:AQ301)=0,"",AR301-LOOKUP(2,1/(AI301:AQ301<>""),AI301:AQ301))) | IF(OR(F301="",AS301=""),"",IF(COUNT(AI301:AR301)=0,"",AS301-LOOKUP(2,1/(AI301:AR301<>""),AI301:AR301))) | IF(OR(F301="",AT301=""),"",IF(COUNT(AI301:AS301)=0,"",AT301-LOOKUP(2,1/(AI301:AS301<>""),AI301:AS301))) | IF(OR(F301="",AU301=""),"",IF(COUNT(AI301:AT301)=0,"",AU301-LOOKUP(2,1/(AI301:AT301<>""),AI301:AT301))) | IF(OR(F301="",AV301=""),"",IF(COUNT(AI301:AU301)=0,"",AV301-LOOKUP(2,1/(AI301:AU301<>""),AI301:AU301))) | IF(J301="","All_Provinces",IFERROR(VLOOKUP(J301,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K301="","All_Districts",IFERROR(VLOOKUP(K301,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F302="","",ROW()-3) | [18 empty] | IF(AQ302="","",AQ302) |  |  |  | IF(W302<>"",W302,IF(OR(T302="",V302=""),"",EDATE(T302,V302))) |  |  |  |  | IF(F302="","",IF(COUNT(AI302:AV302)=0,IF(AA302="","Not started",AA302),SUBSTITUTE(LOOKUP(2,1/(AI302:AV302<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F302="",COUNT(AI302:AV302)=0),"",TODAY()-LOOKUP(2,1/(AI302:AV302<>""),AI302:AV302)) | IF(OR(F302="",COUNT(AI302:AV302)<2),"",LOOKUP(2,1/(AI302:AV302<>""),AI302:AV302)-MIN(AI302:AV302)) | IF(OR(AD302="",AC302="Not started",AC302=""),"",IFERROR(AD302-IF(VLOOKUP(AC302,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC302,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F302="","",IF(OR(AA302="Cancelled",AC302="Cancelled"),"Cancelled",IF(OR(AC302="Completed / Handover",Y302<>"",Z302>=100),"Completed — on track",IF(O302="Not awarded",IF(U302="",IF(X302="","No planned date",IF(TODAY()>X302,"Behind — past planned date",IF(X302-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U302,"Behind — award date passed",IF(U302-TODAY()<=30,"At risk — close to off track","On track"))),IF(X302="","No planned date",IF(AND(TODAY()>X302,OR(Z302="",Z302<100)),"Behind — past end date",IF(AND(T302<>"",X302<>"",Z302<>"",(Z302<100),((TODAY()-T302)/MAX(X302-T302,1)*100)-Z302>15),"Behind — progress lag",IF(AND(X302-TODAY()<=30,X302-TODAY()>=0,OR(Z302="",Z302<90)),"At risk — close to off track","On track")))))))) | IF(OR(F302="",AC302="Completed / Handover",AC302="Cancelled"),"",IF(O302="Not awarded",IF(U302<>"",U302-TODAY(),IF(X302="","",X302-TODAY())),IF(X302="","",X302-TODAY()))) | [14 empty] | IF(OR(F302="",AJ302=""),"",IF(COUNT(AI302:AI302)=0,"",AJ302-LOOKUP(2,1/(AI302:AI302<>""),AI302:AI302))) | IF(OR(F302="",AK302=""),"",IF(COUNT(AI302:AJ302)=0,"",AK302-LOOKUP(2,1/(AI302:AJ302<>""),AI302:AJ302))) | IF(OR(F302="",AL302=""),"",IF(COUNT(AI302:AK302)=0,"",AL302-LOOKUP(2,1/(AI302:AK302<>""),AI302:AK302))) | IF(OR(F302="",AM302=""),"",IF(COUNT(AI302:AL302)=0,"",AM302-LOOKUP(2,1/(AI302:AL302<>""),AI302:AL302))) | IF(OR(F302="",AN302=""),"",IF(COUNT(AI302:AM302)=0,"",AN302-LOOKUP(2,1/(AI302:AM302<>""),AI302:AM302))) | IF(OR(F302="",AO302=""),"",IF(COUNT(AI302:AN302)=0,"",AO302-LOOKUP(2,1/(AI302:AN302<>""),AI302:AN302))) | IF(OR(F302="",AP302=""),"",IF(COUNT(AI302:AO302)=0,"",AP302-LOOKUP(2,1/(AI302:AO302<>""),AI302:AO302))) | IF(OR(F302="",AQ302=""),"",IF(COUNT(AI302:AP302)=0,"",AQ302-LOOKUP(2,1/(AI302:AP302<>""),AI302:AP302))) | IF(OR(F302="",AR302=""),"",IF(COUNT(AI302:AQ302)=0,"",AR302-LOOKUP(2,1/(AI302:AQ302<>""),AI302:AQ302))) | IF(OR(F302="",AS302=""),"",IF(COUNT(AI302:AR302)=0,"",AS302-LOOKUP(2,1/(AI302:AR302<>""),AI302:AR302))) | IF(OR(F302="",AT302=""),"",IF(COUNT(AI302:AS302)=0,"",AT302-LOOKUP(2,1/(AI302:AS302<>""),AI302:AS302))) | IF(OR(F302="",AU302=""),"",IF(COUNT(AI302:AT302)=0,"",AU302-LOOKUP(2,1/(AI302:AT302<>""),AI302:AT302))) | IF(OR(F302="",AV302=""),"",IF(COUNT(AI302:AU302)=0,"",AV302-LOOKUP(2,1/(AI302:AU302<>""),AI302:AU302))) | IF(J302="","All_Provinces",IFERROR(VLOOKUP(J302,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K302="","All_Districts",IFERROR(VLOOKUP(K302,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F303="","",ROW()-3) | [18 empty] | IF(AQ303="","",AQ303) |  |  |  | IF(W303<>"",W303,IF(OR(T303="",V303=""),"",EDATE(T303,V303))) |  |  |  |  | IF(F303="","",IF(COUNT(AI303:AV303)=0,IF(AA303="","Not started",AA303),SUBSTITUTE(LOOKUP(2,1/(AI303:AV303<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F303="",COUNT(AI303:AV303)=0),"",TODAY()-LOOKUP(2,1/(AI303:AV303<>""),AI303:AV303)) | IF(OR(F303="",COUNT(AI303:AV303)<2),"",LOOKUP(2,1/(AI303:AV303<>""),AI303:AV303)-MIN(AI303:AV303)) | IF(OR(AD303="",AC303="Not started",AC303=""),"",IFERROR(AD303-IF(VLOOKUP(AC303,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC303,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F303="","",IF(OR(AA303="Cancelled",AC303="Cancelled"),"Cancelled",IF(OR(AC303="Completed / Handover",Y303<>"",Z303>=100),"Completed — on track",IF(O303="Not awarded",IF(U303="",IF(X303="","No planned date",IF(TODAY()>X303,"Behind — past planned date",IF(X303-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U303,"Behind — award date passed",IF(U303-TODAY()<=30,"At risk — close to off track","On track"))),IF(X303="","No planned date",IF(AND(TODAY()>X303,OR(Z303="",Z303<100)),"Behind — past end date",IF(AND(T303<>"",X303<>"",Z303<>"",(Z303<100),((TODAY()-T303)/MAX(X303-T303,1)*100)-Z303>15),"Behind — progress lag",IF(AND(X303-TODAY()<=30,X303-TODAY()>=0,OR(Z303="",Z303<90)),"At risk — close to off track","On track")))))))) | IF(OR(F303="",AC303="Completed / Handover",AC303="Cancelled"),"",IF(O303="Not awarded",IF(U303<>"",U303-TODAY(),IF(X303="","",X303-TODAY())),IF(X303="","",X303-TODAY()))) | [14 empty] | IF(OR(F303="",AJ303=""),"",IF(COUNT(AI303:AI303)=0,"",AJ303-LOOKUP(2,1/(AI303:AI303<>""),AI303:AI303))) | IF(OR(F303="",AK303=""),"",IF(COUNT(AI303:AJ303)=0,"",AK303-LOOKUP(2,1/(AI303:AJ303<>""),AI303:AJ303))) | IF(OR(F303="",AL303=""),"",IF(COUNT(AI303:AK303)=0,"",AL303-LOOKUP(2,1/(AI303:AK303<>""),AI303:AK303))) | IF(OR(F303="",AM303=""),"",IF(COUNT(AI303:AL303)=0,"",AM303-LOOKUP(2,1/(AI303:AL303<>""),AI303:AL303))) | IF(OR(F303="",AN303=""),"",IF(COUNT(AI303:AM303)=0,"",AN303-LOOKUP(2,1/(AI303:AM303<>""),AI303:AM303))) | IF(OR(F303="",AO303=""),"",IF(COUNT(AI303:AN303)=0,"",AO303-LOOKUP(2,1/(AI303:AN303<>""),AI303:AN303))) | IF(OR(F303="",AP303=""),"",IF(COUNT(AI303:AO303)=0,"",AP303-LOOKUP(2,1/(AI303:AO303<>""),AI303:AO303))) | IF(OR(F303="",AQ303=""),"",IF(COUNT(AI303:AP303)=0,"",AQ303-LOOKUP(2,1/(AI303:AP303<>""),AI303:AP303))) | IF(OR(F303="",AR303=""),"",IF(COUNT(AI303:AQ303)=0,"",AR303-LOOKUP(2,1/(AI303:AQ303<>""),AI303:AQ303))) | IF(OR(F303="",AS303=""),"",IF(COUNT(AI303:AR303)=0,"",AS303-LOOKUP(2,1/(AI303:AR303<>""),AI303:AR303))) | IF(OR(F303="",AT303=""),"",IF(COUNT(AI303:AS303)=0,"",AT303-LOOKUP(2,1/(AI303:AS303<>""),AI303:AS303))) | IF(OR(F303="",AU303=""),"",IF(COUNT(AI303:AT303)=0,"",AU303-LOOKUP(2,1/(AI303:AT303<>""),AI303:AT303))) | IF(OR(F303="",AV303=""),"",IF(COUNT(AI303:AU303)=0,"",AV303-LOOKUP(2,1/(AI303:AU303<>""),AI303:AU303))) | IF(J303="","All_Provinces",IFERROR(VLOOKUP(J303,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K303="","All_Districts",IFERROR(VLOOKUP(K303,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F304="","",ROW()-3) | [18 empty] | IF(AQ304="","",AQ304) |  |  |  | IF(W304<>"",W304,IF(OR(T304="",V304=""),"",EDATE(T304,V304))) |  |  |  |  | IF(F304="","",IF(COUNT(AI304:AV304)=0,IF(AA304="","Not started",AA304),SUBSTITUTE(LOOKUP(2,1/(AI304:AV304<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F304="",COUNT(AI304:AV304)=0),"",TODAY()-LOOKUP(2,1/(AI304:AV304<>""),AI304:AV304)) | IF(OR(F304="",COUNT(AI304:AV304)<2),"",LOOKUP(2,1/(AI304:AV304<>""),AI304:AV304)-MIN(AI304:AV304)) | IF(OR(AD304="",AC304="Not started",AC304=""),"",IFERROR(AD304-IF(VLOOKUP(AC304,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC304,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F304="","",IF(OR(AA304="Cancelled",AC304="Cancelled"),"Cancelled",IF(OR(AC304="Completed / Handover",Y304<>"",Z304>=100),"Completed — on track",IF(O304="Not awarded",IF(U304="",IF(X304="","No planned date",IF(TODAY()>X304,"Behind — past planned date",IF(X304-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U304,"Behind — award date passed",IF(U304-TODAY()<=30,"At risk — close to off track","On track"))),IF(X304="","No planned date",IF(AND(TODAY()>X304,OR(Z304="",Z304<100)),"Behind — past end date",IF(AND(T304<>"",X304<>"",Z304<>"",(Z304<100),((TODAY()-T304)/MAX(X304-T304,1)*100)-Z304>15),"Behind — progress lag",IF(AND(X304-TODAY()<=30,X304-TODAY()>=0,OR(Z304="",Z304<90)),"At risk — close to off track","On track")))))))) | IF(OR(F304="",AC304="Completed / Handover",AC304="Cancelled"),"",IF(O304="Not awarded",IF(U304<>"",U304-TODAY(),IF(X304="","",X304-TODAY())),IF(X304="","",X304-TODAY()))) | [14 empty] | IF(OR(F304="",AJ304=""),"",IF(COUNT(AI304:AI304)=0,"",AJ304-LOOKUP(2,1/(AI304:AI304<>""),AI304:AI304))) | IF(OR(F304="",AK304=""),"",IF(COUNT(AI304:AJ304)=0,"",AK304-LOOKUP(2,1/(AI304:AJ304<>""),AI304:AJ304))) | IF(OR(F304="",AL304=""),"",IF(COUNT(AI304:AK304)=0,"",AL304-LOOKUP(2,1/(AI304:AK304<>""),AI304:AK304))) | IF(OR(F304="",AM304=""),"",IF(COUNT(AI304:AL304)=0,"",AM304-LOOKUP(2,1/(AI304:AL304<>""),AI304:AL304))) | IF(OR(F304="",AN304=""),"",IF(COUNT(AI304:AM304)=0,"",AN304-LOOKUP(2,1/(AI304:AM304<>""),AI304:AM304))) | IF(OR(F304="",AO304=""),"",IF(COUNT(AI304:AN304)=0,"",AO304-LOOKUP(2,1/(AI304:AN304<>""),AI304:AN304))) | IF(OR(F304="",AP304=""),"",IF(COUNT(AI304:AO304)=0,"",AP304-LOOKUP(2,1/(AI304:AO304<>""),AI304:AO304))) | IF(OR(F304="",AQ304=""),"",IF(COUNT(AI304:AP304)=0,"",AQ304-LOOKUP(2,1/(AI304:AP304<>""),AI304:AP304))) | IF(OR(F304="",AR304=""),"",IF(COUNT(AI304:AQ304)=0,"",AR304-LOOKUP(2,1/(AI304:AQ304<>""),AI304:AQ304))) | IF(OR(F304="",AS304=""),"",IF(COUNT(AI304:AR304)=0,"",AS304-LOOKUP(2,1/(AI304:AR304<>""),AI304:AR304))) | IF(OR(F304="",AT304=""),"",IF(COUNT(AI304:AS304)=0,"",AT304-LOOKUP(2,1/(AI304:AS304<>""),AI304:AS304))) | IF(OR(F304="",AU304=""),"",IF(COUNT(AI304:AT304)=0,"",AU304-LOOKUP(2,1/(AI304:AT304<>""),AI304:AT304))) | IF(OR(F304="",AV304=""),"",IF(COUNT(AI304:AU304)=0,"",AV304-LOOKUP(2,1/(AI304:AU304<>""),AI304:AU304))) | IF(J304="","All_Provinces",IFERROR(VLOOKUP(J304,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K304="","All_Districts",IFERROR(VLOOKUP(K304,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F305="","",ROW()-3) | [18 empty] | IF(AQ305="","",AQ305) |  |  |  | IF(W305<>"",W305,IF(OR(T305="",V305=""),"",EDATE(T305,V305))) |  |  |  |  | IF(F305="","",IF(COUNT(AI305:AV305)=0,IF(AA305="","Not started",AA305),SUBSTITUTE(LOOKUP(2,1/(AI305:AV305<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F305="",COUNT(AI305:AV305)=0),"",TODAY()-LOOKUP(2,1/(AI305:AV305<>""),AI305:AV305)) | IF(OR(F305="",COUNT(AI305:AV305)<2),"",LOOKUP(2,1/(AI305:AV305<>""),AI305:AV305)-MIN(AI305:AV305)) | IF(OR(AD305="",AC305="Not started",AC305=""),"",IFERROR(AD305-IF(VLOOKUP(AC305,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC305,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F305="","",IF(OR(AA305="Cancelled",AC305="Cancelled"),"Cancelled",IF(OR(AC305="Completed / Handover",Y305<>"",Z305>=100),"Completed — on track",IF(O305="Not awarded",IF(U305="",IF(X305="","No planned date",IF(TODAY()>X305,"Behind — past planned date",IF(X305-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U305,"Behind — award date passed",IF(U305-TODAY()<=30,"At risk — close to off track","On track"))),IF(X305="","No planned date",IF(AND(TODAY()>X305,OR(Z305="",Z305<100)),"Behind — past end date",IF(AND(T305<>"",X305<>"",Z305<>"",(Z305<100),((TODAY()-T305)/MAX(X305-T305,1)*100)-Z305>15),"Behind — progress lag",IF(AND(X305-TODAY()<=30,X305-TODAY()>=0,OR(Z305="",Z305<90)),"At risk — close to off track","On track")))))))) | IF(OR(F305="",AC305="Completed / Handover",AC305="Cancelled"),"",IF(O305="Not awarded",IF(U305<>"",U305-TODAY(),IF(X305="","",X305-TODAY())),IF(X305="","",X305-TODAY()))) | [14 empty] | IF(OR(F305="",AJ305=""),"",IF(COUNT(AI305:AI305)=0,"",AJ305-LOOKUP(2,1/(AI305:AI305<>""),AI305:AI305))) | IF(OR(F305="",AK305=""),"",IF(COUNT(AI305:AJ305)=0,"",AK305-LOOKUP(2,1/(AI305:AJ305<>""),AI305:AJ305))) | IF(OR(F305="",AL305=""),"",IF(COUNT(AI305:AK305)=0,"",AL305-LOOKUP(2,1/(AI305:AK305<>""),AI305:AK305))) | IF(OR(F305="",AM305=""),"",IF(COUNT(AI305:AL305)=0,"",AM305-LOOKUP(2,1/(AI305:AL305<>""),AI305:AL305))) | IF(OR(F305="",AN305=""),"",IF(COUNT(AI305:AM305)=0,"",AN305-LOOKUP(2,1/(AI305:AM305<>""),AI305:AM305))) | IF(OR(F305="",AO305=""),"",IF(COUNT(AI305:AN305)=0,"",AO305-LOOKUP(2,1/(AI305:AN305<>""),AI305:AN305))) | IF(OR(F305="",AP305=""),"",IF(COUNT(AI305:AO305)=0,"",AP305-LOOKUP(2,1/(AI305:AO305<>""),AI305:AO305))) | IF(OR(F305="",AQ305=""),"",IF(COUNT(AI305:AP305)=0,"",AQ305-LOOKUP(2,1/(AI305:AP305<>""),AI305:AP305))) | IF(OR(F305="",AR305=""),"",IF(COUNT(AI305:AQ305)=0,"",AR305-LOOKUP(2,1/(AI305:AQ305<>""),AI305:AQ305))) | IF(OR(F305="",AS305=""),"",IF(COUNT(AI305:AR305)=0,"",AS305-LOOKUP(2,1/(AI305:AR305<>""),AI305:AR305))) | IF(OR(F305="",AT305=""),"",IF(COUNT(AI305:AS305)=0,"",AT305-LOOKUP(2,1/(AI305:AS305<>""),AI305:AS305))) | IF(OR(F305="",AU305=""),"",IF(COUNT(AI305:AT305)=0,"",AU305-LOOKUP(2,1/(AI305:AT305<>""),AI305:AT305))) | IF(OR(F305="",AV305=""),"",IF(COUNT(AI305:AU305)=0,"",AV305-LOOKUP(2,1/(AI305:AU305<>""),AI305:AU305))) | IF(J305="","All_Provinces",IFERROR(VLOOKUP(J305,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K305="","All_Districts",IFERROR(VLOOKUP(K305,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F306="","",ROW()-3) | [18 empty] | IF(AQ306="","",AQ306) |  |  |  | IF(W306<>"",W306,IF(OR(T306="",V306=""),"",EDATE(T306,V306))) |  |  |  |  | IF(F306="","",IF(COUNT(AI306:AV306)=0,IF(AA306="","Not started",AA306),SUBSTITUTE(LOOKUP(2,1/(AI306:AV306<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F306="",COUNT(AI306:AV306)=0),"",TODAY()-LOOKUP(2,1/(AI306:AV306<>""),AI306:AV306)) | IF(OR(F306="",COUNT(AI306:AV306)<2),"",LOOKUP(2,1/(AI306:AV306<>""),AI306:AV306)-MIN(AI306:AV306)) | IF(OR(AD306="",AC306="Not started",AC306=""),"",IFERROR(AD306-IF(VLOOKUP(AC306,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC306,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F306="","",IF(OR(AA306="Cancelled",AC306="Cancelled"),"Cancelled",IF(OR(AC306="Completed / Handover",Y306<>"",Z306>=100),"Completed — on track",IF(O306="Not awarded",IF(U306="",IF(X306="","No planned date",IF(TODAY()>X306,"Behind — past planned date",IF(X306-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U306,"Behind — award date passed",IF(U306-TODAY()<=30,"At risk — close to off track","On track"))),IF(X306="","No planned date",IF(AND(TODAY()>X306,OR(Z306="",Z306<100)),"Behind — past end date",IF(AND(T306<>"",X306<>"",Z306<>"",(Z306<100),((TODAY()-T306)/MAX(X306-T306,1)*100)-Z306>15),"Behind — progress lag",IF(AND(X306-TODAY()<=30,X306-TODAY()>=0,OR(Z306="",Z306<90)),"At risk — close to off track","On track")))))))) | IF(OR(F306="",AC306="Completed / Handover",AC306="Cancelled"),"",IF(O306="Not awarded",IF(U306<>"",U306-TODAY(),IF(X306="","",X306-TODAY())),IF(X306="","",X306-TODAY()))) | [14 empty] | IF(OR(F306="",AJ306=""),"",IF(COUNT(AI306:AI306)=0,"",AJ306-LOOKUP(2,1/(AI306:AI306<>""),AI306:AI306))) | IF(OR(F306="",AK306=""),"",IF(COUNT(AI306:AJ306)=0,"",AK306-LOOKUP(2,1/(AI306:AJ306<>""),AI306:AJ306))) | IF(OR(F306="",AL306=""),"",IF(COUNT(AI306:AK306)=0,"",AL306-LOOKUP(2,1/(AI306:AK306<>""),AI306:AK306))) | IF(OR(F306="",AM306=""),"",IF(COUNT(AI306:AL306)=0,"",AM306-LOOKUP(2,1/(AI306:AL306<>""),AI306:AL306))) | IF(OR(F306="",AN306=""),"",IF(COUNT(AI306:AM306)=0,"",AN306-LOOKUP(2,1/(AI306:AM306<>""),AI306:AM306))) | IF(OR(F306="",AO306=""),"",IF(COUNT(AI306:AN306)=0,"",AO306-LOOKUP(2,1/(AI306:AN306<>""),AI306:AN306))) | IF(OR(F306="",AP306=""),"",IF(COUNT(AI306:AO306)=0,"",AP306-LOOKUP(2,1/(AI306:AO306<>""),AI306:AO306))) | IF(OR(F306="",AQ306=""),"",IF(COUNT(AI306:AP306)=0,"",AQ306-LOOKUP(2,1/(AI306:AP306<>""),AI306:AP306))) | IF(OR(F306="",AR306=""),"",IF(COUNT(AI306:AQ306)=0,"",AR306-LOOKUP(2,1/(AI306:AQ306<>""),AI306:AQ306))) | IF(OR(F306="",AS306=""),"",IF(COUNT(AI306:AR306)=0,"",AS306-LOOKUP(2,1/(AI306:AR306<>""),AI306:AR306))) | IF(OR(F306="",AT306=""),"",IF(COUNT(AI306:AS306)=0,"",AT306-LOOKUP(2,1/(AI306:AS306<>""),AI306:AS306))) | IF(OR(F306="",AU306=""),"",IF(COUNT(AI306:AT306)=0,"",AU306-LOOKUP(2,1/(AI306:AT306<>""),AI306:AT306))) | IF(OR(F306="",AV306=""),"",IF(COUNT(AI306:AU306)=0,"",AV306-LOOKUP(2,1/(AI306:AU306<>""),AI306:AU306))) | IF(J306="","All_Provinces",IFERROR(VLOOKUP(J306,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K306="","All_Districts",IFERROR(VLOOKUP(K306,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F307="","",ROW()-3) | [18 empty] | IF(AQ307="","",AQ307) |  |  |  | IF(W307<>"",W307,IF(OR(T307="",V307=""),"",EDATE(T307,V307))) |  |  |  |  | IF(F307="","",IF(COUNT(AI307:AV307)=0,IF(AA307="","Not started",AA307),SUBSTITUTE(LOOKUP(2,1/(AI307:AV307<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F307="",COUNT(AI307:AV307)=0),"",TODAY()-LOOKUP(2,1/(AI307:AV307<>""),AI307:AV307)) | IF(OR(F307="",COUNT(AI307:AV307)<2),"",LOOKUP(2,1/(AI307:AV307<>""),AI307:AV307)-MIN(AI307:AV307)) | IF(OR(AD307="",AC307="Not started",AC307=""),"",IFERROR(AD307-IF(VLOOKUP(AC307,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC307,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F307="","",IF(OR(AA307="Cancelled",AC307="Cancelled"),"Cancelled",IF(OR(AC307="Completed / Handover",Y307<>"",Z307>=100),"Completed — on track",IF(O307="Not awarded",IF(U307="",IF(X307="","No planned date",IF(TODAY()>X307,"Behind — past planned date",IF(X307-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U307,"Behind — award date passed",IF(U307-TODAY()<=30,"At risk — close to off track","On track"))),IF(X307="","No planned date",IF(AND(TODAY()>X307,OR(Z307="",Z307<100)),"Behind — past end date",IF(AND(T307<>"",X307<>"",Z307<>"",(Z307<100),((TODAY()-T307)/MAX(X307-T307,1)*100)-Z307>15),"Behind — progress lag",IF(AND(X307-TODAY()<=30,X307-TODAY()>=0,OR(Z307="",Z307<90)),"At risk — close to off track","On track")))))))) | IF(OR(F307="",AC307="Completed / Handover",AC307="Cancelled"),"",IF(O307="Not awarded",IF(U307<>"",U307-TODAY(),IF(X307="","",X307-TODAY())),IF(X307="","",X307-TODAY()))) | [14 empty] | IF(OR(F307="",AJ307=""),"",IF(COUNT(AI307:AI307)=0,"",AJ307-LOOKUP(2,1/(AI307:AI307<>""),AI307:AI307))) | IF(OR(F307="",AK307=""),"",IF(COUNT(AI307:AJ307)=0,"",AK307-LOOKUP(2,1/(AI307:AJ307<>""),AI307:AJ307))) | IF(OR(F307="",AL307=""),"",IF(COUNT(AI307:AK307)=0,"",AL307-LOOKUP(2,1/(AI307:AK307<>""),AI307:AK307))) | IF(OR(F307="",AM307=""),"",IF(COUNT(AI307:AL307)=0,"",AM307-LOOKUP(2,1/(AI307:AL307<>""),AI307:AL307))) | IF(OR(F307="",AN307=""),"",IF(COUNT(AI307:AM307)=0,"",AN307-LOOKUP(2,1/(AI307:AM307<>""),AI307:AM307))) | IF(OR(F307="",AO307=""),"",IF(COUNT(AI307:AN307)=0,"",AO307-LOOKUP(2,1/(AI307:AN307<>""),AI307:AN307))) | IF(OR(F307="",AP307=""),"",IF(COUNT(AI307:AO307)=0,"",AP307-LOOKUP(2,1/(AI307:AO307<>""),AI307:AO307))) | IF(OR(F307="",AQ307=""),"",IF(COUNT(AI307:AP307)=0,"",AQ307-LOOKUP(2,1/(AI307:AP307<>""),AI307:AP307))) | IF(OR(F307="",AR307=""),"",IF(COUNT(AI307:AQ307)=0,"",AR307-LOOKUP(2,1/(AI307:AQ307<>""),AI307:AQ307))) | IF(OR(F307="",AS307=""),"",IF(COUNT(AI307:AR307)=0,"",AS307-LOOKUP(2,1/(AI307:AR307<>""),AI307:AR307))) | IF(OR(F307="",AT307=""),"",IF(COUNT(AI307:AS307)=0,"",AT307-LOOKUP(2,1/(AI307:AS307<>""),AI307:AS307))) | IF(OR(F307="",AU307=""),"",IF(COUNT(AI307:AT307)=0,"",AU307-LOOKUP(2,1/(AI307:AT307<>""),AI307:AT307))) | IF(OR(F307="",AV307=""),"",IF(COUNT(AI307:AU307)=0,"",AV307-LOOKUP(2,1/(AI307:AU307<>""),AI307:AU307))) | IF(J307="","All_Provinces",IFERROR(VLOOKUP(J307,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K307="","All_Districts",IFERROR(VLOOKUP(K307,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F308="","",ROW()-3) | [18 empty] | IF(AQ308="","",AQ308) |  |  |  | IF(W308<>"",W308,IF(OR(T308="",V308=""),"",EDATE(T308,V308))) |  |  |  |  | IF(F308="","",IF(COUNT(AI308:AV308)=0,IF(AA308="","Not started",AA308),SUBSTITUTE(LOOKUP(2,1/(AI308:AV308<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F308="",COUNT(AI308:AV308)=0),"",TODAY()-LOOKUP(2,1/(AI308:AV308<>""),AI308:AV308)) | IF(OR(F308="",COUNT(AI308:AV308)<2),"",LOOKUP(2,1/(AI308:AV308<>""),AI308:AV308)-MIN(AI308:AV308)) | IF(OR(AD308="",AC308="Not started",AC308=""),"",IFERROR(AD308-IF(VLOOKUP(AC308,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC308,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F308="","",IF(OR(AA308="Cancelled",AC308="Cancelled"),"Cancelled",IF(OR(AC308="Completed / Handover",Y308<>"",Z308>=100),"Completed — on track",IF(O308="Not awarded",IF(U308="",IF(X308="","No planned date",IF(TODAY()>X308,"Behind — past planned date",IF(X308-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U308,"Behind — award date passed",IF(U308-TODAY()<=30,"At risk — close to off track","On track"))),IF(X308="","No planned date",IF(AND(TODAY()>X308,OR(Z308="",Z308<100)),"Behind — past end date",IF(AND(T308<>"",X308<>"",Z308<>"",(Z308<100),((TODAY()-T308)/MAX(X308-T308,1)*100)-Z308>15),"Behind — progress lag",IF(AND(X308-TODAY()<=30,X308-TODAY()>=0,OR(Z308="",Z308<90)),"At risk — close to off track","On track")))))))) | IF(OR(F308="",AC308="Completed / Handover",AC308="Cancelled"),"",IF(O308="Not awarded",IF(U308<>"",U308-TODAY(),IF(X308="","",X308-TODAY())),IF(X308="","",X308-TODAY()))) | [14 empty] | IF(OR(F308="",AJ308=""),"",IF(COUNT(AI308:AI308)=0,"",AJ308-LOOKUP(2,1/(AI308:AI308<>""),AI308:AI308))) | IF(OR(F308="",AK308=""),"",IF(COUNT(AI308:AJ308)=0,"",AK308-LOOKUP(2,1/(AI308:AJ308<>""),AI308:AJ308))) | IF(OR(F308="",AL308=""),"",IF(COUNT(AI308:AK308)=0,"",AL308-LOOKUP(2,1/(AI308:AK308<>""),AI308:AK308))) | IF(OR(F308="",AM308=""),"",IF(COUNT(AI308:AL308)=0,"",AM308-LOOKUP(2,1/(AI308:AL308<>""),AI308:AL308))) | IF(OR(F308="",AN308=""),"",IF(COUNT(AI308:AM308)=0,"",AN308-LOOKUP(2,1/(AI308:AM308<>""),AI308:AM308))) | IF(OR(F308="",AO308=""),"",IF(COUNT(AI308:AN308)=0,"",AO308-LOOKUP(2,1/(AI308:AN308<>""),AI308:AN308))) | IF(OR(F308="",AP308=""),"",IF(COUNT(AI308:AO308)=0,"",AP308-LOOKUP(2,1/(AI308:AO308<>""),AI308:AO308))) | IF(OR(F308="",AQ308=""),"",IF(COUNT(AI308:AP308)=0,"",AQ308-LOOKUP(2,1/(AI308:AP308<>""),AI308:AP308))) | IF(OR(F308="",AR308=""),"",IF(COUNT(AI308:AQ308)=0,"",AR308-LOOKUP(2,1/(AI308:AQ308<>""),AI308:AQ308))) | IF(OR(F308="",AS308=""),"",IF(COUNT(AI308:AR308)=0,"",AS308-LOOKUP(2,1/(AI308:AR308<>""),AI308:AR308))) | IF(OR(F308="",AT308=""),"",IF(COUNT(AI308:AS308)=0,"",AT308-LOOKUP(2,1/(AI308:AS308<>""),AI308:AS308))) | IF(OR(F308="",AU308=""),"",IF(COUNT(AI308:AT308)=0,"",AU308-LOOKUP(2,1/(AI308:AT308<>""),AI308:AT308))) | IF(OR(F308="",AV308=""),"",IF(COUNT(AI308:AU308)=0,"",AV308-LOOKUP(2,1/(AI308:AU308<>""),AI308:AU308))) | IF(J308="","All_Provinces",IFERROR(VLOOKUP(J308,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K308="","All_Districts",IFERROR(VLOOKUP(K308,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F309="","",ROW()-3) | [18 empty] | IF(AQ309="","",AQ309) |  |  |  | IF(W309<>"",W309,IF(OR(T309="",V309=""),"",EDATE(T309,V309))) |  |  |  |  | IF(F309="","",IF(COUNT(AI309:AV309)=0,IF(AA309="","Not started",AA309),SUBSTITUTE(LOOKUP(2,1/(AI309:AV309<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F309="",COUNT(AI309:AV309)=0),"",TODAY()-LOOKUP(2,1/(AI309:AV309<>""),AI309:AV309)) | IF(OR(F309="",COUNT(AI309:AV309)<2),"",LOOKUP(2,1/(AI309:AV309<>""),AI309:AV309)-MIN(AI309:AV309)) | IF(OR(AD309="",AC309="Not started",AC309=""),"",IFERROR(AD309-IF(VLOOKUP(AC309,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC309,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F309="","",IF(OR(AA309="Cancelled",AC309="Cancelled"),"Cancelled",IF(OR(AC309="Completed / Handover",Y309<>"",Z309>=100),"Completed — on track",IF(O309="Not awarded",IF(U309="",IF(X309="","No planned date",IF(TODAY()>X309,"Behind — past planned date",IF(X309-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U309,"Behind — award date passed",IF(U309-TODAY()<=30,"At risk — close to off track","On track"))),IF(X309="","No planned date",IF(AND(TODAY()>X309,OR(Z309="",Z309<100)),"Behind — past end date",IF(AND(T309<>"",X309<>"",Z309<>"",(Z309<100),((TODAY()-T309)/MAX(X309-T309,1)*100)-Z309>15),"Behind — progress lag",IF(AND(X309-TODAY()<=30,X309-TODAY()>=0,OR(Z309="",Z309<90)),"At risk — close to off track","On track")))))))) | IF(OR(F309="",AC309="Completed / Handover",AC309="Cancelled"),"",IF(O309="Not awarded",IF(U309<>"",U309-TODAY(),IF(X309="","",X309-TODAY())),IF(X309="","",X309-TODAY()))) | [14 empty] | IF(OR(F309="",AJ309=""),"",IF(COUNT(AI309:AI309)=0,"",AJ309-LOOKUP(2,1/(AI309:AI309<>""),AI309:AI309))) | IF(OR(F309="",AK309=""),"",IF(COUNT(AI309:AJ309)=0,"",AK309-LOOKUP(2,1/(AI309:AJ309<>""),AI309:AJ309))) | IF(OR(F309="",AL309=""),"",IF(COUNT(AI309:AK309)=0,"",AL309-LOOKUP(2,1/(AI309:AK309<>""),AI309:AK309))) | IF(OR(F309="",AM309=""),"",IF(COUNT(AI309:AL309)=0,"",AM309-LOOKUP(2,1/(AI309:AL309<>""),AI309:AL309))) | IF(OR(F309="",AN309=""),"",IF(COUNT(AI309:AM309)=0,"",AN309-LOOKUP(2,1/(AI309:AM309<>""),AI309:AM309))) | IF(OR(F309="",AO309=""),"",IF(COUNT(AI309:AN309)=0,"",AO309-LOOKUP(2,1/(AI309:AN309<>""),AI309:AN309))) | IF(OR(F309="",AP309=""),"",IF(COUNT(AI309:AO309)=0,"",AP309-LOOKUP(2,1/(AI309:AO309<>""),AI309:AO309))) | IF(OR(F309="",AQ309=""),"",IF(COUNT(AI309:AP309)=0,"",AQ309-LOOKUP(2,1/(AI309:AP309<>""),AI309:AP309))) | IF(OR(F309="",AR309=""),"",IF(COUNT(AI309:AQ309)=0,"",AR309-LOOKUP(2,1/(AI309:AQ309<>""),AI309:AQ309))) | IF(OR(F309="",AS309=""),"",IF(COUNT(AI309:AR309)=0,"",AS309-LOOKUP(2,1/(AI309:AR309<>""),AI309:AR309))) | IF(OR(F309="",AT309=""),"",IF(COUNT(AI309:AS309)=0,"",AT309-LOOKUP(2,1/(AI309:AS309<>""),AI309:AS309))) | IF(OR(F309="",AU309=""),"",IF(COUNT(AI309:AT309)=0,"",AU309-LOOKUP(2,1/(AI309:AT309<>""),AI309:AT309))) | IF(OR(F309="",AV309=""),"",IF(COUNT(AI309:AU309)=0,"",AV309-LOOKUP(2,1/(AI309:AU309<>""),AI309:AU309))) | IF(J309="","All_Provinces",IFERROR(VLOOKUP(J309,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K309="","All_Districts",IFERROR(VLOOKUP(K309,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F310="","",ROW()-3) | [18 empty] | IF(AQ310="","",AQ310) |  |  |  | IF(W310<>"",W310,IF(OR(T310="",V310=""),"",EDATE(T310,V310))) |  |  |  |  | IF(F310="","",IF(COUNT(AI310:AV310)=0,IF(AA310="","Not started",AA310),SUBSTITUTE(LOOKUP(2,1/(AI310:AV310<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F310="",COUNT(AI310:AV310)=0),"",TODAY()-LOOKUP(2,1/(AI310:AV310<>""),AI310:AV310)) | IF(OR(F310="",COUNT(AI310:AV310)<2),"",LOOKUP(2,1/(AI310:AV310<>""),AI310:AV310)-MIN(AI310:AV310)) | IF(OR(AD310="",AC310="Not started",AC310=""),"",IFERROR(AD310-IF(VLOOKUP(AC310,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC310,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F310="","",IF(OR(AA310="Cancelled",AC310="Cancelled"),"Cancelled",IF(OR(AC310="Completed / Handover",Y310<>"",Z310>=100),"Completed — on track",IF(O310="Not awarded",IF(U310="",IF(X310="","No planned date",IF(TODAY()>X310,"Behind — past planned date",IF(X310-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U310,"Behind — award date passed",IF(U310-TODAY()<=30,"At risk — close to off track","On track"))),IF(X310="","No planned date",IF(AND(TODAY()>X310,OR(Z310="",Z310<100)),"Behind — past end date",IF(AND(T310<>"",X310<>"",Z310<>"",(Z310<100),((TODAY()-T310)/MAX(X310-T310,1)*100)-Z310>15),"Behind — progress lag",IF(AND(X310-TODAY()<=30,X310-TODAY()>=0,OR(Z310="",Z310<90)),"At risk — close to off track","On track")))))))) | IF(OR(F310="",AC310="Completed / Handover",AC310="Cancelled"),"",IF(O310="Not awarded",IF(U310<>"",U310-TODAY(),IF(X310="","",X310-TODAY())),IF(X310="","",X310-TODAY()))) | [14 empty] | IF(OR(F310="",AJ310=""),"",IF(COUNT(AI310:AI310)=0,"",AJ310-LOOKUP(2,1/(AI310:AI310<>""),AI310:AI310))) | IF(OR(F310="",AK310=""),"",IF(COUNT(AI310:AJ310)=0,"",AK310-LOOKUP(2,1/(AI310:AJ310<>""),AI310:AJ310))) | IF(OR(F310="",AL310=""),"",IF(COUNT(AI310:AK310)=0,"",AL310-LOOKUP(2,1/(AI310:AK310<>""),AI310:AK310))) | IF(OR(F310="",AM310=""),"",IF(COUNT(AI310:AL310)=0,"",AM310-LOOKUP(2,1/(AI310:AL310<>""),AI310:AL310))) | IF(OR(F310="",AN310=""),"",IF(COUNT(AI310:AM310)=0,"",AN310-LOOKUP(2,1/(AI310:AM310<>""),AI310:AM310))) | IF(OR(F310="",AO310=""),"",IF(COUNT(AI310:AN310)=0,"",AO310-LOOKUP(2,1/(AI310:AN310<>""),AI310:AN310))) | IF(OR(F310="",AP310=""),"",IF(COUNT(AI310:AO310)=0,"",AP310-LOOKUP(2,1/(AI310:AO310<>""),AI310:AO310))) | IF(OR(F310="",AQ310=""),"",IF(COUNT(AI310:AP310)=0,"",AQ310-LOOKUP(2,1/(AI310:AP310<>""),AI310:AP310))) | IF(OR(F310="",AR310=""),"",IF(COUNT(AI310:AQ310)=0,"",AR310-LOOKUP(2,1/(AI310:AQ310<>""),AI310:AQ310))) | IF(OR(F310="",AS310=""),"",IF(COUNT(AI310:AR310)=0,"",AS310-LOOKUP(2,1/(AI310:AR310<>""),AI310:AR310))) | IF(OR(F310="",AT310=""),"",IF(COUNT(AI310:AS310)=0,"",AT310-LOOKUP(2,1/(AI310:AS310<>""),AI310:AS310))) | IF(OR(F310="",AU310=""),"",IF(COUNT(AI310:AT310)=0,"",AU310-LOOKUP(2,1/(AI310:AT310<>""),AI310:AT310))) | IF(OR(F310="",AV310=""),"",IF(COUNT(AI310:AU310)=0,"",AV310-LOOKUP(2,1/(AI310:AU310<>""),AI310:AU310))) | IF(J310="","All_Provinces",IFERROR(VLOOKUP(J310,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K310="","All_Districts",IFERROR(VLOOKUP(K310,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F311="","",ROW()-3) | [18 empty] | IF(AQ311="","",AQ311) |  |  |  | IF(W311<>"",W311,IF(OR(T311="",V311=""),"",EDATE(T311,V311))) |  |  |  |  | IF(F311="","",IF(COUNT(AI311:AV311)=0,IF(AA311="","Not started",AA311),SUBSTITUTE(LOOKUP(2,1/(AI311:AV311<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F311="",COUNT(AI311:AV311)=0),"",TODAY()-LOOKUP(2,1/(AI311:AV311<>""),AI311:AV311)) | IF(OR(F311="",COUNT(AI311:AV311)<2),"",LOOKUP(2,1/(AI311:AV311<>""),AI311:AV311)-MIN(AI311:AV311)) | IF(OR(AD311="",AC311="Not started",AC311=""),"",IFERROR(AD311-IF(VLOOKUP(AC311,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC311,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F311="","",IF(OR(AA311="Cancelled",AC311="Cancelled"),"Cancelled",IF(OR(AC311="Completed / Handover",Y311<>"",Z311>=100),"Completed — on track",IF(O311="Not awarded",IF(U311="",IF(X311="","No planned date",IF(TODAY()>X311,"Behind — past planned date",IF(X311-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U311,"Behind — award date passed",IF(U311-TODAY()<=30,"At risk — close to off track","On track"))),IF(X311="","No planned date",IF(AND(TODAY()>X311,OR(Z311="",Z311<100)),"Behind — past end date",IF(AND(T311<>"",X311<>"",Z311<>"",(Z311<100),((TODAY()-T311)/MAX(X311-T311,1)*100)-Z311>15),"Behind — progress lag",IF(AND(X311-TODAY()<=30,X311-TODAY()>=0,OR(Z311="",Z311<90)),"At risk — close to off track","On track")))))))) | IF(OR(F311="",AC311="Completed / Handover",AC311="Cancelled"),"",IF(O311="Not awarded",IF(U311<>"",U311-TODAY(),IF(X311="","",X311-TODAY())),IF(X311="","",X311-TODAY()))) | [14 empty] | IF(OR(F311="",AJ311=""),"",IF(COUNT(AI311:AI311)=0,"",AJ311-LOOKUP(2,1/(AI311:AI311<>""),AI311:AI311))) | IF(OR(F311="",AK311=""),"",IF(COUNT(AI311:AJ311)=0,"",AK311-LOOKUP(2,1/(AI311:AJ311<>""),AI311:AJ311))) | IF(OR(F311="",AL311=""),"",IF(COUNT(AI311:AK311)=0,"",AL311-LOOKUP(2,1/(AI311:AK311<>""),AI311:AK311))) | IF(OR(F311="",AM311=""),"",IF(COUNT(AI311:AL311)=0,"",AM311-LOOKUP(2,1/(AI311:AL311<>""),AI311:AL311))) | IF(OR(F311="",AN311=""),"",IF(COUNT(AI311:AM311)=0,"",AN311-LOOKUP(2,1/(AI311:AM311<>""),AI311:AM311))) | IF(OR(F311="",AO311=""),"",IF(COUNT(AI311:AN311)=0,"",AO311-LOOKUP(2,1/(AI311:AN311<>""),AI311:AN311))) | IF(OR(F311="",AP311=""),"",IF(COUNT(AI311:AO311)=0,"",AP311-LOOKUP(2,1/(AI311:AO311<>""),AI311:AO311))) | IF(OR(F311="",AQ311=""),"",IF(COUNT(AI311:AP311)=0,"",AQ311-LOOKUP(2,1/(AI311:AP311<>""),AI311:AP311))) | IF(OR(F311="",AR311=""),"",IF(COUNT(AI311:AQ311)=0,"",AR311-LOOKUP(2,1/(AI311:AQ311<>""),AI311:AQ311))) | IF(OR(F311="",AS311=""),"",IF(COUNT(AI311:AR311)=0,"",AS311-LOOKUP(2,1/(AI311:AR311<>""),AI311:AR311))) | IF(OR(F311="",AT311=""),"",IF(COUNT(AI311:AS311)=0,"",AT311-LOOKUP(2,1/(AI311:AS311<>""),AI311:AS311))) | IF(OR(F311="",AU311=""),"",IF(COUNT(AI311:AT311)=0,"",AU311-LOOKUP(2,1/(AI311:AT311<>""),AI311:AT311))) | IF(OR(F311="",AV311=""),"",IF(COUNT(AI311:AU311)=0,"",AV311-LOOKUP(2,1/(AI311:AU311<>""),AI311:AU311))) | IF(J311="","All_Provinces",IFERROR(VLOOKUP(J311,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K311="","All_Districts",IFERROR(VLOOKUP(K311,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F312="","",ROW()-3) | [18 empty] | IF(AQ312="","",AQ312) |  |  |  | IF(W312<>"",W312,IF(OR(T312="",V312=""),"",EDATE(T312,V312))) |  |  |  |  | IF(F312="","",IF(COUNT(AI312:AV312)=0,IF(AA312="","Not started",AA312),SUBSTITUTE(LOOKUP(2,1/(AI312:AV312<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F312="",COUNT(AI312:AV312)=0),"",TODAY()-LOOKUP(2,1/(AI312:AV312<>""),AI312:AV312)) | IF(OR(F312="",COUNT(AI312:AV312)<2),"",LOOKUP(2,1/(AI312:AV312<>""),AI312:AV312)-MIN(AI312:AV312)) | IF(OR(AD312="",AC312="Not started",AC312=""),"",IFERROR(AD312-IF(VLOOKUP(AC312,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC312,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F312="","",IF(OR(AA312="Cancelled",AC312="Cancelled"),"Cancelled",IF(OR(AC312="Completed / Handover",Y312<>"",Z312>=100),"Completed — on track",IF(O312="Not awarded",IF(U312="",IF(X312="","No planned date",IF(TODAY()>X312,"Behind — past planned date",IF(X312-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U312,"Behind — award date passed",IF(U312-TODAY()<=30,"At risk — close to off track","On track"))),IF(X312="","No planned date",IF(AND(TODAY()>X312,OR(Z312="",Z312<100)),"Behind — past end date",IF(AND(T312<>"",X312<>"",Z312<>"",(Z312<100),((TODAY()-T312)/MAX(X312-T312,1)*100)-Z312>15),"Behind — progress lag",IF(AND(X312-TODAY()<=30,X312-TODAY()>=0,OR(Z312="",Z312<90)),"At risk — close to off track","On track")))))))) | IF(OR(F312="",AC312="Completed / Handover",AC312="Cancelled"),"",IF(O312="Not awarded",IF(U312<>"",U312-TODAY(),IF(X312="","",X312-TODAY())),IF(X312="","",X312-TODAY()))) | [14 empty] | IF(OR(F312="",AJ312=""),"",IF(COUNT(AI312:AI312)=0,"",AJ312-LOOKUP(2,1/(AI312:AI312<>""),AI312:AI312))) | IF(OR(F312="",AK312=""),"",IF(COUNT(AI312:AJ312)=0,"",AK312-LOOKUP(2,1/(AI312:AJ312<>""),AI312:AJ312))) | IF(OR(F312="",AL312=""),"",IF(COUNT(AI312:AK312)=0,"",AL312-LOOKUP(2,1/(AI312:AK312<>""),AI312:AK312))) | IF(OR(F312="",AM312=""),"",IF(COUNT(AI312:AL312)=0,"",AM312-LOOKUP(2,1/(AI312:AL312<>""),AI312:AL312))) | IF(OR(F312="",AN312=""),"",IF(COUNT(AI312:AM312)=0,"",AN312-LOOKUP(2,1/(AI312:AM312<>""),AI312:AM312))) | IF(OR(F312="",AO312=""),"",IF(COUNT(AI312:AN312)=0,"",AO312-LOOKUP(2,1/(AI312:AN312<>""),AI312:AN312))) | IF(OR(F312="",AP312=""),"",IF(COUNT(AI312:AO312)=0,"",AP312-LOOKUP(2,1/(AI312:AO312<>""),AI312:AO312))) | IF(OR(F312="",AQ312=""),"",IF(COUNT(AI312:AP312)=0,"",AQ312-LOOKUP(2,1/(AI312:AP312<>""),AI312:AP312))) | IF(OR(F312="",AR312=""),"",IF(COUNT(AI312:AQ312)=0,"",AR312-LOOKUP(2,1/(AI312:AQ312<>""),AI312:AQ312))) | IF(OR(F312="",AS312=""),"",IF(COUNT(AI312:AR312)=0,"",AS312-LOOKUP(2,1/(AI312:AR312<>""),AI312:AR312))) | IF(OR(F312="",AT312=""),"",IF(COUNT(AI312:AS312)=0,"",AT312-LOOKUP(2,1/(AI312:AS312<>""),AI312:AS312))) | IF(OR(F312="",AU312=""),"",IF(COUNT(AI312:AT312)=0,"",AU312-LOOKUP(2,1/(AI312:AT312<>""),AI312:AT312))) | IF(OR(F312="",AV312=""),"",IF(COUNT(AI312:AU312)=0,"",AV312-LOOKUP(2,1/(AI312:AU312<>""),AI312:AU312))) | IF(J312="","All_Provinces",IFERROR(VLOOKUP(J312,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K312="","All_Districts",IFERROR(VLOOKUP(K312,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F313="","",ROW()-3) | [18 empty] | IF(AQ313="","",AQ313) |  |  |  | IF(W313<>"",W313,IF(OR(T313="",V313=""),"",EDATE(T313,V313))) |  |  |  |  | IF(F313="","",IF(COUNT(AI313:AV313)=0,IF(AA313="","Not started",AA313),SUBSTITUTE(LOOKUP(2,1/(AI313:AV313<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F313="",COUNT(AI313:AV313)=0),"",TODAY()-LOOKUP(2,1/(AI313:AV313<>""),AI313:AV313)) | IF(OR(F313="",COUNT(AI313:AV313)<2),"",LOOKUP(2,1/(AI313:AV313<>""),AI313:AV313)-MIN(AI313:AV313)) | IF(OR(AD313="",AC313="Not started",AC313=""),"",IFERROR(AD313-IF(VLOOKUP(AC313,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC313,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F313="","",IF(OR(AA313="Cancelled",AC313="Cancelled"),"Cancelled",IF(OR(AC313="Completed / Handover",Y313<>"",Z313>=100),"Completed — on track",IF(O313="Not awarded",IF(U313="",IF(X313="","No planned date",IF(TODAY()>X313,"Behind — past planned date",IF(X313-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U313,"Behind — award date passed",IF(U313-TODAY()<=30,"At risk — close to off track","On track"))),IF(X313="","No planned date",IF(AND(TODAY()>X313,OR(Z313="",Z313<100)),"Behind — past end date",IF(AND(T313<>"",X313<>"",Z313<>"",(Z313<100),((TODAY()-T313)/MAX(X313-T313,1)*100)-Z313>15),"Behind — progress lag",IF(AND(X313-TODAY()<=30,X313-TODAY()>=0,OR(Z313="",Z313<90)),"At risk — close to off track","On track")))))))) | IF(OR(F313="",AC313="Completed / Handover",AC313="Cancelled"),"",IF(O313="Not awarded",IF(U313<>"",U313-TODAY(),IF(X313="","",X313-TODAY())),IF(X313="","",X313-TODAY()))) | [14 empty] | IF(OR(F313="",AJ313=""),"",IF(COUNT(AI313:AI313)=0,"",AJ313-LOOKUP(2,1/(AI313:AI313<>""),AI313:AI313))) | IF(OR(F313="",AK313=""),"",IF(COUNT(AI313:AJ313)=0,"",AK313-LOOKUP(2,1/(AI313:AJ313<>""),AI313:AJ313))) | IF(OR(F313="",AL313=""),"",IF(COUNT(AI313:AK313)=0,"",AL313-LOOKUP(2,1/(AI313:AK313<>""),AI313:AK313))) | IF(OR(F313="",AM313=""),"",IF(COUNT(AI313:AL313)=0,"",AM313-LOOKUP(2,1/(AI313:AL313<>""),AI313:AL313))) | IF(OR(F313="",AN313=""),"",IF(COUNT(AI313:AM313)=0,"",AN313-LOOKUP(2,1/(AI313:AM313<>""),AI313:AM313))) | IF(OR(F313="",AO313=""),"",IF(COUNT(AI313:AN313)=0,"",AO313-LOOKUP(2,1/(AI313:AN313<>""),AI313:AN313))) | IF(OR(F313="",AP313=""),"",IF(COUNT(AI313:AO313)=0,"",AP313-LOOKUP(2,1/(AI313:AO313<>""),AI313:AO313))) | IF(OR(F313="",AQ313=""),"",IF(COUNT(AI313:AP313)=0,"",AQ313-LOOKUP(2,1/(AI313:AP313<>""),AI313:AP313))) | IF(OR(F313="",AR313=""),"",IF(COUNT(AI313:AQ313)=0,"",AR313-LOOKUP(2,1/(AI313:AQ313<>""),AI313:AQ313))) | IF(OR(F313="",AS313=""),"",IF(COUNT(AI313:AR313)=0,"",AS313-LOOKUP(2,1/(AI313:AR313<>""),AI313:AR313))) | IF(OR(F313="",AT313=""),"",IF(COUNT(AI313:AS313)=0,"",AT313-LOOKUP(2,1/(AI313:AS313<>""),AI313:AS313))) | IF(OR(F313="",AU313=""),"",IF(COUNT(AI313:AT313)=0,"",AU313-LOOKUP(2,1/(AI313:AT313<>""),AI313:AT313))) | IF(OR(F313="",AV313=""),"",IF(COUNT(AI313:AU313)=0,"",AV313-LOOKUP(2,1/(AI313:AU313<>""),AI313:AU313))) | IF(J313="","All_Provinces",IFERROR(VLOOKUP(J313,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K313="","All_Districts",IFERROR(VLOOKUP(K313,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F314="","",ROW()-3) | [18 empty] | IF(AQ314="","",AQ314) |  |  |  | IF(W314<>"",W314,IF(OR(T314="",V314=""),"",EDATE(T314,V314))) |  |  |  |  | IF(F314="","",IF(COUNT(AI314:AV314)=0,IF(AA314="","Not started",AA314),SUBSTITUTE(LOOKUP(2,1/(AI314:AV314<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F314="",COUNT(AI314:AV314)=0),"",TODAY()-LOOKUP(2,1/(AI314:AV314<>""),AI314:AV314)) | IF(OR(F314="",COUNT(AI314:AV314)<2),"",LOOKUP(2,1/(AI314:AV314<>""),AI314:AV314)-MIN(AI314:AV314)) | IF(OR(AD314="",AC314="Not started",AC314=""),"",IFERROR(AD314-IF(VLOOKUP(AC314,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC314,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F314="","",IF(OR(AA314="Cancelled",AC314="Cancelled"),"Cancelled",IF(OR(AC314="Completed / Handover",Y314<>"",Z314>=100),"Completed — on track",IF(O314="Not awarded",IF(U314="",IF(X314="","No planned date",IF(TODAY()>X314,"Behind — past planned date",IF(X314-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U314,"Behind — award date passed",IF(U314-TODAY()<=30,"At risk — close to off track","On track"))),IF(X314="","No planned date",IF(AND(TODAY()>X314,OR(Z314="",Z314<100)),"Behind — past end date",IF(AND(T314<>"",X314<>"",Z314<>"",(Z314<100),((TODAY()-T314)/MAX(X314-T314,1)*100)-Z314>15),"Behind — progress lag",IF(AND(X314-TODAY()<=30,X314-TODAY()>=0,OR(Z314="",Z314<90)),"At risk — close to off track","On track")))))))) | IF(OR(F314="",AC314="Completed / Handover",AC314="Cancelled"),"",IF(O314="Not awarded",IF(U314<>"",U314-TODAY(),IF(X314="","",X314-TODAY())),IF(X314="","",X314-TODAY()))) | [14 empty] | IF(OR(F314="",AJ314=""),"",IF(COUNT(AI314:AI314)=0,"",AJ314-LOOKUP(2,1/(AI314:AI314<>""),AI314:AI314))) | IF(OR(F314="",AK314=""),"",IF(COUNT(AI314:AJ314)=0,"",AK314-LOOKUP(2,1/(AI314:AJ314<>""),AI314:AJ314))) | IF(OR(F314="",AL314=""),"",IF(COUNT(AI314:AK314)=0,"",AL314-LOOKUP(2,1/(AI314:AK314<>""),AI314:AK314))) | IF(OR(F314="",AM314=""),"",IF(COUNT(AI314:AL314)=0,"",AM314-LOOKUP(2,1/(AI314:AL314<>""),AI314:AL314))) | IF(OR(F314="",AN314=""),"",IF(COUNT(AI314:AM314)=0,"",AN314-LOOKUP(2,1/(AI314:AM314<>""),AI314:AM314))) | IF(OR(F314="",AO314=""),"",IF(COUNT(AI314:AN314)=0,"",AO314-LOOKUP(2,1/(AI314:AN314<>""),AI314:AN314))) | IF(OR(F314="",AP314=""),"",IF(COUNT(AI314:AO314)=0,"",AP314-LOOKUP(2,1/(AI314:AO314<>""),AI314:AO314))) | IF(OR(F314="",AQ314=""),"",IF(COUNT(AI314:AP314)=0,"",AQ314-LOOKUP(2,1/(AI314:AP314<>""),AI314:AP314))) | IF(OR(F314="",AR314=""),"",IF(COUNT(AI314:AQ314)=0,"",AR314-LOOKUP(2,1/(AI314:AQ314<>""),AI314:AQ314))) | IF(OR(F314="",AS314=""),"",IF(COUNT(AI314:AR314)=0,"",AS314-LOOKUP(2,1/(AI314:AR314<>""),AI314:AR314))) | IF(OR(F314="",AT314=""),"",IF(COUNT(AI314:AS314)=0,"",AT314-LOOKUP(2,1/(AI314:AS314<>""),AI314:AS314))) | IF(OR(F314="",AU314=""),"",IF(COUNT(AI314:AT314)=0,"",AU314-LOOKUP(2,1/(AI314:AT314<>""),AI314:AT314))) | IF(OR(F314="",AV314=""),"",IF(COUNT(AI314:AU314)=0,"",AV314-LOOKUP(2,1/(AI314:AU314<>""),AI314:AU314))) | IF(J314="","All_Provinces",IFERROR(VLOOKUP(J314,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K314="","All_Districts",IFERROR(VLOOKUP(K314,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F315="","",ROW()-3) | [18 empty] | IF(AQ315="","",AQ315) |  |  |  | IF(W315<>"",W315,IF(OR(T315="",V315=""),"",EDATE(T315,V315))) |  |  |  |  | IF(F315="","",IF(COUNT(AI315:AV315)=0,IF(AA315="","Not started",AA315),SUBSTITUTE(LOOKUP(2,1/(AI315:AV315<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F315="",COUNT(AI315:AV315)=0),"",TODAY()-LOOKUP(2,1/(AI315:AV315<>""),AI315:AV315)) | IF(OR(F315="",COUNT(AI315:AV315)<2),"",LOOKUP(2,1/(AI315:AV315<>""),AI315:AV315)-MIN(AI315:AV315)) | IF(OR(AD315="",AC315="Not started",AC315=""),"",IFERROR(AD315-IF(VLOOKUP(AC315,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC315,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F315="","",IF(OR(AA315="Cancelled",AC315="Cancelled"),"Cancelled",IF(OR(AC315="Completed / Handover",Y315<>"",Z315>=100),"Completed — on track",IF(O315="Not awarded",IF(U315="",IF(X315="","No planned date",IF(TODAY()>X315,"Behind — past planned date",IF(X315-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U315,"Behind — award date passed",IF(U315-TODAY()<=30,"At risk — close to off track","On track"))),IF(X315="","No planned date",IF(AND(TODAY()>X315,OR(Z315="",Z315<100)),"Behind — past end date",IF(AND(T315<>"",X315<>"",Z315<>"",(Z315<100),((TODAY()-T315)/MAX(X315-T315,1)*100)-Z315>15),"Behind — progress lag",IF(AND(X315-TODAY()<=30,X315-TODAY()>=0,OR(Z315="",Z315<90)),"At risk — close to off track","On track")))))))) | IF(OR(F315="",AC315="Completed / Handover",AC315="Cancelled"),"",IF(O315="Not awarded",IF(U315<>"",U315-TODAY(),IF(X315="","",X315-TODAY())),IF(X315="","",X315-TODAY()))) | [14 empty] | IF(OR(F315="",AJ315=""),"",IF(COUNT(AI315:AI315)=0,"",AJ315-LOOKUP(2,1/(AI315:AI315<>""),AI315:AI315))) | IF(OR(F315="",AK315=""),"",IF(COUNT(AI315:AJ315)=0,"",AK315-LOOKUP(2,1/(AI315:AJ315<>""),AI315:AJ315))) | IF(OR(F315="",AL315=""),"",IF(COUNT(AI315:AK315)=0,"",AL315-LOOKUP(2,1/(AI315:AK315<>""),AI315:AK315))) | IF(OR(F315="",AM315=""),"",IF(COUNT(AI315:AL315)=0,"",AM315-LOOKUP(2,1/(AI315:AL315<>""),AI315:AL315))) | IF(OR(F315="",AN315=""),"",IF(COUNT(AI315:AM315)=0,"",AN315-LOOKUP(2,1/(AI315:AM315<>""),AI315:AM315))) | IF(OR(F315="",AO315=""),"",IF(COUNT(AI315:AN315)=0,"",AO315-LOOKUP(2,1/(AI315:AN315<>""),AI315:AN315))) | IF(OR(F315="",AP315=""),"",IF(COUNT(AI315:AO315)=0,"",AP315-LOOKUP(2,1/(AI315:AO315<>""),AI315:AO315))) | IF(OR(F315="",AQ315=""),"",IF(COUNT(AI315:AP315)=0,"",AQ315-LOOKUP(2,1/(AI315:AP315<>""),AI315:AP315))) | IF(OR(F315="",AR315=""),"",IF(COUNT(AI315:AQ315)=0,"",AR315-LOOKUP(2,1/(AI315:AQ315<>""),AI315:AQ315))) | IF(OR(F315="",AS315=""),"",IF(COUNT(AI315:AR315)=0,"",AS315-LOOKUP(2,1/(AI315:AR315<>""),AI315:AR315))) | IF(OR(F315="",AT315=""),"",IF(COUNT(AI315:AS315)=0,"",AT315-LOOKUP(2,1/(AI315:AS315<>""),AI315:AS315))) | IF(OR(F315="",AU315=""),"",IF(COUNT(AI315:AT315)=0,"",AU315-LOOKUP(2,1/(AI315:AT315<>""),AI315:AT315))) | IF(OR(F315="",AV315=""),"",IF(COUNT(AI315:AU315)=0,"",AV315-LOOKUP(2,1/(AI315:AU315<>""),AI315:AU315))) | IF(J315="","All_Provinces",IFERROR(VLOOKUP(J315,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K315="","All_Districts",IFERROR(VLOOKUP(K315,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F316="","",ROW()-3) | [18 empty] | IF(AQ316="","",AQ316) |  |  |  | IF(W316<>"",W316,IF(OR(T316="",V316=""),"",EDATE(T316,V316))) |  |  |  |  | IF(F316="","",IF(COUNT(AI316:AV316)=0,IF(AA316="","Not started",AA316),SUBSTITUTE(LOOKUP(2,1/(AI316:AV316<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F316="",COUNT(AI316:AV316)=0),"",TODAY()-LOOKUP(2,1/(AI316:AV316<>""),AI316:AV316)) | IF(OR(F316="",COUNT(AI316:AV316)<2),"",LOOKUP(2,1/(AI316:AV316<>""),AI316:AV316)-MIN(AI316:AV316)) | IF(OR(AD316="",AC316="Not started",AC316=""),"",IFERROR(AD316-IF(VLOOKUP(AC316,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC316,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F316="","",IF(OR(AA316="Cancelled",AC316="Cancelled"),"Cancelled",IF(OR(AC316="Completed / Handover",Y316<>"",Z316>=100),"Completed — on track",IF(O316="Not awarded",IF(U316="",IF(X316="","No planned date",IF(TODAY()>X316,"Behind — past planned date",IF(X316-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U316,"Behind — award date passed",IF(U316-TODAY()<=30,"At risk — close to off track","On track"))),IF(X316="","No planned date",IF(AND(TODAY()>X316,OR(Z316="",Z316<100)),"Behind — past end date",IF(AND(T316<>"",X316<>"",Z316<>"",(Z316<100),((TODAY()-T316)/MAX(X316-T316,1)*100)-Z316>15),"Behind — progress lag",IF(AND(X316-TODAY()<=30,X316-TODAY()>=0,OR(Z316="",Z316<90)),"At risk — close to off track","On track")))))))) | IF(OR(F316="",AC316="Completed / Handover",AC316="Cancelled"),"",IF(O316="Not awarded",IF(U316<>"",U316-TODAY(),IF(X316="","",X316-TODAY())),IF(X316="","",X316-TODAY()))) | [14 empty] | IF(OR(F316="",AJ316=""),"",IF(COUNT(AI316:AI316)=0,"",AJ316-LOOKUP(2,1/(AI316:AI316<>""),AI316:AI316))) | IF(OR(F316="",AK316=""),"",IF(COUNT(AI316:AJ316)=0,"",AK316-LOOKUP(2,1/(AI316:AJ316<>""),AI316:AJ316))) | IF(OR(F316="",AL316=""),"",IF(COUNT(AI316:AK316)=0,"",AL316-LOOKUP(2,1/(AI316:AK316<>""),AI316:AK316))) | IF(OR(F316="",AM316=""),"",IF(COUNT(AI316:AL316)=0,"",AM316-LOOKUP(2,1/(AI316:AL316<>""),AI316:AL316))) | IF(OR(F316="",AN316=""),"",IF(COUNT(AI316:AM316)=0,"",AN316-LOOKUP(2,1/(AI316:AM316<>""),AI316:AM316))) | IF(OR(F316="",AO316=""),"",IF(COUNT(AI316:AN316)=0,"",AO316-LOOKUP(2,1/(AI316:AN316<>""),AI316:AN316))) | IF(OR(F316="",AP316=""),"",IF(COUNT(AI316:AO316)=0,"",AP316-LOOKUP(2,1/(AI316:AO316<>""),AI316:AO316))) | IF(OR(F316="",AQ316=""),"",IF(COUNT(AI316:AP316)=0,"",AQ316-LOOKUP(2,1/(AI316:AP316<>""),AI316:AP316))) | IF(OR(F316="",AR316=""),"",IF(COUNT(AI316:AQ316)=0,"",AR316-LOOKUP(2,1/(AI316:AQ316<>""),AI316:AQ316))) | IF(OR(F316="",AS316=""),"",IF(COUNT(AI316:AR316)=0,"",AS316-LOOKUP(2,1/(AI316:AR316<>""),AI316:AR316))) | IF(OR(F316="",AT316=""),"",IF(COUNT(AI316:AS316)=0,"",AT316-LOOKUP(2,1/(AI316:AS316<>""),AI316:AS316))) | IF(OR(F316="",AU316=""),"",IF(COUNT(AI316:AT316)=0,"",AU316-LOOKUP(2,1/(AI316:AT316<>""),AI316:AT316))) | IF(OR(F316="",AV316=""),"",IF(COUNT(AI316:AU316)=0,"",AV316-LOOKUP(2,1/(AI316:AU316<>""),AI316:AU316))) | IF(J316="","All_Provinces",IFERROR(VLOOKUP(J316,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K316="","All_Districts",IFERROR(VLOOKUP(K316,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F317="","",ROW()-3) | [18 empty] | IF(AQ317="","",AQ317) |  |  |  | IF(W317<>"",W317,IF(OR(T317="",V317=""),"",EDATE(T317,V317))) |  |  |  |  | IF(F317="","",IF(COUNT(AI317:AV317)=0,IF(AA317="","Not started",AA317),SUBSTITUTE(LOOKUP(2,1/(AI317:AV317<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F317="",COUNT(AI317:AV317)=0),"",TODAY()-LOOKUP(2,1/(AI317:AV317<>""),AI317:AV317)) | IF(OR(F317="",COUNT(AI317:AV317)<2),"",LOOKUP(2,1/(AI317:AV317<>""),AI317:AV317)-MIN(AI317:AV317)) | IF(OR(AD317="",AC317="Not started",AC317=""),"",IFERROR(AD317-IF(VLOOKUP(AC317,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC317,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F317="","",IF(OR(AA317="Cancelled",AC317="Cancelled"),"Cancelled",IF(OR(AC317="Completed / Handover",Y317<>"",Z317>=100),"Completed — on track",IF(O317="Not awarded",IF(U317="",IF(X317="","No planned date",IF(TODAY()>X317,"Behind — past planned date",IF(X317-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U317,"Behind — award date passed",IF(U317-TODAY()<=30,"At risk — close to off track","On track"))),IF(X317="","No planned date",IF(AND(TODAY()>X317,OR(Z317="",Z317<100)),"Behind — past end date",IF(AND(T317<>"",X317<>"",Z317<>"",(Z317<100),((TODAY()-T317)/MAX(X317-T317,1)*100)-Z317>15),"Behind — progress lag",IF(AND(X317-TODAY()<=30,X317-TODAY()>=0,OR(Z317="",Z317<90)),"At risk — close to off track","On track")))))))) | IF(OR(F317="",AC317="Completed / Handover",AC317="Cancelled"),"",IF(O317="Not awarded",IF(U317<>"",U317-TODAY(),IF(X317="","",X317-TODAY())),IF(X317="","",X317-TODAY()))) | [14 empty] | IF(OR(F317="",AJ317=""),"",IF(COUNT(AI317:AI317)=0,"",AJ317-LOOKUP(2,1/(AI317:AI317<>""),AI317:AI317))) | IF(OR(F317="",AK317=""),"",IF(COUNT(AI317:AJ317)=0,"",AK317-LOOKUP(2,1/(AI317:AJ317<>""),AI317:AJ317))) | IF(OR(F317="",AL317=""),"",IF(COUNT(AI317:AK317)=0,"",AL317-LOOKUP(2,1/(AI317:AK317<>""),AI317:AK317))) | IF(OR(F317="",AM317=""),"",IF(COUNT(AI317:AL317)=0,"",AM317-LOOKUP(2,1/(AI317:AL317<>""),AI317:AL317))) | IF(OR(F317="",AN317=""),"",IF(COUNT(AI317:AM317)=0,"",AN317-LOOKUP(2,1/(AI317:AM317<>""),AI317:AM317))) | IF(OR(F317="",AO317=""),"",IF(COUNT(AI317:AN317)=0,"",AO317-LOOKUP(2,1/(AI317:AN317<>""),AI317:AN317))) | IF(OR(F317="",AP317=""),"",IF(COUNT(AI317:AO317)=0,"",AP317-LOOKUP(2,1/(AI317:AO317<>""),AI317:AO317))) | IF(OR(F317="",AQ317=""),"",IF(COUNT(AI317:AP317)=0,"",AQ317-LOOKUP(2,1/(AI317:AP317<>""),AI317:AP317))) | IF(OR(F317="",AR317=""),"",IF(COUNT(AI317:AQ317)=0,"",AR317-LOOKUP(2,1/(AI317:AQ317<>""),AI317:AQ317))) | IF(OR(F317="",AS317=""),"",IF(COUNT(AI317:AR317)=0,"",AS317-LOOKUP(2,1/(AI317:AR317<>""),AI317:AR317))) | IF(OR(F317="",AT317=""),"",IF(COUNT(AI317:AS317)=0,"",AT317-LOOKUP(2,1/(AI317:AS317<>""),AI317:AS317))) | IF(OR(F317="",AU317=""),"",IF(COUNT(AI317:AT317)=0,"",AU317-LOOKUP(2,1/(AI317:AT317<>""),AI317:AT317))) | IF(OR(F317="",AV317=""),"",IF(COUNT(AI317:AU317)=0,"",AV317-LOOKUP(2,1/(AI317:AU317<>""),AI317:AU317))) | IF(J317="","All_Provinces",IFERROR(VLOOKUP(J317,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K317="","All_Districts",IFERROR(VLOOKUP(K317,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F318="","",ROW()-3) | [18 empty] | IF(AQ318="","",AQ318) |  |  |  | IF(W318<>"",W318,IF(OR(T318="",V318=""),"",EDATE(T318,V318))) |  |  |  |  | IF(F318="","",IF(COUNT(AI318:AV318)=0,IF(AA318="","Not started",AA318),SUBSTITUTE(LOOKUP(2,1/(AI318:AV318<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F318="",COUNT(AI318:AV318)=0),"",TODAY()-LOOKUP(2,1/(AI318:AV318<>""),AI318:AV318)) | IF(OR(F318="",COUNT(AI318:AV318)<2),"",LOOKUP(2,1/(AI318:AV318<>""),AI318:AV318)-MIN(AI318:AV318)) | IF(OR(AD318="",AC318="Not started",AC318=""),"",IFERROR(AD318-IF(VLOOKUP(AC318,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC318,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F318="","",IF(OR(AA318="Cancelled",AC318="Cancelled"),"Cancelled",IF(OR(AC318="Completed / Handover",Y318<>"",Z318>=100),"Completed — on track",IF(O318="Not awarded",IF(U318="",IF(X318="","No planned date",IF(TODAY()>X318,"Behind — past planned date",IF(X318-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U318,"Behind — award date passed",IF(U318-TODAY()<=30,"At risk — close to off track","On track"))),IF(X318="","No planned date",IF(AND(TODAY()>X318,OR(Z318="",Z318<100)),"Behind — past end date",IF(AND(T318<>"",X318<>"",Z318<>"",(Z318<100),((TODAY()-T318)/MAX(X318-T318,1)*100)-Z318>15),"Behind — progress lag",IF(AND(X318-TODAY()<=30,X318-TODAY()>=0,OR(Z318="",Z318<90)),"At risk — close to off track","On track")))))))) | IF(OR(F318="",AC318="Completed / Handover",AC318="Cancelled"),"",IF(O318="Not awarded",IF(U318<>"",U318-TODAY(),IF(X318="","",X318-TODAY())),IF(X318="","",X318-TODAY()))) | [14 empty] | IF(OR(F318="",AJ318=""),"",IF(COUNT(AI318:AI318)=0,"",AJ318-LOOKUP(2,1/(AI318:AI318<>""),AI318:AI318))) | IF(OR(F318="",AK318=""),"",IF(COUNT(AI318:AJ318)=0,"",AK318-LOOKUP(2,1/(AI318:AJ318<>""),AI318:AJ318))) | IF(OR(F318="",AL318=""),"",IF(COUNT(AI318:AK318)=0,"",AL318-LOOKUP(2,1/(AI318:AK318<>""),AI318:AK318))) | IF(OR(F318="",AM318=""),"",IF(COUNT(AI318:AL318)=0,"",AM318-LOOKUP(2,1/(AI318:AL318<>""),AI318:AL318))) | IF(OR(F318="",AN318=""),"",IF(COUNT(AI318:AM318)=0,"",AN318-LOOKUP(2,1/(AI318:AM318<>""),AI318:AM318))) | IF(OR(F318="",AO318=""),"",IF(COUNT(AI318:AN318)=0,"",AO318-LOOKUP(2,1/(AI318:AN318<>""),AI318:AN318))) | IF(OR(F318="",AP318=""),"",IF(COUNT(AI318:AO318)=0,"",AP318-LOOKUP(2,1/(AI318:AO318<>""),AI318:AO318))) | IF(OR(F318="",AQ318=""),"",IF(COUNT(AI318:AP318)=0,"",AQ318-LOOKUP(2,1/(AI318:AP318<>""),AI318:AP318))) | IF(OR(F318="",AR318=""),"",IF(COUNT(AI318:AQ318)=0,"",AR318-LOOKUP(2,1/(AI318:AQ318<>""),AI318:AQ318))) | IF(OR(F318="",AS318=""),"",IF(COUNT(AI318:AR318)=0,"",AS318-LOOKUP(2,1/(AI318:AR318<>""),AI318:AR318))) | IF(OR(F318="",AT318=""),"",IF(COUNT(AI318:AS318)=0,"",AT318-LOOKUP(2,1/(AI318:AS318<>""),AI318:AS318))) | IF(OR(F318="",AU318=""),"",IF(COUNT(AI318:AT318)=0,"",AU318-LOOKUP(2,1/(AI318:AT318<>""),AI318:AT318))) | IF(OR(F318="",AV318=""),"",IF(COUNT(AI318:AU318)=0,"",AV318-LOOKUP(2,1/(AI318:AU318<>""),AI318:AU318))) | IF(J318="","All_Provinces",IFERROR(VLOOKUP(J318,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K318="","All_Districts",IFERROR(VLOOKUP(K318,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F319="","",ROW()-3) | [18 empty] | IF(AQ319="","",AQ319) |  |  |  | IF(W319<>"",W319,IF(OR(T319="",V319=""),"",EDATE(T319,V319))) |  |  |  |  | IF(F319="","",IF(COUNT(AI319:AV319)=0,IF(AA319="","Not started",AA319),SUBSTITUTE(LOOKUP(2,1/(AI319:AV319<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F319="",COUNT(AI319:AV319)=0),"",TODAY()-LOOKUP(2,1/(AI319:AV319<>""),AI319:AV319)) | IF(OR(F319="",COUNT(AI319:AV319)<2),"",LOOKUP(2,1/(AI319:AV319<>""),AI319:AV319)-MIN(AI319:AV319)) | IF(OR(AD319="",AC319="Not started",AC319=""),"",IFERROR(AD319-IF(VLOOKUP(AC319,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC319,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F319="","",IF(OR(AA319="Cancelled",AC319="Cancelled"),"Cancelled",IF(OR(AC319="Completed / Handover",Y319<>"",Z319>=100),"Completed — on track",IF(O319="Not awarded",IF(U319="",IF(X319="","No planned date",IF(TODAY()>X319,"Behind — past planned date",IF(X319-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U319,"Behind — award date passed",IF(U319-TODAY()<=30,"At risk — close to off track","On track"))),IF(X319="","No planned date",IF(AND(TODAY()>X319,OR(Z319="",Z319<100)),"Behind — past end date",IF(AND(T319<>"",X319<>"",Z319<>"",(Z319<100),((TODAY()-T319)/MAX(X319-T319,1)*100)-Z319>15),"Behind — progress lag",IF(AND(X319-TODAY()<=30,X319-TODAY()>=0,OR(Z319="",Z319<90)),"At risk — close to off track","On track")))))))) | IF(OR(F319="",AC319="Completed / Handover",AC319="Cancelled"),"",IF(O319="Not awarded",IF(U319<>"",U319-TODAY(),IF(X319="","",X319-TODAY())),IF(X319="","",X319-TODAY()))) | [14 empty] | IF(OR(F319="",AJ319=""),"",IF(COUNT(AI319:AI319)=0,"",AJ319-LOOKUP(2,1/(AI319:AI319<>""),AI319:AI319))) | IF(OR(F319="",AK319=""),"",IF(COUNT(AI319:AJ319)=0,"",AK319-LOOKUP(2,1/(AI319:AJ319<>""),AI319:AJ319))) | IF(OR(F319="",AL319=""),"",IF(COUNT(AI319:AK319)=0,"",AL319-LOOKUP(2,1/(AI319:AK319<>""),AI319:AK319))) | IF(OR(F319="",AM319=""),"",IF(COUNT(AI319:AL319)=0,"",AM319-LOOKUP(2,1/(AI319:AL319<>""),AI319:AL319))) | IF(OR(F319="",AN319=""),"",IF(COUNT(AI319:AM319)=0,"",AN319-LOOKUP(2,1/(AI319:AM319<>""),AI319:AM319))) | IF(OR(F319="",AO319=""),"",IF(COUNT(AI319:AN319)=0,"",AO319-LOOKUP(2,1/(AI319:AN319<>""),AI319:AN319))) | IF(OR(F319="",AP319=""),"",IF(COUNT(AI319:AO319)=0,"",AP319-LOOKUP(2,1/(AI319:AO319<>""),AI319:AO319))) | IF(OR(F319="",AQ319=""),"",IF(COUNT(AI319:AP319)=0,"",AQ319-LOOKUP(2,1/(AI319:AP319<>""),AI319:AP319))) | IF(OR(F319="",AR319=""),"",IF(COUNT(AI319:AQ319)=0,"",AR319-LOOKUP(2,1/(AI319:AQ319<>""),AI319:AQ319))) | IF(OR(F319="",AS319=""),"",IF(COUNT(AI319:AR319)=0,"",AS319-LOOKUP(2,1/(AI319:AR319<>""),AI319:AR319))) | IF(OR(F319="",AT319=""),"",IF(COUNT(AI319:AS319)=0,"",AT319-LOOKUP(2,1/(AI319:AS319<>""),AI319:AS319))) | IF(OR(F319="",AU319=""),"",IF(COUNT(AI319:AT319)=0,"",AU319-LOOKUP(2,1/(AI319:AT319<>""),AI319:AT319))) | IF(OR(F319="",AV319=""),"",IF(COUNT(AI319:AU319)=0,"",AV319-LOOKUP(2,1/(AI319:AU319<>""),AI319:AU319))) | IF(J319="","All_Provinces",IFERROR(VLOOKUP(J319,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K319="","All_Districts",IFERROR(VLOOKUP(K319,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F320="","",ROW()-3) | [18 empty] | IF(AQ320="","",AQ320) |  |  |  | IF(W320<>"",W320,IF(OR(T320="",V320=""),"",EDATE(T320,V320))) |  |  |  |  | IF(F320="","",IF(COUNT(AI320:AV320)=0,IF(AA320="","Not started",AA320),SUBSTITUTE(LOOKUP(2,1/(AI320:AV320<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F320="",COUNT(AI320:AV320)=0),"",TODAY()-LOOKUP(2,1/(AI320:AV320<>""),AI320:AV320)) | IF(OR(F320="",COUNT(AI320:AV320)<2),"",LOOKUP(2,1/(AI320:AV320<>""),AI320:AV320)-MIN(AI320:AV320)) | IF(OR(AD320="",AC320="Not started",AC320=""),"",IFERROR(AD320-IF(VLOOKUP(AC320,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC320,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F320="","",IF(OR(AA320="Cancelled",AC320="Cancelled"),"Cancelled",IF(OR(AC320="Completed / Handover",Y320<>"",Z320>=100),"Completed — on track",IF(O320="Not awarded",IF(U320="",IF(X320="","No planned date",IF(TODAY()>X320,"Behind — past planned date",IF(X320-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U320,"Behind — award date passed",IF(U320-TODAY()<=30,"At risk — close to off track","On track"))),IF(X320="","No planned date",IF(AND(TODAY()>X320,OR(Z320="",Z320<100)),"Behind — past end date",IF(AND(T320<>"",X320<>"",Z320<>"",(Z320<100),((TODAY()-T320)/MAX(X320-T320,1)*100)-Z320>15),"Behind — progress lag",IF(AND(X320-TODAY()<=30,X320-TODAY()>=0,OR(Z320="",Z320<90)),"At risk — close to off track","On track")))))))) | IF(OR(F320="",AC320="Completed / Handover",AC320="Cancelled"),"",IF(O320="Not awarded",IF(U320<>"",U320-TODAY(),IF(X320="","",X320-TODAY())),IF(X320="","",X320-TODAY()))) | [14 empty] | IF(OR(F320="",AJ320=""),"",IF(COUNT(AI320:AI320)=0,"",AJ320-LOOKUP(2,1/(AI320:AI320<>""),AI320:AI320))) | IF(OR(F320="",AK320=""),"",IF(COUNT(AI320:AJ320)=0,"",AK320-LOOKUP(2,1/(AI320:AJ320<>""),AI320:AJ320))) | IF(OR(F320="",AL320=""),"",IF(COUNT(AI320:AK320)=0,"",AL320-LOOKUP(2,1/(AI320:AK320<>""),AI320:AK320))) | IF(OR(F320="",AM320=""),"",IF(COUNT(AI320:AL320)=0,"",AM320-LOOKUP(2,1/(AI320:AL320<>""),AI320:AL320))) | IF(OR(F320="",AN320=""),"",IF(COUNT(AI320:AM320)=0,"",AN320-LOOKUP(2,1/(AI320:AM320<>""),AI320:AM320))) | IF(OR(F320="",AO320=""),"",IF(COUNT(AI320:AN320)=0,"",AO320-LOOKUP(2,1/(AI320:AN320<>""),AI320:AN320))) | IF(OR(F320="",AP320=""),"",IF(COUNT(AI320:AO320)=0,"",AP320-LOOKUP(2,1/(AI320:AO320<>""),AI320:AO320))) | IF(OR(F320="",AQ320=""),"",IF(COUNT(AI320:AP320)=0,"",AQ320-LOOKUP(2,1/(AI320:AP320<>""),AI320:AP320))) | IF(OR(F320="",AR320=""),"",IF(COUNT(AI320:AQ320)=0,"",AR320-LOOKUP(2,1/(AI320:AQ320<>""),AI320:AQ320))) | IF(OR(F320="",AS320=""),"",IF(COUNT(AI320:AR320)=0,"",AS320-LOOKUP(2,1/(AI320:AR320<>""),AI320:AR320))) | IF(OR(F320="",AT320=""),"",IF(COUNT(AI320:AS320)=0,"",AT320-LOOKUP(2,1/(AI320:AS320<>""),AI320:AS320))) | IF(OR(F320="",AU320=""),"",IF(COUNT(AI320:AT320)=0,"",AU320-LOOKUP(2,1/(AI320:AT320<>""),AI320:AT320))) | IF(OR(F320="",AV320=""),"",IF(COUNT(AI320:AU320)=0,"",AV320-LOOKUP(2,1/(AI320:AU320<>""),AI320:AU320))) | IF(J320="","All_Provinces",IFERROR(VLOOKUP(J320,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K320="","All_Districts",IFERROR(VLOOKUP(K320,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F321="","",ROW()-3) | [18 empty] | IF(AQ321="","",AQ321) |  |  |  | IF(W321<>"",W321,IF(OR(T321="",V321=""),"",EDATE(T321,V321))) |  |  |  |  | IF(F321="","",IF(COUNT(AI321:AV321)=0,IF(AA321="","Not started",AA321),SUBSTITUTE(LOOKUP(2,1/(AI321:AV321<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F321="",COUNT(AI321:AV321)=0),"",TODAY()-LOOKUP(2,1/(AI321:AV321<>""),AI321:AV321)) | IF(OR(F321="",COUNT(AI321:AV321)<2),"",LOOKUP(2,1/(AI321:AV321<>""),AI321:AV321)-MIN(AI321:AV321)) | IF(OR(AD321="",AC321="Not started",AC321=""),"",IFERROR(AD321-IF(VLOOKUP(AC321,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC321,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F321="","",IF(OR(AA321="Cancelled",AC321="Cancelled"),"Cancelled",IF(OR(AC321="Completed / Handover",Y321<>"",Z321>=100),"Completed — on track",IF(O321="Not awarded",IF(U321="",IF(X321="","No planned date",IF(TODAY()>X321,"Behind — past planned date",IF(X321-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U321,"Behind — award date passed",IF(U321-TODAY()<=30,"At risk — close to off track","On track"))),IF(X321="","No planned date",IF(AND(TODAY()>X321,OR(Z321="",Z321<100)),"Behind — past end date",IF(AND(T321<>"",X321<>"",Z321<>"",(Z321<100),((TODAY()-T321)/MAX(X321-T321,1)*100)-Z321>15),"Behind — progress lag",IF(AND(X321-TODAY()<=30,X321-TODAY()>=0,OR(Z321="",Z321<90)),"At risk — close to off track","On track")))))))) | IF(OR(F321="",AC321="Completed / Handover",AC321="Cancelled"),"",IF(O321="Not awarded",IF(U321<>"",U321-TODAY(),IF(X321="","",X321-TODAY())),IF(X321="","",X321-TODAY()))) | [14 empty] | IF(OR(F321="",AJ321=""),"",IF(COUNT(AI321:AI321)=0,"",AJ321-LOOKUP(2,1/(AI321:AI321<>""),AI321:AI321))) | IF(OR(F321="",AK321=""),"",IF(COUNT(AI321:AJ321)=0,"",AK321-LOOKUP(2,1/(AI321:AJ321<>""),AI321:AJ321))) | IF(OR(F321="",AL321=""),"",IF(COUNT(AI321:AK321)=0,"",AL321-LOOKUP(2,1/(AI321:AK321<>""),AI321:AK321))) | IF(OR(F321="",AM321=""),"",IF(COUNT(AI321:AL321)=0,"",AM321-LOOKUP(2,1/(AI321:AL321<>""),AI321:AL321))) | IF(OR(F321="",AN321=""),"",IF(COUNT(AI321:AM321)=0,"",AN321-LOOKUP(2,1/(AI321:AM321<>""),AI321:AM321))) | IF(OR(F321="",AO321=""),"",IF(COUNT(AI321:AN321)=0,"",AO321-LOOKUP(2,1/(AI321:AN321<>""),AI321:AN321))) | IF(OR(F321="",AP321=""),"",IF(COUNT(AI321:AO321)=0,"",AP321-LOOKUP(2,1/(AI321:AO321<>""),AI321:AO321))) | IF(OR(F321="",AQ321=""),"",IF(COUNT(AI321:AP321)=0,"",AQ321-LOOKUP(2,1/(AI321:AP321<>""),AI321:AP321))) | IF(OR(F321="",AR321=""),"",IF(COUNT(AI321:AQ321)=0,"",AR321-LOOKUP(2,1/(AI321:AQ321<>""),AI321:AQ321))) | IF(OR(F321="",AS321=""),"",IF(COUNT(AI321:AR321)=0,"",AS321-LOOKUP(2,1/(AI321:AR321<>""),AI321:AR321))) | IF(OR(F321="",AT321=""),"",IF(COUNT(AI321:AS321)=0,"",AT321-LOOKUP(2,1/(AI321:AS321<>""),AI321:AS321))) | IF(OR(F321="",AU321=""),"",IF(COUNT(AI321:AT321)=0,"",AU321-LOOKUP(2,1/(AI321:AT321<>""),AI321:AT321))) | IF(OR(F321="",AV321=""),"",IF(COUNT(AI321:AU321)=0,"",AV321-LOOKUP(2,1/(AI321:AU321<>""),AI321:AU321))) | IF(J321="","All_Provinces",IFERROR(VLOOKUP(J321,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K321="","All_Districts",IFERROR(VLOOKUP(K321,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F322="","",ROW()-3) | [18 empty] | IF(AQ322="","",AQ322) |  |  |  | IF(W322<>"",W322,IF(OR(T322="",V322=""),"",EDATE(T322,V322))) |  |  |  |  | IF(F322="","",IF(COUNT(AI322:AV322)=0,IF(AA322="","Not started",AA322),SUBSTITUTE(LOOKUP(2,1/(AI322:AV322<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F322="",COUNT(AI322:AV322)=0),"",TODAY()-LOOKUP(2,1/(AI322:AV322<>""),AI322:AV322)) | IF(OR(F322="",COUNT(AI322:AV322)<2),"",LOOKUP(2,1/(AI322:AV322<>""),AI322:AV322)-MIN(AI322:AV322)) | IF(OR(AD322="",AC322="Not started",AC322=""),"",IFERROR(AD322-IF(VLOOKUP(AC322,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC322,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F322="","",IF(OR(AA322="Cancelled",AC322="Cancelled"),"Cancelled",IF(OR(AC322="Completed / Handover",Y322<>"",Z322>=100),"Completed — on track",IF(O322="Not awarded",IF(U322="",IF(X322="","No planned date",IF(TODAY()>X322,"Behind — past planned date",IF(X322-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U322,"Behind — award date passed",IF(U322-TODAY()<=30,"At risk — close to off track","On track"))),IF(X322="","No planned date",IF(AND(TODAY()>X322,OR(Z322="",Z322<100)),"Behind — past end date",IF(AND(T322<>"",X322<>"",Z322<>"",(Z322<100),((TODAY()-T322)/MAX(X322-T322,1)*100)-Z322>15),"Behind — progress lag",IF(AND(X322-TODAY()<=30,X322-TODAY()>=0,OR(Z322="",Z322<90)),"At risk — close to off track","On track")))))))) | IF(OR(F322="",AC322="Completed / Handover",AC322="Cancelled"),"",IF(O322="Not awarded",IF(U322<>"",U322-TODAY(),IF(X322="","",X322-TODAY())),IF(X322="","",X322-TODAY()))) | [14 empty] | IF(OR(F322="",AJ322=""),"",IF(COUNT(AI322:AI322)=0,"",AJ322-LOOKUP(2,1/(AI322:AI322<>""),AI322:AI322))) | IF(OR(F322="",AK322=""),"",IF(COUNT(AI322:AJ322)=0,"",AK322-LOOKUP(2,1/(AI322:AJ322<>""),AI322:AJ322))) | IF(OR(F322="",AL322=""),"",IF(COUNT(AI322:AK322)=0,"",AL322-LOOKUP(2,1/(AI322:AK322<>""),AI322:AK322))) | IF(OR(F322="",AM322=""),"",IF(COUNT(AI322:AL322)=0,"",AM322-LOOKUP(2,1/(AI322:AL322<>""),AI322:AL322))) | IF(OR(F322="",AN322=""),"",IF(COUNT(AI322:AM322)=0,"",AN322-LOOKUP(2,1/(AI322:AM322<>""),AI322:AM322))) | IF(OR(F322="",AO322=""),"",IF(COUNT(AI322:AN322)=0,"",AO322-LOOKUP(2,1/(AI322:AN322<>""),AI322:AN322))) | IF(OR(F322="",AP322=""),"",IF(COUNT(AI322:AO322)=0,"",AP322-LOOKUP(2,1/(AI322:AO322<>""),AI322:AO322))) | IF(OR(F322="",AQ322=""),"",IF(COUNT(AI322:AP322)=0,"",AQ322-LOOKUP(2,1/(AI322:AP322<>""),AI322:AP322))) | IF(OR(F322="",AR322=""),"",IF(COUNT(AI322:AQ322)=0,"",AR322-LOOKUP(2,1/(AI322:AQ322<>""),AI322:AQ322))) | IF(OR(F322="",AS322=""),"",IF(COUNT(AI322:AR322)=0,"",AS322-LOOKUP(2,1/(AI322:AR322<>""),AI322:AR322))) | IF(OR(F322="",AT322=""),"",IF(COUNT(AI322:AS322)=0,"",AT322-LOOKUP(2,1/(AI322:AS322<>""),AI322:AS322))) | IF(OR(F322="",AU322=""),"",IF(COUNT(AI322:AT322)=0,"",AU322-LOOKUP(2,1/(AI322:AT322<>""),AI322:AT322))) | IF(OR(F322="",AV322=""),"",IF(COUNT(AI322:AU322)=0,"",AV322-LOOKUP(2,1/(AI322:AU322<>""),AI322:AU322))) | IF(J322="","All_Provinces",IFERROR(VLOOKUP(J322,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K322="","All_Districts",IFERROR(VLOOKUP(K322,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F323="","",ROW()-3) | [18 empty] | IF(AQ323="","",AQ323) |  |  |  | IF(W323<>"",W323,IF(OR(T323="",V323=""),"",EDATE(T323,V323))) |  |  |  |  | IF(F323="","",IF(COUNT(AI323:AV323)=0,IF(AA323="","Not started",AA323),SUBSTITUTE(LOOKUP(2,1/(AI323:AV323<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F323="",COUNT(AI323:AV323)=0),"",TODAY()-LOOKUP(2,1/(AI323:AV323<>""),AI323:AV323)) | IF(OR(F323="",COUNT(AI323:AV323)<2),"",LOOKUP(2,1/(AI323:AV323<>""),AI323:AV323)-MIN(AI323:AV323)) | IF(OR(AD323="",AC323="Not started",AC323=""),"",IFERROR(AD323-IF(VLOOKUP(AC323,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC323,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F323="","",IF(OR(AA323="Cancelled",AC323="Cancelled"),"Cancelled",IF(OR(AC323="Completed / Handover",Y323<>"",Z323>=100),"Completed — on track",IF(O323="Not awarded",IF(U323="",IF(X323="","No planned date",IF(TODAY()>X323,"Behind — past planned date",IF(X323-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U323,"Behind — award date passed",IF(U323-TODAY()<=30,"At risk — close to off track","On track"))),IF(X323="","No planned date",IF(AND(TODAY()>X323,OR(Z323="",Z323<100)),"Behind — past end date",IF(AND(T323<>"",X323<>"",Z323<>"",(Z323<100),((TODAY()-T323)/MAX(X323-T323,1)*100)-Z323>15),"Behind — progress lag",IF(AND(X323-TODAY()<=30,X323-TODAY()>=0,OR(Z323="",Z323<90)),"At risk — close to off track","On track")))))))) | IF(OR(F323="",AC323="Completed / Handover",AC323="Cancelled"),"",IF(O323="Not awarded",IF(U323<>"",U323-TODAY(),IF(X323="","",X323-TODAY())),IF(X323="","",X323-TODAY()))) | [14 empty] | IF(OR(F323="",AJ323=""),"",IF(COUNT(AI323:AI323)=0,"",AJ323-LOOKUP(2,1/(AI323:AI323<>""),AI323:AI323))) | IF(OR(F323="",AK323=""),"",IF(COUNT(AI323:AJ323)=0,"",AK323-LOOKUP(2,1/(AI323:AJ323<>""),AI323:AJ323))) | IF(OR(F323="",AL323=""),"",IF(COUNT(AI323:AK323)=0,"",AL323-LOOKUP(2,1/(AI323:AK323<>""),AI323:AK323))) | IF(OR(F323="",AM323=""),"",IF(COUNT(AI323:AL323)=0,"",AM323-LOOKUP(2,1/(AI323:AL323<>""),AI323:AL323))) | IF(OR(F323="",AN323=""),"",IF(COUNT(AI323:AM323)=0,"",AN323-LOOKUP(2,1/(AI323:AM323<>""),AI323:AM323))) | IF(OR(F323="",AO323=""),"",IF(COUNT(AI323:AN323)=0,"",AO323-LOOKUP(2,1/(AI323:AN323<>""),AI323:AN323))) | IF(OR(F323="",AP323=""),"",IF(COUNT(AI323:AO323)=0,"",AP323-LOOKUP(2,1/(AI323:AO323<>""),AI323:AO323))) | IF(OR(F323="",AQ323=""),"",IF(COUNT(AI323:AP323)=0,"",AQ323-LOOKUP(2,1/(AI323:AP323<>""),AI323:AP323))) | IF(OR(F323="",AR323=""),"",IF(COUNT(AI323:AQ323)=0,"",AR323-LOOKUP(2,1/(AI323:AQ323<>""),AI323:AQ323))) | IF(OR(F323="",AS323=""),"",IF(COUNT(AI323:AR323)=0,"",AS323-LOOKUP(2,1/(AI323:AR323<>""),AI323:AR323))) | IF(OR(F323="",AT323=""),"",IF(COUNT(AI323:AS323)=0,"",AT323-LOOKUP(2,1/(AI323:AS323<>""),AI323:AS323))) | IF(OR(F323="",AU323=""),"",IF(COUNT(AI323:AT323)=0,"",AU323-LOOKUP(2,1/(AI323:AT323<>""),AI323:AT323))) | IF(OR(F323="",AV323=""),"",IF(COUNT(AI323:AU323)=0,"",AV323-LOOKUP(2,1/(AI323:AU323<>""),AI323:AU323))) | IF(J323="","All_Provinces",IFERROR(VLOOKUP(J323,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K323="","All_Districts",IFERROR(VLOOKUP(K323,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F324="","",ROW()-3) | [18 empty] | IF(AQ324="","",AQ324) |  |  |  | IF(W324<>"",W324,IF(OR(T324="",V324=""),"",EDATE(T324,V324))) |  |  |  |  | IF(F324="","",IF(COUNT(AI324:AV324)=0,IF(AA324="","Not started",AA324),SUBSTITUTE(LOOKUP(2,1/(AI324:AV324<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F324="",COUNT(AI324:AV324)=0),"",TODAY()-LOOKUP(2,1/(AI324:AV324<>""),AI324:AV324)) | IF(OR(F324="",COUNT(AI324:AV324)<2),"",LOOKUP(2,1/(AI324:AV324<>""),AI324:AV324)-MIN(AI324:AV324)) | IF(OR(AD324="",AC324="Not started",AC324=""),"",IFERROR(AD324-IF(VLOOKUP(AC324,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC324,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F324="","",IF(OR(AA324="Cancelled",AC324="Cancelled"),"Cancelled",IF(OR(AC324="Completed / Handover",Y324<>"",Z324>=100),"Completed — on track",IF(O324="Not awarded",IF(U324="",IF(X324="","No planned date",IF(TODAY()>X324,"Behind — past planned date",IF(X324-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U324,"Behind — award date passed",IF(U324-TODAY()<=30,"At risk — close to off track","On track"))),IF(X324="","No planned date",IF(AND(TODAY()>X324,OR(Z324="",Z324<100)),"Behind — past end date",IF(AND(T324<>"",X324<>"",Z324<>"",(Z324<100),((TODAY()-T324)/MAX(X324-T324,1)*100)-Z324>15),"Behind — progress lag",IF(AND(X324-TODAY()<=30,X324-TODAY()>=0,OR(Z324="",Z324<90)),"At risk — close to off track","On track")))))))) | IF(OR(F324="",AC324="Completed / Handover",AC324="Cancelled"),"",IF(O324="Not awarded",IF(U324<>"",U324-TODAY(),IF(X324="","",X324-TODAY())),IF(X324="","",X324-TODAY()))) | [14 empty] | IF(OR(F324="",AJ324=""),"",IF(COUNT(AI324:AI324)=0,"",AJ324-LOOKUP(2,1/(AI324:AI324<>""),AI324:AI324))) | IF(OR(F324="",AK324=""),"",IF(COUNT(AI324:AJ324)=0,"",AK324-LOOKUP(2,1/(AI324:AJ324<>""),AI324:AJ324))) | IF(OR(F324="",AL324=""),"",IF(COUNT(AI324:AK324)=0,"",AL324-LOOKUP(2,1/(AI324:AK324<>""),AI324:AK324))) | IF(OR(F324="",AM324=""),"",IF(COUNT(AI324:AL324)=0,"",AM324-LOOKUP(2,1/(AI324:AL324<>""),AI324:AL324))) | IF(OR(F324="",AN324=""),"",IF(COUNT(AI324:AM324)=0,"",AN324-LOOKUP(2,1/(AI324:AM324<>""),AI324:AM324))) | IF(OR(F324="",AO324=""),"",IF(COUNT(AI324:AN324)=0,"",AO324-LOOKUP(2,1/(AI324:AN324<>""),AI324:AN324))) | IF(OR(F324="",AP324=""),"",IF(COUNT(AI324:AO324)=0,"",AP324-LOOKUP(2,1/(AI324:AO324<>""),AI324:AO324))) | IF(OR(F324="",AQ324=""),"",IF(COUNT(AI324:AP324)=0,"",AQ324-LOOKUP(2,1/(AI324:AP324<>""),AI324:AP324))) | IF(OR(F324="",AR324=""),"",IF(COUNT(AI324:AQ324)=0,"",AR324-LOOKUP(2,1/(AI324:AQ324<>""),AI324:AQ324))) | IF(OR(F324="",AS324=""),"",IF(COUNT(AI324:AR324)=0,"",AS324-LOOKUP(2,1/(AI324:AR324<>""),AI324:AR324))) | IF(OR(F324="",AT324=""),"",IF(COUNT(AI324:AS324)=0,"",AT324-LOOKUP(2,1/(AI324:AS324<>""),AI324:AS324))) | IF(OR(F324="",AU324=""),"",IF(COUNT(AI324:AT324)=0,"",AU324-LOOKUP(2,1/(AI324:AT324<>""),AI324:AT324))) | IF(OR(F324="",AV324=""),"",IF(COUNT(AI324:AU324)=0,"",AV324-LOOKUP(2,1/(AI324:AU324<>""),AI324:AU324))) | IF(J324="","All_Provinces",IFERROR(VLOOKUP(J324,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K324="","All_Districts",IFERROR(VLOOKUP(K324,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F325="","",ROW()-3) | [18 empty] | IF(AQ325="","",AQ325) |  |  |  | IF(W325<>"",W325,IF(OR(T325="",V325=""),"",EDATE(T325,V325))) |  |  |  |  | IF(F325="","",IF(COUNT(AI325:AV325)=0,IF(AA325="","Not started",AA325),SUBSTITUTE(LOOKUP(2,1/(AI325:AV325<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F325="",COUNT(AI325:AV325)=0),"",TODAY()-LOOKUP(2,1/(AI325:AV325<>""),AI325:AV325)) | IF(OR(F325="",COUNT(AI325:AV325)<2),"",LOOKUP(2,1/(AI325:AV325<>""),AI325:AV325)-MIN(AI325:AV325)) | IF(OR(AD325="",AC325="Not started",AC325=""),"",IFERROR(AD325-IF(VLOOKUP(AC325,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC325,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F325="","",IF(OR(AA325="Cancelled",AC325="Cancelled"),"Cancelled",IF(OR(AC325="Completed / Handover",Y325<>"",Z325>=100),"Completed — on track",IF(O325="Not awarded",IF(U325="",IF(X325="","No planned date",IF(TODAY()>X325,"Behind — past planned date",IF(X325-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U325,"Behind — award date passed",IF(U325-TODAY()<=30,"At risk — close to off track","On track"))),IF(X325="","No planned date",IF(AND(TODAY()>X325,OR(Z325="",Z325<100)),"Behind — past end date",IF(AND(T325<>"",X325<>"",Z325<>"",(Z325<100),((TODAY()-T325)/MAX(X325-T325,1)*100)-Z325>15),"Behind — progress lag",IF(AND(X325-TODAY()<=30,X325-TODAY()>=0,OR(Z325="",Z325<90)),"At risk — close to off track","On track")))))))) | IF(OR(F325="",AC325="Completed / Handover",AC325="Cancelled"),"",IF(O325="Not awarded",IF(U325<>"",U325-TODAY(),IF(X325="","",X325-TODAY())),IF(X325="","",X325-TODAY()))) | [14 empty] | IF(OR(F325="",AJ325=""),"",IF(COUNT(AI325:AI325)=0,"",AJ325-LOOKUP(2,1/(AI325:AI325<>""),AI325:AI325))) | IF(OR(F325="",AK325=""),"",IF(COUNT(AI325:AJ325)=0,"",AK325-LOOKUP(2,1/(AI325:AJ325<>""),AI325:AJ325))) | IF(OR(F325="",AL325=""),"",IF(COUNT(AI325:AK325)=0,"",AL325-LOOKUP(2,1/(AI325:AK325<>""),AI325:AK325))) | IF(OR(F325="",AM325=""),"",IF(COUNT(AI325:AL325)=0,"",AM325-LOOKUP(2,1/(AI325:AL325<>""),AI325:AL325))) | IF(OR(F325="",AN325=""),"",IF(COUNT(AI325:AM325)=0,"",AN325-LOOKUP(2,1/(AI325:AM325<>""),AI325:AM325))) | IF(OR(F325="",AO325=""),"",IF(COUNT(AI325:AN325)=0,"",AO325-LOOKUP(2,1/(AI325:AN325<>""),AI325:AN325))) | IF(OR(F325="",AP325=""),"",IF(COUNT(AI325:AO325)=0,"",AP325-LOOKUP(2,1/(AI325:AO325<>""),AI325:AO325))) | IF(OR(F325="",AQ325=""),"",IF(COUNT(AI325:AP325)=0,"",AQ325-LOOKUP(2,1/(AI325:AP325<>""),AI325:AP325))) | IF(OR(F325="",AR325=""),"",IF(COUNT(AI325:AQ325)=0,"",AR325-LOOKUP(2,1/(AI325:AQ325<>""),AI325:AQ325))) | IF(OR(F325="",AS325=""),"",IF(COUNT(AI325:AR325)=0,"",AS325-LOOKUP(2,1/(AI325:AR325<>""),AI325:AR325))) | IF(OR(F325="",AT325=""),"",IF(COUNT(AI325:AS325)=0,"",AT325-LOOKUP(2,1/(AI325:AS325<>""),AI325:AS325))) | IF(OR(F325="",AU325=""),"",IF(COUNT(AI325:AT325)=0,"",AU325-LOOKUP(2,1/(AI325:AT325<>""),AI325:AT325))) | IF(OR(F325="",AV325=""),"",IF(COUNT(AI325:AU325)=0,"",AV325-LOOKUP(2,1/(AI325:AU325<>""),AI325:AU325))) | IF(J325="","All_Provinces",IFERROR(VLOOKUP(J325,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K325="","All_Districts",IFERROR(VLOOKUP(K325,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F326="","",ROW()-3) | [18 empty] | IF(AQ326="","",AQ326) |  |  |  | IF(W326<>"",W326,IF(OR(T326="",V326=""),"",EDATE(T326,V326))) |  |  |  |  | IF(F326="","",IF(COUNT(AI326:AV326)=0,IF(AA326="","Not started",AA326),SUBSTITUTE(LOOKUP(2,1/(AI326:AV326<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F326="",COUNT(AI326:AV326)=0),"",TODAY()-LOOKUP(2,1/(AI326:AV326<>""),AI326:AV326)) | IF(OR(F326="",COUNT(AI326:AV326)<2),"",LOOKUP(2,1/(AI326:AV326<>""),AI326:AV326)-MIN(AI326:AV326)) | IF(OR(AD326="",AC326="Not started",AC326=""),"",IFERROR(AD326-IF(VLOOKUP(AC326,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC326,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F326="","",IF(OR(AA326="Cancelled",AC326="Cancelled"),"Cancelled",IF(OR(AC326="Completed / Handover",Y326<>"",Z326>=100),"Completed — on track",IF(O326="Not awarded",IF(U326="",IF(X326="","No planned date",IF(TODAY()>X326,"Behind — past planned date",IF(X326-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U326,"Behind — award date passed",IF(U326-TODAY()<=30,"At risk — close to off track","On track"))),IF(X326="","No planned date",IF(AND(TODAY()>X326,OR(Z326="",Z326<100)),"Behind — past end date",IF(AND(T326<>"",X326<>"",Z326<>"",(Z326<100),((TODAY()-T326)/MAX(X326-T326,1)*100)-Z326>15),"Behind — progress lag",IF(AND(X326-TODAY()<=30,X326-TODAY()>=0,OR(Z326="",Z326<90)),"At risk — close to off track","On track")))))))) | IF(OR(F326="",AC326="Completed / Handover",AC326="Cancelled"),"",IF(O326="Not awarded",IF(U326<>"",U326-TODAY(),IF(X326="","",X326-TODAY())),IF(X326="","",X326-TODAY()))) | [14 empty] | IF(OR(F326="",AJ326=""),"",IF(COUNT(AI326:AI326)=0,"",AJ326-LOOKUP(2,1/(AI326:AI326<>""),AI326:AI326))) | IF(OR(F326="",AK326=""),"",IF(COUNT(AI326:AJ326)=0,"",AK326-LOOKUP(2,1/(AI326:AJ326<>""),AI326:AJ326))) | IF(OR(F326="",AL326=""),"",IF(COUNT(AI326:AK326)=0,"",AL326-LOOKUP(2,1/(AI326:AK326<>""),AI326:AK326))) | IF(OR(F326="",AM326=""),"",IF(COUNT(AI326:AL326)=0,"",AM326-LOOKUP(2,1/(AI326:AL326<>""),AI326:AL326))) | IF(OR(F326="",AN326=""),"",IF(COUNT(AI326:AM326)=0,"",AN326-LOOKUP(2,1/(AI326:AM326<>""),AI326:AM326))) | IF(OR(F326="",AO326=""),"",IF(COUNT(AI326:AN326)=0,"",AO326-LOOKUP(2,1/(AI326:AN326<>""),AI326:AN326))) | IF(OR(F326="",AP326=""),"",IF(COUNT(AI326:AO326)=0,"",AP326-LOOKUP(2,1/(AI326:AO326<>""),AI326:AO326))) | IF(OR(F326="",AQ326=""),"",IF(COUNT(AI326:AP326)=0,"",AQ326-LOOKUP(2,1/(AI326:AP326<>""),AI326:AP326))) | IF(OR(F326="",AR326=""),"",IF(COUNT(AI326:AQ326)=0,"",AR326-LOOKUP(2,1/(AI326:AQ326<>""),AI326:AQ326))) | IF(OR(F326="",AS326=""),"",IF(COUNT(AI326:AR326)=0,"",AS326-LOOKUP(2,1/(AI326:AR326<>""),AI326:AR326))) | IF(OR(F326="",AT326=""),"",IF(COUNT(AI326:AS326)=0,"",AT326-LOOKUP(2,1/(AI326:AS326<>""),AI326:AS326))) | IF(OR(F326="",AU326=""),"",IF(COUNT(AI326:AT326)=0,"",AU326-LOOKUP(2,1/(AI326:AT326<>""),AI326:AT326))) | IF(OR(F326="",AV326=""),"",IF(COUNT(AI326:AU326)=0,"",AV326-LOOKUP(2,1/(AI326:AU326<>""),AI326:AU326))) | IF(J326="","All_Provinces",IFERROR(VLOOKUP(J326,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K326="","All_Districts",IFERROR(VLOOKUP(K326,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F327="","",ROW()-3) | [18 empty] | IF(AQ327="","",AQ327) |  |  |  | IF(W327<>"",W327,IF(OR(T327="",V327=""),"",EDATE(T327,V327))) |  |  |  |  | IF(F327="","",IF(COUNT(AI327:AV327)=0,IF(AA327="","Not started",AA327),SUBSTITUTE(LOOKUP(2,1/(AI327:AV327<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F327="",COUNT(AI327:AV327)=0),"",TODAY()-LOOKUP(2,1/(AI327:AV327<>""),AI327:AV327)) | IF(OR(F327="",COUNT(AI327:AV327)<2),"",LOOKUP(2,1/(AI327:AV327<>""),AI327:AV327)-MIN(AI327:AV327)) | IF(OR(AD327="",AC327="Not started",AC327=""),"",IFERROR(AD327-IF(VLOOKUP(AC327,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC327,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F327="","",IF(OR(AA327="Cancelled",AC327="Cancelled"),"Cancelled",IF(OR(AC327="Completed / Handover",Y327<>"",Z327>=100),"Completed — on track",IF(O327="Not awarded",IF(U327="",IF(X327="","No planned date",IF(TODAY()>X327,"Behind — past planned date",IF(X327-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U327,"Behind — award date passed",IF(U327-TODAY()<=30,"At risk — close to off track","On track"))),IF(X327="","No planned date",IF(AND(TODAY()>X327,OR(Z327="",Z327<100)),"Behind — past end date",IF(AND(T327<>"",X327<>"",Z327<>"",(Z327<100),((TODAY()-T327)/MAX(X327-T327,1)*100)-Z327>15),"Behind — progress lag",IF(AND(X327-TODAY()<=30,X327-TODAY()>=0,OR(Z327="",Z327<90)),"At risk — close to off track","On track")))))))) | IF(OR(F327="",AC327="Completed / Handover",AC327="Cancelled"),"",IF(O327="Not awarded",IF(U327<>"",U327-TODAY(),IF(X327="","",X327-TODAY())),IF(X327="","",X327-TODAY()))) | [14 empty] | IF(OR(F327="",AJ327=""),"",IF(COUNT(AI327:AI327)=0,"",AJ327-LOOKUP(2,1/(AI327:AI327<>""),AI327:AI327))) | IF(OR(F327="",AK327=""),"",IF(COUNT(AI327:AJ327)=0,"",AK327-LOOKUP(2,1/(AI327:AJ327<>""),AI327:AJ327))) | IF(OR(F327="",AL327=""),"",IF(COUNT(AI327:AK327)=0,"",AL327-LOOKUP(2,1/(AI327:AK327<>""),AI327:AK327))) | IF(OR(F327="",AM327=""),"",IF(COUNT(AI327:AL327)=0,"",AM327-LOOKUP(2,1/(AI327:AL327<>""),AI327:AL327))) | IF(OR(F327="",AN327=""),"",IF(COUNT(AI327:AM327)=0,"",AN327-LOOKUP(2,1/(AI327:AM327<>""),AI327:AM327))) | IF(OR(F327="",AO327=""),"",IF(COUNT(AI327:AN327)=0,"",AO327-LOOKUP(2,1/(AI327:AN327<>""),AI327:AN327))) | IF(OR(F327="",AP327=""),"",IF(COUNT(AI327:AO327)=0,"",AP327-LOOKUP(2,1/(AI327:AO327<>""),AI327:AO327))) | IF(OR(F327="",AQ327=""),"",IF(COUNT(AI327:AP327)=0,"",AQ327-LOOKUP(2,1/(AI327:AP327<>""),AI327:AP327))) | IF(OR(F327="",AR327=""),"",IF(COUNT(AI327:AQ327)=0,"",AR327-LOOKUP(2,1/(AI327:AQ327<>""),AI327:AQ327))) | IF(OR(F327="",AS327=""),"",IF(COUNT(AI327:AR327)=0,"",AS327-LOOKUP(2,1/(AI327:AR327<>""),AI327:AR327))) | IF(OR(F327="",AT327=""),"",IF(COUNT(AI327:AS327)=0,"",AT327-LOOKUP(2,1/(AI327:AS327<>""),AI327:AS327))) | IF(OR(F327="",AU327=""),"",IF(COUNT(AI327:AT327)=0,"",AU327-LOOKUP(2,1/(AI327:AT327<>""),AI327:AT327))) | IF(OR(F327="",AV327=""),"",IF(COUNT(AI327:AU327)=0,"",AV327-LOOKUP(2,1/(AI327:AU327<>""),AI327:AU327))) | IF(J327="","All_Provinces",IFERROR(VLOOKUP(J327,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K327="","All_Districts",IFERROR(VLOOKUP(K327,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F328="","",ROW()-3) | [18 empty] | IF(AQ328="","",AQ328) |  |  |  | IF(W328<>"",W328,IF(OR(T328="",V328=""),"",EDATE(T328,V328))) |  |  |  |  | IF(F328="","",IF(COUNT(AI328:AV328)=0,IF(AA328="","Not started",AA328),SUBSTITUTE(LOOKUP(2,1/(AI328:AV328<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F328="",COUNT(AI328:AV328)=0),"",TODAY()-LOOKUP(2,1/(AI328:AV328<>""),AI328:AV328)) | IF(OR(F328="",COUNT(AI328:AV328)<2),"",LOOKUP(2,1/(AI328:AV328<>""),AI328:AV328)-MIN(AI328:AV328)) | IF(OR(AD328="",AC328="Not started",AC328=""),"",IFERROR(AD328-IF(VLOOKUP(AC328,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC328,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F328="","",IF(OR(AA328="Cancelled",AC328="Cancelled"),"Cancelled",IF(OR(AC328="Completed / Handover",Y328<>"",Z328>=100),"Completed — on track",IF(O328="Not awarded",IF(U328="",IF(X328="","No planned date",IF(TODAY()>X328,"Behind — past planned date",IF(X328-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U328,"Behind — award date passed",IF(U328-TODAY()<=30,"At risk — close to off track","On track"))),IF(X328="","No planned date",IF(AND(TODAY()>X328,OR(Z328="",Z328<100)),"Behind — past end date",IF(AND(T328<>"",X328<>"",Z328<>"",(Z328<100),((TODAY()-T328)/MAX(X328-T328,1)*100)-Z328>15),"Behind — progress lag",IF(AND(X328-TODAY()<=30,X328-TODAY()>=0,OR(Z328="",Z328<90)),"At risk — close to off track","On track")))))))) | IF(OR(F328="",AC328="Completed / Handover",AC328="Cancelled"),"",IF(O328="Not awarded",IF(U328<>"",U328-TODAY(),IF(X328="","",X328-TODAY())),IF(X328="","",X328-TODAY()))) | [14 empty] | IF(OR(F328="",AJ328=""),"",IF(COUNT(AI328:AI328)=0,"",AJ328-LOOKUP(2,1/(AI328:AI328<>""),AI328:AI328))) | IF(OR(F328="",AK328=""),"",IF(COUNT(AI328:AJ328)=0,"",AK328-LOOKUP(2,1/(AI328:AJ328<>""),AI328:AJ328))) | IF(OR(F328="",AL328=""),"",IF(COUNT(AI328:AK328)=0,"",AL328-LOOKUP(2,1/(AI328:AK328<>""),AI328:AK328))) | IF(OR(F328="",AM328=""),"",IF(COUNT(AI328:AL328)=0,"",AM328-LOOKUP(2,1/(AI328:AL328<>""),AI328:AL328))) | IF(OR(F328="",AN328=""),"",IF(COUNT(AI328:AM328)=0,"",AN328-LOOKUP(2,1/(AI328:AM328<>""),AI328:AM328))) | IF(OR(F328="",AO328=""),"",IF(COUNT(AI328:AN328)=0,"",AO328-LOOKUP(2,1/(AI328:AN328<>""),AI328:AN328))) | IF(OR(F328="",AP328=""),"",IF(COUNT(AI328:AO328)=0,"",AP328-LOOKUP(2,1/(AI328:AO328<>""),AI328:AO328))) | IF(OR(F328="",AQ328=""),"",IF(COUNT(AI328:AP328)=0,"",AQ328-LOOKUP(2,1/(AI328:AP328<>""),AI328:AP328))) | IF(OR(F328="",AR328=""),"",IF(COUNT(AI328:AQ328)=0,"",AR328-LOOKUP(2,1/(AI328:AQ328<>""),AI328:AQ328))) | IF(OR(F328="",AS328=""),"",IF(COUNT(AI328:AR328)=0,"",AS328-LOOKUP(2,1/(AI328:AR328<>""),AI328:AR328))) | IF(OR(F328="",AT328=""),"",IF(COUNT(AI328:AS328)=0,"",AT328-LOOKUP(2,1/(AI328:AS328<>""),AI328:AS328))) | IF(OR(F328="",AU328=""),"",IF(COUNT(AI328:AT328)=0,"",AU328-LOOKUP(2,1/(AI328:AT328<>""),AI328:AT328))) | IF(OR(F328="",AV328=""),"",IF(COUNT(AI328:AU328)=0,"",AV328-LOOKUP(2,1/(AI328:AU328<>""),AI328:AU328))) | IF(J328="","All_Provinces",IFERROR(VLOOKUP(J328,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K328="","All_Districts",IFERROR(VLOOKUP(K328,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F329="","",ROW()-3) | [18 empty] | IF(AQ329="","",AQ329) |  |  |  | IF(W329<>"",W329,IF(OR(T329="",V329=""),"",EDATE(T329,V329))) |  |  |  |  | IF(F329="","",IF(COUNT(AI329:AV329)=0,IF(AA329="","Not started",AA329),SUBSTITUTE(LOOKUP(2,1/(AI329:AV329<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F329="",COUNT(AI329:AV329)=0),"",TODAY()-LOOKUP(2,1/(AI329:AV329<>""),AI329:AV329)) | IF(OR(F329="",COUNT(AI329:AV329)<2),"",LOOKUP(2,1/(AI329:AV329<>""),AI329:AV329)-MIN(AI329:AV329)) | IF(OR(AD329="",AC329="Not started",AC329=""),"",IFERROR(AD329-IF(VLOOKUP(AC329,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC329,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F329="","",IF(OR(AA329="Cancelled",AC329="Cancelled"),"Cancelled",IF(OR(AC329="Completed / Handover",Y329<>"",Z329>=100),"Completed — on track",IF(O329="Not awarded",IF(U329="",IF(X329="","No planned date",IF(TODAY()>X329,"Behind — past planned date",IF(X329-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U329,"Behind — award date passed",IF(U329-TODAY()<=30,"At risk — close to off track","On track"))),IF(X329="","No planned date",IF(AND(TODAY()>X329,OR(Z329="",Z329<100)),"Behind — past end date",IF(AND(T329<>"",X329<>"",Z329<>"",(Z329<100),((TODAY()-T329)/MAX(X329-T329,1)*100)-Z329>15),"Behind — progress lag",IF(AND(X329-TODAY()<=30,X329-TODAY()>=0,OR(Z329="",Z329<90)),"At risk — close to off track","On track")))))))) | IF(OR(F329="",AC329="Completed / Handover",AC329="Cancelled"),"",IF(O329="Not awarded",IF(U329<>"",U329-TODAY(),IF(X329="","",X329-TODAY())),IF(X329="","",X329-TODAY()))) | [14 empty] | IF(OR(F329="",AJ329=""),"",IF(COUNT(AI329:AI329)=0,"",AJ329-LOOKUP(2,1/(AI329:AI329<>""),AI329:AI329))) | IF(OR(F329="",AK329=""),"",IF(COUNT(AI329:AJ329)=0,"",AK329-LOOKUP(2,1/(AI329:AJ329<>""),AI329:AJ329))) | IF(OR(F329="",AL329=""),"",IF(COUNT(AI329:AK329)=0,"",AL329-LOOKUP(2,1/(AI329:AK329<>""),AI329:AK329))) | IF(OR(F329="",AM329=""),"",IF(COUNT(AI329:AL329)=0,"",AM329-LOOKUP(2,1/(AI329:AL329<>""),AI329:AL329))) | IF(OR(F329="",AN329=""),"",IF(COUNT(AI329:AM329)=0,"",AN329-LOOKUP(2,1/(AI329:AM329<>""),AI329:AM329))) | IF(OR(F329="",AO329=""),"",IF(COUNT(AI329:AN329)=0,"",AO329-LOOKUP(2,1/(AI329:AN329<>""),AI329:AN329))) | IF(OR(F329="",AP329=""),"",IF(COUNT(AI329:AO329)=0,"",AP329-LOOKUP(2,1/(AI329:AO329<>""),AI329:AO329))) | IF(OR(F329="",AQ329=""),"",IF(COUNT(AI329:AP329)=0,"",AQ329-LOOKUP(2,1/(AI329:AP329<>""),AI329:AP329))) | IF(OR(F329="",AR329=""),"",IF(COUNT(AI329:AQ329)=0,"",AR329-LOOKUP(2,1/(AI329:AQ329<>""),AI329:AQ329))) | IF(OR(F329="",AS329=""),"",IF(COUNT(AI329:AR329)=0,"",AS329-LOOKUP(2,1/(AI329:AR329<>""),AI329:AR329))) | IF(OR(F329="",AT329=""),"",IF(COUNT(AI329:AS329)=0,"",AT329-LOOKUP(2,1/(AI329:AS329<>""),AI329:AS329))) | IF(OR(F329="",AU329=""),"",IF(COUNT(AI329:AT329)=0,"",AU329-LOOKUP(2,1/(AI329:AT329<>""),AI329:AT329))) | IF(OR(F329="",AV329=""),"",IF(COUNT(AI329:AU329)=0,"",AV329-LOOKUP(2,1/(AI329:AU329<>""),AI329:AU329))) | IF(J329="","All_Provinces",IFERROR(VLOOKUP(J329,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K329="","All_Districts",IFERROR(VLOOKUP(K329,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F330="","",ROW()-3) | [18 empty] | IF(AQ330="","",AQ330) |  |  |  | IF(W330<>"",W330,IF(OR(T330="",V330=""),"",EDATE(T330,V330))) |  |  |  |  | IF(F330="","",IF(COUNT(AI330:AV330)=0,IF(AA330="","Not started",AA330),SUBSTITUTE(LOOKUP(2,1/(AI330:AV330<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F330="",COUNT(AI330:AV330)=0),"",TODAY()-LOOKUP(2,1/(AI330:AV330<>""),AI330:AV330)) | IF(OR(F330="",COUNT(AI330:AV330)<2),"",LOOKUP(2,1/(AI330:AV330<>""),AI330:AV330)-MIN(AI330:AV330)) | IF(OR(AD330="",AC330="Not started",AC330=""),"",IFERROR(AD330-IF(VLOOKUP(AC330,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC330,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F330="","",IF(OR(AA330="Cancelled",AC330="Cancelled"),"Cancelled",IF(OR(AC330="Completed / Handover",Y330<>"",Z330>=100),"Completed — on track",IF(O330="Not awarded",IF(U330="",IF(X330="","No planned date",IF(TODAY()>X330,"Behind — past planned date",IF(X330-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U330,"Behind — award date passed",IF(U330-TODAY()<=30,"At risk — close to off track","On track"))),IF(X330="","No planned date",IF(AND(TODAY()>X330,OR(Z330="",Z330<100)),"Behind — past end date",IF(AND(T330<>"",X330<>"",Z330<>"",(Z330<100),((TODAY()-T330)/MAX(X330-T330,1)*100)-Z330>15),"Behind — progress lag",IF(AND(X330-TODAY()<=30,X330-TODAY()>=0,OR(Z330="",Z330<90)),"At risk — close to off track","On track")))))))) | IF(OR(F330="",AC330="Completed / Handover",AC330="Cancelled"),"",IF(O330="Not awarded",IF(U330<>"",U330-TODAY(),IF(X330="","",X330-TODAY())),IF(X330="","",X330-TODAY()))) | [14 empty] | IF(OR(F330="",AJ330=""),"",IF(COUNT(AI330:AI330)=0,"",AJ330-LOOKUP(2,1/(AI330:AI330<>""),AI330:AI330))) | IF(OR(F330="",AK330=""),"",IF(COUNT(AI330:AJ330)=0,"",AK330-LOOKUP(2,1/(AI330:AJ330<>""),AI330:AJ330))) | IF(OR(F330="",AL330=""),"",IF(COUNT(AI330:AK330)=0,"",AL330-LOOKUP(2,1/(AI330:AK330<>""),AI330:AK330))) | IF(OR(F330="",AM330=""),"",IF(COUNT(AI330:AL330)=0,"",AM330-LOOKUP(2,1/(AI330:AL330<>""),AI330:AL330))) | IF(OR(F330="",AN330=""),"",IF(COUNT(AI330:AM330)=0,"",AN330-LOOKUP(2,1/(AI330:AM330<>""),AI330:AM330))) | IF(OR(F330="",AO330=""),"",IF(COUNT(AI330:AN330)=0,"",AO330-LOOKUP(2,1/(AI330:AN330<>""),AI330:AN330))) | IF(OR(F330="",AP330=""),"",IF(COUNT(AI330:AO330)=0,"",AP330-LOOKUP(2,1/(AI330:AO330<>""),AI330:AO330))) | IF(OR(F330="",AQ330=""),"",IF(COUNT(AI330:AP330)=0,"",AQ330-LOOKUP(2,1/(AI330:AP330<>""),AI330:AP330))) | IF(OR(F330="",AR330=""),"",IF(COUNT(AI330:AQ330)=0,"",AR330-LOOKUP(2,1/(AI330:AQ330<>""),AI330:AQ330))) | IF(OR(F330="",AS330=""),"",IF(COUNT(AI330:AR330)=0,"",AS330-LOOKUP(2,1/(AI330:AR330<>""),AI330:AR330))) | IF(OR(F330="",AT330=""),"",IF(COUNT(AI330:AS330)=0,"",AT330-LOOKUP(2,1/(AI330:AS330<>""),AI330:AS330))) | IF(OR(F330="",AU330=""),"",IF(COUNT(AI330:AT330)=0,"",AU330-LOOKUP(2,1/(AI330:AT330<>""),AI330:AT330))) | IF(OR(F330="",AV330=""),"",IF(COUNT(AI330:AU330)=0,"",AV330-LOOKUP(2,1/(AI330:AU330<>""),AI330:AU330))) | IF(J330="","All_Provinces",IFERROR(VLOOKUP(J330,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K330="","All_Districts",IFERROR(VLOOKUP(K330,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F331="","",ROW()-3) | [18 empty] | IF(AQ331="","",AQ331) |  |  |  | IF(W331<>"",W331,IF(OR(T331="",V331=""),"",EDATE(T331,V331))) |  |  |  |  | IF(F331="","",IF(COUNT(AI331:AV331)=0,IF(AA331="","Not started",AA331),SUBSTITUTE(LOOKUP(2,1/(AI331:AV331<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F331="",COUNT(AI331:AV331)=0),"",TODAY()-LOOKUP(2,1/(AI331:AV331<>""),AI331:AV331)) | IF(OR(F331="",COUNT(AI331:AV331)<2),"",LOOKUP(2,1/(AI331:AV331<>""),AI331:AV331)-MIN(AI331:AV331)) | IF(OR(AD331="",AC331="Not started",AC331=""),"",IFERROR(AD331-IF(VLOOKUP(AC331,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC331,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F331="","",IF(OR(AA331="Cancelled",AC331="Cancelled"),"Cancelled",IF(OR(AC331="Completed / Handover",Y331<>"",Z331>=100),"Completed — on track",IF(O331="Not awarded",IF(U331="",IF(X331="","No planned date",IF(TODAY()>X331,"Behind — past planned date",IF(X331-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U331,"Behind — award date passed",IF(U331-TODAY()<=30,"At risk — close to off track","On track"))),IF(X331="","No planned date",IF(AND(TODAY()>X331,OR(Z331="",Z331<100)),"Behind — past end date",IF(AND(T331<>"",X331<>"",Z331<>"",(Z331<100),((TODAY()-T331)/MAX(X331-T331,1)*100)-Z331>15),"Behind — progress lag",IF(AND(X331-TODAY()<=30,X331-TODAY()>=0,OR(Z331="",Z331<90)),"At risk — close to off track","On track")))))))) | IF(OR(F331="",AC331="Completed / Handover",AC331="Cancelled"),"",IF(O331="Not awarded",IF(U331<>"",U331-TODAY(),IF(X331="","",X331-TODAY())),IF(X331="","",X331-TODAY()))) | [14 empty] | IF(OR(F331="",AJ331=""),"",IF(COUNT(AI331:AI331)=0,"",AJ331-LOOKUP(2,1/(AI331:AI331<>""),AI331:AI331))) | IF(OR(F331="",AK331=""),"",IF(COUNT(AI331:AJ331)=0,"",AK331-LOOKUP(2,1/(AI331:AJ331<>""),AI331:AJ331))) | IF(OR(F331="",AL331=""),"",IF(COUNT(AI331:AK331)=0,"",AL331-LOOKUP(2,1/(AI331:AK331<>""),AI331:AK331))) | IF(OR(F331="",AM331=""),"",IF(COUNT(AI331:AL331)=0,"",AM331-LOOKUP(2,1/(AI331:AL331<>""),AI331:AL331))) | IF(OR(F331="",AN331=""),"",IF(COUNT(AI331:AM331)=0,"",AN331-LOOKUP(2,1/(AI331:AM331<>""),AI331:AM331))) | IF(OR(F331="",AO331=""),"",IF(COUNT(AI331:AN331)=0,"",AO331-LOOKUP(2,1/(AI331:AN331<>""),AI331:AN331))) | IF(OR(F331="",AP331=""),"",IF(COUNT(AI331:AO331)=0,"",AP331-LOOKUP(2,1/(AI331:AO331<>""),AI331:AO331))) | IF(OR(F331="",AQ331=""),"",IF(COUNT(AI331:AP331)=0,"",AQ331-LOOKUP(2,1/(AI331:AP331<>""),AI331:AP331))) | IF(OR(F331="",AR331=""),"",IF(COUNT(AI331:AQ331)=0,"",AR331-LOOKUP(2,1/(AI331:AQ331<>""),AI331:AQ331))) | IF(OR(F331="",AS331=""),"",IF(COUNT(AI331:AR331)=0,"",AS331-LOOKUP(2,1/(AI331:AR331<>""),AI331:AR331))) | IF(OR(F331="",AT331=""),"",IF(COUNT(AI331:AS331)=0,"",AT331-LOOKUP(2,1/(AI331:AS331<>""),AI331:AS331))) | IF(OR(F331="",AU331=""),"",IF(COUNT(AI331:AT331)=0,"",AU331-LOOKUP(2,1/(AI331:AT331<>""),AI331:AT331))) | IF(OR(F331="",AV331=""),"",IF(COUNT(AI331:AU331)=0,"",AV331-LOOKUP(2,1/(AI331:AU331<>""),AI331:AU331))) | IF(J331="","All_Provinces",IFERROR(VLOOKUP(J331,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K331="","All_Districts",IFERROR(VLOOKUP(K331,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F332="","",ROW()-3) | [18 empty] | IF(AQ332="","",AQ332) |  |  |  | IF(W332<>"",W332,IF(OR(T332="",V332=""),"",EDATE(T332,V332))) |  |  |  |  | IF(F332="","",IF(COUNT(AI332:AV332)=0,IF(AA332="","Not started",AA332),SUBSTITUTE(LOOKUP(2,1/(AI332:AV332<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F332="",COUNT(AI332:AV332)=0),"",TODAY()-LOOKUP(2,1/(AI332:AV332<>""),AI332:AV332)) | IF(OR(F332="",COUNT(AI332:AV332)<2),"",LOOKUP(2,1/(AI332:AV332<>""),AI332:AV332)-MIN(AI332:AV332)) | IF(OR(AD332="",AC332="Not started",AC332=""),"",IFERROR(AD332-IF(VLOOKUP(AC332,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC332,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F332="","",IF(OR(AA332="Cancelled",AC332="Cancelled"),"Cancelled",IF(OR(AC332="Completed / Handover",Y332<>"",Z332>=100),"Completed — on track",IF(O332="Not awarded",IF(U332="",IF(X332="","No planned date",IF(TODAY()>X332,"Behind — past planned date",IF(X332-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U332,"Behind — award date passed",IF(U332-TODAY()<=30,"At risk — close to off track","On track"))),IF(X332="","No planned date",IF(AND(TODAY()>X332,OR(Z332="",Z332<100)),"Behind — past end date",IF(AND(T332<>"",X332<>"",Z332<>"",(Z332<100),((TODAY()-T332)/MAX(X332-T332,1)*100)-Z332>15),"Behind — progress lag",IF(AND(X332-TODAY()<=30,X332-TODAY()>=0,OR(Z332="",Z332<90)),"At risk — close to off track","On track")))))))) | IF(OR(F332="",AC332="Completed / Handover",AC332="Cancelled"),"",IF(O332="Not awarded",IF(U332<>"",U332-TODAY(),IF(X332="","",X332-TODAY())),IF(X332="","",X332-TODAY()))) | [14 empty] | IF(OR(F332="",AJ332=""),"",IF(COUNT(AI332:AI332)=0,"",AJ332-LOOKUP(2,1/(AI332:AI332<>""),AI332:AI332))) | IF(OR(F332="",AK332=""),"",IF(COUNT(AI332:AJ332)=0,"",AK332-LOOKUP(2,1/(AI332:AJ332<>""),AI332:AJ332))) | IF(OR(F332="",AL332=""),"",IF(COUNT(AI332:AK332)=0,"",AL332-LOOKUP(2,1/(AI332:AK332<>""),AI332:AK332))) | IF(OR(F332="",AM332=""),"",IF(COUNT(AI332:AL332)=0,"",AM332-LOOKUP(2,1/(AI332:AL332<>""),AI332:AL332))) | IF(OR(F332="",AN332=""),"",IF(COUNT(AI332:AM332)=0,"",AN332-LOOKUP(2,1/(AI332:AM332<>""),AI332:AM332))) | IF(OR(F332="",AO332=""),"",IF(COUNT(AI332:AN332)=0,"",AO332-LOOKUP(2,1/(AI332:AN332<>""),AI332:AN332))) | IF(OR(F332="",AP332=""),"",IF(COUNT(AI332:AO332)=0,"",AP332-LOOKUP(2,1/(AI332:AO332<>""),AI332:AO332))) | IF(OR(F332="",AQ332=""),"",IF(COUNT(AI332:AP332)=0,"",AQ332-LOOKUP(2,1/(AI332:AP332<>""),AI332:AP332))) | IF(OR(F332="",AR332=""),"",IF(COUNT(AI332:AQ332)=0,"",AR332-LOOKUP(2,1/(AI332:AQ332<>""),AI332:AQ332))) | IF(OR(F332="",AS332=""),"",IF(COUNT(AI332:AR332)=0,"",AS332-LOOKUP(2,1/(AI332:AR332<>""),AI332:AR332))) | IF(OR(F332="",AT332=""),"",IF(COUNT(AI332:AS332)=0,"",AT332-LOOKUP(2,1/(AI332:AS332<>""),AI332:AS332))) | IF(OR(F332="",AU332=""),"",IF(COUNT(AI332:AT332)=0,"",AU332-LOOKUP(2,1/(AI332:AT332<>""),AI332:AT332))) | IF(OR(F332="",AV332=""),"",IF(COUNT(AI332:AU332)=0,"",AV332-LOOKUP(2,1/(AI332:AU332<>""),AI332:AU332))) | IF(J332="","All_Provinces",IFERROR(VLOOKUP(J332,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K332="","All_Districts",IFERROR(VLOOKUP(K332,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F333="","",ROW()-3) | [18 empty] | IF(AQ333="","",AQ333) |  |  |  | IF(W333<>"",W333,IF(OR(T333="",V333=""),"",EDATE(T333,V333))) |  |  |  |  | IF(F333="","",IF(COUNT(AI333:AV333)=0,IF(AA333="","Not started",AA333),SUBSTITUTE(LOOKUP(2,1/(AI333:AV333<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F333="",COUNT(AI333:AV333)=0),"",TODAY()-LOOKUP(2,1/(AI333:AV333<>""),AI333:AV333)) | IF(OR(F333="",COUNT(AI333:AV333)<2),"",LOOKUP(2,1/(AI333:AV333<>""),AI333:AV333)-MIN(AI333:AV333)) | IF(OR(AD333="",AC333="Not started",AC333=""),"",IFERROR(AD333-IF(VLOOKUP(AC333,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC333,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F333="","",IF(OR(AA333="Cancelled",AC333="Cancelled"),"Cancelled",IF(OR(AC333="Completed / Handover",Y333<>"",Z333>=100),"Completed — on track",IF(O333="Not awarded",IF(U333="",IF(X333="","No planned date",IF(TODAY()>X333,"Behind — past planned date",IF(X333-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U333,"Behind — award date passed",IF(U333-TODAY()<=30,"At risk — close to off track","On track"))),IF(X333="","No planned date",IF(AND(TODAY()>X333,OR(Z333="",Z333<100)),"Behind — past end date",IF(AND(T333<>"",X333<>"",Z333<>"",(Z333<100),((TODAY()-T333)/MAX(X333-T333,1)*100)-Z333>15),"Behind — progress lag",IF(AND(X333-TODAY()<=30,X333-TODAY()>=0,OR(Z333="",Z333<90)),"At risk — close to off track","On track")))))))) | IF(OR(F333="",AC333="Completed / Handover",AC333="Cancelled"),"",IF(O333="Not awarded",IF(U333<>"",U333-TODAY(),IF(X333="","",X333-TODAY())),IF(X333="","",X333-TODAY()))) | [14 empty] | IF(OR(F333="",AJ333=""),"",IF(COUNT(AI333:AI333)=0,"",AJ333-LOOKUP(2,1/(AI333:AI333<>""),AI333:AI333))) | IF(OR(F333="",AK333=""),"",IF(COUNT(AI333:AJ333)=0,"",AK333-LOOKUP(2,1/(AI333:AJ333<>""),AI333:AJ333))) | IF(OR(F333="",AL333=""),"",IF(COUNT(AI333:AK333)=0,"",AL333-LOOKUP(2,1/(AI333:AK333<>""),AI333:AK333))) | IF(OR(F333="",AM333=""),"",IF(COUNT(AI333:AL333)=0,"",AM333-LOOKUP(2,1/(AI333:AL333<>""),AI333:AL333))) | IF(OR(F333="",AN333=""),"",IF(COUNT(AI333:AM333)=0,"",AN333-LOOKUP(2,1/(AI333:AM333<>""),AI333:AM333))) | IF(OR(F333="",AO333=""),"",IF(COUNT(AI333:AN333)=0,"",AO333-LOOKUP(2,1/(AI333:AN333<>""),AI333:AN333))) | IF(OR(F333="",AP333=""),"",IF(COUNT(AI333:AO333)=0,"",AP333-LOOKUP(2,1/(AI333:AO333<>""),AI333:AO333))) | IF(OR(F333="",AQ333=""),"",IF(COUNT(AI333:AP333)=0,"",AQ333-LOOKUP(2,1/(AI333:AP333<>""),AI333:AP333))) | IF(OR(F333="",AR333=""),"",IF(COUNT(AI333:AQ333)=0,"",AR333-LOOKUP(2,1/(AI333:AQ333<>""),AI333:AQ333))) | IF(OR(F333="",AS333=""),"",IF(COUNT(AI333:AR333)=0,"",AS333-LOOKUP(2,1/(AI333:AR333<>""),AI333:AR333))) | IF(OR(F333="",AT333=""),"",IF(COUNT(AI333:AS333)=0,"",AT333-LOOKUP(2,1/(AI333:AS333<>""),AI333:AS333))) | IF(OR(F333="",AU333=""),"",IF(COUNT(AI333:AT333)=0,"",AU333-LOOKUP(2,1/(AI333:AT333<>""),AI333:AT333))) | IF(OR(F333="",AV333=""),"",IF(COUNT(AI333:AU333)=0,"",AV333-LOOKUP(2,1/(AI333:AU333<>""),AI333:AU333))) | IF(J333="","All_Provinces",IFERROR(VLOOKUP(J333,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K333="","All_Districts",IFERROR(VLOOKUP(K333,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F334="","",ROW()-3) | [18 empty] | IF(AQ334="","",AQ334) |  |  |  | IF(W334<>"",W334,IF(OR(T334="",V334=""),"",EDATE(T334,V334))) |  |  |  |  | IF(F334="","",IF(COUNT(AI334:AV334)=0,IF(AA334="","Not started",AA334),SUBSTITUTE(LOOKUP(2,1/(AI334:AV334<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F334="",COUNT(AI334:AV334)=0),"",TODAY()-LOOKUP(2,1/(AI334:AV334<>""),AI334:AV334)) | IF(OR(F334="",COUNT(AI334:AV334)<2),"",LOOKUP(2,1/(AI334:AV334<>""),AI334:AV334)-MIN(AI334:AV334)) | IF(OR(AD334="",AC334="Not started",AC334=""),"",IFERROR(AD334-IF(VLOOKUP(AC334,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC334,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F334="","",IF(OR(AA334="Cancelled",AC334="Cancelled"),"Cancelled",IF(OR(AC334="Completed / Handover",Y334<>"",Z334>=100),"Completed — on track",IF(O334="Not awarded",IF(U334="",IF(X334="","No planned date",IF(TODAY()>X334,"Behind — past planned date",IF(X334-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U334,"Behind — award date passed",IF(U334-TODAY()<=30,"At risk — close to off track","On track"))),IF(X334="","No planned date",IF(AND(TODAY()>X334,OR(Z334="",Z334<100)),"Behind — past end date",IF(AND(T334<>"",X334<>"",Z334<>"",(Z334<100),((TODAY()-T334)/MAX(X334-T334,1)*100)-Z334>15),"Behind — progress lag",IF(AND(X334-TODAY()<=30,X334-TODAY()>=0,OR(Z334="",Z334<90)),"At risk — close to off track","On track")))))))) | IF(OR(F334="",AC334="Completed / Handover",AC334="Cancelled"),"",IF(O334="Not awarded",IF(U334<>"",U334-TODAY(),IF(X334="","",X334-TODAY())),IF(X334="","",X334-TODAY()))) | [14 empty] | IF(OR(F334="",AJ334=""),"",IF(COUNT(AI334:AI334)=0,"",AJ334-LOOKUP(2,1/(AI334:AI334<>""),AI334:AI334))) | IF(OR(F334="",AK334=""),"",IF(COUNT(AI334:AJ334)=0,"",AK334-LOOKUP(2,1/(AI334:AJ334<>""),AI334:AJ334))) | IF(OR(F334="",AL334=""),"",IF(COUNT(AI334:AK334)=0,"",AL334-LOOKUP(2,1/(AI334:AK334<>""),AI334:AK334))) | IF(OR(F334="",AM334=""),"",IF(COUNT(AI334:AL334)=0,"",AM334-LOOKUP(2,1/(AI334:AL334<>""),AI334:AL334))) | IF(OR(F334="",AN334=""),"",IF(COUNT(AI334:AM334)=0,"",AN334-LOOKUP(2,1/(AI334:AM334<>""),AI334:AM334))) | IF(OR(F334="",AO334=""),"",IF(COUNT(AI334:AN334)=0,"",AO334-LOOKUP(2,1/(AI334:AN334<>""),AI334:AN334))) | IF(OR(F334="",AP334=""),"",IF(COUNT(AI334:AO334)=0,"",AP334-LOOKUP(2,1/(AI334:AO334<>""),AI334:AO334))) | IF(OR(F334="",AQ334=""),"",IF(COUNT(AI334:AP334)=0,"",AQ334-LOOKUP(2,1/(AI334:AP334<>""),AI334:AP334))) | IF(OR(F334="",AR334=""),"",IF(COUNT(AI334:AQ334)=0,"",AR334-LOOKUP(2,1/(AI334:AQ334<>""),AI334:AQ334))) | IF(OR(F334="",AS334=""),"",IF(COUNT(AI334:AR334)=0,"",AS334-LOOKUP(2,1/(AI334:AR334<>""),AI334:AR334))) | IF(OR(F334="",AT334=""),"",IF(COUNT(AI334:AS334)=0,"",AT334-LOOKUP(2,1/(AI334:AS334<>""),AI334:AS334))) | IF(OR(F334="",AU334=""),"",IF(COUNT(AI334:AT334)=0,"",AU334-LOOKUP(2,1/(AI334:AT334<>""),AI334:AT334))) | IF(OR(F334="",AV334=""),"",IF(COUNT(AI334:AU334)=0,"",AV334-LOOKUP(2,1/(AI334:AU334<>""),AI334:AU334))) | IF(J334="","All_Provinces",IFERROR(VLOOKUP(J334,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K334="","All_Districts",IFERROR(VLOOKUP(K334,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F335="","",ROW()-3) | [18 empty] | IF(AQ335="","",AQ335) |  |  |  | IF(W335<>"",W335,IF(OR(T335="",V335=""),"",EDATE(T335,V335))) |  |  |  |  | IF(F335="","",IF(COUNT(AI335:AV335)=0,IF(AA335="","Not started",AA335),SUBSTITUTE(LOOKUP(2,1/(AI335:AV335<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F335="",COUNT(AI335:AV335)=0),"",TODAY()-LOOKUP(2,1/(AI335:AV335<>""),AI335:AV335)) | IF(OR(F335="",COUNT(AI335:AV335)<2),"",LOOKUP(2,1/(AI335:AV335<>""),AI335:AV335)-MIN(AI335:AV335)) | IF(OR(AD335="",AC335="Not started",AC335=""),"",IFERROR(AD335-IF(VLOOKUP(AC335,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC335,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F335="","",IF(OR(AA335="Cancelled",AC335="Cancelled"),"Cancelled",IF(OR(AC335="Completed / Handover",Y335<>"",Z335>=100),"Completed — on track",IF(O335="Not awarded",IF(U335="",IF(X335="","No planned date",IF(TODAY()>X335,"Behind — past planned date",IF(X335-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U335,"Behind — award date passed",IF(U335-TODAY()<=30,"At risk — close to off track","On track"))),IF(X335="","No planned date",IF(AND(TODAY()>X335,OR(Z335="",Z335<100)),"Behind — past end date",IF(AND(T335<>"",X335<>"",Z335<>"",(Z335<100),((TODAY()-T335)/MAX(X335-T335,1)*100)-Z335>15),"Behind — progress lag",IF(AND(X335-TODAY()<=30,X335-TODAY()>=0,OR(Z335="",Z335<90)),"At risk — close to off track","On track")))))))) | IF(OR(F335="",AC335="Completed / Handover",AC335="Cancelled"),"",IF(O335="Not awarded",IF(U335<>"",U335-TODAY(),IF(X335="","",X335-TODAY())),IF(X335="","",X335-TODAY()))) | [14 empty] | IF(OR(F335="",AJ335=""),"",IF(COUNT(AI335:AI335)=0,"",AJ335-LOOKUP(2,1/(AI335:AI335<>""),AI335:AI335))) | IF(OR(F335="",AK335=""),"",IF(COUNT(AI335:AJ335)=0,"",AK335-LOOKUP(2,1/(AI335:AJ335<>""),AI335:AJ335))) | IF(OR(F335="",AL335=""),"",IF(COUNT(AI335:AK335)=0,"",AL335-LOOKUP(2,1/(AI335:AK335<>""),AI335:AK335))) | IF(OR(F335="",AM335=""),"",IF(COUNT(AI335:AL335)=0,"",AM335-LOOKUP(2,1/(AI335:AL335<>""),AI335:AL335))) | IF(OR(F335="",AN335=""),"",IF(COUNT(AI335:AM335)=0,"",AN335-LOOKUP(2,1/(AI335:AM335<>""),AI335:AM335))) | IF(OR(F335="",AO335=""),"",IF(COUNT(AI335:AN335)=0,"",AO335-LOOKUP(2,1/(AI335:AN335<>""),AI335:AN335))) | IF(OR(F335="",AP335=""),"",IF(COUNT(AI335:AO335)=0,"",AP335-LOOKUP(2,1/(AI335:AO335<>""),AI335:AO335))) | IF(OR(F335="",AQ335=""),"",IF(COUNT(AI335:AP335)=0,"",AQ335-LOOKUP(2,1/(AI335:AP335<>""),AI335:AP335))) | IF(OR(F335="",AR335=""),"",IF(COUNT(AI335:AQ335)=0,"",AR335-LOOKUP(2,1/(AI335:AQ335<>""),AI335:AQ335))) | IF(OR(F335="",AS335=""),"",IF(COUNT(AI335:AR335)=0,"",AS335-LOOKUP(2,1/(AI335:AR335<>""),AI335:AR335))) | IF(OR(F335="",AT335=""),"",IF(COUNT(AI335:AS335)=0,"",AT335-LOOKUP(2,1/(AI335:AS335<>""),AI335:AS335))) | IF(OR(F335="",AU335=""),"",IF(COUNT(AI335:AT335)=0,"",AU335-LOOKUP(2,1/(AI335:AT335<>""),AI335:AT335))) | IF(OR(F335="",AV335=""),"",IF(COUNT(AI335:AU335)=0,"",AV335-LOOKUP(2,1/(AI335:AU335<>""),AI335:AU335))) | IF(J335="","All_Provinces",IFERROR(VLOOKUP(J335,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K335="","All_Districts",IFERROR(VLOOKUP(K335,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F336="","",ROW()-3) | [18 empty] | IF(AQ336="","",AQ336) |  |  |  | IF(W336<>"",W336,IF(OR(T336="",V336=""),"",EDATE(T336,V336))) |  |  |  |  | IF(F336="","",IF(COUNT(AI336:AV336)=0,IF(AA336="","Not started",AA336),SUBSTITUTE(LOOKUP(2,1/(AI336:AV336<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F336="",COUNT(AI336:AV336)=0),"",TODAY()-LOOKUP(2,1/(AI336:AV336<>""),AI336:AV336)) | IF(OR(F336="",COUNT(AI336:AV336)<2),"",LOOKUP(2,1/(AI336:AV336<>""),AI336:AV336)-MIN(AI336:AV336)) | IF(OR(AD336="",AC336="Not started",AC336=""),"",IFERROR(AD336-IF(VLOOKUP(AC336,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC336,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F336="","",IF(OR(AA336="Cancelled",AC336="Cancelled"),"Cancelled",IF(OR(AC336="Completed / Handover",Y336<>"",Z336>=100),"Completed — on track",IF(O336="Not awarded",IF(U336="",IF(X336="","No planned date",IF(TODAY()>X336,"Behind — past planned date",IF(X336-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U336,"Behind — award date passed",IF(U336-TODAY()<=30,"At risk — close to off track","On track"))),IF(X336="","No planned date",IF(AND(TODAY()>X336,OR(Z336="",Z336<100)),"Behind — past end date",IF(AND(T336<>"",X336<>"",Z336<>"",(Z336<100),((TODAY()-T336)/MAX(X336-T336,1)*100)-Z336>15),"Behind — progress lag",IF(AND(X336-TODAY()<=30,X336-TODAY()>=0,OR(Z336="",Z336<90)),"At risk — close to off track","On track")))))))) | IF(OR(F336="",AC336="Completed / Handover",AC336="Cancelled"),"",IF(O336="Not awarded",IF(U336<>"",U336-TODAY(),IF(X336="","",X336-TODAY())),IF(X336="","",X336-TODAY()))) | [14 empty] | IF(OR(F336="",AJ336=""),"",IF(COUNT(AI336:AI336)=0,"",AJ336-LOOKUP(2,1/(AI336:AI336<>""),AI336:AI336))) | IF(OR(F336="",AK336=""),"",IF(COUNT(AI336:AJ336)=0,"",AK336-LOOKUP(2,1/(AI336:AJ336<>""),AI336:AJ336))) | IF(OR(F336="",AL336=""),"",IF(COUNT(AI336:AK336)=0,"",AL336-LOOKUP(2,1/(AI336:AK336<>""),AI336:AK336))) | IF(OR(F336="",AM336=""),"",IF(COUNT(AI336:AL336)=0,"",AM336-LOOKUP(2,1/(AI336:AL336<>""),AI336:AL336))) | IF(OR(F336="",AN336=""),"",IF(COUNT(AI336:AM336)=0,"",AN336-LOOKUP(2,1/(AI336:AM336<>""),AI336:AM336))) | IF(OR(F336="",AO336=""),"",IF(COUNT(AI336:AN336)=0,"",AO336-LOOKUP(2,1/(AI336:AN336<>""),AI336:AN336))) | IF(OR(F336="",AP336=""),"",IF(COUNT(AI336:AO336)=0,"",AP336-LOOKUP(2,1/(AI336:AO336<>""),AI336:AO336))) | IF(OR(F336="",AQ336=""),"",IF(COUNT(AI336:AP336)=0,"",AQ336-LOOKUP(2,1/(AI336:AP336<>""),AI336:AP336))) | IF(OR(F336="",AR336=""),"",IF(COUNT(AI336:AQ336)=0,"",AR336-LOOKUP(2,1/(AI336:AQ336<>""),AI336:AQ336))) | IF(OR(F336="",AS336=""),"",IF(COUNT(AI336:AR336)=0,"",AS336-LOOKUP(2,1/(AI336:AR336<>""),AI336:AR336))) | IF(OR(F336="",AT336=""),"",IF(COUNT(AI336:AS336)=0,"",AT336-LOOKUP(2,1/(AI336:AS336<>""),AI336:AS336))) | IF(OR(F336="",AU336=""),"",IF(COUNT(AI336:AT336)=0,"",AU336-LOOKUP(2,1/(AI336:AT336<>""),AI336:AT336))) | IF(OR(F336="",AV336=""),"",IF(COUNT(AI336:AU336)=0,"",AV336-LOOKUP(2,1/(AI336:AU336<>""),AI336:AU336))) | IF(J336="","All_Provinces",IFERROR(VLOOKUP(J336,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K336="","All_Districts",IFERROR(VLOOKUP(K336,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F337="","",ROW()-3) | [18 empty] | IF(AQ337="","",AQ337) |  |  |  | IF(W337<>"",W337,IF(OR(T337="",V337=""),"",EDATE(T337,V337))) |  |  |  |  | IF(F337="","",IF(COUNT(AI337:AV337)=0,IF(AA337="","Not started",AA337),SUBSTITUTE(LOOKUP(2,1/(AI337:AV337<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F337="",COUNT(AI337:AV337)=0),"",TODAY()-LOOKUP(2,1/(AI337:AV337<>""),AI337:AV337)) | IF(OR(F337="",COUNT(AI337:AV337)<2),"",LOOKUP(2,1/(AI337:AV337<>""),AI337:AV337)-MIN(AI337:AV337)) | IF(OR(AD337="",AC337="Not started",AC337=""),"",IFERROR(AD337-IF(VLOOKUP(AC337,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC337,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F337="","",IF(OR(AA337="Cancelled",AC337="Cancelled"),"Cancelled",IF(OR(AC337="Completed / Handover",Y337<>"",Z337>=100),"Completed — on track",IF(O337="Not awarded",IF(U337="",IF(X337="","No planned date",IF(TODAY()>X337,"Behind — past planned date",IF(X337-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U337,"Behind — award date passed",IF(U337-TODAY()<=30,"At risk — close to off track","On track"))),IF(X337="","No planned date",IF(AND(TODAY()>X337,OR(Z337="",Z337<100)),"Behind — past end date",IF(AND(T337<>"",X337<>"",Z337<>"",(Z337<100),((TODAY()-T337)/MAX(X337-T337,1)*100)-Z337>15),"Behind — progress lag",IF(AND(X337-TODAY()<=30,X337-TODAY()>=0,OR(Z337="",Z337<90)),"At risk — close to off track","On track")))))))) | IF(OR(F337="",AC337="Completed / Handover",AC337="Cancelled"),"",IF(O337="Not awarded",IF(U337<>"",U337-TODAY(),IF(X337="","",X337-TODAY())),IF(X337="","",X337-TODAY()))) | [14 empty] | IF(OR(F337="",AJ337=""),"",IF(COUNT(AI337:AI337)=0,"",AJ337-LOOKUP(2,1/(AI337:AI337<>""),AI337:AI337))) | IF(OR(F337="",AK337=""),"",IF(COUNT(AI337:AJ337)=0,"",AK337-LOOKUP(2,1/(AI337:AJ337<>""),AI337:AJ337))) | IF(OR(F337="",AL337=""),"",IF(COUNT(AI337:AK337)=0,"",AL337-LOOKUP(2,1/(AI337:AK337<>""),AI337:AK337))) | IF(OR(F337="",AM337=""),"",IF(COUNT(AI337:AL337)=0,"",AM337-LOOKUP(2,1/(AI337:AL337<>""),AI337:AL337))) | IF(OR(F337="",AN337=""),"",IF(COUNT(AI337:AM337)=0,"",AN337-LOOKUP(2,1/(AI337:AM337<>""),AI337:AM337))) | IF(OR(F337="",AO337=""),"",IF(COUNT(AI337:AN337)=0,"",AO337-LOOKUP(2,1/(AI337:AN337<>""),AI337:AN337))) | IF(OR(F337="",AP337=""),"",IF(COUNT(AI337:AO337)=0,"",AP337-LOOKUP(2,1/(AI337:AO337<>""),AI337:AO337))) | IF(OR(F337="",AQ337=""),"",IF(COUNT(AI337:AP337)=0,"",AQ337-LOOKUP(2,1/(AI337:AP337<>""),AI337:AP337))) | IF(OR(F337="",AR337=""),"",IF(COUNT(AI337:AQ337)=0,"",AR337-LOOKUP(2,1/(AI337:AQ337<>""),AI337:AQ337))) | IF(OR(F337="",AS337=""),"",IF(COUNT(AI337:AR337)=0,"",AS337-LOOKUP(2,1/(AI337:AR337<>""),AI337:AR337))) | IF(OR(F337="",AT337=""),"",IF(COUNT(AI337:AS337)=0,"",AT337-LOOKUP(2,1/(AI337:AS337<>""),AI337:AS337))) | IF(OR(F337="",AU337=""),"",IF(COUNT(AI337:AT337)=0,"",AU337-LOOKUP(2,1/(AI337:AT337<>""),AI337:AT337))) | IF(OR(F337="",AV337=""),"",IF(COUNT(AI337:AU337)=0,"",AV337-LOOKUP(2,1/(AI337:AU337<>""),AI337:AU337))) | IF(J337="","All_Provinces",IFERROR(VLOOKUP(J337,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K337="","All_Districts",IFERROR(VLOOKUP(K337,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F338="","",ROW()-3) | [18 empty] | IF(AQ338="","",AQ338) |  |  |  | IF(W338<>"",W338,IF(OR(T338="",V338=""),"",EDATE(T338,V338))) |  |  |  |  | IF(F338="","",IF(COUNT(AI338:AV338)=0,IF(AA338="","Not started",AA338),SUBSTITUTE(LOOKUP(2,1/(AI338:AV338<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F338="",COUNT(AI338:AV338)=0),"",TODAY()-LOOKUP(2,1/(AI338:AV338<>""),AI338:AV338)) | IF(OR(F338="",COUNT(AI338:AV338)<2),"",LOOKUP(2,1/(AI338:AV338<>""),AI338:AV338)-MIN(AI338:AV338)) | IF(OR(AD338="",AC338="Not started",AC338=""),"",IFERROR(AD338-IF(VLOOKUP(AC338,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC338,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F338="","",IF(OR(AA338="Cancelled",AC338="Cancelled"),"Cancelled",IF(OR(AC338="Completed / Handover",Y338<>"",Z338>=100),"Completed — on track",IF(O338="Not awarded",IF(U338="",IF(X338="","No planned date",IF(TODAY()>X338,"Behind — past planned date",IF(X338-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U338,"Behind — award date passed",IF(U338-TODAY()<=30,"At risk — close to off track","On track"))),IF(X338="","No planned date",IF(AND(TODAY()>X338,OR(Z338="",Z338<100)),"Behind — past end date",IF(AND(T338<>"",X338<>"",Z338<>"",(Z338<100),((TODAY()-T338)/MAX(X338-T338,1)*100)-Z338>15),"Behind — progress lag",IF(AND(X338-TODAY()<=30,X338-TODAY()>=0,OR(Z338="",Z338<90)),"At risk — close to off track","On track")))))))) | IF(OR(F338="",AC338="Completed / Handover",AC338="Cancelled"),"",IF(O338="Not awarded",IF(U338<>"",U338-TODAY(),IF(X338="","",X338-TODAY())),IF(X338="","",X338-TODAY()))) | [14 empty] | IF(OR(F338="",AJ338=""),"",IF(COUNT(AI338:AI338)=0,"",AJ338-LOOKUP(2,1/(AI338:AI338<>""),AI338:AI338))) | IF(OR(F338="",AK338=""),"",IF(COUNT(AI338:AJ338)=0,"",AK338-LOOKUP(2,1/(AI338:AJ338<>""),AI338:AJ338))) | IF(OR(F338="",AL338=""),"",IF(COUNT(AI338:AK338)=0,"",AL338-LOOKUP(2,1/(AI338:AK338<>""),AI338:AK338))) | IF(OR(F338="",AM338=""),"",IF(COUNT(AI338:AL338)=0,"",AM338-LOOKUP(2,1/(AI338:AL338<>""),AI338:AL338))) | IF(OR(F338="",AN338=""),"",IF(COUNT(AI338:AM338)=0,"",AN338-LOOKUP(2,1/(AI338:AM338<>""),AI338:AM338))) | IF(OR(F338="",AO338=""),"",IF(COUNT(AI338:AN338)=0,"",AO338-LOOKUP(2,1/(AI338:AN338<>""),AI338:AN338))) | IF(OR(F338="",AP338=""),"",IF(COUNT(AI338:AO338)=0,"",AP338-LOOKUP(2,1/(AI338:AO338<>""),AI338:AO338))) | IF(OR(F338="",AQ338=""),"",IF(COUNT(AI338:AP338)=0,"",AQ338-LOOKUP(2,1/(AI338:AP338<>""),AI338:AP338))) | IF(OR(F338="",AR338=""),"",IF(COUNT(AI338:AQ338)=0,"",AR338-LOOKUP(2,1/(AI338:AQ338<>""),AI338:AQ338))) | IF(OR(F338="",AS338=""),"",IF(COUNT(AI338:AR338)=0,"",AS338-LOOKUP(2,1/(AI338:AR338<>""),AI338:AR338))) | IF(OR(F338="",AT338=""),"",IF(COUNT(AI338:AS338)=0,"",AT338-LOOKUP(2,1/(AI338:AS338<>""),AI338:AS338))) | IF(OR(F338="",AU338=""),"",IF(COUNT(AI338:AT338)=0,"",AU338-LOOKUP(2,1/(AI338:AT338<>""),AI338:AT338))) | IF(OR(F338="",AV338=""),"",IF(COUNT(AI338:AU338)=0,"",AV338-LOOKUP(2,1/(AI338:AU338<>""),AI338:AU338))) | IF(J338="","All_Provinces",IFERROR(VLOOKUP(J338,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K338="","All_Districts",IFERROR(VLOOKUP(K338,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F339="","",ROW()-3) | [18 empty] | IF(AQ339="","",AQ339) |  |  |  | IF(W339<>"",W339,IF(OR(T339="",V339=""),"",EDATE(T339,V339))) |  |  |  |  | IF(F339="","",IF(COUNT(AI339:AV339)=0,IF(AA339="","Not started",AA339),SUBSTITUTE(LOOKUP(2,1/(AI339:AV339<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F339="",COUNT(AI339:AV339)=0),"",TODAY()-LOOKUP(2,1/(AI339:AV339<>""),AI339:AV339)) | IF(OR(F339="",COUNT(AI339:AV339)<2),"",LOOKUP(2,1/(AI339:AV339<>""),AI339:AV339)-MIN(AI339:AV339)) | IF(OR(AD339="",AC339="Not started",AC339=""),"",IFERROR(AD339-IF(VLOOKUP(AC339,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC339,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F339="","",IF(OR(AA339="Cancelled",AC339="Cancelled"),"Cancelled",IF(OR(AC339="Completed / Handover",Y339<>"",Z339>=100),"Completed — on track",IF(O339="Not awarded",IF(U339="",IF(X339="","No planned date",IF(TODAY()>X339,"Behind — past planned date",IF(X339-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U339,"Behind — award date passed",IF(U339-TODAY()<=30,"At risk — close to off track","On track"))),IF(X339="","No planned date",IF(AND(TODAY()>X339,OR(Z339="",Z339<100)),"Behind — past end date",IF(AND(T339<>"",X339<>"",Z339<>"",(Z339<100),((TODAY()-T339)/MAX(X339-T339,1)*100)-Z339>15),"Behind — progress lag",IF(AND(X339-TODAY()<=30,X339-TODAY()>=0,OR(Z339="",Z339<90)),"At risk — close to off track","On track")))))))) | IF(OR(F339="",AC339="Completed / Handover",AC339="Cancelled"),"",IF(O339="Not awarded",IF(U339<>"",U339-TODAY(),IF(X339="","",X339-TODAY())),IF(X339="","",X339-TODAY()))) | [14 empty] | IF(OR(F339="",AJ339=""),"",IF(COUNT(AI339:AI339)=0,"",AJ339-LOOKUP(2,1/(AI339:AI339<>""),AI339:AI339))) | IF(OR(F339="",AK339=""),"",IF(COUNT(AI339:AJ339)=0,"",AK339-LOOKUP(2,1/(AI339:AJ339<>""),AI339:AJ339))) | IF(OR(F339="",AL339=""),"",IF(COUNT(AI339:AK339)=0,"",AL339-LOOKUP(2,1/(AI339:AK339<>""),AI339:AK339))) | IF(OR(F339="",AM339=""),"",IF(COUNT(AI339:AL339)=0,"",AM339-LOOKUP(2,1/(AI339:AL339<>""),AI339:AL339))) | IF(OR(F339="",AN339=""),"",IF(COUNT(AI339:AM339)=0,"",AN339-LOOKUP(2,1/(AI339:AM339<>""),AI339:AM339))) | IF(OR(F339="",AO339=""),"",IF(COUNT(AI339:AN339)=0,"",AO339-LOOKUP(2,1/(AI339:AN339<>""),AI339:AN339))) | IF(OR(F339="",AP339=""),"",IF(COUNT(AI339:AO339)=0,"",AP339-LOOKUP(2,1/(AI339:AO339<>""),AI339:AO339))) | IF(OR(F339="",AQ339=""),"",IF(COUNT(AI339:AP339)=0,"",AQ339-LOOKUP(2,1/(AI339:AP339<>""),AI339:AP339))) | IF(OR(F339="",AR339=""),"",IF(COUNT(AI339:AQ339)=0,"",AR339-LOOKUP(2,1/(AI339:AQ339<>""),AI339:AQ339))) | IF(OR(F339="",AS339=""),"",IF(COUNT(AI339:AR339)=0,"",AS339-LOOKUP(2,1/(AI339:AR339<>""),AI339:AR339))) | IF(OR(F339="",AT339=""),"",IF(COUNT(AI339:AS339)=0,"",AT339-LOOKUP(2,1/(AI339:AS339<>""),AI339:AS339))) | IF(OR(F339="",AU339=""),"",IF(COUNT(AI339:AT339)=0,"",AU339-LOOKUP(2,1/(AI339:AT339<>""),AI339:AT339))) | IF(OR(F339="",AV339=""),"",IF(COUNT(AI339:AU339)=0,"",AV339-LOOKUP(2,1/(AI339:AU339<>""),AI339:AU339))) | IF(J339="","All_Provinces",IFERROR(VLOOKUP(J339,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K339="","All_Districts",IFERROR(VLOOKUP(K339,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F340="","",ROW()-3) | [18 empty] | IF(AQ340="","",AQ340) |  |  |  | IF(W340<>"",W340,IF(OR(T340="",V340=""),"",EDATE(T340,V340))) |  |  |  |  | IF(F340="","",IF(COUNT(AI340:AV340)=0,IF(AA340="","Not started",AA340),SUBSTITUTE(LOOKUP(2,1/(AI340:AV340<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F340="",COUNT(AI340:AV340)=0),"",TODAY()-LOOKUP(2,1/(AI340:AV340<>""),AI340:AV340)) | IF(OR(F340="",COUNT(AI340:AV340)<2),"",LOOKUP(2,1/(AI340:AV340<>""),AI340:AV340)-MIN(AI340:AV340)) | IF(OR(AD340="",AC340="Not started",AC340=""),"",IFERROR(AD340-IF(VLOOKUP(AC340,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC340,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F340="","",IF(OR(AA340="Cancelled",AC340="Cancelled"),"Cancelled",IF(OR(AC340="Completed / Handover",Y340<>"",Z340>=100),"Completed — on track",IF(O340="Not awarded",IF(U340="",IF(X340="","No planned date",IF(TODAY()>X340,"Behind — past planned date",IF(X340-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U340,"Behind — award date passed",IF(U340-TODAY()<=30,"At risk — close to off track","On track"))),IF(X340="","No planned date",IF(AND(TODAY()>X340,OR(Z340="",Z340<100)),"Behind — past end date",IF(AND(T340<>"",X340<>"",Z340<>"",(Z340<100),((TODAY()-T340)/MAX(X340-T340,1)*100)-Z340>15),"Behind — progress lag",IF(AND(X340-TODAY()<=30,X340-TODAY()>=0,OR(Z340="",Z340<90)),"At risk — close to off track","On track")))))))) | IF(OR(F340="",AC340="Completed / Handover",AC340="Cancelled"),"",IF(O340="Not awarded",IF(U340<>"",U340-TODAY(),IF(X340="","",X340-TODAY())),IF(X340="","",X340-TODAY()))) | [14 empty] | IF(OR(F340="",AJ340=""),"",IF(COUNT(AI340:AI340)=0,"",AJ340-LOOKUP(2,1/(AI340:AI340<>""),AI340:AI340))) | IF(OR(F340="",AK340=""),"",IF(COUNT(AI340:AJ340)=0,"",AK340-LOOKUP(2,1/(AI340:AJ340<>""),AI340:AJ340))) | IF(OR(F340="",AL340=""),"",IF(COUNT(AI340:AK340)=0,"",AL340-LOOKUP(2,1/(AI340:AK340<>""),AI340:AK340))) | IF(OR(F340="",AM340=""),"",IF(COUNT(AI340:AL340)=0,"",AM340-LOOKUP(2,1/(AI340:AL340<>""),AI340:AL340))) | IF(OR(F340="",AN340=""),"",IF(COUNT(AI340:AM340)=0,"",AN340-LOOKUP(2,1/(AI340:AM340<>""),AI340:AM340))) | IF(OR(F340="",AO340=""),"",IF(COUNT(AI340:AN340)=0,"",AO340-LOOKUP(2,1/(AI340:AN340<>""),AI340:AN340))) | IF(OR(F340="",AP340=""),"",IF(COUNT(AI340:AO340)=0,"",AP340-LOOKUP(2,1/(AI340:AO340<>""),AI340:AO340))) | IF(OR(F340="",AQ340=""),"",IF(COUNT(AI340:AP340)=0,"",AQ340-LOOKUP(2,1/(AI340:AP340<>""),AI340:AP340))) | IF(OR(F340="",AR340=""),"",IF(COUNT(AI340:AQ340)=0,"",AR340-LOOKUP(2,1/(AI340:AQ340<>""),AI340:AQ340))) | IF(OR(F340="",AS340=""),"",IF(COUNT(AI340:AR340)=0,"",AS340-LOOKUP(2,1/(AI340:AR340<>""),AI340:AR340))) | IF(OR(F340="",AT340=""),"",IF(COUNT(AI340:AS340)=0,"",AT340-LOOKUP(2,1/(AI340:AS340<>""),AI340:AS340))) | IF(OR(F340="",AU340=""),"",IF(COUNT(AI340:AT340)=0,"",AU340-LOOKUP(2,1/(AI340:AT340<>""),AI340:AT340))) | IF(OR(F340="",AV340=""),"",IF(COUNT(AI340:AU340)=0,"",AV340-LOOKUP(2,1/(AI340:AU340<>""),AI340:AU340))) | IF(J340="","All_Provinces",IFERROR(VLOOKUP(J340,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K340="","All_Districts",IFERROR(VLOOKUP(K340,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F341="","",ROW()-3) | [18 empty] | IF(AQ341="","",AQ341) |  |  |  | IF(W341<>"",W341,IF(OR(T341="",V341=""),"",EDATE(T341,V341))) |  |  |  |  | IF(F341="","",IF(COUNT(AI341:AV341)=0,IF(AA341="","Not started",AA341),SUBSTITUTE(LOOKUP(2,1/(AI341:AV341<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F341="",COUNT(AI341:AV341)=0),"",TODAY()-LOOKUP(2,1/(AI341:AV341<>""),AI341:AV341)) | IF(OR(F341="",COUNT(AI341:AV341)<2),"",LOOKUP(2,1/(AI341:AV341<>""),AI341:AV341)-MIN(AI341:AV341)) | IF(OR(AD341="",AC341="Not started",AC341=""),"",IFERROR(AD341-IF(VLOOKUP(AC341,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC341,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F341="","",IF(OR(AA341="Cancelled",AC341="Cancelled"),"Cancelled",IF(OR(AC341="Completed / Handover",Y341<>"",Z341>=100),"Completed — on track",IF(O341="Not awarded",IF(U341="",IF(X341="","No planned date",IF(TODAY()>X341,"Behind — past planned date",IF(X341-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U341,"Behind — award date passed",IF(U341-TODAY()<=30,"At risk — close to off track","On track"))),IF(X341="","No planned date",IF(AND(TODAY()>X341,OR(Z341="",Z341<100)),"Behind — past end date",IF(AND(T341<>"",X341<>"",Z341<>"",(Z341<100),((TODAY()-T341)/MAX(X341-T341,1)*100)-Z341>15),"Behind — progress lag",IF(AND(X341-TODAY()<=30,X341-TODAY()>=0,OR(Z341="",Z341<90)),"At risk — close to off track","On track")))))))) | IF(OR(F341="",AC341="Completed / Handover",AC341="Cancelled"),"",IF(O341="Not awarded",IF(U341<>"",U341-TODAY(),IF(X341="","",X341-TODAY())),IF(X341="","",X341-TODAY()))) | [14 empty] | IF(OR(F341="",AJ341=""),"",IF(COUNT(AI341:AI341)=0,"",AJ341-LOOKUP(2,1/(AI341:AI341<>""),AI341:AI341))) | IF(OR(F341="",AK341=""),"",IF(COUNT(AI341:AJ341)=0,"",AK341-LOOKUP(2,1/(AI341:AJ341<>""),AI341:AJ341))) | IF(OR(F341="",AL341=""),"",IF(COUNT(AI341:AK341)=0,"",AL341-LOOKUP(2,1/(AI341:AK341<>""),AI341:AK341))) | IF(OR(F341="",AM341=""),"",IF(COUNT(AI341:AL341)=0,"",AM341-LOOKUP(2,1/(AI341:AL341<>""),AI341:AL341))) | IF(OR(F341="",AN341=""),"",IF(COUNT(AI341:AM341)=0,"",AN341-LOOKUP(2,1/(AI341:AM341<>""),AI341:AM341))) | IF(OR(F341="",AO341=""),"",IF(COUNT(AI341:AN341)=0,"",AO341-LOOKUP(2,1/(AI341:AN341<>""),AI341:AN341))) | IF(OR(F341="",AP341=""),"",IF(COUNT(AI341:AO341)=0,"",AP341-LOOKUP(2,1/(AI341:AO341<>""),AI341:AO341))) | IF(OR(F341="",AQ341=""),"",IF(COUNT(AI341:AP341)=0,"",AQ341-LOOKUP(2,1/(AI341:AP341<>""),AI341:AP341))) | IF(OR(F341="",AR341=""),"",IF(COUNT(AI341:AQ341)=0,"",AR341-LOOKUP(2,1/(AI341:AQ341<>""),AI341:AQ341))) | IF(OR(F341="",AS341=""),"",IF(COUNT(AI341:AR341)=0,"",AS341-LOOKUP(2,1/(AI341:AR341<>""),AI341:AR341))) | IF(OR(F341="",AT341=""),"",IF(COUNT(AI341:AS341)=0,"",AT341-LOOKUP(2,1/(AI341:AS341<>""),AI341:AS341))) | IF(OR(F341="",AU341=""),"",IF(COUNT(AI341:AT341)=0,"",AU341-LOOKUP(2,1/(AI341:AT341<>""),AI341:AT341))) | IF(OR(F341="",AV341=""),"",IF(COUNT(AI341:AU341)=0,"",AV341-LOOKUP(2,1/(AI341:AU341<>""),AI341:AU341))) | IF(J341="","All_Provinces",IFERROR(VLOOKUP(J341,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K341="","All_Districts",IFERROR(VLOOKUP(K341,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F342="","",ROW()-3) | [18 empty] | IF(AQ342="","",AQ342) |  |  |  | IF(W342<>"",W342,IF(OR(T342="",V342=""),"",EDATE(T342,V342))) |  |  |  |  | IF(F342="","",IF(COUNT(AI342:AV342)=0,IF(AA342="","Not started",AA342),SUBSTITUTE(LOOKUP(2,1/(AI342:AV342<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F342="",COUNT(AI342:AV342)=0),"",TODAY()-LOOKUP(2,1/(AI342:AV342<>""),AI342:AV342)) | IF(OR(F342="",COUNT(AI342:AV342)<2),"",LOOKUP(2,1/(AI342:AV342<>""),AI342:AV342)-MIN(AI342:AV342)) | IF(OR(AD342="",AC342="Not started",AC342=""),"",IFERROR(AD342-IF(VLOOKUP(AC342,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC342,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F342="","",IF(OR(AA342="Cancelled",AC342="Cancelled"),"Cancelled",IF(OR(AC342="Completed / Handover",Y342<>"",Z342>=100),"Completed — on track",IF(O342="Not awarded",IF(U342="",IF(X342="","No planned date",IF(TODAY()>X342,"Behind — past planned date",IF(X342-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U342,"Behind — award date passed",IF(U342-TODAY()<=30,"At risk — close to off track","On track"))),IF(X342="","No planned date",IF(AND(TODAY()>X342,OR(Z342="",Z342<100)),"Behind — past end date",IF(AND(T342<>"",X342<>"",Z342<>"",(Z342<100),((TODAY()-T342)/MAX(X342-T342,1)*100)-Z342>15),"Behind — progress lag",IF(AND(X342-TODAY()<=30,X342-TODAY()>=0,OR(Z342="",Z342<90)),"At risk — close to off track","On track")))))))) | IF(OR(F342="",AC342="Completed / Handover",AC342="Cancelled"),"",IF(O342="Not awarded",IF(U342<>"",U342-TODAY(),IF(X342="","",X342-TODAY())),IF(X342="","",X342-TODAY()))) | [14 empty] | IF(OR(F342="",AJ342=""),"",IF(COUNT(AI342:AI342)=0,"",AJ342-LOOKUP(2,1/(AI342:AI342<>""),AI342:AI342))) | IF(OR(F342="",AK342=""),"",IF(COUNT(AI342:AJ342)=0,"",AK342-LOOKUP(2,1/(AI342:AJ342<>""),AI342:AJ342))) | IF(OR(F342="",AL342=""),"",IF(COUNT(AI342:AK342)=0,"",AL342-LOOKUP(2,1/(AI342:AK342<>""),AI342:AK342))) | IF(OR(F342="",AM342=""),"",IF(COUNT(AI342:AL342)=0,"",AM342-LOOKUP(2,1/(AI342:AL342<>""),AI342:AL342))) | IF(OR(F342="",AN342=""),"",IF(COUNT(AI342:AM342)=0,"",AN342-LOOKUP(2,1/(AI342:AM342<>""),AI342:AM342))) | IF(OR(F342="",AO342=""),"",IF(COUNT(AI342:AN342)=0,"",AO342-LOOKUP(2,1/(AI342:AN342<>""),AI342:AN342))) | IF(OR(F342="",AP342=""),"",IF(COUNT(AI342:AO342)=0,"",AP342-LOOKUP(2,1/(AI342:AO342<>""),AI342:AO342))) | IF(OR(F342="",AQ342=""),"",IF(COUNT(AI342:AP342)=0,"",AQ342-LOOKUP(2,1/(AI342:AP342<>""),AI342:AP342))) | IF(OR(F342="",AR342=""),"",IF(COUNT(AI342:AQ342)=0,"",AR342-LOOKUP(2,1/(AI342:AQ342<>""),AI342:AQ342))) | IF(OR(F342="",AS342=""),"",IF(COUNT(AI342:AR342)=0,"",AS342-LOOKUP(2,1/(AI342:AR342<>""),AI342:AR342))) | IF(OR(F342="",AT342=""),"",IF(COUNT(AI342:AS342)=0,"",AT342-LOOKUP(2,1/(AI342:AS342<>""),AI342:AS342))) | IF(OR(F342="",AU342=""),"",IF(COUNT(AI342:AT342)=0,"",AU342-LOOKUP(2,1/(AI342:AT342<>""),AI342:AT342))) | IF(OR(F342="",AV342=""),"",IF(COUNT(AI342:AU342)=0,"",AV342-LOOKUP(2,1/(AI342:AU342<>""),AI342:AU342))) | IF(J342="","All_Provinces",IFERROR(VLOOKUP(J342,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K342="","All_Districts",IFERROR(VLOOKUP(K342,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F343="","",ROW()-3) | [18 empty] | IF(AQ343="","",AQ343) |  |  |  | IF(W343<>"",W343,IF(OR(T343="",V343=""),"",EDATE(T343,V343))) |  |  |  |  | IF(F343="","",IF(COUNT(AI343:AV343)=0,IF(AA343="","Not started",AA343),SUBSTITUTE(LOOKUP(2,1/(AI343:AV343<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F343="",COUNT(AI343:AV343)=0),"",TODAY()-LOOKUP(2,1/(AI343:AV343<>""),AI343:AV343)) | IF(OR(F343="",COUNT(AI343:AV343)<2),"",LOOKUP(2,1/(AI343:AV343<>""),AI343:AV343)-MIN(AI343:AV343)) | IF(OR(AD343="",AC343="Not started",AC343=""),"",IFERROR(AD343-IF(VLOOKUP(AC343,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC343,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F343="","",IF(OR(AA343="Cancelled",AC343="Cancelled"),"Cancelled",IF(OR(AC343="Completed / Handover",Y343<>"",Z343>=100),"Completed — on track",IF(O343="Not awarded",IF(U343="",IF(X343="","No planned date",IF(TODAY()>X343,"Behind — past planned date",IF(X343-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U343,"Behind — award date passed",IF(U343-TODAY()<=30,"At risk — close to off track","On track"))),IF(X343="","No planned date",IF(AND(TODAY()>X343,OR(Z343="",Z343<100)),"Behind — past end date",IF(AND(T343<>"",X343<>"",Z343<>"",(Z343<100),((TODAY()-T343)/MAX(X343-T343,1)*100)-Z343>15),"Behind — progress lag",IF(AND(X343-TODAY()<=30,X343-TODAY()>=0,OR(Z343="",Z343<90)),"At risk — close to off track","On track")))))))) | IF(OR(F343="",AC343="Completed / Handover",AC343="Cancelled"),"",IF(O343="Not awarded",IF(U343<>"",U343-TODAY(),IF(X343="","",X343-TODAY())),IF(X343="","",X343-TODAY()))) | [14 empty] | IF(OR(F343="",AJ343=""),"",IF(COUNT(AI343:AI343)=0,"",AJ343-LOOKUP(2,1/(AI343:AI343<>""),AI343:AI343))) | IF(OR(F343="",AK343=""),"",IF(COUNT(AI343:AJ343)=0,"",AK343-LOOKUP(2,1/(AI343:AJ343<>""),AI343:AJ343))) | IF(OR(F343="",AL343=""),"",IF(COUNT(AI343:AK343)=0,"",AL343-LOOKUP(2,1/(AI343:AK343<>""),AI343:AK343))) | IF(OR(F343="",AM343=""),"",IF(COUNT(AI343:AL343)=0,"",AM343-LOOKUP(2,1/(AI343:AL343<>""),AI343:AL343))) | IF(OR(F343="",AN343=""),"",IF(COUNT(AI343:AM343)=0,"",AN343-LOOKUP(2,1/(AI343:AM343<>""),AI343:AM343))) | IF(OR(F343="",AO343=""),"",IF(COUNT(AI343:AN343)=0,"",AO343-LOOKUP(2,1/(AI343:AN343<>""),AI343:AN343))) | IF(OR(F343="",AP343=""),"",IF(COUNT(AI343:AO343)=0,"",AP343-LOOKUP(2,1/(AI343:AO343<>""),AI343:AO343))) | IF(OR(F343="",AQ343=""),"",IF(COUNT(AI343:AP343)=0,"",AQ343-LOOKUP(2,1/(AI343:AP343<>""),AI343:AP343))) | IF(OR(F343="",AR343=""),"",IF(COUNT(AI343:AQ343)=0,"",AR343-LOOKUP(2,1/(AI343:AQ343<>""),AI343:AQ343))) | IF(OR(F343="",AS343=""),"",IF(COUNT(AI343:AR343)=0,"",AS343-LOOKUP(2,1/(AI343:AR343<>""),AI343:AR343))) | IF(OR(F343="",AT343=""),"",IF(COUNT(AI343:AS343)=0,"",AT343-LOOKUP(2,1/(AI343:AS343<>""),AI343:AS343))) | IF(OR(F343="",AU343=""),"",IF(COUNT(AI343:AT343)=0,"",AU343-LOOKUP(2,1/(AI343:AT343<>""),AI343:AT343))) | IF(OR(F343="",AV343=""),"",IF(COUNT(AI343:AU343)=0,"",AV343-LOOKUP(2,1/(AI343:AU343<>""),AI343:AU343))) | IF(J343="","All_Provinces",IFERROR(VLOOKUP(J343,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K343="","All_Districts",IFERROR(VLOOKUP(K343,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F344="","",ROW()-3) | [18 empty] | IF(AQ344="","",AQ344) |  |  |  | IF(W344<>"",W344,IF(OR(T344="",V344=""),"",EDATE(T344,V344))) |  |  |  |  | IF(F344="","",IF(COUNT(AI344:AV344)=0,IF(AA344="","Not started",AA344),SUBSTITUTE(LOOKUP(2,1/(AI344:AV344<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F344="",COUNT(AI344:AV344)=0),"",TODAY()-LOOKUP(2,1/(AI344:AV344<>""),AI344:AV344)) | IF(OR(F344="",COUNT(AI344:AV344)<2),"",LOOKUP(2,1/(AI344:AV344<>""),AI344:AV344)-MIN(AI344:AV344)) | IF(OR(AD344="",AC344="Not started",AC344=""),"",IFERROR(AD344-IF(VLOOKUP(AC344,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC344,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F344="","",IF(OR(AA344="Cancelled",AC344="Cancelled"),"Cancelled",IF(OR(AC344="Completed / Handover",Y344<>"",Z344>=100),"Completed — on track",IF(O344="Not awarded",IF(U344="",IF(X344="","No planned date",IF(TODAY()>X344,"Behind — past planned date",IF(X344-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U344,"Behind — award date passed",IF(U344-TODAY()<=30,"At risk — close to off track","On track"))),IF(X344="","No planned date",IF(AND(TODAY()>X344,OR(Z344="",Z344<100)),"Behind — past end date",IF(AND(T344<>"",X344<>"",Z344<>"",(Z344<100),((TODAY()-T344)/MAX(X344-T344,1)*100)-Z344>15),"Behind — progress lag",IF(AND(X344-TODAY()<=30,X344-TODAY()>=0,OR(Z344="",Z344<90)),"At risk — close to off track","On track")))))))) | IF(OR(F344="",AC344="Completed / Handover",AC344="Cancelled"),"",IF(O344="Not awarded",IF(U344<>"",U344-TODAY(),IF(X344="","",X344-TODAY())),IF(X344="","",X344-TODAY()))) | [14 empty] | IF(OR(F344="",AJ344=""),"",IF(COUNT(AI344:AI344)=0,"",AJ344-LOOKUP(2,1/(AI344:AI344<>""),AI344:AI344))) | IF(OR(F344="",AK344=""),"",IF(COUNT(AI344:AJ344)=0,"",AK344-LOOKUP(2,1/(AI344:AJ344<>""),AI344:AJ344))) | IF(OR(F344="",AL344=""),"",IF(COUNT(AI344:AK344)=0,"",AL344-LOOKUP(2,1/(AI344:AK344<>""),AI344:AK344))) | IF(OR(F344="",AM344=""),"",IF(COUNT(AI344:AL344)=0,"",AM344-LOOKUP(2,1/(AI344:AL344<>""),AI344:AL344))) | IF(OR(F344="",AN344=""),"",IF(COUNT(AI344:AM344)=0,"",AN344-LOOKUP(2,1/(AI344:AM344<>""),AI344:AM344))) | IF(OR(F344="",AO344=""),"",IF(COUNT(AI344:AN344)=0,"",AO344-LOOKUP(2,1/(AI344:AN344<>""),AI344:AN344))) | IF(OR(F344="",AP344=""),"",IF(COUNT(AI344:AO344)=0,"",AP344-LOOKUP(2,1/(AI344:AO344<>""),AI344:AO344))) | IF(OR(F344="",AQ344=""),"",IF(COUNT(AI344:AP344)=0,"",AQ344-LOOKUP(2,1/(AI344:AP344<>""),AI344:AP344))) | IF(OR(F344="",AR344=""),"",IF(COUNT(AI344:AQ344)=0,"",AR344-LOOKUP(2,1/(AI344:AQ344<>""),AI344:AQ344))) | IF(OR(F344="",AS344=""),"",IF(COUNT(AI344:AR344)=0,"",AS344-LOOKUP(2,1/(AI344:AR344<>""),AI344:AR344))) | IF(OR(F344="",AT344=""),"",IF(COUNT(AI344:AS344)=0,"",AT344-LOOKUP(2,1/(AI344:AS344<>""),AI344:AS344))) | IF(OR(F344="",AU344=""),"",IF(COUNT(AI344:AT344)=0,"",AU344-LOOKUP(2,1/(AI344:AT344<>""),AI344:AT344))) | IF(OR(F344="",AV344=""),"",IF(COUNT(AI344:AU344)=0,"",AV344-LOOKUP(2,1/(AI344:AU344<>""),AI344:AU344))) | IF(J344="","All_Provinces",IFERROR(VLOOKUP(J344,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K344="","All_Districts",IFERROR(VLOOKUP(K344,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F345="","",ROW()-3) | [18 empty] | IF(AQ345="","",AQ345) |  |  |  | IF(W345<>"",W345,IF(OR(T345="",V345=""),"",EDATE(T345,V345))) |  |  |  |  | IF(F345="","",IF(COUNT(AI345:AV345)=0,IF(AA345="","Not started",AA345),SUBSTITUTE(LOOKUP(2,1/(AI345:AV345<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F345="",COUNT(AI345:AV345)=0),"",TODAY()-LOOKUP(2,1/(AI345:AV345<>""),AI345:AV345)) | IF(OR(F345="",COUNT(AI345:AV345)<2),"",LOOKUP(2,1/(AI345:AV345<>""),AI345:AV345)-MIN(AI345:AV345)) | IF(OR(AD345="",AC345="Not started",AC345=""),"",IFERROR(AD345-IF(VLOOKUP(AC345,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC345,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F345="","",IF(OR(AA345="Cancelled",AC345="Cancelled"),"Cancelled",IF(OR(AC345="Completed / Handover",Y345<>"",Z345>=100),"Completed — on track",IF(O345="Not awarded",IF(U345="",IF(X345="","No planned date",IF(TODAY()>X345,"Behind — past planned date",IF(X345-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U345,"Behind — award date passed",IF(U345-TODAY()<=30,"At risk — close to off track","On track"))),IF(X345="","No planned date",IF(AND(TODAY()>X345,OR(Z345="",Z345<100)),"Behind — past end date",IF(AND(T345<>"",X345<>"",Z345<>"",(Z345<100),((TODAY()-T345)/MAX(X345-T345,1)*100)-Z345>15),"Behind — progress lag",IF(AND(X345-TODAY()<=30,X345-TODAY()>=0,OR(Z345="",Z345<90)),"At risk — close to off track","On track")))))))) | IF(OR(F345="",AC345="Completed / Handover",AC345="Cancelled"),"",IF(O345="Not awarded",IF(U345<>"",U345-TODAY(),IF(X345="","",X345-TODAY())),IF(X345="","",X345-TODAY()))) | [14 empty] | IF(OR(F345="",AJ345=""),"",IF(COUNT(AI345:AI345)=0,"",AJ345-LOOKUP(2,1/(AI345:AI345<>""),AI345:AI345))) | IF(OR(F345="",AK345=""),"",IF(COUNT(AI345:AJ345)=0,"",AK345-LOOKUP(2,1/(AI345:AJ345<>""),AI345:AJ345))) | IF(OR(F345="",AL345=""),"",IF(COUNT(AI345:AK345)=0,"",AL345-LOOKUP(2,1/(AI345:AK345<>""),AI345:AK345))) | IF(OR(F345="",AM345=""),"",IF(COUNT(AI345:AL345)=0,"",AM345-LOOKUP(2,1/(AI345:AL345<>""),AI345:AL345))) | IF(OR(F345="",AN345=""),"",IF(COUNT(AI345:AM345)=0,"",AN345-LOOKUP(2,1/(AI345:AM345<>""),AI345:AM345))) | IF(OR(F345="",AO345=""),"",IF(COUNT(AI345:AN345)=0,"",AO345-LOOKUP(2,1/(AI345:AN345<>""),AI345:AN345))) | IF(OR(F345="",AP345=""),"",IF(COUNT(AI345:AO345)=0,"",AP345-LOOKUP(2,1/(AI345:AO345<>""),AI345:AO345))) | IF(OR(F345="",AQ345=""),"",IF(COUNT(AI345:AP345)=0,"",AQ345-LOOKUP(2,1/(AI345:AP345<>""),AI345:AP345))) | IF(OR(F345="",AR345=""),"",IF(COUNT(AI345:AQ345)=0,"",AR345-LOOKUP(2,1/(AI345:AQ345<>""),AI345:AQ345))) | IF(OR(F345="",AS345=""),"",IF(COUNT(AI345:AR345)=0,"",AS345-LOOKUP(2,1/(AI345:AR345<>""),AI345:AR345))) | IF(OR(F345="",AT345=""),"",IF(COUNT(AI345:AS345)=0,"",AT345-LOOKUP(2,1/(AI345:AS345<>""),AI345:AS345))) | IF(OR(F345="",AU345=""),"",IF(COUNT(AI345:AT345)=0,"",AU345-LOOKUP(2,1/(AI345:AT345<>""),AI345:AT345))) | IF(OR(F345="",AV345=""),"",IF(COUNT(AI345:AU345)=0,"",AV345-LOOKUP(2,1/(AI345:AU345<>""),AI345:AU345))) | IF(J345="","All_Provinces",IFERROR(VLOOKUP(J345,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K345="","All_Districts",IFERROR(VLOOKUP(K345,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F346="","",ROW()-3) | [18 empty] | IF(AQ346="","",AQ346) |  |  |  | IF(W346<>"",W346,IF(OR(T346="",V346=""),"",EDATE(T346,V346))) |  |  |  |  | IF(F346="","",IF(COUNT(AI346:AV346)=0,IF(AA346="","Not started",AA346),SUBSTITUTE(LOOKUP(2,1/(AI346:AV346<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F346="",COUNT(AI346:AV346)=0),"",TODAY()-LOOKUP(2,1/(AI346:AV346<>""),AI346:AV346)) | IF(OR(F346="",COUNT(AI346:AV346)<2),"",LOOKUP(2,1/(AI346:AV346<>""),AI346:AV346)-MIN(AI346:AV346)) | IF(OR(AD346="",AC346="Not started",AC346=""),"",IFERROR(AD346-IF(VLOOKUP(AC346,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC346,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F346="","",IF(OR(AA346="Cancelled",AC346="Cancelled"),"Cancelled",IF(OR(AC346="Completed / Handover",Y346<>"",Z346>=100),"Completed — on track",IF(O346="Not awarded",IF(U346="",IF(X346="","No planned date",IF(TODAY()>X346,"Behind — past planned date",IF(X346-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U346,"Behind — award date passed",IF(U346-TODAY()<=30,"At risk — close to off track","On track"))),IF(X346="","No planned date",IF(AND(TODAY()>X346,OR(Z346="",Z346<100)),"Behind — past end date",IF(AND(T346<>"",X346<>"",Z346<>"",(Z346<100),((TODAY()-T346)/MAX(X346-T346,1)*100)-Z346>15),"Behind — progress lag",IF(AND(X346-TODAY()<=30,X346-TODAY()>=0,OR(Z346="",Z346<90)),"At risk — close to off track","On track")))))))) | IF(OR(F346="",AC346="Completed / Handover",AC346="Cancelled"),"",IF(O346="Not awarded",IF(U346<>"",U346-TODAY(),IF(X346="","",X346-TODAY())),IF(X346="","",X346-TODAY()))) | [14 empty] | IF(OR(F346="",AJ346=""),"",IF(COUNT(AI346:AI346)=0,"",AJ346-LOOKUP(2,1/(AI346:AI346<>""),AI346:AI346))) | IF(OR(F346="",AK346=""),"",IF(COUNT(AI346:AJ346)=0,"",AK346-LOOKUP(2,1/(AI346:AJ346<>""),AI346:AJ346))) | IF(OR(F346="",AL346=""),"",IF(COUNT(AI346:AK346)=0,"",AL346-LOOKUP(2,1/(AI346:AK346<>""),AI346:AK346))) | IF(OR(F346="",AM346=""),"",IF(COUNT(AI346:AL346)=0,"",AM346-LOOKUP(2,1/(AI346:AL346<>""),AI346:AL346))) | IF(OR(F346="",AN346=""),"",IF(COUNT(AI346:AM346)=0,"",AN346-LOOKUP(2,1/(AI346:AM346<>""),AI346:AM346))) | IF(OR(F346="",AO346=""),"",IF(COUNT(AI346:AN346)=0,"",AO346-LOOKUP(2,1/(AI346:AN346<>""),AI346:AN346))) | IF(OR(F346="",AP346=""),"",IF(COUNT(AI346:AO346)=0,"",AP346-LOOKUP(2,1/(AI346:AO346<>""),AI346:AO346))) | IF(OR(F346="",AQ346=""),"",IF(COUNT(AI346:AP346)=0,"",AQ346-LOOKUP(2,1/(AI346:AP346<>""),AI346:AP346))) | IF(OR(F346="",AR346=""),"",IF(COUNT(AI346:AQ346)=0,"",AR346-LOOKUP(2,1/(AI346:AQ346<>""),AI346:AQ346))) | IF(OR(F346="",AS346=""),"",IF(COUNT(AI346:AR346)=0,"",AS346-LOOKUP(2,1/(AI346:AR346<>""),AI346:AR346))) | IF(OR(F346="",AT346=""),"",IF(COUNT(AI346:AS346)=0,"",AT346-LOOKUP(2,1/(AI346:AS346<>""),AI346:AS346))) | IF(OR(F346="",AU346=""),"",IF(COUNT(AI346:AT346)=0,"",AU346-LOOKUP(2,1/(AI346:AT346<>""),AI346:AT346))) | IF(OR(F346="",AV346=""),"",IF(COUNT(AI346:AU346)=0,"",AV346-LOOKUP(2,1/(AI346:AU346<>""),AI346:AU346))) | IF(J346="","All_Provinces",IFERROR(VLOOKUP(J346,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K346="","All_Districts",IFERROR(VLOOKUP(K346,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F347="","",ROW()-3) | [18 empty] | IF(AQ347="","",AQ347) |  |  |  | IF(W347<>"",W347,IF(OR(T347="",V347=""),"",EDATE(T347,V347))) |  |  |  |  | IF(F347="","",IF(COUNT(AI347:AV347)=0,IF(AA347="","Not started",AA347),SUBSTITUTE(LOOKUP(2,1/(AI347:AV347<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F347="",COUNT(AI347:AV347)=0),"",TODAY()-LOOKUP(2,1/(AI347:AV347<>""),AI347:AV347)) | IF(OR(F347="",COUNT(AI347:AV347)<2),"",LOOKUP(2,1/(AI347:AV347<>""),AI347:AV347)-MIN(AI347:AV347)) | IF(OR(AD347="",AC347="Not started",AC347=""),"",IFERROR(AD347-IF(VLOOKUP(AC347,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC347,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F347="","",IF(OR(AA347="Cancelled",AC347="Cancelled"),"Cancelled",IF(OR(AC347="Completed / Handover",Y347<>"",Z347>=100),"Completed — on track",IF(O347="Not awarded",IF(U347="",IF(X347="","No planned date",IF(TODAY()>X347,"Behind — past planned date",IF(X347-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U347,"Behind — award date passed",IF(U347-TODAY()<=30,"At risk — close to off track","On track"))),IF(X347="","No planned date",IF(AND(TODAY()>X347,OR(Z347="",Z347<100)),"Behind — past end date",IF(AND(T347<>"",X347<>"",Z347<>"",(Z347<100),((TODAY()-T347)/MAX(X347-T347,1)*100)-Z347>15),"Behind — progress lag",IF(AND(X347-TODAY()<=30,X347-TODAY()>=0,OR(Z347="",Z347<90)),"At risk — close to off track","On track")))))))) | IF(OR(F347="",AC347="Completed / Handover",AC347="Cancelled"),"",IF(O347="Not awarded",IF(U347<>"",U347-TODAY(),IF(X347="","",X347-TODAY())),IF(X347="","",X347-TODAY()))) | [14 empty] | IF(OR(F347="",AJ347=""),"",IF(COUNT(AI347:AI347)=0,"",AJ347-LOOKUP(2,1/(AI347:AI347<>""),AI347:AI347))) | IF(OR(F347="",AK347=""),"",IF(COUNT(AI347:AJ347)=0,"",AK347-LOOKUP(2,1/(AI347:AJ347<>""),AI347:AJ347))) | IF(OR(F347="",AL347=""),"",IF(COUNT(AI347:AK347)=0,"",AL347-LOOKUP(2,1/(AI347:AK347<>""),AI347:AK347))) | IF(OR(F347="",AM347=""),"",IF(COUNT(AI347:AL347)=0,"",AM347-LOOKUP(2,1/(AI347:AL347<>""),AI347:AL347))) | IF(OR(F347="",AN347=""),"",IF(COUNT(AI347:AM347)=0,"",AN347-LOOKUP(2,1/(AI347:AM347<>""),AI347:AM347))) | IF(OR(F347="",AO347=""),"",IF(COUNT(AI347:AN347)=0,"",AO347-LOOKUP(2,1/(AI347:AN347<>""),AI347:AN347))) | IF(OR(F347="",AP347=""),"",IF(COUNT(AI347:AO347)=0,"",AP347-LOOKUP(2,1/(AI347:AO347<>""),AI347:AO347))) | IF(OR(F347="",AQ347=""),"",IF(COUNT(AI347:AP347)=0,"",AQ347-LOOKUP(2,1/(AI347:AP347<>""),AI347:AP347))) | IF(OR(F347="",AR347=""),"",IF(COUNT(AI347:AQ347)=0,"",AR347-LOOKUP(2,1/(AI347:AQ347<>""),AI347:AQ347))) | IF(OR(F347="",AS347=""),"",IF(COUNT(AI347:AR347)=0,"",AS347-LOOKUP(2,1/(AI347:AR347<>""),AI347:AR347))) | IF(OR(F347="",AT347=""),"",IF(COUNT(AI347:AS347)=0,"",AT347-LOOKUP(2,1/(AI347:AS347<>""),AI347:AS347))) | IF(OR(F347="",AU347=""),"",IF(COUNT(AI347:AT347)=0,"",AU347-LOOKUP(2,1/(AI347:AT347<>""),AI347:AT347))) | IF(OR(F347="",AV347=""),"",IF(COUNT(AI347:AU347)=0,"",AV347-LOOKUP(2,1/(AI347:AU347<>""),AI347:AU347))) | IF(J347="","All_Provinces",IFERROR(VLOOKUP(J347,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K347="","All_Districts",IFERROR(VLOOKUP(K347,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F348="","",ROW()-3) | [18 empty] | IF(AQ348="","",AQ348) |  |  |  | IF(W348<>"",W348,IF(OR(T348="",V348=""),"",EDATE(T348,V348))) |  |  |  |  | IF(F348="","",IF(COUNT(AI348:AV348)=0,IF(AA348="","Not started",AA348),SUBSTITUTE(LOOKUP(2,1/(AI348:AV348<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F348="",COUNT(AI348:AV348)=0),"",TODAY()-LOOKUP(2,1/(AI348:AV348<>""),AI348:AV348)) | IF(OR(F348="",COUNT(AI348:AV348)<2),"",LOOKUP(2,1/(AI348:AV348<>""),AI348:AV348)-MIN(AI348:AV348)) | IF(OR(AD348="",AC348="Not started",AC348=""),"",IFERROR(AD348-IF(VLOOKUP(AC348,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC348,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F348="","",IF(OR(AA348="Cancelled",AC348="Cancelled"),"Cancelled",IF(OR(AC348="Completed / Handover",Y348<>"",Z348>=100),"Completed — on track",IF(O348="Not awarded",IF(U348="",IF(X348="","No planned date",IF(TODAY()>X348,"Behind — past planned date",IF(X348-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U348,"Behind — award date passed",IF(U348-TODAY()<=30,"At risk — close to off track","On track"))),IF(X348="","No planned date",IF(AND(TODAY()>X348,OR(Z348="",Z348<100)),"Behind — past end date",IF(AND(T348<>"",X348<>"",Z348<>"",(Z348<100),((TODAY()-T348)/MAX(X348-T348,1)*100)-Z348>15),"Behind — progress lag",IF(AND(X348-TODAY()<=30,X348-TODAY()>=0,OR(Z348="",Z348<90)),"At risk — close to off track","On track")))))))) | IF(OR(F348="",AC348="Completed / Handover",AC348="Cancelled"),"",IF(O348="Not awarded",IF(U348<>"",U348-TODAY(),IF(X348="","",X348-TODAY())),IF(X348="","",X348-TODAY()))) | [14 empty] | IF(OR(F348="",AJ348=""),"",IF(COUNT(AI348:AI348)=0,"",AJ348-LOOKUP(2,1/(AI348:AI348<>""),AI348:AI348))) | IF(OR(F348="",AK348=""),"",IF(COUNT(AI348:AJ348)=0,"",AK348-LOOKUP(2,1/(AI348:AJ348<>""),AI348:AJ348))) | IF(OR(F348="",AL348=""),"",IF(COUNT(AI348:AK348)=0,"",AL348-LOOKUP(2,1/(AI348:AK348<>""),AI348:AK348))) | IF(OR(F348="",AM348=""),"",IF(COUNT(AI348:AL348)=0,"",AM348-LOOKUP(2,1/(AI348:AL348<>""),AI348:AL348))) | IF(OR(F348="",AN348=""),"",IF(COUNT(AI348:AM348)=0,"",AN348-LOOKUP(2,1/(AI348:AM348<>""),AI348:AM348))) | IF(OR(F348="",AO348=""),"",IF(COUNT(AI348:AN348)=0,"",AO348-LOOKUP(2,1/(AI348:AN348<>""),AI348:AN348))) | IF(OR(F348="",AP348=""),"",IF(COUNT(AI348:AO348)=0,"",AP348-LOOKUP(2,1/(AI348:AO348<>""),AI348:AO348))) | IF(OR(F348="",AQ348=""),"",IF(COUNT(AI348:AP348)=0,"",AQ348-LOOKUP(2,1/(AI348:AP348<>""),AI348:AP348))) | IF(OR(F348="",AR348=""),"",IF(COUNT(AI348:AQ348)=0,"",AR348-LOOKUP(2,1/(AI348:AQ348<>""),AI348:AQ348))) | IF(OR(F348="",AS348=""),"",IF(COUNT(AI348:AR348)=0,"",AS348-LOOKUP(2,1/(AI348:AR348<>""),AI348:AR348))) | IF(OR(F348="",AT348=""),"",IF(COUNT(AI348:AS348)=0,"",AT348-LOOKUP(2,1/(AI348:AS348<>""),AI348:AS348))) | IF(OR(F348="",AU348=""),"",IF(COUNT(AI348:AT348)=0,"",AU348-LOOKUP(2,1/(AI348:AT348<>""),AI348:AT348))) | IF(OR(F348="",AV348=""),"",IF(COUNT(AI348:AU348)=0,"",AV348-LOOKUP(2,1/(AI348:AU348<>""),AI348:AU348))) | IF(J348="","All_Provinces",IFERROR(VLOOKUP(J348,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K348="","All_Districts",IFERROR(VLOOKUP(K348,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F349="","",ROW()-3) | [18 empty] | IF(AQ349="","",AQ349) |  |  |  | IF(W349<>"",W349,IF(OR(T349="",V349=""),"",EDATE(T349,V349))) |  |  |  |  | IF(F349="","",IF(COUNT(AI349:AV349)=0,IF(AA349="","Not started",AA349),SUBSTITUTE(LOOKUP(2,1/(AI349:AV349<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F349="",COUNT(AI349:AV349)=0),"",TODAY()-LOOKUP(2,1/(AI349:AV349<>""),AI349:AV349)) | IF(OR(F349="",COUNT(AI349:AV349)<2),"",LOOKUP(2,1/(AI349:AV349<>""),AI349:AV349)-MIN(AI349:AV349)) | IF(OR(AD349="",AC349="Not started",AC349=""),"",IFERROR(AD349-IF(VLOOKUP(AC349,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC349,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F349="","",IF(OR(AA349="Cancelled",AC349="Cancelled"),"Cancelled",IF(OR(AC349="Completed / Handover",Y349<>"",Z349>=100),"Completed — on track",IF(O349="Not awarded",IF(U349="",IF(X349="","No planned date",IF(TODAY()>X349,"Behind — past planned date",IF(X349-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U349,"Behind — award date passed",IF(U349-TODAY()<=30,"At risk — close to off track","On track"))),IF(X349="","No planned date",IF(AND(TODAY()>X349,OR(Z349="",Z349<100)),"Behind — past end date",IF(AND(T349<>"",X349<>"",Z349<>"",(Z349<100),((TODAY()-T349)/MAX(X349-T349,1)*100)-Z349>15),"Behind — progress lag",IF(AND(X349-TODAY()<=30,X349-TODAY()>=0,OR(Z349="",Z349<90)),"At risk — close to off track","On track")))))))) | IF(OR(F349="",AC349="Completed / Handover",AC349="Cancelled"),"",IF(O349="Not awarded",IF(U349<>"",U349-TODAY(),IF(X349="","",X349-TODAY())),IF(X349="","",X349-TODAY()))) | [14 empty] | IF(OR(F349="",AJ349=""),"",IF(COUNT(AI349:AI349)=0,"",AJ349-LOOKUP(2,1/(AI349:AI349<>""),AI349:AI349))) | IF(OR(F349="",AK349=""),"",IF(COUNT(AI349:AJ349)=0,"",AK349-LOOKUP(2,1/(AI349:AJ349<>""),AI349:AJ349))) | IF(OR(F349="",AL349=""),"",IF(COUNT(AI349:AK349)=0,"",AL349-LOOKUP(2,1/(AI349:AK349<>""),AI349:AK349))) | IF(OR(F349="",AM349=""),"",IF(COUNT(AI349:AL349)=0,"",AM349-LOOKUP(2,1/(AI349:AL349<>""),AI349:AL349))) | IF(OR(F349="",AN349=""),"",IF(COUNT(AI349:AM349)=0,"",AN349-LOOKUP(2,1/(AI349:AM349<>""),AI349:AM349))) | IF(OR(F349="",AO349=""),"",IF(COUNT(AI349:AN349)=0,"",AO349-LOOKUP(2,1/(AI349:AN349<>""),AI349:AN349))) | IF(OR(F349="",AP349=""),"",IF(COUNT(AI349:AO349)=0,"",AP349-LOOKUP(2,1/(AI349:AO349<>""),AI349:AO349))) | IF(OR(F349="",AQ349=""),"",IF(COUNT(AI349:AP349)=0,"",AQ349-LOOKUP(2,1/(AI349:AP349<>""),AI349:AP349))) | IF(OR(F349="",AR349=""),"",IF(COUNT(AI349:AQ349)=0,"",AR349-LOOKUP(2,1/(AI349:AQ349<>""),AI349:AQ349))) | IF(OR(F349="",AS349=""),"",IF(COUNT(AI349:AR349)=0,"",AS349-LOOKUP(2,1/(AI349:AR349<>""),AI349:AR349))) | IF(OR(F349="",AT349=""),"",IF(COUNT(AI349:AS349)=0,"",AT349-LOOKUP(2,1/(AI349:AS349<>""),AI349:AS349))) | IF(OR(F349="",AU349=""),"",IF(COUNT(AI349:AT349)=0,"",AU349-LOOKUP(2,1/(AI349:AT349<>""),AI349:AT349))) | IF(OR(F349="",AV349=""),"",IF(COUNT(AI349:AU349)=0,"",AV349-LOOKUP(2,1/(AI349:AU349<>""),AI349:AU349))) | IF(J349="","All_Provinces",IFERROR(VLOOKUP(J349,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K349="","All_Districts",IFERROR(VLOOKUP(K349,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F350="","",ROW()-3) | [18 empty] | IF(AQ350="","",AQ350) |  |  |  | IF(W350<>"",W350,IF(OR(T350="",V350=""),"",EDATE(T350,V350))) |  |  |  |  | IF(F350="","",IF(COUNT(AI350:AV350)=0,IF(AA350="","Not started",AA350),SUBSTITUTE(LOOKUP(2,1/(AI350:AV350<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F350="",COUNT(AI350:AV350)=0),"",TODAY()-LOOKUP(2,1/(AI350:AV350<>""),AI350:AV350)) | IF(OR(F350="",COUNT(AI350:AV350)<2),"",LOOKUP(2,1/(AI350:AV350<>""),AI350:AV350)-MIN(AI350:AV350)) | IF(OR(AD350="",AC350="Not started",AC350=""),"",IFERROR(AD350-IF(VLOOKUP(AC350,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC350,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F350="","",IF(OR(AA350="Cancelled",AC350="Cancelled"),"Cancelled",IF(OR(AC350="Completed / Handover",Y350<>"",Z350>=100),"Completed — on track",IF(O350="Not awarded",IF(U350="",IF(X350="","No planned date",IF(TODAY()>X350,"Behind — past planned date",IF(X350-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U350,"Behind — award date passed",IF(U350-TODAY()<=30,"At risk — close to off track","On track"))),IF(X350="","No planned date",IF(AND(TODAY()>X350,OR(Z350="",Z350<100)),"Behind — past end date",IF(AND(T350<>"",X350<>"",Z350<>"",(Z350<100),((TODAY()-T350)/MAX(X350-T350,1)*100)-Z350>15),"Behind — progress lag",IF(AND(X350-TODAY()<=30,X350-TODAY()>=0,OR(Z350="",Z350<90)),"At risk — close to off track","On track")))))))) | IF(OR(F350="",AC350="Completed / Handover",AC350="Cancelled"),"",IF(O350="Not awarded",IF(U350<>"",U350-TODAY(),IF(X350="","",X350-TODAY())),IF(X350="","",X350-TODAY()))) | [14 empty] | IF(OR(F350="",AJ350=""),"",IF(COUNT(AI350:AI350)=0,"",AJ350-LOOKUP(2,1/(AI350:AI350<>""),AI350:AI350))) | IF(OR(F350="",AK350=""),"",IF(COUNT(AI350:AJ350)=0,"",AK350-LOOKUP(2,1/(AI350:AJ350<>""),AI350:AJ350))) | IF(OR(F350="",AL350=""),"",IF(COUNT(AI350:AK350)=0,"",AL350-LOOKUP(2,1/(AI350:AK350<>""),AI350:AK350))) | IF(OR(F350="",AM350=""),"",IF(COUNT(AI350:AL350)=0,"",AM350-LOOKUP(2,1/(AI350:AL350<>""),AI350:AL350))) | IF(OR(F350="",AN350=""),"",IF(COUNT(AI350:AM350)=0,"",AN350-LOOKUP(2,1/(AI350:AM350<>""),AI350:AM350))) | IF(OR(F350="",AO350=""),"",IF(COUNT(AI350:AN350)=0,"",AO350-LOOKUP(2,1/(AI350:AN350<>""),AI350:AN350))) | IF(OR(F350="",AP350=""),"",IF(COUNT(AI350:AO350)=0,"",AP350-LOOKUP(2,1/(AI350:AO350<>""),AI350:AO350))) | IF(OR(F350="",AQ350=""),"",IF(COUNT(AI350:AP350)=0,"",AQ350-LOOKUP(2,1/(AI350:AP350<>""),AI350:AP350))) | IF(OR(F350="",AR350=""),"",IF(COUNT(AI350:AQ350)=0,"",AR350-LOOKUP(2,1/(AI350:AQ350<>""),AI350:AQ350))) | IF(OR(F350="",AS350=""),"",IF(COUNT(AI350:AR350)=0,"",AS350-LOOKUP(2,1/(AI350:AR350<>""),AI350:AR350))) | IF(OR(F350="",AT350=""),"",IF(COUNT(AI350:AS350)=0,"",AT350-LOOKUP(2,1/(AI350:AS350<>""),AI350:AS350))) | IF(OR(F350="",AU350=""),"",IF(COUNT(AI350:AT350)=0,"",AU350-LOOKUP(2,1/(AI350:AT350<>""),AI350:AT350))) | IF(OR(F350="",AV350=""),"",IF(COUNT(AI350:AU350)=0,"",AV350-LOOKUP(2,1/(AI350:AU350<>""),AI350:AU350))) | IF(J350="","All_Provinces",IFERROR(VLOOKUP(J350,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K350="","All_Districts",IFERROR(VLOOKUP(K350,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F351="","",ROW()-3) | [18 empty] | IF(AQ351="","",AQ351) |  |  |  | IF(W351<>"",W351,IF(OR(T351="",V351=""),"",EDATE(T351,V351))) |  |  |  |  | IF(F351="","",IF(COUNT(AI351:AV351)=0,IF(AA351="","Not started",AA351),SUBSTITUTE(LOOKUP(2,1/(AI351:AV351<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F351="",COUNT(AI351:AV351)=0),"",TODAY()-LOOKUP(2,1/(AI351:AV351<>""),AI351:AV351)) | IF(OR(F351="",COUNT(AI351:AV351)<2),"",LOOKUP(2,1/(AI351:AV351<>""),AI351:AV351)-MIN(AI351:AV351)) | IF(OR(AD351="",AC351="Not started",AC351=""),"",IFERROR(AD351-IF(VLOOKUP(AC351,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC351,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F351="","",IF(OR(AA351="Cancelled",AC351="Cancelled"),"Cancelled",IF(OR(AC351="Completed / Handover",Y351<>"",Z351>=100),"Completed — on track",IF(O351="Not awarded",IF(U351="",IF(X351="","No planned date",IF(TODAY()>X351,"Behind — past planned date",IF(X351-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U351,"Behind — award date passed",IF(U351-TODAY()<=30,"At risk — close to off track","On track"))),IF(X351="","No planned date",IF(AND(TODAY()>X351,OR(Z351="",Z351<100)),"Behind — past end date",IF(AND(T351<>"",X351<>"",Z351<>"",(Z351<100),((TODAY()-T351)/MAX(X351-T351,1)*100)-Z351>15),"Behind — progress lag",IF(AND(X351-TODAY()<=30,X351-TODAY()>=0,OR(Z351="",Z351<90)),"At risk — close to off track","On track")))))))) | IF(OR(F351="",AC351="Completed / Handover",AC351="Cancelled"),"",IF(O351="Not awarded",IF(U351<>"",U351-TODAY(),IF(X351="","",X351-TODAY())),IF(X351="","",X351-TODAY()))) | [14 empty] | IF(OR(F351="",AJ351=""),"",IF(COUNT(AI351:AI351)=0,"",AJ351-LOOKUP(2,1/(AI351:AI351<>""),AI351:AI351))) | IF(OR(F351="",AK351=""),"",IF(COUNT(AI351:AJ351)=0,"",AK351-LOOKUP(2,1/(AI351:AJ351<>""),AI351:AJ351))) | IF(OR(F351="",AL351=""),"",IF(COUNT(AI351:AK351)=0,"",AL351-LOOKUP(2,1/(AI351:AK351<>""),AI351:AK351))) | IF(OR(F351="",AM351=""),"",IF(COUNT(AI351:AL351)=0,"",AM351-LOOKUP(2,1/(AI351:AL351<>""),AI351:AL351))) | IF(OR(F351="",AN351=""),"",IF(COUNT(AI351:AM351)=0,"",AN351-LOOKUP(2,1/(AI351:AM351<>""),AI351:AM351))) | IF(OR(F351="",AO351=""),"",IF(COUNT(AI351:AN351)=0,"",AO351-LOOKUP(2,1/(AI351:AN351<>""),AI351:AN351))) | IF(OR(F351="",AP351=""),"",IF(COUNT(AI351:AO351)=0,"",AP351-LOOKUP(2,1/(AI351:AO351<>""),AI351:AO351))) | IF(OR(F351="",AQ351=""),"",IF(COUNT(AI351:AP351)=0,"",AQ351-LOOKUP(2,1/(AI351:AP351<>""),AI351:AP351))) | IF(OR(F351="",AR351=""),"",IF(COUNT(AI351:AQ351)=0,"",AR351-LOOKUP(2,1/(AI351:AQ351<>""),AI351:AQ351))) | IF(OR(F351="",AS351=""),"",IF(COUNT(AI351:AR351)=0,"",AS351-LOOKUP(2,1/(AI351:AR351<>""),AI351:AR351))) | IF(OR(F351="",AT351=""),"",IF(COUNT(AI351:AS351)=0,"",AT351-LOOKUP(2,1/(AI351:AS351<>""),AI351:AS351))) | IF(OR(F351="",AU351=""),"",IF(COUNT(AI351:AT351)=0,"",AU351-LOOKUP(2,1/(AI351:AT351<>""),AI351:AT351))) | IF(OR(F351="",AV351=""),"",IF(COUNT(AI351:AU351)=0,"",AV351-LOOKUP(2,1/(AI351:AU351<>""),AI351:AU351))) | IF(J351="","All_Provinces",IFERROR(VLOOKUP(J351,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K351="","All_Districts",IFERROR(VLOOKUP(K351,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F352="","",ROW()-3) | [18 empty] | IF(AQ352="","",AQ352) |  |  |  | IF(W352<>"",W352,IF(OR(T352="",V352=""),"",EDATE(T352,V352))) |  |  |  |  | IF(F352="","",IF(COUNT(AI352:AV352)=0,IF(AA352="","Not started",AA352),SUBSTITUTE(LOOKUP(2,1/(AI352:AV352<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F352="",COUNT(AI352:AV352)=0),"",TODAY()-LOOKUP(2,1/(AI352:AV352<>""),AI352:AV352)) | IF(OR(F352="",COUNT(AI352:AV352)<2),"",LOOKUP(2,1/(AI352:AV352<>""),AI352:AV352)-MIN(AI352:AV352)) | IF(OR(AD352="",AC352="Not started",AC352=""),"",IFERROR(AD352-IF(VLOOKUP(AC352,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC352,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F352="","",IF(OR(AA352="Cancelled",AC352="Cancelled"),"Cancelled",IF(OR(AC352="Completed / Handover",Y352<>"",Z352>=100),"Completed — on track",IF(O352="Not awarded",IF(U352="",IF(X352="","No planned date",IF(TODAY()>X352,"Behind — past planned date",IF(X352-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U352,"Behind — award date passed",IF(U352-TODAY()<=30,"At risk — close to off track","On track"))),IF(X352="","No planned date",IF(AND(TODAY()>X352,OR(Z352="",Z352<100)),"Behind — past end date",IF(AND(T352<>"",X352<>"",Z352<>"",(Z352<100),((TODAY()-T352)/MAX(X352-T352,1)*100)-Z352>15),"Behind — progress lag",IF(AND(X352-TODAY()<=30,X352-TODAY()>=0,OR(Z352="",Z352<90)),"At risk — close to off track","On track")))))))) | IF(OR(F352="",AC352="Completed / Handover",AC352="Cancelled"),"",IF(O352="Not awarded",IF(U352<>"",U352-TODAY(),IF(X352="","",X352-TODAY())),IF(X352="","",X352-TODAY()))) | [14 empty] | IF(OR(F352="",AJ352=""),"",IF(COUNT(AI352:AI352)=0,"",AJ352-LOOKUP(2,1/(AI352:AI352<>""),AI352:AI352))) | IF(OR(F352="",AK352=""),"",IF(COUNT(AI352:AJ352)=0,"",AK352-LOOKUP(2,1/(AI352:AJ352<>""),AI352:AJ352))) | IF(OR(F352="",AL352=""),"",IF(COUNT(AI352:AK352)=0,"",AL352-LOOKUP(2,1/(AI352:AK352<>""),AI352:AK352))) | IF(OR(F352="",AM352=""),"",IF(COUNT(AI352:AL352)=0,"",AM352-LOOKUP(2,1/(AI352:AL352<>""),AI352:AL352))) | IF(OR(F352="",AN352=""),"",IF(COUNT(AI352:AM352)=0,"",AN352-LOOKUP(2,1/(AI352:AM352<>""),AI352:AM352))) | IF(OR(F352="",AO352=""),"",IF(COUNT(AI352:AN352)=0,"",AO352-LOOKUP(2,1/(AI352:AN352<>""),AI352:AN352))) | IF(OR(F352="",AP352=""),"",IF(COUNT(AI352:AO352)=0,"",AP352-LOOKUP(2,1/(AI352:AO352<>""),AI352:AO352))) | IF(OR(F352="",AQ352=""),"",IF(COUNT(AI352:AP352)=0,"",AQ352-LOOKUP(2,1/(AI352:AP352<>""),AI352:AP352))) | IF(OR(F352="",AR352=""),"",IF(COUNT(AI352:AQ352)=0,"",AR352-LOOKUP(2,1/(AI352:AQ352<>""),AI352:AQ352))) | IF(OR(F352="",AS352=""),"",IF(COUNT(AI352:AR352)=0,"",AS352-LOOKUP(2,1/(AI352:AR352<>""),AI352:AR352))) | IF(OR(F352="",AT352=""),"",IF(COUNT(AI352:AS352)=0,"",AT352-LOOKUP(2,1/(AI352:AS352<>""),AI352:AS352))) | IF(OR(F352="",AU352=""),"",IF(COUNT(AI352:AT352)=0,"",AU352-LOOKUP(2,1/(AI352:AT352<>""),AI352:AT352))) | IF(OR(F352="",AV352=""),"",IF(COUNT(AI352:AU352)=0,"",AV352-LOOKUP(2,1/(AI352:AU352<>""),AI352:AU352))) | IF(J352="","All_Provinces",IFERROR(VLOOKUP(J352,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K352="","All_Districts",IFERROR(VLOOKUP(K352,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F353="","",ROW()-3) | [18 empty] | IF(AQ353="","",AQ353) |  |  |  | IF(W353<>"",W353,IF(OR(T353="",V353=""),"",EDATE(T353,V353))) |  |  |  |  | IF(F353="","",IF(COUNT(AI353:AV353)=0,IF(AA353="","Not started",AA353),SUBSTITUTE(LOOKUP(2,1/(AI353:AV353<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F353="",COUNT(AI353:AV353)=0),"",TODAY()-LOOKUP(2,1/(AI353:AV353<>""),AI353:AV353)) | IF(OR(F353="",COUNT(AI353:AV353)<2),"",LOOKUP(2,1/(AI353:AV353<>""),AI353:AV353)-MIN(AI353:AV353)) | IF(OR(AD353="",AC353="Not started",AC353=""),"",IFERROR(AD353-IF(VLOOKUP(AC353,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC353,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F353="","",IF(OR(AA353="Cancelled",AC353="Cancelled"),"Cancelled",IF(OR(AC353="Completed / Handover",Y353<>"",Z353>=100),"Completed — on track",IF(O353="Not awarded",IF(U353="",IF(X353="","No planned date",IF(TODAY()>X353,"Behind — past planned date",IF(X353-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U353,"Behind — award date passed",IF(U353-TODAY()<=30,"At risk — close to off track","On track"))),IF(X353="","No planned date",IF(AND(TODAY()>X353,OR(Z353="",Z353<100)),"Behind — past end date",IF(AND(T353<>"",X353<>"",Z353<>"",(Z353<100),((TODAY()-T353)/MAX(X353-T353,1)*100)-Z353>15),"Behind — progress lag",IF(AND(X353-TODAY()<=30,X353-TODAY()>=0,OR(Z353="",Z353<90)),"At risk — close to off track","On track")))))))) | IF(OR(F353="",AC353="Completed / Handover",AC353="Cancelled"),"",IF(O353="Not awarded",IF(U353<>"",U353-TODAY(),IF(X353="","",X353-TODAY())),IF(X353="","",X353-TODAY()))) | [14 empty] | IF(OR(F353="",AJ353=""),"",IF(COUNT(AI353:AI353)=0,"",AJ353-LOOKUP(2,1/(AI353:AI353<>""),AI353:AI353))) | IF(OR(F353="",AK353=""),"",IF(COUNT(AI353:AJ353)=0,"",AK353-LOOKUP(2,1/(AI353:AJ353<>""),AI353:AJ353))) | IF(OR(F353="",AL353=""),"",IF(COUNT(AI353:AK353)=0,"",AL353-LOOKUP(2,1/(AI353:AK353<>""),AI353:AK353))) | IF(OR(F353="",AM353=""),"",IF(COUNT(AI353:AL353)=0,"",AM353-LOOKUP(2,1/(AI353:AL353<>""),AI353:AL353))) | IF(OR(F353="",AN353=""),"",IF(COUNT(AI353:AM353)=0,"",AN353-LOOKUP(2,1/(AI353:AM353<>""),AI353:AM353))) | IF(OR(F353="",AO353=""),"",IF(COUNT(AI353:AN353)=0,"",AO353-LOOKUP(2,1/(AI353:AN353<>""),AI353:AN353))) | IF(OR(F353="",AP353=""),"",IF(COUNT(AI353:AO353)=0,"",AP353-LOOKUP(2,1/(AI353:AO353<>""),AI353:AO353))) | IF(OR(F353="",AQ353=""),"",IF(COUNT(AI353:AP353)=0,"",AQ353-LOOKUP(2,1/(AI353:AP353<>""),AI353:AP353))) | IF(OR(F353="",AR353=""),"",IF(COUNT(AI353:AQ353)=0,"",AR353-LOOKUP(2,1/(AI353:AQ353<>""),AI353:AQ353))) | IF(OR(F353="",AS353=""),"",IF(COUNT(AI353:AR353)=0,"",AS353-LOOKUP(2,1/(AI353:AR353<>""),AI353:AR353))) | IF(OR(F353="",AT353=""),"",IF(COUNT(AI353:AS353)=0,"",AT353-LOOKUP(2,1/(AI353:AS353<>""),AI353:AS353))) | IF(OR(F353="",AU353=""),"",IF(COUNT(AI353:AT353)=0,"",AU353-LOOKUP(2,1/(AI353:AT353<>""),AI353:AT353))) | IF(OR(F353="",AV353=""),"",IF(COUNT(AI353:AU353)=0,"",AV353-LOOKUP(2,1/(AI353:AU353<>""),AI353:AU353))) | IF(J353="","All_Provinces",IFERROR(VLOOKUP(J353,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K353="","All_Districts",IFERROR(VLOOKUP(K353,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F354="","",ROW()-3) | [18 empty] | IF(AQ354="","",AQ354) |  |  |  | IF(W354<>"",W354,IF(OR(T354="",V354=""),"",EDATE(T354,V354))) |  |  |  |  | IF(F354="","",IF(COUNT(AI354:AV354)=0,IF(AA354="","Not started",AA354),SUBSTITUTE(LOOKUP(2,1/(AI354:AV354<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F354="",COUNT(AI354:AV354)=0),"",TODAY()-LOOKUP(2,1/(AI354:AV354<>""),AI354:AV354)) | IF(OR(F354="",COUNT(AI354:AV354)<2),"",LOOKUP(2,1/(AI354:AV354<>""),AI354:AV354)-MIN(AI354:AV354)) | IF(OR(AD354="",AC354="Not started",AC354=""),"",IFERROR(AD354-IF(VLOOKUP(AC354,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC354,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F354="","",IF(OR(AA354="Cancelled",AC354="Cancelled"),"Cancelled",IF(OR(AC354="Completed / Handover",Y354<>"",Z354>=100),"Completed — on track",IF(O354="Not awarded",IF(U354="",IF(X354="","No planned date",IF(TODAY()>X354,"Behind — past planned date",IF(X354-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U354,"Behind — award date passed",IF(U354-TODAY()<=30,"At risk — close to off track","On track"))),IF(X354="","No planned date",IF(AND(TODAY()>X354,OR(Z354="",Z354<100)),"Behind — past end date",IF(AND(T354<>"",X354<>"",Z354<>"",(Z354<100),((TODAY()-T354)/MAX(X354-T354,1)*100)-Z354>15),"Behind — progress lag",IF(AND(X354-TODAY()<=30,X354-TODAY()>=0,OR(Z354="",Z354<90)),"At risk — close to off track","On track")))))))) | IF(OR(F354="",AC354="Completed / Handover",AC354="Cancelled"),"",IF(O354="Not awarded",IF(U354<>"",U354-TODAY(),IF(X354="","",X354-TODAY())),IF(X354="","",X354-TODAY()))) | [14 empty] | IF(OR(F354="",AJ354=""),"",IF(COUNT(AI354:AI354)=0,"",AJ354-LOOKUP(2,1/(AI354:AI354<>""),AI354:AI354))) | IF(OR(F354="",AK354=""),"",IF(COUNT(AI354:AJ354)=0,"",AK354-LOOKUP(2,1/(AI354:AJ354<>""),AI354:AJ354))) | IF(OR(F354="",AL354=""),"",IF(COUNT(AI354:AK354)=0,"",AL354-LOOKUP(2,1/(AI354:AK354<>""),AI354:AK354))) | IF(OR(F354="",AM354=""),"",IF(COUNT(AI354:AL354)=0,"",AM354-LOOKUP(2,1/(AI354:AL354<>""),AI354:AL354))) | IF(OR(F354="",AN354=""),"",IF(COUNT(AI354:AM354)=0,"",AN354-LOOKUP(2,1/(AI354:AM354<>""),AI354:AM354))) | IF(OR(F354="",AO354=""),"",IF(COUNT(AI354:AN354)=0,"",AO354-LOOKUP(2,1/(AI354:AN354<>""),AI354:AN354))) | IF(OR(F354="",AP354=""),"",IF(COUNT(AI354:AO354)=0,"",AP354-LOOKUP(2,1/(AI354:AO354<>""),AI354:AO354))) | IF(OR(F354="",AQ354=""),"",IF(COUNT(AI354:AP354)=0,"",AQ354-LOOKUP(2,1/(AI354:AP354<>""),AI354:AP354))) | IF(OR(F354="",AR354=""),"",IF(COUNT(AI354:AQ354)=0,"",AR354-LOOKUP(2,1/(AI354:AQ354<>""),AI354:AQ354))) | IF(OR(F354="",AS354=""),"",IF(COUNT(AI354:AR354)=0,"",AS354-LOOKUP(2,1/(AI354:AR354<>""),AI354:AR354))) | IF(OR(F354="",AT354=""),"",IF(COUNT(AI354:AS354)=0,"",AT354-LOOKUP(2,1/(AI354:AS354<>""),AI354:AS354))) | IF(OR(F354="",AU354=""),"",IF(COUNT(AI354:AT354)=0,"",AU354-LOOKUP(2,1/(AI354:AT354<>""),AI354:AT354))) | IF(OR(F354="",AV354=""),"",IF(COUNT(AI354:AU354)=0,"",AV354-LOOKUP(2,1/(AI354:AU354<>""),AI354:AU354))) | IF(J354="","All_Provinces",IFERROR(VLOOKUP(J354,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K354="","All_Districts",IFERROR(VLOOKUP(K354,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F355="","",ROW()-3) | [18 empty] | IF(AQ355="","",AQ355) |  |  |  | IF(W355<>"",W355,IF(OR(T355="",V355=""),"",EDATE(T355,V355))) |  |  |  |  | IF(F355="","",IF(COUNT(AI355:AV355)=0,IF(AA355="","Not started",AA355),SUBSTITUTE(LOOKUP(2,1/(AI355:AV355<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F355="",COUNT(AI355:AV355)=0),"",TODAY()-LOOKUP(2,1/(AI355:AV355<>""),AI355:AV355)) | IF(OR(F355="",COUNT(AI355:AV355)<2),"",LOOKUP(2,1/(AI355:AV355<>""),AI355:AV355)-MIN(AI355:AV355)) | IF(OR(AD355="",AC355="Not started",AC355=""),"",IFERROR(AD355-IF(VLOOKUP(AC355,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC355,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F355="","",IF(OR(AA355="Cancelled",AC355="Cancelled"),"Cancelled",IF(OR(AC355="Completed / Handover",Y355<>"",Z355>=100),"Completed — on track",IF(O355="Not awarded",IF(U355="",IF(X355="","No planned date",IF(TODAY()>X355,"Behind — past planned date",IF(X355-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U355,"Behind — award date passed",IF(U355-TODAY()<=30,"At risk — close to off track","On track"))),IF(X355="","No planned date",IF(AND(TODAY()>X355,OR(Z355="",Z355<100)),"Behind — past end date",IF(AND(T355<>"",X355<>"",Z355<>"",(Z355<100),((TODAY()-T355)/MAX(X355-T355,1)*100)-Z355>15),"Behind — progress lag",IF(AND(X355-TODAY()<=30,X355-TODAY()>=0,OR(Z355="",Z355<90)),"At risk — close to off track","On track")))))))) | IF(OR(F355="",AC355="Completed / Handover",AC355="Cancelled"),"",IF(O355="Not awarded",IF(U355<>"",U355-TODAY(),IF(X355="","",X355-TODAY())),IF(X355="","",X355-TODAY()))) | [14 empty] | IF(OR(F355="",AJ355=""),"",IF(COUNT(AI355:AI355)=0,"",AJ355-LOOKUP(2,1/(AI355:AI355<>""),AI355:AI355))) | IF(OR(F355="",AK355=""),"",IF(COUNT(AI355:AJ355)=0,"",AK355-LOOKUP(2,1/(AI355:AJ355<>""),AI355:AJ355))) | IF(OR(F355="",AL355=""),"",IF(COUNT(AI355:AK355)=0,"",AL355-LOOKUP(2,1/(AI355:AK355<>""),AI355:AK355))) | IF(OR(F355="",AM355=""),"",IF(COUNT(AI355:AL355)=0,"",AM355-LOOKUP(2,1/(AI355:AL355<>""),AI355:AL355))) | IF(OR(F355="",AN355=""),"",IF(COUNT(AI355:AM355)=0,"",AN355-LOOKUP(2,1/(AI355:AM355<>""),AI355:AM355))) | IF(OR(F355="",AO355=""),"",IF(COUNT(AI355:AN355)=0,"",AO355-LOOKUP(2,1/(AI355:AN355<>""),AI355:AN355))) | IF(OR(F355="",AP355=""),"",IF(COUNT(AI355:AO355)=0,"",AP355-LOOKUP(2,1/(AI355:AO355<>""),AI355:AO355))) | IF(OR(F355="",AQ355=""),"",IF(COUNT(AI355:AP355)=0,"",AQ355-LOOKUP(2,1/(AI355:AP355<>""),AI355:AP355))) | IF(OR(F355="",AR355=""),"",IF(COUNT(AI355:AQ355)=0,"",AR355-LOOKUP(2,1/(AI355:AQ355<>""),AI355:AQ355))) | IF(OR(F355="",AS355=""),"",IF(COUNT(AI355:AR355)=0,"",AS355-LOOKUP(2,1/(AI355:AR355<>""),AI355:AR355))) | IF(OR(F355="",AT355=""),"",IF(COUNT(AI355:AS355)=0,"",AT355-LOOKUP(2,1/(AI355:AS355<>""),AI355:AS355))) | IF(OR(F355="",AU355=""),"",IF(COUNT(AI355:AT355)=0,"",AU355-LOOKUP(2,1/(AI355:AT355<>""),AI355:AT355))) | IF(OR(F355="",AV355=""),"",IF(COUNT(AI355:AU355)=0,"",AV355-LOOKUP(2,1/(AI355:AU355<>""),AI355:AU355))) | IF(J355="","All_Provinces",IFERROR(VLOOKUP(J355,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K355="","All_Districts",IFERROR(VLOOKUP(K355,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F356="","",ROW()-3) | [18 empty] | IF(AQ356="","",AQ356) |  |  |  | IF(W356<>"",W356,IF(OR(T356="",V356=""),"",EDATE(T356,V356))) |  |  |  |  | IF(F356="","",IF(COUNT(AI356:AV356)=0,IF(AA356="","Not started",AA356),SUBSTITUTE(LOOKUP(2,1/(AI356:AV356<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F356="",COUNT(AI356:AV356)=0),"",TODAY()-LOOKUP(2,1/(AI356:AV356<>""),AI356:AV356)) | IF(OR(F356="",COUNT(AI356:AV356)<2),"",LOOKUP(2,1/(AI356:AV356<>""),AI356:AV356)-MIN(AI356:AV356)) | IF(OR(AD356="",AC356="Not started",AC356=""),"",IFERROR(AD356-IF(VLOOKUP(AC356,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC356,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F356="","",IF(OR(AA356="Cancelled",AC356="Cancelled"),"Cancelled",IF(OR(AC356="Completed / Handover",Y356<>"",Z356>=100),"Completed — on track",IF(O356="Not awarded",IF(U356="",IF(X356="","No planned date",IF(TODAY()>X356,"Behind — past planned date",IF(X356-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U356,"Behind — award date passed",IF(U356-TODAY()<=30,"At risk — close to off track","On track"))),IF(X356="","No planned date",IF(AND(TODAY()>X356,OR(Z356="",Z356<100)),"Behind — past end date",IF(AND(T356<>"",X356<>"",Z356<>"",(Z356<100),((TODAY()-T356)/MAX(X356-T356,1)*100)-Z356>15),"Behind — progress lag",IF(AND(X356-TODAY()<=30,X356-TODAY()>=0,OR(Z356="",Z356<90)),"At risk — close to off track","On track")))))))) | IF(OR(F356="",AC356="Completed / Handover",AC356="Cancelled"),"",IF(O356="Not awarded",IF(U356<>"",U356-TODAY(),IF(X356="","",X356-TODAY())),IF(X356="","",X356-TODAY()))) | [14 empty] | IF(OR(F356="",AJ356=""),"",IF(COUNT(AI356:AI356)=0,"",AJ356-LOOKUP(2,1/(AI356:AI356<>""),AI356:AI356))) | IF(OR(F356="",AK356=""),"",IF(COUNT(AI356:AJ356)=0,"",AK356-LOOKUP(2,1/(AI356:AJ356<>""),AI356:AJ356))) | IF(OR(F356="",AL356=""),"",IF(COUNT(AI356:AK356)=0,"",AL356-LOOKUP(2,1/(AI356:AK356<>""),AI356:AK356))) | IF(OR(F356="",AM356=""),"",IF(COUNT(AI356:AL356)=0,"",AM356-LOOKUP(2,1/(AI356:AL356<>""),AI356:AL356))) | IF(OR(F356="",AN356=""),"",IF(COUNT(AI356:AM356)=0,"",AN356-LOOKUP(2,1/(AI356:AM356<>""),AI356:AM356))) | IF(OR(F356="",AO356=""),"",IF(COUNT(AI356:AN356)=0,"",AO356-LOOKUP(2,1/(AI356:AN356<>""),AI356:AN356))) | IF(OR(F356="",AP356=""),"",IF(COUNT(AI356:AO356)=0,"",AP356-LOOKUP(2,1/(AI356:AO356<>""),AI356:AO356))) | IF(OR(F356="",AQ356=""),"",IF(COUNT(AI356:AP356)=0,"",AQ356-LOOKUP(2,1/(AI356:AP356<>""),AI356:AP356))) | IF(OR(F356="",AR356=""),"",IF(COUNT(AI356:AQ356)=0,"",AR356-LOOKUP(2,1/(AI356:AQ356<>""),AI356:AQ356))) | IF(OR(F356="",AS356=""),"",IF(COUNT(AI356:AR356)=0,"",AS356-LOOKUP(2,1/(AI356:AR356<>""),AI356:AR356))) | IF(OR(F356="",AT356=""),"",IF(COUNT(AI356:AS356)=0,"",AT356-LOOKUP(2,1/(AI356:AS356<>""),AI356:AS356))) | IF(OR(F356="",AU356=""),"",IF(COUNT(AI356:AT356)=0,"",AU356-LOOKUP(2,1/(AI356:AT356<>""),AI356:AT356))) | IF(OR(F356="",AV356=""),"",IF(COUNT(AI356:AU356)=0,"",AV356-LOOKUP(2,1/(AI356:AU356<>""),AI356:AU356))) | IF(J356="","All_Provinces",IFERROR(VLOOKUP(J356,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K356="","All_Districts",IFERROR(VLOOKUP(K356,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F357="","",ROW()-3) | [18 empty] | IF(AQ357="","",AQ357) |  |  |  | IF(W357<>"",W357,IF(OR(T357="",V357=""),"",EDATE(T357,V357))) |  |  |  |  | IF(F357="","",IF(COUNT(AI357:AV357)=0,IF(AA357="","Not started",AA357),SUBSTITUTE(LOOKUP(2,1/(AI357:AV357<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F357="",COUNT(AI357:AV357)=0),"",TODAY()-LOOKUP(2,1/(AI357:AV357<>""),AI357:AV357)) | IF(OR(F357="",COUNT(AI357:AV357)<2),"",LOOKUP(2,1/(AI357:AV357<>""),AI357:AV357)-MIN(AI357:AV357)) | IF(OR(AD357="",AC357="Not started",AC357=""),"",IFERROR(AD357-IF(VLOOKUP(AC357,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC357,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F357="","",IF(OR(AA357="Cancelled",AC357="Cancelled"),"Cancelled",IF(OR(AC357="Completed / Handover",Y357<>"",Z357>=100),"Completed — on track",IF(O357="Not awarded",IF(U357="",IF(X357="","No planned date",IF(TODAY()>X357,"Behind — past planned date",IF(X357-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U357,"Behind — award date passed",IF(U357-TODAY()<=30,"At risk — close to off track","On track"))),IF(X357="","No planned date",IF(AND(TODAY()>X357,OR(Z357="",Z357<100)),"Behind — past end date",IF(AND(T357<>"",X357<>"",Z357<>"",(Z357<100),((TODAY()-T357)/MAX(X357-T357,1)*100)-Z357>15),"Behind — progress lag",IF(AND(X357-TODAY()<=30,X357-TODAY()>=0,OR(Z357="",Z357<90)),"At risk — close to off track","On track")))))))) | IF(OR(F357="",AC357="Completed / Handover",AC357="Cancelled"),"",IF(O357="Not awarded",IF(U357<>"",U357-TODAY(),IF(X357="","",X357-TODAY())),IF(X357="","",X357-TODAY()))) | [14 empty] | IF(OR(F357="",AJ357=""),"",IF(COUNT(AI357:AI357)=0,"",AJ357-LOOKUP(2,1/(AI357:AI357<>""),AI357:AI357))) | IF(OR(F357="",AK357=""),"",IF(COUNT(AI357:AJ357)=0,"",AK357-LOOKUP(2,1/(AI357:AJ357<>""),AI357:AJ357))) | IF(OR(F357="",AL357=""),"",IF(COUNT(AI357:AK357)=0,"",AL357-LOOKUP(2,1/(AI357:AK357<>""),AI357:AK357))) | IF(OR(F357="",AM357=""),"",IF(COUNT(AI357:AL357)=0,"",AM357-LOOKUP(2,1/(AI357:AL357<>""),AI357:AL357))) | IF(OR(F357="",AN357=""),"",IF(COUNT(AI357:AM357)=0,"",AN357-LOOKUP(2,1/(AI357:AM357<>""),AI357:AM357))) | IF(OR(F357="",AO357=""),"",IF(COUNT(AI357:AN357)=0,"",AO357-LOOKUP(2,1/(AI357:AN357<>""),AI357:AN357))) | IF(OR(F357="",AP357=""),"",IF(COUNT(AI357:AO357)=0,"",AP357-LOOKUP(2,1/(AI357:AO357<>""),AI357:AO357))) | IF(OR(F357="",AQ357=""),"",IF(COUNT(AI357:AP357)=0,"",AQ357-LOOKUP(2,1/(AI357:AP357<>""),AI357:AP357))) | IF(OR(F357="",AR357=""),"",IF(COUNT(AI357:AQ357)=0,"",AR357-LOOKUP(2,1/(AI357:AQ357<>""),AI357:AQ357))) | IF(OR(F357="",AS357=""),"",IF(COUNT(AI357:AR357)=0,"",AS357-LOOKUP(2,1/(AI357:AR357<>""),AI357:AR357))) | IF(OR(F357="",AT357=""),"",IF(COUNT(AI357:AS357)=0,"",AT357-LOOKUP(2,1/(AI357:AS357<>""),AI357:AS357))) | IF(OR(F357="",AU357=""),"",IF(COUNT(AI357:AT357)=0,"",AU357-LOOKUP(2,1/(AI357:AT357<>""),AI357:AT357))) | IF(OR(F357="",AV357=""),"",IF(COUNT(AI357:AU357)=0,"",AV357-LOOKUP(2,1/(AI357:AU357<>""),AI357:AU357))) | IF(J357="","All_Provinces",IFERROR(VLOOKUP(J357,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K357="","All_Districts",IFERROR(VLOOKUP(K357,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F358="","",ROW()-3) | [18 empty] | IF(AQ358="","",AQ358) |  |  |  | IF(W358<>"",W358,IF(OR(T358="",V358=""),"",EDATE(T358,V358))) |  |  |  |  | IF(F358="","",IF(COUNT(AI358:AV358)=0,IF(AA358="","Not started",AA358),SUBSTITUTE(LOOKUP(2,1/(AI358:AV358<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F358="",COUNT(AI358:AV358)=0),"",TODAY()-LOOKUP(2,1/(AI358:AV358<>""),AI358:AV358)) | IF(OR(F358="",COUNT(AI358:AV358)<2),"",LOOKUP(2,1/(AI358:AV358<>""),AI358:AV358)-MIN(AI358:AV358)) | IF(OR(AD358="",AC358="Not started",AC358=""),"",IFERROR(AD358-IF(VLOOKUP(AC358,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC358,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F358="","",IF(OR(AA358="Cancelled",AC358="Cancelled"),"Cancelled",IF(OR(AC358="Completed / Handover",Y358<>"",Z358>=100),"Completed — on track",IF(O358="Not awarded",IF(U358="",IF(X358="","No planned date",IF(TODAY()>X358,"Behind — past planned date",IF(X358-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U358,"Behind — award date passed",IF(U358-TODAY()<=30,"At risk — close to off track","On track"))),IF(X358="","No planned date",IF(AND(TODAY()>X358,OR(Z358="",Z358<100)),"Behind — past end date",IF(AND(T358<>"",X358<>"",Z358<>"",(Z358<100),((TODAY()-T358)/MAX(X358-T358,1)*100)-Z358>15),"Behind — progress lag",IF(AND(X358-TODAY()<=30,X358-TODAY()>=0,OR(Z358="",Z358<90)),"At risk — close to off track","On track")))))))) | IF(OR(F358="",AC358="Completed / Handover",AC358="Cancelled"),"",IF(O358="Not awarded",IF(U358<>"",U358-TODAY(),IF(X358="","",X358-TODAY())),IF(X358="","",X358-TODAY()))) | [14 empty] | IF(OR(F358="",AJ358=""),"",IF(COUNT(AI358:AI358)=0,"",AJ358-LOOKUP(2,1/(AI358:AI358<>""),AI358:AI358))) | IF(OR(F358="",AK358=""),"",IF(COUNT(AI358:AJ358)=0,"",AK358-LOOKUP(2,1/(AI358:AJ358<>""),AI358:AJ358))) | IF(OR(F358="",AL358=""),"",IF(COUNT(AI358:AK358)=0,"",AL358-LOOKUP(2,1/(AI358:AK358<>""),AI358:AK358))) | IF(OR(F358="",AM358=""),"",IF(COUNT(AI358:AL358)=0,"",AM358-LOOKUP(2,1/(AI358:AL358<>""),AI358:AL358))) | IF(OR(F358="",AN358=""),"",IF(COUNT(AI358:AM358)=0,"",AN358-LOOKUP(2,1/(AI358:AM358<>""),AI358:AM358))) | IF(OR(F358="",AO358=""),"",IF(COUNT(AI358:AN358)=0,"",AO358-LOOKUP(2,1/(AI358:AN358<>""),AI358:AN358))) | IF(OR(F358="",AP358=""),"",IF(COUNT(AI358:AO358)=0,"",AP358-LOOKUP(2,1/(AI358:AO358<>""),AI358:AO358))) | IF(OR(F358="",AQ358=""),"",IF(COUNT(AI358:AP358)=0,"",AQ358-LOOKUP(2,1/(AI358:AP358<>""),AI358:AP358))) | IF(OR(F358="",AR358=""),"",IF(COUNT(AI358:AQ358)=0,"",AR358-LOOKUP(2,1/(AI358:AQ358<>""),AI358:AQ358))) | IF(OR(F358="",AS358=""),"",IF(COUNT(AI358:AR358)=0,"",AS358-LOOKUP(2,1/(AI358:AR358<>""),AI358:AR358))) | IF(OR(F358="",AT358=""),"",IF(COUNT(AI358:AS358)=0,"",AT358-LOOKUP(2,1/(AI358:AS358<>""),AI358:AS358))) | IF(OR(F358="",AU358=""),"",IF(COUNT(AI358:AT358)=0,"",AU358-LOOKUP(2,1/(AI358:AT358<>""),AI358:AT358))) | IF(OR(F358="",AV358=""),"",IF(COUNT(AI358:AU358)=0,"",AV358-LOOKUP(2,1/(AI358:AU358<>""),AI358:AU358))) | IF(J358="","All_Provinces",IFERROR(VLOOKUP(J358,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K358="","All_Districts",IFERROR(VLOOKUP(K358,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F359="","",ROW()-3) | [18 empty] | IF(AQ359="","",AQ359) |  |  |  | IF(W359<>"",W359,IF(OR(T359="",V359=""),"",EDATE(T359,V359))) |  |  |  |  | IF(F359="","",IF(COUNT(AI359:AV359)=0,IF(AA359="","Not started",AA359),SUBSTITUTE(LOOKUP(2,1/(AI359:AV359<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F359="",COUNT(AI359:AV359)=0),"",TODAY()-LOOKUP(2,1/(AI359:AV359<>""),AI359:AV359)) | IF(OR(F359="",COUNT(AI359:AV359)<2),"",LOOKUP(2,1/(AI359:AV359<>""),AI359:AV359)-MIN(AI359:AV359)) | IF(OR(AD359="",AC359="Not started",AC359=""),"",IFERROR(AD359-IF(VLOOKUP(AC359,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC359,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F359="","",IF(OR(AA359="Cancelled",AC359="Cancelled"),"Cancelled",IF(OR(AC359="Completed / Handover",Y359<>"",Z359>=100),"Completed — on track",IF(O359="Not awarded",IF(U359="",IF(X359="","No planned date",IF(TODAY()>X359,"Behind — past planned date",IF(X359-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U359,"Behind — award date passed",IF(U359-TODAY()<=30,"At risk — close to off track","On track"))),IF(X359="","No planned date",IF(AND(TODAY()>X359,OR(Z359="",Z359<100)),"Behind — past end date",IF(AND(T359<>"",X359<>"",Z359<>"",(Z359<100),((TODAY()-T359)/MAX(X359-T359,1)*100)-Z359>15),"Behind — progress lag",IF(AND(X359-TODAY()<=30,X359-TODAY()>=0,OR(Z359="",Z359<90)),"At risk — close to off track","On track")))))))) | IF(OR(F359="",AC359="Completed / Handover",AC359="Cancelled"),"",IF(O359="Not awarded",IF(U359<>"",U359-TODAY(),IF(X359="","",X359-TODAY())),IF(X359="","",X359-TODAY()))) | [14 empty] | IF(OR(F359="",AJ359=""),"",IF(COUNT(AI359:AI359)=0,"",AJ359-LOOKUP(2,1/(AI359:AI359<>""),AI359:AI359))) | IF(OR(F359="",AK359=""),"",IF(COUNT(AI359:AJ359)=0,"",AK359-LOOKUP(2,1/(AI359:AJ359<>""),AI359:AJ359))) | IF(OR(F359="",AL359=""),"",IF(COUNT(AI359:AK359)=0,"",AL359-LOOKUP(2,1/(AI359:AK359<>""),AI359:AK359))) | IF(OR(F359="",AM359=""),"",IF(COUNT(AI359:AL359)=0,"",AM359-LOOKUP(2,1/(AI359:AL359<>""),AI359:AL359))) | IF(OR(F359="",AN359=""),"",IF(COUNT(AI359:AM359)=0,"",AN359-LOOKUP(2,1/(AI359:AM359<>""),AI359:AM359))) | IF(OR(F359="",AO359=""),"",IF(COUNT(AI359:AN359)=0,"",AO359-LOOKUP(2,1/(AI359:AN359<>""),AI359:AN359))) | IF(OR(F359="",AP359=""),"",IF(COUNT(AI359:AO359)=0,"",AP359-LOOKUP(2,1/(AI359:AO359<>""),AI359:AO359))) | IF(OR(F359="",AQ359=""),"",IF(COUNT(AI359:AP359)=0,"",AQ359-LOOKUP(2,1/(AI359:AP359<>""),AI359:AP359))) | IF(OR(F359="",AR359=""),"",IF(COUNT(AI359:AQ359)=0,"",AR359-LOOKUP(2,1/(AI359:AQ359<>""),AI359:AQ359))) | IF(OR(F359="",AS359=""),"",IF(COUNT(AI359:AR359)=0,"",AS359-LOOKUP(2,1/(AI359:AR359<>""),AI359:AR359))) | IF(OR(F359="",AT359=""),"",IF(COUNT(AI359:AS359)=0,"",AT359-LOOKUP(2,1/(AI359:AS359<>""),AI359:AS359))) | IF(OR(F359="",AU359=""),"",IF(COUNT(AI359:AT359)=0,"",AU359-LOOKUP(2,1/(AI359:AT359<>""),AI359:AT359))) | IF(OR(F359="",AV359=""),"",IF(COUNT(AI359:AU359)=0,"",AV359-LOOKUP(2,1/(AI359:AU359<>""),AI359:AU359))) | IF(J359="","All_Provinces",IFERROR(VLOOKUP(J359,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K359="","All_Districts",IFERROR(VLOOKUP(K359,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F360="","",ROW()-3) | [18 empty] | IF(AQ360="","",AQ360) |  |  |  | IF(W360<>"",W360,IF(OR(T360="",V360=""),"",EDATE(T360,V360))) |  |  |  |  | IF(F360="","",IF(COUNT(AI360:AV360)=0,IF(AA360="","Not started",AA360),SUBSTITUTE(LOOKUP(2,1/(AI360:AV360<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F360="",COUNT(AI360:AV360)=0),"",TODAY()-LOOKUP(2,1/(AI360:AV360<>""),AI360:AV360)) | IF(OR(F360="",COUNT(AI360:AV360)<2),"",LOOKUP(2,1/(AI360:AV360<>""),AI360:AV360)-MIN(AI360:AV360)) | IF(OR(AD360="",AC360="Not started",AC360=""),"",IFERROR(AD360-IF(VLOOKUP(AC360,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC360,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F360="","",IF(OR(AA360="Cancelled",AC360="Cancelled"),"Cancelled",IF(OR(AC360="Completed / Handover",Y360<>"",Z360>=100),"Completed — on track",IF(O360="Not awarded",IF(U360="",IF(X360="","No planned date",IF(TODAY()>X360,"Behind — past planned date",IF(X360-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U360,"Behind — award date passed",IF(U360-TODAY()<=30,"At risk — close to off track","On track"))),IF(X360="","No planned date",IF(AND(TODAY()>X360,OR(Z360="",Z360<100)),"Behind — past end date",IF(AND(T360<>"",X360<>"",Z360<>"",(Z360<100),((TODAY()-T360)/MAX(X360-T360,1)*100)-Z360>15),"Behind — progress lag",IF(AND(X360-TODAY()<=30,X360-TODAY()>=0,OR(Z360="",Z360<90)),"At risk — close to off track","On track")))))))) | IF(OR(F360="",AC360="Completed / Handover",AC360="Cancelled"),"",IF(O360="Not awarded",IF(U360<>"",U360-TODAY(),IF(X360="","",X360-TODAY())),IF(X360="","",X360-TODAY()))) | [14 empty] | IF(OR(F360="",AJ360=""),"",IF(COUNT(AI360:AI360)=0,"",AJ360-LOOKUP(2,1/(AI360:AI360<>""),AI360:AI360))) | IF(OR(F360="",AK360=""),"",IF(COUNT(AI360:AJ360)=0,"",AK360-LOOKUP(2,1/(AI360:AJ360<>""),AI360:AJ360))) | IF(OR(F360="",AL360=""),"",IF(COUNT(AI360:AK360)=0,"",AL360-LOOKUP(2,1/(AI360:AK360<>""),AI360:AK360))) | IF(OR(F360="",AM360=""),"",IF(COUNT(AI360:AL360)=0,"",AM360-LOOKUP(2,1/(AI360:AL360<>""),AI360:AL360))) | IF(OR(F360="",AN360=""),"",IF(COUNT(AI360:AM360)=0,"",AN360-LOOKUP(2,1/(AI360:AM360<>""),AI360:AM360))) | IF(OR(F360="",AO360=""),"",IF(COUNT(AI360:AN360)=0,"",AO360-LOOKUP(2,1/(AI360:AN360<>""),AI360:AN360))) | IF(OR(F360="",AP360=""),"",IF(COUNT(AI360:AO360)=0,"",AP360-LOOKUP(2,1/(AI360:AO360<>""),AI360:AO360))) | IF(OR(F360="",AQ360=""),"",IF(COUNT(AI360:AP360)=0,"",AQ360-LOOKUP(2,1/(AI360:AP360<>""),AI360:AP360))) | IF(OR(F360="",AR360=""),"",IF(COUNT(AI360:AQ360)=0,"",AR360-LOOKUP(2,1/(AI360:AQ360<>""),AI360:AQ360))) | IF(OR(F360="",AS360=""),"",IF(COUNT(AI360:AR360)=0,"",AS360-LOOKUP(2,1/(AI360:AR360<>""),AI360:AR360))) | IF(OR(F360="",AT360=""),"",IF(COUNT(AI360:AS360)=0,"",AT360-LOOKUP(2,1/(AI360:AS360<>""),AI360:AS360))) | IF(OR(F360="",AU360=""),"",IF(COUNT(AI360:AT360)=0,"",AU360-LOOKUP(2,1/(AI360:AT360<>""),AI360:AT360))) | IF(OR(F360="",AV360=""),"",IF(COUNT(AI360:AU360)=0,"",AV360-LOOKUP(2,1/(AI360:AU360<>""),AI360:AU360))) | IF(J360="","All_Provinces",IFERROR(VLOOKUP(J360,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K360="","All_Districts",IFERROR(VLOOKUP(K360,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F361="","",ROW()-3) | [18 empty] | IF(AQ361="","",AQ361) |  |  |  | IF(W361<>"",W361,IF(OR(T361="",V361=""),"",EDATE(T361,V361))) |  |  |  |  | IF(F361="","",IF(COUNT(AI361:AV361)=0,IF(AA361="","Not started",AA361),SUBSTITUTE(LOOKUP(2,1/(AI361:AV361<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F361="",COUNT(AI361:AV361)=0),"",TODAY()-LOOKUP(2,1/(AI361:AV361<>""),AI361:AV361)) | IF(OR(F361="",COUNT(AI361:AV361)<2),"",LOOKUP(2,1/(AI361:AV361<>""),AI361:AV361)-MIN(AI361:AV361)) | IF(OR(AD361="",AC361="Not started",AC361=""),"",IFERROR(AD361-IF(VLOOKUP(AC361,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC361,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F361="","",IF(OR(AA361="Cancelled",AC361="Cancelled"),"Cancelled",IF(OR(AC361="Completed / Handover",Y361<>"",Z361>=100),"Completed — on track",IF(O361="Not awarded",IF(U361="",IF(X361="","No planned date",IF(TODAY()>X361,"Behind — past planned date",IF(X361-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U361,"Behind — award date passed",IF(U361-TODAY()<=30,"At risk — close to off track","On track"))),IF(X361="","No planned date",IF(AND(TODAY()>X361,OR(Z361="",Z361<100)),"Behind — past end date",IF(AND(T361<>"",X361<>"",Z361<>"",(Z361<100),((TODAY()-T361)/MAX(X361-T361,1)*100)-Z361>15),"Behind — progress lag",IF(AND(X361-TODAY()<=30,X361-TODAY()>=0,OR(Z361="",Z361<90)),"At risk — close to off track","On track")))))))) | IF(OR(F361="",AC361="Completed / Handover",AC361="Cancelled"),"",IF(O361="Not awarded",IF(U361<>"",U361-TODAY(),IF(X361="","",X361-TODAY())),IF(X361="","",X361-TODAY()))) | [14 empty] | IF(OR(F361="",AJ361=""),"",IF(COUNT(AI361:AI361)=0,"",AJ361-LOOKUP(2,1/(AI361:AI361<>""),AI361:AI361))) | IF(OR(F361="",AK361=""),"",IF(COUNT(AI361:AJ361)=0,"",AK361-LOOKUP(2,1/(AI361:AJ361<>""),AI361:AJ361))) | IF(OR(F361="",AL361=""),"",IF(COUNT(AI361:AK361)=0,"",AL361-LOOKUP(2,1/(AI361:AK361<>""),AI361:AK361))) | IF(OR(F361="",AM361=""),"",IF(COUNT(AI361:AL361)=0,"",AM361-LOOKUP(2,1/(AI361:AL361<>""),AI361:AL361))) | IF(OR(F361="",AN361=""),"",IF(COUNT(AI361:AM361)=0,"",AN361-LOOKUP(2,1/(AI361:AM361<>""),AI361:AM361))) | IF(OR(F361="",AO361=""),"",IF(COUNT(AI361:AN361)=0,"",AO361-LOOKUP(2,1/(AI361:AN361<>""),AI361:AN361))) | IF(OR(F361="",AP361=""),"",IF(COUNT(AI361:AO361)=0,"",AP361-LOOKUP(2,1/(AI361:AO361<>""),AI361:AO361))) | IF(OR(F361="",AQ361=""),"",IF(COUNT(AI361:AP361)=0,"",AQ361-LOOKUP(2,1/(AI361:AP361<>""),AI361:AP361))) | IF(OR(F361="",AR361=""),"",IF(COUNT(AI361:AQ361)=0,"",AR361-LOOKUP(2,1/(AI361:AQ361<>""),AI361:AQ361))) | IF(OR(F361="",AS361=""),"",IF(COUNT(AI361:AR361)=0,"",AS361-LOOKUP(2,1/(AI361:AR361<>""),AI361:AR361))) | IF(OR(F361="",AT361=""),"",IF(COUNT(AI361:AS361)=0,"",AT361-LOOKUP(2,1/(AI361:AS361<>""),AI361:AS361))) | IF(OR(F361="",AU361=""),"",IF(COUNT(AI361:AT361)=0,"",AU361-LOOKUP(2,1/(AI361:AT361<>""),AI361:AT361))) | IF(OR(F361="",AV361=""),"",IF(COUNT(AI361:AU361)=0,"",AV361-LOOKUP(2,1/(AI361:AU361<>""),AI361:AU361))) | IF(J361="","All_Provinces",IFERROR(VLOOKUP(J361,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K361="","All_Districts",IFERROR(VLOOKUP(K361,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F362="","",ROW()-3) | [18 empty] | IF(AQ362="","",AQ362) |  |  |  | IF(W362<>"",W362,IF(OR(T362="",V362=""),"",EDATE(T362,V362))) |  |  |  |  | IF(F362="","",IF(COUNT(AI362:AV362)=0,IF(AA362="","Not started",AA362),SUBSTITUTE(LOOKUP(2,1/(AI362:AV362<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F362="",COUNT(AI362:AV362)=0),"",TODAY()-LOOKUP(2,1/(AI362:AV362<>""),AI362:AV362)) | IF(OR(F362="",COUNT(AI362:AV362)<2),"",LOOKUP(2,1/(AI362:AV362<>""),AI362:AV362)-MIN(AI362:AV362)) | IF(OR(AD362="",AC362="Not started",AC362=""),"",IFERROR(AD362-IF(VLOOKUP(AC362,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC362,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F362="","",IF(OR(AA362="Cancelled",AC362="Cancelled"),"Cancelled",IF(OR(AC362="Completed / Handover",Y362<>"",Z362>=100),"Completed — on track",IF(O362="Not awarded",IF(U362="",IF(X362="","No planned date",IF(TODAY()>X362,"Behind — past planned date",IF(X362-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U362,"Behind — award date passed",IF(U362-TODAY()<=30,"At risk — close to off track","On track"))),IF(X362="","No planned date",IF(AND(TODAY()>X362,OR(Z362="",Z362<100)),"Behind — past end date",IF(AND(T362<>"",X362<>"",Z362<>"",(Z362<100),((TODAY()-T362)/MAX(X362-T362,1)*100)-Z362>15),"Behind — progress lag",IF(AND(X362-TODAY()<=30,X362-TODAY()>=0,OR(Z362="",Z362<90)),"At risk — close to off track","On track")))))))) | IF(OR(F362="",AC362="Completed / Handover",AC362="Cancelled"),"",IF(O362="Not awarded",IF(U362<>"",U362-TODAY(),IF(X362="","",X362-TODAY())),IF(X362="","",X362-TODAY()))) | [14 empty] | IF(OR(F362="",AJ362=""),"",IF(COUNT(AI362:AI362)=0,"",AJ362-LOOKUP(2,1/(AI362:AI362<>""),AI362:AI362))) | IF(OR(F362="",AK362=""),"",IF(COUNT(AI362:AJ362)=0,"",AK362-LOOKUP(2,1/(AI362:AJ362<>""),AI362:AJ362))) | IF(OR(F362="",AL362=""),"",IF(COUNT(AI362:AK362)=0,"",AL362-LOOKUP(2,1/(AI362:AK362<>""),AI362:AK362))) | IF(OR(F362="",AM362=""),"",IF(COUNT(AI362:AL362)=0,"",AM362-LOOKUP(2,1/(AI362:AL362<>""),AI362:AL362))) | IF(OR(F362="",AN362=""),"",IF(COUNT(AI362:AM362)=0,"",AN362-LOOKUP(2,1/(AI362:AM362<>""),AI362:AM362))) | IF(OR(F362="",AO362=""),"",IF(COUNT(AI362:AN362)=0,"",AO362-LOOKUP(2,1/(AI362:AN362<>""),AI362:AN362))) | IF(OR(F362="",AP362=""),"",IF(COUNT(AI362:AO362)=0,"",AP362-LOOKUP(2,1/(AI362:AO362<>""),AI362:AO362))) | IF(OR(F362="",AQ362=""),"",IF(COUNT(AI362:AP362)=0,"",AQ362-LOOKUP(2,1/(AI362:AP362<>""),AI362:AP362))) | IF(OR(F362="",AR362=""),"",IF(COUNT(AI362:AQ362)=0,"",AR362-LOOKUP(2,1/(AI362:AQ362<>""),AI362:AQ362))) | IF(OR(F362="",AS362=""),"",IF(COUNT(AI362:AR362)=0,"",AS362-LOOKUP(2,1/(AI362:AR362<>""),AI362:AR362))) | IF(OR(F362="",AT362=""),"",IF(COUNT(AI362:AS362)=0,"",AT362-LOOKUP(2,1/(AI362:AS362<>""),AI362:AS362))) | IF(OR(F362="",AU362=""),"",IF(COUNT(AI362:AT362)=0,"",AU362-LOOKUP(2,1/(AI362:AT362<>""),AI362:AT362))) | IF(OR(F362="",AV362=""),"",IF(COUNT(AI362:AU362)=0,"",AV362-LOOKUP(2,1/(AI362:AU362<>""),AI362:AU362))) | IF(J362="","All_Provinces",IFERROR(VLOOKUP(J362,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K362="","All_Districts",IFERROR(VLOOKUP(K362,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F363="","",ROW()-3) | [18 empty] | IF(AQ363="","",AQ363) |  |  |  | IF(W363<>"",W363,IF(OR(T363="",V363=""),"",EDATE(T363,V363))) |  |  |  |  | IF(F363="","",IF(COUNT(AI363:AV363)=0,IF(AA363="","Not started",AA363),SUBSTITUTE(LOOKUP(2,1/(AI363:AV363<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F363="",COUNT(AI363:AV363)=0),"",TODAY()-LOOKUP(2,1/(AI363:AV363<>""),AI363:AV363)) | IF(OR(F363="",COUNT(AI363:AV363)<2),"",LOOKUP(2,1/(AI363:AV363<>""),AI363:AV363)-MIN(AI363:AV363)) | IF(OR(AD363="",AC363="Not started",AC363=""),"",IFERROR(AD363-IF(VLOOKUP(AC363,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC363,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F363="","",IF(OR(AA363="Cancelled",AC363="Cancelled"),"Cancelled",IF(OR(AC363="Completed / Handover",Y363<>"",Z363>=100),"Completed — on track",IF(O363="Not awarded",IF(U363="",IF(X363="","No planned date",IF(TODAY()>X363,"Behind — past planned date",IF(X363-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U363,"Behind — award date passed",IF(U363-TODAY()<=30,"At risk — close to off track","On track"))),IF(X363="","No planned date",IF(AND(TODAY()>X363,OR(Z363="",Z363<100)),"Behind — past end date",IF(AND(T363<>"",X363<>"",Z363<>"",(Z363<100),((TODAY()-T363)/MAX(X363-T363,1)*100)-Z363>15),"Behind — progress lag",IF(AND(X363-TODAY()<=30,X363-TODAY()>=0,OR(Z363="",Z363<90)),"At risk — close to off track","On track")))))))) | IF(OR(F363="",AC363="Completed / Handover",AC363="Cancelled"),"",IF(O363="Not awarded",IF(U363<>"",U363-TODAY(),IF(X363="","",X363-TODAY())),IF(X363="","",X363-TODAY()))) | [14 empty] | IF(OR(F363="",AJ363=""),"",IF(COUNT(AI363:AI363)=0,"",AJ363-LOOKUP(2,1/(AI363:AI363<>""),AI363:AI363))) | IF(OR(F363="",AK363=""),"",IF(COUNT(AI363:AJ363)=0,"",AK363-LOOKUP(2,1/(AI363:AJ363<>""),AI363:AJ363))) | IF(OR(F363="",AL363=""),"",IF(COUNT(AI363:AK363)=0,"",AL363-LOOKUP(2,1/(AI363:AK363<>""),AI363:AK363))) | IF(OR(F363="",AM363=""),"",IF(COUNT(AI363:AL363)=0,"",AM363-LOOKUP(2,1/(AI363:AL363<>""),AI363:AL363))) | IF(OR(F363="",AN363=""),"",IF(COUNT(AI363:AM363)=0,"",AN363-LOOKUP(2,1/(AI363:AM363<>""),AI363:AM363))) | IF(OR(F363="",AO363=""),"",IF(COUNT(AI363:AN363)=0,"",AO363-LOOKUP(2,1/(AI363:AN363<>""),AI363:AN363))) | IF(OR(F363="",AP363=""),"",IF(COUNT(AI363:AO363)=0,"",AP363-LOOKUP(2,1/(AI363:AO363<>""),AI363:AO363))) | IF(OR(F363="",AQ363=""),"",IF(COUNT(AI363:AP363)=0,"",AQ363-LOOKUP(2,1/(AI363:AP363<>""),AI363:AP363))) | IF(OR(F363="",AR363=""),"",IF(COUNT(AI363:AQ363)=0,"",AR363-LOOKUP(2,1/(AI363:AQ363<>""),AI363:AQ363))) | IF(OR(F363="",AS363=""),"",IF(COUNT(AI363:AR363)=0,"",AS363-LOOKUP(2,1/(AI363:AR363<>""),AI363:AR363))) | IF(OR(F363="",AT363=""),"",IF(COUNT(AI363:AS363)=0,"",AT363-LOOKUP(2,1/(AI363:AS363<>""),AI363:AS363))) | IF(OR(F363="",AU363=""),"",IF(COUNT(AI363:AT363)=0,"",AU363-LOOKUP(2,1/(AI363:AT363<>""),AI363:AT363))) | IF(OR(F363="",AV363=""),"",IF(COUNT(AI363:AU363)=0,"",AV363-LOOKUP(2,1/(AI363:AU363<>""),AI363:AU363))) | IF(J363="","All_Provinces",IFERROR(VLOOKUP(J363,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K363="","All_Districts",IFERROR(VLOOKUP(K363,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F364="","",ROW()-3) | [18 empty] | IF(AQ364="","",AQ364) |  |  |  | IF(W364<>"",W364,IF(OR(T364="",V364=""),"",EDATE(T364,V364))) |  |  |  |  | IF(F364="","",IF(COUNT(AI364:AV364)=0,IF(AA364="","Not started",AA364),SUBSTITUTE(LOOKUP(2,1/(AI364:AV364<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F364="",COUNT(AI364:AV364)=0),"",TODAY()-LOOKUP(2,1/(AI364:AV364<>""),AI364:AV364)) | IF(OR(F364="",COUNT(AI364:AV364)<2),"",LOOKUP(2,1/(AI364:AV364<>""),AI364:AV364)-MIN(AI364:AV364)) | IF(OR(AD364="",AC364="Not started",AC364=""),"",IFERROR(AD364-IF(VLOOKUP(AC364,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC364,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F364="","",IF(OR(AA364="Cancelled",AC364="Cancelled"),"Cancelled",IF(OR(AC364="Completed / Handover",Y364<>"",Z364>=100),"Completed — on track",IF(O364="Not awarded",IF(U364="",IF(X364="","No planned date",IF(TODAY()>X364,"Behind — past planned date",IF(X364-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U364,"Behind — award date passed",IF(U364-TODAY()<=30,"At risk — close to off track","On track"))),IF(X364="","No planned date",IF(AND(TODAY()>X364,OR(Z364="",Z364<100)),"Behind — past end date",IF(AND(T364<>"",X364<>"",Z364<>"",(Z364<100),((TODAY()-T364)/MAX(X364-T364,1)*100)-Z364>15),"Behind — progress lag",IF(AND(X364-TODAY()<=30,X364-TODAY()>=0,OR(Z364="",Z364<90)),"At risk — close to off track","On track")))))))) | IF(OR(F364="",AC364="Completed / Handover",AC364="Cancelled"),"",IF(O364="Not awarded",IF(U364<>"",U364-TODAY(),IF(X364="","",X364-TODAY())),IF(X364="","",X364-TODAY()))) | [14 empty] | IF(OR(F364="",AJ364=""),"",IF(COUNT(AI364:AI364)=0,"",AJ364-LOOKUP(2,1/(AI364:AI364<>""),AI364:AI364))) | IF(OR(F364="",AK364=""),"",IF(COUNT(AI364:AJ364)=0,"",AK364-LOOKUP(2,1/(AI364:AJ364<>""),AI364:AJ364))) | IF(OR(F364="",AL364=""),"",IF(COUNT(AI364:AK364)=0,"",AL364-LOOKUP(2,1/(AI364:AK364<>""),AI364:AK364))) | IF(OR(F364="",AM364=""),"",IF(COUNT(AI364:AL364)=0,"",AM364-LOOKUP(2,1/(AI364:AL364<>""),AI364:AL364))) | IF(OR(F364="",AN364=""),"",IF(COUNT(AI364:AM364)=0,"",AN364-LOOKUP(2,1/(AI364:AM364<>""),AI364:AM364))) | IF(OR(F364="",AO364=""),"",IF(COUNT(AI364:AN364)=0,"",AO364-LOOKUP(2,1/(AI364:AN364<>""),AI364:AN364))) | IF(OR(F364="",AP364=""),"",IF(COUNT(AI364:AO364)=0,"",AP364-LOOKUP(2,1/(AI364:AO364<>""),AI364:AO364))) | IF(OR(F364="",AQ364=""),"",IF(COUNT(AI364:AP364)=0,"",AQ364-LOOKUP(2,1/(AI364:AP364<>""),AI364:AP364))) | IF(OR(F364="",AR364=""),"",IF(COUNT(AI364:AQ364)=0,"",AR364-LOOKUP(2,1/(AI364:AQ364<>""),AI364:AQ364))) | IF(OR(F364="",AS364=""),"",IF(COUNT(AI364:AR364)=0,"",AS364-LOOKUP(2,1/(AI364:AR364<>""),AI364:AR364))) | IF(OR(F364="",AT364=""),"",IF(COUNT(AI364:AS364)=0,"",AT364-LOOKUP(2,1/(AI364:AS364<>""),AI364:AS364))) | IF(OR(F364="",AU364=""),"",IF(COUNT(AI364:AT364)=0,"",AU364-LOOKUP(2,1/(AI364:AT364<>""),AI364:AT364))) | IF(OR(F364="",AV364=""),"",IF(COUNT(AI364:AU364)=0,"",AV364-LOOKUP(2,1/(AI364:AU364<>""),AI364:AU364))) | IF(J364="","All_Provinces",IFERROR(VLOOKUP(J364,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K364="","All_Districts",IFERROR(VLOOKUP(K364,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F365="","",ROW()-3) | [18 empty] | IF(AQ365="","",AQ365) |  |  |  | IF(W365<>"",W365,IF(OR(T365="",V365=""),"",EDATE(T365,V365))) |  |  |  |  | IF(F365="","",IF(COUNT(AI365:AV365)=0,IF(AA365="","Not started",AA365),SUBSTITUTE(LOOKUP(2,1/(AI365:AV365<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F365="",COUNT(AI365:AV365)=0),"",TODAY()-LOOKUP(2,1/(AI365:AV365<>""),AI365:AV365)) | IF(OR(F365="",COUNT(AI365:AV365)<2),"",LOOKUP(2,1/(AI365:AV365<>""),AI365:AV365)-MIN(AI365:AV365)) | IF(OR(AD365="",AC365="Not started",AC365=""),"",IFERROR(AD365-IF(VLOOKUP(AC365,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC365,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F365="","",IF(OR(AA365="Cancelled",AC365="Cancelled"),"Cancelled",IF(OR(AC365="Completed / Handover",Y365<>"",Z365>=100),"Completed — on track",IF(O365="Not awarded",IF(U365="",IF(X365="","No planned date",IF(TODAY()>X365,"Behind — past planned date",IF(X365-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U365,"Behind — award date passed",IF(U365-TODAY()<=30,"At risk — close to off track","On track"))),IF(X365="","No planned date",IF(AND(TODAY()>X365,OR(Z365="",Z365<100)),"Behind — past end date",IF(AND(T365<>"",X365<>"",Z365<>"",(Z365<100),((TODAY()-T365)/MAX(X365-T365,1)*100)-Z365>15),"Behind — progress lag",IF(AND(X365-TODAY()<=30,X365-TODAY()>=0,OR(Z365="",Z365<90)),"At risk — close to off track","On track")))))))) | IF(OR(F365="",AC365="Completed / Handover",AC365="Cancelled"),"",IF(O365="Not awarded",IF(U365<>"",U365-TODAY(),IF(X365="","",X365-TODAY())),IF(X365="","",X365-TODAY()))) | [14 empty] | IF(OR(F365="",AJ365=""),"",IF(COUNT(AI365:AI365)=0,"",AJ365-LOOKUP(2,1/(AI365:AI365<>""),AI365:AI365))) | IF(OR(F365="",AK365=""),"",IF(COUNT(AI365:AJ365)=0,"",AK365-LOOKUP(2,1/(AI365:AJ365<>""),AI365:AJ365))) | IF(OR(F365="",AL365=""),"",IF(COUNT(AI365:AK365)=0,"",AL365-LOOKUP(2,1/(AI365:AK365<>""),AI365:AK365))) | IF(OR(F365="",AM365=""),"",IF(COUNT(AI365:AL365)=0,"",AM365-LOOKUP(2,1/(AI365:AL365<>""),AI365:AL365))) | IF(OR(F365="",AN365=""),"",IF(COUNT(AI365:AM365)=0,"",AN365-LOOKUP(2,1/(AI365:AM365<>""),AI365:AM365))) | IF(OR(F365="",AO365=""),"",IF(COUNT(AI365:AN365)=0,"",AO365-LOOKUP(2,1/(AI365:AN365<>""),AI365:AN365))) | IF(OR(F365="",AP365=""),"",IF(COUNT(AI365:AO365)=0,"",AP365-LOOKUP(2,1/(AI365:AO365<>""),AI365:AO365))) | IF(OR(F365="",AQ365=""),"",IF(COUNT(AI365:AP365)=0,"",AQ365-LOOKUP(2,1/(AI365:AP365<>""),AI365:AP365))) | IF(OR(F365="",AR365=""),"",IF(COUNT(AI365:AQ365)=0,"",AR365-LOOKUP(2,1/(AI365:AQ365<>""),AI365:AQ365))) | IF(OR(F365="",AS365=""),"",IF(COUNT(AI365:AR365)=0,"",AS365-LOOKUP(2,1/(AI365:AR365<>""),AI365:AR365))) | IF(OR(F365="",AT365=""),"",IF(COUNT(AI365:AS365)=0,"",AT365-LOOKUP(2,1/(AI365:AS365<>""),AI365:AS365))) | IF(OR(F365="",AU365=""),"",IF(COUNT(AI365:AT365)=0,"",AU365-LOOKUP(2,1/(AI365:AT365<>""),AI365:AT365))) | IF(OR(F365="",AV365=""),"",IF(COUNT(AI365:AU365)=0,"",AV365-LOOKUP(2,1/(AI365:AU365<>""),AI365:AU365))) | IF(J365="","All_Provinces",IFERROR(VLOOKUP(J365,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K365="","All_Districts",IFERROR(VLOOKUP(K365,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F366="","",ROW()-3) | [18 empty] | IF(AQ366="","",AQ366) |  |  |  | IF(W366<>"",W366,IF(OR(T366="",V366=""),"",EDATE(T366,V366))) |  |  |  |  | IF(F366="","",IF(COUNT(AI366:AV366)=0,IF(AA366="","Not started",AA366),SUBSTITUTE(LOOKUP(2,1/(AI366:AV366<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F366="",COUNT(AI366:AV366)=0),"",TODAY()-LOOKUP(2,1/(AI366:AV366<>""),AI366:AV366)) | IF(OR(F366="",COUNT(AI366:AV366)<2),"",LOOKUP(2,1/(AI366:AV366<>""),AI366:AV366)-MIN(AI366:AV366)) | IF(OR(AD366="",AC366="Not started",AC366=""),"",IFERROR(AD366-IF(VLOOKUP(AC366,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC366,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F366="","",IF(OR(AA366="Cancelled",AC366="Cancelled"),"Cancelled",IF(OR(AC366="Completed / Handover",Y366<>"",Z366>=100),"Completed — on track",IF(O366="Not awarded",IF(U366="",IF(X366="","No planned date",IF(TODAY()>X366,"Behind — past planned date",IF(X366-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U366,"Behind — award date passed",IF(U366-TODAY()<=30,"At risk — close to off track","On track"))),IF(X366="","No planned date",IF(AND(TODAY()>X366,OR(Z366="",Z366<100)),"Behind — past end date",IF(AND(T366<>"",X366<>"",Z366<>"",(Z366<100),((TODAY()-T366)/MAX(X366-T366,1)*100)-Z366>15),"Behind — progress lag",IF(AND(X366-TODAY()<=30,X366-TODAY()>=0,OR(Z366="",Z366<90)),"At risk — close to off track","On track")))))))) | IF(OR(F366="",AC366="Completed / Handover",AC366="Cancelled"),"",IF(O366="Not awarded",IF(U366<>"",U366-TODAY(),IF(X366="","",X366-TODAY())),IF(X366="","",X366-TODAY()))) | [14 empty] | IF(OR(F366="",AJ366=""),"",IF(COUNT(AI366:AI366)=0,"",AJ366-LOOKUP(2,1/(AI366:AI366<>""),AI366:AI366))) | IF(OR(F366="",AK366=""),"",IF(COUNT(AI366:AJ366)=0,"",AK366-LOOKUP(2,1/(AI366:AJ366<>""),AI366:AJ366))) | IF(OR(F366="",AL366=""),"",IF(COUNT(AI366:AK366)=0,"",AL366-LOOKUP(2,1/(AI366:AK366<>""),AI366:AK366))) | IF(OR(F366="",AM366=""),"",IF(COUNT(AI366:AL366)=0,"",AM366-LOOKUP(2,1/(AI366:AL366<>""),AI366:AL366))) | IF(OR(F366="",AN366=""),"",IF(COUNT(AI366:AM366)=0,"",AN366-LOOKUP(2,1/(AI366:AM366<>""),AI366:AM366))) | IF(OR(F366="",AO366=""),"",IF(COUNT(AI366:AN366)=0,"",AO366-LOOKUP(2,1/(AI366:AN366<>""),AI366:AN366))) | IF(OR(F366="",AP366=""),"",IF(COUNT(AI366:AO366)=0,"",AP366-LOOKUP(2,1/(AI366:AO366<>""),AI366:AO366))) | IF(OR(F366="",AQ366=""),"",IF(COUNT(AI366:AP366)=0,"",AQ366-LOOKUP(2,1/(AI366:AP366<>""),AI366:AP366))) | IF(OR(F366="",AR366=""),"",IF(COUNT(AI366:AQ366)=0,"",AR366-LOOKUP(2,1/(AI366:AQ366<>""),AI366:AQ366))) | IF(OR(F366="",AS366=""),"",IF(COUNT(AI366:AR366)=0,"",AS366-LOOKUP(2,1/(AI366:AR366<>""),AI366:AR366))) | IF(OR(F366="",AT366=""),"",IF(COUNT(AI366:AS366)=0,"",AT366-LOOKUP(2,1/(AI366:AS366<>""),AI366:AS366))) | IF(OR(F366="",AU366=""),"",IF(COUNT(AI366:AT366)=0,"",AU366-LOOKUP(2,1/(AI366:AT366<>""),AI366:AT366))) | IF(OR(F366="",AV366=""),"",IF(COUNT(AI366:AU366)=0,"",AV366-LOOKUP(2,1/(AI366:AU366<>""),AI366:AU366))) | IF(J366="","All_Provinces",IFERROR(VLOOKUP(J366,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K366="","All_Districts",IFERROR(VLOOKUP(K366,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F367="","",ROW()-3) | [18 empty] | IF(AQ367="","",AQ367) |  |  |  | IF(W367<>"",W367,IF(OR(T367="",V367=""),"",EDATE(T367,V367))) |  |  |  |  | IF(F367="","",IF(COUNT(AI367:AV367)=0,IF(AA367="","Not started",AA367),SUBSTITUTE(LOOKUP(2,1/(AI367:AV367<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F367="",COUNT(AI367:AV367)=0),"",TODAY()-LOOKUP(2,1/(AI367:AV367<>""),AI367:AV367)) | IF(OR(F367="",COUNT(AI367:AV367)<2),"",LOOKUP(2,1/(AI367:AV367<>""),AI367:AV367)-MIN(AI367:AV367)) | IF(OR(AD367="",AC367="Not started",AC367=""),"",IFERROR(AD367-IF(VLOOKUP(AC367,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC367,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F367="","",IF(OR(AA367="Cancelled",AC367="Cancelled"),"Cancelled",IF(OR(AC367="Completed / Handover",Y367<>"",Z367>=100),"Completed — on track",IF(O367="Not awarded",IF(U367="",IF(X367="","No planned date",IF(TODAY()>X367,"Behind — past planned date",IF(X367-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U367,"Behind — award date passed",IF(U367-TODAY()<=30,"At risk — close to off track","On track"))),IF(X367="","No planned date",IF(AND(TODAY()>X367,OR(Z367="",Z367<100)),"Behind — past end date",IF(AND(T367<>"",X367<>"",Z367<>"",(Z367<100),((TODAY()-T367)/MAX(X367-T367,1)*100)-Z367>15),"Behind — progress lag",IF(AND(X367-TODAY()<=30,X367-TODAY()>=0,OR(Z367="",Z367<90)),"At risk — close to off track","On track")))))))) | IF(OR(F367="",AC367="Completed / Handover",AC367="Cancelled"),"",IF(O367="Not awarded",IF(U367<>"",U367-TODAY(),IF(X367="","",X367-TODAY())),IF(X367="","",X367-TODAY()))) | [14 empty] | IF(OR(F367="",AJ367=""),"",IF(COUNT(AI367:AI367)=0,"",AJ367-LOOKUP(2,1/(AI367:AI367<>""),AI367:AI367))) | IF(OR(F367="",AK367=""),"",IF(COUNT(AI367:AJ367)=0,"",AK367-LOOKUP(2,1/(AI367:AJ367<>""),AI367:AJ367))) | IF(OR(F367="",AL367=""),"",IF(COUNT(AI367:AK367)=0,"",AL367-LOOKUP(2,1/(AI367:AK367<>""),AI367:AK367))) | IF(OR(F367="",AM367=""),"",IF(COUNT(AI367:AL367)=0,"",AM367-LOOKUP(2,1/(AI367:AL367<>""),AI367:AL367))) | IF(OR(F367="",AN367=""),"",IF(COUNT(AI367:AM367)=0,"",AN367-LOOKUP(2,1/(AI367:AM367<>""),AI367:AM367))) | IF(OR(F367="",AO367=""),"",IF(COUNT(AI367:AN367)=0,"",AO367-LOOKUP(2,1/(AI367:AN367<>""),AI367:AN367))) | IF(OR(F367="",AP367=""),"",IF(COUNT(AI367:AO367)=0,"",AP367-LOOKUP(2,1/(AI367:AO367<>""),AI367:AO367))) | IF(OR(F367="",AQ367=""),"",IF(COUNT(AI367:AP367)=0,"",AQ367-LOOKUP(2,1/(AI367:AP367<>""),AI367:AP367))) | IF(OR(F367="",AR367=""),"",IF(COUNT(AI367:AQ367)=0,"",AR367-LOOKUP(2,1/(AI367:AQ367<>""),AI367:AQ367))) | IF(OR(F367="",AS367=""),"",IF(COUNT(AI367:AR367)=0,"",AS367-LOOKUP(2,1/(AI367:AR367<>""),AI367:AR367))) | IF(OR(F367="",AT367=""),"",IF(COUNT(AI367:AS367)=0,"",AT367-LOOKUP(2,1/(AI367:AS367<>""),AI367:AS367))) | IF(OR(F367="",AU367=""),"",IF(COUNT(AI367:AT367)=0,"",AU367-LOOKUP(2,1/(AI367:AT367<>""),AI367:AT367))) | IF(OR(F367="",AV367=""),"",IF(COUNT(AI367:AU367)=0,"",AV367-LOOKUP(2,1/(AI367:AU367<>""),AI367:AU367))) | IF(J367="","All_Provinces",IFERROR(VLOOKUP(J367,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K367="","All_Districts",IFERROR(VLOOKUP(K367,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F368="","",ROW()-3) | [18 empty] | IF(AQ368="","",AQ368) |  |  |  | IF(W368<>"",W368,IF(OR(T368="",V368=""),"",EDATE(T368,V368))) |  |  |  |  | IF(F368="","",IF(COUNT(AI368:AV368)=0,IF(AA368="","Not started",AA368),SUBSTITUTE(LOOKUP(2,1/(AI368:AV368<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F368="",COUNT(AI368:AV368)=0),"",TODAY()-LOOKUP(2,1/(AI368:AV368<>""),AI368:AV368)) | IF(OR(F368="",COUNT(AI368:AV368)<2),"",LOOKUP(2,1/(AI368:AV368<>""),AI368:AV368)-MIN(AI368:AV368)) | IF(OR(AD368="",AC368="Not started",AC368=""),"",IFERROR(AD368-IF(VLOOKUP(AC368,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC368,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F368="","",IF(OR(AA368="Cancelled",AC368="Cancelled"),"Cancelled",IF(OR(AC368="Completed / Handover",Y368<>"",Z368>=100),"Completed — on track",IF(O368="Not awarded",IF(U368="",IF(X368="","No planned date",IF(TODAY()>X368,"Behind — past planned date",IF(X368-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U368,"Behind — award date passed",IF(U368-TODAY()<=30,"At risk — close to off track","On track"))),IF(X368="","No planned date",IF(AND(TODAY()>X368,OR(Z368="",Z368<100)),"Behind — past end date",IF(AND(T368<>"",X368<>"",Z368<>"",(Z368<100),((TODAY()-T368)/MAX(X368-T368,1)*100)-Z368>15),"Behind — progress lag",IF(AND(X368-TODAY()<=30,X368-TODAY()>=0,OR(Z368="",Z368<90)),"At risk — close to off track","On track")))))))) | IF(OR(F368="",AC368="Completed / Handover",AC368="Cancelled"),"",IF(O368="Not awarded",IF(U368<>"",U368-TODAY(),IF(X368="","",X368-TODAY())),IF(X368="","",X368-TODAY()))) | [14 empty] | IF(OR(F368="",AJ368=""),"",IF(COUNT(AI368:AI368)=0,"",AJ368-LOOKUP(2,1/(AI368:AI368<>""),AI368:AI368))) | IF(OR(F368="",AK368=""),"",IF(COUNT(AI368:AJ368)=0,"",AK368-LOOKUP(2,1/(AI368:AJ368<>""),AI368:AJ368))) | IF(OR(F368="",AL368=""),"",IF(COUNT(AI368:AK368)=0,"",AL368-LOOKUP(2,1/(AI368:AK368<>""),AI368:AK368))) | IF(OR(F368="",AM368=""),"",IF(COUNT(AI368:AL368)=0,"",AM368-LOOKUP(2,1/(AI368:AL368<>""),AI368:AL368))) | IF(OR(F368="",AN368=""),"",IF(COUNT(AI368:AM368)=0,"",AN368-LOOKUP(2,1/(AI368:AM368<>""),AI368:AM368))) | IF(OR(F368="",AO368=""),"",IF(COUNT(AI368:AN368)=0,"",AO368-LOOKUP(2,1/(AI368:AN368<>""),AI368:AN368))) | IF(OR(F368="",AP368=""),"",IF(COUNT(AI368:AO368)=0,"",AP368-LOOKUP(2,1/(AI368:AO368<>""),AI368:AO368))) | IF(OR(F368="",AQ368=""),"",IF(COUNT(AI368:AP368)=0,"",AQ368-LOOKUP(2,1/(AI368:AP368<>""),AI368:AP368))) | IF(OR(F368="",AR368=""),"",IF(COUNT(AI368:AQ368)=0,"",AR368-LOOKUP(2,1/(AI368:AQ368<>""),AI368:AQ368))) | IF(OR(F368="",AS368=""),"",IF(COUNT(AI368:AR368)=0,"",AS368-LOOKUP(2,1/(AI368:AR368<>""),AI368:AR368))) | IF(OR(F368="",AT368=""),"",IF(COUNT(AI368:AS368)=0,"",AT368-LOOKUP(2,1/(AI368:AS368<>""),AI368:AS368))) | IF(OR(F368="",AU368=""),"",IF(COUNT(AI368:AT368)=0,"",AU368-LOOKUP(2,1/(AI368:AT368<>""),AI368:AT368))) | IF(OR(F368="",AV368=""),"",IF(COUNT(AI368:AU368)=0,"",AV368-LOOKUP(2,1/(AI368:AU368<>""),AI368:AU368))) | IF(J368="","All_Provinces",IFERROR(VLOOKUP(J368,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K368="","All_Districts",IFERROR(VLOOKUP(K368,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F369="","",ROW()-3) | [18 empty] | IF(AQ369="","",AQ369) |  |  |  | IF(W369<>"",W369,IF(OR(T369="",V369=""),"",EDATE(T369,V369))) |  |  |  |  | IF(F369="","",IF(COUNT(AI369:AV369)=0,IF(AA369="","Not started",AA369),SUBSTITUTE(LOOKUP(2,1/(AI369:AV369<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F369="",COUNT(AI369:AV369)=0),"",TODAY()-LOOKUP(2,1/(AI369:AV369<>""),AI369:AV369)) | IF(OR(F369="",COUNT(AI369:AV369)<2),"",LOOKUP(2,1/(AI369:AV369<>""),AI369:AV369)-MIN(AI369:AV369)) | IF(OR(AD369="",AC369="Not started",AC369=""),"",IFERROR(AD369-IF(VLOOKUP(AC369,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC369,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F369="","",IF(OR(AA369="Cancelled",AC369="Cancelled"),"Cancelled",IF(OR(AC369="Completed / Handover",Y369<>"",Z369>=100),"Completed — on track",IF(O369="Not awarded",IF(U369="",IF(X369="","No planned date",IF(TODAY()>X369,"Behind — past planned date",IF(X369-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U369,"Behind — award date passed",IF(U369-TODAY()<=30,"At risk — close to off track","On track"))),IF(X369="","No planned date",IF(AND(TODAY()>X369,OR(Z369="",Z369<100)),"Behind — past end date",IF(AND(T369<>"",X369<>"",Z369<>"",(Z369<100),((TODAY()-T369)/MAX(X369-T369,1)*100)-Z369>15),"Behind — progress lag",IF(AND(X369-TODAY()<=30,X369-TODAY()>=0,OR(Z369="",Z369<90)),"At risk — close to off track","On track")))))))) | IF(OR(F369="",AC369="Completed / Handover",AC369="Cancelled"),"",IF(O369="Not awarded",IF(U369<>"",U369-TODAY(),IF(X369="","",X369-TODAY())),IF(X369="","",X369-TODAY()))) | [14 empty] | IF(OR(F369="",AJ369=""),"",IF(COUNT(AI369:AI369)=0,"",AJ369-LOOKUP(2,1/(AI369:AI369<>""),AI369:AI369))) | IF(OR(F369="",AK369=""),"",IF(COUNT(AI369:AJ369)=0,"",AK369-LOOKUP(2,1/(AI369:AJ369<>""),AI369:AJ369))) | IF(OR(F369="",AL369=""),"",IF(COUNT(AI369:AK369)=0,"",AL369-LOOKUP(2,1/(AI369:AK369<>""),AI369:AK369))) | IF(OR(F369="",AM369=""),"",IF(COUNT(AI369:AL369)=0,"",AM369-LOOKUP(2,1/(AI369:AL369<>""),AI369:AL369))) | IF(OR(F369="",AN369=""),"",IF(COUNT(AI369:AM369)=0,"",AN369-LOOKUP(2,1/(AI369:AM369<>""),AI369:AM369))) | IF(OR(F369="",AO369=""),"",IF(COUNT(AI369:AN369)=0,"",AO369-LOOKUP(2,1/(AI369:AN369<>""),AI369:AN369))) | IF(OR(F369="",AP369=""),"",IF(COUNT(AI369:AO369)=0,"",AP369-LOOKUP(2,1/(AI369:AO369<>""),AI369:AO369))) | IF(OR(F369="",AQ369=""),"",IF(COUNT(AI369:AP369)=0,"",AQ369-LOOKUP(2,1/(AI369:AP369<>""),AI369:AP369))) | IF(OR(F369="",AR369=""),"",IF(COUNT(AI369:AQ369)=0,"",AR369-LOOKUP(2,1/(AI369:AQ369<>""),AI369:AQ369))) | IF(OR(F369="",AS369=""),"",IF(COUNT(AI369:AR369)=0,"",AS369-LOOKUP(2,1/(AI369:AR369<>""),AI369:AR369))) | IF(OR(F369="",AT369=""),"",IF(COUNT(AI369:AS369)=0,"",AT369-LOOKUP(2,1/(AI369:AS369<>""),AI369:AS369))) | IF(OR(F369="",AU369=""),"",IF(COUNT(AI369:AT369)=0,"",AU369-LOOKUP(2,1/(AI369:AT369<>""),AI369:AT369))) | IF(OR(F369="",AV369=""),"",IF(COUNT(AI369:AU369)=0,"",AV369-LOOKUP(2,1/(AI369:AU369<>""),AI369:AU369))) | IF(J369="","All_Provinces",IFERROR(VLOOKUP(J369,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K369="","All_Districts",IFERROR(VLOOKUP(K369,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F370="","",ROW()-3) | [18 empty] | IF(AQ370="","",AQ370) |  |  |  | IF(W370<>"",W370,IF(OR(T370="",V370=""),"",EDATE(T370,V370))) |  |  |  |  | IF(F370="","",IF(COUNT(AI370:AV370)=0,IF(AA370="","Not started",AA370),SUBSTITUTE(LOOKUP(2,1/(AI370:AV370<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F370="",COUNT(AI370:AV370)=0),"",TODAY()-LOOKUP(2,1/(AI370:AV370<>""),AI370:AV370)) | IF(OR(F370="",COUNT(AI370:AV370)<2),"",LOOKUP(2,1/(AI370:AV370<>""),AI370:AV370)-MIN(AI370:AV370)) | IF(OR(AD370="",AC370="Not started",AC370=""),"",IFERROR(AD370-IF(VLOOKUP(AC370,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC370,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F370="","",IF(OR(AA370="Cancelled",AC370="Cancelled"),"Cancelled",IF(OR(AC370="Completed / Handover",Y370<>"",Z370>=100),"Completed — on track",IF(O370="Not awarded",IF(U370="",IF(X370="","No planned date",IF(TODAY()>X370,"Behind — past planned date",IF(X370-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U370,"Behind — award date passed",IF(U370-TODAY()<=30,"At risk — close to off track","On track"))),IF(X370="","No planned date",IF(AND(TODAY()>X370,OR(Z370="",Z370<100)),"Behind — past end date",IF(AND(T370<>"",X370<>"",Z370<>"",(Z370<100),((TODAY()-T370)/MAX(X370-T370,1)*100)-Z370>15),"Behind — progress lag",IF(AND(X370-TODAY()<=30,X370-TODAY()>=0,OR(Z370="",Z370<90)),"At risk — close to off track","On track")))))))) | IF(OR(F370="",AC370="Completed / Handover",AC370="Cancelled"),"",IF(O370="Not awarded",IF(U370<>"",U370-TODAY(),IF(X370="","",X370-TODAY())),IF(X370="","",X370-TODAY()))) | [14 empty] | IF(OR(F370="",AJ370=""),"",IF(COUNT(AI370:AI370)=0,"",AJ370-LOOKUP(2,1/(AI370:AI370<>""),AI370:AI370))) | IF(OR(F370="",AK370=""),"",IF(COUNT(AI370:AJ370)=0,"",AK370-LOOKUP(2,1/(AI370:AJ370<>""),AI370:AJ370))) | IF(OR(F370="",AL370=""),"",IF(COUNT(AI370:AK370)=0,"",AL370-LOOKUP(2,1/(AI370:AK370<>""),AI370:AK370))) | IF(OR(F370="",AM370=""),"",IF(COUNT(AI370:AL370)=0,"",AM370-LOOKUP(2,1/(AI370:AL370<>""),AI370:AL370))) | IF(OR(F370="",AN370=""),"",IF(COUNT(AI370:AM370)=0,"",AN370-LOOKUP(2,1/(AI370:AM370<>""),AI370:AM370))) | IF(OR(F370="",AO370=""),"",IF(COUNT(AI370:AN370)=0,"",AO370-LOOKUP(2,1/(AI370:AN370<>""),AI370:AN370))) | IF(OR(F370="",AP370=""),"",IF(COUNT(AI370:AO370)=0,"",AP370-LOOKUP(2,1/(AI370:AO370<>""),AI370:AO370))) | IF(OR(F370="",AQ370=""),"",IF(COUNT(AI370:AP370)=0,"",AQ370-LOOKUP(2,1/(AI370:AP370<>""),AI370:AP370))) | IF(OR(F370="",AR370=""),"",IF(COUNT(AI370:AQ370)=0,"",AR370-LOOKUP(2,1/(AI370:AQ370<>""),AI370:AQ370))) | IF(OR(F370="",AS370=""),"",IF(COUNT(AI370:AR370)=0,"",AS370-LOOKUP(2,1/(AI370:AR370<>""),AI370:AR370))) | IF(OR(F370="",AT370=""),"",IF(COUNT(AI370:AS370)=0,"",AT370-LOOKUP(2,1/(AI370:AS370<>""),AI370:AS370))) | IF(OR(F370="",AU370=""),"",IF(COUNT(AI370:AT370)=0,"",AU370-LOOKUP(2,1/(AI370:AT370<>""),AI370:AT370))) | IF(OR(F370="",AV370=""),"",IF(COUNT(AI370:AU370)=0,"",AV370-LOOKUP(2,1/(AI370:AU370<>""),AI370:AU370))) | IF(J370="","All_Provinces",IFERROR(VLOOKUP(J370,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K370="","All_Districts",IFERROR(VLOOKUP(K370,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F371="","",ROW()-3) | [18 empty] | IF(AQ371="","",AQ371) |  |  |  | IF(W371<>"",W371,IF(OR(T371="",V371=""),"",EDATE(T371,V371))) |  |  |  |  | IF(F371="","",IF(COUNT(AI371:AV371)=0,IF(AA371="","Not started",AA371),SUBSTITUTE(LOOKUP(2,1/(AI371:AV371<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F371="",COUNT(AI371:AV371)=0),"",TODAY()-LOOKUP(2,1/(AI371:AV371<>""),AI371:AV371)) | IF(OR(F371="",COUNT(AI371:AV371)<2),"",LOOKUP(2,1/(AI371:AV371<>""),AI371:AV371)-MIN(AI371:AV371)) | IF(OR(AD371="",AC371="Not started",AC371=""),"",IFERROR(AD371-IF(VLOOKUP(AC371,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC371,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F371="","",IF(OR(AA371="Cancelled",AC371="Cancelled"),"Cancelled",IF(OR(AC371="Completed / Handover",Y371<>"",Z371>=100),"Completed — on track",IF(O371="Not awarded",IF(U371="",IF(X371="","No planned date",IF(TODAY()>X371,"Behind — past planned date",IF(X371-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U371,"Behind — award date passed",IF(U371-TODAY()<=30,"At risk — close to off track","On track"))),IF(X371="","No planned date",IF(AND(TODAY()>X371,OR(Z371="",Z371<100)),"Behind — past end date",IF(AND(T371<>"",X371<>"",Z371<>"",(Z371<100),((TODAY()-T371)/MAX(X371-T371,1)*100)-Z371>15),"Behind — progress lag",IF(AND(X371-TODAY()<=30,X371-TODAY()>=0,OR(Z371="",Z371<90)),"At risk — close to off track","On track")))))))) | IF(OR(F371="",AC371="Completed / Handover",AC371="Cancelled"),"",IF(O371="Not awarded",IF(U371<>"",U371-TODAY(),IF(X371="","",X371-TODAY())),IF(X371="","",X371-TODAY()))) | [14 empty] | IF(OR(F371="",AJ371=""),"",IF(COUNT(AI371:AI371)=0,"",AJ371-LOOKUP(2,1/(AI371:AI371<>""),AI371:AI371))) | IF(OR(F371="",AK371=""),"",IF(COUNT(AI371:AJ371)=0,"",AK371-LOOKUP(2,1/(AI371:AJ371<>""),AI371:AJ371))) | IF(OR(F371="",AL371=""),"",IF(COUNT(AI371:AK371)=0,"",AL371-LOOKUP(2,1/(AI371:AK371<>""),AI371:AK371))) | IF(OR(F371="",AM371=""),"",IF(COUNT(AI371:AL371)=0,"",AM371-LOOKUP(2,1/(AI371:AL371<>""),AI371:AL371))) | IF(OR(F371="",AN371=""),"",IF(COUNT(AI371:AM371)=0,"",AN371-LOOKUP(2,1/(AI371:AM371<>""),AI371:AM371))) | IF(OR(F371="",AO371=""),"",IF(COUNT(AI371:AN371)=0,"",AO371-LOOKUP(2,1/(AI371:AN371<>""),AI371:AN371))) | IF(OR(F371="",AP371=""),"",IF(COUNT(AI371:AO371)=0,"",AP371-LOOKUP(2,1/(AI371:AO371<>""),AI371:AO371))) | IF(OR(F371="",AQ371=""),"",IF(COUNT(AI371:AP371)=0,"",AQ371-LOOKUP(2,1/(AI371:AP371<>""),AI371:AP371))) | IF(OR(F371="",AR371=""),"",IF(COUNT(AI371:AQ371)=0,"",AR371-LOOKUP(2,1/(AI371:AQ371<>""),AI371:AQ371))) | IF(OR(F371="",AS371=""),"",IF(COUNT(AI371:AR371)=0,"",AS371-LOOKUP(2,1/(AI371:AR371<>""),AI371:AR371))) | IF(OR(F371="",AT371=""),"",IF(COUNT(AI371:AS371)=0,"",AT371-LOOKUP(2,1/(AI371:AS371<>""),AI371:AS371))) | IF(OR(F371="",AU371=""),"",IF(COUNT(AI371:AT371)=0,"",AU371-LOOKUP(2,1/(AI371:AT371<>""),AI371:AT371))) | IF(OR(F371="",AV371=""),"",IF(COUNT(AI371:AU371)=0,"",AV371-LOOKUP(2,1/(AI371:AU371<>""),AI371:AU371))) | IF(J371="","All_Provinces",IFERROR(VLOOKUP(J371,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K371="","All_Districts",IFERROR(VLOOKUP(K371,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F372="","",ROW()-3) | [18 empty] | IF(AQ372="","",AQ372) |  |  |  | IF(W372<>"",W372,IF(OR(T372="",V372=""),"",EDATE(T372,V372))) |  |  |  |  | IF(F372="","",IF(COUNT(AI372:AV372)=0,IF(AA372="","Not started",AA372),SUBSTITUTE(LOOKUP(2,1/(AI372:AV372<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F372="",COUNT(AI372:AV372)=0),"",TODAY()-LOOKUP(2,1/(AI372:AV372<>""),AI372:AV372)) | IF(OR(F372="",COUNT(AI372:AV372)<2),"",LOOKUP(2,1/(AI372:AV372<>""),AI372:AV372)-MIN(AI372:AV372)) | IF(OR(AD372="",AC372="Not started",AC372=""),"",IFERROR(AD372-IF(VLOOKUP(AC372,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC372,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F372="","",IF(OR(AA372="Cancelled",AC372="Cancelled"),"Cancelled",IF(OR(AC372="Completed / Handover",Y372<>"",Z372>=100),"Completed — on track",IF(O372="Not awarded",IF(U372="",IF(X372="","No planned date",IF(TODAY()>X372,"Behind — past planned date",IF(X372-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U372,"Behind — award date passed",IF(U372-TODAY()<=30,"At risk — close to off track","On track"))),IF(X372="","No planned date",IF(AND(TODAY()>X372,OR(Z372="",Z372<100)),"Behind — past end date",IF(AND(T372<>"",X372<>"",Z372<>"",(Z372<100),((TODAY()-T372)/MAX(X372-T372,1)*100)-Z372>15),"Behind — progress lag",IF(AND(X372-TODAY()<=30,X372-TODAY()>=0,OR(Z372="",Z372<90)),"At risk — close to off track","On track")))))))) | IF(OR(F372="",AC372="Completed / Handover",AC372="Cancelled"),"",IF(O372="Not awarded",IF(U372<>"",U372-TODAY(),IF(X372="","",X372-TODAY())),IF(X372="","",X372-TODAY()))) | [14 empty] | IF(OR(F372="",AJ372=""),"",IF(COUNT(AI372:AI372)=0,"",AJ372-LOOKUP(2,1/(AI372:AI372<>""),AI372:AI372))) | IF(OR(F372="",AK372=""),"",IF(COUNT(AI372:AJ372)=0,"",AK372-LOOKUP(2,1/(AI372:AJ372<>""),AI372:AJ372))) | IF(OR(F372="",AL372=""),"",IF(COUNT(AI372:AK372)=0,"",AL372-LOOKUP(2,1/(AI372:AK372<>""),AI372:AK372))) | IF(OR(F372="",AM372=""),"",IF(COUNT(AI372:AL372)=0,"",AM372-LOOKUP(2,1/(AI372:AL372<>""),AI372:AL372))) | IF(OR(F372="",AN372=""),"",IF(COUNT(AI372:AM372)=0,"",AN372-LOOKUP(2,1/(AI372:AM372<>""),AI372:AM372))) | IF(OR(F372="",AO372=""),"",IF(COUNT(AI372:AN372)=0,"",AO372-LOOKUP(2,1/(AI372:AN372<>""),AI372:AN372))) | IF(OR(F372="",AP372=""),"",IF(COUNT(AI372:AO372)=0,"",AP372-LOOKUP(2,1/(AI372:AO372<>""),AI372:AO372))) | IF(OR(F372="",AQ372=""),"",IF(COUNT(AI372:AP372)=0,"",AQ372-LOOKUP(2,1/(AI372:AP372<>""),AI372:AP372))) | IF(OR(F372="",AR372=""),"",IF(COUNT(AI372:AQ372)=0,"",AR372-LOOKUP(2,1/(AI372:AQ372<>""),AI372:AQ372))) | IF(OR(F372="",AS372=""),"",IF(COUNT(AI372:AR372)=0,"",AS372-LOOKUP(2,1/(AI372:AR372<>""),AI372:AR372))) | IF(OR(F372="",AT372=""),"",IF(COUNT(AI372:AS372)=0,"",AT372-LOOKUP(2,1/(AI372:AS372<>""),AI372:AS372))) | IF(OR(F372="",AU372=""),"",IF(COUNT(AI372:AT372)=0,"",AU372-LOOKUP(2,1/(AI372:AT372<>""),AI372:AT372))) | IF(OR(F372="",AV372=""),"",IF(COUNT(AI372:AU372)=0,"",AV372-LOOKUP(2,1/(AI372:AU372<>""),AI372:AU372))) | IF(J372="","All_Provinces",IFERROR(VLOOKUP(J372,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K372="","All_Districts",IFERROR(VLOOKUP(K372,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F373="","",ROW()-3) | [18 empty] | IF(AQ373="","",AQ373) |  |  |  | IF(W373<>"",W373,IF(OR(T373="",V373=""),"",EDATE(T373,V373))) |  |  |  |  | IF(F373="","",IF(COUNT(AI373:AV373)=0,IF(AA373="","Not started",AA373),SUBSTITUTE(LOOKUP(2,1/(AI373:AV373<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F373="",COUNT(AI373:AV373)=0),"",TODAY()-LOOKUP(2,1/(AI373:AV373<>""),AI373:AV373)) | IF(OR(F373="",COUNT(AI373:AV373)<2),"",LOOKUP(2,1/(AI373:AV373<>""),AI373:AV373)-MIN(AI373:AV373)) | IF(OR(AD373="",AC373="Not started",AC373=""),"",IFERROR(AD373-IF(VLOOKUP(AC373,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC373,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F373="","",IF(OR(AA373="Cancelled",AC373="Cancelled"),"Cancelled",IF(OR(AC373="Completed / Handover",Y373<>"",Z373>=100),"Completed — on track",IF(O373="Not awarded",IF(U373="",IF(X373="","No planned date",IF(TODAY()>X373,"Behind — past planned date",IF(X373-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U373,"Behind — award date passed",IF(U373-TODAY()<=30,"At risk — close to off track","On track"))),IF(X373="","No planned date",IF(AND(TODAY()>X373,OR(Z373="",Z373<100)),"Behind — past end date",IF(AND(T373<>"",X373<>"",Z373<>"",(Z373<100),((TODAY()-T373)/MAX(X373-T373,1)*100)-Z373>15),"Behind — progress lag",IF(AND(X373-TODAY()<=30,X373-TODAY()>=0,OR(Z373="",Z373<90)),"At risk — close to off track","On track")))))))) | IF(OR(F373="",AC373="Completed / Handover",AC373="Cancelled"),"",IF(O373="Not awarded",IF(U373<>"",U373-TODAY(),IF(X373="","",X373-TODAY())),IF(X373="","",X373-TODAY()))) | [14 empty] | IF(OR(F373="",AJ373=""),"",IF(COUNT(AI373:AI373)=0,"",AJ373-LOOKUP(2,1/(AI373:AI373<>""),AI373:AI373))) | IF(OR(F373="",AK373=""),"",IF(COUNT(AI373:AJ373)=0,"",AK373-LOOKUP(2,1/(AI373:AJ373<>""),AI373:AJ373))) | IF(OR(F373="",AL373=""),"",IF(COUNT(AI373:AK373)=0,"",AL373-LOOKUP(2,1/(AI373:AK373<>""),AI373:AK373))) | IF(OR(F373="",AM373=""),"",IF(COUNT(AI373:AL373)=0,"",AM373-LOOKUP(2,1/(AI373:AL373<>""),AI373:AL373))) | IF(OR(F373="",AN373=""),"",IF(COUNT(AI373:AM373)=0,"",AN373-LOOKUP(2,1/(AI373:AM373<>""),AI373:AM373))) | IF(OR(F373="",AO373=""),"",IF(COUNT(AI373:AN373)=0,"",AO373-LOOKUP(2,1/(AI373:AN373<>""),AI373:AN373))) | IF(OR(F373="",AP373=""),"",IF(COUNT(AI373:AO373)=0,"",AP373-LOOKUP(2,1/(AI373:AO373<>""),AI373:AO373))) | IF(OR(F373="",AQ373=""),"",IF(COUNT(AI373:AP373)=0,"",AQ373-LOOKUP(2,1/(AI373:AP373<>""),AI373:AP373))) | IF(OR(F373="",AR373=""),"",IF(COUNT(AI373:AQ373)=0,"",AR373-LOOKUP(2,1/(AI373:AQ373<>""),AI373:AQ373))) | IF(OR(F373="",AS373=""),"",IF(COUNT(AI373:AR373)=0,"",AS373-LOOKUP(2,1/(AI373:AR373<>""),AI373:AR373))) | IF(OR(F373="",AT373=""),"",IF(COUNT(AI373:AS373)=0,"",AT373-LOOKUP(2,1/(AI373:AS373<>""),AI373:AS373))) | IF(OR(F373="",AU373=""),"",IF(COUNT(AI373:AT373)=0,"",AU373-LOOKUP(2,1/(AI373:AT373<>""),AI373:AT373))) | IF(OR(F373="",AV373=""),"",IF(COUNT(AI373:AU373)=0,"",AV373-LOOKUP(2,1/(AI373:AU373<>""),AI373:AU373))) | IF(J373="","All_Provinces",IFERROR(VLOOKUP(J373,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K373="","All_Districts",IFERROR(VLOOKUP(K373,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F374="","",ROW()-3) | [18 empty] | IF(AQ374="","",AQ374) |  |  |  | IF(W374<>"",W374,IF(OR(T374="",V374=""),"",EDATE(T374,V374))) |  |  |  |  | IF(F374="","",IF(COUNT(AI374:AV374)=0,IF(AA374="","Not started",AA374),SUBSTITUTE(LOOKUP(2,1/(AI374:AV374<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F374="",COUNT(AI374:AV374)=0),"",TODAY()-LOOKUP(2,1/(AI374:AV374<>""),AI374:AV374)) | IF(OR(F374="",COUNT(AI374:AV374)<2),"",LOOKUP(2,1/(AI374:AV374<>""),AI374:AV374)-MIN(AI374:AV374)) | IF(OR(AD374="",AC374="Not started",AC374=""),"",IFERROR(AD374-IF(VLOOKUP(AC374,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC374,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F374="","",IF(OR(AA374="Cancelled",AC374="Cancelled"),"Cancelled",IF(OR(AC374="Completed / Handover",Y374<>"",Z374>=100),"Completed — on track",IF(O374="Not awarded",IF(U374="",IF(X374="","No planned date",IF(TODAY()>X374,"Behind — past planned date",IF(X374-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U374,"Behind — award date passed",IF(U374-TODAY()<=30,"At risk — close to off track","On track"))),IF(X374="","No planned date",IF(AND(TODAY()>X374,OR(Z374="",Z374<100)),"Behind — past end date",IF(AND(T374<>"",X374<>"",Z374<>"",(Z374<100),((TODAY()-T374)/MAX(X374-T374,1)*100)-Z374>15),"Behind — progress lag",IF(AND(X374-TODAY()<=30,X374-TODAY()>=0,OR(Z374="",Z374<90)),"At risk — close to off track","On track")))))))) | IF(OR(F374="",AC374="Completed / Handover",AC374="Cancelled"),"",IF(O374="Not awarded",IF(U374<>"",U374-TODAY(),IF(X374="","",X374-TODAY())),IF(X374="","",X374-TODAY()))) | [14 empty] | IF(OR(F374="",AJ374=""),"",IF(COUNT(AI374:AI374)=0,"",AJ374-LOOKUP(2,1/(AI374:AI374<>""),AI374:AI374))) | IF(OR(F374="",AK374=""),"",IF(COUNT(AI374:AJ374)=0,"",AK374-LOOKUP(2,1/(AI374:AJ374<>""),AI374:AJ374))) | IF(OR(F374="",AL374=""),"",IF(COUNT(AI374:AK374)=0,"",AL374-LOOKUP(2,1/(AI374:AK374<>""),AI374:AK374))) | IF(OR(F374="",AM374=""),"",IF(COUNT(AI374:AL374)=0,"",AM374-LOOKUP(2,1/(AI374:AL374<>""),AI374:AL374))) | IF(OR(F374="",AN374=""),"",IF(COUNT(AI374:AM374)=0,"",AN374-LOOKUP(2,1/(AI374:AM374<>""),AI374:AM374))) | IF(OR(F374="",AO374=""),"",IF(COUNT(AI374:AN374)=0,"",AO374-LOOKUP(2,1/(AI374:AN374<>""),AI374:AN374))) | IF(OR(F374="",AP374=""),"",IF(COUNT(AI374:AO374)=0,"",AP374-LOOKUP(2,1/(AI374:AO374<>""),AI374:AO374))) | IF(OR(F374="",AQ374=""),"",IF(COUNT(AI374:AP374)=0,"",AQ374-LOOKUP(2,1/(AI374:AP374<>""),AI374:AP374))) | IF(OR(F374="",AR374=""),"",IF(COUNT(AI374:AQ374)=0,"",AR374-LOOKUP(2,1/(AI374:AQ374<>""),AI374:AQ374))) | IF(OR(F374="",AS374=""),"",IF(COUNT(AI374:AR374)=0,"",AS374-LOOKUP(2,1/(AI374:AR374<>""),AI374:AR374))) | IF(OR(F374="",AT374=""),"",IF(COUNT(AI374:AS374)=0,"",AT374-LOOKUP(2,1/(AI374:AS374<>""),AI374:AS374))) | IF(OR(F374="",AU374=""),"",IF(COUNT(AI374:AT374)=0,"",AU374-LOOKUP(2,1/(AI374:AT374<>""),AI374:AT374))) | IF(OR(F374="",AV374=""),"",IF(COUNT(AI374:AU374)=0,"",AV374-LOOKUP(2,1/(AI374:AU374<>""),AI374:AU374))) | IF(J374="","All_Provinces",IFERROR(VLOOKUP(J374,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K374="","All_Districts",IFERROR(VLOOKUP(K374,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F375="","",ROW()-3) | [18 empty] | IF(AQ375="","",AQ375) |  |  |  | IF(W375<>"",W375,IF(OR(T375="",V375=""),"",EDATE(T375,V375))) |  |  |  |  | IF(F375="","",IF(COUNT(AI375:AV375)=0,IF(AA375="","Not started",AA375),SUBSTITUTE(LOOKUP(2,1/(AI375:AV375<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F375="",COUNT(AI375:AV375)=0),"",TODAY()-LOOKUP(2,1/(AI375:AV375<>""),AI375:AV375)) | IF(OR(F375="",COUNT(AI375:AV375)<2),"",LOOKUP(2,1/(AI375:AV375<>""),AI375:AV375)-MIN(AI375:AV375)) | IF(OR(AD375="",AC375="Not started",AC375=""),"",IFERROR(AD375-IF(VLOOKUP(AC375,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC375,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F375="","",IF(OR(AA375="Cancelled",AC375="Cancelled"),"Cancelled",IF(OR(AC375="Completed / Handover",Y375<>"",Z375>=100),"Completed — on track",IF(O375="Not awarded",IF(U375="",IF(X375="","No planned date",IF(TODAY()>X375,"Behind — past planned date",IF(X375-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U375,"Behind — award date passed",IF(U375-TODAY()<=30,"At risk — close to off track","On track"))),IF(X375="","No planned date",IF(AND(TODAY()>X375,OR(Z375="",Z375<100)),"Behind — past end date",IF(AND(T375<>"",X375<>"",Z375<>"",(Z375<100),((TODAY()-T375)/MAX(X375-T375,1)*100)-Z375>15),"Behind — progress lag",IF(AND(X375-TODAY()<=30,X375-TODAY()>=0,OR(Z375="",Z375<90)),"At risk — close to off track","On track")))))))) | IF(OR(F375="",AC375="Completed / Handover",AC375="Cancelled"),"",IF(O375="Not awarded",IF(U375<>"",U375-TODAY(),IF(X375="","",X375-TODAY())),IF(X375="","",X375-TODAY()))) | [14 empty] | IF(OR(F375="",AJ375=""),"",IF(COUNT(AI375:AI375)=0,"",AJ375-LOOKUP(2,1/(AI375:AI375<>""),AI375:AI375))) | IF(OR(F375="",AK375=""),"",IF(COUNT(AI375:AJ375)=0,"",AK375-LOOKUP(2,1/(AI375:AJ375<>""),AI375:AJ375))) | IF(OR(F375="",AL375=""),"",IF(COUNT(AI375:AK375)=0,"",AL375-LOOKUP(2,1/(AI375:AK375<>""),AI375:AK375))) | IF(OR(F375="",AM375=""),"",IF(COUNT(AI375:AL375)=0,"",AM375-LOOKUP(2,1/(AI375:AL375<>""),AI375:AL375))) | IF(OR(F375="",AN375=""),"",IF(COUNT(AI375:AM375)=0,"",AN375-LOOKUP(2,1/(AI375:AM375<>""),AI375:AM375))) | IF(OR(F375="",AO375=""),"",IF(COUNT(AI375:AN375)=0,"",AO375-LOOKUP(2,1/(AI375:AN375<>""),AI375:AN375))) | IF(OR(F375="",AP375=""),"",IF(COUNT(AI375:AO375)=0,"",AP375-LOOKUP(2,1/(AI375:AO375<>""),AI375:AO375))) | IF(OR(F375="",AQ375=""),"",IF(COUNT(AI375:AP375)=0,"",AQ375-LOOKUP(2,1/(AI375:AP375<>""),AI375:AP375))) | IF(OR(F375="",AR375=""),"",IF(COUNT(AI375:AQ375)=0,"",AR375-LOOKUP(2,1/(AI375:AQ375<>""),AI375:AQ375))) | IF(OR(F375="",AS375=""),"",IF(COUNT(AI375:AR375)=0,"",AS375-LOOKUP(2,1/(AI375:AR375<>""),AI375:AR375))) | IF(OR(F375="",AT375=""),"",IF(COUNT(AI375:AS375)=0,"",AT375-LOOKUP(2,1/(AI375:AS375<>""),AI375:AS375))) | IF(OR(F375="",AU375=""),"",IF(COUNT(AI375:AT375)=0,"",AU375-LOOKUP(2,1/(AI375:AT375<>""),AI375:AT375))) | IF(OR(F375="",AV375=""),"",IF(COUNT(AI375:AU375)=0,"",AV375-LOOKUP(2,1/(AI375:AU375<>""),AI375:AU375))) | IF(J375="","All_Provinces",IFERROR(VLOOKUP(J375,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K375="","All_Districts",IFERROR(VLOOKUP(K375,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F376="","",ROW()-3) | [18 empty] | IF(AQ376="","",AQ376) |  |  |  | IF(W376<>"",W376,IF(OR(T376="",V376=""),"",EDATE(T376,V376))) |  |  |  |  | IF(F376="","",IF(COUNT(AI376:AV376)=0,IF(AA376="","Not started",AA376),SUBSTITUTE(LOOKUP(2,1/(AI376:AV376<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F376="",COUNT(AI376:AV376)=0),"",TODAY()-LOOKUP(2,1/(AI376:AV376<>""),AI376:AV376)) | IF(OR(F376="",COUNT(AI376:AV376)<2),"",LOOKUP(2,1/(AI376:AV376<>""),AI376:AV376)-MIN(AI376:AV376)) | IF(OR(AD376="",AC376="Not started",AC376=""),"",IFERROR(AD376-IF(VLOOKUP(AC376,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC376,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F376="","",IF(OR(AA376="Cancelled",AC376="Cancelled"),"Cancelled",IF(OR(AC376="Completed / Handover",Y376<>"",Z376>=100),"Completed — on track",IF(O376="Not awarded",IF(U376="",IF(X376="","No planned date",IF(TODAY()>X376,"Behind — past planned date",IF(X376-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U376,"Behind — award date passed",IF(U376-TODAY()<=30,"At risk — close to off track","On track"))),IF(X376="","No planned date",IF(AND(TODAY()>X376,OR(Z376="",Z376<100)),"Behind — past end date",IF(AND(T376<>"",X376<>"",Z376<>"",(Z376<100),((TODAY()-T376)/MAX(X376-T376,1)*100)-Z376>15),"Behind — progress lag",IF(AND(X376-TODAY()<=30,X376-TODAY()>=0,OR(Z376="",Z376<90)),"At risk — close to off track","On track")))))))) | IF(OR(F376="",AC376="Completed / Handover",AC376="Cancelled"),"",IF(O376="Not awarded",IF(U376<>"",U376-TODAY(),IF(X376="","",X376-TODAY())),IF(X376="","",X376-TODAY()))) | [14 empty] | IF(OR(F376="",AJ376=""),"",IF(COUNT(AI376:AI376)=0,"",AJ376-LOOKUP(2,1/(AI376:AI376<>""),AI376:AI376))) | IF(OR(F376="",AK376=""),"",IF(COUNT(AI376:AJ376)=0,"",AK376-LOOKUP(2,1/(AI376:AJ376<>""),AI376:AJ376))) | IF(OR(F376="",AL376=""),"",IF(COUNT(AI376:AK376)=0,"",AL376-LOOKUP(2,1/(AI376:AK376<>""),AI376:AK376))) | IF(OR(F376="",AM376=""),"",IF(COUNT(AI376:AL376)=0,"",AM376-LOOKUP(2,1/(AI376:AL376<>""),AI376:AL376))) | IF(OR(F376="",AN376=""),"",IF(COUNT(AI376:AM376)=0,"",AN376-LOOKUP(2,1/(AI376:AM376<>""),AI376:AM376))) | IF(OR(F376="",AO376=""),"",IF(COUNT(AI376:AN376)=0,"",AO376-LOOKUP(2,1/(AI376:AN376<>""),AI376:AN376))) | IF(OR(F376="",AP376=""),"",IF(COUNT(AI376:AO376)=0,"",AP376-LOOKUP(2,1/(AI376:AO376<>""),AI376:AO376))) | IF(OR(F376="",AQ376=""),"",IF(COUNT(AI376:AP376)=0,"",AQ376-LOOKUP(2,1/(AI376:AP376<>""),AI376:AP376))) | IF(OR(F376="",AR376=""),"",IF(COUNT(AI376:AQ376)=0,"",AR376-LOOKUP(2,1/(AI376:AQ376<>""),AI376:AQ376))) | IF(OR(F376="",AS376=""),"",IF(COUNT(AI376:AR376)=0,"",AS376-LOOKUP(2,1/(AI376:AR376<>""),AI376:AR376))) | IF(OR(F376="",AT376=""),"",IF(COUNT(AI376:AS376)=0,"",AT376-LOOKUP(2,1/(AI376:AS376<>""),AI376:AS376))) | IF(OR(F376="",AU376=""),"",IF(COUNT(AI376:AT376)=0,"",AU376-LOOKUP(2,1/(AI376:AT376<>""),AI376:AT376))) | IF(OR(F376="",AV376=""),"",IF(COUNT(AI376:AU376)=0,"",AV376-LOOKUP(2,1/(AI376:AU376<>""),AI376:AU376))) | IF(J376="","All_Provinces",IFERROR(VLOOKUP(J376,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K376="","All_Districts",IFERROR(VLOOKUP(K376,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F377="","",ROW()-3) | [18 empty] | IF(AQ377="","",AQ377) |  |  |  | IF(W377<>"",W377,IF(OR(T377="",V377=""),"",EDATE(T377,V377))) |  |  |  |  | IF(F377="","",IF(COUNT(AI377:AV377)=0,IF(AA377="","Not started",AA377),SUBSTITUTE(LOOKUP(2,1/(AI377:AV377<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F377="",COUNT(AI377:AV377)=0),"",TODAY()-LOOKUP(2,1/(AI377:AV377<>""),AI377:AV377)) | IF(OR(F377="",COUNT(AI377:AV377)<2),"",LOOKUP(2,1/(AI377:AV377<>""),AI377:AV377)-MIN(AI377:AV377)) | IF(OR(AD377="",AC377="Not started",AC377=""),"",IFERROR(AD377-IF(VLOOKUP(AC377,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC377,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F377="","",IF(OR(AA377="Cancelled",AC377="Cancelled"),"Cancelled",IF(OR(AC377="Completed / Handover",Y377<>"",Z377>=100),"Completed — on track",IF(O377="Not awarded",IF(U377="",IF(X377="","No planned date",IF(TODAY()>X377,"Behind — past planned date",IF(X377-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U377,"Behind — award date passed",IF(U377-TODAY()<=30,"At risk — close to off track","On track"))),IF(X377="","No planned date",IF(AND(TODAY()>X377,OR(Z377="",Z377<100)),"Behind — past end date",IF(AND(T377<>"",X377<>"",Z377<>"",(Z377<100),((TODAY()-T377)/MAX(X377-T377,1)*100)-Z377>15),"Behind — progress lag",IF(AND(X377-TODAY()<=30,X377-TODAY()>=0,OR(Z377="",Z377<90)),"At risk — close to off track","On track")))))))) | IF(OR(F377="",AC377="Completed / Handover",AC377="Cancelled"),"",IF(O377="Not awarded",IF(U377<>"",U377-TODAY(),IF(X377="","",X377-TODAY())),IF(X377="","",X377-TODAY()))) | [14 empty] | IF(OR(F377="",AJ377=""),"",IF(COUNT(AI377:AI377)=0,"",AJ377-LOOKUP(2,1/(AI377:AI377<>""),AI377:AI377))) | IF(OR(F377="",AK377=""),"",IF(COUNT(AI377:AJ377)=0,"",AK377-LOOKUP(2,1/(AI377:AJ377<>""),AI377:AJ377))) | IF(OR(F377="",AL377=""),"",IF(COUNT(AI377:AK377)=0,"",AL377-LOOKUP(2,1/(AI377:AK377<>""),AI377:AK377))) | IF(OR(F377="",AM377=""),"",IF(COUNT(AI377:AL377)=0,"",AM377-LOOKUP(2,1/(AI377:AL377<>""),AI377:AL377))) | IF(OR(F377="",AN377=""),"",IF(COUNT(AI377:AM377)=0,"",AN377-LOOKUP(2,1/(AI377:AM377<>""),AI377:AM377))) | IF(OR(F377="",AO377=""),"",IF(COUNT(AI377:AN377)=0,"",AO377-LOOKUP(2,1/(AI377:AN377<>""),AI377:AN377))) | IF(OR(F377="",AP377=""),"",IF(COUNT(AI377:AO377)=0,"",AP377-LOOKUP(2,1/(AI377:AO377<>""),AI377:AO377))) | IF(OR(F377="",AQ377=""),"",IF(COUNT(AI377:AP377)=0,"",AQ377-LOOKUP(2,1/(AI377:AP377<>""),AI377:AP377))) | IF(OR(F377="",AR377=""),"",IF(COUNT(AI377:AQ377)=0,"",AR377-LOOKUP(2,1/(AI377:AQ377<>""),AI377:AQ377))) | IF(OR(F377="",AS377=""),"",IF(COUNT(AI377:AR377)=0,"",AS377-LOOKUP(2,1/(AI377:AR377<>""),AI377:AR377))) | IF(OR(F377="",AT377=""),"",IF(COUNT(AI377:AS377)=0,"",AT377-LOOKUP(2,1/(AI377:AS377<>""),AI377:AS377))) | IF(OR(F377="",AU377=""),"",IF(COUNT(AI377:AT377)=0,"",AU377-LOOKUP(2,1/(AI377:AT377<>""),AI377:AT377))) | IF(OR(F377="",AV377=""),"",IF(COUNT(AI377:AU377)=0,"",AV377-LOOKUP(2,1/(AI377:AU377<>""),AI377:AU377))) | IF(J377="","All_Provinces",IFERROR(VLOOKUP(J377,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K377="","All_Districts",IFERROR(VLOOKUP(K377,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F378="","",ROW()-3) | [18 empty] | IF(AQ378="","",AQ378) |  |  |  | IF(W378<>"",W378,IF(OR(T378="",V378=""),"",EDATE(T378,V378))) |  |  |  |  | IF(F378="","",IF(COUNT(AI378:AV378)=0,IF(AA378="","Not started",AA378),SUBSTITUTE(LOOKUP(2,1/(AI378:AV378<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F378="",COUNT(AI378:AV378)=0),"",TODAY()-LOOKUP(2,1/(AI378:AV378<>""),AI378:AV378)) | IF(OR(F378="",COUNT(AI378:AV378)<2),"",LOOKUP(2,1/(AI378:AV378<>""),AI378:AV378)-MIN(AI378:AV378)) | IF(OR(AD378="",AC378="Not started",AC378=""),"",IFERROR(AD378-IF(VLOOKUP(AC378,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC378,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F378="","",IF(OR(AA378="Cancelled",AC378="Cancelled"),"Cancelled",IF(OR(AC378="Completed / Handover",Y378<>"",Z378>=100),"Completed — on track",IF(O378="Not awarded",IF(U378="",IF(X378="","No planned date",IF(TODAY()>X378,"Behind — past planned date",IF(X378-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U378,"Behind — award date passed",IF(U378-TODAY()<=30,"At risk — close to off track","On track"))),IF(X378="","No planned date",IF(AND(TODAY()>X378,OR(Z378="",Z378<100)),"Behind — past end date",IF(AND(T378<>"",X378<>"",Z378<>"",(Z378<100),((TODAY()-T378)/MAX(X378-T378,1)*100)-Z378>15),"Behind — progress lag",IF(AND(X378-TODAY()<=30,X378-TODAY()>=0,OR(Z378="",Z378<90)),"At risk — close to off track","On track")))))))) | IF(OR(F378="",AC378="Completed / Handover",AC378="Cancelled"),"",IF(O378="Not awarded",IF(U378<>"",U378-TODAY(),IF(X378="","",X378-TODAY())),IF(X378="","",X378-TODAY()))) | [14 empty] | IF(OR(F378="",AJ378=""),"",IF(COUNT(AI378:AI378)=0,"",AJ378-LOOKUP(2,1/(AI378:AI378<>""),AI378:AI378))) | IF(OR(F378="",AK378=""),"",IF(COUNT(AI378:AJ378)=0,"",AK378-LOOKUP(2,1/(AI378:AJ378<>""),AI378:AJ378))) | IF(OR(F378="",AL378=""),"",IF(COUNT(AI378:AK378)=0,"",AL378-LOOKUP(2,1/(AI378:AK378<>""),AI378:AK378))) | IF(OR(F378="",AM378=""),"",IF(COUNT(AI378:AL378)=0,"",AM378-LOOKUP(2,1/(AI378:AL378<>""),AI378:AL378))) | IF(OR(F378="",AN378=""),"",IF(COUNT(AI378:AM378)=0,"",AN378-LOOKUP(2,1/(AI378:AM378<>""),AI378:AM378))) | IF(OR(F378="",AO378=""),"",IF(COUNT(AI378:AN378)=0,"",AO378-LOOKUP(2,1/(AI378:AN378<>""),AI378:AN378))) | IF(OR(F378="",AP378=""),"",IF(COUNT(AI378:AO378)=0,"",AP378-LOOKUP(2,1/(AI378:AO378<>""),AI378:AO378))) | IF(OR(F378="",AQ378=""),"",IF(COUNT(AI378:AP378)=0,"",AQ378-LOOKUP(2,1/(AI378:AP378<>""),AI378:AP378))) | IF(OR(F378="",AR378=""),"",IF(COUNT(AI378:AQ378)=0,"",AR378-LOOKUP(2,1/(AI378:AQ378<>""),AI378:AQ378))) | IF(OR(F378="",AS378=""),"",IF(COUNT(AI378:AR378)=0,"",AS378-LOOKUP(2,1/(AI378:AR378<>""),AI378:AR378))) | IF(OR(F378="",AT378=""),"",IF(COUNT(AI378:AS378)=0,"",AT378-LOOKUP(2,1/(AI378:AS378<>""),AI378:AS378))) | IF(OR(F378="",AU378=""),"",IF(COUNT(AI378:AT378)=0,"",AU378-LOOKUP(2,1/(AI378:AT378<>""),AI378:AT378))) | IF(OR(F378="",AV378=""),"",IF(COUNT(AI378:AU378)=0,"",AV378-LOOKUP(2,1/(AI378:AU378<>""),AI378:AU378))) | IF(J378="","All_Provinces",IFERROR(VLOOKUP(J378,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K378="","All_Districts",IFERROR(VLOOKUP(K378,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F379="","",ROW()-3) | [18 empty] | IF(AQ379="","",AQ379) |  |  |  | IF(W379<>"",W379,IF(OR(T379="",V379=""),"",EDATE(T379,V379))) |  |  |  |  | IF(F379="","",IF(COUNT(AI379:AV379)=0,IF(AA379="","Not started",AA379),SUBSTITUTE(LOOKUP(2,1/(AI379:AV379<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F379="",COUNT(AI379:AV379)=0),"",TODAY()-LOOKUP(2,1/(AI379:AV379<>""),AI379:AV379)) | IF(OR(F379="",COUNT(AI379:AV379)<2),"",LOOKUP(2,1/(AI379:AV379<>""),AI379:AV379)-MIN(AI379:AV379)) | IF(OR(AD379="",AC379="Not started",AC379=""),"",IFERROR(AD379-IF(VLOOKUP(AC379,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC379,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F379="","",IF(OR(AA379="Cancelled",AC379="Cancelled"),"Cancelled",IF(OR(AC379="Completed / Handover",Y379<>"",Z379>=100),"Completed — on track",IF(O379="Not awarded",IF(U379="",IF(X379="","No planned date",IF(TODAY()>X379,"Behind — past planned date",IF(X379-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U379,"Behind — award date passed",IF(U379-TODAY()<=30,"At risk — close to off track","On track"))),IF(X379="","No planned date",IF(AND(TODAY()>X379,OR(Z379="",Z379<100)),"Behind — past end date",IF(AND(T379<>"",X379<>"",Z379<>"",(Z379<100),((TODAY()-T379)/MAX(X379-T379,1)*100)-Z379>15),"Behind — progress lag",IF(AND(X379-TODAY()<=30,X379-TODAY()>=0,OR(Z379="",Z379<90)),"At risk — close to off track","On track")))))))) | IF(OR(F379="",AC379="Completed / Handover",AC379="Cancelled"),"",IF(O379="Not awarded",IF(U379<>"",U379-TODAY(),IF(X379="","",X379-TODAY())),IF(X379="","",X379-TODAY()))) | [14 empty] | IF(OR(F379="",AJ379=""),"",IF(COUNT(AI379:AI379)=0,"",AJ379-LOOKUP(2,1/(AI379:AI379<>""),AI379:AI379))) | IF(OR(F379="",AK379=""),"",IF(COUNT(AI379:AJ379)=0,"",AK379-LOOKUP(2,1/(AI379:AJ379<>""),AI379:AJ379))) | IF(OR(F379="",AL379=""),"",IF(COUNT(AI379:AK379)=0,"",AL379-LOOKUP(2,1/(AI379:AK379<>""),AI379:AK379))) | IF(OR(F379="",AM379=""),"",IF(COUNT(AI379:AL379)=0,"",AM379-LOOKUP(2,1/(AI379:AL379<>""),AI379:AL379))) | IF(OR(F379="",AN379=""),"",IF(COUNT(AI379:AM379)=0,"",AN379-LOOKUP(2,1/(AI379:AM379<>""),AI379:AM379))) | IF(OR(F379="",AO379=""),"",IF(COUNT(AI379:AN379)=0,"",AO379-LOOKUP(2,1/(AI379:AN379<>""),AI379:AN379))) | IF(OR(F379="",AP379=""),"",IF(COUNT(AI379:AO379)=0,"",AP379-LOOKUP(2,1/(AI379:AO379<>""),AI379:AO379))) | IF(OR(F379="",AQ379=""),"",IF(COUNT(AI379:AP379)=0,"",AQ379-LOOKUP(2,1/(AI379:AP379<>""),AI379:AP379))) | IF(OR(F379="",AR379=""),"",IF(COUNT(AI379:AQ379)=0,"",AR379-LOOKUP(2,1/(AI379:AQ379<>""),AI379:AQ379))) | IF(OR(F379="",AS379=""),"",IF(COUNT(AI379:AR379)=0,"",AS379-LOOKUP(2,1/(AI379:AR379<>""),AI379:AR379))) | IF(OR(F379="",AT379=""),"",IF(COUNT(AI379:AS379)=0,"",AT379-LOOKUP(2,1/(AI379:AS379<>""),AI379:AS379))) | IF(OR(F379="",AU379=""),"",IF(COUNT(AI379:AT379)=0,"",AU379-LOOKUP(2,1/(AI379:AT379<>""),AI379:AT379))) | IF(OR(F379="",AV379=""),"",IF(COUNT(AI379:AU379)=0,"",AV379-LOOKUP(2,1/(AI379:AU379<>""),AI379:AU379))) | IF(J379="","All_Provinces",IFERROR(VLOOKUP(J379,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K379="","All_Districts",IFERROR(VLOOKUP(K379,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F380="","",ROW()-3) | [18 empty] | IF(AQ380="","",AQ380) |  |  |  | IF(W380<>"",W380,IF(OR(T380="",V380=""),"",EDATE(T380,V380))) |  |  |  |  | IF(F380="","",IF(COUNT(AI380:AV380)=0,IF(AA380="","Not started",AA380),SUBSTITUTE(LOOKUP(2,1/(AI380:AV380<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F380="",COUNT(AI380:AV380)=0),"",TODAY()-LOOKUP(2,1/(AI380:AV380<>""),AI380:AV380)) | IF(OR(F380="",COUNT(AI380:AV380)<2),"",LOOKUP(2,1/(AI380:AV380<>""),AI380:AV380)-MIN(AI380:AV380)) | IF(OR(AD380="",AC380="Not started",AC380=""),"",IFERROR(AD380-IF(VLOOKUP(AC380,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC380,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F380="","",IF(OR(AA380="Cancelled",AC380="Cancelled"),"Cancelled",IF(OR(AC380="Completed / Handover",Y380<>"",Z380>=100),"Completed — on track",IF(O380="Not awarded",IF(U380="",IF(X380="","No planned date",IF(TODAY()>X380,"Behind — past planned date",IF(X380-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U380,"Behind — award date passed",IF(U380-TODAY()<=30,"At risk — close to off track","On track"))),IF(X380="","No planned date",IF(AND(TODAY()>X380,OR(Z380="",Z380<100)),"Behind — past end date",IF(AND(T380<>"",X380<>"",Z380<>"",(Z380<100),((TODAY()-T380)/MAX(X380-T380,1)*100)-Z380>15),"Behind — progress lag",IF(AND(X380-TODAY()<=30,X380-TODAY()>=0,OR(Z380="",Z380<90)),"At risk — close to off track","On track")))))))) | IF(OR(F380="",AC380="Completed / Handover",AC380="Cancelled"),"",IF(O380="Not awarded",IF(U380<>"",U380-TODAY(),IF(X380="","",X380-TODAY())),IF(X380="","",X380-TODAY()))) | [14 empty] | IF(OR(F380="",AJ380=""),"",IF(COUNT(AI380:AI380)=0,"",AJ380-LOOKUP(2,1/(AI380:AI380<>""),AI380:AI380))) | IF(OR(F380="",AK380=""),"",IF(COUNT(AI380:AJ380)=0,"",AK380-LOOKUP(2,1/(AI380:AJ380<>""),AI380:AJ380))) | IF(OR(F380="",AL380=""),"",IF(COUNT(AI380:AK380)=0,"",AL380-LOOKUP(2,1/(AI380:AK380<>""),AI380:AK380))) | IF(OR(F380="",AM380=""),"",IF(COUNT(AI380:AL380)=0,"",AM380-LOOKUP(2,1/(AI380:AL380<>""),AI380:AL380))) | IF(OR(F380="",AN380=""),"",IF(COUNT(AI380:AM380)=0,"",AN380-LOOKUP(2,1/(AI380:AM380<>""),AI380:AM380))) | IF(OR(F380="",AO380=""),"",IF(COUNT(AI380:AN380)=0,"",AO380-LOOKUP(2,1/(AI380:AN380<>""),AI380:AN380))) | IF(OR(F380="",AP380=""),"",IF(COUNT(AI380:AO380)=0,"",AP380-LOOKUP(2,1/(AI380:AO380<>""),AI380:AO380))) | IF(OR(F380="",AQ380=""),"",IF(COUNT(AI380:AP380)=0,"",AQ380-LOOKUP(2,1/(AI380:AP380<>""),AI380:AP380))) | IF(OR(F380="",AR380=""),"",IF(COUNT(AI380:AQ380)=0,"",AR380-LOOKUP(2,1/(AI380:AQ380<>""),AI380:AQ380))) | IF(OR(F380="",AS380=""),"",IF(COUNT(AI380:AR380)=0,"",AS380-LOOKUP(2,1/(AI380:AR380<>""),AI380:AR380))) | IF(OR(F380="",AT380=""),"",IF(COUNT(AI380:AS380)=0,"",AT380-LOOKUP(2,1/(AI380:AS380<>""),AI380:AS380))) | IF(OR(F380="",AU380=""),"",IF(COUNT(AI380:AT380)=0,"",AU380-LOOKUP(2,1/(AI380:AT380<>""),AI380:AT380))) | IF(OR(F380="",AV380=""),"",IF(COUNT(AI380:AU380)=0,"",AV380-LOOKUP(2,1/(AI380:AU380<>""),AI380:AU380))) | IF(J380="","All_Provinces",IFERROR(VLOOKUP(J380,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K380="","All_Districts",IFERROR(VLOOKUP(K380,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F381="","",ROW()-3) | [18 empty] | IF(AQ381="","",AQ381) |  |  |  | IF(W381<>"",W381,IF(OR(T381="",V381=""),"",EDATE(T381,V381))) |  |  |  |  | IF(F381="","",IF(COUNT(AI381:AV381)=0,IF(AA381="","Not started",AA381),SUBSTITUTE(LOOKUP(2,1/(AI381:AV381<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F381="",COUNT(AI381:AV381)=0),"",TODAY()-LOOKUP(2,1/(AI381:AV381<>""),AI381:AV381)) | IF(OR(F381="",COUNT(AI381:AV381)<2),"",LOOKUP(2,1/(AI381:AV381<>""),AI381:AV381)-MIN(AI381:AV381)) | IF(OR(AD381="",AC381="Not started",AC381=""),"",IFERROR(AD381-IF(VLOOKUP(AC381,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC381,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F381="","",IF(OR(AA381="Cancelled",AC381="Cancelled"),"Cancelled",IF(OR(AC381="Completed / Handover",Y381<>"",Z381>=100),"Completed — on track",IF(O381="Not awarded",IF(U381="",IF(X381="","No planned date",IF(TODAY()>X381,"Behind — past planned date",IF(X381-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U381,"Behind — award date passed",IF(U381-TODAY()<=30,"At risk — close to off track","On track"))),IF(X381="","No planned date",IF(AND(TODAY()>X381,OR(Z381="",Z381<100)),"Behind — past end date",IF(AND(T381<>"",X381<>"",Z381<>"",(Z381<100),((TODAY()-T381)/MAX(X381-T381,1)*100)-Z381>15),"Behind — progress lag",IF(AND(X381-TODAY()<=30,X381-TODAY()>=0,OR(Z381="",Z381<90)),"At risk — close to off track","On track")))))))) | IF(OR(F381="",AC381="Completed / Handover",AC381="Cancelled"),"",IF(O381="Not awarded",IF(U381<>"",U381-TODAY(),IF(X381="","",X381-TODAY())),IF(X381="","",X381-TODAY()))) | [14 empty] | IF(OR(F381="",AJ381=""),"",IF(COUNT(AI381:AI381)=0,"",AJ381-LOOKUP(2,1/(AI381:AI381<>""),AI381:AI381))) | IF(OR(F381="",AK381=""),"",IF(COUNT(AI381:AJ381)=0,"",AK381-LOOKUP(2,1/(AI381:AJ381<>""),AI381:AJ381))) | IF(OR(F381="",AL381=""),"",IF(COUNT(AI381:AK381)=0,"",AL381-LOOKUP(2,1/(AI381:AK381<>""),AI381:AK381))) | IF(OR(F381="",AM381=""),"",IF(COUNT(AI381:AL381)=0,"",AM381-LOOKUP(2,1/(AI381:AL381<>""),AI381:AL381))) | IF(OR(F381="",AN381=""),"",IF(COUNT(AI381:AM381)=0,"",AN381-LOOKUP(2,1/(AI381:AM381<>""),AI381:AM381))) | IF(OR(F381="",AO381=""),"",IF(COUNT(AI381:AN381)=0,"",AO381-LOOKUP(2,1/(AI381:AN381<>""),AI381:AN381))) | IF(OR(F381="",AP381=""),"",IF(COUNT(AI381:AO381)=0,"",AP381-LOOKUP(2,1/(AI381:AO381<>""),AI381:AO381))) | IF(OR(F381="",AQ381=""),"",IF(COUNT(AI381:AP381)=0,"",AQ381-LOOKUP(2,1/(AI381:AP381<>""),AI381:AP381))) | IF(OR(F381="",AR381=""),"",IF(COUNT(AI381:AQ381)=0,"",AR381-LOOKUP(2,1/(AI381:AQ381<>""),AI381:AQ381))) | IF(OR(F381="",AS381=""),"",IF(COUNT(AI381:AR381)=0,"",AS381-LOOKUP(2,1/(AI381:AR381<>""),AI381:AR381))) | IF(OR(F381="",AT381=""),"",IF(COUNT(AI381:AS381)=0,"",AT381-LOOKUP(2,1/(AI381:AS381<>""),AI381:AS381))) | IF(OR(F381="",AU381=""),"",IF(COUNT(AI381:AT381)=0,"",AU381-LOOKUP(2,1/(AI381:AT381<>""),AI381:AT381))) | IF(OR(F381="",AV381=""),"",IF(COUNT(AI381:AU381)=0,"",AV381-LOOKUP(2,1/(AI381:AU381<>""),AI381:AU381))) | IF(J381="","All_Provinces",IFERROR(VLOOKUP(J381,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K381="","All_Districts",IFERROR(VLOOKUP(K381,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F382="","",ROW()-3) | [18 empty] | IF(AQ382="","",AQ382) |  |  |  | IF(W382<>"",W382,IF(OR(T382="",V382=""),"",EDATE(T382,V382))) |  |  |  |  | IF(F382="","",IF(COUNT(AI382:AV382)=0,IF(AA382="","Not started",AA382),SUBSTITUTE(LOOKUP(2,1/(AI382:AV382<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F382="",COUNT(AI382:AV382)=0),"",TODAY()-LOOKUP(2,1/(AI382:AV382<>""),AI382:AV382)) | IF(OR(F382="",COUNT(AI382:AV382)<2),"",LOOKUP(2,1/(AI382:AV382<>""),AI382:AV382)-MIN(AI382:AV382)) | IF(OR(AD382="",AC382="Not started",AC382=""),"",IFERROR(AD382-IF(VLOOKUP(AC382,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC382,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F382="","",IF(OR(AA382="Cancelled",AC382="Cancelled"),"Cancelled",IF(OR(AC382="Completed / Handover",Y382<>"",Z382>=100),"Completed — on track",IF(O382="Not awarded",IF(U382="",IF(X382="","No planned date",IF(TODAY()>X382,"Behind — past planned date",IF(X382-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U382,"Behind — award date passed",IF(U382-TODAY()<=30,"At risk — close to off track","On track"))),IF(X382="","No planned date",IF(AND(TODAY()>X382,OR(Z382="",Z382<100)),"Behind — past end date",IF(AND(T382<>"",X382<>"",Z382<>"",(Z382<100),((TODAY()-T382)/MAX(X382-T382,1)*100)-Z382>15),"Behind — progress lag",IF(AND(X382-TODAY()<=30,X382-TODAY()>=0,OR(Z382="",Z382<90)),"At risk — close to off track","On track")))))))) | IF(OR(F382="",AC382="Completed / Handover",AC382="Cancelled"),"",IF(O382="Not awarded",IF(U382<>"",U382-TODAY(),IF(X382="","",X382-TODAY())),IF(X382="","",X382-TODAY()))) | [14 empty] | IF(OR(F382="",AJ382=""),"",IF(COUNT(AI382:AI382)=0,"",AJ382-LOOKUP(2,1/(AI382:AI382<>""),AI382:AI382))) | IF(OR(F382="",AK382=""),"",IF(COUNT(AI382:AJ382)=0,"",AK382-LOOKUP(2,1/(AI382:AJ382<>""),AI382:AJ382))) | IF(OR(F382="",AL382=""),"",IF(COUNT(AI382:AK382)=0,"",AL382-LOOKUP(2,1/(AI382:AK382<>""),AI382:AK382))) | IF(OR(F382="",AM382=""),"",IF(COUNT(AI382:AL382)=0,"",AM382-LOOKUP(2,1/(AI382:AL382<>""),AI382:AL382))) | IF(OR(F382="",AN382=""),"",IF(COUNT(AI382:AM382)=0,"",AN382-LOOKUP(2,1/(AI382:AM382<>""),AI382:AM382))) | IF(OR(F382="",AO382=""),"",IF(COUNT(AI382:AN382)=0,"",AO382-LOOKUP(2,1/(AI382:AN382<>""),AI382:AN382))) | IF(OR(F382="",AP382=""),"",IF(COUNT(AI382:AO382)=0,"",AP382-LOOKUP(2,1/(AI382:AO382<>""),AI382:AO382))) | IF(OR(F382="",AQ382=""),"",IF(COUNT(AI382:AP382)=0,"",AQ382-LOOKUP(2,1/(AI382:AP382<>""),AI382:AP382))) | IF(OR(F382="",AR382=""),"",IF(COUNT(AI382:AQ382)=0,"",AR382-LOOKUP(2,1/(AI382:AQ382<>""),AI382:AQ382))) | IF(OR(F382="",AS382=""),"",IF(COUNT(AI382:AR382)=0,"",AS382-LOOKUP(2,1/(AI382:AR382<>""),AI382:AR382))) | IF(OR(F382="",AT382=""),"",IF(COUNT(AI382:AS382)=0,"",AT382-LOOKUP(2,1/(AI382:AS382<>""),AI382:AS382))) | IF(OR(F382="",AU382=""),"",IF(COUNT(AI382:AT382)=0,"",AU382-LOOKUP(2,1/(AI382:AT382<>""),AI382:AT382))) | IF(OR(F382="",AV382=""),"",IF(COUNT(AI382:AU382)=0,"",AV382-LOOKUP(2,1/(AI382:AU382<>""),AI382:AU382))) | IF(J382="","All_Provinces",IFERROR(VLOOKUP(J382,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K382="","All_Districts",IFERROR(VLOOKUP(K382,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F383="","",ROW()-3) | [18 empty] | IF(AQ383="","",AQ383) |  |  |  | IF(W383<>"",W383,IF(OR(T383="",V383=""),"",EDATE(T383,V383))) |  |  |  |  | IF(F383="","",IF(COUNT(AI383:AV383)=0,IF(AA383="","Not started",AA383),SUBSTITUTE(LOOKUP(2,1/(AI383:AV383<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F383="",COUNT(AI383:AV383)=0),"",TODAY()-LOOKUP(2,1/(AI383:AV383<>""),AI383:AV383)) | IF(OR(F383="",COUNT(AI383:AV383)<2),"",LOOKUP(2,1/(AI383:AV383<>""),AI383:AV383)-MIN(AI383:AV383)) | IF(OR(AD383="",AC383="Not started",AC383=""),"",IFERROR(AD383-IF(VLOOKUP(AC383,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC383,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F383="","",IF(OR(AA383="Cancelled",AC383="Cancelled"),"Cancelled",IF(OR(AC383="Completed / Handover",Y383<>"",Z383>=100),"Completed — on track",IF(O383="Not awarded",IF(U383="",IF(X383="","No planned date",IF(TODAY()>X383,"Behind — past planned date",IF(X383-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U383,"Behind — award date passed",IF(U383-TODAY()<=30,"At risk — close to off track","On track"))),IF(X383="","No planned date",IF(AND(TODAY()>X383,OR(Z383="",Z383<100)),"Behind — past end date",IF(AND(T383<>"",X383<>"",Z383<>"",(Z383<100),((TODAY()-T383)/MAX(X383-T383,1)*100)-Z383>15),"Behind — progress lag",IF(AND(X383-TODAY()<=30,X383-TODAY()>=0,OR(Z383="",Z383<90)),"At risk — close to off track","On track")))))))) | IF(OR(F383="",AC383="Completed / Handover",AC383="Cancelled"),"",IF(O383="Not awarded",IF(U383<>"",U383-TODAY(),IF(X383="","",X383-TODAY())),IF(X383="","",X383-TODAY()))) | [14 empty] | IF(OR(F383="",AJ383=""),"",IF(COUNT(AI383:AI383)=0,"",AJ383-LOOKUP(2,1/(AI383:AI383<>""),AI383:AI383))) | IF(OR(F383="",AK383=""),"",IF(COUNT(AI383:AJ383)=0,"",AK383-LOOKUP(2,1/(AI383:AJ383<>""),AI383:AJ383))) | IF(OR(F383="",AL383=""),"",IF(COUNT(AI383:AK383)=0,"",AL383-LOOKUP(2,1/(AI383:AK383<>""),AI383:AK383))) | IF(OR(F383="",AM383=""),"",IF(COUNT(AI383:AL383)=0,"",AM383-LOOKUP(2,1/(AI383:AL383<>""),AI383:AL383))) | IF(OR(F383="",AN383=""),"",IF(COUNT(AI383:AM383)=0,"",AN383-LOOKUP(2,1/(AI383:AM383<>""),AI383:AM383))) | IF(OR(F383="",AO383=""),"",IF(COUNT(AI383:AN383)=0,"",AO383-LOOKUP(2,1/(AI383:AN383<>""),AI383:AN383))) | IF(OR(F383="",AP383=""),"",IF(COUNT(AI383:AO383)=0,"",AP383-LOOKUP(2,1/(AI383:AO383<>""),AI383:AO383))) | IF(OR(F383="",AQ383=""),"",IF(COUNT(AI383:AP383)=0,"",AQ383-LOOKUP(2,1/(AI383:AP383<>""),AI383:AP383))) | IF(OR(F383="",AR383=""),"",IF(COUNT(AI383:AQ383)=0,"",AR383-LOOKUP(2,1/(AI383:AQ383<>""),AI383:AQ383))) | IF(OR(F383="",AS383=""),"",IF(COUNT(AI383:AR383)=0,"",AS383-LOOKUP(2,1/(AI383:AR383<>""),AI383:AR383))) | IF(OR(F383="",AT383=""),"",IF(COUNT(AI383:AS383)=0,"",AT383-LOOKUP(2,1/(AI383:AS383<>""),AI383:AS383))) | IF(OR(F383="",AU383=""),"",IF(COUNT(AI383:AT383)=0,"",AU383-LOOKUP(2,1/(AI383:AT383<>""),AI383:AT383))) | IF(OR(F383="",AV383=""),"",IF(COUNT(AI383:AU383)=0,"",AV383-LOOKUP(2,1/(AI383:AU383<>""),AI383:AU383))) | IF(J383="","All_Provinces",IFERROR(VLOOKUP(J383,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K383="","All_Districts",IFERROR(VLOOKUP(K383,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F384="","",ROW()-3) | [18 empty] | IF(AQ384="","",AQ384) |  |  |  | IF(W384<>"",W384,IF(OR(T384="",V384=""),"",EDATE(T384,V384))) |  |  |  |  | IF(F384="","",IF(COUNT(AI384:AV384)=0,IF(AA384="","Not started",AA384),SUBSTITUTE(LOOKUP(2,1/(AI384:AV384<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F384="",COUNT(AI384:AV384)=0),"",TODAY()-LOOKUP(2,1/(AI384:AV384<>""),AI384:AV384)) | IF(OR(F384="",COUNT(AI384:AV384)<2),"",LOOKUP(2,1/(AI384:AV384<>""),AI384:AV384)-MIN(AI384:AV384)) | IF(OR(AD384="",AC384="Not started",AC384=""),"",IFERROR(AD384-IF(VLOOKUP(AC384,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC384,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F384="","",IF(OR(AA384="Cancelled",AC384="Cancelled"),"Cancelled",IF(OR(AC384="Completed / Handover",Y384<>"",Z384>=100),"Completed — on track",IF(O384="Not awarded",IF(U384="",IF(X384="","No planned date",IF(TODAY()>X384,"Behind — past planned date",IF(X384-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U384,"Behind — award date passed",IF(U384-TODAY()<=30,"At risk — close to off track","On track"))),IF(X384="","No planned date",IF(AND(TODAY()>X384,OR(Z384="",Z384<100)),"Behind — past end date",IF(AND(T384<>"",X384<>"",Z384<>"",(Z384<100),((TODAY()-T384)/MAX(X384-T384,1)*100)-Z384>15),"Behind — progress lag",IF(AND(X384-TODAY()<=30,X384-TODAY()>=0,OR(Z384="",Z384<90)),"At risk — close to off track","On track")))))))) | IF(OR(F384="",AC384="Completed / Handover",AC384="Cancelled"),"",IF(O384="Not awarded",IF(U384<>"",U384-TODAY(),IF(X384="","",X384-TODAY())),IF(X384="","",X384-TODAY()))) | [14 empty] | IF(OR(F384="",AJ384=""),"",IF(COUNT(AI384:AI384)=0,"",AJ384-LOOKUP(2,1/(AI384:AI384<>""),AI384:AI384))) | IF(OR(F384="",AK384=""),"",IF(COUNT(AI384:AJ384)=0,"",AK384-LOOKUP(2,1/(AI384:AJ384<>""),AI384:AJ384))) | IF(OR(F384="",AL384=""),"",IF(COUNT(AI384:AK384)=0,"",AL384-LOOKUP(2,1/(AI384:AK384<>""),AI384:AK384))) | IF(OR(F384="",AM384=""),"",IF(COUNT(AI384:AL384)=0,"",AM384-LOOKUP(2,1/(AI384:AL384<>""),AI384:AL384))) | IF(OR(F384="",AN384=""),"",IF(COUNT(AI384:AM384)=0,"",AN384-LOOKUP(2,1/(AI384:AM384<>""),AI384:AM384))) | IF(OR(F384="",AO384=""),"",IF(COUNT(AI384:AN384)=0,"",AO384-LOOKUP(2,1/(AI384:AN384<>""),AI384:AN384))) | IF(OR(F384="",AP384=""),"",IF(COUNT(AI384:AO384)=0,"",AP384-LOOKUP(2,1/(AI384:AO384<>""),AI384:AO384))) | IF(OR(F384="",AQ384=""),"",IF(COUNT(AI384:AP384)=0,"",AQ384-LOOKUP(2,1/(AI384:AP384<>""),AI384:AP384))) | IF(OR(F384="",AR384=""),"",IF(COUNT(AI384:AQ384)=0,"",AR384-LOOKUP(2,1/(AI384:AQ384<>""),AI384:AQ384))) | IF(OR(F384="",AS384=""),"",IF(COUNT(AI384:AR384)=0,"",AS384-LOOKUP(2,1/(AI384:AR384<>""),AI384:AR384))) | IF(OR(F384="",AT384=""),"",IF(COUNT(AI384:AS384)=0,"",AT384-LOOKUP(2,1/(AI384:AS384<>""),AI384:AS384))) | IF(OR(F384="",AU384=""),"",IF(COUNT(AI384:AT384)=0,"",AU384-LOOKUP(2,1/(AI384:AT384<>""),AI384:AT384))) | IF(OR(F384="",AV384=""),"",IF(COUNT(AI384:AU384)=0,"",AV384-LOOKUP(2,1/(AI384:AU384<>""),AI384:AU384))) | IF(J384="","All_Provinces",IFERROR(VLOOKUP(J384,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K384="","All_Districts",IFERROR(VLOOKUP(K384,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F385="","",ROW()-3) | [18 empty] | IF(AQ385="","",AQ385) |  |  |  | IF(W385<>"",W385,IF(OR(T385="",V385=""),"",EDATE(T385,V385))) |  |  |  |  | IF(F385="","",IF(COUNT(AI385:AV385)=0,IF(AA385="","Not started",AA385),SUBSTITUTE(LOOKUP(2,1/(AI385:AV385<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F385="",COUNT(AI385:AV385)=0),"",TODAY()-LOOKUP(2,1/(AI385:AV385<>""),AI385:AV385)) | IF(OR(F385="",COUNT(AI385:AV385)<2),"",LOOKUP(2,1/(AI385:AV385<>""),AI385:AV385)-MIN(AI385:AV385)) | IF(OR(AD385="",AC385="Not started",AC385=""),"",IFERROR(AD385-IF(VLOOKUP(AC385,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC385,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F385="","",IF(OR(AA385="Cancelled",AC385="Cancelled"),"Cancelled",IF(OR(AC385="Completed / Handover",Y385<>"",Z385>=100),"Completed — on track",IF(O385="Not awarded",IF(U385="",IF(X385="","No planned date",IF(TODAY()>X385,"Behind — past planned date",IF(X385-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U385,"Behind — award date passed",IF(U385-TODAY()<=30,"At risk — close to off track","On track"))),IF(X385="","No planned date",IF(AND(TODAY()>X385,OR(Z385="",Z385<100)),"Behind — past end date",IF(AND(T385<>"",X385<>"",Z385<>"",(Z385<100),((TODAY()-T385)/MAX(X385-T385,1)*100)-Z385>15),"Behind — progress lag",IF(AND(X385-TODAY()<=30,X385-TODAY()>=0,OR(Z385="",Z385<90)),"At risk — close to off track","On track")))))))) | IF(OR(F385="",AC385="Completed / Handover",AC385="Cancelled"),"",IF(O385="Not awarded",IF(U385<>"",U385-TODAY(),IF(X385="","",X385-TODAY())),IF(X385="","",X385-TODAY()))) | [14 empty] | IF(OR(F385="",AJ385=""),"",IF(COUNT(AI385:AI385)=0,"",AJ385-LOOKUP(2,1/(AI385:AI385<>""),AI385:AI385))) | IF(OR(F385="",AK385=""),"",IF(COUNT(AI385:AJ385)=0,"",AK385-LOOKUP(2,1/(AI385:AJ385<>""),AI385:AJ385))) | IF(OR(F385="",AL385=""),"",IF(COUNT(AI385:AK385)=0,"",AL385-LOOKUP(2,1/(AI385:AK385<>""),AI385:AK385))) | IF(OR(F385="",AM385=""),"",IF(COUNT(AI385:AL385)=0,"",AM385-LOOKUP(2,1/(AI385:AL385<>""),AI385:AL385))) | IF(OR(F385="",AN385=""),"",IF(COUNT(AI385:AM385)=0,"",AN385-LOOKUP(2,1/(AI385:AM385<>""),AI385:AM385))) | IF(OR(F385="",AO385=""),"",IF(COUNT(AI385:AN385)=0,"",AO385-LOOKUP(2,1/(AI385:AN385<>""),AI385:AN385))) | IF(OR(F385="",AP385=""),"",IF(COUNT(AI385:AO385)=0,"",AP385-LOOKUP(2,1/(AI385:AO385<>""),AI385:AO385))) | IF(OR(F385="",AQ385=""),"",IF(COUNT(AI385:AP385)=0,"",AQ385-LOOKUP(2,1/(AI385:AP385<>""),AI385:AP385))) | IF(OR(F385="",AR385=""),"",IF(COUNT(AI385:AQ385)=0,"",AR385-LOOKUP(2,1/(AI385:AQ385<>""),AI385:AQ385))) | IF(OR(F385="",AS385=""),"",IF(COUNT(AI385:AR385)=0,"",AS385-LOOKUP(2,1/(AI385:AR385<>""),AI385:AR385))) | IF(OR(F385="",AT385=""),"",IF(COUNT(AI385:AS385)=0,"",AT385-LOOKUP(2,1/(AI385:AS385<>""),AI385:AS385))) | IF(OR(F385="",AU385=""),"",IF(COUNT(AI385:AT385)=0,"",AU385-LOOKUP(2,1/(AI385:AT385<>""),AI385:AT385))) | IF(OR(F385="",AV385=""),"",IF(COUNT(AI385:AU385)=0,"",AV385-LOOKUP(2,1/(AI385:AU385<>""),AI385:AU385))) | IF(J385="","All_Provinces",IFERROR(VLOOKUP(J385,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K385="","All_Districts",IFERROR(VLOOKUP(K385,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F386="","",ROW()-3) | [18 empty] | IF(AQ386="","",AQ386) |  |  |  | IF(W386<>"",W386,IF(OR(T386="",V386=""),"",EDATE(T386,V386))) |  |  |  |  | IF(F386="","",IF(COUNT(AI386:AV386)=0,IF(AA386="","Not started",AA386),SUBSTITUTE(LOOKUP(2,1/(AI386:AV386<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F386="",COUNT(AI386:AV386)=0),"",TODAY()-LOOKUP(2,1/(AI386:AV386<>""),AI386:AV386)) | IF(OR(F386="",COUNT(AI386:AV386)<2),"",LOOKUP(2,1/(AI386:AV386<>""),AI386:AV386)-MIN(AI386:AV386)) | IF(OR(AD386="",AC386="Not started",AC386=""),"",IFERROR(AD386-IF(VLOOKUP(AC386,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC386,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F386="","",IF(OR(AA386="Cancelled",AC386="Cancelled"),"Cancelled",IF(OR(AC386="Completed / Handover",Y386<>"",Z386>=100),"Completed — on track",IF(O386="Not awarded",IF(U386="",IF(X386="","No planned date",IF(TODAY()>X386,"Behind — past planned date",IF(X386-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U386,"Behind — award date passed",IF(U386-TODAY()<=30,"At risk — close to off track","On track"))),IF(X386="","No planned date",IF(AND(TODAY()>X386,OR(Z386="",Z386<100)),"Behind — past end date",IF(AND(T386<>"",X386<>"",Z386<>"",(Z386<100),((TODAY()-T386)/MAX(X386-T386,1)*100)-Z386>15),"Behind — progress lag",IF(AND(X386-TODAY()<=30,X386-TODAY()>=0,OR(Z386="",Z386<90)),"At risk — close to off track","On track")))))))) | IF(OR(F386="",AC386="Completed / Handover",AC386="Cancelled"),"",IF(O386="Not awarded",IF(U386<>"",U386-TODAY(),IF(X386="","",X386-TODAY())),IF(X386="","",X386-TODAY()))) | [14 empty] | IF(OR(F386="",AJ386=""),"",IF(COUNT(AI386:AI386)=0,"",AJ386-LOOKUP(2,1/(AI386:AI386<>""),AI386:AI386))) | IF(OR(F386="",AK386=""),"",IF(COUNT(AI386:AJ386)=0,"",AK386-LOOKUP(2,1/(AI386:AJ386<>""),AI386:AJ386))) | IF(OR(F386="",AL386=""),"",IF(COUNT(AI386:AK386)=0,"",AL386-LOOKUP(2,1/(AI386:AK386<>""),AI386:AK386))) | IF(OR(F386="",AM386=""),"",IF(COUNT(AI386:AL386)=0,"",AM386-LOOKUP(2,1/(AI386:AL386<>""),AI386:AL386))) | IF(OR(F386="",AN386=""),"",IF(COUNT(AI386:AM386)=0,"",AN386-LOOKUP(2,1/(AI386:AM386<>""),AI386:AM386))) | IF(OR(F386="",AO386=""),"",IF(COUNT(AI386:AN386)=0,"",AO386-LOOKUP(2,1/(AI386:AN386<>""),AI386:AN386))) | IF(OR(F386="",AP386=""),"",IF(COUNT(AI386:AO386)=0,"",AP386-LOOKUP(2,1/(AI386:AO386<>""),AI386:AO386))) | IF(OR(F386="",AQ386=""),"",IF(COUNT(AI386:AP386)=0,"",AQ386-LOOKUP(2,1/(AI386:AP386<>""),AI386:AP386))) | IF(OR(F386="",AR386=""),"",IF(COUNT(AI386:AQ386)=0,"",AR386-LOOKUP(2,1/(AI386:AQ386<>""),AI386:AQ386))) | IF(OR(F386="",AS386=""),"",IF(COUNT(AI386:AR386)=0,"",AS386-LOOKUP(2,1/(AI386:AR386<>""),AI386:AR386))) | IF(OR(F386="",AT386=""),"",IF(COUNT(AI386:AS386)=0,"",AT386-LOOKUP(2,1/(AI386:AS386<>""),AI386:AS386))) | IF(OR(F386="",AU386=""),"",IF(COUNT(AI386:AT386)=0,"",AU386-LOOKUP(2,1/(AI386:AT386<>""),AI386:AT386))) | IF(OR(F386="",AV386=""),"",IF(COUNT(AI386:AU386)=0,"",AV386-LOOKUP(2,1/(AI386:AU386<>""),AI386:AU386))) | IF(J386="","All_Provinces",IFERROR(VLOOKUP(J386,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K386="","All_Districts",IFERROR(VLOOKUP(K386,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F387="","",ROW()-3) | [18 empty] | IF(AQ387="","",AQ387) |  |  |  | IF(W387<>"",W387,IF(OR(T387="",V387=""),"",EDATE(T387,V387))) |  |  |  |  | IF(F387="","",IF(COUNT(AI387:AV387)=0,IF(AA387="","Not started",AA387),SUBSTITUTE(LOOKUP(2,1/(AI387:AV387<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F387="",COUNT(AI387:AV387)=0),"",TODAY()-LOOKUP(2,1/(AI387:AV387<>""),AI387:AV387)) | IF(OR(F387="",COUNT(AI387:AV387)<2),"",LOOKUP(2,1/(AI387:AV387<>""),AI387:AV387)-MIN(AI387:AV387)) | IF(OR(AD387="",AC387="Not started",AC387=""),"",IFERROR(AD387-IF(VLOOKUP(AC387,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC387,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F387="","",IF(OR(AA387="Cancelled",AC387="Cancelled"),"Cancelled",IF(OR(AC387="Completed / Handover",Y387<>"",Z387>=100),"Completed — on track",IF(O387="Not awarded",IF(U387="",IF(X387="","No planned date",IF(TODAY()>X387,"Behind — past planned date",IF(X387-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U387,"Behind — award date passed",IF(U387-TODAY()<=30,"At risk — close to off track","On track"))),IF(X387="","No planned date",IF(AND(TODAY()>X387,OR(Z387="",Z387<100)),"Behind — past end date",IF(AND(T387<>"",X387<>"",Z387<>"",(Z387<100),((TODAY()-T387)/MAX(X387-T387,1)*100)-Z387>15),"Behind — progress lag",IF(AND(X387-TODAY()<=30,X387-TODAY()>=0,OR(Z387="",Z387<90)),"At risk — close to off track","On track")))))))) | IF(OR(F387="",AC387="Completed / Handover",AC387="Cancelled"),"",IF(O387="Not awarded",IF(U387<>"",U387-TODAY(),IF(X387="","",X387-TODAY())),IF(X387="","",X387-TODAY()))) | [14 empty] | IF(OR(F387="",AJ387=""),"",IF(COUNT(AI387:AI387)=0,"",AJ387-LOOKUP(2,1/(AI387:AI387<>""),AI387:AI387))) | IF(OR(F387="",AK387=""),"",IF(COUNT(AI387:AJ387)=0,"",AK387-LOOKUP(2,1/(AI387:AJ387<>""),AI387:AJ387))) | IF(OR(F387="",AL387=""),"",IF(COUNT(AI387:AK387)=0,"",AL387-LOOKUP(2,1/(AI387:AK387<>""),AI387:AK387))) | IF(OR(F387="",AM387=""),"",IF(COUNT(AI387:AL387)=0,"",AM387-LOOKUP(2,1/(AI387:AL387<>""),AI387:AL387))) | IF(OR(F387="",AN387=""),"",IF(COUNT(AI387:AM387)=0,"",AN387-LOOKUP(2,1/(AI387:AM387<>""),AI387:AM387))) | IF(OR(F387="",AO387=""),"",IF(COUNT(AI387:AN387)=0,"",AO387-LOOKUP(2,1/(AI387:AN387<>""),AI387:AN387))) | IF(OR(F387="",AP387=""),"",IF(COUNT(AI387:AO387)=0,"",AP387-LOOKUP(2,1/(AI387:AO387<>""),AI387:AO387))) | IF(OR(F387="",AQ387=""),"",IF(COUNT(AI387:AP387)=0,"",AQ387-LOOKUP(2,1/(AI387:AP387<>""),AI387:AP387))) | IF(OR(F387="",AR387=""),"",IF(COUNT(AI387:AQ387)=0,"",AR387-LOOKUP(2,1/(AI387:AQ387<>""),AI387:AQ387))) | IF(OR(F387="",AS387=""),"",IF(COUNT(AI387:AR387)=0,"",AS387-LOOKUP(2,1/(AI387:AR387<>""),AI387:AR387))) | IF(OR(F387="",AT387=""),"",IF(COUNT(AI387:AS387)=0,"",AT387-LOOKUP(2,1/(AI387:AS387<>""),AI387:AS387))) | IF(OR(F387="",AU387=""),"",IF(COUNT(AI387:AT387)=0,"",AU387-LOOKUP(2,1/(AI387:AT387<>""),AI387:AT387))) | IF(OR(F387="",AV387=""),"",IF(COUNT(AI387:AU387)=0,"",AV387-LOOKUP(2,1/(AI387:AU387<>""),AI387:AU387))) | IF(J387="","All_Provinces",IFERROR(VLOOKUP(J387,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K387="","All_Districts",IFERROR(VLOOKUP(K387,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F388="","",ROW()-3) | [18 empty] | IF(AQ388="","",AQ388) |  |  |  | IF(W388<>"",W388,IF(OR(T388="",V388=""),"",EDATE(T388,V388))) |  |  |  |  | IF(F388="","",IF(COUNT(AI388:AV388)=0,IF(AA388="","Not started",AA388),SUBSTITUTE(LOOKUP(2,1/(AI388:AV388<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F388="",COUNT(AI388:AV388)=0),"",TODAY()-LOOKUP(2,1/(AI388:AV388<>""),AI388:AV388)) | IF(OR(F388="",COUNT(AI388:AV388)<2),"",LOOKUP(2,1/(AI388:AV388<>""),AI388:AV388)-MIN(AI388:AV388)) | IF(OR(AD388="",AC388="Not started",AC388=""),"",IFERROR(AD388-IF(VLOOKUP(AC388,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC388,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F388="","",IF(OR(AA388="Cancelled",AC388="Cancelled"),"Cancelled",IF(OR(AC388="Completed / Handover",Y388<>"",Z388>=100),"Completed — on track",IF(O388="Not awarded",IF(U388="",IF(X388="","No planned date",IF(TODAY()>X388,"Behind — past planned date",IF(X388-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U388,"Behind — award date passed",IF(U388-TODAY()<=30,"At risk — close to off track","On track"))),IF(X388="","No planned date",IF(AND(TODAY()>X388,OR(Z388="",Z388<100)),"Behind — past end date",IF(AND(T388<>"",X388<>"",Z388<>"",(Z388<100),((TODAY()-T388)/MAX(X388-T388,1)*100)-Z388>15),"Behind — progress lag",IF(AND(X388-TODAY()<=30,X388-TODAY()>=0,OR(Z388="",Z388<90)),"At risk — close to off track","On track")))))))) | IF(OR(F388="",AC388="Completed / Handover",AC388="Cancelled"),"",IF(O388="Not awarded",IF(U388<>"",U388-TODAY(),IF(X388="","",X388-TODAY())),IF(X388="","",X388-TODAY()))) | [14 empty] | IF(OR(F388="",AJ388=""),"",IF(COUNT(AI388:AI388)=0,"",AJ388-LOOKUP(2,1/(AI388:AI388<>""),AI388:AI388))) | IF(OR(F388="",AK388=""),"",IF(COUNT(AI388:AJ388)=0,"",AK388-LOOKUP(2,1/(AI388:AJ388<>""),AI388:AJ388))) | IF(OR(F388="",AL388=""),"",IF(COUNT(AI388:AK388)=0,"",AL388-LOOKUP(2,1/(AI388:AK388<>""),AI388:AK388))) | IF(OR(F388="",AM388=""),"",IF(COUNT(AI388:AL388)=0,"",AM388-LOOKUP(2,1/(AI388:AL388<>""),AI388:AL388))) | IF(OR(F388="",AN388=""),"",IF(COUNT(AI388:AM388)=0,"",AN388-LOOKUP(2,1/(AI388:AM388<>""),AI388:AM388))) | IF(OR(F388="",AO388=""),"",IF(COUNT(AI388:AN388)=0,"",AO388-LOOKUP(2,1/(AI388:AN388<>""),AI388:AN388))) | IF(OR(F388="",AP388=""),"",IF(COUNT(AI388:AO388)=0,"",AP388-LOOKUP(2,1/(AI388:AO388<>""),AI388:AO388))) | IF(OR(F388="",AQ388=""),"",IF(COUNT(AI388:AP388)=0,"",AQ388-LOOKUP(2,1/(AI388:AP388<>""),AI388:AP388))) | IF(OR(F388="",AR388=""),"",IF(COUNT(AI388:AQ388)=0,"",AR388-LOOKUP(2,1/(AI388:AQ388<>""),AI388:AQ388))) | IF(OR(F388="",AS388=""),"",IF(COUNT(AI388:AR388)=0,"",AS388-LOOKUP(2,1/(AI388:AR388<>""),AI388:AR388))) | IF(OR(F388="",AT388=""),"",IF(COUNT(AI388:AS388)=0,"",AT388-LOOKUP(2,1/(AI388:AS388<>""),AI388:AS388))) | IF(OR(F388="",AU388=""),"",IF(COUNT(AI388:AT388)=0,"",AU388-LOOKUP(2,1/(AI388:AT388<>""),AI388:AT388))) | IF(OR(F388="",AV388=""),"",IF(COUNT(AI388:AU388)=0,"",AV388-LOOKUP(2,1/(AI388:AU388<>""),AI388:AU388))) | IF(J388="","All_Provinces",IFERROR(VLOOKUP(J388,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K388="","All_Districts",IFERROR(VLOOKUP(K388,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F389="","",ROW()-3) | [18 empty] | IF(AQ389="","",AQ389) |  |  |  | IF(W389<>"",W389,IF(OR(T389="",V389=""),"",EDATE(T389,V389))) |  |  |  |  | IF(F389="","",IF(COUNT(AI389:AV389)=0,IF(AA389="","Not started",AA389),SUBSTITUTE(LOOKUP(2,1/(AI389:AV389<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F389="",COUNT(AI389:AV389)=0),"",TODAY()-LOOKUP(2,1/(AI389:AV389<>""),AI389:AV389)) | IF(OR(F389="",COUNT(AI389:AV389)<2),"",LOOKUP(2,1/(AI389:AV389<>""),AI389:AV389)-MIN(AI389:AV389)) | IF(OR(AD389="",AC389="Not started",AC389=""),"",IFERROR(AD389-IF(VLOOKUP(AC389,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC389,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F389="","",IF(OR(AA389="Cancelled",AC389="Cancelled"),"Cancelled",IF(OR(AC389="Completed / Handover",Y389<>"",Z389>=100),"Completed — on track",IF(O389="Not awarded",IF(U389="",IF(X389="","No planned date",IF(TODAY()>X389,"Behind — past planned date",IF(X389-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U389,"Behind — award date passed",IF(U389-TODAY()<=30,"At risk — close to off track","On track"))),IF(X389="","No planned date",IF(AND(TODAY()>X389,OR(Z389="",Z389<100)),"Behind — past end date",IF(AND(T389<>"",X389<>"",Z389<>"",(Z389<100),((TODAY()-T389)/MAX(X389-T389,1)*100)-Z389>15),"Behind — progress lag",IF(AND(X389-TODAY()<=30,X389-TODAY()>=0,OR(Z389="",Z389<90)),"At risk — close to off track","On track")))))))) | IF(OR(F389="",AC389="Completed / Handover",AC389="Cancelled"),"",IF(O389="Not awarded",IF(U389<>"",U389-TODAY(),IF(X389="","",X389-TODAY())),IF(X389="","",X389-TODAY()))) | [14 empty] | IF(OR(F389="",AJ389=""),"",IF(COUNT(AI389:AI389)=0,"",AJ389-LOOKUP(2,1/(AI389:AI389<>""),AI389:AI389))) | IF(OR(F389="",AK389=""),"",IF(COUNT(AI389:AJ389)=0,"",AK389-LOOKUP(2,1/(AI389:AJ389<>""),AI389:AJ389))) | IF(OR(F389="",AL389=""),"",IF(COUNT(AI389:AK389)=0,"",AL389-LOOKUP(2,1/(AI389:AK389<>""),AI389:AK389))) | IF(OR(F389="",AM389=""),"",IF(COUNT(AI389:AL389)=0,"",AM389-LOOKUP(2,1/(AI389:AL389<>""),AI389:AL389))) | IF(OR(F389="",AN389=""),"",IF(COUNT(AI389:AM389)=0,"",AN389-LOOKUP(2,1/(AI389:AM389<>""),AI389:AM389))) | IF(OR(F389="",AO389=""),"",IF(COUNT(AI389:AN389)=0,"",AO389-LOOKUP(2,1/(AI389:AN389<>""),AI389:AN389))) | IF(OR(F389="",AP389=""),"",IF(COUNT(AI389:AO389)=0,"",AP389-LOOKUP(2,1/(AI389:AO389<>""),AI389:AO389))) | IF(OR(F389="",AQ389=""),"",IF(COUNT(AI389:AP389)=0,"",AQ389-LOOKUP(2,1/(AI389:AP389<>""),AI389:AP389))) | IF(OR(F389="",AR389=""),"",IF(COUNT(AI389:AQ389)=0,"",AR389-LOOKUP(2,1/(AI389:AQ389<>""),AI389:AQ389))) | IF(OR(F389="",AS389=""),"",IF(COUNT(AI389:AR389)=0,"",AS389-LOOKUP(2,1/(AI389:AR389<>""),AI389:AR389))) | IF(OR(F389="",AT389=""),"",IF(COUNT(AI389:AS389)=0,"",AT389-LOOKUP(2,1/(AI389:AS389<>""),AI389:AS389))) | IF(OR(F389="",AU389=""),"",IF(COUNT(AI389:AT389)=0,"",AU389-LOOKUP(2,1/(AI389:AT389<>""),AI389:AT389))) | IF(OR(F389="",AV389=""),"",IF(COUNT(AI389:AU389)=0,"",AV389-LOOKUP(2,1/(AI389:AU389<>""),AI389:AU389))) | IF(J389="","All_Provinces",IFERROR(VLOOKUP(J389,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K389="","All_Districts",IFERROR(VLOOKUP(K389,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F390="","",ROW()-3) | [18 empty] | IF(AQ390="","",AQ390) |  |  |  | IF(W390<>"",W390,IF(OR(T390="",V390=""),"",EDATE(T390,V390))) |  |  |  |  | IF(F390="","",IF(COUNT(AI390:AV390)=0,IF(AA390="","Not started",AA390),SUBSTITUTE(LOOKUP(2,1/(AI390:AV390<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F390="",COUNT(AI390:AV390)=0),"",TODAY()-LOOKUP(2,1/(AI390:AV390<>""),AI390:AV390)) | IF(OR(F390="",COUNT(AI390:AV390)<2),"",LOOKUP(2,1/(AI390:AV390<>""),AI390:AV390)-MIN(AI390:AV390)) | IF(OR(AD390="",AC390="Not started",AC390=""),"",IFERROR(AD390-IF(VLOOKUP(AC390,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC390,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F390="","",IF(OR(AA390="Cancelled",AC390="Cancelled"),"Cancelled",IF(OR(AC390="Completed / Handover",Y390<>"",Z390>=100),"Completed — on track",IF(O390="Not awarded",IF(U390="",IF(X390="","No planned date",IF(TODAY()>X390,"Behind — past planned date",IF(X390-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U390,"Behind — award date passed",IF(U390-TODAY()<=30,"At risk — close to off track","On track"))),IF(X390="","No planned date",IF(AND(TODAY()>X390,OR(Z390="",Z390<100)),"Behind — past end date",IF(AND(T390<>"",X390<>"",Z390<>"",(Z390<100),((TODAY()-T390)/MAX(X390-T390,1)*100)-Z390>15),"Behind — progress lag",IF(AND(X390-TODAY()<=30,X390-TODAY()>=0,OR(Z390="",Z390<90)),"At risk — close to off track","On track")))))))) | IF(OR(F390="",AC390="Completed / Handover",AC390="Cancelled"),"",IF(O390="Not awarded",IF(U390<>"",U390-TODAY(),IF(X390="","",X390-TODAY())),IF(X390="","",X390-TODAY()))) | [14 empty] | IF(OR(F390="",AJ390=""),"",IF(COUNT(AI390:AI390)=0,"",AJ390-LOOKUP(2,1/(AI390:AI390<>""),AI390:AI390))) | IF(OR(F390="",AK390=""),"",IF(COUNT(AI390:AJ390)=0,"",AK390-LOOKUP(2,1/(AI390:AJ390<>""),AI390:AJ390))) | IF(OR(F390="",AL390=""),"",IF(COUNT(AI390:AK390)=0,"",AL390-LOOKUP(2,1/(AI390:AK390<>""),AI390:AK390))) | IF(OR(F390="",AM390=""),"",IF(COUNT(AI390:AL390)=0,"",AM390-LOOKUP(2,1/(AI390:AL390<>""),AI390:AL390))) | IF(OR(F390="",AN390=""),"",IF(COUNT(AI390:AM390)=0,"",AN390-LOOKUP(2,1/(AI390:AM390<>""),AI390:AM390))) | IF(OR(F390="",AO390=""),"",IF(COUNT(AI390:AN390)=0,"",AO390-LOOKUP(2,1/(AI390:AN390<>""),AI390:AN390))) | IF(OR(F390="",AP390=""),"",IF(COUNT(AI390:AO390)=0,"",AP390-LOOKUP(2,1/(AI390:AO390<>""),AI390:AO390))) | IF(OR(F390="",AQ390=""),"",IF(COUNT(AI390:AP390)=0,"",AQ390-LOOKUP(2,1/(AI390:AP390<>""),AI390:AP390))) | IF(OR(F390="",AR390=""),"",IF(COUNT(AI390:AQ390)=0,"",AR390-LOOKUP(2,1/(AI390:AQ390<>""),AI390:AQ390))) | IF(OR(F390="",AS390=""),"",IF(COUNT(AI390:AR390)=0,"",AS390-LOOKUP(2,1/(AI390:AR390<>""),AI390:AR390))) | IF(OR(F390="",AT390=""),"",IF(COUNT(AI390:AS390)=0,"",AT390-LOOKUP(2,1/(AI390:AS390<>""),AI390:AS390))) | IF(OR(F390="",AU390=""),"",IF(COUNT(AI390:AT390)=0,"",AU390-LOOKUP(2,1/(AI390:AT390<>""),AI390:AT390))) | IF(OR(F390="",AV390=""),"",IF(COUNT(AI390:AU390)=0,"",AV390-LOOKUP(2,1/(AI390:AU390<>""),AI390:AU390))) | IF(J390="","All_Provinces",IFERROR(VLOOKUP(J390,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K390="","All_Districts",IFERROR(VLOOKUP(K390,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F391="","",ROW()-3) | [18 empty] | IF(AQ391="","",AQ391) |  |  |  | IF(W391<>"",W391,IF(OR(T391="",V391=""),"",EDATE(T391,V391))) |  |  |  |  | IF(F391="","",IF(COUNT(AI391:AV391)=0,IF(AA391="","Not started",AA391),SUBSTITUTE(LOOKUP(2,1/(AI391:AV391<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F391="",COUNT(AI391:AV391)=0),"",TODAY()-LOOKUP(2,1/(AI391:AV391<>""),AI391:AV391)) | IF(OR(F391="",COUNT(AI391:AV391)<2),"",LOOKUP(2,1/(AI391:AV391<>""),AI391:AV391)-MIN(AI391:AV391)) | IF(OR(AD391="",AC391="Not started",AC391=""),"",IFERROR(AD391-IF(VLOOKUP(AC391,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC391,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F391="","",IF(OR(AA391="Cancelled",AC391="Cancelled"),"Cancelled",IF(OR(AC391="Completed / Handover",Y391<>"",Z391>=100),"Completed — on track",IF(O391="Not awarded",IF(U391="",IF(X391="","No planned date",IF(TODAY()>X391,"Behind — past planned date",IF(X391-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U391,"Behind — award date passed",IF(U391-TODAY()<=30,"At risk — close to off track","On track"))),IF(X391="","No planned date",IF(AND(TODAY()>X391,OR(Z391="",Z391<100)),"Behind — past end date",IF(AND(T391<>"",X391<>"",Z391<>"",(Z391<100),((TODAY()-T391)/MAX(X391-T391,1)*100)-Z391>15),"Behind — progress lag",IF(AND(X391-TODAY()<=30,X391-TODAY()>=0,OR(Z391="",Z391<90)),"At risk — close to off track","On track")))))))) | IF(OR(F391="",AC391="Completed / Handover",AC391="Cancelled"),"",IF(O391="Not awarded",IF(U391<>"",U391-TODAY(),IF(X391="","",X391-TODAY())),IF(X391="","",X391-TODAY()))) | [14 empty] | IF(OR(F391="",AJ391=""),"",IF(COUNT(AI391:AI391)=0,"",AJ391-LOOKUP(2,1/(AI391:AI391<>""),AI391:AI391))) | IF(OR(F391="",AK391=""),"",IF(COUNT(AI391:AJ391)=0,"",AK391-LOOKUP(2,1/(AI391:AJ391<>""),AI391:AJ391))) | IF(OR(F391="",AL391=""),"",IF(COUNT(AI391:AK391)=0,"",AL391-LOOKUP(2,1/(AI391:AK391<>""),AI391:AK391))) | IF(OR(F391="",AM391=""),"",IF(COUNT(AI391:AL391)=0,"",AM391-LOOKUP(2,1/(AI391:AL391<>""),AI391:AL391))) | IF(OR(F391="",AN391=""),"",IF(COUNT(AI391:AM391)=0,"",AN391-LOOKUP(2,1/(AI391:AM391<>""),AI391:AM391))) | IF(OR(F391="",AO391=""),"",IF(COUNT(AI391:AN391)=0,"",AO391-LOOKUP(2,1/(AI391:AN391<>""),AI391:AN391))) | IF(OR(F391="",AP391=""),"",IF(COUNT(AI391:AO391)=0,"",AP391-LOOKUP(2,1/(AI391:AO391<>""),AI391:AO391))) | IF(OR(F391="",AQ391=""),"",IF(COUNT(AI391:AP391)=0,"",AQ391-LOOKUP(2,1/(AI391:AP391<>""),AI391:AP391))) | IF(OR(F391="",AR391=""),"",IF(COUNT(AI391:AQ391)=0,"",AR391-LOOKUP(2,1/(AI391:AQ391<>""),AI391:AQ391))) | IF(OR(F391="",AS391=""),"",IF(COUNT(AI391:AR391)=0,"",AS391-LOOKUP(2,1/(AI391:AR391<>""),AI391:AR391))) | IF(OR(F391="",AT391=""),"",IF(COUNT(AI391:AS391)=0,"",AT391-LOOKUP(2,1/(AI391:AS391<>""),AI391:AS391))) | IF(OR(F391="",AU391=""),"",IF(COUNT(AI391:AT391)=0,"",AU391-LOOKUP(2,1/(AI391:AT391<>""),AI391:AT391))) | IF(OR(F391="",AV391=""),"",IF(COUNT(AI391:AU391)=0,"",AV391-LOOKUP(2,1/(AI391:AU391<>""),AI391:AU391))) | IF(J391="","All_Provinces",IFERROR(VLOOKUP(J391,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K391="","All_Districts",IFERROR(VLOOKUP(K391,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F392="","",ROW()-3) | [18 empty] | IF(AQ392="","",AQ392) |  |  |  | IF(W392<>"",W392,IF(OR(T392="",V392=""),"",EDATE(T392,V392))) |  |  |  |  | IF(F392="","",IF(COUNT(AI392:AV392)=0,IF(AA392="","Not started",AA392),SUBSTITUTE(LOOKUP(2,1/(AI392:AV392<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F392="",COUNT(AI392:AV392)=0),"",TODAY()-LOOKUP(2,1/(AI392:AV392<>""),AI392:AV392)) | IF(OR(F392="",COUNT(AI392:AV392)<2),"",LOOKUP(2,1/(AI392:AV392<>""),AI392:AV392)-MIN(AI392:AV392)) | IF(OR(AD392="",AC392="Not started",AC392=""),"",IFERROR(AD392-IF(VLOOKUP(AC392,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC392,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F392="","",IF(OR(AA392="Cancelled",AC392="Cancelled"),"Cancelled",IF(OR(AC392="Completed / Handover",Y392<>"",Z392>=100),"Completed — on track",IF(O392="Not awarded",IF(U392="",IF(X392="","No planned date",IF(TODAY()>X392,"Behind — past planned date",IF(X392-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U392,"Behind — award date passed",IF(U392-TODAY()<=30,"At risk — close to off track","On track"))),IF(X392="","No planned date",IF(AND(TODAY()>X392,OR(Z392="",Z392<100)),"Behind — past end date",IF(AND(T392<>"",X392<>"",Z392<>"",(Z392<100),((TODAY()-T392)/MAX(X392-T392,1)*100)-Z392>15),"Behind — progress lag",IF(AND(X392-TODAY()<=30,X392-TODAY()>=0,OR(Z392="",Z392<90)),"At risk — close to off track","On track")))))))) | IF(OR(F392="",AC392="Completed / Handover",AC392="Cancelled"),"",IF(O392="Not awarded",IF(U392<>"",U392-TODAY(),IF(X392="","",X392-TODAY())),IF(X392="","",X392-TODAY()))) | [14 empty] | IF(OR(F392="",AJ392=""),"",IF(COUNT(AI392:AI392)=0,"",AJ392-LOOKUP(2,1/(AI392:AI392<>""),AI392:AI392))) | IF(OR(F392="",AK392=""),"",IF(COUNT(AI392:AJ392)=0,"",AK392-LOOKUP(2,1/(AI392:AJ392<>""),AI392:AJ392))) | IF(OR(F392="",AL392=""),"",IF(COUNT(AI392:AK392)=0,"",AL392-LOOKUP(2,1/(AI392:AK392<>""),AI392:AK392))) | IF(OR(F392="",AM392=""),"",IF(COUNT(AI392:AL392)=0,"",AM392-LOOKUP(2,1/(AI392:AL392<>""),AI392:AL392))) | IF(OR(F392="",AN392=""),"",IF(COUNT(AI392:AM392)=0,"",AN392-LOOKUP(2,1/(AI392:AM392<>""),AI392:AM392))) | IF(OR(F392="",AO392=""),"",IF(COUNT(AI392:AN392)=0,"",AO392-LOOKUP(2,1/(AI392:AN392<>""),AI392:AN392))) | IF(OR(F392="",AP392=""),"",IF(COUNT(AI392:AO392)=0,"",AP392-LOOKUP(2,1/(AI392:AO392<>""),AI392:AO392))) | IF(OR(F392="",AQ392=""),"",IF(COUNT(AI392:AP392)=0,"",AQ392-LOOKUP(2,1/(AI392:AP392<>""),AI392:AP392))) | IF(OR(F392="",AR392=""),"",IF(COUNT(AI392:AQ392)=0,"",AR392-LOOKUP(2,1/(AI392:AQ392<>""),AI392:AQ392))) | IF(OR(F392="",AS392=""),"",IF(COUNT(AI392:AR392)=0,"",AS392-LOOKUP(2,1/(AI392:AR392<>""),AI392:AR392))) | IF(OR(F392="",AT392=""),"",IF(COUNT(AI392:AS392)=0,"",AT392-LOOKUP(2,1/(AI392:AS392<>""),AI392:AS392))) | IF(OR(F392="",AU392=""),"",IF(COUNT(AI392:AT392)=0,"",AU392-LOOKUP(2,1/(AI392:AT392<>""),AI392:AT392))) | IF(OR(F392="",AV392=""),"",IF(COUNT(AI392:AU392)=0,"",AV392-LOOKUP(2,1/(AI392:AU392<>""),AI392:AU392))) | IF(J392="","All_Provinces",IFERROR(VLOOKUP(J392,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K392="","All_Districts",IFERROR(VLOOKUP(K392,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F393="","",ROW()-3) | [18 empty] | IF(AQ393="","",AQ393) |  |  |  | IF(W393<>"",W393,IF(OR(T393="",V393=""),"",EDATE(T393,V393))) |  |  |  |  | IF(F393="","",IF(COUNT(AI393:AV393)=0,IF(AA393="","Not started",AA393),SUBSTITUTE(LOOKUP(2,1/(AI393:AV393<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F393="",COUNT(AI393:AV393)=0),"",TODAY()-LOOKUP(2,1/(AI393:AV393<>""),AI393:AV393)) | IF(OR(F393="",COUNT(AI393:AV393)<2),"",LOOKUP(2,1/(AI393:AV393<>""),AI393:AV393)-MIN(AI393:AV393)) | IF(OR(AD393="",AC393="Not started",AC393=""),"",IFERROR(AD393-IF(VLOOKUP(AC393,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC393,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F393="","",IF(OR(AA393="Cancelled",AC393="Cancelled"),"Cancelled",IF(OR(AC393="Completed / Handover",Y393<>"",Z393>=100),"Completed — on track",IF(O393="Not awarded",IF(U393="",IF(X393="","No planned date",IF(TODAY()>X393,"Behind — past planned date",IF(X393-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U393,"Behind — award date passed",IF(U393-TODAY()<=30,"At risk — close to off track","On track"))),IF(X393="","No planned date",IF(AND(TODAY()>X393,OR(Z393="",Z393<100)),"Behind — past end date",IF(AND(T393<>"",X393<>"",Z393<>"",(Z393<100),((TODAY()-T393)/MAX(X393-T393,1)*100)-Z393>15),"Behind — progress lag",IF(AND(X393-TODAY()<=30,X393-TODAY()>=0,OR(Z393="",Z393<90)),"At risk — close to off track","On track")))))))) | IF(OR(F393="",AC393="Completed / Handover",AC393="Cancelled"),"",IF(O393="Not awarded",IF(U393<>"",U393-TODAY(),IF(X393="","",X393-TODAY())),IF(X393="","",X393-TODAY()))) | [14 empty] | IF(OR(F393="",AJ393=""),"",IF(COUNT(AI393:AI393)=0,"",AJ393-LOOKUP(2,1/(AI393:AI393<>""),AI393:AI393))) | IF(OR(F393="",AK393=""),"",IF(COUNT(AI393:AJ393)=0,"",AK393-LOOKUP(2,1/(AI393:AJ393<>""),AI393:AJ393))) | IF(OR(F393="",AL393=""),"",IF(COUNT(AI393:AK393)=0,"",AL393-LOOKUP(2,1/(AI393:AK393<>""),AI393:AK393))) | IF(OR(F393="",AM393=""),"",IF(COUNT(AI393:AL393)=0,"",AM393-LOOKUP(2,1/(AI393:AL393<>""),AI393:AL393))) | IF(OR(F393="",AN393=""),"",IF(COUNT(AI393:AM393)=0,"",AN393-LOOKUP(2,1/(AI393:AM393<>""),AI393:AM393))) | IF(OR(F393="",AO393=""),"",IF(COUNT(AI393:AN393)=0,"",AO393-LOOKUP(2,1/(AI393:AN393<>""),AI393:AN393))) | IF(OR(F393="",AP393=""),"",IF(COUNT(AI393:AO393)=0,"",AP393-LOOKUP(2,1/(AI393:AO393<>""),AI393:AO393))) | IF(OR(F393="",AQ393=""),"",IF(COUNT(AI393:AP393)=0,"",AQ393-LOOKUP(2,1/(AI393:AP393<>""),AI393:AP393))) | IF(OR(F393="",AR393=""),"",IF(COUNT(AI393:AQ393)=0,"",AR393-LOOKUP(2,1/(AI393:AQ393<>""),AI393:AQ393))) | IF(OR(F393="",AS393=""),"",IF(COUNT(AI393:AR393)=0,"",AS393-LOOKUP(2,1/(AI393:AR393<>""),AI393:AR393))) | IF(OR(F393="",AT393=""),"",IF(COUNT(AI393:AS393)=0,"",AT393-LOOKUP(2,1/(AI393:AS393<>""),AI393:AS393))) | IF(OR(F393="",AU393=""),"",IF(COUNT(AI393:AT393)=0,"",AU393-LOOKUP(2,1/(AI393:AT393<>""),AI393:AT393))) | IF(OR(F393="",AV393=""),"",IF(COUNT(AI393:AU393)=0,"",AV393-LOOKUP(2,1/(AI393:AU393<>""),AI393:AU393))) | IF(J393="","All_Provinces",IFERROR(VLOOKUP(J393,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K393="","All_Districts",IFERROR(VLOOKUP(K393,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F394="","",ROW()-3) | [18 empty] | IF(AQ394="","",AQ394) |  |  |  | IF(W394<>"",W394,IF(OR(T394="",V394=""),"",EDATE(T394,V394))) |  |  |  |  | IF(F394="","",IF(COUNT(AI394:AV394)=0,IF(AA394="","Not started",AA394),SUBSTITUTE(LOOKUP(2,1/(AI394:AV394<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F394="",COUNT(AI394:AV394)=0),"",TODAY()-LOOKUP(2,1/(AI394:AV394<>""),AI394:AV394)) | IF(OR(F394="",COUNT(AI394:AV394)<2),"",LOOKUP(2,1/(AI394:AV394<>""),AI394:AV394)-MIN(AI394:AV394)) | IF(OR(AD394="",AC394="Not started",AC394=""),"",IFERROR(AD394-IF(VLOOKUP(AC394,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC394,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F394="","",IF(OR(AA394="Cancelled",AC394="Cancelled"),"Cancelled",IF(OR(AC394="Completed / Handover",Y394<>"",Z394>=100),"Completed — on track",IF(O394="Not awarded",IF(U394="",IF(X394="","No planned date",IF(TODAY()>X394,"Behind — past planned date",IF(X394-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U394,"Behind — award date passed",IF(U394-TODAY()<=30,"At risk — close to off track","On track"))),IF(X394="","No planned date",IF(AND(TODAY()>X394,OR(Z394="",Z394<100)),"Behind — past end date",IF(AND(T394<>"",X394<>"",Z394<>"",(Z394<100),((TODAY()-T394)/MAX(X394-T394,1)*100)-Z394>15),"Behind — progress lag",IF(AND(X394-TODAY()<=30,X394-TODAY()>=0,OR(Z394="",Z394<90)),"At risk — close to off track","On track")))))))) | IF(OR(F394="",AC394="Completed / Handover",AC394="Cancelled"),"",IF(O394="Not awarded",IF(U394<>"",U394-TODAY(),IF(X394="","",X394-TODAY())),IF(X394="","",X394-TODAY()))) | [14 empty] | IF(OR(F394="",AJ394=""),"",IF(COUNT(AI394:AI394)=0,"",AJ394-LOOKUP(2,1/(AI394:AI394<>""),AI394:AI394))) | IF(OR(F394="",AK394=""),"",IF(COUNT(AI394:AJ394)=0,"",AK394-LOOKUP(2,1/(AI394:AJ394<>""),AI394:AJ394))) | IF(OR(F394="",AL394=""),"",IF(COUNT(AI394:AK394)=0,"",AL394-LOOKUP(2,1/(AI394:AK394<>""),AI394:AK394))) | IF(OR(F394="",AM394=""),"",IF(COUNT(AI394:AL394)=0,"",AM394-LOOKUP(2,1/(AI394:AL394<>""),AI394:AL394))) | IF(OR(F394="",AN394=""),"",IF(COUNT(AI394:AM394)=0,"",AN394-LOOKUP(2,1/(AI394:AM394<>""),AI394:AM394))) | IF(OR(F394="",AO394=""),"",IF(COUNT(AI394:AN394)=0,"",AO394-LOOKUP(2,1/(AI394:AN394<>""),AI394:AN394))) | IF(OR(F394="",AP394=""),"",IF(COUNT(AI394:AO394)=0,"",AP394-LOOKUP(2,1/(AI394:AO394<>""),AI394:AO394))) | IF(OR(F394="",AQ394=""),"",IF(COUNT(AI394:AP394)=0,"",AQ394-LOOKUP(2,1/(AI394:AP394<>""),AI394:AP394))) | IF(OR(F394="",AR394=""),"",IF(COUNT(AI394:AQ394)=0,"",AR394-LOOKUP(2,1/(AI394:AQ394<>""),AI394:AQ394))) | IF(OR(F394="",AS394=""),"",IF(COUNT(AI394:AR394)=0,"",AS394-LOOKUP(2,1/(AI394:AR394<>""),AI394:AR394))) | IF(OR(F394="",AT394=""),"",IF(COUNT(AI394:AS394)=0,"",AT394-LOOKUP(2,1/(AI394:AS394<>""),AI394:AS394))) | IF(OR(F394="",AU394=""),"",IF(COUNT(AI394:AT394)=0,"",AU394-LOOKUP(2,1/(AI394:AT394<>""),AI394:AT394))) | IF(OR(F394="",AV394=""),"",IF(COUNT(AI394:AU394)=0,"",AV394-LOOKUP(2,1/(AI394:AU394<>""),AI394:AU394))) | IF(J394="","All_Provinces",IFERROR(VLOOKUP(J394,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K394="","All_Districts",IFERROR(VLOOKUP(K394,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F395="","",ROW()-3) | [18 empty] | IF(AQ395="","",AQ395) |  |  |  | IF(W395<>"",W395,IF(OR(T395="",V395=""),"",EDATE(T395,V395))) |  |  |  |  | IF(F395="","",IF(COUNT(AI395:AV395)=0,IF(AA395="","Not started",AA395),SUBSTITUTE(LOOKUP(2,1/(AI395:AV395<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F395="",COUNT(AI395:AV395)=0),"",TODAY()-LOOKUP(2,1/(AI395:AV395<>""),AI395:AV395)) | IF(OR(F395="",COUNT(AI395:AV395)<2),"",LOOKUP(2,1/(AI395:AV395<>""),AI395:AV395)-MIN(AI395:AV395)) | IF(OR(AD395="",AC395="Not started",AC395=""),"",IFERROR(AD395-IF(VLOOKUP(AC395,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC395,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F395="","",IF(OR(AA395="Cancelled",AC395="Cancelled"),"Cancelled",IF(OR(AC395="Completed / Handover",Y395<>"",Z395>=100),"Completed — on track",IF(O395="Not awarded",IF(U395="",IF(X395="","No planned date",IF(TODAY()>X395,"Behind — past planned date",IF(X395-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U395,"Behind — award date passed",IF(U395-TODAY()<=30,"At risk — close to off track","On track"))),IF(X395="","No planned date",IF(AND(TODAY()>X395,OR(Z395="",Z395<100)),"Behind — past end date",IF(AND(T395<>"",X395<>"",Z395<>"",(Z395<100),((TODAY()-T395)/MAX(X395-T395,1)*100)-Z395>15),"Behind — progress lag",IF(AND(X395-TODAY()<=30,X395-TODAY()>=0,OR(Z395="",Z395<90)),"At risk — close to off track","On track")))))))) | IF(OR(F395="",AC395="Completed / Handover",AC395="Cancelled"),"",IF(O395="Not awarded",IF(U395<>"",U395-TODAY(),IF(X395="","",X395-TODAY())),IF(X395="","",X395-TODAY()))) | [14 empty] | IF(OR(F395="",AJ395=""),"",IF(COUNT(AI395:AI395)=0,"",AJ395-LOOKUP(2,1/(AI395:AI395<>""),AI395:AI395))) | IF(OR(F395="",AK395=""),"",IF(COUNT(AI395:AJ395)=0,"",AK395-LOOKUP(2,1/(AI395:AJ395<>""),AI395:AJ395))) | IF(OR(F395="",AL395=""),"",IF(COUNT(AI395:AK395)=0,"",AL395-LOOKUP(2,1/(AI395:AK395<>""),AI395:AK395))) | IF(OR(F395="",AM395=""),"",IF(COUNT(AI395:AL395)=0,"",AM395-LOOKUP(2,1/(AI395:AL395<>""),AI395:AL395))) | IF(OR(F395="",AN395=""),"",IF(COUNT(AI395:AM395)=0,"",AN395-LOOKUP(2,1/(AI395:AM395<>""),AI395:AM395))) | IF(OR(F395="",AO395=""),"",IF(COUNT(AI395:AN395)=0,"",AO395-LOOKUP(2,1/(AI395:AN395<>""),AI395:AN395))) | IF(OR(F395="",AP395=""),"",IF(COUNT(AI395:AO395)=0,"",AP395-LOOKUP(2,1/(AI395:AO395<>""),AI395:AO395))) | IF(OR(F395="",AQ395=""),"",IF(COUNT(AI395:AP395)=0,"",AQ395-LOOKUP(2,1/(AI395:AP395<>""),AI395:AP395))) | IF(OR(F395="",AR395=""),"",IF(COUNT(AI395:AQ395)=0,"",AR395-LOOKUP(2,1/(AI395:AQ395<>""),AI395:AQ395))) | IF(OR(F395="",AS395=""),"",IF(COUNT(AI395:AR395)=0,"",AS395-LOOKUP(2,1/(AI395:AR395<>""),AI395:AR395))) | IF(OR(F395="",AT395=""),"",IF(COUNT(AI395:AS395)=0,"",AT395-LOOKUP(2,1/(AI395:AS395<>""),AI395:AS395))) | IF(OR(F395="",AU395=""),"",IF(COUNT(AI395:AT395)=0,"",AU395-LOOKUP(2,1/(AI395:AT395<>""),AI395:AT395))) | IF(OR(F395="",AV395=""),"",IF(COUNT(AI395:AU395)=0,"",AV395-LOOKUP(2,1/(AI395:AU395<>""),AI395:AU395))) | IF(J395="","All_Provinces",IFERROR(VLOOKUP(J395,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K395="","All_Districts",IFERROR(VLOOKUP(K395,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F396="","",ROW()-3) | [18 empty] | IF(AQ396="","",AQ396) |  |  |  | IF(W396<>"",W396,IF(OR(T396="",V396=""),"",EDATE(T396,V396))) |  |  |  |  | IF(F396="","",IF(COUNT(AI396:AV396)=0,IF(AA396="","Not started",AA396),SUBSTITUTE(LOOKUP(2,1/(AI396:AV396<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F396="",COUNT(AI396:AV396)=0),"",TODAY()-LOOKUP(2,1/(AI396:AV396<>""),AI396:AV396)) | IF(OR(F396="",COUNT(AI396:AV396)<2),"",LOOKUP(2,1/(AI396:AV396<>""),AI396:AV396)-MIN(AI396:AV396)) | IF(OR(AD396="",AC396="Not started",AC396=""),"",IFERROR(AD396-IF(VLOOKUP(AC396,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC396,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F396="","",IF(OR(AA396="Cancelled",AC396="Cancelled"),"Cancelled",IF(OR(AC396="Completed / Handover",Y396<>"",Z396>=100),"Completed — on track",IF(O396="Not awarded",IF(U396="",IF(X396="","No planned date",IF(TODAY()>X396,"Behind — past planned date",IF(X396-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U396,"Behind — award date passed",IF(U396-TODAY()<=30,"At risk — close to off track","On track"))),IF(X396="","No planned date",IF(AND(TODAY()>X396,OR(Z396="",Z396<100)),"Behind — past end date",IF(AND(T396<>"",X396<>"",Z396<>"",(Z396<100),((TODAY()-T396)/MAX(X396-T396,1)*100)-Z396>15),"Behind — progress lag",IF(AND(X396-TODAY()<=30,X396-TODAY()>=0,OR(Z396="",Z396<90)),"At risk — close to off track","On track")))))))) | IF(OR(F396="",AC396="Completed / Handover",AC396="Cancelled"),"",IF(O396="Not awarded",IF(U396<>"",U396-TODAY(),IF(X396="","",X396-TODAY())),IF(X396="","",X396-TODAY()))) | [14 empty] | IF(OR(F396="",AJ396=""),"",IF(COUNT(AI396:AI396)=0,"",AJ396-LOOKUP(2,1/(AI396:AI396<>""),AI396:AI396))) | IF(OR(F396="",AK396=""),"",IF(COUNT(AI396:AJ396)=0,"",AK396-LOOKUP(2,1/(AI396:AJ396<>""),AI396:AJ396))) | IF(OR(F396="",AL396=""),"",IF(COUNT(AI396:AK396)=0,"",AL396-LOOKUP(2,1/(AI396:AK396<>""),AI396:AK396))) | IF(OR(F396="",AM396=""),"",IF(COUNT(AI396:AL396)=0,"",AM396-LOOKUP(2,1/(AI396:AL396<>""),AI396:AL396))) | IF(OR(F396="",AN396=""),"",IF(COUNT(AI396:AM396)=0,"",AN396-LOOKUP(2,1/(AI396:AM396<>""),AI396:AM396))) | IF(OR(F396="",AO396=""),"",IF(COUNT(AI396:AN396)=0,"",AO396-LOOKUP(2,1/(AI396:AN396<>""),AI396:AN396))) | IF(OR(F396="",AP396=""),"",IF(COUNT(AI396:AO396)=0,"",AP396-LOOKUP(2,1/(AI396:AO396<>""),AI396:AO396))) | IF(OR(F396="",AQ396=""),"",IF(COUNT(AI396:AP396)=0,"",AQ396-LOOKUP(2,1/(AI396:AP396<>""),AI396:AP396))) | IF(OR(F396="",AR396=""),"",IF(COUNT(AI396:AQ396)=0,"",AR396-LOOKUP(2,1/(AI396:AQ396<>""),AI396:AQ396))) | IF(OR(F396="",AS396=""),"",IF(COUNT(AI396:AR396)=0,"",AS396-LOOKUP(2,1/(AI396:AR396<>""),AI396:AR396))) | IF(OR(F396="",AT396=""),"",IF(COUNT(AI396:AS396)=0,"",AT396-LOOKUP(2,1/(AI396:AS396<>""),AI396:AS396))) | IF(OR(F396="",AU396=""),"",IF(COUNT(AI396:AT396)=0,"",AU396-LOOKUP(2,1/(AI396:AT396<>""),AI396:AT396))) | IF(OR(F396="",AV396=""),"",IF(COUNT(AI396:AU396)=0,"",AV396-LOOKUP(2,1/(AI396:AU396<>""),AI396:AU396))) | IF(J396="","All_Provinces",IFERROR(VLOOKUP(J396,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K396="","All_Districts",IFERROR(VLOOKUP(K396,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F397="","",ROW()-3) | [18 empty] | IF(AQ397="","",AQ397) |  |  |  | IF(W397<>"",W397,IF(OR(T397="",V397=""),"",EDATE(T397,V397))) |  |  |  |  | IF(F397="","",IF(COUNT(AI397:AV397)=0,IF(AA397="","Not started",AA397),SUBSTITUTE(LOOKUP(2,1/(AI397:AV397<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F397="",COUNT(AI397:AV397)=0),"",TODAY()-LOOKUP(2,1/(AI397:AV397<>""),AI397:AV397)) | IF(OR(F397="",COUNT(AI397:AV397)<2),"",LOOKUP(2,1/(AI397:AV397<>""),AI397:AV397)-MIN(AI397:AV397)) | IF(OR(AD397="",AC397="Not started",AC397=""),"",IFERROR(AD397-IF(VLOOKUP(AC397,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC397,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F397="","",IF(OR(AA397="Cancelled",AC397="Cancelled"),"Cancelled",IF(OR(AC397="Completed / Handover",Y397<>"",Z397>=100),"Completed — on track",IF(O397="Not awarded",IF(U397="",IF(X397="","No planned date",IF(TODAY()>X397,"Behind — past planned date",IF(X397-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U397,"Behind — award date passed",IF(U397-TODAY()<=30,"At risk — close to off track","On track"))),IF(X397="","No planned date",IF(AND(TODAY()>X397,OR(Z397="",Z397<100)),"Behind — past end date",IF(AND(T397<>"",X397<>"",Z397<>"",(Z397<100),((TODAY()-T397)/MAX(X397-T397,1)*100)-Z397>15),"Behind — progress lag",IF(AND(X397-TODAY()<=30,X397-TODAY()>=0,OR(Z397="",Z397<90)),"At risk — close to off track","On track")))))))) | IF(OR(F397="",AC397="Completed / Handover",AC397="Cancelled"),"",IF(O397="Not awarded",IF(U397<>"",U397-TODAY(),IF(X397="","",X397-TODAY())),IF(X397="","",X397-TODAY()))) | [14 empty] | IF(OR(F397="",AJ397=""),"",IF(COUNT(AI397:AI397)=0,"",AJ397-LOOKUP(2,1/(AI397:AI397<>""),AI397:AI397))) | IF(OR(F397="",AK397=""),"",IF(COUNT(AI397:AJ397)=0,"",AK397-LOOKUP(2,1/(AI397:AJ397<>""),AI397:AJ397))) | IF(OR(F397="",AL397=""),"",IF(COUNT(AI397:AK397)=0,"",AL397-LOOKUP(2,1/(AI397:AK397<>""),AI397:AK397))) | IF(OR(F397="",AM397=""),"",IF(COUNT(AI397:AL397)=0,"",AM397-LOOKUP(2,1/(AI397:AL397<>""),AI397:AL397))) | IF(OR(F397="",AN397=""),"",IF(COUNT(AI397:AM397)=0,"",AN397-LOOKUP(2,1/(AI397:AM397<>""),AI397:AM397))) | IF(OR(F397="",AO397=""),"",IF(COUNT(AI397:AN397)=0,"",AO397-LOOKUP(2,1/(AI397:AN397<>""),AI397:AN397))) | IF(OR(F397="",AP397=""),"",IF(COUNT(AI397:AO397)=0,"",AP397-LOOKUP(2,1/(AI397:AO397<>""),AI397:AO397))) | IF(OR(F397="",AQ397=""),"",IF(COUNT(AI397:AP397)=0,"",AQ397-LOOKUP(2,1/(AI397:AP397<>""),AI397:AP397))) | IF(OR(F397="",AR397=""),"",IF(COUNT(AI397:AQ397)=0,"",AR397-LOOKUP(2,1/(AI397:AQ397<>""),AI397:AQ397))) | IF(OR(F397="",AS397=""),"",IF(COUNT(AI397:AR397)=0,"",AS397-LOOKUP(2,1/(AI397:AR397<>""),AI397:AR397))) | IF(OR(F397="",AT397=""),"",IF(COUNT(AI397:AS397)=0,"",AT397-LOOKUP(2,1/(AI397:AS397<>""),AI397:AS397))) | IF(OR(F397="",AU397=""),"",IF(COUNT(AI397:AT397)=0,"",AU397-LOOKUP(2,1/(AI397:AT397<>""),AI397:AT397))) | IF(OR(F397="",AV397=""),"",IF(COUNT(AI397:AU397)=0,"",AV397-LOOKUP(2,1/(AI397:AU397<>""),AI397:AU397))) | IF(J397="","All_Provinces",IFERROR(VLOOKUP(J397,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K397="","All_Districts",IFERROR(VLOOKUP(K397,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F398="","",ROW()-3) | [18 empty] | IF(AQ398="","",AQ398) |  |  |  | IF(W398<>"",W398,IF(OR(T398="",V398=""),"",EDATE(T398,V398))) |  |  |  |  | IF(F398="","",IF(COUNT(AI398:AV398)=0,IF(AA398="","Not started",AA398),SUBSTITUTE(LOOKUP(2,1/(AI398:AV398<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F398="",COUNT(AI398:AV398)=0),"",TODAY()-LOOKUP(2,1/(AI398:AV398<>""),AI398:AV398)) | IF(OR(F398="",COUNT(AI398:AV398)<2),"",LOOKUP(2,1/(AI398:AV398<>""),AI398:AV398)-MIN(AI398:AV398)) | IF(OR(AD398="",AC398="Not started",AC398=""),"",IFERROR(AD398-IF(VLOOKUP(AC398,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC398,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F398="","",IF(OR(AA398="Cancelled",AC398="Cancelled"),"Cancelled",IF(OR(AC398="Completed / Handover",Y398<>"",Z398>=100),"Completed — on track",IF(O398="Not awarded",IF(U398="",IF(X398="","No planned date",IF(TODAY()>X398,"Behind — past planned date",IF(X398-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U398,"Behind — award date passed",IF(U398-TODAY()<=30,"At risk — close to off track","On track"))),IF(X398="","No planned date",IF(AND(TODAY()>X398,OR(Z398="",Z398<100)),"Behind — past end date",IF(AND(T398<>"",X398<>"",Z398<>"",(Z398<100),((TODAY()-T398)/MAX(X398-T398,1)*100)-Z398>15),"Behind — progress lag",IF(AND(X398-TODAY()<=30,X398-TODAY()>=0,OR(Z398="",Z398<90)),"At risk — close to off track","On track")))))))) | IF(OR(F398="",AC398="Completed / Handover",AC398="Cancelled"),"",IF(O398="Not awarded",IF(U398<>"",U398-TODAY(),IF(X398="","",X398-TODAY())),IF(X398="","",X398-TODAY()))) | [14 empty] | IF(OR(F398="",AJ398=""),"",IF(COUNT(AI398:AI398)=0,"",AJ398-LOOKUP(2,1/(AI398:AI398<>""),AI398:AI398))) | IF(OR(F398="",AK398=""),"",IF(COUNT(AI398:AJ398)=0,"",AK398-LOOKUP(2,1/(AI398:AJ398<>""),AI398:AJ398))) | IF(OR(F398="",AL398=""),"",IF(COUNT(AI398:AK398)=0,"",AL398-LOOKUP(2,1/(AI398:AK398<>""),AI398:AK398))) | IF(OR(F398="",AM398=""),"",IF(COUNT(AI398:AL398)=0,"",AM398-LOOKUP(2,1/(AI398:AL398<>""),AI398:AL398))) | IF(OR(F398="",AN398=""),"",IF(COUNT(AI398:AM398)=0,"",AN398-LOOKUP(2,1/(AI398:AM398<>""),AI398:AM398))) | IF(OR(F398="",AO398=""),"",IF(COUNT(AI398:AN398)=0,"",AO398-LOOKUP(2,1/(AI398:AN398<>""),AI398:AN398))) | IF(OR(F398="",AP398=""),"",IF(COUNT(AI398:AO398)=0,"",AP398-LOOKUP(2,1/(AI398:AO398<>""),AI398:AO398))) | IF(OR(F398="",AQ398=""),"",IF(COUNT(AI398:AP398)=0,"",AQ398-LOOKUP(2,1/(AI398:AP398<>""),AI398:AP398))) | IF(OR(F398="",AR398=""),"",IF(COUNT(AI398:AQ398)=0,"",AR398-LOOKUP(2,1/(AI398:AQ398<>""),AI398:AQ398))) | IF(OR(F398="",AS398=""),"",IF(COUNT(AI398:AR398)=0,"",AS398-LOOKUP(2,1/(AI398:AR398<>""),AI398:AR398))) | IF(OR(F398="",AT398=""),"",IF(COUNT(AI398:AS398)=0,"",AT398-LOOKUP(2,1/(AI398:AS398<>""),AI398:AS398))) | IF(OR(F398="",AU398=""),"",IF(COUNT(AI398:AT398)=0,"",AU398-LOOKUP(2,1/(AI398:AT398<>""),AI398:AT398))) | IF(OR(F398="",AV398=""),"",IF(COUNT(AI398:AU398)=0,"",AV398-LOOKUP(2,1/(AI398:AU398<>""),AI398:AU398))) | IF(J398="","All_Provinces",IFERROR(VLOOKUP(J398,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K398="","All_Districts",IFERROR(VLOOKUP(K398,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F399="","",ROW()-3) | [18 empty] | IF(AQ399="","",AQ399) |  |  |  | IF(W399<>"",W399,IF(OR(T399="",V399=""),"",EDATE(T399,V399))) |  |  |  |  | IF(F399="","",IF(COUNT(AI399:AV399)=0,IF(AA399="","Not started",AA399),SUBSTITUTE(LOOKUP(2,1/(AI399:AV399<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F399="",COUNT(AI399:AV399)=0),"",TODAY()-LOOKUP(2,1/(AI399:AV399<>""),AI399:AV399)) | IF(OR(F399="",COUNT(AI399:AV399)<2),"",LOOKUP(2,1/(AI399:AV399<>""),AI399:AV399)-MIN(AI399:AV399)) | IF(OR(AD399="",AC399="Not started",AC399=""),"",IFERROR(AD399-IF(VLOOKUP(AC399,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC399,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F399="","",IF(OR(AA399="Cancelled",AC399="Cancelled"),"Cancelled",IF(OR(AC399="Completed / Handover",Y399<>"",Z399>=100),"Completed — on track",IF(O399="Not awarded",IF(U399="",IF(X399="","No planned date",IF(TODAY()>X399,"Behind — past planned date",IF(X399-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U399,"Behind — award date passed",IF(U399-TODAY()<=30,"At risk — close to off track","On track"))),IF(X399="","No planned date",IF(AND(TODAY()>X399,OR(Z399="",Z399<100)),"Behind — past end date",IF(AND(T399<>"",X399<>"",Z399<>"",(Z399<100),((TODAY()-T399)/MAX(X399-T399,1)*100)-Z399>15),"Behind — progress lag",IF(AND(X399-TODAY()<=30,X399-TODAY()>=0,OR(Z399="",Z399<90)),"At risk — close to off track","On track")))))))) | IF(OR(F399="",AC399="Completed / Handover",AC399="Cancelled"),"",IF(O399="Not awarded",IF(U399<>"",U399-TODAY(),IF(X399="","",X399-TODAY())),IF(X399="","",X399-TODAY()))) | [14 empty] | IF(OR(F399="",AJ399=""),"",IF(COUNT(AI399:AI399)=0,"",AJ399-LOOKUP(2,1/(AI399:AI399<>""),AI399:AI399))) | IF(OR(F399="",AK399=""),"",IF(COUNT(AI399:AJ399)=0,"",AK399-LOOKUP(2,1/(AI399:AJ399<>""),AI399:AJ399))) | IF(OR(F399="",AL399=""),"",IF(COUNT(AI399:AK399)=0,"",AL399-LOOKUP(2,1/(AI399:AK399<>""),AI399:AK399))) | IF(OR(F399="",AM399=""),"",IF(COUNT(AI399:AL399)=0,"",AM399-LOOKUP(2,1/(AI399:AL399<>""),AI399:AL399))) | IF(OR(F399="",AN399=""),"",IF(COUNT(AI399:AM399)=0,"",AN399-LOOKUP(2,1/(AI399:AM399<>""),AI399:AM399))) | IF(OR(F399="",AO399=""),"",IF(COUNT(AI399:AN399)=0,"",AO399-LOOKUP(2,1/(AI399:AN399<>""),AI399:AN399))) | IF(OR(F399="",AP399=""),"",IF(COUNT(AI399:AO399)=0,"",AP399-LOOKUP(2,1/(AI399:AO399<>""),AI399:AO399))) | IF(OR(F399="",AQ399=""),"",IF(COUNT(AI399:AP399)=0,"",AQ399-LOOKUP(2,1/(AI399:AP399<>""),AI399:AP399))) | IF(OR(F399="",AR399=""),"",IF(COUNT(AI399:AQ399)=0,"",AR399-LOOKUP(2,1/(AI399:AQ399<>""),AI399:AQ399))) | IF(OR(F399="",AS399=""),"",IF(COUNT(AI399:AR399)=0,"",AS399-LOOKUP(2,1/(AI399:AR399<>""),AI399:AR399))) | IF(OR(F399="",AT399=""),"",IF(COUNT(AI399:AS399)=0,"",AT399-LOOKUP(2,1/(AI399:AS399<>""),AI399:AS399))) | IF(OR(F399="",AU399=""),"",IF(COUNT(AI399:AT399)=0,"",AU399-LOOKUP(2,1/(AI399:AT399<>""),AI399:AT399))) | IF(OR(F399="",AV399=""),"",IF(COUNT(AI399:AU399)=0,"",AV399-LOOKUP(2,1/(AI399:AU399<>""),AI399:AU399))) | IF(J399="","All_Provinces",IFERROR(VLOOKUP(J399,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K399="","All_Districts",IFERROR(VLOOKUP(K399,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F400="","",ROW()-3) | [18 empty] | IF(AQ400="","",AQ400) |  |  |  | IF(W400<>"",W400,IF(OR(T400="",V400=""),"",EDATE(T400,V400))) |  |  |  |  | IF(F400="","",IF(COUNT(AI400:AV400)=0,IF(AA400="","Not started",AA400),SUBSTITUTE(LOOKUP(2,1/(AI400:AV400<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F400="",COUNT(AI400:AV400)=0),"",TODAY()-LOOKUP(2,1/(AI400:AV400<>""),AI400:AV400)) | IF(OR(F400="",COUNT(AI400:AV400)<2),"",LOOKUP(2,1/(AI400:AV400<>""),AI400:AV400)-MIN(AI400:AV400)) | IF(OR(AD400="",AC400="Not started",AC400=""),"",IFERROR(AD400-IF(VLOOKUP(AC400,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC400,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F400="","",IF(OR(AA400="Cancelled",AC400="Cancelled"),"Cancelled",IF(OR(AC400="Completed / Handover",Y400<>"",Z400>=100),"Completed — on track",IF(O400="Not awarded",IF(U400="",IF(X400="","No planned date",IF(TODAY()>X400,"Behind — past planned date",IF(X400-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U400,"Behind — award date passed",IF(U400-TODAY()<=30,"At risk — close to off track","On track"))),IF(X400="","No planned date",IF(AND(TODAY()>X400,OR(Z400="",Z400<100)),"Behind — past end date",IF(AND(T400<>"",X400<>"",Z400<>"",(Z400<100),((TODAY()-T400)/MAX(X400-T400,1)*100)-Z400>15),"Behind — progress lag",IF(AND(X400-TODAY()<=30,X400-TODAY()>=0,OR(Z400="",Z400<90)),"At risk — close to off track","On track")))))))) | IF(OR(F400="",AC400="Completed / Handover",AC400="Cancelled"),"",IF(O400="Not awarded",IF(U400<>"",U400-TODAY(),IF(X400="","",X400-TODAY())),IF(X400="","",X400-TODAY()))) | [14 empty] | IF(OR(F400="",AJ400=""),"",IF(COUNT(AI400:AI400)=0,"",AJ400-LOOKUP(2,1/(AI400:AI400<>""),AI400:AI400))) | IF(OR(F400="",AK400=""),"",IF(COUNT(AI400:AJ400)=0,"",AK400-LOOKUP(2,1/(AI400:AJ400<>""),AI400:AJ400))) | IF(OR(F400="",AL400=""),"",IF(COUNT(AI400:AK400)=0,"",AL400-LOOKUP(2,1/(AI400:AK400<>""),AI400:AK400))) | IF(OR(F400="",AM400=""),"",IF(COUNT(AI400:AL400)=0,"",AM400-LOOKUP(2,1/(AI400:AL400<>""),AI400:AL400))) | IF(OR(F400="",AN400=""),"",IF(COUNT(AI400:AM400)=0,"",AN400-LOOKUP(2,1/(AI400:AM400<>""),AI400:AM400))) | IF(OR(F400="",AO400=""),"",IF(COUNT(AI400:AN400)=0,"",AO400-LOOKUP(2,1/(AI400:AN400<>""),AI400:AN400))) | IF(OR(F400="",AP400=""),"",IF(COUNT(AI400:AO400)=0,"",AP400-LOOKUP(2,1/(AI400:AO400<>""),AI400:AO400))) | IF(OR(F400="",AQ400=""),"",IF(COUNT(AI400:AP400)=0,"",AQ400-LOOKUP(2,1/(AI400:AP400<>""),AI400:AP400))) | IF(OR(F400="",AR400=""),"",IF(COUNT(AI400:AQ400)=0,"",AR400-LOOKUP(2,1/(AI400:AQ400<>""),AI400:AQ400))) | IF(OR(F400="",AS400=""),"",IF(COUNT(AI400:AR400)=0,"",AS400-LOOKUP(2,1/(AI400:AR400<>""),AI400:AR400))) | IF(OR(F400="",AT400=""),"",IF(COUNT(AI400:AS400)=0,"",AT400-LOOKUP(2,1/(AI400:AS400<>""),AI400:AS400))) | IF(OR(F400="",AU400=""),"",IF(COUNT(AI400:AT400)=0,"",AU400-LOOKUP(2,1/(AI400:AT400<>""),AI400:AT400))) | IF(OR(F400="",AV400=""),"",IF(COUNT(AI400:AU400)=0,"",AV400-LOOKUP(2,1/(AI400:AU400<>""),AI400:AU400))) | IF(J400="","All_Provinces",IFERROR(VLOOKUP(J400,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K400="","All_Districts",IFERROR(VLOOKUP(K400,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F401="","",ROW()-3) | [18 empty] | IF(AQ401="","",AQ401) |  |  |  | IF(W401<>"",W401,IF(OR(T401="",V401=""),"",EDATE(T401,V401))) |  |  |  |  | IF(F401="","",IF(COUNT(AI401:AV401)=0,IF(AA401="","Not started",AA401),SUBSTITUTE(LOOKUP(2,1/(AI401:AV401<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F401="",COUNT(AI401:AV401)=0),"",TODAY()-LOOKUP(2,1/(AI401:AV401<>""),AI401:AV401)) | IF(OR(F401="",COUNT(AI401:AV401)<2),"",LOOKUP(2,1/(AI401:AV401<>""),AI401:AV401)-MIN(AI401:AV401)) | IF(OR(AD401="",AC401="Not started",AC401=""),"",IFERROR(AD401-IF(VLOOKUP(AC401,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC401,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F401="","",IF(OR(AA401="Cancelled",AC401="Cancelled"),"Cancelled",IF(OR(AC401="Completed / Handover",Y401<>"",Z401>=100),"Completed — on track",IF(O401="Not awarded",IF(U401="",IF(X401="","No planned date",IF(TODAY()>X401,"Behind — past planned date",IF(X401-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U401,"Behind — award date passed",IF(U401-TODAY()<=30,"At risk — close to off track","On track"))),IF(X401="","No planned date",IF(AND(TODAY()>X401,OR(Z401="",Z401<100)),"Behind — past end date",IF(AND(T401<>"",X401<>"",Z401<>"",(Z401<100),((TODAY()-T401)/MAX(X401-T401,1)*100)-Z401>15),"Behind — progress lag",IF(AND(X401-TODAY()<=30,X401-TODAY()>=0,OR(Z401="",Z401<90)),"At risk — close to off track","On track")))))))) | IF(OR(F401="",AC401="Completed / Handover",AC401="Cancelled"),"",IF(O401="Not awarded",IF(U401<>"",U401-TODAY(),IF(X401="","",X401-TODAY())),IF(X401="","",X401-TODAY()))) | [14 empty] | IF(OR(F401="",AJ401=""),"",IF(COUNT(AI401:AI401)=0,"",AJ401-LOOKUP(2,1/(AI401:AI401<>""),AI401:AI401))) | IF(OR(F401="",AK401=""),"",IF(COUNT(AI401:AJ401)=0,"",AK401-LOOKUP(2,1/(AI401:AJ401<>""),AI401:AJ401))) | IF(OR(F401="",AL401=""),"",IF(COUNT(AI401:AK401)=0,"",AL401-LOOKUP(2,1/(AI401:AK401<>""),AI401:AK401))) | IF(OR(F401="",AM401=""),"",IF(COUNT(AI401:AL401)=0,"",AM401-LOOKUP(2,1/(AI401:AL401<>""),AI401:AL401))) | IF(OR(F401="",AN401=""),"",IF(COUNT(AI401:AM401)=0,"",AN401-LOOKUP(2,1/(AI401:AM401<>""),AI401:AM401))) | IF(OR(F401="",AO401=""),"",IF(COUNT(AI401:AN401)=0,"",AO401-LOOKUP(2,1/(AI401:AN401<>""),AI401:AN401))) | IF(OR(F401="",AP401=""),"",IF(COUNT(AI401:AO401)=0,"",AP401-LOOKUP(2,1/(AI401:AO401<>""),AI401:AO401))) | IF(OR(F401="",AQ401=""),"",IF(COUNT(AI401:AP401)=0,"",AQ401-LOOKUP(2,1/(AI401:AP401<>""),AI401:AP401))) | IF(OR(F401="",AR401=""),"",IF(COUNT(AI401:AQ401)=0,"",AR401-LOOKUP(2,1/(AI401:AQ401<>""),AI401:AQ401))) | IF(OR(F401="",AS401=""),"",IF(COUNT(AI401:AR401)=0,"",AS401-LOOKUP(2,1/(AI401:AR401<>""),AI401:AR401))) | IF(OR(F401="",AT401=""),"",IF(COUNT(AI401:AS401)=0,"",AT401-LOOKUP(2,1/(AI401:AS401<>""),AI401:AS401))) | IF(OR(F401="",AU401=""),"",IF(COUNT(AI401:AT401)=0,"",AU401-LOOKUP(2,1/(AI401:AT401<>""),AI401:AT401))) | IF(OR(F401="",AV401=""),"",IF(COUNT(AI401:AU401)=0,"",AV401-LOOKUP(2,1/(AI401:AU401<>""),AI401:AU401))) | IF(J401="","All_Provinces",IFERROR(VLOOKUP(J401,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K401="","All_Districts",IFERROR(VLOOKUP(K401,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F402="","",ROW()-3) | [18 empty] | IF(AQ402="","",AQ402) |  |  |  | IF(W402<>"",W402,IF(OR(T402="",V402=""),"",EDATE(T402,V402))) |  |  |  |  | IF(F402="","",IF(COUNT(AI402:AV402)=0,IF(AA402="","Not started",AA402),SUBSTITUTE(LOOKUP(2,1/(AI402:AV402<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F402="",COUNT(AI402:AV402)=0),"",TODAY()-LOOKUP(2,1/(AI402:AV402<>""),AI402:AV402)) | IF(OR(F402="",COUNT(AI402:AV402)<2),"",LOOKUP(2,1/(AI402:AV402<>""),AI402:AV402)-MIN(AI402:AV402)) | IF(OR(AD402="",AC402="Not started",AC402=""),"",IFERROR(AD402-IF(VLOOKUP(AC402,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC402,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F402="","",IF(OR(AA402="Cancelled",AC402="Cancelled"),"Cancelled",IF(OR(AC402="Completed / Handover",Y402<>"",Z402>=100),"Completed — on track",IF(O402="Not awarded",IF(U402="",IF(X402="","No planned date",IF(TODAY()>X402,"Behind — past planned date",IF(X402-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U402,"Behind — award date passed",IF(U402-TODAY()<=30,"At risk — close to off track","On track"))),IF(X402="","No planned date",IF(AND(TODAY()>X402,OR(Z402="",Z402<100)),"Behind — past end date",IF(AND(T402<>"",X402<>"",Z402<>"",(Z402<100),((TODAY()-T402)/MAX(X402-T402,1)*100)-Z402>15),"Behind — progress lag",IF(AND(X402-TODAY()<=30,X402-TODAY()>=0,OR(Z402="",Z402<90)),"At risk — close to off track","On track")))))))) | IF(OR(F402="",AC402="Completed / Handover",AC402="Cancelled"),"",IF(O402="Not awarded",IF(U402<>"",U402-TODAY(),IF(X402="","",X402-TODAY())),IF(X402="","",X402-TODAY()))) | [14 empty] | IF(OR(F402="",AJ402=""),"",IF(COUNT(AI402:AI402)=0,"",AJ402-LOOKUP(2,1/(AI402:AI402<>""),AI402:AI402))) | IF(OR(F402="",AK402=""),"",IF(COUNT(AI402:AJ402)=0,"",AK402-LOOKUP(2,1/(AI402:AJ402<>""),AI402:AJ402))) | IF(OR(F402="",AL402=""),"",IF(COUNT(AI402:AK402)=0,"",AL402-LOOKUP(2,1/(AI402:AK402<>""),AI402:AK402))) | IF(OR(F402="",AM402=""),"",IF(COUNT(AI402:AL402)=0,"",AM402-LOOKUP(2,1/(AI402:AL402<>""),AI402:AL402))) | IF(OR(F402="",AN402=""),"",IF(COUNT(AI402:AM402)=0,"",AN402-LOOKUP(2,1/(AI402:AM402<>""),AI402:AM402))) | IF(OR(F402="",AO402=""),"",IF(COUNT(AI402:AN402)=0,"",AO402-LOOKUP(2,1/(AI402:AN402<>""),AI402:AN402))) | IF(OR(F402="",AP402=""),"",IF(COUNT(AI402:AO402)=0,"",AP402-LOOKUP(2,1/(AI402:AO402<>""),AI402:AO402))) | IF(OR(F402="",AQ402=""),"",IF(COUNT(AI402:AP402)=0,"",AQ402-LOOKUP(2,1/(AI402:AP402<>""),AI402:AP402))) | IF(OR(F402="",AR402=""),"",IF(COUNT(AI402:AQ402)=0,"",AR402-LOOKUP(2,1/(AI402:AQ402<>""),AI402:AQ402))) | IF(OR(F402="",AS402=""),"",IF(COUNT(AI402:AR402)=0,"",AS402-LOOKUP(2,1/(AI402:AR402<>""),AI402:AR402))) | IF(OR(F402="",AT402=""),"",IF(COUNT(AI402:AS402)=0,"",AT402-LOOKUP(2,1/(AI402:AS402<>""),AI402:AS402))) | IF(OR(F402="",AU402=""),"",IF(COUNT(AI402:AT402)=0,"",AU402-LOOKUP(2,1/(AI402:AT402<>""),AI402:AT402))) | IF(OR(F402="",AV402=""),"",IF(COUNT(AI402:AU402)=0,"",AV402-LOOKUP(2,1/(AI402:AU402<>""),AI402:AU402))) | IF(J402="","All_Provinces",IFERROR(VLOOKUP(J402,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K402="","All_Districts",IFERROR(VLOOKUP(K402,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F403="","",ROW()-3) | [18 empty] | IF(AQ403="","",AQ403) |  |  |  | IF(W403<>"",W403,IF(OR(T403="",V403=""),"",EDATE(T403,V403))) |  |  |  |  | IF(F403="","",IF(COUNT(AI403:AV403)=0,IF(AA403="","Not started",AA403),SUBSTITUTE(LOOKUP(2,1/(AI403:AV403<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F403="",COUNT(AI403:AV403)=0),"",TODAY()-LOOKUP(2,1/(AI403:AV403<>""),AI403:AV403)) | IF(OR(F403="",COUNT(AI403:AV403)<2),"",LOOKUP(2,1/(AI403:AV403<>""),AI403:AV403)-MIN(AI403:AV403)) | IF(OR(AD403="",AC403="Not started",AC403=""),"",IFERROR(AD403-IF(VLOOKUP(AC403,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC403,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F403="","",IF(OR(AA403="Cancelled",AC403="Cancelled"),"Cancelled",IF(OR(AC403="Completed / Handover",Y403<>"",Z403>=100),"Completed — on track",IF(O403="Not awarded",IF(U403="",IF(X403="","No planned date",IF(TODAY()>X403,"Behind — past planned date",IF(X403-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U403,"Behind — award date passed",IF(U403-TODAY()<=30,"At risk — close to off track","On track"))),IF(X403="","No planned date",IF(AND(TODAY()>X403,OR(Z403="",Z403<100)),"Behind — past end date",IF(AND(T403<>"",X403<>"",Z403<>"",(Z403<100),((TODAY()-T403)/MAX(X403-T403,1)*100)-Z403>15),"Behind — progress lag",IF(AND(X403-TODAY()<=30,X403-TODAY()>=0,OR(Z403="",Z403<90)),"At risk — close to off track","On track")))))))) | IF(OR(F403="",AC403="Completed / Handover",AC403="Cancelled"),"",IF(O403="Not awarded",IF(U403<>"",U403-TODAY(),IF(X403="","",X403-TODAY())),IF(X403="","",X403-TODAY()))) | [14 empty] | IF(OR(F403="",AJ403=""),"",IF(COUNT(AI403:AI403)=0,"",AJ403-LOOKUP(2,1/(AI403:AI403<>""),AI403:AI403))) | IF(OR(F403="",AK403=""),"",IF(COUNT(AI403:AJ403)=0,"",AK403-LOOKUP(2,1/(AI403:AJ403<>""),AI403:AJ403))) | IF(OR(F403="",AL403=""),"",IF(COUNT(AI403:AK403)=0,"",AL403-LOOKUP(2,1/(AI403:AK403<>""),AI403:AK403))) | IF(OR(F403="",AM403=""),"",IF(COUNT(AI403:AL403)=0,"",AM403-LOOKUP(2,1/(AI403:AL403<>""),AI403:AL403))) | IF(OR(F403="",AN403=""),"",IF(COUNT(AI403:AM403)=0,"",AN403-LOOKUP(2,1/(AI403:AM403<>""),AI403:AM403))) | IF(OR(F403="",AO403=""),"",IF(COUNT(AI403:AN403)=0,"",AO403-LOOKUP(2,1/(AI403:AN403<>""),AI403:AN403))) | IF(OR(F403="",AP403=""),"",IF(COUNT(AI403:AO403)=0,"",AP403-LOOKUP(2,1/(AI403:AO403<>""),AI403:AO403))) | IF(OR(F403="",AQ403=""),"",IF(COUNT(AI403:AP403)=0,"",AQ403-LOOKUP(2,1/(AI403:AP403<>""),AI403:AP403))) | IF(OR(F403="",AR403=""),"",IF(COUNT(AI403:AQ403)=0,"",AR403-LOOKUP(2,1/(AI403:AQ403<>""),AI403:AQ403))) | IF(OR(F403="",AS403=""),"",IF(COUNT(AI403:AR403)=0,"",AS403-LOOKUP(2,1/(AI403:AR403<>""),AI403:AR403))) | IF(OR(F403="",AT403=""),"",IF(COUNT(AI403:AS403)=0,"",AT403-LOOKUP(2,1/(AI403:AS403<>""),AI403:AS403))) | IF(OR(F403="",AU403=""),"",IF(COUNT(AI403:AT403)=0,"",AU403-LOOKUP(2,1/(AI403:AT403<>""),AI403:AT403))) | IF(OR(F403="",AV403=""),"",IF(COUNT(AI403:AU403)=0,"",AV403-LOOKUP(2,1/(AI403:AU403<>""),AI403:AU403))) | IF(J403="","All_Provinces",IFERROR(VLOOKUP(J403,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K403="","All_Districts",IFERROR(VLOOKUP(K403,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F404="","",ROW()-3) | [18 empty] | IF(AQ404="","",AQ404) |  |  |  | IF(W404<>"",W404,IF(OR(T404="",V404=""),"",EDATE(T404,V404))) |  |  |  |  | IF(F404="","",IF(COUNT(AI404:AV404)=0,IF(AA404="","Not started",AA404),SUBSTITUTE(LOOKUP(2,1/(AI404:AV404<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F404="",COUNT(AI404:AV404)=0),"",TODAY()-LOOKUP(2,1/(AI404:AV404<>""),AI404:AV404)) | IF(OR(F404="",COUNT(AI404:AV404)<2),"",LOOKUP(2,1/(AI404:AV404<>""),AI404:AV404)-MIN(AI404:AV404)) | IF(OR(AD404="",AC404="Not started",AC404=""),"",IFERROR(AD404-IF(VLOOKUP(AC404,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC404,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F404="","",IF(OR(AA404="Cancelled",AC404="Cancelled"),"Cancelled",IF(OR(AC404="Completed / Handover",Y404<>"",Z404>=100),"Completed — on track",IF(O404="Not awarded",IF(U404="",IF(X404="","No planned date",IF(TODAY()>X404,"Behind — past planned date",IF(X404-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U404,"Behind — award date passed",IF(U404-TODAY()<=30,"At risk — close to off track","On track"))),IF(X404="","No planned date",IF(AND(TODAY()>X404,OR(Z404="",Z404<100)),"Behind — past end date",IF(AND(T404<>"",X404<>"",Z404<>"",(Z404<100),((TODAY()-T404)/MAX(X404-T404,1)*100)-Z404>15),"Behind — progress lag",IF(AND(X404-TODAY()<=30,X404-TODAY()>=0,OR(Z404="",Z404<90)),"At risk — close to off track","On track")))))))) | IF(OR(F404="",AC404="Completed / Handover",AC404="Cancelled"),"",IF(O404="Not awarded",IF(U404<>"",U404-TODAY(),IF(X404="","",X404-TODAY())),IF(X404="","",X404-TODAY()))) | [14 empty] | IF(OR(F404="",AJ404=""),"",IF(COUNT(AI404:AI404)=0,"",AJ404-LOOKUP(2,1/(AI404:AI404<>""),AI404:AI404))) | IF(OR(F404="",AK404=""),"",IF(COUNT(AI404:AJ404)=0,"",AK404-LOOKUP(2,1/(AI404:AJ404<>""),AI404:AJ404))) | IF(OR(F404="",AL404=""),"",IF(COUNT(AI404:AK404)=0,"",AL404-LOOKUP(2,1/(AI404:AK404<>""),AI404:AK404))) | IF(OR(F404="",AM404=""),"",IF(COUNT(AI404:AL404)=0,"",AM404-LOOKUP(2,1/(AI404:AL404<>""),AI404:AL404))) | IF(OR(F404="",AN404=""),"",IF(COUNT(AI404:AM404)=0,"",AN404-LOOKUP(2,1/(AI404:AM404<>""),AI404:AM404))) | IF(OR(F404="",AO404=""),"",IF(COUNT(AI404:AN404)=0,"",AO404-LOOKUP(2,1/(AI404:AN404<>""),AI404:AN404))) | IF(OR(F404="",AP404=""),"",IF(COUNT(AI404:AO404)=0,"",AP404-LOOKUP(2,1/(AI404:AO404<>""),AI404:AO404))) | IF(OR(F404="",AQ404=""),"",IF(COUNT(AI404:AP404)=0,"",AQ404-LOOKUP(2,1/(AI404:AP404<>""),AI404:AP404))) | IF(OR(F404="",AR404=""),"",IF(COUNT(AI404:AQ404)=0,"",AR404-LOOKUP(2,1/(AI404:AQ404<>""),AI404:AQ404))) | IF(OR(F404="",AS404=""),"",IF(COUNT(AI404:AR404)=0,"",AS404-LOOKUP(2,1/(AI404:AR404<>""),AI404:AR404))) | IF(OR(F404="",AT404=""),"",IF(COUNT(AI404:AS404)=0,"",AT404-LOOKUP(2,1/(AI404:AS404<>""),AI404:AS404))) | IF(OR(F404="",AU404=""),"",IF(COUNT(AI404:AT404)=0,"",AU404-LOOKUP(2,1/(AI404:AT404<>""),AI404:AT404))) | IF(OR(F404="",AV404=""),"",IF(COUNT(AI404:AU404)=0,"",AV404-LOOKUP(2,1/(AI404:AU404<>""),AI404:AU404))) | IF(J404="","All_Provinces",IFERROR(VLOOKUP(J404,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K404="","All_Districts",IFERROR(VLOOKUP(K404,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F405="","",ROW()-3) | [18 empty] | IF(AQ405="","",AQ405) |  |  |  | IF(W405<>"",W405,IF(OR(T405="",V405=""),"",EDATE(T405,V405))) |  |  |  |  | IF(F405="","",IF(COUNT(AI405:AV405)=0,IF(AA405="","Not started",AA405),SUBSTITUTE(LOOKUP(2,1/(AI405:AV405<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F405="",COUNT(AI405:AV405)=0),"",TODAY()-LOOKUP(2,1/(AI405:AV405<>""),AI405:AV405)) | IF(OR(F405="",COUNT(AI405:AV405)<2),"",LOOKUP(2,1/(AI405:AV405<>""),AI405:AV405)-MIN(AI405:AV405)) | IF(OR(AD405="",AC405="Not started",AC405=""),"",IFERROR(AD405-IF(VLOOKUP(AC405,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC405,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F405="","",IF(OR(AA405="Cancelled",AC405="Cancelled"),"Cancelled",IF(OR(AC405="Completed / Handover",Y405<>"",Z405>=100),"Completed — on track",IF(O405="Not awarded",IF(U405="",IF(X405="","No planned date",IF(TODAY()>X405,"Behind — past planned date",IF(X405-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U405,"Behind — award date passed",IF(U405-TODAY()<=30,"At risk — close to off track","On track"))),IF(X405="","No planned date",IF(AND(TODAY()>X405,OR(Z405="",Z405<100)),"Behind — past end date",IF(AND(T405<>"",X405<>"",Z405<>"",(Z405<100),((TODAY()-T405)/MAX(X405-T405,1)*100)-Z405>15),"Behind — progress lag",IF(AND(X405-TODAY()<=30,X405-TODAY()>=0,OR(Z405="",Z405<90)),"At risk — close to off track","On track")))))))) | IF(OR(F405="",AC405="Completed / Handover",AC405="Cancelled"),"",IF(O405="Not awarded",IF(U405<>"",U405-TODAY(),IF(X405="","",X405-TODAY())),IF(X405="","",X405-TODAY()))) | [14 empty] | IF(OR(F405="",AJ405=""),"",IF(COUNT(AI405:AI405)=0,"",AJ405-LOOKUP(2,1/(AI405:AI405<>""),AI405:AI405))) | IF(OR(F405="",AK405=""),"",IF(COUNT(AI405:AJ405)=0,"",AK405-LOOKUP(2,1/(AI405:AJ405<>""),AI405:AJ405))) | IF(OR(F405="",AL405=""),"",IF(COUNT(AI405:AK405)=0,"",AL405-LOOKUP(2,1/(AI405:AK405<>""),AI405:AK405))) | IF(OR(F405="",AM405=""),"",IF(COUNT(AI405:AL405)=0,"",AM405-LOOKUP(2,1/(AI405:AL405<>""),AI405:AL405))) | IF(OR(F405="",AN405=""),"",IF(COUNT(AI405:AM405)=0,"",AN405-LOOKUP(2,1/(AI405:AM405<>""),AI405:AM405))) | IF(OR(F405="",AO405=""),"",IF(COUNT(AI405:AN405)=0,"",AO405-LOOKUP(2,1/(AI405:AN405<>""),AI405:AN405))) | IF(OR(F405="",AP405=""),"",IF(COUNT(AI405:AO405)=0,"",AP405-LOOKUP(2,1/(AI405:AO405<>""),AI405:AO405))) | IF(OR(F405="",AQ405=""),"",IF(COUNT(AI405:AP405)=0,"",AQ405-LOOKUP(2,1/(AI405:AP405<>""),AI405:AP405))) | IF(OR(F405="",AR405=""),"",IF(COUNT(AI405:AQ405)=0,"",AR405-LOOKUP(2,1/(AI405:AQ405<>""),AI405:AQ405))) | IF(OR(F405="",AS405=""),"",IF(COUNT(AI405:AR405)=0,"",AS405-LOOKUP(2,1/(AI405:AR405<>""),AI405:AR405))) | IF(OR(F405="",AT405=""),"",IF(COUNT(AI405:AS405)=0,"",AT405-LOOKUP(2,1/(AI405:AS405<>""),AI405:AS405))) | IF(OR(F405="",AU405=""),"",IF(COUNT(AI405:AT405)=0,"",AU405-LOOKUP(2,1/(AI405:AT405<>""),AI405:AT405))) | IF(OR(F405="",AV405=""),"",IF(COUNT(AI405:AU405)=0,"",AV405-LOOKUP(2,1/(AI405:AU405<>""),AI405:AU405))) | IF(J405="","All_Provinces",IFERROR(VLOOKUP(J405,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K405="","All_Districts",IFERROR(VLOOKUP(K405,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F406="","",ROW()-3) | [18 empty] | IF(AQ406="","",AQ406) |  |  |  | IF(W406<>"",W406,IF(OR(T406="",V406=""),"",EDATE(T406,V406))) |  |  |  |  | IF(F406="","",IF(COUNT(AI406:AV406)=0,IF(AA406="","Not started",AA406),SUBSTITUTE(LOOKUP(2,1/(AI406:AV406<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F406="",COUNT(AI406:AV406)=0),"",TODAY()-LOOKUP(2,1/(AI406:AV406<>""),AI406:AV406)) | IF(OR(F406="",COUNT(AI406:AV406)<2),"",LOOKUP(2,1/(AI406:AV406<>""),AI406:AV406)-MIN(AI406:AV406)) | IF(OR(AD406="",AC406="Not started",AC406=""),"",IFERROR(AD406-IF(VLOOKUP(AC406,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC406,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F406="","",IF(OR(AA406="Cancelled",AC406="Cancelled"),"Cancelled",IF(OR(AC406="Completed / Handover",Y406<>"",Z406>=100),"Completed — on track",IF(O406="Not awarded",IF(U406="",IF(X406="","No planned date",IF(TODAY()>X406,"Behind — past planned date",IF(X406-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U406,"Behind — award date passed",IF(U406-TODAY()<=30,"At risk — close to off track","On track"))),IF(X406="","No planned date",IF(AND(TODAY()>X406,OR(Z406="",Z406<100)),"Behind — past end date",IF(AND(T406<>"",X406<>"",Z406<>"",(Z406<100),((TODAY()-T406)/MAX(X406-T406,1)*100)-Z406>15),"Behind — progress lag",IF(AND(X406-TODAY()<=30,X406-TODAY()>=0,OR(Z406="",Z406<90)),"At risk — close to off track","On track")))))))) | IF(OR(F406="",AC406="Completed / Handover",AC406="Cancelled"),"",IF(O406="Not awarded",IF(U406<>"",U406-TODAY(),IF(X406="","",X406-TODAY())),IF(X406="","",X406-TODAY()))) | [14 empty] | IF(OR(F406="",AJ406=""),"",IF(COUNT(AI406:AI406)=0,"",AJ406-LOOKUP(2,1/(AI406:AI406<>""),AI406:AI406))) | IF(OR(F406="",AK406=""),"",IF(COUNT(AI406:AJ406)=0,"",AK406-LOOKUP(2,1/(AI406:AJ406<>""),AI406:AJ406))) | IF(OR(F406="",AL406=""),"",IF(COUNT(AI406:AK406)=0,"",AL406-LOOKUP(2,1/(AI406:AK406<>""),AI406:AK406))) | IF(OR(F406="",AM406=""),"",IF(COUNT(AI406:AL406)=0,"",AM406-LOOKUP(2,1/(AI406:AL406<>""),AI406:AL406))) | IF(OR(F406="",AN406=""),"",IF(COUNT(AI406:AM406)=0,"",AN406-LOOKUP(2,1/(AI406:AM406<>""),AI406:AM406))) | IF(OR(F406="",AO406=""),"",IF(COUNT(AI406:AN406)=0,"",AO406-LOOKUP(2,1/(AI406:AN406<>""),AI406:AN406))) | IF(OR(F406="",AP406=""),"",IF(COUNT(AI406:AO406)=0,"",AP406-LOOKUP(2,1/(AI406:AO406<>""),AI406:AO406))) | IF(OR(F406="",AQ406=""),"",IF(COUNT(AI406:AP406)=0,"",AQ406-LOOKUP(2,1/(AI406:AP406<>""),AI406:AP406))) | IF(OR(F406="",AR406=""),"",IF(COUNT(AI406:AQ406)=0,"",AR406-LOOKUP(2,1/(AI406:AQ406<>""),AI406:AQ406))) | IF(OR(F406="",AS406=""),"",IF(COUNT(AI406:AR406)=0,"",AS406-LOOKUP(2,1/(AI406:AR406<>""),AI406:AR406))) | IF(OR(F406="",AT406=""),"",IF(COUNT(AI406:AS406)=0,"",AT406-LOOKUP(2,1/(AI406:AS406<>""),AI406:AS406))) | IF(OR(F406="",AU406=""),"",IF(COUNT(AI406:AT406)=0,"",AU406-LOOKUP(2,1/(AI406:AT406<>""),AI406:AT406))) | IF(OR(F406="",AV406=""),"",IF(COUNT(AI406:AU406)=0,"",AV406-LOOKUP(2,1/(AI406:AU406<>""),AI406:AU406))) | IF(J406="","All_Provinces",IFERROR(VLOOKUP(J406,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K406="","All_Districts",IFERROR(VLOOKUP(K406,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F407="","",ROW()-3) | [18 empty] | IF(AQ407="","",AQ407) |  |  |  | IF(W407<>"",W407,IF(OR(T407="",V407=""),"",EDATE(T407,V407))) |  |  |  |  | IF(F407="","",IF(COUNT(AI407:AV407)=0,IF(AA407="","Not started",AA407),SUBSTITUTE(LOOKUP(2,1/(AI407:AV407<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F407="",COUNT(AI407:AV407)=0),"",TODAY()-LOOKUP(2,1/(AI407:AV407<>""),AI407:AV407)) | IF(OR(F407="",COUNT(AI407:AV407)<2),"",LOOKUP(2,1/(AI407:AV407<>""),AI407:AV407)-MIN(AI407:AV407)) | IF(OR(AD407="",AC407="Not started",AC407=""),"",IFERROR(AD407-IF(VLOOKUP(AC407,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC407,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F407="","",IF(OR(AA407="Cancelled",AC407="Cancelled"),"Cancelled",IF(OR(AC407="Completed / Handover",Y407<>"",Z407>=100),"Completed — on track",IF(O407="Not awarded",IF(U407="",IF(X407="","No planned date",IF(TODAY()>X407,"Behind — past planned date",IF(X407-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U407,"Behind — award date passed",IF(U407-TODAY()<=30,"At risk — close to off track","On track"))),IF(X407="","No planned date",IF(AND(TODAY()>X407,OR(Z407="",Z407<100)),"Behind — past end date",IF(AND(T407<>"",X407<>"",Z407<>"",(Z407<100),((TODAY()-T407)/MAX(X407-T407,1)*100)-Z407>15),"Behind — progress lag",IF(AND(X407-TODAY()<=30,X407-TODAY()>=0,OR(Z407="",Z407<90)),"At risk — close to off track","On track")))))))) | IF(OR(F407="",AC407="Completed / Handover",AC407="Cancelled"),"",IF(O407="Not awarded",IF(U407<>"",U407-TODAY(),IF(X407="","",X407-TODAY())),IF(X407="","",X407-TODAY()))) | [14 empty] | IF(OR(F407="",AJ407=""),"",IF(COUNT(AI407:AI407)=0,"",AJ407-LOOKUP(2,1/(AI407:AI407<>""),AI407:AI407))) | IF(OR(F407="",AK407=""),"",IF(COUNT(AI407:AJ407)=0,"",AK407-LOOKUP(2,1/(AI407:AJ407<>""),AI407:AJ407))) | IF(OR(F407="",AL407=""),"",IF(COUNT(AI407:AK407)=0,"",AL407-LOOKUP(2,1/(AI407:AK407<>""),AI407:AK407))) | IF(OR(F407="",AM407=""),"",IF(COUNT(AI407:AL407)=0,"",AM407-LOOKUP(2,1/(AI407:AL407<>""),AI407:AL407))) | IF(OR(F407="",AN407=""),"",IF(COUNT(AI407:AM407)=0,"",AN407-LOOKUP(2,1/(AI407:AM407<>""),AI407:AM407))) | IF(OR(F407="",AO407=""),"",IF(COUNT(AI407:AN407)=0,"",AO407-LOOKUP(2,1/(AI407:AN407<>""),AI407:AN407))) | IF(OR(F407="",AP407=""),"",IF(COUNT(AI407:AO407)=0,"",AP407-LOOKUP(2,1/(AI407:AO407<>""),AI407:AO407))) | IF(OR(F407="",AQ407=""),"",IF(COUNT(AI407:AP407)=0,"",AQ407-LOOKUP(2,1/(AI407:AP407<>""),AI407:AP407))) | IF(OR(F407="",AR407=""),"",IF(COUNT(AI407:AQ407)=0,"",AR407-LOOKUP(2,1/(AI407:AQ407<>""),AI407:AQ407))) | IF(OR(F407="",AS407=""),"",IF(COUNT(AI407:AR407)=0,"",AS407-LOOKUP(2,1/(AI407:AR407<>""),AI407:AR407))) | IF(OR(F407="",AT407=""),"",IF(COUNT(AI407:AS407)=0,"",AT407-LOOKUP(2,1/(AI407:AS407<>""),AI407:AS407))) | IF(OR(F407="",AU407=""),"",IF(COUNT(AI407:AT407)=0,"",AU407-LOOKUP(2,1/(AI407:AT407<>""),AI407:AT407))) | IF(OR(F407="",AV407=""),"",IF(COUNT(AI407:AU407)=0,"",AV407-LOOKUP(2,1/(AI407:AU407<>""),AI407:AU407))) | IF(J407="","All_Provinces",IFERROR(VLOOKUP(J407,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K407="","All_Districts",IFERROR(VLOOKUP(K407,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F408="","",ROW()-3) | [18 empty] | IF(AQ408="","",AQ408) |  |  |  | IF(W408<>"",W408,IF(OR(T408="",V408=""),"",EDATE(T408,V408))) |  |  |  |  | IF(F408="","",IF(COUNT(AI408:AV408)=0,IF(AA408="","Not started",AA408),SUBSTITUTE(LOOKUP(2,1/(AI408:AV408<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F408="",COUNT(AI408:AV408)=0),"",TODAY()-LOOKUP(2,1/(AI408:AV408<>""),AI408:AV408)) | IF(OR(F408="",COUNT(AI408:AV408)<2),"",LOOKUP(2,1/(AI408:AV408<>""),AI408:AV408)-MIN(AI408:AV408)) | IF(OR(AD408="",AC408="Not started",AC408=""),"",IFERROR(AD408-IF(VLOOKUP(AC408,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC408,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F408="","",IF(OR(AA408="Cancelled",AC408="Cancelled"),"Cancelled",IF(OR(AC408="Completed / Handover",Y408<>"",Z408>=100),"Completed — on track",IF(O408="Not awarded",IF(U408="",IF(X408="","No planned date",IF(TODAY()>X408,"Behind — past planned date",IF(X408-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U408,"Behind — award date passed",IF(U408-TODAY()<=30,"At risk — close to off track","On track"))),IF(X408="","No planned date",IF(AND(TODAY()>X408,OR(Z408="",Z408<100)),"Behind — past end date",IF(AND(T408<>"",X408<>"",Z408<>"",(Z408<100),((TODAY()-T408)/MAX(X408-T408,1)*100)-Z408>15),"Behind — progress lag",IF(AND(X408-TODAY()<=30,X408-TODAY()>=0,OR(Z408="",Z408<90)),"At risk — close to off track","On track")))))))) | IF(OR(F408="",AC408="Completed / Handover",AC408="Cancelled"),"",IF(O408="Not awarded",IF(U408<>"",U408-TODAY(),IF(X408="","",X408-TODAY())),IF(X408="","",X408-TODAY()))) | [14 empty] | IF(OR(F408="",AJ408=""),"",IF(COUNT(AI408:AI408)=0,"",AJ408-LOOKUP(2,1/(AI408:AI408<>""),AI408:AI408))) | IF(OR(F408="",AK408=""),"",IF(COUNT(AI408:AJ408)=0,"",AK408-LOOKUP(2,1/(AI408:AJ408<>""),AI408:AJ408))) | IF(OR(F408="",AL408=""),"",IF(COUNT(AI408:AK408)=0,"",AL408-LOOKUP(2,1/(AI408:AK408<>""),AI408:AK408))) | IF(OR(F408="",AM408=""),"",IF(COUNT(AI408:AL408)=0,"",AM408-LOOKUP(2,1/(AI408:AL408<>""),AI408:AL408))) | IF(OR(F408="",AN408=""),"",IF(COUNT(AI408:AM408)=0,"",AN408-LOOKUP(2,1/(AI408:AM408<>""),AI408:AM408))) | IF(OR(F408="",AO408=""),"",IF(COUNT(AI408:AN408)=0,"",AO408-LOOKUP(2,1/(AI408:AN408<>""),AI408:AN408))) | IF(OR(F408="",AP408=""),"",IF(COUNT(AI408:AO408)=0,"",AP408-LOOKUP(2,1/(AI408:AO408<>""),AI408:AO408))) | IF(OR(F408="",AQ408=""),"",IF(COUNT(AI408:AP408)=0,"",AQ408-LOOKUP(2,1/(AI408:AP408<>""),AI408:AP408))) | IF(OR(F408="",AR408=""),"",IF(COUNT(AI408:AQ408)=0,"",AR408-LOOKUP(2,1/(AI408:AQ408<>""),AI408:AQ408))) | IF(OR(F408="",AS408=""),"",IF(COUNT(AI408:AR408)=0,"",AS408-LOOKUP(2,1/(AI408:AR408<>""),AI408:AR408))) | IF(OR(F408="",AT408=""),"",IF(COUNT(AI408:AS408)=0,"",AT408-LOOKUP(2,1/(AI408:AS408<>""),AI408:AS408))) | IF(OR(F408="",AU408=""),"",IF(COUNT(AI408:AT408)=0,"",AU408-LOOKUP(2,1/(AI408:AT408<>""),AI408:AT408))) | IF(OR(F408="",AV408=""),"",IF(COUNT(AI408:AU408)=0,"",AV408-LOOKUP(2,1/(AI408:AU408<>""),AI408:AU408))) | IF(J408="","All_Provinces",IFERROR(VLOOKUP(J408,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K408="","All_Districts",IFERROR(VLOOKUP(K408,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F409="","",ROW()-3) | [18 empty] | IF(AQ409="","",AQ409) |  |  |  | IF(W409<>"",W409,IF(OR(T409="",V409=""),"",EDATE(T409,V409))) |  |  |  |  | IF(F409="","",IF(COUNT(AI409:AV409)=0,IF(AA409="","Not started",AA409),SUBSTITUTE(LOOKUP(2,1/(AI409:AV409<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F409="",COUNT(AI409:AV409)=0),"",TODAY()-LOOKUP(2,1/(AI409:AV409<>""),AI409:AV409)) | IF(OR(F409="",COUNT(AI409:AV409)<2),"",LOOKUP(2,1/(AI409:AV409<>""),AI409:AV409)-MIN(AI409:AV409)) | IF(OR(AD409="",AC409="Not started",AC409=""),"",IFERROR(AD409-IF(VLOOKUP(AC409,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC409,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F409="","",IF(OR(AA409="Cancelled",AC409="Cancelled"),"Cancelled",IF(OR(AC409="Completed / Handover",Y409<>"",Z409>=100),"Completed — on track",IF(O409="Not awarded",IF(U409="",IF(X409="","No planned date",IF(TODAY()>X409,"Behind — past planned date",IF(X409-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U409,"Behind — award date passed",IF(U409-TODAY()<=30,"At risk — close to off track","On track"))),IF(X409="","No planned date",IF(AND(TODAY()>X409,OR(Z409="",Z409<100)),"Behind — past end date",IF(AND(T409<>"",X409<>"",Z409<>"",(Z409<100),((TODAY()-T409)/MAX(X409-T409,1)*100)-Z409>15),"Behind — progress lag",IF(AND(X409-TODAY()<=30,X409-TODAY()>=0,OR(Z409="",Z409<90)),"At risk — close to off track","On track")))))))) | IF(OR(F409="",AC409="Completed / Handover",AC409="Cancelled"),"",IF(O409="Not awarded",IF(U409<>"",U409-TODAY(),IF(X409="","",X409-TODAY())),IF(X409="","",X409-TODAY()))) | [14 empty] | IF(OR(F409="",AJ409=""),"",IF(COUNT(AI409:AI409)=0,"",AJ409-LOOKUP(2,1/(AI409:AI409<>""),AI409:AI409))) | IF(OR(F409="",AK409=""),"",IF(COUNT(AI409:AJ409)=0,"",AK409-LOOKUP(2,1/(AI409:AJ409<>""),AI409:AJ409))) | IF(OR(F409="",AL409=""),"",IF(COUNT(AI409:AK409)=0,"",AL409-LOOKUP(2,1/(AI409:AK409<>""),AI409:AK409))) | IF(OR(F409="",AM409=""),"",IF(COUNT(AI409:AL409)=0,"",AM409-LOOKUP(2,1/(AI409:AL409<>""),AI409:AL409))) | IF(OR(F409="",AN409=""),"",IF(COUNT(AI409:AM409)=0,"",AN409-LOOKUP(2,1/(AI409:AM409<>""),AI409:AM409))) | IF(OR(F409="",AO409=""),"",IF(COUNT(AI409:AN409)=0,"",AO409-LOOKUP(2,1/(AI409:AN409<>""),AI409:AN409))) | IF(OR(F409="",AP409=""),"",IF(COUNT(AI409:AO409)=0,"",AP409-LOOKUP(2,1/(AI409:AO409<>""),AI409:AO409))) | IF(OR(F409="",AQ409=""),"",IF(COUNT(AI409:AP409)=0,"",AQ409-LOOKUP(2,1/(AI409:AP409<>""),AI409:AP409))) | IF(OR(F409="",AR409=""),"",IF(COUNT(AI409:AQ409)=0,"",AR409-LOOKUP(2,1/(AI409:AQ409<>""),AI409:AQ409))) | IF(OR(F409="",AS409=""),"",IF(COUNT(AI409:AR409)=0,"",AS409-LOOKUP(2,1/(AI409:AR409<>""),AI409:AR409))) | IF(OR(F409="",AT409=""),"",IF(COUNT(AI409:AS409)=0,"",AT409-LOOKUP(2,1/(AI409:AS409<>""),AI409:AS409))) | IF(OR(F409="",AU409=""),"",IF(COUNT(AI409:AT409)=0,"",AU409-LOOKUP(2,1/(AI409:AT409<>""),AI409:AT409))) | IF(OR(F409="",AV409=""),"",IF(COUNT(AI409:AU409)=0,"",AV409-LOOKUP(2,1/(AI409:AU409<>""),AI409:AU409))) | IF(J409="","All_Provinces",IFERROR(VLOOKUP(J409,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K409="","All_Districts",IFERROR(VLOOKUP(K409,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F410="","",ROW()-3) | [18 empty] | IF(AQ410="","",AQ410) |  |  |  | IF(W410<>"",W410,IF(OR(T410="",V410=""),"",EDATE(T410,V410))) |  |  |  |  | IF(F410="","",IF(COUNT(AI410:AV410)=0,IF(AA410="","Not started",AA410),SUBSTITUTE(LOOKUP(2,1/(AI410:AV410<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F410="",COUNT(AI410:AV410)=0),"",TODAY()-LOOKUP(2,1/(AI410:AV410<>""),AI410:AV410)) | IF(OR(F410="",COUNT(AI410:AV410)<2),"",LOOKUP(2,1/(AI410:AV410<>""),AI410:AV410)-MIN(AI410:AV410)) | IF(OR(AD410="",AC410="Not started",AC410=""),"",IFERROR(AD410-IF(VLOOKUP(AC410,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC410,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F410="","",IF(OR(AA410="Cancelled",AC410="Cancelled"),"Cancelled",IF(OR(AC410="Completed / Handover",Y410<>"",Z410>=100),"Completed — on track",IF(O410="Not awarded",IF(U410="",IF(X410="","No planned date",IF(TODAY()>X410,"Behind — past planned date",IF(X410-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U410,"Behind — award date passed",IF(U410-TODAY()<=30,"At risk — close to off track","On track"))),IF(X410="","No planned date",IF(AND(TODAY()>X410,OR(Z410="",Z410<100)),"Behind — past end date",IF(AND(T410<>"",X410<>"",Z410<>"",(Z410<100),((TODAY()-T410)/MAX(X410-T410,1)*100)-Z410>15),"Behind — progress lag",IF(AND(X410-TODAY()<=30,X410-TODAY()>=0,OR(Z410="",Z410<90)),"At risk — close to off track","On track")))))))) | IF(OR(F410="",AC410="Completed / Handover",AC410="Cancelled"),"",IF(O410="Not awarded",IF(U410<>"",U410-TODAY(),IF(X410="","",X410-TODAY())),IF(X410="","",X410-TODAY()))) | [14 empty] | IF(OR(F410="",AJ410=""),"",IF(COUNT(AI410:AI410)=0,"",AJ410-LOOKUP(2,1/(AI410:AI410<>""),AI410:AI410))) | IF(OR(F410="",AK410=""),"",IF(COUNT(AI410:AJ410)=0,"",AK410-LOOKUP(2,1/(AI410:AJ410<>""),AI410:AJ410))) | IF(OR(F410="",AL410=""),"",IF(COUNT(AI410:AK410)=0,"",AL410-LOOKUP(2,1/(AI410:AK410<>""),AI410:AK410))) | IF(OR(F410="",AM410=""),"",IF(COUNT(AI410:AL410)=0,"",AM410-LOOKUP(2,1/(AI410:AL410<>""),AI410:AL410))) | IF(OR(F410="",AN410=""),"",IF(COUNT(AI410:AM410)=0,"",AN410-LOOKUP(2,1/(AI410:AM410<>""),AI410:AM410))) | IF(OR(F410="",AO410=""),"",IF(COUNT(AI410:AN410)=0,"",AO410-LOOKUP(2,1/(AI410:AN410<>""),AI410:AN410))) | IF(OR(F410="",AP410=""),"",IF(COUNT(AI410:AO410)=0,"",AP410-LOOKUP(2,1/(AI410:AO410<>""),AI410:AO410))) | IF(OR(F410="",AQ410=""),"",IF(COUNT(AI410:AP410)=0,"",AQ410-LOOKUP(2,1/(AI410:AP410<>""),AI410:AP410))) | IF(OR(F410="",AR410=""),"",IF(COUNT(AI410:AQ410)=0,"",AR410-LOOKUP(2,1/(AI410:AQ410<>""),AI410:AQ410))) | IF(OR(F410="",AS410=""),"",IF(COUNT(AI410:AR410)=0,"",AS410-LOOKUP(2,1/(AI410:AR410<>""),AI410:AR410))) | IF(OR(F410="",AT410=""),"",IF(COUNT(AI410:AS410)=0,"",AT410-LOOKUP(2,1/(AI410:AS410<>""),AI410:AS410))) | IF(OR(F410="",AU410=""),"",IF(COUNT(AI410:AT410)=0,"",AU410-LOOKUP(2,1/(AI410:AT410<>""),AI410:AT410))) | IF(OR(F410="",AV410=""),"",IF(COUNT(AI410:AU410)=0,"",AV410-LOOKUP(2,1/(AI410:AU410<>""),AI410:AU410))) | IF(J410="","All_Provinces",IFERROR(VLOOKUP(J410,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K410="","All_Districts",IFERROR(VLOOKUP(K410,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F411="","",ROW()-3) | [18 empty] | IF(AQ411="","",AQ411) |  |  |  | IF(W411<>"",W411,IF(OR(T411="",V411=""),"",EDATE(T411,V411))) |  |  |  |  | IF(F411="","",IF(COUNT(AI411:AV411)=0,IF(AA411="","Not started",AA411),SUBSTITUTE(LOOKUP(2,1/(AI411:AV411<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F411="",COUNT(AI411:AV411)=0),"",TODAY()-LOOKUP(2,1/(AI411:AV411<>""),AI411:AV411)) | IF(OR(F411="",COUNT(AI411:AV411)<2),"",LOOKUP(2,1/(AI411:AV411<>""),AI411:AV411)-MIN(AI411:AV411)) | IF(OR(AD411="",AC411="Not started",AC411=""),"",IFERROR(AD411-IF(VLOOKUP(AC411,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC411,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F411="","",IF(OR(AA411="Cancelled",AC411="Cancelled"),"Cancelled",IF(OR(AC411="Completed / Handover",Y411<>"",Z411>=100),"Completed — on track",IF(O411="Not awarded",IF(U411="",IF(X411="","No planned date",IF(TODAY()>X411,"Behind — past planned date",IF(X411-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U411,"Behind — award date passed",IF(U411-TODAY()<=30,"At risk — close to off track","On track"))),IF(X411="","No planned date",IF(AND(TODAY()>X411,OR(Z411="",Z411<100)),"Behind — past end date",IF(AND(T411<>"",X411<>"",Z411<>"",(Z411<100),((TODAY()-T411)/MAX(X411-T411,1)*100)-Z411>15),"Behind — progress lag",IF(AND(X411-TODAY()<=30,X411-TODAY()>=0,OR(Z411="",Z411<90)),"At risk — close to off track","On track")))))))) | IF(OR(F411="",AC411="Completed / Handover",AC411="Cancelled"),"",IF(O411="Not awarded",IF(U411<>"",U411-TODAY(),IF(X411="","",X411-TODAY())),IF(X411="","",X411-TODAY()))) | [14 empty] | IF(OR(F411="",AJ411=""),"",IF(COUNT(AI411:AI411)=0,"",AJ411-LOOKUP(2,1/(AI411:AI411<>""),AI411:AI411))) | IF(OR(F411="",AK411=""),"",IF(COUNT(AI411:AJ411)=0,"",AK411-LOOKUP(2,1/(AI411:AJ411<>""),AI411:AJ411))) | IF(OR(F411="",AL411=""),"",IF(COUNT(AI411:AK411)=0,"",AL411-LOOKUP(2,1/(AI411:AK411<>""),AI411:AK411))) | IF(OR(F411="",AM411=""),"",IF(COUNT(AI411:AL411)=0,"",AM411-LOOKUP(2,1/(AI411:AL411<>""),AI411:AL411))) | IF(OR(F411="",AN411=""),"",IF(COUNT(AI411:AM411)=0,"",AN411-LOOKUP(2,1/(AI411:AM411<>""),AI411:AM411))) | IF(OR(F411="",AO411=""),"",IF(COUNT(AI411:AN411)=0,"",AO411-LOOKUP(2,1/(AI411:AN411<>""),AI411:AN411))) | IF(OR(F411="",AP411=""),"",IF(COUNT(AI411:AO411)=0,"",AP411-LOOKUP(2,1/(AI411:AO411<>""),AI411:AO411))) | IF(OR(F411="",AQ411=""),"",IF(COUNT(AI411:AP411)=0,"",AQ411-LOOKUP(2,1/(AI411:AP411<>""),AI411:AP411))) | IF(OR(F411="",AR411=""),"",IF(COUNT(AI411:AQ411)=0,"",AR411-LOOKUP(2,1/(AI411:AQ411<>""),AI411:AQ411))) | IF(OR(F411="",AS411=""),"",IF(COUNT(AI411:AR411)=0,"",AS411-LOOKUP(2,1/(AI411:AR411<>""),AI411:AR411))) | IF(OR(F411="",AT411=""),"",IF(COUNT(AI411:AS411)=0,"",AT411-LOOKUP(2,1/(AI411:AS411<>""),AI411:AS411))) | IF(OR(F411="",AU411=""),"",IF(COUNT(AI411:AT411)=0,"",AU411-LOOKUP(2,1/(AI411:AT411<>""),AI411:AT411))) | IF(OR(F411="",AV411=""),"",IF(COUNT(AI411:AU411)=0,"",AV411-LOOKUP(2,1/(AI411:AU411<>""),AI411:AU411))) | IF(J411="","All_Provinces",IFERROR(VLOOKUP(J411,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K411="","All_Districts",IFERROR(VLOOKUP(K411,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F412="","",ROW()-3) | [18 empty] | IF(AQ412="","",AQ412) |  |  |  | IF(W412<>"",W412,IF(OR(T412="",V412=""),"",EDATE(T412,V412))) |  |  |  |  | IF(F412="","",IF(COUNT(AI412:AV412)=0,IF(AA412="","Not started",AA412),SUBSTITUTE(LOOKUP(2,1/(AI412:AV412<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F412="",COUNT(AI412:AV412)=0),"",TODAY()-LOOKUP(2,1/(AI412:AV412<>""),AI412:AV412)) | IF(OR(F412="",COUNT(AI412:AV412)<2),"",LOOKUP(2,1/(AI412:AV412<>""),AI412:AV412)-MIN(AI412:AV412)) | IF(OR(AD412="",AC412="Not started",AC412=""),"",IFERROR(AD412-IF(VLOOKUP(AC412,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC412,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F412="","",IF(OR(AA412="Cancelled",AC412="Cancelled"),"Cancelled",IF(OR(AC412="Completed / Handover",Y412<>"",Z412>=100),"Completed — on track",IF(O412="Not awarded",IF(U412="",IF(X412="","No planned date",IF(TODAY()>X412,"Behind — past planned date",IF(X412-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U412,"Behind — award date passed",IF(U412-TODAY()<=30,"At risk — close to off track","On track"))),IF(X412="","No planned date",IF(AND(TODAY()>X412,OR(Z412="",Z412<100)),"Behind — past end date",IF(AND(T412<>"",X412<>"",Z412<>"",(Z412<100),((TODAY()-T412)/MAX(X412-T412,1)*100)-Z412>15),"Behind — progress lag",IF(AND(X412-TODAY()<=30,X412-TODAY()>=0,OR(Z412="",Z412<90)),"At risk — close to off track","On track")))))))) | IF(OR(F412="",AC412="Completed / Handover",AC412="Cancelled"),"",IF(O412="Not awarded",IF(U412<>"",U412-TODAY(),IF(X412="","",X412-TODAY())),IF(X412="","",X412-TODAY()))) | [14 empty] | IF(OR(F412="",AJ412=""),"",IF(COUNT(AI412:AI412)=0,"",AJ412-LOOKUP(2,1/(AI412:AI412<>""),AI412:AI412))) | IF(OR(F412="",AK412=""),"",IF(COUNT(AI412:AJ412)=0,"",AK412-LOOKUP(2,1/(AI412:AJ412<>""),AI412:AJ412))) | IF(OR(F412="",AL412=""),"",IF(COUNT(AI412:AK412)=0,"",AL412-LOOKUP(2,1/(AI412:AK412<>""),AI412:AK412))) | IF(OR(F412="",AM412=""),"",IF(COUNT(AI412:AL412)=0,"",AM412-LOOKUP(2,1/(AI412:AL412<>""),AI412:AL412))) | IF(OR(F412="",AN412=""),"",IF(COUNT(AI412:AM412)=0,"",AN412-LOOKUP(2,1/(AI412:AM412<>""),AI412:AM412))) | IF(OR(F412="",AO412=""),"",IF(COUNT(AI412:AN412)=0,"",AO412-LOOKUP(2,1/(AI412:AN412<>""),AI412:AN412))) | IF(OR(F412="",AP412=""),"",IF(COUNT(AI412:AO412)=0,"",AP412-LOOKUP(2,1/(AI412:AO412<>""),AI412:AO412))) | IF(OR(F412="",AQ412=""),"",IF(COUNT(AI412:AP412)=0,"",AQ412-LOOKUP(2,1/(AI412:AP412<>""),AI412:AP412))) | IF(OR(F412="",AR412=""),"",IF(COUNT(AI412:AQ412)=0,"",AR412-LOOKUP(2,1/(AI412:AQ412<>""),AI412:AQ412))) | IF(OR(F412="",AS412=""),"",IF(COUNT(AI412:AR412)=0,"",AS412-LOOKUP(2,1/(AI412:AR412<>""),AI412:AR412))) | IF(OR(F412="",AT412=""),"",IF(COUNT(AI412:AS412)=0,"",AT412-LOOKUP(2,1/(AI412:AS412<>""),AI412:AS412))) | IF(OR(F412="",AU412=""),"",IF(COUNT(AI412:AT412)=0,"",AU412-LOOKUP(2,1/(AI412:AT412<>""),AI412:AT412))) | IF(OR(F412="",AV412=""),"",IF(COUNT(AI412:AU412)=0,"",AV412-LOOKUP(2,1/(AI412:AU412<>""),AI412:AU412))) | IF(J412="","All_Provinces",IFERROR(VLOOKUP(J412,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K412="","All_Districts",IFERROR(VLOOKUP(K412,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F413="","",ROW()-3) | [18 empty] | IF(AQ413="","",AQ413) |  |  |  | IF(W413<>"",W413,IF(OR(T413="",V413=""),"",EDATE(T413,V413))) |  |  |  |  | IF(F413="","",IF(COUNT(AI413:AV413)=0,IF(AA413="","Not started",AA413),SUBSTITUTE(LOOKUP(2,1/(AI413:AV413<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F413="",COUNT(AI413:AV413)=0),"",TODAY()-LOOKUP(2,1/(AI413:AV413<>""),AI413:AV413)) | IF(OR(F413="",COUNT(AI413:AV413)<2),"",LOOKUP(2,1/(AI413:AV413<>""),AI413:AV413)-MIN(AI413:AV413)) | IF(OR(AD413="",AC413="Not started",AC413=""),"",IFERROR(AD413-IF(VLOOKUP(AC413,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC413,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F413="","",IF(OR(AA413="Cancelled",AC413="Cancelled"),"Cancelled",IF(OR(AC413="Completed / Handover",Y413<>"",Z413>=100),"Completed — on track",IF(O413="Not awarded",IF(U413="",IF(X413="","No planned date",IF(TODAY()>X413,"Behind — past planned date",IF(X413-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U413,"Behind — award date passed",IF(U413-TODAY()<=30,"At risk — close to off track","On track"))),IF(X413="","No planned date",IF(AND(TODAY()>X413,OR(Z413="",Z413<100)),"Behind — past end date",IF(AND(T413<>"",X413<>"",Z413<>"",(Z413<100),((TODAY()-T413)/MAX(X413-T413,1)*100)-Z413>15),"Behind — progress lag",IF(AND(X413-TODAY()<=30,X413-TODAY()>=0,OR(Z413="",Z413<90)),"At risk — close to off track","On track")))))))) | IF(OR(F413="",AC413="Completed / Handover",AC413="Cancelled"),"",IF(O413="Not awarded",IF(U413<>"",U413-TODAY(),IF(X413="","",X413-TODAY())),IF(X413="","",X413-TODAY()))) | [14 empty] | IF(OR(F413="",AJ413=""),"",IF(COUNT(AI413:AI413)=0,"",AJ413-LOOKUP(2,1/(AI413:AI413<>""),AI413:AI413))) | IF(OR(F413="",AK413=""),"",IF(COUNT(AI413:AJ413)=0,"",AK413-LOOKUP(2,1/(AI413:AJ413<>""),AI413:AJ413))) | IF(OR(F413="",AL413=""),"",IF(COUNT(AI413:AK413)=0,"",AL413-LOOKUP(2,1/(AI413:AK413<>""),AI413:AK413))) | IF(OR(F413="",AM413=""),"",IF(COUNT(AI413:AL413)=0,"",AM413-LOOKUP(2,1/(AI413:AL413<>""),AI413:AL413))) | IF(OR(F413="",AN413=""),"",IF(COUNT(AI413:AM413)=0,"",AN413-LOOKUP(2,1/(AI413:AM413<>""),AI413:AM413))) | IF(OR(F413="",AO413=""),"",IF(COUNT(AI413:AN413)=0,"",AO413-LOOKUP(2,1/(AI413:AN413<>""),AI413:AN413))) | IF(OR(F413="",AP413=""),"",IF(COUNT(AI413:AO413)=0,"",AP413-LOOKUP(2,1/(AI413:AO413<>""),AI413:AO413))) | IF(OR(F413="",AQ413=""),"",IF(COUNT(AI413:AP413)=0,"",AQ413-LOOKUP(2,1/(AI413:AP413<>""),AI413:AP413))) | IF(OR(F413="",AR413=""),"",IF(COUNT(AI413:AQ413)=0,"",AR413-LOOKUP(2,1/(AI413:AQ413<>""),AI413:AQ413))) | IF(OR(F413="",AS413=""),"",IF(COUNT(AI413:AR413)=0,"",AS413-LOOKUP(2,1/(AI413:AR413<>""),AI413:AR413))) | IF(OR(F413="",AT413=""),"",IF(COUNT(AI413:AS413)=0,"",AT413-LOOKUP(2,1/(AI413:AS413<>""),AI413:AS413))) | IF(OR(F413="",AU413=""),"",IF(COUNT(AI413:AT413)=0,"",AU413-LOOKUP(2,1/(AI413:AT413<>""),AI413:AT413))) | IF(OR(F413="",AV413=""),"",IF(COUNT(AI413:AU413)=0,"",AV413-LOOKUP(2,1/(AI413:AU413<>""),AI413:AU413))) | IF(J413="","All_Provinces",IFERROR(VLOOKUP(J413,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K413="","All_Districts",IFERROR(VLOOKUP(K413,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F414="","",ROW()-3) | [18 empty] | IF(AQ414="","",AQ414) |  |  |  | IF(W414<>"",W414,IF(OR(T414="",V414=""),"",EDATE(T414,V414))) |  |  |  |  | IF(F414="","",IF(COUNT(AI414:AV414)=0,IF(AA414="","Not started",AA414),SUBSTITUTE(LOOKUP(2,1/(AI414:AV414<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F414="",COUNT(AI414:AV414)=0),"",TODAY()-LOOKUP(2,1/(AI414:AV414<>""),AI414:AV414)) | IF(OR(F414="",COUNT(AI414:AV414)<2),"",LOOKUP(2,1/(AI414:AV414<>""),AI414:AV414)-MIN(AI414:AV414)) | IF(OR(AD414="",AC414="Not started",AC414=""),"",IFERROR(AD414-IF(VLOOKUP(AC414,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC414,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F414="","",IF(OR(AA414="Cancelled",AC414="Cancelled"),"Cancelled",IF(OR(AC414="Completed / Handover",Y414<>"",Z414>=100),"Completed — on track",IF(O414="Not awarded",IF(U414="",IF(X414="","No planned date",IF(TODAY()>X414,"Behind — past planned date",IF(X414-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U414,"Behind — award date passed",IF(U414-TODAY()<=30,"At risk — close to off track","On track"))),IF(X414="","No planned date",IF(AND(TODAY()>X414,OR(Z414="",Z414<100)),"Behind — past end date",IF(AND(T414<>"",X414<>"",Z414<>"",(Z414<100),((TODAY()-T414)/MAX(X414-T414,1)*100)-Z414>15),"Behind — progress lag",IF(AND(X414-TODAY()<=30,X414-TODAY()>=0,OR(Z414="",Z414<90)),"At risk — close to off track","On track")))))))) | IF(OR(F414="",AC414="Completed / Handover",AC414="Cancelled"),"",IF(O414="Not awarded",IF(U414<>"",U414-TODAY(),IF(X414="","",X414-TODAY())),IF(X414="","",X414-TODAY()))) | [14 empty] | IF(OR(F414="",AJ414=""),"",IF(COUNT(AI414:AI414)=0,"",AJ414-LOOKUP(2,1/(AI414:AI414<>""),AI414:AI414))) | IF(OR(F414="",AK414=""),"",IF(COUNT(AI414:AJ414)=0,"",AK414-LOOKUP(2,1/(AI414:AJ414<>""),AI414:AJ414))) | IF(OR(F414="",AL414=""),"",IF(COUNT(AI414:AK414)=0,"",AL414-LOOKUP(2,1/(AI414:AK414<>""),AI414:AK414))) | IF(OR(F414="",AM414=""),"",IF(COUNT(AI414:AL414)=0,"",AM414-LOOKUP(2,1/(AI414:AL414<>""),AI414:AL414))) | IF(OR(F414="",AN414=""),"",IF(COUNT(AI414:AM414)=0,"",AN414-LOOKUP(2,1/(AI414:AM414<>""),AI414:AM414))) | IF(OR(F414="",AO414=""),"",IF(COUNT(AI414:AN414)=0,"",AO414-LOOKUP(2,1/(AI414:AN414<>""),AI414:AN414))) | IF(OR(F414="",AP414=""),"",IF(COUNT(AI414:AO414)=0,"",AP414-LOOKUP(2,1/(AI414:AO414<>""),AI414:AO414))) | IF(OR(F414="",AQ414=""),"",IF(COUNT(AI414:AP414)=0,"",AQ414-LOOKUP(2,1/(AI414:AP414<>""),AI414:AP414))) | IF(OR(F414="",AR414=""),"",IF(COUNT(AI414:AQ414)=0,"",AR414-LOOKUP(2,1/(AI414:AQ414<>""),AI414:AQ414))) | IF(OR(F414="",AS414=""),"",IF(COUNT(AI414:AR414)=0,"",AS414-LOOKUP(2,1/(AI414:AR414<>""),AI414:AR414))) | IF(OR(F414="",AT414=""),"",IF(COUNT(AI414:AS414)=0,"",AT414-LOOKUP(2,1/(AI414:AS414<>""),AI414:AS414))) | IF(OR(F414="",AU414=""),"",IF(COUNT(AI414:AT414)=0,"",AU414-LOOKUP(2,1/(AI414:AT414<>""),AI414:AT414))) | IF(OR(F414="",AV414=""),"",IF(COUNT(AI414:AU414)=0,"",AV414-LOOKUP(2,1/(AI414:AU414<>""),AI414:AU414))) | IF(J414="","All_Provinces",IFERROR(VLOOKUP(J414,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K414="","All_Districts",IFERROR(VLOOKUP(K414,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F415="","",ROW()-3) | [18 empty] | IF(AQ415="","",AQ415) |  |  |  | IF(W415<>"",W415,IF(OR(T415="",V415=""),"",EDATE(T415,V415))) |  |  |  |  | IF(F415="","",IF(COUNT(AI415:AV415)=0,IF(AA415="","Not started",AA415),SUBSTITUTE(LOOKUP(2,1/(AI415:AV415<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F415="",COUNT(AI415:AV415)=0),"",TODAY()-LOOKUP(2,1/(AI415:AV415<>""),AI415:AV415)) | IF(OR(F415="",COUNT(AI415:AV415)<2),"",LOOKUP(2,1/(AI415:AV415<>""),AI415:AV415)-MIN(AI415:AV415)) | IF(OR(AD415="",AC415="Not started",AC415=""),"",IFERROR(AD415-IF(VLOOKUP(AC415,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC415,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F415="","",IF(OR(AA415="Cancelled",AC415="Cancelled"),"Cancelled",IF(OR(AC415="Completed / Handover",Y415<>"",Z415>=100),"Completed — on track",IF(O415="Not awarded",IF(U415="",IF(X415="","No planned date",IF(TODAY()>X415,"Behind — past planned date",IF(X415-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U415,"Behind — award date passed",IF(U415-TODAY()<=30,"At risk — close to off track","On track"))),IF(X415="","No planned date",IF(AND(TODAY()>X415,OR(Z415="",Z415<100)),"Behind — past end date",IF(AND(T415<>"",X415<>"",Z415<>"",(Z415<100),((TODAY()-T415)/MAX(X415-T415,1)*100)-Z415>15),"Behind — progress lag",IF(AND(X415-TODAY()<=30,X415-TODAY()>=0,OR(Z415="",Z415<90)),"At risk — close to off track","On track")))))))) | IF(OR(F415="",AC415="Completed / Handover",AC415="Cancelled"),"",IF(O415="Not awarded",IF(U415<>"",U415-TODAY(),IF(X415="","",X415-TODAY())),IF(X415="","",X415-TODAY()))) | [14 empty] | IF(OR(F415="",AJ415=""),"",IF(COUNT(AI415:AI415)=0,"",AJ415-LOOKUP(2,1/(AI415:AI415<>""),AI415:AI415))) | IF(OR(F415="",AK415=""),"",IF(COUNT(AI415:AJ415)=0,"",AK415-LOOKUP(2,1/(AI415:AJ415<>""),AI415:AJ415))) | IF(OR(F415="",AL415=""),"",IF(COUNT(AI415:AK415)=0,"",AL415-LOOKUP(2,1/(AI415:AK415<>""),AI415:AK415))) | IF(OR(F415="",AM415=""),"",IF(COUNT(AI415:AL415)=0,"",AM415-LOOKUP(2,1/(AI415:AL415<>""),AI415:AL415))) | IF(OR(F415="",AN415=""),"",IF(COUNT(AI415:AM415)=0,"",AN415-LOOKUP(2,1/(AI415:AM415<>""),AI415:AM415))) | IF(OR(F415="",AO415=""),"",IF(COUNT(AI415:AN415)=0,"",AO415-LOOKUP(2,1/(AI415:AN415<>""),AI415:AN415))) | IF(OR(F415="",AP415=""),"",IF(COUNT(AI415:AO415)=0,"",AP415-LOOKUP(2,1/(AI415:AO415<>""),AI415:AO415))) | IF(OR(F415="",AQ415=""),"",IF(COUNT(AI415:AP415)=0,"",AQ415-LOOKUP(2,1/(AI415:AP415<>""),AI415:AP415))) | IF(OR(F415="",AR415=""),"",IF(COUNT(AI415:AQ415)=0,"",AR415-LOOKUP(2,1/(AI415:AQ415<>""),AI415:AQ415))) | IF(OR(F415="",AS415=""),"",IF(COUNT(AI415:AR415)=0,"",AS415-LOOKUP(2,1/(AI415:AR415<>""),AI415:AR415))) | IF(OR(F415="",AT415=""),"",IF(COUNT(AI415:AS415)=0,"",AT415-LOOKUP(2,1/(AI415:AS415<>""),AI415:AS415))) | IF(OR(F415="",AU415=""),"",IF(COUNT(AI415:AT415)=0,"",AU415-LOOKUP(2,1/(AI415:AT415<>""),AI415:AT415))) | IF(OR(F415="",AV415=""),"",IF(COUNT(AI415:AU415)=0,"",AV415-LOOKUP(2,1/(AI415:AU415<>""),AI415:AU415))) | IF(J415="","All_Provinces",IFERROR(VLOOKUP(J415,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K415="","All_Districts",IFERROR(VLOOKUP(K415,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F416="","",ROW()-3) | [18 empty] | IF(AQ416="","",AQ416) |  |  |  | IF(W416<>"",W416,IF(OR(T416="",V416=""),"",EDATE(T416,V416))) |  |  |  |  | IF(F416="","",IF(COUNT(AI416:AV416)=0,IF(AA416="","Not started",AA416),SUBSTITUTE(LOOKUP(2,1/(AI416:AV416<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F416="",COUNT(AI416:AV416)=0),"",TODAY()-LOOKUP(2,1/(AI416:AV416<>""),AI416:AV416)) | IF(OR(F416="",COUNT(AI416:AV416)<2),"",LOOKUP(2,1/(AI416:AV416<>""),AI416:AV416)-MIN(AI416:AV416)) | IF(OR(AD416="",AC416="Not started",AC416=""),"",IFERROR(AD416-IF(VLOOKUP(AC416,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC416,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F416="","",IF(OR(AA416="Cancelled",AC416="Cancelled"),"Cancelled",IF(OR(AC416="Completed / Handover",Y416<>"",Z416>=100),"Completed — on track",IF(O416="Not awarded",IF(U416="",IF(X416="","No planned date",IF(TODAY()>X416,"Behind — past planned date",IF(X416-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U416,"Behind — award date passed",IF(U416-TODAY()<=30,"At risk — close to off track","On track"))),IF(X416="","No planned date",IF(AND(TODAY()>X416,OR(Z416="",Z416<100)),"Behind — past end date",IF(AND(T416<>"",X416<>"",Z416<>"",(Z416<100),((TODAY()-T416)/MAX(X416-T416,1)*100)-Z416>15),"Behind — progress lag",IF(AND(X416-TODAY()<=30,X416-TODAY()>=0,OR(Z416="",Z416<90)),"At risk — close to off track","On track")))))))) | IF(OR(F416="",AC416="Completed / Handover",AC416="Cancelled"),"",IF(O416="Not awarded",IF(U416<>"",U416-TODAY(),IF(X416="","",X416-TODAY())),IF(X416="","",X416-TODAY()))) | [14 empty] | IF(OR(F416="",AJ416=""),"",IF(COUNT(AI416:AI416)=0,"",AJ416-LOOKUP(2,1/(AI416:AI416<>""),AI416:AI416))) | IF(OR(F416="",AK416=""),"",IF(COUNT(AI416:AJ416)=0,"",AK416-LOOKUP(2,1/(AI416:AJ416<>""),AI416:AJ416))) | IF(OR(F416="",AL416=""),"",IF(COUNT(AI416:AK416)=0,"",AL416-LOOKUP(2,1/(AI416:AK416<>""),AI416:AK416))) | IF(OR(F416="",AM416=""),"",IF(COUNT(AI416:AL416)=0,"",AM416-LOOKUP(2,1/(AI416:AL416<>""),AI416:AL416))) | IF(OR(F416="",AN416=""),"",IF(COUNT(AI416:AM416)=0,"",AN416-LOOKUP(2,1/(AI416:AM416<>""),AI416:AM416))) | IF(OR(F416="",AO416=""),"",IF(COUNT(AI416:AN416)=0,"",AO416-LOOKUP(2,1/(AI416:AN416<>""),AI416:AN416))) | IF(OR(F416="",AP416=""),"",IF(COUNT(AI416:AO416)=0,"",AP416-LOOKUP(2,1/(AI416:AO416<>""),AI416:AO416))) | IF(OR(F416="",AQ416=""),"",IF(COUNT(AI416:AP416)=0,"",AQ416-LOOKUP(2,1/(AI416:AP416<>""),AI416:AP416))) | IF(OR(F416="",AR416=""),"",IF(COUNT(AI416:AQ416)=0,"",AR416-LOOKUP(2,1/(AI416:AQ416<>""),AI416:AQ416))) | IF(OR(F416="",AS416=""),"",IF(COUNT(AI416:AR416)=0,"",AS416-LOOKUP(2,1/(AI416:AR416<>""),AI416:AR416))) | IF(OR(F416="",AT416=""),"",IF(COUNT(AI416:AS416)=0,"",AT416-LOOKUP(2,1/(AI416:AS416<>""),AI416:AS416))) | IF(OR(F416="",AU416=""),"",IF(COUNT(AI416:AT416)=0,"",AU416-LOOKUP(2,1/(AI416:AT416<>""),AI416:AT416))) | IF(OR(F416="",AV416=""),"",IF(COUNT(AI416:AU416)=0,"",AV416-LOOKUP(2,1/(AI416:AU416<>""),AI416:AU416))) | IF(J416="","All_Provinces",IFERROR(VLOOKUP(J416,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K416="","All_Districts",IFERROR(VLOOKUP(K416,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F417="","",ROW()-3) | [18 empty] | IF(AQ417="","",AQ417) |  |  |  | IF(W417<>"",W417,IF(OR(T417="",V417=""),"",EDATE(T417,V417))) |  |  |  |  | IF(F417="","",IF(COUNT(AI417:AV417)=0,IF(AA417="","Not started",AA417),SUBSTITUTE(LOOKUP(2,1/(AI417:AV417<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F417="",COUNT(AI417:AV417)=0),"",TODAY()-LOOKUP(2,1/(AI417:AV417<>""),AI417:AV417)) | IF(OR(F417="",COUNT(AI417:AV417)<2),"",LOOKUP(2,1/(AI417:AV417<>""),AI417:AV417)-MIN(AI417:AV417)) | IF(OR(AD417="",AC417="Not started",AC417=""),"",IFERROR(AD417-IF(VLOOKUP(AC417,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC417,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F417="","",IF(OR(AA417="Cancelled",AC417="Cancelled"),"Cancelled",IF(OR(AC417="Completed / Handover",Y417<>"",Z417>=100),"Completed — on track",IF(O417="Not awarded",IF(U417="",IF(X417="","No planned date",IF(TODAY()>X417,"Behind — past planned date",IF(X417-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U417,"Behind — award date passed",IF(U417-TODAY()<=30,"At risk — close to off track","On track"))),IF(X417="","No planned date",IF(AND(TODAY()>X417,OR(Z417="",Z417<100)),"Behind — past end date",IF(AND(T417<>"",X417<>"",Z417<>"",(Z417<100),((TODAY()-T417)/MAX(X417-T417,1)*100)-Z417>15),"Behind — progress lag",IF(AND(X417-TODAY()<=30,X417-TODAY()>=0,OR(Z417="",Z417<90)),"At risk — close to off track","On track")))))))) | IF(OR(F417="",AC417="Completed / Handover",AC417="Cancelled"),"",IF(O417="Not awarded",IF(U417<>"",U417-TODAY(),IF(X417="","",X417-TODAY())),IF(X417="","",X417-TODAY()))) | [14 empty] | IF(OR(F417="",AJ417=""),"",IF(COUNT(AI417:AI417)=0,"",AJ417-LOOKUP(2,1/(AI417:AI417<>""),AI417:AI417))) | IF(OR(F417="",AK417=""),"",IF(COUNT(AI417:AJ417)=0,"",AK417-LOOKUP(2,1/(AI417:AJ417<>""),AI417:AJ417))) | IF(OR(F417="",AL417=""),"",IF(COUNT(AI417:AK417)=0,"",AL417-LOOKUP(2,1/(AI417:AK417<>""),AI417:AK417))) | IF(OR(F417="",AM417=""),"",IF(COUNT(AI417:AL417)=0,"",AM417-LOOKUP(2,1/(AI417:AL417<>""),AI417:AL417))) | IF(OR(F417="",AN417=""),"",IF(COUNT(AI417:AM417)=0,"",AN417-LOOKUP(2,1/(AI417:AM417<>""),AI417:AM417))) | IF(OR(F417="",AO417=""),"",IF(COUNT(AI417:AN417)=0,"",AO417-LOOKUP(2,1/(AI417:AN417<>""),AI417:AN417))) | IF(OR(F417="",AP417=""),"",IF(COUNT(AI417:AO417)=0,"",AP417-LOOKUP(2,1/(AI417:AO417<>""),AI417:AO417))) | IF(OR(F417="",AQ417=""),"",IF(COUNT(AI417:AP417)=0,"",AQ417-LOOKUP(2,1/(AI417:AP417<>""),AI417:AP417))) | IF(OR(F417="",AR417=""),"",IF(COUNT(AI417:AQ417)=0,"",AR417-LOOKUP(2,1/(AI417:AQ417<>""),AI417:AQ417))) | IF(OR(F417="",AS417=""),"",IF(COUNT(AI417:AR417)=0,"",AS417-LOOKUP(2,1/(AI417:AR417<>""),AI417:AR417))) | IF(OR(F417="",AT417=""),"",IF(COUNT(AI417:AS417)=0,"",AT417-LOOKUP(2,1/(AI417:AS417<>""),AI417:AS417))) | IF(OR(F417="",AU417=""),"",IF(COUNT(AI417:AT417)=0,"",AU417-LOOKUP(2,1/(AI417:AT417<>""),AI417:AT417))) | IF(OR(F417="",AV417=""),"",IF(COUNT(AI417:AU417)=0,"",AV417-LOOKUP(2,1/(AI417:AU417<>""),AI417:AU417))) | IF(J417="","All_Provinces",IFERROR(VLOOKUP(J417,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K417="","All_Districts",IFERROR(VLOOKUP(K417,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F418="","",ROW()-3) | [18 empty] | IF(AQ418="","",AQ418) |  |  |  | IF(W418<>"",W418,IF(OR(T418="",V418=""),"",EDATE(T418,V418))) |  |  |  |  | IF(F418="","",IF(COUNT(AI418:AV418)=0,IF(AA418="","Not started",AA418),SUBSTITUTE(LOOKUP(2,1/(AI418:AV418<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F418="",COUNT(AI418:AV418)=0),"",TODAY()-LOOKUP(2,1/(AI418:AV418<>""),AI418:AV418)) | IF(OR(F418="",COUNT(AI418:AV418)<2),"",LOOKUP(2,1/(AI418:AV418<>""),AI418:AV418)-MIN(AI418:AV418)) | IF(OR(AD418="",AC418="Not started",AC418=""),"",IFERROR(AD418-IF(VLOOKUP(AC418,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC418,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F418="","",IF(OR(AA418="Cancelled",AC418="Cancelled"),"Cancelled",IF(OR(AC418="Completed / Handover",Y418<>"",Z418>=100),"Completed — on track",IF(O418="Not awarded",IF(U418="",IF(X418="","No planned date",IF(TODAY()>X418,"Behind — past planned date",IF(X418-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U418,"Behind — award date passed",IF(U418-TODAY()<=30,"At risk — close to off track","On track"))),IF(X418="","No planned date",IF(AND(TODAY()>X418,OR(Z418="",Z418<100)),"Behind — past end date",IF(AND(T418<>"",X418<>"",Z418<>"",(Z418<100),((TODAY()-T418)/MAX(X418-T418,1)*100)-Z418>15),"Behind — progress lag",IF(AND(X418-TODAY()<=30,X418-TODAY()>=0,OR(Z418="",Z418<90)),"At risk — close to off track","On track")))))))) | IF(OR(F418="",AC418="Completed / Handover",AC418="Cancelled"),"",IF(O418="Not awarded",IF(U418<>"",U418-TODAY(),IF(X418="","",X418-TODAY())),IF(X418="","",X418-TODAY()))) | [14 empty] | IF(OR(F418="",AJ418=""),"",IF(COUNT(AI418:AI418)=0,"",AJ418-LOOKUP(2,1/(AI418:AI418<>""),AI418:AI418))) | IF(OR(F418="",AK418=""),"",IF(COUNT(AI418:AJ418)=0,"",AK418-LOOKUP(2,1/(AI418:AJ418<>""),AI418:AJ418))) | IF(OR(F418="",AL418=""),"",IF(COUNT(AI418:AK418)=0,"",AL418-LOOKUP(2,1/(AI418:AK418<>""),AI418:AK418))) | IF(OR(F418="",AM418=""),"",IF(COUNT(AI418:AL418)=0,"",AM418-LOOKUP(2,1/(AI418:AL418<>""),AI418:AL418))) | IF(OR(F418="",AN418=""),"",IF(COUNT(AI418:AM418)=0,"",AN418-LOOKUP(2,1/(AI418:AM418<>""),AI418:AM418))) | IF(OR(F418="",AO418=""),"",IF(COUNT(AI418:AN418)=0,"",AO418-LOOKUP(2,1/(AI418:AN418<>""),AI418:AN418))) | IF(OR(F418="",AP418=""),"",IF(COUNT(AI418:AO418)=0,"",AP418-LOOKUP(2,1/(AI418:AO418<>""),AI418:AO418))) | IF(OR(F418="",AQ418=""),"",IF(COUNT(AI418:AP418)=0,"",AQ418-LOOKUP(2,1/(AI418:AP418<>""),AI418:AP418))) | IF(OR(F418="",AR418=""),"",IF(COUNT(AI418:AQ418)=0,"",AR418-LOOKUP(2,1/(AI418:AQ418<>""),AI418:AQ418))) | IF(OR(F418="",AS418=""),"",IF(COUNT(AI418:AR418)=0,"",AS418-LOOKUP(2,1/(AI418:AR418<>""),AI418:AR418))) | IF(OR(F418="",AT418=""),"",IF(COUNT(AI418:AS418)=0,"",AT418-LOOKUP(2,1/(AI418:AS418<>""),AI418:AS418))) | IF(OR(F418="",AU418=""),"",IF(COUNT(AI418:AT418)=0,"",AU418-LOOKUP(2,1/(AI418:AT418<>""),AI418:AT418))) | IF(OR(F418="",AV418=""),"",IF(COUNT(AI418:AU418)=0,"",AV418-LOOKUP(2,1/(AI418:AU418<>""),AI418:AU418))) | IF(J418="","All_Provinces",IFERROR(VLOOKUP(J418,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K418="","All_Districts",IFERROR(VLOOKUP(K418,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F419="","",ROW()-3) | [18 empty] | IF(AQ419="","",AQ419) |  |  |  | IF(W419<>"",W419,IF(OR(T419="",V419=""),"",EDATE(T419,V419))) |  |  |  |  | IF(F419="","",IF(COUNT(AI419:AV419)=0,IF(AA419="","Not started",AA419),SUBSTITUTE(LOOKUP(2,1/(AI419:AV419<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F419="",COUNT(AI419:AV419)=0),"",TODAY()-LOOKUP(2,1/(AI419:AV419<>""),AI419:AV419)) | IF(OR(F419="",COUNT(AI419:AV419)<2),"",LOOKUP(2,1/(AI419:AV419<>""),AI419:AV419)-MIN(AI419:AV419)) | IF(OR(AD419="",AC419="Not started",AC419=""),"",IFERROR(AD419-IF(VLOOKUP(AC419,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC419,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F419="","",IF(OR(AA419="Cancelled",AC419="Cancelled"),"Cancelled",IF(OR(AC419="Completed / Handover",Y419<>"",Z419>=100),"Completed — on track",IF(O419="Not awarded",IF(U419="",IF(X419="","No planned date",IF(TODAY()>X419,"Behind — past planned date",IF(X419-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U419,"Behind — award date passed",IF(U419-TODAY()<=30,"At risk — close to off track","On track"))),IF(X419="","No planned date",IF(AND(TODAY()>X419,OR(Z419="",Z419<100)),"Behind — past end date",IF(AND(T419<>"",X419<>"",Z419<>"",(Z419<100),((TODAY()-T419)/MAX(X419-T419,1)*100)-Z419>15),"Behind — progress lag",IF(AND(X419-TODAY()<=30,X419-TODAY()>=0,OR(Z419="",Z419<90)),"At risk — close to off track","On track")))))))) | IF(OR(F419="",AC419="Completed / Handover",AC419="Cancelled"),"",IF(O419="Not awarded",IF(U419<>"",U419-TODAY(),IF(X419="","",X419-TODAY())),IF(X419="","",X419-TODAY()))) | [14 empty] | IF(OR(F419="",AJ419=""),"",IF(COUNT(AI419:AI419)=0,"",AJ419-LOOKUP(2,1/(AI419:AI419<>""),AI419:AI419))) | IF(OR(F419="",AK419=""),"",IF(COUNT(AI419:AJ419)=0,"",AK419-LOOKUP(2,1/(AI419:AJ419<>""),AI419:AJ419))) | IF(OR(F419="",AL419=""),"",IF(COUNT(AI419:AK419)=0,"",AL419-LOOKUP(2,1/(AI419:AK419<>""),AI419:AK419))) | IF(OR(F419="",AM419=""),"",IF(COUNT(AI419:AL419)=0,"",AM419-LOOKUP(2,1/(AI419:AL419<>""),AI419:AL419))) | IF(OR(F419="",AN419=""),"",IF(COUNT(AI419:AM419)=0,"",AN419-LOOKUP(2,1/(AI419:AM419<>""),AI419:AM419))) | IF(OR(F419="",AO419=""),"",IF(COUNT(AI419:AN419)=0,"",AO419-LOOKUP(2,1/(AI419:AN419<>""),AI419:AN419))) | IF(OR(F419="",AP419=""),"",IF(COUNT(AI419:AO419)=0,"",AP419-LOOKUP(2,1/(AI419:AO419<>""),AI419:AO419))) | IF(OR(F419="",AQ419=""),"",IF(COUNT(AI419:AP419)=0,"",AQ419-LOOKUP(2,1/(AI419:AP419<>""),AI419:AP419))) | IF(OR(F419="",AR419=""),"",IF(COUNT(AI419:AQ419)=0,"",AR419-LOOKUP(2,1/(AI419:AQ419<>""),AI419:AQ419))) | IF(OR(F419="",AS419=""),"",IF(COUNT(AI419:AR419)=0,"",AS419-LOOKUP(2,1/(AI419:AR419<>""),AI419:AR419))) | IF(OR(F419="",AT419=""),"",IF(COUNT(AI419:AS419)=0,"",AT419-LOOKUP(2,1/(AI419:AS419<>""),AI419:AS419))) | IF(OR(F419="",AU419=""),"",IF(COUNT(AI419:AT419)=0,"",AU419-LOOKUP(2,1/(AI419:AT419<>""),AI419:AT419))) | IF(OR(F419="",AV419=""),"",IF(COUNT(AI419:AU419)=0,"",AV419-LOOKUP(2,1/(AI419:AU419<>""),AI419:AU419))) | IF(J419="","All_Provinces",IFERROR(VLOOKUP(J419,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K419="","All_Districts",IFERROR(VLOOKUP(K419,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F420="","",ROW()-3) | [18 empty] | IF(AQ420="","",AQ420) |  |  |  | IF(W420<>"",W420,IF(OR(T420="",V420=""),"",EDATE(T420,V420))) |  |  |  |  | IF(F420="","",IF(COUNT(AI420:AV420)=0,IF(AA420="","Not started",AA420),SUBSTITUTE(LOOKUP(2,1/(AI420:AV420<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F420="",COUNT(AI420:AV420)=0),"",TODAY()-LOOKUP(2,1/(AI420:AV420<>""),AI420:AV420)) | IF(OR(F420="",COUNT(AI420:AV420)<2),"",LOOKUP(2,1/(AI420:AV420<>""),AI420:AV420)-MIN(AI420:AV420)) | IF(OR(AD420="",AC420="Not started",AC420=""),"",IFERROR(AD420-IF(VLOOKUP(AC420,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC420,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F420="","",IF(OR(AA420="Cancelled",AC420="Cancelled"),"Cancelled",IF(OR(AC420="Completed / Handover",Y420<>"",Z420>=100),"Completed — on track",IF(O420="Not awarded",IF(U420="",IF(X420="","No planned date",IF(TODAY()>X420,"Behind — past planned date",IF(X420-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U420,"Behind — award date passed",IF(U420-TODAY()<=30,"At risk — close to off track","On track"))),IF(X420="","No planned date",IF(AND(TODAY()>X420,OR(Z420="",Z420<100)),"Behind — past end date",IF(AND(T420<>"",X420<>"",Z420<>"",(Z420<100),((TODAY()-T420)/MAX(X420-T420,1)*100)-Z420>15),"Behind — progress lag",IF(AND(X420-TODAY()<=30,X420-TODAY()>=0,OR(Z420="",Z420<90)),"At risk — close to off track","On track")))))))) | IF(OR(F420="",AC420="Completed / Handover",AC420="Cancelled"),"",IF(O420="Not awarded",IF(U420<>"",U420-TODAY(),IF(X420="","",X420-TODAY())),IF(X420="","",X420-TODAY()))) | [14 empty] | IF(OR(F420="",AJ420=""),"",IF(COUNT(AI420:AI420)=0,"",AJ420-LOOKUP(2,1/(AI420:AI420<>""),AI420:AI420))) | IF(OR(F420="",AK420=""),"",IF(COUNT(AI420:AJ420)=0,"",AK420-LOOKUP(2,1/(AI420:AJ420<>""),AI420:AJ420))) | IF(OR(F420="",AL420=""),"",IF(COUNT(AI420:AK420)=0,"",AL420-LOOKUP(2,1/(AI420:AK420<>""),AI420:AK420))) | IF(OR(F420="",AM420=""),"",IF(COUNT(AI420:AL420)=0,"",AM420-LOOKUP(2,1/(AI420:AL420<>""),AI420:AL420))) | IF(OR(F420="",AN420=""),"",IF(COUNT(AI420:AM420)=0,"",AN420-LOOKUP(2,1/(AI420:AM420<>""),AI420:AM420))) | IF(OR(F420="",AO420=""),"",IF(COUNT(AI420:AN420)=0,"",AO420-LOOKUP(2,1/(AI420:AN420<>""),AI420:AN420))) | IF(OR(F420="",AP420=""),"",IF(COUNT(AI420:AO420)=0,"",AP420-LOOKUP(2,1/(AI420:AO420<>""),AI420:AO420))) | IF(OR(F420="",AQ420=""),"",IF(COUNT(AI420:AP420)=0,"",AQ420-LOOKUP(2,1/(AI420:AP420<>""),AI420:AP420))) | IF(OR(F420="",AR420=""),"",IF(COUNT(AI420:AQ420)=0,"",AR420-LOOKUP(2,1/(AI420:AQ420<>""),AI420:AQ420))) | IF(OR(F420="",AS420=""),"",IF(COUNT(AI420:AR420)=0,"",AS420-LOOKUP(2,1/(AI420:AR420<>""),AI420:AR420))) | IF(OR(F420="",AT420=""),"",IF(COUNT(AI420:AS420)=0,"",AT420-LOOKUP(2,1/(AI420:AS420<>""),AI420:AS420))) | IF(OR(F420="",AU420=""),"",IF(COUNT(AI420:AT420)=0,"",AU420-LOOKUP(2,1/(AI420:AT420<>""),AI420:AT420))) | IF(OR(F420="",AV420=""),"",IF(COUNT(AI420:AU420)=0,"",AV420-LOOKUP(2,1/(AI420:AU420<>""),AI420:AU420))) | IF(J420="","All_Provinces",IFERROR(VLOOKUP(J420,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K420="","All_Districts",IFERROR(VLOOKUP(K420,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F421="","",ROW()-3) | [18 empty] | IF(AQ421="","",AQ421) |  |  |  | IF(W421<>"",W421,IF(OR(T421="",V421=""),"",EDATE(T421,V421))) |  |  |  |  | IF(F421="","",IF(COUNT(AI421:AV421)=0,IF(AA421="","Not started",AA421),SUBSTITUTE(LOOKUP(2,1/(AI421:AV421<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F421="",COUNT(AI421:AV421)=0),"",TODAY()-LOOKUP(2,1/(AI421:AV421<>""),AI421:AV421)) | IF(OR(F421="",COUNT(AI421:AV421)<2),"",LOOKUP(2,1/(AI421:AV421<>""),AI421:AV421)-MIN(AI421:AV421)) | IF(OR(AD421="",AC421="Not started",AC421=""),"",IFERROR(AD421-IF(VLOOKUP(AC421,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC421,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F421="","",IF(OR(AA421="Cancelled",AC421="Cancelled"),"Cancelled",IF(OR(AC421="Completed / Handover",Y421<>"",Z421>=100),"Completed — on track",IF(O421="Not awarded",IF(U421="",IF(X421="","No planned date",IF(TODAY()>X421,"Behind — past planned date",IF(X421-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U421,"Behind — award date passed",IF(U421-TODAY()<=30,"At risk — close to off track","On track"))),IF(X421="","No planned date",IF(AND(TODAY()>X421,OR(Z421="",Z421<100)),"Behind — past end date",IF(AND(T421<>"",X421<>"",Z421<>"",(Z421<100),((TODAY()-T421)/MAX(X421-T421,1)*100)-Z421>15),"Behind — progress lag",IF(AND(X421-TODAY()<=30,X421-TODAY()>=0,OR(Z421="",Z421<90)),"At risk — close to off track","On track")))))))) | IF(OR(F421="",AC421="Completed / Handover",AC421="Cancelled"),"",IF(O421="Not awarded",IF(U421<>"",U421-TODAY(),IF(X421="","",X421-TODAY())),IF(X421="","",X421-TODAY()))) | [14 empty] | IF(OR(F421="",AJ421=""),"",IF(COUNT(AI421:AI421)=0,"",AJ421-LOOKUP(2,1/(AI421:AI421<>""),AI421:AI421))) | IF(OR(F421="",AK421=""),"",IF(COUNT(AI421:AJ421)=0,"",AK421-LOOKUP(2,1/(AI421:AJ421<>""),AI421:AJ421))) | IF(OR(F421="",AL421=""),"",IF(COUNT(AI421:AK421)=0,"",AL421-LOOKUP(2,1/(AI421:AK421<>""),AI421:AK421))) | IF(OR(F421="",AM421=""),"",IF(COUNT(AI421:AL421)=0,"",AM421-LOOKUP(2,1/(AI421:AL421<>""),AI421:AL421))) | IF(OR(F421="",AN421=""),"",IF(COUNT(AI421:AM421)=0,"",AN421-LOOKUP(2,1/(AI421:AM421<>""),AI421:AM421))) | IF(OR(F421="",AO421=""),"",IF(COUNT(AI421:AN421)=0,"",AO421-LOOKUP(2,1/(AI421:AN421<>""),AI421:AN421))) | IF(OR(F421="",AP421=""),"",IF(COUNT(AI421:AO421)=0,"",AP421-LOOKUP(2,1/(AI421:AO421<>""),AI421:AO421))) | IF(OR(F421="",AQ421=""),"",IF(COUNT(AI421:AP421)=0,"",AQ421-LOOKUP(2,1/(AI421:AP421<>""),AI421:AP421))) | IF(OR(F421="",AR421=""),"",IF(COUNT(AI421:AQ421)=0,"",AR421-LOOKUP(2,1/(AI421:AQ421<>""),AI421:AQ421))) | IF(OR(F421="",AS421=""),"",IF(COUNT(AI421:AR421)=0,"",AS421-LOOKUP(2,1/(AI421:AR421<>""),AI421:AR421))) | IF(OR(F421="",AT421=""),"",IF(COUNT(AI421:AS421)=0,"",AT421-LOOKUP(2,1/(AI421:AS421<>""),AI421:AS421))) | IF(OR(F421="",AU421=""),"",IF(COUNT(AI421:AT421)=0,"",AU421-LOOKUP(2,1/(AI421:AT421<>""),AI421:AT421))) | IF(OR(F421="",AV421=""),"",IF(COUNT(AI421:AU421)=0,"",AV421-LOOKUP(2,1/(AI421:AU421<>""),AI421:AU421))) | IF(J421="","All_Provinces",IFERROR(VLOOKUP(J421,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K421="","All_Districts",IFERROR(VLOOKUP(K421,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F422="","",ROW()-3) | [18 empty] | IF(AQ422="","",AQ422) |  |  |  | IF(W422<>"",W422,IF(OR(T422="",V422=""),"",EDATE(T422,V422))) |  |  |  |  | IF(F422="","",IF(COUNT(AI422:AV422)=0,IF(AA422="","Not started",AA422),SUBSTITUTE(LOOKUP(2,1/(AI422:AV422<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F422="",COUNT(AI422:AV422)=0),"",TODAY()-LOOKUP(2,1/(AI422:AV422<>""),AI422:AV422)) | IF(OR(F422="",COUNT(AI422:AV422)<2),"",LOOKUP(2,1/(AI422:AV422<>""),AI422:AV422)-MIN(AI422:AV422)) | IF(OR(AD422="",AC422="Not started",AC422=""),"",IFERROR(AD422-IF(VLOOKUP(AC422,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC422,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F422="","",IF(OR(AA422="Cancelled",AC422="Cancelled"),"Cancelled",IF(OR(AC422="Completed / Handover",Y422<>"",Z422>=100),"Completed — on track",IF(O422="Not awarded",IF(U422="",IF(X422="","No planned date",IF(TODAY()>X422,"Behind — past planned date",IF(X422-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U422,"Behind — award date passed",IF(U422-TODAY()<=30,"At risk — close to off track","On track"))),IF(X422="","No planned date",IF(AND(TODAY()>X422,OR(Z422="",Z422<100)),"Behind — past end date",IF(AND(T422<>"",X422<>"",Z422<>"",(Z422<100),((TODAY()-T422)/MAX(X422-T422,1)*100)-Z422>15),"Behind — progress lag",IF(AND(X422-TODAY()<=30,X422-TODAY()>=0,OR(Z422="",Z422<90)),"At risk — close to off track","On track")))))))) | IF(OR(F422="",AC422="Completed / Handover",AC422="Cancelled"),"",IF(O422="Not awarded",IF(U422<>"",U422-TODAY(),IF(X422="","",X422-TODAY())),IF(X422="","",X422-TODAY()))) | [14 empty] | IF(OR(F422="",AJ422=""),"",IF(COUNT(AI422:AI422)=0,"",AJ422-LOOKUP(2,1/(AI422:AI422<>""),AI422:AI422))) | IF(OR(F422="",AK422=""),"",IF(COUNT(AI422:AJ422)=0,"",AK422-LOOKUP(2,1/(AI422:AJ422<>""),AI422:AJ422))) | IF(OR(F422="",AL422=""),"",IF(COUNT(AI422:AK422)=0,"",AL422-LOOKUP(2,1/(AI422:AK422<>""),AI422:AK422))) | IF(OR(F422="",AM422=""),"",IF(COUNT(AI422:AL422)=0,"",AM422-LOOKUP(2,1/(AI422:AL422<>""),AI422:AL422))) | IF(OR(F422="",AN422=""),"",IF(COUNT(AI422:AM422)=0,"",AN422-LOOKUP(2,1/(AI422:AM422<>""),AI422:AM422))) | IF(OR(F422="",AO422=""),"",IF(COUNT(AI422:AN422)=0,"",AO422-LOOKUP(2,1/(AI422:AN422<>""),AI422:AN422))) | IF(OR(F422="",AP422=""),"",IF(COUNT(AI422:AO422)=0,"",AP422-LOOKUP(2,1/(AI422:AO422<>""),AI422:AO422))) | IF(OR(F422="",AQ422=""),"",IF(COUNT(AI422:AP422)=0,"",AQ422-LOOKUP(2,1/(AI422:AP422<>""),AI422:AP422))) | IF(OR(F422="",AR422=""),"",IF(COUNT(AI422:AQ422)=0,"",AR422-LOOKUP(2,1/(AI422:AQ422<>""),AI422:AQ422))) | IF(OR(F422="",AS422=""),"",IF(COUNT(AI422:AR422)=0,"",AS422-LOOKUP(2,1/(AI422:AR422<>""),AI422:AR422))) | IF(OR(F422="",AT422=""),"",IF(COUNT(AI422:AS422)=0,"",AT422-LOOKUP(2,1/(AI422:AS422<>""),AI422:AS422))) | IF(OR(F422="",AU422=""),"",IF(COUNT(AI422:AT422)=0,"",AU422-LOOKUP(2,1/(AI422:AT422<>""),AI422:AT422))) | IF(OR(F422="",AV422=""),"",IF(COUNT(AI422:AU422)=0,"",AV422-LOOKUP(2,1/(AI422:AU422<>""),AI422:AU422))) | IF(J422="","All_Provinces",IFERROR(VLOOKUP(J422,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K422="","All_Districts",IFERROR(VLOOKUP(K422,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F423="","",ROW()-3) | [18 empty] | IF(AQ423="","",AQ423) |  |  |  | IF(W423<>"",W423,IF(OR(T423="",V423=""),"",EDATE(T423,V423))) |  |  |  |  | IF(F423="","",IF(COUNT(AI423:AV423)=0,IF(AA423="","Not started",AA423),SUBSTITUTE(LOOKUP(2,1/(AI423:AV423<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F423="",COUNT(AI423:AV423)=0),"",TODAY()-LOOKUP(2,1/(AI423:AV423<>""),AI423:AV423)) | IF(OR(F423="",COUNT(AI423:AV423)<2),"",LOOKUP(2,1/(AI423:AV423<>""),AI423:AV423)-MIN(AI423:AV423)) | IF(OR(AD423="",AC423="Not started",AC423=""),"",IFERROR(AD423-IF(VLOOKUP(AC423,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC423,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F423="","",IF(OR(AA423="Cancelled",AC423="Cancelled"),"Cancelled",IF(OR(AC423="Completed / Handover",Y423<>"",Z423>=100),"Completed — on track",IF(O423="Not awarded",IF(U423="",IF(X423="","No planned date",IF(TODAY()>X423,"Behind — past planned date",IF(X423-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U423,"Behind — award date passed",IF(U423-TODAY()<=30,"At risk — close to off track","On track"))),IF(X423="","No planned date",IF(AND(TODAY()>X423,OR(Z423="",Z423<100)),"Behind — past end date",IF(AND(T423<>"",X423<>"",Z423<>"",(Z423<100),((TODAY()-T423)/MAX(X423-T423,1)*100)-Z423>15),"Behind — progress lag",IF(AND(X423-TODAY()<=30,X423-TODAY()>=0,OR(Z423="",Z423<90)),"At risk — close to off track","On track")))))))) | IF(OR(F423="",AC423="Completed / Handover",AC423="Cancelled"),"",IF(O423="Not awarded",IF(U423<>"",U423-TODAY(),IF(X423="","",X423-TODAY())),IF(X423="","",X423-TODAY()))) | [14 empty] | IF(OR(F423="",AJ423=""),"",IF(COUNT(AI423:AI423)=0,"",AJ423-LOOKUP(2,1/(AI423:AI423<>""),AI423:AI423))) | IF(OR(F423="",AK423=""),"",IF(COUNT(AI423:AJ423)=0,"",AK423-LOOKUP(2,1/(AI423:AJ423<>""),AI423:AJ423))) | IF(OR(F423="",AL423=""),"",IF(COUNT(AI423:AK423)=0,"",AL423-LOOKUP(2,1/(AI423:AK423<>""),AI423:AK423))) | IF(OR(F423="",AM423=""),"",IF(COUNT(AI423:AL423)=0,"",AM423-LOOKUP(2,1/(AI423:AL423<>""),AI423:AL423))) | IF(OR(F423="",AN423=""),"",IF(COUNT(AI423:AM423)=0,"",AN423-LOOKUP(2,1/(AI423:AM423<>""),AI423:AM423))) | IF(OR(F423="",AO423=""),"",IF(COUNT(AI423:AN423)=0,"",AO423-LOOKUP(2,1/(AI423:AN423<>""),AI423:AN423))) | IF(OR(F423="",AP423=""),"",IF(COUNT(AI423:AO423)=0,"",AP423-LOOKUP(2,1/(AI423:AO423<>""),AI423:AO423))) | IF(OR(F423="",AQ423=""),"",IF(COUNT(AI423:AP423)=0,"",AQ423-LOOKUP(2,1/(AI423:AP423<>""),AI423:AP423))) | IF(OR(F423="",AR423=""),"",IF(COUNT(AI423:AQ423)=0,"",AR423-LOOKUP(2,1/(AI423:AQ423<>""),AI423:AQ423))) | IF(OR(F423="",AS423=""),"",IF(COUNT(AI423:AR423)=0,"",AS423-LOOKUP(2,1/(AI423:AR423<>""),AI423:AR423))) | IF(OR(F423="",AT423=""),"",IF(COUNT(AI423:AS423)=0,"",AT423-LOOKUP(2,1/(AI423:AS423<>""),AI423:AS423))) | IF(OR(F423="",AU423=""),"",IF(COUNT(AI423:AT423)=0,"",AU423-LOOKUP(2,1/(AI423:AT423<>""),AI423:AT423))) | IF(OR(F423="",AV423=""),"",IF(COUNT(AI423:AU423)=0,"",AV423-LOOKUP(2,1/(AI423:AU423<>""),AI423:AU423))) | IF(J423="","All_Provinces",IFERROR(VLOOKUP(J423,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K423="","All_Districts",IFERROR(VLOOKUP(K423,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F424="","",ROW()-3) | [18 empty] | IF(AQ424="","",AQ424) |  |  |  | IF(W424<>"",W424,IF(OR(T424="",V424=""),"",EDATE(T424,V424))) |  |  |  |  | IF(F424="","",IF(COUNT(AI424:AV424)=0,IF(AA424="","Not started",AA424),SUBSTITUTE(LOOKUP(2,1/(AI424:AV424<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F424="",COUNT(AI424:AV424)=0),"",TODAY()-LOOKUP(2,1/(AI424:AV424<>""),AI424:AV424)) | IF(OR(F424="",COUNT(AI424:AV424)<2),"",LOOKUP(2,1/(AI424:AV424<>""),AI424:AV424)-MIN(AI424:AV424)) | IF(OR(AD424="",AC424="Not started",AC424=""),"",IFERROR(AD424-IF(VLOOKUP(AC424,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC424,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F424="","",IF(OR(AA424="Cancelled",AC424="Cancelled"),"Cancelled",IF(OR(AC424="Completed / Handover",Y424<>"",Z424>=100),"Completed — on track",IF(O424="Not awarded",IF(U424="",IF(X424="","No planned date",IF(TODAY()>X424,"Behind — past planned date",IF(X424-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U424,"Behind — award date passed",IF(U424-TODAY()<=30,"At risk — close to off track","On track"))),IF(X424="","No planned date",IF(AND(TODAY()>X424,OR(Z424="",Z424<100)),"Behind — past end date",IF(AND(T424<>"",X424<>"",Z424<>"",(Z424<100),((TODAY()-T424)/MAX(X424-T424,1)*100)-Z424>15),"Behind — progress lag",IF(AND(X424-TODAY()<=30,X424-TODAY()>=0,OR(Z424="",Z424<90)),"At risk — close to off track","On track")))))))) | IF(OR(F424="",AC424="Completed / Handover",AC424="Cancelled"),"",IF(O424="Not awarded",IF(U424<>"",U424-TODAY(),IF(X424="","",X424-TODAY())),IF(X424="","",X424-TODAY()))) | [14 empty] | IF(OR(F424="",AJ424=""),"",IF(COUNT(AI424:AI424)=0,"",AJ424-LOOKUP(2,1/(AI424:AI424<>""),AI424:AI424))) | IF(OR(F424="",AK424=""),"",IF(COUNT(AI424:AJ424)=0,"",AK424-LOOKUP(2,1/(AI424:AJ424<>""),AI424:AJ424))) | IF(OR(F424="",AL424=""),"",IF(COUNT(AI424:AK424)=0,"",AL424-LOOKUP(2,1/(AI424:AK424<>""),AI424:AK424))) | IF(OR(F424="",AM424=""),"",IF(COUNT(AI424:AL424)=0,"",AM424-LOOKUP(2,1/(AI424:AL424<>""),AI424:AL424))) | IF(OR(F424="",AN424=""),"",IF(COUNT(AI424:AM424)=0,"",AN424-LOOKUP(2,1/(AI424:AM424<>""),AI424:AM424))) | IF(OR(F424="",AO424=""),"",IF(COUNT(AI424:AN424)=0,"",AO424-LOOKUP(2,1/(AI424:AN424<>""),AI424:AN424))) | IF(OR(F424="",AP424=""),"",IF(COUNT(AI424:AO424)=0,"",AP424-LOOKUP(2,1/(AI424:AO424<>""),AI424:AO424))) | IF(OR(F424="",AQ424=""),"",IF(COUNT(AI424:AP424)=0,"",AQ424-LOOKUP(2,1/(AI424:AP424<>""),AI424:AP424))) | IF(OR(F424="",AR424=""),"",IF(COUNT(AI424:AQ424)=0,"",AR424-LOOKUP(2,1/(AI424:AQ424<>""),AI424:AQ424))) | IF(OR(F424="",AS424=""),"",IF(COUNT(AI424:AR424)=0,"",AS424-LOOKUP(2,1/(AI424:AR424<>""),AI424:AR424))) | IF(OR(F424="",AT424=""),"",IF(COUNT(AI424:AS424)=0,"",AT424-LOOKUP(2,1/(AI424:AS424<>""),AI424:AS424))) | IF(OR(F424="",AU424=""),"",IF(COUNT(AI424:AT424)=0,"",AU424-LOOKUP(2,1/(AI424:AT424<>""),AI424:AT424))) | IF(OR(F424="",AV424=""),"",IF(COUNT(AI424:AU424)=0,"",AV424-LOOKUP(2,1/(AI424:AU424<>""),AI424:AU424))) | IF(J424="","All_Provinces",IFERROR(VLOOKUP(J424,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K424="","All_Districts",IFERROR(VLOOKUP(K424,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F425="","",ROW()-3) | [18 empty] | IF(AQ425="","",AQ425) |  |  |  | IF(W425<>"",W425,IF(OR(T425="",V425=""),"",EDATE(T425,V425))) |  |  |  |  | IF(F425="","",IF(COUNT(AI425:AV425)=0,IF(AA425="","Not started",AA425),SUBSTITUTE(LOOKUP(2,1/(AI425:AV425<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F425="",COUNT(AI425:AV425)=0),"",TODAY()-LOOKUP(2,1/(AI425:AV425<>""),AI425:AV425)) | IF(OR(F425="",COUNT(AI425:AV425)<2),"",LOOKUP(2,1/(AI425:AV425<>""),AI425:AV425)-MIN(AI425:AV425)) | IF(OR(AD425="",AC425="Not started",AC425=""),"",IFERROR(AD425-IF(VLOOKUP(AC425,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC425,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F425="","",IF(OR(AA425="Cancelled",AC425="Cancelled"),"Cancelled",IF(OR(AC425="Completed / Handover",Y425<>"",Z425>=100),"Completed — on track",IF(O425="Not awarded",IF(U425="",IF(X425="","No planned date",IF(TODAY()>X425,"Behind — past planned date",IF(X425-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U425,"Behind — award date passed",IF(U425-TODAY()<=30,"At risk — close to off track","On track"))),IF(X425="","No planned date",IF(AND(TODAY()>X425,OR(Z425="",Z425<100)),"Behind — past end date",IF(AND(T425<>"",X425<>"",Z425<>"",(Z425<100),((TODAY()-T425)/MAX(X425-T425,1)*100)-Z425>15),"Behind — progress lag",IF(AND(X425-TODAY()<=30,X425-TODAY()>=0,OR(Z425="",Z425<90)),"At risk — close to off track","On track")))))))) | IF(OR(F425="",AC425="Completed / Handover",AC425="Cancelled"),"",IF(O425="Not awarded",IF(U425<>"",U425-TODAY(),IF(X425="","",X425-TODAY())),IF(X425="","",X425-TODAY()))) | [14 empty] | IF(OR(F425="",AJ425=""),"",IF(COUNT(AI425:AI425)=0,"",AJ425-LOOKUP(2,1/(AI425:AI425<>""),AI425:AI425))) | IF(OR(F425="",AK425=""),"",IF(COUNT(AI425:AJ425)=0,"",AK425-LOOKUP(2,1/(AI425:AJ425<>""),AI425:AJ425))) | IF(OR(F425="",AL425=""),"",IF(COUNT(AI425:AK425)=0,"",AL425-LOOKUP(2,1/(AI425:AK425<>""),AI425:AK425))) | IF(OR(F425="",AM425=""),"",IF(COUNT(AI425:AL425)=0,"",AM425-LOOKUP(2,1/(AI425:AL425<>""),AI425:AL425))) | IF(OR(F425="",AN425=""),"",IF(COUNT(AI425:AM425)=0,"",AN425-LOOKUP(2,1/(AI425:AM425<>""),AI425:AM425))) | IF(OR(F425="",AO425=""),"",IF(COUNT(AI425:AN425)=0,"",AO425-LOOKUP(2,1/(AI425:AN425<>""),AI425:AN425))) | IF(OR(F425="",AP425=""),"",IF(COUNT(AI425:AO425)=0,"",AP425-LOOKUP(2,1/(AI425:AO425<>""),AI425:AO425))) | IF(OR(F425="",AQ425=""),"",IF(COUNT(AI425:AP425)=0,"",AQ425-LOOKUP(2,1/(AI425:AP425<>""),AI425:AP425))) | IF(OR(F425="",AR425=""),"",IF(COUNT(AI425:AQ425)=0,"",AR425-LOOKUP(2,1/(AI425:AQ425<>""),AI425:AQ425))) | IF(OR(F425="",AS425=""),"",IF(COUNT(AI425:AR425)=0,"",AS425-LOOKUP(2,1/(AI425:AR425<>""),AI425:AR425))) | IF(OR(F425="",AT425=""),"",IF(COUNT(AI425:AS425)=0,"",AT425-LOOKUP(2,1/(AI425:AS425<>""),AI425:AS425))) | IF(OR(F425="",AU425=""),"",IF(COUNT(AI425:AT425)=0,"",AU425-LOOKUP(2,1/(AI425:AT425<>""),AI425:AT425))) | IF(OR(F425="",AV425=""),"",IF(COUNT(AI425:AU425)=0,"",AV425-LOOKUP(2,1/(AI425:AU425<>""),AI425:AU425))) | IF(J425="","All_Provinces",IFERROR(VLOOKUP(J425,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K425="","All_Districts",IFERROR(VLOOKUP(K425,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F426="","",ROW()-3) | [18 empty] | IF(AQ426="","",AQ426) |  |  |  | IF(W426<>"",W426,IF(OR(T426="",V426=""),"",EDATE(T426,V426))) |  |  |  |  | IF(F426="","",IF(COUNT(AI426:AV426)=0,IF(AA426="","Not started",AA426),SUBSTITUTE(LOOKUP(2,1/(AI426:AV426<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F426="",COUNT(AI426:AV426)=0),"",TODAY()-LOOKUP(2,1/(AI426:AV426<>""),AI426:AV426)) | IF(OR(F426="",COUNT(AI426:AV426)<2),"",LOOKUP(2,1/(AI426:AV426<>""),AI426:AV426)-MIN(AI426:AV426)) | IF(OR(AD426="",AC426="Not started",AC426=""),"",IFERROR(AD426-IF(VLOOKUP(AC426,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC426,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F426="","",IF(OR(AA426="Cancelled",AC426="Cancelled"),"Cancelled",IF(OR(AC426="Completed / Handover",Y426<>"",Z426>=100),"Completed — on track",IF(O426="Not awarded",IF(U426="",IF(X426="","No planned date",IF(TODAY()>X426,"Behind — past planned date",IF(X426-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U426,"Behind — award date passed",IF(U426-TODAY()<=30,"At risk — close to off track","On track"))),IF(X426="","No planned date",IF(AND(TODAY()>X426,OR(Z426="",Z426<100)),"Behind — past end date",IF(AND(T426<>"",X426<>"",Z426<>"",(Z426<100),((TODAY()-T426)/MAX(X426-T426,1)*100)-Z426>15),"Behind — progress lag",IF(AND(X426-TODAY()<=30,X426-TODAY()>=0,OR(Z426="",Z426<90)),"At risk — close to off track","On track")))))))) | IF(OR(F426="",AC426="Completed / Handover",AC426="Cancelled"),"",IF(O426="Not awarded",IF(U426<>"",U426-TODAY(),IF(X426="","",X426-TODAY())),IF(X426="","",X426-TODAY()))) | [14 empty] | IF(OR(F426="",AJ426=""),"",IF(COUNT(AI426:AI426)=0,"",AJ426-LOOKUP(2,1/(AI426:AI426<>""),AI426:AI426))) | IF(OR(F426="",AK426=""),"",IF(COUNT(AI426:AJ426)=0,"",AK426-LOOKUP(2,1/(AI426:AJ426<>""),AI426:AJ426))) | IF(OR(F426="",AL426=""),"",IF(COUNT(AI426:AK426)=0,"",AL426-LOOKUP(2,1/(AI426:AK426<>""),AI426:AK426))) | IF(OR(F426="",AM426=""),"",IF(COUNT(AI426:AL426)=0,"",AM426-LOOKUP(2,1/(AI426:AL426<>""),AI426:AL426))) | IF(OR(F426="",AN426=""),"",IF(COUNT(AI426:AM426)=0,"",AN426-LOOKUP(2,1/(AI426:AM426<>""),AI426:AM426))) | IF(OR(F426="",AO426=""),"",IF(COUNT(AI426:AN426)=0,"",AO426-LOOKUP(2,1/(AI426:AN426<>""),AI426:AN426))) | IF(OR(F426="",AP426=""),"",IF(COUNT(AI426:AO426)=0,"",AP426-LOOKUP(2,1/(AI426:AO426<>""),AI426:AO426))) | IF(OR(F426="",AQ426=""),"",IF(COUNT(AI426:AP426)=0,"",AQ426-LOOKUP(2,1/(AI426:AP426<>""),AI426:AP426))) | IF(OR(F426="",AR426=""),"",IF(COUNT(AI426:AQ426)=0,"",AR426-LOOKUP(2,1/(AI426:AQ426<>""),AI426:AQ426))) | IF(OR(F426="",AS426=""),"",IF(COUNT(AI426:AR426)=0,"",AS426-LOOKUP(2,1/(AI426:AR426<>""),AI426:AR426))) | IF(OR(F426="",AT426=""),"",IF(COUNT(AI426:AS426)=0,"",AT426-LOOKUP(2,1/(AI426:AS426<>""),AI426:AS426))) | IF(OR(F426="",AU426=""),"",IF(COUNT(AI426:AT426)=0,"",AU426-LOOKUP(2,1/(AI426:AT426<>""),AI426:AT426))) | IF(OR(F426="",AV426=""),"",IF(COUNT(AI426:AU426)=0,"",AV426-LOOKUP(2,1/(AI426:AU426<>""),AI426:AU426))) | IF(J426="","All_Provinces",IFERROR(VLOOKUP(J426,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K426="","All_Districts",IFERROR(VLOOKUP(K426,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F427="","",ROW()-3) | [18 empty] | IF(AQ427="","",AQ427) |  |  |  | IF(W427<>"",W427,IF(OR(T427="",V427=""),"",EDATE(T427,V427))) |  |  |  |  | IF(F427="","",IF(COUNT(AI427:AV427)=0,IF(AA427="","Not started",AA427),SUBSTITUTE(LOOKUP(2,1/(AI427:AV427<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F427="",COUNT(AI427:AV427)=0),"",TODAY()-LOOKUP(2,1/(AI427:AV427<>""),AI427:AV427)) | IF(OR(F427="",COUNT(AI427:AV427)<2),"",LOOKUP(2,1/(AI427:AV427<>""),AI427:AV427)-MIN(AI427:AV427)) | IF(OR(AD427="",AC427="Not started",AC427=""),"",IFERROR(AD427-IF(VLOOKUP(AC427,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC427,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F427="","",IF(OR(AA427="Cancelled",AC427="Cancelled"),"Cancelled",IF(OR(AC427="Completed / Handover",Y427<>"",Z427>=100),"Completed — on track",IF(O427="Not awarded",IF(U427="",IF(X427="","No planned date",IF(TODAY()>X427,"Behind — past planned date",IF(X427-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U427,"Behind — award date passed",IF(U427-TODAY()<=30,"At risk — close to off track","On track"))),IF(X427="","No planned date",IF(AND(TODAY()>X427,OR(Z427="",Z427<100)),"Behind — past end date",IF(AND(T427<>"",X427<>"",Z427<>"",(Z427<100),((TODAY()-T427)/MAX(X427-T427,1)*100)-Z427>15),"Behind — progress lag",IF(AND(X427-TODAY()<=30,X427-TODAY()>=0,OR(Z427="",Z427<90)),"At risk — close to off track","On track")))))))) | IF(OR(F427="",AC427="Completed / Handover",AC427="Cancelled"),"",IF(O427="Not awarded",IF(U427<>"",U427-TODAY(),IF(X427="","",X427-TODAY())),IF(X427="","",X427-TODAY()))) | [14 empty] | IF(OR(F427="",AJ427=""),"",IF(COUNT(AI427:AI427)=0,"",AJ427-LOOKUP(2,1/(AI427:AI427<>""),AI427:AI427))) | IF(OR(F427="",AK427=""),"",IF(COUNT(AI427:AJ427)=0,"",AK427-LOOKUP(2,1/(AI427:AJ427<>""),AI427:AJ427))) | IF(OR(F427="",AL427=""),"",IF(COUNT(AI427:AK427)=0,"",AL427-LOOKUP(2,1/(AI427:AK427<>""),AI427:AK427))) | IF(OR(F427="",AM427=""),"",IF(COUNT(AI427:AL427)=0,"",AM427-LOOKUP(2,1/(AI427:AL427<>""),AI427:AL427))) | IF(OR(F427="",AN427=""),"",IF(COUNT(AI427:AM427)=0,"",AN427-LOOKUP(2,1/(AI427:AM427<>""),AI427:AM427))) | IF(OR(F427="",AO427=""),"",IF(COUNT(AI427:AN427)=0,"",AO427-LOOKUP(2,1/(AI427:AN427<>""),AI427:AN427))) | IF(OR(F427="",AP427=""),"",IF(COUNT(AI427:AO427)=0,"",AP427-LOOKUP(2,1/(AI427:AO427<>""),AI427:AO427))) | IF(OR(F427="",AQ427=""),"",IF(COUNT(AI427:AP427)=0,"",AQ427-LOOKUP(2,1/(AI427:AP427<>""),AI427:AP427))) | IF(OR(F427="",AR427=""),"",IF(COUNT(AI427:AQ427)=0,"",AR427-LOOKUP(2,1/(AI427:AQ427<>""),AI427:AQ427))) | IF(OR(F427="",AS427=""),"",IF(COUNT(AI427:AR427)=0,"",AS427-LOOKUP(2,1/(AI427:AR427<>""),AI427:AR427))) | IF(OR(F427="",AT427=""),"",IF(COUNT(AI427:AS427)=0,"",AT427-LOOKUP(2,1/(AI427:AS427<>""),AI427:AS427))) | IF(OR(F427="",AU427=""),"",IF(COUNT(AI427:AT427)=0,"",AU427-LOOKUP(2,1/(AI427:AT427<>""),AI427:AT427))) | IF(OR(F427="",AV427=""),"",IF(COUNT(AI427:AU427)=0,"",AV427-LOOKUP(2,1/(AI427:AU427<>""),AI427:AU427))) | IF(J427="","All_Provinces",IFERROR(VLOOKUP(J427,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K427="","All_Districts",IFERROR(VLOOKUP(K427,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F428="","",ROW()-3) | [18 empty] | IF(AQ428="","",AQ428) |  |  |  | IF(W428<>"",W428,IF(OR(T428="",V428=""),"",EDATE(T428,V428))) |  |  |  |  | IF(F428="","",IF(COUNT(AI428:AV428)=0,IF(AA428="","Not started",AA428),SUBSTITUTE(LOOKUP(2,1/(AI428:AV428<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F428="",COUNT(AI428:AV428)=0),"",TODAY()-LOOKUP(2,1/(AI428:AV428<>""),AI428:AV428)) | IF(OR(F428="",COUNT(AI428:AV428)<2),"",LOOKUP(2,1/(AI428:AV428<>""),AI428:AV428)-MIN(AI428:AV428)) | IF(OR(AD428="",AC428="Not started",AC428=""),"",IFERROR(AD428-IF(VLOOKUP(AC428,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC428,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F428="","",IF(OR(AA428="Cancelled",AC428="Cancelled"),"Cancelled",IF(OR(AC428="Completed / Handover",Y428<>"",Z428>=100),"Completed — on track",IF(O428="Not awarded",IF(U428="",IF(X428="","No planned date",IF(TODAY()>X428,"Behind — past planned date",IF(X428-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U428,"Behind — award date passed",IF(U428-TODAY()<=30,"At risk — close to off track","On track"))),IF(X428="","No planned date",IF(AND(TODAY()>X428,OR(Z428="",Z428<100)),"Behind — past end date",IF(AND(T428<>"",X428<>"",Z428<>"",(Z428<100),((TODAY()-T428)/MAX(X428-T428,1)*100)-Z428>15),"Behind — progress lag",IF(AND(X428-TODAY()<=30,X428-TODAY()>=0,OR(Z428="",Z428<90)),"At risk — close to off track","On track")))))))) | IF(OR(F428="",AC428="Completed / Handover",AC428="Cancelled"),"",IF(O428="Not awarded",IF(U428<>"",U428-TODAY(),IF(X428="","",X428-TODAY())),IF(X428="","",X428-TODAY()))) | [14 empty] | IF(OR(F428="",AJ428=""),"",IF(COUNT(AI428:AI428)=0,"",AJ428-LOOKUP(2,1/(AI428:AI428<>""),AI428:AI428))) | IF(OR(F428="",AK428=""),"",IF(COUNT(AI428:AJ428)=0,"",AK428-LOOKUP(2,1/(AI428:AJ428<>""),AI428:AJ428))) | IF(OR(F428="",AL428=""),"",IF(COUNT(AI428:AK428)=0,"",AL428-LOOKUP(2,1/(AI428:AK428<>""),AI428:AK428))) | IF(OR(F428="",AM428=""),"",IF(COUNT(AI428:AL428)=0,"",AM428-LOOKUP(2,1/(AI428:AL428<>""),AI428:AL428))) | IF(OR(F428="",AN428=""),"",IF(COUNT(AI428:AM428)=0,"",AN428-LOOKUP(2,1/(AI428:AM428<>""),AI428:AM428))) | IF(OR(F428="",AO428=""),"",IF(COUNT(AI428:AN428)=0,"",AO428-LOOKUP(2,1/(AI428:AN428<>""),AI428:AN428))) | IF(OR(F428="",AP428=""),"",IF(COUNT(AI428:AO428)=0,"",AP428-LOOKUP(2,1/(AI428:AO428<>""),AI428:AO428))) | IF(OR(F428="",AQ428=""),"",IF(COUNT(AI428:AP428)=0,"",AQ428-LOOKUP(2,1/(AI428:AP428<>""),AI428:AP428))) | IF(OR(F428="",AR428=""),"",IF(COUNT(AI428:AQ428)=0,"",AR428-LOOKUP(2,1/(AI428:AQ428<>""),AI428:AQ428))) | IF(OR(F428="",AS428=""),"",IF(COUNT(AI428:AR428)=0,"",AS428-LOOKUP(2,1/(AI428:AR428<>""),AI428:AR428))) | IF(OR(F428="",AT428=""),"",IF(COUNT(AI428:AS428)=0,"",AT428-LOOKUP(2,1/(AI428:AS428<>""),AI428:AS428))) | IF(OR(F428="",AU428=""),"",IF(COUNT(AI428:AT428)=0,"",AU428-LOOKUP(2,1/(AI428:AT428<>""),AI428:AT428))) | IF(OR(F428="",AV428=""),"",IF(COUNT(AI428:AU428)=0,"",AV428-LOOKUP(2,1/(AI428:AU428<>""),AI428:AU428))) | IF(J428="","All_Provinces",IFERROR(VLOOKUP(J428,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K428="","All_Districts",IFERROR(VLOOKUP(K428,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F429="","",ROW()-3) | [18 empty] | IF(AQ429="","",AQ429) |  |  |  | IF(W429<>"",W429,IF(OR(T429="",V429=""),"",EDATE(T429,V429))) |  |  |  |  | IF(F429="","",IF(COUNT(AI429:AV429)=0,IF(AA429="","Not started",AA429),SUBSTITUTE(LOOKUP(2,1/(AI429:AV429<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F429="",COUNT(AI429:AV429)=0),"",TODAY()-LOOKUP(2,1/(AI429:AV429<>""),AI429:AV429)) | IF(OR(F429="",COUNT(AI429:AV429)<2),"",LOOKUP(2,1/(AI429:AV429<>""),AI429:AV429)-MIN(AI429:AV429)) | IF(OR(AD429="",AC429="Not started",AC429=""),"",IFERROR(AD429-IF(VLOOKUP(AC429,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC429,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F429="","",IF(OR(AA429="Cancelled",AC429="Cancelled"),"Cancelled",IF(OR(AC429="Completed / Handover",Y429<>"",Z429>=100),"Completed — on track",IF(O429="Not awarded",IF(U429="",IF(X429="","No planned date",IF(TODAY()>X429,"Behind — past planned date",IF(X429-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U429,"Behind — award date passed",IF(U429-TODAY()<=30,"At risk — close to off track","On track"))),IF(X429="","No planned date",IF(AND(TODAY()>X429,OR(Z429="",Z429<100)),"Behind — past end date",IF(AND(T429<>"",X429<>"",Z429<>"",(Z429<100),((TODAY()-T429)/MAX(X429-T429,1)*100)-Z429>15),"Behind — progress lag",IF(AND(X429-TODAY()<=30,X429-TODAY()>=0,OR(Z429="",Z429<90)),"At risk — close to off track","On track")))))))) | IF(OR(F429="",AC429="Completed / Handover",AC429="Cancelled"),"",IF(O429="Not awarded",IF(U429<>"",U429-TODAY(),IF(X429="","",X429-TODAY())),IF(X429="","",X429-TODAY()))) | [14 empty] | IF(OR(F429="",AJ429=""),"",IF(COUNT(AI429:AI429)=0,"",AJ429-LOOKUP(2,1/(AI429:AI429<>""),AI429:AI429))) | IF(OR(F429="",AK429=""),"",IF(COUNT(AI429:AJ429)=0,"",AK429-LOOKUP(2,1/(AI429:AJ429<>""),AI429:AJ429))) | IF(OR(F429="",AL429=""),"",IF(COUNT(AI429:AK429)=0,"",AL429-LOOKUP(2,1/(AI429:AK429<>""),AI429:AK429))) | IF(OR(F429="",AM429=""),"",IF(COUNT(AI429:AL429)=0,"",AM429-LOOKUP(2,1/(AI429:AL429<>""),AI429:AL429))) | IF(OR(F429="",AN429=""),"",IF(COUNT(AI429:AM429)=0,"",AN429-LOOKUP(2,1/(AI429:AM429<>""),AI429:AM429))) | IF(OR(F429="",AO429=""),"",IF(COUNT(AI429:AN429)=0,"",AO429-LOOKUP(2,1/(AI429:AN429<>""),AI429:AN429))) | IF(OR(F429="",AP429=""),"",IF(COUNT(AI429:AO429)=0,"",AP429-LOOKUP(2,1/(AI429:AO429<>""),AI429:AO429))) | IF(OR(F429="",AQ429=""),"",IF(COUNT(AI429:AP429)=0,"",AQ429-LOOKUP(2,1/(AI429:AP429<>""),AI429:AP429))) | IF(OR(F429="",AR429=""),"",IF(COUNT(AI429:AQ429)=0,"",AR429-LOOKUP(2,1/(AI429:AQ429<>""),AI429:AQ429))) | IF(OR(F429="",AS429=""),"",IF(COUNT(AI429:AR429)=0,"",AS429-LOOKUP(2,1/(AI429:AR429<>""),AI429:AR429))) | IF(OR(F429="",AT429=""),"",IF(COUNT(AI429:AS429)=0,"",AT429-LOOKUP(2,1/(AI429:AS429<>""),AI429:AS429))) | IF(OR(F429="",AU429=""),"",IF(COUNT(AI429:AT429)=0,"",AU429-LOOKUP(2,1/(AI429:AT429<>""),AI429:AT429))) | IF(OR(F429="",AV429=""),"",IF(COUNT(AI429:AU429)=0,"",AV429-LOOKUP(2,1/(AI429:AU429<>""),AI429:AU429))) | IF(J429="","All_Provinces",IFERROR(VLOOKUP(J429,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K429="","All_Districts",IFERROR(VLOOKUP(K429,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F430="","",ROW()-3) | [18 empty] | IF(AQ430="","",AQ430) |  |  |  | IF(W430<>"",W430,IF(OR(T430="",V430=""),"",EDATE(T430,V430))) |  |  |  |  | IF(F430="","",IF(COUNT(AI430:AV430)=0,IF(AA430="","Not started",AA430),SUBSTITUTE(LOOKUP(2,1/(AI430:AV430<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F430="",COUNT(AI430:AV430)=0),"",TODAY()-LOOKUP(2,1/(AI430:AV430<>""),AI430:AV430)) | IF(OR(F430="",COUNT(AI430:AV430)<2),"",LOOKUP(2,1/(AI430:AV430<>""),AI430:AV430)-MIN(AI430:AV430)) | IF(OR(AD430="",AC430="Not started",AC430=""),"",IFERROR(AD430-IF(VLOOKUP(AC430,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC430,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F430="","",IF(OR(AA430="Cancelled",AC430="Cancelled"),"Cancelled",IF(OR(AC430="Completed / Handover",Y430<>"",Z430>=100),"Completed — on track",IF(O430="Not awarded",IF(U430="",IF(X430="","No planned date",IF(TODAY()>X430,"Behind — past planned date",IF(X430-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U430,"Behind — award date passed",IF(U430-TODAY()<=30,"At risk — close to off track","On track"))),IF(X430="","No planned date",IF(AND(TODAY()>X430,OR(Z430="",Z430<100)),"Behind — past end date",IF(AND(T430<>"",X430<>"",Z430<>"",(Z430<100),((TODAY()-T430)/MAX(X430-T430,1)*100)-Z430>15),"Behind — progress lag",IF(AND(X430-TODAY()<=30,X430-TODAY()>=0,OR(Z430="",Z430<90)),"At risk — close to off track","On track")))))))) | IF(OR(F430="",AC430="Completed / Handover",AC430="Cancelled"),"",IF(O430="Not awarded",IF(U430<>"",U430-TODAY(),IF(X430="","",X430-TODAY())),IF(X430="","",X430-TODAY()))) | [14 empty] | IF(OR(F430="",AJ430=""),"",IF(COUNT(AI430:AI430)=0,"",AJ430-LOOKUP(2,1/(AI430:AI430<>""),AI430:AI430))) | IF(OR(F430="",AK430=""),"",IF(COUNT(AI430:AJ430)=0,"",AK430-LOOKUP(2,1/(AI430:AJ430<>""),AI430:AJ430))) | IF(OR(F430="",AL430=""),"",IF(COUNT(AI430:AK430)=0,"",AL430-LOOKUP(2,1/(AI430:AK430<>""),AI430:AK430))) | IF(OR(F430="",AM430=""),"",IF(COUNT(AI430:AL430)=0,"",AM430-LOOKUP(2,1/(AI430:AL430<>""),AI430:AL430))) | IF(OR(F430="",AN430=""),"",IF(COUNT(AI430:AM430)=0,"",AN430-LOOKUP(2,1/(AI430:AM430<>""),AI430:AM430))) | IF(OR(F430="",AO430=""),"",IF(COUNT(AI430:AN430)=0,"",AO430-LOOKUP(2,1/(AI430:AN430<>""),AI430:AN430))) | IF(OR(F430="",AP430=""),"",IF(COUNT(AI430:AO430)=0,"",AP430-LOOKUP(2,1/(AI430:AO430<>""),AI430:AO430))) | IF(OR(F430="",AQ430=""),"",IF(COUNT(AI430:AP430)=0,"",AQ430-LOOKUP(2,1/(AI430:AP430<>""),AI430:AP430))) | IF(OR(F430="",AR430=""),"",IF(COUNT(AI430:AQ430)=0,"",AR430-LOOKUP(2,1/(AI430:AQ430<>""),AI430:AQ430))) | IF(OR(F430="",AS430=""),"",IF(COUNT(AI430:AR430)=0,"",AS430-LOOKUP(2,1/(AI430:AR430<>""),AI430:AR430))) | IF(OR(F430="",AT430=""),"",IF(COUNT(AI430:AS430)=0,"",AT430-LOOKUP(2,1/(AI430:AS430<>""),AI430:AS430))) | IF(OR(F430="",AU430=""),"",IF(COUNT(AI430:AT430)=0,"",AU430-LOOKUP(2,1/(AI430:AT430<>""),AI430:AT430))) | IF(OR(F430="",AV430=""),"",IF(COUNT(AI430:AU430)=0,"",AV430-LOOKUP(2,1/(AI430:AU430<>""),AI430:AU430))) | IF(J430="","All_Provinces",IFERROR(VLOOKUP(J430,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K430="","All_Districts",IFERROR(VLOOKUP(K430,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F431="","",ROW()-3) | [18 empty] | IF(AQ431="","",AQ431) |  |  |  | IF(W431<>"",W431,IF(OR(T431="",V431=""),"",EDATE(T431,V431))) |  |  |  |  | IF(F431="","",IF(COUNT(AI431:AV431)=0,IF(AA431="","Not started",AA431),SUBSTITUTE(LOOKUP(2,1/(AI431:AV431<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F431="",COUNT(AI431:AV431)=0),"",TODAY()-LOOKUP(2,1/(AI431:AV431<>""),AI431:AV431)) | IF(OR(F431="",COUNT(AI431:AV431)<2),"",LOOKUP(2,1/(AI431:AV431<>""),AI431:AV431)-MIN(AI431:AV431)) | IF(OR(AD431="",AC431="Not started",AC431=""),"",IFERROR(AD431-IF(VLOOKUP(AC431,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC431,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F431="","",IF(OR(AA431="Cancelled",AC431="Cancelled"),"Cancelled",IF(OR(AC431="Completed / Handover",Y431<>"",Z431>=100),"Completed — on track",IF(O431="Not awarded",IF(U431="",IF(X431="","No planned date",IF(TODAY()>X431,"Behind — past planned date",IF(X431-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U431,"Behind — award date passed",IF(U431-TODAY()<=30,"At risk — close to off track","On track"))),IF(X431="","No planned date",IF(AND(TODAY()>X431,OR(Z431="",Z431<100)),"Behind — past end date",IF(AND(T431<>"",X431<>"",Z431<>"",(Z431<100),((TODAY()-T431)/MAX(X431-T431,1)*100)-Z431>15),"Behind — progress lag",IF(AND(X431-TODAY()<=30,X431-TODAY()>=0,OR(Z431="",Z431<90)),"At risk — close to off track","On track")))))))) | IF(OR(F431="",AC431="Completed / Handover",AC431="Cancelled"),"",IF(O431="Not awarded",IF(U431<>"",U431-TODAY(),IF(X431="","",X431-TODAY())),IF(X431="","",X431-TODAY()))) | [14 empty] | IF(OR(F431="",AJ431=""),"",IF(COUNT(AI431:AI431)=0,"",AJ431-LOOKUP(2,1/(AI431:AI431<>""),AI431:AI431))) | IF(OR(F431="",AK431=""),"",IF(COUNT(AI431:AJ431)=0,"",AK431-LOOKUP(2,1/(AI431:AJ431<>""),AI431:AJ431))) | IF(OR(F431="",AL431=""),"",IF(COUNT(AI431:AK431)=0,"",AL431-LOOKUP(2,1/(AI431:AK431<>""),AI431:AK431))) | IF(OR(F431="",AM431=""),"",IF(COUNT(AI431:AL431)=0,"",AM431-LOOKUP(2,1/(AI431:AL431<>""),AI431:AL431))) | IF(OR(F431="",AN431=""),"",IF(COUNT(AI431:AM431)=0,"",AN431-LOOKUP(2,1/(AI431:AM431<>""),AI431:AM431))) | IF(OR(F431="",AO431=""),"",IF(COUNT(AI431:AN431)=0,"",AO431-LOOKUP(2,1/(AI431:AN431<>""),AI431:AN431))) | IF(OR(F431="",AP431=""),"",IF(COUNT(AI431:AO431)=0,"",AP431-LOOKUP(2,1/(AI431:AO431<>""),AI431:AO431))) | IF(OR(F431="",AQ431=""),"",IF(COUNT(AI431:AP431)=0,"",AQ431-LOOKUP(2,1/(AI431:AP431<>""),AI431:AP431))) | IF(OR(F431="",AR431=""),"",IF(COUNT(AI431:AQ431)=0,"",AR431-LOOKUP(2,1/(AI431:AQ431<>""),AI431:AQ431))) | IF(OR(F431="",AS431=""),"",IF(COUNT(AI431:AR431)=0,"",AS431-LOOKUP(2,1/(AI431:AR431<>""),AI431:AR431))) | IF(OR(F431="",AT431=""),"",IF(COUNT(AI431:AS431)=0,"",AT431-LOOKUP(2,1/(AI431:AS431<>""),AI431:AS431))) | IF(OR(F431="",AU431=""),"",IF(COUNT(AI431:AT431)=0,"",AU431-LOOKUP(2,1/(AI431:AT431<>""),AI431:AT431))) | IF(OR(F431="",AV431=""),"",IF(COUNT(AI431:AU431)=0,"",AV431-LOOKUP(2,1/(AI431:AU431<>""),AI431:AU431))) | IF(J431="","All_Provinces",IFERROR(VLOOKUP(J431,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K431="","All_Districts",IFERROR(VLOOKUP(K431,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F432="","",ROW()-3) | [18 empty] | IF(AQ432="","",AQ432) |  |  |  | IF(W432<>"",W432,IF(OR(T432="",V432=""),"",EDATE(T432,V432))) |  |  |  |  | IF(F432="","",IF(COUNT(AI432:AV432)=0,IF(AA432="","Not started",AA432),SUBSTITUTE(LOOKUP(2,1/(AI432:AV432<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F432="",COUNT(AI432:AV432)=0),"",TODAY()-LOOKUP(2,1/(AI432:AV432<>""),AI432:AV432)) | IF(OR(F432="",COUNT(AI432:AV432)<2),"",LOOKUP(2,1/(AI432:AV432<>""),AI432:AV432)-MIN(AI432:AV432)) | IF(OR(AD432="",AC432="Not started",AC432=""),"",IFERROR(AD432-IF(VLOOKUP(AC432,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC432,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F432="","",IF(OR(AA432="Cancelled",AC432="Cancelled"),"Cancelled",IF(OR(AC432="Completed / Handover",Y432<>"",Z432>=100),"Completed — on track",IF(O432="Not awarded",IF(U432="",IF(X432="","No planned date",IF(TODAY()>X432,"Behind — past planned date",IF(X432-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U432,"Behind — award date passed",IF(U432-TODAY()<=30,"At risk — close to off track","On track"))),IF(X432="","No planned date",IF(AND(TODAY()>X432,OR(Z432="",Z432<100)),"Behind — past end date",IF(AND(T432<>"",X432<>"",Z432<>"",(Z432<100),((TODAY()-T432)/MAX(X432-T432,1)*100)-Z432>15),"Behind — progress lag",IF(AND(X432-TODAY()<=30,X432-TODAY()>=0,OR(Z432="",Z432<90)),"At risk — close to off track","On track")))))))) | IF(OR(F432="",AC432="Completed / Handover",AC432="Cancelled"),"",IF(O432="Not awarded",IF(U432<>"",U432-TODAY(),IF(X432="","",X432-TODAY())),IF(X432="","",X432-TODAY()))) | [14 empty] | IF(OR(F432="",AJ432=""),"",IF(COUNT(AI432:AI432)=0,"",AJ432-LOOKUP(2,1/(AI432:AI432<>""),AI432:AI432))) | IF(OR(F432="",AK432=""),"",IF(COUNT(AI432:AJ432)=0,"",AK432-LOOKUP(2,1/(AI432:AJ432<>""),AI432:AJ432))) | IF(OR(F432="",AL432=""),"",IF(COUNT(AI432:AK432)=0,"",AL432-LOOKUP(2,1/(AI432:AK432<>""),AI432:AK432))) | IF(OR(F432="",AM432=""),"",IF(COUNT(AI432:AL432)=0,"",AM432-LOOKUP(2,1/(AI432:AL432<>""),AI432:AL432))) | IF(OR(F432="",AN432=""),"",IF(COUNT(AI432:AM432)=0,"",AN432-LOOKUP(2,1/(AI432:AM432<>""),AI432:AM432))) | IF(OR(F432="",AO432=""),"",IF(COUNT(AI432:AN432)=0,"",AO432-LOOKUP(2,1/(AI432:AN432<>""),AI432:AN432))) | IF(OR(F432="",AP432=""),"",IF(COUNT(AI432:AO432)=0,"",AP432-LOOKUP(2,1/(AI432:AO432<>""),AI432:AO432))) | IF(OR(F432="",AQ432=""),"",IF(COUNT(AI432:AP432)=0,"",AQ432-LOOKUP(2,1/(AI432:AP432<>""),AI432:AP432))) | IF(OR(F432="",AR432=""),"",IF(COUNT(AI432:AQ432)=0,"",AR432-LOOKUP(2,1/(AI432:AQ432<>""),AI432:AQ432))) | IF(OR(F432="",AS432=""),"",IF(COUNT(AI432:AR432)=0,"",AS432-LOOKUP(2,1/(AI432:AR432<>""),AI432:AR432))) | IF(OR(F432="",AT432=""),"",IF(COUNT(AI432:AS432)=0,"",AT432-LOOKUP(2,1/(AI432:AS432<>""),AI432:AS432))) | IF(OR(F432="",AU432=""),"",IF(COUNT(AI432:AT432)=0,"",AU432-LOOKUP(2,1/(AI432:AT432<>""),AI432:AT432))) | IF(OR(F432="",AV432=""),"",IF(COUNT(AI432:AU432)=0,"",AV432-LOOKUP(2,1/(AI432:AU432<>""),AI432:AU432))) | IF(J432="","All_Provinces",IFERROR(VLOOKUP(J432,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K432="","All_Districts",IFERROR(VLOOKUP(K432,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F433="","",ROW()-3) | [18 empty] | IF(AQ433="","",AQ433) |  |  |  | IF(W433<>"",W433,IF(OR(T433="",V433=""),"",EDATE(T433,V433))) |  |  |  |  | IF(F433="","",IF(COUNT(AI433:AV433)=0,IF(AA433="","Not started",AA433),SUBSTITUTE(LOOKUP(2,1/(AI433:AV433<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F433="",COUNT(AI433:AV433)=0),"",TODAY()-LOOKUP(2,1/(AI433:AV433<>""),AI433:AV433)) | IF(OR(F433="",COUNT(AI433:AV433)<2),"",LOOKUP(2,1/(AI433:AV433<>""),AI433:AV433)-MIN(AI433:AV433)) | IF(OR(AD433="",AC433="Not started",AC433=""),"",IFERROR(AD433-IF(VLOOKUP(AC433,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC433,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F433="","",IF(OR(AA433="Cancelled",AC433="Cancelled"),"Cancelled",IF(OR(AC433="Completed / Handover",Y433<>"",Z433>=100),"Completed — on track",IF(O433="Not awarded",IF(U433="",IF(X433="","No planned date",IF(TODAY()>X433,"Behind — past planned date",IF(X433-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U433,"Behind — award date passed",IF(U433-TODAY()<=30,"At risk — close to off track","On track"))),IF(X433="","No planned date",IF(AND(TODAY()>X433,OR(Z433="",Z433<100)),"Behind — past end date",IF(AND(T433<>"",X433<>"",Z433<>"",(Z433<100),((TODAY()-T433)/MAX(X433-T433,1)*100)-Z433>15),"Behind — progress lag",IF(AND(X433-TODAY()<=30,X433-TODAY()>=0,OR(Z433="",Z433<90)),"At risk — close to off track","On track")))))))) | IF(OR(F433="",AC433="Completed / Handover",AC433="Cancelled"),"",IF(O433="Not awarded",IF(U433<>"",U433-TODAY(),IF(X433="","",X433-TODAY())),IF(X433="","",X433-TODAY()))) | [14 empty] | IF(OR(F433="",AJ433=""),"",IF(COUNT(AI433:AI433)=0,"",AJ433-LOOKUP(2,1/(AI433:AI433<>""),AI433:AI433))) | IF(OR(F433="",AK433=""),"",IF(COUNT(AI433:AJ433)=0,"",AK433-LOOKUP(2,1/(AI433:AJ433<>""),AI433:AJ433))) | IF(OR(F433="",AL433=""),"",IF(COUNT(AI433:AK433)=0,"",AL433-LOOKUP(2,1/(AI433:AK433<>""),AI433:AK433))) | IF(OR(F433="",AM433=""),"",IF(COUNT(AI433:AL433)=0,"",AM433-LOOKUP(2,1/(AI433:AL433<>""),AI433:AL433))) | IF(OR(F433="",AN433=""),"",IF(COUNT(AI433:AM433)=0,"",AN433-LOOKUP(2,1/(AI433:AM433<>""),AI433:AM433))) | IF(OR(F433="",AO433=""),"",IF(COUNT(AI433:AN433)=0,"",AO433-LOOKUP(2,1/(AI433:AN433<>""),AI433:AN433))) | IF(OR(F433="",AP433=""),"",IF(COUNT(AI433:AO433)=0,"",AP433-LOOKUP(2,1/(AI433:AO433<>""),AI433:AO433))) | IF(OR(F433="",AQ433=""),"",IF(COUNT(AI433:AP433)=0,"",AQ433-LOOKUP(2,1/(AI433:AP433<>""),AI433:AP433))) | IF(OR(F433="",AR433=""),"",IF(COUNT(AI433:AQ433)=0,"",AR433-LOOKUP(2,1/(AI433:AQ433<>""),AI433:AQ433))) | IF(OR(F433="",AS433=""),"",IF(COUNT(AI433:AR433)=0,"",AS433-LOOKUP(2,1/(AI433:AR433<>""),AI433:AR433))) | IF(OR(F433="",AT433=""),"",IF(COUNT(AI433:AS433)=0,"",AT433-LOOKUP(2,1/(AI433:AS433<>""),AI433:AS433))) | IF(OR(F433="",AU433=""),"",IF(COUNT(AI433:AT433)=0,"",AU433-LOOKUP(2,1/(AI433:AT433<>""),AI433:AT433))) | IF(OR(F433="",AV433=""),"",IF(COUNT(AI433:AU433)=0,"",AV433-LOOKUP(2,1/(AI433:AU433<>""),AI433:AU433))) | IF(J433="","All_Provinces",IFERROR(VLOOKUP(J433,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K433="","All_Districts",IFERROR(VLOOKUP(K433,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F434="","",ROW()-3) | [18 empty] | IF(AQ434="","",AQ434) |  |  |  | IF(W434<>"",W434,IF(OR(T434="",V434=""),"",EDATE(T434,V434))) |  |  |  |  | IF(F434="","",IF(COUNT(AI434:AV434)=0,IF(AA434="","Not started",AA434),SUBSTITUTE(LOOKUP(2,1/(AI434:AV434<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F434="",COUNT(AI434:AV434)=0),"",TODAY()-LOOKUP(2,1/(AI434:AV434<>""),AI434:AV434)) | IF(OR(F434="",COUNT(AI434:AV434)<2),"",LOOKUP(2,1/(AI434:AV434<>""),AI434:AV434)-MIN(AI434:AV434)) | IF(OR(AD434="",AC434="Not started",AC434=""),"",IFERROR(AD434-IF(VLOOKUP(AC434,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC434,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F434="","",IF(OR(AA434="Cancelled",AC434="Cancelled"),"Cancelled",IF(OR(AC434="Completed / Handover",Y434<>"",Z434>=100),"Completed — on track",IF(O434="Not awarded",IF(U434="",IF(X434="","No planned date",IF(TODAY()>X434,"Behind — past planned date",IF(X434-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U434,"Behind — award date passed",IF(U434-TODAY()<=30,"At risk — close to off track","On track"))),IF(X434="","No planned date",IF(AND(TODAY()>X434,OR(Z434="",Z434<100)),"Behind — past end date",IF(AND(T434<>"",X434<>"",Z434<>"",(Z434<100),((TODAY()-T434)/MAX(X434-T434,1)*100)-Z434>15),"Behind — progress lag",IF(AND(X434-TODAY()<=30,X434-TODAY()>=0,OR(Z434="",Z434<90)),"At risk — close to off track","On track")))))))) | IF(OR(F434="",AC434="Completed / Handover",AC434="Cancelled"),"",IF(O434="Not awarded",IF(U434<>"",U434-TODAY(),IF(X434="","",X434-TODAY())),IF(X434="","",X434-TODAY()))) | [14 empty] | IF(OR(F434="",AJ434=""),"",IF(COUNT(AI434:AI434)=0,"",AJ434-LOOKUP(2,1/(AI434:AI434<>""),AI434:AI434))) | IF(OR(F434="",AK434=""),"",IF(COUNT(AI434:AJ434)=0,"",AK434-LOOKUP(2,1/(AI434:AJ434<>""),AI434:AJ434))) | IF(OR(F434="",AL434=""),"",IF(COUNT(AI434:AK434)=0,"",AL434-LOOKUP(2,1/(AI434:AK434<>""),AI434:AK434))) | IF(OR(F434="",AM434=""),"",IF(COUNT(AI434:AL434)=0,"",AM434-LOOKUP(2,1/(AI434:AL434<>""),AI434:AL434))) | IF(OR(F434="",AN434=""),"",IF(COUNT(AI434:AM434)=0,"",AN434-LOOKUP(2,1/(AI434:AM434<>""),AI434:AM434))) | IF(OR(F434="",AO434=""),"",IF(COUNT(AI434:AN434)=0,"",AO434-LOOKUP(2,1/(AI434:AN434<>""),AI434:AN434))) | IF(OR(F434="",AP434=""),"",IF(COUNT(AI434:AO434)=0,"",AP434-LOOKUP(2,1/(AI434:AO434<>""),AI434:AO434))) | IF(OR(F434="",AQ434=""),"",IF(COUNT(AI434:AP434)=0,"",AQ434-LOOKUP(2,1/(AI434:AP434<>""),AI434:AP434))) | IF(OR(F434="",AR434=""),"",IF(COUNT(AI434:AQ434)=0,"",AR434-LOOKUP(2,1/(AI434:AQ434<>""),AI434:AQ434))) | IF(OR(F434="",AS434=""),"",IF(COUNT(AI434:AR434)=0,"",AS434-LOOKUP(2,1/(AI434:AR434<>""),AI434:AR434))) | IF(OR(F434="",AT434=""),"",IF(COUNT(AI434:AS434)=0,"",AT434-LOOKUP(2,1/(AI434:AS434<>""),AI434:AS434))) | IF(OR(F434="",AU434=""),"",IF(COUNT(AI434:AT434)=0,"",AU434-LOOKUP(2,1/(AI434:AT434<>""),AI434:AT434))) | IF(OR(F434="",AV434=""),"",IF(COUNT(AI434:AU434)=0,"",AV434-LOOKUP(2,1/(AI434:AU434<>""),AI434:AU434))) | IF(J434="","All_Provinces",IFERROR(VLOOKUP(J434,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K434="","All_Districts",IFERROR(VLOOKUP(K434,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F435="","",ROW()-3) | [18 empty] | IF(AQ435="","",AQ435) |  |  |  | IF(W435<>"",W435,IF(OR(T435="",V435=""),"",EDATE(T435,V435))) |  |  |  |  | IF(F435="","",IF(COUNT(AI435:AV435)=0,IF(AA435="","Not started",AA435),SUBSTITUTE(LOOKUP(2,1/(AI435:AV435<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F435="",COUNT(AI435:AV435)=0),"",TODAY()-LOOKUP(2,1/(AI435:AV435<>""),AI435:AV435)) | IF(OR(F435="",COUNT(AI435:AV435)<2),"",LOOKUP(2,1/(AI435:AV435<>""),AI435:AV435)-MIN(AI435:AV435)) | IF(OR(AD435="",AC435="Not started",AC435=""),"",IFERROR(AD435-IF(VLOOKUP(AC435,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC435,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F435="","",IF(OR(AA435="Cancelled",AC435="Cancelled"),"Cancelled",IF(OR(AC435="Completed / Handover",Y435<>"",Z435>=100),"Completed — on track",IF(O435="Not awarded",IF(U435="",IF(X435="","No planned date",IF(TODAY()>X435,"Behind — past planned date",IF(X435-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U435,"Behind — award date passed",IF(U435-TODAY()<=30,"At risk — close to off track","On track"))),IF(X435="","No planned date",IF(AND(TODAY()>X435,OR(Z435="",Z435<100)),"Behind — past end date",IF(AND(T435<>"",X435<>"",Z435<>"",(Z435<100),((TODAY()-T435)/MAX(X435-T435,1)*100)-Z435>15),"Behind — progress lag",IF(AND(X435-TODAY()<=30,X435-TODAY()>=0,OR(Z435="",Z435<90)),"At risk — close to off track","On track")))))))) | IF(OR(F435="",AC435="Completed / Handover",AC435="Cancelled"),"",IF(O435="Not awarded",IF(U435<>"",U435-TODAY(),IF(X435="","",X435-TODAY())),IF(X435="","",X435-TODAY()))) | [14 empty] | IF(OR(F435="",AJ435=""),"",IF(COUNT(AI435:AI435)=0,"",AJ435-LOOKUP(2,1/(AI435:AI435<>""),AI435:AI435))) | IF(OR(F435="",AK435=""),"",IF(COUNT(AI435:AJ435)=0,"",AK435-LOOKUP(2,1/(AI435:AJ435<>""),AI435:AJ435))) | IF(OR(F435="",AL435=""),"",IF(COUNT(AI435:AK435)=0,"",AL435-LOOKUP(2,1/(AI435:AK435<>""),AI435:AK435))) | IF(OR(F435="",AM435=""),"",IF(COUNT(AI435:AL435)=0,"",AM435-LOOKUP(2,1/(AI435:AL435<>""),AI435:AL435))) | IF(OR(F435="",AN435=""),"",IF(COUNT(AI435:AM435)=0,"",AN435-LOOKUP(2,1/(AI435:AM435<>""),AI435:AM435))) | IF(OR(F435="",AO435=""),"",IF(COUNT(AI435:AN435)=0,"",AO435-LOOKUP(2,1/(AI435:AN435<>""),AI435:AN435))) | IF(OR(F435="",AP435=""),"",IF(COUNT(AI435:AO435)=0,"",AP435-LOOKUP(2,1/(AI435:AO435<>""),AI435:AO435))) | IF(OR(F435="",AQ435=""),"",IF(COUNT(AI435:AP435)=0,"",AQ435-LOOKUP(2,1/(AI435:AP435<>""),AI435:AP435))) | IF(OR(F435="",AR435=""),"",IF(COUNT(AI435:AQ435)=0,"",AR435-LOOKUP(2,1/(AI435:AQ435<>""),AI435:AQ435))) | IF(OR(F435="",AS435=""),"",IF(COUNT(AI435:AR435)=0,"",AS435-LOOKUP(2,1/(AI435:AR435<>""),AI435:AR435))) | IF(OR(F435="",AT435=""),"",IF(COUNT(AI435:AS435)=0,"",AT435-LOOKUP(2,1/(AI435:AS435<>""),AI435:AS435))) | IF(OR(F435="",AU435=""),"",IF(COUNT(AI435:AT435)=0,"",AU435-LOOKUP(2,1/(AI435:AT435<>""),AI435:AT435))) | IF(OR(F435="",AV435=""),"",IF(COUNT(AI435:AU435)=0,"",AV435-LOOKUP(2,1/(AI435:AU435<>""),AI435:AU435))) | IF(J435="","All_Provinces",IFERROR(VLOOKUP(J435,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K435="","All_Districts",IFERROR(VLOOKUP(K435,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F436="","",ROW()-3) | [18 empty] | IF(AQ436="","",AQ436) |  |  |  | IF(W436<>"",W436,IF(OR(T436="",V436=""),"",EDATE(T436,V436))) |  |  |  |  | IF(F436="","",IF(COUNT(AI436:AV436)=0,IF(AA436="","Not started",AA436),SUBSTITUTE(LOOKUP(2,1/(AI436:AV436<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F436="",COUNT(AI436:AV436)=0),"",TODAY()-LOOKUP(2,1/(AI436:AV436<>""),AI436:AV436)) | IF(OR(F436="",COUNT(AI436:AV436)<2),"",LOOKUP(2,1/(AI436:AV436<>""),AI436:AV436)-MIN(AI436:AV436)) | IF(OR(AD436="",AC436="Not started",AC436=""),"",IFERROR(AD436-IF(VLOOKUP(AC436,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC436,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F436="","",IF(OR(AA436="Cancelled",AC436="Cancelled"),"Cancelled",IF(OR(AC436="Completed / Handover",Y436<>"",Z436>=100),"Completed — on track",IF(O436="Not awarded",IF(U436="",IF(X436="","No planned date",IF(TODAY()>X436,"Behind — past planned date",IF(X436-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U436,"Behind — award date passed",IF(U436-TODAY()<=30,"At risk — close to off track","On track"))),IF(X436="","No planned date",IF(AND(TODAY()>X436,OR(Z436="",Z436<100)),"Behind — past end date",IF(AND(T436<>"",X436<>"",Z436<>"",(Z436<100),((TODAY()-T436)/MAX(X436-T436,1)*100)-Z436>15),"Behind — progress lag",IF(AND(X436-TODAY()<=30,X436-TODAY()>=0,OR(Z436="",Z436<90)),"At risk — close to off track","On track")))))))) | IF(OR(F436="",AC436="Completed / Handover",AC436="Cancelled"),"",IF(O436="Not awarded",IF(U436<>"",U436-TODAY(),IF(X436="","",X436-TODAY())),IF(X436="","",X436-TODAY()))) | [14 empty] | IF(OR(F436="",AJ436=""),"",IF(COUNT(AI436:AI436)=0,"",AJ436-LOOKUP(2,1/(AI436:AI436<>""),AI436:AI436))) | IF(OR(F436="",AK436=""),"",IF(COUNT(AI436:AJ436)=0,"",AK436-LOOKUP(2,1/(AI436:AJ436<>""),AI436:AJ436))) | IF(OR(F436="",AL436=""),"",IF(COUNT(AI436:AK436)=0,"",AL436-LOOKUP(2,1/(AI436:AK436<>""),AI436:AK436))) | IF(OR(F436="",AM436=""),"",IF(COUNT(AI436:AL436)=0,"",AM436-LOOKUP(2,1/(AI436:AL436<>""),AI436:AL436))) | IF(OR(F436="",AN436=""),"",IF(COUNT(AI436:AM436)=0,"",AN436-LOOKUP(2,1/(AI436:AM436<>""),AI436:AM436))) | IF(OR(F436="",AO436=""),"",IF(COUNT(AI436:AN436)=0,"",AO436-LOOKUP(2,1/(AI436:AN436<>""),AI436:AN436))) | IF(OR(F436="",AP436=""),"",IF(COUNT(AI436:AO436)=0,"",AP436-LOOKUP(2,1/(AI436:AO436<>""),AI436:AO436))) | IF(OR(F436="",AQ436=""),"",IF(COUNT(AI436:AP436)=0,"",AQ436-LOOKUP(2,1/(AI436:AP436<>""),AI436:AP436))) | IF(OR(F436="",AR436=""),"",IF(COUNT(AI436:AQ436)=0,"",AR436-LOOKUP(2,1/(AI436:AQ436<>""),AI436:AQ436))) | IF(OR(F436="",AS436=""),"",IF(COUNT(AI436:AR436)=0,"",AS436-LOOKUP(2,1/(AI436:AR436<>""),AI436:AR436))) | IF(OR(F436="",AT436=""),"",IF(COUNT(AI436:AS436)=0,"",AT436-LOOKUP(2,1/(AI436:AS436<>""),AI436:AS436))) | IF(OR(F436="",AU436=""),"",IF(COUNT(AI436:AT436)=0,"",AU436-LOOKUP(2,1/(AI436:AT436<>""),AI436:AT436))) | IF(OR(F436="",AV436=""),"",IF(COUNT(AI436:AU436)=0,"",AV436-LOOKUP(2,1/(AI436:AU436<>""),AI436:AU436))) | IF(J436="","All_Provinces",IFERROR(VLOOKUP(J436,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K436="","All_Districts",IFERROR(VLOOKUP(K436,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F437="","",ROW()-3) | [18 empty] | IF(AQ437="","",AQ437) |  |  |  | IF(W437<>"",W437,IF(OR(T437="",V437=""),"",EDATE(T437,V437))) |  |  |  |  | IF(F437="","",IF(COUNT(AI437:AV437)=0,IF(AA437="","Not started",AA437),SUBSTITUTE(LOOKUP(2,1/(AI437:AV437<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F437="",COUNT(AI437:AV437)=0),"",TODAY()-LOOKUP(2,1/(AI437:AV437<>""),AI437:AV437)) | IF(OR(F437="",COUNT(AI437:AV437)<2),"",LOOKUP(2,1/(AI437:AV437<>""),AI437:AV437)-MIN(AI437:AV437)) | IF(OR(AD437="",AC437="Not started",AC437=""),"",IFERROR(AD437-IF(VLOOKUP(AC437,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC437,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F437="","",IF(OR(AA437="Cancelled",AC437="Cancelled"),"Cancelled",IF(OR(AC437="Completed / Handover",Y437<>"",Z437>=100),"Completed — on track",IF(O437="Not awarded",IF(U437="",IF(X437="","No planned date",IF(TODAY()>X437,"Behind — past planned date",IF(X437-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U437,"Behind — award date passed",IF(U437-TODAY()<=30,"At risk — close to off track","On track"))),IF(X437="","No planned date",IF(AND(TODAY()>X437,OR(Z437="",Z437<100)),"Behind — past end date",IF(AND(T437<>"",X437<>"",Z437<>"",(Z437<100),((TODAY()-T437)/MAX(X437-T437,1)*100)-Z437>15),"Behind — progress lag",IF(AND(X437-TODAY()<=30,X437-TODAY()>=0,OR(Z437="",Z437<90)),"At risk — close to off track","On track")))))))) | IF(OR(F437="",AC437="Completed / Handover",AC437="Cancelled"),"",IF(O437="Not awarded",IF(U437<>"",U437-TODAY(),IF(X437="","",X437-TODAY())),IF(X437="","",X437-TODAY()))) | [14 empty] | IF(OR(F437="",AJ437=""),"",IF(COUNT(AI437:AI437)=0,"",AJ437-LOOKUP(2,1/(AI437:AI437<>""),AI437:AI437))) | IF(OR(F437="",AK437=""),"",IF(COUNT(AI437:AJ437)=0,"",AK437-LOOKUP(2,1/(AI437:AJ437<>""),AI437:AJ437))) | IF(OR(F437="",AL437=""),"",IF(COUNT(AI437:AK437)=0,"",AL437-LOOKUP(2,1/(AI437:AK437<>""),AI437:AK437))) | IF(OR(F437="",AM437=""),"",IF(COUNT(AI437:AL437)=0,"",AM437-LOOKUP(2,1/(AI437:AL437<>""),AI437:AL437))) | IF(OR(F437="",AN437=""),"",IF(COUNT(AI437:AM437)=0,"",AN437-LOOKUP(2,1/(AI437:AM437<>""),AI437:AM437))) | IF(OR(F437="",AO437=""),"",IF(COUNT(AI437:AN437)=0,"",AO437-LOOKUP(2,1/(AI437:AN437<>""),AI437:AN437))) | IF(OR(F437="",AP437=""),"",IF(COUNT(AI437:AO437)=0,"",AP437-LOOKUP(2,1/(AI437:AO437<>""),AI437:AO437))) | IF(OR(F437="",AQ437=""),"",IF(COUNT(AI437:AP437)=0,"",AQ437-LOOKUP(2,1/(AI437:AP437<>""),AI437:AP437))) | IF(OR(F437="",AR437=""),"",IF(COUNT(AI437:AQ437)=0,"",AR437-LOOKUP(2,1/(AI437:AQ437<>""),AI437:AQ437))) | IF(OR(F437="",AS437=""),"",IF(COUNT(AI437:AR437)=0,"",AS437-LOOKUP(2,1/(AI437:AR437<>""),AI437:AR437))) | IF(OR(F437="",AT437=""),"",IF(COUNT(AI437:AS437)=0,"",AT437-LOOKUP(2,1/(AI437:AS437<>""),AI437:AS437))) | IF(OR(F437="",AU437=""),"",IF(COUNT(AI437:AT437)=0,"",AU437-LOOKUP(2,1/(AI437:AT437<>""),AI437:AT437))) | IF(OR(F437="",AV437=""),"",IF(COUNT(AI437:AU437)=0,"",AV437-LOOKUP(2,1/(AI437:AU437<>""),AI437:AU437))) | IF(J437="","All_Provinces",IFERROR(VLOOKUP(J437,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K437="","All_Districts",IFERROR(VLOOKUP(K437,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F438="","",ROW()-3) | [18 empty] | IF(AQ438="","",AQ438) |  |  |  | IF(W438<>"",W438,IF(OR(T438="",V438=""),"",EDATE(T438,V438))) |  |  |  |  | IF(F438="","",IF(COUNT(AI438:AV438)=0,IF(AA438="","Not started",AA438),SUBSTITUTE(LOOKUP(2,1/(AI438:AV438<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F438="",COUNT(AI438:AV438)=0),"",TODAY()-LOOKUP(2,1/(AI438:AV438<>""),AI438:AV438)) | IF(OR(F438="",COUNT(AI438:AV438)<2),"",LOOKUP(2,1/(AI438:AV438<>""),AI438:AV438)-MIN(AI438:AV438)) | IF(OR(AD438="",AC438="Not started",AC438=""),"",IFERROR(AD438-IF(VLOOKUP(AC438,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC438,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F438="","",IF(OR(AA438="Cancelled",AC438="Cancelled"),"Cancelled",IF(OR(AC438="Completed / Handover",Y438<>"",Z438>=100),"Completed — on track",IF(O438="Not awarded",IF(U438="",IF(X438="","No planned date",IF(TODAY()>X438,"Behind — past planned date",IF(X438-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U438,"Behind — award date passed",IF(U438-TODAY()<=30,"At risk — close to off track","On track"))),IF(X438="","No planned date",IF(AND(TODAY()>X438,OR(Z438="",Z438<100)),"Behind — past end date",IF(AND(T438<>"",X438<>"",Z438<>"",(Z438<100),((TODAY()-T438)/MAX(X438-T438,1)*100)-Z438>15),"Behind — progress lag",IF(AND(X438-TODAY()<=30,X438-TODAY()>=0,OR(Z438="",Z438<90)),"At risk — close to off track","On track")))))))) | IF(OR(F438="",AC438="Completed / Handover",AC438="Cancelled"),"",IF(O438="Not awarded",IF(U438<>"",U438-TODAY(),IF(X438="","",X438-TODAY())),IF(X438="","",X438-TODAY()))) | [14 empty] | IF(OR(F438="",AJ438=""),"",IF(COUNT(AI438:AI438)=0,"",AJ438-LOOKUP(2,1/(AI438:AI438<>""),AI438:AI438))) | IF(OR(F438="",AK438=""),"",IF(COUNT(AI438:AJ438)=0,"",AK438-LOOKUP(2,1/(AI438:AJ438<>""),AI438:AJ438))) | IF(OR(F438="",AL438=""),"",IF(COUNT(AI438:AK438)=0,"",AL438-LOOKUP(2,1/(AI438:AK438<>""),AI438:AK438))) | IF(OR(F438="",AM438=""),"",IF(COUNT(AI438:AL438)=0,"",AM438-LOOKUP(2,1/(AI438:AL438<>""),AI438:AL438))) | IF(OR(F438="",AN438=""),"",IF(COUNT(AI438:AM438)=0,"",AN438-LOOKUP(2,1/(AI438:AM438<>""),AI438:AM438))) | IF(OR(F438="",AO438=""),"",IF(COUNT(AI438:AN438)=0,"",AO438-LOOKUP(2,1/(AI438:AN438<>""),AI438:AN438))) | IF(OR(F438="",AP438=""),"",IF(COUNT(AI438:AO438)=0,"",AP438-LOOKUP(2,1/(AI438:AO438<>""),AI438:AO438))) | IF(OR(F438="",AQ438=""),"",IF(COUNT(AI438:AP438)=0,"",AQ438-LOOKUP(2,1/(AI438:AP438<>""),AI438:AP438))) | IF(OR(F438="",AR438=""),"",IF(COUNT(AI438:AQ438)=0,"",AR438-LOOKUP(2,1/(AI438:AQ438<>""),AI438:AQ438))) | IF(OR(F438="",AS438=""),"",IF(COUNT(AI438:AR438)=0,"",AS438-LOOKUP(2,1/(AI438:AR438<>""),AI438:AR438))) | IF(OR(F438="",AT438=""),"",IF(COUNT(AI438:AS438)=0,"",AT438-LOOKUP(2,1/(AI438:AS438<>""),AI438:AS438))) | IF(OR(F438="",AU438=""),"",IF(COUNT(AI438:AT438)=0,"",AU438-LOOKUP(2,1/(AI438:AT438<>""),AI438:AT438))) | IF(OR(F438="",AV438=""),"",IF(COUNT(AI438:AU438)=0,"",AV438-LOOKUP(2,1/(AI438:AU438<>""),AI438:AU438))) | IF(J438="","All_Provinces",IFERROR(VLOOKUP(J438,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K438="","All_Districts",IFERROR(VLOOKUP(K438,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F439="","",ROW()-3) | [18 empty] | IF(AQ439="","",AQ439) |  |  |  | IF(W439<>"",W439,IF(OR(T439="",V439=""),"",EDATE(T439,V439))) |  |  |  |  | IF(F439="","",IF(COUNT(AI439:AV439)=0,IF(AA439="","Not started",AA439),SUBSTITUTE(LOOKUP(2,1/(AI439:AV439<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F439="",COUNT(AI439:AV439)=0),"",TODAY()-LOOKUP(2,1/(AI439:AV439<>""),AI439:AV439)) | IF(OR(F439="",COUNT(AI439:AV439)<2),"",LOOKUP(2,1/(AI439:AV439<>""),AI439:AV439)-MIN(AI439:AV439)) | IF(OR(AD439="",AC439="Not started",AC439=""),"",IFERROR(AD439-IF(VLOOKUP(AC439,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC439,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F439="","",IF(OR(AA439="Cancelled",AC439="Cancelled"),"Cancelled",IF(OR(AC439="Completed / Handover",Y439<>"",Z439>=100),"Completed — on track",IF(O439="Not awarded",IF(U439="",IF(X439="","No planned date",IF(TODAY()>X439,"Behind — past planned date",IF(X439-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U439,"Behind — award date passed",IF(U439-TODAY()<=30,"At risk — close to off track","On track"))),IF(X439="","No planned date",IF(AND(TODAY()>X439,OR(Z439="",Z439<100)),"Behind — past end date",IF(AND(T439<>"",X439<>"",Z439<>"",(Z439<100),((TODAY()-T439)/MAX(X439-T439,1)*100)-Z439>15),"Behind — progress lag",IF(AND(X439-TODAY()<=30,X439-TODAY()>=0,OR(Z439="",Z439<90)),"At risk — close to off track","On track")))))))) | IF(OR(F439="",AC439="Completed / Handover",AC439="Cancelled"),"",IF(O439="Not awarded",IF(U439<>"",U439-TODAY(),IF(X439="","",X439-TODAY())),IF(X439="","",X439-TODAY()))) | [14 empty] | IF(OR(F439="",AJ439=""),"",IF(COUNT(AI439:AI439)=0,"",AJ439-LOOKUP(2,1/(AI439:AI439<>""),AI439:AI439))) | IF(OR(F439="",AK439=""),"",IF(COUNT(AI439:AJ439)=0,"",AK439-LOOKUP(2,1/(AI439:AJ439<>""),AI439:AJ439))) | IF(OR(F439="",AL439=""),"",IF(COUNT(AI439:AK439)=0,"",AL439-LOOKUP(2,1/(AI439:AK439<>""),AI439:AK439))) | IF(OR(F439="",AM439=""),"",IF(COUNT(AI439:AL439)=0,"",AM439-LOOKUP(2,1/(AI439:AL439<>""),AI439:AL439))) | IF(OR(F439="",AN439=""),"",IF(COUNT(AI439:AM439)=0,"",AN439-LOOKUP(2,1/(AI439:AM439<>""),AI439:AM439))) | IF(OR(F439="",AO439=""),"",IF(COUNT(AI439:AN439)=0,"",AO439-LOOKUP(2,1/(AI439:AN439<>""),AI439:AN439))) | IF(OR(F439="",AP439=""),"",IF(COUNT(AI439:AO439)=0,"",AP439-LOOKUP(2,1/(AI439:AO439<>""),AI439:AO439))) | IF(OR(F439="",AQ439=""),"",IF(COUNT(AI439:AP439)=0,"",AQ439-LOOKUP(2,1/(AI439:AP439<>""),AI439:AP439))) | IF(OR(F439="",AR439=""),"",IF(COUNT(AI439:AQ439)=0,"",AR439-LOOKUP(2,1/(AI439:AQ439<>""),AI439:AQ439))) | IF(OR(F439="",AS439=""),"",IF(COUNT(AI439:AR439)=0,"",AS439-LOOKUP(2,1/(AI439:AR439<>""),AI439:AR439))) | IF(OR(F439="",AT439=""),"",IF(COUNT(AI439:AS439)=0,"",AT439-LOOKUP(2,1/(AI439:AS439<>""),AI439:AS439))) | IF(OR(F439="",AU439=""),"",IF(COUNT(AI439:AT439)=0,"",AU439-LOOKUP(2,1/(AI439:AT439<>""),AI439:AT439))) | IF(OR(F439="",AV439=""),"",IF(COUNT(AI439:AU439)=0,"",AV439-LOOKUP(2,1/(AI439:AU439<>""),AI439:AU439))) | IF(J439="","All_Provinces",IFERROR(VLOOKUP(J439,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K439="","All_Districts",IFERROR(VLOOKUP(K439,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F440="","",ROW()-3) | [18 empty] | IF(AQ440="","",AQ440) |  |  |  | IF(W440<>"",W440,IF(OR(T440="",V440=""),"",EDATE(T440,V440))) |  |  |  |  | IF(F440="","",IF(COUNT(AI440:AV440)=0,IF(AA440="","Not started",AA440),SUBSTITUTE(LOOKUP(2,1/(AI440:AV440<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F440="",COUNT(AI440:AV440)=0),"",TODAY()-LOOKUP(2,1/(AI440:AV440<>""),AI440:AV440)) | IF(OR(F440="",COUNT(AI440:AV440)<2),"",LOOKUP(2,1/(AI440:AV440<>""),AI440:AV440)-MIN(AI440:AV440)) | IF(OR(AD440="",AC440="Not started",AC440=""),"",IFERROR(AD440-IF(VLOOKUP(AC440,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC440,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F440="","",IF(OR(AA440="Cancelled",AC440="Cancelled"),"Cancelled",IF(OR(AC440="Completed / Handover",Y440<>"",Z440>=100),"Completed — on track",IF(O440="Not awarded",IF(U440="",IF(X440="","No planned date",IF(TODAY()>X440,"Behind — past planned date",IF(X440-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U440,"Behind — award date passed",IF(U440-TODAY()<=30,"At risk — close to off track","On track"))),IF(X440="","No planned date",IF(AND(TODAY()>X440,OR(Z440="",Z440<100)),"Behind — past end date",IF(AND(T440<>"",X440<>"",Z440<>"",(Z440<100),((TODAY()-T440)/MAX(X440-T440,1)*100)-Z440>15),"Behind — progress lag",IF(AND(X440-TODAY()<=30,X440-TODAY()>=0,OR(Z440="",Z440<90)),"At risk — close to off track","On track")))))))) | IF(OR(F440="",AC440="Completed / Handover",AC440="Cancelled"),"",IF(O440="Not awarded",IF(U440<>"",U440-TODAY(),IF(X440="","",X440-TODAY())),IF(X440="","",X440-TODAY()))) | [14 empty] | IF(OR(F440="",AJ440=""),"",IF(COUNT(AI440:AI440)=0,"",AJ440-LOOKUP(2,1/(AI440:AI440<>""),AI440:AI440))) | IF(OR(F440="",AK440=""),"",IF(COUNT(AI440:AJ440)=0,"",AK440-LOOKUP(2,1/(AI440:AJ440<>""),AI440:AJ440))) | IF(OR(F440="",AL440=""),"",IF(COUNT(AI440:AK440)=0,"",AL440-LOOKUP(2,1/(AI440:AK440<>""),AI440:AK440))) | IF(OR(F440="",AM440=""),"",IF(COUNT(AI440:AL440)=0,"",AM440-LOOKUP(2,1/(AI440:AL440<>""),AI440:AL440))) | IF(OR(F440="",AN440=""),"",IF(COUNT(AI440:AM440)=0,"",AN440-LOOKUP(2,1/(AI440:AM440<>""),AI440:AM440))) | IF(OR(F440="",AO440=""),"",IF(COUNT(AI440:AN440)=0,"",AO440-LOOKUP(2,1/(AI440:AN440<>""),AI440:AN440))) | IF(OR(F440="",AP440=""),"",IF(COUNT(AI440:AO440)=0,"",AP440-LOOKUP(2,1/(AI440:AO440<>""),AI440:AO440))) | IF(OR(F440="",AQ440=""),"",IF(COUNT(AI440:AP440)=0,"",AQ440-LOOKUP(2,1/(AI440:AP440<>""),AI440:AP440))) | IF(OR(F440="",AR440=""),"",IF(COUNT(AI440:AQ440)=0,"",AR440-LOOKUP(2,1/(AI440:AQ440<>""),AI440:AQ440))) | IF(OR(F440="",AS440=""),"",IF(COUNT(AI440:AR440)=0,"",AS440-LOOKUP(2,1/(AI440:AR440<>""),AI440:AR440))) | IF(OR(F440="",AT440=""),"",IF(COUNT(AI440:AS440)=0,"",AT440-LOOKUP(2,1/(AI440:AS440<>""),AI440:AS440))) | IF(OR(F440="",AU440=""),"",IF(COUNT(AI440:AT440)=0,"",AU440-LOOKUP(2,1/(AI440:AT440<>""),AI440:AT440))) | IF(OR(F440="",AV440=""),"",IF(COUNT(AI440:AU440)=0,"",AV440-LOOKUP(2,1/(AI440:AU440<>""),AI440:AU440))) | IF(J440="","All_Provinces",IFERROR(VLOOKUP(J440,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K440="","All_Districts",IFERROR(VLOOKUP(K440,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F441="","",ROW()-3) | [18 empty] | IF(AQ441="","",AQ441) |  |  |  | IF(W441<>"",W441,IF(OR(T441="",V441=""),"",EDATE(T441,V441))) |  |  |  |  | IF(F441="","",IF(COUNT(AI441:AV441)=0,IF(AA441="","Not started",AA441),SUBSTITUTE(LOOKUP(2,1/(AI441:AV441<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F441="",COUNT(AI441:AV441)=0),"",TODAY()-LOOKUP(2,1/(AI441:AV441<>""),AI441:AV441)) | IF(OR(F441="",COUNT(AI441:AV441)<2),"",LOOKUP(2,1/(AI441:AV441<>""),AI441:AV441)-MIN(AI441:AV441)) | IF(OR(AD441="",AC441="Not started",AC441=""),"",IFERROR(AD441-IF(VLOOKUP(AC441,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC441,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F441="","",IF(OR(AA441="Cancelled",AC441="Cancelled"),"Cancelled",IF(OR(AC441="Completed / Handover",Y441<>"",Z441>=100),"Completed — on track",IF(O441="Not awarded",IF(U441="",IF(X441="","No planned date",IF(TODAY()>X441,"Behind — past planned date",IF(X441-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U441,"Behind — award date passed",IF(U441-TODAY()<=30,"At risk — close to off track","On track"))),IF(X441="","No planned date",IF(AND(TODAY()>X441,OR(Z441="",Z441<100)),"Behind — past end date",IF(AND(T441<>"",X441<>"",Z441<>"",(Z441<100),((TODAY()-T441)/MAX(X441-T441,1)*100)-Z441>15),"Behind — progress lag",IF(AND(X441-TODAY()<=30,X441-TODAY()>=0,OR(Z441="",Z441<90)),"At risk — close to off track","On track")))))))) | IF(OR(F441="",AC441="Completed / Handover",AC441="Cancelled"),"",IF(O441="Not awarded",IF(U441<>"",U441-TODAY(),IF(X441="","",X441-TODAY())),IF(X441="","",X441-TODAY()))) | [14 empty] | IF(OR(F441="",AJ441=""),"",IF(COUNT(AI441:AI441)=0,"",AJ441-LOOKUP(2,1/(AI441:AI441<>""),AI441:AI441))) | IF(OR(F441="",AK441=""),"",IF(COUNT(AI441:AJ441)=0,"",AK441-LOOKUP(2,1/(AI441:AJ441<>""),AI441:AJ441))) | IF(OR(F441="",AL441=""),"",IF(COUNT(AI441:AK441)=0,"",AL441-LOOKUP(2,1/(AI441:AK441<>""),AI441:AK441))) | IF(OR(F441="",AM441=""),"",IF(COUNT(AI441:AL441)=0,"",AM441-LOOKUP(2,1/(AI441:AL441<>""),AI441:AL441))) | IF(OR(F441="",AN441=""),"",IF(COUNT(AI441:AM441)=0,"",AN441-LOOKUP(2,1/(AI441:AM441<>""),AI441:AM441))) | IF(OR(F441="",AO441=""),"",IF(COUNT(AI441:AN441)=0,"",AO441-LOOKUP(2,1/(AI441:AN441<>""),AI441:AN441))) | IF(OR(F441="",AP441=""),"",IF(COUNT(AI441:AO441)=0,"",AP441-LOOKUP(2,1/(AI441:AO441<>""),AI441:AO441))) | IF(OR(F441="",AQ441=""),"",IF(COUNT(AI441:AP441)=0,"",AQ441-LOOKUP(2,1/(AI441:AP441<>""),AI441:AP441))) | IF(OR(F441="",AR441=""),"",IF(COUNT(AI441:AQ441)=0,"",AR441-LOOKUP(2,1/(AI441:AQ441<>""),AI441:AQ441))) | IF(OR(F441="",AS441=""),"",IF(COUNT(AI441:AR441)=0,"",AS441-LOOKUP(2,1/(AI441:AR441<>""),AI441:AR441))) | IF(OR(F441="",AT441=""),"",IF(COUNT(AI441:AS441)=0,"",AT441-LOOKUP(2,1/(AI441:AS441<>""),AI441:AS441))) | IF(OR(F441="",AU441=""),"",IF(COUNT(AI441:AT441)=0,"",AU441-LOOKUP(2,1/(AI441:AT441<>""),AI441:AT441))) | IF(OR(F441="",AV441=""),"",IF(COUNT(AI441:AU441)=0,"",AV441-LOOKUP(2,1/(AI441:AU441<>""),AI441:AU441))) | IF(J441="","All_Provinces",IFERROR(VLOOKUP(J441,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K441="","All_Districts",IFERROR(VLOOKUP(K441,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F442="","",ROW()-3) | [18 empty] | IF(AQ442="","",AQ442) |  |  |  | IF(W442<>"",W442,IF(OR(T442="",V442=""),"",EDATE(T442,V442))) |  |  |  |  | IF(F442="","",IF(COUNT(AI442:AV442)=0,IF(AA442="","Not started",AA442),SUBSTITUTE(LOOKUP(2,1/(AI442:AV442<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F442="",COUNT(AI442:AV442)=0),"",TODAY()-LOOKUP(2,1/(AI442:AV442<>""),AI442:AV442)) | IF(OR(F442="",COUNT(AI442:AV442)<2),"",LOOKUP(2,1/(AI442:AV442<>""),AI442:AV442)-MIN(AI442:AV442)) | IF(OR(AD442="",AC442="Not started",AC442=""),"",IFERROR(AD442-IF(VLOOKUP(AC442,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC442,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F442="","",IF(OR(AA442="Cancelled",AC442="Cancelled"),"Cancelled",IF(OR(AC442="Completed / Handover",Y442<>"",Z442>=100),"Completed — on track",IF(O442="Not awarded",IF(U442="",IF(X442="","No planned date",IF(TODAY()>X442,"Behind — past planned date",IF(X442-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U442,"Behind — award date passed",IF(U442-TODAY()<=30,"At risk — close to off track","On track"))),IF(X442="","No planned date",IF(AND(TODAY()>X442,OR(Z442="",Z442<100)),"Behind — past end date",IF(AND(T442<>"",X442<>"",Z442<>"",(Z442<100),((TODAY()-T442)/MAX(X442-T442,1)*100)-Z442>15),"Behind — progress lag",IF(AND(X442-TODAY()<=30,X442-TODAY()>=0,OR(Z442="",Z442<90)),"At risk — close to off track","On track")))))))) | IF(OR(F442="",AC442="Completed / Handover",AC442="Cancelled"),"",IF(O442="Not awarded",IF(U442<>"",U442-TODAY(),IF(X442="","",X442-TODAY())),IF(X442="","",X442-TODAY()))) | [14 empty] | IF(OR(F442="",AJ442=""),"",IF(COUNT(AI442:AI442)=0,"",AJ442-LOOKUP(2,1/(AI442:AI442<>""),AI442:AI442))) | IF(OR(F442="",AK442=""),"",IF(COUNT(AI442:AJ442)=0,"",AK442-LOOKUP(2,1/(AI442:AJ442<>""),AI442:AJ442))) | IF(OR(F442="",AL442=""),"",IF(COUNT(AI442:AK442)=0,"",AL442-LOOKUP(2,1/(AI442:AK442<>""),AI442:AK442))) | IF(OR(F442="",AM442=""),"",IF(COUNT(AI442:AL442)=0,"",AM442-LOOKUP(2,1/(AI442:AL442<>""),AI442:AL442))) | IF(OR(F442="",AN442=""),"",IF(COUNT(AI442:AM442)=0,"",AN442-LOOKUP(2,1/(AI442:AM442<>""),AI442:AM442))) | IF(OR(F442="",AO442=""),"",IF(COUNT(AI442:AN442)=0,"",AO442-LOOKUP(2,1/(AI442:AN442<>""),AI442:AN442))) | IF(OR(F442="",AP442=""),"",IF(COUNT(AI442:AO442)=0,"",AP442-LOOKUP(2,1/(AI442:AO442<>""),AI442:AO442))) | IF(OR(F442="",AQ442=""),"",IF(COUNT(AI442:AP442)=0,"",AQ442-LOOKUP(2,1/(AI442:AP442<>""),AI442:AP442))) | IF(OR(F442="",AR442=""),"",IF(COUNT(AI442:AQ442)=0,"",AR442-LOOKUP(2,1/(AI442:AQ442<>""),AI442:AQ442))) | IF(OR(F442="",AS442=""),"",IF(COUNT(AI442:AR442)=0,"",AS442-LOOKUP(2,1/(AI442:AR442<>""),AI442:AR442))) | IF(OR(F442="",AT442=""),"",IF(COUNT(AI442:AS442)=0,"",AT442-LOOKUP(2,1/(AI442:AS442<>""),AI442:AS442))) | IF(OR(F442="",AU442=""),"",IF(COUNT(AI442:AT442)=0,"",AU442-LOOKUP(2,1/(AI442:AT442<>""),AI442:AT442))) | IF(OR(F442="",AV442=""),"",IF(COUNT(AI442:AU442)=0,"",AV442-LOOKUP(2,1/(AI442:AU442<>""),AI442:AU442))) | IF(J442="","All_Provinces",IFERROR(VLOOKUP(J442,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K442="","All_Districts",IFERROR(VLOOKUP(K442,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F443="","",ROW()-3) | [18 empty] | IF(AQ443="","",AQ443) |  |  |  | IF(W443<>"",W443,IF(OR(T443="",V443=""),"",EDATE(T443,V443))) |  |  |  |  | IF(F443="","",IF(COUNT(AI443:AV443)=0,IF(AA443="","Not started",AA443),SUBSTITUTE(LOOKUP(2,1/(AI443:AV443<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F443="",COUNT(AI443:AV443)=0),"",TODAY()-LOOKUP(2,1/(AI443:AV443<>""),AI443:AV443)) | IF(OR(F443="",COUNT(AI443:AV443)<2),"",LOOKUP(2,1/(AI443:AV443<>""),AI443:AV443)-MIN(AI443:AV443)) | IF(OR(AD443="",AC443="Not started",AC443=""),"",IFERROR(AD443-IF(VLOOKUP(AC443,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC443,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F443="","",IF(OR(AA443="Cancelled",AC443="Cancelled"),"Cancelled",IF(OR(AC443="Completed / Handover",Y443<>"",Z443>=100),"Completed — on track",IF(O443="Not awarded",IF(U443="",IF(X443="","No planned date",IF(TODAY()>X443,"Behind — past planned date",IF(X443-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U443,"Behind — award date passed",IF(U443-TODAY()<=30,"At risk — close to off track","On track"))),IF(X443="","No planned date",IF(AND(TODAY()>X443,OR(Z443="",Z443<100)),"Behind — past end date",IF(AND(T443<>"",X443<>"",Z443<>"",(Z443<100),((TODAY()-T443)/MAX(X443-T443,1)*100)-Z443>15),"Behind — progress lag",IF(AND(X443-TODAY()<=30,X443-TODAY()>=0,OR(Z443="",Z443<90)),"At risk — close to off track","On track")))))))) | IF(OR(F443="",AC443="Completed / Handover",AC443="Cancelled"),"",IF(O443="Not awarded",IF(U443<>"",U443-TODAY(),IF(X443="","",X443-TODAY())),IF(X443="","",X443-TODAY()))) | [14 empty] | IF(OR(F443="",AJ443=""),"",IF(COUNT(AI443:AI443)=0,"",AJ443-LOOKUP(2,1/(AI443:AI443<>""),AI443:AI443))) | IF(OR(F443="",AK443=""),"",IF(COUNT(AI443:AJ443)=0,"",AK443-LOOKUP(2,1/(AI443:AJ443<>""),AI443:AJ443))) | IF(OR(F443="",AL443=""),"",IF(COUNT(AI443:AK443)=0,"",AL443-LOOKUP(2,1/(AI443:AK443<>""),AI443:AK443))) | IF(OR(F443="",AM443=""),"",IF(COUNT(AI443:AL443)=0,"",AM443-LOOKUP(2,1/(AI443:AL443<>""),AI443:AL443))) | IF(OR(F443="",AN443=""),"",IF(COUNT(AI443:AM443)=0,"",AN443-LOOKUP(2,1/(AI443:AM443<>""),AI443:AM443))) | IF(OR(F443="",AO443=""),"",IF(COUNT(AI443:AN443)=0,"",AO443-LOOKUP(2,1/(AI443:AN443<>""),AI443:AN443))) | IF(OR(F443="",AP443=""),"",IF(COUNT(AI443:AO443)=0,"",AP443-LOOKUP(2,1/(AI443:AO443<>""),AI443:AO443))) | IF(OR(F443="",AQ443=""),"",IF(COUNT(AI443:AP443)=0,"",AQ443-LOOKUP(2,1/(AI443:AP443<>""),AI443:AP443))) | IF(OR(F443="",AR443=""),"",IF(COUNT(AI443:AQ443)=0,"",AR443-LOOKUP(2,1/(AI443:AQ443<>""),AI443:AQ443))) | IF(OR(F443="",AS443=""),"",IF(COUNT(AI443:AR443)=0,"",AS443-LOOKUP(2,1/(AI443:AR443<>""),AI443:AR443))) | IF(OR(F443="",AT443=""),"",IF(COUNT(AI443:AS443)=0,"",AT443-LOOKUP(2,1/(AI443:AS443<>""),AI443:AS443))) | IF(OR(F443="",AU443=""),"",IF(COUNT(AI443:AT443)=0,"",AU443-LOOKUP(2,1/(AI443:AT443<>""),AI443:AT443))) | IF(OR(F443="",AV443=""),"",IF(COUNT(AI443:AU443)=0,"",AV443-LOOKUP(2,1/(AI443:AU443<>""),AI443:AU443))) | IF(J443="","All_Provinces",IFERROR(VLOOKUP(J443,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K443="","All_Districts",IFERROR(VLOOKUP(K443,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F444="","",ROW()-3) | [18 empty] | IF(AQ444="","",AQ444) |  |  |  | IF(W444<>"",W444,IF(OR(T444="",V444=""),"",EDATE(T444,V444))) |  |  |  |  | IF(F444="","",IF(COUNT(AI444:AV444)=0,IF(AA444="","Not started",AA444),SUBSTITUTE(LOOKUP(2,1/(AI444:AV444<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F444="",COUNT(AI444:AV444)=0),"",TODAY()-LOOKUP(2,1/(AI444:AV444<>""),AI444:AV444)) | IF(OR(F444="",COUNT(AI444:AV444)<2),"",LOOKUP(2,1/(AI444:AV444<>""),AI444:AV444)-MIN(AI444:AV444)) | IF(OR(AD444="",AC444="Not started",AC444=""),"",IFERROR(AD444-IF(VLOOKUP(AC444,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC444,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F444="","",IF(OR(AA444="Cancelled",AC444="Cancelled"),"Cancelled",IF(OR(AC444="Completed / Handover",Y444<>"",Z444>=100),"Completed — on track",IF(O444="Not awarded",IF(U444="",IF(X444="","No planned date",IF(TODAY()>X444,"Behind — past planned date",IF(X444-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U444,"Behind — award date passed",IF(U444-TODAY()<=30,"At risk — close to off track","On track"))),IF(X444="","No planned date",IF(AND(TODAY()>X444,OR(Z444="",Z444<100)),"Behind — past end date",IF(AND(T444<>"",X444<>"",Z444<>"",(Z444<100),((TODAY()-T444)/MAX(X444-T444,1)*100)-Z444>15),"Behind — progress lag",IF(AND(X444-TODAY()<=30,X444-TODAY()>=0,OR(Z444="",Z444<90)),"At risk — close to off track","On track")))))))) | IF(OR(F444="",AC444="Completed / Handover",AC444="Cancelled"),"",IF(O444="Not awarded",IF(U444<>"",U444-TODAY(),IF(X444="","",X444-TODAY())),IF(X444="","",X444-TODAY()))) | [14 empty] | IF(OR(F444="",AJ444=""),"",IF(COUNT(AI444:AI444)=0,"",AJ444-LOOKUP(2,1/(AI444:AI444<>""),AI444:AI444))) | IF(OR(F444="",AK444=""),"",IF(COUNT(AI444:AJ444)=0,"",AK444-LOOKUP(2,1/(AI444:AJ444<>""),AI444:AJ444))) | IF(OR(F444="",AL444=""),"",IF(COUNT(AI444:AK444)=0,"",AL444-LOOKUP(2,1/(AI444:AK444<>""),AI444:AK444))) | IF(OR(F444="",AM444=""),"",IF(COUNT(AI444:AL444)=0,"",AM444-LOOKUP(2,1/(AI444:AL444<>""),AI444:AL444))) | IF(OR(F444="",AN444=""),"",IF(COUNT(AI444:AM444)=0,"",AN444-LOOKUP(2,1/(AI444:AM444<>""),AI444:AM444))) | IF(OR(F444="",AO444=""),"",IF(COUNT(AI444:AN444)=0,"",AO444-LOOKUP(2,1/(AI444:AN444<>""),AI444:AN444))) | IF(OR(F444="",AP444=""),"",IF(COUNT(AI444:AO444)=0,"",AP444-LOOKUP(2,1/(AI444:AO444<>""),AI444:AO444))) | IF(OR(F444="",AQ444=""),"",IF(COUNT(AI444:AP444)=0,"",AQ444-LOOKUP(2,1/(AI444:AP444<>""),AI444:AP444))) | IF(OR(F444="",AR444=""),"",IF(COUNT(AI444:AQ444)=0,"",AR444-LOOKUP(2,1/(AI444:AQ444<>""),AI444:AQ444))) | IF(OR(F444="",AS444=""),"",IF(COUNT(AI444:AR444)=0,"",AS444-LOOKUP(2,1/(AI444:AR444<>""),AI444:AR444))) | IF(OR(F444="",AT444=""),"",IF(COUNT(AI444:AS444)=0,"",AT444-LOOKUP(2,1/(AI444:AS444<>""),AI444:AS444))) | IF(OR(F444="",AU444=""),"",IF(COUNT(AI444:AT444)=0,"",AU444-LOOKUP(2,1/(AI444:AT444<>""),AI444:AT444))) | IF(OR(F444="",AV444=""),"",IF(COUNT(AI444:AU444)=0,"",AV444-LOOKUP(2,1/(AI444:AU444<>""),AI444:AU444))) | IF(J444="","All_Provinces",IFERROR(VLOOKUP(J444,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K444="","All_Districts",IFERROR(VLOOKUP(K444,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F445="","",ROW()-3) | [18 empty] | IF(AQ445="","",AQ445) |  |  |  | IF(W445<>"",W445,IF(OR(T445="",V445=""),"",EDATE(T445,V445))) |  |  |  |  | IF(F445="","",IF(COUNT(AI445:AV445)=0,IF(AA445="","Not started",AA445),SUBSTITUTE(LOOKUP(2,1/(AI445:AV445<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F445="",COUNT(AI445:AV445)=0),"",TODAY()-LOOKUP(2,1/(AI445:AV445<>""),AI445:AV445)) | IF(OR(F445="",COUNT(AI445:AV445)<2),"",LOOKUP(2,1/(AI445:AV445<>""),AI445:AV445)-MIN(AI445:AV445)) | IF(OR(AD445="",AC445="Not started",AC445=""),"",IFERROR(AD445-IF(VLOOKUP(AC445,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC445,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F445="","",IF(OR(AA445="Cancelled",AC445="Cancelled"),"Cancelled",IF(OR(AC445="Completed / Handover",Y445<>"",Z445>=100),"Completed — on track",IF(O445="Not awarded",IF(U445="",IF(X445="","No planned date",IF(TODAY()>X445,"Behind — past planned date",IF(X445-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U445,"Behind — award date passed",IF(U445-TODAY()<=30,"At risk — close to off track","On track"))),IF(X445="","No planned date",IF(AND(TODAY()>X445,OR(Z445="",Z445<100)),"Behind — past end date",IF(AND(T445<>"",X445<>"",Z445<>"",(Z445<100),((TODAY()-T445)/MAX(X445-T445,1)*100)-Z445>15),"Behind — progress lag",IF(AND(X445-TODAY()<=30,X445-TODAY()>=0,OR(Z445="",Z445<90)),"At risk — close to off track","On track")))))))) | IF(OR(F445="",AC445="Completed / Handover",AC445="Cancelled"),"",IF(O445="Not awarded",IF(U445<>"",U445-TODAY(),IF(X445="","",X445-TODAY())),IF(X445="","",X445-TODAY()))) | [14 empty] | IF(OR(F445="",AJ445=""),"",IF(COUNT(AI445:AI445)=0,"",AJ445-LOOKUP(2,1/(AI445:AI445<>""),AI445:AI445))) | IF(OR(F445="",AK445=""),"",IF(COUNT(AI445:AJ445)=0,"",AK445-LOOKUP(2,1/(AI445:AJ445<>""),AI445:AJ445))) | IF(OR(F445="",AL445=""),"",IF(COUNT(AI445:AK445)=0,"",AL445-LOOKUP(2,1/(AI445:AK445<>""),AI445:AK445))) | IF(OR(F445="",AM445=""),"",IF(COUNT(AI445:AL445)=0,"",AM445-LOOKUP(2,1/(AI445:AL445<>""),AI445:AL445))) | IF(OR(F445="",AN445=""),"",IF(COUNT(AI445:AM445)=0,"",AN445-LOOKUP(2,1/(AI445:AM445<>""),AI445:AM445))) | IF(OR(F445="",AO445=""),"",IF(COUNT(AI445:AN445)=0,"",AO445-LOOKUP(2,1/(AI445:AN445<>""),AI445:AN445))) | IF(OR(F445="",AP445=""),"",IF(COUNT(AI445:AO445)=0,"",AP445-LOOKUP(2,1/(AI445:AO445<>""),AI445:AO445))) | IF(OR(F445="",AQ445=""),"",IF(COUNT(AI445:AP445)=0,"",AQ445-LOOKUP(2,1/(AI445:AP445<>""),AI445:AP445))) | IF(OR(F445="",AR445=""),"",IF(COUNT(AI445:AQ445)=0,"",AR445-LOOKUP(2,1/(AI445:AQ445<>""),AI445:AQ445))) | IF(OR(F445="",AS445=""),"",IF(COUNT(AI445:AR445)=0,"",AS445-LOOKUP(2,1/(AI445:AR445<>""),AI445:AR445))) | IF(OR(F445="",AT445=""),"",IF(COUNT(AI445:AS445)=0,"",AT445-LOOKUP(2,1/(AI445:AS445<>""),AI445:AS445))) | IF(OR(F445="",AU445=""),"",IF(COUNT(AI445:AT445)=0,"",AU445-LOOKUP(2,1/(AI445:AT445<>""),AI445:AT445))) | IF(OR(F445="",AV445=""),"",IF(COUNT(AI445:AU445)=0,"",AV445-LOOKUP(2,1/(AI445:AU445<>""),AI445:AU445))) | IF(J445="","All_Provinces",IFERROR(VLOOKUP(J445,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K445="","All_Districts",IFERROR(VLOOKUP(K445,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F446="","",ROW()-3) | [18 empty] | IF(AQ446="","",AQ446) |  |  |  | IF(W446<>"",W446,IF(OR(T446="",V446=""),"",EDATE(T446,V446))) |  |  |  |  | IF(F446="","",IF(COUNT(AI446:AV446)=0,IF(AA446="","Not started",AA446),SUBSTITUTE(LOOKUP(2,1/(AI446:AV446<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F446="",COUNT(AI446:AV446)=0),"",TODAY()-LOOKUP(2,1/(AI446:AV446<>""),AI446:AV446)) | IF(OR(F446="",COUNT(AI446:AV446)<2),"",LOOKUP(2,1/(AI446:AV446<>""),AI446:AV446)-MIN(AI446:AV446)) | IF(OR(AD446="",AC446="Not started",AC446=""),"",IFERROR(AD446-IF(VLOOKUP(AC446,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC446,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F446="","",IF(OR(AA446="Cancelled",AC446="Cancelled"),"Cancelled",IF(OR(AC446="Completed / Handover",Y446<>"",Z446>=100),"Completed — on track",IF(O446="Not awarded",IF(U446="",IF(X446="","No planned date",IF(TODAY()>X446,"Behind — past planned date",IF(X446-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U446,"Behind — award date passed",IF(U446-TODAY()<=30,"At risk — close to off track","On track"))),IF(X446="","No planned date",IF(AND(TODAY()>X446,OR(Z446="",Z446<100)),"Behind — past end date",IF(AND(T446<>"",X446<>"",Z446<>"",(Z446<100),((TODAY()-T446)/MAX(X446-T446,1)*100)-Z446>15),"Behind — progress lag",IF(AND(X446-TODAY()<=30,X446-TODAY()>=0,OR(Z446="",Z446<90)),"At risk — close to off track","On track")))))))) | IF(OR(F446="",AC446="Completed / Handover",AC446="Cancelled"),"",IF(O446="Not awarded",IF(U446<>"",U446-TODAY(),IF(X446="","",X446-TODAY())),IF(X446="","",X446-TODAY()))) | [14 empty] | IF(OR(F446="",AJ446=""),"",IF(COUNT(AI446:AI446)=0,"",AJ446-LOOKUP(2,1/(AI446:AI446<>""),AI446:AI446))) | IF(OR(F446="",AK446=""),"",IF(COUNT(AI446:AJ446)=0,"",AK446-LOOKUP(2,1/(AI446:AJ446<>""),AI446:AJ446))) | IF(OR(F446="",AL446=""),"",IF(COUNT(AI446:AK446)=0,"",AL446-LOOKUP(2,1/(AI446:AK446<>""),AI446:AK446))) | IF(OR(F446="",AM446=""),"",IF(COUNT(AI446:AL446)=0,"",AM446-LOOKUP(2,1/(AI446:AL446<>""),AI446:AL446))) | IF(OR(F446="",AN446=""),"",IF(COUNT(AI446:AM446)=0,"",AN446-LOOKUP(2,1/(AI446:AM446<>""),AI446:AM446))) | IF(OR(F446="",AO446=""),"",IF(COUNT(AI446:AN446)=0,"",AO446-LOOKUP(2,1/(AI446:AN446<>""),AI446:AN446))) | IF(OR(F446="",AP446=""),"",IF(COUNT(AI446:AO446)=0,"",AP446-LOOKUP(2,1/(AI446:AO446<>""),AI446:AO446))) | IF(OR(F446="",AQ446=""),"",IF(COUNT(AI446:AP446)=0,"",AQ446-LOOKUP(2,1/(AI446:AP446<>""),AI446:AP446))) | IF(OR(F446="",AR446=""),"",IF(COUNT(AI446:AQ446)=0,"",AR446-LOOKUP(2,1/(AI446:AQ446<>""),AI446:AQ446))) | IF(OR(F446="",AS446=""),"",IF(COUNT(AI446:AR446)=0,"",AS446-LOOKUP(2,1/(AI446:AR446<>""),AI446:AR446))) | IF(OR(F446="",AT446=""),"",IF(COUNT(AI446:AS446)=0,"",AT446-LOOKUP(2,1/(AI446:AS446<>""),AI446:AS446))) | IF(OR(F446="",AU446=""),"",IF(COUNT(AI446:AT446)=0,"",AU446-LOOKUP(2,1/(AI446:AT446<>""),AI446:AT446))) | IF(OR(F446="",AV446=""),"",IF(COUNT(AI446:AU446)=0,"",AV446-LOOKUP(2,1/(AI446:AU446<>""),AI446:AU446))) | IF(J446="","All_Provinces",IFERROR(VLOOKUP(J446,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K446="","All_Districts",IFERROR(VLOOKUP(K446,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F447="","",ROW()-3) | [18 empty] | IF(AQ447="","",AQ447) |  |  |  | IF(W447<>"",W447,IF(OR(T447="",V447=""),"",EDATE(T447,V447))) |  |  |  |  | IF(F447="","",IF(COUNT(AI447:AV447)=0,IF(AA447="","Not started",AA447),SUBSTITUTE(LOOKUP(2,1/(AI447:AV447<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F447="",COUNT(AI447:AV447)=0),"",TODAY()-LOOKUP(2,1/(AI447:AV447<>""),AI447:AV447)) | IF(OR(F447="",COUNT(AI447:AV447)<2),"",LOOKUP(2,1/(AI447:AV447<>""),AI447:AV447)-MIN(AI447:AV447)) | IF(OR(AD447="",AC447="Not started",AC447=""),"",IFERROR(AD447-IF(VLOOKUP(AC447,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC447,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F447="","",IF(OR(AA447="Cancelled",AC447="Cancelled"),"Cancelled",IF(OR(AC447="Completed / Handover",Y447<>"",Z447>=100),"Completed — on track",IF(O447="Not awarded",IF(U447="",IF(X447="","No planned date",IF(TODAY()>X447,"Behind — past planned date",IF(X447-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U447,"Behind — award date passed",IF(U447-TODAY()<=30,"At risk — close to off track","On track"))),IF(X447="","No planned date",IF(AND(TODAY()>X447,OR(Z447="",Z447<100)),"Behind — past end date",IF(AND(T447<>"",X447<>"",Z447<>"",(Z447<100),((TODAY()-T447)/MAX(X447-T447,1)*100)-Z447>15),"Behind — progress lag",IF(AND(X447-TODAY()<=30,X447-TODAY()>=0,OR(Z447="",Z447<90)),"At risk — close to off track","On track")))))))) | IF(OR(F447="",AC447="Completed / Handover",AC447="Cancelled"),"",IF(O447="Not awarded",IF(U447<>"",U447-TODAY(),IF(X447="","",X447-TODAY())),IF(X447="","",X447-TODAY()))) | [14 empty] | IF(OR(F447="",AJ447=""),"",IF(COUNT(AI447:AI447)=0,"",AJ447-LOOKUP(2,1/(AI447:AI447<>""),AI447:AI447))) | IF(OR(F447="",AK447=""),"",IF(COUNT(AI447:AJ447)=0,"",AK447-LOOKUP(2,1/(AI447:AJ447<>""),AI447:AJ447))) | IF(OR(F447="",AL447=""),"",IF(COUNT(AI447:AK447)=0,"",AL447-LOOKUP(2,1/(AI447:AK447<>""),AI447:AK447))) | IF(OR(F447="",AM447=""),"",IF(COUNT(AI447:AL447)=0,"",AM447-LOOKUP(2,1/(AI447:AL447<>""),AI447:AL447))) | IF(OR(F447="",AN447=""),"",IF(COUNT(AI447:AM447)=0,"",AN447-LOOKUP(2,1/(AI447:AM447<>""),AI447:AM447))) | IF(OR(F447="",AO447=""),"",IF(COUNT(AI447:AN447)=0,"",AO447-LOOKUP(2,1/(AI447:AN447<>""),AI447:AN447))) | IF(OR(F447="",AP447=""),"",IF(COUNT(AI447:AO447)=0,"",AP447-LOOKUP(2,1/(AI447:AO447<>""),AI447:AO447))) | IF(OR(F447="",AQ447=""),"",IF(COUNT(AI447:AP447)=0,"",AQ447-LOOKUP(2,1/(AI447:AP447<>""),AI447:AP447))) | IF(OR(F447="",AR447=""),"",IF(COUNT(AI447:AQ447)=0,"",AR447-LOOKUP(2,1/(AI447:AQ447<>""),AI447:AQ447))) | IF(OR(F447="",AS447=""),"",IF(COUNT(AI447:AR447)=0,"",AS447-LOOKUP(2,1/(AI447:AR447<>""),AI447:AR447))) | IF(OR(F447="",AT447=""),"",IF(COUNT(AI447:AS447)=0,"",AT447-LOOKUP(2,1/(AI447:AS447<>""),AI447:AS447))) | IF(OR(F447="",AU447=""),"",IF(COUNT(AI447:AT447)=0,"",AU447-LOOKUP(2,1/(AI447:AT447<>""),AI447:AT447))) | IF(OR(F447="",AV447=""),"",IF(COUNT(AI447:AU447)=0,"",AV447-LOOKUP(2,1/(AI447:AU447<>""),AI447:AU447))) | IF(J447="","All_Provinces",IFERROR(VLOOKUP(J447,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K447="","All_Districts",IFERROR(VLOOKUP(K447,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F448="","",ROW()-3) | [18 empty] | IF(AQ448="","",AQ448) |  |  |  | IF(W448<>"",W448,IF(OR(T448="",V448=""),"",EDATE(T448,V448))) |  |  |  |  | IF(F448="","",IF(COUNT(AI448:AV448)=0,IF(AA448="","Not started",AA448),SUBSTITUTE(LOOKUP(2,1/(AI448:AV448<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F448="",COUNT(AI448:AV448)=0),"",TODAY()-LOOKUP(2,1/(AI448:AV448<>""),AI448:AV448)) | IF(OR(F448="",COUNT(AI448:AV448)<2),"",LOOKUP(2,1/(AI448:AV448<>""),AI448:AV448)-MIN(AI448:AV448)) | IF(OR(AD448="",AC448="Not started",AC448=""),"",IFERROR(AD448-IF(VLOOKUP(AC448,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC448,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F448="","",IF(OR(AA448="Cancelled",AC448="Cancelled"),"Cancelled",IF(OR(AC448="Completed / Handover",Y448<>"",Z448>=100),"Completed — on track",IF(O448="Not awarded",IF(U448="",IF(X448="","No planned date",IF(TODAY()>X448,"Behind — past planned date",IF(X448-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U448,"Behind — award date passed",IF(U448-TODAY()<=30,"At risk — close to off track","On track"))),IF(X448="","No planned date",IF(AND(TODAY()>X448,OR(Z448="",Z448<100)),"Behind — past end date",IF(AND(T448<>"",X448<>"",Z448<>"",(Z448<100),((TODAY()-T448)/MAX(X448-T448,1)*100)-Z448>15),"Behind — progress lag",IF(AND(X448-TODAY()<=30,X448-TODAY()>=0,OR(Z448="",Z448<90)),"At risk — close to off track","On track")))))))) | IF(OR(F448="",AC448="Completed / Handover",AC448="Cancelled"),"",IF(O448="Not awarded",IF(U448<>"",U448-TODAY(),IF(X448="","",X448-TODAY())),IF(X448="","",X448-TODAY()))) | [14 empty] | IF(OR(F448="",AJ448=""),"",IF(COUNT(AI448:AI448)=0,"",AJ448-LOOKUP(2,1/(AI448:AI448<>""),AI448:AI448))) | IF(OR(F448="",AK448=""),"",IF(COUNT(AI448:AJ448)=0,"",AK448-LOOKUP(2,1/(AI448:AJ448<>""),AI448:AJ448))) | IF(OR(F448="",AL448=""),"",IF(COUNT(AI448:AK448)=0,"",AL448-LOOKUP(2,1/(AI448:AK448<>""),AI448:AK448))) | IF(OR(F448="",AM448=""),"",IF(COUNT(AI448:AL448)=0,"",AM448-LOOKUP(2,1/(AI448:AL448<>""),AI448:AL448))) | IF(OR(F448="",AN448=""),"",IF(COUNT(AI448:AM448)=0,"",AN448-LOOKUP(2,1/(AI448:AM448<>""),AI448:AM448))) | IF(OR(F448="",AO448=""),"",IF(COUNT(AI448:AN448)=0,"",AO448-LOOKUP(2,1/(AI448:AN448<>""),AI448:AN448))) | IF(OR(F448="",AP448=""),"",IF(COUNT(AI448:AO448)=0,"",AP448-LOOKUP(2,1/(AI448:AO448<>""),AI448:AO448))) | IF(OR(F448="",AQ448=""),"",IF(COUNT(AI448:AP448)=0,"",AQ448-LOOKUP(2,1/(AI448:AP448<>""),AI448:AP448))) | IF(OR(F448="",AR448=""),"",IF(COUNT(AI448:AQ448)=0,"",AR448-LOOKUP(2,1/(AI448:AQ448<>""),AI448:AQ448))) | IF(OR(F448="",AS448=""),"",IF(COUNT(AI448:AR448)=0,"",AS448-LOOKUP(2,1/(AI448:AR448<>""),AI448:AR448))) | IF(OR(F448="",AT448=""),"",IF(COUNT(AI448:AS448)=0,"",AT448-LOOKUP(2,1/(AI448:AS448<>""),AI448:AS448))) | IF(OR(F448="",AU448=""),"",IF(COUNT(AI448:AT448)=0,"",AU448-LOOKUP(2,1/(AI448:AT448<>""),AI448:AT448))) | IF(OR(F448="",AV448=""),"",IF(COUNT(AI448:AU448)=0,"",AV448-LOOKUP(2,1/(AI448:AU448<>""),AI448:AU448))) | IF(J448="","All_Provinces",IFERROR(VLOOKUP(J448,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K448="","All_Districts",IFERROR(VLOOKUP(K448,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F449="","",ROW()-3) | [18 empty] | IF(AQ449="","",AQ449) |  |  |  | IF(W449<>"",W449,IF(OR(T449="",V449=""),"",EDATE(T449,V449))) |  |  |  |  | IF(F449="","",IF(COUNT(AI449:AV449)=0,IF(AA449="","Not started",AA449),SUBSTITUTE(LOOKUP(2,1/(AI449:AV449<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F449="",COUNT(AI449:AV449)=0),"",TODAY()-LOOKUP(2,1/(AI449:AV449<>""),AI449:AV449)) | IF(OR(F449="",COUNT(AI449:AV449)<2),"",LOOKUP(2,1/(AI449:AV449<>""),AI449:AV449)-MIN(AI449:AV449)) | IF(OR(AD449="",AC449="Not started",AC449=""),"",IFERROR(AD449-IF(VLOOKUP(AC449,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC449,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F449="","",IF(OR(AA449="Cancelled",AC449="Cancelled"),"Cancelled",IF(OR(AC449="Completed / Handover",Y449<>"",Z449>=100),"Completed — on track",IF(O449="Not awarded",IF(U449="",IF(X449="","No planned date",IF(TODAY()>X449,"Behind — past planned date",IF(X449-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U449,"Behind — award date passed",IF(U449-TODAY()<=30,"At risk — close to off track","On track"))),IF(X449="","No planned date",IF(AND(TODAY()>X449,OR(Z449="",Z449<100)),"Behind — past end date",IF(AND(T449<>"",X449<>"",Z449<>"",(Z449<100),((TODAY()-T449)/MAX(X449-T449,1)*100)-Z449>15),"Behind — progress lag",IF(AND(X449-TODAY()<=30,X449-TODAY()>=0,OR(Z449="",Z449<90)),"At risk — close to off track","On track")))))))) | IF(OR(F449="",AC449="Completed / Handover",AC449="Cancelled"),"",IF(O449="Not awarded",IF(U449<>"",U449-TODAY(),IF(X449="","",X449-TODAY())),IF(X449="","",X449-TODAY()))) | [14 empty] | IF(OR(F449="",AJ449=""),"",IF(COUNT(AI449:AI449)=0,"",AJ449-LOOKUP(2,1/(AI449:AI449<>""),AI449:AI449))) | IF(OR(F449="",AK449=""),"",IF(COUNT(AI449:AJ449)=0,"",AK449-LOOKUP(2,1/(AI449:AJ449<>""),AI449:AJ449))) | IF(OR(F449="",AL449=""),"",IF(COUNT(AI449:AK449)=0,"",AL449-LOOKUP(2,1/(AI449:AK449<>""),AI449:AK449))) | IF(OR(F449="",AM449=""),"",IF(COUNT(AI449:AL449)=0,"",AM449-LOOKUP(2,1/(AI449:AL449<>""),AI449:AL449))) | IF(OR(F449="",AN449=""),"",IF(COUNT(AI449:AM449)=0,"",AN449-LOOKUP(2,1/(AI449:AM449<>""),AI449:AM449))) | IF(OR(F449="",AO449=""),"",IF(COUNT(AI449:AN449)=0,"",AO449-LOOKUP(2,1/(AI449:AN449<>""),AI449:AN449))) | IF(OR(F449="",AP449=""),"",IF(COUNT(AI449:AO449)=0,"",AP449-LOOKUP(2,1/(AI449:AO449<>""),AI449:AO449))) | IF(OR(F449="",AQ449=""),"",IF(COUNT(AI449:AP449)=0,"",AQ449-LOOKUP(2,1/(AI449:AP449<>""),AI449:AP449))) | IF(OR(F449="",AR449=""),"",IF(COUNT(AI449:AQ449)=0,"",AR449-LOOKUP(2,1/(AI449:AQ449<>""),AI449:AQ449))) | IF(OR(F449="",AS449=""),"",IF(COUNT(AI449:AR449)=0,"",AS449-LOOKUP(2,1/(AI449:AR449<>""),AI449:AR449))) | IF(OR(F449="",AT449=""),"",IF(COUNT(AI449:AS449)=0,"",AT449-LOOKUP(2,1/(AI449:AS449<>""),AI449:AS449))) | IF(OR(F449="",AU449=""),"",IF(COUNT(AI449:AT449)=0,"",AU449-LOOKUP(2,1/(AI449:AT449<>""),AI449:AT449))) | IF(OR(F449="",AV449=""),"",IF(COUNT(AI449:AU449)=0,"",AV449-LOOKUP(2,1/(AI449:AU449<>""),AI449:AU449))) | IF(J449="","All_Provinces",IFERROR(VLOOKUP(J449,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K449="","All_Districts",IFERROR(VLOOKUP(K449,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F450="","",ROW()-3) | [18 empty] | IF(AQ450="","",AQ450) |  |  |  | IF(W450<>"",W450,IF(OR(T450="",V450=""),"",EDATE(T450,V450))) |  |  |  |  | IF(F450="","",IF(COUNT(AI450:AV450)=0,IF(AA450="","Not started",AA450),SUBSTITUTE(LOOKUP(2,1/(AI450:AV450<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F450="",COUNT(AI450:AV450)=0),"",TODAY()-LOOKUP(2,1/(AI450:AV450<>""),AI450:AV450)) | IF(OR(F450="",COUNT(AI450:AV450)<2),"",LOOKUP(2,1/(AI450:AV450<>""),AI450:AV450)-MIN(AI450:AV450)) | IF(OR(AD450="",AC450="Not started",AC450=""),"",IFERROR(AD450-IF(VLOOKUP(AC450,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC450,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F450="","",IF(OR(AA450="Cancelled",AC450="Cancelled"),"Cancelled",IF(OR(AC450="Completed / Handover",Y450<>"",Z450>=100),"Completed — on track",IF(O450="Not awarded",IF(U450="",IF(X450="","No planned date",IF(TODAY()>X450,"Behind — past planned date",IF(X450-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U450,"Behind — award date passed",IF(U450-TODAY()<=30,"At risk — close to off track","On track"))),IF(X450="","No planned date",IF(AND(TODAY()>X450,OR(Z450="",Z450<100)),"Behind — past end date",IF(AND(T450<>"",X450<>"",Z450<>"",(Z450<100),((TODAY()-T450)/MAX(X450-T450,1)*100)-Z450>15),"Behind — progress lag",IF(AND(X450-TODAY()<=30,X450-TODAY()>=0,OR(Z450="",Z450<90)),"At risk — close to off track","On track")))))))) | IF(OR(F450="",AC450="Completed / Handover",AC450="Cancelled"),"",IF(O450="Not awarded",IF(U450<>"",U450-TODAY(),IF(X450="","",X450-TODAY())),IF(X450="","",X450-TODAY()))) | [14 empty] | IF(OR(F450="",AJ450=""),"",IF(COUNT(AI450:AI450)=0,"",AJ450-LOOKUP(2,1/(AI450:AI450<>""),AI450:AI450))) | IF(OR(F450="",AK450=""),"",IF(COUNT(AI450:AJ450)=0,"",AK450-LOOKUP(2,1/(AI450:AJ450<>""),AI450:AJ450))) | IF(OR(F450="",AL450=""),"",IF(COUNT(AI450:AK450)=0,"",AL450-LOOKUP(2,1/(AI450:AK450<>""),AI450:AK450))) | IF(OR(F450="",AM450=""),"",IF(COUNT(AI450:AL450)=0,"",AM450-LOOKUP(2,1/(AI450:AL450<>""),AI450:AL450))) | IF(OR(F450="",AN450=""),"",IF(COUNT(AI450:AM450)=0,"",AN450-LOOKUP(2,1/(AI450:AM450<>""),AI450:AM450))) | IF(OR(F450="",AO450=""),"",IF(COUNT(AI450:AN450)=0,"",AO450-LOOKUP(2,1/(AI450:AN450<>""),AI450:AN450))) | IF(OR(F450="",AP450=""),"",IF(COUNT(AI450:AO450)=0,"",AP450-LOOKUP(2,1/(AI450:AO450<>""),AI450:AO450))) | IF(OR(F450="",AQ450=""),"",IF(COUNT(AI450:AP450)=0,"",AQ450-LOOKUP(2,1/(AI450:AP450<>""),AI450:AP450))) | IF(OR(F450="",AR450=""),"",IF(COUNT(AI450:AQ450)=0,"",AR450-LOOKUP(2,1/(AI450:AQ450<>""),AI450:AQ450))) | IF(OR(F450="",AS450=""),"",IF(COUNT(AI450:AR450)=0,"",AS450-LOOKUP(2,1/(AI450:AR450<>""),AI450:AR450))) | IF(OR(F450="",AT450=""),"",IF(COUNT(AI450:AS450)=0,"",AT450-LOOKUP(2,1/(AI450:AS450<>""),AI450:AS450))) | IF(OR(F450="",AU450=""),"",IF(COUNT(AI450:AT450)=0,"",AU450-LOOKUP(2,1/(AI450:AT450<>""),AI450:AT450))) | IF(OR(F450="",AV450=""),"",IF(COUNT(AI450:AU450)=0,"",AV450-LOOKUP(2,1/(AI450:AU450<>""),AI450:AU450))) | IF(J450="","All_Provinces",IFERROR(VLOOKUP(J450,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K450="","All_Districts",IFERROR(VLOOKUP(K450,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F451="","",ROW()-3) | [18 empty] | IF(AQ451="","",AQ451) |  |  |  | IF(W451<>"",W451,IF(OR(T451="",V451=""),"",EDATE(T451,V451))) |  |  |  |  | IF(F451="","",IF(COUNT(AI451:AV451)=0,IF(AA451="","Not started",AA451),SUBSTITUTE(LOOKUP(2,1/(AI451:AV451<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F451="",COUNT(AI451:AV451)=0),"",TODAY()-LOOKUP(2,1/(AI451:AV451<>""),AI451:AV451)) | IF(OR(F451="",COUNT(AI451:AV451)<2),"",LOOKUP(2,1/(AI451:AV451<>""),AI451:AV451)-MIN(AI451:AV451)) | IF(OR(AD451="",AC451="Not started",AC451=""),"",IFERROR(AD451-IF(VLOOKUP(AC451,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC451,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F451="","",IF(OR(AA451="Cancelled",AC451="Cancelled"),"Cancelled",IF(OR(AC451="Completed / Handover",Y451<>"",Z451>=100),"Completed — on track",IF(O451="Not awarded",IF(U451="",IF(X451="","No planned date",IF(TODAY()>X451,"Behind — past planned date",IF(X451-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U451,"Behind — award date passed",IF(U451-TODAY()<=30,"At risk — close to off track","On track"))),IF(X451="","No planned date",IF(AND(TODAY()>X451,OR(Z451="",Z451<100)),"Behind — past end date",IF(AND(T451<>"",X451<>"",Z451<>"",(Z451<100),((TODAY()-T451)/MAX(X451-T451,1)*100)-Z451>15),"Behind — progress lag",IF(AND(X451-TODAY()<=30,X451-TODAY()>=0,OR(Z451="",Z451<90)),"At risk — close to off track","On track")))))))) | IF(OR(F451="",AC451="Completed / Handover",AC451="Cancelled"),"",IF(O451="Not awarded",IF(U451<>"",U451-TODAY(),IF(X451="","",X451-TODAY())),IF(X451="","",X451-TODAY()))) | [14 empty] | IF(OR(F451="",AJ451=""),"",IF(COUNT(AI451:AI451)=0,"",AJ451-LOOKUP(2,1/(AI451:AI451<>""),AI451:AI451))) | IF(OR(F451="",AK451=""),"",IF(COUNT(AI451:AJ451)=0,"",AK451-LOOKUP(2,1/(AI451:AJ451<>""),AI451:AJ451))) | IF(OR(F451="",AL451=""),"",IF(COUNT(AI451:AK451)=0,"",AL451-LOOKUP(2,1/(AI451:AK451<>""),AI451:AK451))) | IF(OR(F451="",AM451=""),"",IF(COUNT(AI451:AL451)=0,"",AM451-LOOKUP(2,1/(AI451:AL451<>""),AI451:AL451))) | IF(OR(F451="",AN451=""),"",IF(COUNT(AI451:AM451)=0,"",AN451-LOOKUP(2,1/(AI451:AM451<>""),AI451:AM451))) | IF(OR(F451="",AO451=""),"",IF(COUNT(AI451:AN451)=0,"",AO451-LOOKUP(2,1/(AI451:AN451<>""),AI451:AN451))) | IF(OR(F451="",AP451=""),"",IF(COUNT(AI451:AO451)=0,"",AP451-LOOKUP(2,1/(AI451:AO451<>""),AI451:AO451))) | IF(OR(F451="",AQ451=""),"",IF(COUNT(AI451:AP451)=0,"",AQ451-LOOKUP(2,1/(AI451:AP451<>""),AI451:AP451))) | IF(OR(F451="",AR451=""),"",IF(COUNT(AI451:AQ451)=0,"",AR451-LOOKUP(2,1/(AI451:AQ451<>""),AI451:AQ451))) | IF(OR(F451="",AS451=""),"",IF(COUNT(AI451:AR451)=0,"",AS451-LOOKUP(2,1/(AI451:AR451<>""),AI451:AR451))) | IF(OR(F451="",AT451=""),"",IF(COUNT(AI451:AS451)=0,"",AT451-LOOKUP(2,1/(AI451:AS451<>""),AI451:AS451))) | IF(OR(F451="",AU451=""),"",IF(COUNT(AI451:AT451)=0,"",AU451-LOOKUP(2,1/(AI451:AT451<>""),AI451:AT451))) | IF(OR(F451="",AV451=""),"",IF(COUNT(AI451:AU451)=0,"",AV451-LOOKUP(2,1/(AI451:AU451<>""),AI451:AU451))) | IF(J451="","All_Provinces",IFERROR(VLOOKUP(J451,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K451="","All_Districts",IFERROR(VLOOKUP(K451,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F452="","",ROW()-3) | [18 empty] | IF(AQ452="","",AQ452) |  |  |  | IF(W452<>"",W452,IF(OR(T452="",V452=""),"",EDATE(T452,V452))) |  |  |  |  | IF(F452="","",IF(COUNT(AI452:AV452)=0,IF(AA452="","Not started",AA452),SUBSTITUTE(LOOKUP(2,1/(AI452:AV452<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F452="",COUNT(AI452:AV452)=0),"",TODAY()-LOOKUP(2,1/(AI452:AV452<>""),AI452:AV452)) | IF(OR(F452="",COUNT(AI452:AV452)<2),"",LOOKUP(2,1/(AI452:AV452<>""),AI452:AV452)-MIN(AI452:AV452)) | IF(OR(AD452="",AC452="Not started",AC452=""),"",IFERROR(AD452-IF(VLOOKUP(AC452,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC452,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F452="","",IF(OR(AA452="Cancelled",AC452="Cancelled"),"Cancelled",IF(OR(AC452="Completed / Handover",Y452<>"",Z452>=100),"Completed — on track",IF(O452="Not awarded",IF(U452="",IF(X452="","No planned date",IF(TODAY()>X452,"Behind — past planned date",IF(X452-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U452,"Behind — award date passed",IF(U452-TODAY()<=30,"At risk — close to off track","On track"))),IF(X452="","No planned date",IF(AND(TODAY()>X452,OR(Z452="",Z452<100)),"Behind — past end date",IF(AND(T452<>"",X452<>"",Z452<>"",(Z452<100),((TODAY()-T452)/MAX(X452-T452,1)*100)-Z452>15),"Behind — progress lag",IF(AND(X452-TODAY()<=30,X452-TODAY()>=0,OR(Z452="",Z452<90)),"At risk — close to off track","On track")))))))) | IF(OR(F452="",AC452="Completed / Handover",AC452="Cancelled"),"",IF(O452="Not awarded",IF(U452<>"",U452-TODAY(),IF(X452="","",X452-TODAY())),IF(X452="","",X452-TODAY()))) | [14 empty] | IF(OR(F452="",AJ452=""),"",IF(COUNT(AI452:AI452)=0,"",AJ452-LOOKUP(2,1/(AI452:AI452<>""),AI452:AI452))) | IF(OR(F452="",AK452=""),"",IF(COUNT(AI452:AJ452)=0,"",AK452-LOOKUP(2,1/(AI452:AJ452<>""),AI452:AJ452))) | IF(OR(F452="",AL452=""),"",IF(COUNT(AI452:AK452)=0,"",AL452-LOOKUP(2,1/(AI452:AK452<>""),AI452:AK452))) | IF(OR(F452="",AM452=""),"",IF(COUNT(AI452:AL452)=0,"",AM452-LOOKUP(2,1/(AI452:AL452<>""),AI452:AL452))) | IF(OR(F452="",AN452=""),"",IF(COUNT(AI452:AM452)=0,"",AN452-LOOKUP(2,1/(AI452:AM452<>""),AI452:AM452))) | IF(OR(F452="",AO452=""),"",IF(COUNT(AI452:AN452)=0,"",AO452-LOOKUP(2,1/(AI452:AN452<>""),AI452:AN452))) | IF(OR(F452="",AP452=""),"",IF(COUNT(AI452:AO452)=0,"",AP452-LOOKUP(2,1/(AI452:AO452<>""),AI452:AO452))) | IF(OR(F452="",AQ452=""),"",IF(COUNT(AI452:AP452)=0,"",AQ452-LOOKUP(2,1/(AI452:AP452<>""),AI452:AP452))) | IF(OR(F452="",AR452=""),"",IF(COUNT(AI452:AQ452)=0,"",AR452-LOOKUP(2,1/(AI452:AQ452<>""),AI452:AQ452))) | IF(OR(F452="",AS452=""),"",IF(COUNT(AI452:AR452)=0,"",AS452-LOOKUP(2,1/(AI452:AR452<>""),AI452:AR452))) | IF(OR(F452="",AT452=""),"",IF(COUNT(AI452:AS452)=0,"",AT452-LOOKUP(2,1/(AI452:AS452<>""),AI452:AS452))) | IF(OR(F452="",AU452=""),"",IF(COUNT(AI452:AT452)=0,"",AU452-LOOKUP(2,1/(AI452:AT452<>""),AI452:AT452))) | IF(OR(F452="",AV452=""),"",IF(COUNT(AI452:AU452)=0,"",AV452-LOOKUP(2,1/(AI452:AU452<>""),AI452:AU452))) | IF(J452="","All_Provinces",IFERROR(VLOOKUP(J452,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K452="","All_Districts",IFERROR(VLOOKUP(K452,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
IF(F453="","",ROW()-3) | [18 empty] | IF(AQ453="","",AQ453) |  |  |  | IF(W453<>"",W453,IF(OR(T453="",V453=""),"",EDATE(T453,V453))) |  |  |  |  | IF(F453="","",IF(COUNT(AI453:AV453)=0,IF(AA453="","Not started",AA453),SUBSTITUTE(LOOKUP(2,1/(AI453:AV453<>""),$AI$3:$AV$3),"Date: ",""))) | IF(OR(F453="",COUNT(AI453:AV453)=0),"",TODAY()-LOOKUP(2,1/(AI453:AV453<>""),AI453:AV453)) | IF(OR(F453="",COUNT(AI453:AV453)<2),"",LOOKUP(2,1/(AI453:AV453<>""),AI453:AV453)-MIN(AI453:AV453)) | IF(OR(AD453="",AC453="Not started",AC453=""),"",IFERROR(AD453-IF(VLOOKUP(AC453,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)="",0,VLOOKUP(AC453,'06_Status_Pipeline'!$B$3:$E$20,4,FALSE)),"")) | IF(F453="","",IF(OR(AA453="Cancelled",AC453="Cancelled"),"Cancelled",IF(OR(AC453="Completed / Handover",Y453<>"",Z453>=100),"Completed — on track",IF(O453="Not awarded",IF(U453="",IF(X453="","No planned date",IF(TODAY()>X453,"Behind — past planned date",IF(X453-TODAY()<=30,"At risk — close to off track","On track"))),IF(TODAY()>U453,"Behind — award date passed",IF(U453-TODAY()<=30,"At risk — close to off track","On track"))),IF(X453="","No planned date",IF(AND(TODAY()>X453,OR(Z453="",Z453<100)),"Behind — past end date",IF(AND(T453<>"",X453<>"",Z453<>"",(Z453<100),((TODAY()-T453)/MAX(X453-T453,1)*100)-Z453>15),"Behind — progress lag",IF(AND(X453-TODAY()<=30,X453-TODAY()>=0,OR(Z453="",Z453<90)),"At risk — close to off track","On track")))))))) | IF(OR(F453="",AC453="Completed / Handover",AC453="Cancelled"),"",IF(O453="Not awarded",IF(U453<>"",U453-TODAY(),IF(X453="","",X453-TODAY())),IF(X453="","",X453-TODAY()))) | [14 empty] | IF(OR(F453="",AJ453=""),"",IF(COUNT(AI453:AI453)=0,"",AJ453-LOOKUP(2,1/(AI453:AI453<>""),AI453:AI453))) | IF(OR(F453="",AK453=""),"",IF(COUNT(AI453:AJ453)=0,"",AK453-LOOKUP(2,1/(AI453:AJ453<>""),AI453:AJ453))) | IF(OR(F453="",AL453=""),"",IF(COUNT(AI453:AK453)=0,"",AL453-LOOKUP(2,1/(AI453:AK453<>""),AI453:AK453))) | IF(OR(F453="",AM453=""),"",IF(COUNT(AI453:AL453)=0,"",AM453-LOOKUP(2,1/(AI453:AL453<>""),AI453:AL453))) | IF(OR(F453="",AN453=""),"",IF(COUNT(AI453:AM453)=0,"",AN453-LOOKUP(2,1/(AI453:AM453<>""),AI453:AM453))) | IF(OR(F453="",AO453=""),"",IF(COUNT(AI453:AN453)=0,"",AO453-LOOKUP(2,1/(AI453:AN453<>""),AI453:AN453))) | IF(OR(F453="",AP453=""),"",IF(COUNT(AI453:AO453)=0,"",AP453-LOOKUP(2,1/(AI453:AO453<>""),AI453:AO453))) | IF(OR(F453="",AQ453=""),"",IF(COUNT(AI453:AP453)=0,"",AQ453-LOOKUP(2,1/(AI453:AP453<>""),AI453:AP453))) | IF(OR(F453="",AR453=""),"",IF(COUNT(AI453:AQ453)=0,"",AR453-LOOKUP(2,1/(AI453:AQ453<>""),AI453:AQ453))) | IF(OR(F453="",AS453=""),"",IF(COUNT(AI453:AR453)=0,"",AS453-LOOKUP(2,1/(AI453:AR453<>""),AI453:AR453))) | IF(OR(F453="",AT453=""),"",IF(COUNT(AI453:AS453)=0,"",AT453-LOOKUP(2,1/(AI453:AS453<>""),AI453:AS453))) | IF(OR(F453="",AU453=""),"",IF(COUNT(AI453:AT453)=0,"",AU453-LOOKUP(2,1/(AI453:AT453<>""),AI453:AT453))) | IF(OR(F453="",AV453=""),"",IF(COUNT(AI453:AU453)=0,"",AV453-LOOKUP(2,1/(AI453:AU453<>""),AI453:AU453))) | IF(J453="","All_Provinces",IFERROR(VLOOKUP(J453,'09_Lookups'!$A$4:$B$20,2,FALSE),"All_Provinces")) | IF(K453="","All_Districts",IFERROR(VLOOKUP(K453,'09_Lookups'!$E$4:$F$42,2,FALSE),"All_Districts"))
Note on B3: Same Package ID on every sub-project of one contract. Package #8-AF2 IS is two canals / two rows; Package #10-AF2 IS is four canals / four rows. Use the outline +/- on the left to collapse extra sites.
Note on C3: Full Package / Contract Name from the master file. Repeated on every sub-project row of that package.
Note on D3: Position of this site inside the package, for example 2 of 4.
Note on G3: Major type: Watershed Management, Irrigation Scheme, Drip Irrigation, Agroforestry saplings / seeds, or Laser Land Leveler (LLL).
Note on H3: Sub-type under the major intervention: irrigation canal, protection wall, check dam, and so on.
Note on O3: Awarded = contract signed. Not awarded = still in design / procurement.
Note on Q3: Repeated on every sub-project of the same contract. To count unique contracts for this company, filter 10_By_Contractor or 03_Package_Summary — do not count the number of rows here. ZSCC on Package #10 is one contract / four canals.
Note on T3: Copies Date: Awarded. Enter the contract signature date in the Awarded status-date column.
Note on AA3: Use this until official step dates are entered. Current Status follows dates once they exist.
Note on AC3: Latest step that has a date. If no dates are entered, uses Reported Status.
Note on AD3: TODAY minus the latest status date. Turns red after 30 days.
Note on AG3: Green = on track. Amber = within 30 days of a planned date (close to off track). Red = behind the planned award or end date, or physical progress lagging the elapsed contract time by more than 15 points.
Note on AH3: Positive = days remaining until the planned award (Not awarded) or contract end (Awarded). Negative = days behind that date.

## 06_Status_Pipeline
Status pipeline — add a name in a spare slot to create a new step on the tracker
Slot | Status name (edit / add here) | Short name | Description | Target days | Notes
1 | Under Design | Design | Detailed design, surveys, and drawings are being prepared. | 30 | Used by tracker date headers and duration labels.
2 | Under Review of WRI | WRI Review | Water Resources / WRI is reviewing the design package. | 14 | Used by tracker date headers and duration labels.
3 | Under LTO Review | LTO Review | Legal / LTO clearance of the package. | 10 | Used by tracker date headers and duration labels.
4 | PR to be Raised | PR | Purchase request / procurement request still to be raised. | 10 | Used by tracker date headers and duration labels.
5 | ITB Launched | ITB | Invitation to Bid has been issued. | 21 | Used by tracker date headers and duration labels.
6 | Retendered (Re-ITB) | Re-ITB | Previous bid failed or was cancelled; invitation re-issued. | 21 | Used by tracker date headers and duration labels.
7 | Under Technical Evaluation | Tech Eval | Bids are under technical evaluation. | 14 | Used by tracker date headers and duration labels.
8 | Under Awarding | Awarding | Award recommendation, negotiations, and approval. | 14 | Used by tracker date headers and duration labels.
9 | Awarded | Awarded | Contract signed / notice of award issued. | 0 | Used by tracker date headers and duration labels.
10 | Under Construction | Construction | Contractor is mobilised and physical works are ongoing. | 150 | Used by tracker date headers and duration labels.
11 | Completed / Handover | Completed | Works completed and handed over. | 0 | Used by tracker date headers and duration labels.
12 |  |  | Spare slot — type a status name here to add a step. |  | Type a status name in column B to activate this date column on the tracker.
13 |  |  | Spare slot — type a status name here to add a step. |  | Type a status name in column B to activate this date column on the tracker.
14 |  |  | Spare slot — type a status name here to add a step. |  | Type a status name in column B to activate this date column on the tracker.

## 07_Domains
Domains — type a new value in the first empty cell of a column to add it to the dropdowns
Interventions | Donors | Projects | Regions | Statuses | All_Provinces | All_Districts | AwardGroups | Families | Contractors
Irrigation Canal | World Bank (WBK/AF-2) | Emergency Food Security Project (EFSP) – WBK/AF-2 | West / Herat | Under Design | Herat | Herat | Awarded | Irrigation Scheme | Abdul Ghafour
Protection Wall | World Bank (WBK) | Emergency Food Security Project (EFSP) | East / Jalalabad | Under Review of WRI | Badghis | Injil | Not awarded | Watershed Management | Abdul Qadeer
Karez Rehabilitation | WFP | WBK/AF-2 Component 2: Water and Resilience Services | Central / Kabul | Under LTO Review | Farah | Guzara |  | Drip Irrigation | Abdul Qayum
Intake / Diversion | FAO |  | Central Highland / Bamyan | PR to be Raised | Ghor | Karukh |  | Laser Land Leveler (LLL) | Abdul Rahman
Check Dam | UNICEF |  | Southeast / Gardez | ITB Launched | Nangarhar | Pashtun Zarghun |  | Agroforestry saplings / seeds | Abdullah
Boulder Check Dam | ADB |  | South / Kandahar | Retendered (Re-ITB) | Kunar | Zindajan |  |  | Abdur Raqeeb
Check Dam and Water Pond | Government |  | North / Mazar | Under Technical Evaluation | Laghman | Gulran |  |  | Afghan Aakam Construction and Road Company C. JV with D-Amini Mashwani Construction Road Juroni and Construction Materials Production Company (AACRC&JV DAMCC)
Gabion Structure | Other |  | Northeast / Kunduz | Under Awarding | Nuristan | Kohsan |  |  | Afghan Aakam Construction and Road Company. JV with D- Amini Mashwani Construction Company (AACC)
Flood Protection |  |  |  | Awarded | Kabul | Ghoryan |  |  | Afghan Eithad construction and Road Building company (AECC)
Drip Irrigation Plot |  |  |  | Under Construction | Parwan | Obe |  |  | Afghan Laser Engineering and Construction Company (ALCC)
LLL unit |  |  |  | Completed / Handover | Kapisa | Chishti Sharif |  |  | AFGHAN LUCKY CONSTRUCTION COMPANY (ALCC)
Saplings and seeds |  |  |  | Not started | Logar | Shindand |  |  | Ahmad
Water Supply Scheme |  |  |  | Cancelled | Maidan Wardak | Adraskan |  |  | Ahmad Zia
Other |  |  |  |  | Panjshir | Farsi |  |  | Akhtar Mohammad
[5 empty] | Bamyan | Qala-e-Naw |  |  | Alberoni University
[5 empty] | Daykundi | Qadis |  |  | Ali Dost
[5 empty] | Paktya | Muqur |  |  | ALTIN CONSTRUCTION AND ROAD BUILDING COMPANY (ACC)
[5 empty] | Paktika | Bala Murghab |  |  | Arman Millad Construction Company (AMCC)
[5 empty] | Khost | Jawand |  |  | Arman Sharq Construction Company ASCC)
[5 empty] | Ghazni | Ab Kamari |  |  | Awrish builder construction company (ABCC)
[5 empty] | Kandahar | Ghormach |  |  | Bahartamadun Construction Company (BCC)
[5 empty] | Helmand | Farah |  |  | Bakhter Pairoz Construction Company (BPCC)
[5 empty] | Zabul | Pusht Rod |  |  | Da Maidan Zawahnono Construction Company (DMZCC)
[5 empty] | Uruzgan | Khaki Safed |  |  | Edi Mohammad
[5 empty] | Nimroz | Qala-e-Kah |  |  | Ehsanullah
[5 empty] | Balkh | Shib Koh |  |  | Estehkam Baba Construction and Road Construction Company (EBCC)
[5 empty] | Samangan | Bala Buluk |  |  | Estehkam Baba Construction Company JV Tamadon Bamik Construction Company (EBCC)
[5 empty] | Jawzjan | Gulistan |  |  | Faiz Qurbani Construction Company (FQCC)
[5 empty] | Sar-e-Pul | Pur Chaman |  |  | Farhad Matoonyar Construction Company (FMCC)
[5 empty] | Faryab | Bakwa |  |  | Fazal Din
[5 empty] | Kunduz | Lash wa Juwayn |  |  | Fazel Rahman
[5 empty] | Baghlan | Anar Dara |  |  | Fazl Ahmad
[5 empty] | Takhar | Firozkoh |  |  | Fida Mohammad
[5 empty] | Badakhshan | Lal wa Sarjangal |  |  | Gafoor Jan
[6 empty] | Tulak |  |  | Ghazi Khan
[6 empty] | Shahrak |  |  | Ghulam
[6 empty] | Dawlat Yar |  |  | Ghulam Haider Shah
[6 empty] | Charsada |  |  | Ghulam Hussain
[6 empty] | Pasaband |  |  | Ghulam Mahboob
[6 empty] | Saghar |  |  | Green Bentley construction Company (GBCC)
[6 empty] | Taywara |  |  | Habibullah
[6 empty] | Du Layna |  |  | Habiburahman
[6 empty] | Jalalabad |  |  | Haji Abdul Qaiyom
[6 empty] | Behsud |  |  | Haji Amir Gul
[6 empty] | Surkh Rod |  |  | Haji Hamayoon Salimi
[6 empty] | Kama |  |  | Haji Jamal
[6 empty] | Kuz Kunar |  |  | Haji Nazar Gul
[6 empty] | Rodat |  |  | Haji Yaqoub
[6 empty] | Bati Kot |  |  | Hakim Khan
[6 empty] | Shinwar |  |  | Hasan Khil
[6 empty] | Achin |  |  | Hayatullah
[6 empty] | Nazyan |  |  | Hazrat Wali
[6 empty] | Dur Baba |  |  | Hemat Ghorzang Construction & Logistic Service Company (HGCC)
[6 empty] | Mohmand Dara |  |  | Hemat safi construction company (HSCC)
[6 empty] | Lal Pur |  |  | Islam Gul
[6 empty] | Goshta |  |  | Jalal
[6 empty] | Chaparhar |  |  | Kapisa Kohna Dah Construction Company (KKCC)
[6 empty] | Khogyani |  |  | Khairullah Zia
[6 empty] | Pachir wa Agam |  |  | Khaliqi Building & Road Construction Company (KBRCC)
[6 empty] | Sherzad |  |  | Kunar University
[6 empty] | Hesarak |  |  | M. Afzal
[6 empty] | Darah-i-Nur |  |  | M. Nabi
[6 empty] | Asadabad |  |  | Mahmood Raqi Nawin Construction & Road Building Company (MRCC)
[6 empty] | Narang |  |  | Malik Hajdar Construction and Road Company (MHCC)
[6 empty] | Sawkai |  |  | Malik Rostam
[6 empty] | Khas Kunar |  |  | Mateeullah
[6 empty] | Nurgal |  |  | Mohammad Akbar
[6 empty] | Chawkay |  |  | Mohammad Ali
[6 empty] | Dangam |  |  | Mohammad Arif
[6 empty] | Ghaziabad |  |  | Mohammad Hashim
[6 empty] | Marawara |  |  | Mohammad Ibrahim
[6 empty] | Shigal |  |  | Mohammad Naim
[6 empty] | Wata Pur |  |  | Mohammad Qasim
[6 empty] | Naray |  |  | Mohammad Rasool Gharani
[6 empty] | Dara-i-Pech |  |  | Mohammad Waseem
[6 empty] | Mihtarlam |  |  | Mohammad Yousaf
[6 empty] | Qarghayi |  |  | Mudeser Bigmurad Construction Company (MBCC)
[6 empty] | Alishing |  |  | Naeemi Safi Construction & Construction Material Company (NSCC)
[6 empty] | Alingar |  |  | Najeebullah
[6 empty] | Dawlat Shah |  |  | Naser Khan
[6 empty] | Parun |  |  | Nasratullah
[6 empty] | Wama |  |  | Nazar Khan
[6 empty] | Kamdesh |  |  | Nesar Ahmad, Koklam
[6 empty] | Barg-i-Matal |  |  | New Safi Zada Construction & Road Building Company JV with Elyas Aryoubi Constructin Road building and Logistic Company (NSZ&EACC)
[6 empty] | Mandol |  |  | Nomae Shahr Construction Company (NSCC)
[6 empty] | Du Ab |  |  | Omar Mortaza Construction & Road Building JV Karwan Seraji Construction and Road Building Company (OMCC&KSCC)
[6 empty] | Nurgaram |  |  | Ramin
[6 empty] | Waygal |  |  | Reg-e-Rawa park
[6 empty] | PD#13 Kabul |  |  | Reza
[6 empty] | Deh Sabz |  |  | Sadullah
[6 empty] | Bagrami |  |  | Saifuddin
[6 empty] | Paghman |  |  | Saifullah
[6 empty] | Char Asiab |  |  | Sakht shamal construction and road building company (SSCC)
[6 empty] | Shakardara |  |  | Salam Jan
[6 empty] | Musayi |  |  | Sayed Abad Construction Company (SACC)
[6 empty] | Kalakan |  |  | Sayed Hassan
[6 empty] | Qarabagh |  |  | Sayed Mohammad
[6 empty] | Istalif |  |  | Sayed Shirazi Construction and Road Building Company (SCRC)
[6 empty] | Farza |  |  | Seddiq Amini Construction and Logistic Services (SACC)
[6 empty] | Guldara |  |  | Shafiqullah Wahidi Construction Company (SWCC)
[6 empty] | Khak-e-Jabbar |  |  | SHAMAL KARDAN ROAD CONSTRUCTION AND LOGISTIC SERVICES COMPANY LTD (SKRCC)
[6 empty] | Surobi |  |  | Shams Afghan Vision Construction and Logistic Services (SAVCC)
[6 empty] | Charikar |  |  | Shamsurahman
[6 empty] | Bagram |  |  | Shirali Khan Barakatzai Construction Company (SBCC)
[6 empty] | Jabal Saraj |  |  | Sobhan
[6 empty] | Salang |  |  | Trust Grow Construction and Engineering Company (TGCC)
[6 empty] | Shinwari |  |  | Unique Wahaj Construction Company (UWCC)
[6 empty] | Sayed Khel |  |  | Waheed Wahaj Construction Company (WWCC)
[6 empty] | Koh-i-Safi |  |  | Wardak University
[6 empty] | Surkhi Parsa |  |  | Wasif Construction Company
[6 empty] | Shekh Ali |  |  | Zabihullah
[6 empty] | Ghorband |  |  | Zahid Saeed Engineering and Construction Company (ZSCC)
[6 empty] | Mahmud Raqi |  |  | Ziaurrahman Mohammadi
Hisa-i-Awal Kohistan
Hisa-i-Duwum Kohistan
Koh Band
Nijrab
Tagab
Alasay
Puli Alam
Muhammad Agha
Kharwar
Khoshi
Baraki Barak
Azra
Charkh
Maidan Shahr
Nirkh
Jalrez
Hisa-i-Awal Behsud
Markazi Behsud
Day Mirdad
Chaki Wardak
Saydabad
Jaghatu
Bazarak
Rokha
Shotul
Darah
Hisa-i-Awal
Hisa-i-Duwum
Paryan
Bamyan
Shibar
Kahmard
Yakawlang
Panjab
Waras
Saighan
Nili
Ashtarlay
Sang Takht wa Bandar
Khadir
Kiti
Miramor
Shahristan
Gizab
Gardez
Sayed Karam
Ahmadabad
Jaji
Zurmat
Dand wa Patan
Gerda Serai
Laja Ahmad Khel
Mirzaka
Shwak
Sharana
Sarubi
Urgun
Barmal
Gomal
Mata Khan
Omna
Sar Hawza
Terwa
Waza Khwa
Yosuf Khel
Ziruk
Gayan
Dila
Nika
Khost
Zazai Maidan
Mandozai
Tani
Spera
Nadir Shah Kot
Musa Khel
Qalandar
Sabari
Bak
Jaji Maidan
Gurbuz
Shamul
Ghazni
Andar
Deh Yak
Gelan
Giro
Jaghori
Malistan
Nawa
Nawur
Rashidan
Waghaz
Zana Khan
Kandahar
Ghorak
Nesh
Arghandab
Daman
Panjwayi
Spin Boldak
Khakrez
Shah Wali Kot
Maiwand
Zhari
Arghistan
Maruf
Reg
Shorabak
Lashkar Gah
Nawzad
Washer
Nad Ali
Nahr-e-Saraj
Sangin
Musa Qala
Kajaki
Garmser
Dishu
Khanashin
Baghran
Nawa-i-Barakzayi
Qalat
Mizana
Shahjoy
Shamulzayi
Atghar
Daychopan
Kakar
Naw Bahar
Shinkay
Tarnak wa Jaldak
Tarin Kot
Deh Rawud
Chora
Shahidi Hassas
Khas Uruzgan
Zaranj
Kang
Chakhansur
Chahar Burjak
Khash Rod
Mazar-e-Sharif
Alburz
Dehdadi
Nahr-e-Shahi
Chimtal
Dawlatabad
Sholgara
Kishindih
Zari
Shortepa
Kaldar
Khulm
Marmul
Aybak
Hazrati Sultan
Khuram wa Sarbagh
Ruyi Du Ab
Dara-i-Sufi Payin
Dara-i-Sufi Bala
Feroz Nakhchir
Sheberghan
Aqcha
Faizabad
Khamyab
Khwaja Du Koh
Mardyan
Mingajik
Qarqin
Qush Tepa
Darzab
Shibirghan
Sar-e-Pul
Balkhab
Gosfandi
Kohistanat
Sangcharak
Sayyad
Sozma Qala
Maymana
Andkhoy
Almar
Bilchiragh
Gurziwan
Khwaja Sabz Posh
Kohistan
Pashtun Kot
Qaramqol
Qaysar
Shirin Tagab
Kunduz
Ali Abad
Kalbad
Qala-e-Zal
Imam Sahib
Khanabad
Chahar Dara
Dasht-e-Archi
Puli Khumri
Baghlan
Dahana-i-Ghori
Dushi
Khinjan
Khost wa Firing
Nahrin
Andarab
Tala wa Barfak
Burka
Taloqan
Baharak
Bangi
Chah Ab
Chal
Darqad
Dashti Qala
Farkhar
Ishkamish
Kalafgan
Khwaja Ghar
Rustaq
Warsaj
Yangi Qala
Fayzabad
Jurm
Kishim
Yaftal
Arghanj Khwa
Darwaz
Ishkashim
Kuf Ab
Raghistan
Shighnan
Wakhan
Zebak

## 08_Geography
Geography lists — add a province under its region code, or a district under its province column. Do not leave blank cells in the middle of a list.
PROVINCES BY REGION (column header is the region code used in named ranges)
West_Herat | East_Jalalabad | Central_Kabul | Central_Highland_Bamyan | Southeast_Gardez | South_Kandahar | North_Mazar | Northeast_Kunduz
Herat | Nangarhar | Kabul | Bamyan | Paktya | Kandahar | Balkh | Kunduz
Badghis | Kunar | Parwan | Daykundi | Paktika | Helmand | Samangan | Baghlan
Farah | Laghman | Kapisa |  | Khost | Zabul | Jawzjan | Takhar
Ghor | Nuristan | Logar |  | Ghazni | Uruzgan | Sar-e-Pul | Badakhshan
|  | Maidan Wardak |  |  | Nimroz | Faryab
Panjshir
DISTRICTS BY PROVINCE (column header is the province; add districts below)
Herat | Badghis | Farah | Ghor | Nangarhar | Kunar | Laghman | Nuristan | Kabul | Parwan | Kapisa | Logar | Maidan Wardak | Panjshir | Bamyan | Daykundi | Paktya | Paktika | Khost | Ghazni | Kandahar | Helmand | Zabul | Uruzgan | Nimroz | Balkh | Samangan | Jawzjan | Sar-e-Pul | Faryab | Kunduz | Baghlan | Takhar | Badakhshan
Herat | Qala-e-Naw | Farah | Firozkoh | Jalalabad | Asadabad | Mihtarlam | Parun | PD#13 Kabul | Charikar | Mahmud Raqi | Puli Alam | Maidan Shahr | Bazarak | Bamyan | Nili | Gardez | Sharana | Khost | Ghazni | Kandahar | Lashkar Gah | Qalat | Tarin Kot | Zaranj | Mazar-e-Sharif | Aybak | Sheberghan | Sar-e-Pul | Maymana | Kunduz | Puli Khumri | Taloqan | Fayzabad
Injil | Qadis | Pusht Rod | Lal wa Sarjangal | Behsud | Narang | Qarghayi | Wama | Deh Sabz | Bagram | Hisa-i-Awal Kohistan | Muhammad Agha | Nirkh | Rokha | Shibar | Ashtarlay | Sayed Karam | Sarubi | Zazai Maidan | Andar | Ghorak | Nawzad | Mizana | Deh Rawud | Kang | Alburz | Hazrati Sultan | Aqcha | Balkhab | Andkhoy | Ali Abad | Baghlan | Baharak | Jurm
Guzara | Muqur | Khaki Safed | Tulak | Surkh Rod | Sawkai | Alishing | Kamdesh | Bagrami | Jabal Saraj | Hisa-i-Duwum Kohistan | Kharwar | Jalrez | Shotul | Kahmard | Sang Takht wa Bandar | Ahmadabad | Urgun | Mandozai | Deh Yak | Nesh | Washer | Shahjoy | Chora | Chakhansur | Dehdadi | Khuram wa Sarbagh | Faizabad | Gosfandi | Almar | Kalbad | Dahana-i-Ghori | Bangi | Baharak
Karukh | Bala Murghab | Qala-e-Kah | Shahrak | Kama | Khas Kunar | Alingar | Barg-i-Matal | Paghman | Salang | Koh Band | Khoshi | Hisa-i-Awal Behsud | Darah | Yakawlang | Khadir | Jaji | Barmal | Tani | Gelan | Arghandab | Nad Ali | Shamulzayi | Shahidi Hassas | Chahar Burjak | Nahr-e-Shahi | Ruyi Du Ab | Khamyab | Kohistanat | Bilchiragh | Qala-e-Zal | Dushi | Chah Ab | Kishim
Pashtun Zarghun | Jawand | Shib Koh | Dawlat Yar | Kuz Kunar | Nurgal | Dawlat Shah | Mandol | Char Asiab | Shinwari | Nijrab | Baraki Barak | Markazi Behsud | Hisa-i-Awal | Panjab | Kiti | Zurmat | Gomal | Spera | Giro | Daman | Nahr-e-Saraj | Arghandab | Khas Uruzgan | Khash Rod | Chimtal | Dara-i-Sufi Payin | Khwaja Du Koh | Sangcharak | Dawlatabad | Imam Sahib | Khinjan | Chal | Yaftal
Zindajan | Ab Kamari | Bala Buluk | Charsada | Rodat | Chawkay |  | Du Ab | Shakardara | Sayed Khel | Tagab | Azra | Day Mirdad | Hisa-i-Duwum | Waras | Miramor | Dand wa Patan | Mata Khan | Nadir Shah Kot | Jaghatu | Panjwayi | Sangin | Atghar | Gizab |  | Dawlatabad | Dara-i-Sufi Bala | Mardyan | Sayyad | Gurziwan | Khanabad | Khost wa Firing | Darqad | Arghanj Khwa
Gulran | Ghormach | Gulistan | Pasaband | Bati Kot | Dangam |  | Nurgaram | Musayi | Koh-i-Safi | Alasay | Charkh | Chaki Wardak | Paryan | Saighan | Shahristan | Gerda Serai | Omna | Musa Khel | Jaghori | Spin Boldak | Musa Qala | Daychopan |  |  | Sholgara | Feroz Nakhchir | Mingajik | Sozma Qala | Khwaja Sabz Posh | Chahar Dara | Nahrin | Dashti Qala | Darwaz
Kohsan |  | Pur Chaman | Saghar | Shinwar | Ghaziabad |  | Waygal | Kalakan | Surkhi Parsa |  |  | Saydabad |  |  | Gizab | Laja Ahmad Khel | Sar Hawza | Qalandar | Malistan | Khakrez | Kajaki | Kakar |  |  | Kishindih |  | Qarqin |  | Kohistan | Dasht-e-Archi | Andarab | Farkhar | Ishkashim
Ghoryan |  | Bakwa | Taywara | Achin | Marawara |  |  | Qarabagh | Shekh Ali |  |  | Jaghatu |  |  |  | Mirzaka | Terwa | Sabari | Muqur | Shah Wali Kot | Garmser | Naw Bahar |  |  | Zari |  | Qush Tepa |  | Pashtun Kot |  | Tala wa Barfak | Ishkamish | Kuf Ab
Obe |  | Lash wa Juwayn | Du Layna | Nazyan | Shigal |  |  | Istalif | Ghorband | [6 empty] | Shwak | Waza Khwa | Bak | Nawa | Maiwand | Dishu | Shinkay |  |  | Shortepa |  | Darzab |  | Qaramqol |  | Burka | Kalafgan | Raghistan
Chishti Sharif |  | Anar Dara |  | Dur Baba | Wata Pur |  |  | Farza | [8 empty] | Yosuf Khel | Jaji Maidan | Nawur | Zhari | Khanashin | Tarnak wa Jaldak |  |  | Kaldar |  | Shibirghan |  | Qaysar |  |  | Khwaja Ghar | Shighnan
Shindand |  |  |  | Mohmand Dara | Naray |  |  | Guldara | [8 empty] | Ziruk | Gurbuz | Qarabagh | Arghistan | Baghran |  |  |  | Khulm |  |  |  | Shirin Tagab |  |  | Rustaq | Wakhan
Adraskan |  |  |  | Lal Pur | Dara-i-Pech |  |  | Khak-e-Jabbar | [8 empty] | Gayan | Shamul | Rashidan | Maruf | Nawa-i-Barakzayi |  |  |  | Marmul | [6 empty] | Warsaj | Zebak
Farsi |  |  |  | Goshta |  |  |  | Surobi | [8 empty] | Dila |  | Waghaz | Reg | [11 empty] | Yangi Qala
|  |  |  | Chaparhar | [12 empty] | Nika |  | Zana Khan | Shorabak
Khogyani
Pachir wa Agam
Sherzad
Hesarak
Darah-i-Nur

## 09_Lookups
Lookups used by cascading dropdowns — add a row when you add a region or province
Region display name | Province named range | Region code | Province | District named range
West / Herat | Prov_West_Herat | West_Herat | Herat | Dist_Herat
East / Jalalabad | Prov_East_Jalalabad | East_Jalalabad | Badghis | Dist_Badghis
Central / Kabul | Prov_Central_Kabul | Central_Kabul | Farah | Dist_Farah
Central Highland / Bamyan | Prov_Central_Highland_Bamyan | Central_Highland_Bamyan | Ghor | Dist_Ghor
Southeast / Gardez | Prov_Southeast_Gardez | Southeast_Gardez | Nangarhar | Dist_Nangarhar
South / Kandahar | Prov_South_Kandahar | South_Kandahar | Kunar | Dist_Kunar
North / Mazar | Prov_North_Mazar | North_Mazar | Laghman | Dist_Laghman
Northeast / Kunduz | Prov_Northeast_Kunduz | Northeast_Kunduz | Nuristan | Dist_Nuristan
|  |  | Kabul | Dist_Kabul
|  |  | Parwan | Dist_Parwan
|  |  | Kapisa | Dist_Kapisa
|  |  | Logar | Dist_Logar
|  |  | Maidan Wardak | Dist_Maidan_Wardak
|  |  | Panjshir | Dist_Panjshir
|  |  | Bamyan | Dist_Bamyan
|  |  | Daykundi | Dist_Daykundi
|  |  | Paktya | Dist_Paktya
|  |  | Paktika | Dist_Paktika
|  |  | Khost | Dist_Khost
|  |  | Ghazni | Dist_Ghazni
|  |  | Kandahar | Dist_Kandahar
|  |  | Helmand | Dist_Helmand
|  |  | Zabul | Dist_Zabul
|  |  | Uruzgan | Dist_Uruzgan
|  |  | Nimroz | Dist_Nimroz
|  |  | Balkh | Dist_Balkh
|  |  | Samangan | Dist_Samangan
|  |  | Jawzjan | Dist_Jawzjan
|  |  | Sar-e-Pul | Dist_Sar_e_Pul
|  |  | Faryab | Dist_Faryab
|  |  | Kunduz | Dist_Kunduz
|  |  | Baghlan | Dist_Baghlan
|  |  | Takhar | Dist_Takhar
|  |  | Badakhshan | Dist_Badakhshan